ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1051 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Closed Cooling Water System for Block #1 |  | 1CF3030W74A08 | (CCWS) Installation & Test - Elec. | (CCWS) Installation & Test - Elec. | 2008-08-19 | 2008-10-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Closed Cooling Water System for Block #1 1CF3030W74A08 (CCWS) Installation & Test - Elec. | Activity | 1CF3030W74A08 | (CCWS) Installation & Test - Elec. | 2008-08-19 00:00:00 | 2008-10-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1052 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Closed Cooling Water System for Block #1 |  | 1CF3030W90A09 | (CCWS) Installation & Test - I&C | (CCWS) Installation & Test - I&C | 2008-08-19 | 2008-10-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Closed Cooling Water System for Block #1 1CF3030W90A09 (CCWS) Installation & Test - I&C | Activity | 1CF3030W90A09 | (CCWS) Installation & Test - I&C | 2008-08-19 00:00:00 | 2008-10-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1053 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Closed Cooling Water System for Block #1 |  | 1CF3030W68A06 | (EXP Head Tank) Installation | (EXP Head Tank) Installation | 2008-09-15 | 2008-10-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Closed Cooling Water System for Block #1 1CF3030W68A06 (EXP Head Tank) Installation | Activity | 1CF3030W68A06 | (EXP Head Tank) Installation | 2008-09-15 00:00:00 | 2008-10-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1054 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Closed Cooling Water System for Block #1 |  | 1CF3030W42A16 | (CCW H/EX) Installation | (CCW H/EX) Installation | 2008-09-17 | 2008-10-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Closed Cooling Water System for Block #1 1CF3030W42A16 (CCW H/EX) Installation | Activity | 1CF3030W42A16 | (CCW H/EX) Installation | 2008-09-17 00:00:00 | 2008-10-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1055 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Closed Cooling Water System for Block #1 |  | 1SF3030W62A24 | (CCWS) Loop chek | (CCWS) Loop chek | 2008-10-19 | 2008-10-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Closed Cooling Water System for Block #1 1SF3030W62A24 (CCWS) Loop chek | Activity | 1SF3030W62A24 | (CCWS) Loop chek | 2008-10-19 00:00:00 | 2008-10-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1056 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Closed Cooling Water System for Block #1 |  | 1SF3030W62A25 | (CCWS) System Function Test | (CCWS) System Function Test | 2008-10-24 | 2008-10-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Closed Cooling Water System for Block #1 1SF3030W62A25 (CCWS) System Function Test | Activity | 1SF3030W62A25 | (CCWS) System Function Test | 2008-10-24 00:00:00 | 2008-10-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1057 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Closed Cooling Water System for Block #1 |  | 1SF3030W62A26 | (CCWS) Pump Operation | (CCWS) Pump Operation | 2008-10-29 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Closed Cooling Water System for Block #1 1SF3030W62A26 (CCWS) Pump Operation | Activity | 1SF3030W62A26 | (CCWS) Pump Operation | 2008-10-29 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1059 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 > Temporary Cooling Tower | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Closed Cooling Water System for Block #1 | Temporary Cooling Tower | 1EF3030W42A01 | (Temp. Cooling Tower) MPS Issue | (Temp. Cooling Tower) MPS Issue |  | 2007-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Closed Cooling Water System for Block #1 Temporary Cooling Tower 1EF3030W42A01 (Temp. Cooling Tower) MPS Issue | Activity | 1EF3030W42A01 | (Temp. Cooling Tower) MPS Issue |  | 2007-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1060 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 > Temporary Cooling Tower | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Closed Cooling Water System for Block #1 | Temporary Cooling Tower | 1PF3030W42A02P | (Temp. Cooling Tower) P.O & Procurement | (Temp. Cooling Tower) P.O & Procurement | 2008-02-21 | 2008-06-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Closed Cooling Water System for Block #1 Temporary Cooling Tower 1PF3030W42A02P (Temp. Cooling Tower) P.O & Procurement | Activity | 1PF3030W42A02P | (Temp. Cooling Tower) P.O & Procurement | 2008-02-21 00:00:00 | 2008-06-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1061 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 > Temporary Cooling Tower | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Closed Cooling Water System for Block #1 | Temporary Cooling Tower | 1PF3030W42A03T | (Temp. Cooling Tower)Transportation | (Temp. Cooling Tower)Transportation | 2008-06-20 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Closed Cooling Water System for Block #1 Temporary Cooling Tower 1PF3030W42A03T (Temp. Cooling Tower)Transportation | Activity | 1PF3030W42A03T | (Temp. Cooling Tower)Transportation | 2008-06-20 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1062 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 > Temporary Cooling Tower | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Closed Cooling Water System for Block #1 | Temporary Cooling Tower | 1CF3030W42A04 | (Temp. Cooling Tower) Installation | (Temp. Cooling Tower) Installation | 2008-08-05 | 2008-09-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Closed Cooling Water System for Block #1 Temporary Cooling Tower 1CF3030W42A04 (Temp. Cooling Tower) Installation | Activity | 1CF3030W42A04 | (Temp. Cooling Tower) Installation | 2008-08-05 00:00:00 | 2008-09-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1063 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Closed Cooling Water System for Block #1 > Temporary Cooling Tower | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Closed Cooling Water System for Block #1 | Temporary Cooling Tower | 1CF3030W58A05 | (Temp. Cooling Tower) Temp. pipe install | (Temp. Cooling Tower) Temp. pipe install | 2008-09-17 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Closed Cooling Water System for Block #1 Temporary Cooling Tower 1CF3030W58A05 (Temp. Cooling Tower) Temp. pipe install | Activity | 1CF3030W58A05 | (Temp. Cooling Tower) Temp. pipe install | 2008-09-17 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1065 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1EF3546W00A02 | (Clean & Dirty Oil System) P&ID & System Design | (Clean & Dirty Oil System) P&ID & System Design | 2007-04-02 | 2007-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1EF3546W00A02 (Clean & Dirty Oil System) P&ID & System Design | Activity | 1EF3546W00A02 | (Clean & Dirty Oil System) P&ID & System Design | 2007-04-02 00:00:00 | 2007-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1066 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1EF3546W00A01 | (Clean & Dirty Oil System) Key data | (Clean & Dirty Oil System) Key data | 2007-04-27 | 2007-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1EF3546W00A01 (Clean & Dirty Oil System) Key data | Activity | 1EF3546W00A01 | (Clean & Dirty Oil System) Key data | 2007-04-27 00:00:00 | 2007-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1067 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1EF3546W42A11 | (Dirty Oil Tank) MPS Issue | (Dirty Oil Tank) MPS Issue |  | 2007-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1EF3546W42A11 (Dirty Oil Tank) MPS Issue | Activity | 1EF3546W42A11 | (Dirty Oil Tank) MPS Issue |  | 2007-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1068 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1EF3546W42A05 | (Clean Oil Tank) MPS Issue | (Clean Oil Tank) MPS Issue |  | 2007-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1EF3546W42A05 (Clean Oil Tank) MPS Issue | Activity | 1EF3546W42A05 | (Clean Oil Tank) MPS Issue |  | 2007-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1069 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1EF3546W42A17 | (Clean & Dirty LOP) MPS Issue | (Clean & Dirty LOP) MPS Issue |  | 2007-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1EF3546W42A17 (Clean & Dirty LOP) MPS Issue | Activity | 1EF3546W42A17 | (Clean & Dirty LOP) MPS Issue |  | 2007-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1070 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1PF3546W42A18P | (Clean & Dirty LOP) P.O & Procurement | (Clean & Dirty LOP) P.O & Procurement | 2007-10-31 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1PF3546W42A18P (Clean & Dirty LOP) P.O & Procurement | Activity | 1PF3546W42A18P | (Clean & Dirty LOP) P.O & Procurement | 2007-10-31 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1071 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1EF3546W16A15 | (Clean & Dirty LOP) FDN Design | (Clean & Dirty LOP) FDN Design | 2007-10-31 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1EF3546W16A15 (Clean & Dirty LOP) FDN Design | Activity | 1EF3546W16A15 | (Clean & Dirty LOP) FDN Design | 2007-10-31 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1072 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1PF3546W42A06P | (Clean Oil Tank) P.O & Procurement | (Clean Oil Tank) P.O & Procurement | 2007-11-01 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1PF3546W42A06P (Clean Oil Tank) P.O & Procurement | Activity | 1PF3546W42A06P | (Clean Oil Tank) P.O & Procurement | 2007-11-01 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1073 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1EF3546W16A03 | (Clean Oil Tank) FDN Design | (Clean Oil Tank) FDN Design | 2007-11-01 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1EF3546W16A03 (Clean Oil Tank) FDN Design | Activity | 1EF3546W16A03 | (Clean Oil Tank) FDN Design | 2007-11-01 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1074 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1PF3546W42A12P | (Dirty Oil Tank) P.O & Procurement | (Dirty Oil Tank) P.O & Procurement | 2007-11-01 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1PF3546W42A12P (Dirty Oil Tank) P.O & Procurement | Activity | 1PF3546W42A12P | (Dirty Oil Tank) P.O & Procurement | 2007-11-01 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1075 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1EF3546W16A09 | (Dirty Oil Tank) FDN Design | (Dirty Oil Tank) FDN Design | 2007-11-01 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1EF3546W16A09 (Dirty Oil Tank) FDN Design | Activity | 1EF3546W16A09 | (Dirty Oil Tank) FDN Design | 2007-11-01 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1076 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1CF3546W16A04 | (Clean Oil Tank) FDN Work | (Clean Oil Tank) FDN Work | 2008-04-01 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1CF3546W16A04 (Clean Oil Tank) FDN Work | Activity | 1CF3546W16A04 | (Clean Oil Tank) FDN Work | 2008-04-01 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1077 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1CF3546W16A10 | (Dirty Oil Tank) FDN Work | (Dirty Oil Tank) FDN Work | 2008-04-01 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1CF3546W16A10 (Dirty Oil Tank) FDN Work | Activity | 1CF3546W16A10 | (Dirty Oil Tank) FDN Work | 2008-04-01 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1078 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1CF3546W16A16 | (Clean & Dirty LOP) FDN Work | (Clean & Dirty LOP) FDN Work | 2008-04-01 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1CF3546W16A16 (Clean & Dirty LOP) FDN Work | Activity | 1CF3546W16A16 | (Clean & Dirty LOP) FDN Work | 2008-04-01 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1079 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1PF3546W42A07T | (Clean Oil Tank) Transportation | (Clean Oil Tank) Transportation | 2008-10-02 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1PF3546W42A07T (Clean Oil Tank) Transportation | Activity | 1PF3546W42A07T | (Clean Oil Tank) Transportation | 2008-10-02 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1080 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1PF3546W42A13T | (Dirty Oil Tank) Transportation | (Dirty Oil Tank) Transportation | 2008-10-02 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1PF3546W42A13T (Dirty Oil Tank) Transportation | Activity | 1PF3546W42A13T | (Dirty Oil Tank) Transportation | 2008-10-02 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1081 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1PF3546W42A19T | (Clean & Dirty LOP) Transportation | (Clean & Dirty LOP) Transportation | 2008-10-02 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1PF3546W42A19T (Clean & Dirty LOP) Transportation | Activity | 1PF3546W42A19T | (Clean & Dirty LOP) Transportation | 2008-10-02 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1082 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1CF3546W42A08 | (Clean Oil Tank) Installation | (Clean Oil Tank) Installation | 2008-11-17 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1CF3546W42A08 (Clean Oil Tank) Installation | Activity | 1CF3546W42A08 | (Clean Oil Tank) Installation | 2008-11-17 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1083 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1CF3546W42A14 | (Dirty Oil Tank) Installation | (Dirty Oil Tank) Installation | 2008-11-17 | 2009-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1CF3546W42A14 (Dirty Oil Tank) Installation | Activity | 1CF3546W42A14 | (Dirty Oil Tank) Installation | 2008-11-17 00:00:00 | 2009-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1084 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1CF3546W42A20 | (Clean & Dirty LOP) Installation & Test | (Clean & Dirty LOP) Installation & Test | 2008-11-17 | 2008-12-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1CF3546W42A20 (Clean & Dirty LOP) Installation & Test | Activity | 1CF3546W42A20 | (Clean & Dirty LOP) Installation & Test | 2008-11-17 00:00:00 | 2008-12-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1085 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1CF3546W58A21 | (Clean & Dirty Oil System) Piping Work | (Clean & Dirty Oil System) Piping Work | 2008-11-17 | 2009-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1CF3546W58A21 (Clean & Dirty Oil System) Piping Work | Activity | 1CF3546W58A21 | (Clean & Dirty Oil System) Piping Work | 2008-11-17 00:00:00 | 2009-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1086 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1CF3546W74A22 | (Clean & Dirty Oil System) Installation & Test - Elec. | (Clean & Dirty Oil System) Installation & Test - Elec. | 2009-01-01 | 2009-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1CF3546W74A22 (Clean & Dirty Oil System) Installation & Test - Elec. | Activity | 1CF3546W74A22 | (Clean & Dirty Oil System) Installation & Test - Elec. | 2009-01-01 00:00:00 | 2009-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1087 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean & Dirty Oil System |  | 1CF3546W90A23 | (Clean & Dirty Oil System) Installation & Test - I&C | (Clean & Dirty Oil System) Installation & Test - I&C | 2009-01-01 | 2009-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean & Dirty Oil System 1CF3546W90A23 (Clean & Dirty Oil System) Installation & Test - I&C | Activity | 1CF3546W90A23 | (Clean & Dirty Oil System) Installation & Test - I&C | 2009-01-01 00:00:00 | 2009-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1089 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1EF3015W00A01 | (FWS) BFP Key data | (FWS) BFP Key data | 2007-04-02 | 2007-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1EF3015W00A01 (FWS) BFP Key data | Activity | 1EF3015W00A01 | (FWS) BFP Key data | 2007-04-02 00:00:00 | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1090 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1EF3015W00A02 | (FWS) P&ID & System Design | (FWS) P&ID & System Design | 2007-04-02 | 2007-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1EF3015W00A02 (FWS) P&ID & System Design | Activity | 1EF3015W00A02 | (FWS) P&ID & System Design | 2007-04-02 00:00:00 | 2007-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1091 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1EF3015W42A05 | (FWP) MPS Issue | (FWP) MPS Issue |  | 2007-06-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1EF3015W42A05 (FWP) MPS Issue | Activity | 1EF3015W42A05 | (FWP) MPS Issue |  | 2007-06-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1092 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1PF3015W42A06P | (FWP) P.O & Procurement | (FWP) P.O & Procurement | 2007-08-30 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1PF3015W42A06P (FWP) P.O & Procurement | Activity | 1PF3015W42A06P | (FWP) P.O & Procurement | 2007-08-30 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1093 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1EF3015W58A13 | (FW PIPING) MPS Issue | (FW PIPING) MPS Issue |  | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1EF3015W58A13 (FW PIPING) MPS Issue | Activity | 1EF3015W58A13 | (FW PIPING) MPS Issue |  | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1094 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | (FWP Shelter) GA & Load Data to Civil Design | 2007-10-31 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1EF3015W00A09 (FWP Shelter) GA & Load Data to Civil Design | Activity | 1EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | 2007-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1095 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1EF3015W32A10 | (FWP Shelter) FDN & Shelter Design | (FWP Shelter) FDN & Shelter Design | 2007-10-31 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1EF3015W32A10 (FWP Shelter) FDN & Shelter Design | Activity | 1EF3015W32A10 | (FWP Shelter) FDN & Shelter Design | 2007-10-31 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1096 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1EF3015W16A03 | (FWP) FDN Design | (FWP) FDN Design | 2007-10-31 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1EF3015W16A03 (FWP) FDN Design | Activity | 1EF3015W16A03 | (FWP) FDN Design | 2007-10-31 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1097 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1PF3015W58A14P | (FW PIPING) P.O & Procurement | (FW PIPING) P.O & Procurement | 2007-11-02 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1PF3015W58A14P (FW PIPING) P.O & Procurement | Activity | 1PF3015W58A14P | (FW PIPING) P.O & Procurement | 2007-11-02 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1098 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1CF3015W16A11 | (FWP Shelter) FDN Work | (FWP Shelter) FDN Work | 2008-01-31 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1CF3015W16A11 (FWP Shelter) FDN Work | Activity | 1CF3015W16A11 | (FWP Shelter) FDN Work | 2008-01-31 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1099 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1CF3015W16A04 | (FWP) FDN Work | (FWP) FDN Work | 2008-01-31 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1CF3015W16A04 (FWP) FDN Work | Activity | 1CF3015W16A04 | (FWP) FDN Work | 2008-01-31 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1100 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1CF3015W32A12 | (FWP Shelter) Shelter Structure Work | (FWP Shelter) Shelter Structure Work | 2008-04-02 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1CF3015W32A12 (FWP Shelter) Shelter Structure Work | Activity | 1CF3015W32A12 | (FWP Shelter) Shelter Structure Work | 2008-04-02 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1101 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1PF3015W58A15T | (FW PIPING) Transportation | (FW PIPING) Transportation | 2008-07-01 | 2008-08-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1PF3015W58A15T (FW PIPING) Transportation | Activity | 1PF3015W58A15T | (FW PIPING) Transportation | 2008-07-01 00:00:00 | 2008-08-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1102 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1CF3015W58A16 | (FW PIPING) Piping Work (incl. Insulation) | (FW PIPING) Piping Work (incl. Insulation) | 2008-08-15 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1CF3015W58A16 (FW PIPING) Piping Work (incl. Insulation) | Activity | 1CF3015W58A16 | (FW PIPING) Piping Work (incl. Insulation) | 2008-08-15 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1103 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1PF3015W42A07T | (FWP) Transportation | (FWP) Transportation | 2008-08-30 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1PF3015W42A07T (FWP) Transportation | Activity | 1PF3015W42A07T | (FWP) Transportation | 2008-08-30 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1104 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1CF3015W74A18 | (FWS) Installation & Test - Elec. | (FWS) Installation & Test - Elec. | 2008-10-15 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1CF3015W74A18 (FWS) Installation & Test - Elec. | Activity | 1CF3015W74A18 | (FWS) Installation & Test - Elec. | 2008-10-15 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1105 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1CF3015W90A19 | (FWS) Installation & Test - I&C | (FWS) Installation & Test - I&C | 2008-10-15 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1CF3015W90A19 (FWS) Installation & Test - I&C | Activity | 1CF3015W90A19 | (FWS) Installation & Test - I&C | 2008-10-15 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1106 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1CF3015W42A08 | (FWP) Installation | (FWP) Installation | 2008-10-15 | 2008-11-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1CF3015W42A08 (FWP) Installation | Activity | 1CF3015W42A08 | (FWP) Installation | 2008-10-15 00:00:00 | 2008-11-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1107 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1CF3015W62A17 | (FW PIPING) Hydro Test | (FW PIPING) Hydro Test | 2008-11-17 | 2008-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1CF3015W62A17 (FW PIPING) Hydro Test | Activity | 1CF3015W62A17 | (FW PIPING) Hydro Test | 2008-11-17 00:00:00 | 2008-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1108 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1SF3015W62A20 | (FWS) Loop check | (FWS) Loop check | 2008-12-16 | 2009-01-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1SF3015W62A20 (FWS) Loop check | Activity | 1SF3015W62A20 | (FWS) Loop check | 2008-12-16 00:00:00 | 2009-01-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1109 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1SF3015W62A21 | (FWS) System Function Test | (FWS) System Function Test | 2009-01-05 | 2009-01-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1SF3015W62A21 (FWS) System Function Test | Activity | 1SF3015W62A21 | (FWS) System Function Test | 2009-01-05 00:00:00 | 2009-01-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1110 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Feed Water System |  | 1SF3015W62A22 | (FWS) Pump Operation | (FWS) Pump Operation | 2009-01-19 | 2009-01-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Feed Water System 1SF3015W62A22 (FWS) Pump Operation | Activity | 1SF3015W62A22 | (FWS) Pump Operation | 2009-01-19 00:00:00 | 2009-01-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1112 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | (Chemical Dosing System) P&ID & System Design | 2007-04-02 | 2007-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1EF3045W00A01 (Chemical Dosing System) P&ID & System Design | Activity | 1EF3045W00A01 | (Chemical Dosing System) P&ID & System Design | 2007-04-02 00:00:00 | 2007-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1113 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1EF3045W42A02 | (Chemical Dosing Equip) MPS Issue | (Chemical Dosing Equip) MPS Issue |  | 2007-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1EF3045W42A02 (Chemical Dosing Equip) MPS Issue | Activity | 1EF3045W42A02 | (Chemical Dosing Equip) MPS Issue |  | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1114 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | (Chemical Dosing BLDG) GA & Load Data to Civil Design | 2007-09-26 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1EF3045W00A06 (Chemical Dosing BLDG) GA & Load Data to Civil Design | Activity | 1EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | 2007-09-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1115 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | (Chemical Dosing BLDG) FDN Design | 2007-09-26 | 2008-01-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1EF3045W16A07 (Chemical Dosing BLDG) FDN Design | Activity | 1EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | 2007-09-26 00:00:00 | 2008-01-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1116 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | (Chemical Dosing BLDG) Structure Design | 2007-09-26 | 2008-01-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1EF3045W32A09 (Chemical Dosing BLDG) Structure Design | Activity | 1EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | 2007-09-26 00:00:00 | 2008-01-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1117 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | (Chemical Dosing Equip) P.O & Procurement | 2007-09-26 | 2008-07-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1PF3045W42A03P (Chemical Dosing Equip) P.O & Procurement | Activity | 1PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | 2007-09-26 00:00:00 | 2008-07-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1118 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1CF3045W16A08 | (Chemical Dosing BLDG) FDN Work | (Chemical Dosing BLDG) FDN Work | 2008-01-24 | 2008-03-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1CF3045W16A08 (Chemical Dosing BLDG) FDN Work | Activity | 1CF3045W16A08 | (Chemical Dosing BLDG) FDN Work | 2008-01-24 00:00:00 | 2008-03-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1119 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1CF3045W32A10 | (Chemical Dosing BLDG) Structure Work | (Chemical Dosing BLDG) Structure Work | 2008-03-26 | 2008-07-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1CF3045W32A10 (Chemical Dosing BLDG) Structure Work | Activity | 1CF3045W32A10 | (Chemical Dosing BLDG) Structure Work | 2008-03-26 00:00:00 | 2008-07-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1120 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1PF3045W42A04T | (Chemical Dosing Equip) Transportation | (Chemical Dosing Equip) Transportation | 2008-07-25 | 2008-09-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1PF3045W42A04T (Chemical Dosing Equip) Transportation | Activity | 1PF3045W42A04T | (Chemical Dosing Equip) Transportation | 2008-07-25 00:00:00 | 2008-09-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1121 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1CF3045W58A16 | (Chemical Dosing System) Piping Work | (Chemical Dosing System) Piping Work | 2008-09-09 | 2008-12-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1CF3045W58A16 (Chemical Dosing System) Piping Work | Activity | 1CF3045W58A16 | (Chemical Dosing System) Piping Work | 2008-09-09 00:00:00 | 2008-12-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1122 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1CF3045W42A05 | (Chemical Dosing Equip) Installation | (Chemical Dosing Equip) Installation | 2008-09-09 | 2008-11-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1CF3045W42A05 (Chemical Dosing Equip) Installation | Activity | 1CF3045W42A05 | (Chemical Dosing Equip) Installation | 2008-09-09 00:00:00 | 2008-11-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1123 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1CF3045W74A17 | (Chemical Dosing System) Installation & Test - Elec. | (Chemical Dosing System) Installation & Test - Elec. | 2008-10-04 | 2008-12-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1CF3045W74A17 (Chemical Dosing System) Installation & Test - Elec. | Activity | 1CF3045W74A17 | (Chemical Dosing System) Installation & Test - Elec. | 2008-10-04 00:00:00 | 2008-12-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1124 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1CF3045W90A18 | (Chemical Dosing System) Installation & Test - I&C | (Chemical Dosing System) Installation & Test - I&C | 2008-10-04 | 2008-12-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1CF3045W90A18 (Chemical Dosing System) Installation & Test - I&C | Activity | 1CF3045W90A18 | (Chemical Dosing System) Installation & Test - I&C | 2008-10-04 00:00:00 | 2008-12-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1125 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1CF3045W38A11 | (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1CF3045W38A11 (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | Activity | 1CF3045W38A11 | (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1126 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1CF3045W36A12 | (Chemical Dosing BLDG) Installation & Test - HVAC | (Chemical Dosing BLDG) Installation & Test - HVAC | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1CF3045W36A12 (Chemical Dosing BLDG) Installation & Test - HVAC | Activity | 1CF3045W36A12 | (Chemical Dosing BLDG) Installation & Test - HVAC | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1127 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1CF3045W74A13 | (Chemical Dosing BLDG) Installation & Test - Elec | (Chemical Dosing BLDG) Installation & Test - Elec | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1CF3045W74A13 (Chemical Dosing BLDG) Installation & Test - Elec | Activity | 1CF3045W74A13 | (Chemical Dosing BLDG) Installation & Test - Elec | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1128 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1CF3045W24A15 | (Chemical Dosing BLDG) Building Finish | (Chemical Dosing BLDG) Building Finish | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1CF3045W24A15 (Chemical Dosing BLDG) Building Finish | Activity | 1CF3045W24A15 | (Chemical Dosing BLDG) Building Finish | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1129 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1CF3045W90A14 | (Chemical Dosing BLDG) Installation & Test - I&C | (Chemical Dosing BLDG) Installation & Test - I&C | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1CF3045W90A14 (Chemical Dosing BLDG) Installation & Test - I&C | Activity | 1CF3045W90A14 | (Chemical Dosing BLDG) Installation & Test - I&C | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1130 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1SF3045W62A19 | (Chemical Dosing System) Loop chek | (Chemical Dosing System) Loop chek | 2008-12-28 | 2009-01-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1SF3045W62A19 (Chemical Dosing System) Loop chek | Activity | 1SF3045W62A19 | (Chemical Dosing System) Loop chek | 2008-12-28 00:00:00 | 2009-01-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1131 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1SF3045W62A20 | (Chemical Dosing System) System Function Test | (Chemical Dosing System) System Function Test | 2009-01-12 | 2009-01-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1SF3045W62A20 (Chemical Dosing System) System Function Test | Activity | 1SF3045W62A20 | (Chemical Dosing System) System Function Test | 2009-01-12 00:00:00 | 2009-01-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1132 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Chemical Dosing System |  | 1SF3045W62A21 | (Chemical Dosing System) System Operation | (Chemical Dosing System) System Operation | 2009-01-19 | 2009-01-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Chemical Dosing System 1SF3045W62A21 (Chemical Dosing System) System Operation | Activity | 1SF3045W62A21 | (Chemical Dosing System) System Operation | 2009-01-19 00:00:00 | 2009-01-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1134 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1EF3040W00A01 | (Sampling System) P&ID & System Design | (Sampling System) P&ID & System Design | 2007-04-02 | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1EF3040W00A01 (Sampling System) P&ID & System Design | Activity | 1EF3040W00A01 | (Sampling System) P&ID & System Design | 2007-04-02 00:00:00 | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1135 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1EF3040W42A04 | (Sampling Equip) MPS Issue | (Sampling Equip) MPS Issue |  | 2007-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1EF3040W42A04 (Sampling Equip) MPS Issue | Activity | 1EF3040W42A04 | (Sampling Equip) MPS Issue |  | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1136 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1PF3040W42A05P | (Sampling Equip) P.O & Procurement | (Sampling Equip) P.O & Procurement | 2007-10-01 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1PF3040W42A05P (Sampling Equip) P.O & Procurement | Activity | 1PF3040W42A05P | (Sampling Equip) P.O & Procurement | 2007-10-01 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1137 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1EF3040W16A02 | (Sampling Equip) FDN Design | (Sampling Equip) FDN Design | 2008-01-01 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1EF3040W16A02 (Sampling Equip) FDN Design | Activity | 1EF3040W16A02 | (Sampling Equip) FDN Design | 2008-01-01 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1138 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1CF3040W16A03 | (Sampling Equip) FDN Work | (Sampling Equip) FDN Work | 2008-04-03 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1CF3040W16A03 (Sampling Equip) FDN Work | Activity | 1CF3040W16A03 | (Sampling Equip) FDN Work | 2008-04-03 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1139 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1PF3040W42A06T | (Sampling Equip) Transportation | (Sampling Equip) Transportation | 2008-07-31 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1PF3040W42A06T (Sampling Equip) Transportation | Activity | 1PF3040W42A06T | (Sampling Equip) Transportation | 2008-07-31 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1140 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1CF3040W42A07 | (Sampling Equip) Installation | (Sampling Equip) Installation | 2008-09-16 | 2008-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1CF3040W42A07 (Sampling Equip) Installation | Activity | 1CF3040W42A07 | (Sampling Equip) Installation | 2008-09-16 00:00:00 | 2008-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1141 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1CF3040W58A08 | (Sampling System) Piping Work | (Sampling System) Piping Work | 2008-10-17 | 2009-01-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1CF3040W58A08 (Sampling System) Piping Work | Activity | 1CF3040W58A08 | (Sampling System) Piping Work | 2008-10-17 00:00:00 | 2009-01-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1142 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1CF3040W74A09 | (Sampling System) Installation & Test - Elec. | (Sampling System) Installation & Test - Elec. | 2008-12-11 | 2009-01-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1CF3040W74A09 (Sampling System) Installation & Test - Elec. | Activity | 1CF3040W74A09 | (Sampling System) Installation & Test - Elec. | 2008-12-11 00:00:00 | 2009-01-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1143 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1CF3040W90A10 | (Sampling System) Installation & Test - I&C | (Sampling System) Installation & Test - I&C | 2008-12-11 | 2009-01-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1CF3040W90A10 (Sampling System) Installation & Test - I&C | Activity | 1CF3040W90A10 | (Sampling System) Installation & Test - I&C | 2008-12-11 00:00:00 | 2009-01-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1144 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1SF3040W62A11 | (Sampling System) Loop chek | (Sampling System) Loop chek | 2009-01-11 | 2009-01-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1SF3040W62A11 (Sampling System) Loop chek | Activity | 1SF3040W62A11 | (Sampling System) Loop chek | 2009-01-11 00:00:00 | 2009-01-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1145 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1SF3040W62A12 | (Sampling System) Chiller Function Test | (Sampling System) Chiller Function Test | 2009-01-21 | 2009-01-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1SF3040W62A12 (Sampling System) Chiller Function Test | Activity | 1SF3040W62A12 | (Sampling System) Chiller Function Test | 2009-01-21 00:00:00 | 2009-01-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1146 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1SF3040W62A13 | (Sampling System) Sampling System Function Test | (Sampling System) Sampling System Function Test | 2009-01-26 | 2009-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1SF3040W62A13 (Sampling System) Sampling System Function Test | Activity | 1SF3040W62A13 | (Sampling System) Sampling System Function Test | 2009-01-26 00:00:00 | 2009-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1147 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Sampling System |  | 1SF3040W62A14 | (Sampling System) System Service | (Sampling System) System Service | 2009-01-31 | 2009-02-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Sampling System 1SF3040W62A14 (Sampling System) System Service | Activity | 1SF3040W62A14 | (Sampling System) System Service | 2009-01-31 00:00:00 | 2009-02-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1150 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1EF3020W00A15 | (COND) Condenser Design Data | (COND) Condenser Design Data | 2007-03-01 | 2007-04-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1EF3020W00A15 (COND) Condenser Design Data | Activity | 1EF3020W00A15 | (COND) Condenser Design Data | 2007-03-01 00:00:00 | 2007-04-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1151 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1EF3020W00A16 | (COND) Utility Consumption Data | (COND) Utility Consumption Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1EF3020W00A16 (COND) Utility Consumption Data | Activity | 1EF3020W00A16 | (COND) Utility Consumption Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1152 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1EF3020W00A01 | (COND System) P&ID & System Design | (COND System) P&ID & System Design | 2007-04-02 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1EF3020W00A01 (COND System) P&ID & System Design | Activity | 1EF3020W00A01 | (COND System) P&ID & System Design | 2007-04-02 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1153 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1EF3020W00A02 | (COND System) Key data | (COND System) Key data | 2007-04-13 | 2007-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1EF3020W00A02 (COND System) Key data | Activity | 1EF3020W00A02 | (COND System) Key data | 2007-04-13 00:00:00 | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1154 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1EF3020W42A11 | (COND Flash Box) MPS Issue | (COND Flash Box) MPS Issue |  | 2007-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1EF3020W42A11 (COND Flash Box) MPS Issue | Activity | 1EF3020W42A11 | (COND Flash Box) MPS Issue |  | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1155 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1EF3020W42A19 | (COND) MPS Issue | (COND) MPS Issue |  | 2007-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1EF3020W42A19 (COND) MPS Issue | Activity | 1EF3020W42A19 | (COND) MPS Issue |  | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1156 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1EF3020W42A05 | (COND Air EXT Equip) MPS Issue | (COND Air EXT Equip) MPS Issue |  | 2007-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1EF3020W42A05 (COND Air EXT Equip) MPS Issue | Activity | 1EF3020W42A05 | (COND Air EXT Equip) MPS Issue |  | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1157 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1PF3020W42A12P | (COND Flash Box) P.O & Procurement | (COND Flash Box) P.O & Procurement | 2007-10-03 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1PF3020W42A12P (COND Flash Box) P.O & Procurement | Activity | 1PF3020W42A12P | (COND Flash Box) P.O & Procurement | 2007-10-03 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1158 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1EF3020W16A17 | (COND) FDN Design | (COND) FDN Design | 2007-10-03 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1EF3020W16A17 (COND) FDN Design | Activity | 1EF3020W16A17 | (COND) FDN Design | 2007-10-03 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1159 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1PF3020W42A20P | (COND) P.O & Procurement | (COND) P.O & Procurement | 2007-10-03 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1PF3020W42A20P (COND) P.O & Procurement | Activity | 1PF3020W42A20P | (COND) P.O & Procurement | 2007-10-03 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1160 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | (COND Air EXT Equip) P.O & Procurement | 2007-10-03 | 2008-08-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1PF3020W42A06P (COND Air EXT Equip) P.O & Procurement | Activity | 1PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | 2007-10-03 00:00:00 | 2008-08-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1161 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1EF3020W16A09 | (COND Flash Box) FDN Design | (COND Flash Box) FDN Design | 2008-01-02 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1EF3020W16A09 (COND Flash Box) FDN Design | Activity | 1EF3020W16A09 | (COND Flash Box) FDN Design | 2008-01-02 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1162 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1CF3020W16A18 | (COND) FDN Work | (COND) FDN Work | 2008-01-31 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1CF3020W16A18 (COND) FDN Work | Activity | 1CF3020W16A18 | (COND) FDN Work | 2008-01-31 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1163 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | (COND Air EXT Equip) FDN Design | 2008-03-01 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1EF3020W16A03 (COND Air EXT Equip) FDN Design | Activity | 1EF3020W16A03 | (COND Air EXT Equip) FDN Design | 2008-03-01 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1164 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1CF3020W16A10 | (COND Flash Box) FDN Work | (COND Flash Box) FDN Work | 2008-04-01 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1CF3020W16A10 (COND Flash Box) FDN Work | Activity | 1CF3020W16A10 | (COND Flash Box) FDN Work | 2008-04-01 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1165 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1CF3020W16A04 | (COND Air EXT Equip) FDN Work | (COND Air EXT Equip) FDN Work | 2008-05-30 | 2008-07-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1CF3020W16A04 (COND Air EXT Equip) FDN Work | Activity | 1CF3020W16A04 | (COND Air EXT Equip) FDN Work | 2008-05-30 00:00:00 | 2008-07-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1166 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1PF3020W42A13T | (COND Flash Box) Transportation | (COND Flash Box) Transportation | 2008-07-02 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1PF3020W42A13T (COND Flash Box) Transportation | Activity | 1PF3020W42A13T | (COND Flash Box) Transportation | 2008-07-02 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1167 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1PF3020W42A21T | (COND) Transportation | (COND) Transportation | 2008-07-31 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1PF3020W42A21T (COND) Transportation | Activity | 1PF3020W42A21T | (COND) Transportation | 2008-07-31 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1168 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1PF3020W42A07T | (COND Air EXT Equip) Transportation | (COND Air EXT Equip) Transportation | 2008-08-13 | 2008-09-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1PF3020W42A07T (COND Air EXT Equip) Transportation | Activity | 1PF3020W42A07T | (COND Air EXT Equip) Transportation | 2008-08-13 00:00:00 | 2008-09-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1169 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1CF3020W42A14 | (COND Flash Box) Installation | (COND Flash Box) Installation | 2008-08-16 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1CF3020W42A14 (COND Flash Box) Installation | Activity | 1CF3020W42A14 | (COND Flash Box) Installation | 2008-08-16 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1170 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1CF3020W42A22 | (COND) Installation | (COND) Installation | 2008-09-15 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1CF3020W42A22 (COND) Installation | Activity | 1CF3020W42A22 | (COND) Installation | 2008-09-15 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1171 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1CF3020W58A23 | (COND System) Piping Work(incl. Insulation) | (COND System) Piping Work(incl. Insulation) | 2008-09-23 | 2008-12-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1CF3020W58A23 (COND System) Piping Work(incl. Insulation) | Activity | 1CF3020W58A23 | (COND System) Piping Work(incl. Insulation) | 2008-09-23 00:00:00 | 2008-12-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1172 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1CF3020W74A24 | (COND System) Installation & Test - Elec. | (COND System) Installation & Test - Elec. | 2008-09-23 | 2008-12-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1CF3020W74A24 (COND System) Installation & Test - Elec. | Activity | 1CF3020W74A24 | (COND System) Installation & Test - Elec. | 2008-09-23 00:00:00 | 2008-12-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1173 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1CF3020W90A25 | (COND System) Installation & Test - I&C | (COND System) Installation & Test - I&C | 2008-09-23 | 2008-12-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1CF3020W90A25 (COND System) Installation & Test - I&C | Activity | 1CF3020W90A25 | (COND System) Installation & Test - I&C | 2008-09-23 00:00:00 | 2008-12-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1174 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1CF3020W42A08 | (COND Air EXT Equip) Installation | (COND Air EXT Equip) Installation | 2008-09-27 | 2008-11-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1CF3020W42A08 (COND Air EXT Equip) Installation | Activity | 1CF3020W42A08 | (COND Air EXT Equip) Installation | 2008-09-27 00:00:00 | 2008-11-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1175 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1SF3020W62A26 | (COND System) Loop check | (COND System) Loop check | 2008-12-24 | 2009-01-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1SF3020W62A26 (COND System) Loop check | Activity | 1SF3020W62A26 | (COND System) Loop check | 2008-12-24 00:00:00 | 2009-01-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1176 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1SF3020W62A27 | (COND System) System Function Test | (COND System) System Function Test | 2009-01-08 | 2009-01-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1SF3020W62A27 (COND System) System Function Test | Activity | 1SF3020W62A27 | (COND System) System Function Test | 2009-01-08 00:00:00 | 2009-01-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1177 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser | 1SF3020W62A28 | (COND System) Pump Operation | (COND System) Pump Operation | 2009-01-18 | 2009-01-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser 1SF3020W62A28 (COND System) Pump Operation | Activity | 1SF3020W62A28 | (COND System) Pump Operation | 2009-01-18 00:00:00 | 2009-01-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1179 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser Tube Cleaning System | 1EF3020W42A01 | (CTCS) MPS Issue | (CTCS) MPS Issue |  | 2007-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser Tube Cleaning System 1EF3020W42A01 (CTCS) MPS Issue | Activity | 1EF3020W42A01 | (CTCS) MPS Issue |  | 2007-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1180 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser Tube Cleaning System | 1PF3020W42A02P | (CTCS) P.O & Procurement | (CTCS) P.O & Procurement | 2007-10-31 | 2008-09-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser Tube Cleaning System 1PF3020W42A02P (CTCS) P.O & Procurement | Activity | 1PF3020W42A02P | (CTCS) P.O & Procurement | 2007-10-31 00:00:00 | 2008-09-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1181 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser Tube Cleaning System | 1PF3020W42A03T | (CTCS) Transportation | (CTCS) Transportation | 2008-09-02 | 2008-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser Tube Cleaning System 1PF3020W42A03T (CTCS) Transportation | Activity | 1PF3020W42A03T | (CTCS) Transportation | 2008-09-02 00:00:00 | 2008-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1182 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condenser Tube Cleaning System | 1CF3020W42A04 | (CTCS) Installation | (CTCS) Installation | 2008-10-17 | 2008-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condenser Tube Cleaning System 1CF3020W42A04 (CTCS) Installation | Activity | 1CF3020W42A04 | (CTCS) Installation | 2008-10-17 00:00:00 | 2008-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1184 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 1EF3020W42A03 | (CEP) MPS Issue | (CEP) MPS Issue |  | 2007-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condensate Extraction Pump 1EF3020W42A03 (CEP) MPS Issue | Activity | 1EF3020W42A03 | (CEP) MPS Issue |  | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1185 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 1PF3020W42A04P | (CEP) P.O & Procurement | (CEP) P.O & Procurement | 2007-09-07 | 2008-08-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condensate Extraction Pump 1PF3020W42A04P (CEP) P.O & Procurement | Activity | 1PF3020W42A04P | (CEP) P.O & Procurement | 2007-09-07 00:00:00 | 2008-08-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1186 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 1EF3020W16A01 | (CEP) FDN Design | (CEP) FDN Design | 2007-10-09 | 2008-01-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condensate Extraction Pump 1EF3020W16A01 (CEP) FDN Design | Activity | 1EF3020W16A01 | (CEP) FDN Design | 2007-10-09 00:00:00 | 2008-01-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1187 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 1CF3020W16A02 | (CEP) FDN Work | (CEP) FDN Work | 2008-01-05 | 2008-05-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condensate Extraction Pump 1CF3020W16A02 (CEP) FDN Work | Activity | 1CF3020W16A02 | (CEP) FDN Work | 2008-01-05 00:00:00 | 2008-05-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1188 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 1PF3020W42A05T | (CEP) Transportation | (CEP) Transportation | 2008-08-08 | 2008-09-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condensate Extraction Pump 1PF3020W42A05T (CEP) Transportation | Activity | 1PF3020W42A05T | (CEP) Transportation | 2008-08-08 00:00:00 | 2008-09-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1189 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 1CF3020W42A06 | (CEP) Installation | (CEP) Installation | 2008-09-23 | 2008-12-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Condensate System Condensate Extraction Pump 1CF3020W42A06 (CEP) Installation | Activity | 1CF3020W42A06 | (CEP) Installation | 2008-09-23 00:00:00 | 2008-12-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1191 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1EF3030W00A01 | (ACWS) P&ID & System Design | (ACWS) P&ID & System Design | 2007-04-02 | 2007-10-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1EF3030W00A01 (ACWS) P&ID & System Design | Activity | 1EF3030W00A01 | (ACWS) P&ID & System Design | 2007-04-02 00:00:00 | 2007-10-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1192 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1EF3030W00A02 | (ACWS) ACWP Key data | (ACWS) ACWP Key data | 2007-04-13 | 2007-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1EF3030W00A02 (ACWS) ACWP Key data | Activity | 1EF3030W00A02 | (ACWS) ACWP Key data | 2007-04-13 00:00:00 | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1193 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1EF3030W42A03 | (ACW PUMP) MPS Issue | (ACW PUMP) MPS Issue |  | 2007-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1EF3030W42A03 (ACW PUMP) MPS Issue | Activity | 1EF3030W42A03 | (ACW PUMP) MPS Issue |  | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1194 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1EF3030W58A09 | (ACW Piping) MPS Issue | (ACW Piping) MPS Issue |  | 2007-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1EF3030W58A09 (ACW Piping) MPS Issue | Activity | 1EF3030W58A09 | (ACW Piping) MPS Issue |  | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1195 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1PF3030W42A04P | (ACW PUMP) P.O & Procurement | (ACW PUMP) P.O & Procurement | 2007-10-03 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1PF3030W42A04P (ACW PUMP) P.O & Procurement | Activity | 1PF3030W42A04P | (ACW PUMP) P.O & Procurement | 2007-10-03 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1196 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1PF3030W58A10P | (ACW Piping) P.O & Procurement | (ACW Piping) P.O & Procurement | 2007-10-03 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1PF3030W58A10P (ACW Piping) P.O & Procurement | Activity | 1PF3030W58A10P | (ACW Piping) P.O & Procurement | 2007-10-03 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1197 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1PF3030W58A11T | (ACW Piping) Transportation | (ACW Piping) Transportation | 2008-07-02 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1PF3030W58A11T (ACW Piping) Transportation | Activity | 1PF3030W58A11T | (ACW Piping) Transportation | 2008-07-02 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1198 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1CF3030W58A12 | (ACW Piping) Piping Work | (ACW Piping) Piping Work | 2008-09-08 | 2008-12-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1CF3030W58A12 (ACW Piping) Piping Work | Activity | 1CF3030W58A12 | (ACW Piping) Piping Work | 2008-09-08 00:00:00 | 2008-12-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1199 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1PF3030W42A05T | (ACW PUMP) Transportation | (ACW PUMP) Transportation | 2008-10-01 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1PF3030W42A05T (ACW PUMP) Transportation | Activity | 1PF3030W42A05T | (ACW PUMP) Transportation | 2008-10-01 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1200 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1CF3030W42A06 | (ACW PUMP) Installation | (ACW PUMP) Installation | 2008-11-15 | 2008-12-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1CF3030W42A06 (ACW PUMP) Installation | Activity | 1CF3030W42A06 | (ACW PUMP) Installation | 2008-11-15 00:00:00 | 2008-12-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1201 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1CF3030W62A13 | (ACW Piping) Hydro Test | (ACW Piping) Hydro Test | 2008-12-10 | 2009-01-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1CF3030W62A13 (ACW Piping) Hydro Test | Activity | 1CF3030W62A13 | (ACW Piping) Hydro Test | 2008-12-10 00:00:00 | 2009-01-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1202 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1CF3030W74A07 | (ACW PUMP) Installation - Elec | (ACW PUMP) Installation - Elec | 2008-12-10 | 2008-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1CF3030W74A07 (ACW PUMP) Installation - Elec | Activity | 1CF3030W74A07 | (ACW PUMP) Installation - Elec | 2008-12-10 00:00:00 | 2008-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1203 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1CF3030W90A08 | (ACW PUMP) Installation - I&C | (ACW PUMP) Installation - I&C | 2008-12-10 | 2008-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1CF3030W90A08 (ACW PUMP) Installation - I&C | Activity | 1CF3030W90A08 | (ACW PUMP) Installation - I&C | 2008-12-10 00:00:00 | 2008-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1204 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1SF3030W62A14 | (ACWS) Loop check | (ACWS) Loop check | 2009-02-24 | 2009-03-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1SF3030W62A14 (ACWS) Loop check | Activity | 1SF3030W62A14 | (ACWS) Loop check | 2009-02-24 00:00:00 | 2009-03-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1205 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1SF3030W62A15 | (ACWS) System Function Test | (ACWS) System Function Test | 2009-03-06 | 2009-03-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1SF3030W62A15 (ACWS) System Function Test | Activity | 1SF3030W62A15 | (ACWS) System Function Test | 2009-03-06 00:00:00 | 2009-03-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1206 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Auxiliary Cooling Water System |  | 1SF3030W62A16 | (ACWS) Pump Operation | (ACWS) Pump Operation | 2009-03-11 | 2009-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Auxiliary Cooling Water System 1SF3030W62A16 (ACWS) Pump Operation | Activity | 1SF3030W62A16 | (ACWS) Pump Operation | 2009-03-11 00:00:00 | 2009-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1208 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1EF2510W00A02 | (Steam System) Silencer Key data | (Steam System) Silencer Key data | 2007-03-30 | 2007-07-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1EF2510W00A02 (Steam System) Silencer Key data | Activity | 1EF2510W00A02 | (Steam System) Silencer Key data | 2007-03-30 00:00:00 | 2007-07-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1209 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1EF2510W00A01 | (Steam System) P&ID | (Steam System) P&ID | 2007-04-02 | 2007-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1EF2510W00A01 (Steam System) P&ID | Activity | 1EF2510W00A01 | (Steam System) P&ID | 2007-04-02 00:00:00 | 2007-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1210 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1EF2510W42A03 | (Silencer) MPS Issue | (Silencer) MPS Issue |  | 2007-07-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1EF2510W42A03 (Silencer) MPS Issue | Activity | 1EF2510W42A03 | (Silencer) MPS Issue |  | 2007-07-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1211 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1EF2510W58A07 | (Steam PIPING) MPS Issue | (Steam PIPING) MPS Issue |  | 2007-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1EF2510W58A07 (Steam PIPING) MPS Issue | Activity | 1EF2510W58A07 | (Steam PIPING) MPS Issue |  | 2007-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1212 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | (Steam PIPING) P.O & Procurement | 2007-10-01 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1PF2510W58A08P (Steam PIPING) P.O & Procurement | Activity | 1PF2510W58A08P | (Steam PIPING) P.O & Procurement | 2007-10-01 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1213 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1PF2510W42A04P | (Silencer) P.O & Procurement | (Silencer) P.O & Procurement | 2007-10-15 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1PF2510W42A04P (Silencer) P.O & Procurement | Activity | 1PF2510W42A04P | (Silencer) P.O & Procurement | 2007-10-15 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1214 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1PF2510W58A09T | (Steam PIPING) Transportation | (Steam PIPING) Transportation | 2008-05-02 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1PF2510W58A09T (Steam PIPING) Transportation | Activity | 1PF2510W58A09T | (Steam PIPING) Transportation | 2008-05-02 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1215 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1CF2510W58A10 | (Steam PIPING) Piping Work | (Steam PIPING) Piping Work | 2008-06-17 | 2008-11-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1CF2510W58A10 (Steam PIPING) Piping Work | Activity | 1CF2510W58A10 | (Steam PIPING) Piping Work | 2008-06-17 00:00:00 | 2008-11-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1216 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1PF2510W42A05T | (Silencer) Transportation | (Silencer) Transportation | 2008-07-16 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1PF2510W42A05T (Silencer) Transportation | Activity | 1PF2510W42A05T | (Silencer) Transportation | 2008-07-16 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1217 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1CF2510W74A12 | (Steam System) Installation & Test - Elec. | (Steam System) Installation & Test - Elec. | 2008-08-30 | 2008-11-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1CF2510W74A12 (Steam System) Installation & Test - Elec. | Activity | 1CF2510W74A12 | (Steam System) Installation & Test - Elec. | 2008-08-30 00:00:00 | 2008-11-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1218 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1CF2510W90A13 | (Steam System) Installation & Test - I&C | (Steam System) Installation & Test - I&C | 2008-08-30 | 2008-11-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1CF2510W90A13 (Steam System) Installation & Test - I&C | Activity | 1CF2510W90A13 | (Steam System) Installation & Test - I&C | 2008-08-30 00:00:00 | 2008-11-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1219 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1CF2510W42A06 | (Silencer) Installation | (Silencer) Installation | 2008-08-30 | 2008-09-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1CF2510W42A06 (Silencer) Installation | Activity | 1CF2510W42A06 | (Silencer) Installation | 2008-08-30 00:00:00 | 2008-09-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1220 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1CF2510W62A11 | (Steam PIPING) Hydro Test | (Steam PIPING) Hydro Test | 2008-11-19 | 2008-12-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1CF2510W62A11 (Steam PIPING) Hydro Test | Activity | 1CF2510W62A11 | (Steam PIPING) Hydro Test | 2008-11-19 00:00:00 | 2008-12-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1221 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1SF2510W62A14 | (Steam System) Loop chek | (Steam System) Loop chek | 2008-12-19 | 2009-01-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1SF2510W62A14 (Steam System) Loop chek | Activity | 1SF2510W62A14 | (Steam System) Loop chek | 2008-12-19 00:00:00 | 2009-01-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1222 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1SF2510W62A15 | (Steam System) System Function Test | (Steam System) System Function Test | 2009-01-08 | 2009-01-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1SF2510W62A15 (Steam System) System Function Test | Activity | 1SF2510W62A15 | (Steam System) System Function Test | 2009-01-08 00:00:00 | 2009-01-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1223 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Steam System |  | 1SF2510W62A16 | (Steam System) System Service | (Steam System) System Service | 2009-01-18 | 2009-01-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Steam System 1SF2510W62A16 (Steam System) System Service | Activity | 1SF2510W62A16 | (Steam System) System Service | 2009-01-18 00:00:00 | 2009-01-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1225 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1EF2510W00A02.1 | (Bypass System) Bypass Valve, PRDS key data | (Bypass System) Bypass Valve, PRDS key data | 2007-03-21 | 2007-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1EF2510W00A02.1 (Bypass System) Bypass Valve, PRDS key data | Activity | 1EF2510W00A02.1 | (Bypass System) Bypass Valve, PRDS key data | 2007-03-21 00:00:00 | 2007-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1226 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1EF2510W00A01.1 | (Bypass System) P&ID & System Design | (Bypass System) P&ID & System Design | 2007-04-02 | 2007-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1EF2510W00A01.1 (Bypass System) P&ID & System Design | Activity | 1EF2510W00A01.1 | (Bypass System) P&ID & System Design | 2007-04-02 00:00:00 | 2007-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1227 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1EF2510W42A03.1 | (Bypass Valve) MPS Issue | (Bypass Valve) MPS Issue |  | 2007-05-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1EF2510W42A03.1 (Bypass Valve) MPS Issue | Activity | 1EF2510W42A03.1 | (Bypass Valve) MPS Issue |  | 2007-05-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1228 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1PF2510W42A04.1P | (Bypass Valve) P.O & Procurement | (Bypass Valve) P.O & Procurement | 2007-08-20 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1PF2510W42A04.1P (Bypass Valve) P.O & Procurement | Activity | 1PF2510W42A04.1P | (Bypass Valve) P.O & Procurement | 2007-08-20 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1229 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1PF2510W42A05.1T | (Bypass Valve) Transportation | (Bypass Valve) Transportation | 2008-06-14 | 2008-07-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1PF2510W42A05.1T (Bypass Valve) Transportation | Activity | 1PF2510W42A05.1T | (Bypass Valve) Transportation | 2008-06-14 00:00:00 | 2008-07-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1230 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1CF2510W58A07.1 | (Bypass System) Piping Work | (Bypass System) Piping Work | 2008-07-30 | 2008-10-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1CF2510W58A07.1 (Bypass System) Piping Work | Activity | 1CF2510W58A07.1 | (Bypass System) Piping Work | 2008-07-30 00:00:00 | 2008-10-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1231 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1CF2510W90A10.1 | (Bypass System) Installation & Test - I&C | (Bypass System) Installation & Test - I&C | 2008-07-30 | 2008-09-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1CF2510W90A10.1 (Bypass System) Installation & Test - I&C | Activity | 1CF2510W90A10.1 | (Bypass System) Installation & Test - I&C | 2008-07-30 00:00:00 | 2008-09-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1232 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1CF2510W74A09.1 | (Bypass System) Installation & Test - Elec. | (Bypass System) Installation & Test - Elec. | 2008-07-30 | 2008-09-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1CF2510W74A09.1 (Bypass System) Installation & Test - Elec. | Activity | 1CF2510W74A09.1 | (Bypass System) Installation & Test - Elec. | 2008-07-30 00:00:00 | 2008-09-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1233 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1CF2510W42A06.1 | (Bypass Valve) Installation | (Bypass Valve) Installation | 2008-07-30 | 2008-09-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1CF2510W42A06.1 (Bypass Valve) Installation | Activity | 1CF2510W42A06.1 | (Bypass Valve) Installation | 2008-07-30 00:00:00 | 2008-09-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1234 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1CF2510W62A08.1 | (Bypass System) Hydro Test | (Bypass System) Hydro Test | 2008-10-30 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1CF2510W62A08.1 (Bypass System) Hydro Test | Activity | 1CF2510W62A08.1 | (Bypass System) Hydro Test | 2008-10-30 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1235 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1SF2510W62A11.1 | (Bypass System) Loop check | (Bypass System) Loop check | 2008-11-16 | 2008-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1SF2510W62A11.1 (Bypass System) Loop check | Activity | 1SF2510W62A11.1 | (Bypass System) Loop check | 2008-11-16 00:00:00 | 2008-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1236 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1SF2510W62A12.1 | (Bypass System) System Function Test | (Bypass System) System Function Test | 2008-11-30 | 2008-12-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1SF2510W62A12.1 (Bypass System) System Function Test | Activity | 1SF2510W62A12.1 | (Bypass System) System Function Test | 2008-11-30 00:00:00 | 2008-12-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1237 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Bypass System |  | 1SF2510W62A13.1 | (Bypass System) System Service | (Bypass System) System Service | 2008-12-10 | 2008-12-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Bypass System 1SF2510W62A13.1 (Bypass System) System Service | Activity | 1SF2510W62A13.1 | (Bypass System) System Service | 2008-12-10 00:00:00 | 2008-12-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1239 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | (Clean Drain System) P&ID & System Design | 2007-03-15 | 2008-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1EF3020W00A01.1 (Clean Drain System) P&ID & System Design | Activity | 1EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | 2007-03-15 00:00:00 | 2008-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1240 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1EF3020W00A02.1 | (Clean Drain System) Clean drain pump Key data | (Clean Drain System) Clean drain pump Key data | 2007-04-02 | 2007-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1EF3020W00A02.1 (Clean Drain System) Clean drain pump Key data | Activity | 1EF3020W00A02.1 | (Clean Drain System) Clean drain pump Key data | 2007-04-02 00:00:00 | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1241 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1EF3020W42A05.1 | (Clean Drain Flash Vessel) MPS Issue | (Clean Drain Flash Vessel) MPS Issue |  | 2007-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1EF3020W42A05.1 (Clean Drain Flash Vessel) MPS Issue | Activity | 1EF3020W42A05.1 | (Clean Drain Flash Vessel) MPS Issue |  | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1242 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1EF3020W42A17.1 | (Clean Drain Pump) MPS Issue | (Clean Drain Pump) MPS Issue |  | 2007-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1EF3020W42A17.1 (Clean Drain Pump) MPS Issue | Activity | 1EF3020W42A17.1 | (Clean Drain Pump) MPS Issue |  | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1243 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1EF3020W42A11.1 | (Clean Drain Tank) MPS Issue | (Clean Drain Tank) MPS Issue |  | 2007-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1EF3020W42A11.1 (Clean Drain Tank) MPS Issue | Activity | 1EF3020W42A11.1 | (Clean Drain Tank) MPS Issue |  | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1244 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1PF3020W42A12.1P | (Clean Drain Tank) P.O & Procurement | (Clean Drain Tank) P.O & Procurement | 2007-10-01 | 2008-09-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1PF3020W42A12.1P (Clean Drain Tank) P.O & Procurement | Activity | 1PF3020W42A12.1P | (Clean Drain Tank) P.O & Procurement | 2007-10-01 00:00:00 | 2008-09-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1245 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1PF3020W42A06.1P | (Clean Drain Flash Vessel) P.O & Procurement | (Clean Drain Flash Vessel) P.O & Procurement | 2007-10-03 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1PF3020W42A06.1P (Clean Drain Flash Vessel) P.O & Procurement | Activity | 1PF3020W42A06.1P | (Clean Drain Flash Vessel) P.O & Procurement | 2007-10-03 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1246 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | (Clean Drain Flash Vessel) FDN Design | 2007-10-03 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1EF3020W16A03.1 (Clean Drain Flash Vessel) FDN Design | Activity | 1EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | 2007-10-03 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1247 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1EF3020W16A15.1 | (Clean Drain Pump) FDN Design | (Clean Drain Pump) FDN Design | 2007-10-03 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1EF3020W16A15.1 (Clean Drain Pump) FDN Design | Activity | 1EF3020W16A15.1 | (Clean Drain Pump) FDN Design | 2007-10-03 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1248 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1PF3020W42A18.1P | (Clean Drain Pump) P.O & Procurement | (Clean Drain Pump) P.O & Procurement | 2007-10-03 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1PF3020W42A18.1P (Clean Drain Pump) P.O & Procurement | Activity | 1PF3020W42A18.1P | (Clean Drain Pump) P.O & Procurement | 2007-10-03 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1249 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1EF3020W16A09.1 | (Clean Drain Tank) FDN Design | (Clean Drain Tank) FDN Design | 2007-12-06 | 2008-05-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1EF3020W16A09.1 (Clean Drain Tank) FDN Design | Activity | 1EF3020W16A09.1 | (Clean Drain Tank) FDN Design | 2007-12-06 00:00:00 | 2008-05-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1250 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1CF3020W16A04.1 | (Clean Drain Flash Vessel) FDN Work | (Clean Drain Flash Vessel) FDN Work | 2008-03-01 | 2008-04-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1CF3020W16A04.1 (Clean Drain Flash Vessel) FDN Work | Activity | 1CF3020W16A04.1 | (Clean Drain Flash Vessel) FDN Work | 2008-03-01 00:00:00 | 2008-04-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1251 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1CF3020W16A16.1 | (Clean Drain Pump) FDN Work | (Clean Drain Pump) FDN Work | 2008-03-01 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1CF3020W16A16.1 (Clean Drain Pump) FDN Work | Activity | 1CF3020W16A16.1 | (Clean Drain Pump) FDN Work | 2008-03-01 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1252 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1PF3020W42A07.1T | (Clean Drain Flash Vessel) Transportation | (Clean Drain Flash Vessel) Transportation | 2008-04-03 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1PF3020W42A07.1T (Clean Drain Flash Vessel) Transportation | Activity | 1PF3020W42A07.1T | (Clean Drain Flash Vessel) Transportation | 2008-04-03 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1253 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1CF3020W16A10.1 | (Clean Drain Tank) FDN Work | (Clean Drain Tank) FDN Work | 2008-05-06 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1CF3020W16A10.1 (Clean Drain Tank) FDN Work | Activity | 1CF3020W16A10.1 | (Clean Drain Tank) FDN Work | 2008-05-06 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1254 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1CF3020W42A08.1 | (Clean Drain Flash Vessel) Installation | (Clean Drain Flash Vessel) Installation | 2008-05-19 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1CF3020W42A08.1 (Clean Drain Flash Vessel) Installation | Activity | 1CF3020W42A08.1 | (Clean Drain Flash Vessel) Installation | 2008-05-19 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1255 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1PF3020W42A19.1T | (Clean Drain Pump) Transportation | (Clean Drain Pump) Transportation | 2008-07-18 | 2008-09-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1PF3020W42A19.1T (Clean Drain Pump) Transportation | Activity | 1PF3020W42A19.1T | (Clean Drain Pump) Transportation | 2008-07-18 00:00:00 | 2008-09-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1256 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1CF3020W42A20.1 | (Clean Drain Pump) Installation | (Clean Drain Pump) Installation | 2008-09-02 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1CF3020W42A20.1 (Clean Drain Pump) Installation | Activity | 1CF3020W42A20.1 | (Clean Drain Pump) Installation | 2008-09-02 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1257 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1PF3020W42A13.1T | (Clean Drain Tank) Transportation | (Clean Drain Tank) Transportation | 2008-09-02 | 2008-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1PF3020W42A13.1T (Clean Drain Tank) Transportation | Activity | 1PF3020W42A13.1T | (Clean Drain Tank) Transportation | 2008-09-02 00:00:00 | 2008-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1258 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1CF3020W58A21.1 | (Clean Drain System) Piping Work | (Clean Drain System) Piping Work | 2008-10-17 | 2009-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1CF3020W58A21.1 (Clean Drain System) Piping Work | Activity | 1CF3020W58A21.1 | (Clean Drain System) Piping Work | 2008-10-17 00:00:00 | 2009-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1259 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1CF3020W42A14.1 | (Clean Drain Tank) Installation | (Clean Drain Tank) Installation | 2008-10-17 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1CF3020W42A14.1 (Clean Drain Tank) Installation | Activity | 1CF3020W42A14.1 | (Clean Drain Tank) Installation | 2008-10-17 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1260 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1CF3020W74A23.1 | (Clean Drain System) Installation & Test - Elec. | (Clean Drain System) Installation & Test - Elec. | 2008-12-17 | 2009-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1CF3020W74A23.1 (Clean Drain System) Installation & Test - Elec. | Activity | 1CF3020W74A23.1 | (Clean Drain System) Installation & Test - Elec. | 2008-12-17 00:00:00 | 2009-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1261 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1CF3020W90A24.1 | (Clean Drain System) Installation & Test - I&C | (Clean Drain System) Installation & Test - I&C | 2008-12-17 | 2009-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1CF3020W90A24.1 (Clean Drain System) Installation & Test - I&C | Activity | 1CF3020W90A24.1 | (Clean Drain System) Installation & Test - I&C | 2008-12-17 00:00:00 | 2009-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1262 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1CF3020W62A22.1 | (Clean Drain System) Hydro Test | (Clean Drain System) Hydro Test | 2009-01-17 | 2009-02-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1CF3020W62A22.1 (Clean Drain System) Hydro Test | Activity | 1CF3020W62A22.1 | (Clean Drain System) Hydro Test | 2009-01-17 00:00:00 | 2009-02-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1263 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1SF3020W62A25.1 | (Clean Drain System) Loop chek | (Clean Drain System) Loop chek | 2009-02-15 | 2009-03-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1SF3020W62A25.1 (Clean Drain System) Loop chek | Activity | 1SF3020W62A25.1 | (Clean Drain System) Loop chek | 2009-02-15 00:00:00 | 2009-03-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1264 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1SF3020W62A26.1 | (Clean Drain System) System Function Test | (Clean Drain System) System Function Test | 2009-03-07 | 2009-03-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1SF3020W62A26.1 (Clean Drain System) System Function Test | Activity | 1SF3020W62A26.1 | (Clean Drain System) System Function Test | 2009-03-07 00:00:00 | 2009-03-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1265 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Combined Power Block Common | Clean Drain System |  | 1SF3020W62A27.1 | (Clean Drain System) System Service | (Clean Drain System) System Service | 2009-03-10 | 2009-03-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Combined Power Block Common Clean Drain System 1SF3020W62A27.1 (Clean Drain System) System Service | Activity | 1SF3020W62A27.1 | (Clean Drain System) System Service | 2009-03-10 00:00:00 | 2009-03-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1268 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Gas Supply System (GTG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Gas Supply System (GTG) |  | 1CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | (Gas Supply System) Piping Work(Yard area) | 2008-05-20 | 2008-07-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Gas Supply System (GTG) 1CF3520W58A01 (Gas Supply System) Piping Work(Yard area) | Activity | 1CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | 2008-05-20 00:00:00 | 2008-07-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1270 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Oil Supply System (GTG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Oil Supply System (GTG) |  | 1CF3520W58A01.1 | (Oil Supply System) Piping Work(Yard area) | (Oil Supply System) Piping Work(Yard area) | 2008-03-03 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Oil Supply System (GTG) 1CF3520W58A01.1 (Oil Supply System) Piping Work(Yard area) | Activity | 1CF3520W58A01.1 | (Oil Supply System) Piping Work(Yard area) | 2008-03-03 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1271 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Oil Supply System (GTG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Oil Supply System (GTG) |  | 1CF3520W62A02.1 | (Oil Supply System) Hydro Test | (Oil Supply System) Hydro Test | 2008-05-03 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Oil Supply System (GTG) 1CF3520W62A02.1 (Oil Supply System) Hydro Test | Activity | 1CF3520W62A02.1 | (Oil Supply System) Hydro Test | 2008-05-03 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1273 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Make Up Wate Supply System (STG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Make Up Wate Supply System (STG) |  | 1CF3010W58A01 | (Make Up WTR Supply System) Piping Work(Block #1) | (Make Up WTR Supply System) Piping Work(Block #1) | 2008-05-19 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Make Up Wate Supply System (STG) 1CF3010W58A01 (Make Up WTR Supply System) Piping Work(Block #1) | Activity | 1CF3010W58A01 | (Make Up WTR Supply System) Piping Work(Block #1) | 2008-05-19 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1274 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Make Up Wate Supply System (STG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Make Up Wate Supply System (STG) |  | 1CF3010W62A02 | (Make Up WTR Supply System) Hydro Test | (Make Up WTR Supply System) Hydro Test | 2008-07-19 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Make Up Wate Supply System (STG) 1CF3010W62A02 (Make Up WTR Supply System) Hydro Test | Activity | 1CF3010W62A02 | (Make Up WTR Supply System) Hydro Test | 2008-07-19 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1276 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Water Treatment Sytstem (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Water Treatment Sytstem (BOP) |  | 1CF3010W58A01.1 | (Water Treatment System) Piping Work(Block #1) | (Water Treatment System) Piping Work(Block #1) | 2008-10-17 | 2008-12-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Water Treatment Sytstem (BOP) 1CF3010W58A01.1 (Water Treatment System) Piping Work(Block #1) | Activity | 1CF3010W58A01.1 | (Water Treatment System) Piping Work(Block #1) | 2008-10-17 00:00:00 | 2008-12-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1277 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Water Treatment Sytstem (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Water Treatment Sytstem (BOP) |  | 1CF3010W62A02.1 | (Water Treatment System) Hydro Test | (Water Treatment System) Hydro Test | 2008-12-17 | 2009-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Water Treatment Sytstem (BOP) 1CF3010W62A02.1 (Water Treatment System) Hydro Test | Activity | 1CF3010W62A02.1 | (Water Treatment System) Hydro Test | 2008-12-17 00:00:00 | 2009-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1279 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Service Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Service Water System (BOP) |  | 1CF3035W58A01 | (SWS) Piping Work(Block #1) | (SWS) Piping Work(Block #1) | 2008-10-17 | 2008-12-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Service Water System (BOP) 1CF3035W58A01 (SWS) Piping Work(Block #1) | Activity | 1CF3035W58A01 | (SWS) Piping Work(Block #1) | 2008-10-17 00:00:00 | 2008-12-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1280 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Service Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Service Water System (BOP) |  | 1CF3035W62A02 | (SWS) Hydro Test | (SWS) Hydro Test | 2008-12-17 | 2009-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Service Water System (BOP) 1CF3035W62A02 (SWS) Hydro Test | Activity | 1CF3035W62A02 | (SWS) Hydro Test | 2008-12-17 00:00:00 | 2009-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1282 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Potable Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Potable Water System (BOP) |  | 1CF3035W58A01.1 | (PWS) Piping Work(Block #1) | (PWS) Piping Work(Block #1) | 2008-11-04 | 2009-01-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Potable Water System (BOP) 1CF3035W58A01.1 (PWS) Piping Work(Block #1) | Activity | 1CF3035W58A01.1 | (PWS) Piping Work(Block #1) | 2008-11-04 00:00:00 | 2009-01-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1283 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Potable Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Potable Water System (BOP) |  | 1CF3035W62A02.1 | (PWS) Hydro Test | (PWS) Hydro Test | 2009-01-03 | 2009-01-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Potable Water System (BOP) 1CF3035W62A02.1 (PWS) Hydro Test | Activity | 1CF3035W62A02.1 | (PWS) Hydro Test | 2009-01-03 00:00:00 | 2009-01-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1285 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Compressed Air System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Compressed Air System (BOP) |  | 1CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_Block #1 | (COMP Air System) Piping Work(incl. Air blowing)_Block #1 | 2008-09-02 | 2008-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Compressed Air System (BOP) 1CF3510W58A01 (COMP Air System) Piping Work(incl. Air blowing)_Block #1 | Activity | 1CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_Block #1 | 2008-09-02 00:00:00 | 2008-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1287 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Waste Water Treatment System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Waste Water Treatment System (BOP) |  | 1CF4035W58A01 | (WWTS) Piping Work(Blcok #1) | (WWTS) Piping Work(Blcok #1) | 2008-10-17 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Waste Water Treatment System (BOP) 1CF4035W58A01 (WWTS) Piping Work(Blcok #1) | Activity | 1CF4035W58A01 | (WWTS) Piping Work(Blcok #1) | 2008-10-17 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1288 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Waste Water Treatment System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Waste Water Treatment System (BOP) |  | 1CF4035W62A02 | (WWTS) Hydro Test | (WWTS) Hydro Test | 2009-01-16 | 2009-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Waste Water Treatment System (BOP) 1CF4035W62A02 (WWTS) Hydro Test | Activity | 1CF4035W62A02 | (WWTS) Hydro Test | 2009-01-16 00:00:00 | 2009-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1290 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Sewage Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Sewage Water System (BOP) |  | 1CF4035W58A01.1 | (STS) Piping Work(Block #1) | (STS) Piping Work(Block #1) | 2008-10-17 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Sewage Water System (BOP) 1CF4035W58A01.1 (STS) Piping Work(Block #1) | Activity | 1CF4035W58A01.1 | (STS) Piping Work(Block #1) | 2008-10-17 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1291 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Sewage Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Sewage Water System (BOP) |  | 1CF4035W62A02.1 | (STS) Hydro Test | (STS) Hydro Test | 2009-01-16 | 2009-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Sewage Water System (BOP) 1CF4035W62A02.1 (STS) Hydro Test | Activity | 1CF4035W62A02.1 | (STS) Hydro Test | 2009-01-16 00:00:00 | 2009-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1293 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > U/G Line | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | U/G Line |  | 1CF4035W22A01 | (STRS) Piping Work(Block #1) | (STRS) Piping Work(Block #1) | 2008-10-17 | 2009-01-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common U/G Line 1CF4035W22A01 (STRS) Piping Work(Block #1) | Activity | 1CF4035W22A01 | (STRS) Piping Work(Block #1) | 2008-10-17 00:00:00 | 2009-01-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1294 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > U/G Line | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | U/G Line |  | 1CF4035W22A02 | (SWS) Piping Work(Block #1) | (SWS) Piping Work(Block #1) | 2008-10-17 | 2009-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common U/G Line 1CF4035W22A02 (SWS) Piping Work(Block #1) | Activity | 1CF4035W22A02 | (SWS) Piping Work(Block #1) | 2008-10-17 00:00:00 | 2009-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1296 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Pipe Rack |  | 1EF5550W00A01 | (PipeRack) Pipe Rack Key Data | (PipeRack) Pipe Rack Key Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Pipe Rack 1EF5550W00A01 (PipeRack) Pipe Rack Key Data | Activity | 1EF5550W00A01 | (PipeRack) Pipe Rack Key Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1297 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Pipe Rack |  | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | (PipeRack) GA & Load Data to Civil Design | 2007-03-30 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Pipe Rack 1EF5550W00A02 (PipeRack) GA & Load Data to Civil Design | Activity | 1EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1298 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Pipe Rack |  | 1EF5550W46A07 | (PipeRack) MPS Issue | (PipeRack) MPS Issue |  | 2007-03-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Pipe Rack 1EF5550W46A07 (PipeRack) MPS Issue | Activity | 1EF5550W46A07 | (PipeRack) MPS Issue |  | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1299 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Pipe Rack |  | 1EF5550W20A05 | (PipeRack) Structure Design | (PipeRack) Structure Design | 2007-05-30 | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Pipe Rack 1EF5550W20A05 (PipeRack) Structure Design | Activity | 1EF5550W20A05 | (PipeRack) Structure Design | 2007-05-30 00:00:00 | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1300 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Pipe Rack |  | 1EF5550W16A03 | (PipeRack) FDN Design | (PipeRack) FDN Design | 2007-05-30 | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Pipe Rack 1EF5550W16A03 (PipeRack) FDN Design | Activity | 1EF5550W16A03 | (PipeRack) FDN Design | 2007-05-30 00:00:00 | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1301 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Pipe Rack |  | 1PF5550W46A08P | (PipeRack) P.O & Procurement | (PipeRack) P.O & Procurement | 2007-06-28 | 2008-01-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Pipe Rack 1PF5550W46A08P (PipeRack) P.O & Procurement | Activity | 1PF5550W46A08P | (PipeRack) P.O & Procurement | 2007-06-28 00:00:00 | 2008-01-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1302 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Pipe Rack |  | 1CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | (PipeRack) FDN Work Block #1 Area | 2007-09-01 | 2008-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Pipe Rack 1CF5550W16A04 (PipeRack) FDN Work Block #1 Area | Activity | 1CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | 2007-09-01 00:00:00 | 2008-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1303 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Pipe Rack |  | 1PF5550W46A09T | (PipeRack) Trasnportation | (PipeRack) Trasnportation | 2008-01-03 | 2008-02-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Pipe Rack 1PF5550W46A09T (PipeRack) Trasnportation | Activity | 1PF5550W46A09T | (PipeRack) Trasnportation | 2008-01-03 00:00:00 | 2008-02-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1304 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > BOP Piping for Block #1 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | BOP Piping for Block #1 Common | Pipe Rack |  | 1CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | (PipeRack) Structure Work for Block #1 Area | 2008-02-18 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 BOP Piping for Block #1 Common Pipe Rack 1CF5550W46A06 (PipeRack) Structure Work for Block #1 Area | Activity | 1CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | 2008-02-18 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1307 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | (GTG Common BLDG) GA & Load Data to Civil Design | 2007-03-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1EF1210W00A06 (GTG Common BLDG) GA & Load Data to Civil Design | Activity | 1EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | 2007-03-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1308 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1EF1210W16A07 | (GTG Common BLDG) FDN Design | (GTG Common BLDG) FDN Design | 2007-03-01 | 2007-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1EF1210W16A07 (GTG Common BLDG) FDN Design | Activity | 1EF1210W16A07 | (GTG Common BLDG) FDN Design | 2007-03-01 00:00:00 | 2007-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1309 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1EF1210W20A09 | (GTG Common BLDG) Structure Design | (GTG Common BLDG) Structure Design | 2007-03-01 | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1EF1210W20A09 (GTG Common BLDG) Structure Design | Activity | 1EF1210W20A09 | (GTG Common BLDG) Structure Design | 2007-03-01 00:00:00 | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1310 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | 2007-03-01 | 2007-03-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1EF1200W00A01 (GTG #11/#12) GTG Process Data (FG, FO, CCW) | Activity | 1EF1200W00A01 | (GTG #11/#12) GTG Process Data (FG, FO, CCW) | 2007-03-01 00:00:00 | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1311 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1EF1200W00A02 | (GTG #11/#12) Instrument, Service Air, Aux steam Data | (GTG #11/#12) Instrument, Service Air, Aux steam Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1EF1200W00A02 (GTG #11/#12) Instrument, Service Air, Aux steam Data | Activity | 1EF1200W00A02 | (GTG #11/#12) Instrument, Service Air, Aux steam Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1312 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1EF1200W00A03 | (GTG #11/#12) Utility Consumption Data | (GTG #11/#12) Utility Consumption Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1EF1200W00A03 (GTG #11/#12) Utility Consumption Data | Activity | 1EF1200W00A03 | (GTG #11/#12) Utility Consumption Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1313 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1EF1200W00A04 | (GTG #11/#12) Emergency Load Data | (GTG #11/#12) Emergency Load Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1EF1200W00A04 (GTG #11/#12) Emergency Load Data | Activity | 1EF1200W00A04 | (GTG #11/#12) Emergency Load Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1314 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1EF1200W00A05 | (GTG #11/#12) Black Start Load Data | (GTG #11/#12) Black Start Load Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1EF1200W00A05 (GTG #11/#12) Black Start Load Data | Activity | 1EF1200W00A05 | (GTG #11/#12) Black Start Load Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1315 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1CF1210W16A08 | (GTG Common BLDG) FDN Work | (GTG Common BLDG) FDN Work | 2007-09-01 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1CF1210W16A08 (GTG Common BLDG) FDN Work | Activity | 1CF1210W16A08 | (GTG Common BLDG) FDN Work | 2007-09-01 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1316 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | (GTG Common BLDG) P.O & Procurement(Steel Structure) | 2007-09-03 | 2008-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1PF1210W20A09P (GTG Common BLDG) P.O & Procurement(Steel Structure) | Activity | 1PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | 2007-09-03 00:00:00 | 2008-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1317 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | 2008-01-16 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1CF1210W20A10 (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | Activity | 1CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | 2008-01-16 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1318 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1CF1210W36A12 | (GTG Common BLDG) Installation & Test - HVAC | (GTG Common BLDG) Installation & Test - HVAC | 2008-05-15 | 2008-07-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1CF1210W36A12 (GTG Common BLDG) Installation & Test - HVAC | Activity | 1CF1210W36A12 | (GTG Common BLDG) Installation & Test - HVAC | 2008-05-15 00:00:00 | 2008-07-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1319 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1CF1210W74A13 | (GTG Common BLDG) Installation & Test - Elec | (GTG Common BLDG) Installation & Test - Elec | 2008-05-20 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1CF1210W74A13 (GTG Common BLDG) Installation & Test - Elec | Activity | 1CF1210W74A13 | (GTG Common BLDG) Installation & Test - Elec | 2008-05-20 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1320 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1CF1210W90A14 | (GTG Common BLDG) Installation & Test - I&C | (GTG Common BLDG) Installation & Test - I&C | 2008-05-20 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1CF1210W90A14 (GTG Common BLDG) Installation & Test - I&C | Activity | 1CF1210W90A14 | (GTG Common BLDG) Installation & Test - I&C | 2008-05-20 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1321 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1CF1210W38A11 | (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1CF1210W38A11 (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | Activity | 1CF1210W38A11 | (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 00:00:00 | 2008-07-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1322 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG Common |  | 1CF1210W24A15 | (GTG Common BLDG) Building Finish | (GTG Common BLDG) Building Finish | 2008-06-27 | 2008-08-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG Common 1CF1210W24A15 (GTG Common BLDG) Building Finish | Activity | 1CF1210W24A15 | (GTG Common BLDG) Building Finish | 2008-06-27 00:00:00 | 2008-08-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1324 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 LEB |  | 1EF1200W00A01.1 | (GTG #11 LEB) GA & Load Data to Civil Design | (GTG #11 LEB) GA & Load Data to Civil Design | 2007-05-31 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 LEB 1EF1200W00A01.1 (GTG #11 LEB) GA & Load Data to Civil Design | Activity | 1EF1200W00A01.1 | (GTG #11 LEB) GA & Load Data to Civil Design | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1325 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 LEB |  | 1EF1200W16A02 | (GTG #11 LEB) FDN Design | (GTG #11 LEB) FDN Design | 2007-08-01 | 2007-11-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 LEB 1EF1200W16A02 (GTG #11 LEB) FDN Design | Activity | 1EF1200W16A02 | (GTG #11 LEB) FDN Design | 2007-08-01 00:00:00 | 2007-11-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1326 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 LEB |  | 1EF1200W32A04 | (GTG #11 LEB) Structure Design | (GTG #11 LEB) Structure Design | 2007-08-01 | 2007-11-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 LEB 1EF1200W32A04 (GTG #11 LEB) Structure Design | Activity | 1EF1200W32A04 | (GTG #11 LEB) Structure Design | 2007-08-01 00:00:00 | 2007-11-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1327 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 LEB |  | 1CF1200W16A03 | (GTG #11 LEB) FDN Work | (GTG #11 LEB) FDN Work | 2007-11-28 | 2008-01-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 LEB 1CF1200W16A03 (GTG #11 LEB) FDN Work | Activity | 1CF1200W16A03 | (GTG #11 LEB) FDN Work | 2007-11-28 00:00:00 | 2008-01-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1328 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 LEB |  | 1CF1200W32A05 | (GTG #11 LEB) Structure Work | (GTG #11 LEB) Structure Work | 2008-01-25 | 2008-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 LEB 1CF1200W32A05 (GTG #11 LEB) Structure Work | Activity | 1CF1200W32A05 | (GTG #11 LEB) Structure Work | 2008-01-25 00:00:00 | 2008-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1329 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 LEB |  | 1CF1200W36A07 | (GTG #11 LEB) Installation & Test - HVAC | (GTG #11 LEB) Installation & Test - HVAC | 2008-05-15 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 LEB 1CF1200W36A07 (GTG #11 LEB) Installation & Test - HVAC | Activity | 1CF1200W36A07 | (GTG #11 LEB) Installation & Test - HVAC | 2008-05-15 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1330 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 LEB |  | 1CF1200W24A10 | (GTG #11 LEB) Building Finish | (GTG #11 LEB) Building Finish | 2008-05-27 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 LEB 1CF1200W24A10 (GTG #11 LEB) Building Finish | Activity | 1CF1200W24A10 | (GTG #11 LEB) Building Finish | 2008-05-27 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1331 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 LEB |  | 1CF1200W38A06 | (GTG #11 LEB) Installation & Test - Fire Fighting Sys. | (GTG #11 LEB) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 LEB 1CF1200W38A06 (GTG #11 LEB) Installation & Test - Fire Fighting Sys. | Activity | 1CF1200W38A06 | (GTG #11 LEB) Installation & Test - Fire Fighting Sys. | 2008-05-31 00:00:00 | 2008-07-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1332 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 LEB |  | 1CF1200W74A08 | (GTG #11 LEB) Installation & Test - Elec | (GTG #11 LEB) Installation & Test - Elec | 2008-06-04 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 LEB 1CF1200W74A08 (GTG #11 LEB) Installation & Test - Elec | Activity | 1CF1200W74A08 | (GTG #11 LEB) Installation & Test - Elec | 2008-06-04 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1333 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 LEB |  | 1CF1200W90A09 | (GTG #11 LEB) Installation & Test - I&C | (GTG #11 LEB) Installation & Test - I&C | 2008-06-04 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 LEB 1CF1200W90A09 (GTG #11 LEB) Installation & Test - I&C | Activity | 1CF1200W90A09 | (GTG #11 LEB) Installation & Test - I&C | 2008-06-04 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1336 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Main body | 1PF1213W42A08P | (GEN #11) P.O & Procurement | (GEN #11) P.O & Procurement | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Main body 1PF1213W42A08P (GEN #11) P.O & Procurement | Activity | 1PF1213W42A08P | (GEN #11) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1337 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Main body | 1EF1213W16A06 | (GEN #11) FDN Design | (GEN #11) FDN Design | 2007-03-01 | 2007-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Main body 1EF1213W16A06 (GEN #11) FDN Design | Activity | 1EF1213W16A06 | (GEN #11) FDN Design | 2007-03-01 00:00:00 | 2007-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1338 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Main body | 1PF1213W42A03P | (GT #11) P.O & Procurement | (GT #11) P.O & Procurement | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Main body 1PF1213W42A03P (GT #11) P.O & Procurement | Activity | 1PF1213W42A03P | (GT #11) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1339 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Main body | 1EF1213W16A01 | (GT #11) FDN Design | (GT #11) FDN Design | 2007-03-01 | 2007-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Main body 1EF1213W16A01 (GT #11) FDN Design | Activity | 1EF1213W16A01 | (GT #11) FDN Design | 2007-03-01 00:00:00 | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1340 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Main body | 1CF1213W16A07 | (GEN #11) FDN Work | (GEN #11) FDN Work | 2007-08-01 | 2007-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Main body 1CF1213W16A07 (GEN #11) FDN Work | Activity | 1CF1213W16A07 | (GEN #11) FDN Work | 2007-08-01 00:00:00 | 2007-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1341 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Main body | 1CF1213W16A02 | (GT #11) FDN Work | (GT #11) FDN Work | 2007-08-01 | 2007-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Main body 1CF1213W16A02 (GT #11) FDN Work | Activity | 1CF1213W16A02 | (GT #11) FDN Work | 2007-08-01 00:00:00 | 2007-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1342 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Main body | 1PF1213W42A09T | (GEN #11) Transportation | (GEN #11) Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Main body 1PF1213W42A09T (GEN #11) Transportation | Activity | 1PF1213W42A09T | (GEN #11) Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1343 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Main body | 1PF1213W42A04T | (GT #11) Transportation | (GT #11) Transportation | 2008-02-01 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Main body 1PF1213W42A04T (GT #11) Transportation | Activity | 1PF1213W42A04T | (GT #11) Transportation | 2008-02-01 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1344 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Main body | 1CF1213W42A05 | (GT #11) Installation(On FDN~Final Alignment) | (GT #11) Installation(On FDN~Final Alignment) | 2008-03-17 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Main body 1CF1213W42A05 (GT #11) Installation(On FDN~Final Alignment) | Activity | 1CF1213W42A05 | (GT #11) Installation(On FDN~Final Alignment) | 2008-03-17 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1345 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Main body | 1CF1213W42A10 | (GEN #11) Installation | (GEN #11) Installation | 2008-04-01 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Main body 1CF1213W42A10 (GEN #11) Installation | Activity | 1CF1213W42A10 | (GEN #11) Installation | 2008-04-01 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1346 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Main body | 1CF1213W52A11 | (GTG #11) Insulation | (GTG #11) Insulation | 2008-06-16 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Main body 1CF1213W52A11 (GTG #11) Insulation | Activity | 1CF1213W52A11 | (GTG #11) Insulation | 2008-06-16 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1348 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Electrical System | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | (GTG#11 Electrical) P.O & Procurement | 2007-03-01 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Electrical System 1PF1255W70A01P (GTG#11 Electrical) P.O & Procurement | Activity | 1PF1255W70A01P | (GTG#11 Electrical) P.O & Procurement | 2007-03-01 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1349 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Electrical System | 1PF1255W70A02T | (GTG#11 Electrical) Transportation | (GTG#11 Electrical) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Electrical System 1PF1255W70A02T (GTG#11 Electrical) Transportation | Activity | 1PF1255W70A02T | (GTG#11 Electrical) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1350 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Electrical System | 1CF1255W70A03 | (GTG#11 Electrical) Installation- PCC | (GTG#11 Electrical) Installation- PCC | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Electrical System 1CF1255W70A03 (GTG#11 Electrical) Installation- PCC | Activity | 1CF1255W70A03 | (GTG#11 Electrical) Installation- PCC | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1351 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Electrical System | 1CF1255W70A04 | (GTG#11 Electrical) Installation- MCC | (GTG#11 Electrical) Installation- MCC | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Electrical System 1CF1255W70A04 (GTG#11 Electrical) Installation- MCC | Activity | 1CF1255W70A04 | (GTG#11 Electrical) Installation- MCC | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1352 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Electrical System | 1CF1255W70A05 | (GTG#11 Electrical) Installation- Protection Sys. | (GTG#11 Electrical) Installation- Protection Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Electrical System 1CF1255W70A05 (GTG#11 Electrical) Installation- Protection Sys. | Activity | 1CF1255W70A05 | (GTG#11 Electrical) Installation- Protection Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1353 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Electrical System | 1CF1255W70A07 | (GTG#11 Electrical) Installation- SEE&SFC Sys. | (GTG#11 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Electrical System 1CF1255W70A07 (GTG#11 Electrical) Installation- SEE&SFC Sys. | Activity | 1CF1255W70A07 | (GTG#11 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1354 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Electrical System | 1CF1255W70A08 | (GTG#11 Electrical) Installation- DC&UPS Sys. | (GTG#11 Electrical) Installation- DC&UPS Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Electrical System 1CF1255W70A08 (GTG#11 Electrical) Installation- DC&UPS Sys. | Activity | 1CF1255W70A08 | (GTG#11 Electrical) Installation- DC&UPS Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1355 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Electrical System | 1CF1255W74A09 | (GTG#11 Electrical) Cable work | (GTG#11 Electrical) Cable work | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Electrical System 1CF1255W74A09 (GTG#11 Electrical) Cable work | Activity | 1CF1255W74A09 | (GTG#11 Electrical) Cable work | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1356 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Electrical System | 1CF1255W86A06 | (GTG#11 Electrical) Installation- GT control Sys. | (GTG#11 Electrical) Installation- GT control Sys. | 2008-08-04 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Electrical System 1CF1255W86A06 (GTG#11 Electrical) Installation- GT control Sys. | Activity | 1CF1255W86A06 | (GTG#11 Electrical) Installation- GT control Sys. | 2008-08-04 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1357 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Electrical System | 1CF1255W62A10 | (GTG#11 Electrical) Electrical Function Test | (GTG#11 Electrical) Electrical Function Test | 2008-09-16 | 2008-09-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Electrical System 1CF1255W62A10 (GTG#11 Electrical) Electrical Function Test | Activity | 1CF1255W62A10 | (GTG#11 Electrical) Electrical Function Test | 2008-09-16 00:00:00 | 2008-09-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1358 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Electrical System | 1CF1255W62A11 | (GTG#11 Electrical) Loop Test | (GTG#11 Electrical) Loop Test | 2008-09-22 | 2008-09-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Electrical System 1CF1255W62A11 (GTG#11 Electrical) Loop Test | Activity | 1CF1255W62A11 | (GTG#11 Electrical) Loop Test | 2008-09-22 00:00:00 | 2008-09-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1360 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Starting System(Turning Device) | 1PF1265W42A01P | (Turning Gear) P.O & Procurement | (Turning Gear) P.O & Procurement | 2007-03-01 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Starting System(Turning Device) 1PF1265W42A01P (Turning Gear) P.O & Procurement | Activity | 1PF1265W42A01P | (Turning Gear) P.O & Procurement | 2007-03-01 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1361 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Starting System(Turning Device) | 1PF1265W42A02T | (Turning Gear) Transportation | (Turning Gear) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Starting System(Turning Device) 1PF1265W42A02T (Turning Gear) Transportation | Activity | 1PF1265W42A02T | (Turning Gear) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1362 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Starting System(Turning Device) | 1CF1265W42A03 | (Turning Gear) Installation | (Turning Gear) Installation | 2008-04-16 | 2008-04-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Starting System(Turning Device) 1CF1265W42A03 (Turning Gear) Installation | Activity | 1CF1265W42A03 | (Turning Gear) Installation | 2008-04-16 00:00:00 | 2008-04-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1363 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Starting System(Turning Device) | 1CF1265W74A04 | (Turning Gear) Installation- Elec. | (Turning Gear) Installation- Elec. | 2008-04-24 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Starting System(Turning Device) 1CF1265W74A04 (Turning Gear) Installation- Elec. | Activity | 1CF1265W74A04 | (Turning Gear) Installation- Elec. | 2008-04-24 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1364 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Starting System(Turning Device) | 1CF1265W90A05 | (Turning Gear) Installation- I&C | (Turning Gear) Installation- I&C | 2008-04-24 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Starting System(Turning Device) 1CF1265W90A05 (Turning Gear) Installation- I&C | Activity | 1CF1265W90A05 | (Turning Gear) Installation- I&C | 2008-04-24 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1365 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Starting System(Turning Device) | 1SF1265W62A06 | (Turning Gear) Loop check | (Turning Gear) Loop check | 2008-05-02 | 2008-05-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Starting System(Turning Device) 1SF1265W62A06 (Turning Gear) Loop check | Activity | 1SF1265W62A06 | (Turning Gear) Loop check | 2008-05-02 00:00:00 | 2008-05-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1366 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Starting System(Turning Device) | 1SF1265W62A07.0 | (Turning Gear) Function Test | (Turning Gear) Function Test | 2008-05-25 | 2008-05-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Starting System(Turning Device) 1SF1265W62A07.0 (Turning Gear) Function Test | Activity | 1SF1265W62A07.0 | (Turning Gear) Function Test | 2008-05-25 00:00:00 | 2008-05-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1368 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1PF1230W20A02P | (Air Intake) P.O & Procurement_Steel Sturucture | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1PF1230W20A02P (Air Intake) P.O & Procurement_Steel Sturucture | Activity | 1PF1230W20A02P | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1369 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1PF1230W64A05P | (Air Intake) P.O & Procurement_Inlet Duct | (Air Intake) P.O & Procurement_Inlet Duct | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1PF1230W64A05P (Air Intake) P.O & Procurement_Inlet Duct | Activity | 1PF1230W64A05P | (Air Intake) P.O & Procurement_Inlet Duct | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1370 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1PF1230W64A08P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1PF1230W64A08P (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 1PF1230W64A08P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1371 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1CF1230W16A01 | (Air Intake) FDN Work_Steel Sturucture | (Air Intake) FDN Work_Steel Sturucture | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1CF1230W16A01 (Air Intake) FDN Work_Steel Sturucture | Activity | 1CF1230W16A01 | (Air Intake) FDN Work_Steel Sturucture | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1372 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1PF1230W20A03T | (Air Intake) Transportation_Steel Sturucture | (Air Intake) Transportation_Steel Sturucture | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1PF1230W20A03T (Air Intake) Transportation_Steel Sturucture | Activity | 1PF1230W20A03T | (Air Intake) Transportation_Steel Sturucture | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1373 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1PF1230W64A06T | (Air Intake) Transportation_Inlet Duct | (Air Intake) Transportation_Inlet Duct | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1PF1230W64A06T (Air Intake) Transportation_Inlet Duct | Activity | 1PF1230W64A06T | (Air Intake) Transportation_Inlet Duct | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1374 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1PF1230W64A09T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1PF1230W64A09T (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 1PF1230W64A09T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1375 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1CF1230W20A04 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-03-18 | 2008-04-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1CF1230W20A04 (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | Activity | 1CF1230W20A04 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-03-18 00:00:00 | 2008-04-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1376 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1CF1230W64A07 | (Air Intake) Installation_Inlet Duct | (Air Intake) Installation_Inlet Duct | 2008-04-19 | 2008-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1CF1230W64A07 (Air Intake) Installation_Inlet Duct | Activity | 1CF1230W64A07 | (Air Intake) Installation_Inlet Duct | 2008-04-19 00:00:00 | 2008-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1377 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1CF1230W64A10 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-04-28 | 2008-05-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1CF1230W64A10 (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 1CF1230W64A10 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-04-28 00:00:00 | 2008-05-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1378 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1CF1230W74A11 | (Air Intake) Installation- Elec. | (Air Intake) Installation- Elec. | 2008-05-22 | 2008-06-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1CF1230W74A11 (Air Intake) Installation- Elec. | Activity | 1CF1230W74A11 | (Air Intake) Installation- Elec. | 2008-05-22 00:00:00 | 2008-06-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1379 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1CF1230W90A12 | (Air Intake) Installation- I&C | (Air Intake) Installation- I&C | 2008-05-22 | 2008-06-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1CF1230W90A12 (Air Intake) Installation- I&C | Activity | 1CF1230W90A12 | (Air Intake) Installation- I&C | 2008-05-22 00:00:00 | 2008-06-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1380 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1SF1230W62A13 | (Air Intake) Loop chek | (Air Intake) Loop chek | 2008-06-05 | 2008-06-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1SF1230W62A13 (Air Intake) Loop chek | Activity | 1SF1230W62A13 | (Air Intake) Loop chek | 2008-06-05 00:00:00 | 2008-06-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1381 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1SF1230W62A14 | (Air Intake) Function Test | (Air Intake) Function Test | 2008-06-11 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1SF1230W62A14 (Air Intake) Function Test | Activity | 1SF1230W62A14 | (Air Intake) Function Test | 2008-06-11 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1382 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air Intake System | 1SF1230W62A15 | (Air Intake) Load(Running) Test | (Air Intake) Load(Running) Test | 2008-06-14 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air Intake System 1SF1230W62A15 (Air Intake) Load(Running) Test | Activity | 1SF1230W62A15 | (Air Intake) Load(Running) Test | 2008-06-14 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1384 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air and Flue Gas System | 1PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air and Flue Gas System 1PF1265W64A01P (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | Activity | 1PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1385 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air and Flue Gas System | 1PF1265W64A02T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air and Flue Gas System 1PF1265W64A02T (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | Activity | 1PF1265W64A02T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1386 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air and Flue Gas System | 1CF1265W64A03 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-03-18 | 2008-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air and Flue Gas System 1CF1265W64A03 (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | Activity | 1CF1265W64A03 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-03-18 00:00:00 | 2008-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1387 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air and Flue Gas System | 1CF1265W64A04 | (Air&Flue Gas System) Duct work | (Air&Flue Gas System) Duct work | 2008-04-18 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air and Flue Gas System 1CF1265W64A04 (Air&Flue Gas System) Duct work | Activity | 1CF1265W64A04 | (Air&Flue Gas System) Duct work | 2008-04-18 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1388 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air and Flue Gas System | 1CF1265W74A05 | (Air&Flue Gas System) Installation- Elec. | (Air&Flue Gas System) Installation- Elec. | 2008-05-03 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air and Flue Gas System 1CF1265W74A05 (Air&Flue Gas System) Installation- Elec. | Activity | 1CF1265W74A05 | (Air&Flue Gas System) Installation- Elec. | 2008-05-03 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1389 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air and Flue Gas System | 1CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | (Air&Flue Gas System) Installation- I&C | 2008-05-03 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air and Flue Gas System 1CF1265W90A06 (Air&Flue Gas System) Installation- I&C | Activity | 1CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | 2008-05-03 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1390 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air and Flue Gas System | 1SF1265W62A07 | (Air&Flue Gas System) Loop chek | (Air&Flue Gas System) Loop chek | 2008-05-14 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air and Flue Gas System 1SF1265W62A07 (Air&Flue Gas System) Loop chek | Activity | 1SF1265W62A07 | (Air&Flue Gas System) Loop chek | 2008-05-14 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1391 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Air and Flue Gas System | 1SF1265W62A08 | (Air&Flue Gas System) Function Test | (Air&Flue Gas System) Function Test | 2008-05-17 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Air and Flue Gas System 1SF1265W62A08 (Air&Flue Gas System) Function Test | Activity | 1SF1265W62A08 | (Air&Flue Gas System) Function Test | 2008-05-17 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1393 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1PF1250W42A02P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-03-01 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1PF1250W42A02P (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | Activity | 1PF1250W42A02P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-03-01 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1394 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-03-01 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1PF1250W42A06P (Lube Oil System) P.O & Procurement_Lube oil functional Module | Activity | 1PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-03-01 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1395 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1PF1250W42A10P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-03-01 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1PF1250W42A10P (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | Activity | 1PF1250W42A10P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-03-01 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1396 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1CF1250W16A01 | (Lube Oil System) FDN Work_Lube Oil Supply Module | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1CF1250W16A01 (Lube Oil System) FDN Work_Lube Oil Supply Module | Activity | 1CF1250W16A01 | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1397 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1CF1250W16A05 | (Lube Oil System) FDN Work_Lube oil functional Module | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1CF1250W16A05 (Lube Oil System) FDN Work_Lube oil functional Module | Activity | 1CF1250W16A05 | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1398 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1CF1250W16A09 | (Lube Oil System) FDN Work_Lube oil Mist Separator | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1CF1250W16A09 (Lube Oil System) FDN Work_Lube oil Mist Separator | Activity | 1CF1250W16A09 | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1399 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1PF1250W42A03T | (Lube Oil System) Transportation_Lube Oil Supply Module | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-01-31 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1PF1250W42A03T (Lube Oil System) Transportation_Lube Oil Supply Module | Activity | 1PF1250W42A03T | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-01-31 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1400 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1PF1250W42A07T | (Lube Oil System) Transportation_Lube oil functional Module | (Lube Oil System) Transportation_Lube oil functional Module | 2008-01-31 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1PF1250W42A07T (Lube Oil System) Transportation_Lube oil functional Module | Activity | 1PF1250W42A07T | (Lube Oil System) Transportation_Lube oil functional Module | 2008-01-31 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1401 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1PF1250W42A11T | (Lube Oil System) Transportation_Lube oil Mist Separator | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-01-31 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1PF1250W42A11T (Lube Oil System) Transportation_Lube oil Mist Separator | Activity | 1PF1250W42A11T | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-01-31 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1402 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1CF1250W42A04 | (Lube Oil System) Installation_Lube Oil Supply Module | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-03-17 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1CF1250W42A04 (Lube Oil System) Installation_Lube Oil Supply Module | Activity | 1CF1250W42A04 | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-03-17 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1403 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1CF1250W42A08 | (Lube Oil System) Installation_Lube oil functional Module | (Lube Oil System) Installation_Lube oil functional Module | 2008-03-17 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1CF1250W42A08 (Lube Oil System) Installation_Lube oil functional Module | Activity | 1CF1250W42A08 | (Lube Oil System) Installation_Lube oil functional Module | 2008-03-17 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1404 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1CF1250W42A12 | (Lube Oil System) Installation_Lube oil Mist Separator | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-03-17 | 2008-03-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1CF1250W42A12 (Lube Oil System) Installation_Lube oil Mist Separator | Activity | 1CF1250W42A12 | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-03-17 00:00:00 | 2008-03-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1405 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1CF1250W58A13 | (Lube Oil System) Piping work | (Lube Oil System) Piping work | 2008-04-02 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1CF1250W58A13 (Lube Oil System) Piping work | Activity | 1CF1250W58A13 | (Lube Oil System) Piping work | 2008-04-02 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1406 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1CF1250W62A16 | (GTG #11) Lube Oil Flushing | (GTG #11) Lube Oil Flushing | 2008-05-02 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1CF1250W62A16 (GTG #11) Lube Oil Flushing | Activity | 1CF1250W62A16 | (GTG #11) Lube Oil Flushing | 2008-05-02 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1407 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1CF1250W74A14 | (Lube Oil System) Installation- Elec. | (Lube Oil System) Installation- Elec. | 2008-05-03 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1CF1250W74A14 (Lube Oil System) Installation- Elec. | Activity | 1CF1250W74A14 | (Lube Oil System) Installation- Elec. | 2008-05-03 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1408 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1CF1250W90A15 | (Lube Oil System) Installation- I&C | (Lube Oil System) Installation- I&C | 2008-05-03 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1CF1250W90A15 (Lube Oil System) Installation- I&C | Activity | 1CF1250W90A15 | (Lube Oil System) Installation- I&C | 2008-05-03 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1409 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1SF1250W62A17 | (Lube Oil System) Loop chek | (Lube Oil System) Loop chek | 2008-05-17 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1SF1250W62A17 (Lube Oil System) Loop chek | Activity | 1SF1250W62A17 | (Lube Oil System) Loop chek | 2008-05-17 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1410 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1SF1250W62A18 | (Lube Oil System) Function Test | (Lube Oil System) Function Test | 2008-05-20 | 2008-05-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1SF1250W62A18 (Lube Oil System) Function Test | Activity | 1SF1250W62A18 | (Lube Oil System) Function Test | 2008-05-20 00:00:00 | 2008-05-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1411 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Lube Oil System | 1SF1250W62A19 | (Lube Oil System) Load Test | (Lube Oil System) Load Test | 2008-05-23 | 2008-05-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Lube Oil System 1SF1250W62A19 (Lube Oil System) Load Test | Activity | 1SF1250W62A19 | (Lube Oil System) Load Test | 2008-05-23 00:00:00 | 2008-05-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1413 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG#11 Generator Seal Oil System | 1PF1250W42A02.1P | (GEN Seal Oil Sys.) P.O & Procurement | (GEN Seal Oil Sys.) P.O & Procurement | 2007-03-01 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG#11 Generator Seal Oil System 1PF1250W42A02.1P (GEN Seal Oil Sys.) P.O & Procurement | Activity | 1PF1250W42A02.1P | (GEN Seal Oil Sys.) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1414 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG#11 Generator Seal Oil System | 1CF1250W16A01.1 | (GEN Seal Oil Sys.) FDN Work | (GEN Seal Oil Sys.) FDN Work | 2007-10-01 | 2007-12-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG#11 Generator Seal Oil System 1CF1250W16A01.1 (GEN Seal Oil Sys.) FDN Work | Activity | 1CF1250W16A01.1 | (GEN Seal Oil Sys.) FDN Work | 2007-10-01 00:00:00 | 2007-12-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1415 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG#11 Generator Seal Oil System | 1PF1250W42A03.1T | (GEN Seal Oil Sys.) Transportation | (GEN Seal Oil Sys.) Transportation | 2008-01-31 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG#11 Generator Seal Oil System 1PF1250W42A03.1T (GEN Seal Oil Sys.) Transportation | Activity | 1PF1250W42A03.1T | (GEN Seal Oil Sys.) Transportation | 2008-01-31 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1416 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG#11 Generator Seal Oil System | 1CF1250W42A04.1 | (GEN Seal Oil Sys.) Installation | (GEN Seal Oil Sys.) Installation | 2008-03-17 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG#11 Generator Seal Oil System 1CF1250W42A04.1 (GEN Seal Oil Sys.) Installation | Activity | 1CF1250W42A04.1 | (GEN Seal Oil Sys.) Installation | 2008-03-17 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1417 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG#11 Generator Seal Oil System | 1CF1250W58A05.1 | (GEN Seal Oil Sys.) Piping Work | (GEN Seal Oil Sys.) Piping Work | 2008-04-01 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG#11 Generator Seal Oil System 1CF1250W58A05.1 (GEN Seal Oil Sys.) Piping Work | Activity | 1CF1250W58A05.1 | (GEN Seal Oil Sys.) Piping Work | 2008-04-01 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1418 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG#11 Generator Seal Oil System | 1CF1250W74A06.1 | (GEN Seal Oil Sys.) Installation- Elec. | (GEN Seal Oil Sys.) Installation- Elec. | 2008-05-02 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG#11 Generator Seal Oil System 1CF1250W74A06.1 (GEN Seal Oil Sys.) Installation- Elec. | Activity | 1CF1250W74A06.1 | (GEN Seal Oil Sys.) Installation- Elec. | 2008-05-02 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1419 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG#11 Generator Seal Oil System | 1CF1250W90A07.1 | (GEN Seal Oil Sys.) Installation- I&C | (GEN Seal Oil Sys.) Installation- I&C | 2008-05-02 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG#11 Generator Seal Oil System 1CF1250W90A07.1 (GEN Seal Oil Sys.) Installation- I&C | Activity | 1CF1250W90A07.1 | (GEN Seal Oil Sys.) Installation- I&C | 2008-05-02 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1420 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG#11 Generator Seal Oil System | 1SF1250W62A08.1 | (GEN Seal Oil Sys.) Oil Flushing | (GEN Seal Oil Sys.) Oil Flushing | 2008-05-02 | 2008-05-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG#11 Generator Seal Oil System 1SF1250W62A08.1 (GEN Seal Oil Sys.) Oil Flushing | Activity | 1SF1250W62A08.1 | (GEN Seal Oil Sys.) Oil Flushing | 2008-05-02 00:00:00 | 2008-05-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1421 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG#11 Generator Seal Oil System | 1SF1250W62A09.1 | (GEN Seal Oil Sys.) Loop chek | (GEN Seal Oil Sys.) Loop chek | 2008-05-16 | 2008-05-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG#11 Generator Seal Oil System 1SF1250W62A09.1 (GEN Seal Oil Sys.) Loop chek | Activity | 1SF1250W62A09.1 | (GEN Seal Oil Sys.) Loop chek | 2008-05-16 00:00:00 | 2008-05-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1422 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG#11 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG#11 Generator Seal Oil System | 1SF1250W62A10.1 | (GEN Seal Oil Sys.) Function Test | (GEN Seal Oil Sys.) Function Test | 2008-05-19 | 2008-05-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG#11 Generator Seal Oil System 1SF1250W62A10.1 (GEN Seal Oil Sys.) Function Test | Activity | 1SF1250W62A10.1 | (GEN Seal Oil Sys.) Function Test | 2008-05-19 00:00:00 | 2008-05-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1424 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1PF1265W42A13P | (TCA Cooler) P.O & Procurement | (TCA Cooler) P.O & Procurement | 2007-03-01 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1PF1265W42A13P (TCA Cooler) P.O & Procurement | Activity | 1PF1265W42A13P | (TCA Cooler) P.O & Procurement | 2007-03-01 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1425 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1PF1265W42A03P | (Gas Final Filter & Metering Skid) P.O & Procurement | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-03-01 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1PF1265W42A03P (Gas Final Filter & Metering Skid) P.O & Procurement | Activity | 1PF1265W42A03P | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1426 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | (Gas Final Filter & Metering Skid) FDN Design | 2007-03-01 | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1EF1265W16A01 (Gas Final Filter & Metering Skid) FDN Design | Activity | 1EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | 2007-03-01 00:00:00 | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1427 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1CF1265W16A02 | (Gas Final Filter & Metering Skid) FDN Work | (Gas Final Filter & Metering Skid) FDN Work | 2007-09-01 | 2007-11-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1CF1265W16A02 (Gas Final Filter & Metering Skid) FDN Work | Activity | 1CF1265W16A02 | (Gas Final Filter & Metering Skid) FDN Work | 2007-09-01 00:00:00 | 2007-11-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1428 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1CF1265W16A12 | (TCA Cooler) FDN Work | (TCA Cooler) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1CF1265W16A12 (TCA Cooler) FDN Work | Activity | 1CF1265W16A12 | (TCA Cooler) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1429 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1PF1265W42A04T | (Gas Final Filter & Metering Skid) Transportation | (Gas Final Filter & Metering Skid) Transportation | 2008-01-31 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1PF1265W42A04T (Gas Final Filter & Metering Skid) Transportation | Activity | 1PF1265W42A04T | (Gas Final Filter & Metering Skid) Transportation | 2008-01-31 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1430 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1PF1265W42A14T | (TCA Cooler) Transportation | (TCA Cooler) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1PF1265W42A14T (TCA Cooler) Transportation | Activity | 1PF1265W42A14T | (TCA Cooler) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1431 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1CF1265W42A05 | (Gas Final Filter & Metering Skid) Installation | (Gas Final Filter & Metering Skid) Installation | 2008-03-17 | 2008-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1CF1265W42A05 (Gas Final Filter & Metering Skid) Installation | Activity | 1CF1265W42A05 | (Gas Final Filter & Metering Skid) Installation | 2008-03-17 00:00:00 | 2008-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1432 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1CF1265W42A15 | (TCA Cooler) Installation | (TCA Cooler) Installation | 2008-04-16 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1CF1265W42A15 (TCA Cooler) Installation | Activity | 1CF1265W42A15 | (TCA Cooler) Installation | 2008-04-16 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1433 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1CF1265W58A06 | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | 2008-05-20 | 2008-07-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1CF1265W58A06 (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | Activity | 1CF1265W58A06 | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | 2008-05-20 00:00:00 | 2008-07-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1434 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1CF1265W74A07 | (FGSS) Installation- Elec. | (FGSS) Installation- Elec. | 2008-07-05 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1CF1265W74A07 (FGSS) Installation- Elec. | Activity | 1CF1265W74A07 | (FGSS) Installation- Elec. | 2008-07-05 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1435 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1CF1265W90A08 | (FGSS) Installation- I&C | (FGSS) Installation- I&C | 2008-07-05 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1CF1265W90A08 (FGSS) Installation- I&C | Activity | 1CF1265W90A08 | (FGSS) Installation- I&C | 2008-07-05 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1436 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1SF1265W62A09 | (FGSS) Loop chek | (FGSS) Loop chek | 2008-08-03 | 2008-08-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1SF1265W62A09 (FGSS) Loop chek | Activity | 1SF1265W62A09 | (FGSS) Loop chek | 2008-08-03 00:00:00 | 2008-08-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1437 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1SF1265W62A10.0 | (FGSS) Function Test | (FGSS) Function Test | 2008-08-13 | 2008-08-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1SF1265W62A10.0 (FGSS) Function Test | Activity | 1SF1265W62A10.0 | (FGSS) Function Test | 2008-08-13 00:00:00 | 2008-08-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1438 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Gas Supply System | 1SF1265W62A11.0 | (FGSS) Gas Receiving upto GT Final Control Valve | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-09-22 | 2008-09-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Gas Supply System 1SF1265W62A11.0 (FGSS) Gas Receiving upto GT Final Control Valve | Activity | 1SF1265W62A11.0 | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-09-22 00:00:00 | 2008-09-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1440 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Washing & Drain System | 1PF1265W42A02.0P | (Washing & Drain system Skid) P.O & Procurement | (Washing & Drain system Skid) P.O & Procurement | 2007-03-01 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Washing & Drain System 1PF1265W42A02.0P (Washing & Drain system Skid) P.O & Procurement | Activity | 1PF1265W42A02.0P | (Washing & Drain system Skid) P.O & Procurement | 2007-03-01 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1441 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Washing & Drain System | 1CF1265W16A01 | (Washing & Drain system Skid) FDN Work | (Washing & Drain system Skid) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Washing & Drain System 1CF1265W16A01 (Washing & Drain system Skid) FDN Work | Activity | 1CF1265W16A01 | (Washing & Drain system Skid) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1442 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Washing & Drain System | 1PF1265W42A03.0T | (Washing & Drain system Skid) Transportation | (Washing & Drain system Skid) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Washing & Drain System 1PF1265W42A03.0T (Washing & Drain system Skid) Transportation | Activity | 1PF1265W42A03.0T | (Washing & Drain system Skid) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1443 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Washing & Drain System | 1CF1265W42A04 | (Washing & Drain system Skid) Installation | (Washing & Drain system Skid) Installation | 2008-04-16 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Washing & Drain System 1CF1265W42A04 (Washing & Drain system Skid) Installation | Activity | 1CF1265W42A04 | (Washing & Drain system Skid) Installation | 2008-04-16 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1444 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Washing & Drain System | 1CF1265W58A05 | (Washing & Drain system Skid) Piping work | (Washing & Drain system Skid) Piping work | 2008-05-03 | 2008-06-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Washing & Drain System 1CF1265W58A05 (Washing & Drain system Skid) Piping work | Activity | 1CF1265W58A05 | (Washing & Drain system Skid) Piping work | 2008-05-03 00:00:00 | 2008-06-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1445 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Washing & Drain System | 1CF1265W62A08 | (Washing & Drain system Skid) Flushing | (Washing & Drain system Skid) Flushing | 2008-06-04 | 2008-06-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Washing & Drain System 1CF1265W62A08 (Washing & Drain system Skid) Flushing | Activity | 1CF1265W62A08 | (Washing & Drain system Skid) Flushing | 2008-06-04 00:00:00 | 2008-06-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1446 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Washing & Drain System | 1CF1265W74A06 | (Washing & Drain system Skid) Installation- Elec. | (Washing & Drain system Skid) Installation- Elec. | 2008-06-04 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Washing & Drain System 1CF1265W74A06 (Washing & Drain system Skid) Installation- Elec. | Activity | 1CF1265W74A06 | (Washing & Drain system Skid) Installation- Elec. | 2008-06-04 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1447 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Washing & Drain System | 1CF1265W90A07 | (Washing & Drain system Skid) Installation- I&C | (Washing & Drain system Skid) Installation- I&C | 2008-06-04 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Washing & Drain System 1CF1265W90A07 (Washing & Drain system Skid) Installation- I&C | Activity | 1CF1265W90A07 | (Washing & Drain system Skid) Installation- I&C | 2008-06-04 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1448 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Washing & Drain System | 1SF1265W62A09.0 | (Washing & Drain system Skid) Loop chek | (Washing & Drain system Skid) Loop chek | 2008-06-18 | 2008-06-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Washing & Drain System 1SF1265W62A09.0 (Washing & Drain system Skid) Loop chek | Activity | 1SF1265W62A09.0 | (Washing & Drain system Skid) Loop chek | 2008-06-18 00:00:00 | 2008-06-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1449 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Washing & Drain System | 1SF1265W62A10 | (Washing & Drain system Skid) Function Test | (Washing & Drain system Skid) Function Test | 2008-06-23 | 2008-06-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Washing & Drain System 1SF1265W62A10 (Washing & Drain system Skid) Function Test | Activity | 1SF1265W62A10 | (Washing & Drain system Skid) Function Test | 2008-06-23 00:00:00 | 2008-06-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1450 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Washing & Drain System | 1SF1265W62A11 | (Washing & Drain system Skid) Load(Running) Test | (Washing & Drain system Skid) Load(Running) Test | 2008-08-12 | 2008-08-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Washing & Drain System 1SF1265W62A11 (Washing & Drain system Skid) Load(Running) Test | Activity | 1SF1265W62A11 | (Washing & Drain system Skid) Load(Running) Test | 2008-08-12 00:00:00 | 2008-08-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1452 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1PF1265W42A02.00P | (Fuel oil injection System) P.O & Procurement | (Fuel oil injection System) P.O & Procurement | 2007-03-01 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1PF1265W42A02.00P (Fuel oil injection System) P.O & Procurement | Activity | 1PF1265W42A02.00P | (Fuel oil injection System) P.O & Procurement | 2007-03-01 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1453 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1PF1265W42A09P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1PF1265W42A09P (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | Activity | 1PF1265W42A09P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1454 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1PF1265W42A16P | (Water injection System) P.O & Procurement | (Water injection System) P.O & Procurement | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1PF1265W42A16P (Water injection System) P.O & Procurement | Activity | 1PF1265W42A16P | (Water injection System) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1455 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1CF1265W16A01.0 | (Fuel oil injection System) FDN Work | (Fuel oil injection System) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1CF1265W16A01.0 (Fuel oil injection System) FDN Work | Activity | 1CF1265W16A01.0 | (Fuel oil injection System) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1456 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1CF1265W16A08 | (Fuel oil injection Pump & actuator) FDN Work | (Fuel oil injection Pump & actuator) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1CF1265W16A08 (Fuel oil injection Pump & actuator) FDN Work | Activity | 1CF1265W16A08 | (Fuel oil injection Pump & actuator) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1457 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1CF1265W16A15 | (Water injection System) FDN Work | (Water injection System) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1CF1265W16A15 (Water injection System) FDN Work | Activity | 1CF1265W16A15 | (Water injection System) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1458 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1PF1265W42A10T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1PF1265W42A10T (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | Activity | 1PF1265W42A10T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1459 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1PF1265W42A17T | (Water injection System) Transportation | (Water injection System) Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1PF1265W42A17T (Water injection System) Transportation | Activity | 1PF1265W42A17T | (Water injection System) Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1460 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1PF1265W42A03.00T | (Fuel oil injection System) Transportation | (Fuel oil injection System) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1PF1265W42A03.00T (Fuel oil injection System) Transportation | Activity | 1PF1265W42A03.00T | (Fuel oil injection System) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1461 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1CF1265W42A11 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-03-18 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1CF1265W42A11 (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | Activity | 1CF1265W42A11 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-03-18 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1462 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1CF1265W42A18 | (Water injection System) Installation | (Water injection System) Installation | 2008-03-18 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1CF1265W42A18 (Water injection System) Installation | Activity | 1CF1265W42A18 | (Water injection System) Installation | 2008-03-18 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1463 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1CF1265W58A19 | (Water injection System) Piping work | (Water injection System) Piping work | 2008-04-02 | 2008-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1CF1265W58A19 (Water injection System) Piping work | Activity | 1CF1265W58A19 | (Water injection System) Piping work | 2008-04-02 00:00:00 | 2008-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1464 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1CF1265W42A04.0 | (Fuel oil injection System) Installation | (Fuel oil injection System) Installation | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1CF1265W42A04.0 (Fuel oil injection System) Installation | Activity | 1CF1265W42A04.0 | (Fuel oil injection System) Installation | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1465 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1CF1265W74A20 | (Water injection System) Installation- Elec. | (Water injection System) Installation- Elec. | 2008-04-17 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1CF1265W74A20 (Water injection System) Installation- Elec. | Activity | 1CF1265W74A20 | (Water injection System) Installation- Elec. | 2008-04-17 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1466 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1CF1265W90A21 | (Water injection System) Installation- I&C | (Water injection System) Installation- I&C | 2008-04-17 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1CF1265W90A21 (Water injection System) Installation- I&C | Activity | 1CF1265W90A21 | (Water injection System) Installation- I&C | 2008-04-17 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1467 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1SF1265W62A22 | (Water injection System) Loop chek | (Water injection System) Loop chek | 2008-05-01 | 2008-05-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1SF1265W62A22 (Water injection System) Loop chek | Activity | 1SF1265W62A22 | (Water injection System) Loop chek | 2008-05-01 00:00:00 | 2008-05-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1468 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1CF1265W58A05.0 | (Fuel oil injection System) Piping work | (Fuel oil injection System) Piping work | 2008-05-05 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1CF1265W58A05.0 (Fuel oil injection System) Piping work | Activity | 1CF1265W58A05.0 | (Fuel oil injection System) Piping work | 2008-05-05 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1469 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1SF1265W62A23 | (Water injection System) Function Test | (Water injection System) Function Test | 2008-05-06 | 2008-05-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1SF1265W62A23 (Water injection System) Function Test | Activity | 1SF1265W62A23 | (Water injection System) Function Test | 2008-05-06 00:00:00 | 2008-05-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1470 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1CF1265W74A06.0 | (Fuel oil injection System) Installation- Elec. | (Fuel oil injection System) Installation- Elec. | 2008-05-20 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1CF1265W74A06.0 (Fuel oil injection System) Installation- Elec. | Activity | 1CF1265W74A06.0 | (Fuel oil injection System) Installation- Elec. | 2008-05-20 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1471 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1CF1265W90A07.0 | (Fuel oil injection System) Installation- I&C | (Fuel oil injection System) Installation- I&C | 2008-05-20 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1CF1265W90A07.0 (Fuel oil injection System) Installation- I&C | Activity | 1CF1265W90A07.0 | (Fuel oil injection System) Installation- I&C | 2008-05-20 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1472 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1SF1265W62A12 | (Fuel oil injection System) Loop chek | (Fuel oil injection System) Loop chek | 2008-06-03 | 2008-06-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1SF1265W62A12 (Fuel oil injection System) Loop chek | Activity | 1SF1265W62A12 | (Fuel oil injection System) Loop chek | 2008-06-03 00:00:00 | 2008-06-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1473 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1SF1265W62A24 | (Water injection System) Load Test | (Water injection System) Load Test | 2008-08-12 | 2008-08-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1SF1265W62A24 (Water injection System) Load Test | Activity | 1SF1265W62A24 | (Water injection System) Load Test | 2008-08-12 00:00:00 | 2008-08-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1474 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1SF1265W62A13 | (Fuel oil injection System) Function Test | (Fuel oil injection System) Function Test | 2008-08-15 | 2008-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1SF1265W62A13 (Fuel oil injection System) Function Test | Activity | 1SF1265W62A13 | (Fuel oil injection System) Function Test | 2008-08-15 00:00:00 | 2008-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1475 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fuel Oil Injection System | 1SF1265W62A14 | (Fuel oil injection System) Flushing | (Fuel oil injection System) Flushing | 2008-08-30 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fuel Oil Injection System 1SF1265W62A14 (Fuel oil injection System) Flushing | Activity | 1SF1265W62A14 | (Fuel oil injection System) Flushing | 2008-08-30 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1477 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Vibration Monitoring System (VMS) | 1EF1260W86A01 | (VMS) MPS Issue for GT | (VMS) MPS Issue for GT |  | 2007-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Vibration Monitoring System (VMS) 1EF1260W86A01 (VMS) MPS Issue for GT | Activity | 1EF1260W86A01 | (VMS) MPS Issue for GT |  | 2007-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1478 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Vibration Monitoring System (VMS) | 1PF1260W86A02P | (VMS) P.O & Procurement for GT | (VMS) P.O & Procurement for GT | 2007-08-31 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Vibration Monitoring System (VMS) 1PF1260W86A02P (VMS) P.O & Procurement for GT | Activity | 1PF1260W86A02P | (VMS) P.O & Procurement for GT | 2007-08-31 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1479 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Vibration Monitoring System (VMS) | 1PF1260W86A03T | (VMS) Transportation for GT | (VMS) Transportation for GT | 2008-05-02 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Vibration Monitoring System (VMS) 1PF1260W86A03T (VMS) Transportation for GT | Activity | 1PF1260W86A03T | (VMS) Transportation for GT | 2008-05-02 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1480 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Vibration Monitoring System (VMS) | 1CF1260W86A04 | (VMS) Installation for GT | (VMS) Installation for GT | 2008-07-31 | 2008-08-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Vibration Monitoring System (VMS) 1CF1260W86A04 (VMS) Installation for GT | Activity | 1CF1260W86A04 | (VMS) Installation for GT | 2008-07-31 00:00:00 | 2008-08-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1481 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Vibration Monitoring System (VMS) | 1SF1260W62A05 | (VMS) Function Test for GT | (VMS) Function Test for GT | 2008-08-08 | 2008-08-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Vibration Monitoring System (VMS) 1SF1260W62A05 (VMS) Function Test for GT | Activity | 1SF1260W62A05 | (VMS) Function Test for GT | 2008-08-08 00:00:00 | 2008-08-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1483 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1EF1225W00A01 | (CCWS) CCW H/EX key data | (CCWS) CCW H/EX key data | 2007-03-01 | 2007-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1EF1225W00A01 (CCWS) CCW H/EX key data | Activity | 1EF1225W00A01 | (CCWS) CCW H/EX key data | 2007-03-01 00:00:00 | 2007-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1484 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1EF1225W00A08 | (CCWP) Key data for GT | (CCWP) Key data for GT | 2007-03-01 | 2007-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1EF1225W00A08 (CCWP) Key data for GT | Activity | 1EF1225W00A08 | (CCWP) Key data for GT | 2007-03-01 00:00:00 | 2007-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1485 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1EF1225W42A17 | (EXP Head Tank) MPS Issue | (EXP Head Tank) MPS Issue |  | 2007-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1EF1225W42A17 (EXP Head Tank) MPS Issue | Activity | 1EF1225W42A17 | (EXP Head Tank) MPS Issue |  | 2007-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1486 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1EF1225W00A11 | (CCWP) MPS Issue for GT | (CCWP) MPS Issue for GT |  | 2007-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1EF1225W00A11 (CCWP) MPS Issue for GT | Activity | 1EF1225W00A11 | (CCWP) MPS Issue for GT |  | 2007-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1487 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1EF1225W42A04 | (CCW H/EX) MPS Issue_Fin fan cooler | (CCW H/EX) MPS Issue_Fin fan cooler |  | 2007-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1EF1225W42A04 (CCW H/EX) MPS Issue_Fin fan cooler | Activity | 1EF1225W42A04 | (CCW H/EX) MPS Issue_Fin fan cooler |  | 2007-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1488 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1PF1225W42A18P | (EXP Head Tank) P.O & Procurement | (EXP Head Tank) P.O & Procurement | 2007-07-03 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1PF1225W42A18P (EXP Head Tank) P.O & Procurement | Activity | 1PF1225W42A18P | (EXP Head Tank) P.O & Procurement | 2007-07-03 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1489 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1EF1225W16A15 | (EXP Head Tank) FDN Design | (EXP Head Tank) FDN Design | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1EF1225W16A15 (EXP Head Tank) FDN Design | Activity | 1EF1225W16A15 | (EXP Head Tank) FDN Design | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1490 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1PF1225W42A12P | (CCWP) P.O & Procurement for GT | (CCWP) P.O & Procurement for GT | 2007-07-03 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1PF1225W42A12P (CCWP) P.O & Procurement for GT | Activity | 1PF1225W42A12P | (CCWP) P.O & Procurement for GT | 2007-07-03 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1491 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1EF1225W16A09 | (CCWP) FDN Design | (CCWP) FDN Design | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1EF1225W16A09 (CCWP) FDN Design | Activity | 1EF1225W16A09 | (CCWP) FDN Design | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1492 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1PF1225W42A05P (CCW H/EX) P.O & Procurement_Fin fan cooler | Activity | 1PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1493 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1EF1225W16A02 (CCW H/EX) FDN Design_Fin fan cooler | Activity | 1EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1494 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1CF1225W16A16 | (EXP Head Tank) FDN Work | (EXP Head Tank) FDN Work | 2007-11-30 | 2007-12-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1CF1225W16A16 (EXP Head Tank) FDN Work | Activity | 1CF1225W16A16 | (EXP Head Tank) FDN Work | 2007-11-30 00:00:00 | 2007-12-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1495 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1CF1225W16A10 | (CCWP) FDN Work | (CCWP) FDN Work | 2007-11-30 | 2008-01-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1CF1225W16A10 (CCWP) FDN Work | Activity | 1CF1225W16A10 | (CCWP) FDN Work | 2007-11-30 00:00:00 | 2008-01-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1496 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1CF1225W16A03 | (CCW H/EX) FDN Work_Fin fan cooler | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 | 2008-02-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1CF1225W16A03 (CCW H/EX) FDN Work_Fin fan cooler | Activity | 1CF1225W16A03 | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 00:00:00 | 2008-02-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1497 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1PF1225W42A19T | (EXP Head Tank) Transportation | (EXP Head Tank) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1PF1225W42A19T (EXP Head Tank) Transportation | Activity | 1PF1225W42A19T | (EXP Head Tank) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1498 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1PF1225W42A13T | (CCWP) Transportation for GT | (CCWP) Transportation for GT | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1PF1225W42A13T (CCWP) Transportation for GT | Activity | 1PF1225W42A13T | (CCWP) Transportation for GT | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1499 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1PF1225W42A06T | (CCW H/EX) Transportation_Fin fan cooler | (CCW H/EX) Transportation_Fin fan cooler | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1PF1225W42A06T (CCW H/EX) Transportation_Fin fan cooler | Activity | 1PF1225W42A06T | (CCW H/EX) Transportation_Fin fan cooler | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1500 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1CF1225W58A21 | (CCWS) Piping Work | (CCWS) Piping Work | 2008-04-26 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1CF1225W58A21 (CCWS) Piping Work | Activity | 1CF1225W58A21 | (CCWS) Piping Work | 2008-04-26 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1501 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1CF1225W42A20 | (EXP Head Tank) Installation | (EXP Head Tank) Installation | 2008-05-16 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1CF1225W42A20 (EXP Head Tank) Installation | Activity | 1CF1225W42A20 | (EXP Head Tank) Installation | 2008-05-16 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1502 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1CF1225W42A14 | (CCWP) Installation | (CCWP) Installation | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1CF1225W42A14 (CCWP) Installation | Activity | 1CF1225W42A14 | (CCWP) Installation | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1503 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | (CCW H/EX) Installation_Fin fan cooler | 2008-05-16 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1CF1225W42A07 (CCW H/EX) Installation_Fin fan cooler | Activity | 1CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | 2008-05-16 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1504 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1CF1225W74A22 | (CCWS) Installation & Test - Elec. | (CCWS) Installation & Test - Elec. | 2008-05-30 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1CF1225W74A22 (CCWS) Installation & Test - Elec. | Activity | 1CF1225W74A22 | (CCWS) Installation & Test - Elec. | 2008-05-30 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1505 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1CF1225W90A23 | (CCWS) Installation & Test - I&C | (CCWS) Installation & Test - I&C | 2008-05-30 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1CF1225W90A23 (CCWS) Installation & Test - I&C | Activity | 1CF1225W90A23 | (CCWS) Installation & Test - I&C | 2008-05-30 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1506 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1SF1225W62A24 | (CCWS) Loop chek | (CCWS) Loop chek | 2008-07-01 | 2008-07-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1SF1225W62A24 (CCWS) Loop chek | Activity | 1SF1225W62A24 | (CCWS) Loop chek | 2008-07-01 00:00:00 | 2008-07-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1507 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1SF1225W62A25 | (CCWS) Function Test | (CCWS) Function Test | 2008-07-11 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1SF1225W62A25 (CCWS) Function Test | Activity | 1SF1225W62A25 | (CCWS) Function Test | 2008-07-11 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1508 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Closed Cooling Water System | 1SF1225W62A26 | (CCWS) Flushing | (CCWS) Flushing | 2008-08-08 | 2008-08-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Closed Cooling Water System 1SF1225W62A26 (CCWS) Flushing | Activity | 1SF1225W62A26 | (CCWS) Flushing | 2008-08-08 00:00:00 | 2008-08-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1510 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fire fighting System | 1PF1265W38A01P | (F/F GTG#11) P.O & Procurement_CO2 FF System | (F/F GTG#11) P.O & Procurement_CO2 FF System | 2007-03-01 | 2008-03-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fire fighting System 1PF1265W38A01P (F/F GTG#11) P.O & Procurement_CO2 FF System | Activity | 1PF1265W38A01P | (F/F GTG#11) P.O & Procurement_CO2 FF System | 2007-03-01 00:00:00 | 2008-03-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1511 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fire fighting System | 1PF1265W38A04P | (F/F GTG#11) P.O & Procurement_Clean Agent FF System | (F/F GTG#11) P.O & Procurement_Clean Agent FF System | 2007-03-01 | 2008-03-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fire fighting System 1PF1265W38A04P (F/F GTG#11) P.O & Procurement_Clean Agent FF System | Activity | 1PF1265W38A04P | (F/F GTG#11) P.O & Procurement_Clean Agent FF System | 2007-03-01 00:00:00 | 2008-03-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1512 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fire fighting System | 1PF1265W38A02T | (F/F GTG#11) Transportation_CO2 FF System | (F/F GTG#11) Transportation_CO2 FF System | 2008-03-15 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fire fighting System 1PF1265W38A02T (F/F GTG#11) Transportation_CO2 FF System | Activity | 1PF1265W38A02T | (F/F GTG#11) Transportation_CO2 FF System | 2008-03-15 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1513 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fire fighting System | 1PF1265W38A05T | (F/F GTG#11) Transportation_Clean Agent FF System | (F/F GTG#11) Transportation_Clean Agent FF System | 2008-03-15 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fire fighting System 1PF1265W38A05T (F/F GTG#11) Transportation_Clean Agent FF System | Activity | 1PF1265W38A05T | (F/F GTG#11) Transportation_Clean Agent FF System | 2008-03-15 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1514 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fire fighting System | 1CF1265W38A03 | (F/F GTG#11) Installation_CO2 FF System | (F/F GTG#11) Installation_CO2 FF System | 2008-04-30 | 2008-05-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fire fighting System 1CF1265W38A03 (F/F GTG#11) Installation_CO2 FF System | Activity | 1CF1265W38A03 | (F/F GTG#11) Installation_CO2 FF System | 2008-04-30 00:00:00 | 2008-05-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1515 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fire fighting System | 1CF1265W38A06 | (F/F GTG#11) Installation_Clean Agent FF System | (F/F GTG#11) Installation_Clean Agent FF System | 2008-04-30 | 2008-05-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fire fighting System 1CF1265W38A06 (F/F GTG#11) Installation_Clean Agent FF System | Activity | 1CF1265W38A06 | (F/F GTG#11) Installation_Clean Agent FF System | 2008-04-30 00:00:00 | 2008-05-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1516 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fire fighting System | 1CF1265W38A07 | (F/F GTG#11) Piping work | (F/F GTG#11) Piping work | 2008-05-15 | 2008-06-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fire fighting System 1CF1265W38A07 (F/F GTG#11) Piping work | Activity | 1CF1265W38A07 | (F/F GTG#11) Piping work | 2008-05-15 00:00:00 | 2008-06-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1517 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fire fighting System | 1SF1265W62A08.2 | (F/F GTG#11) Loop chek | (F/F GTG#11) Loop chek | 2008-06-08 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fire fighting System 1SF1265W62A08.2 (F/F GTG#11) Loop chek | Activity | 1SF1265W62A08.2 | (F/F GTG#11) Loop chek | 2008-06-08 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1518 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fire fighting System | 1SF1265W62A09.2 | (F/F GTG#11) Function Test(incl. Alarm Test) | (F/F GTG#11) Function Test(incl. Alarm Test) | 2008-06-15 | 2008-06-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fire fighting System 1SF1265W62A09.2 (F/F GTG#11) Function Test(incl. Alarm Test) | Activity | 1SF1265W62A09.2 | (F/F GTG#11) Function Test(incl. Alarm Test) | 2008-06-15 00:00:00 | 2008-06-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1519 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Fire fighting System | 1SF1265W62A10.2 | (F/F GTG#11) CO2 Discharge Test | (F/F GTG#11) CO2 Discharge Test | 2008-06-25 | 2008-07-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Fire fighting System 1SF1265W62A10.2 (F/F GTG#11) CO2 Discharge Test | Activity | 1SF1265W62A10.2 | (F/F GTG#11) CO2 Discharge Test | 2008-06-25 00:00:00 | 2008-07-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1521 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1PF1265W42A02.3P | (Purge Air System) P.O & Procurement | (Purge Air System) P.O & Procurement | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1PF1265W42A02.3P (Purge Air System) P.O & Procurement | Activity | 1PF1265W42A02.3P | (Purge Air System) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1522 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1PF1265W42A12P | (Control Oil) P.O & Procurement | (Control Oil) P.O & Procurement | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1PF1265W42A12P (Control Oil) P.O & Procurement | Activity | 1PF1265W42A12P | (Control Oil) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1523 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1CF1265W16A01.3 | (Purge Air System) FDN Work | (Purge Air System) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1CF1265W16A01.3 (Purge Air System) FDN Work | Activity | 1CF1265W16A01.3 | (Purge Air System) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1524 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1CF1265W16A11 | (Control Oil) FDN Work | (Control Oil) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1CF1265W16A11 (Control Oil) FDN Work | Activity | 1CF1265W16A11 | (Control Oil) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1525 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1PF1265W42A03.3T | (Purge Air System) Transportation | (Purge Air System) Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1PF1265W42A03.3T (Purge Air System) Transportation | Activity | 1PF1265W42A03.3T | (Purge Air System) Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1526 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1PF1265W42A13.0T | (Control Oil)Transportation | (Control Oil)Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1PF1265W42A13.0T (Control Oil)Transportation | Activity | 1PF1265W42A13.0T | (Control Oil)Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1527 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1CF1265W42A04.3 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-03-18 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1CF1265W42A04.3 (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | Activity | 1CF1265W42A04.3 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-03-18 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1528 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1CF1265W42A14 | (Control Oil) Installation | (Control Oil) Installation | 2008-03-18 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1CF1265W42A14 (Control Oil) Installation | Activity | 1CF1265W42A14 | (Control Oil) Installation | 2008-03-18 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1529 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1CF1265W58A05.3 | (Purge Air System) Piping work | (Purge Air System) Piping work | 2008-04-02 | 2008-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1CF1265W58A05.3 (Purge Air System) Piping work | Activity | 1CF1265W58A05.3 | (Purge Air System) Piping work | 2008-04-02 00:00:00 | 2008-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1530 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1CF1265W58A15 | (Control Oil) Piping work | (Control Oil) Piping work | 2008-04-02 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1CF1265W58A15 (Control Oil) Piping work | Activity | 1CF1265W58A15 | (Control Oil) Piping work | 2008-04-02 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1531 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1CF1265W74A06.3 | (Purge Air System) Installation- Elec. | (Purge Air System) Installation- Elec. | 2008-04-17 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1CF1265W74A06.3 (Purge Air System) Installation- Elec. | Activity | 1CF1265W74A06.3 | (Purge Air System) Installation- Elec. | 2008-04-17 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1532 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1CF1265W90A07.3 | (Purge Air System) Installation- I&C | (Purge Air System) Installation- I&C | 2008-04-17 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1CF1265W90A07.3 (Purge Air System) Installation- I&C | Activity | 1CF1265W90A07.3 | (Purge Air System) Installation- I&C | 2008-04-17 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1533 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1SF1265W62A08.3 | (Purge Air System) Loop chek | (Purge Air System) Loop chek | 2008-05-01 | 2008-05-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1SF1265W62A08.3 (Purge Air System) Loop chek | Activity | 1SF1265W62A08.3 | (Purge Air System) Loop chek | 2008-05-01 00:00:00 | 2008-05-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1534 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1CF1265W74A16 | (Control Oil) Installation- Elec. | (Control Oil) Installation- Elec. | 2008-05-03 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1CF1265W74A16 (Control Oil) Installation- Elec. | Activity | 1CF1265W74A16 | (Control Oil) Installation- Elec. | 2008-05-03 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1535 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1CF1265W90A17 | (Control Oil) Installation- I&C | (Control Oil) Installation- I&C | 2008-05-03 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1CF1265W90A17 (Control Oil) Installation- I&C | Activity | 1CF1265W90A17 | (Control Oil) Installation- I&C | 2008-05-03 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1536 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1SF1265W62A09.3 | (Purge Air System) Function Test | (Purge Air System) Function Test | 2008-05-04 | 2008-05-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1SF1265W62A09.3 (Purge Air System) Function Test | Activity | 1SF1265W62A09.3 | (Purge Air System) Function Test | 2008-05-04 00:00:00 | 2008-05-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1537 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1SF1265W62A10.3 | (Purge Air System) Load Test | (Purge Air System) Load Test | 2008-05-07 | 2008-05-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1SF1265W62A10.3 (Purge Air System) Load Test | Activity | 1SF1265W62A10.3 | (Purge Air System) Load Test | 2008-05-07 00:00:00 | 2008-05-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1538 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1SF1265W62A18 | (Control Oil) Loop chek | (Control Oil) Loop chek | 2008-05-17 | 2008-05-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1SF1265W62A18 (Control Oil) Loop chek | Activity | 1SF1265W62A18 | (Control Oil) Loop chek | 2008-05-17 00:00:00 | 2008-05-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1539 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1SF1265W62A19 | (Control Oil) Function Test | (Control Oil) Function Test | 2008-05-22 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1SF1265W62A19 (Control Oil) Function Test | Activity | 1SF1265W62A19 | (Control Oil) Function Test | 2008-05-22 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1540 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Auxiliary System | 1SF1265W62A20 | (Control Oil) Flushing | (Control Oil) Flushing | 2008-06-01 | 2008-06-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Auxiliary System 1SF1265W62A20 (Control Oil) Flushing | Activity | 1SF1265W62A20 | (Control Oil) Flushing | 2008-06-01 00:00:00 | 2008-06-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1542 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9011W62A01 | (GTG #11) Fuel Gas System Final Function Test | (GTG #11) Fuel Gas System Final Function Test | 2008-09-29 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9011W62A01 (GTG #11) Fuel Gas System Final Function Test | Activity | 1SF9011W62A01 | (GTG #11) Fuel Gas System Final Function Test | 2008-09-29 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1543 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9011W62A02 | (GTG #11) Turning Gear Operation | (GTG #11) Turning Gear Operation | 2008-10-02 | 2008-10-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9011W62A02 (GTG #11) Turning Gear Operation | Activity | 1SF9011W62A02 | (GTG #11) Turning Gear Operation | 2008-10-02 00:00:00 | 2008-10-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1544 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9011W62A03 | (GTG #11) Initial Firing with FSNL | (GTG #11) Initial Firing with FSNL | 2008-10-04 | 2008-10-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9011W62A03 (GTG #11) Initial Firing with FSNL | Activity | 1SF9011W62A03 | (GTG #11) Initial Firing with FSNL | 2008-10-04 00:00:00 | 2008-10-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1545 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9012W62A04 | (GTG #11) TBN & GEN Protection Test | (GTG #11) TBN & GEN Protection Test | 2008-10-22 | 2008-10-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9012W62A04 (GTG #11) TBN & GEN Protection Test | Activity | 1SF9012W62A04 | (GTG #11) TBN & GEN Protection Test | 2008-10-22 00:00:00 | 2008-10-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1546 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9012W62A05 | (GTG #11) 1st Synchronization | (GTG #11) 1st Synchronization | 2008-10-24 | 2008-10-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9012W62A05 (GTG #11) 1st Synchronization | Activity | 1SF9012W62A05 | (GTG #11) 1st Synchronization | 2008-10-24 00:00:00 | 2008-10-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1547 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9012W62A06 | (GTG #11) Optimization with Fuel Gas | (GTG #11) Optimization with Fuel Gas | 2008-10-25 | 2008-10-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9012W62A06 (GTG #11) Optimization with Fuel Gas | Activity | 1SF9012W62A06 | (GTG #11) Optimization with Fuel Gas | 2008-10-25 00:00:00 | 2008-10-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1548 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9012W62A07 | (GTG #11) Fuel Oil System Final Function Test | (GTG #11) Fuel Oil System Final Function Test | 2008-10-31 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9012W62A07 (GTG #11) Fuel Oil System Final Function Test | Activity | 1SF9012W62A07 | (GTG #11) Fuel Oil System Final Function Test | 2008-10-31 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1549 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9012W62A08 | (GTG #11) Optimization with Fuel Oil | (GTG #11) Optimization with Fuel Oil | 2008-10-31 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9012W62A08 (GTG #11) Optimization with Fuel Oil | Activity | 1SF9012W62A08 | (GTG #11) Optimization with Fuel Oil | 2008-10-31 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1550 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9012W62A09 | (GTG #11) Black start Test with GT | (GTG #11) Black start Test with GT | 2008-10-31 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9012W62A09 (GTG #11) Black start Test with GT | Activity | 1SF9012W62A09 | (GTG #11) Black start Test with GT | 2008-10-31 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1551 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9012W62A10 | (GTG #11) Trial Run Test | (GTG #11) Trial Run Test | 2008-11-01 | 2008-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9012W62A10 (GTG #11) Trial Run Test | Activity | 1SF9012W62A10 | (GTG #11) Trial Run Test | 2008-11-01 00:00:00 | 2008-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1552 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9013W62A11 | (GTG #11) Reliability Test | (GTG #11) Reliability Test | 2008-11-02 | 2008-11-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9013W62A11 (GTG #11) Reliability Test | Activity | 1SF9013W62A11 | (GTG #11) Reliability Test | 2008-11-02 00:00:00 | 2008-11-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1553 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9013W62A12 | (GTG #11) Performance Test (Fuel Gas & Fuel Oil) | (GTG #11) Performance Test (Fuel Gas & Fuel Oil) | 2008-11-17 | 2008-11-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9013W62A12 (GTG #11) Performance Test (Fuel Gas & Fuel Oil) | Activity | 1SF9013W62A12 | (GTG #11) Performance Test (Fuel Gas & Fuel Oil) | 2008-11-17 00:00:00 | 2008-11-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1554 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #11 > GTG #11 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #11 | GTG #11 Commissioning | 1SF9012W62A13 | (GTG #11) Fuel Change-Over Test | (GTG #11) Fuel Change-Over Test | 2008-11-27 | 2008-11-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #11 GTG #11 Commissioning 1SF9012W62A13 (GTG #11) Fuel Change-Over Test | Activity | 1SF9012W62A13 | (GTG #11) Fuel Change-Over Test | 2008-11-27 00:00:00 | 2008-11-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1557 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Main body | 1PF1213W42A08.1P | (Gen #12) P.O & Procurement | (Gen #12) P.O & Procurement | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Main body 1PF1213W42A08.1P (Gen #12) P.O & Procurement | Activity | 1PF1213W42A08.1P | (Gen #12) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1558 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Main body | 1EF1213W16A06.1 | (Gen #12) FDN Design | (Gen #12) FDN Design | 2007-03-01 | 2007-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Main body 1EF1213W16A06.1 (Gen #12) FDN Design | Activity | 1EF1213W16A06.1 | (Gen #12) FDN Design | 2007-03-01 00:00:00 | 2007-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1559 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Main body | 1PF1213W42A03.1P | (GT #12) P.O & Procurement | (GT #12) P.O & Procurement | 2007-03-01 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Main body 1PF1213W42A03.1P (GT #12) P.O & Procurement | Activity | 1PF1213W42A03.1P | (GT #12) P.O & Procurement | 2007-03-01 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1560 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Main body | 1EF1213W16A01.1 | (GT #12) FDN Design | (GT #12) FDN Design | 2007-03-01 | 2007-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Main body 1EF1213W16A01.1 (GT #12) FDN Design | Activity | 1EF1213W16A01.1 | (GT #12) FDN Design | 2007-03-01 00:00:00 | 2007-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1561 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Main body | 1CF1213W16A07.1 | (Gen #12) FDN Work | (Gen #12) FDN Work | 2007-08-01 | 2007-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Main body 1CF1213W16A07.1 (Gen #12) FDN Work | Activity | 1CF1213W16A07.1 | (Gen #12) FDN Work | 2007-08-01 00:00:00 | 2007-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1562 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Main body | 1CF1213W16A02.1 | (GT #12) FDN Work | (GT #12) FDN Work | 2007-08-01 | 2007-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Main body 1CF1213W16A02.1 (GT #12) FDN Work | Activity | 1CF1213W16A02.1 | (GT #12) FDN Work | 2007-08-01 00:00:00 | 2007-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1563 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Main body | 1PF1213W42A09.1T | (Gen #12) Transportation | (Gen #12) Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Main body 1PF1213W42A09.1T (Gen #12) Transportation | Activity | 1PF1213W42A09.1T | (Gen #12) Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1564 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Main body | 1PF1213W42A04.1T | (GT #12) Transportation | (GT #12) Transportation | 2008-03-01 | 2008-04-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Main body 1PF1213W42A04.1T (GT #12) Transportation | Activity | 1PF1213W42A04.1T | (GT #12) Transportation | 2008-03-01 00:00:00 | 2008-04-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1565 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Main body | 1CF1213W42A10.1 | (Gen #12) Installation | (Gen #12) Installation | 2008-03-18 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Main body 1CF1213W42A10.1 (Gen #12) Installation | Activity | 1CF1213W42A10.1 | (Gen #12) Installation | 2008-03-18 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1566 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Main body | 1CF1213W42A05.1 | (GT #12) Installation(On FDN~Final Alignment) | (GT #12) Installation(On FDN~Final Alignment) | 2008-04-15 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Main body 1CF1213W42A05.1 (GT #12) Installation(On FDN~Final Alignment) | Activity | 1CF1213W42A05.1 | (GT #12) Installation(On FDN~Final Alignment) | 2008-04-15 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1567 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Main body | 1CF1213W52A11.1 | (GT #12) Insulation | (GT #12) Insulation | 2008-06-16 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Main body 1CF1213W52A11.1 (GT #12) Insulation | Activity | 1CF1213W52A11.1 | (GT #12) Insulation | 2008-06-16 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1569 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Electrical System | 1PF1255W70A01.1P | (GTG#12 Electrical) P.O & Procurement | (GTG#12 Electrical) P.O & Procurement | 2007-03-01 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Electrical System 1PF1255W70A01.1P (GTG#12 Electrical) P.O & Procurement | Activity | 1PF1255W70A01.1P | (GTG#12 Electrical) P.O & Procurement | 2007-03-01 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1570 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Electrical System | 1PF1255W70A02.1T | (GTG#12 Electrical) Transportation | (GTG#12 Electrical) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Electrical System 1PF1255W70A02.1T (GTG#12 Electrical) Transportation | Activity | 1PF1255W70A02.1T | (GTG#12 Electrical) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1571 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Electrical System | 1CF1255W70A03.1 | (GTG#12 Electrical) Installation- PCC | (GTG#12 Electrical) Installation- PCC | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Electrical System 1CF1255W70A03.1 (GTG#12 Electrical) Installation- PCC | Activity | 1CF1255W70A03.1 | (GTG#12 Electrical) Installation- PCC | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1572 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Electrical System | 1CF1255W70A04.1 | (GTG#12 Electrical) Installation- MCC | (GTG#12 Electrical) Installation- MCC | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Electrical System 1CF1255W70A04.1 (GTG#12 Electrical) Installation- MCC | Activity | 1CF1255W70A04.1 | (GTG#12 Electrical) Installation- MCC | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1573 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Electrical System | 1CF1255W70A05.1 | (GTG#12 Electrical) Installation- Protection Sys. | (GTG#12 Electrical) Installation- Protection Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Electrical System 1CF1255W70A05.1 (GTG#12 Electrical) Installation- Protection Sys. | Activity | 1CF1255W70A05.1 | (GTG#12 Electrical) Installation- Protection Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1574 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Electrical System | 1CF1255W70A07.1 | (GTG#12 Electrical) Installation- SEE&SFC Sys. | (GTG#12 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Electrical System 1CF1255W70A07.1 (GTG#12 Electrical) Installation- SEE&SFC Sys. | Activity | 1CF1255W70A07.1 | (GTG#12 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1575 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Electrical System | 1CF1255W70A08.1 | (GTG#12 Electrical) Installation- DC&UPS Sys. | (GTG#12 Electrical) Installation- DC&UPS Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Electrical System 1CF1255W70A08.1 (GTG#12 Electrical) Installation- DC&UPS Sys. | Activity | 1CF1255W70A08.1 | (GTG#12 Electrical) Installation- DC&UPS Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1576 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Electrical System | 1CF1255W74A09.1 | (GTG#12 Electrical) Cable work | (GTG#12 Electrical) Cable work | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Electrical System 1CF1255W74A09.1 (GTG#12 Electrical) Cable work | Activity | 1CF1255W74A09.1 | (GTG#12 Electrical) Cable work | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1577 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Electrical System | 1CF1255W86A06.1 | (GTG#12 Electrical) Installation- GT control Sys. | (GTG#12 Electrical) Installation- GT control Sys. | 2008-08-04 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Electrical System 1CF1255W86A06.1 (GTG#12 Electrical) Installation- GT control Sys. | Activity | 1CF1255W86A06.1 | (GTG#12 Electrical) Installation- GT control Sys. | 2008-08-04 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1578 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Electrical System | 1CF1255W62A10.1 | (GTG#12 Electrical) Electrical Function Test | (GTG#12 Electrical) Electrical Function Test | 2008-09-16 | 2008-09-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Electrical System 1CF1255W62A10.1 (GTG#12 Electrical) Electrical Function Test | Activity | 1CF1255W62A10.1 | (GTG#12 Electrical) Electrical Function Test | 2008-09-16 00:00:00 | 2008-09-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1579 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Electrical System | 1CF1255W62A11.1 | (GTG#12 Electrical) Loop Test | (GTG#12 Electrical) Loop Test | 2008-09-22 | 2008-09-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Electrical System 1CF1255W62A11.1 (GTG#12 Electrical) Loop Test | Activity | 1CF1255W62A11.1 | (GTG#12 Electrical) Loop Test | 2008-09-22 00:00:00 | 2008-09-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1581 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Starting System(Turning Device) | 1PF1265W42A01.1P | (Turning Gear) P.O & Procurement | (Turning Gear) P.O & Procurement | 2007-03-01 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Starting System(Turning Device) 1PF1265W42A01.1P (Turning Gear) P.O & Procurement | Activity | 1PF1265W42A01.1P | (Turning Gear) P.O & Procurement | 2007-03-01 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1582 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Starting System(Turning Device) | 1PF1265W42A02.1T | (Turning Gear) Transportation | (Turning Gear) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Starting System(Turning Device) 1PF1265W42A02.1T (Turning Gear) Transportation | Activity | 1PF1265W42A02.1T | (Turning Gear) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1583 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Starting System(Turning Device) | 1CF1265W42A03.1 | (Turning Gear) Installation | (Turning Gear) Installation | 2008-04-16 | 2008-04-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Starting System(Turning Device) 1CF1265W42A03.1 (Turning Gear) Installation | Activity | 1CF1265W42A03.1 | (Turning Gear) Installation | 2008-04-16 00:00:00 | 2008-04-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1584 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Starting System(Turning Device) | 1CF1265W74A04.1 | (Turning Gear) Installation- Elec. | (Turning Gear) Installation- Elec. | 2008-04-24 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Starting System(Turning Device) 1CF1265W74A04.1 (Turning Gear) Installation- Elec. | Activity | 1CF1265W74A04.1 | (Turning Gear) Installation- Elec. | 2008-04-24 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1585 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Starting System(Turning Device) | 1CF1265W90A05.1 | (Turning Gear) Installation- I&C | (Turning Gear) Installation- I&C | 2008-04-24 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Starting System(Turning Device) 1CF1265W90A05.1 (Turning Gear) Installation- I&C | Activity | 1CF1265W90A05.1 | (Turning Gear) Installation- I&C | 2008-04-24 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1586 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Starting System(Turning Device) | 1SF1265W62A06.1 | (Turning Gear) Loop check | (Turning Gear) Loop check | 2008-05-02 | 2008-05-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Starting System(Turning Device) 1SF1265W62A06.1 (Turning Gear) Loop check | Activity | 1SF1265W62A06.1 | (Turning Gear) Loop check | 2008-05-02 00:00:00 | 2008-05-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1587 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Starting System(Turning Device) | 1SF1265W62A07.1 | (Turning Gear) Function Test | (Turning Gear) Function Test | 2008-05-26 | 2008-05-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Starting System(Turning Device) 1SF1265W62A07.1 (Turning Gear) Function Test | Activity | 1SF1265W62A07.1 | (Turning Gear) Function Test | 2008-05-26 00:00:00 | 2008-05-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1589 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1PF1230W20A02.1P | (Air Intake) P.O & Procurement_Steel Sturucture | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1PF1230W20A02.1P (Air Intake) P.O & Procurement_Steel Sturucture | Activity | 1PF1230W20A02.1P | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1590 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1PF1230W64A05.1P | (Air Intake) P.O & Procurement_Inlet Duct | (Air Intake) P.O & Procurement_Inlet Duct | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1PF1230W64A05.1P (Air Intake) P.O & Procurement_Inlet Duct | Activity | 1PF1230W64A05.1P | (Air Intake) P.O & Procurement_Inlet Duct | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1591 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1PF1230W64A08.1P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1PF1230W64A08.1P (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 1PF1230W64A08.1P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1592 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1CF1230W16A01.1 | (Air Intake) FDN Work_Steel Sturucture | (Air Intake) FDN Work_Steel Sturucture | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1CF1230W16A01.1 (Air Intake) FDN Work_Steel Sturucture | Activity | 1CF1230W16A01.1 | (Air Intake) FDN Work_Steel Sturucture | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1593 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1PF1230W20A03.1T | (Air Intake) Transportation_Steel Sturucture | (Air Intake) Transportation_Steel Sturucture | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1PF1230W20A03.1T (Air Intake) Transportation_Steel Sturucture | Activity | 1PF1230W20A03.1T | (Air Intake) Transportation_Steel Sturucture | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1594 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1PF1230W64A06.1T | (Air Intake) Transportation_Inlet Duct | (Air Intake) Transportation_Inlet Duct | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1PF1230W64A06.1T (Air Intake) Transportation_Inlet Duct | Activity | 1PF1230W64A06.1T | (Air Intake) Transportation_Inlet Duct | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1595 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1PF1230W64A09.1T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1PF1230W64A09.1T (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 1PF1230W64A09.1T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1596 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1CF1230W20A04.1 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-04-01 | 2008-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1CF1230W20A04.1 (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | Activity | 1CF1230W20A04.1 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-04-01 00:00:00 | 2008-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1597 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1CF1230W64A07.1 | (Air Intake) Installation_Inlet Duct | (Air Intake) Installation_Inlet Duct | 2008-04-18 | 2008-04-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1CF1230W64A07.1 (Air Intake) Installation_Inlet Duct | Activity | 1CF1230W64A07.1 | (Air Intake) Installation_Inlet Duct | 2008-04-18 00:00:00 | 2008-04-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1598 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1CF1230W64A10.1 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-04-26 | 2008-05-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1CF1230W64A10.1 (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 1CF1230W64A10.1 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-04-26 00:00:00 | 2008-05-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1599 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1CF1230W74A11.1 | (Air Intake) Installation- Elec. | (Air Intake) Installation- Elec. | 2008-05-21 | 2008-06-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1CF1230W74A11.1 (Air Intake) Installation- Elec. | Activity | 1CF1230W74A11.1 | (Air Intake) Installation- Elec. | 2008-05-21 00:00:00 | 2008-06-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1600 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1CF1230W90A12.1 | (Air Intake) Installation- I&C | (Air Intake) Installation- I&C | 2008-05-21 | 2008-06-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1CF1230W90A12.1 (Air Intake) Installation- I&C | Activity | 1CF1230W90A12.1 | (Air Intake) Installation- I&C | 2008-05-21 00:00:00 | 2008-06-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1601 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1SF1230W62A13.1 | (Air Intake) Loop chek | (Air Intake) Loop chek | 2008-06-04 | 2008-06-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1SF1230W62A13.1 (Air Intake) Loop chek | Activity | 1SF1230W62A13.1 | (Air Intake) Loop chek | 2008-06-04 00:00:00 | 2008-06-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1602 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1SF1230W62A14.1 | (Air Intake) Function Test | (Air Intake) Function Test | 2008-06-11 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1SF1230W62A14.1 (Air Intake) Function Test | Activity | 1SF1230W62A14.1 | (Air Intake) Function Test | 2008-06-11 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1603 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air Intake System | 1SF1230W62A15.1 | (Air Intake) Load(Running) Test | (Air Intake) Load(Running) Test | 2008-06-14 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air Intake System 1SF1230W62A15.1 (Air Intake) Load(Running) Test | Activity | 1SF1230W62A15.1 | (Air Intake) Load(Running) Test | 2008-06-14 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1605 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air and Flue Gas System | 1PF1265W64A01.1P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air and Flue Gas System 1PF1265W64A01.1P (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | Activity | 1PF1265W64A01.1P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1606 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air and Flue Gas System | 1PF1265W64A02.1T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air and Flue Gas System 1PF1265W64A02.1T (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | Activity | 1PF1265W64A02.1T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1607 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air and Flue Gas System | 1CF1265W64A03.1 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-03-18 | 2008-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air and Flue Gas System 1CF1265W64A03.1 (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | Activity | 1CF1265W64A03.1 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-03-18 00:00:00 | 2008-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1608 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air and Flue Gas System | 1CF1265W64A04.1 | (Air&Flue Gas System) Duct work | (Air&Flue Gas System) Duct work | 2008-04-18 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air and Flue Gas System 1CF1265W64A04.1 (Air&Flue Gas System) Duct work | Activity | 1CF1265W64A04.1 | (Air&Flue Gas System) Duct work | 2008-04-18 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1609 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air and Flue Gas System | 1CF1265W74A06.1 | (Air&Flue Gas System) Installation- Elec. | (Air&Flue Gas System) Installation- Elec. | 2008-05-03 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air and Flue Gas System 1CF1265W74A06.1 (Air&Flue Gas System) Installation- Elec. | Activity | 1CF1265W74A06.1 | (Air&Flue Gas System) Installation- Elec. | 2008-05-03 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1610 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air and Flue Gas System | 1CF1265W90A07.1 | (Air&Flue Gas System) Installation- I&C | (Air&Flue Gas System) Installation- I&C | 2008-05-03 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air and Flue Gas System 1CF1265W90A07.1 (Air&Flue Gas System) Installation- I&C | Activity | 1CF1265W90A07.1 | (Air&Flue Gas System) Installation- I&C | 2008-05-03 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1611 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air and Flue Gas System | 1SF1265W62A05.1 | (Air&Flue Gas System) Loop chek | (Air&Flue Gas System) Loop chek | 2008-05-14 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air and Flue Gas System 1SF1265W62A05.1 (Air&Flue Gas System) Loop chek | Activity | 1SF1265W62A05.1 | (Air&Flue Gas System) Loop chek | 2008-05-14 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1612 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Air and Flue Gas System | 1SF1265W62A08.1 | (Air&Flue Gas System) Function Test | (Air&Flue Gas System) Function Test | 2008-05-17 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Air and Flue Gas System 1SF1265W62A08.1 (Air&Flue Gas System) Function Test | Activity | 1SF1265W62A08.1 | (Air&Flue Gas System) Function Test | 2008-05-17 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1614 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1PF1250W42A10.2P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1PF1250W42A10.2P (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | Activity | 1PF1250W42A10.2P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1615 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1PF1250W42A02.2P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1PF1250W42A02.2P (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | Activity | 1PF1250W42A02.2P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1616 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1PF1250W42A06.2P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1PF1250W42A06.2P (Lube Oil System) P.O & Procurement_Lube oil functional Module | Activity | 1PF1250W42A06.2P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1617 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1CF1250W16A05.2 | (Lube Oil System) FDN Work_Lube oil functional Module | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1CF1250W16A05.2 (Lube Oil System) FDN Work_Lube oil functional Module | Activity | 1CF1250W16A05.2 | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1618 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1CF1250W16A09.2 | (Lube Oil System) FDN Work_Lube oil Mist Separator | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1CF1250W16A09.2 (Lube Oil System) FDN Work_Lube oil Mist Separator | Activity | 1CF1250W16A09.2 | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1619 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1CF1250W16A01.2 | (Lube Oil System) FDN Work_Lube Oil Supply Module | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1CF1250W16A01.2 (Lube Oil System) FDN Work_Lube Oil Supply Module | Activity | 1CF1250W16A01.2 | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1620 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1PF1250W42A07.2T | (Lube Oil System) Transportation_Lube oil functional Module | (Lube Oil System) Transportation_Lube oil functional Module | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1PF1250W42A07.2T (Lube Oil System) Transportation_Lube oil functional Module | Activity | 1PF1250W42A07.2T | (Lube Oil System) Transportation_Lube oil functional Module | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1621 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1PF1250W42A11.2T | (Lube Oil System) Transportation_Lube oil Mist Separator | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1PF1250W42A11.2T (Lube Oil System) Transportation_Lube oil Mist Separator | Activity | 1PF1250W42A11.2T | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1622 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1PF1250W42A03.2T | (Lube Oil System) Transportation_Lube Oil Supply Module | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1PF1250W42A03.2T (Lube Oil System) Transportation_Lube Oil Supply Module | Activity | 1PF1250W42A03.2T | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1623 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1CF1250W42A08.2 | (Lube Oil System) Installation_Lube oil functional Module | (Lube Oil System) Installation_Lube oil functional Module | 2008-03-18 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1CF1250W42A08.2 (Lube Oil System) Installation_Lube oil functional Module | Activity | 1CF1250W42A08.2 | (Lube Oil System) Installation_Lube oil functional Module | 2008-03-18 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1624 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1CF1250W42A12.2 | (Lube Oil System) Installation_Lube oil Mist Separator | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-03-18 | 2008-03-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1CF1250W42A12.2 (Lube Oil System) Installation_Lube oil Mist Separator | Activity | 1CF1250W42A12.2 | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-03-18 00:00:00 | 2008-03-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1625 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1CF1250W42A04.2 | (Lube Oil System) Installation_Lube Oil Supply Module | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-03-18 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1CF1250W42A04.2 (Lube Oil System) Installation_Lube Oil Supply Module | Activity | 1CF1250W42A04.2 | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-03-18 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1626 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1CF1250W58A13.2 | (Lube Oil System) Piping work | (Lube Oil System) Piping work | 2008-04-03 | 2008-05-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1CF1250W58A13.2 (Lube Oil System) Piping work | Activity | 1CF1250W58A13.2 | (Lube Oil System) Piping work | 2008-04-03 00:00:00 | 2008-05-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1627 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1CF1250W62A16.2 | (GTG #12) Lube Oil Flushing | (GTG #12) Lube Oil Flushing | 2008-05-03 | 2008-05-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1CF1250W62A16.2 (GTG #12) Lube Oil Flushing | Activity | 1CF1250W62A16.2 | (GTG #12) Lube Oil Flushing | 2008-05-03 00:00:00 | 2008-05-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1628 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1CF1250W74A14.2 | (Lube Oil System) Installation- Elec. | (Lube Oil System) Installation- Elec. | 2008-05-05 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1CF1250W74A14.2 (Lube Oil System) Installation- Elec. | Activity | 1CF1250W74A14.2 | (Lube Oil System) Installation- Elec. | 2008-05-05 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1629 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1CF1250W90A15.2 | (Lube Oil System) Installation- I&C | (Lube Oil System) Installation- I&C | 2008-05-05 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1CF1250W90A15.2 (Lube Oil System) Installation- I&C | Activity | 1CF1250W90A15.2 | (Lube Oil System) Installation- I&C | 2008-05-05 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1630 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1SF1250W62A17.2 | (Lube Oil System) Loop chek | (Lube Oil System) Loop chek | 2008-05-18 | 2008-05-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1SF1250W62A17.2 (Lube Oil System) Loop chek | Activity | 1SF1250W62A17.2 | (Lube Oil System) Loop chek | 2008-05-18 00:00:00 | 2008-05-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1631 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1SF1250W62A18.2 | (Lube Oil System) Function Test | (Lube Oil System) Function Test | 2008-05-21 | 2008-05-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1SF1250W62A18.2 (Lube Oil System) Function Test | Activity | 1SF1250W62A18.2 | (Lube Oil System) Function Test | 2008-05-21 00:00:00 | 2008-05-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1632 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Lube Oil System | 1SF1250W62A19.2 | (Lube Oil System) Load Test | (Lube Oil System) Load Test | 2008-05-24 | 2008-05-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Lube Oil System 1SF1250W62A19.2 (Lube Oil System) Load Test | Activity | 1SF1250W62A19.2 | (Lube Oil System) Load Test | 2008-05-24 00:00:00 | 2008-05-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1634 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Generator Seal Oil System | 1PF1250W42A02.3P | (GEN Seal Oil Sys.) P.O & Procurement | (GEN Seal Oil Sys.) P.O & Procurement | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Generator Seal Oil System 1PF1250W42A02.3P (GEN Seal Oil Sys.) P.O & Procurement | Activity | 1PF1250W42A02.3P | (GEN Seal Oil Sys.) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1635 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Generator Seal Oil System | 1CF1250W16A01.3 | (GEN Seal Oil Sys.) FDN Work | (GEN Seal Oil Sys.) FDN Work | 2007-10-01 | 2007-12-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Generator Seal Oil System 1CF1250W16A01.3 (GEN Seal Oil Sys.) FDN Work | Activity | 1CF1250W16A01.3 | (GEN Seal Oil Sys.) FDN Work | 2007-10-01 00:00:00 | 2007-12-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1636 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Generator Seal Oil System | 1PF1250W42A03.3T | (GEN Seal Oil Sys.) Transportation | (GEN Seal Oil Sys.) Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Generator Seal Oil System 1PF1250W42A03.3T (GEN Seal Oil Sys.) Transportation | Activity | 1PF1250W42A03.3T | (GEN Seal Oil Sys.) Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1637 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Generator Seal Oil System | 1CF1250W42A04.3 | (GEN Seal Oil Sys.) Installation | (GEN Seal Oil Sys.) Installation | 2008-03-18 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Generator Seal Oil System 1CF1250W42A04.3 (GEN Seal Oil Sys.) Installation | Activity | 1CF1250W42A04.3 | (GEN Seal Oil Sys.) Installation | 2008-03-18 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1638 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Generator Seal Oil System | 1CF1250W58A05.3 | (GEN Seal Oil Sys.) Piping Work | (GEN Seal Oil Sys.) Piping Work | 2008-04-02 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Generator Seal Oil System 1CF1250W58A05.3 (GEN Seal Oil Sys.) Piping Work | Activity | 1CF1250W58A05.3 | (GEN Seal Oil Sys.) Piping Work | 2008-04-02 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1639 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Generator Seal Oil System | 1CF1250W74A07.3 | (GEN Seal Oil Sys.) Installation- Elec. | (GEN Seal Oil Sys.) Installation- Elec. | 2008-05-03 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Generator Seal Oil System 1CF1250W74A07.3 (GEN Seal Oil Sys.) Installation- Elec. | Activity | 1CF1250W74A07.3 | (GEN Seal Oil Sys.) Installation- Elec. | 2008-05-03 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1640 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Generator Seal Oil System | 1CF1250W90A08.3 | (GEN Seal Oil Sys.) Installation- I&C | (GEN Seal Oil Sys.) Installation- I&C | 2008-05-03 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Generator Seal Oil System 1CF1250W90A08.3 (GEN Seal Oil Sys.) Installation- I&C | Activity | 1CF1250W90A08.3 | (GEN Seal Oil Sys.) Installation- I&C | 2008-05-03 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1641 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Generator Seal Oil System | 1SF1250W62A06.3 | (GEN Seal Oil Sys.) Oil Flushing | (GEN Seal Oil Sys.) Oil Flushing | 2008-05-03 | 2008-05-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Generator Seal Oil System 1SF1250W62A06.3 (GEN Seal Oil Sys.) Oil Flushing | Activity | 1SF1250W62A06.3 | (GEN Seal Oil Sys.) Oil Flushing | 2008-05-03 00:00:00 | 2008-05-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1642 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Generator Seal Oil System | 1SF1250W62A09.3 | (GEN Seal Oil Sys.) Loop chek | (GEN Seal Oil Sys.) Loop chek | 2008-05-17 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Generator Seal Oil System 1SF1250W62A09.3 (GEN Seal Oil Sys.) Loop chek | Activity | 1SF1250W62A09.3 | (GEN Seal Oil Sys.) Loop chek | 2008-05-17 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1643 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Generator Seal Oil System | 1SF1250W62A10.3 | (GEN Seal Oil Sys.) Function Test | (GEN Seal Oil Sys.) Function Test | 2008-05-20 | 2008-05-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Generator Seal Oil System 1SF1250W62A10.3 (GEN Seal Oil Sys.) Function Test | Activity | 1SF1250W62A10.3 | (GEN Seal Oil Sys.) Function Test | 2008-05-20 00:00:00 | 2008-05-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1645 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1PF1265W42A13.4P | (TCA Cooler) P.O & Procurement | (TCA Cooler) P.O & Procurement | 2007-03-01 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1PF1265W42A13.4P (TCA Cooler) P.O & Procurement | Activity | 1PF1265W42A13.4P | (TCA Cooler) P.O & Procurement | 2007-03-01 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1646 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1PF1265W42A03.4P | (Gas Final Filter & Metering Skid) P.O & Procurement | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1PF1265W42A03.4P (Gas Final Filter & Metering Skid) P.O & Procurement | Activity | 1PF1265W42A03.4P | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1647 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1EF1265W16A01.4 | (Gas Final Filter & Metering Skid) FDN Design | (Gas Final Filter & Metering Skid) FDN Design | 2007-03-01 | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1EF1265W16A01.4 (Gas Final Filter & Metering Skid) FDN Design | Activity | 1EF1265W16A01.4 | (Gas Final Filter & Metering Skid) FDN Design | 2007-03-01 00:00:00 | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1648 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1CF1265W16A02.4 | (Gas Final Filter & Metering Skid) FDN Work | (Gas Final Filter & Metering Skid) FDN Work | 2007-09-01 | 2007-11-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1CF1265W16A02.4 (Gas Final Filter & Metering Skid) FDN Work | Activity | 1CF1265W16A02.4 | (Gas Final Filter & Metering Skid) FDN Work | 2007-09-01 00:00:00 | 2007-11-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1649 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1CF1265W16A12.4 | (TCA Cooler) FDN Work | (TCA Cooler) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1CF1265W16A12.4 (TCA Cooler) FDN Work | Activity | 1CF1265W16A12.4 | (TCA Cooler) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1650 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1PF1265W42A04.4T | (Gas Final Filter & Metering Skid) Transportation | (Gas Final Filter & Metering Skid) Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1PF1265W42A04.4T (Gas Final Filter & Metering Skid) Transportation | Activity | 1PF1265W42A04.4T | (Gas Final Filter & Metering Skid) Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1651 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1PF1265W42A14.4T | (TCA Cooler) Transportation | (TCA Cooler) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1PF1265W42A14.4T (TCA Cooler) Transportation | Activity | 1PF1265W42A14.4T | (TCA Cooler) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1652 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1CF1265W42A05.4 | (Gas Final Filter & Metering Skid) Installation | (Gas Final Filter & Metering Skid) Installation | 2008-03-18 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1CF1265W42A05.4 (Gas Final Filter & Metering Skid) Installation | Activity | 1CF1265W42A05.4 | (Gas Final Filter & Metering Skid) Installation | 2008-03-18 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1653 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1CF1265W42A15.4 | (TCA Cooler) Installation | (TCA Cooler) Installation | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1CF1265W42A15.4 (TCA Cooler) Installation | Activity | 1CF1265W42A15.4 | (TCA Cooler) Installation | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1654 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1CF1265W58A06.4 | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | 2008-05-20 | 2008-06-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1CF1265W58A06.4 (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | Activity | 1CF1265W58A06.4 | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | 2008-05-20 00:00:00 | 2008-06-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1655 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1CF1265W74A07.4 | (FGSS) Installation- Elec. | (FGSS) Installation- Elec. | 2008-06-20 | 2008-07-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1CF1265W74A07.4 (FGSS) Installation- Elec. | Activity | 1CF1265W74A07.4 | (FGSS) Installation- Elec. | 2008-06-20 00:00:00 | 2008-07-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1656 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1CF1265W90A08.4 | (FGSS) Installation- I&C | (FGSS) Installation- I&C | 2008-06-20 | 2008-07-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1CF1265W90A08.4 (FGSS) Installation- I&C | Activity | 1CF1265W90A08.4 | (FGSS) Installation- I&C | 2008-06-20 00:00:00 | 2008-07-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1657 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1SF1265W62A09.4 | (FGSS) Loop chek | (FGSS) Loop chek | 2008-08-03 | 2008-08-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1SF1265W62A09.4 (FGSS) Loop chek | Activity | 1SF1265W62A09.4 | (FGSS) Loop chek | 2008-08-03 00:00:00 | 2008-08-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1658 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1SF1265W62A10.4 | (FGSS) Function Test | (FGSS) Function Test | 2008-08-13 | 2008-08-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1SF1265W62A10.4 (FGSS) Function Test | Activity | 1SF1265W62A10.4 | (FGSS) Function Test | 2008-08-13 00:00:00 | 2008-08-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1659 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Gas Supply System | 1SF1265W62A11.4 | (FGSS) Gas Receiving upto GT Final Control Valve | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-09-22 | 2008-09-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Gas Supply System 1SF1265W62A11.4 (FGSS) Gas Receiving upto GT Final Control Valve | Activity | 1SF1265W62A11.4 | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-09-22 00:00:00 | 2008-09-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1661 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Washing & Drain System | 1PF1265W42A02.5P | (Washing & Drain system Skid) P.O & Procurement | (Washing & Drain system Skid) P.O & Procurement | 2007-03-01 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Washing & Drain System 1PF1265W42A02.5P (Washing & Drain system Skid) P.O & Procurement | Activity | 1PF1265W42A02.5P | (Washing & Drain system Skid) P.O & Procurement | 2007-03-01 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1662 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Washing & Drain System | 1CF1265W16A01.5 | (Washing & Drain system Skid) FDN Work | (Washing & Drain system Skid) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Washing & Drain System 1CF1265W16A01.5 (Washing & Drain system Skid) FDN Work | Activity | 1CF1265W16A01.5 | (Washing & Drain system Skid) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1663 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Washing & Drain System | 1PF1265W42A03.5T | (Washing & Drain system Skid) Transportation | (Washing & Drain system Skid) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Washing & Drain System 1PF1265W42A03.5T (Washing & Drain system Skid) Transportation | Activity | 1PF1265W42A03.5T | (Washing & Drain system Skid) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1664 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Washing & Drain System | 1CF1265W42A04.5 | (Washing & Drain system Skid) Installation | (Washing & Drain system Skid) Installation | 2008-04-16 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Washing & Drain System 1CF1265W42A04.5 (Washing & Drain system Skid) Installation | Activity | 1CF1265W42A04.5 | (Washing & Drain system Skid) Installation | 2008-04-16 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1665 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Washing & Drain System | 1CF1265W58A05.5 | (Washing & Drain system Skid) Piping work | (Washing & Drain system Skid) Piping work | 2008-05-03 | 2008-06-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Washing & Drain System 1CF1265W58A05.5 (Washing & Drain system Skid) Piping work | Activity | 1CF1265W58A05.5 | (Washing & Drain system Skid) Piping work | 2008-05-03 00:00:00 | 2008-06-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1666 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Washing & Drain System | 1CF1265W74A07.5 | (Washing & Drain system Skid) Installation- Elec. | (Washing & Drain system Skid) Installation- Elec. | 2008-06-04 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Washing & Drain System 1CF1265W74A07.5 (Washing & Drain system Skid) Installation- Elec. | Activity | 1CF1265W74A07.5 | (Washing & Drain system Skid) Installation- Elec. | 2008-06-04 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1667 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Washing & Drain System | 1CF1265W90A08.5 | (Washing & Drain system Skid) Installation- I&C | (Washing & Drain system Skid) Installation- I&C | 2008-06-04 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Washing & Drain System 1CF1265W90A08.5 (Washing & Drain system Skid) Installation- I&C | Activity | 1CF1265W90A08.5 | (Washing & Drain system Skid) Installation- I&C | 2008-06-04 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1668 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Washing & Drain System | 1CF1265W62A06.5 | (Washing & Drain system Skid) Flushing | (Washing & Drain system Skid) Flushing | 2008-06-04 | 2008-06-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Washing & Drain System 1CF1265W62A06.5 (Washing & Drain system Skid) Flushing | Activity | 1CF1265W62A06.5 | (Washing & Drain system Skid) Flushing | 2008-06-04 00:00:00 | 2008-06-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1669 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Washing & Drain System | 1SF1265W62A09.5 | (Washing & Drain system Skid) Loop chek | (Washing & Drain system Skid) Loop chek | 2008-06-18 | 2008-06-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Washing & Drain System 1SF1265W62A09.5 (Washing & Drain system Skid) Loop chek | Activity | 1SF1265W62A09.5 | (Washing & Drain system Skid) Loop chek | 2008-06-18 00:00:00 | 2008-06-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1670 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Washing & Drain System | 1SF1265W62A10.5 | (Washing & Drain system Skid) Function Test | (Washing & Drain system Skid) Function Test | 2008-06-23 | 2008-06-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Washing & Drain System 1SF1265W62A10.5 (Washing & Drain system Skid) Function Test | Activity | 1SF1265W62A10.5 | (Washing & Drain system Skid) Function Test | 2008-06-23 00:00:00 | 2008-06-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1671 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Washing & Drain System | 1SF1265W62A11.5 | (Washing & Drain system Skid) Load(Running) Test | (Washing & Drain system Skid) Load(Running) Test | 2008-08-12 | 2008-08-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Washing & Drain System 1SF1265W62A11.5 (Washing & Drain system Skid) Load(Running) Test | Activity | 1SF1265W62A11.5 | (Washing & Drain system Skid) Load(Running) Test | 2008-08-12 00:00:00 | 2008-08-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1673 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1PF1265W42A02.6P | (Fuel oil injection System) P.O & Procurement | (Fuel oil injection System) P.O & Procurement | 2007-03-01 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1PF1265W42A02.6P (Fuel oil injection System) P.O & Procurement | Activity | 1PF1265W42A02.6P | (Fuel oil injection System) P.O & Procurement | 2007-03-01 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1674 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1PF1265W42A12.6P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1PF1265W42A12.6P (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | Activity | 1PF1265W42A12.6P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1675 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1PF1265W42A15.6P | (Water injection System) P.O & Procurement | (Water injection System) P.O & Procurement | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1PF1265W42A15.6P (Water injection System) P.O & Procurement | Activity | 1PF1265W42A15.6P | (Water injection System) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1676 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1CF1265W16A01.6 | (Fuel oil injection System) FDN Work | (Fuel oil injection System) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1CF1265W16A01.6 (Fuel oil injection System) FDN Work | Activity | 1CF1265W16A01.6 | (Fuel oil injection System) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1677 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1CF1265W16A11.6 | (Fuel oil injection Pump & actuator) FDN Work | (Fuel oil injection Pump & actuator) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1CF1265W16A11.6 (Fuel oil injection Pump & actuator) FDN Work | Activity | 1CF1265W16A11.6 | (Fuel oil injection Pump & actuator) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1678 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1CF1265W16A15.6 | (Water injection System) FDN Work | (Water injection System) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1CF1265W16A15.6 (Water injection System) FDN Work | Activity | 1CF1265W16A15.6 | (Water injection System) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1679 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1PF1265W42A13.6T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1PF1265W42A13.6T (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | Activity | 1PF1265W42A13.6T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1680 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1PF1265W42A16.6T | (Water injection System) Transportation | (Water injection System) Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1PF1265W42A16.6T (Water injection System) Transportation | Activity | 1PF1265W42A16.6T | (Water injection System) Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1681 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1PF1265W42A03.6T | (Fuel oil injection System) Transportation | (Fuel oil injection System) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1PF1265W42A03.6T (Fuel oil injection System) Transportation | Activity | 1PF1265W42A03.6T | (Fuel oil injection System) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1682 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1CF1265W42A14.6 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-03-18 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1CF1265W42A14.6 (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | Activity | 1CF1265W42A14.6 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-03-18 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1683 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1CF1265W42A17.6 | (Water injection System) Installation | (Water injection System) Installation | 2008-03-18 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1CF1265W42A17.6 (Water injection System) Installation | Activity | 1CF1265W42A17.6 | (Water injection System) Installation | 2008-03-18 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1684 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1CF1265W58A18.6 | (Water injection System) Piping work | (Water injection System) Piping work | 2008-04-02 | 2008-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1CF1265W58A18.6 (Water injection System) Piping work | Activity | 1CF1265W58A18.6 | (Water injection System) Piping work | 2008-04-02 00:00:00 | 2008-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1685 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1CF1265W42A04.6 | (Fuel oil injection System) Installation | (Fuel oil injection System) Installation | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1CF1265W42A04.6 (Fuel oil injection System) Installation | Activity | 1CF1265W42A04.6 | (Fuel oil injection System) Installation | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1686 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1CF1265W74A19.6 | (Water injection System) Installation- Elec. | (Water injection System) Installation- Elec. | 2008-04-17 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1CF1265W74A19.6 (Water injection System) Installation- Elec. | Activity | 1CF1265W74A19.6 | (Water injection System) Installation- Elec. | 2008-04-17 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1687 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1CF1265W90A20.6 | (Water injection System) Installation- I&C | (Water injection System) Installation- I&C | 2008-04-17 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1CF1265W90A20.6 (Water injection System) Installation- I&C | Activity | 1CF1265W90A20.6 | (Water injection System) Installation- I&C | 2008-04-17 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1688 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1SF1265W62A21.6 | (Water injection System) Loop chek | (Water injection System) Loop chek | 2008-05-01 | 2008-05-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1SF1265W62A21.6 (Water injection System) Loop chek | Activity | 1SF1265W62A21.6 | (Water injection System) Loop chek | 2008-05-01 00:00:00 | 2008-05-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1689 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1CF1265W58A05.6 | (Fuel oil injection System) Piping work | (Fuel oil injection System) Piping work | 2008-05-05 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1CF1265W58A05.6 (Fuel oil injection System) Piping work | Activity | 1CF1265W58A05.6 | (Fuel oil injection System) Piping work | 2008-05-05 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1690 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1SF1265W62A22.6 | (Water injection System) Function Test | (Water injection System) Function Test | 2008-05-06 | 2008-05-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1SF1265W62A22.6 (Water injection System) Function Test | Activity | 1SF1265W62A22.6 | (Water injection System) Function Test | 2008-05-06 00:00:00 | 2008-05-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1691 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1CF1265W74A06.6 | (Fuel oil injection System) Installation- Elec. | (Fuel oil injection System) Installation- Elec. | 2008-05-20 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1CF1265W74A06.6 (Fuel oil injection System) Installation- Elec. | Activity | 1CF1265W74A06.6 | (Fuel oil injection System) Installation- Elec. | 2008-05-20 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1692 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1CF1265W90A07.6 | (Fuel oil injection System) Installation- I&C | (Fuel oil injection System) Installation- I&C | 2008-05-20 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1CF1265W90A07.6 (Fuel oil injection System) Installation- I&C | Activity | 1CF1265W90A07.6 | (Fuel oil injection System) Installation- I&C | 2008-05-20 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1693 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1SF1265W62A08.6 | (Fuel oil injection System) Loop chek | (Fuel oil injection System) Loop chek | 2008-06-03 | 2008-06-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1SF1265W62A08.6 (Fuel oil injection System) Loop chek | Activity | 1SF1265W62A08.6 | (Fuel oil injection System) Loop chek | 2008-06-03 00:00:00 | 2008-06-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1694 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1SF1265W62A23.6 | (Water injection System) Load Test | (Water injection System) Load Test | 2008-08-12 | 2008-08-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1SF1265W62A23.6 (Water injection System) Load Test | Activity | 1SF1265W62A23.6 | (Water injection System) Load Test | 2008-08-12 00:00:00 | 2008-08-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1695 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1SF1265W62A09.6 | (Fuel oil injection System) Function Test | (Fuel oil injection System) Function Test | 2008-08-15 | 2008-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1SF1265W62A09.6 (Fuel oil injection System) Function Test | Activity | 1SF1265W62A09.6 | (Fuel oil injection System) Function Test | 2008-08-15 00:00:00 | 2008-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1696 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fuel Oil Injection System | 1SF1265W62A10.6 | (Fuel oil injection System) Flushing | (Fuel oil injection System) Flushing | 2008-08-30 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fuel Oil Injection System 1SF1265W62A10.6 (Fuel oil injection System) Flushing | Activity | 1SF1265W62A10.6 | (Fuel oil injection System) Flushing | 2008-08-30 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1698 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Vibration Monitoring System (VMS) | 1EF1260W86A01.1 | (VMS) MPS Issue for GT | (VMS) MPS Issue for GT |  | 2007-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Vibration Monitoring System (VMS) 1EF1260W86A01.1 (VMS) MPS Issue for GT | Activity | 1EF1260W86A01.1 | (VMS) MPS Issue for GT |  | 2007-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1699 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Vibration Monitoring System (VMS) | 1PF1260W86A02.1P | (VMS) P.O & Procurement for GT | (VMS) P.O & Procurement for GT | 2007-08-31 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Vibration Monitoring System (VMS) 1PF1260W86A02.1P (VMS) P.O & Procurement for GT | Activity | 1PF1260W86A02.1P | (VMS) P.O & Procurement for GT | 2007-08-31 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1700 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Vibration Monitoring System (VMS) | 1PF1260W86A03.1T | (VMS) Transportation for GT | (VMS) Transportation for GT | 2008-05-02 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Vibration Monitoring System (VMS) 1PF1260W86A03.1T (VMS) Transportation for GT | Activity | 1PF1260W86A03.1T | (VMS) Transportation for GT | 2008-05-02 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1701 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Vibration Monitoring System (VMS) | 1CF1260W86A04.1 | (VMS) Installation for GT | (VMS) Installation for GT | 2008-08-16 | 2008-08-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Vibration Monitoring System (VMS) 1CF1260W86A04.1 (VMS) Installation for GT | Activity | 1CF1260W86A04.1 | (VMS) Installation for GT | 2008-08-16 00:00:00 | 2008-08-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1702 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Vibration Monitoring System (VMS) | 1SF1260W62A05.1 | (VMS) Function Test for GT | (VMS) Function Test for GT | 2008-08-24 | 2008-08-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Vibration Monitoring System (VMS) 1SF1260W62A05.1 (VMS) Function Test for GT | Activity | 1SF1260W62A05.1 | (VMS) Function Test for GT | 2008-08-24 00:00:00 | 2008-08-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1704 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1EF1225W00A01.1 | (CCWS) CCW H/EX key data | (CCWS) CCW H/EX key data | 2007-03-01 | 2007-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1EF1225W00A01.1 (CCWS) CCW H/EX key data | Activity | 1EF1225W00A01.1 | (CCWS) CCW H/EX key data | 2007-03-01 00:00:00 | 2007-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1705 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1EF1225W00A02.1 | (CCWP) Key data for GT | (CCWP) Key data for GT | 2007-03-01 | 2007-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1EF1225W00A02.1 (CCWP) Key data for GT | Activity | 1EF1225W00A02.1 | (CCWP) Key data for GT | 2007-03-01 00:00:00 | 2007-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1706 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1EF1225W42A11.1 | (EXP Head Tank) MPS Issue | (EXP Head Tank) MPS Issue |  | 2007-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1EF1225W42A11.1 (EXP Head Tank) MPS Issue | Activity | 1EF1225W42A11.1 | (EXP Head Tank) MPS Issue |  | 2007-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1707 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1EF1225W42A05.1 | (CCWP) MPS Issue for GT | (CCWP) MPS Issue for GT |  | 2007-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1EF1225W42A05.1 (CCWP) MPS Issue for GT | Activity | 1EF1225W42A05.1 | (CCWP) MPS Issue for GT |  | 2007-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1708 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1EF1225W42A17.1 | (CCW H/EX) MPS Issue_Fin fan cooler | (CCW H/EX) MPS Issue_Fin fan cooler |  | 2007-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1EF1225W42A17.1 (CCW H/EX) MPS Issue_Fin fan cooler | Activity | 1EF1225W42A17.1 | (CCW H/EX) MPS Issue_Fin fan cooler |  | 2007-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1709 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1PF1225W42A12.1P | (EXP Head Tank) P.O & Procurement | (EXP Head Tank) P.O & Procurement | 2007-07-03 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1PF1225W42A12.1P (EXP Head Tank) P.O & Procurement | Activity | 1PF1225W42A12.1P | (EXP Head Tank) P.O & Procurement | 2007-07-03 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1710 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1EF1225W16A09.1 | (EXP Head Tank) FDN Design | (EXP Head Tank) FDN Design | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1EF1225W16A09.1 (EXP Head Tank) FDN Design | Activity | 1EF1225W16A09.1 | (EXP Head Tank) FDN Design | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1711 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1PF1225W42A06.1P | (CCWP) P.O & Procurement for GT | (CCWP) P.O & Procurement for GT | 2007-07-03 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1PF1225W42A06.1P (CCWP) P.O & Procurement for GT | Activity | 1PF1225W42A06.1P | (CCWP) P.O & Procurement for GT | 2007-07-03 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1712 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1EF1225W16A03.1 | (CCWP) FDN Design | (CCWP) FDN Design | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1EF1225W16A03.1 (CCWP) FDN Design | Activity | 1EF1225W16A03.1 | (CCWP) FDN Design | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1713 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1PF1225W42A18.1P | (CCW H/EX) P.O & Procurement_Fin fan cooler | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1PF1225W42A18.1P (CCW H/EX) P.O & Procurement_Fin fan cooler | Activity | 1PF1225W42A18.1P | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1714 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1EF1225W16A15.1 | (CCW H/EX) FDN Design_Fin fan cooler | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1EF1225W16A15.1 (CCW H/EX) FDN Design_Fin fan cooler | Activity | 1EF1225W16A15.1 | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1715 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1CF1225W16A10.1 | (EXP Head Tank) FDN Work | (EXP Head Tank) FDN Work | 2007-11-30 | 2007-12-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1CF1225W16A10.1 (EXP Head Tank) FDN Work | Activity | 1CF1225W16A10.1 | (EXP Head Tank) FDN Work | 2007-11-30 00:00:00 | 2007-12-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1716 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1CF1225W16A04.1 | (CCWP) FDN Work | (CCWP) FDN Work | 2007-11-30 | 2008-01-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1CF1225W16A04.1 (CCWP) FDN Work | Activity | 1CF1225W16A04.1 | (CCWP) FDN Work | 2007-11-30 00:00:00 | 2008-01-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1717 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1CF1225W16A16.1 | (CCW H/EX) FDN Work_Fin fan cooler | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 | 2008-02-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1CF1225W16A16.1 (CCW H/EX) FDN Work_Fin fan cooler | Activity | 1CF1225W16A16.1 | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 00:00:00 | 2008-02-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1718 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1PF1225W42A13.1T | (EXP Head Tank) Transportation | (EXP Head Tank) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1PF1225W42A13.1T (EXP Head Tank) Transportation | Activity | 1PF1225W42A13.1T | (EXP Head Tank) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1719 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1PF1225W42A07.1T | (CCWP) Transportation for GT | (CCWP) Transportation for GT | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1PF1225W42A07.1T (CCWP) Transportation for GT | Activity | 1PF1225W42A07.1T | (CCWP) Transportation for GT | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1720 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1PF1225W42A19.1T | (CCW H/EX) Transportation_Fin fan cooler | (CCW H/EX) Transportation_Fin fan cooler | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1PF1225W42A19.1T (CCW H/EX) Transportation_Fin fan cooler | Activity | 1PF1225W42A19.1T | (CCW H/EX) Transportation_Fin fan cooler | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1721 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1CF1225W58A21.1 | (CCWS) Piping Work | (CCWS) Piping Work | 2008-05-09 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1CF1225W58A21.1 (CCWS) Piping Work | Activity | 1CF1225W58A21.1 | (CCWS) Piping Work | 2008-05-09 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1722 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1CF1225W42A14.1 | (EXP Head Tank) Installation | (EXP Head Tank) Installation | 2008-05-16 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1CF1225W42A14.1 (EXP Head Tank) Installation | Activity | 1CF1225W42A14.1 | (EXP Head Tank) Installation | 2008-05-16 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1723 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1CF1225W42A08.1 | (CCWP) Installation | (CCWP) Installation | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1CF1225W42A08.1 (CCWP) Installation | Activity | 1CF1225W42A08.1 | (CCWP) Installation | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1724 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1CF1225W42A20.1 | (CCW H/EX) Installation_Fin fan cooler | (CCW H/EX) Installation_Fin fan cooler | 2008-05-16 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1CF1225W42A20.1 (CCW H/EX) Installation_Fin fan cooler | Activity | 1CF1225W42A20.1 | (CCW H/EX) Installation_Fin fan cooler | 2008-05-16 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1725 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1CF1225W74A22.1 | (CCWS) Installation & Test - Elec. | (CCWS) Installation & Test - Elec. | 2008-05-30 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1CF1225W74A22.1 (CCWS) Installation & Test - Elec. | Activity | 1CF1225W74A22.1 | (CCWS) Installation & Test - Elec. | 2008-05-30 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1726 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1CF1225W90A23.1 | (CCWS) Installation & Test - I&C | (CCWS) Installation & Test - I&C | 2008-05-30 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1CF1225W90A23.1 (CCWS) Installation & Test - I&C | Activity | 1CF1225W90A23.1 | (CCWS) Installation & Test - I&C | 2008-05-30 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1727 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1SF1225W62A24.1 | (CCWS) Loop chek | (CCWS) Loop chek | 2008-07-01 | 2008-07-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1SF1225W62A24.1 (CCWS) Loop chek | Activity | 1SF1225W62A24.1 | (CCWS) Loop chek | 2008-07-01 00:00:00 | 2008-07-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1728 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1SF1225W62A25.1 | (CCWS) Function Test | (CCWS) Function Test | 2008-07-11 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1SF1225W62A25.1 (CCWS) Function Test | Activity | 1SF1225W62A25.1 | (CCWS) Function Test | 2008-07-11 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1729 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Closed Cooling Water System | 1SF1225W62A26.1 | (CCWS) Flushing | (CCWS) Flushing | 2008-08-08 | 2008-08-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Closed Cooling Water System 1SF1225W62A26.1 (CCWS) Flushing | Activity | 1SF1225W62A26.1 | (CCWS) Flushing | 2008-08-08 00:00:00 | 2008-08-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1731 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fire fighting System | 1PF1265W38A01.7P | (F/F GTG#12) P.O & Procurement_CO2 FF System | (F/F GTG#12) P.O & Procurement_CO2 FF System | 2007-03-01 | 2008-03-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fire fighting System 1PF1265W38A01.7P (F/F GTG#12) P.O & Procurement_CO2 FF System | Activity | 1PF1265W38A01.7P | (F/F GTG#12) P.O & Procurement_CO2 FF System | 2007-03-01 00:00:00 | 2008-03-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1732 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fire fighting System | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | 2007-03-01 | 2008-03-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fire fighting System 1PF1265W38A04.7P (F/F GTG#12) P.O & Procurement_Clean Agent FF System | Activity | 1PF1265W38A04.7P | (F/F GTG#12) P.O & Procurement_Clean Agent FF System | 2007-03-01 00:00:00 | 2008-03-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1733 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fire fighting System | 1PF1265W38A02.7T | (F/F GTG#12) Transportation_CO2 FF System | (F/F GTG#12) Transportation_CO2 FF System | 2008-03-15 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fire fighting System 1PF1265W38A02.7T (F/F GTG#12) Transportation_CO2 FF System | Activity | 1PF1265W38A02.7T | (F/F GTG#12) Transportation_CO2 FF System | 2008-03-15 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1734 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fire fighting System | 1PF1265W38A05.7T | (F/F GTG#12) Transportation_Clean Agent FF System | (F/F GTG#12) Transportation_Clean Agent FF System | 2008-03-15 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fire fighting System 1PF1265W38A05.7T (F/F GTG#12) Transportation_Clean Agent FF System | Activity | 1PF1265W38A05.7T | (F/F GTG#12) Transportation_Clean Agent FF System | 2008-03-15 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1735 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fire fighting System | 1CF1265W38A03.7 | (F/F GTG#12) Installation_CO2 FF System | (F/F GTG#12) Installation_CO2 FF System | 2008-04-30 | 2008-05-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fire fighting System 1CF1265W38A03.7 (F/F GTG#12) Installation_CO2 FF System | Activity | 1CF1265W38A03.7 | (F/F GTG#12) Installation_CO2 FF System | 2008-04-30 00:00:00 | 2008-05-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1736 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fire fighting System | 1CF1265W38A06.7 | (F/F GTG#12) Installation_Clean Agent FF System | (F/F GTG#12) Installation_Clean Agent FF System | 2008-04-30 | 2008-05-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fire fighting System 1CF1265W38A06.7 (F/F GTG#12) Installation_Clean Agent FF System | Activity | 1CF1265W38A06.7 | (F/F GTG#12) Installation_Clean Agent FF System | 2008-04-30 00:00:00 | 2008-05-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1737 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fire fighting System | 1CF1265W38A07.7 | (F/F GTG#12) Piping work | (F/F GTG#12) Piping work | 2008-05-15 | 2008-06-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fire fighting System 1CF1265W38A07.7 (F/F GTG#12) Piping work | Activity | 1CF1265W38A07.7 | (F/F GTG#12) Piping work | 2008-05-15 00:00:00 | 2008-06-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1738 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fire fighting System | 1SF1265W62A08.7 | (F/F GTG#12) Loop chek | (F/F GTG#12) Loop chek | 2008-06-08 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fire fighting System 1SF1265W62A08.7 (F/F GTG#12) Loop chek | Activity | 1SF1265W62A08.7 | (F/F GTG#12) Loop chek | 2008-06-08 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1739 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fire fighting System | 1SF1265W62A09.7 | (F/F GTG#12) Function Test(incl. Alarm Test) | (F/F GTG#12) Function Test(incl. Alarm Test) | 2008-06-15 | 2008-06-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fire fighting System 1SF1265W62A09.7 (F/F GTG#12) Function Test(incl. Alarm Test) | Activity | 1SF1265W62A09.7 | (F/F GTG#12) Function Test(incl. Alarm Test) | 2008-06-15 00:00:00 | 2008-06-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1740 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Fire fighting System | 1SF1265W62A10.7 | (F/F GTG#12) CO2 Discharge Test | (F/F GTG#12) CO2 Discharge Test | 2008-06-25 | 2008-07-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Fire fighting System 1SF1265W62A10.7 (F/F GTG#12) CO2 Discharge Test | Activity | 1SF1265W62A10.7 | (F/F GTG#12) CO2 Discharge Test | 2008-06-25 00:00:00 | 2008-07-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1742 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1PF1265W42A02.8P | (Purge Air System) P.O & Procurement | (Purge Air System) P.O & Procurement | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1PF1265W42A02.8P (Purge Air System) P.O & Procurement | Activity | 1PF1265W42A02.8P | (Purge Air System) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1743 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1PF1265W42A12.8P | (Control Oil) P.O & Procurement | (Control Oil) P.O & Procurement | 2007-03-01 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1PF1265W42A12.8P (Control Oil) P.O & Procurement | Activity | 1PF1265W42A12.8P | (Control Oil) P.O & Procurement | 2007-03-01 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1744 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1CF1265W16A01.8 | (Purge Air System) FDN Work | (Purge Air System) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1CF1265W16A01.8 (Purge Air System) FDN Work | Activity | 1CF1265W16A01.8 | (Purge Air System) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1745 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1CF1265W16A11.8 | (Control Oil) FDN Work | (Control Oil) FDN Work | 2007-10-01 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1CF1265W16A11.8 (Control Oil) FDN Work | Activity | 1CF1265W16A11.8 | (Control Oil) FDN Work | 2007-10-01 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1746 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1PF1265W42A03.8T | (Purge Air System) Transportation | (Purge Air System) Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1PF1265W42A03.8T (Purge Air System) Transportation | Activity | 1PF1265W42A03.8T | (Purge Air System) Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1747 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1PF1265W42A13.8T | (Control Oil)Transportation | (Control Oil)Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1PF1265W42A13.8T (Control Oil)Transportation | Activity | 1PF1265W42A13.8T | (Control Oil)Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1748 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1CF1265W42A04.8 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-03-18 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1CF1265W42A04.8 (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | Activity | 1CF1265W42A04.8 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-03-18 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1749 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1CF1265W42A14.8 | (Control Oil) Installation | (Control Oil) Installation | 2008-03-18 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1CF1265W42A14.8 (Control Oil) Installation | Activity | 1CF1265W42A14.8 | (Control Oil) Installation | 2008-03-18 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1750 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1CF1265W16A05.8 | (Purge Air System) Piping work | (Purge Air System) Piping work | 2008-04-02 | 2008-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1CF1265W16A05.8 (Purge Air System) Piping work | Activity | 1CF1265W16A05.8 | (Purge Air System) Piping work | 2008-04-02 00:00:00 | 2008-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1751 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1CF1265W16A15.8 | (Control Oil) Piping work | (Control Oil) Piping work | 2008-04-02 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1CF1265W16A15.8 (Control Oil) Piping work | Activity | 1CF1265W16A15.8 | (Control Oil) Piping work | 2008-04-02 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1752 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1CF1265W74A06.8 | (Purge Air System) Installation- Elec. | (Purge Air System) Installation- Elec. | 2008-04-17 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1CF1265W74A06.8 (Purge Air System) Installation- Elec. | Activity | 1CF1265W74A06.8 | (Purge Air System) Installation- Elec. | 2008-04-17 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1753 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1CF1265W90A07.8 | (Purge Air System) Installation- I&C | (Purge Air System) Installation- I&C | 2008-04-17 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1CF1265W90A07.8 (Purge Air System) Installation- I&C | Activity | 1CF1265W90A07.8 | (Purge Air System) Installation- I&C | 2008-04-17 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1754 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1SF1265W62A08.8 | (Purge Air System) Loop chek | (Purge Air System) Loop chek | 2008-05-01 | 2008-05-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1SF1265W62A08.8 (Purge Air System) Loop chek | Activity | 1SF1265W62A08.8 | (Purge Air System) Loop chek | 2008-05-01 00:00:00 | 2008-05-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1755 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1CF1265W74A16.8 | (Control Oil) Installation- Elec. | (Control Oil) Installation- Elec. | 2008-05-03 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1CF1265W74A16.8 (Control Oil) Installation- Elec. | Activity | 1CF1265W74A16.8 | (Control Oil) Installation- Elec. | 2008-05-03 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1756 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1CF1265W90A17.8 | (Control Oil) Installation- I&C | (Control Oil) Installation- I&C | 2008-05-03 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1CF1265W90A17.8 (Control Oil) Installation- I&C | Activity | 1CF1265W90A17.8 | (Control Oil) Installation- I&C | 2008-05-03 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1757 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1SF1265W62A09.8 | (Purge Air System) Function Test | (Purge Air System) Function Test | 2008-05-04 | 2008-05-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1SF1265W62A09.8 (Purge Air System) Function Test | Activity | 1SF1265W62A09.8 | (Purge Air System) Function Test | 2008-05-04 00:00:00 | 2008-05-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1758 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1SF1265W62A10.8 | (Purge Air System) Load Test | (Purge Air System) Load Test | 2008-05-07 | 2008-05-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1SF1265W62A10.8 (Purge Air System) Load Test | Activity | 1SF1265W62A10.8 | (Purge Air System) Load Test | 2008-05-07 00:00:00 | 2008-05-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1759 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1SF1265W62A18.8 | (Control Oil) Loop chek | (Control Oil) Loop chek | 2008-05-17 | 2008-05-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1SF1265W62A18.8 (Control Oil) Loop chek | Activity | 1SF1265W62A18.8 | (Control Oil) Loop chek | 2008-05-17 00:00:00 | 2008-05-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1760 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1SF1265W62A19.8 | (Control Oil) Function Test | (Control Oil) Function Test | 2008-05-22 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1SF1265W62A19.8 (Control Oil) Function Test | Activity | 1SF1265W62A19.8 | (Control Oil) Function Test | 2008-05-22 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1761 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Auxiliary System | 1SF1265W62A20.8 | (Control Oil) Flushing | (Control Oil) Flushing | 2008-06-01 | 2008-06-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Auxiliary System 1SF1265W62A20.8 (Control Oil) Flushing | Activity | 1SF1265W62A20.8 | (Control Oil) Flushing | 2008-06-01 00:00:00 | 2008-06-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1763 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9011W62A01.1 | (GTG #12) Fuel Gas System Final Function Test | (GTG #12) Fuel Gas System Final Function Test | 2008-09-29 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9011W62A01.1 (GTG #12) Fuel Gas System Final Function Test | Activity | 1SF9011W62A01.1 | (GTG #12) Fuel Gas System Final Function Test | 2008-09-29 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1764 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9011W62A02.1 | (GTG #12) Turning Gear Operation | (GTG #12) Turning Gear Operation | 2008-10-02 | 2008-10-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9011W62A02.1 (GTG #12) Turning Gear Operation | Activity | 1SF9011W62A02.1 | (GTG #12) Turning Gear Operation | 2008-10-02 00:00:00 | 2008-10-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1765 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9011W62A03.1 | (GTG #12) Initial Firing with FSNL | (GTG #12) Initial Firing with FSNL | 2008-10-04 | 2008-10-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9011W62A03.1 (GTG #12) Initial Firing with FSNL | Activity | 1SF9011W62A03.1 | (GTG #12) Initial Firing with FSNL | 2008-10-04 00:00:00 | 2008-10-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1766 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9012W62A04.1 | (GTG #12) TBN & GEN Protection Test | (GTG #12) TBN & GEN Protection Test | 2008-10-05 | 2008-10-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9012W62A04.1 (GTG #12) TBN & GEN Protection Test | Activity | 1SF9012W62A04.1 | (GTG #12) TBN & GEN Protection Test | 2008-10-05 00:00:00 | 2008-10-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1767 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9012W62A05.1 | (GTG #12) 1st Synchronization | (GTG #12) 1st Synchronization | 2008-10-13 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9012W62A05.1 (GTG #12) 1st Synchronization | Activity | 1SF9012W62A05.1 | (GTG #12) 1st Synchronization | 2008-10-13 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1768 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9012W62A06.1 | (GTG #12) Optimization with Fuel Gas | (GTG #12) Optimization with Fuel Gas | 2008-10-15 | 2008-10-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9012W62A06.1 (GTG #12) Optimization with Fuel Gas | Activity | 1SF9012W62A06.1 | (GTG #12) Optimization with Fuel Gas | 2008-10-15 00:00:00 | 2008-10-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1769 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9012W62A09.1 | (GTG #12) Black start Test with GT | (GTG #12) Black start Test with GT | 2008-10-21 | 2008-10-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9012W62A09.1 (GTG #12) Black start Test with GT | Activity | 1SF9012W62A09.1 | (GTG #12) Black start Test with GT | 2008-10-21 00:00:00 | 2008-10-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1770 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9012W62A07.1 | (GTG #12) Fuel Oil System Final Function Test | (GTG #12) Fuel Oil System Final Function Test | 2008-10-21 | 2008-10-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9012W62A07.1 (GTG #12) Fuel Oil System Final Function Test | Activity | 1SF9012W62A07.1 | (GTG #12) Fuel Oil System Final Function Test | 2008-10-21 00:00:00 | 2008-10-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1771 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9012W62A08.1 | (GTG #12) Optimization with Fuel Oil | (GTG #12) Optimization with Fuel Oil | 2008-10-21 | 2008-10-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9012W62A08.1 (GTG #12) Optimization with Fuel Oil | Activity | 1SF9012W62A08.1 | (GTG #12) Optimization with Fuel Oil | 2008-10-21 00:00:00 | 2008-10-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1772 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9012W62A10.1 | (GTG #12) Trial Run Test | (GTG #12) Trial Run Test | 2008-10-22 | 2008-10-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9012W62A10.1 (GTG #12) Trial Run Test | Activity | 1SF9012W62A10.1 | (GTG #12) Trial Run Test | 2008-10-22 00:00:00 | 2008-10-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1773 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9013W62A11.1 | (GTG #12) Reliability Test | (GTG #12) Reliability Test | 2008-10-23 | 2008-11-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9013W62A11.1 (GTG #12) Reliability Test | Activity | 1SF9013W62A11.1 | (GTG #12) Reliability Test | 2008-10-23 00:00:00 | 2008-11-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1774 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9013W62A12.1 | (GTG #12) Performance Test (Fuel Gas & Fuel Oil) | (GTG #12) Performance Test (Fuel Gas & Fuel Oil) | 2008-11-07 | 2008-11-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9013W62A12.1 (GTG #12) Performance Test (Fuel Gas & Fuel Oil) | Activity | 1SF9013W62A12.1 | (GTG #12) Performance Test (Fuel Gas & Fuel Oil) | 2008-11-07 00:00:00 | 2008-11-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1775 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Gas Turbine & Generator #11 & #12 > GTG #12 > GTG #12 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Gas Turbine & Generator #11 & #12 | GTG #12 | GTG #12 Commissioning | 1SF9012W62A13.1 | (GTG #12) Fuel Change-Over Test | (GTG #12) Fuel Change-Over Test | 2008-11-17 | 2008-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Gas Turbine & Generator #11 & #12 GTG #12 GTG #12 Commissioning 1SF9012W62A13.1 (GTG #12) Fuel Change-Over Test | Activity | 1SF9012W62A13.1 | (GTG #12) Fuel Change-Over Test | 2008-11-17 00:00:00 | 2008-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1778 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG Common |  | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | (HRSG #11/#12) HRSG Process, GA Data | 2007-03-01 | 2007-03-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG Common 1EF1600W00A02 (HRSG #11/#12) HRSG Process, GA Data | Activity | 1EF1600W00A02 | (HRSG #11/#12) HRSG Process, GA Data | 2007-03-01 00:00:00 | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1779 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG Common |  | 1EF1600W00A03 | (HRSG #11/#12) Instrument, Service Air Data | (HRSG #11/#12) Instrument, Service Air Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG Common 1EF1600W00A03 (HRSG #11/#12) Instrument, Service Air Data | Activity | 1EF1600W00A03 | (HRSG #11/#12) Instrument, Service Air Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1780 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG Common |  | 1EF1600W00A04 | (HRSG #11/#12) Utility Consumption Data | (HRSG #11/#12) Utility Consumption Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG Common 1EF1600W00A04 (HRSG #11/#12) Utility Consumption Data | Activity | 1EF1600W00A04 | (HRSG #11/#12) Utility Consumption Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1781 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG Common |  | 1EF1600W00A05 | (HRSG #11/#12) Emergency Load Data | (HRSG #11/#12) Emergency Load Data | 2007-03-01 | 2007-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG Common 1EF1600W00A05 (HRSG #11/#12) Emergency Load Data | Activity | 1EF1600W00A05 | (HRSG #11/#12) Emergency Load Data | 2007-03-01 00:00:00 | 2007-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1782 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG Common |  | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | (HRSG #11/#12) P&ID & System Design | 2007-03-19 | 2008-03-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG Common 1EF1600W00A01.0 (HRSG #11/#12) P&ID & System Design | Activity | 1EF1600W00A01.0 | (HRSG #11/#12) P&ID & System Design | 2007-03-19 00:00:00 | 2008-03-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1785 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1EF1600W74A05 | (HRSG #11 LEB) MPS Issue - Elec | (HRSG #11 LEB) MPS Issue - Elec |  | 2007-06-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1EF1600W74A05 (HRSG #11 LEB) MPS Issue - Elec | Activity | 1EF1600W74A05 | (HRSG #11 LEB) MPS Issue - Elec |  | 2007-06-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1786 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1EF1600W90A09 | (HRSG #11 LEB) MPS Issue - I&C | (HRSG #11 LEB) MPS Issue - I&C |  | 2007-06-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1EF1600W90A09 (HRSG #11 LEB) MPS Issue - I&C | Activity | 1EF1600W90A09 | (HRSG #11 LEB) MPS Issue - I&C |  | 2007-06-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1787 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1EF1600W00A01 | (HRSG #11 LEB) GA & Load Data to Civil Design | (HRSG #11 LEB) GA & Load Data to Civil Design | 2007-06-20 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1EF1600W00A01 (HRSG #11 LEB) GA & Load Data to Civil Design | Activity | 1EF1600W00A01 | (HRSG #11 LEB) GA & Load Data to Civil Design | 2007-06-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1788 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1EF1600W32A02 | (HRSG #11 LEB) Building Design | (HRSG #11 LEB) Building Design | 2007-06-20 | 2007-11-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1EF1600W32A02 (HRSG #11 LEB) Building Design | Activity | 1EF1600W32A02 | (HRSG #11 LEB) Building Design | 2007-06-20 00:00:00 | 2007-11-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1789 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1PF1600W74A06P | (HRSG #11 LEB) P.O & Procurement - Elec | (HRSG #11 LEB) P.O & Procurement - Elec | 2007-09-15 | 2008-07-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1PF1600W74A06P (HRSG #11 LEB) P.O & Procurement - Elec | Activity | 1PF1600W74A06P | (HRSG #11 LEB) P.O & Procurement - Elec | 2007-09-15 00:00:00 | 2008-07-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1790 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | (HRSG #11 LEB) P.O & Procurement - I&C | 2007-09-15 | 2008-07-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1PF1600W90A10P (HRSG #11 LEB) P.O & Procurement - I&C | Activity | 1PF1600W90A10P | (HRSG #11 LEB) P.O & Procurement - I&C | 2007-09-15 00:00:00 | 2008-07-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1791 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1CF1600W16A03 | (HRSG #11 LEB) FDN Work | (HRSG #11 LEB) FDN Work | 2008-01-01 | 2008-02-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1CF1600W16A03 (HRSG #11 LEB) FDN Work | Activity | 1CF1600W16A03 | (HRSG #11 LEB) FDN Work | 2008-01-01 00:00:00 | 2008-02-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1792 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1CF1600W32A04 | (HRSG #11 LEB) Structure Work | (HRSG #11 LEB) Structure Work | 2008-02-28 | 2008-05-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1CF1600W32A04 (HRSG #11 LEB) Structure Work | Activity | 1CF1600W32A04 | (HRSG #11 LEB) Structure Work | 2008-02-28 00:00:00 | 2008-05-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1793 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1PF1600W74A07T | (HRSG #11 LEB) Transportataion - Elec | (HRSG #11 LEB) Transportataion - Elec | 2008-07-11 | 2008-08-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1PF1600W74A07T (HRSG #11 LEB) Transportataion - Elec | Activity | 1PF1600W74A07T | (HRSG #11 LEB) Transportataion - Elec | 2008-07-11 00:00:00 | 2008-08-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1794 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1PF1600W90A11T | (HRSG #11 LEB) Transportataion - I&C | (HRSG #11 LEB) Transportataion - I&C | 2008-07-11 | 2008-08-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1PF1600W90A11T (HRSG #11 LEB) Transportataion - I&C | Activity | 1PF1600W90A11T | (HRSG #11 LEB) Transportataion - I&C | 2008-07-11 00:00:00 | 2008-08-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1795 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1CF1600W36A14 | (HRSG #11 LEB) Installation & Test - HVAC | (HRSG #11 LEB) Installation & Test - HVAC | 2008-07-31 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1CF1600W36A14 (HRSG #11 LEB) Installation & Test - HVAC | Activity | 1CF1600W36A14 | (HRSG #11 LEB) Installation & Test - HVAC | 2008-07-31 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1796 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1CF1600W74A08 | (HRSG #11 LEB) Installation & Test - Elec | (HRSG #11 LEB) Installation & Test - Elec | 2008-10-20 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1CF1600W74A08 (HRSG #11 LEB) Installation & Test - Elec | Activity | 1CF1600W74A08 | (HRSG #11 LEB) Installation & Test - Elec | 2008-10-20 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1797 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1CF1600W90A12 | (HRSG #11 LEB) Installation & Test - I&C | (HRSG #11 LEB) Installation & Test - I&C | 2008-10-20 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1CF1600W90A12 (HRSG #11 LEB) Installation & Test - I&C | Activity | 1CF1600W90A12 | (HRSG #11 LEB) Installation & Test - I&C | 2008-10-20 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1798 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | HRSG LEB | 1CF1600W38A13 | (HRSG #11 LEB) Installation & Test - Fire Fighting Sys. | (HRSG #11 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 HRSG LEB 1CF1600W38A13 (HRSG #11 LEB) Installation & Test - Fire Fighting Sys. | Activity | 1CF1600W38A13 | (HRSG #11 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1800 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Steel Structure & Casing | 1EF1610W20A01 | (HRSG #11 S/Structure & Casing) Design | (HRSG #11 S/Structure & Casing) Design | 2007-04-18 | 2007-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Steel Structure & Casing 1EF1610W20A01 (HRSG #11 S/Structure & Casing) Design | Activity | 1EF1610W20A01 | (HRSG #11 S/Structure & Casing) Design | 2007-04-18 00:00:00 | 2007-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1801 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Steel Structure & Casing | 1EF1610W20A02 | (HRSG #11 S/Structure & Casing) MPS Issue | (HRSG #11 S/Structure & Casing) MPS Issue |  | 2007-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Steel Structure & Casing 1EF1610W20A02 (HRSG #11 S/Structure & Casing) MPS Issue | Activity | 1EF1610W20A02 | (HRSG #11 S/Structure & Casing) MPS Issue |  | 2007-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1802 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Steel Structure & Casing | 1PF1610W20A03P | (HRSG #11 S/Structure & Casing) P.O & Procurement | (HRSG #11 S/Structure & Casing) P.O & Procurement | 2007-06-14 | 2008-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Steel Structure & Casing 1PF1610W20A03P (HRSG #11 S/Structure & Casing) P.O & Procurement | Activity | 1PF1610W20A03P | (HRSG #11 S/Structure & Casing) P.O & Procurement | 2007-06-14 00:00:00 | 2008-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1803 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Steel Structure & Casing | 1PF1610W20A04T | (HRSG #11 S/Structure & Casing) Transportation | (HRSG #11 S/Structure & Casing) Transportation | 2008-01-02 | 2008-02-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Steel Structure & Casing 1PF1610W20A04T (HRSG #11 S/Structure & Casing) Transportation | Activity | 1PF1610W20A04T | (HRSG #11 S/Structure & Casing) Transportation | 2008-01-02 00:00:00 | 2008-02-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1804 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Steel Structure & Casing | 1CF1610W20A05 | (HRSG #11 S/Structure & Casing) S/Structure Installation | (HRSG #11 S/Structure & Casing) S/Structure Installation | 2008-03-17 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Steel Structure & Casing 1CF1610W20A05 (HRSG #11 S/Structure & Casing) S/Structure Installation | Activity | 1CF1610W20A05 | (HRSG #11 S/Structure & Casing) S/Structure Installation | 2008-03-17 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1805 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Steel Structure & Casing | 1CF1610W20A06 | (HRSG #11 S/Structure & Casing) Casing Installation | (HRSG #11 S/Structure & Casing) Casing Installation | 2008-05-17 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Steel Structure & Casing 1CF1610W20A06 (HRSG #11 S/Structure & Casing) Casing Installation | Activity | 1CF1610W20A06 | (HRSG #11 S/Structure & Casing) Casing Installation | 2008-05-17 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1807 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1EF1615W64A04 | (HRSG #11 Duct) Design | (HRSG #11 Duct) Design | 2007-04-17 | 2007-10-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1EF1615W64A04 (HRSG #11 Duct) Design | Activity | 1EF1615W64A04 | (HRSG #11 Duct) Design | 2007-04-17 00:00:00 | 2007-10-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1808 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1EF1615W64A13 | (HRSG #11 EXP Joint & Bellows) MPS Issue | (HRSG #11 EXP Joint & Bellows) MPS Issue |  | 2007-04-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1EF1615W64A13 (HRSG #11 EXP Joint & Bellows) MPS Issue | Activity | 1EF1615W64A13 | (HRSG #11 EXP Joint & Bellows) MPS Issue |  | 2007-04-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1809 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1EF1615W64A09 | (HRSG #11 Damper) MPS Issue | (HRSG #11 Damper) MPS Issue |  | 2007-04-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1EF1615W64A09 (HRSG #11 Damper) MPS Issue | Activity | 1EF1615W64A09 | (HRSG #11 Damper) MPS Issue |  | 2007-04-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1810 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1EF1615W00A01 | (HRSG #11 Duct) GA & Load Data to Civil Design | (HRSG #11 Duct) GA & Load Data to Civil Design | 2007-04-30 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1EF1615W00A01 (HRSG #11 Duct) GA & Load Data to Civil Design | Activity | 1EF1615W00A01 | (HRSG #11 Duct) GA & Load Data to Civil Design | 2007-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1811 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1EF1615W64A05 | (HRSG #11 Duct) MPS Issue | (HRSG #11 Duct) MPS Issue |  | 2007-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1EF1615W64A05 (HRSG #11 Duct) MPS Issue | Activity | 1EF1615W64A05 | (HRSG #11 Duct) MPS Issue |  | 2007-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1812 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1PF1615W64A14P | (HRSG #11 EXP Joint & Bellows) P.O & Procurement | (HRSG #11 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1PF1615W64A14P (HRSG #11 EXP Joint & Bellows) P.O & Procurement | Activity | 1PF1615W64A14P | (HRSG #11 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1813 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1PF1615W64A10P | (HRSG #11 Damper) P.O & Procurement | (HRSG #11 Damper) P.O & Procurement | 2007-06-13 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1PF1615W64A10P (HRSG #11 Damper) P.O & Procurement | Activity | 1PF1615W64A10P | (HRSG #11 Damper) P.O & Procurement | 2007-06-13 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1814 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1PF1615W64A06P | (HRSG #11 Duct) P.O & Procurement | (HRSG #11 Duct) P.O & Procurement | 2007-06-14 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1PF1615W64A06P (HRSG #11 Duct) P.O & Procurement | Activity | 1PF1615W64A06P | (HRSG #11 Duct) P.O & Procurement | 2007-06-14 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1815 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1EF1615W16A02 | (HRSG #11 Duct) FDN Design | (HRSG #11 Duct) FDN Design | 2007-08-02 | 2007-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1EF1615W16A02 (HRSG #11 Duct) FDN Design | Activity | 1EF1615W16A02 | (HRSG #11 Duct) FDN Design | 2007-08-02 00:00:00 | 2007-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1816 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1CF1615W16A03 | (HRSG #11 Duct) FDN Work | (HRSG #11 Duct) FDN Work | 2007-12-14 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1CF1615W16A03 (HRSG #11 Duct) FDN Work | Activity | 1CF1615W16A03 | (HRSG #11 Duct) FDN Work | 2007-12-14 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1817 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1PF1615W64A07T | (HRSG #11 Duct) Transportation | (HRSG #11 Duct) Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1PF1615W64A07T (HRSG #11 Duct) Transportation | Activity | 1PF1615W64A07T | (HRSG #11 Duct) Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1818 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1PF1615W64A11T | (HRSG #11 Damper) Transportation | (HRSG #11 Damper) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1PF1615W64A11T (HRSG #11 Damper) Transportation | Activity | 1PF1615W64A11T | (HRSG #11 Damper) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1819 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1PF1615W64A15T | (HRSG #11 EXP Joint & Bellows) Transportation | (HRSG #11 EXP Joint & Bellows) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1PF1615W64A15T (HRSG #11 EXP Joint & Bellows) Transportation | Activity | 1PF1615W64A15T | (HRSG #11 EXP Joint & Bellows) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1820 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1CF1615W64A12 | (HRSG #11 Damper) Installation | (HRSG #11 Damper) Installation | 2008-04-16 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1CF1615W64A12 (HRSG #11 Damper) Installation | Activity | 1CF1615W64A12 | (HRSG #11 Damper) Installation | 2008-04-16 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1821 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1CF1615W64A17 | (HRSG #11) Installation_Diverter Damper | (HRSG #11) Installation_Diverter Damper | 2008-05-03 | 2008-05-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1CF1615W64A17 (HRSG #11) Installation_Diverter Damper | Activity | 1CF1615W64A17 | (HRSG #11) Installation_Diverter Damper | 2008-05-03 00:00:00 | 2008-05-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1822 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1CF1615W64A20 | (HRSG #11) Installation_Guillotine Damper | (HRSG #11) Installation_Guillotine Damper | 2008-05-28 | 2008-06-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1CF1615W64A20 (HRSG #11) Installation_Guillotine Damper | Activity | 1CF1615W64A20 | (HRSG #11) Installation_Guillotine Damper | 2008-05-28 00:00:00 | 2008-06-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1823 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1CF1615W86A18 | (HRSG #11) Installation_Diverter Damper Control Unit | (HRSG #11) Installation_Diverter Damper Control Unit | 2008-05-28 | 2008-06-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1CF1615W86A18 (HRSG #11) Installation_Diverter Damper Control Unit | Activity | 1CF1615W86A18 | (HRSG #11) Installation_Diverter Damper Control Unit | 2008-05-28 00:00:00 | 2008-06-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1824 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1CF1615W62A19 | (HRSG #11) Diverter Damper Control Unit Flushing | (HRSG #11) Diverter Damper Control Unit Flushing | 2008-06-09 | 2008-06-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1CF1615W62A19 (HRSG #11) Diverter Damper Control Unit Flushing | Activity | 1CF1615W62A19 | (HRSG #11) Diverter Damper Control Unit Flushing | 2008-06-09 00:00:00 | 2008-06-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1825 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1SF1615W62A21 | (HRSG #11) Diverter Damper Function Test for GT #11 | (HRSG #11) Diverter Damper Function Test for GT #11 | 2008-08-05 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1SF1615W62A21 (HRSG #11) Diverter Damper Function Test for GT #11 | Activity | 1SF1615W62A21 | (HRSG #11) Diverter Damper Function Test for GT #11 | 2008-08-05 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1826 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1SF1615W62A22 | (HRSG #11) Guillotine Damper Function Test for GT #11 | (HRSG #11) Guillotine Damper Function Test for GT #11 | 2008-08-05 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1SF1615W62A22 (HRSG #11) Guillotine Damper Function Test for GT #11 | Activity | 1SF1615W62A22 | (HRSG #11) Guillotine Damper Function Test for GT #11 | 2008-08-05 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1827 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1CF1615W64A08 | (HRSG #11 Duct) Duct Installation | (HRSG #11 Duct) Duct Installation | 2008-09-16 | 2008-12-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1CF1615W64A08 (HRSG #11 Duct) Duct Installation | Activity | 1CF1615W64A08 | (HRSG #11 Duct) Duct Installation | 2008-09-16 00:00:00 | 2008-12-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1828 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Duct | 1CF1615W64A16 | (HRSG #11 EXP Joint & Bellows) Installation | (HRSG #11 EXP Joint & Bellows) Installation | 2008-11-19 | 2009-01-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Duct 1CF1615W64A16 (HRSG #11 EXP Joint & Bellows) Installation | Activity | 1CF1615W64A16 | (HRSG #11 EXP Joint & Bellows) Installation | 2008-11-19 00:00:00 | 2009-01-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1830 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Module | 1EF1610W42A01 | (HRSG #11 Module) MPS Issue | (HRSG #11 Module) MPS Issue |  | 2007-06-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Module 1EF1610W42A01 (HRSG #11 Module) MPS Issue | Activity | 1EF1610W42A01 | (HRSG #11 Module) MPS Issue |  | 2007-06-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1831 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Module | 1PF1610W42A02P | (HRSG #11 Module) P.O & Procurement | (HRSG #11 Module) P.O & Procurement | 2007-07-03 | 2008-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Module 1PF1610W42A02P (HRSG #11 Module) P.O & Procurement | Activity | 1PF1610W42A02P | (HRSG #11 Module) P.O & Procurement | 2007-07-03 00:00:00 | 2008-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1832 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Module | 1PF1610W42A03T | (HRSG #11 Module) Transportation | (HRSG #11 Module) Transportation | 2008-03-04 | 2008-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Module 1PF1610W42A03T (HRSG #11 Module) Transportation | Activity | 1PF1610W42A03T | (HRSG #11 Module) Transportation | 2008-03-04 00:00:00 | 2008-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1833 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Module | 1CF1610W42A04 | (HRSG #11 Module) Installation | (HRSG #11 Module) Installation | 2008-07-16 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Module 1CF1610W42A04 (HRSG #11 Module) Installation | Activity | 1CF1610W42A04 | (HRSG #11 Module) Installation | 2008-07-16 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1835 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Drum | 1EF1645W42A01 | (HRSG #11 Drum) Design | (HRSG #11 Drum) Design | 2007-04-17 | 2007-11-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Drum 1EF1645W42A01 (HRSG #11 Drum) Design | Activity | 1EF1645W42A01 | (HRSG #11 Drum) Design | 2007-04-17 00:00:00 | 2007-11-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1836 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Drum | 1EF1645W42A02 | (HRSG #11 Drum) MPS Issue | (HRSG #11 Drum) MPS Issue | 2007-05-15 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Drum 1EF1645W42A02 (HRSG #11 Drum) MPS Issue | Activity | 1EF1645W42A02 | (HRSG #11 Drum) MPS Issue | 2007-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1837 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Drum | 1PF1645W42A03P | (HRSG #11 Drum) P.O & Procurement | (HRSG #11 Drum) P.O & Procurement | 2007-06-13 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Drum 1PF1645W42A03P (HRSG #11 Drum) P.O & Procurement | Activity | 1PF1645W42A03P | (HRSG #11 Drum) P.O & Procurement | 2007-06-13 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1838 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Drum | 1PF1645W42A04T | (HRSG #11 Drum) Transportation | (HRSG #11 Drum) Transportation | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Drum 1PF1645W42A04T (HRSG #11 Drum) Transportation | Activity | 1PF1645W42A04T | (HRSG #11 Drum) Transportation | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1839 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Drum | 1CF1645W42A05 | (HRSG #11 Drum) Installation | (HRSG #11 Drum) Installation | 2008-09-16 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Drum 1CF1645W42A05 (HRSG #11 Drum) Installation | Activity | 1CF1645W42A05 | (HRSG #11 Drum) Installation | 2008-09-16 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1841 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Bypass Stack | 1EF1625W42A04 | (HRSG #11 Bypass Stack) Design | (HRSG #11 Bypass Stack) Design | 2007-04-17 | 2007-10-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Bypass Stack 1EF1625W42A04 (HRSG #11 Bypass Stack) Design | Activity | 1EF1625W42A04 | (HRSG #11 Bypass Stack) Design | 2007-04-17 00:00:00 | 2007-10-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1842 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Bypass Stack | 1EF1625W42A09 | (HRSG #11 Bypass Stack Silencer) MPS Issue | (HRSG #11 Bypass Stack Silencer) MPS Issue |  | 2007-04-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Bypass Stack 1EF1625W42A09 (HRSG #11 Bypass Stack Silencer) MPS Issue | Activity | 1EF1625W42A09 | (HRSG #11 Bypass Stack Silencer) MPS Issue |  | 2007-04-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1843 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Bypass Stack | 1EF1625W42A05 | (HRSG #11 Bypass Stack) MPS Issue | (HRSG #11 Bypass Stack) MPS Issue |  | 2007-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Bypass Stack 1EF1625W42A05 (HRSG #11 Bypass Stack) MPS Issue | Activity | 1EF1625W42A05 | (HRSG #11 Bypass Stack) MPS Issue |  | 2007-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1844 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Bypass Stack | 1EF1625W00A01 | (HRSG #11 Bypass Stack) GA & Load Data to Civil Design | (HRSG #11 Bypass Stack) GA & Load Data to Civil Design | 2007-05-31 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Bypass Stack 1EF1625W00A01 (HRSG #11 Bypass Stack) GA & Load Data to Civil Design | Activity | 1EF1625W00A01 | (HRSG #11 Bypass Stack) GA & Load Data to Civil Design | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1845 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Bypass Stack | 1PF1625W42A10P | (HRSG #11 Bypass Stack Silencer) P.O & Procurement | (HRSG #11 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Bypass Stack 1PF1625W42A10P (HRSG #11 Bypass Stack Silencer) P.O & Procurement | Activity | 1PF1625W42A10P | (HRSG #11 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1846 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Bypass Stack | 1PF1625W42A06P | (HRSG #11 Bypass Stack) P.O & Procurement | (HRSG #11 Bypass Stack) P.O & Procurement | 2007-07-03 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Bypass Stack 1PF1625W42A06P (HRSG #11 Bypass Stack) P.O & Procurement | Activity | 1PF1625W42A06P | (HRSG #11 Bypass Stack) P.O & Procurement | 2007-07-03 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1847 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Bypass Stack | 1EF1625W16A02 | (HRSG #11 Bypass Stack) FDN Design | (HRSG #11 Bypass Stack) FDN Design | 2007-09-04 | 2008-01-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Bypass Stack 1EF1625W16A02 (HRSG #11 Bypass Stack) FDN Design | Activity | 1EF1625W16A02 | (HRSG #11 Bypass Stack) FDN Design | 2007-09-04 00:00:00 | 2008-01-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1848 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Bypass Stack | 1CF1625W16A03 | (HRSG #11 Bypass Stack) FDN Work | (HRSG #11 Bypass Stack) FDN Work | 2008-01-11 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Bypass Stack 1CF1625W16A03 (HRSG #11 Bypass Stack) FDN Work | Activity | 1CF1625W16A03 | (HRSG #11 Bypass Stack) FDN Work | 2008-01-11 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1849 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Bypass Stack | 1PF1625W42A07T | (HRSG #11 Bypass Stack) Transportation | (HRSG #11 Bypass Stack) Transportation | 2008-01-31 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Bypass Stack 1PF1625W42A07T (HRSG #11 Bypass Stack) Transportation | Activity | 1PF1625W42A07T | (HRSG #11 Bypass Stack) Transportation | 2008-01-31 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1850 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Bypass Stack | 1CF1625W42A08 | (HRSG #11 Bypass Stack) Installation | (HRSG #11 Bypass Stack) Installation | 2008-03-31 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Bypass Stack 1CF1625W42A08 (HRSG #11 Bypass Stack) Installation | Activity | 1CF1625W42A08 | (HRSG #11 Bypass Stack) Installation | 2008-03-31 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1851 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Bypass Stack | 1PF1625W42A11T | (HRSG #11 Bypass Stack Silencer) Transportation | (HRSG #11 Bypass Stack Silencer) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Bypass Stack 1PF1625W42A11T (HRSG #11 Bypass Stack Silencer) Transportation | Activity | 1PF1625W42A11T | (HRSG #11 Bypass Stack Silencer) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1852 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Bypass Stack | 1CF1625W42A12 | (HRSG #11 Bypass Stack Silencer) Installation | (HRSG #11 Bypass Stack Silencer) Installation | 2008-05-31 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Bypass Stack 1CF1625W42A12 (HRSG #11 Bypass Stack Silencer) Installation | Activity | 1CF1625W42A12 | (HRSG #11 Bypass Stack Silencer) Installation | 2008-05-31 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1854 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Main Stack | 1EF1625W42A05.0 | (HRSG #11 Main Stack) MPS Issue | (HRSG #11 Main Stack) MPS Issue |  | 2007-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Main Stack 1EF1625W42A05.0 (HRSG #11 Main Stack) MPS Issue | Activity | 1EF1625W42A05.0 | (HRSG #11 Main Stack) MPS Issue |  | 2007-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1855 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Main Stack | 1EF1625W42A01 | (HRSG #11 Main Stack) Design | (HRSG #11 Main Stack) Design | 2007-04-17 | 2007-10-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Main Stack 1EF1625W42A01 (HRSG #11 Main Stack) Design | Activity | 1EF1625W42A01 | (HRSG #11 Main Stack) Design | 2007-04-17 00:00:00 | 2007-10-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1856 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Main Stack | 1EF1625W42A09.0 | (HRSG #11 Main Stack Silencer) MPS Issue | (HRSG #11 Main Stack Silencer) MPS Issue |  | 2007-04-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Main Stack 1EF1625W42A09.0 (HRSG #11 Main Stack Silencer) MPS Issue | Activity | 1EF1625W42A09.0 | (HRSG #11 Main Stack Silencer) MPS Issue |  | 2007-04-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1857 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Main Stack | 1PF1625W42A06.0P | (HRSG #11 Main Stack) P.O & Procurement | (HRSG #11 Main Stack) P.O & Procurement | 2007-06-04 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Main Stack 1PF1625W42A06.0P (HRSG #11 Main Stack) P.O & Procurement | Activity | 1PF1625W42A06.0P | (HRSG #11 Main Stack) P.O & Procurement | 2007-06-04 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1858 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Main Stack | 1EF1625W00A02 | (HRSG #11 Main Stack) GA & Load Data to Civil Design | (HRSG #11 Main Stack) GA & Load Data to Civil Design | 2007-06-05 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Main Stack 1EF1625W00A02 (HRSG #11 Main Stack) GA & Load Data to Civil Design | Activity | 1EF1625W00A02 | (HRSG #11 Main Stack) GA & Load Data to Civil Design | 2007-06-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1859 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Main Stack | 1PF1625W42A10.0P | (HRSG #11 Main Stack Silencer) P.O & Procurement | (HRSG #11 Main Stack Silencer) P.O & Procurement | 2007-07-27 | 2008-05-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Main Stack 1PF1625W42A10.0P (HRSG #11 Main Stack Silencer) P.O & Procurement | Activity | 1PF1625W42A10.0P | (HRSG #11 Main Stack Silencer) P.O & Procurement | 2007-07-27 00:00:00 | 2008-05-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1860 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Main Stack | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | (HRSG #11 Main Stack) FDN Design | 2007-09-07 | 2008-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Main Stack 1EF1625W16A03 (HRSG #11 Main Stack) FDN Design | Activity | 1EF1625W16A03 | (HRSG #11 Main Stack) FDN Design | 2007-09-07 00:00:00 | 2008-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1861 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Main Stack | 1CF1625W16A04 | (HRSG #11 Main Stack) FDN Work | (HRSG #11 Main Stack) FDN Work | 2008-01-16 | 2008-04-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Main Stack 1CF1625W16A04 (HRSG #11 Main Stack) FDN Work | Activity | 1CF1625W16A04 | (HRSG #11 Main Stack) FDN Work | 2008-01-16 00:00:00 | 2008-04-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1862 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Main Stack | 1PF1625W42A07.0T | (HRSG #11 Main Stack) Transportation | (HRSG #11 Main Stack) Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Main Stack 1PF1625W42A07.0T (HRSG #11 Main Stack) Transportation | Activity | 1PF1625W42A07.0T | (HRSG #11 Main Stack) Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1863 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Main Stack | 1PF1625W42A11.0T | (HRSG #11 Main Stack Silencer) Transportation | (HRSG #11 Main Stack Silencer) Transportation | 2008-05-15 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Main Stack 1PF1625W42A11.0T (HRSG #11 Main Stack Silencer) Transportation | Activity | 1PF1625W42A11.0T | (HRSG #11 Main Stack Silencer) Transportation | 2008-05-15 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1864 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Main Stack | 1CF1625W42A08.0 | (HRSG #11 Main Stack) Installation | (HRSG #11 Main Stack) Installation | 2008-11-13 | 2009-02-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Main Stack 1CF1625W42A08.0 (HRSG #11 Main Stack) Installation | Activity | 1CF1625W42A08.0 | (HRSG #11 Main Stack) Installation | 2008-11-13 00:00:00 | 2009-02-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1865 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Main Stack | 1CF1625W42A12.0 | (HRSG #11 Main Stack Silencer) Installation | (HRSG #11 Main Stack Silencer) Installation | 2009-01-21 | 2009-02-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Main Stack 1CF1625W42A12.0 (HRSG #11 Main Stack Silencer) Installation | Activity | 1CF1625W42A12.0 | (HRSG #11 Main Stack Silencer) Installation | 2009-01-21 00:00:00 | 2009-02-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1867 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Piping Work | 1EF1650W52A01 | (HRSG #11 Insulation) MPS Issue | (HRSG #11 Insulation) MPS Issue |  | 2007-11-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Piping Work 1EF1650W52A01 (HRSG #11 Insulation) MPS Issue | Activity | 1EF1650W52A01 | (HRSG #11 Insulation) MPS Issue |  | 2007-11-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1868 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Piping Work | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | (HRSG #11 Insulation) P.O & Procurement | 2008-01-09 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Piping Work 1PF1650W52A02P (HRSG #11 Insulation) P.O & Procurement | Activity | 1PF1650W52A02P | (HRSG #11 Insulation) P.O & Procurement | 2008-01-09 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1869 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Piping Work | 1CF1640W58A05 | (HRSG #11) Piping Work | (HRSG #11) Piping Work | 2008-09-30 | 2008-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Piping Work 1CF1640W58A05 (HRSG #11) Piping Work | Activity | 1CF1640W58A05 | (HRSG #11) Piping Work | 2008-09-30 00:00:00 | 2008-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1870 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Piping Work | 1PF1650W52A03T | (HRSG #11 Insulation) Transportation | (HRSG #11 Insulation) Transportation | 2008-10-01 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Piping Work 1PF1650W52A03T (HRSG #11 Insulation) Transportation | Activity | 1PF1650W52A03T | (HRSG #11 Insulation) Transportation | 2008-10-01 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1871 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Piping Work | 1CF1640W62A06 | (HRSG #11) Hydro Test | (HRSG #11) Hydro Test | 2009-01-01 | 2009-01-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Piping Work 1CF1640W62A06 (HRSG #11) Hydro Test | Activity | 1CF1640W62A06 | (HRSG #11) Hydro Test | 2009-01-01 00:00:00 | 2009-01-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1872 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Piping Work | 1CF1650W52A04 | (HRSG #11 Insulation) Installation | (HRSG #11 Insulation) Installation | 2009-01-15 | 2009-02-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Piping Work 1CF1650W52A04 (HRSG #11 Insulation) Installation | Activity | 1CF1650W52A04 | (HRSG #11 Insulation) Installation | 2009-01-15 00:00:00 | 2009-02-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1873 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Piping Work | 1CF1640W60A07 | (HRSG #11) Acid Cleaning | (HRSG #11) Acid Cleaning | 2009-01-26 | 2009-02-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Piping Work 1CF1640W60A07 (HRSG #11) Acid Cleaning | Activity | 1CF1640W60A07 | (HRSG #11) Acid Cleaning | 2009-01-26 00:00:00 | 2009-02-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1875 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | CEMS | 1EF1660W86A03 | (CEMS) MPS Issue | (CEMS) MPS Issue |  | 2007-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 CEMS 1EF1660W86A03 (CEMS) MPS Issue | Activity | 1EF1660W86A03 | (CEMS) MPS Issue |  | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1876 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | CEMS | 1PF1660W86A04P | (CEMS) P.O & Procurement | (CEMS) P.O & Procurement | 2007-08-29 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 CEMS 1PF1660W86A04P (CEMS) P.O & Procurement | Activity | 1PF1660W86A04P | (CEMS) P.O & Procurement | 2007-08-29 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1877 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | CEMS | 1EF1660W16A01 | (CEMS) FDN Design | (CEMS) FDN Design | 2007-10-30 | 2008-01-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 CEMS 1EF1660W16A01 (CEMS) FDN Design | Activity | 1EF1660W16A01 | (CEMS) FDN Design | 2007-10-30 00:00:00 | 2008-01-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1878 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | CEMS | 1CF1660W16A02 | (CEMS) FDN Work | (CEMS) FDN Work | 2008-01-26 | 2008-03-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 CEMS 1CF1660W16A02 (CEMS) FDN Work | Activity | 1CF1660W16A02 | (CEMS) FDN Work | 2008-01-26 00:00:00 | 2008-03-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1879 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | CEMS | 1PF1660W86A05T | (CEMS) Transportation | (CEMS) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 CEMS 1PF1660W86A05T (CEMS) Transportation | Activity | 1PF1660W86A05T | (CEMS) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1880 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | CEMS | 1CF1660W86A06 | (CEMS) Installation(incl. Elec, I&C) | (CEMS) Installation(incl. Elec, I&C) | 2008-05-16 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 CEMS 1CF1660W86A06 (CEMS) Installation(incl. Elec, I&C) | Activity | 1CF1660W86A06 | (CEMS) Installation(incl. Elec, I&C) | 2008-05-16 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1881 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | CEMS | 1CF1660W62A07 | (CEMS) Loop Test | (CEMS) Loop Test | 2008-06-02 | 2008-06-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 CEMS 1CF1660W62A07 (CEMS) Loop Test | Activity | 1CF1660W62A07 | (CEMS) Loop Test | 2008-06-02 00:00:00 | 2008-06-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1882 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | CEMS | 1SF1615W62A08 | (HRSG #11) CEMS Function Test for GT #11(Bypass stack) | (HRSG #11) CEMS Function Test for GT #11(Bypass stack) | 2008-08-05 | 2008-08-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 CEMS 1SF1615W62A08 (HRSG #11) CEMS Function Test for GT #11(Bypass stack) | Activity | 1SF1615W62A08 | (HRSG #11) CEMS Function Test for GT #11(Bypass stack) | 2008-08-05 00:00:00 | 2008-08-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1884 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1EF1660W70A05 | (HRSG #11 ELEC Vendor Equip) MPS Issue | (HRSG #11 ELEC Vendor Equip) MPS Issue |  | 2007-06-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1EF1660W70A05 (HRSG #11 ELEC Vendor Equip) MPS Issue | Activity | 1EF1660W70A05 | (HRSG #11 ELEC Vendor Equip) MPS Issue |  | 2007-06-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1885 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1EF1660W86A10 | (HRSG #11 I&C Vendor Equip) MPS Issue | (HRSG #11 I&C Vendor Equip) MPS Issue |  | 2007-06-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1EF1660W86A10 (HRSG #11 I&C Vendor Equip) MPS Issue | Activity | 1EF1660W86A10 | (HRSG #11 I&C Vendor Equip) MPS Issue |  | 2007-06-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1886 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1EF1665W42A01 | (HRSG #11 MECH Vendor Equip) MPS Issue | (HRSG #11 MECH Vendor Equip) MPS Issue |  | 2007-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1EF1665W42A01 (HRSG #11 MECH Vendor Equip) MPS Issue | Activity | 1EF1665W42A01 | (HRSG #11 MECH Vendor Equip) MPS Issue |  | 2007-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1887 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | (HRSG #11 MECH Vendor Equip) P.O & Procurement | 2007-09-10 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1PF1665W42A02P (HRSG #11 MECH Vendor Equip) P.O & Procurement | Activity | 1PF1665W42A02P | (HRSG #11 MECH Vendor Equip) P.O & Procurement | 2007-09-10 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1888 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1PF1660W70A06P | (HRSG #11 ELEC Vendor Equip) P.O & Procurement | (HRSG #11 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1PF1660W70A06P (HRSG #11 ELEC Vendor Equip) P.O & Procurement | Activity | 1PF1660W70A06P | (HRSG #11 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1889 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1PF1660W86A11P | (HRSG #11 I&C Vendor Equip) P.O & Procurement | (HRSG #11 I&C Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1PF1660W86A11P (HRSG #11 I&C Vendor Equip) P.O & Procurement | Activity | 1PF1660W86A11P | (HRSG #11 I&C Vendor Equip) P.O & Procurement | 2007-10-02 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1890 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1PF1665W42A03T | (HRSG #11 MECH Vendor Equip) Transportation | (HRSG #11 MECH Vendor Equip) Transportation | 2008-08-02 | 2008-09-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1PF1665W42A03T (HRSG #11 MECH Vendor Equip) Transportation | Activity | 1PF1665W42A03T | (HRSG #11 MECH Vendor Equip) Transportation | 2008-08-02 00:00:00 | 2008-09-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1891 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1PF1660W70A07T | (HRSG #11 ELEC Vendor Equip) Transportation | (HRSG #11 ELEC Vendor Equip) Transportation | 2008-08-05 | 2008-09-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1PF1660W70A07T (HRSG #11 ELEC Vendor Equip) Transportation | Activity | 1PF1660W70A07T | (HRSG #11 ELEC Vendor Equip) Transportation | 2008-08-05 00:00:00 | 2008-09-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1892 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1PF1660W86A12T | (HRSG #11 I&C Vendor Equip) Transportation | (HRSG #11 I&C Vendor Equip) Transportation | 2008-08-05 | 2008-09-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1PF1660W86A12T (HRSG #11 I&C Vendor Equip) Transportation | Activity | 1PF1660W86A12T | (HRSG #11 I&C Vendor Equip) Transportation | 2008-08-05 00:00:00 | 2008-09-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1893 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1CF1665W42A04 | (HRSG #11 MECH Vendor Equip) Installation | (HRSG #11 MECH Vendor Equip) Installation | 2008-09-17 | 2008-12-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1CF1665W42A04 (HRSG #11 MECH Vendor Equip) Installation | Activity | 1CF1665W42A04 | (HRSG #11 MECH Vendor Equip) Installation | 2008-09-17 00:00:00 | 2008-12-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1894 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1CF1660W70A08 | (HRSG #11 ELEC Vendor Equip) Installation | (HRSG #11 ELEC Vendor Equip) Installation | 2008-09-19 | 2009-01-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1CF1660W70A08 (HRSG #11 ELEC Vendor Equip) Installation | Activity | 1CF1660W70A08 | (HRSG #11 ELEC Vendor Equip) Installation | 2008-09-19 00:00:00 | 2009-01-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1895 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1CF1660W86A13 | (HRSG #11 I&C Vendor Equip) Installation | (HRSG #11 I&C Vendor Equip) Installation | 2008-09-19 | 2009-01-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1CF1660W86A13 (HRSG #11 I&C Vendor Equip) Installation | Activity | 1CF1660W86A13 | (HRSG #11 I&C Vendor Equip) Installation | 2008-09-19 00:00:00 | 2009-01-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1896 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1CF1655W74A09 | (HRSG #11) Installation & Test - Elec. | (HRSG #11) Installation & Test - Elec. | 2008-10-29 | 2009-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1CF1655W74A09 (HRSG #11) Installation & Test - Elec. | Activity | 1CF1655W74A09 | (HRSG #11) Installation & Test - Elec. | 2008-10-29 00:00:00 | 2009-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1897 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Auxiliary System | 1CF1660W90A14 | (HRSG #11) Installation & Test - I&C | (HRSG #11) Installation & Test - I&C | 2008-10-29 | 2009-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Auxiliary System 1CF1660W90A14 (HRSG #11) Installation & Test - I&C | Activity | 1CF1660W90A14 | (HRSG #11) Installation & Test - I&C | 2008-10-29 00:00:00 | 2009-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1899 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Commissioning | 1SF1600W62A01 | (HRSG #11) Cold Commissioning for HRSG #11 | (HRSG #11) Cold Commissioning for HRSG #11 | 2009-02-19 | 2009-03-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Commissioning 1SF1600W62A01 (HRSG #11) Cold Commissioning for HRSG #11 | Activity | 1SF1600W62A01 | (HRSG #11) Cold Commissioning for HRSG #11 | 2009-02-19 00:00:00 | 2009-03-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1900 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #11 > Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #11 | Commissioning | 1SF1600W62A02 | (HRSG #11) Function Test for HRSG #11 | (HRSG #11) Function Test for HRSG #11 | 2009-03-11 | 2009-03-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #11 Commissioning 1SF1600W62A02 (HRSG #11) Function Test for HRSG #11 | Activity | 1SF1600W62A02 | (HRSG #11) Function Test for HRSG #11 | 2009-03-11 00:00:00 | 2009-03-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1903 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1EF1600W74A05.1 | (HRSG #12 LEB) MPS Issue - Elec | (HRSG #12 LEB) MPS Issue - Elec |  | 2007-06-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1EF1600W74A05.1 (HRSG #12 LEB) MPS Issue - Elec | Activity | 1EF1600W74A05.1 | (HRSG #12 LEB) MPS Issue - Elec |  | 2007-06-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1904 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1EF1600W90A09.1 | (HRSG #12 LEB) MPS Issue - I&C | (HRSG #12 LEB) MPS Issue - I&C |  | 2007-06-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1EF1600W90A09.1 (HRSG #12 LEB) MPS Issue - I&C | Activity | 1EF1600W90A09.1 | (HRSG #12 LEB) MPS Issue - I&C |  | 2007-06-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1905 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1EF1600W00A01.1 | (HRSG #12 LEB) GA & Load Data to Civil Design | (HRSG #12 LEB) GA & Load Data to Civil Design | 2007-06-20 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1EF1600W00A01.1 (HRSG #12 LEB) GA & Load Data to Civil Design | Activity | 1EF1600W00A01.1 | (HRSG #12 LEB) GA & Load Data to Civil Design | 2007-06-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1906 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1EF1600W32A02.1 | (HRSG #12 LEB) Building Design | (HRSG #12 LEB) Building Design | 2007-06-20 | 2007-11-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1EF1600W32A02.1 (HRSG #12 LEB) Building Design | Activity | 1EF1600W32A02.1 | (HRSG #12 LEB) Building Design | 2007-06-20 00:00:00 | 2007-11-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1907 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1PF1600W74A06.1P | (HRSG #12 LEB) P.O & Procurement - Elec | (HRSG #12 LEB) P.O & Procurement - Elec | 2007-09-15 | 2008-07-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1PF1600W74A06.1P (HRSG #12 LEB) P.O & Procurement - Elec | Activity | 1PF1600W74A06.1P | (HRSG #12 LEB) P.O & Procurement - Elec | 2007-09-15 00:00:00 | 2008-07-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1908 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1PF1600W90A10.1P | (HRSG #12 LEB) P.O & Procurement - I&C | (HRSG #12 LEB) P.O & Procurement - I&C | 2007-09-15 | 2008-07-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1PF1600W90A10.1P (HRSG #12 LEB) P.O & Procurement - I&C | Activity | 1PF1600W90A10.1P | (HRSG #12 LEB) P.O & Procurement - I&C | 2007-09-15 00:00:00 | 2008-07-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1909 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1CF1600W16A03.1 | (HRSG #12 LEB)FDN Work | (HRSG #12 LEB)FDN Work | 2008-01-01 | 2008-02-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1CF1600W16A03.1 (HRSG #12 LEB)FDN Work | Activity | 1CF1600W16A03.1 | (HRSG #12 LEB)FDN Work | 2008-01-01 00:00:00 | 2008-02-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1910 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1CF1600W32A04.1 | (HRSG #12 LEB)Structure Work | (HRSG #12 LEB)Structure Work | 2008-02-28 | 2008-05-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1CF1600W32A04.1 (HRSG #12 LEB)Structure Work | Activity | 1CF1600W32A04.1 | (HRSG #12 LEB)Structure Work | 2008-02-28 00:00:00 | 2008-05-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1911 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1PF1600W74A07.1T | (HRSG #12 LEB) Transportataion - Elec | (HRSG #12 LEB) Transportataion - Elec | 2008-07-11 | 2008-08-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1PF1600W74A07.1T (HRSG #12 LEB) Transportataion - Elec | Activity | 1PF1600W74A07.1T | (HRSG #12 LEB) Transportataion - Elec | 2008-07-11 00:00:00 | 2008-08-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1912 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1PF1600W90A11.1T | (HRSG #12 LEB) Transportataion - I&C | (HRSG #12 LEB) Transportataion - I&C | 2008-07-11 | 2008-08-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1PF1600W90A11.1T (HRSG #12 LEB) Transportataion - I&C | Activity | 1PF1600W90A11.1T | (HRSG #12 LEB) Transportataion - I&C | 2008-07-11 00:00:00 | 2008-08-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1913 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1CF1600W36A13.1 | (HRSG #12 LEB) Installation & Test - HVAC | (HRSG #12 LEB) Installation & Test - HVAC | 2008-07-31 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1CF1600W36A13.1 (HRSG #12 LEB) Installation & Test - HVAC | Activity | 1CF1600W36A13.1 | (HRSG #12 LEB) Installation & Test - HVAC | 2008-07-31 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1914 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1CF1600W74A08.1 | (HRSG #12 LEB) Installation & Test - Elec | (HRSG #12 LEB) Installation & Test - Elec | 2008-10-20 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1CF1600W74A08.1 (HRSG #12 LEB) Installation & Test - Elec | Activity | 1CF1600W74A08.1 | (HRSG #12 LEB) Installation & Test - Elec | 2008-10-20 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1915 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1CF1600W90A12.1 | (HRSG #12 LEB) Installation & Test - I&C | (HRSG #12 LEB) Installation & Test - I&C | 2008-10-20 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1CF1600W90A12.1 (HRSG #12 LEB) Installation & Test - I&C | Activity | 1CF1600W90A12.1 | (HRSG #12 LEB) Installation & Test - I&C | 2008-10-20 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1916 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | HRSG LEB | 1CF1600W38A14.1 | (HRSG #12 LEB) Installation & Test - Fire Fighting Sys. | (HRSG #12 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 HRSG LEB 1CF1600W38A14.1 (HRSG #12 LEB) Installation & Test - Fire Fighting Sys. | Activity | 1CF1600W38A14.1 | (HRSG #12 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1918 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Steel Structure & Casing | 1EF1610W20A01.1 | (HRSG #12 S/Structure & Casing) Design | (HRSG #12 S/Structure & Casing) Design | 2007-04-18 | 2007-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Steel Structure & Casing 1EF1610W20A01.1 (HRSG #12 S/Structure & Casing) Design | Activity | 1EF1610W20A01.1 | (HRSG #12 S/Structure & Casing) Design | 2007-04-18 00:00:00 | 2007-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1919 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Steel Structure & Casing | 1EF1610W20A02.1 | (HRSG #12 S/Structure & Casing) MPS Issue | (HRSG #12 S/Structure & Casing) MPS Issue |  | 2007-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Steel Structure & Casing 1EF1610W20A02.1 (HRSG #12 S/Structure & Casing) MPS Issue | Activity | 1EF1610W20A02.1 | (HRSG #12 S/Structure & Casing) MPS Issue |  | 2007-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1920 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Steel Structure & Casing | 1PF1610W20A03.1P | (HRSG #12 S/Structure & Casing) P.O & Procurement | (HRSG #12 S/Structure & Casing) P.O & Procurement | 2007-06-14 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Steel Structure & Casing 1PF1610W20A03.1P (HRSG #12 S/Structure & Casing) P.O & Procurement | Activity | 1PF1610W20A03.1P | (HRSG #12 S/Structure & Casing) P.O & Procurement | 2007-06-14 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1921 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Steel Structure & Casing | 1PF1610W20A04.1T | (HRSG #12 S/Structure & Casing) Transportation | (HRSG #12 S/Structure & Casing) Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Steel Structure & Casing 1PF1610W20A04.1T (HRSG #12 S/Structure & Casing) Transportation | Activity | 1PF1610W20A04.1T | (HRSG #12 S/Structure & Casing) Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1922 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Steel Structure & Casing | 1CF1610W20A05.1 | (HRSG #12 S/Structure & Casing) S/Structure Installation | (HRSG #12 S/Structure & Casing) S/Structure Installation | 2008-03-18 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Steel Structure & Casing 1CF1610W20A05.1 (HRSG #12 S/Structure & Casing) S/Structure Installation | Activity | 1CF1610W20A05.1 | (HRSG #12 S/Structure & Casing) S/Structure Installation | 2008-03-18 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1923 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Steel Structure & Casing | 1CF1610W20A06.1 | (HRSG #12 S/Structure & Casing) Casing Installation | (HRSG #12 S/Structure & Casing) Casing Installation | 2008-05-18 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Steel Structure & Casing 1CF1610W20A06.1 (HRSG #12 S/Structure & Casing) Casing Installation | Activity | 1CF1610W20A06.1 | (HRSG #12 S/Structure & Casing) Casing Installation | 2008-05-18 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1925 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1EF1615W64A01.1 | (HRSG #12 Duct) Design | (HRSG #12 Duct) Design | 2007-04-17 | 2007-10-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1EF1615W64A01.1 (HRSG #12 Duct) Design | Activity | 1EF1615W64A01.1 | (HRSG #12 Duct) Design | 2007-04-17 00:00:00 | 2007-10-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1926 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1EF1665W64A13.1 | (HRSG #12 EXP Joint & Bellows) MPS Issue | (HRSG #12 EXP Joint & Bellows) MPS Issue |  | 2007-04-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1EF1665W64A13.1 (HRSG #12 EXP Joint & Bellows) MPS Issue | Activity | 1EF1665W64A13.1 | (HRSG #12 EXP Joint & Bellows) MPS Issue |  | 2007-04-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1927 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1EF1615W64A09.1 | (HRSG #12 Damper) MPS Issue | (HRSG #12 Damper) MPS Issue |  | 2007-04-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1EF1615W64A09.1 (HRSG #12 Damper) MPS Issue | Activity | 1EF1615W64A09.1 | (HRSG #12 Damper) MPS Issue |  | 2007-04-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1928 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1EF1615W00A02.1 | (HRSG #12 Duct) GA & Load Data to Civil Design | (HRSG #12 Duct) GA & Load Data to Civil Design | 2007-04-30 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1EF1615W00A02.1 (HRSG #12 Duct) GA & Load Data to Civil Design | Activity | 1EF1615W00A02.1 | (HRSG #12 Duct) GA & Load Data to Civil Design | 2007-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1929 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1EF1615W64A05.1 | (HRSG #12 Duct) MPS Issue | (HRSG #12 Duct) MPS Issue |  | 2007-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1EF1615W64A05.1 (HRSG #12 Duct) MPS Issue | Activity | 1EF1615W64A05.1 | (HRSG #12 Duct) MPS Issue |  | 2007-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1930 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1PF1665W64A14.1P | (HRSG #12 EXP Joint & Bellows) P.O & Procurement | (HRSG #12 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1PF1665W64A14.1P (HRSG #12 EXP Joint & Bellows) P.O & Procurement | Activity | 1PF1665W64A14.1P | (HRSG #12 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1931 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1PF1615W64A10.1P | (HRSG #12 Damper) P.O & Procurement | (HRSG #12 Damper) P.O & Procurement | 2007-06-13 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1PF1615W64A10.1P (HRSG #12 Damper) P.O & Procurement | Activity | 1PF1615W64A10.1P | (HRSG #12 Damper) P.O & Procurement | 2007-06-13 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1932 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | (HRSG #12 Duct) P.O & Procurement | 2007-06-14 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1PF1615W64A06.1P (HRSG #12 Duct) P.O & Procurement | Activity | 1PF1615W64A06.1P | (HRSG #12 Duct) P.O & Procurement | 2007-06-14 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1933 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1EF1615W16A03.1 | (HRSG #12 Duct) FDN Design | (HRSG #12 Duct) FDN Design | 2007-08-02 | 2007-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1EF1615W16A03.1 (HRSG #12 Duct) FDN Design | Activity | 1EF1615W16A03.1 | (HRSG #12 Duct) FDN Design | 2007-08-02 00:00:00 | 2007-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1934 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1CF1615W16A04.1 | (HRSG #12 Duct) FDN Work | (HRSG #12 Duct) FDN Work | 2007-12-14 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1CF1615W16A04.1 (HRSG #12 Duct) FDN Work | Activity | 1CF1615W16A04.1 | (HRSG #12 Duct) FDN Work | 2007-12-14 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1935 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1PF1615W64A07.1T | (HRSG #12 Duct) Transportation | (HRSG #12 Duct) Transportation | 2008-02-01 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1PF1615W64A07.1T (HRSG #12 Duct) Transportation | Activity | 1PF1615W64A07.1T | (HRSG #12 Duct) Transportation | 2008-02-01 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1936 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1PF1615W64A11.1T | (HRSG #12 Damper) Transportation | (HRSG #12 Damper) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1PF1615W64A11.1T (HRSG #12 Damper) Transportation | Activity | 1PF1615W64A11.1T | (HRSG #12 Damper) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1937 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1PF1665W64A15.1T | (HRSG #12 EXP Joint & Bellows) Transportation | (HRSG #12 EXP Joint & Bellows) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1PF1665W64A15.1T (HRSG #12 EXP Joint & Bellows) Transportation | Activity | 1PF1665W64A15.1T | (HRSG #12 EXP Joint & Bellows) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1938 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1CF1615W64A12.1 | (HRSG #12 Damper) Installation | (HRSG #12 Damper) Installation | 2008-04-16 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1CF1615W64A12.1 (HRSG #12 Damper) Installation | Activity | 1CF1615W64A12.1 | (HRSG #12 Damper) Installation | 2008-04-16 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1939 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1CF1615W64A17.1 | (HRSG #12) Installation_Diverter Damper | (HRSG #12) Installation_Diverter Damper | 2008-05-03 | 2008-05-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1CF1615W64A17.1 (HRSG #12) Installation_Diverter Damper | Activity | 1CF1615W64A17.1 | (HRSG #12) Installation_Diverter Damper | 2008-05-03 00:00:00 | 2008-05-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1940 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1CF1615W64A18.1 | (HRSG #12) Installation_Guillotine Damper | (HRSG #12) Installation_Guillotine Damper | 2008-05-28 | 2008-06-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1CF1615W64A18.1 (HRSG #12) Installation_Guillotine Damper | Activity | 1CF1615W64A18.1 | (HRSG #12) Installation_Guillotine Damper | 2008-05-28 00:00:00 | 2008-06-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1941 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1CF1615W86A19.1 | (HRSG #12) Installation_Diverter Damper Control Unit | (HRSG #12) Installation_Diverter Damper Control Unit | 2008-05-28 | 2008-06-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1CF1615W86A19.1 (HRSG #12) Installation_Diverter Damper Control Unit | Activity | 1CF1615W86A19.1 | (HRSG #12) Installation_Diverter Damper Control Unit | 2008-05-28 00:00:00 | 2008-06-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1942 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1CF1615W62A20.1 | (HRSG #12) Diverter Damper Control Unit Flushing | (HRSG #12) Diverter Damper Control Unit Flushing | 2008-06-09 | 2008-06-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1CF1615W62A20.1 (HRSG #12) Diverter Damper Control Unit Flushing | Activity | 1CF1615W62A20.1 | (HRSG #12) Diverter Damper Control Unit Flushing | 2008-06-09 00:00:00 | 2008-06-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1943 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1SF1615W62A21.1 | (HRSG #12) Diverter Damper Function Test for GT #12 | (HRSG #12) Diverter Damper Function Test for GT #12 | 2008-08-05 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1SF1615W62A21.1 (HRSG #12) Diverter Damper Function Test for GT #12 | Activity | 1SF1615W62A21.1 | (HRSG #12) Diverter Damper Function Test for GT #12 | 2008-08-05 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1944 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1SF1615W62A22.1 | (HRSG #12) Guillotine Damper Function Test for GT #12 | (HRSG #12) Guillotine Damper Function Test for GT #12 | 2008-08-05 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1SF1615W62A22.1 (HRSG #12) Guillotine Damper Function Test for GT #12 | Activity | 1SF1615W62A22.1 | (HRSG #12) Guillotine Damper Function Test for GT #12 | 2008-08-05 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1945 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1CF1615W64A08.1 | (HRSG #12 Duct) Duct Installation | (HRSG #12 Duct) Duct Installation | 2008-09-17 | 2008-12-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1CF1615W64A08.1 (HRSG #12 Duct) Duct Installation | Activity | 1CF1615W64A08.1 | (HRSG #12 Duct) Duct Installation | 2008-09-17 00:00:00 | 2008-12-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1946 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Duct | 1CF1665W64A16.1 | (HRSG #12 EXP Joint & Bellows) Installation | (HRSG #12 EXP Joint & Bellows) Installation | 2008-11-20 | 2009-01-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Duct 1CF1665W64A16.1 (HRSG #12 EXP Joint & Bellows) Installation | Activity | 1CF1665W64A16.1 | (HRSG #12 EXP Joint & Bellows) Installation | 2008-11-20 00:00:00 | 2009-01-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1948 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Module | 1EF1610W42A01.1 | (HRSG #12 Module) MPS Issue | (HRSG #12 Module) MPS Issue |  | 2007-06-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Module 1EF1610W42A01.1 (HRSG #12 Module) MPS Issue | Activity | 1EF1610W42A01.1 | (HRSG #12 Module) MPS Issue |  | 2007-06-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1949 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Module | 1PF1610W42A02.1P | (HRSG #12 Module) P.O & Procurement | (HRSG #12 Module) P.O & Procurement | 2007-07-03 | 2008-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Module 1PF1610W42A02.1P (HRSG #12 Module) P.O & Procurement | Activity | 1PF1610W42A02.1P | (HRSG #12 Module) P.O & Procurement | 2007-07-03 00:00:00 | 2008-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1950 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Module | 1PF1610W42A03.1T | (HRSG #12 Module) Transportation | (HRSG #12 Module) Transportation | 2008-03-04 | 2008-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Module 1PF1610W42A03.1T (HRSG #12 Module) Transportation | Activity | 1PF1610W42A03.1T | (HRSG #12 Module) Transportation | 2008-03-04 00:00:00 | 2008-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1951 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Module | 1CF1610W42A04.1 | (HRSG #12 Module) Installation | (HRSG #12 Module) Installation | 2008-07-17 | 2008-09-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Module 1CF1610W42A04.1 (HRSG #12 Module) Installation | Activity | 1CF1610W42A04.1 | (HRSG #12 Module) Installation | 2008-07-17 00:00:00 | 2008-09-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1953 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Drum | 1EF1645W42A01.1 | (HRSG #12 Drum) Design | (HRSG #12 Drum) Design | 2007-04-17 | 2007-11-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Drum 1EF1645W42A01.1 (HRSG #12 Drum) Design | Activity | 1EF1645W42A01.1 | (HRSG #12 Drum) Design | 2007-04-17 00:00:00 | 2007-11-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1954 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Drum | 1EF1645W42A02.1 | (HRSG #12 Drum) MPS Issue | (HRSG #12 Drum) MPS Issue | 2007-05-15 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Drum 1EF1645W42A02.1 (HRSG #12 Drum) MPS Issue | Activity | 1EF1645W42A02.1 | (HRSG #12 Drum) MPS Issue | 2007-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1955 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Drum | 1PF1645W42A03.1P | (HRSG #12 Drum) P.O & Procurement | (HRSG #12 Drum) P.O & Procurement | 2007-06-13 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Drum 1PF1645W42A03.1P (HRSG #12 Drum) P.O & Procurement | Activity | 1PF1645W42A03.1P | (HRSG #12 Drum) P.O & Procurement | 2007-06-13 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1956 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Drum | 1PF1645W42A04.1T | (HRSG #12 Drum) Transportation | (HRSG #12 Drum) Transportation | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Drum 1PF1645W42A04.1T (HRSG #12 Drum) Transportation | Activity | 1PF1645W42A04.1T | (HRSG #12 Drum) Transportation | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1957 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Drum | 1CF1645W42A05.1 | (HRSG #12 Drum) Installation | (HRSG #12 Drum) Installation | 2008-09-17 | 2008-10-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Drum 1CF1645W42A05.1 (HRSG #12 Drum) Installation | Activity | 1CF1645W42A05.1 | (HRSG #12 Drum) Installation | 2008-09-17 00:00:00 | 2008-10-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1959 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Bypass Stack | 1EF1625W42A01.1 | (HRSG #12 Bypass Stack) Design | (HRSG #12 Bypass Stack) Design | 2007-04-17 | 2007-10-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Bypass Stack 1EF1625W42A01.1 (HRSG #12 Bypass Stack) Design | Activity | 1EF1625W42A01.1 | (HRSG #12 Bypass Stack) Design | 2007-04-17 00:00:00 | 2007-10-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1960 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Bypass Stack | 1EF1625W42A09.1 | (HRSG #12 Bypass Stack Silencer) MPS Issue | (HRSG #12 Bypass Stack Silencer) MPS Issue |  | 2007-04-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Bypass Stack 1EF1625W42A09.1 (HRSG #12 Bypass Stack Silencer) MPS Issue | Activity | 1EF1625W42A09.1 | (HRSG #12 Bypass Stack Silencer) MPS Issue |  | 2007-04-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1961 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Bypass Stack | 1EF1625W42A05.1 | (HRSG #12 Bypass Stack) MPS Issue | (HRSG #12 Bypass Stack) MPS Issue |  | 2007-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Bypass Stack 1EF1625W42A05.1 (HRSG #12 Bypass Stack) MPS Issue | Activity | 1EF1625W42A05.1 | (HRSG #12 Bypass Stack) MPS Issue |  | 2007-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1962 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Bypass Stack | 1EF1625W00A02.1 | (HRSG #12 Bypass Stack) GA & Load Data to Civil Design | (HRSG #12 Bypass Stack) GA & Load Data to Civil Design | 2007-05-31 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Bypass Stack 1EF1625W00A02.1 (HRSG #12 Bypass Stack) GA & Load Data to Civil Design | Activity | 1EF1625W00A02.1 | (HRSG #12 Bypass Stack) GA & Load Data to Civil Design | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1963 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Bypass Stack | 1PF1625W42A10.1P | (HRSG #12 Bypass Stack Silencer) P.O & Procurement | (HRSG #12 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Bypass Stack 1PF1625W42A10.1P (HRSG #12 Bypass Stack Silencer) P.O & Procurement | Activity | 1PF1625W42A10.1P | (HRSG #12 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1964 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Bypass Stack | 1PF1625W42A06.1P | (HRSG #12 Bypass Stack) P.O & Procurement | (HRSG #12 Bypass Stack) P.O & Procurement | 2007-07-03 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Bypass Stack 1PF1625W42A06.1P (HRSG #12 Bypass Stack) P.O & Procurement | Activity | 1PF1625W42A06.1P | (HRSG #12 Bypass Stack) P.O & Procurement | 2007-07-03 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1965 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Bypass Stack | 1EF1625W16A03.1 | (HRSG #12 Bypass Stack) FDN Design | (HRSG #12 Bypass Stack) FDN Design | 2007-09-04 | 2008-01-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Bypass Stack 1EF1625W16A03.1 (HRSG #12 Bypass Stack) FDN Design | Activity | 1EF1625W16A03.1 | (HRSG #12 Bypass Stack) FDN Design | 2007-09-04 00:00:00 | 2008-01-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1966 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Bypass Stack | 1CF1625W16A04.1 | (HRSG #12 Bypass Stack) FDN Work | (HRSG #12 Bypass Stack) FDN Work | 2008-01-11 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Bypass Stack 1CF1625W16A04.1 (HRSG #12 Bypass Stack) FDN Work | Activity | 1CF1625W16A04.1 | (HRSG #12 Bypass Stack) FDN Work | 2008-01-11 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1967 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Bypass Stack | 1PF1625W42A07.1T | (HRSG #12 Bypass Stack) Transportation | (HRSG #12 Bypass Stack) Transportation | 2008-01-31 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Bypass Stack 1PF1625W42A07.1T (HRSG #12 Bypass Stack) Transportation | Activity | 1PF1625W42A07.1T | (HRSG #12 Bypass Stack) Transportation | 2008-01-31 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1968 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Bypass Stack | 1CF1625W42A08.1 | (HRSG #12 Bypass Stack) Installation | (HRSG #12 Bypass Stack) Installation | 2008-03-31 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Bypass Stack 1CF1625W42A08.1 (HRSG #12 Bypass Stack) Installation | Activity | 1CF1625W42A08.1 | (HRSG #12 Bypass Stack) Installation | 2008-03-31 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1969 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Bypass Stack | 1PF1625W42A11.1T | (HRSG #12 Bypass Stack Silencer) Transportation | (HRSG #12 Bypass Stack Silencer) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Bypass Stack 1PF1625W42A11.1T (HRSG #12 Bypass Stack Silencer) Transportation | Activity | 1PF1625W42A11.1T | (HRSG #12 Bypass Stack Silencer) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1970 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Bypass Stack | 1CF1625W42A12.1 | (HRSG #12 Bypass Stack Silencer) Installation | (HRSG #12 Bypass Stack Silencer) Installation | 2008-05-31 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Bypass Stack 1CF1625W42A12.1 (HRSG #12 Bypass Stack Silencer) Installation | Activity | 1CF1625W42A12.1 | (HRSG #12 Bypass Stack Silencer) Installation | 2008-05-31 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1972 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Main Stack | 1EF1625W42A05.2 | (HRSG #12 Main Stack) MPS Issue | (HRSG #12 Main Stack) MPS Issue |  | 2007-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Main Stack 1EF1625W42A05.2 (HRSG #12 Main Stack) MPS Issue | Activity | 1EF1625W42A05.2 | (HRSG #12 Main Stack) MPS Issue |  | 2007-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1973 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Main Stack | 1EF1625W42A01.2 | (HRSG #12 Main Stack) Design | (HRSG #12 Main Stack) Design | 2007-04-17 | 2007-10-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Main Stack 1EF1625W42A01.2 (HRSG #12 Main Stack) Design | Activity | 1EF1625W42A01.2 | (HRSG #12 Main Stack) Design | 2007-04-17 00:00:00 | 2007-10-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1974 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Main Stack | 1EF1625W42A09.2 | (HRSG #12 Main Stack Silencer) MPS Issue | (HRSG #12 Main Stack Silencer) MPS Issue |  | 2007-04-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Main Stack 1EF1625W42A09.2 (HRSG #12 Main Stack Silencer) MPS Issue | Activity | 1EF1625W42A09.2 | (HRSG #12 Main Stack Silencer) MPS Issue |  | 2007-04-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1975 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Main Stack | 1EF1625W00A02.2 | (HRSG #12 Main Stack) GA & Load Data to Civil Design | (HRSG #12 Main Stack) GA & Load Data to Civil Design | 2007-06-05 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Main Stack 1EF1625W00A02.2 (HRSG #12 Main Stack) GA & Load Data to Civil Design | Activity | 1EF1625W00A02.2 | (HRSG #12 Main Stack) GA & Load Data to Civil Design | 2007-06-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1976 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Main Stack | 1PF1625W42A10.2P | (HRSG #12 Main Stack Silencer) P.O & Procurement | (HRSG #12 Main Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Main Stack 1PF1625W42A10.2P (HRSG #12 Main Stack Silencer) P.O & Procurement | Activity | 1PF1625W42A10.2P | (HRSG #12 Main Stack Silencer) P.O & Procurement | 2007-06-13 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1977 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Main Stack | 1PF1625W42A06.2P | (HRSG #12 Main Stack) P.O & Procurement | (HRSG #12 Main Stack) P.O & Procurement | 2007-07-18 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Main Stack 1PF1625W42A06.2P (HRSG #12 Main Stack) P.O & Procurement | Activity | 1PF1625W42A06.2P | (HRSG #12 Main Stack) P.O & Procurement | 2007-07-18 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1978 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Main Stack | 1EF1625W16A03.2 | (HRSG #12 Main Stack) FDN Design | (HRSG #12 Main Stack) FDN Design | 2007-09-07 | 2008-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Main Stack 1EF1625W16A03.2 (HRSG #12 Main Stack) FDN Design | Activity | 1EF1625W16A03.2 | (HRSG #12 Main Stack) FDN Design | 2007-09-07 00:00:00 | 2008-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1979 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Main Stack | 1CF1625W16A04.2 | (HRSG #12 Main Stack) FDN Work | (HRSG #12 Main Stack) FDN Work | 2008-01-16 | 2008-04-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Main Stack 1CF1625W16A04.2 (HRSG #12 Main Stack) FDN Work | Activity | 1CF1625W16A04.2 | (HRSG #12 Main Stack) FDN Work | 2008-01-16 00:00:00 | 2008-04-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1980 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Main Stack | 1PF1625W42A07.2T | (HRSG #12 Main Stack) Transportation | (HRSG #12 Main Stack) Transportation | 2008-03-18 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Main Stack 1PF1625W42A07.2T (HRSG #12 Main Stack) Transportation | Activity | 1PF1625W42A07.2T | (HRSG #12 Main Stack) Transportation | 2008-03-18 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1981 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Main Stack | 1PF1625W42A11.2T | (HRSG #12 Main Stack Silencer) Transportation | (HRSG #12 Main Stack Silencer) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Main Stack 1PF1625W42A11.2T (HRSG #12 Main Stack Silencer) Transportation | Activity | 1PF1625W42A11.2T | (HRSG #12 Main Stack Silencer) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1982 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Main Stack | 1CF1625W42A08.2 | (HRSG #12 Main Stack) Installation | (HRSG #12 Main Stack) Installation | 2008-11-14 | 2009-01-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Main Stack 1CF1625W42A08.2 (HRSG #12 Main Stack) Installation | Activity | 1CF1625W42A08.2 | (HRSG #12 Main Stack) Installation | 2008-11-14 00:00:00 | 2009-01-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1983 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Main Stack | 1CF1625W42A12.2 | (HRSG #12 Main Stack Silencer) Installation | (HRSG #12 Main Stack Silencer) Installation | 2009-01-22 | 2009-02-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Main Stack 1CF1625W42A12.2 (HRSG #12 Main Stack Silencer) Installation | Activity | 1CF1625W42A12.2 | (HRSG #12 Main Stack Silencer) Installation | 2009-01-22 00:00:00 | 2009-02-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1985 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Piping Work | 1EF1650W52A01.1 | (HRSG #12 Insulation) MPS Issue | (HRSG #12 Insulation) MPS Issue |  | 2007-11-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Piping Work 1EF1650W52A01.1 (HRSG #12 Insulation) MPS Issue | Activity | 1EF1650W52A01.1 | (HRSG #12 Insulation) MPS Issue |  | 2007-11-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1986 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Piping Work | 1PF1650W52A02.1P | (HRSG #12 Insulation) P.O & Procurement | (HRSG #12 Insulation) P.O & Procurement | 2008-01-09 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Piping Work 1PF1650W52A02.1P (HRSG #12 Insulation) P.O & Procurement | Activity | 1PF1650W52A02.1P | (HRSG #12 Insulation) P.O & Procurement | 2008-01-09 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1987 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Piping Work | 1CF1640W58A05.1 | (HRSG #12) Piping Work | (HRSG #12) Piping Work | 2008-10-01 | 2008-12-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Piping Work 1CF1640W58A05.1 (HRSG #12) Piping Work | Activity | 1CF1640W58A05.1 | (HRSG #12) Piping Work | 2008-10-01 00:00:00 | 2008-12-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1988 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Piping Work | 1PF1650W52A03.1T | (HRSG #12 Insulation) Transportation | (HRSG #12 Insulation) Transportation | 2008-10-01 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Piping Work 1PF1650W52A03.1T (HRSG #12 Insulation) Transportation | Activity | 1PF1650W52A03.1T | (HRSG #12 Insulation) Transportation | 2008-10-01 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1989 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Piping Work | 1CF1640W62A06.1 | (HRSG #12) Hydro Test | (HRSG #12) Hydro Test | 2008-12-20 | 2009-01-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Piping Work 1CF1640W62A06.1 (HRSG #12) Hydro Test | Activity | 1CF1640W62A06.1 | (HRSG #12) Hydro Test | 2008-12-20 00:00:00 | 2009-01-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1990 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Piping Work | 1CF1650W52A04.1 | (HRSG #12 Insulation) Installation | (HRSG #12 Insulation) Installation | 2009-01-03 | 2009-02-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Piping Work 1CF1650W52A04.1 (HRSG #12 Insulation) Installation | Activity | 1CF1650W52A04.1 | (HRSG #12 Insulation) Installation | 2009-01-03 00:00:00 | 2009-02-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1991 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Piping Work | 1CF1640W60A07.1 | (HRSG #12)Acid Cleaning | (HRSG #12)Acid Cleaning | 2009-01-14 | 2009-02-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Piping Work 1CF1640W60A07.1 (HRSG #12)Acid Cleaning | Activity | 1CF1640W60A07.1 | (HRSG #12)Acid Cleaning | 2009-01-14 00:00:00 | 2009-02-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1993 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | CEMS | 1EF1660W86A03.1 | (CEMS) MPS Issue | (CEMS) MPS Issue |  | 2007-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 CEMS 1EF1660W86A03.1 (CEMS) MPS Issue | Activity | 1EF1660W86A03.1 | (CEMS) MPS Issue |  | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1994 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | CEMS | 1PF1660W86A04.1P | (CEMS) P.O & Procurement | (CEMS) P.O & Procurement | 2007-08-29 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 CEMS 1PF1660W86A04.1P (CEMS) P.O & Procurement | Activity | 1PF1660W86A04.1P | (CEMS) P.O & Procurement | 2007-08-29 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1995 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | CEMS | 1EF1660W16A01.1 | (CEMS) FDN Design | (CEMS) FDN Design | 2007-10-30 | 2008-01-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 CEMS 1EF1660W16A01.1 (CEMS) FDN Design | Activity | 1EF1660W16A01.1 | (CEMS) FDN Design | 2007-10-30 00:00:00 | 2008-01-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1996 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | CEMS | 1CF1660W16A02.1 | (CEMS) FDN Work | (CEMS) FDN Work | 2008-01-26 | 2008-03-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 CEMS 1CF1660W16A02.1 (CEMS) FDN Work | Activity | 1CF1660W16A02.1 | (CEMS) FDN Work | 2008-01-26 00:00:00 | 2008-03-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1997 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | CEMS | 1PF1660W86A05.1T | (CEMS) Transportation | (CEMS) Transportation | 2008-04-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 CEMS 1PF1660W86A05.1T (CEMS) Transportation | Activity | 1PF1660W86A05.1T | (CEMS) Transportation | 2008-04-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1998 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | CEMS | 1CF1660W86A06.1 | (CEMS) Installation(incl. Elec, I&C) | (CEMS) Installation(incl. Elec, I&C) | 2008-06-14 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 CEMS 1CF1660W86A06.1 (CEMS) Installation(incl. Elec, I&C) | Activity | 1CF1660W86A06.1 | (CEMS) Installation(incl. Elec, I&C) | 2008-06-14 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 1999 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | CEMS | 1CF1660W86A07.1 | (CEMS) Loop Test | (CEMS) Loop Test | 2008-07-01 | 2008-07-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 CEMS 1CF1660W86A07.1 (CEMS) Loop Test | Activity | 1CF1660W86A07.1 | (CEMS) Loop Test | 2008-07-01 00:00:00 | 2008-07-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2000 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | CEMS | 1SF1660W62A08.1 | (HRSG #12) CEMS Function Test for GT #11(Bypass stack) | (HRSG #12) CEMS Function Test for GT #11(Bypass stack) | 2008-08-05 | 2008-08-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 CEMS 1SF1660W62A08.1 (HRSG #12) CEMS Function Test for GT #11(Bypass stack) | Activity | 1SF1660W62A08.1 | (HRSG #12) CEMS Function Test for GT #11(Bypass stack) | 2008-08-05 00:00:00 | 2008-08-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2002 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1EF1660W70A01.1 | (HRSG #12 ELEC Vendor Equip) MPS Issue | (HRSG #12 ELEC Vendor Equip) MPS Issue |  | 2007-06-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1EF1660W70A01.1 (HRSG #12 ELEC Vendor Equip) MPS Issue | Activity | 1EF1660W70A01.1 | (HRSG #12 ELEC Vendor Equip) MPS Issue |  | 2007-06-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2003 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1EF1660W86A06.1 | (HRSG #12 I&C Vendor Equip) MPS Issue | (HRSG #12 I&C Vendor Equip) MPS Issue |  | 2007-06-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1EF1660W86A06.1 (HRSG #12 I&C Vendor Equip) MPS Issue | Activity | 1EF1660W86A06.1 | (HRSG #12 I&C Vendor Equip) MPS Issue |  | 2007-06-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2004 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1EF1665W42A11.1 | (HRSG #12 MECH Vendor Equip) MPS Issue | (HRSG #12 MECH Vendor Equip) MPS Issue |  | 2007-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1EF1665W42A11.1 (HRSG #12 MECH Vendor Equip) MPS Issue | Activity | 1EF1665W42A11.1 | (HRSG #12 MECH Vendor Equip) MPS Issue |  | 2007-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2005 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1PF1665W42A12.1P | (HRSG #12 MECH Vendor Equip) P.O & Procurement | (HRSG #12 MECH Vendor Equip) P.O & Procurement | 2007-09-10 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1PF1665W42A12.1P (HRSG #12 MECH Vendor Equip) P.O & Procurement | Activity | 1PF1665W42A12.1P | (HRSG #12 MECH Vendor Equip) P.O & Procurement | 2007-09-10 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2006 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1PF1660W70A02.1P | (HRSG #12 ELEC Vendor Equip) P.O & Procurement | (HRSG #12 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1PF1660W70A02.1P (HRSG #12 ELEC Vendor Equip) P.O & Procurement | Activity | 1PF1660W70A02.1P | (HRSG #12 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2007 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1PF1660W86A07.1P | (HRSG #12 I&C Vendor Equip) P.O & Procurement | (HRSG #12 I&C Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1PF1660W86A07.1P (HRSG #12 I&C Vendor Equip) P.O & Procurement | Activity | 1PF1660W86A07.1P | (HRSG #12 I&C Vendor Equip) P.O & Procurement | 2007-10-02 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2008 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1PF1665W42A13.1T | (HRSG #12 MECH Vendor Equip) Transportation | (HRSG #12 MECH Vendor Equip) Transportation | 2008-08-02 | 2008-09-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1PF1665W42A13.1T (HRSG #12 MECH Vendor Equip) Transportation | Activity | 1PF1665W42A13.1T | (HRSG #12 MECH Vendor Equip) Transportation | 2008-08-02 00:00:00 | 2008-09-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2009 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1PF1660W70A03.1T | (HRSG #12 ELEC Vendor Equip) Transportation | (HRSG #12 ELEC Vendor Equip) Transportation | 2008-08-05 | 2008-09-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1PF1660W70A03.1T (HRSG #12 ELEC Vendor Equip) Transportation | Activity | 1PF1660W70A03.1T | (HRSG #12 ELEC Vendor Equip) Transportation | 2008-08-05 00:00:00 | 2008-09-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2010 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1PF1660W86A08.1T | (HRSG #12 I&C Vendor Equip) Transportation | (HRSG #12 I&C Vendor Equip) Transportation | 2008-08-05 | 2008-09-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1PF1660W86A08.1T (HRSG #12 I&C Vendor Equip) Transportation | Activity | 1PF1660W86A08.1T | (HRSG #12 I&C Vendor Equip) Transportation | 2008-08-05 00:00:00 | 2008-09-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2011 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1CF1665W42A14.1 | (HRSG #12 MECH Vendor Equip) Installation | (HRSG #12 MECH Vendor Equip) Installation | 2008-09-17 | 2008-12-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1CF1665W42A14.1 (HRSG #12 MECH Vendor Equip) Installation | Activity | 1CF1665W42A14.1 | (HRSG #12 MECH Vendor Equip) Installation | 2008-09-17 00:00:00 | 2008-12-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2012 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1CF1660W70A04.1 | (HRSG #12 ELEC Vendor Equip) Installation | (HRSG #12 ELEC Vendor Equip) Installation | 2008-09-19 | 2009-01-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1CF1660W70A04.1 (HRSG #12 ELEC Vendor Equip) Installation | Activity | 1CF1660W70A04.1 | (HRSG #12 ELEC Vendor Equip) Installation | 2008-09-19 00:00:00 | 2009-01-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2013 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1CF1660W86A09.1 | (HRSG #12 I&C Vendor Equip) Installation | (HRSG #12 I&C Vendor Equip) Installation | 2008-09-19 | 2009-01-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1CF1660W86A09.1 (HRSG #12 I&C Vendor Equip) Installation | Activity | 1CF1660W86A09.1 | (HRSG #12 I&C Vendor Equip) Installation | 2008-09-19 00:00:00 | 2009-01-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2014 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1CF1655W74A05.1 | (HRSG #12) Installation & Test - Elec. | (HRSG #12) Installation & Test - Elec. | 2008-10-30 | 2009-01-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1CF1655W74A05.1 (HRSG #12) Installation & Test - Elec. | Activity | 1CF1655W74A05.1 | (HRSG #12) Installation & Test - Elec. | 2008-10-30 00:00:00 | 2009-01-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2015 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Auxiliary System | 1CF1660W90A10.1 | (HRSG #12) Installation & Test - I&C | (HRSG #12) Installation & Test - I&C | 2008-10-30 | 2009-01-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Auxiliary System 1CF1660W90A10.1 (HRSG #12) Installation & Test - I&C | Activity | 1CF1660W90A10.1 | (HRSG #12) Installation & Test - I&C | 2008-10-30 00:00:00 | 2009-01-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2017 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Commissioning | 1SF1600W62A01.1 | (HRSG #12) Cold Commissioning for HRSG #11 | (HRSG #12) Cold Commissioning for HRSG #11 | 2009-02-20 | 2009-03-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Commissioning 1SF1600W62A01.1 (HRSG #12) Cold Commissioning for HRSG #11 | Activity | 1SF1600W62A01.1 | (HRSG #12) Cold Commissioning for HRSG #11 | 2009-02-20 00:00:00 | 2009-03-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2018 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > HRSG #11 & #12 > HRSG #12 > Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | HRSG #11 & #12 | HRSG #12 | Commissioning | 1SF1600W62A02.1 | (HRSG #12) Function Test for HRSG #12 | (HRSG #12) Function Test for HRSG #12 | 2009-03-12 | 2009-03-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 HRSG #11 & #12 HRSG #12 Commissioning 1SF1600W62A02.1 (HRSG #12) Function Test for HRSG #12 | Activity | 1SF1600W62A02.1 | (HRSG #12) Function Test for HRSG #12 | 2009-03-12 00:00:00 | 2009-03-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2021 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Building |  | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | (STG #10 BLDG) GA & Load Data to Civil Design | 2007-03-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Building 1EF2010W00A01 (STG #10 BLDG) GA & Load Data to Civil Design | Activity | 1EF2010W00A01 | (STG #10 BLDG) GA & Load Data to Civil Design | 2007-03-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2022 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Building |  | 1EF2010W20A02 | (STG #10 BLDG) Buliding Design | (STG #10 BLDG) Buliding Design | 2007-03-01 | 2007-09-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Building 1EF2010W20A02 (STG #10 BLDG) Buliding Design | Activity | 1EF2010W20A02 | (STG #10 BLDG) Buliding Design | 2007-03-01 00:00:00 | 2007-09-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2023 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Building |  | 1PF2010W20A04P | (STG #10 BLDG) P.O & Procurement - Structure Work(S/S) | (STG #10 BLDG) P.O & Procurement - Structure Work(S/S) | 2007-09-19 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Building 1PF2010W20A04P (STG #10 BLDG) P.O & Procurement - Structure Work(S/S) | Activity | 1PF2010W20A04P | (STG #10 BLDG) P.O & Procurement - Structure Work(S/S) | 2007-09-19 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2024 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Building |  | 1CF2010W16A03 | (STG #10 BLDG) FDN Work | (STG #10 BLDG) FDN Work | 2007-11-02 | 2008-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Building 1CF2010W16A03 (STG #10 BLDG) FDN Work | Activity | 1CF2010W16A03 | (STG #10 BLDG) FDN Work | 2007-11-02 00:00:00 | 2008-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2025 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Building |  | 1PF2010W20A05T | (STG #10 BLDG) Transportation - Structure Work(S/S) | (STG #10 BLDG) Transportation - Structure Work(S/S) | 2008-02-01 | 2008-03-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Building 1PF2010W20A05T (STG #10 BLDG) Transportation - Structure Work(S/S) | Activity | 1PF2010W20A05T | (STG #10 BLDG) Transportation - Structure Work(S/S) | 2008-02-01 00:00:00 | 2008-03-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2026 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Building |  | 1CF2010W20A06 | (STG #10 BLDG) Structure Work(S/S) | (STG #10 BLDG) Structure Work(S/S) | 2008-03-17 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Building 1CF2010W20A06 (STG #10 BLDG) Structure Work(S/S) | Activity | 1CF2010W20A06 | (STG #10 BLDG) Structure Work(S/S) | 2008-03-17 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2027 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Building |  | 1CF2010W20A07 | (STG #10 BLDG) Cladding Work | (STG #10 BLDG) Cladding Work | 2008-05-26 | 2008-10-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Building 1CF2010W20A07 (STG #10 BLDG) Cladding Work | Activity | 1CF2010W20A07 | (STG #10 BLDG) Cladding Work | 2008-05-26 00:00:00 | 2008-10-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2028 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Building |  | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | (STG #10 BLDG) Roof Work | 2008-08-05 | 2008-11-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Building 1CF2010W20A08 (STG #10 BLDG) Roof Work | Activity | 1CF2010W20A08 | (STG #10 BLDG) Roof Work | 2008-08-05 00:00:00 | 2008-11-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2029 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Building |  | 1CF2010W36A10 | (STG #10 BLDG) Installation & Test - HVAC | (STG #10 BLDG) Installation & Test - HVAC | 2008-10-13 | 2008-12-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Building 1CF2010W36A10 (STG #10 BLDG) Installation & Test - HVAC | Activity | 1CF2010W36A10 | (STG #10 BLDG) Installation & Test - HVAC | 2008-10-13 00:00:00 | 2008-12-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2030 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Building |  | 1CF2010W74A11 | (STG #10 BLDG) Installation & Test - Elec | (STG #10 BLDG) Installation & Test - Elec | 2008-10-13 | 2009-01-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Building 1CF2010W74A11 (STG #10 BLDG) Installation & Test - Elec | Activity | 1CF2010W74A11 | (STG #10 BLDG) Installation & Test - Elec | 2008-10-13 00:00:00 | 2009-01-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2031 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Building |  | 1CF2010W90A12 | (STG #10 BLDG) Installation & Test - I&C | (STG #10 BLDG) Installation & Test - I&C | 2008-10-13 | 2009-01-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Building 1CF2010W90A12 (STG #10 BLDG) Installation & Test - I&C | Activity | 1CF2010W90A12 | (STG #10 BLDG) Installation & Test - I&C | 2008-10-13 00:00:00 | 2009-01-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2032 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Building |  | 1CF2010W38A09 | (STG #10 BLDG) Installation & Test - Fire Fighting Sys. | (STG #10 BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Building 1CF2010W38A09 (STG #10 BLDG) Installation & Test - Fire Fighting Sys. | Activity | 1CF2010W38A09 | (STG #10 BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2034 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Unit Step-up Transformer |  | 1EF6500W70A06 | (STG #10 & UST Shelter) MPS Issue - Main TR | (STG #10 & UST Shelter) MPS Issue - Main TR |  | 2007-03-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Unit Step-up Transformer 1EF6500W70A06 (STG #10 & UST Shelter) MPS Issue - Main TR | Activity | 1EF6500W70A06 | (STG #10 & UST Shelter) MPS Issue - Main TR |  | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2035 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Unit Step-up Transformer |  | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | (STG #10 & UST Shelter) P.O & Procurement - Main TR | 2007-06-29 | 2008-06-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Unit Step-up Transformer 1PF6500W70A07P (STG #10 & UST Shelter) P.O & Procurement - Main TR | Activity | 1PF6500W70A07P | (STG #10 & UST Shelter) P.O & Procurement - Main TR | 2007-06-29 00:00:00 | 2008-06-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2036 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Unit Step-up Transformer |  | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | (STG #10 & UST Shelter) GA & Load Data to Civil Design | 2007-11-28 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Unit Step-up Transformer 1EF6500W00A01 (STG #10 & UST Shelter) GA & Load Data to Civil Design | Activity | 1EF6500W00A01 | (STG #10 & UST Shelter) GA & Load Data to Civil Design | 2007-11-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2037 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Unit Step-up Transformer |  | 1EF6500W16A02 | (STG #10 & UST Shelter) FDN & Firewall Design | (STG #10 & UST Shelter) FDN & Firewall Design | 2007-11-28 | 2008-03-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Unit Step-up Transformer 1EF6500W16A02 (STG #10 & UST Shelter) FDN & Firewall Design | Activity | 1EF6500W16A02 | (STG #10 & UST Shelter) FDN & Firewall Design | 2007-11-28 00:00:00 | 2008-03-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2038 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Unit Step-up Transformer |  | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | (STG #10 & UST Shelter) Structure Design | 2007-11-28 | 2008-03-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Unit Step-up Transformer 1EF6500W32A04 (STG #10 & UST Shelter) Structure Design | Activity | 1EF6500W32A04 | (STG #10 & UST Shelter) Structure Design | 2007-11-28 00:00:00 | 2008-03-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2039 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Unit Step-up Transformer |  | 1CF6500W16A03 | (STG #10 & UST Shelter) FDN Work | (STG #10 & UST Shelter) FDN Work | 2008-03-11 | 2008-06-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Unit Step-up Transformer 1CF6500W16A03 (STG #10 & UST Shelter) FDN Work | Activity | 1CF6500W16A03 | (STG #10 & UST Shelter) FDN Work | 2008-03-11 00:00:00 | 2008-06-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2040 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Unit Step-up Transformer |  | 1CF6500W16A05 | (STG #10 & UST Shelter) Firewall Work | (STG #10 & UST Shelter) Firewall Work | 2008-06-10 | 2008-08-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Unit Step-up Transformer 1CF6500W16A05 (STG #10 & UST Shelter) Firewall Work | Activity | 1CF6500W16A05 | (STG #10 & UST Shelter) Firewall Work | 2008-06-10 00:00:00 | 2008-08-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2041 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Unit Step-up Transformer |  | 1PF6500W70A08T | (STG #10 & UST Shelter) Transportation - Main TR | (STG #10 & UST Shelter) Transportation - Main TR | 2008-06-23 | 2008-08-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Unit Step-up Transformer 1PF6500W70A08T (STG #10 & UST Shelter) Transportation - Main TR | Activity | 1PF6500W70A08T | (STG #10 & UST Shelter) Transportation - Main TR | 2008-06-23 00:00:00 | 2008-08-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2042 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Unit Step-up Transformer |  | 1CF6500W70A09 | (STG #10 & UST Shelter) Installation - Main TR | (STG #10 & UST Shelter) Installation - Main TR | 2008-08-10 | 2008-10-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Unit Step-up Transformer 1CF6500W70A09 (STG #10 & UST Shelter) Installation - Main TR | Activity | 1CF6500W70A09 | (STG #10 & UST Shelter) Installation - Main TR | 2008-08-10 00:00:00 | 2008-10-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2044 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Steam Turbine |  | 1EF2020W00A01 | (ST #10) ST Process Data | (ST #10) ST Process Data | 2007-03-01 | 2007-03-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Steam Turbine 1EF2020W00A01 (ST #10) ST Process Data | Activity | 1EF2020W00A01 | (ST #10) ST Process Data | 2007-03-01 00:00:00 | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2045 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Steam Turbine |  | 1EF2020W00A02 | (ST #10) ST Aux' Steam Consumption Data | (ST #10) ST Aux' Steam Consumption Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Steam Turbine 1EF2020W00A02 (ST #10) ST Aux' Steam Consumption Data | Activity | 1EF2020W00A02 | (ST #10) ST Aux' Steam Consumption Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2046 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Steam Turbine |  | 1EF2020W00A03 | (ST #10) Instrument, Service Air Data | (ST #10) Instrument, Service Air Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Steam Turbine 1EF2020W00A03 (ST #10) Instrument, Service Air Data | Activity | 1EF2020W00A03 | (ST #10) Instrument, Service Air Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2047 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Steam Turbine |  | 1EF2020W00A04 | (ST #10) Utility Consumption Data | (ST #10) Utility Consumption Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Steam Turbine 1EF2020W00A04 (ST #10) Utility Consumption Data | Activity | 1EF2020W00A04 | (ST #10) Utility Consumption Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2048 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Steam Turbine |  | 1EF2020W00A05 | (ST #10) Emergency Load Data | (ST #10) Emergency Load Data | 2007-03-01 | 2007-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Steam Turbine 1EF2020W00A05 (ST #10) Emergency Load Data | Activity | 1EF2020W00A05 | (ST #10) Emergency Load Data | 2007-03-01 00:00:00 | 2007-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2049 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Steam Turbine |  | 1EF2020W42A09 | (ST #10) MPS Issue | (ST #10) MPS Issue |  | 2007-03-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Steam Turbine 1EF2020W42A09 (ST #10) MPS Issue | Activity | 1EF2020W42A09 | (ST #10) MPS Issue |  | 2007-03-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2050 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Steam Turbine |  | 1PF2020W42A10P | (ST #10) P.O & Procurement | (ST #10) P.O & Procurement | 2007-03-01 | 2008-09-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Steam Turbine 1PF2020W42A10P (ST #10) P.O & Procurement | Activity | 1PF2020W42A10P | (ST #10) P.O & Procurement | 2007-03-01 00:00:00 | 2008-09-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2051 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Steam Turbine |  | 1EF2020W16A06 | (ST #10) FDN Design | (ST #10) FDN Design | 2007-07-03 | 2007-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Steam Turbine 1EF2020W16A06 (ST #10) FDN Design | Activity | 1EF2020W16A06 | (ST #10) FDN Design | 2007-07-03 00:00:00 | 2007-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2052 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Steam Turbine |  | 1CF2020W16A07 | (ST #10) FDN Work | (ST #10) FDN Work | 2007-11-02 | 2008-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Steam Turbine 1CF2020W16A07 (ST #10) FDN Work | Activity | 1CF2020W16A07 | (ST #10) FDN Work | 2007-11-02 00:00:00 | 2008-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2053 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Steam Turbine |  | 1CF2020W16A08 | (ST #10) Pedestal & Top Slab Work | (ST #10) Pedestal & Top Slab Work | 2008-03-04 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Steam Turbine 1CF2020W16A08 (ST #10) Pedestal & Top Slab Work | Activity | 1CF2020W16A08 | (ST #10) Pedestal & Top Slab Work | 2008-03-04 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2054 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Steam Turbine |  | 1PF2020W42A11T | (ST #10) Transportation | (ST #10) Transportation | 2008-09-02 | 2008-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Steam Turbine 1PF2020W42A11T (ST #10) Transportation | Activity | 1PF2020W42A11T | (ST #10) Transportation | 2008-09-02 00:00:00 | 2008-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2055 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Steam Turbine |  | 1CF2020W42A12 | (ST #10) Installation | (ST #10) Installation | 2008-10-17 | 2009-03-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Steam Turbine 1CF2020W42A12 (ST #10) Installation | Activity | 1CF2020W42A12 | (ST #10) Installation | 2008-10-17 00:00:00 | 2009-03-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2057 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | ST Generator |  | 1EF2040W42A01 | (STG #10) MPS Issue | (STG #10) MPS Issue |  | 2007-03-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 ST Generator 1EF2040W42A01 (STG #10) MPS Issue | Activity | 1EF2040W42A01 | (STG #10) MPS Issue |  | 2007-03-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2058 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | ST Generator |  | 1PF2040W42A02P | (STG #10) P.O & Procurement | (STG #10) P.O & Procurement | 2007-03-01 | 2008-09-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 ST Generator 1PF2040W42A02P (STG #10) P.O & Procurement | Activity | 1PF2040W42A02P | (STG #10) P.O & Procurement | 2007-03-01 00:00:00 | 2008-09-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2059 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | ST Generator |  | 1PF2040W42A03T | (STG #10) Transportation | (STG #10) Transportation | 2008-09-02 | 2008-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 ST Generator 1PF2040W42A03T (STG #10) Transportation | Activity | 1PF2040W42A03T | (STG #10) Transportation | 2008-09-02 00:00:00 | 2008-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2060 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > ST Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | ST Generator |  | 1CF2040W42A04 | (STG #10) Installation | (STG #10) Installation | 2008-10-17 | 2009-02-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 ST Generator 1CF2040W42A04 (STG #10) Installation | Activity | 1CF2040W42A04 | (STG #10) Installation | 2008-10-17 00:00:00 | 2009-02-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2062 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Auxiliary Equipment |  | 1EF2070W42A03 | (STG #10 Aux. Equip) MPS Issue | (STG #10 Aux. Equip) MPS Issue |  | 2007-03-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Auxiliary Equipment 1EF2070W42A03 (STG #10 Aux. Equip) MPS Issue | Activity | 1EF2070W42A03 | (STG #10 Aux. Equip) MPS Issue |  | 2007-03-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2063 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Auxiliary Equipment |  | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | (STG #10 Aux. Equip) P.O & Procurement | 2007-04-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Auxiliary Equipment 1PF2070W42A04P (STG #10 Aux. Equip) P.O & Procurement | Activity | 1PF2070W42A04P | (STG #10 Aux. Equip) P.O & Procurement | 2007-04-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2064 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Auxiliary Equipment |  | 1EF2070W16A01 | (STG #10 Aux. Equip) FDN Design | (STG #10 Aux. Equip) FDN Design | 2007-12-24 | 2008-05-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Auxiliary Equipment 1EF2070W16A01 (STG #10 Aux. Equip) FDN Design | Activity | 1EF2070W16A01 | (STG #10 Aux. Equip) FDN Design | 2007-12-24 00:00:00 | 2008-05-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2065 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Auxiliary Equipment |  | 1CF2070W16A02 | (STG #10 Aux. Equip) FDN Work | (STG #10 Aux. Equip) FDN Work | 2008-05-22 | 2008-08-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Auxiliary Equipment 1CF2070W16A02 (STG #10 Aux. Equip) FDN Work | Activity | 1CF2070W16A02 | (STG #10 Aux. Equip) FDN Work | 2008-05-22 00:00:00 | 2008-08-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2066 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Auxiliary Equipment |  | 1PF2070W42A05T | (STG #10 Aux. Equip) Transportation | (STG #10 Aux. Equip) Transportation | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Auxiliary Equipment 1PF2070W42A05T (STG #10 Aux. Equip) Transportation | Activity | 1PF2070W42A05T | (STG #10 Aux. Equip) Transportation | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2067 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | STG Auxiliary Equipment |  | 1CF2070W42A06 | (STG #10 Aux. Equip) Installation | (STG #10 Aux. Equip) Installation | 2008-09-16 | 2009-01-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 STG Auxiliary Equipment 1CF2070W42A06 (STG #10 Aux. Equip) Installation | Activity | 1CF2070W42A06 | (STG #10 Aux. Equip) Installation | 2008-09-16 00:00:00 | 2009-01-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2069 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Piping & Etc. | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Piping & Etc. |  | 1CF2035W58A01 | (ST #10) Piping Work | (ST #10) Piping Work | 2008-08-11 | 2009-01-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Piping & Etc. 1CF2035W58A01 (ST #10) Piping Work | Activity | 1CF2035W58A01 | (ST #10) Piping Work | 2008-08-11 00:00:00 | 2009-01-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2070 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Piping & Etc. | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Piping & Etc. |  | 1CF2060W74A03 | (ST #10) Installation & Test - Elec. | (ST #10) Installation & Test - Elec. | 2008-11-18 | 2009-02-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Piping & Etc. 1CF2060W74A03 (ST #10) Installation & Test - Elec. | Activity | 1CF2060W74A03 | (ST #10) Installation & Test - Elec. | 2008-11-18 00:00:00 | 2009-02-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2071 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Piping & Etc. | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Piping & Etc. |  | 1CF2065W90A04 | (ST #10) Installation & Test - I&C | (ST #10) Installation & Test - I&C | 2008-11-18 | 2009-02-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Piping & Etc. 1CF2065W90A04 (ST #10) Installation & Test - I&C | Activity | 1CF2065W90A04 | (ST #10) Installation & Test - I&C | 2008-11-18 00:00:00 | 2009-02-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2072 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Piping & Etc. | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Piping & Etc. |  | 1CF2035W62A02 | (ST #10) Hydro Test | (ST #10) Hydro Test | 2009-01-12 | 2009-02-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Piping & Etc. 1CF2035W62A02 (ST #10) Hydro Test | Activity | 1CF2035W62A02 | (ST #10) Hydro Test | 2009-01-12 00:00:00 | 2009-02-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2074 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Lube Oil System |  | 1EF2030W42A03 | (Lube Oil Sys.) MPS Issue | (Lube Oil Sys.) MPS Issue |  | 2007-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Lube Oil System 1EF2030W42A03 (Lube Oil Sys.) MPS Issue | Activity | 1EF2030W42A03 | (Lube Oil Sys.) MPS Issue |  | 2007-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2075 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Lube Oil System |  | 1PF2030W42A04P | (Lube Oil Sys.) P.O & Procurement | (Lube Oil Sys.) P.O & Procurement | 2007-07-31 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Lube Oil System 1PF2030W42A04P (Lube Oil Sys.) P.O & Procurement | Activity | 1PF2030W42A04P | (Lube Oil Sys.) P.O & Procurement | 2007-07-31 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2076 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Lube Oil System |  | 1EF2030W16A01 | (Lube Oil Sys.) FDN Design | (Lube Oil Sys.) FDN Design | 2007-10-23 | 2008-01-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Lube Oil System 1EF2030W16A01 (Lube Oil Sys.) FDN Design | Activity | 1EF2030W16A01 | (Lube Oil Sys.) FDN Design | 2007-10-23 00:00:00 | 2008-01-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2077 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Lube Oil System |  | 1CF2030W16A02 | (Lube Oil Sys.) FDN Work | (Lube Oil Sys.) FDN Work | 2008-01-23 | 2008-05-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Lube Oil System 1CF2030W16A02 (Lube Oil Sys.) FDN Work | Activity | 1CF2030W16A02 | (Lube Oil Sys.) FDN Work | 2008-01-23 00:00:00 | 2008-05-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2078 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Lube Oil System |  | 1PF2030W42A05T | (Lube Oil Sys.) Transportation | (Lube Oil Sys.) Transportation | 2008-07-31 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Lube Oil System 1PF2030W42A05T (Lube Oil Sys.) Transportation | Activity | 1PF2030W42A05T | (Lube Oil Sys.) Transportation | 2008-07-31 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2079 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Lube Oil System |  | 1CF2030W42A06 | (Lube Oil Sys.) Equipment Installation | (Lube Oil Sys.) Equipment Installation | 2008-09-15 | 2008-10-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Lube Oil System 1CF2030W42A06 (Lube Oil Sys.) Equipment Installation | Activity | 1CF2030W42A06 | (Lube Oil Sys.) Equipment Installation | 2008-09-15 00:00:00 | 2008-10-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2080 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Lube Oil System |  | 1CF2030W58A07 | (Lube Oil Sys.) Pipe Installation | (Lube Oil Sys.) Pipe Installation | 2008-10-31 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Lube Oil System 1CF2030W58A07 (Lube Oil Sys.) Pipe Installation | Activity | 1CF2030W58A07 | (Lube Oil Sys.) Pipe Installation | 2008-10-31 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2081 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Lube Oil System |  | 1CF2030W62A08 | (Lube Oil Sys.) Lube oil flushing | (Lube Oil Sys.) Lube oil flushing | 2009-01-16 | 2009-02-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Lube Oil System 1CF2030W62A08 (Lube Oil Sys.) Lube oil flushing | Activity | 1CF2030W62A08 | (Lube Oil Sys.) Lube oil flushing | 2009-01-16 00:00:00 | 2009-02-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2082 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Lube Oil System |  | 1CF2030W58A09 | (Lube Oil Sys.) Remove Temp. Pipe | (Lube Oil Sys.) Remove Temp. Pipe | 2009-02-14 | 2009-02-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Lube Oil System 1CF2030W58A09 (Lube Oil Sys.) Remove Temp. Pipe | Activity | 1CF2030W58A09 | (Lube Oil Sys.) Remove Temp. Pipe | 2009-02-14 00:00:00 | 2009-02-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2084 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Test & Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Test & Commissioning |  | 1SF2000W62A02 | (ST #10) Pre-Commissioning | (ST #10) Pre-Commissioning | 2009-02-27 | 2009-03-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Test & Commissioning 1SF2000W62A02 (ST #10) Pre-Commissioning | Activity | 1SF2000W62A02 | (ST #10) Pre-Commissioning | 2009-02-27 00:00:00 | 2009-03-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2085 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Test & Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Test & Commissioning |  | 1SF2000W62A01 | (ST #10) Aux. Equipment Function Test | (ST #10) Aux. Equipment Function Test | 2009-03-09 | 2009-03-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Test & Commissioning 1SF2000W62A01 (ST #10) Aux. Equipment Function Test | Activity | 1SF2000W62A01 | (ST #10) Aux. Equipment Function Test | 2009-03-09 00:00:00 | 2009-03-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2086 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Steam Turbine & Generator #10 > Test & Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Steam Turbine & Generator #10 | Test & Commissioning |  | 1SF2000W62A03 | (ST #10) Turnning Gear Operation | (ST #10) Turnning Gear Operation | 2009-03-29 | 2009-03-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Steam Turbine & Generator #10 Test & Commissioning 1SF2000W62A03 (ST #10) Turnning Gear Operation | Activity | 1SF2000W62A03 | (ST #10) Turnning Gear Operation | 2009-03-29 00:00:00 | 2009-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2088 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9035W62A01 | (Comm'g) Steam Blowing | (Comm'g) Steam Blowing | 2009-03-31 | 2009-04-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9035W62A01 (Comm'g) Steam Blowing | Activity | 1SF9035W62A01 | (Comm'g) Steam Blowing | 2009-03-31 00:00:00 | 2009-04-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2089 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1CF9035W62A02 | (Comm'g) Temporary Piping Restoration | (Comm'g) Temporary Piping Restoration | 2009-04-20 | 2009-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1CF9035W62A02 (Comm'g) Temporary Piping Restoration | Activity | 1CF9035W62A02 | (Comm'g) Temporary Piping Restoration | 2009-04-20 00:00:00 | 2009-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2090 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9035W62A03 | (Comm'g) Bypass Operation | (Comm'g) Bypass Operation | 2009-04-30 | 2009-05-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9035W62A03 (Comm'g) Bypass Operation | Activity | 1SF9035W62A03 | (Comm'g) Bypass Operation | 2009-04-30 00:00:00 | 2009-05-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2091 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9035W62A04 | (Comm'g) Safety & Interlock Test | (Comm'g) Safety & Interlock Test | 2009-05-02 | 2009-05-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9035W62A04 (Comm'g) Safety & Interlock Test | Activity | 1SF9035W62A04 | (Comm'g) Safety & Interlock Test | 2009-05-02 00:00:00 | 2009-05-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2092 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9035W62A05 | (Comm'g) Steam Admission | (Comm'g) Steam Admission | 2009-05-07 | 2009-05-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9035W62A05 (Comm'g) Steam Admission | Activity | 1SF9035W62A05 | (Comm'g) Steam Admission | 2009-05-07 00:00:00 | 2009-05-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2093 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9040W62A06 | (Comm'g) TBN & GEN. Test | (Comm'g) TBN & GEN. Test | 2009-05-09 | 2009-05-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9040W62A06 (Comm'g) TBN & GEN. Test | Activity | 1SF9040W62A06 | (Comm'g) TBN & GEN. Test | 2009-05-09 00:00:00 | 2009-05-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2094 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9040W62A07 | (Comm'g) Synchronization Test | (Comm'g) Synchronization Test | 2009-05-22 | 2009-05-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9040W62A07 (Comm'g) Synchronization Test | Activity | 1SF9040W62A07 | (Comm'g) Synchronization Test | 2009-05-22 00:00:00 | 2009-05-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2095 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9040W62A08 | (Comm'g) Optimaization Test | (Comm'g) Optimaization Test | 2009-05-23 | 2009-06-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9040W62A08 (Comm'g) Optimaization Test | Activity | 1SF9040W62A08 | (Comm'g) Optimaization Test | 2009-05-23 00:00:00 | 2009-06-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2096 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9040W62A09 | (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | 2009-06-10 | 2009-06-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9040W62A09 (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | Activity | 1SF9040W62A09 | (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | 2009-06-10 00:00:00 | 2009-06-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2097 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9040W62A10 | (Comm'g) Outage Period | (Comm'g) Outage Period | 2009-06-10 | 2009-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9040W62A10 (Comm'g) Outage Period | Activity | 1SF9040W62A10 | (Comm'g) Outage Period | 2009-06-10 00:00:00 | 2009-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2098 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9040W62A11 | (Comm'g) APS & Stability Guarantee Test | (Comm'g) APS & Stability Guarantee Test | 2009-06-17 | 2009-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9040W62A11 (Comm'g) APS & Stability Guarantee Test | Activity | 1SF9040W62A11 | (Comm'g) APS & Stability Guarantee Test | 2009-06-17 00:00:00 | 2009-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2099 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9040W62A12 | (Comm'g) Trial Run Test | (Comm'g) Trial Run Test | 2009-07-19 | 2009-07-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9040W62A12 (Comm'g) Trial Run Test | Activity | 1SF9040W62A12 | (Comm'g) Trial Run Test | 2009-07-19 00:00:00 | 2009-07-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2100 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9041W62A14 | (Comm'g) Reliability Test | (Comm'g) Reliability Test | 2009-07-21 | 2009-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9041W62A14 (Comm'g) Reliability Test | Activity | 1SF9041W62A14 | (Comm'g) Reliability Test | 2009-07-21 00:00:00 | 2009-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2101 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9040W62A13 | (Comm'g) Initial Operation Test | (Comm'g) Initial Operation Test | 2009-07-21 | 2009-07-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9040W62A13 (Comm'g) Initial Operation Test | Activity | 1SF9040W62A13 | (Comm'g) Initial Operation Test | 2009-07-21 00:00:00 | 2009-07-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2102 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #1 > Block #1 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #1 | Block #1 Commisssioning |  |  | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | 2009-08-20 | 2009-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #1 Block #1 Commisssioning 1SF9042W62A15 (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | Activity | 1SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | 2009-08-20 00:00:00 | 2009-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2106 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2CF3520W16A01 | (FGSS #21) FDN Work(Misc. Equipment) | (FGSS #21) FDN Work(Misc. Equipment) | 2008-01-01 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2CF3520W16A01 (FGSS #21) FDN Work(Misc. Equipment) | Activity | 2CF3520W16A01 | (FGSS #21) FDN Work(Misc. Equipment) | 2008-01-01 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2107 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2CF3520W16A08 | (FGSS #22) FDN Work(Misc. Equipment) | (FGSS #22) FDN Work(Misc. Equipment) | 2008-01-01 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2CF3520W16A08 (FGSS #22) FDN Work(Misc. Equipment) | Activity | 2CF3520W16A08 | (FGSS #22) FDN Work(Misc. Equipment) | 2008-01-01 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2108 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2CF3520W58A03 | (FGSS #21) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | (FGSS #21) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | 2008-06-19 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2CF3520W58A03 (FGSS #21) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | Activity | 2CF3520W58A03 | (FGSS #21) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | 2008-06-19 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2109 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2CF3520W58A10 | (FGSS #22) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | (FGSS #22) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | 2008-06-19 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2CF3520W58A10 (FGSS #22) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | Activity | 2CF3520W58A10 | (FGSS #22) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | 2008-06-19 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2110 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2CF3520W86A02 | (FGSS #21) ESD Valve Skid installation | (FGSS #21) ESD Valve Skid installation | 2008-06-19 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2CF3520W86A02 (FGSS #21) ESD Valve Skid installation | Activity | 2CF3520W86A02 | (FGSS #21) ESD Valve Skid installation | 2008-06-19 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2111 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2CF3520W86A09 | (FGSS #22) ESD Valve Skid installation | (FGSS #22) ESD Valve Skid installation | 2008-06-19 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2CF3520W86A09 (FGSS #22) ESD Valve Skid installation | Activity | 2CF3520W86A09 | (FGSS #22) ESD Valve Skid installation | 2008-06-19 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2112 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2CF3520W74A04 | (FGSS #21) Installation & Test - Elec. | (FGSS #21) Installation & Test - Elec. | 2008-07-04 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2CF3520W74A04 (FGSS #21) Installation & Test - Elec. | Activity | 2CF3520W74A04 | (FGSS #21) Installation & Test - Elec. | 2008-07-04 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2113 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2CF3520W90A05 | (FGSS #21) Installation & Test - I&C | (FGSS #21) Installation & Test - I&C | 2008-07-04 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2CF3520W90A05 (FGSS #21) Installation & Test - I&C | Activity | 2CF3520W90A05 | (FGSS #21) Installation & Test - I&C | 2008-07-04 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2114 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2CF3520W74A11 | (FGSS #22) Installation & Test - Elec. | (FGSS #22) Installation & Test - Elec. | 2008-07-04 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2CF3520W74A11 (FGSS #22) Installation & Test - Elec. | Activity | 2CF3520W74A11 | (FGSS #22) Installation & Test - Elec. | 2008-07-04 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2115 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2CF3520W90A12 | (FGSS #22) Installation & Test - I&C | (FGSS #22) Installation & Test - I&C | 2008-07-04 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2CF3520W90A12 (FGSS #22) Installation & Test - I&C | Activity | 2CF3520W90A12 | (FGSS #22) Installation & Test - I&C | 2008-07-04 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2116 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2SF3520W62A06 | (FGSS #21) Fuel Gas Receiving | (FGSS #21) Fuel Gas Receiving | 2008-09-21 | 2008-09-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2SF3520W62A06 (FGSS #21) Fuel Gas Receiving | Activity | 2SF3520W62A06 | (FGSS #21) Fuel Gas Receiving | 2008-09-21 00:00:00 | 2008-09-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2117 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2SF3520W62A13 | (FGSS #22) Fuel Gas Receiving | (FGSS #22) Fuel Gas Receiving | 2008-09-21 | 2008-09-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2SF3520W62A13 (FGSS #22) Fuel Gas Receiving | Activity | 2SF3520W62A13 | (FGSS #22) Fuel Gas Receiving | 2008-09-21 00:00:00 | 2008-09-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2118 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2SF3520W62A07.2 | (FGSS #21) Metering System Calibration with supplier | (FGSS #21) Metering System Calibration with supplier | 2008-09-24 | 2008-09-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2SF3520W62A07.2 (FGSS #21) Metering System Calibration with supplier | Activity | 2SF3520W62A07.2 | (FGSS #21) Metering System Calibration with supplier | 2008-09-24 00:00:00 | 2008-09-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2119 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System |  | 2SF3520W62A14 | (FGSS #22) Metering System Calibration with supplier | (FGSS #22) Metering System Calibration with supplier | 2008-09-24 | 2008-09-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System 2SF3520W62A14 (FGSS #22) Metering System Calibration with supplier | Activity | 2SF3520W62A14 | (FGSS #22) Metering System Calibration with supplier | 2008-09-24 00:00:00 | 2008-09-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2121 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | 2007-06-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2EF3520W00A28 (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | Activity | 2EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | 2007-06-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2122 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2EF3520W16A29 | (GT/HRSG GPRS Shelter) FDN Design | (GT/HRSG GPRS Shelter) FDN Design | 2007-06-01 | 2007-10-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2EF3520W16A29 (GT/HRSG GPRS Shelter) FDN Design | Activity | 2EF3520W16A29 | (GT/HRSG GPRS Shelter) FDN Design | 2007-06-01 00:00:00 | 2007-10-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2123 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2EF3520W32A31 | (GT/HRSG GPRS Shelter) Structure Design | (GT/HRSG GPRS Shelter) Structure Design | 2007-06-01 | 2007-10-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2EF3520W32A31 (GT/HRSG GPRS Shelter) Structure Design | Activity | 2EF3520W32A31 | (GT/HRSG GPRS Shelter) Structure Design | 2007-06-01 00:00:00 | 2007-10-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2124 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2PF3520W42A04P | (GPRS) P.O & Procurement for GT | (GPRS) P.O & Procurement for GT | 2007-06-01 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2PF3520W42A04P (GPRS) P.O & Procurement for GT | Activity | 2PF3520W42A04P | (GPRS) P.O & Procurement for GT | 2007-06-01 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2125 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2PF3520W42A14P | (GPRS) P.O & Procurement for HRSG | (GPRS) P.O & Procurement for HRSG | 2007-07-03 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2PF3520W42A14P (GPRS) P.O & Procurement for HRSG | Activity | 2PF3520W42A14P | (GPRS) P.O & Procurement for HRSG | 2007-07-03 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2126 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2EF3520W16A12 | (GPRS) FDN Design for HRSG | (GPRS) FDN Design for HRSG | 2007-07-03 | 2007-11-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2EF3520W16A12 (GPRS) FDN Design for HRSG | Activity | 2EF3520W16A12 | (GPRS) FDN Design for HRSG | 2007-07-03 00:00:00 | 2007-11-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2127 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2EF3520W16A01 | (GPRS) FDN Design for GT | (GPRS) FDN Design for GT | 2007-08-02 | 2007-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2EF3520W16A01 (GPRS) FDN Design for GT | Activity | 2EF3520W16A01 | (GPRS) FDN Design for GT | 2007-08-02 00:00:00 | 2007-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2128 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2CF3520W16A02 | (GPRS) FDN Work for GT | (GPRS) FDN Work for GT | 2007-11-02 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2CF3520W16A02 (GPRS) FDN Work for GT | Activity | 2CF3520W16A02 | (GPRS) FDN Work for GT | 2007-11-02 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2129 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2CF3520W16A13 | (GPRS) FDN Work for HRSG | (GPRS) FDN Work for HRSG | 2007-11-27 | 2008-01-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2CF3520W16A13 (GPRS) FDN Work for HRSG | Activity | 2CF3520W16A13 | (GPRS) FDN Work for HRSG | 2007-11-27 00:00:00 | 2008-01-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2130 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2CF3520W16A30 | (GT/HRSG GPRS Shelter) FDN Work | (GT/HRSG GPRS Shelter) FDN Work | 2007-12-13 | 2008-02-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2CF3520W16A30 (GT/HRSG GPRS Shelter) FDN Work | Activity | 2CF3520W16A30 | (GT/HRSG GPRS Shelter) FDN Work | 2007-12-13 00:00:00 | 2008-02-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2131 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2CF3520W32A32 | (GT/HRSG GPRS Shelter) Structure Work | (GT/HRSG GPRS Shelter) Structure Work | 2008-02-13 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2CF3520W32A32 (GT/HRSG GPRS Shelter) Structure Work | Activity | 2CF3520W32A32 | (GT/HRSG GPRS Shelter) Structure Work | 2008-02-13 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2132 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2PF3520W42A05T | (GPRS) Transportation for GT | (GPRS) Transportation for GT | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2PF3520W42A05T (GPRS) Transportation for GT | Activity | 2PF3520W42A05T | (GPRS) Transportation for GT | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2133 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2PF3520W42A15T | (GPRS) Transportation for HRSG | (GPRS) Transportation for HRSG | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2PF3520W42A15T (GPRS) Transportation for HRSG | Activity | 2PF3520W42A15T | (GPRS) Transportation for HRSG | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2134 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2CF3520W42A06 | (GPRS #21) Installation for GT | (GPRS #21) Installation for GT | 2008-06-16 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2CF3520W42A06 (GPRS #21) Installation for GT | Activity | 2CF3520W42A06 | (GPRS #21) Installation for GT | 2008-06-16 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2135 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2CF3520W42A09 | (GPRS #22) Installation for GT | (GPRS #22) Installation for GT | 2008-06-16 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2CF3520W42A09 (GPRS #22) Installation for GT | Activity | 2CF3520W42A09 | (GPRS #22) Installation for GT | 2008-06-16 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2136 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2CF3520W42A22 | (GPRS #21 for Fuel Change over) Installation | (GPRS #21 for Fuel Change over) Installation | 2008-06-16 | 2008-07-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2CF3520W42A22 (GPRS #21 for Fuel Change over) Installation | Activity | 2CF3520W42A22 | (GPRS #21 for Fuel Change over) Installation | 2008-06-16 00:00:00 | 2008-07-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2137 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2CF3520W42A25 | (GPRS #22 for Fuel Change over) Installation | (GPRS #22 for Fuel Change over) Installation | 2008-06-16 | 2008-07-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2CF3520W42A25 (GPRS #22 for Fuel Change over) Installation | Activity | 2CF3520W42A25 | (GPRS #22 for Fuel Change over) Installation | 2008-06-16 00:00:00 | 2008-07-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2138 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2CF3520W24A33 | (GT/HRSG GPRS Shelter) Shelter Finish | (GT/HRSG GPRS Shelter) Shelter Finish | 2008-07-09 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2CF3520W24A33 (GT/HRSG GPRS Shelter) Shelter Finish | Activity | 2CF3520W24A33 | (GT/HRSG GPRS Shelter) Shelter Finish | 2008-07-09 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2139 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2CF3520W42A16 | (GPRS #21) Installation for HRSG | (GPRS #21) Installation for HRSG | 2008-07-16 | 2008-08-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2CF3520W42A16 (GPRS #21) Installation for HRSG | Activity | 2CF3520W42A16 | (GPRS #21) Installation for HRSG | 2008-07-16 00:00:00 | 2008-08-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2140 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2CF3520W42A19 | (GPRS #22) Installation for HRSG | (GPRS #22) Installation for HRSG | 2008-07-16 | 2008-08-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2CF3520W42A19 (GPRS #22) Installation for HRSG | Activity | 2CF3520W42A19 | (GPRS #22) Installation for HRSG | 2008-07-16 00:00:00 | 2008-08-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2141 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2SF3520W62A23 | (GPRS #21 for Fuel Change over) Loop chek & Motor Solo Test | (GPRS #21 for Fuel Change over) Loop chek & Motor Solo Test | 2008-07-27 | 2008-07-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2SF3520W62A23 (GPRS #21 for Fuel Change over) Loop chek & Motor Solo Test | Activity | 2SF3520W62A23 | (GPRS #21 for Fuel Change over) Loop chek & Motor Solo Test | 2008-07-27 00:00:00 | 2008-07-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2142 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2SF3520W62A26 | (GPRS #22 for Fuel Change over) Loop chek & Motor Solo Test | (GPRS #22 for Fuel Change over) Loop chek & Motor Solo Test | 2008-07-27 | 2008-07-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2SF3520W62A26 (GPRS #22 for Fuel Change over) Loop chek & Motor Solo Test | Activity | 2SF3520W62A26 | (GPRS #22 for Fuel Change over) Loop chek & Motor Solo Test | 2008-07-27 00:00:00 | 2008-07-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2143 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2SF3520W62A24 | (GPRS #21 for Fuel Change over) Function Test | (GPRS #21 for Fuel Change over) Function Test | 2008-07-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2SF3520W62A24 (GPRS #21 for Fuel Change over) Function Test | Activity | 2SF3520W62A24 | (GPRS #21 for Fuel Change over) Function Test | 2008-07-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2144 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2SF3520W62A27 | (GPRS #22 for Fuel Change over) Function Test | (GPRS #22 for Fuel Change over) Function Test | 2008-07-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2SF3520W62A27 (GPRS #22 for Fuel Change over) Function Test | Activity | 2SF3520W62A27 | (GPRS #22 for Fuel Change over) Function Test | 2008-07-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2145 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2SF3520W62A17 | (GPRS #21) Loop chek & Motor Solo Test for HRSG | (GPRS #21) Loop chek & Motor Solo Test for HRSG | 2008-08-27 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2SF3520W62A17 (GPRS #21) Loop chek & Motor Solo Test for HRSG | Activity | 2SF3520W62A17 | (GPRS #21) Loop chek & Motor Solo Test for HRSG | 2008-08-27 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2146 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2SF3520W62A20 | (GPRS #22) Loop chek & Motor Solo Test for HRSG | (GPRS #22) Loop chek & Motor Solo Test for HRSG | 2008-08-27 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2SF3520W62A20 (GPRS #22) Loop chek & Motor Solo Test for HRSG | Activity | 2SF3520W62A20 | (GPRS #22) Loop chek & Motor Solo Test for HRSG | 2008-08-27 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2147 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2SF3520W62A18 | (GPRS #21) Function Test for HRSG | (GPRS #21) Function Test for HRSG | 2008-08-30 | 2008-09-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2SF3520W62A18 (GPRS #21) Function Test for HRSG | Activity | 2SF3520W62A18 | (GPRS #21) Function Test for HRSG | 2008-08-30 00:00:00 | 2008-09-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2148 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2SF3520W62A21 | (GPRS #22) Function Test for HRSG | (GPRS #22) Function Test for HRSG | 2008-08-30 | 2008-09-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2SF3520W62A21 (GPRS #22) Function Test for HRSG | Activity | 2SF3520W62A21 | (GPRS #22) Function Test for HRSG | 2008-08-30 00:00:00 | 2008-09-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2149 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2SF3520W62A07 | (GPRS #21) Loop check for GT | (GPRS #21) Loop check for GT | 2008-08-31 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2SF3520W62A07 (GPRS #21) Loop check for GT | Activity | 2SF3520W62A07 | (GPRS #21) Loop check for GT | 2008-08-31 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2150 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2SF3520W62A10 | (GPRS #22) Loop check for GT | (GPRS #22) Loop check for GT | 2008-08-31 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2SF3520W62A10 (GPRS #22) Loop check for GT | Activity | 2SF3520W62A10 | (GPRS #22) Loop check for GT | 2008-08-31 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2151 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2SF3520W62A08 | (GPRS #21) Function Test for GT | (GPRS #21) Function Test for GT | 2008-09-03 | 2008-09-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2SF3520W62A08 (GPRS #21) Function Test for GT | Activity | 2SF3520W62A08 | (GPRS #21) Function Test for GT | 2008-09-03 00:00:00 | 2008-09-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2152 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 2SF3520W62A11 | (GPRS #22) Function Test for GT | (GPRS #22) Function Test for GT | 2008-09-03 | 2008-09-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 2SF3520W62A11 (GPRS #22) Function Test for GT | Activity | 2SF3520W62A11 | (GPRS #22) Function Test for GT | 2008-09-03 00:00:00 | 2008-09-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2154 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2EF3520W00A10 | (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | 2007-06-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2EF3520W00A10 (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | Activity | 2EF3520W00A10 | (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | 2007-06-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2155 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2EF3520W16A11 | (Filtering/Metering Station Shelter) FDN Design | (Filtering/Metering Station Shelter) FDN Design | 2007-06-01 | 2007-10-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2EF3520W16A11 (Filtering/Metering Station Shelter) FDN Design | Activity | 2EF3520W16A11 | (Filtering/Metering Station Shelter) FDN Design | 2007-06-01 00:00:00 | 2007-10-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2156 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2EF3520W32A13 | (Filtering/Metering Station Shelter) Structure Design | (Filtering/Metering Station Shelter) Structure Design | 2007-06-01 | 2007-10-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2EF3520W32A13 (Filtering/Metering Station Shelter) Structure Design | Activity | 2EF3520W32A13 | (Filtering/Metering Station Shelter) Structure Design | 2007-06-01 00:00:00 | 2007-10-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2157 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2PF3520W42A02.3P | (Filtering/Metering Station) P.O & Procurement | (Filtering/Metering Station) P.O & Procurement | 2007-07-03 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2PF3520W42A02.3P (Filtering/Metering Station) P.O & Procurement | Activity | 2PF3520W42A02.3P | (Filtering/Metering Station) P.O & Procurement | 2007-07-03 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2158 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2CF3520W16A12 | (Filtering/Metering Station Shelter) FDN Work | (Filtering/Metering Station Shelter) FDN Work | 2007-11-15 | 2008-01-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2CF3520W16A12 (Filtering/Metering Station Shelter) FDN Work | Activity | 2CF3520W16A12 | (Filtering/Metering Station Shelter) FDN Work | 2007-11-15 00:00:00 | 2008-01-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2159 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2CF3520W32A14 | (Filtering/Metering Station Shelter) Structure Work | (Filtering/Metering Station Shelter) Structure Work | 2008-01-12 | 2008-03-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2CF3520W32A14 (Filtering/Metering Station Shelter) Structure Work | Activity | 2CF3520W32A14 | (Filtering/Metering Station Shelter) Structure Work | 2008-01-12 00:00:00 | 2008-03-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2160 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2PF3520W42A03.3T | (Filtering/Metering Station) Transportation | (Filtering/Metering Station) Transportation | 2008-05-20 | 2008-07-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2PF3520W42A03.3T (Filtering/Metering Station) Transportation | Activity | 2PF3520W42A03.3T | (Filtering/Metering Station) Transportation | 2008-05-20 00:00:00 | 2008-07-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2161 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2CF3520W42A04.3 | (Filtering/Metering Station #21) Installation | (Filtering/Metering Station #21) Installation | 2008-07-04 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2CF3520W42A04.3 (Filtering/Metering Station #21) Installation | Activity | 2CF3520W42A04.3 | (Filtering/Metering Station #21) Installation | 2008-07-04 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2162 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2CF3520W42A07.3 | (Filtering/Metering Station #22) Installation | (Filtering/Metering Station #22) Installation | 2008-07-04 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2CF3520W42A07.3 (Filtering/Metering Station #22) Installation | Activity | 2CF3520W42A07.3 | (Filtering/Metering Station #22) Installation | 2008-07-04 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2163 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2CF3520W24A15 | (Filtering/Metering Station Shelter) Shelter Finish | (Filtering/Metering Station Shelter) Shelter Finish | 2008-07-19 | 2008-08-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2CF3520W24A15 (Filtering/Metering Station Shelter) Shelter Finish | Activity | 2CF3520W24A15 | (Filtering/Metering Station Shelter) Shelter Finish | 2008-07-19 00:00:00 | 2008-08-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2164 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2SF3520W62A05.3 | (Filtering/Metering Station #21) Loop chek | (Filtering/Metering Station #21) Loop chek | 2008-07-19 | 2008-07-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2SF3520W62A05.3 (Filtering/Metering Station #21) Loop chek | Activity | 2SF3520W62A05.3 | (Filtering/Metering Station #21) Loop chek | 2008-07-19 00:00:00 | 2008-07-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2165 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2SF3520W62A08.3 | (Filtering/Metering Station #22) Loop chek | (Filtering/Metering Station #22) Loop chek | 2008-07-19 | 2008-07-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2SF3520W62A08.3 (Filtering/Metering Station #22) Loop chek | Activity | 2SF3520W62A08.3 | (Filtering/Metering Station #22) Loop chek | 2008-07-19 00:00:00 | 2008-07-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2166 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2SF3520W62A06.3 | (Filtering/Metering Station #21) Function Test | (Filtering/Metering Station #21) Function Test | 2008-07-22 | 2008-07-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2SF3520W62A06.3 (Filtering/Metering Station #21) Function Test | Activity | 2SF3520W62A06.3 | (Filtering/Metering Station #21) Function Test | 2008-07-22 00:00:00 | 2008-07-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2167 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 2SF3520W62A09.3 | (Filtering/Metering Station #22) Function Test | (Filtering/Metering Station #22) Function Test | 2008-07-22 | 2008-07-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 2SF3520W62A09.3 (Filtering/Metering Station #22) Function Test | Activity | 2SF3520W62A09.3 | (Filtering/Metering Station #22) Function Test | 2008-07-22 00:00:00 | 2008-07-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2169 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2EF3520W16A01.2 | (Gas HTR) FDN Design | (Gas HTR) FDN Design | 2007-07-03 | 2007-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2EF3520W16A01.2 (Gas HTR) FDN Design | Activity | 2EF3520W16A01.2 | (Gas HTR) FDN Design | 2007-07-03 00:00:00 | 2007-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2170 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2EF3520W32A03.2 | (Gas HTR) Structure Design | (Gas HTR) Structure Design | 2007-07-03 | 2007-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2EF3520W32A03.2 (Gas HTR) Structure Design | Activity | 2EF3520W32A03.2 | (Gas HTR) Structure Design | 2007-07-03 00:00:00 | 2007-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2171 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2PF3520W42A07.2P | (Gas HTR) P.O & Procurement | (Gas HTR) P.O & Procurement | 2007-07-03 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2PF3520W42A07.2P (Gas HTR) P.O & Procurement | Activity | 2PF3520W42A07.2P | (Gas HTR) P.O & Procurement | 2007-07-03 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2172 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2CF3520W16A02.2 | (Gas HTR) FDN Work | (Gas HTR) FDN Work | 2007-10-02 | 2007-11-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2CF3520W16A02.2 (Gas HTR) FDN Work | Activity | 2CF3520W16A02.2 | (Gas HTR) FDN Work | 2007-10-02 00:00:00 | 2007-11-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2173 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2CF3520W32A04.2 | (Gas HTR) Structure Work | (Gas HTR) Structure Work | 2007-11-29 | 2008-01-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2CF3520W32A04.2 (Gas HTR) Structure Work | Activity | 2CF3520W32A04.2 | (Gas HTR) Structure Work | 2007-11-29 00:00:00 | 2008-01-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2174 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2PF3520W42A08.2T | (Gas HTR) Transportation | (Gas HTR) Transportation | 2008-06-03 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2PF3520W42A08.2T (Gas HTR) Transportation | Activity | 2PF3520W42A08.2T | (Gas HTR) Transportation | 2008-06-03 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2175 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2CF3520W24A05.2 | (Gas HTR) Shelter Finish | (Gas HTR) Shelter Finish | 2008-07-18 | 2008-08-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2CF3520W24A05.2 (Gas HTR) Shelter Finish | Activity | 2CF3520W24A05.2 | (Gas HTR) Shelter Finish | 2008-07-18 00:00:00 | 2008-08-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2176 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2CF3520W42A09.2 | (Gas HTR #21) Installation | (Gas HTR #21) Installation | 2008-07-18 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2CF3520W42A09.2 (Gas HTR #21) Installation | Activity | 2CF3520W42A09.2 | (Gas HTR #21) Installation | 2008-07-18 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2177 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2CF3520W42A12.2 | (Gas HTR #22) Installation | (Gas HTR #22) Installation | 2008-07-18 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2CF3520W42A12.2 (Gas HTR #22) Installation | Activity | 2CF3520W42A12.2 | (Gas HTR #22) Installation | 2008-07-18 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2178 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2SF3520W62A10.2 | (Gas HTR #21) Loop chek | (Gas HTR #21) Loop chek | 2008-08-03 | 2008-08-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2SF3520W62A10.2 (Gas HTR #21) Loop chek | Activity | 2SF3520W62A10.2 | (Gas HTR #21) Loop chek | 2008-08-03 00:00:00 | 2008-08-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2179 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2SF3520W62A13.2 | (Gas HTR #22) Loop chek | (Gas HTR #22) Loop chek | 2008-08-03 | 2008-08-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2SF3520W62A13.2 (Gas HTR #22) Loop chek | Activity | 2SF3520W62A13.2 | (Gas HTR #22) Loop chek | 2008-08-03 00:00:00 | 2008-08-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2180 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2SF3520W62A11.2 | (Gas HTR #21) Function Test | (Gas HTR #21) Function Test | 2008-08-06 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2SF3520W62A11.2 (Gas HTR #21) Function Test | Activity | 2SF3520W62A11.2 | (Gas HTR #21) Function Test | 2008-08-06 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2181 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 2SF3520W62A14.2 | (Gas HTR #22) Function Test | (Gas HTR #22) Function Test | 2008-08-06 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Heater 2SF3520W62A14.2 (Gas HTR #22) Function Test | Activity | 2SF3520W62A14.2 | (Gas HTR #22) Function Test | 2008-08-06 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2183 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2EF3520W00A25.1 | (Gas COMP House) GA & Load Data to Civil Design | (Gas COMP House) GA & Load Data to Civil Design | 2007-03-02 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2EF3520W00A25.1 (Gas COMP House) GA & Load Data to Civil Design | Activity | 2EF3520W00A25.1 | (Gas COMP House) GA & Load Data to Civil Design | 2007-03-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2184 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | (Gas COMP PKG) P.O & Procurement | 2007-03-15 | 2008-05-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2PF3520W42A05.1P (Gas COMP PKG) P.O & Procurement | Activity | 2PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | 2007-03-15 00:00:00 | 2008-05-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2185 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2EF3520W16A26.1 | (Gas COMP House) FDN Design | (Gas COMP House) FDN Design | 2007-04-03 | 2007-09-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2EF3520W16A26.1 (Gas COMP House) FDN Design | Activity | 2EF3520W16A26.1 | (Gas COMP House) FDN Design | 2007-04-03 00:00:00 | 2007-09-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2186 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2EF3520W32A28.1 | (Gas COMP House) Structure Design | (Gas COMP House) Structure Design | 2007-04-03 | 2007-09-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2EF3520W32A28.1 (Gas COMP House) Structure Design | Activity | 2EF3520W32A28.1 | (Gas COMP House) Structure Design | 2007-04-03 00:00:00 | 2007-09-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2187 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2EF3520W16A01.1 | (Gas COMP PKG) FDN Design | (Gas COMP PKG) FDN Design | 2007-08-02 | 2007-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2EF3520W16A01.1 (Gas COMP PKG) FDN Design | Activity | 2EF3520W16A01.1 | (Gas COMP PKG) FDN Design | 2007-08-02 00:00:00 | 2007-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2188 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W16A02.1 | (Gas COMP PKG) FDN Work | (Gas COMP PKG) FDN Work | 2007-11-02 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W16A02.1 (Gas COMP PKG) FDN Work | Activity | 2CF3520W16A02.1 | (Gas COMP PKG) FDN Work | 2007-11-02 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2189 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W16A27.1 | (Gas COMP House) FDN Work | (Gas COMP House) FDN Work | 2007-11-03 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W16A27.1 (Gas COMP House) FDN Work | Activity | 2CF3520W16A27.1 | (Gas COMP House) FDN Work | 2007-11-03 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2190 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W32A29.1 | (Gas COMP House) Structure Work | (Gas COMP House) Structure Work | 2008-01-01 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W32A29.1 (Gas COMP House) Structure Work | Activity | 2CF3520W32A29.1 | (Gas COMP House) Structure Work | 2008-01-01 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2191 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2PF3520W42A06.1T | (Gas COMP PKG)Transportation | (Gas COMP PKG)Transportation | 2008-05-15 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2PF3520W42A06.1T (Gas COMP PKG)Transportation | Activity | 2PF3520W42A06.1T | (Gas COMP PKG)Transportation | 2008-05-15 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2192 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W42A07.1 | (Gas COMP PKG #21) Installation_Gas Compressor | (Gas COMP PKG #21) Installation_Gas Compressor | 2008-06-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W42A07.1 (Gas COMP PKG #21) Installation_Gas Compressor | Activity | 2CF3520W42A07.1 | (Gas COMP PKG #21) Installation_Gas Compressor | 2008-06-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2193 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W42A16.1 | (Gas COMP PKG #22) Installation_Gas Compressor | (Gas COMP PKG #22) Installation_Gas Compressor | 2008-06-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W42A16.1 (Gas COMP PKG #22) Installation_Gas Compressor | Activity | 2CF3520W42A16.1 | (Gas COMP PKG #22) Installation_Gas Compressor | 2008-06-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2194 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W42A11.1 | (Gas COMP PKG #21) Installation_Lube oil Sys.(incl. Flushing) | (Gas COMP PKG #21) Installation_Lube oil Sys.(incl. Flushing) | 2008-06-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W42A11.1 (Gas COMP PKG #21) Installation_Lube oil Sys.(incl. Flushing) | Activity | 2CF3520W42A11.1 | (Gas COMP PKG #21) Installation_Lube oil Sys.(incl. Flushing) | 2008-06-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2195 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W42A08.1 | (Gas COMP PKG #21) Installation_Air Compressor | (Gas COMP PKG #21) Installation_Air Compressor | 2008-06-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W42A08.1 (Gas COMP PKG #21) Installation_Air Compressor | Activity | 2CF3520W42A08.1 | (Gas COMP PKG #21) Installation_Air Compressor | 2008-06-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2196 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W42A09.1 | (Gas COMP PKG #21) Installation_Air Ventilation | (Gas COMP PKG #21) Installation_Air Ventilation | 2008-06-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W42A09.1 (Gas COMP PKG #21) Installation_Air Ventilation | Activity | 2CF3520W42A09.1 | (Gas COMP PKG #21) Installation_Air Ventilation | 2008-06-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2197 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W42A20.1 | (Gas COMP PKG #22) Installation_Lube oil Sys.(incl. Flushing) | (Gas COMP PKG #22) Installation_Lube oil Sys.(incl. Flushing) | 2008-06-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W42A20.1 (Gas COMP PKG #22) Installation_Lube oil Sys.(incl. Flushing) | Activity | 2CF3520W42A20.1 | (Gas COMP PKG #22) Installation_Lube oil Sys.(incl. Flushing) | 2008-06-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2198 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W42A17.1 | (Gas COMP PKG #22) Installation_Air Compressor | (Gas COMP PKG #22) Installation_Air Compressor | 2008-06-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W42A17.1 (Gas COMP PKG #22) Installation_Air Compressor | Activity | 2CF3520W42A17.1 | (Gas COMP PKG #22) Installation_Air Compressor | 2008-06-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2199 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W42A18.1 | (Gas COMP PKG #22) Installation_Air Ventilation | (Gas COMP PKG #22) Installation_Air Ventilation | 2008-06-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W42A18.1 (Gas COMP PKG #22) Installation_Air Ventilation | Activity | 2CF3520W42A18.1 | (Gas COMP PKG #22) Installation_Air Ventilation | 2008-06-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2200 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W24A30.1 | (Gas COMP House) Shelter finish | (Gas COMP House) Shelter finish | 2008-08-01 | 2008-09-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W24A30.1 (Gas COMP House) Shelter finish | Activity | 2CF3520W24A30.1 | (Gas COMP House) Shelter finish | 2008-08-01 00:00:00 | 2008-09-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2201 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W42A12.1 | (Gas COMP PKG #21) Installation_N2 Generation Sys. | (Gas COMP PKG #21) Installation_N2 Generation Sys. | 2008-08-01 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W42A12.1 (Gas COMP PKG #21) Installation_N2 Generation Sys. | Activity | 2CF3520W42A12.1 | (Gas COMP PKG #21) Installation_N2 Generation Sys. | 2008-08-01 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2202 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W42A10.1 | (Gas COMP PKG #21) Installation_Seal Gas Sys. | (Gas COMP PKG #21) Installation_Seal Gas Sys. | 2008-08-01 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W42A10.1 (Gas COMP PKG #21) Installation_Seal Gas Sys. | Activity | 2CF3520W42A10.1 | (Gas COMP PKG #21) Installation_Seal Gas Sys. | 2008-08-01 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2203 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W42A21.1 | (Gas COMP PKG #22) Installation_N2 Generation Sys. | (Gas COMP PKG #22) Installation_N2 Generation Sys. | 2008-08-01 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W42A21.1 (Gas COMP PKG #22) Installation_N2 Generation Sys. | Activity | 2CF3520W42A21.1 | (Gas COMP PKG #22) Installation_N2 Generation Sys. | 2008-08-01 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2204 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2CF3520W42A19.1 | (Gas COMP PKG #22) Installation_Seal Gas Sys. | (Gas COMP PKG #22) Installation_Seal Gas Sys. | 2008-08-01 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2CF3520W42A19.1 (Gas COMP PKG #22) Installation_Seal Gas Sys. | Activity | 2CF3520W42A19.1 | (Gas COMP PKG #22) Installation_Seal Gas Sys. | 2008-08-01 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2205 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2SF3520W62A13.1 | (Gas COMP PKG #21) Loop chek | (Gas COMP PKG #21) Loop chek | 2008-09-03 | 2008-09-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2SF3520W62A13.1 (Gas COMP PKG #21) Loop chek | Activity | 2SF3520W62A13.1 | (Gas COMP PKG #21) Loop chek | 2008-09-03 00:00:00 | 2008-09-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2206 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2SF3520W62A22.1 | (Gas COMP PKG #22) Loop chek | (Gas COMP PKG #22) Loop chek | 2008-09-03 | 2008-09-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2SF3520W62A22.1 (Gas COMP PKG #22) Loop chek | Activity | 2SF3520W62A22.1 | (Gas COMP PKG #22) Loop chek | 2008-09-03 00:00:00 | 2008-09-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2207 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2SF3520W62A14.1 | (Gas COMP PKG #21) Function Test | (Gas COMP PKG #21) Function Test | 2008-09-16 | 2008-09-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2SF3520W62A14.1 (Gas COMP PKG #21) Function Test | Activity | 2SF3520W62A14.1 | (Gas COMP PKG #21) Function Test | 2008-09-16 00:00:00 | 2008-09-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2208 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2SF3520W62A23.1 | (Gas COMP PKG #22) Function Test | (Gas COMP PKG #22) Function Test | 2008-09-16 | 2008-09-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2SF3520W62A23.1 (Gas COMP PKG #22) Function Test | Activity | 2SF3520W62A23.1 | (Gas COMP PKG #22) Function Test | 2008-09-16 00:00:00 | 2008-09-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2209 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2SF3520W62A15.1 | (Gas COMP PKG #21) Running Test | (Gas COMP PKG #21) Running Test | 2008-09-22 | 2008-09-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2SF3520W62A15.1 (Gas COMP PKG #21) Running Test | Activity | 2SF3520W62A15.1 | (Gas COMP PKG #21) Running Test | 2008-09-22 00:00:00 | 2008-09-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2210 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 2SF3520W62A24.1 | (Gas COMP PKG #22) Running Test | (Gas COMP PKG #22) Running Test | 2008-09-22 | 2008-09-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas Compressor 2SF3520W62A24.1 (Gas COMP PKG #22) Running Test | Activity | 2SF3520W62A24.1 | (Gas COMP PKG #22) Running Test | 2008-09-22 00:00:00 | 2008-09-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2212 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 2CF3520W42A01.1 | (Gas Cooler #21) Installation(incl. fan) | (Gas Cooler #21) Installation(incl. fan) | 2008-06-30 | 2008-07-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas cooler 2CF3520W42A01.1 (Gas Cooler #21) Installation(incl. fan) | Activity | 2CF3520W42A01.1 | (Gas Cooler #21) Installation(incl. fan) | 2008-06-30 00:00:00 | 2008-07-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2213 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 2CF3520W42A05.1 | (Gas Cooler #22) Installation(incl. fan) | (Gas Cooler #22) Installation(incl. fan) | 2008-06-30 | 2008-07-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas cooler 2CF3520W42A05.1 (Gas Cooler #22) Installation(incl. fan) | Activity | 2CF3520W42A05.1 | (Gas Cooler #22) Installation(incl. fan) | 2008-06-30 00:00:00 | 2008-07-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2214 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 2SF3520W62A02.1 | (Gas Cooler #21) Loop chek | (Gas Cooler #21) Loop chek | 2008-07-22 | 2008-07-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas cooler 2SF3520W62A02.1 (Gas Cooler #21) Loop chek | Activity | 2SF3520W62A02.1 | (Gas Cooler #21) Loop chek | 2008-07-22 00:00:00 | 2008-07-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2215 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 2SF3520W62A06.1 | (Gas Cooler #22) Loop chek | (Gas Cooler #22) Loop chek | 2008-07-22 | 2008-07-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas cooler 2SF3520W62A06.1 (Gas Cooler #22) Loop chek | Activity | 2SF3520W62A06.1 | (Gas Cooler #22) Loop chek | 2008-07-22 00:00:00 | 2008-07-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2216 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 2SF3520W62A03.1 | (Gas Cooler #21) Function Test | (Gas Cooler #21) Function Test | 2008-07-27 | 2008-07-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas cooler 2SF3520W62A03.1 (Gas Cooler #21) Function Test | Activity | 2SF3520W62A03.1 | (Gas Cooler #21) Function Test | 2008-07-27 00:00:00 | 2008-07-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2217 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 2SF3520W62A07.1 | (Gas Cooler #22) Function Test | (Gas Cooler #22) Function Test | 2008-07-27 | 2008-07-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas cooler 2SF3520W62A07.1 (Gas Cooler #22) Function Test | Activity | 2SF3520W62A07.1 | (Gas Cooler #22) Function Test | 2008-07-27 00:00:00 | 2008-07-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2218 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 2SF3520W62A04.1 | (Gas Cooler #21) Running Test | (Gas Cooler #21) Running Test | 2008-07-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas cooler 2SF3520W62A04.1 (Gas Cooler #21) Running Test | Activity | 2SF3520W62A04.1 | (Gas Cooler #21) Running Test | 2008-07-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2219 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 2SF3520W62A08.1 | (Gas Cooler #22) Running Test | (Gas Cooler #22) Running Test | 2008-07-30 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Fuel Gas Supply System Gas cooler 2SF3520W62A08.1 (Gas Cooler #22) Running Test | Activity | 2SF3520W62A08.1 | (Gas Cooler #22) Running Test | 2008-07-30 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2221 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | N2 Gas System |  | 2PF3515W42A04P | (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | 2007-11-01 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common N2 Gas System 2PF3515W42A04P (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | Activity | 2PF3515W42A04P | (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | 2007-11-01 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2222 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | N2 Gas System |  | 2EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | (N2 Gas Station Shelter) GA & Load Data to Civil Design | 2007-12-03 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common N2 Gas System 2EF3515W00A06 (N2 Gas Station Shelter) GA & Load Data to Civil Design | Activity | 2EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | 2007-12-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2223 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | N2 Gas System |  | 2EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | (N2 Gas Station Shelter) Shelter Design | 2007-12-03 | 2008-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common N2 Gas System 2EF3515W32A08 (N2 Gas Station Shelter) Shelter Design | Activity | 2EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | 2007-12-03 00:00:00 | 2008-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2224 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | N2 Gas System |  | 2CF3515W16A07 | (N2 Gas Station Shelter) FDN Work | (N2 Gas Station Shelter) FDN Work | 2008-04-05 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common N2 Gas System 2CF3515W16A07 (N2 Gas Station Shelter) FDN Work | Activity | 2CF3515W16A07 | (N2 Gas Station Shelter) FDN Work | 2008-04-05 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2225 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | N2 Gas System |  | 2CF3515W42A05 | (N2 Gas Equip) Installation for FGSS | (N2 Gas Equip) Installation for FGSS | 2008-05-31 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common N2 Gas System 2CF3515W42A05 (N2 Gas Equip) Installation for FGSS | Activity | 2CF3515W42A05 | (N2 Gas Equip) Installation for FGSS | 2008-05-31 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2226 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > N2 Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | N2 Gas System |  | 2CF3515W32A09 | (N2 Gas Station Shelter) Shelter Work | (N2 Gas Station Shelter) Shelter Work | 2008-06-03 | 2008-09-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common N2 Gas System 2CF3515W32A09 (N2 Gas Station Shelter) Shelter Work | Activity | 2CF3515W32A09 | (N2 Gas Station Shelter) Shelter Work | 2008-06-03 00:00:00 | 2008-09-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2229 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 2PF6500W86A02P | (GT GCB) P.O & Procurement | (GT GCB) P.O & Procurement | 2007-05-31 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 2PF6500W86A02P (GT GCB) P.O & Procurement | Activity | 2PF6500W86A02P | (GT GCB) P.O & Procurement | 2007-05-31 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2230 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 2PF6500W86A07P | (ST GCB) P.O & Procurement | (ST GCB) P.O & Procurement | 2007-10-02 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 2PF6500W86A07P (ST GCB) P.O & Procurement | Activity | 2PF6500W86A07P | (ST GCB) P.O & Procurement | 2007-10-02 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2231 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 2PF6500W86A03T | (GT GCB) Transportation | (GT GCB) Transportation | 2008-05-02 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 2PF6500W86A03T (GT GCB) Transportation | Activity | 2PF6500W86A03T | (GT GCB) Transportation | 2008-05-02 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2232 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 2CF6500W86A04 | (GT GCB) Installation | (GT GCB) Installation | 2008-06-17 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 2CF6500W86A04 (GT GCB) Installation | Activity | 2CF6500W86A04 | (GT GCB) Installation | 2008-06-17 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2233 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 2SF6500W62A05 | (GT GCB) Function Test | (GT GCB) Function Test | 2008-07-18 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 2SF6500W62A05 (GT GCB) Function Test | Activity | 2SF6500W62A05 | (GT GCB) Function Test | 2008-07-18 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2234 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 2PF6500W86A08T | (ST GCB) Transportation | (ST GCB) Transportation | 2008-08-30 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 2PF6500W86A08T (ST GCB) Transportation | Activity | 2PF6500W86A08T | (ST GCB) Transportation | 2008-08-30 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2235 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 2CF6500W86A09 | (ST GCB) Installation | (ST GCB) Installation | 2008-12-20 | 2009-01-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 2CF6500W86A09 (ST GCB) Installation | Activity | 2CF6500W86A09 | (ST GCB) Installation | 2008-12-20 00:00:00 | 2009-01-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2236 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 2SF6500W62A10 | (ST GCB) Function Test | (ST GCB) Function Test | 2009-01-21 | 2009-02-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 2SF6500W62A10 (ST GCB) Function Test | Activity | 2SF6500W62A10 | (ST GCB) Function Test | 2009-01-21 00:00:00 | 2009-02-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2238 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Extra High Voltage Cable | 2PF6040W74A06P | (EHV Cable) P.O & Procurement | (EHV Cable) P.O & Procurement | 2007-08-02 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Extra High Voltage Cable 2PF6040W74A06P (EHV Cable) P.O & Procurement | Activity | 2PF6040W74A06P | (EHV Cable) P.O & Procurement | 2007-08-02 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2239 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Extra High Voltage Cable | 2EF6040W16A02 | (Cable tunnel) FDN Design | (Cable tunnel) FDN Design | 2007-08-02 | 2007-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Extra High Voltage Cable 2EF6040W16A02 (Cable tunnel) FDN Design | Activity | 2EF6040W16A02 | (Cable tunnel) FDN Design | 2007-08-02 00:00:00 | 2007-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2240 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Extra High Voltage Cable | 2EF6040W16A01 | (Cable tunnel) Cable tunnel Design | (Cable tunnel) Cable tunnel Design | 2007-08-02 | 2008-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Extra High Voltage Cable 2EF6040W16A01 (Cable tunnel) Cable tunnel Design | Activity | 2EF6040W16A01 | (Cable tunnel) Cable tunnel Design | 2007-08-02 00:00:00 | 2008-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2241 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Extra High Voltage Cable | 2CF6040W16A03 | (Cable tunnel) Civil Work | (Cable tunnel) Civil Work | 2007-11-02 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Extra High Voltage Cable 2CF6040W16A03 (Cable tunnel) Civil Work | Activity | 2CF6040W16A03 | (Cable tunnel) Civil Work | 2007-11-02 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2242 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Extra High Voltage Cable | 2PF6040W74A07T | (EHV Cable) Transportation | (EHV Cable) Transportation | 2008-04-02 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Extra High Voltage Cable 2PF6040W74A07T (EHV Cable) Transportation | Activity | 2PF6040W74A07T | (EHV Cable) Transportation | 2008-04-02 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2243 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Extra High Voltage Cable | 2CF6040W74A08 | (EHV Cable) Cable Electrical Work | (EHV Cable) Cable Electrical Work | 2008-05-17 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Extra High Voltage Cable 2CF6040W74A08 (EHV Cable) Cable Electrical Work | Activity | 2CF6040W74A08 | (EHV Cable) Cable Electrical Work | 2008-05-17 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2244 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Extra High Voltage Cable | 2CF6040W38A04 | (Cable tunnel) F/F Work & Test | (Cable tunnel) F/F Work & Test | 2008-05-31 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Extra High Voltage Cable 2CF6040W38A04 (Cable tunnel) F/F Work & Test | Activity | 2CF6040W38A04 | (Cable tunnel) F/F Work & Test | 2008-05-31 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2245 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Extra High Voltage Cable | 2CF6040W62A09 | (EHV Cable) Function Test | (EHV Cable) Function Test | 2008-08-02 | 2008-08-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Extra High Voltage Cable 2CF6040W62A09 (EHV Cable) Function Test | Activity | 2CF6040W62A09 | (EHV Cable) Function Test | 2008-08-02 00:00:00 | 2008-08-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2246 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Extra High Voltage Cable | 2CF6040W74A10 | (EHV Cable) Connection with GIS & TR | (EHV Cable) Connection with GIS & TR | 2008-08-16 | 2008-08-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Extra High Voltage Cable 2CF6040W74A10 (EHV Cable) Connection with GIS & TR | Activity | 2CF6040W74A10 | (EHV Cable) Connection with GIS & TR | 2008-08-16 00:00:00 | 2008-08-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2248 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Isolated Phase Busduct (IPB) | 2PF6500W74A02P | (IPB) P.O & Procurement | (IPB) P.O & Procurement | 2007-08-02 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Isolated Phase Busduct (IPB) 2PF6500W74A02P (IPB) P.O & Procurement | Activity | 2PF6500W74A02P | (IPB) P.O & Procurement | 2007-08-02 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2249 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Isolated Phase Busduct (IPB) | 2PF6500W74A03T | (IPB) Transportation | (IPB) Transportation | 2008-04-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Isolated Phase Busduct (IPB) 2PF6500W74A03T (IPB) Transportation | Activity | 2PF6500W74A03T | (IPB) Transportation | 2008-04-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2250 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Isolated Phase Busduct (IPB) | 2CF6500W74A04 | (IPB) Installation form TR to GCB(incl. Support) | (IPB) Installation form TR to GCB(incl. Support) | 2008-05-31 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Isolated Phase Busduct (IPB) 2CF6500W74A04 (IPB) Installation form TR to GCB(incl. Support) | Activity | 2CF6500W74A04 | (IPB) Installation form TR to GCB(incl. Support) | 2008-05-31 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2251 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Isolated Phase Busduct (IPB) | 2CF6500W62A05 | (IPB) Insulation Test & Hi potential Test | (IPB) Insulation Test & Hi potential Test | 2008-08-02 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Isolated Phase Busduct (IPB) 2CF6500W62A05 (IPB) Insulation Test & Hi potential Test | Activity | 2CF6500W62A05 | (IPB) Insulation Test & Hi potential Test | 2008-08-02 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2252 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Isolated Phase Busduct (IPB) | 2CF6500W74A06 | (IPB) IPB connection with TR & GCB | (IPB) IPB connection with TR & GCB | 2008-09-06 | 2008-09-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Isolated Phase Busduct (IPB) 2CF6500W74A06 (IPB) IPB connection with TR & GCB | Activity | 2CF6500W74A06 | (IPB) IPB connection with TR & GCB | 2008-09-06 00:00:00 | 2008-09-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2254 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2PF6500W70A04P | (GTG TR) P.O & Procurement | (GTG TR) P.O & Procurement | 2007-04-02 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2PF6500W70A04P (GTG TR) P.O & Procurement | Activity | 2PF6500W70A04P | (GTG TR) P.O & Procurement | 2007-04-02 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2255 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2PF6500W70A12P | (STG TR) P.O & Procurement | (STG TR) P.O & Procurement | 2007-08-02 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2PF6500W70A12P (STG TR) P.O & Procurement | Activity | 2PF6500W70A12P | (STG TR) P.O & Procurement | 2007-08-02 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2256 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2EF6500W16A01 | (GTG TR) FDN Design | (GTG TR) FDN Design | 2007-08-02 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2EF6500W16A01 (GTG TR) FDN Design | Activity | 2EF6500W16A01 | (GTG TR) FDN Design | 2007-08-02 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2257 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2CF6500W16A02 | (GTG TR) FDN & Firewall Work | (GTG TR) FDN & Firewall Work | 2007-12-01 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2CF6500W16A02 (GTG TR) FDN & Firewall Work | Activity | 2CF6500W16A02 | (GTG TR) FDN & Firewall Work | 2007-12-01 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2258 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2EF6500W16A09 | (STG TR) FDN Design | (STG TR) FDN Design | 2008-02-06 | 2008-07-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2EF6500W16A09 (STG TR) FDN Design | Activity | 2EF6500W16A09 | (STG TR) FDN Design | 2008-02-06 00:00:00 | 2008-07-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2259 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2PF6500W70A05T | (GTG TR) Transportation | (GTG TR) Transportation | 2008-05-16 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2PF6500W70A05T (GTG TR) Transportation | Activity | 2PF6500W70A05T | (GTG TR) Transportation | 2008-05-16 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2260 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2CF6500W70A06 | (GTG TR) Installation | (GTG TR) Installation | 2008-07-01 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2CF6500W70A06 (GTG TR) Installation | Activity | 2CF6500W70A06 | (GTG TR) Installation | 2008-07-01 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2261 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2CF6500W16A10 | (STG TR) FDN & Firewall Work | (STG TR) FDN & Firewall Work | 2008-07-05 | 2008-11-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2CF6500W16A10 (STG TR) FDN & Firewall Work | Activity | 2CF6500W16A10 | (STG TR) FDN & Firewall Work | 2008-07-05 00:00:00 | 2008-11-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2262 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2CF6500W38A07 | (GTG TR) F/F Install & test | (GTG TR) F/F Install & test | 2008-08-16 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2CF6500W38A07 (GTG TR) F/F Install & test | Activity | 2CF6500W38A07 | (GTG TR) F/F Install & test | 2008-08-16 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2263 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2PF6500W70A13T | (STG TR) Transportation | (STG TR) Transportation | 2008-08-30 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2PF6500W70A13T (STG TR) Transportation | Activity | 2PF6500W70A13T | (STG TR) Transportation | 2008-08-30 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2264 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2SF6500W62A08 | (GTG TR) Function Test | (GTG TR) Function Test | 2008-08-30 | 2008-09-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2SF6500W62A08 (GTG TR) Function Test | Activity | 2SF6500W62A08 | (GTG TR) Function Test | 2008-08-30 00:00:00 | 2008-09-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2265 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2CF6500W70A14 | (STG TR) Installation | (STG TR) Installation | 2008-11-05 | 2008-12-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2CF6500W70A14 (STG TR) Installation | Activity | 2CF6500W70A14 | (STG TR) Installation | 2008-11-05 00:00:00 | 2008-12-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2266 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2CF6500W38A15 | (STG TR) F/F test | (STG TR) F/F test | 2008-12-20 | 2008-12-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2CF6500W38A15 (STG TR) F/F test | Activity | 2CF6500W38A15 | (STG TR) F/F test | 2008-12-20 00:00:00 | 2008-12-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2267 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Power Transformer | 2SF6500W62A16 | (STG TR) Function Test | (STG TR) Function Test | 2009-02-05 | 2009-02-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Power Transformer 2SF6500W62A16 (STG TR) Function Test | Activity | 2SF6500W62A16 | (STG TR) Function Test | 2009-02-05 00:00:00 | 2009-02-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2269 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2PF6500W70A04.1P | (GTG UAT) P.O & Procurement | (GTG UAT) P.O & Procurement | 2007-03-30 | 2008-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2PF6500W70A04.1P (GTG UAT) P.O & Procurement | Activity | 2PF6500W70A04.1P | (GTG UAT) P.O & Procurement | 2007-03-30 00:00:00 | 2008-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2270 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2EF6500W16A01.1 | (GTG UAT) FDN Design | (GTG UAT) FDN Design | 2007-05-01 | 2007-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2EF6500W16A01.1 (GTG UAT) FDN Design | Activity | 2EF6500W16A01.1 | (GTG UAT) FDN Design | 2007-05-01 00:00:00 | 2007-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2271 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | 2007-05-31 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2EF6500W00A09 (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | Activity | 2EF6500W00A09 | (GTG #21 & UAT Shelter) GA & Load Data to Civil Design | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2272 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2EF6500W16A10 | (GTG #21 & UAT Shelter) FDN Design | (GTG #21 & UAT Shelter) FDN Design | 2007-07-02 | 2007-10-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2EF6500W16A10 (GTG #21 & UAT Shelter) FDN Design | Activity | 2EF6500W16A10 | (GTG #21 & UAT Shelter) FDN Design | 2007-07-02 00:00:00 | 2007-10-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2273 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2EF6500W32A12 | (GTG #21 & UAT Shelter) Structure Design | (GTG #21 & UAT Shelter) Structure Design | 2007-07-02 | 2007-10-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2EF6500W32A12 (GTG #21 & UAT Shelter) Structure Design | Activity | 2EF6500W32A12 | (GTG #21 & UAT Shelter) Structure Design | 2007-07-02 00:00:00 | 2007-10-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2274 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2CF6500W16A02.1 | (GTG UAT) FDN Work & Firewall Work | (GTG UAT) FDN Work & Firewall Work | 2007-11-02 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2CF6500W16A02.1 (GTG UAT) FDN Work & Firewall Work | Activity | 2CF6500W16A02.1 | (GTG UAT) FDN Work & Firewall Work | 2007-11-02 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2275 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2CF6500W16A11 | (GTG #21 & UAT Shelter) FDN Work | (GTG #21 & UAT Shelter) FDN Work | 2007-11-02 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2CF6500W16A11 (GTG #21 & UAT Shelter) FDN Work | Activity | 2CF6500W16A11 | (GTG #21 & UAT Shelter) FDN Work | 2007-11-02 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2276 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2CF6500W32A13 | (GTG #21 & UAT Shelter) Structure Work | (GTG #21 & UAT Shelter) Structure Work | 2007-12-31 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2CF6500W32A13 (GTG #21 & UAT Shelter) Structure Work | Activity | 2CF6500W32A13 | (GTG #21 & UAT Shelter) Structure Work | 2007-12-31 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2277 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2PF6500W70A05.1T | (GTG UAT) Transportation | (GTG UAT) Transportation | 2008-04-17 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2PF6500W70A05.1T (GTG UAT) Transportation | Activity | 2PF6500W70A05.1T | (GTG UAT) Transportation | 2008-04-17 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2278 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2CF6500W90A16 | (GTG #21 & UAT Shelter) Installation & Test - I&C | (GTG #21 & UAT Shelter) Installation & Test - I&C | 2008-05-31 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2CF6500W90A16 (GTG #21 & UAT Shelter) Installation & Test - I&C | Activity | 2CF6500W90A16 | (GTG #21 & UAT Shelter) Installation & Test - I&C | 2008-05-31 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2279 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2CF6500W38A14 | (GTG #21 & UAT Shelter) Installation & Test - Fire Fighting Sys. | (GTG #21 & UAT Shelter) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2CF6500W38A14 (GTG #21 & UAT Shelter) Installation & Test - Fire Fighting Sys. | Activity | 2CF6500W38A14 | (GTG #21 & UAT Shelter) Installation & Test - Fire Fighting Sys. | 2008-05-31 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2280 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2CF6500W74A15 | (GTG #21 & UAT Shelter) Installation & Test - Elec | (GTG #21 & UAT Shelter) Installation & Test - Elec | 2008-05-31 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2CF6500W74A15 (GTG #21 & UAT Shelter) Installation & Test - Elec | Activity | 2CF6500W74A15 | (GTG #21 & UAT Shelter) Installation & Test - Elec | 2008-05-31 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2281 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2CF6500W70A06.1 | (GTG UAT) Installation | (GTG UAT) Installation | 2008-06-02 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2CF6500W70A06.1 (GTG UAT) Installation | Activity | 2CF6500W70A06.1 | (GTG UAT) Installation | 2008-06-02 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2282 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2CF6500W38A07.1 | (GTG UAT) F/F Install & test | (GTG UAT) F/F Install & test | 2008-07-18 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2CF6500W38A07.1 (GTG UAT) F/F Install & test | Activity | 2CF6500W38A07.1 | (GTG UAT) F/F Install & test | 2008-07-18 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2283 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Auxiliary Transformer | 2SF6500W62A08.1 | (GTG UAT) Function Test | (GTG UAT) Function Test | 2008-08-03 | 2008-08-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Auxiliary Transformer 2SF6500W62A08.1 (GTG UAT) Function Test | Activity | 2SF6500W62A08.1 | (GTG UAT) Function Test | 2008-08-03 00:00:00 | 2008-08-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2285 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2EF3530W00A01 | (Block #2 EDG) GA & Load Data to Civil Design | (Block #2 EDG) GA & Load Data to Civil Design | 2007-08-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2EF3530W00A01 (Block #2 EDG) GA & Load Data to Civil Design | Activity | 2EF3530W00A01 | (Block #2 EDG) GA & Load Data to Civil Design | 2007-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2286 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2EF3530W16A14 | (Block #2 EDG BLDG) FDN Design | (Block #2 EDG BLDG) FDN Design | 2007-08-01 | 2007-10-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2EF3530W16A14 (Block #2 EDG BLDG) FDN Design | Activity | 2EF3530W16A14 | (Block #2 EDG BLDG) FDN Design | 2007-08-01 00:00:00 | 2007-10-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2287 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2EF3530W32A16 | (Block #2 EDG BLDG) Structure Design | (Block #2 EDG BLDG) Structure Design | 2007-08-01 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2EF3530W32A16 (Block #2 EDG BLDG) Structure Design | Activity | 2EF3530W32A16 | (Block #2 EDG BLDG) Structure Design | 2007-08-01 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2288 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2PF3530W42A06P | (Block #2 EDG) P.O & Procurement | (Block #2 EDG) P.O & Procurement | 2007-08-01 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2PF3530W42A06P (Block #2 EDG) P.O & Procurement | Activity | 2PF3530W42A06P | (Block #2 EDG) P.O & Procurement | 2007-08-01 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2289 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2EF3530W16A02 | (Block #2 EDG) FDN Design | (Block #2 EDG) FDN Design | 2007-08-01 | 2007-10-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2EF3530W16A02 (Block #2 EDG) FDN Design | Activity | 2EF3530W16A02 | (Block #2 EDG) FDN Design | 2007-08-01 00:00:00 | 2007-10-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2290 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2CF3530W16A15 | (Block #2 EDG BLDG) FDN Work | (Block #2 EDG BLDG) FDN Work | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2CF3530W16A15 (Block #2 EDG BLDG) FDN Work | Activity | 2CF3530W16A15 | (Block #2 EDG BLDG) FDN Work | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2291 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2CF3530W16A03 | (Block #2 EDG) FDN Work | (Block #2 EDG) FDN Work | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2CF3530W16A03 (Block #2 EDG) FDN Work | Activity | 2CF3530W16A03 | (Block #2 EDG) FDN Work | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2292 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2CF3530W32A17 | (Block #2 EDG BLDG) Structure Work | (Block #2 EDG BLDG) Structure Work | 2008-01-31 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2CF3530W32A17 (Block #2 EDG BLDG) Structure Work | Activity | 2CF3530W32A17 | (Block #2 EDG BLDG) Structure Work | 2008-01-31 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2293 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2CF3530W90A21 | (Block #2 EDG BLDG) Installation & Test - I&C | (Block #2 EDG BLDG) Installation & Test - I&C | 2008-05-03 | 2008-06-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2CF3530W90A21 (Block #2 EDG BLDG) Installation & Test - I&C | Activity | 2CF3530W90A21 | (Block #2 EDG BLDG) Installation & Test - I&C | 2008-05-03 00:00:00 | 2008-06-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2294 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2CF3530W38A18 | (Block #2 EDG BLDG) Installation - Fire Fighting Sys. | (Block #2 EDG BLDG) Installation - Fire Fighting Sys. | 2008-05-03 | 2008-06-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2CF3530W38A18 (Block #2 EDG BLDG) Installation - Fire Fighting Sys. | Activity | 2CF3530W38A18 | (Block #2 EDG BLDG) Installation - Fire Fighting Sys. | 2008-05-03 00:00:00 | 2008-06-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2295 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2CF3530W36A19 | (Block #2 EDG BLDG) Installation & Test - HVAC | (Block #2 EDG BLDG) Installation & Test - HVAC | 2008-05-03 | 2008-06-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2CF3530W36A19 (Block #2 EDG BLDG) Installation & Test - HVAC | Activity | 2CF3530W36A19 | (Block #2 EDG BLDG) Installation & Test - HVAC | 2008-05-03 00:00:00 | 2008-06-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2296 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2CF3530W74A20 | (Block #2 EDG BLDG) Installation & Test - Elec | (Block #2 EDG BLDG) Installation & Test - Elec | 2008-05-03 | 2008-06-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2CF3530W74A20 (Block #2 EDG BLDG) Installation & Test - Elec | Activity | 2CF3530W74A20 | (Block #2 EDG BLDG) Installation & Test - Elec | 2008-05-03 00:00:00 | 2008-06-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2297 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2CF3530W24A22 | (Block #2 EDG BLDG) Building Finish | (Block #2 EDG BLDG) Building Finish | 2008-05-03 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2CF3530W24A22 (Block #2 EDG BLDG) Building Finish | Activity | 2CF3530W24A22 | (Block #2 EDG BLDG) Building Finish | 2008-05-03 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2298 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2PF3530W42A07T | (Block #2 EDG) Transportation | (Block #2 EDG) Transportation | 2008-07-02 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2PF3530W42A07T (Block #2 EDG) Transportation | Activity | 2PF3530W42A07T | (Block #2 EDG) Transportation | 2008-07-02 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2299 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2CF3530W42A08 | (Block #2 EDG) Installation | (Block #2 EDG) Installation | 2008-08-16 | 2008-09-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2CF3530W42A08 (Block #2 EDG) Installation | Activity | 2CF3530W42A08 | (Block #2 EDG) Installation | 2008-08-16 00:00:00 | 2008-09-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2300 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2SF3530W62A09 | (Block #2 EDG) Loop chek | (Block #2 EDG) Loop chek | 2008-09-06 | 2008-09-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2SF3530W62A09 (Block #2 EDG) Loop chek | Activity | 2SF3530W62A09 | (Block #2 EDG) Loop chek | 2008-09-06 00:00:00 | 2008-09-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2301 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2SF3530W62A10 | (Block #2 EDG) Function Test | (Block #2 EDG) Function Test | 2008-09-08 | 2008-09-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2SF3530W62A10 (Block #2 EDG) Function Test | Activity | 2SF3530W62A10 | (Block #2 EDG) Function Test | 2008-09-08 00:00:00 | 2008-09-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2302 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2SF3530W62A11 | (Block #2 EDG) System Operation | (Block #2 EDG) System Operation | 2008-09-10 | 2008-09-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2SF3530W62A11 (Block #2 EDG) System Operation | Activity | 2SF3530W62A11 | (Block #2 EDG) System Operation | 2008-09-10 00:00:00 | 2008-09-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2303 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2SF3530W62A12 | (Block #2 EDG) Synchronization | (Block #2 EDG) Synchronization | 2008-09-12 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2SF3530W62A12 (Block #2 EDG) Synchronization | Activity | 2SF3530W62A12 | (Block #2 EDG) Synchronization | 2008-09-12 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2304 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Early Power Block Common | Electrical System | Emergency Diesel Generator | 2SF3530W62A13 | (Block #2 EDG) Load Operation | (Block #2 EDG) Load Operation | 2008-09-14 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Early Power Block Common Electrical System Emergency Diesel Generator 2SF3530W62A13 (Block #2 EDG) Load Operation | Activity | 2SF3530W62A13 | (Block #2 EDG) Load Operation | 2008-09-14 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2307 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2PF3030W68A04P | (EXP Head Tank) P.O & Procurement | (EXP Head Tank) P.O & Procurement | 2007-09-03 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2PF3030W68A04P (EXP Head Tank) P.O & Procurement | Activity | 2PF3030W68A04P | (EXP Head Tank) P.O & Procurement | 2007-09-03 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2308 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2PF3030W42A21P | (CCWP) P.O & Procurement | (CCWP) P.O & Procurement | 2007-09-03 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2PF3030W42A21P (CCWP) P.O & Procurement | Activity | 2PF3030W42A21P | (CCWP) P.O & Procurement | 2007-09-03 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2309 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2EF3030W16A17 | (CCWP) FDN Design | (CCWP) FDN Design | 2007-09-03 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2EF3030W16A17 (CCWP) FDN Design | Activity | 2EF3030W16A17 | (CCWP) FDN Design | 2007-09-03 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2310 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2PF3030W42A14P | (CCW H/EX) P.O & Procurement | (CCW H/EX) P.O & Procurement | 2007-09-03 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2PF3030W42A14P (CCW H/EX) P.O & Procurement | Activity | 2PF3030W42A14P | (CCW H/EX) P.O & Procurement | 2007-09-03 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2311 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2EF3030W16A10 | (CCW H/EX) FDN Design | (CCW H/EX) FDN Design | 2007-09-03 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2EF3030W16A10 (CCW H/EX) FDN Design | Activity | 2EF3030W16A10 | (CCW H/EX) FDN Design | 2007-09-03 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2312 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2EF3030W16A01 | (EXP Head Tank) FDN Design | (EXP Head Tank) FDN Design | 2007-11-02 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2EF3030W16A01 (EXP Head Tank) FDN Design | Activity | 2EF3030W16A01 | (EXP Head Tank) FDN Design | 2007-11-02 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2313 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2CF3030W16A18 | (CCWP) FDN Work | (CCWP) FDN Work | 2008-03-03 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2CF3030W16A18 (CCWP) FDN Work | Activity | 2CF3030W16A18 | (CCWP) FDN Work | 2008-03-03 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2314 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2CF3030W16A11 | (CCW H/EX) FDN Work | (CCW H/EX) FDN Work | 2008-03-03 | 2008-05-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2CF3030W16A11 (CCW H/EX) FDN Work | Activity | 2CF3030W16A11 | (CCW H/EX) FDN Work | 2008-03-03 00:00:00 | 2008-05-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2315 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2CF3030W16A02 | (EXP Head Tank) FDN Work | (EXP Head Tank) FDN Work | 2008-05-03 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2CF3030W16A02 (EXP Head Tank) FDN Work | Activity | 2CF3030W16A02 | (EXP Head Tank) FDN Work | 2008-05-03 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2316 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2CF3030W58A07 | (CCWS) Piping Work | (CCWS) Piping Work | 2008-07-01 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2CF3030W58A07 (CCWS) Piping Work | Activity | 2CF3030W58A07 | (CCWS) Piping Work | 2008-07-01 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2317 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2PF3030W42A22T | (CCWP) Transportation | (CCWP) Transportation | 2008-08-02 | 2008-09-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2PF3030W42A22T (CCWP) Transportation | Activity | 2PF3030W42A22T | (CCWP) Transportation | 2008-08-02 00:00:00 | 2008-09-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2318 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2PF3030W42A15T | (CCW H/EX) Transportation | (CCW H/EX) Transportation | 2008-08-16 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2PF3030W42A15T (CCW H/EX) Transportation | Activity | 2PF3030W42A15T | (CCW H/EX) Transportation | 2008-08-16 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2319 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2PF3030W68A05T | (EXP Head Tank) Transportation | (EXP Head Tank) Transportation | 2008-08-30 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2PF3030W68A05T (EXP Head Tank) Transportation | Activity | 2PF3030W68A05T | (EXP Head Tank) Transportation | 2008-08-30 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2320 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2CF3030W74A08 | (CCWS) Installation & Test - Elec. | (CCWS) Installation & Test - Elec. | 2008-09-12 | 2008-11-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2CF3030W74A08 (CCWS) Installation & Test - Elec. | Activity | 2CF3030W74A08 | (CCWS) Installation & Test - Elec. | 2008-09-12 00:00:00 | 2008-11-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2321 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2CF3030W90A09 | (CCWS) Installation & Test - I&C | (CCWS) Installation & Test - I&C | 2008-09-12 | 2008-11-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2CF3030W90A09 (CCWS) Installation & Test - I&C | Activity | 2CF3030W90A09 | (CCWS) Installation & Test - I&C | 2008-09-12 00:00:00 | 2008-11-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2322 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2CF3030W42A23 | (CCWP) Installation | (CCWP) Installation | 2008-09-17 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2CF3030W42A23 (CCWP) Installation | Activity | 2CF3030W42A23 | (CCWP) Installation | 2008-09-17 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2323 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2CF3030W42A16 | (CCW H/EX) Installation | (CCW H/EX) Installation | 2008-10-02 | 2008-11-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2CF3030W42A16 (CCW H/EX) Installation | Activity | 2CF3030W42A16 | (CCW H/EX) Installation | 2008-10-02 00:00:00 | 2008-11-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2324 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2CF3030W68A06 | (EXP Head Tank) Installation | (EXP Head Tank) Installation | 2008-10-15 | 2008-11-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2CF3030W68A06 (EXP Head Tank) Installation | Activity | 2CF3030W68A06 | (EXP Head Tank) Installation | 2008-10-15 00:00:00 | 2008-11-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2325 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2SF3030W62A24 | (CCWS) Loop chek | (CCWS) Loop chek | 2008-11-13 | 2008-11-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2SF3030W62A24 (CCWS) Loop chek | Activity | 2SF3030W62A24 | (CCWS) Loop chek | 2008-11-13 00:00:00 | 2008-11-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2326 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2SF3030W62A25 | (CCWS) System Function Test | (CCWS) System Function Test | 2008-11-18 | 2008-11-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2SF3030W62A25 (CCWS) System Function Test | Activity | 2SF3030W62A25 | (CCWS) System Function Test | 2008-11-18 00:00:00 | 2008-11-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2327 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Closed Cooling Water System for Block #2 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Closed Cooling Water System for Block #2 |  | 2SF3030W62A26 | (CCWS) Pump Operation | (CCWS) Pump Operation | 2008-11-23 | 2008-11-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Closed Cooling Water System for Block #2 2SF3030W62A26 (CCWS) Pump Operation | Activity | 2SF3030W62A26 | (CCWS) Pump Operation | 2008-11-23 00:00:00 | 2008-11-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2329 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2PF3546W42A18P | (Clean & Dirty LOP) P.O & Procurement | (Clean & Dirty LOP) P.O & Procurement | 2007-10-31 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2PF3546W42A18P (Clean & Dirty LOP) P.O & Procurement | Activity | 2PF3546W42A18P | (Clean & Dirty LOP) P.O & Procurement | 2007-10-31 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2330 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2EF3546W16A15 | (Clean & Dirty LOP) FDN Design | (Clean & Dirty LOP) FDN Design | 2007-10-31 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2EF3546W16A15 (Clean & Dirty LOP) FDN Design | Activity | 2EF3546W16A15 | (Clean & Dirty LOP) FDN Design | 2007-10-31 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2331 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2PF3546W42A06P | (Clean Oil Tank) P.O & Procurement | (Clean Oil Tank) P.O & Procurement | 2007-11-01 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2PF3546W42A06P (Clean Oil Tank) P.O & Procurement | Activity | 2PF3546W42A06P | (Clean Oil Tank) P.O & Procurement | 2007-11-01 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2332 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2EF3546W16A03 | (Clean Oil Tank) FDN Design | (Clean Oil Tank) FDN Design | 2007-11-01 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2EF3546W16A03 (Clean Oil Tank) FDN Design | Activity | 2EF3546W16A03 | (Clean Oil Tank) FDN Design | 2007-11-01 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2333 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2PF3546W42A12P | (Dirty Oil Tank) P.O & Procurement | (Dirty Oil Tank) P.O & Procurement | 2007-11-01 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2PF3546W42A12P (Dirty Oil Tank) P.O & Procurement | Activity | 2PF3546W42A12P | (Dirty Oil Tank) P.O & Procurement | 2007-11-01 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2334 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2EF3546W16A09 | (Dirty Oil Tank) FDN Design | (Dirty Oil Tank) FDN Design | 2007-11-01 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2EF3546W16A09 (Dirty Oil Tank) FDN Design | Activity | 2EF3546W16A09 | (Dirty Oil Tank) FDN Design | 2007-11-01 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2335 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2CF3546W16A04 | (Clean Oil Tank) FDN Work | (Clean Oil Tank) FDN Work | 2008-05-02 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2CF3546W16A04 (Clean Oil Tank) FDN Work | Activity | 2CF3546W16A04 | (Clean Oil Tank) FDN Work | 2008-05-02 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2336 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2CF3546W16A10 | (Dirty Oil Tank) FDN Work | (Dirty Oil Tank) FDN Work | 2008-05-02 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2CF3546W16A10 (Dirty Oil Tank) FDN Work | Activity | 2CF3546W16A10 | (Dirty Oil Tank) FDN Work | 2008-05-02 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2337 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2CF3546W16A16 | (Clean & Dirty LOP) FDN Work | (Clean & Dirty LOP) FDN Work | 2008-05-02 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2CF3546W16A16 (Clean & Dirty LOP) FDN Work | Activity | 2CF3546W16A16 | (Clean & Dirty LOP) FDN Work | 2008-05-02 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2338 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2PF3546W42A07T | (Clean Oil Tank) Transportation | (Clean Oil Tank) Transportation | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2PF3546W42A07T (Clean Oil Tank) Transportation | Activity | 2PF3546W42A07T | (Clean Oil Tank) Transportation | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2339 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2PF3546W42A13T | (Dirty Oil Tank) Transportation | (Dirty Oil Tank) Transportation | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2PF3546W42A13T (Dirty Oil Tank) Transportation | Activity | 2PF3546W42A13T | (Dirty Oil Tank) Transportation | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2340 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2PF3546W42A19T | (Clean & Dirty LOP) Transportation | (Clean & Dirty LOP) Transportation | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2PF3546W42A19T (Clean & Dirty LOP) Transportation | Activity | 2PF3546W42A19T | (Clean & Dirty LOP) Transportation | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2341 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2CF3546W42A08 | (Clean Oil Tank) Installation | (Clean Oil Tank) Installation | 2008-12-16 | 2009-02-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2CF3546W42A08 (Clean Oil Tank) Installation | Activity | 2CF3546W42A08 | (Clean Oil Tank) Installation | 2008-12-16 00:00:00 | 2009-02-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2342 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2CF3546W42A14 | (Dirty Oil Tank) Installation | (Dirty Oil Tank) Installation | 2008-12-16 | 2009-02-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2CF3546W42A14 (Dirty Oil Tank) Installation | Activity | 2CF3546W42A14 | (Dirty Oil Tank) Installation | 2008-12-16 00:00:00 | 2009-02-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2343 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2CF3546W42A20 | (Clean & Dirty LOP) Installation & Test | (Clean & Dirty LOP) Installation & Test | 2008-12-16 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2CF3546W42A20 (Clean & Dirty LOP) Installation & Test | Activity | 2CF3546W42A20 | (Clean & Dirty LOP) Installation & Test | 2008-12-16 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2344 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2CF3546W58A21 | (Clean & Dirty Oil System) Piping Work | (Clean & Dirty Oil System) Piping Work | 2008-12-16 | 2009-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2CF3546W58A21 (Clean & Dirty Oil System) Piping Work | Activity | 2CF3546W58A21 | (Clean & Dirty Oil System) Piping Work | 2008-12-16 00:00:00 | 2009-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2345 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2CF3546W74A22 | (Clean & Dirty Oil System) Installation & Test - Elec. | (Clean & Dirty Oil System) Installation & Test - Elec. | 2009-01-31 | 2009-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2CF3546W74A22 (Clean & Dirty Oil System) Installation & Test - Elec. | Activity | 2CF3546W74A22 | (Clean & Dirty Oil System) Installation & Test - Elec. | 2009-01-31 00:00:00 | 2009-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2346 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean & Dirty Oil System |  | 2CF3546W90A23 | (Clean & Dirty Oil System) Installation & Test - I&C | (Clean & Dirty Oil System) Installation & Test - I&C | 2009-01-31 | 2009-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean & Dirty Oil System 2CF3546W90A23 (Clean & Dirty Oil System) Installation & Test - I&C | Activity | 2CF3546W90A23 | (Clean & Dirty Oil System) Installation & Test - I&C | 2009-01-31 00:00:00 | 2009-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2348 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2PF3015W42A06P | (FWP) P.O & Procurement | (FWP) P.O & Procurement | 2007-08-30 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2PF3015W42A06P (FWP) P.O & Procurement | Activity | 2PF3015W42A06P | (FWP) P.O & Procurement | 2007-08-30 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2349 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | (FWP Shelter) GA & Load Data to Civil Design | 2007-10-31 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2EF3015W00A09 (FWP Shelter) GA & Load Data to Civil Design | Activity | 2EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | 2007-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2350 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2EF3015W32A10 | (FWP Shelter) FDN & Shelter Design | (FWP Shelter) FDN & Shelter Design | 2007-10-31 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2EF3015W32A10 (FWP Shelter) FDN & Shelter Design | Activity | 2EF3015W32A10 | (FWP Shelter) FDN & Shelter Design | 2007-10-31 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2351 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2EF3015W16A03 | (FWP) FDN Design | (FWP) FDN Design | 2007-10-31 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2EF3015W16A03 (FWP) FDN Design | Activity | 2EF3015W16A03 | (FWP) FDN Design | 2007-10-31 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2352 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2PF3015W58A14P | (FW PIPING) P.O & Procurement | (FW PIPING) P.O & Procurement | 2007-11-02 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2PF3015W58A14P (FW PIPING) P.O & Procurement | Activity | 2PF3015W58A14P | (FW PIPING) P.O & Procurement | 2007-11-02 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2353 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2CF3015W16A11 | (FWP Shelter) FDN Work | (FWP Shelter) FDN Work | 2008-01-31 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2CF3015W16A11 (FWP Shelter) FDN Work | Activity | 2CF3015W16A11 | (FWP Shelter) FDN Work | 2008-01-31 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2354 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2CF3015W16A04 | (FWP) FDN Work | (FWP) FDN Work | 2008-03-03 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2CF3015W16A04 (FWP) FDN Work | Activity | 2CF3015W16A04 | (FWP) FDN Work | 2008-03-03 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2355 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2CF3015W32A12 | (FWP Shelter) Shelter Structure Work | (FWP Shelter) Shelter Structure Work | 2008-04-02 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2CF3015W32A12 (FWP Shelter) Shelter Structure Work | Activity | 2CF3015W32A12 | (FWP Shelter) Shelter Structure Work | 2008-04-02 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2356 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2PF3015W58A15T | (FW PIPING) Transportation | (FW PIPING) Transportation | 2008-07-31 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2PF3015W58A15T (FW PIPING) Transportation | Activity | 2PF3015W58A15T | (FW PIPING) Transportation | 2008-07-31 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2357 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2CF3015W58A16 | (FW PIPING) Piping Work (incl. Insulation) | (FW PIPING) Piping Work (incl. Insulation) | 2008-09-15 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2CF3015W58A16 (FW PIPING) Piping Work (incl. Insulation) | Activity | 2CF3015W58A16 | (FW PIPING) Piping Work (incl. Insulation) | 2008-09-15 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2358 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2PF3015W42A07T | (FWP) Transportation | (FWP) Transportation | 2008-10-01 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2PF3015W42A07T (FWP) Transportation | Activity | 2PF3015W42A07T | (FWP) Transportation | 2008-10-01 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2359 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2CF3015W74A18 | (FWS) Installation & Test - Elec. | (FWS) Installation & Test - Elec. | 2008-11-15 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2CF3015W74A18 (FWS) Installation & Test - Elec. | Activity | 2CF3015W74A18 | (FWS) Installation & Test - Elec. | 2008-11-15 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2360 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2CF3015W90A19 | (FWS) Installation & Test - I&C | (FWS) Installation & Test - I&C | 2008-11-15 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2CF3015W90A19 (FWS) Installation & Test - I&C | Activity | 2CF3015W90A19 | (FWS) Installation & Test - I&C | 2008-11-15 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2361 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2CF3015W42A08 | (FWP) Installation | (FWP) Installation | 2008-11-15 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2CF3015W42A08 (FWP) Installation | Activity | 2CF3015W42A08 | (FWP) Installation | 2008-11-15 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2362 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2CF3015W62A17 | (FW PIPING) Hydro Test | (FW PIPING) Hydro Test | 2008-12-16 | 2009-01-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2CF3015W62A17 (FW PIPING) Hydro Test | Activity | 2CF3015W62A17 | (FW PIPING) Hydro Test | 2008-12-16 00:00:00 | 2009-01-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2363 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2SF3015W62A20 | (FWS) Loop check | (FWS) Loop check | 2009-01-16 | 2009-02-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2SF3015W62A20 (FWS) Loop check | Activity | 2SF3015W62A20 | (FWS) Loop check | 2009-01-16 00:00:00 | 2009-02-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2364 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2SF3015W62A21 | (FWS) System Function Test | (FWS) System Function Test | 2009-02-05 | 2009-02-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2SF3015W62A21 (FWS) System Function Test | Activity | 2SF3015W62A21 | (FWS) System Function Test | 2009-02-05 00:00:00 | 2009-02-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2365 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Feed Water System |  | 2SF3015W62A22 | (FWS) Pump Operation | (FWS) Pump Operation | 2009-02-19 | 2009-02-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Feed Water System 2SF3015W62A22 (FWS) Pump Operation | Activity | 2SF3015W62A22 | (FWS) Pump Operation | 2009-02-19 00:00:00 | 2009-02-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2367 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | (Chemical Dosing BLDG) GA & Load Data to Civil Design | 2007-09-26 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2EF3045W00A06 (Chemical Dosing BLDG) GA & Load Data to Civil Design | Activity | 2EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | 2007-09-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2368 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | (Chemical Dosing BLDG) FDN Design | 2007-09-26 | 2008-01-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2EF3045W16A07 (Chemical Dosing BLDG) FDN Design | Activity | 2EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | 2007-09-26 00:00:00 | 2008-01-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2369 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | (Chemical Dosing BLDG) Structure Design | 2007-09-26 | 2008-01-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2EF3045W32A09 (Chemical Dosing BLDG) Structure Design | Activity | 2EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | 2007-09-26 00:00:00 | 2008-01-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2370 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | (Chemical Dosing Equip) P.O & Procurement | 2007-09-26 | 2008-08-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2PF3045W42A03P (Chemical Dosing Equip) P.O & Procurement | Activity | 2PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | 2007-09-26 00:00:00 | 2008-08-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2371 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2CF3045W16A08 | (Chemical Dosing BLDG) FDN Work | (Chemical Dosing BLDG) FDN Work | 2008-01-24 | 2008-03-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2CF3045W16A08 (Chemical Dosing BLDG) FDN Work | Activity | 2CF3045W16A08 | (Chemical Dosing BLDG) FDN Work | 2008-01-24 00:00:00 | 2008-03-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2372 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2CF3045W32A10 | (Chemical Dosing BLDG) Structure Work | (Chemical Dosing BLDG) Structure Work | 2008-03-26 | 2008-07-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2CF3045W32A10 (Chemical Dosing BLDG) Structure Work | Activity | 2CF3045W32A10 | (Chemical Dosing BLDG) Structure Work | 2008-03-26 00:00:00 | 2008-07-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2373 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2PF3045W42A04T | (Chemical Dosing Equip) Transportation | (Chemical Dosing Equip) Transportation | 2008-08-26 | 2008-10-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2PF3045W42A04T (Chemical Dosing Equip) Transportation | Activity | 2PF3045W42A04T | (Chemical Dosing Equip) Transportation | 2008-08-26 00:00:00 | 2008-10-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2374 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2CF3045W58A16 | (Chemical Dosing System) Piping Work | (Chemical Dosing System) Piping Work | 2008-10-10 | 2009-01-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2CF3045W58A16 (Chemical Dosing System) Piping Work | Activity | 2CF3045W58A16 | (Chemical Dosing System) Piping Work | 2008-10-10 00:00:00 | 2009-01-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2375 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2CF3045W42A05 | (Chemical Dosing Equip) Installation | (Chemical Dosing Equip) Installation | 2008-10-10 | 2008-12-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2CF3045W42A05 (Chemical Dosing Equip) Installation | Activity | 2CF3045W42A05 | (Chemical Dosing Equip) Installation | 2008-10-10 00:00:00 | 2008-12-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2376 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2CF3045W38A11 | (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2CF3045W38A11 (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | Activity | 2CF3045W38A11 | (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2377 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2CF3045W36A12 | (Chemical Dosing BLDG) Installation & Test - HVAC | (Chemical Dosing BLDG) Installation & Test - HVAC | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2CF3045W36A12 (Chemical Dosing BLDG) Installation & Test - HVAC | Activity | 2CF3045W36A12 | (Chemical Dosing BLDG) Installation & Test - HVAC | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2378 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2CF3045W74A13 | (Chemical Dosing BLDG) Installation & Test - Elec | (Chemical Dosing BLDG) Installation & Test - Elec | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2CF3045W74A13 (Chemical Dosing BLDG) Installation & Test - Elec | Activity | 2CF3045W74A13 | (Chemical Dosing BLDG) Installation & Test - Elec | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2379 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2CF3045W24A15 | (Chemical Dosing BLDG) Building Finish | (Chemical Dosing BLDG) Building Finish | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2CF3045W24A15 (Chemical Dosing BLDG) Building Finish | Activity | 2CF3045W24A15 | (Chemical Dosing BLDG) Building Finish | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2380 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2CF3045W90A14 | (Chemical Dosing BLDG) Installation & Test - I&C | (Chemical Dosing BLDG) Installation & Test - I&C | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2CF3045W90A14 (Chemical Dosing BLDG) Installation & Test - I&C | Activity | 2CF3045W90A14 | (Chemical Dosing BLDG) Installation & Test - I&C | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2381 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2CF3045W74A17 | (Chemical Dosing System) Installation & Test - Elec. | (Chemical Dosing System) Installation & Test - Elec. | 2008-11-05 | 2009-01-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2CF3045W74A17 (Chemical Dosing System) Installation & Test - Elec. | Activity | 2CF3045W74A17 | (Chemical Dosing System) Installation & Test - Elec. | 2008-11-05 00:00:00 | 2009-01-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2382 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2CF3045W90A18 | (Chemical Dosing System) Installation & Test - I&C | (Chemical Dosing System) Installation & Test - I&C | 2008-11-05 | 2009-01-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2CF3045W90A18 (Chemical Dosing System) Installation & Test - I&C | Activity | 2CF3045W90A18 | (Chemical Dosing System) Installation & Test - I&C | 2008-11-05 00:00:00 | 2009-01-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2383 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2SF3045W62A19 | (Chemical Dosing System) Loop chek | (Chemical Dosing System) Loop chek | 2009-01-10 | 2009-01-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2SF3045W62A19 (Chemical Dosing System) Loop chek | Activity | 2SF3045W62A19 | (Chemical Dosing System) Loop chek | 2009-01-10 00:00:00 | 2009-01-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2384 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2SF3045W62A20 | (Chemical Dosing System) System Function Test | (Chemical Dosing System) System Function Test | 2009-01-25 | 2009-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2SF3045W62A20 (Chemical Dosing System) System Function Test | Activity | 2SF3045W62A20 | (Chemical Dosing System) System Function Test | 2009-01-25 00:00:00 | 2009-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2385 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Chemical Dosing System |  | 2SF3045W62A21 | (Chemical Dosing System) System Operation | (Chemical Dosing System) System Operation | 2009-02-01 | 2009-02-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Chemical Dosing System 2SF3045W62A21 (Chemical Dosing System) System Operation | Activity | 2SF3045W62A21 | (Chemical Dosing System) System Operation | 2009-02-01 00:00:00 | 2009-02-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2387 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Sampling System |  | 2PF3040W42A05P | (Sampling Equip) P.O & Procurement | (Sampling Equip) P.O & Procurement | 2007-10-01 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Sampling System 2PF3040W42A05P (Sampling Equip) P.O & Procurement | Activity | 2PF3040W42A05P | (Sampling Equip) P.O & Procurement | 2007-10-01 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2388 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Sampling System |  | 2EF3040W16A02 | (Sampling Equip) FDN Design | (Sampling Equip) FDN Design | 2008-01-01 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Sampling System 2EF3040W16A02 (Sampling Equip) FDN Design | Activity | 2EF3040W16A02 | (Sampling Equip) FDN Design | 2008-01-01 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2389 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Sampling System |  | 2CF3040W16A03 | (Sampling Equip) FDN Work | (Sampling Equip) FDN Work | 2008-04-03 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Sampling System 2CF3040W16A03 (Sampling Equip) FDN Work | Activity | 2CF3040W16A03 | (Sampling Equip) FDN Work | 2008-04-03 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2390 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Sampling System |  | 2PF3040W42A06T | (Sampling Equip) Transportation | (Sampling Equip) Transportation | 2008-08-30 | 2008-10-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Sampling System 2PF3040W42A06T (Sampling Equip) Transportation | Activity | 2PF3040W42A06T | (Sampling Equip) Transportation | 2008-08-30 00:00:00 | 2008-10-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2391 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Sampling System |  | 2CF3040W42A07 | (Sampling Equip) Installation | (Sampling Equip) Installation | 2008-10-16 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Sampling System 2CF3040W42A07 (Sampling Equip) Installation | Activity | 2CF3040W42A07 | (Sampling Equip) Installation | 2008-10-16 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2392 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Sampling System |  | 2CF3040W58A08 | (Sampling System) Piping Work | (Sampling System) Piping Work | 2008-11-17 | 2009-02-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Sampling System 2CF3040W58A08 (Sampling System) Piping Work | Activity | 2CF3040W58A08 | (Sampling System) Piping Work | 2008-11-17 00:00:00 | 2009-02-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2393 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Sampling System |  | 2CF3040W74A09 | (Sampling System) Installation & Test - Elec. | (Sampling System) Installation & Test - Elec. | 2009-01-10 | 2009-02-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Sampling System 2CF3040W74A09 (Sampling System) Installation & Test - Elec. | Activity | 2CF3040W74A09 | (Sampling System) Installation & Test - Elec. | 2009-01-10 00:00:00 | 2009-02-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2394 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Sampling System |  | 2CF3040W90A10 | (Sampling System) Installation & Test - I&C | (Sampling System) Installation & Test - I&C | 2009-01-10 | 2009-02-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Sampling System 2CF3040W90A10 (Sampling System) Installation & Test - I&C | Activity | 2CF3040W90A10 | (Sampling System) Installation & Test - I&C | 2009-01-10 00:00:00 | 2009-02-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2395 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Sampling System |  | 2SF3040W62A11 | (Sampling System) Loop chek | (Sampling System) Loop chek | 2009-02-11 | 2009-02-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Sampling System 2SF3040W62A11 (Sampling System) Loop chek | Activity | 2SF3040W62A11 | (Sampling System) Loop chek | 2009-02-11 00:00:00 | 2009-02-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2396 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Sampling System |  | 2SF3040W62A12 | (Sampling System) Chiller Function Test | (Sampling System) Chiller Function Test | 2009-02-21 | 2009-02-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Sampling System 2SF3040W62A12 (Sampling System) Chiller Function Test | Activity | 2SF3040W62A12 | (Sampling System) Chiller Function Test | 2009-02-21 00:00:00 | 2009-02-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2397 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Sampling System |  | 2SF3040W62A13 | (Sampling System) Sampling System Function Test | (Sampling System) Sampling System Function Test | 2009-02-26 | 2009-03-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Sampling System 2SF3040W62A13 (Sampling System) Sampling System Function Test | Activity | 2SF3040W62A13 | (Sampling System) Sampling System Function Test | 2009-02-26 00:00:00 | 2009-03-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2398 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Sampling System |  | 2SF3040W62A14 | (Sampling System) System Service | (Sampling System) System Service | 2009-03-03 | 2009-03-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Sampling System 2SF3040W62A14 (Sampling System) System Service | Activity | 2SF3040W62A14 | (Sampling System) System Service | 2009-03-03 00:00:00 | 2009-03-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2401 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2EF3020W00A15 | (COND) Condenser Design Data | (COND) Condenser Design Data | 2007-03-01 | 2007-04-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2EF3020W00A15 (COND) Condenser Design Data | Activity | 2EF3020W00A15 | (COND) Condenser Design Data | 2007-03-01 00:00:00 | 2007-04-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2402 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2PF3020W42A12P | (COND Flash Box) P.O & Procurement | (COND Flash Box) P.O & Procurement | 2007-10-03 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2PF3020W42A12P (COND Flash Box) P.O & Procurement | Activity | 2PF3020W42A12P | (COND Flash Box) P.O & Procurement | 2007-10-03 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2403 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2EF3020W16A17 | (COND) FDN Design | (COND) FDN Design | 2007-10-03 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2EF3020W16A17 (COND) FDN Design | Activity | 2EF3020W16A17 | (COND) FDN Design | 2007-10-03 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2404 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2PF3020W42A20P | (COND) P.O & Procurement | (COND) P.O & Procurement | 2007-10-03 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2PF3020W42A20P (COND) P.O & Procurement | Activity | 2PF3020W42A20P | (COND) P.O & Procurement | 2007-10-03 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2405 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | (COND Air EXT Equip) P.O & Procurement | 2007-10-03 | 2008-09-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2PF3020W42A06P (COND Air EXT Equip) P.O & Procurement | Activity | 2PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | 2007-10-03 00:00:00 | 2008-09-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2406 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2EF3020W16A09 | (COND Flash Box) FDN Design | (COND Flash Box) FDN Design | 2008-01-02 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2EF3020W16A09 (COND Flash Box) FDN Design | Activity | 2EF3020W16A09 | (COND Flash Box) FDN Design | 2008-01-02 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2407 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2CF3020W16A18 | (COND) FDN Work | (COND) FDN Work | 2008-01-31 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2CF3020W16A18 (COND) FDN Work | Activity | 2CF3020W16A18 | (COND) FDN Work | 2008-01-31 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2408 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2EF3020W16A03 | (COND Air EXT Equip) FDN Design | (COND Air EXT Equip) FDN Design | 2008-03-01 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2EF3020W16A03 (COND Air EXT Equip) FDN Design | Activity | 2EF3020W16A03 | (COND Air EXT Equip) FDN Design | 2008-03-01 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2409 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2CF3020W16A10 | (COND Flash Box) FDN Work | (COND Flash Box) FDN Work | 2008-04-01 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2CF3020W16A10 (COND Flash Box) FDN Work | Activity | 2CF3020W16A10 | (COND Flash Box) FDN Work | 2008-04-01 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2410 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2CF3020W16A04 | (COND Air EXT Equip) FDN Work | (COND Air EXT Equip) FDN Work | 2008-05-30 | 2008-07-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2CF3020W16A04 (COND Air EXT Equip) FDN Work | Activity | 2CF3020W16A04 | (COND Air EXT Equip) FDN Work | 2008-05-30 00:00:00 | 2008-07-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2411 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2PF3020W42A13T | (COND Flash Box) Transportation | (COND Flash Box) Transportation | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2PF3020W42A13T (COND Flash Box) Transportation | Activity | 2PF3020W42A13T | (COND Flash Box) Transportation | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2412 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2PF3020W42A21T | (COND) Transportation | (COND) Transportation | 2008-08-30 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2PF3020W42A21T (COND) Transportation | Activity | 2PF3020W42A21T | (COND) Transportation | 2008-08-30 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2413 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2PF3020W42A07T | (COND Air EXT Equip) Transportation | (COND Air EXT Equip) Transportation | 2008-09-12 | 2008-10-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2PF3020W42A07T (COND Air EXT Equip) Transportation | Activity | 2PF3020W42A07T | (COND Air EXT Equip) Transportation | 2008-09-12 00:00:00 | 2008-10-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2414 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2CF3020W42A14 | (COND Flash Box) Installation | (COND Flash Box) Installation | 2008-09-16 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2CF3020W42A14 (COND Flash Box) Installation | Activity | 2CF3020W42A14 | (COND Flash Box) Installation | 2008-09-16 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2415 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2CF3020W42A22 | (COND) Installation | (COND) Installation | 2008-10-15 | 2009-01-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2CF3020W42A22 (COND) Installation | Activity | 2CF3020W42A22 | (COND) Installation | 2008-10-15 00:00:00 | 2009-01-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2416 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2CF3020W58A23 | (COND System) Piping Work(incl. Insulation) | (COND System) Piping Work(incl. Insulation) | 2008-10-24 | 2009-01-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2CF3020W58A23 (COND System) Piping Work(incl. Insulation) | Activity | 2CF3020W58A23 | (COND System) Piping Work(incl. Insulation) | 2008-10-24 00:00:00 | 2009-01-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2417 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2CF3020W74A24 | (COND System) Installation & Test - Elec. | (COND System) Installation & Test - Elec. | 2008-10-24 | 2009-01-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2CF3020W74A24 (COND System) Installation & Test - Elec. | Activity | 2CF3020W74A24 | (COND System) Installation & Test - Elec. | 2008-10-24 00:00:00 | 2009-01-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2418 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2CF3020W90A25 | (COND System) Installation & Test - I&C | (COND System) Installation & Test - I&C | 2008-10-24 | 2009-01-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2CF3020W90A25 (COND System) Installation & Test - I&C | Activity | 2CF3020W90A25 | (COND System) Installation & Test - I&C | 2008-10-24 00:00:00 | 2009-01-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2419 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2CF3020W42A08 | (COND Air EXT Equip) Installation | (COND Air EXT Equip) Installation | 2008-10-28 | 2008-12-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2CF3020W42A08 (COND Air EXT Equip) Installation | Activity | 2CF3020W42A08 | (COND Air EXT Equip) Installation | 2008-10-28 00:00:00 | 2008-12-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2420 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2SF3020W62A26 | (COND System) Loop check | (COND System) Loop check | 2009-01-24 | 2009-02-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2SF3020W62A26 (COND System) Loop check | Activity | 2SF3020W62A26 | (COND System) Loop check | 2009-01-24 00:00:00 | 2009-02-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2421 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2SF3020W62A27 | (COND System) System Function Test | (COND System) System Function Test | 2009-02-08 | 2009-02-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2SF3020W62A27 (COND System) System Function Test | Activity | 2SF3020W62A27 | (COND System) System Function Test | 2009-02-08 00:00:00 | 2009-02-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2422 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser | 2SF3020W62A28 | (COND System) Pump Operation | (COND System) Pump Operation | 2009-02-18 | 2009-02-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser 2SF3020W62A28 (COND System) Pump Operation | Activity | 2SF3020W62A28 | (COND System) Pump Operation | 2009-02-18 00:00:00 | 2009-02-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2424 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser Tube Cleaning System | 2PF3020W42A02P | (CTCS) P.O & Procurement | (CTCS) P.O & Procurement | 2007-10-31 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser Tube Cleaning System 2PF3020W42A02P (CTCS) P.O & Procurement | Activity | 2PF3020W42A02P | (CTCS) P.O & Procurement | 2007-10-31 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2425 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser Tube Cleaning System | 2PF3020W42A03T | (CTCS) Transportation | (CTCS) Transportation | 2008-10-02 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser Tube Cleaning System 2PF3020W42A03T (CTCS) Transportation | Activity | 2PF3020W42A03T | (CTCS) Transportation | 2008-10-02 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2426 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condenser Tube Cleaning System | 2CF3020W42A04 | (CTCS) Installation | (CTCS) Installation | 2008-11-17 | 2008-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condenser Tube Cleaning System 2CF3020W42A04 (CTCS) Installation | Activity | 2CF3020W42A04 | (CTCS) Installation | 2008-11-17 00:00:00 | 2008-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2428 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 2PF3020W42A04P | (CEP) P.O & Procurement | (CEP) P.O & Procurement | 2007-09-07 | 2008-09-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condensate Extraction Pump 2PF3020W42A04P (CEP) P.O & Procurement | Activity | 2PF3020W42A04P | (CEP) P.O & Procurement | 2007-09-07 00:00:00 | 2008-09-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2429 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 2EF3020W16A01 | (CEP) FDN Design | (CEP) FDN Design | 2007-10-09 | 2008-01-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condensate Extraction Pump 2EF3020W16A01 (CEP) FDN Design | Activity | 2EF3020W16A01 | (CEP) FDN Design | 2007-10-09 00:00:00 | 2008-01-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2430 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 2CF3020W16A02 | (CEP) FDN Work | (CEP) FDN Work | 2008-01-05 | 2008-05-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condensate Extraction Pump 2CF3020W16A02 (CEP) FDN Work | Activity | 2CF3020W16A02 | (CEP) FDN Work | 2008-01-05 00:00:00 | 2008-05-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2431 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 2PF3020W42A05T | (CEP) Transportation | (CEP) Transportation | 2008-09-09 | 2008-10-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condensate Extraction Pump 2PF3020W42A05T (CEP) Transportation | Activity | 2PF3020W42A05T | (CEP) Transportation | 2008-09-09 00:00:00 | 2008-10-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2432 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 2CF3020W42A06 | (CEP) Installation | (CEP) Installation | 2008-10-24 | 2009-01-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Condensate System Condensate Extraction Pump 2CF3020W42A06 (CEP) Installation | Activity | 2CF3020W42A06 | (CEP) Installation | 2008-10-24 00:00:00 | 2009-01-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2434 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Auxiliary Cooling Water System |  | 2PF3030W42A04P | (ACW PUMP) P.O & Procurement | (ACW PUMP) P.O & Procurement | 2007-10-03 | 2008-10-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Auxiliary Cooling Water System 2PF3030W42A04P (ACW PUMP) P.O & Procurement | Activity | 2PF3030W42A04P | (ACW PUMP) P.O & Procurement | 2007-10-03 00:00:00 | 2008-10-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2435 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Auxiliary Cooling Water System |  | 2PF3030W58A10P | (ACW Piping) P.O & Procurement | (ACW Piping) P.O & Procurement | 2007-10-03 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Auxiliary Cooling Water System 2PF3030W58A10P (ACW Piping) P.O & Procurement | Activity | 2PF3030W58A10P | (ACW Piping) P.O & Procurement | 2007-10-03 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2436 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Auxiliary Cooling Water System |  | 2PF3030W58A11T | (ACW Piping) Transportation | (ACW Piping) Transportation | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Auxiliary Cooling Water System 2PF3030W58A11T (ACW Piping) Transportation | Activity | 2PF3030W58A11T | (ACW Piping) Transportation | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2437 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Auxiliary Cooling Water System |  | 2CF3030W58A12 | (ACW Piping) Piping Work | (ACW Piping) Piping Work | 2008-10-08 | 2009-01-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Auxiliary Cooling Water System 2CF3030W58A12 (ACW Piping) Piping Work | Activity | 2CF3030W58A12 | (ACW Piping) Piping Work | 2008-10-08 00:00:00 | 2009-01-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2438 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Auxiliary Cooling Water System |  | 2PF3030W42A05T | (ACW PUMP) Transportation | (ACW PUMP) Transportation | 2008-10-31 | 2008-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Auxiliary Cooling Water System 2PF3030W42A05T (ACW PUMP) Transportation | Activity | 2PF3030W42A05T | (ACW PUMP) Transportation | 2008-10-31 00:00:00 | 2008-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2439 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Auxiliary Cooling Water System |  | 2CF3030W42A06 | (ACW PUMP) Installation | (ACW PUMP) Installation | 2008-12-15 | 2009-01-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Auxiliary Cooling Water System 2CF3030W42A06 (ACW PUMP) Installation | Activity | 2CF3030W42A06 | (ACW PUMP) Installation | 2008-12-15 00:00:00 | 2009-01-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2440 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Auxiliary Cooling Water System |  | 2CF3030W62A13 | (ACW Piping) Hydro Test | (ACW Piping) Hydro Test | 2009-01-09 | 2009-02-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Auxiliary Cooling Water System 2CF3030W62A13 (ACW Piping) Hydro Test | Activity | 2CF3030W62A13 | (ACW Piping) Hydro Test | 2009-01-09 00:00:00 | 2009-02-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2441 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Auxiliary Cooling Water System |  | 2CF3030W90A08 | (ACW PUMP) Installation - I&C | (ACW PUMP) Installation - I&C | 2009-01-09 | 2009-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Auxiliary Cooling Water System 2CF3030W90A08 (ACW PUMP) Installation - I&C | Activity | 2CF3030W90A08 | (ACW PUMP) Installation - I&C | 2009-01-09 00:00:00 | 2009-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2442 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Auxiliary Cooling Water System |  | 2CF3030W74A07 | (ACW PUMP) Installation - Elec | (ACW PUMP) Installation - Elec | 2009-01-09 | 2009-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Auxiliary Cooling Water System 2CF3030W74A07 (ACW PUMP) Installation - Elec | Activity | 2CF3030W74A07 | (ACW PUMP) Installation - Elec | 2009-01-09 00:00:00 | 2009-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2443 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Auxiliary Cooling Water System |  | 2SF3030W62A14 | (ACWS) Loop check | (ACWS) Loop check | 2009-02-24 | 2009-03-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Auxiliary Cooling Water System 2SF3030W62A14 (ACWS) Loop check | Activity | 2SF3030W62A14 | (ACWS) Loop check | 2009-02-24 00:00:00 | 2009-03-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2444 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Auxiliary Cooling Water System |  | 2SF3030W62A15 | (ACWS) System Function Test | (ACWS) System Function Test | 2009-03-06 | 2009-03-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Auxiliary Cooling Water System 2SF3030W62A15 (ACWS) System Function Test | Activity | 2SF3030W62A15 | (ACWS) System Function Test | 2009-03-06 00:00:00 | 2009-03-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2445 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Auxiliary Cooling Water System |  | 2SF3030W62A16 | (ACWS) Pump Operation | (ACWS) Pump Operation | 2009-03-11 | 2009-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Auxiliary Cooling Water System 2SF3030W62A16 (ACWS) Pump Operation | Activity | 2SF3030W62A16 | (ACWS) Pump Operation | 2009-03-11 00:00:00 | 2009-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2447 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2EF2510W00A01 | (Steam System) P&ID | (Steam System) P&ID | 2007-04-02 | 2007-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2EF2510W00A01 (Steam System) P&ID | Activity | 2EF2510W00A01 | (Steam System) P&ID | 2007-04-02 00:00:00 | 2007-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2448 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2PF2510W58A08P | (Steam PIPING) P.O & Procurement | (Steam PIPING) P.O & Procurement | 2007-10-01 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2PF2510W58A08P (Steam PIPING) P.O & Procurement | Activity | 2PF2510W58A08P | (Steam PIPING) P.O & Procurement | 2007-10-01 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2449 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2PF2510W42A04P | (Silencer) P.O & Procurement | (Silencer) P.O & Procurement | 2007-10-15 | 2008-08-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2PF2510W42A04P (Silencer) P.O & Procurement | Activity | 2PF2510W42A04P | (Silencer) P.O & Procurement | 2007-10-15 00:00:00 | 2008-08-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2450 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2PF2510W58A09T | (Steam PIPING) Transportation | (Steam PIPING) Transportation | 2008-06-03 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2PF2510W58A09T (Steam PIPING) Transportation | Activity | 2PF2510W58A09T | (Steam PIPING) Transportation | 2008-06-03 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2451 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2CF2510W58A10 | (Steam PIPING) Piping Work | (Steam PIPING) Piping Work | 2008-07-18 | 2008-12-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2CF2510W58A10 (Steam PIPING) Piping Work | Activity | 2CF2510W58A10 | (Steam PIPING) Piping Work | 2008-07-18 00:00:00 | 2008-12-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2452 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2PF2510W42A05T | (Silencer) Transportation | (Silencer) Transportation | 2008-08-15 | 2008-09-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2PF2510W42A05T (Silencer) Transportation | Activity | 2PF2510W42A05T | (Silencer) Transportation | 2008-08-15 00:00:00 | 2008-09-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2453 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2CF2510W74A12 | (Steam System) Installation & Test - Elec. | (Steam System) Installation & Test - Elec. | 2008-09-30 | 2008-12-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2CF2510W74A12 (Steam System) Installation & Test - Elec. | Activity | 2CF2510W74A12 | (Steam System) Installation & Test - Elec. | 2008-09-30 00:00:00 | 2008-12-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2454 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2CF2510W90A13 | (Steam System) Installation & Test - I&C | (Steam System) Installation & Test - I&C | 2008-09-30 | 2008-12-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2CF2510W90A13 (Steam System) Installation & Test - I&C | Activity | 2CF2510W90A13 | (Steam System) Installation & Test - I&C | 2008-09-30 00:00:00 | 2008-12-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2455 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2CF2510W42A06 | (Silencer) Installation | (Silencer) Installation | 2008-09-30 | 2008-10-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2CF2510W42A06 (Silencer) Installation | Activity | 2CF2510W42A06 | (Silencer) Installation | 2008-09-30 00:00:00 | 2008-10-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2456 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2CF2510W62A11 | (Steam PIPING) Hydro Test | (Steam PIPING) Hydro Test | 2008-12-19 | 2009-01-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2CF2510W62A11 (Steam PIPING) Hydro Test | Activity | 2CF2510W62A11 | (Steam PIPING) Hydro Test | 2008-12-19 00:00:00 | 2009-01-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2457 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2SF2510W62A14 | (Steam System) Loop chek | (Steam System) Loop chek | 2009-01-20 | 2009-02-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2SF2510W62A14 (Steam System) Loop chek | Activity | 2SF2510W62A14 | (Steam System) Loop chek | 2009-01-20 00:00:00 | 2009-02-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2458 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2SF2510W62A15 | (Steam System) System Function Test | (Steam System) System Function Test | 2009-02-09 | 2009-02-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2SF2510W62A15 (Steam System) System Function Test | Activity | 2SF2510W62A15 | (Steam System) System Function Test | 2009-02-09 00:00:00 | 2009-02-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2459 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Steam System |  | 2SF2510W62A16 | (Steam System) System Service | (Steam System) System Service | 2009-02-19 | 2009-02-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Steam System 2SF2510W62A16 (Steam System) System Service | Activity | 2SF2510W62A16 | (Steam System) System Service | 2009-02-19 00:00:00 | 2009-02-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2461 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Bypass System |  | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | (Bypass System) P&ID & System Design | 2007-04-02 | 2007-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Bypass System 2EF2510W00A01.1 (Bypass System) P&ID & System Design | Activity | 2EF2510W00A01.1 | (Bypass System) P&ID & System Design | 2007-04-02 00:00:00 | 2007-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2462 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Bypass System |  | 2PF2510W42A04.1P | (Bypass Valve) P.O & Procurement | (Bypass Valve) P.O & Procurement | 2007-08-20 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Bypass System 2PF2510W42A04.1P (Bypass Valve) P.O & Procurement | Activity | 2PF2510W42A04.1P | (Bypass Valve) P.O & Procurement | 2007-08-20 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2463 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Bypass System |  | 2PF2510W42A05.1T | (Bypass Valve) Transportation | (Bypass Valve) Transportation | 2008-07-31 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Bypass System 2PF2510W42A05.1T (Bypass Valve) Transportation | Activity | 2PF2510W42A05.1T | (Bypass Valve) Transportation | 2008-07-31 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2464 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Bypass System |  | 2CF2510W58A07.1 | (Bypass System) Piping Work | (Bypass System) Piping Work | 2008-09-15 | 2008-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Bypass System 2CF2510W58A07.1 (Bypass System) Piping Work | Activity | 2CF2510W58A07.1 | (Bypass System) Piping Work | 2008-09-15 00:00:00 | 2008-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2465 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Bypass System |  | 2CF2510W90A10.1 | (Bypass System) Installation & Test - I&C | (Bypass System) Installation & Test - I&C | 2008-09-15 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Bypass System 2CF2510W90A10.1 (Bypass System) Installation & Test - I&C | Activity | 2CF2510W90A10.1 | (Bypass System) Installation & Test - I&C | 2008-09-15 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2466 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Bypass System |  | 2CF2510W74A09.1 | (Bypass System) Installation & Test - Elec. | (Bypass System) Installation & Test - Elec. | 2008-09-15 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Bypass System 2CF2510W74A09.1 (Bypass System) Installation & Test - Elec. | Activity | 2CF2510W74A09.1 | (Bypass System) Installation & Test - Elec. | 2008-09-15 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2467 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Bypass System |  | 2CF2510W42A06.1 | (Bypass Valve) Installation | (Bypass Valve) Installation | 2008-09-15 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Bypass System 2CF2510W42A06.1 (Bypass Valve) Installation | Activity | 2CF2510W42A06.1 | (Bypass Valve) Installation | 2008-09-15 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2468 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Bypass System |  | 2CF2510W62A08.1 | (Bypass System) Hydro Test | (Bypass System) Hydro Test | 2008-12-15 | 2008-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Bypass System 2CF2510W62A08.1 (Bypass System) Hydro Test | Activity | 2CF2510W62A08.1 | (Bypass System) Hydro Test | 2008-12-15 00:00:00 | 2008-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2469 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Bypass System |  | 2SF2510W62A11.1 | (Bypass System) Loop check | (Bypass System) Loop check | 2009-01-01 | 2009-01-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Bypass System 2SF2510W62A11.1 (Bypass System) Loop check | Activity | 2SF2510W62A11.1 | (Bypass System) Loop check | 2009-01-01 00:00:00 | 2009-01-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2470 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Bypass System |  | 2SF2510W62A12.1 | (Bypass System) System Function Test | (Bypass System) System Function Test | 2009-01-15 | 2009-01-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Bypass System 2SF2510W62A12.1 (Bypass System) System Function Test | Activity | 2SF2510W62A12.1 | (Bypass System) System Function Test | 2009-01-15 00:00:00 | 2009-01-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2471 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Bypass System |  | 2SF2510W62A13.1 | (Bypass System) System Service | (Bypass System) System Service | 2009-01-25 | 2009-01-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Bypass System 2SF2510W62A13.1 (Bypass System) System Service | Activity | 2SF2510W62A13.1 | (Bypass System) System Service | 2009-01-25 00:00:00 | 2009-01-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2473 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | (Clean Drain System) P&ID & System Design | 2007-03-15 | 2008-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2EF3020W00A01.1 (Clean Drain System) P&ID & System Design | Activity | 2EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | 2007-03-15 00:00:00 | 2008-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2474 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2PF3020W42A12.1P | (Clean Drain Tank) P.O & Procurement | (Clean Drain Tank) P.O & Procurement | 2007-10-01 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2PF3020W42A12.1P (Clean Drain Tank) P.O & Procurement | Activity | 2PF3020W42A12.1P | (Clean Drain Tank) P.O & Procurement | 2007-10-01 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2475 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2PF3020W42A06.1P | (Clean Drain Flash Vessel) P.O & Procurement | (Clean Drain Flash Vessel) P.O & Procurement | 2007-10-03 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2PF3020W42A06.1P (Clean Drain Flash Vessel) P.O & Procurement | Activity | 2PF3020W42A06.1P | (Clean Drain Flash Vessel) P.O & Procurement | 2007-10-03 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2476 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | (Clean Drain Flash Vessel) FDN Design | 2007-10-03 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2EF3020W16A03.1 (Clean Drain Flash Vessel) FDN Design | Activity | 2EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | 2007-10-03 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2477 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2EF3020W16A15.1 | (Clean Drain Pump) FDN Design | (Clean Drain Pump) FDN Design | 2007-10-03 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2EF3020W16A15.1 (Clean Drain Pump) FDN Design | Activity | 2EF3020W16A15.1 | (Clean Drain Pump) FDN Design | 2007-10-03 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2478 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2PF3020W42A18.1P | (Clean Drain Pump) P.O & Procurement | (Clean Drain Pump) P.O & Procurement | 2007-10-03 | 2008-08-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2PF3020W42A18.1P (Clean Drain Pump) P.O & Procurement | Activity | 2PF3020W42A18.1P | (Clean Drain Pump) P.O & Procurement | 2007-10-03 00:00:00 | 2008-08-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2479 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2EF3020W16A09.1 | (Clean Drain Tank) FDN Design | (Clean Drain Tank) FDN Design | 2007-12-06 | 2008-05-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2EF3020W16A09.1 (Clean Drain Tank) FDN Design | Activity | 2EF3020W16A09.1 | (Clean Drain Tank) FDN Design | 2007-12-06 00:00:00 | 2008-05-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2480 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2CF3020W16A04.1 | (Clean Drain Flash Vessel) FDN Work | (Clean Drain Flash Vessel) FDN Work | 2008-03-01 | 2008-04-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2CF3020W16A04.1 (Clean Drain Flash Vessel) FDN Work | Activity | 2CF3020W16A04.1 | (Clean Drain Flash Vessel) FDN Work | 2008-03-01 00:00:00 | 2008-04-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2481 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2CF3020W16A16.1 | (Clean Drain Pump) FDN Work | (Clean Drain Pump) FDN Work | 2008-03-01 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2CF3020W16A16.1 (Clean Drain Pump) FDN Work | Activity | 2CF3020W16A16.1 | (Clean Drain Pump) FDN Work | 2008-03-01 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2482 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2PF3020W42A07.1T | (Clean Drain Flash Vessel) Transportation | (Clean Drain Flash Vessel) Transportation | 2008-05-03 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2PF3020W42A07.1T (Clean Drain Flash Vessel) Transportation | Activity | 2PF3020W42A07.1T | (Clean Drain Flash Vessel) Transportation | 2008-05-03 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2483 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2CF3020W16A10.1 | (Clean Drain Tank) FDN Work | (Clean Drain Tank) FDN Work | 2008-05-06 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2CF3020W16A10.1 (Clean Drain Tank) FDN Work | Activity | 2CF3020W16A10.1 | (Clean Drain Tank) FDN Work | 2008-05-06 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2484 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2CF3020W42A08.1 | (Clean Drain Flash Vessel) Installation | (Clean Drain Flash Vessel) Installation | 2008-06-18 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2CF3020W42A08.1 (Clean Drain Flash Vessel) Installation | Activity | 2CF3020W42A08.1 | (Clean Drain Flash Vessel) Installation | 2008-06-18 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2485 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2PF3020W42A19.1T | (Clean Drain Pump) Transportation | (Clean Drain Pump) Transportation | 2008-08-19 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2PF3020W42A19.1T (Clean Drain Pump) Transportation | Activity | 2PF3020W42A19.1T | (Clean Drain Pump) Transportation | 2008-08-19 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2486 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2PF3020W42A13.1T | (Clean Drain Tank) Transportation | (Clean Drain Tank) Transportation | 2008-10-02 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2PF3020W42A13.1T (Clean Drain Tank) Transportation | Activity | 2PF3020W42A13.1T | (Clean Drain Tank) Transportation | 2008-10-02 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2487 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2CF3020W42A20.1 | (Clean Drain Pump) Installation | (Clean Drain Pump) Installation | 2008-10-03 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2CF3020W42A20.1 (Clean Drain Pump) Installation | Activity | 2CF3020W42A20.1 | (Clean Drain Pump) Installation | 2008-10-03 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2488 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2CF3020W58A21.1 | (Clean Drain System) Piping Work | (Clean Drain System) Piping Work | 2008-11-17 | 2009-02-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2CF3020W58A21.1 (Clean Drain System) Piping Work | Activity | 2CF3020W58A21.1 | (Clean Drain System) Piping Work | 2008-11-17 00:00:00 | 2009-02-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2489 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2CF3020W42A14.1 | (Clean Drain Tank) Installation | (Clean Drain Tank) Installation | 2008-11-17 | 2008-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2CF3020W42A14.1 (Clean Drain Tank) Installation | Activity | 2CF3020W42A14.1 | (Clean Drain Tank) Installation | 2008-11-17 00:00:00 | 2008-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2490 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2CF3020W74A23.1 | (Clean Drain System) Installation & Test - Elec. | (Clean Drain System) Installation & Test - Elec. | 2009-01-16 | 2009-02-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2CF3020W74A23.1 (Clean Drain System) Installation & Test - Elec. | Activity | 2CF3020W74A23.1 | (Clean Drain System) Installation & Test - Elec. | 2009-01-16 00:00:00 | 2009-02-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2491 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2CF3020W90A24.1 | (Clean Drain System) Installation & Test - I&C | (Clean Drain System) Installation & Test - I&C | 2009-01-16 | 2009-02-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2CF3020W90A24.1 (Clean Drain System) Installation & Test - I&C | Activity | 2CF3020W90A24.1 | (Clean Drain System) Installation & Test - I&C | 2009-01-16 00:00:00 | 2009-02-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2492 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2CF3020W62A22.1 | (Clean Drain System) Hydro Test | (Clean Drain System) Hydro Test | 2009-02-17 | 2009-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2CF3020W62A22.1 (Clean Drain System) Hydro Test | Activity | 2CF3020W62A22.1 | (Clean Drain System) Hydro Test | 2009-02-17 00:00:00 | 2009-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2493 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2SF3020W62A25.1 | (Clean Drain System) Loop chek | (Clean Drain System) Loop chek | 2009-03-18 | 2009-04-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2SF3020W62A25.1 (Clean Drain System) Loop chek | Activity | 2SF3020W62A25.1 | (Clean Drain System) Loop chek | 2009-03-18 00:00:00 | 2009-04-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2494 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2SF3020W62A26.1 | (Clean Drain System) System Function Test | (Clean Drain System) System Function Test | 2009-04-07 | 2009-04-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2SF3020W62A26.1 (Clean Drain System) System Function Test | Activity | 2SF3020W62A26.1 | (Clean Drain System) System Function Test | 2009-04-07 00:00:00 | 2009-04-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2495 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Combined Power Block Common | Clean Drain System |  | 2SF3020W62A27.1 | (Clean Drain System) System Service | (Clean Drain System) System Service | 2009-04-10 | 2009-04-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Combined Power Block Common Clean Drain System 2SF3020W62A27.1 (Clean Drain System) System Service | Activity | 2SF3020W62A27.1 | (Clean Drain System) System Service | 2009-04-10 00:00:00 | 2009-04-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2498 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Gas Supply System (GTG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Gas Supply System (GTG) |  | 2CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | (Gas Supply System) Piping Work(Yard area) | 2008-06-19 | 2008-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Gas Supply System (GTG) 2CF3520W58A01 (Gas Supply System) Piping Work(Yard area) | Activity | 2CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | 2008-06-19 00:00:00 | 2008-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2500 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Oil Supply System (GTG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Oil Supply System (GTG) |  | 2CF3520W58A01.1 | (Oil Supply System) Piping Work(Yard area) | (Oil Supply System) Piping Work(Yard area) | 2008-03-03 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Oil Supply System (GTG) 2CF3520W58A01.1 (Oil Supply System) Piping Work(Yard area) | Activity | 2CF3520W58A01.1 | (Oil Supply System) Piping Work(Yard area) | 2008-03-03 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2501 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Oil Supply System (GTG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Oil Supply System (GTG) |  | 2CF3520W62A02 | (Oil Supply System) Hydro Test | (Oil Supply System) Hydro Test | 2008-05-03 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Oil Supply System (GTG) 2CF3520W62A02 (Oil Supply System) Hydro Test | Activity | 2CF3520W62A02 | (Oil Supply System) Hydro Test | 2008-05-03 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2503 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Make Up Wate Supply System (STG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Make Up Wate Supply System (STG) |  | 2CF3010W58A01 | (Make Up WTR Supply System) Piping Work(Block #2) | (Make Up WTR Supply System) Piping Work(Block #2) | 2008-05-19 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Make Up Wate Supply System (STG) 2CF3010W58A01 (Make Up WTR Supply System) Piping Work(Block #2) | Activity | 2CF3010W58A01 | (Make Up WTR Supply System) Piping Work(Block #2) | 2008-05-19 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2504 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Make Up Wate Supply System (STG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Make Up Wate Supply System (STG) |  | 2CF3010W62A02 | (Make Up WTR Supply System) Hydro Test(Block #2) | (Make Up WTR Supply System) Hydro Test(Block #2) | 2008-07-19 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Make Up Wate Supply System (STG) 2CF3010W62A02 (Make Up WTR Supply System) Hydro Test(Block #2) | Activity | 2CF3010W62A02 | (Make Up WTR Supply System) Hydro Test(Block #2) | 2008-07-19 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2506 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Water Treatment Sytstem (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Water Treatment Sytstem (BOP) |  | 2CF3010W58A01.1 | (Water Treatment System) Piping Work(Block #2) | (Water Treatment System) Piping Work(Block #2) | 2008-10-17 | 2008-12-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Water Treatment Sytstem (BOP) 2CF3010W58A01.1 (Water Treatment System) Piping Work(Block #2) | Activity | 2CF3010W58A01.1 | (Water Treatment System) Piping Work(Block #2) | 2008-10-17 00:00:00 | 2008-12-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2507 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Water Treatment Sytstem (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Water Treatment Sytstem (BOP) |  | 2CF3010W62A02.1 | (Water Treatment System) Hydro Test(Block #2) | (Water Treatment System) Hydro Test(Block #2) | 2008-12-17 | 2009-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Water Treatment Sytstem (BOP) 2CF3010W62A02.1 (Water Treatment System) Hydro Test(Block #2) | Activity | 2CF3010W62A02.1 | (Water Treatment System) Hydro Test(Block #2) | 2008-12-17 00:00:00 | 2009-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2509 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Service Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Service Water System (BOP) |  | 2CF3035W58A01 | (SWS) Piping Work(Block #2) | (SWS) Piping Work(Block #2) | 2008-10-17 | 2008-12-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Service Water System (BOP) 2CF3035W58A01 (SWS) Piping Work(Block #2) | Activity | 2CF3035W58A01 | (SWS) Piping Work(Block #2) | 2008-10-17 00:00:00 | 2008-12-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2510 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Service Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Service Water System (BOP) |  | 2CF3035W62A02 | (SWS) Hydro Test(Block #2) | (SWS) Hydro Test(Block #2) | 2008-12-17 | 2009-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Service Water System (BOP) 2CF3035W62A02 (SWS) Hydro Test(Block #2) | Activity | 2CF3035W62A02 | (SWS) Hydro Test(Block #2) | 2008-12-17 00:00:00 | 2009-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2512 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Potable Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Potable Water System (BOP) |  | 2CF3035W58A01.1 | (PWS) Piping Work(Block #2) | (PWS) Piping Work(Block #2) | 2008-11-04 | 2009-01-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Potable Water System (BOP) 2CF3035W58A01.1 (PWS) Piping Work(Block #2) | Activity | 2CF3035W58A01.1 | (PWS) Piping Work(Block #2) | 2008-11-04 00:00:00 | 2009-01-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2513 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Potable Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Potable Water System (BOP) |  | 2CF3035W62A02.1 | (PWS) Hydro Test(Block #2) | (PWS) Hydro Test(Block #2) | 2009-01-03 | 2009-01-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Potable Water System (BOP) 2CF3035W62A02.1 (PWS) Hydro Test(Block #2) | Activity | 2CF3035W62A02.1 | (PWS) Hydro Test(Block #2) | 2009-01-03 00:00:00 | 2009-01-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2515 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Compressed Air System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Compressed Air System (BOP) |  | 2CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_(Block #2) | (COMP Air System) Piping Work(incl. Air blowing)_(Block #2) | 2008-09-02 | 2008-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Compressed Air System (BOP) 2CF3510W58A01 (COMP Air System) Piping Work(incl. Air blowing)_(Block #2) | Activity | 2CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_(Block #2) | 2008-09-02 00:00:00 | 2008-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2517 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Waste Water Treatment System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Waste Water Treatment System (BOP) |  | 2CF4035W58A01 | (WWTS) Piping Work(Block #2) | (WWTS) Piping Work(Block #2) | 2008-10-17 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Waste Water Treatment System (BOP) 2CF4035W58A01 (WWTS) Piping Work(Block #2) | Activity | 2CF4035W58A01 | (WWTS) Piping Work(Block #2) | 2008-10-17 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2518 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Waste Water Treatment System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Waste Water Treatment System (BOP) |  | 2CF4035W62A02 | (WWTS) Hydro Test(Block #2) | (WWTS) Hydro Test(Block #2) | 2009-01-16 | 2009-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Waste Water Treatment System (BOP) 2CF4035W62A02 (WWTS) Hydro Test(Block #2) | Activity | 2CF4035W62A02 | (WWTS) Hydro Test(Block #2) | 2009-01-16 00:00:00 | 2009-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2520 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Sewage Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Sewage Water System (BOP) |  | 2CF4035W58A01.1 | (STS) Piping Work(Block #2) | (STS) Piping Work(Block #2) | 2008-10-17 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Sewage Water System (BOP) 2CF4035W58A01.1 (STS) Piping Work(Block #2) | Activity | 2CF4035W58A01.1 | (STS) Piping Work(Block #2) | 2008-10-17 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2521 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Sewage Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Sewage Water System (BOP) |  | 2CF4035W62A02.1 | (STS) Hydro Test(Block #2) | (STS) Hydro Test(Block #2) | 2009-01-16 | 2009-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Sewage Water System (BOP) 2CF4035W62A02.1 (STS) Hydro Test(Block #2) | Activity | 2CF4035W62A02.1 | (STS) Hydro Test(Block #2) | 2009-01-16 00:00:00 | 2009-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2523 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > U/G Line | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | U/G Line |  | 2CF4035W22A01 | (STRS) Piping Work(Block #2) | (STRS) Piping Work(Block #2) | 2008-10-17 | 2009-01-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common U/G Line 2CF4035W22A01 (STRS) Piping Work(Block #2) | Activity | 2CF4035W22A01 | (STRS) Piping Work(Block #2) | 2008-10-17 00:00:00 | 2009-01-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2524 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > U/G Line | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | U/G Line |  | 2CF4035W22A02 | (SWS) Piping Work(Block #2) | (SWS) Piping Work(Block #2) | 2008-10-17 | 2009-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common U/G Line 2CF4035W22A02 (SWS) Piping Work(Block #2) | Activity | 2CF4035W22A02 | (SWS) Piping Work(Block #2) | 2008-10-17 00:00:00 | 2009-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2526 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Pipe Rack |  | 2EF5550W00A01 | (PipeRack) Pipe Rack Key Data | (PipeRack) Pipe Rack Key Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Pipe Rack 2EF5550W00A01 (PipeRack) Pipe Rack Key Data | Activity | 2EF5550W00A01 | (PipeRack) Pipe Rack Key Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2527 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Pipe Rack |  | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | (PipeRack) GA & Load Data to Civil Design | 2007-03-30 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Pipe Rack 2EF5550W00A02 (PipeRack) GA & Load Data to Civil Design | Activity | 2EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2528 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Pipe Rack |  | 2EF5550W16A03 | (PipeRack) FDN Design | (PipeRack) FDN Design | 2007-05-30 | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Pipe Rack 2EF5550W16A03 (PipeRack) FDN Design | Activity | 2EF5550W16A03 | (PipeRack) FDN Design | 2007-05-30 00:00:00 | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2529 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Pipe Rack |  | 2EF5550W20A05 | (PipeRack) Structure Design | (PipeRack) Structure Design | 2007-05-30 | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Pipe Rack 2EF5550W20A05 (PipeRack) Structure Design | Activity | 2EF5550W20A05 | (PipeRack) Structure Design | 2007-05-30 00:00:00 | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2530 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Pipe Rack |  | 2PF5550W46A08P | (PipeRack) P.O & Procurement | (PipeRack) P.O & Procurement | 2007-06-28 | 2008-02-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Pipe Rack 2PF5550W46A08P (PipeRack) P.O & Procurement | Activity | 2PF5550W46A08P | (PipeRack) P.O & Procurement | 2007-06-28 00:00:00 | 2008-02-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2531 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Pipe Rack |  | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | (PipeRack) FDN Work Block #1 Area | 2007-09-01 | 2008-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Pipe Rack 2CF5550W16A04 (PipeRack) FDN Work Block #1 Area | Activity | 2CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | 2007-09-01 00:00:00 | 2008-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2532 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Pipe Rack |  | 2PF5550W46A09T | (PipeRack) Trasnportation | (PipeRack) Trasnportation | 2008-02-02 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Pipe Rack 2PF5550W46A09T (PipeRack) Trasnportation | Activity | 2PF5550W46A09T | (PipeRack) Trasnportation | 2008-02-02 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2533 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > BOP Piping for Block #2 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | BOP Piping for Block #2 Common | Pipe Rack |  | 2CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | (PipeRack) Structure Work for Block #1 Area | 2008-03-18 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 BOP Piping for Block #2 Common Pipe Rack 2CF5550W46A06 (PipeRack) Structure Work for Block #1 Area | Activity | 2CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | 2008-03-18 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2536 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | (GTG Common BLDG) GA & Load Data to Civil Design | 2007-03-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2EF1210W00A06 (GTG Common BLDG) GA & Load Data to Civil Design | Activity | 2EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | 2007-03-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2537 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2EF1210W16A07 | (GTG Common BLDG) FDN Design | (GTG Common BLDG) FDN Design | 2007-03-01 | 2007-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2EF1210W16A07 (GTG Common BLDG) FDN Design | Activity | 2EF1210W16A07 | (GTG Common BLDG) FDN Design | 2007-03-01 00:00:00 | 2007-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2538 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2EF1210W20A09 | (GTG Common BLDG) Structure Design | (GTG Common BLDG) Structure Design | 2007-03-01 | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2EF1210W20A09 (GTG Common BLDG) Structure Design | Activity | 2EF1210W20A09 | (GTG Common BLDG) Structure Design | 2007-03-01 00:00:00 | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2539 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | 2007-03-01 | 2007-03-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2EF1200W00A01 (GTG #21/#22) GTG Process Data (FG, FO, CCW) | Activity | 2EF1200W00A01 | (GTG #21/#22) GTG Process Data (FG, FO, CCW) | 2007-03-01 00:00:00 | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2540 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2EF1200W00A02 | (GTG #21/#22) Instrument, Service Air, Aux steam Data | (GTG #21/#22) Instrument, Service Air, Aux steam Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2EF1200W00A02 (GTG #21/#22) Instrument, Service Air, Aux steam Data | Activity | 2EF1200W00A02 | (GTG #21/#22) Instrument, Service Air, Aux steam Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2541 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2EF1200W00A03 | (GTG #21/#22) Utility Consumption Data | (GTG #21/#22) Utility Consumption Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2EF1200W00A03 (GTG #21/#22) Utility Consumption Data | Activity | 2EF1200W00A03 | (GTG #21/#22) Utility Consumption Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2542 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2EF1200W00A04 | (GTG #21/#22) Emergency Load Data | (GTG #21/#22) Emergency Load Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2EF1200W00A04 (GTG #21/#22) Emergency Load Data | Activity | 2EF1200W00A04 | (GTG #21/#22) Emergency Load Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2543 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2EF1200W00A05 | (GTG #21/#22) Black Start Load Data | (GTG #21/#22) Black Start Load Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2EF1200W00A05 (GTG #21/#22) Black Start Load Data | Activity | 2EF1200W00A05 | (GTG #21/#22) Black Start Load Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2544 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | (GTG Common BLDG) P.O & Procurement(Steel Structure) | 2007-09-03 | 2008-02-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2PF1210W20A09P (GTG Common BLDG) P.O & Procurement(Steel Structure) | Activity | 2PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | 2007-09-03 00:00:00 | 2008-02-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2545 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2CF1210W16A08 | (GTG Common BLDG) FDN Work | (GTG Common BLDG) FDN Work | 2007-10-02 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2CF1210W16A08 (GTG Common BLDG) FDN Work | Activity | 2CF1210W16A08 | (GTG Common BLDG) FDN Work | 2007-10-02 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2546 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | 2008-02-15 | 2008-06-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2CF1210W20A10 (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | Activity | 2CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | 2008-02-15 00:00:00 | 2008-06-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2547 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2CF1210W36A12 | (GTG Common BLDG) Installation & Test - HVAC | (GTG Common BLDG) Installation & Test - HVAC | 2008-05-15 | 2008-07-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2CF1210W36A12 (GTG Common BLDG) Installation & Test - HVAC | Activity | 2CF1210W36A12 | (GTG Common BLDG) Installation & Test - HVAC | 2008-05-15 00:00:00 | 2008-07-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2548 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2CF1210W38A11 | (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2CF1210W38A11 (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | Activity | 2CF1210W38A11 | (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 00:00:00 | 2008-07-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2549 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2CF1210W90A14 | (GTG Common BLDG) Installation & Test - I&C | (GTG Common BLDG) Installation & Test - I&C | 2008-06-19 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2CF1210W90A14 (GTG Common BLDG) Installation & Test - I&C | Activity | 2CF1210W90A14 | (GTG Common BLDG) Installation & Test - I&C | 2008-06-19 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2550 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2CF1210W74A13 | (GTG Common BLDG) Installation & Test - Elec | (GTG Common BLDG) Installation & Test - Elec | 2008-06-19 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2CF1210W74A13 (GTG Common BLDG) Installation & Test - Elec | Activity | 2CF1210W74A13 | (GTG Common BLDG) Installation & Test - Elec | 2008-06-19 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2551 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG Common |  | 2CF1210W24A15 | (GTG Common BLDG) Building Finish | (GTG Common BLDG) Building Finish | 2008-06-27 | 2008-08-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG Common 2CF1210W24A15 (GTG Common BLDG) Building Finish | Activity | 2CF1210W24A15 | (GTG Common BLDG) Building Finish | 2008-06-27 00:00:00 | 2008-08-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2553 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 LEB |  | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | (GTG #21 LEB) GA & Load Data to Civil Design | 2007-05-31 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 LEB 2EF1200W00A01.1 (GTG #21 LEB) GA & Load Data to Civil Design | Activity | 2EF1200W00A01.1 | (GTG #21 LEB) GA & Load Data to Civil Design | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2554 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 LEB |  | 2EF1200W16A02 | (GTG #21 LEB) FDN Design | (GTG #21 LEB) FDN Design | 2007-08-01 | 2007-11-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 LEB 2EF1200W16A02 (GTG #21 LEB) FDN Design | Activity | 2EF1200W16A02 | (GTG #21 LEB) FDN Design | 2007-08-01 00:00:00 | 2007-11-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2555 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 LEB |  | 2EF1200W32A04 | (GTG #21 LEB) Structure Design | (GTG #21 LEB) Structure Design | 2007-08-01 | 2007-11-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 LEB 2EF1200W32A04 (GTG #21 LEB) Structure Design | Activity | 2EF1200W32A04 | (GTG #21 LEB) Structure Design | 2007-08-01 00:00:00 | 2007-11-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2556 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 LEB |  | 2CF1200W16A03 | (GTG #21 LEB) FDN Work | (GTG #21 LEB) FDN Work | 2007-11-28 | 2008-01-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 LEB 2CF1200W16A03 (GTG #21 LEB) FDN Work | Activity | 2CF1200W16A03 | (GTG #21 LEB) FDN Work | 2007-11-28 00:00:00 | 2008-01-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2557 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 LEB |  | 2CF1200W32A05 | (GTG #21 LEB) Structure Work | (GTG #21 LEB) Structure Work | 2008-01-25 | 2008-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 LEB 2CF1200W32A05 (GTG #21 LEB) Structure Work | Activity | 2CF1200W32A05 | (GTG #21 LEB) Structure Work | 2008-01-25 00:00:00 | 2008-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2558 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 LEB |  | 2CF1200W36A07 | (GTG #21 LEB) Installation & Test - HVAC | (GTG #21 LEB) Installation & Test - HVAC | 2008-05-15 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 LEB 2CF1200W36A07 (GTG #21 LEB) Installation & Test - HVAC | Activity | 2CF1200W36A07 | (GTG #21 LEB) Installation & Test - HVAC | 2008-05-15 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2559 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 LEB |  | 2CF1200W24A10 | (GTG #21 LEB) Building Finish | (GTG #21 LEB) Building Finish | 2008-05-27 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 LEB 2CF1200W24A10 (GTG #21 LEB) Building Finish | Activity | 2CF1200W24A10 | (GTG #21 LEB) Building Finish | 2008-05-27 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2560 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 LEB |  | 2CF1200W38A06 | (GTG #21 LEB) Installation & Test - Fire Fighting Sys. | (GTG #21 LEB) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 LEB 2CF1200W38A06 (GTG #21 LEB) Installation & Test - Fire Fighting Sys. | Activity | 2CF1200W38A06 | (GTG #21 LEB) Installation & Test - Fire Fighting Sys. | 2008-05-31 00:00:00 | 2008-07-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2561 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 LEB |  | 2CF1200W90A09 | (GTG #21 LEB) Installation & Test - I&C | (GTG #21 LEB) Installation & Test - I&C | 2008-06-04 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 LEB 2CF1200W90A09 (GTG #21 LEB) Installation & Test - I&C | Activity | 2CF1200W90A09 | (GTG #21 LEB) Installation & Test - I&C | 2008-06-04 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2562 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 LEB |  | 2CF1200W74A08 | (GTG #21 LEB) Installation & Test - Elec | (GTG #21 LEB) Installation & Test - Elec | 2008-06-04 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 LEB 2CF1200W74A08 (GTG #21 LEB) Installation & Test - Elec | Activity | 2CF1200W74A08 | (GTG #21 LEB) Installation & Test - Elec | 2008-06-04 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2565 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Main body | 2PF1213W42A08P | (GEN #21) P.O & Procurement | (GEN #21) P.O & Procurement | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Main body 2PF1213W42A08P (GEN #21) P.O & Procurement | Activity | 2PF1213W42A08P | (GEN #21) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2566 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Main body | 2EF1213W16A06 | (GEN #21) FDN Design | (GEN #21) FDN Design | 2007-03-30 | 2007-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Main body 2EF1213W16A06 (GEN #21) FDN Design | Activity | 2EF1213W16A06 | (GEN #21) FDN Design | 2007-03-30 00:00:00 | 2007-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2567 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Main body | 2PF1213W42A03P | (GT #21) P.O & Procurement | (GT #21) P.O & Procurement | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Main body 2PF1213W42A03P (GT #21) P.O & Procurement | Activity | 2PF1213W42A03P | (GT #21) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2568 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Main body | 2EF1213W16A01 | (GT #21) FDN Design | (GT #21) FDN Design | 2007-03-30 | 2007-06-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Main body 2EF1213W16A01 (GT #21) FDN Design | Activity | 2EF1213W16A01 | (GT #21) FDN Design | 2007-03-30 00:00:00 | 2007-06-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2569 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Main body | 2CF1213W16A07 | (GEN #21) FDN Work | (GEN #21) FDN Work | 2007-08-31 | 2008-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Main body 2CF1213W16A07 (GEN #21) FDN Work | Activity | 2CF1213W16A07 | (GEN #21) FDN Work | 2007-08-31 00:00:00 | 2008-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2570 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Main body | 2CF1213W16A02 | (GT #21) FDN Work | (GT #21) FDN Work | 2007-08-31 | 2008-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Main body 2CF1213W16A02 (GT #21) FDN Work | Activity | 2CF1213W16A02 | (GT #21) FDN Work | 2007-08-31 00:00:00 | 2008-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2571 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Main body | 2PF1213W42A09T | (GEN #21) Transportation | (GEN #21) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Main body 2PF1213W42A09T (GEN #21) Transportation | Activity | 2PF1213W42A09T | (GEN #21) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2572 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Main body | 2PF1213W42A04T | (GT #21) Transportation | (GT #21) Transportation | 2008-03-01 | 2008-04-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Main body 2PF1213W42A04T (GT #21) Transportation | Activity | 2PF1213W42A04T | (GT #21) Transportation | 2008-03-01 00:00:00 | 2008-04-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2573 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Main body | 2CF1213W42A05 | (GT #21) Installation(On FDN~Final Alignment) | (GT #21) Installation(On FDN~Final Alignment) | 2008-04-15 | 2008-08-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Main body 2CF1213W42A05 (GT #21) Installation(On FDN~Final Alignment) | Activity | 2CF1213W42A05 | (GT #21) Installation(On FDN~Final Alignment) | 2008-04-15 00:00:00 | 2008-08-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2574 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Main body | 2CF1213W42A10 | (GEN #21) Installation | (GEN #21) Installation | 2008-05-14 | 2008-09-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Main body 2CF1213W42A10 (GEN #21) Installation | Activity | 2CF1213W42A10 | (GEN #21) Installation | 2008-05-14 00:00:00 | 2008-09-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2575 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Main body | 2CF1213W52A11 | (GEN #21) Insulation | (GEN #21) Insulation | 2008-06-18 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Main body 2CF1213W52A11 (GEN #21) Insulation | Activity | 2CF1213W52A11 | (GEN #21) Insulation | 2008-06-18 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2577 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Electrical System | 2PF1255W70A01P | (GTG#21 Electrical) P.O & Procurement | (GTG#21 Electrical) P.O & Procurement | 2007-03-30 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Electrical System 2PF1255W70A01P (GTG#21 Electrical) P.O & Procurement | Activity | 2PF1255W70A01P | (GTG#21 Electrical) P.O & Procurement | 2007-03-30 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2578 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Electrical System | 2PF1255W70A02T | (GTG#21 Electrical) Transportation | (GTG#21 Electrical) Transportation | 2008-04-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Electrical System 2PF1255W70A02T (GTG#21 Electrical) Transportation | Activity | 2PF1255W70A02T | (GTG#21 Electrical) Transportation | 2008-04-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2579 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Electrical System | 2CF1255W70A03 | (GTG#21 Electrical) Installation- PCC | (GTG#21 Electrical) Installation- PCC | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Electrical System 2CF1255W70A03 (GTG#21 Electrical) Installation- PCC | Activity | 2CF1255W70A03 | (GTG#21 Electrical) Installation- PCC | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2580 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Electrical System | 2CF1255W70A04 | (GTG#21 Electrical) Installation- MCC | (GTG#21 Electrical) Installation- MCC | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Electrical System 2CF1255W70A04 (GTG#21 Electrical) Installation- MCC | Activity | 2CF1255W70A04 | (GTG#21 Electrical) Installation- MCC | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2581 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Electrical System | 2CF1255W70A05 | (GTG#21 Electrical) Installation- Protection Sys. | (GTG#21 Electrical) Installation- Protection Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Electrical System 2CF1255W70A05 (GTG#21 Electrical) Installation- Protection Sys. | Activity | 2CF1255W70A05 | (GTG#21 Electrical) Installation- Protection Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2582 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Electrical System | 2CF1255W70A07 | (GTG#21 Electrical) Installation- SEE&SFC Sys. | (GTG#21 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Electrical System 2CF1255W70A07 (GTG#21 Electrical) Installation- SEE&SFC Sys. | Activity | 2CF1255W70A07 | (GTG#21 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2583 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Electrical System | 2CF1255W70A08 | (GTG#21 Electrical) Installation- DC&UPS Sys. | (GTG#21 Electrical) Installation- DC&UPS Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Electrical System 2CF1255W70A08 (GTG#21 Electrical) Installation- DC&UPS Sys. | Activity | 2CF1255W70A08 | (GTG#21 Electrical) Installation- DC&UPS Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2584 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Electrical System | 2CF1255W74A09 | (GTG#21 Electrical) Cable work | (GTG#21 Electrical) Cable work | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Electrical System 2CF1255W74A09 (GTG#21 Electrical) Cable work | Activity | 2CF1255W74A09 | (GTG#21 Electrical) Cable work | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2585 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Electrical System | 2CF1255W86A06 | (GTG#21 Electrical) Installation- GT control Sys. | (GTG#21 Electrical) Installation- GT control Sys. | 2008-08-04 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Electrical System 2CF1255W86A06 (GTG#21 Electrical) Installation- GT control Sys. | Activity | 2CF1255W86A06 | (GTG#21 Electrical) Installation- GT control Sys. | 2008-08-04 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2586 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Electrical System | 2CF1255W62A10 | (GTG#21 Electrical) Electrical Function Test | (GTG#21 Electrical) Electrical Function Test | 2008-09-16 | 2008-09-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Electrical System 2CF1255W62A10 (GTG#21 Electrical) Electrical Function Test | Activity | 2CF1255W62A10 | (GTG#21 Electrical) Electrical Function Test | 2008-09-16 00:00:00 | 2008-09-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2587 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Electrical System | 2CF1255W62A11 | (GTG#21 Electrical) Loop Test | (GTG#21 Electrical) Loop Test | 2008-09-22 | 2008-09-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Electrical System 2CF1255W62A11 (GTG#21 Electrical) Loop Test | Activity | 2CF1255W62A11 | (GTG#21 Electrical) Loop Test | 2008-09-22 00:00:00 | 2008-09-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2589 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Starting System(Turning Device) | 2PF1265W42A01P | (Turning Gear) P.O & Procurement | (Turning Gear) P.O & Procurement | 2007-03-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Starting System(Turning Device) 2PF1265W42A01P (Turning Gear) P.O & Procurement | Activity | 2PF1265W42A01P | (Turning Gear) P.O & Procurement | 2007-03-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2590 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Starting System(Turning Device) | 2PF1265W42A02T | (Turning Gear) Transportation | (Turning Gear) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Starting System(Turning Device) 2PF1265W42A02T (Turning Gear) Transportation | Activity | 2PF1265W42A02T | (Turning Gear) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2591 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Starting System(Turning Device) | 2CF1265W42A03 | (Turning Gear) Installation | (Turning Gear) Installation | 2008-05-16 | 2008-05-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Starting System(Turning Device) 2CF1265W42A03 (Turning Gear) Installation | Activity | 2CF1265W42A03 | (Turning Gear) Installation | 2008-05-16 00:00:00 | 2008-05-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2592 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Starting System(Turning Device) | 2CF1265W74A04 | (Turning Gear) Installation- Elec. | (Turning Gear) Installation- Elec. | 2008-05-24 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Starting System(Turning Device) 2CF1265W74A04 (Turning Gear) Installation- Elec. | Activity | 2CF1265W74A04 | (Turning Gear) Installation- Elec. | 2008-05-24 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2593 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Starting System(Turning Device) | 2CF1265W90A05 | (Turning Gear) Installation- I&C | (Turning Gear) Installation- I&C | 2008-05-24 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Starting System(Turning Device) 2CF1265W90A05 (Turning Gear) Installation- I&C | Activity | 2CF1265W90A05 | (Turning Gear) Installation- I&C | 2008-05-24 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2594 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Starting System(Turning Device) | 2SF1265W62A06 | (Turning Gear) Loop check | (Turning Gear) Loop check | 2008-06-01 | 2008-06-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Starting System(Turning Device) 2SF1265W62A06 (Turning Gear) Loop check | Activity | 2SF1265W62A06 | (Turning Gear) Loop check | 2008-06-01 00:00:00 | 2008-06-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2595 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Starting System(Turning Device) | 2SF1265W62A07.0 | (Turning Gear) Function Test | (Turning Gear) Function Test | 2008-06-23 | 2008-06-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Starting System(Turning Device) 2SF1265W62A07.0 (Turning Gear) Function Test | Activity | 2SF1265W62A07.0 | (Turning Gear) Function Test | 2008-06-23 00:00:00 | 2008-06-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2597 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air and Flue Gas System | 2PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air and Flue Gas System 2PF1265W64A01P (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | Activity | 2PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2598 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air and Flue Gas System | 2PF1265W64A02T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air and Flue Gas System 2PF1265W64A02T (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | Activity | 2PF1265W64A02T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2599 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air and Flue Gas System | 2CF1265W64A03 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-04-16 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air and Flue Gas System 2CF1265W64A03 (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | Activity | 2CF1265W64A03 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-04-16 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2600 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air and Flue Gas System | 2CF1265W64A04 | (Air&Flue Gas System) Duct work | (Air&Flue Gas System) Duct work | 2008-05-17 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air and Flue Gas System 2CF1265W64A04 (Air&Flue Gas System) Duct work | Activity | 2CF1265W64A04 | (Air&Flue Gas System) Duct work | 2008-05-17 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2601 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air and Flue Gas System | 2CF1265W74A05 | (Air&Flue Gas System) Installation- Elec. | (Air&Flue Gas System) Installation- Elec. | 2008-06-02 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air and Flue Gas System 2CF1265W74A05 (Air&Flue Gas System) Installation- Elec. | Activity | 2CF1265W74A05 | (Air&Flue Gas System) Installation- Elec. | 2008-06-02 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2602 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air and Flue Gas System | 2CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | (Air&Flue Gas System) Installation- I&C | 2008-06-02 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air and Flue Gas System 2CF1265W90A06 (Air&Flue Gas System) Installation- I&C | Activity | 2CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | 2008-06-02 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2603 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air and Flue Gas System | 2SF1265W62A07 | (Air&Flue Gas System) Loop chek | (Air&Flue Gas System) Loop chek | 2008-06-12 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air and Flue Gas System 2SF1265W62A07 (Air&Flue Gas System) Loop chek | Activity | 2SF1265W62A07 | (Air&Flue Gas System) Loop chek | 2008-06-12 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2604 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air and Flue Gas System | 2SF1265W62A08 | (Air&Flue Gas System) Function Test | (Air&Flue Gas System) Function Test | 2008-06-15 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air and Flue Gas System 2SF1265W62A08 (Air&Flue Gas System) Function Test | Activity | 2SF1265W62A08 | (Air&Flue Gas System) Function Test | 2008-06-15 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2606 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2PF1230W20A02P | (Air Intake) P.O & Procurement_Steel Sturucture | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2PF1230W20A02P (Air Intake) P.O & Procurement_Steel Sturucture | Activity | 2PF1230W20A02P | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2607 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2PF1230W64A05P | (Air Intake) P.O & Procurement_Inlet Duct | (Air Intake) P.O & Procurement_Inlet Duct | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2PF1230W64A05P (Air Intake) P.O & Procurement_Inlet Duct | Activity | 2PF1230W64A05P | (Air Intake) P.O & Procurement_Inlet Duct | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2608 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2PF1230W64A08P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2PF1230W64A08P (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 2PF1230W64A08P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2609 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2CF1230W16A01 | (Air Intake) FDN Work_Steel Sturucture | (Air Intake) FDN Work_Steel Sturucture | 2007-10-31 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2CF1230W16A01 (Air Intake) FDN Work_Steel Sturucture | Activity | 2CF1230W16A01 | (Air Intake) FDN Work_Steel Sturucture | 2007-10-31 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2610 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2PF1230W20A03T | (Air Intake) Transportation_Steel Sturucture | (Air Intake) Transportation_Steel Sturucture | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2PF1230W20A03T (Air Intake) Transportation_Steel Sturucture | Activity | 2PF1230W20A03T | (Air Intake) Transportation_Steel Sturucture | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2611 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2PF1230W64A06T | (Air Intake) Transportation_Inlet Duct | (Air Intake) Transportation_Inlet Duct | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2PF1230W64A06T (Air Intake) Transportation_Inlet Duct | Activity | 2PF1230W64A06T | (Air Intake) Transportation_Inlet Duct | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2612 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2PF1230W64A09T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2PF1230W64A09T (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 2PF1230W64A09T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2613 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2CF1230W20A04 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-04-16 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2CF1230W20A04 (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | Activity | 2CF1230W20A04 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-04-16 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2614 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2CF1230W64A07 | (Air Intake) Installation_Inlet Duct | (Air Intake) Installation_Inlet Duct | 2008-05-19 | 2008-05-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2CF1230W64A07 (Air Intake) Installation_Inlet Duct | Activity | 2CF1230W64A07 | (Air Intake) Installation_Inlet Duct | 2008-05-19 00:00:00 | 2008-05-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2615 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2CF1230W64A10 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-05-27 | 2008-06-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2CF1230W64A10 (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 2CF1230W64A10 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-05-27 00:00:00 | 2008-06-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2616 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2CF1230W74A11 | (Air Intake) Installation- Elec. | (Air Intake) Installation- Elec. | 2008-06-20 | 2008-07-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2CF1230W74A11 (Air Intake) Installation- Elec. | Activity | 2CF1230W74A11 | (Air Intake) Installation- Elec. | 2008-06-20 00:00:00 | 2008-07-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2617 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2CF1230W90A12 | (Air Intake) Installation- I&C | (Air Intake) Installation- I&C | 2008-06-20 | 2008-07-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2CF1230W90A12 (Air Intake) Installation- I&C | Activity | 2CF1230W90A12 | (Air Intake) Installation- I&C | 2008-06-20 00:00:00 | 2008-07-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2618 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2SF1230W62A13 | (Air Intake) Loop chek | (Air Intake) Loop chek | 2008-07-04 | 2008-07-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2SF1230W62A13 (Air Intake) Loop chek | Activity | 2SF1230W62A13 | (Air Intake) Loop chek | 2008-07-04 00:00:00 | 2008-07-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2619 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2SF1230W62A14 | (Air Intake) Function Test | (Air Intake) Function Test | 2008-07-10 | 2008-07-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2SF1230W62A14 (Air Intake) Function Test | Activity | 2SF1230W62A14 | (Air Intake) Function Test | 2008-07-10 00:00:00 | 2008-07-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2620 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Air Intake System | 2SF1230W62A15 | (Air Intake) Load(Running) Test | (Air Intake) Load(Running) Test | 2008-07-13 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Air Intake System 2SF1230W62A15 (Air Intake) Load(Running) Test | Activity | 2SF1230W62A15 | (Air Intake) Load(Running) Test | 2008-07-13 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2622 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2PF1250W42A02P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-03-30 | 2008-02-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2PF1250W42A02P (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | Activity | 2PF1250W42A02P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-03-30 00:00:00 | 2008-02-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2623 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-03-30 | 2008-02-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2PF1250W42A06P (Lube Oil System) P.O & Procurement_Lube oil functional Module | Activity | 2PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-03-30 00:00:00 | 2008-02-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2624 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2PF1250W42A10P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-03-30 | 2008-02-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2PF1250W42A10P (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | Activity | 2PF1250W42A10P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-03-30 00:00:00 | 2008-02-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2625 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2CF1250W16A01 | (Lube Oil System) FDN Work_Lube Oil Supply Module | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-10-31 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2CF1250W16A01 (Lube Oil System) FDN Work_Lube Oil Supply Module | Activity | 2CF1250W16A01 | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-10-31 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2626 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2CF1250W16A05 | (Lube Oil System) FDN Work_Lube oil functional Module | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-10-31 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2CF1250W16A05 (Lube Oil System) FDN Work_Lube oil functional Module | Activity | 2CF1250W16A05 | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-10-31 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2627 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2CF1250W16A09 | (Lube Oil System) FDN Work_Lube oil Mist Separator | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-10-31 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2CF1250W16A09 (Lube Oil System) FDN Work_Lube oil Mist Separator | Activity | 2CF1250W16A09 | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-10-31 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2628 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2PF1250W42A03T | (Lube Oil System) Transportation_Lube Oil Supply Module | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-02-29 | 2008-04-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2PF1250W42A03T (Lube Oil System) Transportation_Lube Oil Supply Module | Activity | 2PF1250W42A03T | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-02-29 00:00:00 | 2008-04-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2629 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2PF1250W42A07T | (Lube Oil System) Transportation_Lube oil functional Module | (Lube Oil System) Transportation_Lube oil functional Module | 2008-02-29 | 2008-04-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2PF1250W42A07T (Lube Oil System) Transportation_Lube oil functional Module | Activity | 2PF1250W42A07T | (Lube Oil System) Transportation_Lube oil functional Module | 2008-02-29 00:00:00 | 2008-04-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2630 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2PF1250W42A11T | (Lube Oil System) Transportation_Lube oil Mist Separator | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-02-29 | 2008-04-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2PF1250W42A11T (Lube Oil System) Transportation_Lube oil Mist Separator | Activity | 2PF1250W42A11T | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-02-29 00:00:00 | 2008-04-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2631 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2CF1250W42A04 | (Lube Oil System) Installation_Lube Oil Supply Module | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-04-15 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2CF1250W42A04 (Lube Oil System) Installation_Lube Oil Supply Module | Activity | 2CF1250W42A04 | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-04-15 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2632 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2CF1250W42A08 | (Lube Oil System) Installation_Lube oil functional Module | (Lube Oil System) Installation_Lube oil functional Module | 2008-04-15 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2CF1250W42A08 (Lube Oil System) Installation_Lube oil functional Module | Activity | 2CF1250W42A08 | (Lube Oil System) Installation_Lube oil functional Module | 2008-04-15 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2633 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2CF1250W42A12 | (Lube Oil System) Installation_Lube oil Mist Separator | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-04-15 | 2008-04-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2CF1250W42A12 (Lube Oil System) Installation_Lube oil Mist Separator | Activity | 2CF1250W42A12 | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-04-15 00:00:00 | 2008-04-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2634 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2CF1250W58A13 | (Lube Oil System) Piping work | (Lube Oil System) Piping work | 2008-05-01 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2CF1250W58A13 (Lube Oil System) Piping work | Activity | 2CF1250W58A13 | (Lube Oil System) Piping work | 2008-05-01 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2635 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2CF1250W62A16 | (GTG #11) Lube Oil Flushing | (GTG #11) Lube Oil Flushing | 2008-05-31 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2CF1250W62A16 (GTG #11) Lube Oil Flushing | Activity | 2CF1250W62A16 | (GTG #11) Lube Oil Flushing | 2008-05-31 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2636 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2CF1250W74A14 | (Lube Oil System) Installation- Elec. | (Lube Oil System) Installation- Elec. | 2008-06-02 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2CF1250W74A14 (Lube Oil System) Installation- Elec. | Activity | 2CF1250W74A14 | (Lube Oil System) Installation- Elec. | 2008-06-02 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2637 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2CF1250W90A15 | (Lube Oil System) Installation- I&C | (Lube Oil System) Installation- I&C | 2008-06-02 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2CF1250W90A15 (Lube Oil System) Installation- I&C | Activity | 2CF1250W90A15 | (Lube Oil System) Installation- I&C | 2008-06-02 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2638 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2SF1250W62A17 | (Lube Oil System) Loop chek | (Lube Oil System) Loop chek | 2008-06-15 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2SF1250W62A17 (Lube Oil System) Loop chek | Activity | 2SF1250W62A17 | (Lube Oil System) Loop chek | 2008-06-15 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2639 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2SF1250W62A18 | (Lube Oil System) Function Test | (Lube Oil System) Function Test | 2008-06-18 | 2008-06-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2SF1250W62A18 (Lube Oil System) Function Test | Activity | 2SF1250W62A18 | (Lube Oil System) Function Test | 2008-06-18 00:00:00 | 2008-06-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2640 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Lube Oil System | 2SF1250W62A19 | (Lube Oil System) Load Test | (Lube Oil System) Load Test | 2008-06-21 | 2008-06-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Lube Oil System 2SF1250W62A19 (Lube Oil System) Load Test | Activity | 2SF1250W62A19 | (Lube Oil System) Load Test | 2008-06-21 00:00:00 | 2008-06-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2642 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Generator Seal Oil System | 2PF1250W42A02.1P | (GEN Seal Oil Sys.) P.O & Procurement | (GEN Seal Oil Sys.) P.O & Procurement | 2007-03-30 | 2008-02-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Generator Seal Oil System 2PF1250W42A02.1P (GEN Seal Oil Sys.) P.O & Procurement | Activity | 2PF1250W42A02.1P | (GEN Seal Oil Sys.) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2643 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Generator Seal Oil System | 2CF1250W16A01.1 | (GEN Seal Oil Sys.) FDN Work | (GEN Seal Oil Sys.) FDN Work | 2007-10-31 | 2008-01-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Generator Seal Oil System 2CF1250W16A01.1 (GEN Seal Oil Sys.) FDN Work | Activity | 2CF1250W16A01.1 | (GEN Seal Oil Sys.) FDN Work | 2007-10-31 00:00:00 | 2008-01-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2644 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Generator Seal Oil System | 2PF1250W42A03.1T | (GEN Seal Oil Sys.) Transportation | (GEN Seal Oil Sys.) Transportation | 2008-02-29 | 2008-04-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Generator Seal Oil System 2PF1250W42A03.1T (GEN Seal Oil Sys.) Transportation | Activity | 2PF1250W42A03.1T | (GEN Seal Oil Sys.) Transportation | 2008-02-29 00:00:00 | 2008-04-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2645 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Generator Seal Oil System | 2CF1250W42A04.1 | (GEN Seal Oil Sys.) Installation | (GEN Seal Oil Sys.) Installation | 2008-04-15 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Generator Seal Oil System 2CF1250W42A04.1 (GEN Seal Oil Sys.) Installation | Activity | 2CF1250W42A04.1 | (GEN Seal Oil Sys.) Installation | 2008-04-15 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2646 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Generator Seal Oil System | 2CF1250W58A05.1 | (GEN Seal Oil Sys.) Piping Work | (GEN Seal Oil Sys.) Piping Work | 2008-04-30 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Generator Seal Oil System 2CF1250W58A05.1 (GEN Seal Oil Sys.) Piping Work | Activity | 2CF1250W58A05.1 | (GEN Seal Oil Sys.) Piping Work | 2008-04-30 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2647 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Generator Seal Oil System | 2CF1250W74A06.1 | (GEN Seal Oil Sys.) Installation- Elec. | (GEN Seal Oil Sys.) Installation- Elec. | 2008-05-31 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Generator Seal Oil System 2CF1250W74A06.1 (GEN Seal Oil Sys.) Installation- Elec. | Activity | 2CF1250W74A06.1 | (GEN Seal Oil Sys.) Installation- Elec. | 2008-05-31 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2648 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Generator Seal Oil System | 2CF1250W90A07.1 | (GEN Seal Oil Sys.) Installation- I&C | (GEN Seal Oil Sys.) Installation- I&C | 2008-05-31 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Generator Seal Oil System 2CF1250W90A07.1 (GEN Seal Oil Sys.) Installation- I&C | Activity | 2CF1250W90A07.1 | (GEN Seal Oil Sys.) Installation- I&C | 2008-05-31 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2649 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Generator Seal Oil System | 2SF1250W62A08.1 | (GEN Seal Oil Sys.) Oil Flushing | (GEN Seal Oil Sys.) Oil Flushing | 2008-05-31 | 2008-06-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Generator Seal Oil System 2SF1250W62A08.1 (GEN Seal Oil Sys.) Oil Flushing | Activity | 2SF1250W62A08.1 | (GEN Seal Oil Sys.) Oil Flushing | 2008-05-31 00:00:00 | 2008-06-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2650 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Generator Seal Oil System | 2SF1250W62A09.1 | (GEN Seal Oil Sys.) Loop chek | (GEN Seal Oil Sys.) Loop chek | 2008-06-14 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Generator Seal Oil System 2SF1250W62A09.1 (GEN Seal Oil Sys.) Loop chek | Activity | 2SF1250W62A09.1 | (GEN Seal Oil Sys.) Loop chek | 2008-06-14 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2651 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Generator Seal Oil System | 2SF1250W62A10.1 | (GEN Seal Oil Sys.) Function Test | (GEN Seal Oil Sys.) Function Test | 2008-06-17 | 2008-06-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Generator Seal Oil System 2SF1250W62A10.1 (GEN Seal Oil Sys.) Function Test | Activity | 2SF1250W62A10.1 | (GEN Seal Oil Sys.) Function Test | 2008-06-17 00:00:00 | 2008-06-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2653 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2PF1265W42A03P | (Gas Final Filter & Metering Skid) P.O & Procurement | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-03-30 | 2008-02-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2PF1265W42A03P (Gas Final Filter & Metering Skid) P.O & Procurement | Activity | 2PF1265W42A03P | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2654 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | (Gas Final Filter & Metering Skid) FDN Design | 2007-03-30 | 2007-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2EF1265W16A01 (Gas Final Filter & Metering Skid) FDN Design | Activity | 2EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | 2007-03-30 00:00:00 | 2007-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2655 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2PF1265W42A13P | (TCA Cooler) P.O & Procurement | (TCA Cooler) P.O & Procurement | 2007-03-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2PF1265W42A13P (TCA Cooler) P.O & Procurement | Activity | 2PF1265W42A13P | (TCA Cooler) P.O & Procurement | 2007-03-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2656 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2CF1265W16A02 | (Gas Final Filter & Metering Skid) FDN Work | (Gas Final Filter & Metering Skid) FDN Work | 2007-10-02 | 2007-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2CF1265W16A02 (Gas Final Filter & Metering Skid) FDN Work | Activity | 2CF1265W16A02 | (Gas Final Filter & Metering Skid) FDN Work | 2007-10-02 00:00:00 | 2007-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2657 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2CF1265W16A12 | (TCA Cooler) FDN Work | (TCA Cooler) FDN Work | 2007-10-31 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2CF1265W16A12 (TCA Cooler) FDN Work | Activity | 2CF1265W16A12 | (TCA Cooler) FDN Work | 2007-10-31 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2658 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2PF1265W42A04T | (Gas Final Filter & Metering Skid) Transportation | (Gas Final Filter & Metering Skid) Transportation | 2008-02-29 | 2008-04-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2PF1265W42A04T (Gas Final Filter & Metering Skid) Transportation | Activity | 2PF1265W42A04T | (Gas Final Filter & Metering Skid) Transportation | 2008-02-29 00:00:00 | 2008-04-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2659 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2PF1265W42A14T | (TCA Cooler) Transportation | (TCA Cooler) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2PF1265W42A14T (TCA Cooler) Transportation | Activity | 2PF1265W42A14T | (TCA Cooler) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2660 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2CF1265W42A05 | (Gas Final Filter & Metering Skid) Installation | (Gas Final Filter & Metering Skid) Installation | 2008-04-15 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2CF1265W42A05 (Gas Final Filter & Metering Skid) Installation | Activity | 2CF1265W42A05 | (Gas Final Filter & Metering Skid) Installation | 2008-04-15 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2661 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2CF1265W42A15 | (TCA Cooler) Installation | (TCA Cooler) Installation | 2008-05-16 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2CF1265W42A15 (TCA Cooler) Installation | Activity | 2CF1265W42A15 | (TCA Cooler) Installation | 2008-05-16 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2662 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2CF1265W58A06 | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | 2008-06-19 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2CF1265W58A06 (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | Activity | 2CF1265W58A06 | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | 2008-06-19 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2663 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2CF1265W74A07 | (FGSS) Installation- Elec. | (FGSS) Installation- Elec. | 2008-08-05 | 2008-08-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2CF1265W74A07 (FGSS) Installation- Elec. | Activity | 2CF1265W74A07 | (FGSS) Installation- Elec. | 2008-08-05 00:00:00 | 2008-08-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2664 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2CF1265W90A08 | (FGSS) Installation- I&C | (FGSS) Installation- I&C | 2008-08-05 | 2008-08-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2CF1265W90A08 (FGSS) Installation- I&C | Activity | 2CF1265W90A08 | (FGSS) Installation- I&C | 2008-08-05 00:00:00 | 2008-08-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2665 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2SF1265W62A09 | (FGSS) Loop chek | (FGSS) Loop chek | 2008-09-03 | 2008-09-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2SF1265W62A09 (FGSS) Loop chek | Activity | 2SF1265W62A09 | (FGSS) Loop chek | 2008-09-03 00:00:00 | 2008-09-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2666 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2SF1265W62A10.0 | (FGSS) Function Test | (FGSS) Function Test | 2008-09-13 | 2008-09-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2SF1265W62A10.0 (FGSS) Function Test | Activity | 2SF1265W62A10.0 | (FGSS) Function Test | 2008-09-13 00:00:00 | 2008-09-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2667 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Gas Supply System | 2SF1265W62A11.0 | (FGSS) Gas Receiving upto GT Final Control Valve | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-09-22 | 2008-09-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Gas Supply System 2SF1265W62A11.0 (FGSS) Gas Receiving upto GT Final Control Valve | Activity | 2SF1265W62A11.0 | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-09-22 00:00:00 | 2008-09-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2669 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Washing & Drain System | 2PF1265W42A02.0P | (Washing & Drain system Skid) P.O & Procurement | (Washing & Drain system Skid) P.O & Procurement | 2007-03-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Washing & Drain System 2PF1265W42A02.0P (Washing & Drain system Skid) P.O & Procurement | Activity | 2PF1265W42A02.0P | (Washing & Drain system Skid) P.O & Procurement | 2007-03-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2670 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Washing & Drain System | 2CF1265W16A01 | (Washing & Drain system Skid) FDN Work | (Washing & Drain system Skid) FDN Work | 2007-10-31 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Washing & Drain System 2CF1265W16A01 (Washing & Drain system Skid) FDN Work | Activity | 2CF1265W16A01 | (Washing & Drain system Skid) FDN Work | 2007-10-31 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2671 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Washing & Drain System | 2PF1265W42A03.0T | (Washing & Drain system Skid) Transportation | (Washing & Drain system Skid) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Washing & Drain System 2PF1265W42A03.0T (Washing & Drain system Skid) Transportation | Activity | 2PF1265W42A03.0T | (Washing & Drain system Skid) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2672 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Washing & Drain System | 2CF1265W42A04 | (Washing & Drain system Skid) Installation | (Washing & Drain system Skid) Installation | 2008-05-16 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Washing & Drain System 2CF1265W42A04 (Washing & Drain system Skid) Installation | Activity | 2CF1265W42A04 | (Washing & Drain system Skid) Installation | 2008-05-16 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2673 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Washing & Drain System | 2CF1265W58A05 | (Washing & Drain system Skid) Piping work | (Washing & Drain system Skid) Piping work | 2008-06-03 | 2008-07-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Washing & Drain System 2CF1265W58A05 (Washing & Drain system Skid) Piping work | Activity | 2CF1265W58A05 | (Washing & Drain system Skid) Piping work | 2008-06-03 00:00:00 | 2008-07-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2674 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Washing & Drain System | 2CF1265W74A06 | (Washing & Drain system Skid) Installation- Elec. | (Washing & Drain system Skid) Installation- Elec. | 2008-07-04 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Washing & Drain System 2CF1265W74A06 (Washing & Drain system Skid) Installation- Elec. | Activity | 2CF1265W74A06 | (Washing & Drain system Skid) Installation- Elec. | 2008-07-04 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2675 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Washing & Drain System | 2CF1265W90A07 | (Washing & Drain system Skid) Installation- I&C | (Washing & Drain system Skid) Installation- I&C | 2008-07-04 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Washing & Drain System 2CF1265W90A07 (Washing & Drain system Skid) Installation- I&C | Activity | 2CF1265W90A07 | (Washing & Drain system Skid) Installation- I&C | 2008-07-04 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2676 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Washing & Drain System | 2CF1265W62A08 | (Washing & Drain system Skid) Flushing | (Washing & Drain system Skid) Flushing | 2008-07-04 | 2008-07-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Washing & Drain System 2CF1265W62A08 (Washing & Drain system Skid) Flushing | Activity | 2CF1265W62A08 | (Washing & Drain system Skid) Flushing | 2008-07-04 00:00:00 | 2008-07-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2677 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Washing & Drain System | 2SF1265W62A09.0 | (Washing & Drain system Skid) Loop chek | (Washing & Drain system Skid) Loop chek | 2008-07-18 | 2008-07-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Washing & Drain System 2SF1265W62A09.0 (Washing & Drain system Skid) Loop chek | Activity | 2SF1265W62A09.0 | (Washing & Drain system Skid) Loop chek | 2008-07-18 00:00:00 | 2008-07-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2678 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Washing & Drain System | 2SF1265W62A10 | (Washing & Drain system Skid) Function Test | (Washing & Drain system Skid) Function Test | 2008-07-23 | 2008-07-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Washing & Drain System 2SF1265W62A10 (Washing & Drain system Skid) Function Test | Activity | 2SF1265W62A10 | (Washing & Drain system Skid) Function Test | 2008-07-23 00:00:00 | 2008-07-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2679 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Washing & Drain System | 2SF1265W62A11 | (Washing & Drain system Skid) Load(Running) Test | (Washing & Drain system Skid) Load(Running) Test | 2008-08-12 | 2008-08-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Washing & Drain System 2SF1265W62A11 (Washing & Drain system Skid) Load(Running) Test | Activity | 2SF1265W62A11 | (Washing & Drain system Skid) Load(Running) Test | 2008-08-12 00:00:00 | 2008-08-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2681 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2PF1265W42A02.2P | (Fuel oil injection System) P.O & Procurement | (Fuel oil injection System) P.O & Procurement | 2007-03-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2PF1265W42A02.2P (Fuel oil injection System) P.O & Procurement | Activity | 2PF1265W42A02.2P | (Fuel oil injection System) P.O & Procurement | 2007-03-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2682 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2PF1265W42A09P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2PF1265W42A09P (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | Activity | 2PF1265W42A09P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2683 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2PF1265W42A16P | (Water injection System) P.O & Procurement | (Water injection System) P.O & Procurement | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2PF1265W42A16P (Water injection System) P.O & Procurement | Activity | 2PF1265W42A16P | (Water injection System) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2684 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2CF1265W16A01.0 | (Fuel oil injection System) FDN Work | (Fuel oil injection System) FDN Work | 2007-10-31 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2CF1265W16A01.0 (Fuel oil injection System) FDN Work | Activity | 2CF1265W16A01.0 | (Fuel oil injection System) FDN Work | 2007-10-31 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2685 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2CF1265W16A08 | (Fuel oil injection Pump & actuator) FDN Work | (Fuel oil injection Pump & actuator) FDN Work | 2007-10-31 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2CF1265W16A08 (Fuel oil injection Pump & actuator) FDN Work | Activity | 2CF1265W16A08 | (Fuel oil injection Pump & actuator) FDN Work | 2007-10-31 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2686 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2CF1265W16A15 | (Water injection System) FDN Work | (Water injection System) FDN Work | 2007-10-31 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2CF1265W16A15 (Water injection System) FDN Work | Activity | 2CF1265W16A15 | (Water injection System) FDN Work | 2007-10-31 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2687 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2PF1265W42A10T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2PF1265W42A10T (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | Activity | 2PF1265W42A10T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2688 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2PF1265W42A17T | (Water injection System) Transportation | (Water injection System) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2PF1265W42A17T (Water injection System) Transportation | Activity | 2PF1265W42A17T | (Water injection System) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2689 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2PF1265W42A03.2T | (Fuel oil injection System) Transportation | (Fuel oil injection System) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2PF1265W42A03.2T (Fuel oil injection System) Transportation | Activity | 2PF1265W42A03.2T | (Fuel oil injection System) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2690 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2CF1265W42A11 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2CF1265W42A11 (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | Activity | 2CF1265W42A11 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2691 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2CF1265W42A18 | (Water injection System) Installation | (Water injection System) Installation | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2CF1265W42A18 (Water injection System) Installation | Activity | 2CF1265W42A18 | (Water injection System) Installation | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2692 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2CF1265W58A19 | (Water injection System) Piping work | (Water injection System) Piping work | 2008-05-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2CF1265W58A19 (Water injection System) Piping work | Activity | 2CF1265W58A19 | (Water injection System) Piping work | 2008-05-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2693 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2CF1265W42A04.0 | (Fuel oil injection System) Installation | (Fuel oil injection System) Installation | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2CF1265W42A04.0 (Fuel oil injection System) Installation | Activity | 2CF1265W42A04.0 | (Fuel oil injection System) Installation | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2694 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2CF1265W74A20 | (Water injection System) Installation- Elec. | (Water injection System) Installation- Elec. | 2008-05-16 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2CF1265W74A20 (Water injection System) Installation- Elec. | Activity | 2CF1265W74A20 | (Water injection System) Installation- Elec. | 2008-05-16 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2695 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2CF1265W90A21 | (Water injection System) Installation- I&C | (Water injection System) Installation- I&C | 2008-05-16 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2CF1265W90A21 (Water injection System) Installation- I&C | Activity | 2CF1265W90A21 | (Water injection System) Installation- I&C | 2008-05-16 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2696 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2SF1265W62A22 | (Water injection System) Loop chek | (Water injection System) Loop chek | 2008-05-30 | 2008-06-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2SF1265W62A22 (Water injection System) Loop chek | Activity | 2SF1265W62A22 | (Water injection System) Loop chek | 2008-05-30 00:00:00 | 2008-06-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2697 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2CF1265W58A05.0 | (Fuel oil injection System) Piping work | (Fuel oil injection System) Piping work | 2008-05-31 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2CF1265W58A05.0 (Fuel oil injection System) Piping work | Activity | 2CF1265W58A05.0 | (Fuel oil injection System) Piping work | 2008-05-31 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2698 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2SF1265W62A23 | (Water injection System) Function Test | (Water injection System) Function Test | 2008-06-04 | 2008-06-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2SF1265W62A23 (Water injection System) Function Test | Activity | 2SF1265W62A23 | (Water injection System) Function Test | 2008-06-04 00:00:00 | 2008-06-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2699 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2CF1265W74A06.0 | (Fuel oil injection System) Installation- Elec. | (Fuel oil injection System) Installation- Elec. | 2008-06-16 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2CF1265W74A06.0 (Fuel oil injection System) Installation- Elec. | Activity | 2CF1265W74A06.0 | (Fuel oil injection System) Installation- Elec. | 2008-06-16 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2700 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2CF1265W90A07.0 | (Fuel oil injection System) Installation- I&C | (Fuel oil injection System) Installation- I&C | 2008-06-16 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2CF1265W90A07.0 (Fuel oil injection System) Installation- I&C | Activity | 2CF1265W90A07.0 | (Fuel oil injection System) Installation- I&C | 2008-06-16 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2701 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2SF1265W62A12 | (Fuel oil injection System) Loop chek | (Fuel oil injection System) Loop chek | 2008-06-29 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2SF1265W62A12 (Fuel oil injection System) Loop chek | Activity | 2SF1265W62A12 | (Fuel oil injection System) Loop chek | 2008-06-29 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2702 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2SF1265W62A24 | (Water injection System) Load Test | (Water injection System) Load Test | 2008-08-12 | 2008-08-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2SF1265W62A24 (Water injection System) Load Test | Activity | 2SF1265W62A24 | (Water injection System) Load Test | 2008-08-12 00:00:00 | 2008-08-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2703 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2SF1265W62A13 | (Fuel oil injection System) Function Test | (Fuel oil injection System) Function Test | 2008-08-15 | 2008-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2SF1265W62A13 (Fuel oil injection System) Function Test | Activity | 2SF1265W62A13 | (Fuel oil injection System) Function Test | 2008-08-15 00:00:00 | 2008-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2704 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fuel Oil Injection System | 2SF1265W62A14 | (Fuel oil injection System) Flushing | (Fuel oil injection System) Flushing | 2008-08-30 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fuel Oil Injection System 2SF1265W62A14 (Fuel oil injection System) Flushing | Activity | 2SF1265W62A14 | (Fuel oil injection System) Flushing | 2008-08-30 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2706 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Vibration Monitoring System (VMS) | 2PF1260W86A02P | (VMS) P.O & Procurement for GT | (VMS) P.O & Procurement for GT | 2007-08-31 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Vibration Monitoring System (VMS) 2PF1260W86A02P (VMS) P.O & Procurement for GT | Activity | 2PF1260W86A02P | (VMS) P.O & Procurement for GT | 2007-08-31 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2707 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Vibration Monitoring System (VMS) | 2PF1260W86A03T | (VMS) Transportation for GT | (VMS) Transportation for GT | 2008-06-03 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Vibration Monitoring System (VMS) 2PF1260W86A03T (VMS) Transportation for GT | Activity | 2PF1260W86A03T | (VMS) Transportation for GT | 2008-06-03 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2708 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Vibration Monitoring System (VMS) | 2CF1260W86A04 | (VMS) Installation for GT | (VMS) Installation for GT | 2008-08-29 | 2008-09-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Vibration Monitoring System (VMS) 2CF1260W86A04 (VMS) Installation for GT | Activity | 2CF1260W86A04 | (VMS) Installation for GT | 2008-08-29 00:00:00 | 2008-09-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2709 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Vibration Monitoring System (VMS) | 2SF1260W62A05 | (VMS) Function Test for GT | (VMS) Function Test for GT | 2008-09-06 | 2008-09-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Vibration Monitoring System (VMS) 2SF1260W62A05 (VMS) Function Test for GT | Activity | 2SF1260W62A05 | (VMS) Function Test for GT | 2008-09-06 00:00:00 | 2008-09-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2711 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2EF1225W00A01 | (CCWS) CCW H/EX key data | (CCWS) CCW H/EX key data | 2007-03-30 | 2007-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2EF1225W00A01 (CCWS) CCW H/EX key data | Activity | 2EF1225W00A01 | (CCWS) CCW H/EX key data | 2007-03-30 00:00:00 | 2007-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2712 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2PF1225W42A18P | (EXP Head Tank) P.O & Procurement | (EXP Head Tank) P.O & Procurement | 2007-07-03 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2PF1225W42A18P (EXP Head Tank) P.O & Procurement | Activity | 2PF1225W42A18P | (EXP Head Tank) P.O & Procurement | 2007-07-03 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2713 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2EF1225W16A15 | (EXP Head Tank) FDN Design | (EXP Head Tank) FDN Design | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2EF1225W16A15 (EXP Head Tank) FDN Design | Activity | 2EF1225W16A15 | (EXP Head Tank) FDN Design | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2714 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2PF1225W42A12P | (CCWP) P.O & Procurement for GT | (CCWP) P.O & Procurement for GT | 2007-07-03 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2PF1225W42A12P (CCWP) P.O & Procurement for GT | Activity | 2PF1225W42A12P | (CCWP) P.O & Procurement for GT | 2007-07-03 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2715 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2EF1225W16A09 | (CCWP) FDN Design | (CCWP) FDN Design | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2EF1225W16A09 (CCWP) FDN Design | Activity | 2EF1225W16A09 | (CCWP) FDN Design | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2716 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2PF1225W42A05P (CCW H/EX) P.O & Procurement_Fin fan cooler | Activity | 2PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2717 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2EF1225W16A02 (CCW H/EX) FDN Design_Fin fan cooler | Activity | 2EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2718 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2CF1225W16A10 | (CCWP) FDN Work | (CCWP) FDN Work | 2007-11-30 | 2008-01-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2CF1225W16A10 (CCWP) FDN Work | Activity | 2CF1225W16A10 | (CCWP) FDN Work | 2007-11-30 00:00:00 | 2008-01-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2719 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2CF1225W16A03 | (CCW H/EX) FDN Work_Fin fan cooler | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 | 2008-02-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2CF1225W16A03 (CCW H/EX) FDN Work_Fin fan cooler | Activity | 2CF1225W16A03 | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 00:00:00 | 2008-02-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2720 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2CF1225W16A16 | (EXP Head Tank) FDN Work | (EXP Head Tank) FDN Work | 2008-01-01 | 2008-01-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2CF1225W16A16 (EXP Head Tank) FDN Work | Activity | 2CF1225W16A16 | (EXP Head Tank) FDN Work | 2008-01-01 00:00:00 | 2008-01-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2721 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2PF1225W42A19T | (EXP Head Tank) Transportation | (EXP Head Tank) Transportation | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2PF1225W42A19T (EXP Head Tank) Transportation | Activity | 2PF1225W42A19T | (EXP Head Tank) Transportation | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2722 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2PF1225W42A13T | (CCWP) Transportation for GT | (CCWP) Transportation for GT | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2PF1225W42A13T (CCWP) Transportation for GT | Activity | 2PF1225W42A13T | (CCWP) Transportation for GT | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2723 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2PF1225W42A06T | (CCW H/EX) Transportation_Fin fan cooler | (CCW H/EX) Transportation_Fin fan cooler | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2PF1225W42A06T (CCW H/EX) Transportation_Fin fan cooler | Activity | 2PF1225W42A06T | (CCW H/EX) Transportation_Fin fan cooler | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2724 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2CF1225W58A21 | (CCWS) Piping Work | (CCWS) Piping Work | 2008-05-27 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2CF1225W58A21 (CCWS) Piping Work | Activity | 2CF1225W58A21 | (CCWS) Piping Work | 2008-05-27 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2725 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2CF1225W42A20 | (EXP Head Tank) Installation | (EXP Head Tank) Installation | 2008-06-16 | 2008-07-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2CF1225W42A20 (EXP Head Tank) Installation | Activity | 2CF1225W42A20 | (EXP Head Tank) Installation | 2008-06-16 00:00:00 | 2008-07-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2726 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2CF1225W42A14 | (CCWP) Installation | (CCWP) Installation | 2008-06-16 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2CF1225W42A14 (CCWP) Installation | Activity | 2CF1225W42A14 | (CCWP) Installation | 2008-06-16 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2727 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | (CCW H/EX) Installation_Fin fan cooler | 2008-06-16 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2CF1225W42A07 (CCW H/EX) Installation_Fin fan cooler | Activity | 2CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | 2008-06-16 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2728 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2CF1225W74A22 | (CCWS) Installation & Test - Elec. | (CCWS) Installation & Test - Elec. | 2008-06-30 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2CF1225W74A22 (CCWS) Installation & Test - Elec. | Activity | 2CF1225W74A22 | (CCWS) Installation & Test - Elec. | 2008-06-30 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2729 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2CF1225W90A23 | (CCWS) Installation & Test - I&C | (CCWS) Installation & Test - I&C | 2008-06-30 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2CF1225W90A23 (CCWS) Installation & Test - I&C | Activity | 2CF1225W90A23 | (CCWS) Installation & Test - I&C | 2008-06-30 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2730 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2SF1225W62A24 | (CCWS) Loop chek | (CCWS) Loop chek | 2008-07-31 | 2008-08-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2SF1225W62A24 (CCWS) Loop chek | Activity | 2SF1225W62A24 | (CCWS) Loop chek | 2008-07-31 00:00:00 | 2008-08-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2731 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2SF1225W62A25 | (CCWS) Function Test | (CCWS) Function Test | 2008-08-10 | 2008-08-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2SF1225W62A25 (CCWS) Function Test | Activity | 2SF1225W62A25 | (CCWS) Function Test | 2008-08-10 00:00:00 | 2008-08-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2732 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Closed Cooling Water System | 2SF1225W62A26 | (CCWS) Flushing | (CCWS) Flushing | 2008-08-15 | 2008-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Closed Cooling Water System 2SF1225W62A26 (CCWS) Flushing | Activity | 2SF1225W62A26 | (CCWS) Flushing | 2008-08-15 00:00:00 | 2008-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2734 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fire fighting System | 2PF1265W38A01P | (F/F GTG#21) P.O & Procurement_CO2 FF System | (F/F GTG#21) P.O & Procurement_CO2 FF System | 2007-03-30 | 2008-04-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fire fighting System 2PF1265W38A01P (F/F GTG#21) P.O & Procurement_CO2 FF System | Activity | 2PF1265W38A01P | (F/F GTG#21) P.O & Procurement_CO2 FF System | 2007-03-30 00:00:00 | 2008-04-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2735 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fire fighting System | 2PF1265W38A04P | (F/F GTG#21)P.O & Procurement_Clean Agent FF System | (F/F GTG#21)P.O & Procurement_Clean Agent FF System | 2007-03-30 | 2008-04-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fire fighting System 2PF1265W38A04P (F/F GTG#21)P.O & Procurement_Clean Agent FF System | Activity | 2PF1265W38A04P | (F/F GTG#21)P.O & Procurement_Clean Agent FF System | 2007-03-30 00:00:00 | 2008-04-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2736 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fire fighting System | 2PF1265W38A02T | (F/F GTG#21) Transportation_CO2 FF System | (F/F GTG#21) Transportation_CO2 FF System | 2008-04-15 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fire fighting System 2PF1265W38A02T (F/F GTG#21) Transportation_CO2 FF System | Activity | 2PF1265W38A02T | (F/F GTG#21) Transportation_CO2 FF System | 2008-04-15 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2737 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fire fighting System | 2PF1265W38A05T | (F/F GTG#21) Transportation_Clean Agent FF System | (F/F GTG#21) Transportation_Clean Agent FF System | 2008-04-15 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fire fighting System 2PF1265W38A05T (F/F GTG#21) Transportation_Clean Agent FF System | Activity | 2PF1265W38A05T | (F/F GTG#21) Transportation_Clean Agent FF System | 2008-04-15 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2738 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fire fighting System | 2CF1265W38A03 | (F/F GTG#21) Installation_CO2 FF System | (F/F GTG#21) Installation_CO2 FF System | 2008-05-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fire fighting System 2CF1265W38A03 (F/F GTG#21) Installation_CO2 FF System | Activity | 2CF1265W38A03 | (F/F GTG#21) Installation_CO2 FF System | 2008-05-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2739 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fire fighting System | 2CF1265W38A06 | (F/F GTG#21) Installation_Clean Agent FF System | (F/F GTG#21) Installation_Clean Agent FF System | 2008-05-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fire fighting System 2CF1265W38A06 (F/F GTG#21) Installation_Clean Agent FF System | Activity | 2CF1265W38A06 | (F/F GTG#21) Installation_Clean Agent FF System | 2008-05-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2740 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fire fighting System | 2CF1265W38A07 | (F/F GTG#21) Piping work | (F/F GTG#21) Piping work | 2008-06-14 | 2008-07-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fire fighting System 2CF1265W38A07 (F/F GTG#21) Piping work | Activity | 2CF1265W38A07 | (F/F GTG#21) Piping work | 2008-06-14 00:00:00 | 2008-07-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2741 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fire fighting System | 2SF1265W62A08.2 | (F/F GTG#21) Loop chek | (F/F GTG#21) Loop chek | 2008-07-09 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fire fighting System 2SF1265W62A08.2 (F/F GTG#21) Loop chek | Activity | 2SF1265W62A08.2 | (F/F GTG#21) Loop chek | 2008-07-09 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2742 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fire fighting System | 2SF1265W62A09.2 | (F/F GTG#21) Function Test(incl. Alarm Test) | (F/F GTG#21) Function Test(incl. Alarm Test) | 2008-07-16 | 2008-07-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fire fighting System 2SF1265W62A09.2 (F/F GTG#21) Function Test(incl. Alarm Test) | Activity | 2SF1265W62A09.2 | (F/F GTG#21) Function Test(incl. Alarm Test) | 2008-07-16 00:00:00 | 2008-07-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2743 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Fire fighting System | 2SF1265W62A10.2 | (F/F GTG#21) CO2 Discharge Test | (F/F GTG#21) CO2 Discharge Test | 2008-07-26 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Fire fighting System 2SF1265W62A10.2 (F/F GTG#21) CO2 Discharge Test | Activity | 2SF1265W62A10.2 | (F/F GTG#21) CO2 Discharge Test | 2008-07-26 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2745 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2PF1265W42A02.3P | (Purge Air System) P.O & Procurement | (Purge Air System) P.O & Procurement | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2PF1265W42A02.3P (Purge Air System) P.O & Procurement | Activity | 2PF1265W42A02.3P | (Purge Air System) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2746 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2PF1265W42A12P | (Control Oil) P.O & Procurement | (Control Oil) P.O & Procurement | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2PF1265W42A12P (Control Oil) P.O & Procurement | Activity | 2PF1265W42A12P | (Control Oil) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2747 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2CF1265W16A01.3 | (Purge Air System) FDN Work | (Purge Air System) FDN Work | 2007-10-31 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2CF1265W16A01.3 (Purge Air System) FDN Work | Activity | 2CF1265W16A01.3 | (Purge Air System) FDN Work | 2007-10-31 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2748 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2CF1265W16A11 | (Control Oil) FDN Work | (Control Oil) FDN Work | 2007-10-31 | 2007-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2CF1265W16A11 (Control Oil) FDN Work | Activity | 2CF1265W16A11 | (Control Oil) FDN Work | 2007-10-31 00:00:00 | 2007-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2749 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2PF1265W42A03.3T | (Purge Air System) Transportation | (Purge Air System) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2PF1265W42A03.3T (Purge Air System) Transportation | Activity | 2PF1265W42A03.3T | (Purge Air System) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2750 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2PF1265W42A13.0T | (Control Oil)Transportation | (Control Oil)Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2PF1265W42A13.0T (Control Oil)Transportation | Activity | 2PF1265W42A13.0T | (Control Oil)Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2751 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2CF1265W42A04.3 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2CF1265W42A04.3 (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | Activity | 2CF1265W42A04.3 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2752 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2CF1265W42A14 | (Control Oil) Installation | (Control Oil) Installation | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2CF1265W42A14 (Control Oil) Installation | Activity | 2CF1265W42A14 | (Control Oil) Installation | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2753 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2CF1265W58A05.3 | (Purge Air System) Piping work | (Purge Air System) Piping work | 2008-05-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2CF1265W58A05.3 (Purge Air System) Piping work | Activity | 2CF1265W58A05.3 | (Purge Air System) Piping work | 2008-05-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2754 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2CF1265W58A15 | (Control Oil) Piping work | (Control Oil) Piping work | 2008-05-01 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2CF1265W58A15 (Control Oil) Piping work | Activity | 2CF1265W58A15 | (Control Oil) Piping work | 2008-05-01 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2755 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2CF1265W74A06.3 | (Purge Air System) Installation- Elec. | (Purge Air System) Installation- Elec. | 2008-05-16 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2CF1265W74A06.3 (Purge Air System) Installation- Elec. | Activity | 2CF1265W74A06.3 | (Purge Air System) Installation- Elec. | 2008-05-16 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2756 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2CF1265W90A07.3 | (Purge Air System) Installation- I&C | (Purge Air System) Installation- I&C | 2008-05-16 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2CF1265W90A07.3 (Purge Air System) Installation- I&C | Activity | 2CF1265W90A07.3 | (Purge Air System) Installation- I&C | 2008-05-16 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2757 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2SF1265W62A08.3 | (Purge Air System) Loop chek | (Purge Air System) Loop chek | 2008-05-30 | 2008-06-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2SF1265W62A08.3 (Purge Air System) Loop chek | Activity | 2SF1265W62A08.3 | (Purge Air System) Loop chek | 2008-05-30 00:00:00 | 2008-06-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2758 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2SF1265W62A09.3 | (Purge Air System) Function Test | (Purge Air System) Function Test | 2008-06-02 | 2008-06-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2SF1265W62A09.3 (Purge Air System) Function Test | Activity | 2SF1265W62A09.3 | (Purge Air System) Function Test | 2008-06-02 00:00:00 | 2008-06-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2759 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2CF1265W74A16 | (Control Oil) Installation- Elec. | (Control Oil) Installation- Elec. | 2008-06-02 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2CF1265W74A16 (Control Oil) Installation- Elec. | Activity | 2CF1265W74A16 | (Control Oil) Installation- Elec. | 2008-06-02 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2760 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2CF1265W90A17 | (Control Oil) Installation- I&C | (Control Oil) Installation- I&C | 2008-06-02 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2CF1265W90A17 (Control Oil) Installation- I&C | Activity | 2CF1265W90A17 | (Control Oil) Installation- I&C | 2008-06-02 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2761 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2SF1265W62A10.3 | (Purge Air System) Load Test | (Purge Air System) Load Test | 2008-06-05 | 2008-06-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2SF1265W62A10.3 (Purge Air System) Load Test | Activity | 2SF1265W62A10.3 | (Purge Air System) Load Test | 2008-06-05 00:00:00 | 2008-06-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2762 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2SF1265W62A18 | (Control Oil) Loop chek | (Control Oil) Loop chek | 2008-06-15 | 2008-06-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2SF1265W62A18 (Control Oil) Loop chek | Activity | 2SF1265W62A18 | (Control Oil) Loop chek | 2008-06-15 00:00:00 | 2008-06-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2763 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2SF1265W62A19 | (Control Oil) Function Test | (Control Oil) Function Test | 2008-06-20 | 2008-06-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2SF1265W62A19 (Control Oil) Function Test | Activity | 2SF1265W62A19 | (Control Oil) Function Test | 2008-06-20 00:00:00 | 2008-06-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2764 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Auxiliary System | 2SF1265W62A20 | (Control Oil) Flushing | (Control Oil) Flushing | 2008-06-30 | 2008-07-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Auxiliary System 2SF1265W62A20 (Control Oil) Flushing | Activity | 2SF1265W62A20 | (Control Oil) Flushing | 2008-06-30 00:00:00 | 2008-07-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2766 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9011W62A01 | (GTG #21) Fuel Gas System Final Function Test | (GTG #21) Fuel Gas System Final Function Test | 2008-09-29 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9011W62A01 (GTG #21) Fuel Gas System Final Function Test | Activity | 2SF9011W62A01 | (GTG #21) Fuel Gas System Final Function Test | 2008-09-29 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2767 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9011W62A02 | (GTG #21) Turning Gear Operation | (GTG #21) Turning Gear Operation | 2008-10-02 | 2008-10-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9011W62A02 (GTG #21) Turning Gear Operation | Activity | 2SF9011W62A02 | (GTG #21) Turning Gear Operation | 2008-10-02 00:00:00 | 2008-10-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2768 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9011W62A03 | (GTG #21) Initial Firing with FSNL | (GTG #21) Initial Firing with FSNL | 2008-10-04 | 2008-10-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9011W62A03 (GTG #21) Initial Firing with FSNL | Activity | 2SF9011W62A03 | (GTG #21) Initial Firing with FSNL | 2008-10-04 00:00:00 | 2008-10-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2769 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9012W62A04 | (GTG #21) TBN & GEN Protection Test | (GTG #21) TBN & GEN Protection Test | 2008-10-05 | 2008-10-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9012W62A04 (GTG #21) TBN & GEN Protection Test | Activity | 2SF9012W62A04 | (GTG #21) TBN & GEN Protection Test | 2008-10-05 00:00:00 | 2008-10-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2770 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9012W62A05 | (GTG #21) 1st Synchronization | (GTG #21) 1st Synchronization | 2008-10-07 | 2008-10-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9012W62A05 (GTG #21) 1st Synchronization | Activity | 2SF9012W62A05 | (GTG #21) 1st Synchronization | 2008-10-07 00:00:00 | 2008-10-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2771 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9012W62A06 | (GTG #21) Optimization with Fuel Gas | (GTG #21) Optimization with Fuel Gas | 2008-10-09 | 2008-10-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9012W62A06 (GTG #21) Optimization with Fuel Gas | Activity | 2SF9012W62A06 | (GTG #21) Optimization with Fuel Gas | 2008-10-09 00:00:00 | 2008-10-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2772 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9012W62A07 | (GTG #21) Fuel Oil System Final Function Test | (GTG #21) Fuel Oil System Final Function Test | 2008-10-24 | 2008-11-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9012W62A07 (GTG #21) Fuel Oil System Final Function Test | Activity | 2SF9012W62A07 | (GTG #21) Fuel Oil System Final Function Test | 2008-10-24 00:00:00 | 2008-11-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2773 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9012W62A08 | (GTG #21) Optimization with Fuel Oil | (GTG #21) Optimization with Fuel Oil | 2008-11-03 | 2008-12-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9012W62A08 (GTG #21) Optimization with Fuel Oil | Activity | 2SF9012W62A08 | (GTG #21) Optimization with Fuel Oil | 2008-11-03 00:00:00 | 2008-12-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2774 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9012W62A09 | (GTG #21) Black start Test with GT | (GTG #21) Black start Test with GT | 2008-12-03 | 2008-12-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9012W62A09 (GTG #21) Black start Test with GT | Activity | 2SF9012W62A09 | (GTG #21) Black start Test with GT | 2008-12-03 00:00:00 | 2008-12-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2775 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9012W62A13 | (GTG #21) Fuel Change-Over Test | (GTG #21) Fuel Change-Over Test | 2008-12-03 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9012W62A13 (GTG #21) Fuel Change-Over Test | Activity | 2SF9012W62A13 | (GTG #21) Fuel Change-Over Test | 2008-12-03 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2776 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9012W62A10 | (GTG #21) Trial Run Test | (GTG #21) Trial Run Test | 2008-12-04 | 2008-12-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9012W62A10 (GTG #21) Trial Run Test | Activity | 2SF9012W62A10 | (GTG #21) Trial Run Test | 2008-12-04 00:00:00 | 2008-12-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2777 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9013W62A11 | (GTG #21) Reliability Test | (GTG #21) Reliability Test | 2008-12-05 | 2008-12-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9013W62A11 (GTG #21) Reliability Test | Activity | 2SF9013W62A11 | (GTG #21) Reliability Test | 2008-12-05 00:00:00 | 2008-12-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2778 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #21 > GTG #21 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #21 | GTG #21 Commissioning | 2SF9013W62A12 | (GTG #21) Performance Test (Fuel Gas & Fuel Oil) | (GTG #21) Performance Test (Fuel Gas & Fuel Oil) | 2008-12-20 | 2009-01-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #21 GTG #21 Commissioning 2SF9013W62A12 (GTG #21) Performance Test (Fuel Gas & Fuel Oil) | Activity | 2SF9013W62A12 | (GTG #21) Performance Test (Fuel Gas & Fuel Oil) | 2008-12-20 00:00:00 | 2009-01-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2781 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Main body | 2PF1213W42A08.1P | (Gen #22) P.O & Procurement | (Gen #22) P.O & Procurement | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Main body 2PF1213W42A08.1P (Gen #22) P.O & Procurement | Activity | 2PF1213W42A08.1P | (Gen #22) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2782 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Main body | 2EF1213W16A06.1 | (Gen #22) FDN Design | (Gen #22) FDN Design | 2007-03-30 | 2007-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Main body 2EF1213W16A06.1 (Gen #22) FDN Design | Activity | 2EF1213W16A06.1 | (Gen #22) FDN Design | 2007-03-30 00:00:00 | 2007-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2783 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Main body | 2PF1213W42A03.1P | (GT #22) P.O & Procurement | (GT #22) P.O & Procurement | 2007-03-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Main body 2PF1213W42A03.1P (GT #22) P.O & Procurement | Activity | 2PF1213W42A03.1P | (GT #22) P.O & Procurement | 2007-03-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2784 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Main body | 2EF1213W16A01.1 | (GT #22) FDN Design | (GT #22) FDN Design | 2007-03-30 | 2007-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Main body 2EF1213W16A01.1 (GT #22) FDN Design | Activity | 2EF1213W16A01.1 | (GT #22) FDN Design | 2007-03-30 00:00:00 | 2007-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2785 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Main body | 2CF1213W16A07.1 | (Gen #22) FDN Work | (Gen #22) FDN Work | 2007-08-30 | 2008-01-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Main body 2CF1213W16A07.1 (Gen #22) FDN Work | Activity | 2CF1213W16A07.1 | (Gen #22) FDN Work | 2007-08-30 00:00:00 | 2008-01-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2786 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Main body | 2CF1213W16A02.1 | (GT #22) FDN Work | (GT #22) FDN Work | 2007-08-30 | 2008-01-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Main body 2CF1213W16A02.1 (GT #22) FDN Work | Activity | 2CF1213W16A02.1 | (GT #22) FDN Work | 2007-08-30 00:00:00 | 2008-01-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2787 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Main body | 2PF1213W42A09.1T | (Gen #22) Transportation | (Gen #22) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Main body 2PF1213W42A09.1T (Gen #22) Transportation | Activity | 2PF1213W42A09.1T | (Gen #22) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2788 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Main body | 2PF1213W42A04.1T | (GT #22) Transportation | (GT #22) Transportation | 2008-04-01 | 2008-05-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Main body 2PF1213W42A04.1T (GT #22) Transportation | Activity | 2PF1213W42A04.1T | (GT #22) Transportation | 2008-04-01 00:00:00 | 2008-05-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2789 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Main body | 2CF1213W42A10.1 | (Gen #22) Installation | (Gen #22) Installation | 2008-04-16 | 2008-08-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Main body 2CF1213W42A10.1 (Gen #22) Installation | Activity | 2CF1213W42A10.1 | (Gen #22) Installation | 2008-04-16 00:00:00 | 2008-08-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2790 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Main body | 2CF1213W42A05.1 | (GT #22) Installation(On FDN~Final Alignment) | (GT #22) Installation(On FDN~Final Alignment) | 2008-05-15 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Main body 2CF1213W42A05.1 (GT #22) Installation(On FDN~Final Alignment) | Activity | 2CF1213W42A05.1 | (GT #22) Installation(On FDN~Final Alignment) | 2008-05-15 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2791 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Main body | 2CF1213W52A11.1 | (GT #22) Insulation | (GT #22) Insulation | 2008-06-19 | 2008-07-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Main body 2CF1213W52A11.1 (GT #22) Insulation | Activity | 2CF1213W52A11.1 | (GT #22) Insulation | 2008-06-19 00:00:00 | 2008-07-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2793 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Electrical System | 2PF1255W70A01.1P | (GTG#22 Electrical) P.O & Procurement | (GTG#22 Electrical) P.O & Procurement | 2007-03-30 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Electrical System 2PF1255W70A01.1P (GTG#22 Electrical) P.O & Procurement | Activity | 2PF1255W70A01.1P | (GTG#22 Electrical) P.O & Procurement | 2007-03-30 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2794 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Electrical System | 2PF1255W70A02.1T | (GTG#22 Electrical) Transportation | (GTG#22 Electrical) Transportation | 2008-04-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Electrical System 2PF1255W70A02.1T (GTG#22 Electrical) Transportation | Activity | 2PF1255W70A02.1T | (GTG#22 Electrical) Transportation | 2008-04-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2795 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Electrical System | 2CF1255W70A03.1 | (GTG#22 Electrical) Installation- PCC | (GTG#22 Electrical) Installation- PCC | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Electrical System 2CF1255W70A03.1 (GTG#22 Electrical) Installation- PCC | Activity | 2CF1255W70A03.1 | (GTG#22 Electrical) Installation- PCC | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2796 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Electrical System | 2CF1255W70A04.1 | (GTG#22 Electrical) Installation- MCC | (GTG#22 Electrical) Installation- MCC | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Electrical System 2CF1255W70A04.1 (GTG#22 Electrical) Installation- MCC | Activity | 2CF1255W70A04.1 | (GTG#22 Electrical) Installation- MCC | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2797 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Electrical System | 2CF1255W70A05.1 | (GTG#22 Electrical) Installation- Protection Sys. | (GTG#22 Electrical) Installation- Protection Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Electrical System 2CF1255W70A05.1 (GTG#22 Electrical) Installation- Protection Sys. | Activity | 2CF1255W70A05.1 | (GTG#22 Electrical) Installation- Protection Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2798 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Electrical System | 2CF1255W70A07.1 | (GTG#22 Electrical) Installation- SEE&SFC Sys. | (GTG#22 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Electrical System 2CF1255W70A07.1 (GTG#22 Electrical) Installation- SEE&SFC Sys. | Activity | 2CF1255W70A07.1 | (GTG#22 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2799 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Electrical System | 2CF1255W70A08.1 | (GTG#22 Electrical) Installation- DC&UPS Sys. | (GTG#22 Electrical) Installation- DC&UPS Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Electrical System 2CF1255W70A08.1 (GTG#22 Electrical) Installation- DC&UPS Sys. | Activity | 2CF1255W70A08.1 | (GTG#22 Electrical) Installation- DC&UPS Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2800 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Electrical System | 2CF1255W74A09.1 | (GTG#22 Electrical) Cable work | (GTG#22 Electrical) Cable work | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Electrical System 2CF1255W74A09.1 (GTG#22 Electrical) Cable work | Activity | 2CF1255W74A09.1 | (GTG#22 Electrical) Cable work | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2801 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Electrical System | 2CF1255W86A06.1 | (GTG#22 Electrical) Installation- GT control Sys. | (GTG#22 Electrical) Installation- GT control Sys. | 2008-08-04 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Electrical System 2CF1255W86A06.1 (GTG#22 Electrical) Installation- GT control Sys. | Activity | 2CF1255W86A06.1 | (GTG#22 Electrical) Installation- GT control Sys. | 2008-08-04 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2802 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Electrical System | 2CF1255W62A10.1 | (GTG#22 Electrical) Electrical Function Test | (GTG#22 Electrical) Electrical Function Test | 2008-09-16 | 2008-09-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Electrical System 2CF1255W62A10.1 (GTG#22 Electrical) Electrical Function Test | Activity | 2CF1255W62A10.1 | (GTG#22 Electrical) Electrical Function Test | 2008-09-16 00:00:00 | 2008-09-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2803 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Electrical System | 2CF1255W62A11.1 | (GTG#22 Electrical) Loop Test | (GTG#22 Electrical) Loop Test | 2008-09-22 | 2008-09-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Electrical System 2CF1255W62A11.1 (GTG#22 Electrical) Loop Test | Activity | 2CF1255W62A11.1 | (GTG#22 Electrical) Loop Test | 2008-09-22 00:00:00 | 2008-09-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2805 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Starting System(Turning Device) | 2PF1265W42A01.1P | (Turning Gear) P.O & Procurement | (Turning Gear) P.O & Procurement | 2007-03-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Starting System(Turning Device) 2PF1265W42A01.1P (Turning Gear) P.O & Procurement | Activity | 2PF1265W42A01.1P | (Turning Gear) P.O & Procurement | 2007-03-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2806 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Starting System(Turning Device) | 2PF1265W42A02.1T | (Turning Gear) Transportation | (Turning Gear) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Starting System(Turning Device) 2PF1265W42A02.1T (Turning Gear) Transportation | Activity | 2PF1265W42A02.1T | (Turning Gear) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2807 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Starting System(Turning Device) | 2CF1265W42A03.1 | (Turning Gear) Installation | (Turning Gear) Installation | 2008-05-16 | 2008-05-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Starting System(Turning Device) 2CF1265W42A03.1 (Turning Gear) Installation | Activity | 2CF1265W42A03.1 | (Turning Gear) Installation | 2008-05-16 00:00:00 | 2008-05-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2808 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Starting System(Turning Device) | 2CF1265W74A04.1 | (Turning Gear) Installation- Elec. | (Turning Gear) Installation- Elec. | 2008-05-24 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Starting System(Turning Device) 2CF1265W74A04.1 (Turning Gear) Installation- Elec. | Activity | 2CF1265W74A04.1 | (Turning Gear) Installation- Elec. | 2008-05-24 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2809 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Starting System(Turning Device) | 2CF1265W90A05.1 | (Turning Gear) Installation- I&C | (Turning Gear) Installation- I&C | 2008-05-24 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Starting System(Turning Device) 2CF1265W90A05.1 (Turning Gear) Installation- I&C | Activity | 2CF1265W90A05.1 | (Turning Gear) Installation- I&C | 2008-05-24 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2810 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Starting System(Turning Device) | 2SF1265W62A06.1 | (Turning Gear) Loop check | (Turning Gear) Loop check | 2008-06-01 | 2008-06-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Starting System(Turning Device) 2SF1265W62A06.1 (Turning Gear) Loop check | Activity | 2SF1265W62A06.1 | (Turning Gear) Loop check | 2008-06-01 00:00:00 | 2008-06-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2811 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Starting System(Turning Device) | 2SF1265W62A07.1 | (Turning Gear) Function Test | (Turning Gear) Function Test | 2008-06-25 | 2008-06-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Starting System(Turning Device) 2SF1265W62A07.1 (Turning Gear) Function Test | Activity | 2SF1265W62A07.1 | (Turning Gear) Function Test | 2008-06-25 00:00:00 | 2008-06-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2813 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2PF1230W20A02.1P | (Air Intake) P.O & Procurement_Steel Sturucture | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2PF1230W20A02.1P (Air Intake) P.O & Procurement_Steel Sturucture | Activity | 2PF1230W20A02.1P | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2814 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2PF1230W64A05.1P | (Air Intake) P.O & Procurement_Inlet Duct | (Air Intake) P.O & Procurement_Inlet Duct | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2PF1230W64A05.1P (Air Intake) P.O & Procurement_Inlet Duct | Activity | 2PF1230W64A05.1P | (Air Intake) P.O & Procurement_Inlet Duct | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2815 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2PF1230W64A08.1P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2PF1230W64A08.1P (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 2PF1230W64A08.1P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2816 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2CF1230W16A01.1 | (Air Intake) FDN Work_Steel Sturucture | (Air Intake) FDN Work_Steel Sturucture | 2007-10-30 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2CF1230W16A01.1 (Air Intake) FDN Work_Steel Sturucture | Activity | 2CF1230W16A01.1 | (Air Intake) FDN Work_Steel Sturucture | 2007-10-30 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2817 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2PF1230W20A03.1T | (Air Intake) Transportation_Steel Sturucture | (Air Intake) Transportation_Steel Sturucture | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2PF1230W20A03.1T (Air Intake) Transportation_Steel Sturucture | Activity | 2PF1230W20A03.1T | (Air Intake) Transportation_Steel Sturucture | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2818 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2PF1230W64A06.1T | (Air Intake) Transportation_Inlet Duct | (Air Intake) Transportation_Inlet Duct | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2PF1230W64A06.1T (Air Intake) Transportation_Inlet Duct | Activity | 2PF1230W64A06.1T | (Air Intake) Transportation_Inlet Duct | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2819 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2PF1230W64A09.1T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2PF1230W64A09.1T (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 2PF1230W64A09.1T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2820 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2CF1230W20A04.1 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-05-01 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2CF1230W20A04.1 (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | Activity | 2CF1230W20A04.1 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-05-01 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2821 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2CF1230W64A07.1 | (Air Intake) Installation_Inlet Duct | (Air Intake) Installation_Inlet Duct | 2008-05-19 | 2008-05-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2CF1230W64A07.1 (Air Intake) Installation_Inlet Duct | Activity | 2CF1230W64A07.1 | (Air Intake) Installation_Inlet Duct | 2008-05-19 00:00:00 | 2008-05-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2822 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2CF1230W64A10.1 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-05-27 | 2008-06-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2CF1230W64A10.1 (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 2CF1230W64A10.1 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-05-27 00:00:00 | 2008-06-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2823 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2CF1230W74A11.1 | (Air Intake) Installation- Elec. | (Air Intake) Installation- Elec. | 2008-06-20 | 2008-07-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2CF1230W74A11.1 (Air Intake) Installation- Elec. | Activity | 2CF1230W74A11.1 | (Air Intake) Installation- Elec. | 2008-06-20 00:00:00 | 2008-07-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2824 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2CF1230W90A12.1 | (Air Intake) Installation- I&C | (Air Intake) Installation- I&C | 2008-06-20 | 2008-07-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2CF1230W90A12.1 (Air Intake) Installation- I&C | Activity | 2CF1230W90A12.1 | (Air Intake) Installation- I&C | 2008-06-20 00:00:00 | 2008-07-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2825 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2SF1230W62A13.1 | (Air Intake) Loop chek | (Air Intake) Loop chek | 2008-07-04 | 2008-07-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2SF1230W62A13.1 (Air Intake) Loop chek | Activity | 2SF1230W62A13.1 | (Air Intake) Loop chek | 2008-07-04 00:00:00 | 2008-07-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2826 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2SF1230W62A14.1 | (Air Intake) Function Test | (Air Intake) Function Test | 2008-07-10 | 2008-07-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2SF1230W62A14.1 (Air Intake) Function Test | Activity | 2SF1230W62A14.1 | (Air Intake) Function Test | 2008-07-10 00:00:00 | 2008-07-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2827 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air Intake System | 2SF1230W62A15.1 | (Air Intake) Load(Running) Test | (Air Intake) Load(Running) Test | 2008-07-13 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air Intake System 2SF1230W62A15.1 (Air Intake) Load(Running) Test | Activity | 2SF1230W62A15.1 | (Air Intake) Load(Running) Test | 2008-07-13 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2829 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air and Flue Gas System | 2PF1265W64A01.1P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air and Flue Gas System 2PF1265W64A01.1P (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | Activity | 2PF1265W64A01.1P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2830 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air and Flue Gas System | 2PF1265W64A02.1T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air and Flue Gas System 2PF1265W64A02.1T (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | Activity | 2PF1265W64A02.1T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2831 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air and Flue Gas System | 2CF1265W64A03.1 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-04-16 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air and Flue Gas System 2CF1265W64A03.1 (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | Activity | 2CF1265W64A03.1 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-04-16 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2832 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air and Flue Gas System | 2CF1265W64A04.1 | (Air&Flue Gas System) Duct work | (Air&Flue Gas System) Duct work | 2008-05-17 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air and Flue Gas System 2CF1265W64A04.1 (Air&Flue Gas System) Duct work | Activity | 2CF1265W64A04.1 | (Air&Flue Gas System) Duct work | 2008-05-17 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2833 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air and Flue Gas System | 2CF1265W74A06.1 | (Air&Flue Gas System) Installation- Elec. | (Air&Flue Gas System) Installation- Elec. | 2008-06-02 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air and Flue Gas System 2CF1265W74A06.1 (Air&Flue Gas System) Installation- Elec. | Activity | 2CF1265W74A06.1 | (Air&Flue Gas System) Installation- Elec. | 2008-06-02 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2834 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air and Flue Gas System | 2CF1265W90A07.1 | (Air&Flue Gas System) Installation- I&C | (Air&Flue Gas System) Installation- I&C | 2008-06-02 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air and Flue Gas System 2CF1265W90A07.1 (Air&Flue Gas System) Installation- I&C | Activity | 2CF1265W90A07.1 | (Air&Flue Gas System) Installation- I&C | 2008-06-02 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2835 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air and Flue Gas System | 2SF1265W62A05.1 | (Air&Flue Gas System) Loop chek | (Air&Flue Gas System) Loop chek | 2008-06-12 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air and Flue Gas System 2SF1265W62A05.1 (Air&Flue Gas System) Loop chek | Activity | 2SF1265W62A05.1 | (Air&Flue Gas System) Loop chek | 2008-06-12 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2836 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Air and Flue Gas System | 2SF1265W62A08.1 | (Air&Flue Gas System) Function Test | (Air&Flue Gas System) Function Test | 2008-06-15 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Air and Flue Gas System 2SF1265W62A08.1 (Air&Flue Gas System) Function Test | Activity | 2SF1265W62A08.1 | (Air&Flue Gas System) Function Test | 2008-06-15 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2838 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2PF1250W42A02.2P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2PF1250W42A02.2P (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | Activity | 2PF1250W42A02.2P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2839 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2PF1250W42A06.2P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2PF1250W42A06.2P (Lube Oil System) P.O & Procurement_Lube oil functional Module | Activity | 2PF1250W42A06.2P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2840 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2PF1250W42A10.2P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2PF1250W42A10.2P (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | Activity | 2PF1250W42A10.2P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2841 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2CF1250W16A01.2 | (Lube Oil System) FDN Work_Lube Oil Supply Module | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-10-30 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2CF1250W16A01.2 (Lube Oil System) FDN Work_Lube Oil Supply Module | Activity | 2CF1250W16A01.2 | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-10-30 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2842 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2CF1250W16A05.2 | (Lube Oil System) FDN Work_Lube oil functional Module | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-10-30 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2CF1250W16A05.2 (Lube Oil System) FDN Work_Lube oil functional Module | Activity | 2CF1250W16A05.2 | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-10-30 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2843 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2CF1250W16A09.2 | (Lube Oil System) FDN Work_Lube oil Mist Separator | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-10-30 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2CF1250W16A09.2 (Lube Oil System) FDN Work_Lube oil Mist Separator | Activity | 2CF1250W16A09.2 | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-10-30 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2844 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2PF1250W42A03.2T | (Lube Oil System) Transportation_Lube Oil Supply Module | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2PF1250W42A03.2T (Lube Oil System) Transportation_Lube Oil Supply Module | Activity | 2PF1250W42A03.2T | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2845 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2PF1250W42A07.2T | (Lube Oil System) Transportation_Lube oil functional Module | (Lube Oil System) Transportation_Lube oil functional Module | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2PF1250W42A07.2T (Lube Oil System) Transportation_Lube oil functional Module | Activity | 2PF1250W42A07.2T | (Lube Oil System) Transportation_Lube oil functional Module | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2846 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2PF1250W42A11.2T | (Lube Oil System) Transportation_Lube oil Mist Separator | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2PF1250W42A11.2T (Lube Oil System) Transportation_Lube oil Mist Separator | Activity | 2PF1250W42A11.2T | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2847 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2CF1250W42A04.2 | (Lube Oil System) Installation_Lube Oil Supply Module | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-04-16 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2CF1250W42A04.2 (Lube Oil System) Installation_Lube Oil Supply Module | Activity | 2CF1250W42A04.2 | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-04-16 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2848 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2CF1250W42A08.2 | (Lube Oil System) Installation_Lube oil functional Module | (Lube Oil System) Installation_Lube oil functional Module | 2008-04-16 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2CF1250W42A08.2 (Lube Oil System) Installation_Lube oil functional Module | Activity | 2CF1250W42A08.2 | (Lube Oil System) Installation_Lube oil functional Module | 2008-04-16 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2849 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2CF1250W42A12.2 | (Lube Oil System) Installation_Lube oil Mist Separator | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-04-16 | 2008-04-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2CF1250W42A12.2 (Lube Oil System) Installation_Lube oil Mist Separator | Activity | 2CF1250W42A12.2 | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-04-16 00:00:00 | 2008-04-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2850 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2CF1250W58A13.2 | (Lube Oil System) Piping work | (Lube Oil System) Piping work | 2008-05-02 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2CF1250W58A13.2 (Lube Oil System) Piping work | Activity | 2CF1250W58A13.2 | (Lube Oil System) Piping work | 2008-05-02 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2851 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2CF1250W62A16.2 | (GTG #22) Lube Oil Flushing | (GTG #22) Lube Oil Flushing | 2008-06-02 | 2008-06-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2CF1250W62A16.2 (GTG #22) Lube Oil Flushing | Activity | 2CF1250W62A16.2 | (GTG #22) Lube Oil Flushing | 2008-06-02 00:00:00 | 2008-06-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2852 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2CF1250W74A14.2 | (Lube Oil System) Installation- Elec. | (Lube Oil System) Installation- Elec. | 2008-06-03 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2CF1250W74A14.2 (Lube Oil System) Installation- Elec. | Activity | 2CF1250W74A14.2 | (Lube Oil System) Installation- Elec. | 2008-06-03 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2853 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2CF1250W90A15.2 | (Lube Oil System) Installation- I&C | (Lube Oil System) Installation- I&C | 2008-06-03 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2CF1250W90A15.2 (Lube Oil System) Installation- I&C | Activity | 2CF1250W90A15.2 | (Lube Oil System) Installation- I&C | 2008-06-03 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2854 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2SF1250W62A17.2 | (Lube Oil System) Loop chek | (Lube Oil System) Loop chek | 2008-06-17 | 2008-06-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2SF1250W62A17.2 (Lube Oil System) Loop chek | Activity | 2SF1250W62A17.2 | (Lube Oil System) Loop chek | 2008-06-17 00:00:00 | 2008-06-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2855 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2SF1250W62A18.2 | (Lube Oil System) Function Test | (Lube Oil System) Function Test | 2008-06-20 | 2008-06-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2SF1250W62A18.2 (Lube Oil System) Function Test | Activity | 2SF1250W62A18.2 | (Lube Oil System) Function Test | 2008-06-20 00:00:00 | 2008-06-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2856 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Lube Oil System | 2SF1250W62A19.2 | (Lube Oil System) Load Test | (Lube Oil System) Load Test | 2008-06-23 | 2008-06-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Lube Oil System 2SF1250W62A19.2 (Lube Oil System) Load Test | Activity | 2SF1250W62A19.2 | (Lube Oil System) Load Test | 2008-06-23 00:00:00 | 2008-06-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2858 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Generator Seal Oil System | 2PF1250W42A02.3P | (GEN Seal Oil Sys.) P.O & Procurement | (GEN Seal Oil Sys.) P.O & Procurement | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Generator Seal Oil System 2PF1250W42A02.3P (GEN Seal Oil Sys.) P.O & Procurement | Activity | 2PF1250W42A02.3P | (GEN Seal Oil Sys.) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2859 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Generator Seal Oil System | 2CF1250W16A01.3 | (GEN Seal Oil Sys.) FDN Work | (GEN Seal Oil Sys.) FDN Work | 2007-10-30 | 2008-01-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Generator Seal Oil System 2CF1250W16A01.3 (GEN Seal Oil Sys.) FDN Work | Activity | 2CF1250W16A01.3 | (GEN Seal Oil Sys.) FDN Work | 2007-10-30 00:00:00 | 2008-01-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2860 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Generator Seal Oil System | 2PF1250W42A03.3T | (GEN Seal Oil Sys.) Transportation | (GEN Seal Oil Sys.) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Generator Seal Oil System 2PF1250W42A03.3T (GEN Seal Oil Sys.) Transportation | Activity | 2PF1250W42A03.3T | (GEN Seal Oil Sys.) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2861 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Generator Seal Oil System | 2CF1250W42A04.3 | (GEN Seal Oil Sys.) Installation | (GEN Seal Oil Sys.) Installation | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Generator Seal Oil System 2CF1250W42A04.3 (GEN Seal Oil Sys.) Installation | Activity | 2CF1250W42A04.3 | (GEN Seal Oil Sys.) Installation | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2862 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Generator Seal Oil System | 2CF1250W58A05.3 | (GEN Seal Oil Sys.) Piping Work | (GEN Seal Oil Sys.) Piping Work | 2008-05-01 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Generator Seal Oil System 2CF1250W58A05.3 (GEN Seal Oil Sys.) Piping Work | Activity | 2CF1250W58A05.3 | (GEN Seal Oil Sys.) Piping Work | 2008-05-01 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2863 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Generator Seal Oil System | 2CF1250W74A07.3 | (GEN Seal Oil Sys.) Installation- Elec. | (GEN Seal Oil Sys.) Installation- Elec. | 2008-06-02 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Generator Seal Oil System 2CF1250W74A07.3 (GEN Seal Oil Sys.) Installation- Elec. | Activity | 2CF1250W74A07.3 | (GEN Seal Oil Sys.) Installation- Elec. | 2008-06-02 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2864 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Generator Seal Oil System | 2CF1250W90A08.3 | (GEN Seal Oil Sys.) Installation- I&C | (GEN Seal Oil Sys.) Installation- I&C | 2008-06-02 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Generator Seal Oil System 2CF1250W90A08.3 (GEN Seal Oil Sys.) Installation- I&C | Activity | 2CF1250W90A08.3 | (GEN Seal Oil Sys.) Installation- I&C | 2008-06-02 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2865 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Generator Seal Oil System | 2SF1250W62A06.3 | (GEN Seal Oil Sys.) Oil Flushing | (GEN Seal Oil Sys.) Oil Flushing | 2008-06-02 | 2008-06-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Generator Seal Oil System 2SF1250W62A06.3 (GEN Seal Oil Sys.) Oil Flushing | Activity | 2SF1250W62A06.3 | (GEN Seal Oil Sys.) Oil Flushing | 2008-06-02 00:00:00 | 2008-06-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2866 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Generator Seal Oil System | 2SF1250W62A09.3 | (GEN Seal Oil Sys.) Loop chek | (GEN Seal Oil Sys.) Loop chek | 2008-06-15 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Generator Seal Oil System 2SF1250W62A09.3 (GEN Seal Oil Sys.) Loop chek | Activity | 2SF1250W62A09.3 | (GEN Seal Oil Sys.) Loop chek | 2008-06-15 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2867 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Generator Seal Oil System | 2SF1250W62A10.3 | (GEN Seal Oil Sys.) Function Test | (GEN Seal Oil Sys.) Function Test | 2008-06-18 | 2008-06-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Generator Seal Oil System 2SF1250W62A10.3 (GEN Seal Oil Sys.) Function Test | Activity | 2SF1250W62A10.3 | (GEN Seal Oil Sys.) Function Test | 2008-06-18 00:00:00 | 2008-06-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2869 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2PF1265W42A03.4P | (Gas Final Filter & Metering Skid) P.O & Procurement | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2PF1265W42A03.4P (Gas Final Filter & Metering Skid) P.O & Procurement | Activity | 2PF1265W42A03.4P | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2870 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2EF1265W16A01.4 | (Gas Final Filter & Metering Skid) FDN Design | (Gas Final Filter & Metering Skid) FDN Design | 2007-03-30 | 2007-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2EF1265W16A01.4 (Gas Final Filter & Metering Skid) FDN Design | Activity | 2EF1265W16A01.4 | (Gas Final Filter & Metering Skid) FDN Design | 2007-03-30 00:00:00 | 2007-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2871 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2PF1265W42A13.4P | (TCA Cooler) P.O & Procurement | (TCA Cooler) P.O & Procurement | 2007-03-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2PF1265W42A13.4P (TCA Cooler) P.O & Procurement | Activity | 2PF1265W42A13.4P | (TCA Cooler) P.O & Procurement | 2007-03-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2872 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2CF1265W16A02.4 | (Gas Final Filter & Metering Skid) FDN Work | (Gas Final Filter & Metering Skid) FDN Work | 2007-10-02 | 2007-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2CF1265W16A02.4 (Gas Final Filter & Metering Skid) FDN Work | Activity | 2CF1265W16A02.4 | (Gas Final Filter & Metering Skid) FDN Work | 2007-10-02 00:00:00 | 2007-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2873 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2CF1265W16A12.4 | (TCA Cooler) FDN Work | (TCA Cooler) FDN Work | 2007-10-30 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2CF1265W16A12.4 (TCA Cooler) FDN Work | Activity | 2CF1265W16A12.4 | (TCA Cooler) FDN Work | 2007-10-30 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2874 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2PF1265W42A04.4T | (Gas Final Filter & Metering Skid) Transportation | (Gas Final Filter & Metering Skid) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2PF1265W42A04.4T (Gas Final Filter & Metering Skid) Transportation | Activity | 2PF1265W42A04.4T | (Gas Final Filter & Metering Skid) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2875 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2PF1265W42A14.4T | (TCA Cooler) Transportation | (TCA Cooler) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2PF1265W42A14.4T (TCA Cooler) Transportation | Activity | 2PF1265W42A14.4T | (TCA Cooler) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2876 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2CF1265W42A05.4 | (Gas Final Filter & Metering Skid) Installation | (Gas Final Filter & Metering Skid) Installation | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2CF1265W42A05.4 (Gas Final Filter & Metering Skid) Installation | Activity | 2CF1265W42A05.4 | (Gas Final Filter & Metering Skid) Installation | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2877 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2CF1265W42A15.4 | (TCA Cooler) Installation | (TCA Cooler) Installation | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2CF1265W42A15.4 (TCA Cooler) Installation | Activity | 2CF1265W42A15.4 | (TCA Cooler) Installation | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2878 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2CF1265W58A06.4 | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | 2008-06-19 | 2008-07-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2CF1265W58A06.4 (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | Activity | 2CF1265W58A06.4 | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | 2008-06-19 00:00:00 | 2008-07-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2879 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2CF1265W74A07.4 | (FGSS) Installation- Elec. | (FGSS) Installation- Elec. | 2008-07-21 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2CF1265W74A07.4 (FGSS) Installation- Elec. | Activity | 2CF1265W74A07.4 | (FGSS) Installation- Elec. | 2008-07-21 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2880 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2CF1265W90A08.4 | (FGSS) Installation- I&C | (FGSS) Installation- I&C | 2008-07-21 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2CF1265W90A08.4 (FGSS) Installation- I&C | Activity | 2CF1265W90A08.4 | (FGSS) Installation- I&C | 2008-07-21 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2881 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2SF1265W62A09.4 | (FGSS) Loop chek | (FGSS) Loop chek | 2008-09-03 | 2008-09-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2SF1265W62A09.4 (FGSS) Loop chek | Activity | 2SF1265W62A09.4 | (FGSS) Loop chek | 2008-09-03 00:00:00 | 2008-09-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2882 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2SF1265W62A10.4 | (FGSS) Function Test | (FGSS) Function Test | 2008-09-13 | 2008-09-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2SF1265W62A10.4 (FGSS) Function Test | Activity | 2SF1265W62A10.4 | (FGSS) Function Test | 2008-09-13 00:00:00 | 2008-09-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2883 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Gas Supply System | 2SF1265W62A11.4 | (FGSS) Gas Receiving upto GT Final Control Valve | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-09-22 | 2008-09-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Gas Supply System 2SF1265W62A11.4 (FGSS) Gas Receiving upto GT Final Control Valve | Activity | 2SF1265W62A11.4 | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-09-22 00:00:00 | 2008-09-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2885 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Washing & Drain System | 2PF1265W42A02.5P | (Washing & Drain system Skid) P.O & Procurement | (Washing & Drain system Skid) P.O & Procurement | 2007-03-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Washing & Drain System 2PF1265W42A02.5P (Washing & Drain system Skid) P.O & Procurement | Activity | 2PF1265W42A02.5P | (Washing & Drain system Skid) P.O & Procurement | 2007-03-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2886 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Washing & Drain System | 2CF1265W16A01.1 | (Washing & Drain system Skid) FDN Work | (Washing & Drain system Skid) FDN Work | 2007-10-30 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Washing & Drain System 2CF1265W16A01.1 (Washing & Drain system Skid) FDN Work | Activity | 2CF1265W16A01.1 | (Washing & Drain system Skid) FDN Work | 2007-10-30 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2887 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Washing & Drain System | 2PF1265W42A03.5T | (Washing & Drain system Skid) Transportation | (Washing & Drain system Skid) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Washing & Drain System 2PF1265W42A03.5T (Washing & Drain system Skid) Transportation | Activity | 2PF1265W42A03.5T | (Washing & Drain system Skid) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2888 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Washing & Drain System | 2CF1265W42A04.1 | (Washing & Drain system Skid) Installation | (Washing & Drain system Skid) Installation | 2008-05-16 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Washing & Drain System 2CF1265W42A04.1 (Washing & Drain system Skid) Installation | Activity | 2CF1265W42A04.1 | (Washing & Drain system Skid) Installation | 2008-05-16 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2889 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Washing & Drain System | 2CF1265W58A05.1 | (Washing & Drain system Skid) Piping work | (Washing & Drain system Skid) Piping work | 2008-06-03 | 2008-07-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Washing & Drain System 2CF1265W58A05.1 (Washing & Drain system Skid) Piping work | Activity | 2CF1265W58A05.1 | (Washing & Drain system Skid) Piping work | 2008-06-03 00:00:00 | 2008-07-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2890 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Washing & Drain System | 2CF1265W74A07.5 | (Washing & Drain system Skid) Installation- Elec. | (Washing & Drain system Skid) Installation- Elec. | 2008-07-04 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Washing & Drain System 2CF1265W74A07.5 (Washing & Drain system Skid) Installation- Elec. | Activity | 2CF1265W74A07.5 | (Washing & Drain system Skid) Installation- Elec. | 2008-07-04 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2891 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Washing & Drain System | 2CF1265W90A08.5 | (Washing & Drain system Skid) Installation- I&C | (Washing & Drain system Skid) Installation- I&C | 2008-07-04 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Washing & Drain System 2CF1265W90A08.5 (Washing & Drain system Skid) Installation- I&C | Activity | 2CF1265W90A08.5 | (Washing & Drain system Skid) Installation- I&C | 2008-07-04 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2892 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Washing & Drain System | 2CF1265W62A06.1 | (Washing & Drain system Skid) Flushing | (Washing & Drain system Skid) Flushing | 2008-07-04 | 2008-07-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Washing & Drain System 2CF1265W62A06.1 (Washing & Drain system Skid) Flushing | Activity | 2CF1265W62A06.1 | (Washing & Drain system Skid) Flushing | 2008-07-04 00:00:00 | 2008-07-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2893 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Washing & Drain System | 2SF1265W62A09.5 | (Washing & Drain system Skid) Loop chek | (Washing & Drain system Skid) Loop chek | 2008-07-18 | 2008-07-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Washing & Drain System 2SF1265W62A09.5 (Washing & Drain system Skid) Loop chek | Activity | 2SF1265W62A09.5 | (Washing & Drain system Skid) Loop chek | 2008-07-18 00:00:00 | 2008-07-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2894 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Washing & Drain System | 2SF1265W62A10.1 | (Washing & Drain system Skid) Function Test | (Washing & Drain system Skid) Function Test | 2008-07-23 | 2008-07-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Washing & Drain System 2SF1265W62A10.1 (Washing & Drain system Skid) Function Test | Activity | 2SF1265W62A10.1 | (Washing & Drain system Skid) Function Test | 2008-07-23 00:00:00 | 2008-07-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2895 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Washing & Drain System | 2SF1265W62A11.1 | (Washing & Drain system Skid) Load(Running) Test | (Washing & Drain system Skid) Load(Running) Test | 2008-08-12 | 2008-08-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Washing & Drain System 2SF1265W62A11.1 (Washing & Drain system Skid) Load(Running) Test | Activity | 2SF1265W62A11.1 | (Washing & Drain system Skid) Load(Running) Test | 2008-08-12 00:00:00 | 2008-08-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2897 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2PF1265W42A02.6P | (Fuel oil injection System) P.O & Procurement | (Fuel oil injection System) P.O & Procurement | 2007-03-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2PF1265W42A02.6P (Fuel oil injection System) P.O & Procurement | Activity | 2PF1265W42A02.6P | (Fuel oil injection System) P.O & Procurement | 2007-03-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2898 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2PF1265W42A12.1P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2PF1265W42A12.1P (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | Activity | 2PF1265W42A12.1P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2899 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2PF1265W42A15.1P | (Water injection System) P.O & Procurement | (Water injection System) P.O & Procurement | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2PF1265W42A15.1P (Water injection System) P.O & Procurement | Activity | 2PF1265W42A15.1P | (Water injection System) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2900 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2CF1265W16A01.6 | (Fuel oil injection System) FDN Work | (Fuel oil injection System) FDN Work | 2007-10-30 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2CF1265W16A01.6 (Fuel oil injection System) FDN Work | Activity | 2CF1265W16A01.6 | (Fuel oil injection System) FDN Work | 2007-10-30 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2901 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2CF1265W16A11.1 | (Fuel oil injection Pump & actuator) FDN Work | (Fuel oil injection Pump & actuator) FDN Work | 2007-10-30 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2CF1265W16A11.1 (Fuel oil injection Pump & actuator) FDN Work | Activity | 2CF1265W16A11.1 | (Fuel oil injection Pump & actuator) FDN Work | 2007-10-30 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2902 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2CF1265W16A15.1 | (Water injection System) FDN Work | (Water injection System) FDN Work | 2007-10-30 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2CF1265W16A15.1 (Water injection System) FDN Work | Activity | 2CF1265W16A15.1 | (Water injection System) FDN Work | 2007-10-30 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2903 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2PF1265W42A13.1T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2PF1265W42A13.1T (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | Activity | 2PF1265W42A13.1T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2904 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2PF1265W42A16.1T | (Water injection System) Transportation | (Water injection System) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2PF1265W42A16.1T (Water injection System) Transportation | Activity | 2PF1265W42A16.1T | (Water injection System) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2905 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2PF1265W42A03.6T | (Fuel oil injection System) Transportation | (Fuel oil injection System) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2PF1265W42A03.6T (Fuel oil injection System) Transportation | Activity | 2PF1265W42A03.6T | (Fuel oil injection System) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2906 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2CF1265W42A14.1 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2CF1265W42A14.1 (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | Activity | 2CF1265W42A14.1 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2907 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2CF1265W42A17.1 | (Water injection System) Installation | (Water injection System) Installation | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2CF1265W42A17.1 (Water injection System) Installation | Activity | 2CF1265W42A17.1 | (Water injection System) Installation | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2908 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2CF1265W58A18.1 | (Water injection System) Piping work | (Water injection System) Piping work | 2008-05-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2CF1265W58A18.1 (Water injection System) Piping work | Activity | 2CF1265W58A18.1 | (Water injection System) Piping work | 2008-05-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2909 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2CF1265W42A04.6 | (Fuel oil injection System) Installation | (Fuel oil injection System) Installation | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2CF1265W42A04.6 (Fuel oil injection System) Installation | Activity | 2CF1265W42A04.6 | (Fuel oil injection System) Installation | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2910 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2CF1265W74A19.1 | (Water injection System) Installation- Elec. | (Water injection System) Installation- Elec. | 2008-05-16 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2CF1265W74A19.1 (Water injection System) Installation- Elec. | Activity | 2CF1265W74A19.1 | (Water injection System) Installation- Elec. | 2008-05-16 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2911 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2CF1265W90A20.1 | (Water injection System) Installation- I&C | (Water injection System) Installation- I&C | 2008-05-16 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2CF1265W90A20.1 (Water injection System) Installation- I&C | Activity | 2CF1265W90A20.1 | (Water injection System) Installation- I&C | 2008-05-16 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2912 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2SF1265W62A21.1 | (Water injection System) Loop chek | (Water injection System) Loop chek | 2008-05-30 | 2008-06-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2SF1265W62A21.1 (Water injection System) Loop chek | Activity | 2SF1265W62A21.1 | (Water injection System) Loop chek | 2008-05-30 00:00:00 | 2008-06-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2913 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2CF1265W58A05.6 | (Fuel oil injection System) Piping work | (Fuel oil injection System) Piping work | 2008-05-31 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2CF1265W58A05.6 (Fuel oil injection System) Piping work | Activity | 2CF1265W58A05.6 | (Fuel oil injection System) Piping work | 2008-05-31 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2914 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2SF1265W62A22.1 | (Water injection System) Function Test | (Water injection System) Function Test | 2008-06-04 | 2008-06-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2SF1265W62A22.1 (Water injection System) Function Test | Activity | 2SF1265W62A22.1 | (Water injection System) Function Test | 2008-06-04 00:00:00 | 2008-06-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2915 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2CF1265W74A06.6 | (Fuel oil injection System) Installation- Elec. | (Fuel oil injection System) Installation- Elec. | 2008-06-16 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2CF1265W74A06.6 (Fuel oil injection System) Installation- Elec. | Activity | 2CF1265W74A06.6 | (Fuel oil injection System) Installation- Elec. | 2008-06-16 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2916 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2CF1265W90A07.6 | (Fuel oil injection System) Installation- I&C | (Fuel oil injection System) Installation- I&C | 2008-06-16 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2CF1265W90A07.6 (Fuel oil injection System) Installation- I&C | Activity | 2CF1265W90A07.6 | (Fuel oil injection System) Installation- I&C | 2008-06-16 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2917 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2SF1265W62A08.6 | (Fuel oil injection System) Loop chek | (Fuel oil injection System) Loop chek | 2008-06-29 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2SF1265W62A08.6 (Fuel oil injection System) Loop chek | Activity | 2SF1265W62A08.6 | (Fuel oil injection System) Loop chek | 2008-06-29 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2918 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2SF1265W62A23.1 | (Water injection System) Load Test | (Water injection System) Load Test | 2008-08-12 | 2008-08-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2SF1265W62A23.1 (Water injection System) Load Test | Activity | 2SF1265W62A23.1 | (Water injection System) Load Test | 2008-08-12 00:00:00 | 2008-08-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2919 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2SF1265W62A09.6 | (Fuel oil injection System) Function Test | (Fuel oil injection System) Function Test | 2008-08-15 | 2008-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2SF1265W62A09.6 (Fuel oil injection System) Function Test | Activity | 2SF1265W62A09.6 | (Fuel oil injection System) Function Test | 2008-08-15 00:00:00 | 2008-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2920 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fuel Oil Injection System | 2SF1265W62A10.6 | (Fuel oil injection System) Flushing | (Fuel oil injection System) Flushing | 2008-08-30 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fuel Oil Injection System 2SF1265W62A10.6 (Fuel oil injection System) Flushing | Activity | 2SF1265W62A10.6 | (Fuel oil injection System) Flushing | 2008-08-30 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2922 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Vibration Monitoring System (VMS) | 2PF1260W86A02.1P | (VMS) P.O & Procurement for GT | (VMS) P.O & Procurement for GT | 2007-08-31 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Vibration Monitoring System (VMS) 2PF1260W86A02.1P (VMS) P.O & Procurement for GT | Activity | 2PF1260W86A02.1P | (VMS) P.O & Procurement for GT | 2007-08-31 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2923 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Vibration Monitoring System (VMS) | 2PF1260W86A03.1T | (VMS) Transportation for GT | (VMS) Transportation for GT | 2008-06-03 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Vibration Monitoring System (VMS) 2PF1260W86A03.1T (VMS) Transportation for GT | Activity | 2PF1260W86A03.1T | (VMS) Transportation for GT | 2008-06-03 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2924 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Vibration Monitoring System (VMS) | 2CF1260W86A04.1 | (VMS) Installation for GT | (VMS) Installation for GT | 2008-09-16 | 2008-09-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Vibration Monitoring System (VMS) 2CF1260W86A04.1 (VMS) Installation for GT | Activity | 2CF1260W86A04.1 | (VMS) Installation for GT | 2008-09-16 00:00:00 | 2008-09-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2925 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Vibration Monitoring System (VMS) | 2SF1260W62A05.1 | (VMS) Function Test for GT | (VMS) Function Test for GT | 2008-09-24 | 2008-09-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Vibration Monitoring System (VMS) 2SF1260W62A05.1 (VMS) Function Test for GT | Activity | 2SF1260W62A05.1 | (VMS) Function Test for GT | 2008-09-24 00:00:00 | 2008-09-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2927 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2EF1225W00A01.1 | (CCWS) CCW H/EX key data | (CCWS) CCW H/EX key data | 2007-03-30 | 2007-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2EF1225W00A01.1 (CCWS) CCW H/EX key data | Activity | 2EF1225W00A01.1 | (CCWS) CCW H/EX key data | 2007-03-30 00:00:00 | 2007-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2928 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2PF1225W42A12.1P | (EXP Head Tank) P.O & Procurement | (EXP Head Tank) P.O & Procurement | 2007-07-03 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2PF1225W42A12.1P (EXP Head Tank) P.O & Procurement | Activity | 2PF1225W42A12.1P | (EXP Head Tank) P.O & Procurement | 2007-07-03 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2929 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2EF1225W16A09.1 | (EXP Head Tank) FDN Design | (EXP Head Tank) FDN Design | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2EF1225W16A09.1 (EXP Head Tank) FDN Design | Activity | 2EF1225W16A09.1 | (EXP Head Tank) FDN Design | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2930 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2PF1225W42A06.1P | (CCWP) P.O & Procurement for GT | (CCWP) P.O & Procurement for GT | 2007-07-03 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2PF1225W42A06.1P (CCWP) P.O & Procurement for GT | Activity | 2PF1225W42A06.1P | (CCWP) P.O & Procurement for GT | 2007-07-03 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2931 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2EF1225W16A03.1 | (CCWP) FDN Design | (CCWP) FDN Design | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2EF1225W16A03.1 (CCWP) FDN Design | Activity | 2EF1225W16A03.1 | (CCWP) FDN Design | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2932 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2PF1225W42A18.1P | (CCW H/EX) P.O & Procurement_Fin fan cooler | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2PF1225W42A18.1P (CCW H/EX) P.O & Procurement_Fin fan cooler | Activity | 2PF1225W42A18.1P | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2933 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2EF1225W16A15.1 | (CCW H/EX) FDN Design_Fin fan cooler | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2EF1225W16A15.1 (CCW H/EX) FDN Design_Fin fan cooler | Activity | 2EF1225W16A15.1 | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2934 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2CF1225W16A04.1 | (CCWP) FDN Work | (CCWP) FDN Work | 2007-11-30 | 2008-01-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2CF1225W16A04.1 (CCWP) FDN Work | Activity | 2CF1225W16A04.1 | (CCWP) FDN Work | 2007-11-30 00:00:00 | 2008-01-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2935 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2CF1225W16A16.1 | (CCW H/EX) FDN Work_Fin fan cooler | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 | 2008-02-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2CF1225W16A16.1 (CCW H/EX) FDN Work_Fin fan cooler | Activity | 2CF1225W16A16.1 | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 00:00:00 | 2008-02-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2936 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2CF1225W16A10.1 | (EXP Head Tank) FDN Work | (EXP Head Tank) FDN Work | 2008-01-01 | 2008-01-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2CF1225W16A10.1 (EXP Head Tank) FDN Work | Activity | 2CF1225W16A10.1 | (EXP Head Tank) FDN Work | 2008-01-01 00:00:00 | 2008-01-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2937 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2PF1225W42A13.1T | (EXP Head Tank) Transportation | (EXP Head Tank) Transportation | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2PF1225W42A13.1T (EXP Head Tank) Transportation | Activity | 2PF1225W42A13.1T | (EXP Head Tank) Transportation | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2938 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2PF1225W42A07.1T | (CCWP) Transportation for GT | (CCWP) Transportation for GT | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2PF1225W42A07.1T (CCWP) Transportation for GT | Activity | 2PF1225W42A07.1T | (CCWP) Transportation for GT | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2939 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2PF1225W42A19.1T | (CCW H/EX) Transportation_Fin fan cooler | (CCW H/EX) Transportation_Fin fan cooler | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2PF1225W42A19.1T (CCW H/EX) Transportation_Fin fan cooler | Activity | 2PF1225W42A19.1T | (CCW H/EX) Transportation_Fin fan cooler | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2940 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2CF1225W58A21.1 | (CCWS) Piping Work | (CCWS) Piping Work | 2008-06-09 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2CF1225W58A21.1 (CCWS) Piping Work | Activity | 2CF1225W58A21.1 | (CCWS) Piping Work | 2008-06-09 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2941 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2CF1225W42A14.1 | (EXP Head Tank) Installation | (EXP Head Tank) Installation | 2008-06-16 | 2008-07-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2CF1225W42A14.1 (EXP Head Tank) Installation | Activity | 2CF1225W42A14.1 | (EXP Head Tank) Installation | 2008-06-16 00:00:00 | 2008-07-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2942 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2CF1225W42A08.1 | (CCWP) Installation | (CCWP) Installation | 2008-06-16 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2CF1225W42A08.1 (CCWP) Installation | Activity | 2CF1225W42A08.1 | (CCWP) Installation | 2008-06-16 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2943 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2CF1225W42A20.1 | (CCW H/EX) Installation_Fin fan cooler | (CCW H/EX) Installation_Fin fan cooler | 2008-06-16 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2CF1225W42A20.1 (CCW H/EX) Installation_Fin fan cooler | Activity | 2CF1225W42A20.1 | (CCW H/EX) Installation_Fin fan cooler | 2008-06-16 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2944 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2CF1225W74A22.1 | (CCWS) Installation & Test - Elec. | (CCWS) Installation & Test - Elec. | 2008-06-30 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2CF1225W74A22.1 (CCWS) Installation & Test - Elec. | Activity | 2CF1225W74A22.1 | (CCWS) Installation & Test - Elec. | 2008-06-30 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2945 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2CF1225W90A23.1 | (CCWS) Installation & Test - I&C | (CCWS) Installation & Test - I&C | 2008-06-30 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2CF1225W90A23.1 (CCWS) Installation & Test - I&C | Activity | 2CF1225W90A23.1 | (CCWS) Installation & Test - I&C | 2008-06-30 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2946 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2SF1225W62A24.1 | (CCWS) Loop chek | (CCWS) Loop chek | 2008-07-31 | 2008-08-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2SF1225W62A24.1 (CCWS) Loop chek | Activity | 2SF1225W62A24.1 | (CCWS) Loop chek | 2008-07-31 00:00:00 | 2008-08-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2947 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2SF1225W62A25.1 | (CCWS) Function Test | (CCWS) Function Test | 2008-08-10 | 2008-08-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2SF1225W62A25.1 (CCWS) Function Test | Activity | 2SF1225W62A25.1 | (CCWS) Function Test | 2008-08-10 00:00:00 | 2008-08-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2948 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Closed Cooling Water System | 2SF1225W62A26.1 | (CCWS) Flushing | (CCWS) Flushing | 2008-08-15 | 2008-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Closed Cooling Water System 2SF1225W62A26.1 (CCWS) Flushing | Activity | 2SF1225W62A26.1 | (CCWS) Flushing | 2008-08-15 00:00:00 | 2008-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2950 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fire fighting System | 2PF1265W38A01.1P | (F/F GTG#22) P.O & Procurement_CO2 FF System | (F/F GTG#22) P.O & Procurement_CO2 FF System | 2007-03-30 | 2008-04-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fire fighting System 2PF1265W38A01.1P (F/F GTG#22) P.O & Procurement_CO2 FF System | Activity | 2PF1265W38A01.1P | (F/F GTG#22) P.O & Procurement_CO2 FF System | 2007-03-30 00:00:00 | 2008-04-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2951 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fire fighting System | 2PF1265W38A04.1P | (F/F GTG#22) P.O & Procurement_Clean Agent FF System | (F/F GTG#22) P.O & Procurement_Clean Agent FF System | 2007-03-30 | 2008-04-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fire fighting System 2PF1265W38A04.1P (F/F GTG#22) P.O & Procurement_Clean Agent FF System | Activity | 2PF1265W38A04.1P | (F/F GTG#22) P.O & Procurement_Clean Agent FF System | 2007-03-30 00:00:00 | 2008-04-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2952 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fire fighting System | 2PF1265W38A02.1T | (F/F GTG#22) Transportation_CO2 FF System | (F/F GTG#22) Transportation_CO2 FF System | 2008-04-15 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fire fighting System 2PF1265W38A02.1T (F/F GTG#22) Transportation_CO2 FF System | Activity | 2PF1265W38A02.1T | (F/F GTG#22) Transportation_CO2 FF System | 2008-04-15 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2953 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fire fighting System | 2PF1265W38A05.1T | (F/F GTG#22) Transportation_Clean Agent FF System | (F/F GTG#22) Transportation_Clean Agent FF System | 2008-04-15 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fire fighting System 2PF1265W38A05.1T (F/F GTG#22) Transportation_Clean Agent FF System | Activity | 2PF1265W38A05.1T | (F/F GTG#22) Transportation_Clean Agent FF System | 2008-04-15 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2954 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fire fighting System | 2CF1265W38A03.1 | (F/F GTG#22) Installation_CO2 FF System | (F/F GTG#22) Installation_CO2 FF System | 2008-05-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fire fighting System 2CF1265W38A03.1 (F/F GTG#22) Installation_CO2 FF System | Activity | 2CF1265W38A03.1 | (F/F GTG#22) Installation_CO2 FF System | 2008-05-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2955 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fire fighting System | 2CF1265W38A06.1 | (F/F GTG#22) Installation_Clean Agent FF System | (F/F GTG#22) Installation_Clean Agent FF System | 2008-05-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fire fighting System 2CF1265W38A06.1 (F/F GTG#22) Installation_Clean Agent FF System | Activity | 2CF1265W38A06.1 | (F/F GTG#22) Installation_Clean Agent FF System | 2008-05-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2956 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fire fighting System | 2CF1265W38A07.1 | (F/F GTG#22) Piping work | (F/F GTG#22) Piping work | 2008-06-14 | 2008-07-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fire fighting System 2CF1265W38A07.1 (F/F GTG#22) Piping work | Activity | 2CF1265W38A07.1 | (F/F GTG#22) Piping work | 2008-06-14 00:00:00 | 2008-07-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2957 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fire fighting System | 2SF1265W62A08.7 | (F/F GTG#22) Loop chek | (F/F GTG#22) Loop chek | 2008-07-09 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fire fighting System 2SF1265W62A08.7 (F/F GTG#22) Loop chek | Activity | 2SF1265W62A08.7 | (F/F GTG#22) Loop chek | 2008-07-09 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2958 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fire fighting System | 2SF1265W62A09.7 | (F/F GTG#22) Function Test(incl. Alarm Test) | (F/F GTG#22) Function Test(incl. Alarm Test) | 2008-07-16 | 2008-07-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fire fighting System 2SF1265W62A09.7 (F/F GTG#22) Function Test(incl. Alarm Test) | Activity | 2SF1265W62A09.7 | (F/F GTG#22) Function Test(incl. Alarm Test) | 2008-07-16 00:00:00 | 2008-07-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2959 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Fire fighting System | 2SF1265W62A10.7 | (F/F GTG#22) CO2 Discharge Test | (F/F GTG#22) CO2 Discharge Test | 2008-07-26 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Fire fighting System 2SF1265W62A10.7 (F/F GTG#22) CO2 Discharge Test | Activity | 2SF1265W62A10.7 | (F/F GTG#22) CO2 Discharge Test | 2008-07-26 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2961 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2PF1265W42A02.8P | (Purge Air System) P.O & Procurement | (Purge Air System) P.O & Procurement | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2PF1265W42A02.8P (Purge Air System) P.O & Procurement | Activity | 2PF1265W42A02.8P | (Purge Air System) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2962 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2PF1265W42A12.8P | (Control Oil) P.O & Procurement | (Control Oil) P.O & Procurement | 2007-03-30 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2PF1265W42A12.8P (Control Oil) P.O & Procurement | Activity | 2PF1265W42A12.8P | (Control Oil) P.O & Procurement | 2007-03-30 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2963 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2CF1265W16A01.8 | (Purge Air System) FDN Work | (Purge Air System) FDN Work | 2007-10-30 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2CF1265W16A01.8 (Purge Air System) FDN Work | Activity | 2CF1265W16A01.8 | (Purge Air System) FDN Work | 2007-10-30 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2964 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2CF1265W16A11.8 | (Control Oil) FDN Work | (Control Oil) FDN Work | 2007-10-30 | 2007-12-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2CF1265W16A11.8 (Control Oil) FDN Work | Activity | 2CF1265W16A11.8 | (Control Oil) FDN Work | 2007-10-30 00:00:00 | 2007-12-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2965 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2PF1265W42A03.8T | (Purge Air System) Transportation | (Purge Air System) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2PF1265W42A03.8T (Purge Air System) Transportation | Activity | 2PF1265W42A03.8T | (Purge Air System) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2966 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2PF1265W42A13.8T | (Control Oil)Transportation | (Control Oil)Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2PF1265W42A13.8T (Control Oil)Transportation | Activity | 2PF1265W42A13.8T | (Control Oil)Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2967 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2CF1265W42A04.8 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2CF1265W42A04.8 (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | Activity | 2CF1265W42A04.8 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2968 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2CF1265W42A14.8 | (Control Oil) Installation | (Control Oil) Installation | 2008-04-16 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2CF1265W42A14.8 (Control Oil) Installation | Activity | 2CF1265W42A14.8 | (Control Oil) Installation | 2008-04-16 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2969 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2CF1265W16A05.8 | (Purge Air System) Piping work | (Purge Air System) Piping work | 2008-05-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2CF1265W16A05.8 (Purge Air System) Piping work | Activity | 2CF1265W16A05.8 | (Purge Air System) Piping work | 2008-05-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2970 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2CF1265W16A15.8 | (Control Oil) Piping work | (Control Oil) Piping work | 2008-05-01 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2CF1265W16A15.8 (Control Oil) Piping work | Activity | 2CF1265W16A15.8 | (Control Oil) Piping work | 2008-05-01 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2971 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2CF1265W74A06.8 | (Purge Air System) Installation- Elec. | (Purge Air System) Installation- Elec. | 2008-05-16 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2CF1265W74A06.8 (Purge Air System) Installation- Elec. | Activity | 2CF1265W74A06.8 | (Purge Air System) Installation- Elec. | 2008-05-16 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2972 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2CF1265W90A07.8 | (Purge Air System) Installation- I&C | (Purge Air System) Installation- I&C | 2008-05-16 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2CF1265W90A07.8 (Purge Air System) Installation- I&C | Activity | 2CF1265W90A07.8 | (Purge Air System) Installation- I&C | 2008-05-16 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2973 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2SF1265W62A08.8 | (Purge Air System) Loop chek | (Purge Air System) Loop chek | 2008-05-30 | 2008-06-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2SF1265W62A08.8 (Purge Air System) Loop chek | Activity | 2SF1265W62A08.8 | (Purge Air System) Loop chek | 2008-05-30 00:00:00 | 2008-06-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2974 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2SF1265W62A09.8 | (Purge Air System) Function Test | (Purge Air System) Function Test | 2008-06-02 | 2008-06-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2SF1265W62A09.8 (Purge Air System) Function Test | Activity | 2SF1265W62A09.8 | (Purge Air System) Function Test | 2008-06-02 00:00:00 | 2008-06-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2975 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2CF1265W74A16.8 | (Control Oil) Installation- Elec. | (Control Oil) Installation- Elec. | 2008-06-02 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2CF1265W74A16.8 (Control Oil) Installation- Elec. | Activity | 2CF1265W74A16.8 | (Control Oil) Installation- Elec. | 2008-06-02 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2976 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2CF1265W90A17.8 | (Control Oil) Installation- I&C | (Control Oil) Installation- I&C | 2008-06-02 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2CF1265W90A17.8 (Control Oil) Installation- I&C | Activity | 2CF1265W90A17.8 | (Control Oil) Installation- I&C | 2008-06-02 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2977 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2SF1265W62A10.8 | (Purge Air System) Load Test | (Purge Air System) Load Test | 2008-06-05 | 2008-06-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2SF1265W62A10.8 (Purge Air System) Load Test | Activity | 2SF1265W62A10.8 | (Purge Air System) Load Test | 2008-06-05 00:00:00 | 2008-06-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2978 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2SF1265W62A18.8 | (Control Oil) Loop chek | (Control Oil) Loop chek | 2008-06-15 | 2008-06-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2SF1265W62A18.8 (Control Oil) Loop chek | Activity | 2SF1265W62A18.8 | (Control Oil) Loop chek | 2008-06-15 00:00:00 | 2008-06-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2979 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2SF1265W62A19.8 | (Control Oil) Function Test | (Control Oil) Function Test | 2008-06-20 | 2008-06-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2SF1265W62A19.8 (Control Oil) Function Test | Activity | 2SF1265W62A19.8 | (Control Oil) Function Test | 2008-06-20 00:00:00 | 2008-06-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2980 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Auxiliary System | 2SF1265W62A20.8 | (Control Oil) Flushing | (Control Oil) Flushing | 2008-06-30 | 2008-07-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Auxiliary System 2SF1265W62A20.8 (Control Oil) Flushing | Activity | 2SF1265W62A20.8 | (Control Oil) Flushing | 2008-06-30 00:00:00 | 2008-07-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2982 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9011W62A01.1 | (GTG #22) Fuel Gas System Final Function Test | (GTG #22) Fuel Gas System Final Function Test | 2008-09-29 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9011W62A01.1 (GTG #22) Fuel Gas System Final Function Test | Activity | 2SF9011W62A01.1 | (GTG #22) Fuel Gas System Final Function Test | 2008-09-29 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2983 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9011W62A02.1 | (GTG #22) Turning Gear Operation | (GTG #22) Turning Gear Operation | 2008-10-02 | 2008-10-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9011W62A02.1 (GTG #22) Turning Gear Operation | Activity | 2SF9011W62A02.1 | (GTG #22) Turning Gear Operation | 2008-10-02 00:00:00 | 2008-10-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2984 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9011W62A03.1 | (GTG #22) Initial Firing with FSNL | (GTG #22) Initial Firing with FSNL | 2008-10-04 | 2008-10-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9011W62A03.1 (GTG #22) Initial Firing with FSNL | Activity | 2SF9011W62A03.1 | (GTG #22) Initial Firing with FSNL | 2008-10-04 00:00:00 | 2008-10-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2985 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9012W62A04.1 | (GTG #22) TBN & GEN Protection Test | (GTG #22) TBN & GEN Protection Test | 2008-10-05 | 2008-10-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9012W62A04.1 (GTG #22) TBN & GEN Protection Test | Activity | 2SF9012W62A04.1 | (GTG #22) TBN & GEN Protection Test | 2008-10-05 00:00:00 | 2008-10-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2986 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9012W62A05.1 | (GTG #22) 1st Synchronization | (GTG #22) 1st Synchronization | 2008-10-07 | 2008-10-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9012W62A05.1 (GTG #22) 1st Synchronization | Activity | 2SF9012W62A05.1 | (GTG #22) 1st Synchronization | 2008-10-07 00:00:00 | 2008-10-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2987 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9012W62A06.1 | (GTG #22) Optimization with Fuel Gas | (GTG #22) Optimization with Fuel Gas | 2008-10-09 | 2008-10-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9012W62A06.1 (GTG #22) Optimization with Fuel Gas | Activity | 2SF9012W62A06.1 | (GTG #22) Optimization with Fuel Gas | 2008-10-09 00:00:00 | 2008-10-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2988 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9012W62A07.1 | (GTG #22) Fuel Oil System Final Function Test | (GTG #22) Fuel Oil System Final Function Test | 2008-10-24 | 2008-11-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9012W62A07.1 (GTG #22) Fuel Oil System Final Function Test | Activity | 2SF9012W62A07.1 | (GTG #22) Fuel Oil System Final Function Test | 2008-10-24 00:00:00 | 2008-11-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2989 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9012W62A08.1 | (GTG #22) Optimization with Fuel Oil | (GTG #22) Optimization with Fuel Oil | 2008-11-03 | 2008-12-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9012W62A08.1 (GTG #22) Optimization with Fuel Oil | Activity | 2SF9012W62A08.1 | (GTG #22) Optimization with Fuel Oil | 2008-11-03 00:00:00 | 2008-12-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2990 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9012W62A13.1 | (GTG #22) Fuel Change-Over Test | (GTG #22) Fuel Change-Over Test | 2008-12-03 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9012W62A13.1 (GTG #22) Fuel Change-Over Test | Activity | 2SF9012W62A13.1 | (GTG #22) Fuel Change-Over Test | 2008-12-03 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2991 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9012W62A09.1 | (GTG #22) Black start Test with GT | (GTG #22) Black start Test with GT | 2008-12-03 | 2008-12-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9012W62A09.1 (GTG #22) Black start Test with GT | Activity | 2SF9012W62A09.1 | (GTG #22) Black start Test with GT | 2008-12-03 00:00:00 | 2008-12-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2992 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9012W62A10.1 | (GTG #22) Trial Run Test | (GTG #22) Trial Run Test | 2008-12-04 | 2008-12-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9012W62A10.1 (GTG #22) Trial Run Test | Activity | 2SF9012W62A10.1 | (GTG #22) Trial Run Test | 2008-12-04 00:00:00 | 2008-12-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2993 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9013W62A11.1 | (GTG #22) Reliability Test | (GTG #22) Reliability Test | 2008-12-05 | 2008-12-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9013W62A11.1 (GTG #22) Reliability Test | Activity | 2SF9013W62A11.1 | (GTG #22) Reliability Test | 2008-12-05 00:00:00 | 2008-12-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2994 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Gas Turbine & Generator #21 & #22 > GTG #22 > GTG #22 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Gas Turbine & Generator #21 & #22 | GTG #22 | GTG #22 Commissioning | 2SF9013W62A12.1 | (GTG #22) Performance Test (Fuel Gas & Fuel Oil) | (GTG #22) Performance Test (Fuel Gas & Fuel Oil) | 2008-12-20 | 2009-01-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Gas Turbine & Generator #21 & #22 GTG #22 GTG #22 Commissioning 2SF9013W62A12.1 (GTG #22) Performance Test (Fuel Gas & Fuel Oil) | Activity | 2SF9013W62A12.1 | (GTG #22) Performance Test (Fuel Gas & Fuel Oil) | 2008-12-20 00:00:00 | 2009-01-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2997 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG Common |  | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | (HRSG #21/#22) HRSG Process, GA Data | 2007-03-01 | 2007-03-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG Common 2EF1600W00A02 (HRSG #21/#22) HRSG Process, GA Data | Activity | 2EF1600W00A02 | (HRSG #21/#22) HRSG Process, GA Data | 2007-03-01 00:00:00 | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2998 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG Common |  | 2EF1600W00A03 | (HRSG #21/#22) Instrument, Service Air Data | (HRSG #21/#22) Instrument, Service Air Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG Common 2EF1600W00A03 (HRSG #21/#22) Instrument, Service Air Data | Activity | 2EF1600W00A03 | (HRSG #21/#22) Instrument, Service Air Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 2999 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG Common |  | 2EF1600W00A04 | (HRSG #21/#22) Utility Consumption Data | (HRSG #21/#22) Utility Consumption Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG Common 2EF1600W00A04 (HRSG #21/#22) Utility Consumption Data | Activity | 2EF1600W00A04 | (HRSG #21/#22) Utility Consumption Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3000 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG Common |  | 2EF1600W00A05 | (HRSG #21/#22) Emergency Load Data | (HRSG #21/#22) Emergency Load Data | 2007-03-01 | 2007-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG Common 2EF1600W00A05 (HRSG #21/#22) Emergency Load Data | Activity | 2EF1600W00A05 | (HRSG #21/#22) Emergency Load Data | 2007-03-01 00:00:00 | 2007-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3001 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG Common |  | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | (HRSG #21/#22) P&ID & System Design | 2007-04-18 | 2008-04-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG Common 2EF1600W00A01.0 (HRSG #21/#22) P&ID & System Design | Activity | 2EF1600W00A01.0 | (HRSG #21/#22) P&ID & System Design | 2007-04-18 00:00:00 | 2008-04-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3004 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | HRSG LEB | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | (HRSG #21 LEB) GA & Load Data to Civil Design | 2007-06-20 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 HRSG LEB 2EF1600W00A01 (HRSG #21 LEB) GA & Load Data to Civil Design | Activity | 2EF1600W00A01 | (HRSG #21 LEB) GA & Load Data to Civil Design | 2007-06-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3005 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | HRSG LEB | 2EF1600W32A02 | (HRSG #21 LEB) Building Design | (HRSG #21 LEB) Building Design | 2007-06-20 | 2007-11-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 HRSG LEB 2EF1600W32A02 (HRSG #21 LEB) Building Design | Activity | 2EF1600W32A02 | (HRSG #21 LEB) Building Design | 2007-06-20 00:00:00 | 2007-11-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3006 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | HRSG LEB | 2PF1600W90A10P | (HRSG #21 LEB) P.O & Procurement - I&C | (HRSG #21 LEB) P.O & Procurement - I&C | 2007-09-15 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 HRSG LEB 2PF1600W90A10P (HRSG #21 LEB) P.O & Procurement - I&C | Activity | 2PF1600W90A10P | (HRSG #21 LEB) P.O & Procurement - I&C | 2007-09-15 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3007 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | HRSG LEB | 2PF1600W74A06P | (HRSG #21 LEB) P.O & Procurement - Elec | (HRSG #21 LEB) P.O & Procurement - Elec | 2007-09-15 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 HRSG LEB 2PF1600W74A06P (HRSG #21 LEB) P.O & Procurement - Elec | Activity | 2PF1600W74A06P | (HRSG #21 LEB) P.O & Procurement - Elec | 2007-09-15 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3008 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | HRSG LEB | 2CF1600W16A03 | (HRSG #21 LEB) FDN Work | (HRSG #21 LEB) FDN Work | 2008-02-01 | 2008-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 HRSG LEB 2CF1600W16A03 (HRSG #21 LEB) FDN Work | Activity | 2CF1600W16A03 | (HRSG #21 LEB) FDN Work | 2008-02-01 00:00:00 | 2008-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3009 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | HRSG LEB | 2CF1600W32A04 | (HRSG #21 LEB) Structure Work | (HRSG #21 LEB) Structure Work | 2008-03-31 | 2008-06-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 HRSG LEB 2CF1600W32A04 (HRSG #21 LEB) Structure Work | Activity | 2CF1600W32A04 | (HRSG #21 LEB) Structure Work | 2008-03-31 00:00:00 | 2008-06-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3010 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | HRSG LEB | 2CF1600W36A14 | (HRSG #21 LEB) Installation & Test - HVAC | (HRSG #21 LEB) Installation & Test - HVAC | 2008-07-31 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 HRSG LEB 2CF1600W36A14 (HRSG #21 LEB) Installation & Test - HVAC | Activity | 2CF1600W36A14 | (HRSG #21 LEB) Installation & Test - HVAC | 2008-07-31 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3011 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | HRSG LEB | 2PF1600W90A11T | (HRSG #21 LEB) Transportataion - I&C | (HRSG #21 LEB) Transportataion - I&C | 2008-08-02 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 HRSG LEB 2PF1600W90A11T (HRSG #21 LEB) Transportataion - I&C | Activity | 2PF1600W90A11T | (HRSG #21 LEB) Transportataion - I&C | 2008-08-02 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3012 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | HRSG LEB | 2PF1600W74A07T | (HRSG #21 LEB) Transportataion - Elec | (HRSG #21 LEB) Transportataion - Elec | 2008-08-02 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 HRSG LEB 2PF1600W74A07T (HRSG #21 LEB) Transportataion - Elec | Activity | 2PF1600W74A07T | (HRSG #21 LEB) Transportataion - Elec | 2008-08-02 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3013 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | HRSG LEB | 2CF1600W90A12 | (HRSG #21 LEB) Installation & Test - I&C | (HRSG #21 LEB) Installation & Test - I&C | 2008-10-20 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 HRSG LEB 2CF1600W90A12 (HRSG #21 LEB) Installation & Test - I&C | Activity | 2CF1600W90A12 | (HRSG #21 LEB) Installation & Test - I&C | 2008-10-20 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3014 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | HRSG LEB | 2CF1600W74A08 | (HRSG #21 LEB) Installation & Test - Elec | (HRSG #21 LEB) Installation & Test - Elec | 2008-10-20 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 HRSG LEB 2CF1600W74A08 (HRSG #21 LEB) Installation & Test - Elec | Activity | 2CF1600W74A08 | (HRSG #21 LEB) Installation & Test - Elec | 2008-10-20 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3015 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | HRSG LEB | 2CF1600W38A13 | (HRSG #21 LEB) Installation & Test - Fire Fighting Sys. | (HRSG #21 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 HRSG LEB 2CF1600W38A13 (HRSG #21 LEB) Installation & Test - Fire Fighting Sys. | Activity | 2CF1600W38A13 | (HRSG #21 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3017 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Steel Structure & Casing | 2EF1610W20A01 | (HRSG #21 S/Structure & Casing) Design | (HRSG #21 S/Structure & Casing) Design | 2007-05-18 | 2007-12-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Steel Structure & Casing 2EF1610W20A01 (HRSG #21 S/Structure & Casing) Design | Activity | 2EF1610W20A01 | (HRSG #21 S/Structure & Casing) Design | 2007-05-18 00:00:00 | 2007-12-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3018 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Steel Structure & Casing | 2PF1610W20A03P | (HRSG #21 S/Structure & Casing) P.O & Procurement | (HRSG #21 S/Structure & Casing) P.O & Procurement | 2007-06-14 | 2008-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Steel Structure & Casing 2PF1610W20A03P (HRSG #21 S/Structure & Casing) P.O & Procurement | Activity | 2PF1610W20A03P | (HRSG #21 S/Structure & Casing) P.O & Procurement | 2007-06-14 00:00:00 | 2008-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3019 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Steel Structure & Casing | 2PF1610W20A04T | (HRSG #21 S/Structure & Casing) Transportation | (HRSG #21 S/Structure & Casing) Transportation | 2008-03-04 | 2008-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Steel Structure & Casing 2PF1610W20A04T (HRSG #21 S/Structure & Casing) Transportation | Activity | 2PF1610W20A04T | (HRSG #21 S/Structure & Casing) Transportation | 2008-03-04 00:00:00 | 2008-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3020 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Steel Structure & Casing | 2CF1610W20A05 | (HRSG #21 S/Structure & Casing) S/Structure Installation | (HRSG #21 S/Structure & Casing) S/Structure Installation | 2008-04-18 | 2008-06-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Steel Structure & Casing 2CF1610W20A05 (HRSG #21 S/Structure & Casing) S/Structure Installation | Activity | 2CF1610W20A05 | (HRSG #21 S/Structure & Casing) S/Structure Installation | 2008-04-18 00:00:00 | 2008-06-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3021 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Steel Structure & Casing | 2CF1610W20A06 | (HRSG #21 S/Structure & Casing) Casing Installation | (HRSG #21 S/Structure & Casing) Casing Installation | 2008-06-19 | 2008-08-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Steel Structure & Casing 2CF1610W20A06 (HRSG #21 S/Structure & Casing) Casing Installation | Activity | 2CF1610W20A06 | (HRSG #21 S/Structure & Casing) Casing Installation | 2008-06-19 00:00:00 | 2008-08-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3023 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2EF1615W64A04 | (HRSG #21 Duct) Design | (HRSG #21 Duct) Design | 2007-05-17 | 2007-11-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2EF1615W64A04 (HRSG #21 Duct) Design | Activity | 2EF1615W64A04 | (HRSG #21 Duct) Design | 2007-05-17 00:00:00 | 2007-11-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3024 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | (HRSG #21 Duct) GA & Load Data to Civil Design | 2007-05-30 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2EF1615W00A01 (HRSG #21 Duct) GA & Load Data to Civil Design | Activity | 2EF1615W00A01 | (HRSG #21 Duct) GA & Load Data to Civil Design | 2007-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3025 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2PF1615W64A14P | (HRSG #21 EXP Joint & Bellows) P.O & Procurement | (HRSG #21 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2PF1615W64A14P (HRSG #21 EXP Joint & Bellows) P.O & Procurement | Activity | 2PF1615W64A14P | (HRSG #21 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3026 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2PF1615W64A10P | (HRSG #21 Damper) P.O & Procurement | (HRSG #21 Damper) P.O & Procurement | 2007-06-13 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2PF1615W64A10P (HRSG #21 Damper) P.O & Procurement | Activity | 2PF1615W64A10P | (HRSG #21 Damper) P.O & Procurement | 2007-06-13 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3027 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | (HRSG #21 Duct) P.O & Procurement | 2007-06-14 | 2008-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2PF1615W64A06P (HRSG #21 Duct) P.O & Procurement | Activity | 2PF1615W64A06P | (HRSG #21 Duct) P.O & Procurement | 2007-06-14 00:00:00 | 2008-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3028 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2EF1615W16A02 | (HRSG #21 Duct) FDN Design | (HRSG #21 Duct) FDN Design | 2007-09-03 | 2008-01-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2EF1615W16A02 (HRSG #21 Duct) FDN Design | Activity | 2EF1615W16A02 | (HRSG #21 Duct) FDN Design | 2007-09-03 00:00:00 | 2008-01-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3029 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2CF1615W16A03 | (HRSG #21 Duct) FDN Work | (HRSG #21 Duct) FDN Work | 2008-01-15 | 2008-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2CF1615W16A03 (HRSG #21 Duct) FDN Work | Activity | 2CF1615W16A03 | (HRSG #21 Duct) FDN Work | 2008-01-15 00:00:00 | 2008-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3030 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2PF1615W64A07T | (HRSG #21 Duct) Transportation | (HRSG #21 Duct) Transportation | 2008-03-04 | 2008-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2PF1615W64A07T (HRSG #21 Duct) Transportation | Activity | 2PF1615W64A07T | (HRSG #21 Duct) Transportation | 2008-03-04 00:00:00 | 2008-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3031 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2PF1615W64A11T | (HRSG #21 Damper) Transportation | (HRSG #21 Damper) Transportation | 2008-04-02 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2PF1615W64A11T (HRSG #21 Damper) Transportation | Activity | 2PF1615W64A11T | (HRSG #21 Damper) Transportation | 2008-04-02 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3032 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2PF1615W64A15T | (HRSG #21 EXP Joint & Bellows) Transportation | (HRSG #21 EXP Joint & Bellows) Transportation | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2PF1615W64A15T (HRSG #21 EXP Joint & Bellows) Transportation | Activity | 2PF1615W64A15T | (HRSG #21 EXP Joint & Bellows) Transportation | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3033 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2CF1615W64A12 | (HRSG #21 Damper) Installation | (HRSG #21 Damper) Installation | 2008-05-17 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2CF1615W64A12 (HRSG #21 Damper) Installation | Activity | 2CF1615W64A12 | (HRSG #21 Damper) Installation | 2008-05-17 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3034 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2CF1615W64A17 | (HRSG #21) Installation_Diverter Damper | (HRSG #21) Installation_Diverter Damper | 2008-06-02 | 2008-06-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2CF1615W64A17 (HRSG #21) Installation_Diverter Damper | Activity | 2CF1615W64A17 | (HRSG #21) Installation_Diverter Damper | 2008-06-02 00:00:00 | 2008-06-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3035 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2CF1615W64A20 | (HRSG #21) Installation_Guillotine Damper | (HRSG #21) Installation_Guillotine Damper | 2008-06-26 | 2008-07-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2CF1615W64A20 (HRSG #21) Installation_Guillotine Damper | Activity | 2CF1615W64A20 | (HRSG #21) Installation_Guillotine Damper | 2008-06-26 00:00:00 | 2008-07-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3036 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2CF1615W86A18 | (HRSG #21) Installation_Diverter Damper Control Unit | (HRSG #21) Installation_Diverter Damper Control Unit | 2008-06-26 | 2008-07-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2CF1615W86A18 (HRSG #21) Installation_Diverter Damper Control Unit | Activity | 2CF1615W86A18 | (HRSG #21) Installation_Diverter Damper Control Unit | 2008-06-26 00:00:00 | 2008-07-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3037 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2CF1615W62A19 | (HRSG #21) Diverter Damper Control Unit Flushing | (HRSG #21) Diverter Damper Control Unit Flushing | 2008-07-08 | 2008-07-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2CF1615W62A19 (HRSG #21) Diverter Damper Control Unit Flushing | Activity | 2CF1615W62A19 | (HRSG #21) Diverter Damper Control Unit Flushing | 2008-07-08 00:00:00 | 2008-07-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3038 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2SF1615W62A21 | (HRSG #21) Diverter Damper Function Test for GT #21 | (HRSG #21) Diverter Damper Function Test for GT #21 | 2008-08-05 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2SF1615W62A21 (HRSG #21) Diverter Damper Function Test for GT #21 | Activity | 2SF1615W62A21 | (HRSG #21) Diverter Damper Function Test for GT #21 | 2008-08-05 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3039 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2SF1615W62A22 | (HRSG #21) Guillotine Damper Function Test for GT #21 | (HRSG #21) Guillotine Damper Function Test for GT #21 | 2008-08-05 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2SF1615W62A22 (HRSG #21) Guillotine Damper Function Test for GT #21 | Activity | 2SF1615W62A22 | (HRSG #21) Guillotine Damper Function Test for GT #21 | 2008-08-05 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3040 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2CF1615W64A08 | (HRSG #21 Duct) Duct Installation | (HRSG #21 Duct) Duct Installation | 2008-10-18 | 2009-01-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2CF1615W64A08 (HRSG #21 Duct) Duct Installation | Activity | 2CF1615W64A08 | (HRSG #21 Duct) Duct Installation | 2008-10-18 00:00:00 | 2009-01-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3041 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Duct | 2CF1615W64A16 | (HRSG #21 EXP Joint & Bellows) Installation | (HRSG #21 EXP Joint & Bellows) Installation | 2008-12-20 | 2009-02-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Duct 2CF1615W64A16 (HRSG #21 EXP Joint & Bellows) Installation | Activity | 2CF1615W64A16 | (HRSG #21 EXP Joint & Bellows) Installation | 2008-12-20 00:00:00 | 2009-02-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3043 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Module | 2PF1610W42A02P | (HRSG #21 Module) P.O & Procurement | (HRSG #21 Module) P.O & Procurement | 2007-07-03 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Module 2PF1610W42A02P (HRSG #21 Module) P.O & Procurement | Activity | 2PF1610W42A02P | (HRSG #21 Module) P.O & Procurement | 2007-07-03 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3044 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Module | 2PF1610W42A03T | (HRSG #21 Module) Transportation | (HRSG #21 Module) Transportation | 2008-04-03 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Module 2PF1610W42A03T (HRSG #21 Module) Transportation | Activity | 2PF1610W42A03T | (HRSG #21 Module) Transportation | 2008-04-03 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3045 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Module | 2CF1610W42A04 | (HRSG #21 Module) Installation | (HRSG #21 Module) Installation | 2008-08-18 | 2008-10-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Module 2CF1610W42A04 (HRSG #21 Module) Installation | Activity | 2CF1610W42A04 | (HRSG #21 Module) Installation | 2008-08-18 00:00:00 | 2008-10-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3047 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Drum | 2EF1645W42A01 | (HRSG #21 Drum) Design | (HRSG #21 Drum) Design | 2007-05-17 | 2007-12-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Drum 2EF1645W42A01 (HRSG #21 Drum) Design | Activity | 2EF1645W42A01 | (HRSG #21 Drum) Design | 2007-05-17 00:00:00 | 2007-12-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3048 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Drum | 2PF1645W42A03P | (HRSG #21 Drum) P.O & Procurement | (HRSG #21 Drum) P.O & Procurement | 2007-06-13 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Drum 2PF1645W42A03P (HRSG #21 Drum) P.O & Procurement | Activity | 2PF1645W42A03P | (HRSG #21 Drum) P.O & Procurement | 2007-06-13 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3049 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Drum | 2PF1645W42A04T | (HRSG #21 Drum) Transportation | (HRSG #21 Drum) Transportation | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Drum 2PF1645W42A04T (HRSG #21 Drum) Transportation | Activity | 2PF1645W42A04T | (HRSG #21 Drum) Transportation | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3050 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Drum | 2CF1645W42A05 | (HRSG #21 Drum) Installation | (HRSG #21 Drum) Installation | 2008-10-18 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Drum 2CF1645W42A05 (HRSG #21 Drum) Installation | Activity | 2CF1645W42A05 | (HRSG #21 Drum) Installation | 2008-10-18 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3052 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Bypass Stack | 2EF1625W42A04 | (HRSG #21 Bypass Stack) Design | (HRSG #21 Bypass Stack) Design | 2007-05-17 | 2007-11-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Bypass Stack 2EF1625W42A04 (HRSG #21 Bypass Stack) Design | Activity | 2EF1625W42A04 | (HRSG #21 Bypass Stack) Design | 2007-05-17 00:00:00 | 2007-11-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3053 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Bypass Stack | 2PF1625W42A10P | (HRSG #21 Bypass Stack Silencer) P.O & Procurement | (HRSG #21 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Bypass Stack 2PF1625W42A10P (HRSG #21 Bypass Stack Silencer) P.O & Procurement | Activity | 2PF1625W42A10P | (HRSG #21 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3054 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Bypass Stack | 2EF1625W00A01 | (HRSG #21 Bypass Stack) GA & Load Data to Civil Design | (HRSG #21 Bypass Stack) GA & Load Data to Civil Design | 2007-07-02 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Bypass Stack 2EF1625W00A01 (HRSG #21 Bypass Stack) GA & Load Data to Civil Design | Activity | 2EF1625W00A01 | (HRSG #21 Bypass Stack) GA & Load Data to Civil Design | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3055 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Bypass Stack | 2PF1625W42A06P | (HRSG #21 Bypass Stack) P.O & Procurement | (HRSG #21 Bypass Stack) P.O & Procurement | 2007-07-03 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Bypass Stack 2PF1625W42A06P (HRSG #21 Bypass Stack) P.O & Procurement | Activity | 2PF1625W42A06P | (HRSG #21 Bypass Stack) P.O & Procurement | 2007-07-03 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3056 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Bypass Stack | 2EF1625W16A02 | (HRSG #21 Bypass Stack) FDN Design | (HRSG #21 Bypass Stack) FDN Design | 2007-10-04 | 2008-02-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Bypass Stack 2EF1625W16A02 (HRSG #21 Bypass Stack) FDN Design | Activity | 2EF1625W16A02 | (HRSG #21 Bypass Stack) FDN Design | 2007-10-04 00:00:00 | 2008-02-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3057 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Bypass Stack | 2CF1625W16A03 | (HRSG #21 Bypass Stack) FDN Work | (HRSG #21 Bypass Stack) FDN Work | 2008-02-12 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Bypass Stack 2CF1625W16A03 (HRSG #21 Bypass Stack) FDN Work | Activity | 2CF1625W16A03 | (HRSG #21 Bypass Stack) FDN Work | 2008-02-12 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3058 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Bypass Stack | 2PF1625W42A07T | (HRSG #21 Bypass Stack) Transportation | (HRSG #21 Bypass Stack) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Bypass Stack 2PF1625W42A07T (HRSG #21 Bypass Stack) Transportation | Activity | 2PF1625W42A07T | (HRSG #21 Bypass Stack) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3059 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Bypass Stack | 2PF1625W42A11T | (HRSG #21 Bypass Stack Silencer) Transportation | (HRSG #21 Bypass Stack Silencer) Transportation | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Bypass Stack 2PF1625W42A11T (HRSG #21 Bypass Stack Silencer) Transportation | Activity | 2PF1625W42A11T | (HRSG #21 Bypass Stack Silencer) Transportation | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3060 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Bypass Stack | 2CF1625W42A08 | (HRSG #21 Bypass Stack) Installation | (HRSG #21 Bypass Stack) Installation | 2008-05-01 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Bypass Stack 2CF1625W42A08 (HRSG #21 Bypass Stack) Installation | Activity | 2CF1625W42A08 | (HRSG #21 Bypass Stack) Installation | 2008-05-01 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3061 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Bypass Stack | 2CF1625W42A12 | (HRSG #21 Bypass Stack Silencer) Installation | (HRSG #21 Bypass Stack Silencer) Installation | 2008-07-02 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Bypass Stack 2CF1625W42A12 (HRSG #21 Bypass Stack Silencer) Installation | Activity | 2CF1625W42A12 | (HRSG #21 Bypass Stack Silencer) Installation | 2008-07-02 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3063 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Main Stack | 2EF1625W42A01 | (HRSG #21 Main Stack) Design | (HRSG #21 Main Stack) Design | 2007-05-17 | 2007-11-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Main Stack 2EF1625W42A01 (HRSG #21 Main Stack) Design | Activity | 2EF1625W42A01 | (HRSG #21 Main Stack) Design | 2007-05-17 00:00:00 | 2007-11-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3064 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Main Stack | 2PF1625W42A06.0P | (HRSG #21 Main Stack) P.O & Procurement | (HRSG #21 Main Stack) P.O & Procurement | 2007-06-04 | 2008-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Main Stack 2PF1625W42A06.0P (HRSG #21 Main Stack) P.O & Procurement | Activity | 2PF1625W42A06.0P | (HRSG #21 Main Stack) P.O & Procurement | 2007-06-04 00:00:00 | 2008-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3065 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Main Stack | 2EF1625W00A02 | (HRSG #21 Main Stack) GA & Load Data to Civil Design | (HRSG #21 Main Stack) GA & Load Data to Civil Design | 2007-07-05 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Main Stack 2EF1625W00A02 (HRSG #21 Main Stack) GA & Load Data to Civil Design | Activity | 2EF1625W00A02 | (HRSG #21 Main Stack) GA & Load Data to Civil Design | 2007-07-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3066 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Main Stack | 2PF1625W42A10.0P | (HRSG #21 Main Stack Silencer) P.O & Procurement | (HRSG #21 Main Stack Silencer) P.O & Procurement | 2007-07-27 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Main Stack 2PF1625W42A10.0P (HRSG #21 Main Stack Silencer) P.O & Procurement | Activity | 2PF1625W42A10.0P | (HRSG #21 Main Stack Silencer) P.O & Procurement | 2007-07-27 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3067 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Main Stack | 2EF1625W16A03 | (HRSG #21 Main Stack) FDN Design | (HRSG #21 Main Stack) FDN Design | 2007-10-09 | 2008-02-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Main Stack 2EF1625W16A03 (HRSG #21 Main Stack) FDN Design | Activity | 2EF1625W16A03 | (HRSG #21 Main Stack) FDN Design | 2007-10-09 00:00:00 | 2008-02-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3068 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Main Stack | 2CF1625W16A04 | (HRSG #21 Main Stack) FDN Work | (HRSG #21 Main Stack) FDN Work | 2008-02-15 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Main Stack 2CF1625W16A04 (HRSG #21 Main Stack) FDN Work | Activity | 2CF1625W16A04 | (HRSG #21 Main Stack) FDN Work | 2008-02-15 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3069 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Main Stack | 2PF1625W42A07.0T | (HRSG #21 Main Stack) Transportation | (HRSG #21 Main Stack) Transportation | 2008-03-04 | 2008-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Main Stack 2PF1625W42A07.0T (HRSG #21 Main Stack) Transportation | Activity | 2PF1625W42A07.0T | (HRSG #21 Main Stack) Transportation | 2008-03-04 00:00:00 | 2008-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3070 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Main Stack | 2PF1625W42A11.0T | (HRSG #21 Main Stack Silencer) Transportation | (HRSG #21 Main Stack Silencer) Transportation | 2008-06-14 | 2008-07-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Main Stack 2PF1625W42A11.0T (HRSG #21 Main Stack Silencer) Transportation | Activity | 2PF1625W42A11.0T | (HRSG #21 Main Stack Silencer) Transportation | 2008-06-14 00:00:00 | 2008-07-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3071 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Main Stack | 2CF1625W42A08.0 | (HRSG #21 Main Stack) Installation | (HRSG #21 Main Stack) Installation | 2008-12-15 | 2009-03-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Main Stack 2CF1625W42A08.0 (HRSG #21 Main Stack) Installation | Activity | 2CF1625W42A08.0 | (HRSG #21 Main Stack) Installation | 2008-12-15 00:00:00 | 2009-03-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3072 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Main Stack | 2CF1625W42A12.0 | (HRSG #21 Main Stack Silencer) Installation | (HRSG #21 Main Stack Silencer) Installation | 2009-02-23 | 2009-03-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Main Stack 2CF1625W42A12.0 (HRSG #21 Main Stack Silencer) Installation | Activity | 2CF1625W42A12.0 | (HRSG #21 Main Stack Silencer) Installation | 2009-02-23 00:00:00 | 2009-03-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3074 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Piping Work | 2PF1650W52A02P | (HRSG #21 Insulation) P.O & Procurement | (HRSG #21 Insulation) P.O & Procurement | 2008-01-09 | 2008-10-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Piping Work 2PF1650W52A02P (HRSG #21 Insulation) P.O & Procurement | Activity | 2PF1650W52A02P | (HRSG #21 Insulation) P.O & Procurement | 2008-01-09 00:00:00 | 2008-10-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3075 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Piping Work | 2PF1650W52A03T | (HRSG #21 Insulation) Transportation | (HRSG #21 Insulation) Transportation | 2008-10-31 | 2008-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Piping Work 2PF1650W52A03T (HRSG #21 Insulation) Transportation | Activity | 2PF1650W52A03T | (HRSG #21 Insulation) Transportation | 2008-10-31 00:00:00 | 2008-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3076 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Piping Work | 2CF1640W58A05 | (HRSG #21) Piping Work | (HRSG #21) Piping Work | 2008-11-01 | 2009-02-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Piping Work 2CF1640W58A05 (HRSG #21) Piping Work | Activity | 2CF1640W58A05 | (HRSG #21) Piping Work | 2008-11-01 00:00:00 | 2009-02-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3077 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Piping Work | 2CF1640W62A06 | (HRSG #21 Hydro Test | (HRSG #21 Hydro Test | 2009-02-03 | 2009-02-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Piping Work 2CF1640W62A06 (HRSG #21 Hydro Test | Activity | 2CF1640W62A06 | (HRSG #21 Hydro Test | 2009-02-03 00:00:00 | 2009-02-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3078 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Piping Work | 2CF1650W52A04 | (HRSG #21 Insulation) Installation | (HRSG #21 Insulation) Installation | 2009-02-17 | 2009-03-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Piping Work 2CF1650W52A04 (HRSG #21 Insulation) Installation | Activity | 2CF1650W52A04 | (HRSG #21 Insulation) Installation | 2009-02-17 00:00:00 | 2009-03-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3079 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Piping Work | 2CF1640W60A07 | (HRSG #21) Acid Cleaning | (HRSG #21) Acid Cleaning | 2009-02-27 | 2009-03-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Piping Work 2CF1640W60A07 (HRSG #21) Acid Cleaning | Activity | 2CF1640W60A07 | (HRSG #21) Acid Cleaning | 2009-02-27 00:00:00 | 2009-03-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3081 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | CEMS | 2PF1660W86A04P | (CEMS) P.O & Procurement | (CEMS) P.O & Procurement | 2007-08-29 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 CEMS 2PF1660W86A04P (CEMS) P.O & Procurement | Activity | 2PF1660W86A04P | (CEMS) P.O & Procurement | 2007-08-29 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3082 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | CEMS | 2EF1660W16A01 | (CEMS) FDN Design | (CEMS) FDN Design | 2007-10-30 | 2008-01-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 CEMS 2EF1660W16A01 (CEMS) FDN Design | Activity | 2EF1660W16A01 | (CEMS) FDN Design | 2007-10-30 00:00:00 | 2008-01-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3083 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | CEMS | 2CF1660W16A02 | (CEMS) FDN Work | (CEMS) FDN Work | 2008-01-26 | 2008-03-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 CEMS 2CF1660W16A02 (CEMS) FDN Work | Activity | 2CF1660W16A02 | (CEMS) FDN Work | 2008-01-26 00:00:00 | 2008-03-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3084 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | CEMS | 2PF1660W86A05T | (CEMS) Transportation | (CEMS) Transportation | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 CEMS 2PF1660W86A05T (CEMS) Transportation | Activity | 2PF1660W86A05T | (CEMS) Transportation | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3085 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | CEMS | 2CF1660W86A06 | (CEMS) Installation(incl. Elec, I&C) | (CEMS) Installation(incl. Elec, I&C) | 2008-06-16 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 CEMS 2CF1660W86A06 (CEMS) Installation(incl. Elec, I&C) | Activity | 2CF1660W86A06 | (CEMS) Installation(incl. Elec, I&C) | 2008-06-16 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3086 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | CEMS | 2CF1660W62A07 | (CEMS) Loop Test | (CEMS) Loop Test | 2008-07-02 | 2008-07-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 CEMS 2CF1660W62A07 (CEMS) Loop Test | Activity | 2CF1660W62A07 | (CEMS) Loop Test | 2008-07-02 00:00:00 | 2008-07-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3087 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | CEMS | 2SF1615W62A08 | (HRSG #21) CEMS Function Test for GT #21(Bypass stack) | (HRSG #21) CEMS Function Test for GT #21(Bypass stack) | 2008-08-05 | 2008-08-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 CEMS 2SF1615W62A08 (HRSG #21) CEMS Function Test for GT #21(Bypass stack) | Activity | 2SF1615W62A08 | (HRSG #21) CEMS Function Test for GT #21(Bypass stack) | 2008-08-05 00:00:00 | 2008-08-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3089 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Auxiliary System | 2PF1665W42A02P | (HRSG #21 MECH Vendor Equip) P.O & Procurement | (HRSG #21 MECH Vendor Equip) P.O & Procurement | 2007-09-10 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Auxiliary System 2PF1665W42A02P (HRSG #21 MECH Vendor Equip) P.O & Procurement | Activity | 2PF1665W42A02P | (HRSG #21 MECH Vendor Equip) P.O & Procurement | 2007-09-10 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3090 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Auxiliary System | 2PF1660W86A11P | (HRSG #21 I&C Vendor Equip) P.O & Procurement | (HRSG #21 I&C Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-09-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Auxiliary System 2PF1660W86A11P (HRSG #21 I&C Vendor Equip) P.O & Procurement | Activity | 2PF1660W86A11P | (HRSG #21 I&C Vendor Equip) P.O & Procurement | 2007-10-02 00:00:00 | 2008-09-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3091 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Auxiliary System | 2PF1660W70A06P | (HRSG #21 ELEC Vendor Equip) P.O & Procurement | (HRSG #21 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-09-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Auxiliary System 2PF1660W70A06P (HRSG #21 ELEC Vendor Equip) P.O & Procurement | Activity | 2PF1660W70A06P | (HRSG #21 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 00:00:00 | 2008-09-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3092 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Auxiliary System | 2PF1665W42A03T | (HRSG #21 MECH Vendor Equip) Transportation | (HRSG #21 MECH Vendor Equip) Transportation | 2008-09-03 | 2008-10-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Auxiliary System 2PF1665W42A03T (HRSG #21 MECH Vendor Equip) Transportation | Activity | 2PF1665W42A03T | (HRSG #21 MECH Vendor Equip) Transportation | 2008-09-03 00:00:00 | 2008-10-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3093 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Auxiliary System | 2PF1660W86A12T | (HRSG #21 I&C Vendor Equip) Transportation | (HRSG #21 I&C Vendor Equip) Transportation | 2008-09-04 | 2008-10-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Auxiliary System 2PF1660W86A12T (HRSG #21 I&C Vendor Equip) Transportation | Activity | 2PF1660W86A12T | (HRSG #21 I&C Vendor Equip) Transportation | 2008-09-04 00:00:00 | 2008-10-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3094 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Auxiliary System | 2PF1660W70A07T | (HRSG #21 ELEC Vendor Equip) Transportation | (HRSG #21 ELEC Vendor Equip) Transportation | 2008-09-04 | 2008-10-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Auxiliary System 2PF1660W70A07T (HRSG #21 ELEC Vendor Equip) Transportation | Activity | 2PF1660W70A07T | (HRSG #21 ELEC Vendor Equip) Transportation | 2008-09-04 00:00:00 | 2008-10-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3095 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Auxiliary System | 2CF1665W42A04 | (HRSG #21 MECH Vendor Equip) Installation | (HRSG #21 MECH Vendor Equip) Installation | 2008-10-18 | 2009-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Auxiliary System 2CF1665W42A04 (HRSG #21 MECH Vendor Equip) Installation | Activity | 2CF1665W42A04 | (HRSG #21 MECH Vendor Equip) Installation | 2008-10-18 00:00:00 | 2009-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3096 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Auxiliary System | 2CF1660W86A13 | (HRSG #21 I&C Vendor Equip) Installation | (HRSG #21 I&C Vendor Equip) Installation | 2008-10-20 | 2009-02-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Auxiliary System 2CF1660W86A13 (HRSG #21 I&C Vendor Equip) Installation | Activity | 2CF1660W86A13 | (HRSG #21 I&C Vendor Equip) Installation | 2008-10-20 00:00:00 | 2009-02-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3097 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Auxiliary System | 2CF1660W70A08 | (HRSG #21 ELEC Vendor Equip) Installation | (HRSG #21 ELEC Vendor Equip) Installation | 2008-10-20 | 2009-02-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Auxiliary System 2CF1660W70A08 (HRSG #21 ELEC Vendor Equip) Installation | Activity | 2CF1660W70A08 | (HRSG #21 ELEC Vendor Equip) Installation | 2008-10-20 00:00:00 | 2009-02-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3098 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Auxiliary System | 2CF1655W74A09 | (HRSG #21) Installation & Test - Elec. | (HRSG #21) Installation & Test - Elec. | 2008-11-30 | 2009-03-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Auxiliary System 2CF1655W74A09 (HRSG #21) Installation & Test - Elec. | Activity | 2CF1655W74A09 | (HRSG #21) Installation & Test - Elec. | 2008-11-30 00:00:00 | 2009-03-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3099 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Auxiliary System | 2CF1660W90A14 | (HRSG #21) Installation & Test - I&C | (HRSG #21) Installation & Test - I&C | 2008-11-30 | 2009-03-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Auxiliary System 2CF1660W90A14 (HRSG #21) Installation & Test - I&C | Activity | 2CF1660W90A14 | (HRSG #21) Installation & Test - I&C | 2008-11-30 00:00:00 | 2009-03-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3101 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Commissioning | 2SF1600W62A01 | (HRSG #21) Cold Commissioning for HRSG #21 | (HRSG #21) Cold Commissioning for HRSG #21 | 2009-03-24 | 2009-04-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Commissioning 2SF1600W62A01 (HRSG #21) Cold Commissioning for HRSG #21 | Activity | 2SF1600W62A01 | (HRSG #21) Cold Commissioning for HRSG #21 | 2009-03-24 00:00:00 | 2009-04-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3102 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #21 > Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #21 | Commissioning | 2SF1600W62A02 | (HRSG #21) Function Test for HRSG #21 | (HRSG #21) Function Test for HRSG #21 | 2009-04-13 | 2009-04-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #21 Commissioning 2SF1600W62A02 (HRSG #21) Function Test for HRSG #21 | Activity | 2SF1600W62A02 | (HRSG #21) Function Test for HRSG #21 | 2009-04-13 00:00:00 | 2009-04-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3105 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | HRSG LEB | 2EF1600W00A01.1 | (HRSG #22 LEB) GA & Load Data to Civil Design | (HRSG #22 LEB) GA & Load Data to Civil Design | 2007-06-20 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 HRSG LEB 2EF1600W00A01.1 (HRSG #22 LEB) GA & Load Data to Civil Design | Activity | 2EF1600W00A01.1 | (HRSG #22 LEB) GA & Load Data to Civil Design | 2007-06-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3106 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | HRSG LEB | 2EF1600W32A02.1 | (HRSG #22 LEB) Building Design | (HRSG #22 LEB) Building Design | 2007-06-20 | 2007-11-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 HRSG LEB 2EF1600W32A02.1 (HRSG #22 LEB) Building Design | Activity | 2EF1600W32A02.1 | (HRSG #22 LEB) Building Design | 2007-06-20 00:00:00 | 2007-11-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3107 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | HRSG LEB | 2PF1600W90A10.1P | (HRSG #22 LEB) P.O & Procurement - I&C | (HRSG #22 LEB) P.O & Procurement - I&C | 2007-09-15 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 HRSG LEB 2PF1600W90A10.1P (HRSG #22 LEB) P.O & Procurement - I&C | Activity | 2PF1600W90A10.1P | (HRSG #22 LEB) P.O & Procurement - I&C | 2007-09-15 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3108 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | HRSG LEB | 2PF1600W74A06.1P | (HRSG #22 LEB) P.O & Procurement - Elec | (HRSG #22 LEB) P.O & Procurement - Elec | 2007-09-15 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 HRSG LEB 2PF1600W74A06.1P (HRSG #22 LEB) P.O & Procurement - Elec | Activity | 2PF1600W74A06.1P | (HRSG #22 LEB) P.O & Procurement - Elec | 2007-09-15 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3109 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | HRSG LEB | 2CF1600W16A03.1 | (HRSG #22 LEB)FDN Work | (HRSG #22 LEB)FDN Work | 2008-02-01 | 2008-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 HRSG LEB 2CF1600W16A03.1 (HRSG #22 LEB)FDN Work | Activity | 2CF1600W16A03.1 | (HRSG #22 LEB)FDN Work | 2008-02-01 00:00:00 | 2008-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3110 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | HRSG LEB | 2CF1600W32A04.1 | (HRSG #22 LEB)Structure Work | (HRSG #22 LEB)Structure Work | 2008-03-31 | 2008-06-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 HRSG LEB 2CF1600W32A04.1 (HRSG #22 LEB)Structure Work | Activity | 2CF1600W32A04.1 | (HRSG #22 LEB)Structure Work | 2008-03-31 00:00:00 | 2008-06-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3111 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | HRSG LEB | 2CF1600W36A13.1 | (HRSG #22 LEB) Installation & Test - HVAC | (HRSG #22 LEB) Installation & Test - HVAC | 2008-07-31 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 HRSG LEB 2CF1600W36A13.1 (HRSG #22 LEB) Installation & Test - HVAC | Activity | 2CF1600W36A13.1 | (HRSG #22 LEB) Installation & Test - HVAC | 2008-07-31 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3112 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | HRSG LEB | 2PF1600W90A11.1T | (HRSG #22 LEB) Transportataion - I&C | (HRSG #22 LEB) Transportataion - I&C | 2008-08-02 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 HRSG LEB 2PF1600W90A11.1T (HRSG #22 LEB) Transportataion - I&C | Activity | 2PF1600W90A11.1T | (HRSG #22 LEB) Transportataion - I&C | 2008-08-02 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3113 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | HRSG LEB | 2PF1600W74A07.1T | (HRSG #22 LEB) Transportataion - Elec | (HRSG #22 LEB) Transportataion - Elec | 2008-08-02 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 HRSG LEB 2PF1600W74A07.1T (HRSG #22 LEB) Transportataion - Elec | Activity | 2PF1600W74A07.1T | (HRSG #22 LEB) Transportataion - Elec | 2008-08-02 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3114 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | HRSG LEB | 2CF1600W90A12.1 | (HRSG #22 LEB) Installation & Test - I&C | (HRSG #22 LEB) Installation & Test - I&C | 2008-10-20 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 HRSG LEB 2CF1600W90A12.1 (HRSG #22 LEB) Installation & Test - I&C | Activity | 2CF1600W90A12.1 | (HRSG #22 LEB) Installation & Test - I&C | 2008-10-20 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3115 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | HRSG LEB | 2CF1600W74A08.1 | (HRSG #22 LEB) Installation & Test - Elec | (HRSG #22 LEB) Installation & Test - Elec | 2008-10-20 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 HRSG LEB 2CF1600W74A08.1 (HRSG #22 LEB) Installation & Test - Elec | Activity | 2CF1600W74A08.1 | (HRSG #22 LEB) Installation & Test - Elec | 2008-10-20 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3116 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | HRSG LEB | 2CF1600W38A14.1 | (HRSG #22 LEB) Installation & Test - Fire Fighting Sys. | (HRSG #22 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 HRSG LEB 2CF1600W38A14.1 (HRSG #22 LEB) Installation & Test - Fire Fighting Sys. | Activity | 2CF1600W38A14.1 | (HRSG #22 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3118 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Steel Structure & Casing | 2EF1610W20A01.1 | (HRSG #22 S/Structure & Casing) Design | (HRSG #22 S/Structure & Casing) Design | 2007-05-18 | 2007-12-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Steel Structure & Casing 2EF1610W20A01.1 (HRSG #22 S/Structure & Casing) Design | Activity | 2EF1610W20A01.1 | (HRSG #22 S/Structure & Casing) Design | 2007-05-18 00:00:00 | 2007-12-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3119 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Steel Structure & Casing | 2PF1610W20A03.1P | (HRSG #22 S/Structure & Casing) P.O & Procurement | (HRSG #22 S/Structure & Casing) P.O & Procurement | 2007-06-14 | 2008-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Steel Structure & Casing 2PF1610W20A03.1P (HRSG #22 S/Structure & Casing) P.O & Procurement | Activity | 2PF1610W20A03.1P | (HRSG #22 S/Structure & Casing) P.O & Procurement | 2007-06-14 00:00:00 | 2008-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3120 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Steel Structure & Casing | 2PF1610W20A04.1T | (HRSG #22 S/Structure & Casing) Transportation | (HRSG #22 S/Structure & Casing) Transportation | 2008-03-04 | 2008-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Steel Structure & Casing 2PF1610W20A04.1T (HRSG #22 S/Structure & Casing) Transportation | Activity | 2PF1610W20A04.1T | (HRSG #22 S/Structure & Casing) Transportation | 2008-03-04 00:00:00 | 2008-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3121 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Steel Structure & Casing | 2CF1610W20A05.1 | (HRSG #22 S/Structure & Casing) S/Structure Installation | (HRSG #22 S/Structure & Casing) S/Structure Installation | 2008-04-18 | 2008-06-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Steel Structure & Casing 2CF1610W20A05.1 (HRSG #22 S/Structure & Casing) S/Structure Installation | Activity | 2CF1610W20A05.1 | (HRSG #22 S/Structure & Casing) S/Structure Installation | 2008-04-18 00:00:00 | 2008-06-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3122 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Steel Structure & Casing | 2CF1610W20A06.1 | (HRSG #22 S/Structure & Casing) Casing Installation | (HRSG #22 S/Structure & Casing) Casing Installation | 2008-06-19 | 2008-08-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Steel Structure & Casing 2CF1610W20A06.1 (HRSG #22 S/Structure & Casing) Casing Installation | Activity | 2CF1610W20A06.1 | (HRSG #22 S/Structure & Casing) Casing Installation | 2008-06-19 00:00:00 | 2008-08-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3124 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2EF1615W64A01.1 | (HRSG #22 Duct) Design | (HRSG #22 Duct) Design | 2007-05-17 | 2007-11-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2EF1615W64A01.1 (HRSG #22 Duct) Design | Activity | 2EF1615W64A01.1 | (HRSG #22 Duct) Design | 2007-05-17 00:00:00 | 2007-11-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3125 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2EF1615W00A02.1 | (HRSG #22 Duct) GA & Load Data to Civil Design | (HRSG #22 Duct) GA & Load Data to Civil Design | 2007-05-30 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2EF1615W00A02.1 (HRSG #22 Duct) GA & Load Data to Civil Design | Activity | 2EF1615W00A02.1 | (HRSG #22 Duct) GA & Load Data to Civil Design | 2007-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3126 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2PF1665W64A14.1P | (HRSG #22 EXP Joint & Bellows) P.O & Procurement | (HRSG #22 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2PF1665W64A14.1P (HRSG #22 EXP Joint & Bellows) P.O & Procurement | Activity | 2PF1665W64A14.1P | (HRSG #22 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3127 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2PF1615W64A10.1P | (HRSG #22 Damper) P.O & Procurement | (HRSG #22 Damper) P.O & Procurement | 2007-06-13 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2PF1615W64A10.1P (HRSG #22 Damper) P.O & Procurement | Activity | 2PF1615W64A10.1P | (HRSG #22 Damper) P.O & Procurement | 2007-06-13 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3128 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2PF1615W64A06.1P | (HRSG #22 Duct) P.O & Procurement | (HRSG #22 Duct) P.O & Procurement | 2007-06-14 | 2008-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2PF1615W64A06.1P (HRSG #22 Duct) P.O & Procurement | Activity | 2PF1615W64A06.1P | (HRSG #22 Duct) P.O & Procurement | 2007-06-14 00:00:00 | 2008-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3129 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2EF1615W16A03.1 | (HRSG #22 Duct) FDN Design | (HRSG #22 Duct) FDN Design | 2007-09-03 | 2008-01-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2EF1615W16A03.1 (HRSG #22 Duct) FDN Design | Activity | 2EF1615W16A03.1 | (HRSG #22 Duct) FDN Design | 2007-09-03 00:00:00 | 2008-01-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3130 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2CF1615W16A04.1 | (HRSG #22 Duct) FDN Work | (HRSG #22 Duct) FDN Work | 2008-01-15 | 2008-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2CF1615W16A04.1 (HRSG #22 Duct) FDN Work | Activity | 2CF1615W16A04.1 | (HRSG #22 Duct) FDN Work | 2008-01-15 00:00:00 | 2008-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3131 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2PF1615W64A07.1T | (HRSG #22 Duct) Transportation | (HRSG #22 Duct) Transportation | 2008-03-04 | 2008-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2PF1615W64A07.1T (HRSG #22 Duct) Transportation | Activity | 2PF1615W64A07.1T | (HRSG #22 Duct) Transportation | 2008-03-04 00:00:00 | 2008-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3132 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2PF1615W64A11.1T | (HRSG #22 Damper) Transportation | (HRSG #22 Damper) Transportation | 2008-04-02 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2PF1615W64A11.1T (HRSG #22 Damper) Transportation | Activity | 2PF1615W64A11.1T | (HRSG #22 Damper) Transportation | 2008-04-02 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3133 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2PF1665W64A15.1T | (HRSG #22 EXP Joint & Bellows) Transportation | (HRSG #22 EXP Joint & Bellows) Transportation | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2PF1665W64A15.1T (HRSG #22 EXP Joint & Bellows) Transportation | Activity | 2PF1665W64A15.1T | (HRSG #22 EXP Joint & Bellows) Transportation | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3134 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2CF1615W64A12.1 | (HRSG #22 Damper) Installation | (HRSG #22 Damper) Installation | 2008-05-17 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2CF1615W64A12.1 (HRSG #22 Damper) Installation | Activity | 2CF1615W64A12.1 | (HRSG #22 Damper) Installation | 2008-05-17 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3135 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2CF1615W64A17.1 | (HRSG #22) Installation_Diverter Damper | (HRSG #22) Installation_Diverter Damper | 2008-06-02 | 2008-06-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2CF1615W64A17.1 (HRSG #22) Installation_Diverter Damper | Activity | 2CF1615W64A17.1 | (HRSG #22) Installation_Diverter Damper | 2008-06-02 00:00:00 | 2008-06-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3136 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2CF1615W64A18.1 | (HRSG #22) Installation_Guillotine Damper | (HRSG #22) Installation_Guillotine Damper | 2008-06-26 | 2008-07-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2CF1615W64A18.1 (HRSG #22) Installation_Guillotine Damper | Activity | 2CF1615W64A18.1 | (HRSG #22) Installation_Guillotine Damper | 2008-06-26 00:00:00 | 2008-07-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3137 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2CF1615W86A19.1 | (HRSG #22) Installation_Diverter Damper Control Unit | (HRSG #22) Installation_Diverter Damper Control Unit | 2008-06-26 | 2008-07-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2CF1615W86A19.1 (HRSG #22) Installation_Diverter Damper Control Unit | Activity | 2CF1615W86A19.1 | (HRSG #22) Installation_Diverter Damper Control Unit | 2008-06-26 00:00:00 | 2008-07-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3138 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2CF1615W62A20.1 | (HRSG #22) Diverter Damper Control Unit Flushing | (HRSG #22) Diverter Damper Control Unit Flushing | 2008-07-08 | 2008-07-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2CF1615W62A20.1 (HRSG #22) Diverter Damper Control Unit Flushing | Activity | 2CF1615W62A20.1 | (HRSG #22) Diverter Damper Control Unit Flushing | 2008-07-08 00:00:00 | 2008-07-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3139 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2SF1615W62A21.1 | (HRSG #22) Diverter Damper Function Test for GT #22 | (HRSG #22) Diverter Damper Function Test for GT #22 | 2008-08-05 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2SF1615W62A21.1 (HRSG #22) Diverter Damper Function Test for GT #22 | Activity | 2SF1615W62A21.1 | (HRSG #22) Diverter Damper Function Test for GT #22 | 2008-08-05 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3140 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2SF1615W62A22.1 | (HRSG #22) Guillotine Damper Function Test for GT #22 | (HRSG #22) Guillotine Damper Function Test for GT #22 | 2008-08-05 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2SF1615W62A22.1 (HRSG #22) Guillotine Damper Function Test for GT #22 | Activity | 2SF1615W62A22.1 | (HRSG #22) Guillotine Damper Function Test for GT #22 | 2008-08-05 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3141 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2CF1615W64A08.1 | (HRSG #22 Duct) Duct Installation | (HRSG #22 Duct) Duct Installation | 2008-10-18 | 2009-01-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2CF1615W64A08.1 (HRSG #22 Duct) Duct Installation | Activity | 2CF1615W64A08.1 | (HRSG #22 Duct) Duct Installation | 2008-10-18 00:00:00 | 2009-01-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3142 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Duct | 2CF1665W64A16.1 | (HRSG #22 EXP Joint & Bellows) Installation | (HRSG #22 EXP Joint & Bellows) Installation | 2008-12-20 | 2009-02-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Duct 2CF1665W64A16.1 (HRSG #22 EXP Joint & Bellows) Installation | Activity | 2CF1665W64A16.1 | (HRSG #22 EXP Joint & Bellows) Installation | 2008-12-20 00:00:00 | 2009-02-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3144 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Module | 2PF1610W42A02.1P | (HRSG #22 Module) P.O & Procurement | (HRSG #22 Module) P.O & Procurement | 2007-07-03 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Module 2PF1610W42A02.1P (HRSG #22 Module) P.O & Procurement | Activity | 2PF1610W42A02.1P | (HRSG #22 Module) P.O & Procurement | 2007-07-03 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3145 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Module | 2PF1610W42A03.1T | (HRSG #22 Module) Transportation | (HRSG #22 Module) Transportation | 2008-04-03 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Module 2PF1610W42A03.1T (HRSG #22 Module) Transportation | Activity | 2PF1610W42A03.1T | (HRSG #22 Module) Transportation | 2008-04-03 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3146 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Module | 2CF1610W42A04.1 | (HRSG #22 Module) Installation | (HRSG #22 Module) Installation | 2008-08-18 | 2008-10-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Module 2CF1610W42A04.1 (HRSG #22 Module) Installation | Activity | 2CF1610W42A04.1 | (HRSG #22 Module) Installation | 2008-08-18 00:00:00 | 2008-10-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3148 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Drum | 2EF1645W42A01.1 | (HRSG #22 Drum) Design | (HRSG #22 Drum) Design | 2007-05-17 | 2007-12-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Drum 2EF1645W42A01.1 (HRSG #22 Drum) Design | Activity | 2EF1645W42A01.1 | (HRSG #22 Drum) Design | 2007-05-17 00:00:00 | 2007-12-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3149 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Drum | 2PF1645W42A03.1P | (HRSG #22 Drum) P.O & Procurement | (HRSG #22 Drum) P.O & Procurement | 2007-06-13 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Drum 2PF1645W42A03.1P (HRSG #22 Drum) P.O & Procurement | Activity | 2PF1645W42A03.1P | (HRSG #22 Drum) P.O & Procurement | 2007-06-13 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3150 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Drum | 2PF1645W42A04.1T | (HRSG #22 Drum) Transportation | (HRSG #22 Drum) Transportation | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Drum 2PF1645W42A04.1T (HRSG #22 Drum) Transportation | Activity | 2PF1645W42A04.1T | (HRSG #22 Drum) Transportation | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3151 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Drum | 2CF1645W42A05.1 | (HRSG #22 Drum) Installation | (HRSG #22 Drum) Installation | 2008-10-18 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Drum 2CF1645W42A05.1 (HRSG #22 Drum) Installation | Activity | 2CF1645W42A05.1 | (HRSG #22 Drum) Installation | 2008-10-18 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3153 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Bypass Stack | 2EF1625W42A01.1 | (HRSG #22 Bypass Stack) Design | (HRSG #22 Bypass Stack) Design | 2007-05-17 | 2007-11-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Bypass Stack 2EF1625W42A01.1 (HRSG #22 Bypass Stack) Design | Activity | 2EF1625W42A01.1 | (HRSG #22 Bypass Stack) Design | 2007-05-17 00:00:00 | 2007-11-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3154 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Bypass Stack | 2PF1625W42A10.1P | (HRSG #22 Bypass Stack Silencer) P.O & Procurement | (HRSG #22 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Bypass Stack 2PF1625W42A10.1P (HRSG #22 Bypass Stack Silencer) P.O & Procurement | Activity | 2PF1625W42A10.1P | (HRSG #22 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3155 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Bypass Stack | 2EF1625W00A02.1 | (HRSG #22 Bypass Stack) GA & Load Data to Civil Design | (HRSG #22 Bypass Stack) GA & Load Data to Civil Design | 2007-07-02 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Bypass Stack 2EF1625W00A02.1 (HRSG #22 Bypass Stack) GA & Load Data to Civil Design | Activity | 2EF1625W00A02.1 | (HRSG #22 Bypass Stack) GA & Load Data to Civil Design | 2007-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3156 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Bypass Stack | 2PF1625W42A06.1P | (HRSG #22 Bypass Stack) P.O & Procurement | (HRSG #22 Bypass Stack) P.O & Procurement | 2007-07-03 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Bypass Stack 2PF1625W42A06.1P (HRSG #22 Bypass Stack) P.O & Procurement | Activity | 2PF1625W42A06.1P | (HRSG #22 Bypass Stack) P.O & Procurement | 2007-07-03 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3157 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Bypass Stack | 2EF1625W16A03.1 | (HRSG #22 Bypass Stack) FDN Design | (HRSG #22 Bypass Stack) FDN Design | 2007-10-04 | 2008-02-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Bypass Stack 2EF1625W16A03.1 (HRSG #22 Bypass Stack) FDN Design | Activity | 2EF1625W16A03.1 | (HRSG #22 Bypass Stack) FDN Design | 2007-10-04 00:00:00 | 2008-02-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3158 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Bypass Stack | 2CF1625W16A04.1 | (HRSG #22 Bypass Stack) FDN Work | (HRSG #22 Bypass Stack) FDN Work | 2008-02-12 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Bypass Stack 2CF1625W16A04.1 (HRSG #22 Bypass Stack) FDN Work | Activity | 2CF1625W16A04.1 | (HRSG #22 Bypass Stack) FDN Work | 2008-02-12 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3159 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Bypass Stack | 2PF1625W42A07.1T | (HRSG #22 Bypass Stack) Transportation | (HRSG #22 Bypass Stack) Transportation | 2008-03-01 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Bypass Stack 2PF1625W42A07.1T (HRSG #22 Bypass Stack) Transportation | Activity | 2PF1625W42A07.1T | (HRSG #22 Bypass Stack) Transportation | 2008-03-01 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3160 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Bypass Stack | 2PF1625W42A11.1T | (HRSG #22 Bypass Stack Silencer) Transportation | (HRSG #22 Bypass Stack Silencer) Transportation | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Bypass Stack 2PF1625W42A11.1T (HRSG #22 Bypass Stack Silencer) Transportation | Activity | 2PF1625W42A11.1T | (HRSG #22 Bypass Stack Silencer) Transportation | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3161 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Bypass Stack | 2CF1625W42A08.1 | (HRSG #22 Bypass Stack) Installation | (HRSG #22 Bypass Stack) Installation | 2008-05-01 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Bypass Stack 2CF1625W42A08.1 (HRSG #22 Bypass Stack) Installation | Activity | 2CF1625W42A08.1 | (HRSG #22 Bypass Stack) Installation | 2008-05-01 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3162 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Bypass Stack | 2CF1625W42A12.1 | (HRSG #22 Bypass Stack Silencer) Installation | (HRSG #22 Bypass Stack Silencer) Installation | 2008-07-02 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Bypass Stack 2CF1625W42A12.1 (HRSG #22 Bypass Stack Silencer) Installation | Activity | 2CF1625W42A12.1 | (HRSG #22 Bypass Stack Silencer) Installation | 2008-07-02 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3164 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Main Stack | 2EF1625W42A01.2 | (HRSG #22 Main Stack) Design | (HRSG #22 Main Stack) Design | 2007-05-17 | 2007-11-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Main Stack 2EF1625W42A01.2 (HRSG #22 Main Stack) Design | Activity | 2EF1625W42A01.2 | (HRSG #22 Main Stack) Design | 2007-05-17 00:00:00 | 2007-11-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3165 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Main Stack | 2PF1625W42A10.2P | (HRSG #22 Main Stack Silencer) P.O & Procurement | (HRSG #22 Main Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Main Stack 2PF1625W42A10.2P (HRSG #22 Main Stack Silencer) P.O & Procurement | Activity | 2PF1625W42A10.2P | (HRSG #22 Main Stack Silencer) P.O & Procurement | 2007-06-13 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3166 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Main Stack | 2EF1625W00A02.2 | (HRSG #22 Main Stack) GA & Load Data to Civil Design | (HRSG #22 Main Stack) GA & Load Data to Civil Design | 2007-07-05 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Main Stack 2EF1625W00A02.2 (HRSG #22 Main Stack) GA & Load Data to Civil Design | Activity | 2EF1625W00A02.2 | (HRSG #22 Main Stack) GA & Load Data to Civil Design | 2007-07-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3167 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Main Stack | 2PF1625W42A06.2P | (HRSG #22 Main Stack) P.O & Procurement | (HRSG #22 Main Stack) P.O & Procurement | 2007-07-18 | 2008-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Main Stack 2PF1625W42A06.2P (HRSG #22 Main Stack) P.O & Procurement | Activity | 2PF1625W42A06.2P | (HRSG #22 Main Stack) P.O & Procurement | 2007-07-18 00:00:00 | 2008-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3168 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Main Stack | 2EF1625W16A03.2 | (HRSG #22 Main Stack) FDN Design | (HRSG #22 Main Stack) FDN Design | 2007-10-09 | 2008-02-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Main Stack 2EF1625W16A03.2 (HRSG #22 Main Stack) FDN Design | Activity | 2EF1625W16A03.2 | (HRSG #22 Main Stack) FDN Design | 2007-10-09 00:00:00 | 2008-02-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3169 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Main Stack | 2CF1625W16A04.2 | (HRSG #22 Main Stack) FDN Work | (HRSG #22 Main Stack) FDN Work | 2008-02-15 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Main Stack 2CF1625W16A04.2 (HRSG #22 Main Stack) FDN Work | Activity | 2CF1625W16A04.2 | (HRSG #22 Main Stack) FDN Work | 2008-02-15 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3170 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Main Stack | 2PF1625W42A07.2T | (HRSG #22 Main Stack) Transportation | (HRSG #22 Main Stack) Transportation | 2008-04-17 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Main Stack 2PF1625W42A07.2T (HRSG #22 Main Stack) Transportation | Activity | 2PF1625W42A07.2T | (HRSG #22 Main Stack) Transportation | 2008-04-17 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3171 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Main Stack | 2PF1625W42A11.2T | (HRSG #22 Main Stack Silencer) Transportation | (HRSG #22 Main Stack Silencer) Transportation | 2008-05-01 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Main Stack 2PF1625W42A11.2T (HRSG #22 Main Stack Silencer) Transportation | Activity | 2PF1625W42A11.2T | (HRSG #22 Main Stack Silencer) Transportation | 2008-05-01 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3172 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Main Stack | 2CF1625W42A08.2 | (HRSG #22 Main Stack) Installation | (HRSG #22 Main Stack) Installation | 2008-12-15 | 2009-02-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Main Stack 2CF1625W42A08.2 (HRSG #22 Main Stack) Installation | Activity | 2CF1625W42A08.2 | (HRSG #22 Main Stack) Installation | 2008-12-15 00:00:00 | 2009-02-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3173 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Main Stack | 2CF1625W42A12.2 | (HRSG #22 Main Stack Silencer) Installation | (HRSG #22 Main Stack Silencer) Installation | 2009-02-23 | 2009-03-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Main Stack 2CF1625W42A12.2 (HRSG #22 Main Stack Silencer) Installation | Activity | 2CF1625W42A12.2 | (HRSG #22 Main Stack Silencer) Installation | 2009-02-23 00:00:00 | 2009-03-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3175 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Piping Work | 2PF1650W52A02.1P | (HRSG #22 Insulation) P.O & Procurement | (HRSG #22 Insulation) P.O & Procurement | 2008-01-09 | 2008-10-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Piping Work 2PF1650W52A02.1P (HRSG #22 Insulation) P.O & Procurement | Activity | 2PF1650W52A02.1P | (HRSG #22 Insulation) P.O & Procurement | 2008-01-09 00:00:00 | 2008-10-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3176 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Piping Work | 2PF1650W52A03.1T | (HRSG #22 Insulation) Transportation | (HRSG #22 Insulation) Transportation | 2008-10-31 | 2008-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Piping Work 2PF1650W52A03.1T (HRSG #22 Insulation) Transportation | Activity | 2PF1650W52A03.1T | (HRSG #22 Insulation) Transportation | 2008-10-31 00:00:00 | 2008-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3177 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Piping Work | 2CF1640W58A05.1 | (HRSG #22) Piping Work | (HRSG #22) Piping Work | 2008-11-01 | 2009-01-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Piping Work 2CF1640W58A05.1 (HRSG #22) Piping Work | Activity | 2CF1640W58A05.1 | (HRSG #22) Piping Work | 2008-11-01 00:00:00 | 2009-01-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3178 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Piping Work | 2CF1640W62A06.1 | (HRSG #22) Hydro Test | (HRSG #22) Hydro Test | 2009-01-30 | 2009-02-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Piping Work 2CF1640W62A06.1 (HRSG #22) Hydro Test | Activity | 2CF1640W62A06.1 | (HRSG #22) Hydro Test | 2009-01-30 00:00:00 | 2009-02-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3179 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Piping Work | 2CF1650W52A04.1 | (HRSG #22 Insulation) Installation | (HRSG #22 Insulation) Installation | 2009-02-13 | 2009-03-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Piping Work 2CF1650W52A04.1 (HRSG #22 Insulation) Installation | Activity | 2CF1650W52A04.1 | (HRSG #22 Insulation) Installation | 2009-02-13 00:00:00 | 2009-03-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3180 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Piping Work | 2CF1640W60A07.1 | (HRSG #22) Acid Cleaning | (HRSG #22) Acid Cleaning | 2009-02-24 | 2009-03-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Piping Work 2CF1640W60A07.1 (HRSG #22) Acid Cleaning | Activity | 2CF1640W60A07.1 | (HRSG #22) Acid Cleaning | 2009-02-24 00:00:00 | 2009-03-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3182 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | CEMS | 2PF1660W86A04.1P | (CEMS) P.O & Procurement | (CEMS) P.O & Procurement | 2007-08-29 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 CEMS 2PF1660W86A04.1P (CEMS) P.O & Procurement | Activity | 2PF1660W86A04.1P | (CEMS) P.O & Procurement | 2007-08-29 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3183 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | CEMS | 2EF1660W16A01.1 | (CEMS) FDN Design | (CEMS) FDN Design | 2007-10-30 | 2008-01-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 CEMS 2EF1660W16A01.1 (CEMS) FDN Design | Activity | 2EF1660W16A01.1 | (CEMS) FDN Design | 2007-10-30 00:00:00 | 2008-01-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3184 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | CEMS | 2CF1660W16A02.1 | (CEMS) FDN Work | (CEMS) FDN Work | 2008-01-26 | 2008-03-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 CEMS 2CF1660W16A02.1 (CEMS) FDN Work | Activity | 2CF1660W16A02.1 | (CEMS) FDN Work | 2008-01-26 00:00:00 | 2008-03-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3185 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | CEMS | 2PF1660W86A05.1T | (CEMS) Transportation | (CEMS) Transportation | 2008-05-30 | 2008-07-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 CEMS 2PF1660W86A05.1T (CEMS) Transportation | Activity | 2PF1660W86A05.1T | (CEMS) Transportation | 2008-05-30 00:00:00 | 2008-07-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3186 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | CEMS | 2CF1660W86A06.1 | (CEMS) Installation(incl. Elec, I&C) | (CEMS) Installation(incl. Elec, I&C) | 2008-07-15 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 CEMS 2CF1660W86A06.1 (CEMS) Installation(incl. Elec, I&C) | Activity | 2CF1660W86A06.1 | (CEMS) Installation(incl. Elec, I&C) | 2008-07-15 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3187 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | CEMS | 2CF1660W86A07.1 | (CEMS) Loop Test | (CEMS) Loop Test | 2008-07-31 | 2008-08-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 CEMS 2CF1660W86A07.1 (CEMS) Loop Test | Activity | 2CF1660W86A07.1 | (CEMS) Loop Test | 2008-07-31 00:00:00 | 2008-08-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3188 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | CEMS | 2SF1660W62A08.1 | (HRSG #22) CEMS Function Test for GT #11(Bypass stack) | (HRSG #22) CEMS Function Test for GT #11(Bypass stack) | 2008-08-06 | 2008-08-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 CEMS 2SF1660W62A08.1 (HRSG #22) CEMS Function Test for GT #11(Bypass stack) | Activity | 2SF1660W62A08.1 | (HRSG #22) CEMS Function Test for GT #11(Bypass stack) | 2008-08-06 00:00:00 | 2008-08-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3190 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Auxiliary System | 2PF1665W42A12.1P | (HRSG #22 MECH Vendor Equip) P.O & Procurement | (HRSG #22 MECH Vendor Equip) P.O & Procurement | 2007-09-10 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Auxiliary System 2PF1665W42A12.1P (HRSG #22 MECH Vendor Equip) P.O & Procurement | Activity | 2PF1665W42A12.1P | (HRSG #22 MECH Vendor Equip) P.O & Procurement | 2007-09-10 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3191 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Auxiliary System | 2PF1660W86A07.1P | (HRSG #22 I&C Vendor Equip) P.O & Procurement | (HRSG #22 I&C Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-09-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Auxiliary System 2PF1660W86A07.1P (HRSG #22 I&C Vendor Equip) P.O & Procurement | Activity | 2PF1660W86A07.1P | (HRSG #22 I&C Vendor Equip) P.O & Procurement | 2007-10-02 00:00:00 | 2008-09-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3192 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Auxiliary System | 2PF1660W70A02.1P | (HRSG #22 ELEC Vendor Equip) P.O & Procurement | (HRSG #22 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-09-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Auxiliary System 2PF1660W70A02.1P (HRSG #22 ELEC Vendor Equip) P.O & Procurement | Activity | 2PF1660W70A02.1P | (HRSG #22 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 00:00:00 | 2008-09-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3193 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Auxiliary System | 2PF1665W42A13.1T | (HRSG #22 MECH Vendor Equip) Transportation | (HRSG #22 MECH Vendor Equip) Transportation | 2008-09-03 | 2008-10-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Auxiliary System 2PF1665W42A13.1T (HRSG #22 MECH Vendor Equip) Transportation | Activity | 2PF1665W42A13.1T | (HRSG #22 MECH Vendor Equip) Transportation | 2008-09-03 00:00:00 | 2008-10-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3194 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Auxiliary System | 2PF1660W86A08.1T | (HRSG #22 I&C Vendor Equip) Transportation | (HRSG #22 I&C Vendor Equip) Transportation | 2008-09-04 | 2008-10-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Auxiliary System 2PF1660W86A08.1T (HRSG #22 I&C Vendor Equip) Transportation | Activity | 2PF1660W86A08.1T | (HRSG #22 I&C Vendor Equip) Transportation | 2008-09-04 00:00:00 | 2008-10-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3195 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Auxiliary System | 2PF1660W70A03.1T | (HRSG #22 ELEC Vendor Equip) Transportation | (HRSG #22 ELEC Vendor Equip) Transportation | 2008-09-04 | 2008-10-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Auxiliary System 2PF1660W70A03.1T (HRSG #22 ELEC Vendor Equip) Transportation | Activity | 2PF1660W70A03.1T | (HRSG #22 ELEC Vendor Equip) Transportation | 2008-09-04 00:00:00 | 2008-10-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3196 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Auxiliary System | 2CF1665W42A14.1 | (HRSG #22 MECH Vendor Equip) Installation | (HRSG #22 MECH Vendor Equip) Installation | 2008-10-18 | 2009-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Auxiliary System 2CF1665W42A14.1 (HRSG #22 MECH Vendor Equip) Installation | Activity | 2CF1665W42A14.1 | (HRSG #22 MECH Vendor Equip) Installation | 2008-10-18 00:00:00 | 2009-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3197 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Auxiliary System | 2CF1660W86A09.1 | (HRSG #22 I&C Vendor Equip) Installation | (HRSG #22 I&C Vendor Equip) Installation | 2008-10-20 | 2009-02-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Auxiliary System 2CF1660W86A09.1 (HRSG #22 I&C Vendor Equip) Installation | Activity | 2CF1660W86A09.1 | (HRSG #22 I&C Vendor Equip) Installation | 2008-10-20 00:00:00 | 2009-02-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3198 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Auxiliary System | 2CF1660W70A04.1 | (HRSG #22 ELEC Vendor Equip) Installation | (HRSG #22 ELEC Vendor Equip) Installation | 2008-10-20 | 2009-02-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Auxiliary System 2CF1660W70A04.1 (HRSG #22 ELEC Vendor Equip) Installation | Activity | 2CF1660W70A04.1 | (HRSG #22 ELEC Vendor Equip) Installation | 2008-10-20 00:00:00 | 2009-02-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3199 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Auxiliary System | 2CF1655W74A05.1 | (HRSG #22) Installation & Test - Elec. | (HRSG #22) Installation & Test - Elec. | 2008-11-30 | 2009-03-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Auxiliary System 2CF1655W74A05.1 (HRSG #22) Installation & Test - Elec. | Activity | 2CF1655W74A05.1 | (HRSG #22) Installation & Test - Elec. | 2008-11-30 00:00:00 | 2009-03-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3200 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Auxiliary System | 2CF1660W90A10.1 | (HRSG #22) Installation & Test - I&C | (HRSG #22) Installation & Test - I&C | 2008-11-30 | 2009-03-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Auxiliary System 2CF1660W90A10.1 (HRSG #22) Installation & Test - I&C | Activity | 2CF1660W90A10.1 | (HRSG #22) Installation & Test - I&C | 2008-11-30 00:00:00 | 2009-03-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3202 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Commissioning | 2SF1600W62A01.1 | (HRSG #22)Cold Commissioning for HRSG #21 | (HRSG #22)Cold Commissioning for HRSG #21 | 2009-03-24 | 2009-04-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Commissioning 2SF1600W62A01.1 (HRSG #22)Cold Commissioning for HRSG #21 | Activity | 2SF1600W62A01.1 | (HRSG #22)Cold Commissioning for HRSG #21 | 2009-03-24 00:00:00 | 2009-04-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3203 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > HRSG #21 & #22 > HRSG #22 > Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | HRSG #21 & #22 | HRSG #22 | Commissioning | 2SF1600W62A02.1 | (HRSG #22) Function Test for HRSG #22 | (HRSG #22) Function Test for HRSG #22 | 2009-04-13 | 2009-04-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 HRSG #21 & #22 HRSG #22 Commissioning 2SF1600W62A02.1 (HRSG #22) Function Test for HRSG #22 | Activity | 2SF1600W62A02.1 | (HRSG #22) Function Test for HRSG #22 | 2009-04-13 00:00:00 | 2009-04-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3206 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Building |  | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | (STG #20 BLDG) GA & Load Data to Civil Design | 2007-03-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Building 2EF2010W00A01 (STG #20 BLDG) GA & Load Data to Civil Design | Activity | 2EF2010W00A01 | (STG #20 BLDG) GA & Load Data to Civil Design | 2007-03-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3207 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Building |  | 2EF2010W20A02 | (STG #20 BLDG) Buliding Design | (STG #20 BLDG) Buliding Design | 2007-03-01 | 2007-09-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Building 2EF2010W20A02 (STG #20 BLDG) Buliding Design | Activity | 2EF2010W20A02 | (STG #20 BLDG) Buliding Design | 2007-03-01 00:00:00 | 2007-09-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3208 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Building |  | 2PF2010W20A04P | (STG #20 BLDG) P.O & Procurement - Structure Work(S/S) | (STG #20 BLDG) P.O & Procurement - Structure Work(S/S) | 2007-09-19 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Building 2PF2010W20A04P (STG #20 BLDG) P.O & Procurement - Structure Work(S/S) | Activity | 2PF2010W20A04P | (STG #20 BLDG) P.O & Procurement - Structure Work(S/S) | 2007-09-19 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3209 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Building |  | 2CF2010W16A03 | (STG #20 BLDG) FDN Work | (STG #20 BLDG) FDN Work | 2007-11-15 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Building 2CF2010W16A03 (STG #20 BLDG) FDN Work | Activity | 2CF2010W16A03 | (STG #20 BLDG) FDN Work | 2007-11-15 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3210 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Building |  | 2PF2010W20A05T | (STG #20 BLDG) Transportation - Structure Work(S/S) | (STG #20 BLDG) Transportation - Structure Work(S/S) | 2008-02-01 | 2008-03-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Building 2PF2010W20A05T (STG #20 BLDG) Transportation - Structure Work(S/S) | Activity | 2PF2010W20A05T | (STG #20 BLDG) Transportation - Structure Work(S/S) | 2008-02-01 00:00:00 | 2008-03-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3211 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Building |  | 2CF2010W20A06 | (STG #20 BLDG) Structure Work(S/S) | (STG #20 BLDG) Structure Work(S/S) | 2008-03-17 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Building 2CF2010W20A06 (STG #20 BLDG) Structure Work(S/S) | Activity | 2CF2010W20A06 | (STG #20 BLDG) Structure Work(S/S) | 2008-03-17 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3212 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Building |  | 2CF2010W20A07 | (STG #20 BLDG) Cladding Work | (STG #20 BLDG) Cladding Work | 2008-05-26 | 2008-10-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Building 2CF2010W20A07 (STG #20 BLDG) Cladding Work | Activity | 2CF2010W20A07 | (STG #20 BLDG) Cladding Work | 2008-05-26 00:00:00 | 2008-10-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3213 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Building |  | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | (STG #20 BLDG) Roof Work | 2008-08-05 | 2008-11-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Building 2CF2010W20A08 (STG #20 BLDG) Roof Work | Activity | 2CF2010W20A08 | (STG #20 BLDG) Roof Work | 2008-08-05 00:00:00 | 2008-11-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3214 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Building |  | 2CF2010W90A12 | (STG #20 BLDG) Installation & Test - I&C | (STG #20 BLDG) Installation & Test - I&C | 2008-10-13 | 2009-01-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Building 2CF2010W90A12 (STG #20 BLDG) Installation & Test - I&C | Activity | 2CF2010W90A12 | (STG #20 BLDG) Installation & Test - I&C | 2008-10-13 00:00:00 | 2009-01-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3215 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Building |  | 2CF2010W36A10 | (STG #20 BLDG) Installation & Test - HVAC | (STG #20 BLDG) Installation & Test - HVAC | 2008-10-13 | 2008-12-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Building 2CF2010W36A10 (STG #20 BLDG) Installation & Test - HVAC | Activity | 2CF2010W36A10 | (STG #20 BLDG) Installation & Test - HVAC | 2008-10-13 00:00:00 | 2008-12-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3216 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Building |  | 2CF2010W74A11 | (STG #20 BLDG) Installation & Test - Elec | (STG #20 BLDG) Installation & Test - Elec | 2008-10-13 | 2009-01-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Building 2CF2010W74A11 (STG #20 BLDG) Installation & Test - Elec | Activity | 2CF2010W74A11 | (STG #20 BLDG) Installation & Test - Elec | 2008-10-13 00:00:00 | 2009-01-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3217 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Building |  | 2CF2010W38A09 | (STG #20 BLDG) Installation & Test - Fire Fighting Sys. | (STG #20 BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Building 2CF2010W38A09 (STG #20 BLDG) Installation & Test - Fire Fighting Sys. | Activity | 2CF2010W38A09 | (STG #20 BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3219 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Unit Step-up Transformer |  | 2PF6500W70A07P | (STG #20 & UST Shelter) P.O & Procurement - Main TR | (STG #20 & UST Shelter) P.O & Procurement - Main TR | 2007-06-29 | 2008-07-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Unit Step-up Transformer 2PF6500W70A07P (STG #20 & UST Shelter) P.O & Procurement - Main TR | Activity | 2PF6500W70A07P | (STG #20 & UST Shelter) P.O & Procurement - Main TR | 2007-06-29 00:00:00 | 2008-07-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3220 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Unit Step-up Transformer |  | 2EF6500W00A01 | (STG #20 & UST Shelter) GA & Load Data to Civil Design | (STG #20 & UST Shelter) GA & Load Data to Civil Design | 2007-11-28 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Unit Step-up Transformer 2EF6500W00A01 (STG #20 & UST Shelter) GA & Load Data to Civil Design | Activity | 2EF6500W00A01 | (STG #20 & UST Shelter) GA & Load Data to Civil Design | 2007-11-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3221 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Unit Step-up Transformer |  | 2EF6500W16A02 | (STG #20 & UST Shelter) FDN & Firewall Design | (STG #20 & UST Shelter) FDN & Firewall Design | 2007-11-28 | 2008-03-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Unit Step-up Transformer 2EF6500W16A02 (STG #20 & UST Shelter) FDN & Firewall Design | Activity | 2EF6500W16A02 | (STG #20 & UST Shelter) FDN & Firewall Design | 2007-11-28 00:00:00 | 2008-03-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3222 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Unit Step-up Transformer |  | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | (STG #20 & STG #10 & UST Shelter) Structure Design | 2007-11-28 | 2008-03-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Unit Step-up Transformer 2EF6500W32A04 (STG #20 & STG #10 & UST Shelter) Structure Design | Activity | 2EF6500W32A04 | (STG #20 & STG #10 & UST Shelter) Structure Design | 2007-11-28 00:00:00 | 2008-03-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3223 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Unit Step-up Transformer |  | 2CF6500W16A03 | (STG #20 & UST Shelter) FDN Work | (STG #20 & UST Shelter) FDN Work | 2008-03-11 | 2008-06-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Unit Step-up Transformer 2CF6500W16A03 (STG #20 & UST Shelter) FDN Work | Activity | 2CF6500W16A03 | (STG #20 & UST Shelter) FDN Work | 2008-03-11 00:00:00 | 2008-06-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3224 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Unit Step-up Transformer |  | 2CF6500W16A05 | (STG #20 & UST Shelter) Firewall Work | (STG #20 & UST Shelter) Firewall Work | 2008-06-10 | 2008-08-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Unit Step-up Transformer 2CF6500W16A05 (STG #20 & UST Shelter) Firewall Work | Activity | 2CF6500W16A05 | (STG #20 & UST Shelter) Firewall Work | 2008-06-10 00:00:00 | 2008-08-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3225 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Unit Step-up Transformer |  | 2PF6500W70A08T | (STG #20 & UST Shelter) Transportation - Main TR | (STG #20 & UST Shelter) Transportation - Main TR | 2008-07-15 | 2008-08-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Unit Step-up Transformer 2PF6500W70A08T (STG #20 & UST Shelter) Transportation - Main TR | Activity | 2PF6500W70A08T | (STG #20 & UST Shelter) Transportation - Main TR | 2008-07-15 00:00:00 | 2008-08-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3226 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Unit Step-up Transformer |  | 2CF6500W70A09 | (STG #20 & UST Shelter) Installation - Main TR | (STG #20 & UST Shelter) Installation - Main TR | 2008-08-29 | 2008-10-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Unit Step-up Transformer 2CF6500W70A09 (STG #20 & UST Shelter) Installation - Main TR | Activity | 2CF6500W70A09 | (STG #20 & UST Shelter) Installation - Main TR | 2008-08-29 00:00:00 | 2008-10-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3228 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Steam Turbine |  | 2PF2020W42A10P | (ST #20) P.O & Procurement | (ST #20) P.O & Procurement | 2007-03-01 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Steam Turbine 2PF2020W42A10P (ST #20) P.O & Procurement | Activity | 2PF2020W42A10P | (ST #20) P.O & Procurement | 2007-03-01 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3229 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Steam Turbine |  | 2EF2020W00A01 | (ST #20) ST Process Data | (ST #20) ST Process Data | 2007-03-01 | 2007-03-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Steam Turbine 2EF2020W00A01 (ST #20) ST Process Data | Activity | 2EF2020W00A01 | (ST #20) ST Process Data | 2007-03-01 00:00:00 | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3230 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Steam Turbine |  | 2EF2020W00A03 | (ST #20) Instrument, Service Air Data | (ST #20) Instrument, Service Air Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Steam Turbine 2EF2020W00A03 (ST #20) Instrument, Service Air Data | Activity | 2EF2020W00A03 | (ST #20) Instrument, Service Air Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3231 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Steam Turbine |  | 2EF2020W00A04 | (ST #20) Utility Consumption Data | (ST #20) Utility Consumption Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Steam Turbine 2EF2020W00A04 (ST #20) Utility Consumption Data | Activity | 2EF2020W00A04 | (ST #20) Utility Consumption Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3232 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Steam Turbine |  | 2EF2020W00A05 | (ST #20) Emergency Load Data | (ST #20) Emergency Load Data | 2007-03-01 | 2007-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Steam Turbine 2EF2020W00A05 (ST #20) Emergency Load Data | Activity | 2EF2020W00A05 | (ST #20) Emergency Load Data | 2007-03-01 00:00:00 | 2007-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3233 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Steam Turbine |  | 2EF2020W00A02 | (ST #20) ST Aux' Steam Consumption Data | (ST #20) ST Aux' Steam Consumption Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Steam Turbine 2EF2020W00A02 (ST #20) ST Aux' Steam Consumption Data | Activity | 2EF2020W00A02 | (ST #20) ST Aux' Steam Consumption Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3234 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Steam Turbine |  | 2EF2020W16A06 | (ST #20) FDN Design | (ST #20) FDN Design | 2007-07-03 | 2007-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Steam Turbine 2EF2020W16A06 (ST #20) FDN Design | Activity | 2EF2020W16A06 | (ST #20) FDN Design | 2007-07-03 00:00:00 | 2007-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3235 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Steam Turbine |  | 2CF2020W16A07 | (ST #20) FDN Work | (ST #20) FDN Work | 2007-11-15 | 2008-03-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Steam Turbine 2CF2020W16A07 (ST #20) FDN Work | Activity | 2CF2020W16A07 | (ST #20) FDN Work | 2007-11-15 00:00:00 | 2008-03-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3236 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Steam Turbine |  | 2CF2020W16A08 | (ST #20) Pedestal & Top Slab Work | (ST #20) Pedestal & Top Slab Work | 2008-03-17 | 2008-09-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Steam Turbine 2CF2020W16A08 (ST #20) Pedestal & Top Slab Work | Activity | 2CF2020W16A08 | (ST #20) Pedestal & Top Slab Work | 2008-03-17 00:00:00 | 2008-09-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3237 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Steam Turbine |  | 2PF2020W42A11T | (ST #20) Transportation | (ST #20) Transportation | 2008-10-02 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Steam Turbine 2PF2020W42A11T (ST #20) Transportation | Activity | 2PF2020W42A11T | (ST #20) Transportation | 2008-10-02 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3238 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Steam Turbine |  | 2CF2020W42A12 | (ST #20) Installation | (ST #20) Installation | 2008-11-17 | 2009-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Steam Turbine 2CF2020W42A12 (ST #20) Installation | Activity | 2CF2020W42A12 | (ST #20) Installation | 2008-11-17 00:00:00 | 2009-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3240 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > ST Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | ST Generator |  | 2PF2040W42A02P | (STG #20) P.O & Procurement | (STG #20) P.O & Procurement | 2007-03-01 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 ST Generator 2PF2040W42A02P (STG #20) P.O & Procurement | Activity | 2PF2040W42A02P | (STG #20) P.O & Procurement | 2007-03-01 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3241 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > ST Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | ST Generator |  | 2PF2040W42A03T | (STG #20) Transportation | (STG #20) Transportation | 2008-10-02 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 ST Generator 2PF2040W42A03T (STG #20) Transportation | Activity | 2PF2040W42A03T | (STG #20) Transportation | 2008-10-02 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3242 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > ST Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | ST Generator |  | 2CF2040W42A04 | (STG #20) Installation | (STG #20) Installation | 2008-11-17 | 2009-03-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 ST Generator 2CF2040W42A04 (STG #20) Installation | Activity | 2CF2040W42A04 | (STG #20) Installation | 2008-11-17 00:00:00 | 2009-03-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3244 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Auxiliary Equipment |  | 2PF2070W42A04P | (STG #20 Aux. Equip) P.O & Procurement | (STG #20 Aux. Equip) P.O & Procurement | 2007-04-30 | 2008-09-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Auxiliary Equipment 2PF2070W42A04P (STG #20 Aux. Equip) P.O & Procurement | Activity | 2PF2070W42A04P | (STG #20 Aux. Equip) P.O & Procurement | 2007-04-30 00:00:00 | 2008-09-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3245 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Auxiliary Equipment |  | 2EF2070W16A01 | (STG #20 Aux. Equip) FDN Design | (STG #20 Aux. Equip) FDN Design | 2007-12-24 | 2008-05-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Auxiliary Equipment 2EF2070W16A01 (STG #20 Aux. Equip) FDN Design | Activity | 2EF2070W16A01 | (STG #20 Aux. Equip) FDN Design | 2007-12-24 00:00:00 | 2008-05-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3246 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Auxiliary Equipment |  | 2CF2070W16A02 | (STG #20 Aux. Equip) FDN Work | (STG #20 Aux. Equip) FDN Work | 2008-05-22 | 2008-08-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Auxiliary Equipment 2CF2070W16A02 (STG #20 Aux. Equip) FDN Work | Activity | 2CF2070W16A02 | (STG #20 Aux. Equip) FDN Work | 2008-05-22 00:00:00 | 2008-08-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3247 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Auxiliary Equipment |  | 2PF2070W42A05T | (STG #20 Aux. Equip) Transportation | (STG #20 Aux. Equip) Transportation | 2008-09-02 | 2008-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Auxiliary Equipment 2PF2070W42A05T (STG #20 Aux. Equip) Transportation | Activity | 2PF2070W42A05T | (STG #20 Aux. Equip) Transportation | 2008-09-02 00:00:00 | 2008-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3248 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | STG Auxiliary Equipment |  | 2CF2070W42A06 | (STG #20 Aux. Equip) Installation | (STG #20 Aux. Equip) Installation | 2008-10-17 | 2009-02-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 STG Auxiliary Equipment 2CF2070W42A06 (STG #20 Aux. Equip) Installation | Activity | 2CF2070W42A06 | (STG #20 Aux. Equip) Installation | 2008-10-17 00:00:00 | 2009-02-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3250 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Piping & Etc. | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Piping & Etc. |  | 2CF2035W58A01 | (ST #20) Piping Work | (ST #20) Piping Work | 2008-08-11 | 2009-01-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Piping & Etc. 2CF2035W58A01 (ST #20) Piping Work | Activity | 2CF2035W58A01 | (ST #20) Piping Work | 2008-08-11 00:00:00 | 2009-01-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3251 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Piping & Etc. | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Piping & Etc. |  | 2CF2060W74A03 | (ST #20) Installation & Test - Elec. | (ST #20) Installation & Test - Elec. | 2008-12-17 | 2009-03-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Piping & Etc. 2CF2060W74A03 (ST #20) Installation & Test - Elec. | Activity | 2CF2060W74A03 | (ST #20) Installation & Test - Elec. | 2008-12-17 00:00:00 | 2009-03-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3252 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Piping & Etc. | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Piping & Etc. |  | 2CF2065W90A04 | (ST #20) Installation & Test - I&C | (ST #20) Installation & Test - I&C | 2008-12-17 | 2009-03-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Piping & Etc. 2CF2065W90A04 (ST #20) Installation & Test - I&C | Activity | 2CF2065W90A04 | (ST #20) Installation & Test - I&C | 2008-12-17 00:00:00 | 2009-03-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3253 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Piping & Etc. | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Piping & Etc. |  | 2CF2035W62A02 | (ST #20) Hydro Test | (ST #20) Hydro Test | 2009-01-12 | 2009-02-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Piping & Etc. 2CF2035W62A02 (ST #20) Hydro Test | Activity | 2CF2035W62A02 | (ST #20) Hydro Test | 2009-01-12 00:00:00 | 2009-02-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3255 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Lube Oil System |  | 2PF2030W42A04P | (Lube Oil Sys.) P.O & Procurement | (Lube Oil Sys.) P.O & Procurement | 2007-07-31 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Lube Oil System 2PF2030W42A04P (Lube Oil Sys.) P.O & Procurement | Activity | 2PF2030W42A04P | (Lube Oil Sys.) P.O & Procurement | 2007-07-31 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3256 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Lube Oil System |  | 2EF2030W16A01 | (Lube Oil Sys.) FDN Design | (Lube Oil Sys.) FDN Design | 2007-10-23 | 2008-01-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Lube Oil System 2EF2030W16A01 (Lube Oil Sys.) FDN Design | Activity | 2EF2030W16A01 | (Lube Oil Sys.) FDN Design | 2007-10-23 00:00:00 | 2008-01-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3257 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Lube Oil System |  | 2CF2030W16A02 | (Lube Oil Sys.) FDN Work | (Lube Oil Sys.) FDN Work | 2008-01-23 | 2008-05-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Lube Oil System 2CF2030W16A02 (Lube Oil Sys.) FDN Work | Activity | 2CF2030W16A02 | (Lube Oil Sys.) FDN Work | 2008-01-23 00:00:00 | 2008-05-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3258 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Lube Oil System |  | 2PF2030W42A05T | (Lube Oil Sys.) Transportation | (Lube Oil Sys.) Transportation | 2008-08-30 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Lube Oil System 2PF2030W42A05T (Lube Oil Sys.) Transportation | Activity | 2PF2030W42A05T | (Lube Oil Sys.) Transportation | 2008-08-30 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3259 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Lube Oil System |  | 2CF2030W42A06 | (Lube Oil Sys.) Equipment Installation | (Lube Oil Sys.) Equipment Installation | 2008-10-15 | 2008-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Lube Oil System 2CF2030W42A06 (Lube Oil Sys.) Equipment Installation | Activity | 2CF2030W42A06 | (Lube Oil Sys.) Equipment Installation | 2008-10-15 00:00:00 | 2008-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3260 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Lube Oil System |  | 2CF2030W58A07 | (Lube Oil Sys.) Pipe Installation | (Lube Oil Sys.) Pipe Installation | 2008-11-30 | 2009-02-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Lube Oil System 2CF2030W58A07 (Lube Oil Sys.) Pipe Installation | Activity | 2CF2030W58A07 | (Lube Oil Sys.) Pipe Installation | 2008-11-30 00:00:00 | 2009-02-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3261 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Lube Oil System |  | 2CF2030W62A08 | (Lube Oil Sys.) Lube oil flushing | (Lube Oil Sys.) Lube oil flushing | 2009-02-16 | 2009-03-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Lube Oil System 2CF2030W62A08 (Lube Oil Sys.) Lube oil flushing | Activity | 2CF2030W62A08 | (Lube Oil Sys.) Lube oil flushing | 2009-02-16 00:00:00 | 2009-03-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3262 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Lube Oil System |  | 2CF2030W58A09 | (Lube Oil Sys.) Remove Temp. Pipe | (Lube Oil Sys.) Remove Temp. Pipe | 2009-03-17 | 2009-03-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Lube Oil System 2CF2030W58A09 (Lube Oil Sys.) Remove Temp. Pipe | Activity | 2CF2030W58A09 | (Lube Oil Sys.) Remove Temp. Pipe | 2009-03-17 00:00:00 | 2009-03-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3264 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Test & Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Test & Commissioning |  | 2SF2000W62A02 | (ST #20) Pre-Commissioning | (ST #20) Pre-Commissioning | 2009-03-29 | 2009-04-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Test & Commissioning 2SF2000W62A02 (ST #20) Pre-Commissioning | Activity | 2SF2000W62A02 | (ST #20) Pre-Commissioning | 2009-03-29 00:00:00 | 2009-04-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3265 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Test & Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Test & Commissioning |  | 2SF2000W62A01 | (ST #20) Aux. Equipment Function Test | (ST #20) Aux. Equipment Function Test | 2009-04-08 | 2009-04-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Test & Commissioning 2SF2000W62A01 (ST #20) Aux. Equipment Function Test | Activity | 2SF2000W62A01 | (ST #20) Aux. Equipment Function Test | 2009-04-08 00:00:00 | 2009-04-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3266 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Steam Turbine & Generator #20 > Test & Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Steam Turbine & Generator #20 | Test & Commissioning |  | 2SF2000W62A03 | (ST #20) Turnning Gear Operation | (ST #20) Turnning Gear Operation | 2009-04-28 | 2009-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Steam Turbine & Generator #20 Test & Commissioning 2SF2000W62A03 (ST #20) Turnning Gear Operation | Activity | 2SF2000W62A03 | (ST #20) Turnning Gear Operation | 2009-04-28 00:00:00 | 2009-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3268 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9035W62A01 | (Comm'g) Steam Blowing | (Comm'g) Steam Blowing | 2009-04-30 | 2009-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9035W62A01 (Comm'g) Steam Blowing | Activity | 2SF9035W62A01 | (Comm'g) Steam Blowing | 2009-04-30 00:00:00 | 2009-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3269 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2CF9035W62A02 | (Comm'g) Temporary Piping Restoration | (Comm'g) Temporary Piping Restoration | 2009-05-20 | 2009-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2CF9035W62A02 (Comm'g) Temporary Piping Restoration | Activity | 2CF9035W62A02 | (Comm'g) Temporary Piping Restoration | 2009-05-20 00:00:00 | 2009-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3270 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9035W62A03 | (Comm'g) Bypass Operation | (Comm'g) Bypass Operation | 2009-05-30 | 2009-06-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9035W62A03 (Comm'g) Bypass Operation | Activity | 2SF9035W62A03 | (Comm'g) Bypass Operation | 2009-05-30 00:00:00 | 2009-06-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3271 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9035W62A04 | (Comm'g) Safety & Interlock Test | (Comm'g) Safety & Interlock Test | 2009-06-01 | 2009-06-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9035W62A04 (Comm'g) Safety & Interlock Test | Activity | 2SF9035W62A04 | (Comm'g) Safety & Interlock Test | 2009-06-01 00:00:00 | 2009-06-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3272 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9035W62A05 | (Comm'g) Steam Admission | (Comm'g) Steam Admission | 2009-06-06 | 2009-06-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9035W62A05 (Comm'g) Steam Admission | Activity | 2SF9035W62A05 | (Comm'g) Steam Admission | 2009-06-06 00:00:00 | 2009-06-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3273 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9040W62A06 | (Comm'g) TBN & GEN. Test | (Comm'g) TBN & GEN. Test | 2009-06-08 | 2009-06-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9040W62A06 (Comm'g) TBN & GEN. Test | Activity | 2SF9040W62A06 | (Comm'g) TBN & GEN. Test | 2009-06-08 00:00:00 | 2009-06-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3274 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9040W62A07 | (Comm'g) Synchronization Test | (Comm'g) Synchronization Test | 2009-06-21 | 2009-06-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9040W62A07 (Comm'g) Synchronization Test | Activity | 2SF9040W62A07 | (Comm'g) Synchronization Test | 2009-06-21 00:00:00 | 2009-06-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3275 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9040W62A08 | (Comm'g) Optimaization Test | (Comm'g) Optimaization Test | 2009-06-22 | 2009-07-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9040W62A08 (Comm'g) Optimaization Test | Activity | 2SF9040W62A08 | (Comm'g) Optimaization Test | 2009-06-22 00:00:00 | 2009-07-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3276 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9040W62A09 | (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | 2009-07-10 | 2009-07-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9040W62A09 (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | Activity | 2SF9040W62A09 | (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | 2009-07-10 00:00:00 | 2009-07-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3277 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9040W62A10 | (Comm'g) Outage Period | (Comm'g) Outage Period | 2009-07-10 | 2009-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9040W62A10 (Comm'g) Outage Period | Activity | 2SF9040W62A10 | (Comm'g) Outage Period | 2009-07-10 00:00:00 | 2009-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3278 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9040W62A11 | (Comm'g) APS & Stability Guarantee Test | (Comm'g) APS & Stability Guarantee Test | 2009-07-17 | 2009-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9040W62A11 (Comm'g) APS & Stability Guarantee Test | Activity | 2SF9040W62A11 | (Comm'g) APS & Stability Guarantee Test | 2009-07-17 00:00:00 | 2009-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3279 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9040W62A12 | (Comm'g) Trial Run Test | (Comm'g) Trial Run Test | 2009-08-20 | 2009-08-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9040W62A12 (Comm'g) Trial Run Test | Activity | 2SF9040W62A12 | (Comm'g) Trial Run Test | 2009-08-20 00:00:00 | 2009-08-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3280 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9041W62A14 | (Comm'g) Reliability Test | (Comm'g) Reliability Test | 2009-08-22 | 2009-09-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9041W62A14 (Comm'g) Reliability Test | Activity | 2SF9041W62A14 | (Comm'g) Reliability Test | 2009-08-22 00:00:00 | 2009-09-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3281 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9040W62A13 | (Comm'g) Initial Operation Test | (Comm'g) Initial Operation Test | 2009-08-22 | 2009-08-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9040W62A13 (Comm'g) Initial Operation Test | Activity | 2SF9040W62A13 | (Comm'g) Initial Operation Test | 2009-08-22 00:00:00 | 2009-08-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3282 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #2 > Block #2 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #2 | Block #2 Commisssioning |  |  | 2SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | 2009-09-21 | 2009-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #2 Block #2 Commisssioning 2SF9042W62A15 (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | Activity | 2SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | 2009-09-21 00:00:00 | 2009-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3286 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3CF3520W16A01 | (FGSS #31) FDN Work(Misc. Equipment) | (FGSS #31) FDN Work(Misc. Equipment) | 2007-11-29 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3CF3520W16A01 (FGSS #31) FDN Work(Misc. Equipment) | Activity | 3CF3520W16A01 | (FGSS #31) FDN Work(Misc. Equipment) | 2007-11-29 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3287 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3CF3520W16A08 | (FGSS #32) FDN Work(Misc. Equipment) | (FGSS #32) FDN Work(Misc. Equipment) | 2007-11-29 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3CF3520W16A08 (FGSS #32) FDN Work(Misc. Equipment) | Activity | 3CF3520W16A08 | (FGSS #32) FDN Work(Misc. Equipment) | 2007-11-29 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3288 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3CF3520W58A10 | (FGSS #32) Piping Work(incl. Air leak Test & Blowing) | (FGSS #32) Piping Work(incl. Air leak Test & Blowing) | 2008-07-19 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3CF3520W58A10 (FGSS #32) Piping Work(incl. Air leak Test & Blowing) | Activity | 3CF3520W58A10 | (FGSS #32) Piping Work(incl. Air leak Test & Blowing) | 2008-07-19 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3289 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3CF3520W86A02 | (FGSS #31) ESD Valve Skid installation | (FGSS #31) ESD Valve Skid installation | 2008-07-19 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3CF3520W86A02 (FGSS #31) ESD Valve Skid installation | Activity | 3CF3520W86A02 | (FGSS #31) ESD Valve Skid installation | 2008-07-19 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3290 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3CF3520W86A09 | (FGSS #32) ESD Valve Skid installation | (FGSS #32) ESD Valve Skid installation | 2008-07-19 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3CF3520W86A09 (FGSS #32) ESD Valve Skid installation | Activity | 3CF3520W86A09 | (FGSS #32) ESD Valve Skid installation | 2008-07-19 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3291 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3CF3520W58A03 | (FGSS #31) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | (FGSS #31) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | 2008-07-19 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3CF3520W58A03 (FGSS #31) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | Activity | 3CF3520W58A03 | (FGSS #31) Piping Work(incl. Air leak Test & Blowing)_Gas Farm Area | 2008-07-19 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3292 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3CF3520W74A11 | (FGSS #32) Installation & Test - Elec. | (FGSS #32) Installation & Test - Elec. | 2008-08-04 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3CF3520W74A11 (FGSS #32) Installation & Test - Elec. | Activity | 3CF3520W74A11 | (FGSS #32) Installation & Test - Elec. | 2008-08-04 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3293 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3CF3520W90A12 | (FGSS #32) Installation & Test - I&C | (FGSS #32) Installation & Test - I&C | 2008-08-04 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3CF3520W90A12 (FGSS #32) Installation & Test - I&C | Activity | 3CF3520W90A12 | (FGSS #32) Installation & Test - I&C | 2008-08-04 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3294 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3CF3520W74A04 | (FGSS #31) Installation & Test - Elec. | (FGSS #31) Installation & Test - Elec. | 2008-08-04 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3CF3520W74A04 (FGSS #31) Installation & Test - Elec. | Activity | 3CF3520W74A04 | (FGSS #31) Installation & Test - Elec. | 2008-08-04 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3295 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3CF3520W90A05 | (FGSS #31) Installation & Test - I&C | (FGSS #31) Installation & Test - I&C | 2008-08-04 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3CF3520W90A05 (FGSS #31) Installation & Test - I&C | Activity | 3CF3520W90A05 | (FGSS #31) Installation & Test - I&C | 2008-08-04 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3296 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3SF3520W62A13 | (FGSS #32) Fuel Gas Receiving | (FGSS #32) Fuel Gas Receiving | 2008-10-18 | 2008-10-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3SF3520W62A13 (FGSS #32) Fuel Gas Receiving | Activity | 3SF3520W62A13 | (FGSS #32) Fuel Gas Receiving | 2008-10-18 00:00:00 | 2008-10-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3297 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3SF3520W62A06 | (FGSS #31)Fuel Gas Receiving | (FGSS #31)Fuel Gas Receiving | 2008-10-18 | 2008-10-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3SF3520W62A06 (FGSS #31)Fuel Gas Receiving | Activity | 3SF3520W62A06 | (FGSS #31)Fuel Gas Receiving | 2008-10-18 00:00:00 | 2008-10-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3298 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3SF3520W62A14 | (FGSS #32) Metering System Calibration with supplier | (FGSS #32) Metering System Calibration with supplier | 2008-10-21 | 2008-10-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3SF3520W62A14 (FGSS #32) Metering System Calibration with supplier | Activity | 3SF3520W62A14 | (FGSS #32) Metering System Calibration with supplier | 2008-10-21 00:00:00 | 2008-10-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3299 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System |  | 3SF3520W62A07.2 | (FGSS #31) Metering System Calibration with supplier | (FGSS #31) Metering System Calibration with supplier | 2008-10-21 | 2008-10-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System 3SF3520W62A07.2 (FGSS #31) Metering System Calibration with supplier | Activity | 3SF3520W62A07.2 | (FGSS #31) Metering System Calibration with supplier | 2008-10-21 00:00:00 | 2008-10-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3301 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | 2007-06-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3EF3520W00A28 (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | Activity | 3EF3520W00A28 | (GT/HRSG GPRS Shelter) GA & Load Data to Civil Design | 2007-06-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3302 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3EF3520W16A29 | (GT/HRSG GPRS Shelter) FDN Design | (GT/HRSG GPRS Shelter) FDN Design | 2007-06-01 | 2007-10-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3EF3520W16A29 (GT/HRSG GPRS Shelter) FDN Design | Activity | 3EF3520W16A29 | (GT/HRSG GPRS Shelter) FDN Design | 2007-06-01 00:00:00 | 2007-10-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3303 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3EF3520W32A31 | (GT/HRSG GPRS Shelter) Structure Design | (GT/HRSG GPRS Shelter) Structure Design | 2007-06-01 | 2007-10-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3EF3520W32A31 (GT/HRSG GPRS Shelter) Structure Design | Activity | 3EF3520W32A31 | (GT/HRSG GPRS Shelter) Structure Design | 2007-06-01 00:00:00 | 2007-10-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3304 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3PF3520W42A04P | (GPRS) P.O & Procurement for GT | (GPRS) P.O & Procurement for GT | 2007-06-01 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3PF3520W42A04P (GPRS) P.O & Procurement for GT | Activity | 3PF3520W42A04P | (GPRS) P.O & Procurement for GT | 2007-06-01 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3305 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3PF3520W42A14P | (GPRS) P.O & Procurement for HRSG | (GPRS) P.O & Procurement for HRSG | 2007-07-03 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3PF3520W42A14P (GPRS) P.O & Procurement for HRSG | Activity | 3PF3520W42A14P | (GPRS) P.O & Procurement for HRSG | 2007-07-03 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3306 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3EF3520W16A12 | (GPRS) FDN Design for HRSG | (GPRS) FDN Design for HRSG | 2007-07-03 | 2007-11-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3EF3520W16A12 (GPRS) FDN Design for HRSG | Activity | 3EF3520W16A12 | (GPRS) FDN Design for HRSG | 2007-07-03 00:00:00 | 2007-11-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3307 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3EF3520W16A01 | (GPRS) FDN Design for GT | (GPRS) FDN Design for GT | 2007-08-02 | 2007-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3EF3520W16A01 (GPRS) FDN Design for GT | Activity | 3EF3520W16A01 | (GPRS) FDN Design for GT | 2007-08-02 00:00:00 | 2007-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3308 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3CF3520W16A02 | (GPRS) FDN Work for GT | (GPRS) FDN Work for GT | 2007-10-17 | 2007-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3CF3520W16A02 (GPRS) FDN Work for GT | Activity | 3CF3520W16A02 | (GPRS) FDN Work for GT | 2007-10-17 00:00:00 | 2007-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3309 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3CF3520W16A30 | (GT/HRSG GPRS Shelter) FDN Work | (GT/HRSG GPRS Shelter) FDN Work | 2007-11-10 | 2008-01-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3CF3520W16A30 (GT/HRSG GPRS Shelter) FDN Work | Activity | 3CF3520W16A30 | (GT/HRSG GPRS Shelter) FDN Work | 2007-11-10 00:00:00 | 2008-01-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3310 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3CF3520W16A13 | (GPRS) FDN Work for HRSG | (GPRS) FDN Work for HRSG | 2007-11-10 | 2008-01-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3CF3520W16A13 (GPRS) FDN Work for HRSG | Activity | 3CF3520W16A13 | (GPRS) FDN Work for HRSG | 2007-11-10 00:00:00 | 2008-01-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3311 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3CF3520W32A32 | (GT/HRSG GPRS Shelter) Structure Work | (GT/HRSG GPRS Shelter) Structure Work | 2008-01-11 | 2008-04-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3CF3520W32A32 (GT/HRSG GPRS Shelter) Structure Work | Activity | 3CF3520W32A32 | (GT/HRSG GPRS Shelter) Structure Work | 2008-01-11 00:00:00 | 2008-04-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3312 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3PF3520W42A05T | (GPRS) Transportation for GT | (GPRS) Transportation for GT | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3PF3520W42A05T (GPRS) Transportation for GT | Activity | 3PF3520W42A05T | (GPRS) Transportation for GT | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3313 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3PF3520W42A15T | (GPRS) Transportation for HRSG | (GPRS) Transportation for HRSG | 2008-07-02 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3PF3520W42A15T (GPRS) Transportation for HRSG | Activity | 3PF3520W42A15T | (GPRS) Transportation for HRSG | 2008-07-02 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3314 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3CF3520W42A06 | (GPRS #31) Installation for GT | (GPRS #31) Installation for GT | 2008-07-16 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3CF3520W42A06 (GPRS #31) Installation for GT | Activity | 3CF3520W42A06 | (GPRS #31) Installation for GT | 2008-07-16 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3315 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3CF3520W42A09 | (GPRS #32) Installation for GT | (GPRS #32) Installation for GT | 2008-07-16 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3CF3520W42A09 (GPRS #32) Installation for GT | Activity | 3CF3520W42A09 | (GPRS #32) Installation for GT | 2008-07-16 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3316 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3CF3520W42A22 | (GPRS #31 for Fuel Change over) Installation | (GPRS #31 for Fuel Change over) Installation | 2008-07-16 | 2008-08-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3CF3520W42A22 (GPRS #31 for Fuel Change over) Installation | Activity | 3CF3520W42A22 | (GPRS #31 for Fuel Change over) Installation | 2008-07-16 00:00:00 | 2008-08-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3317 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3CF3520W42A25 | (GPRS #32 for Fuel Change over) Installation | (GPRS #32 for Fuel Change over) Installation | 2008-07-16 | 2008-08-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3CF3520W42A25 (GPRS #32 for Fuel Change over) Installation | Activity | 3CF3520W42A25 | (GPRS #32 for Fuel Change over) Installation | 2008-07-16 00:00:00 | 2008-08-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3318 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3CF3520W24A33 | (GT/HRSG GPRS Shelter) Shelter Finish | (GT/HRSG GPRS Shelter) Shelter Finish | 2008-08-09 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3CF3520W24A33 (GT/HRSG GPRS Shelter) Shelter Finish | Activity | 3CF3520W24A33 | (GT/HRSG GPRS Shelter) Shelter Finish | 2008-08-09 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3319 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3CF3520W42A16 | (GPRS #31) Installation for HRSG | (GPRS #31) Installation for HRSG | 2008-08-16 | 2008-09-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3CF3520W42A16 (GPRS #31) Installation for HRSG | Activity | 3CF3520W42A16 | (GPRS #31) Installation for HRSG | 2008-08-16 00:00:00 | 2008-09-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3320 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3CF3520W42A19 | (GPRS #32) Installation for HRSG | (GPRS #32) Installation for HRSG | 2008-08-16 | 2008-09-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3CF3520W42A19 (GPRS #32) Installation for HRSG | Activity | 3CF3520W42A19 | (GPRS #32) Installation for HRSG | 2008-08-16 00:00:00 | 2008-09-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3321 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3SF3520W62A23 | (GPRS #31 for Fuel Change over) Loop chek & Motor Solo Test | (GPRS #31 for Fuel Change over) Loop chek & Motor Solo Test | 2008-08-27 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3SF3520W62A23 (GPRS #31 for Fuel Change over) Loop chek & Motor Solo Test | Activity | 3SF3520W62A23 | (GPRS #31 for Fuel Change over) Loop chek & Motor Solo Test | 2008-08-27 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3322 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3SF3520W62A26 | (GPRS #32 for Fuel Change over) Loop chek & Motor Solo Test | (GPRS #32 for Fuel Change over) Loop chek & Motor Solo Test | 2008-08-27 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3SF3520W62A26 (GPRS #32 for Fuel Change over) Loop chek & Motor Solo Test | Activity | 3SF3520W62A26 | (GPRS #32 for Fuel Change over) Loop chek & Motor Solo Test | 2008-08-27 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3323 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3SF3520W62A24 | (GPRS #31 for Fuel Change over) Function Test | (GPRS #31 for Fuel Change over) Function Test | 2008-08-30 | 2008-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3SF3520W62A24 (GPRS #31 for Fuel Change over) Function Test | Activity | 3SF3520W62A24 | (GPRS #31 for Fuel Change over) Function Test | 2008-08-30 00:00:00 | 2008-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3324 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3SF3520W62A27 | (GPRS #32 for Fuel Change over) Function Test | (GPRS #32 for Fuel Change over) Function Test | 2008-08-30 | 2008-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3SF3520W62A27 (GPRS #32 for Fuel Change over) Function Test | Activity | 3SF3520W62A27 | (GPRS #32 for Fuel Change over) Function Test | 2008-08-30 00:00:00 | 2008-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3325 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3SF3520W62A17 | (GPRS #31) Loop chek & Motor Solo Test for HRSG | (GPRS #31) Loop chek & Motor Solo Test for HRSG | 2008-09-27 | 2008-09-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3SF3520W62A17 (GPRS #31) Loop chek & Motor Solo Test for HRSG | Activity | 3SF3520W62A17 | (GPRS #31) Loop chek & Motor Solo Test for HRSG | 2008-09-27 00:00:00 | 2008-09-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3326 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3SF3520W62A20 | (GPRS #32) Loop chek & Motor Solo Test for HRSG | (GPRS #32) Loop chek & Motor Solo Test for HRSG | 2008-09-27 | 2008-09-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3SF3520W62A20 (GPRS #32) Loop chek & Motor Solo Test for HRSG | Activity | 3SF3520W62A20 | (GPRS #32) Loop chek & Motor Solo Test for HRSG | 2008-09-27 00:00:00 | 2008-09-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3327 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3SF3520W62A18 | (GPRS #31) Function Test for HRSG | (GPRS #31) Function Test for HRSG | 2008-09-30 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3SF3520W62A18 (GPRS #31) Function Test for HRSG | Activity | 3SF3520W62A18 | (GPRS #31) Function Test for HRSG | 2008-09-30 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3328 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3SF3520W62A21 | (GPRS #32) Function Test for HRSG | (GPRS #32) Function Test for HRSG | 2008-09-30 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3SF3520W62A21 (GPRS #32) Function Test for HRSG | Activity | 3SF3520W62A21 | (GPRS #32) Function Test for HRSG | 2008-09-30 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3329 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3SF3520W62A07 | (GPRS #31) Loop check for GT | (GPRS #31) Loop check for GT | 2008-10-01 | 2008-10-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3SF3520W62A07 (GPRS #31) Loop check for GT | Activity | 3SF3520W62A07 | (GPRS #31) Loop check for GT | 2008-10-01 00:00:00 | 2008-10-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3330 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3SF3520W62A10 | (GPRS #32) Loop check for GT | (GPRS #32) Loop check for GT | 2008-10-01 | 2008-10-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3SF3520W62A10 (GPRS #32) Loop check for GT | Activity | 3SF3520W62A10 | (GPRS #32) Loop check for GT | 2008-10-01 00:00:00 | 2008-10-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3331 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3SF3520W62A08 | (GPRS #31) Function Test for GT | (GPRS #31) Function Test for GT | 2008-10-04 | 2008-10-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3SF3520W62A08 (GPRS #31) Function Test for GT | Activity | 3SF3520W62A08 | (GPRS #31) Function Test for GT | 2008-10-04 00:00:00 | 2008-10-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3332 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Pressure Reducing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Pressure Reducing System | 3SF3520W62A11 | (GPRS #32) Function Test for GT | (GPRS #32) Function Test for GT | 2008-10-04 | 2008-10-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Pressure Reducing System 3SF3520W62A11 (GPRS #32) Function Test for GT | Activity | 3SF3520W62A11 | (GPRS #32) Function Test for GT | 2008-10-04 00:00:00 | 2008-10-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3334 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3EF3520W00A10 | (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | 2007-06-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3EF3520W00A10 (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | Activity | 3EF3520W00A10 | (Filtering/Metering Station Shelter) GA & Load Data to Civil Design | 2007-06-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3335 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3EF3520W16A11 | (Filtering/Metering Station Shelter) FDN Design | (Filtering/Metering Station Shelter) FDN Design | 2007-06-01 | 2007-10-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3EF3520W16A11 (Filtering/Metering Station Shelter) FDN Design | Activity | 3EF3520W16A11 | (Filtering/Metering Station Shelter) FDN Design | 2007-06-01 00:00:00 | 2007-10-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3336 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3EF3520W32A13 | (Filtering/Metering Station Shelter) Structure Design | (Filtering/Metering Station Shelter) Structure Design | 2007-06-01 | 2007-10-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3EF3520W32A13 (Filtering/Metering Station Shelter) Structure Design | Activity | 3EF3520W32A13 | (Filtering/Metering Station Shelter) Structure Design | 2007-06-01 00:00:00 | 2007-10-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3337 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3PF3520W42A02.3P | (Filtering/Metering Station) P.O & Procurement | (Filtering/Metering Station) P.O & Procurement | 2007-07-03 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3PF3520W42A02.3P (Filtering/Metering Station) P.O & Procurement | Activity | 3PF3520W42A02.3P | (Filtering/Metering Station) P.O & Procurement | 2007-07-03 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3338 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3CF3520W16A12 | (Filtering/Metering Station Shelter) FDN Work | (Filtering/Metering Station Shelter) FDN Work | 2007-10-13 | 2007-12-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3CF3520W16A12 (Filtering/Metering Station Shelter) FDN Work | Activity | 3CF3520W16A12 | (Filtering/Metering Station Shelter) FDN Work | 2007-10-13 00:00:00 | 2007-12-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3339 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3CF3520W32A14 | (Filtering/Metering Station Shelter) Structure Work | (Filtering/Metering Station Shelter) Structure Work | 2007-12-11 | 2008-02-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3CF3520W32A14 (Filtering/Metering Station Shelter) Structure Work | Activity | 3CF3520W32A14 | (Filtering/Metering Station Shelter) Structure Work | 2007-12-11 00:00:00 | 2008-02-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3340 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3PF3520W42A03.3T | (Filtering/Metering Station) Transportation | (Filtering/Metering Station) Transportation | 2008-06-03 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3PF3520W42A03.3T (Filtering/Metering Station) Transportation | Activity | 3PF3520W42A03.3T | (Filtering/Metering Station) Transportation | 2008-06-03 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3341 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3CF3520W42A07.3 | (Filtering/Metering Station #32) Installation | (Filtering/Metering Station #32) Installation | 2008-07-18 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3CF3520W42A07.3 (Filtering/Metering Station #32) Installation | Activity | 3CF3520W42A07.3 | (Filtering/Metering Station #32) Installation | 2008-07-18 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3342 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3CF3520W42A04.3 | (Filtering/Metering Station #31) Installation | (Filtering/Metering Station #31) Installation | 2008-07-18 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3CF3520W42A04.3 (Filtering/Metering Station #31) Installation | Activity | 3CF3520W42A04.3 | (Filtering/Metering Station #31) Installation | 2008-07-18 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3343 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3SF3520W62A08.3 | (Filtering/Metering Station #32) Loop chek | (Filtering/Metering Station #32) Loop chek | 2008-08-02 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3SF3520W62A08.3 (Filtering/Metering Station #32) Loop chek | Activity | 3SF3520W62A08.3 | (Filtering/Metering Station #32) Loop chek | 2008-08-02 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3344 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3CF3520W24A15 | (Filtering/Metering Station Shelter) Shelter Finish | (Filtering/Metering Station Shelter) Shelter Finish | 2008-08-02 | 2008-08-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3CF3520W24A15 (Filtering/Metering Station Shelter) Shelter Finish | Activity | 3CF3520W24A15 | (Filtering/Metering Station Shelter) Shelter Finish | 2008-08-02 00:00:00 | 2008-08-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3345 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3SF3520W62A05.3 | (Filtering/Metering Station #31) Loop chek | (Filtering/Metering Station #31) Loop chek | 2008-08-02 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3SF3520W62A05.3 (Filtering/Metering Station #31) Loop chek | Activity | 3SF3520W62A05.3 | (Filtering/Metering Station #31) Loop chek | 2008-08-02 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3346 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3SF3520W62A09.3 | (Filtering/Metering Station #32) Function Test | (Filtering/Metering Station #32) Function Test | 2008-08-05 | 2008-08-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3SF3520W62A09.3 (Filtering/Metering Station #32) Function Test | Activity | 3SF3520W62A09.3 | (Filtering/Metering Station #32) Function Test | 2008-08-05 00:00:00 | 2008-08-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3347 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Fuel Gas Filter & Metering System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Fuel Gas Filter & Metering System | 3SF3520W62A06.3 | (Filtering/Metering Station #31) Function Test | (Filtering/Metering Station #31) Function Test | 2008-08-05 | 2008-08-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Fuel Gas Filter & Metering System 3SF3520W62A06.3 (Filtering/Metering Station #31) Function Test | Activity | 3SF3520W62A06.3 | (Filtering/Metering Station #31) Function Test | 2008-08-05 00:00:00 | 2008-08-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3349 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3EF3520W16A01.2 | (Gas HTR) FDN Design | (Gas HTR) FDN Design | 2007-07-03 | 2007-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3EF3520W16A01.2 (Gas HTR) FDN Design | Activity | 3EF3520W16A01.2 | (Gas HTR) FDN Design | 2007-07-03 00:00:00 | 2007-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3350 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3EF3520W32A03.2 | (Gas HTR) Structure Design | (Gas HTR) Structure Design | 2007-07-03 | 2007-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3EF3520W32A03.2 (Gas HTR) Structure Design | Activity | 3EF3520W32A03.2 | (Gas HTR) Structure Design | 2007-07-03 00:00:00 | 2007-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3351 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3PF3520W42A07.2P | (Gas HTR) P.O & Procurement | (Gas HTR) P.O & Procurement | 2007-07-03 | 2008-06-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3PF3520W42A07.2P (Gas HTR) P.O & Procurement | Activity | 3PF3520W42A07.2P | (Gas HTR) P.O & Procurement | 2007-07-03 00:00:00 | 2008-06-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3352 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3CF3520W16A02.2 | (Gas HTR) FDN Work | (Gas HTR) FDN Work | 2007-10-02 | 2007-11-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3CF3520W16A02.2 (Gas HTR) FDN Work | Activity | 3CF3520W16A02.2 | (Gas HTR) FDN Work | 2007-10-02 00:00:00 | 2007-11-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3353 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3CF3520W32A04.2 | (Gas HTR) Structure Work | (Gas HTR) Structure Work | 2007-11-29 | 2008-01-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3CF3520W32A04.2 (Gas HTR) Structure Work | Activity | 3CF3520W32A04.2 | (Gas HTR) Structure Work | 2007-11-29 00:00:00 | 2008-01-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3354 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3PF3520W42A08.2T | (Gas HTR) Transportation | (Gas HTR) Transportation | 2008-06-03 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3PF3520W42A08.2T (Gas HTR) Transportation | Activity | 3PF3520W42A08.2T | (Gas HTR) Transportation | 2008-06-03 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3355 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3CF3520W24A05.2 | (Gas HTR) Shelter Finish | (Gas HTR) Shelter Finish | 2008-07-18 | 2008-08-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3CF3520W24A05.2 (Gas HTR) Shelter Finish | Activity | 3CF3520W24A05.2 | (Gas HTR) Shelter Finish | 2008-07-18 00:00:00 | 2008-08-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3356 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3CF3520W42A09.2 | (Gas HTR #31) Installation | (Gas HTR #31) Installation | 2008-07-18 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3CF3520W42A09.2 (Gas HTR #31) Installation | Activity | 3CF3520W42A09.2 | (Gas HTR #31) Installation | 2008-07-18 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3357 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3CF3520W42A12.2 | (Gas HTR #32) Installation | (Gas HTR #32) Installation | 2008-07-18 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3CF3520W42A12.2 (Gas HTR #32) Installation | Activity | 3CF3520W42A12.2 | (Gas HTR #32) Installation | 2008-07-18 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3358 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3SF3520W62A10.2 | (Gas HTR #31) Loop chek | (Gas HTR #31) Loop chek | 2008-08-03 | 2008-08-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3SF3520W62A10.2 (Gas HTR #31) Loop chek | Activity | 3SF3520W62A10.2 | (Gas HTR #31) Loop chek | 2008-08-03 00:00:00 | 2008-08-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3359 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3SF3520W62A13.2 | (Gas HTR #32) Loop chek | (Gas HTR #32) Loop chek | 2008-08-03 | 2008-08-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3SF3520W62A13.2 (Gas HTR #32) Loop chek | Activity | 3SF3520W62A13.2 | (Gas HTR #32) Loop chek | 2008-08-03 00:00:00 | 2008-08-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3360 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3SF3520W62A11.2 | (Gas HTR #31) Function Test | (Gas HTR #31) Function Test | 2008-08-06 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3SF3520W62A11.2 (Gas HTR #31) Function Test | Activity | 3SF3520W62A11.2 | (Gas HTR #31) Function Test | 2008-08-06 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3361 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Heater | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Heater | 3SF3520W62A14.2 | (Gas HTR #32) Function Test | (Gas HTR #32) Function Test | 2008-08-06 | 2008-08-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Heater 3SF3520W62A14.2 (Gas HTR #32) Function Test | Activity | 3SF3520W62A14.2 | (Gas HTR #32) Function Test | 2008-08-06 00:00:00 | 2008-08-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3363 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | (Gas COMP PKG) P.O & Procurement | 2007-03-15 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3PF3520W42A05.1P (Gas COMP PKG) P.O & Procurement | Activity | 3PF3520W42A05.1P | (Gas COMP PKG) P.O & Procurement | 2007-03-15 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3364 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3EF3520W00A25.1 | (Gas COMP House) GA & Load Data to Civil Design | (Gas COMP House) GA & Load Data to Civil Design | 2007-03-30 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3EF3520W00A25.1 (Gas COMP House) GA & Load Data to Civil Design | Activity | 3EF3520W00A25.1 | (Gas COMP House) GA & Load Data to Civil Design | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3365 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3EF3520W16A26.1 | (Gas COMP House) FDN Design | (Gas COMP House) FDN Design | 2007-05-01 | 2007-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3EF3520W16A26.1 (Gas COMP House) FDN Design | Activity | 3EF3520W16A26.1 | (Gas COMP House) FDN Design | 2007-05-01 00:00:00 | 2007-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3366 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3EF3520W32A28.1 | (Gas COMP House) Structure Design | (Gas COMP House) Structure Design | 2007-05-01 | 2007-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3EF3520W32A28.1 (Gas COMP House) Structure Design | Activity | 3EF3520W32A28.1 | (Gas COMP House) Structure Design | 2007-05-01 00:00:00 | 2007-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3367 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3EF3520W16A01.1 | (Gas COMP PKG) FDN Design | (Gas COMP PKG) FDN Design | 2007-08-02 | 2007-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3EF3520W16A01.1 (Gas COMP PKG) FDN Design | Activity | 3EF3520W16A01.1 | (Gas COMP PKG) FDN Design | 2007-08-02 00:00:00 | 2007-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3368 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W16A27.1 | (Gas COMP House) FDN Work | (Gas COMP House) FDN Work | 2007-10-02 | 2007-11-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W16A27.1 (Gas COMP House) FDN Work | Activity | 3CF3520W16A27.1 | (Gas COMP House) FDN Work | 2007-10-02 00:00:00 | 2007-11-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3369 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W16A02.1 | (Gas COMP PKG) FDN Work | (Gas COMP PKG) FDN Work | 2007-11-02 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W16A02.1 (Gas COMP PKG) FDN Work | Activity | 3CF3520W16A02.1 | (Gas COMP PKG) FDN Work | 2007-11-02 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3370 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W32A29.1 | (Gas COMP House) Structure Work | (Gas COMP House) Structure Work | 2007-11-29 | 2008-02-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W32A29.1 (Gas COMP House) Structure Work | Activity | 3CF3520W32A29.1 | (Gas COMP House) Structure Work | 2007-11-29 00:00:00 | 2008-02-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3371 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3PF3520W42A06.1T | (Gas COMP PKG)Transportation | (Gas COMP PKG)Transportation | 2008-06-14 | 2008-07-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3PF3520W42A06.1T (Gas COMP PKG)Transportation | Activity | 3PF3520W42A06.1T | (Gas COMP PKG)Transportation | 2008-06-14 00:00:00 | 2008-07-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3372 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W42A20.1 | (Gas COMP PKG #32) Installation_Lube oil Sys.(incl. Flushing) | (Gas COMP PKG #32) Installation_Lube oil Sys.(incl. Flushing) | 2008-07-30 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W42A20.1 (Gas COMP PKG #32) Installation_Lube oil Sys.(incl. Flushing) | Activity | 3CF3520W42A20.1 | (Gas COMP PKG #32) Installation_Lube oil Sys.(incl. Flushing) | 2008-07-30 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3373 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W42A17.1 | (Gas COMP PKG #32) Installation_Air Compressor | (Gas COMP PKG #32) Installation_Air Compressor | 2008-07-30 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W42A17.1 (Gas COMP PKG #32) Installation_Air Compressor | Activity | 3CF3520W42A17.1 | (Gas COMP PKG #32) Installation_Air Compressor | 2008-07-30 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3374 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W42A18.1 | (Gas COMP PKG #32) Installation_Air Ventilation | (Gas COMP PKG #32) Installation_Air Ventilation | 2008-07-30 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W42A18.1 (Gas COMP PKG #32) Installation_Air Ventilation | Activity | 3CF3520W42A18.1 | (Gas COMP PKG #32) Installation_Air Ventilation | 2008-07-30 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3375 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W42A07.1 | (Gas COMP PKG #31) Installation_Gas Compressor | (Gas COMP PKG #31) Installation_Gas Compressor | 2008-07-30 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W42A07.1 (Gas COMP PKG #31) Installation_Gas Compressor | Activity | 3CF3520W42A07.1 | (Gas COMP PKG #31) Installation_Gas Compressor | 2008-07-30 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3376 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W42A16.1 | (Gas COMP PKG #32) Installation_Gas Compressor | (Gas COMP PKG #32) Installation_Gas Compressor | 2008-07-30 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W42A16.1 (Gas COMP PKG #32) Installation_Gas Compressor | Activity | 3CF3520W42A16.1 | (Gas COMP PKG #32) Installation_Gas Compressor | 2008-07-30 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3377 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W42A11.1 | (Gas COMP PKG #31) Installation_Lube oil Sys.(incl. Flushing) | (Gas COMP PKG #31) Installation_Lube oil Sys.(incl. Flushing) | 2008-07-30 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W42A11.1 (Gas COMP PKG #31) Installation_Lube oil Sys.(incl. Flushing) | Activity | 3CF3520W42A11.1 | (Gas COMP PKG #31) Installation_Lube oil Sys.(incl. Flushing) | 2008-07-30 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3378 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W42A08.1 | (Gas COMP PKG #31) Installation_Air Compressor | (Gas COMP PKG #31) Installation_Air Compressor | 2008-07-30 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W42A08.1 (Gas COMP PKG #31) Installation_Air Compressor | Activity | 3CF3520W42A08.1 | (Gas COMP PKG #31) Installation_Air Compressor | 2008-07-30 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3379 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W42A09.1 | (Gas COMP PKG #31) Installation_Air Ventilation | (Gas COMP PKG #31) Installation_Air Ventilation | 2008-07-30 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W42A09.1 (Gas COMP PKG #31) Installation_Air Ventilation | Activity | 3CF3520W42A09.1 | (Gas COMP PKG #31) Installation_Air Ventilation | 2008-07-30 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3380 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W42A21.1 | (Gas COMP PKG #32) Installation_N2 Generation Sys. | (Gas COMP PKG #32) Installation_N2 Generation Sys. | 2008-09-01 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W42A21.1 (Gas COMP PKG #32) Installation_N2 Generation Sys. | Activity | 3CF3520W42A21.1 | (Gas COMP PKG #32) Installation_N2 Generation Sys. | 2008-09-01 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3381 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W42A19.1 | (Gas COMP PKG #32) Installation_Seal Gas Sys. | (Gas COMP PKG #32) Installation_Seal Gas Sys. | 2008-09-01 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W42A19.1 (Gas COMP PKG #32) Installation_Seal Gas Sys. | Activity | 3CF3520W42A19.1 | (Gas COMP PKG #32) Installation_Seal Gas Sys. | 2008-09-01 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3382 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W24A30.1 | (Gas COMP House) Shelter finish | (Gas COMP House) Shelter finish | 2008-09-01 | 2008-10-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W24A30.1 (Gas COMP House) Shelter finish | Activity | 3CF3520W24A30.1 | (Gas COMP House) Shelter finish | 2008-09-01 00:00:00 | 2008-10-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3383 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W42A12.1 | (Gas COMP PKG #31) Installation_N2 Generation Sys. | (Gas COMP PKG #31) Installation_N2 Generation Sys. | 2008-09-01 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W42A12.1 (Gas COMP PKG #31) Installation_N2 Generation Sys. | Activity | 3CF3520W42A12.1 | (Gas COMP PKG #31) Installation_N2 Generation Sys. | 2008-09-01 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3384 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3CF3520W42A10.1 | (Gas COMP PKG #31) Installation_Seal Gas Sys. | (Gas COMP PKG #31) Installation_Seal Gas Sys. | 2008-09-01 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3CF3520W42A10.1 (Gas COMP PKG #31) Installation_Seal Gas Sys. | Activity | 3CF3520W42A10.1 | (Gas COMP PKG #31) Installation_Seal Gas Sys. | 2008-09-01 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3385 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3SF3520W62A13.1 | (Gas COMP PKG #31) Loop chek | (Gas COMP PKG #31) Loop chek | 2008-10-03 | 2008-10-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3SF3520W62A13.1 (Gas COMP PKG #31) Loop chek | Activity | 3SF3520W62A13.1 | (Gas COMP PKG #31) Loop chek | 2008-10-03 00:00:00 | 2008-10-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3386 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3SF3520W62A22.1 | (Gas COMP PKG #32) Loop chek | (Gas COMP PKG #32) Loop chek | 2008-10-03 | 2008-10-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3SF3520W62A22.1 (Gas COMP PKG #32) Loop chek | Activity | 3SF3520W62A22.1 | (Gas COMP PKG #32) Loop chek | 2008-10-03 00:00:00 | 2008-10-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3387 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3SF3520W62A14.1 | (Gas COMP PKG #31) Function Test | (Gas COMP PKG #31) Function Test | 2008-10-13 | 2008-10-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3SF3520W62A14.1 (Gas COMP PKG #31) Function Test | Activity | 3SF3520W62A14.1 | (Gas COMP PKG #31) Function Test | 2008-10-13 00:00:00 | 2008-10-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3388 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3SF3520W62A23.1 | (Gas COMP PKG #32) Function Test | (Gas COMP PKG #32) Function Test | 2008-10-13 | 2008-10-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3SF3520W62A23.1 (Gas COMP PKG #32) Function Test | Activity | 3SF3520W62A23.1 | (Gas COMP PKG #32) Function Test | 2008-10-13 00:00:00 | 2008-10-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3389 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3SF3520W62A15.1 | (Gas COMP PKG #31) Running Test | (Gas COMP PKG #31) Running Test | 2008-10-19 | 2008-10-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3SF3520W62A15.1 (Gas COMP PKG #31) Running Test | Activity | 3SF3520W62A15.1 | (Gas COMP PKG #31) Running Test | 2008-10-19 00:00:00 | 2008-10-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3390 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas Compressor | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas Compressor | 3SF3520W62A24.1 | (Gas COMP PKG #32) Running Test | (Gas COMP PKG #32) Running Test | 2008-10-19 | 2008-10-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas Compressor 3SF3520W62A24.1 (Gas COMP PKG #32) Running Test | Activity | 3SF3520W62A24.1 | (Gas COMP PKG #32) Running Test | 2008-10-19 00:00:00 | 2008-10-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3392 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 3CF3520W42A01.1 | (Gas Cooler #11) Installation(incl. fan) | (Gas Cooler #11) Installation(incl. fan) | 2008-07-30 | 2008-08-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas cooler 3CF3520W42A01.1 (Gas Cooler #11) Installation(incl. fan) | Activity | 3CF3520W42A01.1 | (Gas Cooler #11) Installation(incl. fan) | 2008-07-30 00:00:00 | 2008-08-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3393 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 3CF3520W42A05.1 | (Gas Cooler #32) Installation(incl. fan) | (Gas Cooler #32) Installation(incl. fan) | 2008-07-30 | 2008-08-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas cooler 3CF3520W42A05.1 (Gas Cooler #32) Installation(incl. fan) | Activity | 3CF3520W42A05.1 | (Gas Cooler #32) Installation(incl. fan) | 2008-07-30 00:00:00 | 2008-08-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3394 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 3SF3520W62A02.1 | (Gas Cooler #31) Loop chek | (Gas Cooler #31) Loop chek | 2008-08-21 | 2008-08-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas cooler 3SF3520W62A02.1 (Gas Cooler #31) Loop chek | Activity | 3SF3520W62A02.1 | (Gas Cooler #31) Loop chek | 2008-08-21 00:00:00 | 2008-08-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3395 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 3SF3520W62A06.1 | (Gas Cooler #32) Loop chek | (Gas Cooler #32) Loop chek | 2008-08-21 | 2008-08-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas cooler 3SF3520W62A06.1 (Gas Cooler #32) Loop chek | Activity | 3SF3520W62A06.1 | (Gas Cooler #32) Loop chek | 2008-08-21 00:00:00 | 2008-08-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3396 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 3SF3520W62A03.1 | (Gas Cooler #31) Function Test | (Gas Cooler #31) Function Test | 2008-08-26 | 2008-08-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas cooler 3SF3520W62A03.1 (Gas Cooler #31) Function Test | Activity | 3SF3520W62A03.1 | (Gas Cooler #31) Function Test | 2008-08-26 00:00:00 | 2008-08-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3397 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 3SF3520W62A07.1 | (Gas Cooler #32) Function Test | (Gas Cooler #32) Function Test | 2008-08-26 | 2008-08-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas cooler 3SF3520W62A07.1 (Gas Cooler #32) Function Test | Activity | 3SF3520W62A07.1 | (Gas Cooler #32) Function Test | 2008-08-26 00:00:00 | 2008-08-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3398 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 3SF3520W62A04.1 | (Gas Cooler #31) Running Test | (Gas Cooler #31) Running Test | 2008-08-29 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas cooler 3SF3520W62A04.1 (Gas Cooler #31) Running Test | Activity | 3SF3520W62A04.1 | (Gas Cooler #31) Running Test | 2008-08-29 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3399 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Fuel Gas Supply System > Gas cooler | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Fuel Gas Supply System | Gas cooler | 3SF3520W62A08.1 | (Gas Cooler #32) Running Test | (Gas Cooler #32) Running Test | 2008-08-29 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Fuel Gas Supply System Gas cooler 3SF3520W62A08.1 (Gas Cooler #32) Running Test | Activity | 3SF3520W62A08.1 | (Gas Cooler #32) Running Test | 2008-08-29 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3401 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > N2 Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | N2 Gas System |  | 3PF3515W42A04P | (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | 2007-11-01 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common N2 Gas System 3PF3515W42A04P (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | Activity | 3PF3515W42A04P | (N2 Gas Equip) P.O & Procurement for FGSS(Local PROC.) | 2007-11-01 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3402 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > N2 Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | N2 Gas System |  | 3EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | (N2 Gas Station Shelter) GA & Load Data to Civil Design | 2007-12-03 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common N2 Gas System 3EF3515W00A06 (N2 Gas Station Shelter) GA & Load Data to Civil Design | Activity | 3EF3515W00A06 | (N2 Gas Station Shelter) GA & Load Data to Civil Design | 2007-12-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3403 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > N2 Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | N2 Gas System |  | 3EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | (N2 Gas Station Shelter) Shelter Design | 2007-12-03 | 2008-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common N2 Gas System 3EF3515W32A08 (N2 Gas Station Shelter) Shelter Design | Activity | 3EF3515W32A08 | (N2 Gas Station Shelter) Shelter Design | 2007-12-03 00:00:00 | 2008-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3404 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > N2 Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | N2 Gas System |  | 3CF3515W16A07 | (N2 Gas Station Shelter) FDN Work | (N2 Gas Station Shelter) FDN Work | 2008-03-04 | 2008-04-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common N2 Gas System 3CF3515W16A07 (N2 Gas Station Shelter) FDN Work | Activity | 3CF3515W16A07 | (N2 Gas Station Shelter) FDN Work | 2008-03-04 00:00:00 | 2008-04-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3405 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > N2 Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | N2 Gas System |  | 3CF3515W32A09 | (N2 Gas Station Shelter) Shelter Work | (N2 Gas Station Shelter) Shelter Work | 2008-05-01 | 2008-08-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common N2 Gas System 3CF3515W32A09 (N2 Gas Station Shelter) Shelter Work | Activity | 3CF3515W32A09 | (N2 Gas Station Shelter) Shelter Work | 2008-05-01 00:00:00 | 2008-08-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3406 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > N2 Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | N2 Gas System |  | 3CF3515W42A05 | (N2 Gas Equip) Installation for FGSS | (N2 Gas Equip) Installation for FGSS | 2008-07-02 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common N2 Gas System 3CF3515W42A05 (N2 Gas Equip) Installation for FGSS | Activity | 3CF3515W42A05 | (N2 Gas Equip) Installation for FGSS | 2008-07-02 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3409 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 3PF6500W86A02P | (GT GCB) P.O & Procurement | (GT GCB) P.O & Procurement | 2007-05-31 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 3PF6500W86A02P (GT GCB) P.O & Procurement | Activity | 3PF6500W86A02P | (GT GCB) P.O & Procurement | 2007-05-31 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3410 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 3PF6500W86A07P | (ST GCB) P.O & Procurement | (ST GCB) P.O & Procurement | 2007-10-02 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 3PF6500W86A07P (ST GCB) P.O & Procurement | Activity | 3PF6500W86A07P | (ST GCB) P.O & Procurement | 2007-10-02 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3411 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 3PF6500W86A03T | (GT GCB) Transportation | (GT GCB) Transportation | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 3PF6500W86A03T (GT GCB) Transportation | Activity | 3PF6500W86A03T | (GT GCB) Transportation | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3412 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 3CF6500W86A04 | (GT GCB) Installation | (GT GCB) Installation | 2008-07-16 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 3CF6500W86A04 (GT GCB) Installation | Activity | 3CF6500W86A04 | (GT GCB) Installation | 2008-07-16 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3413 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 3SF6500W62A05 | (GT GCB) Function Test | (GT GCB) Function Test | 2008-08-16 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 3SF6500W62A05 (GT GCB) Function Test | Activity | 3SF6500W62A05 | (GT GCB) Function Test | 2008-08-16 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3414 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 3PF6500W86A08T | (ST GCB) Transportation | (ST GCB) Transportation | 2008-10-01 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 3PF6500W86A08T (ST GCB) Transportation | Activity | 3PF6500W86A08T | (ST GCB) Transportation | 2008-10-01 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3415 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 3CF6500W86A09 | (ST GCB) Installation | (ST GCB) Installation | 2009-01-20 | 2009-02-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 3CF6500W86A09 (ST GCB) Installation | Activity | 3CF6500W86A09 | (ST GCB) Installation | 2009-01-20 00:00:00 | 2009-02-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3416 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Generator Circuit Breaker (GCB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Generator Circuit Breaker (GCB) | 3SF6500W62A10 | (ST GCB) Function Test | (ST GCB) Function Test | 2009-02-20 | 2009-03-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Generator Circuit Breaker (GCB) 3SF6500W62A10 (ST GCB) Function Test | Activity | 3SF6500W62A10 | (ST GCB) Function Test | 2009-02-20 00:00:00 | 2009-03-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3418 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Extra High Voltage Cable | 3PF6040W74A06P | (EHV Cable) P.O & Procurement | (EHV Cable) P.O & Procurement | 2007-08-02 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Extra High Voltage Cable 3PF6040W74A06P (EHV Cable) P.O & Procurement | Activity | 3PF6040W74A06P | (EHV Cable) P.O & Procurement | 2007-08-02 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3419 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Extra High Voltage Cable | 3EF6040W16A02 | (Cable tunnel) FDN Design | (Cable tunnel) FDN Design | 2007-08-02 | 2007-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Extra High Voltage Cable 3EF6040W16A02 (Cable tunnel) FDN Design | Activity | 3EF6040W16A02 | (Cable tunnel) FDN Design | 2007-08-02 00:00:00 | 2007-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3420 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Extra High Voltage Cable | 3EF6040W16A01 | (Cable tunnel) Cable tunnel Design | (Cable tunnel) Cable tunnel Design | 2007-08-02 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Extra High Voltage Cable 3EF6040W16A01 (Cable tunnel) Cable tunnel Design | Activity | 3EF6040W16A01 | (Cable tunnel) Cable tunnel Design | 2007-08-02 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3421 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Extra High Voltage Cable | 3CF6040W16A03 | (Cable tunnel) Civil Work | (Cable tunnel) Civil Work | 2007-11-02 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Extra High Voltage Cable 3CF6040W16A03 (Cable tunnel) Civil Work | Activity | 3CF6040W16A03 | (Cable tunnel) Civil Work | 2007-11-02 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3422 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Extra High Voltage Cable | 3PF6040W74A07T | (EHV Cable) Transportation | (EHV Cable) Transportation | 2008-05-02 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Extra High Voltage Cable 3PF6040W74A07T (EHV Cable) Transportation | Activity | 3PF6040W74A07T | (EHV Cable) Transportation | 2008-05-02 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3423 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Extra High Voltage Cable | 3CF6040W38A04 | (Cable tunnel) F/F Work & Test | (Cable tunnel) F/F Work & Test | 2008-05-31 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Extra High Voltage Cable 3CF6040W38A04 (Cable tunnel) F/F Work & Test | Activity | 3CF6040W38A04 | (Cable tunnel) F/F Work & Test | 2008-05-31 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3424 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Extra High Voltage Cable | 3CF6040W74A08 | (EHV Cable) Cable Electrical Work | (EHV Cable) Cable Electrical Work | 2008-06-17 | 2008-09-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Extra High Voltage Cable 3CF6040W74A08 (EHV Cable) Cable Electrical Work | Activity | 3CF6040W74A08 | (EHV Cable) Cable Electrical Work | 2008-06-17 00:00:00 | 2008-09-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3425 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Extra High Voltage Cable | 3CF6040W62A09 | (EHV Cable) Function Test | (EHV Cable) Function Test | 2008-09-02 | 2008-09-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Extra High Voltage Cable 3CF6040W62A09 (EHV Cable) Function Test | Activity | 3CF6040W62A09 | (EHV Cable) Function Test | 2008-09-02 00:00:00 | 2008-09-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3426 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Extra High Voltage Cable | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Extra High Voltage Cable | 3CF6040W74A10 | (EHV Cable) Connection with GIS & TR | (EHV Cable) Connection with GIS & TR | 2008-09-17 | 2008-09-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Extra High Voltage Cable 3CF6040W74A10 (EHV Cable) Connection with GIS & TR | Activity | 3CF6040W74A10 | (EHV Cable) Connection with GIS & TR | 2008-09-17 00:00:00 | 2008-09-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3428 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Isolated Phase Busduct (IPB) | 3PF6500W74A02P | (IPB) P.O & Procurement | (IPB) P.O & Procurement | 2007-08-02 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Isolated Phase Busduct (IPB) 3PF6500W74A02P (IPB) P.O & Procurement | Activity | 3PF6500W74A02P | (IPB) P.O & Procurement | 2007-08-02 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3429 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Isolated Phase Busduct (IPB) | 3PF6500W74A03T | (IPB) Transportation | (IPB) Transportation | 2008-05-16 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Isolated Phase Busduct (IPB) 3PF6500W74A03T (IPB) Transportation | Activity | 3PF6500W74A03T | (IPB) Transportation | 2008-05-16 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3430 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Isolated Phase Busduct (IPB) | 3CF6500W74A04 | (IPB) Installation form TR to GCB(incl. Support) | (IPB) Installation form TR to GCB(incl. Support) | 2008-07-01 | 2008-09-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Isolated Phase Busduct (IPB) 3CF6500W74A04 (IPB) Installation form TR to GCB(incl. Support) | Activity | 3CF6500W74A04 | (IPB) Installation form TR to GCB(incl. Support) | 2008-07-01 00:00:00 | 2008-09-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3431 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Isolated Phase Busduct (IPB) | 3CF6500W62A05 | (IPB) Insulation Test & Hi potential Test | (IPB) Insulation Test & Hi potential Test | 2008-09-02 | 2008-09-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Isolated Phase Busduct (IPB) 3CF6500W62A05 (IPB) Insulation Test & Hi potential Test | Activity | 3CF6500W62A05 | (IPB) Insulation Test & Hi potential Test | 2008-09-02 00:00:00 | 2008-09-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3432 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Isolated Phase Busduct (IPB) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Isolated Phase Busduct (IPB) | 3CF6500W74A06 | (IPB) IPB connection with TR & GCB | (IPB) IPB connection with TR & GCB | 2008-10-21 | 2008-10-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Isolated Phase Busduct (IPB) 3CF6500W74A06 (IPB) IPB connection with TR & GCB | Activity | 3CF6500W74A06 | (IPB) IPB connection with TR & GCB | 2008-10-21 00:00:00 | 2008-10-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3434 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3PF6500W70A04P | (GTG TR) P.O & Procurement | (GTG TR) P.O & Procurement | 2007-04-02 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3PF6500W70A04P (GTG TR) P.O & Procurement | Activity | 3PF6500W70A04P | (GTG TR) P.O & Procurement | 2007-04-02 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3435 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3PF6500W70A12P | (STG TR) P.O & Procurement | (STG TR) P.O & Procurement | 2007-08-02 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3PF6500W70A12P (STG TR) P.O & Procurement | Activity | 3PF6500W70A12P | (STG TR) P.O & Procurement | 2007-08-02 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3436 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3EF6500W16A01 | (GTG TR) FDN Design | (GTG TR) FDN Design | 2007-08-02 | 2007-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3EF6500W16A01 (GTG TR) FDN Design | Activity | 3EF6500W16A01 | (GTG TR) FDN Design | 2007-08-02 00:00:00 | 2007-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3437 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3CF6500W16A02 | (GTG TR) FDN & Firewall Work | (GTG TR) FDN & Firewall Work | 2007-12-01 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3CF6500W16A02 (GTG TR) FDN & Firewall Work | Activity | 3CF6500W16A02 | (GTG TR) FDN & Firewall Work | 2007-12-01 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3438 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3EF6500W16A09 | (STG TR) FDN Design | (STG TR) FDN Design | 2008-02-06 | 2008-07-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3EF6500W16A09 (STG TR) FDN Design | Activity | 3EF6500W16A09 | (STG TR) FDN Design | 2008-02-06 00:00:00 | 2008-07-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3439 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3PF6500W70A05T | (GTG TR) Transportation | (GTG TR) Transportation | 2008-06-17 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3PF6500W70A05T (GTG TR) Transportation | Activity | 3PF6500W70A05T | (GTG TR) Transportation | 2008-06-17 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3440 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3CF6500W16A10 | (STG TR) FDN & Firewall Work | (STG TR) FDN & Firewall Work | 2008-07-05 | 2008-11-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3CF6500W16A10 (STG TR) FDN & Firewall Work | Activity | 3CF6500W16A10 | (STG TR) FDN & Firewall Work | 2008-07-05 00:00:00 | 2008-11-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3441 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3CF6500W70A06 | (GTG TR) Installation | (GTG TR) Installation | 2008-08-01 | 2008-09-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3CF6500W70A06 (GTG TR) Installation | Activity | 3CF6500W70A06 | (GTG TR) Installation | 2008-08-01 00:00:00 | 2008-09-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3442 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3CF6500W38A07 | (GTG TR) F/F Install & test | (GTG TR) F/F Install & test | 2008-09-17 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3CF6500W38A07 (GTG TR) F/F Install & test | Activity | 3CF6500W38A07 | (GTG TR) F/F Install & test | 2008-09-17 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3443 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3PF6500W70A13T | (STG TR) Transportation | (STG TR) Transportation | 2008-10-01 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3PF6500W70A13T (STG TR) Transportation | Activity | 3PF6500W70A13T | (STG TR) Transportation | 2008-10-01 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3444 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3SF6500W62A08 | (GTG TR) Function Test | (GTG TR) Function Test | 2008-10-01 | 2008-10-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3SF6500W62A08 (GTG TR) Function Test | Activity | 3SF6500W62A08 | (GTG TR) Function Test | 2008-10-01 00:00:00 | 2008-10-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3445 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3CF6500W70A14 | (STG TR) Installation | (STG TR) Installation | 2008-11-15 | 2008-12-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3CF6500W70A14 (STG TR) Installation | Activity | 3CF6500W70A14 | (STG TR) Installation | 2008-11-15 00:00:00 | 2008-12-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3446 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3CF6500W38A15 | (STG TR) F/F test | (STG TR) F/F test | 2008-12-31 | 2009-01-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3CF6500W38A15 (STG TR) F/F test | Activity | 3CF6500W38A15 | (STG TR) F/F test | 2008-12-31 00:00:00 | 2009-01-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3447 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Power Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Power Transformer | 3SF6500W62A16 | (STG TR) Function Test | (STG TR) Function Test | 2009-03-07 | 2009-03-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Power Transformer 3SF6500W62A16 (STG TR) Function Test | Activity | 3SF6500W62A16 | (STG TR) Function Test | 2009-03-07 00:00:00 | 2009-03-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3449 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3PF6500W70A04.1P | (GTG UAT) P.O & Procurement | (GTG UAT) P.O & Procurement | 2007-03-30 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3PF6500W70A04.1P (GTG UAT) P.O & Procurement | Activity | 3PF6500W70A04.1P | (GTG UAT) P.O & Procurement | 2007-03-30 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3450 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3EF6500W16A01.1 | (GTG UAT) FDN Design | (GTG UAT) FDN Design | 2007-05-01 | 2007-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3EF6500W16A01.1 (GTG UAT) FDN Design | Activity | 3EF6500W16A01.1 | (GTG UAT) FDN Design | 2007-05-01 00:00:00 | 2007-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3451 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3EF6500W00A09 | (GTG #31 & UAT Shelter) GA & Load Data to Civil Design | (GTG #31 & UAT Shelter) GA & Load Data to Civil Design | 2007-05-31 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3EF6500W00A09 (GTG #31 & UAT Shelter) GA & Load Data to Civil Design | Activity | 3EF6500W00A09 | (GTG #31 & UAT Shelter) GA & Load Data to Civil Design | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3452 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3EF6500W16A10 | (GTG #31 & UAT Shelter) FDN Design | (GTG #31 & UAT Shelter) FDN Design | 2007-07-02 | 2007-10-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3EF6500W16A10 (GTG #31 & UAT Shelter) FDN Design | Activity | 3EF6500W16A10 | (GTG #31 & UAT Shelter) FDN Design | 2007-07-02 00:00:00 | 2007-10-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3453 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3EF6500W32A12 | (GTG #31 & UAT Shelter) Structure Design | (GTG #31 & UAT Shelter) Structure Design | 2007-07-02 | 2007-10-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3EF6500W32A12 (GTG #31 & UAT Shelter) Structure Design | Activity | 3EF6500W32A12 | (GTG #31 & UAT Shelter) Structure Design | 2007-07-02 00:00:00 | 2007-10-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3454 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3CF6500W16A02.1 | (GTG UAT) FDN Work & Firewall Work | (GTG UAT) FDN Work & Firewall Work | 2007-12-04 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3CF6500W16A02.1 (GTG UAT) FDN Work & Firewall Work | Activity | 3CF6500W16A02.1 | (GTG UAT) FDN Work & Firewall Work | 2007-12-04 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3455 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3CF6500W16A11 | (GTG #31 & UAT Shelter) FDN Work | (GTG #31 & UAT Shelter) FDN Work | 2008-04-02 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3CF6500W16A11 (GTG #31 & UAT Shelter) FDN Work | Activity | 3CF6500W16A11 | (GTG #31 & UAT Shelter) FDN Work | 2008-04-02 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3456 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3PF6500W70A05.1T | (GTG UAT) Transportation | (GTG UAT) Transportation | 2008-05-17 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3PF6500W70A05.1T (GTG UAT) Transportation | Activity | 3PF6500W70A05.1T | (GTG UAT) Transportation | 2008-05-17 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3457 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3CF6500W32A13 | (GTG #31 & UAT Shelter) Structure Work | (GTG #31 & UAT Shelter) Structure Work | 2008-05-30 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3CF6500W32A13 (GTG #31 & UAT Shelter) Structure Work | Activity | 3CF6500W32A13 | (GTG #31 & UAT Shelter) Structure Work | 2008-05-30 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3458 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3CF6500W70A06.1 | (GTG UAT) Installation | (GTG UAT) Installation | 2008-07-02 | 2008-08-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3CF6500W70A06.1 (GTG UAT) Installation | Activity | 3CF6500W70A06.1 | (GTG UAT) Installation | 2008-07-02 00:00:00 | 2008-08-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3459 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3CF6500W38A07.1 | (GTG UAT) F/F Install & test | (GTG UAT) F/F Install & test | 2008-08-18 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3CF6500W38A07.1 (GTG UAT) F/F Install & test | Activity | 3CF6500W38A07.1 | (GTG UAT) F/F Install & test | 2008-08-18 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3460 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3CF6500W38A14 | (GTG #31 & UAT Shelter) Installation & Test - Fire Fighting Sys. | (GTG #31 & UAT Shelter) Installation & Test - Fire Fighting Sys. | 2008-09-01 | 2008-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3CF6500W38A14 (GTG #31 & UAT Shelter) Installation & Test - Fire Fighting Sys. | Activity | 3CF6500W38A14 | (GTG #31 & UAT Shelter) Installation & Test - Fire Fighting Sys. | 2008-09-01 00:00:00 | 2008-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3461 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3CF6500W74A15 | (GTG #31 & UAT Shelter) Installation & Test - Elec | (GTG #31 & UAT Shelter) Installation & Test - Elec | 2008-09-01 | 2008-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3CF6500W74A15 (GTG #31 & UAT Shelter) Installation & Test - Elec | Activity | 3CF6500W74A15 | (GTG #31 & UAT Shelter) Installation & Test - Elec | 2008-09-01 00:00:00 | 2008-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3462 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3CF6500W90A16 | (GTG #31 & UAT Shelter) Installation & Test - I&C | (GTG #31 & UAT Shelter) Installation & Test - I&C | 2008-09-01 | 2008-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3CF6500W90A16 (GTG #31 & UAT Shelter) Installation & Test - I&C | Activity | 3CF6500W90A16 | (GTG #31 & UAT Shelter) Installation & Test - I&C | 2008-09-01 00:00:00 | 2008-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3463 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Auxiliary Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Auxiliary Transformer | 3SF6500W62A08.1 | (GTG UAT) Function Test | (GTG UAT) Function Test | 2008-10-17 | 2008-10-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Auxiliary Transformer 3SF6500W62A08.1 (GTG UAT) Function Test | Activity | 3SF6500W62A08.1 | (GTG UAT) Function Test | 2008-10-17 00:00:00 | 2008-10-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3465 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3EF3530W00A01 | (Block #3 EDG) GA & Load Data to Civil Design | (Block #3 EDG) GA & Load Data to Civil Design | 2007-08-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3EF3530W00A01 (Block #3 EDG) GA & Load Data to Civil Design | Activity | 3EF3530W00A01 | (Block #3 EDG) GA & Load Data to Civil Design | 2007-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3466 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3EF3530W16A14 | (Block #3 EDG BLDG) FDN Design | (Block #3 EDG BLDG) FDN Design | 2007-08-01 | 2007-10-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3EF3530W16A14 (Block #3 EDG BLDG) FDN Design | Activity | 3EF3530W16A14 | (Block #3 EDG BLDG) FDN Design | 2007-08-01 00:00:00 | 2007-10-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3467 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3EF3530W32A16 | (Block #3 EDG BLDG) Structure Design | (Block #3 EDG BLDG) Structure Design | 2007-08-01 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3EF3530W32A16 (Block #3 EDG BLDG) Structure Design | Activity | 3EF3530W32A16 | (Block #3 EDG BLDG) Structure Design | 2007-08-01 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3468 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3PF3530W42A06P | (Block #3 EDG) P.O & Procurement | (Block #3 EDG) P.O & Procurement | 2007-08-01 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3PF3530W42A06P (Block #3 EDG) P.O & Procurement | Activity | 3PF3530W42A06P | (Block #3 EDG) P.O & Procurement | 2007-08-01 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3469 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3EF3530W16A02 | (Block #3 EDG) FDN Design | (Block #3 EDG) FDN Design | 2007-08-01 | 2007-10-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3EF3530W16A02 (Block #3 EDG) FDN Design | Activity | 3EF3530W16A02 | (Block #3 EDG) FDN Design | 2007-08-01 00:00:00 | 2007-10-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3470 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3CF3530W16A15 | (Block #3 EDG BLDG) FDN Work | (Block #3 EDG BLDG) FDN Work | 2008-01-01 | 2008-03-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3CF3530W16A15 (Block #3 EDG BLDG) FDN Work | Activity | 3CF3530W16A15 | (Block #3 EDG BLDG) FDN Work | 2008-01-01 00:00:00 | 2008-03-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3471 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3CF3530W16A03 | (Block #3 EDG) FDN Work | (Block #3 EDG) FDN Work | 2008-01-01 | 2008-03-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3CF3530W16A03 (Block #3 EDG) FDN Work | Activity | 3CF3530W16A03 | (Block #3 EDG) FDN Work | 2008-01-01 00:00:00 | 2008-03-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3472 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3CF3530W32A17 | (Block #3 EDG BLDG) Structure Work | (Block #3 EDG BLDG) Structure Work | 2008-03-03 | 2008-06-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3CF3530W32A17 (Block #3 EDG BLDG) Structure Work | Activity | 3CF3530W32A17 | (Block #3 EDG BLDG) Structure Work | 2008-03-03 00:00:00 | 2008-06-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3473 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3CF3530W90A21 | (Block #3 EDG BLDG) Installation & Test - I&C | (Block #3 EDG BLDG) Installation & Test - I&C | 2008-06-04 | 2008-07-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3CF3530W90A21 (Block #3 EDG BLDG) Installation & Test - I&C | Activity | 3CF3530W90A21 | (Block #3 EDG BLDG) Installation & Test - I&C | 2008-06-04 00:00:00 | 2008-07-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3474 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3CF3530W38A18 | (Block #3 EDG BLDG) Installation - Fire Fighting Sys. | (Block #3 EDG BLDG) Installation - Fire Fighting Sys. | 2008-06-04 | 2008-07-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3CF3530W38A18 (Block #3 EDG BLDG) Installation - Fire Fighting Sys. | Activity | 3CF3530W38A18 | (Block #3 EDG BLDG) Installation - Fire Fighting Sys. | 2008-06-04 00:00:00 | 2008-07-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3475 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3CF3530W36A19 | (Block #3 EDG BLDG) Installation & Test - HVAC | (Block #3 EDG BLDG) Installation & Test - HVAC | 2008-06-04 | 2008-07-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3CF3530W36A19 (Block #3 EDG BLDG) Installation & Test - HVAC | Activity | 3CF3530W36A19 | (Block #3 EDG BLDG) Installation & Test - HVAC | 2008-06-04 00:00:00 | 2008-07-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3476 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3CF3530W74A20 | (Block #3 EDG BLDG) Installation & Test - Elec | (Block #3 EDG BLDG) Installation & Test - Elec | 2008-06-04 | 2008-07-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3CF3530W74A20 (Block #3 EDG BLDG) Installation & Test - Elec | Activity | 3CF3530W74A20 | (Block #3 EDG BLDG) Installation & Test - Elec | 2008-06-04 00:00:00 | 2008-07-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3477 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3CF3530W24A22 | (Block #3 EDG BLDG) Building Finish | (Block #3 EDG BLDG) Building Finish | 2008-06-04 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3CF3530W24A22 (Block #3 EDG BLDG) Building Finish | Activity | 3CF3530W24A22 | (Block #3 EDG BLDG) Building Finish | 2008-06-04 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3478 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3PF3530W42A07T | (Block #3 EDG) Transportation | (Block #3 EDG) Transportation | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3PF3530W42A07T (Block #3 EDG) Transportation | Activity | 3PF3530W42A07T | (Block #3 EDG) Transportation | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3479 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3CF3530W42A08 | (Block #3 EDG) Installation | (Block #3 EDG) Installation | 2008-09-16 | 2008-10-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3CF3530W42A08 (Block #3 EDG) Installation | Activity | 3CF3530W42A08 | (Block #3 EDG) Installation | 2008-09-16 00:00:00 | 2008-10-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3480 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3SF3530W62A09 | (Block #3 EDG) Loop chek | (Block #3 EDG) Loop chek | 2008-10-07 | 2008-10-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3SF3530W62A09 (Block #3 EDG) Loop chek | Activity | 3SF3530W62A09 | (Block #3 EDG) Loop chek | 2008-10-07 00:00:00 | 2008-10-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3481 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3SF3530W62A10 | (Block #3 EDG) Function Test | (Block #3 EDG) Function Test | 2008-10-09 | 2008-10-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3SF3530W62A10 (Block #3 EDG) Function Test | Activity | 3SF3530W62A10 | (Block #3 EDG) Function Test | 2008-10-09 00:00:00 | 2008-10-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3482 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3SF3530W62A11 | (Block #3 EDG) System Operation | (Block #3 EDG) System Operation | 2008-10-11 | 2008-10-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3SF3530W62A11 (Block #3 EDG) System Operation | Activity | 3SF3530W62A11 | (Block #3 EDG) System Operation | 2008-10-11 00:00:00 | 2008-10-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3483 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3SF3530W62A12 | (Block #3 EDG) Synchronization | (Block #3 EDG) Synchronization | 2008-10-13 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3SF3530W62A12 (Block #3 EDG) Synchronization | Activity | 3SF3530W62A12 | (Block #3 EDG) Synchronization | 2008-10-13 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3484 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Early Power Block Common > Electrical System > Emergency Diesel Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Early Power Block Common | Electrical System | Emergency Diesel Generator | 3SF3530W62A13 | (Block #3 EDG) Load Operation | (Block #3 EDG) Load Operation | 2008-10-15 | 2008-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Early Power Block Common Electrical System Emergency Diesel Generator 3SF3530W62A13 (Block #3 EDG) Load Operation | Activity | 3SF3530W62A13 | (Block #3 EDG) Load Operation | 2008-10-15 00:00:00 | 2008-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3487 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3PF3030W68A04P | (EXP Head Tank) P.O & Procurement | (EXP Head Tank) P.O & Procurement | 2007-09-03 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3PF3030W68A04P (EXP Head Tank) P.O & Procurement | Activity | 3PF3030W68A04P | (EXP Head Tank) P.O & Procurement | 2007-09-03 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3488 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3PF3030W42A21P | (CCWP) P.O & Procurement | (CCWP) P.O & Procurement | 2007-09-03 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3PF3030W42A21P (CCWP) P.O & Procurement | Activity | 3PF3030W42A21P | (CCWP) P.O & Procurement | 2007-09-03 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3489 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3EF3030W16A17 | (CCWP) FDN Design | (CCWP) FDN Design | 2007-09-03 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3EF3030W16A17 (CCWP) FDN Design | Activity | 3EF3030W16A17 | (CCWP) FDN Design | 2007-09-03 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3490 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3PF3030W42A14P | (CCW H/EX) P.O & Procurement | (CCW H/EX) P.O & Procurement | 2007-09-03 | 2008-09-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3PF3030W42A14P (CCW H/EX) P.O & Procurement | Activity | 3PF3030W42A14P | (CCW H/EX) P.O & Procurement | 2007-09-03 00:00:00 | 2008-09-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3491 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3EF3030W16A10 | (CCW H/EX) FDN Design | (CCW H/EX) FDN Design | 2007-09-03 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3EF3030W16A10 (CCW H/EX) FDN Design | Activity | 3EF3030W16A10 | (CCW H/EX) FDN Design | 2007-09-03 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3492 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3EF3030W16A01 | (EXP Head Tank) FDN Design | (EXP Head Tank) FDN Design | 2007-11-02 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3EF3030W16A01 (EXP Head Tank) FDN Design | Activity | 3EF3030W16A01 | (EXP Head Tank) FDN Design | 2007-11-02 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3493 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3CF3030W16A18 | (CCWP) FDN Work | (CCWP) FDN Work | 2008-04-03 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3CF3030W16A18 (CCWP) FDN Work | Activity | 3CF3030W16A18 | (CCWP) FDN Work | 2008-04-03 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3494 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3CF3030W16A11 | (CCW H/EX) FDN Work | (CCW H/EX) FDN Work | 2008-04-03 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3CF3030W16A11 (CCW H/EX) FDN Work | Activity | 3CF3030W16A11 | (CCW H/EX) FDN Work | 2008-04-03 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3495 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3CF3030W16A02 | (EXP Head Tank) FDN Work | (EXP Head Tank) FDN Work | 2008-06-04 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3CF3030W16A02 (EXP Head Tank) FDN Work | Activity | 3CF3030W16A02 | (EXP Head Tank) FDN Work | 2008-06-04 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3496 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3CF3030W58A07 | (CCWS) Piping Work | (CCWS) Piping Work | 2008-08-01 | 2008-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3CF3030W58A07 (CCWS) Piping Work | Activity | 3CF3030W58A07 | (CCWS) Piping Work | 2008-08-01 00:00:00 | 2008-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3497 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3PF3030W42A22T | (CCWP) Transportation | (CCWP) Transportation | 2008-09-03 | 2008-10-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3PF3030W42A22T (CCWP) Transportation | Activity | 3PF3030W42A22T | (CCWP) Transportation | 2008-09-03 00:00:00 | 2008-10-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3498 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3PF3030W42A15T | (CCW H/EX) Transportation | (CCW H/EX) Transportation | 2008-09-17 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3PF3030W42A15T (CCW H/EX) Transportation | Activity | 3PF3030W42A15T | (CCW H/EX) Transportation | 2008-09-17 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3499 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3PF3030W68A05T | (EXP Head Tank) Transportation | (EXP Head Tank) Transportation | 2008-10-01 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3PF3030W68A05T (EXP Head Tank) Transportation | Activity | 3PF3030W68A05T | (EXP Head Tank) Transportation | 2008-10-01 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3500 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3CF3030W74A08 | (CCWS) Installation & Test - Elec. | (CCWS) Installation & Test - Elec. | 2008-10-14 | 2008-12-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3CF3030W74A08 (CCWS) Installation & Test - Elec. | Activity | 3CF3030W74A08 | (CCWS) Installation & Test - Elec. | 2008-10-14 00:00:00 | 2008-12-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3501 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3CF3030W90A09 | (CCWS) Installation & Test - I&C | (CCWS) Installation & Test - I&C | 2008-10-14 | 2008-12-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3CF3030W90A09 (CCWS) Installation & Test - I&C | Activity | 3CF3030W90A09 | (CCWS) Installation & Test - I&C | 2008-10-14 00:00:00 | 2008-12-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3502 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3CF3030W42A23 | (CCWP) Installation | (CCWP) Installation | 2008-10-18 | 2008-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3CF3030W42A23 (CCWP) Installation | Activity | 3CF3030W42A23 | (CCWP) Installation | 2008-10-18 00:00:00 | 2008-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3503 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3CF3030W42A16 | (CCW H/EX) Installation | (CCW H/EX) Installation | 2008-11-03 | 2008-12-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3CF3030W42A16 (CCW H/EX) Installation | Activity | 3CF3030W42A16 | (CCW H/EX) Installation | 2008-11-03 00:00:00 | 2008-12-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3504 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3CF3030W68A06 | (EXP Head Tank) Installation | (EXP Head Tank) Installation | 2008-11-15 | 2008-12-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3CF3030W68A06 (EXP Head Tank) Installation | Activity | 3CF3030W68A06 | (EXP Head Tank) Installation | 2008-11-15 00:00:00 | 2008-12-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3505 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3SF3030W62A24 | (CCWS) Loop chek | (CCWS) Loop chek | 2008-12-13 | 2008-12-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3SF3030W62A24 (CCWS) Loop chek | Activity | 3SF3030W62A24 | (CCWS) Loop chek | 2008-12-13 00:00:00 | 2008-12-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3506 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3SF3030W62A25 | (CCWS) System Function Test | (CCWS) System Function Test | 2008-12-18 | 2008-12-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3SF3030W62A25 (CCWS) System Function Test | Activity | 3SF3030W62A25 | (CCWS) System Function Test | 2008-12-18 00:00:00 | 2008-12-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3507 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Closed Cooling Water System for Block #3 | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Closed Cooling Water System for Block #3 |  | 3SF3030W62A26 | (CCWS) Pump Operation | (CCWS) Pump Operation | 2008-12-23 | 2008-12-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Closed Cooling Water System for Block #3 3SF3030W62A26 (CCWS) Pump Operation | Activity | 3SF3030W62A26 | (CCWS) Pump Operation | 2008-12-23 00:00:00 | 2008-12-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3509 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3PF3546W42A18P | (Clean & Dirty LOP) P.O & Procurement | (Clean & Dirty LOP) P.O & Procurement | 2007-10-31 | 2008-12-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3PF3546W42A18P (Clean & Dirty LOP) P.O & Procurement | Activity | 3PF3546W42A18P | (Clean & Dirty LOP) P.O & Procurement | 2007-10-31 00:00:00 | 2008-12-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3510 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3EF3546W16A15 | (Clean & Dirty LOP) FDN Design | (Clean & Dirty LOP) FDN Design | 2007-10-31 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3EF3546W16A15 (Clean & Dirty LOP) FDN Design | Activity | 3EF3546W16A15 | (Clean & Dirty LOP) FDN Design | 2007-10-31 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3511 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3PF3546W42A06P | (Clean Oil Tank) P.O & Procurement | (Clean Oil Tank) P.O & Procurement | 2007-11-01 | 2008-12-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3PF3546W42A06P (Clean Oil Tank) P.O & Procurement | Activity | 3PF3546W42A06P | (Clean Oil Tank) P.O & Procurement | 2007-11-01 00:00:00 | 2008-12-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3512 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3EF3546W16A03 | (Clean Oil Tank) FDN Design | (Clean Oil Tank) FDN Design | 2007-11-01 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3EF3546W16A03 (Clean Oil Tank) FDN Design | Activity | 3EF3546W16A03 | (Clean Oil Tank) FDN Design | 2007-11-01 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3513 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3PF3546W42A12P | (Dirty Oil Tank) P.O & Procurement | (Dirty Oil Tank) P.O & Procurement | 2007-11-01 | 2008-12-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3PF3546W42A12P (Dirty Oil Tank) P.O & Procurement | Activity | 3PF3546W42A12P | (Dirty Oil Tank) P.O & Procurement | 2007-11-01 00:00:00 | 2008-12-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3514 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3EF3546W16A09 | (Dirty Oil Tank) FDN Design | (Dirty Oil Tank) FDN Design | 2007-11-01 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3EF3546W16A09 (Dirty Oil Tank) FDN Design | Activity | 3EF3546W16A09 | (Dirty Oil Tank) FDN Design | 2007-11-01 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3515 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3CF3546W16A04 | (Clean Oil Tank) FDN Work | (Clean Oil Tank) FDN Work | 2008-06-03 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3CF3546W16A04 (Clean Oil Tank) FDN Work | Activity | 3CF3546W16A04 | (Clean Oil Tank) FDN Work | 2008-06-03 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3516 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3CF3546W16A10 | (Dirty Oil Tank) FDN Work | (Dirty Oil Tank) FDN Work | 2008-06-03 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3CF3546W16A10 (Dirty Oil Tank) FDN Work | Activity | 3CF3546W16A10 | (Dirty Oil Tank) FDN Work | 2008-06-03 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3517 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3CF3546W16A16 | (Clean & Dirty LOP) FDN Work | (Clean & Dirty LOP) FDN Work | 2008-06-03 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3CF3546W16A16 (Clean & Dirty LOP) FDN Work | Activity | 3CF3546W16A16 | (Clean & Dirty LOP) FDN Work | 2008-06-03 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3518 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3PF3546W42A07T | (Clean Oil Tank) Transportation | (Clean Oil Tank) Transportation | 2008-12-03 | 2009-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3PF3546W42A07T (Clean Oil Tank) Transportation | Activity | 3PF3546W42A07T | (Clean Oil Tank) Transportation | 2008-12-03 00:00:00 | 2009-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3519 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3PF3546W42A13T | (Dirty Oil Tank) Transportation | (Dirty Oil Tank) Transportation | 2008-12-03 | 2009-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3PF3546W42A13T (Dirty Oil Tank) Transportation | Activity | 3PF3546W42A13T | (Dirty Oil Tank) Transportation | 2008-12-03 00:00:00 | 2009-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3520 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3PF3546W42A19T | (Clean & Dirty LOP) Transportation | (Clean & Dirty LOP) Transportation | 2008-12-03 | 2009-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3PF3546W42A19T (Clean & Dirty LOP) Transportation | Activity | 3PF3546W42A19T | (Clean & Dirty LOP) Transportation | 2008-12-03 00:00:00 | 2009-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3521 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3CF3546W42A08 | (Clean Oil Tank) Installation | (Clean Oil Tank) Installation | 2009-01-17 | 2009-03-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3CF3546W42A08 (Clean Oil Tank) Installation | Activity | 3CF3546W42A08 | (Clean Oil Tank) Installation | 2009-01-17 00:00:00 | 2009-03-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3522 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3CF3546W42A14 | (Dirty Oil Tank) Installation | (Dirty Oil Tank) Installation | 2009-01-17 | 2009-03-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3CF3546W42A14 (Dirty Oil Tank) Installation | Activity | 3CF3546W42A14 | (Dirty Oil Tank) Installation | 2009-01-17 00:00:00 | 2009-03-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3523 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3CF3546W42A20 | (Clean & Dirty LOP) Installation & Test | (Clean & Dirty LOP) Installation & Test | 2009-01-17 | 2009-02-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3CF3546W42A20 (Clean & Dirty LOP) Installation & Test | Activity | 3CF3546W42A20 | (Clean & Dirty LOP) Installation & Test | 2009-01-17 00:00:00 | 2009-02-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3524 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3CF3546W58A21 | (Clean & Dirty Oil System) Piping Work | (Clean & Dirty Oil System) Piping Work | 2009-01-17 | 2009-04-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3CF3546W58A21 (Clean & Dirty Oil System) Piping Work | Activity | 3CF3546W58A21 | (Clean & Dirty Oil System) Piping Work | 2009-01-17 00:00:00 | 2009-04-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3525 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3CF3546W74A22 | (Clean & Dirty Oil System) Installation & Test - Elec. | (Clean & Dirty Oil System) Installation & Test - Elec. | 2009-03-05 | 2009-04-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3CF3546W74A22 (Clean & Dirty Oil System) Installation & Test - Elec. | Activity | 3CF3546W74A22 | (Clean & Dirty Oil System) Installation & Test - Elec. | 2009-03-05 00:00:00 | 2009-04-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3526 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean & Dirty Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean & Dirty Oil System |  | 3CF3546W90A23 | (Clean & Dirty Oil System) Installation & Test - I&C | (Clean & Dirty Oil System) Installation & Test - I&C | 2009-03-05 | 2009-04-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean & Dirty Oil System 3CF3546W90A23 (Clean & Dirty Oil System) Installation & Test - I&C | Activity | 3CF3546W90A23 | (Clean & Dirty Oil System) Installation & Test - I&C | 2009-03-05 00:00:00 | 2009-04-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3528 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3PF3015W42A06P | (FWP) P.O & Procurement | (FWP) P.O & Procurement | 2007-08-30 | 2008-10-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3PF3015W42A06P (FWP) P.O & Procurement | Activity | 3PF3015W42A06P | (FWP) P.O & Procurement | 2007-08-30 00:00:00 | 2008-10-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3529 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | (FWP Shelter) GA & Load Data to Civil Design | 2007-10-31 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3EF3015W00A09 (FWP Shelter) GA & Load Data to Civil Design | Activity | 3EF3015W00A09 | (FWP Shelter) GA & Load Data to Civil Design | 2007-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3530 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3EF3015W32A10 | (FWP Shelter) FDN & Shelter Design | (FWP Shelter) FDN & Shelter Design | 2007-10-31 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3EF3015W32A10 (FWP Shelter) FDN & Shelter Design | Activity | 3EF3015W32A10 | (FWP Shelter) FDN & Shelter Design | 2007-10-31 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3531 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3EF3015W16A03 | (FWP) FDN Design | (FWP) FDN Design | 2007-10-31 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3EF3015W16A03 (FWP) FDN Design | Activity | 3EF3015W16A03 | (FWP) FDN Design | 2007-10-31 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3532 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3PF3015W58A14P | (FW PIPING) P.O & Procurement | (FW PIPING) P.O & Procurement | 2007-11-02 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3PF3015W58A14P (FW PIPING) P.O & Procurement | Activity | 3PF3015W58A14P | (FW PIPING) P.O & Procurement | 2007-11-02 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3533 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3CF3015W16A11 | (FWP Shelter) FDN Work | (FWP Shelter) FDN Work | 2008-01-31 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3CF3015W16A11 (FWP Shelter) FDN Work | Activity | 3CF3015W16A11 | (FWP Shelter) FDN Work | 2008-01-31 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3534 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3CF3015W32A12 | (FWP Shelter) Shelter Structure Work | (FWP Shelter) Shelter Structure Work | 2008-04-02 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3CF3015W32A12 (FWP Shelter) Shelter Structure Work | Activity | 3CF3015W32A12 | (FWP Shelter) Shelter Structure Work | 2008-04-02 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3535 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3CF3015W16A04 | (FWP) FDN Work | (FWP) FDN Work | 2008-04-03 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3CF3015W16A04 (FWP) FDN Work | Activity | 3CF3015W16A04 | (FWP) FDN Work | 2008-04-03 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3536 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3PF3015W58A15 | (FW PIPING) Transportation | (FW PIPING) Transportation | 2008-08-30 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3PF3015W58A15 (FW PIPING) Transportation | Activity | 3PF3015W58A15 | (FW PIPING) Transportation | 2008-08-30 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3537 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3CF3015W58A16 | (FW PIPING) Piping Work (incl. Insulation) | (FW PIPING) Piping Work (incl. Insulation) | 2008-10-15 | 2009-01-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3CF3015W58A16 (FW PIPING) Piping Work (incl. Insulation) | Activity | 3CF3015W58A16 | (FW PIPING) Piping Work (incl. Insulation) | 2008-10-15 00:00:00 | 2009-01-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3538 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3PF3015W42A07 | (FWP) Transportation | (FWP) Transportation | 2008-10-31 | 2008-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3PF3015W42A07 (FWP) Transportation | Activity | 3PF3015W42A07 | (FWP) Transportation | 2008-10-31 00:00:00 | 2008-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3539 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3CF3015W74A18 | (FWS) Installation & Test - Elec. | (FWS) Installation & Test - Elec. | 2008-12-15 | 2009-02-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3CF3015W74A18 (FWS) Installation & Test - Elec. | Activity | 3CF3015W74A18 | (FWS) Installation & Test - Elec. | 2008-12-15 00:00:00 | 2009-02-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3540 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3CF3015W90A19 | (FWS) Installation & Test - I&C | (FWS) Installation & Test - I&C | 2008-12-15 | 2009-02-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3CF3015W90A19 (FWS) Installation & Test - I&C | Activity | 3CF3015W90A19 | (FWS) Installation & Test - I&C | 2008-12-15 00:00:00 | 2009-02-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3541 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3CF3015W42A08 | (FWP) Installation | (FWP) Installation | 2008-12-15 | 2009-01-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3CF3015W42A08 (FWP) Installation | Activity | 3CF3015W42A08 | (FWP) Installation | 2008-12-15 00:00:00 | 2009-01-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3542 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3CF3015W62A17 | (FW PIPING) Hydro Test | (FW PIPING) Hydro Test | 2009-01-15 | 2009-02-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3CF3015W62A17 (FW PIPING) Hydro Test | Activity | 3CF3015W62A17 | (FW PIPING) Hydro Test | 2009-01-15 00:00:00 | 2009-02-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3543 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3SF3015W62A20 | (FWS) Loop check | (FWS) Loop check | 2009-02-15 | 2009-03-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3SF3015W62A20 (FWS) Loop check | Activity | 3SF3015W62A20 | (FWS) Loop check | 2009-02-15 00:00:00 | 2009-03-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3544 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3SF3015W62A21 | (FWS) System Function Test | (FWS) System Function Test | 2009-03-07 | 2009-03-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3SF3015W62A21 (FWS) System Function Test | Activity | 3SF3015W62A21 | (FWS) System Function Test | 2009-03-07 00:00:00 | 2009-03-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3545 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Feed Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Feed Water System |  | 3SF3015W62A22 | (FWS) Pump Operation | (FWS) Pump Operation | 2009-03-21 | 2009-03-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Feed Water System 3SF3015W62A22 (FWS) Pump Operation | Activity | 3SF3015W62A22 | (FWS) Pump Operation | 2009-03-21 00:00:00 | 2009-03-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3547 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | (Chemical Dosing BLDG) GA & Load Data to Civil Design | 2007-09-26 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3EF3045W00A06 (Chemical Dosing BLDG) GA & Load Data to Civil Design | Activity | 3EF3045W00A06 | (Chemical Dosing BLDG) GA & Load Data to Civil Design | 2007-09-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3548 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | (Chemical Dosing BLDG) FDN Design | 2007-09-26 | 2008-01-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3EF3045W16A07 (Chemical Dosing BLDG) FDN Design | Activity | 3EF3045W16A07 | (Chemical Dosing BLDG) FDN Design | 2007-09-26 00:00:00 | 2008-01-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3549 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | (Chemical Dosing BLDG) Structure Design | 2007-09-26 | 2008-01-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3EF3045W32A09 (Chemical Dosing BLDG) Structure Design | Activity | 3EF3045W32A09 | (Chemical Dosing BLDG) Structure Design | 2007-09-26 00:00:00 | 2008-01-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3550 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | (Chemical Dosing Equip) P.O & Procurement | 2007-09-26 | 2008-09-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3PF3045W42A03P (Chemical Dosing Equip) P.O & Procurement | Activity | 3PF3045W42A03P | (Chemical Dosing Equip) P.O & Procurement | 2007-09-26 00:00:00 | 2008-09-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3551 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3CF3045W16A08 | (Chemical Dosing BLDG) FDN Work | (Chemical Dosing BLDG) FDN Work | 2008-01-24 | 2008-03-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3CF3045W16A08 (Chemical Dosing BLDG) FDN Work | Activity | 3CF3045W16A08 | (Chemical Dosing BLDG) FDN Work | 2008-01-24 00:00:00 | 2008-03-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3552 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3CF3045W32A10 | (Chemical Dosing BLDG) Structure Work | (Chemical Dosing BLDG) Structure Work | 2008-03-26 | 2008-07-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3CF3045W32A10 (Chemical Dosing BLDG) Structure Work | Activity | 3CF3045W32A10 | (Chemical Dosing BLDG) Structure Work | 2008-03-26 00:00:00 | 2008-07-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3553 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3PF3045W42A04 | (Chemical Dosing Equip) Transportation | (Chemical Dosing Equip) Transportation | 2008-09-25 | 2008-11-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3PF3045W42A04 (Chemical Dosing Equip) Transportation | Activity | 3PF3045W42A04 | (Chemical Dosing Equip) Transportation | 2008-09-25 00:00:00 | 2008-11-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3554 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3CF3045W38A11 | (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3CF3045W38A11 (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | Activity | 3CF3045W38A11 | (Chemical Dosing BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3555 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3CF3045W36A12 | (Chemical Dosing BLDG) Installation & Test - HVAC | (Chemical Dosing BLDG) Installation & Test - HVAC | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3CF3045W36A12 (Chemical Dosing BLDG) Installation & Test - HVAC | Activity | 3CF3045W36A12 | (Chemical Dosing BLDG) Installation & Test - HVAC | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3556 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3CF3045W74A13 | (Chemical Dosing BLDG) Installation & Test - Elec | (Chemical Dosing BLDG) Installation & Test - Elec | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3CF3045W74A13 (Chemical Dosing BLDG) Installation & Test - Elec | Activity | 3CF3045W74A13 | (Chemical Dosing BLDG) Installation & Test - Elec | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3557 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3CF3045W24A15 | (Chemical Dosing BLDG) Building Finish | (Chemical Dosing BLDG) Building Finish | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3CF3045W24A15 (Chemical Dosing BLDG) Building Finish | Activity | 3CF3045W24A15 | (Chemical Dosing BLDG) Building Finish | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3558 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3CF3045W90A14 | (Chemical Dosing BLDG) Installation & Test - I&C | (Chemical Dosing BLDG) Installation & Test - I&C | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3CF3045W90A14 (Chemical Dosing BLDG) Installation & Test - I&C | Activity | 3CF3045W90A14 | (Chemical Dosing BLDG) Installation & Test - I&C | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3559 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3CF3045W58A16 | (Chemical Dosing System) Piping Work | (Chemical Dosing System) Piping Work | 2008-11-10 | 2009-02-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3CF3045W58A16 (Chemical Dosing System) Piping Work | Activity | 3CF3045W58A16 | (Chemical Dosing System) Piping Work | 2008-11-10 00:00:00 | 2009-02-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3560 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3CF3045W42A05 | (Chemical Dosing Equip) Installation | (Chemical Dosing Equip) Installation | 2008-11-10 | 2009-01-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3CF3045W42A05 (Chemical Dosing Equip) Installation | Activity | 3CF3045W42A05 | (Chemical Dosing Equip) Installation | 2008-11-10 00:00:00 | 2009-01-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3561 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3CF3045W74A17 | (Chemical Dosing System) Installation & Test - Elec. | (Chemical Dosing System) Installation & Test - Elec. | 2008-12-04 | 2009-02-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3CF3045W74A17 (Chemical Dosing System) Installation & Test - Elec. | Activity | 3CF3045W74A17 | (Chemical Dosing System) Installation & Test - Elec. | 2008-12-04 00:00:00 | 2009-02-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3562 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3CF3045W90A18 | (Chemical Dosing System) Installation & Test - I&C | (Chemical Dosing System) Installation & Test - I&C | 2008-12-04 | 2009-02-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3CF3045W90A18 (Chemical Dosing System) Installation & Test - I&C | Activity | 3CF3045W90A18 | (Chemical Dosing System) Installation & Test - I&C | 2008-12-04 00:00:00 | 2009-02-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3563 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3SF3045W62A19 | (Chemical Dosing System) Loop chek | (Chemical Dosing System) Loop chek | 2009-02-10 | 2009-02-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3SF3045W62A19 (Chemical Dosing System) Loop chek | Activity | 3SF3045W62A19 | (Chemical Dosing System) Loop chek | 2009-02-10 00:00:00 | 2009-02-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3564 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3SF3045W62A20 | (Chemical Dosing System) System Function Test | (Chemical Dosing System) System Function Test | 2009-02-25 | 2009-03-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3SF3045W62A20 (Chemical Dosing System) System Function Test | Activity | 3SF3045W62A20 | (Chemical Dosing System) System Function Test | 2009-02-25 00:00:00 | 2009-03-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3565 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Chemical Dosing System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Chemical Dosing System |  | 3SF3045W62A21 | (Chemical Dosing System) System Operation | (Chemical Dosing System) System Operation | 2009-03-04 | 2009-03-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Chemical Dosing System 3SF3045W62A21 (Chemical Dosing System) System Operation | Activity | 3SF3045W62A21 | (Chemical Dosing System) System Operation | 2009-03-04 00:00:00 | 2009-03-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3567 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Sampling System |  | 3PF3040W42A05P | (Sampling Equip) P.O & Procurement | (Sampling Equip) P.O & Procurement | 2007-10-01 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Sampling System 3PF3040W42A05P (Sampling Equip) P.O & Procurement | Activity | 3PF3040W42A05P | (Sampling Equip) P.O & Procurement | 2007-10-01 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3568 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Sampling System |  | 3EF3040W16A02 | (Sampling Equip) FDN Design | (Sampling Equip) FDN Design | 2008-01-01 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Sampling System 3EF3040W16A02 (Sampling Equip) FDN Design | Activity | 3EF3040W16A02 | (Sampling Equip) FDN Design | 2008-01-01 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3569 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Sampling System |  | 3CF3040W16A03 | (Sampling Equip) FDN Work | (Sampling Equip) FDN Work | 2008-04-03 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Sampling System 3CF3040W16A03 (Sampling Equip) FDN Work | Activity | 3CF3040W16A03 | (Sampling Equip) FDN Work | 2008-04-03 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3570 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Sampling System |  | 3PF3040W42A06 | (Sampling Equip) Transportation | (Sampling Equip) Transportation | 2008-10-01 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Sampling System 3PF3040W42A06 (Sampling Equip) Transportation | Activity | 3PF3040W42A06 | (Sampling Equip) Transportation | 2008-10-01 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3571 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Sampling System |  | 3CF3040W42A07 | (Sampling Equip) Installation | (Sampling Equip) Installation | 2008-11-17 | 2008-12-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Sampling System 3CF3040W42A07 (Sampling Equip) Installation | Activity | 3CF3040W42A07 | (Sampling Equip) Installation | 2008-11-17 00:00:00 | 2008-12-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3572 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Sampling System |  | 3CF3040W58A08 | (Sampling System) Piping Work | (Sampling System) Piping Work | 2008-12-17 | 2009-03-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Sampling System 3CF3040W58A08 (Sampling System) Piping Work | Activity | 3CF3040W58A08 | (Sampling System) Piping Work | 2008-12-17 00:00:00 | 2009-03-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3573 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Sampling System |  | 3CF3040W74A09 | (Sampling System) Installation & Test - Elec. | (Sampling System) Installation & Test - Elec. | 2009-02-11 | 2009-03-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Sampling System 3CF3040W74A09 (Sampling System) Installation & Test - Elec. | Activity | 3CF3040W74A09 | (Sampling System) Installation & Test - Elec. | 2009-02-11 00:00:00 | 2009-03-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3574 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Sampling System |  | 3CF3040W90A10 | (Sampling System) Installation & Test - I&C | (Sampling System) Installation & Test - I&C | 2009-02-11 | 2009-03-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Sampling System 3CF3040W90A10 (Sampling System) Installation & Test - I&C | Activity | 3CF3040W90A10 | (Sampling System) Installation & Test - I&C | 2009-02-11 00:00:00 | 2009-03-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3575 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Sampling System |  | 3SF3040W62A11 | (Sampling System) Loop chek | (Sampling System) Loop chek | 2009-03-14 | 2009-03-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Sampling System 3SF3040W62A11 (Sampling System) Loop chek | Activity | 3SF3040W62A11 | (Sampling System) Loop chek | 2009-03-14 00:00:00 | 2009-03-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3576 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Sampling System |  | 3SF3040W62A12 | (Sampling System) Chiller Function Test | (Sampling System) Chiller Function Test | 2009-03-24 | 2009-03-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Sampling System 3SF3040W62A12 (Sampling System) Chiller Function Test | Activity | 3SF3040W62A12 | (Sampling System) Chiller Function Test | 2009-03-24 00:00:00 | 2009-03-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3577 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Sampling System |  | 3SF3040W62A13 | (Sampling System) Sampling System Function Test | (Sampling System) Sampling System Function Test | 2009-03-29 | 2009-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Sampling System 3SF3040W62A13 (Sampling System) Sampling System Function Test | Activity | 3SF3040W62A13 | (Sampling System) Sampling System Function Test | 2009-03-29 00:00:00 | 2009-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3578 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Sampling System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Sampling System |  | 3SF3040W62A14 | (Sampling System) System Service | (Sampling System) System Service | 2009-04-03 | 2009-04-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Sampling System 3SF3040W62A14 (Sampling System) System Service | Activity | 3SF3040W62A14 | (Sampling System) System Service | 2009-04-03 00:00:00 | 2009-04-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3581 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3EF3020W00A15 | (COND) Condenser Design Data | (COND) Condenser Design Data | 2007-03-01 | 2007-04-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3EF3020W00A15 (COND) Condenser Design Data | Activity | 3EF3020W00A15 | (COND) Condenser Design Data | 2007-03-01 00:00:00 | 2007-04-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3582 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | (COND Air EXT Equip) P.O & Procurement | 2007-10-03 | 2008-10-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3PF3020W42A06P (COND Air EXT Equip) P.O & Procurement | Activity | 3PF3020W42A06P | (COND Air EXT Equip) P.O & Procurement | 2007-10-03 00:00:00 | 2008-10-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3583 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3PF3020W42A12P | (COND Flash Box) P.O & Procurement | (COND Flash Box) P.O & Procurement | 2007-10-03 | 2008-09-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3PF3020W42A12P (COND Flash Box) P.O & Procurement | Activity | 3PF3020W42A12P | (COND Flash Box) P.O & Procurement | 2007-10-03 00:00:00 | 2008-09-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3584 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3EF3020W16A17 | (COND) FDN Design | (COND) FDN Design | 2007-10-03 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3EF3020W16A17 (COND) FDN Design | Activity | 3EF3020W16A17 | (COND) FDN Design | 2007-10-03 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3585 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3PF3020W42A20P | (COND) P.O & Procurement | (COND) P.O & Procurement | 2007-10-03 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3PF3020W42A20P (COND) P.O & Procurement | Activity | 3PF3020W42A20P | (COND) P.O & Procurement | 2007-10-03 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3586 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3EF3020W16A09 | (COND Flash Box) FDN Design | (COND Flash Box) FDN Design | 2008-01-02 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3EF3020W16A09 (COND Flash Box) FDN Design | Activity | 3EF3020W16A09 | (COND Flash Box) FDN Design | 2008-01-02 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3587 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3CF3020W16A18 | (COND) FDN Work | (COND) FDN Work | 2008-01-31 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3CF3020W16A18 (COND) FDN Work | Activity | 3CF3020W16A18 | (COND) FDN Work | 2008-01-31 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3588 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3EF3020W16A03 | (COND Air EXT Equip) FDN Design | (COND Air EXT Equip) FDN Design | 2008-03-01 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3EF3020W16A03 (COND Air EXT Equip) FDN Design | Activity | 3EF3020W16A03 | (COND Air EXT Equip) FDN Design | 2008-03-01 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3589 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3CF3020W16A10 | (COND Flash Box) FDN Work | (COND Flash Box) FDN Work | 2008-04-01 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3CF3020W16A10 (COND Flash Box) FDN Work | Activity | 3CF3020W16A10 | (COND Flash Box) FDN Work | 2008-04-01 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3590 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3CF3020W16A04 | (COND Air EXT Equip) FDN Work | (COND Air EXT Equip) FDN Work | 2008-05-30 | 2008-07-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3CF3020W16A04 (COND Air EXT Equip) FDN Work | Activity | 3CF3020W16A04 | (COND Air EXT Equip) FDN Work | 2008-05-30 00:00:00 | 2008-07-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3591 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3PF3020W42A13T | (COND Flash Box) Transportation | (COND Flash Box) Transportation | 2008-09-02 | 2008-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3PF3020W42A13T (COND Flash Box) Transportation | Activity | 3PF3020W42A13T | (COND Flash Box) Transportation | 2008-09-02 00:00:00 | 2008-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3592 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3PF3020W42A21T | (COND) Transportation | (COND) Transportation | 2008-10-01 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3PF3020W42A21T (COND) Transportation | Activity | 3PF3020W42A21T | (COND) Transportation | 2008-10-01 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3593 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3PF3020W42A07T | (COND Air EXT Equip) Transportation | (COND Air EXT Equip) Transportation | 2008-10-14 | 2008-11-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3PF3020W42A07T (COND Air EXT Equip) Transportation | Activity | 3PF3020W42A07T | (COND Air EXT Equip) Transportation | 2008-10-14 00:00:00 | 2008-11-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3594 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3CF3020W42A14 | (COND Flash Box) Installation | (COND Flash Box) Installation | 2008-10-17 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3CF3020W42A14 (COND Flash Box) Installation | Activity | 3CF3020W42A14 | (COND Flash Box) Installation | 2008-10-17 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3595 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3CF3020W42A22 | (COND) Installation | (COND) Installation | 2008-11-15 | 2009-02-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3CF3020W42A22 (COND) Installation | Activity | 3CF3020W42A22 | (COND) Installation | 2008-11-15 00:00:00 | 2009-02-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3596 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3CF3020W58A23 | (COND System) Piping Work(incl. Insulation) | (COND System) Piping Work(incl. Insulation) | 2008-11-24 | 2009-02-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3CF3020W58A23 (COND System) Piping Work(incl. Insulation) | Activity | 3CF3020W58A23 | (COND System) Piping Work(incl. Insulation) | 2008-11-24 00:00:00 | 2009-02-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3597 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3CF3020W74A24 | (COND System) Installation & Test - Elec. | (COND System) Installation & Test - Elec. | 2008-11-24 | 2009-02-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3CF3020W74A24 (COND System) Installation & Test - Elec. | Activity | 3CF3020W74A24 | (COND System) Installation & Test - Elec. | 2008-11-24 00:00:00 | 2009-02-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3598 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3CF3020W90A25 | (COND System) Installation & Test - I&C | (COND System) Installation & Test - I&C | 2008-11-24 | 2009-02-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3CF3020W90A25 (COND System) Installation & Test - I&C | Activity | 3CF3020W90A25 | (COND System) Installation & Test - I&C | 2008-11-24 00:00:00 | 2009-02-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3599 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3CF3020W42A08 | (COND Air EXT Equip) Installation | (COND Air EXT Equip) Installation | 2008-11-28 | 2009-01-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3CF3020W42A08 (COND Air EXT Equip) Installation | Activity | 3CF3020W42A08 | (COND Air EXT Equip) Installation | 2008-11-28 00:00:00 | 2009-01-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3600 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3SF3020W62A26 | (COND System) Loop check | (COND System) Loop check | 2009-02-24 | 2009-03-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3SF3020W62A26 (COND System) Loop check | Activity | 3SF3020W62A26 | (COND System) Loop check | 2009-02-24 00:00:00 | 2009-03-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3601 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3SF3020W62A27 | (COND System) System Function Test | (COND System) System Function Test | 2009-03-11 | 2009-03-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3SF3020W62A27 (COND System) System Function Test | Activity | 3SF3020W62A27 | (COND System) System Function Test | 2009-03-11 00:00:00 | 2009-03-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3602 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser | 3SF3020W62A28 | (COND System) Pump Operation | (COND System) Pump Operation | 2009-03-21 | 2009-03-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser 3SF3020W62A28 (COND System) Pump Operation | Activity | 3SF3020W62A28 | (COND System) Pump Operation | 2009-03-21 00:00:00 | 2009-03-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3604 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser Tube Cleaning System | 3PF3020W42A02P | (CTCS) P.O & Procurement | (CTCS) P.O & Procurement | 2007-10-31 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser Tube Cleaning System 3PF3020W42A02P (CTCS) P.O & Procurement | Activity | 3PF3020W42A02P | (CTCS) P.O & Procurement | 2007-10-31 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3605 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser Tube Cleaning System | 3PF3020W42A03T | (CTCS) Transportation | (CTCS) Transportation | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser Tube Cleaning System 3PF3020W42A03T (CTCS) Transportation | Activity | 3PF3020W42A03T | (CTCS) Transportation | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3606 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condenser Tube Cleaning System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condenser Tube Cleaning System | 3CF3020W42A04 | (CTCS) Installation | (CTCS) Installation | 2008-12-16 | 2009-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condenser Tube Cleaning System 3CF3020W42A04 (CTCS) Installation | Activity | 3CF3020W42A04 | (CTCS) Installation | 2008-12-16 00:00:00 | 2009-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3608 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 3PF3020W42A04P | (CEP) P.O & Procurement | (CEP) P.O & Procurement | 2007-09-07 | 2008-10-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condensate Extraction Pump 3PF3020W42A04P (CEP) P.O & Procurement | Activity | 3PF3020W42A04P | (CEP) P.O & Procurement | 2007-09-07 00:00:00 | 2008-10-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3609 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 3EF3020W16A01 | (CEP) FDN Design | (CEP) FDN Design | 2007-10-09 | 2008-01-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condensate Extraction Pump 3EF3020W16A01 (CEP) FDN Design | Activity | 3EF3020W16A01 | (CEP) FDN Design | 2007-10-09 00:00:00 | 2008-01-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3610 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 3CF3020W16A02 | (CEP) FDN Work | (CEP) FDN Work | 2008-01-05 | 2008-05-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condensate Extraction Pump 3CF3020W16A02 (CEP) FDN Work | Activity | 3CF3020W16A02 | (CEP) FDN Work | 2008-01-05 00:00:00 | 2008-05-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3611 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 3PF3020W42A05T | (CEP) Transportation | (CEP) Transportation | 2008-10-09 | 2008-11-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condensate Extraction Pump 3PF3020W42A05T (CEP) Transportation | Activity | 3PF3020W42A05T | (CEP) Transportation | 2008-10-09 00:00:00 | 2008-11-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3612 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Condensate System > Condensate Extraction Pump | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Condensate System | Condensate Extraction Pump | 3CF3020W42A06 | (CEP) Installation | (CEP) Installation | 2008-11-24 | 2009-02-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Condensate System Condensate Extraction Pump 3CF3020W42A06 (CEP) Installation | Activity | 3CF3020W42A06 | (CEP) Installation | 2008-11-24 00:00:00 | 2009-02-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3614 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Auxiliary Cooling Water System |  | 3PF3030W42A04P | (ACW PUMP) P.O & Procurement | (ACW PUMP) P.O & Procurement | 2007-10-03 | 2008-12-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Auxiliary Cooling Water System 3PF3030W42A04P (ACW PUMP) P.O & Procurement | Activity | 3PF3030W42A04P | (ACW PUMP) P.O & Procurement | 2007-10-03 00:00:00 | 2008-12-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3615 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Auxiliary Cooling Water System |  | 3PF3030W58A10P | (ACW Piping) P.O & Procurement | (ACW Piping) P.O & Procurement | 2007-10-03 | 2008-09-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Auxiliary Cooling Water System 3PF3030W58A10P (ACW Piping) P.O & Procurement | Activity | 3PF3030W58A10P | (ACW Piping) P.O & Procurement | 2007-10-03 00:00:00 | 2008-09-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3616 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Auxiliary Cooling Water System |  | 3PF3030W58A11T | (ACW Piping) Transportation | (ACW Piping) Transportation | 2008-09-02 | 2008-10-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Auxiliary Cooling Water System 3PF3030W58A11T (ACW Piping) Transportation | Activity | 3PF3030W58A11T | (ACW Piping) Transportation | 2008-09-02 00:00:00 | 2008-10-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3617 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Auxiliary Cooling Water System |  | 3CF3030W58A12 | (ACW Piping) Piping Work | (ACW Piping) Piping Work | 2008-11-10 | 2009-02-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Auxiliary Cooling Water System 3CF3030W58A12 (ACW Piping) Piping Work | Activity | 3CF3030W58A12 | (ACW Piping) Piping Work | 2008-11-10 00:00:00 | 2009-02-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3618 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Auxiliary Cooling Water System |  | 3PF3030W42A05T | (ACW PUMP) Transportation | (ACW PUMP) Transportation | 2008-12-02 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Auxiliary Cooling Water System 3PF3030W42A05T (ACW PUMP) Transportation | Activity | 3PF3030W42A05T | (ACW PUMP) Transportation | 2008-12-02 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3619 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Auxiliary Cooling Water System |  | 3CF3030W42A06 | (ACW PUMP) Installation | (ACW PUMP) Installation | 2009-01-16 | 2009-02-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Auxiliary Cooling Water System 3CF3030W42A06 (ACW PUMP) Installation | Activity | 3CF3030W42A06 | (ACW PUMP) Installation | 2009-01-16 00:00:00 | 2009-02-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3620 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Auxiliary Cooling Water System |  | 3CF3030W74A07 | (ACW PUMP) Installation - Elec | (ACW PUMP) Installation - Elec | 2009-02-11 | 2009-03-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Auxiliary Cooling Water System 3CF3030W74A07 (ACW PUMP) Installation - Elec | Activity | 3CF3030W74A07 | (ACW PUMP) Installation - Elec | 2009-02-11 00:00:00 | 2009-03-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3621 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Auxiliary Cooling Water System |  | 3CF3030W90A08 | (ACW PUMP) Installation - I&C | (ACW PUMP) Installation - I&C | 2009-02-11 | 2009-03-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Auxiliary Cooling Water System 3CF3030W90A08 (ACW PUMP) Installation - I&C | Activity | 3CF3030W90A08 | (ACW PUMP) Installation - I&C | 2009-02-11 00:00:00 | 2009-03-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3622 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Auxiliary Cooling Water System |  | 3CF3030W62A13 | (ACW Piping) Hydro Test | (ACW Piping) Hydro Test | 2009-02-11 | 2009-03-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Auxiliary Cooling Water System 3CF3030W62A13 (ACW Piping) Hydro Test | Activity | 3CF3030W62A13 | (ACW Piping) Hydro Test | 2009-02-11 00:00:00 | 2009-03-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3623 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Auxiliary Cooling Water System |  | 3SF3030W62A14 | (ACWS) Loop check | (ACWS) Loop check | 2009-03-12 | 2009-03-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Auxiliary Cooling Water System 3SF3030W62A14 (ACWS) Loop check | Activity | 3SF3030W62A14 | (ACWS) Loop check | 2009-03-12 00:00:00 | 2009-03-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3624 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Auxiliary Cooling Water System |  | 3SF3030W62A15 | (ACWS) System Function Test | (ACWS) System Function Test | 2009-03-22 | 2009-03-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Auxiliary Cooling Water System 3SF3030W62A15 (ACWS) System Function Test | Activity | 3SF3030W62A15 | (ACWS) System Function Test | 2009-03-22 00:00:00 | 2009-03-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3625 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Auxiliary Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Auxiliary Cooling Water System |  | 3SF3030W62A16 | (ACWS) Pump Operation | (ACWS) Pump Operation | 2009-03-27 | 2009-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Auxiliary Cooling Water System 3SF3030W62A16 (ACWS) Pump Operation | Activity | 3SF3030W62A16 | (ACWS) Pump Operation | 2009-03-27 00:00:00 | 2009-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3627 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3EF2510W00A01 | (Steam System) P&ID | (Steam System) P&ID | 2007-04-02 | 2007-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3EF2510W00A01 (Steam System) P&ID | Activity | 3EF2510W00A01 | (Steam System) P&ID | 2007-04-02 00:00:00 | 2007-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3628 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3PF2510W58A08P | (Steam PIPING) P.O & Procurement | (Steam PIPING) P.O & Procurement | 2007-10-01 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3PF2510W58A08P (Steam PIPING) P.O & Procurement | Activity | 3PF2510W58A08P | (Steam PIPING) P.O & Procurement | 2007-10-01 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3629 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3PF2510W42A04P | (Silencer) P.O & Procurement | (Silencer) P.O & Procurement | 2007-10-15 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3PF2510W42A04P (Silencer) P.O & Procurement | Activity | 3PF2510W42A04P | (Silencer) P.O & Procurement | 2007-10-15 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3630 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3PF2510W58A09T | (Steam PIPING) Transportation | (Steam PIPING) Transportation | 2008-07-03 | 2008-08-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3PF2510W58A09T (Steam PIPING) Transportation | Activity | 3PF2510W58A09T | (Steam PIPING) Transportation | 2008-07-03 00:00:00 | 2008-08-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3631 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3CF2510W58A10 | (Steam PIPING) Piping Work | (Steam PIPING) Piping Work | 2008-08-18 | 2009-01-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3CF2510W58A10 (Steam PIPING) Piping Work | Activity | 3CF2510W58A10 | (Steam PIPING) Piping Work | 2008-08-18 00:00:00 | 2009-01-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3632 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3PF2510W42A05T | (Silencer) Transportation | (Silencer) Transportation | 2008-09-16 | 2008-10-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3PF2510W42A05T (Silencer) Transportation | Activity | 3PF2510W42A05T | (Silencer) Transportation | 2008-09-16 00:00:00 | 2008-10-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3633 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3CF2510W74A12 | (Steam System) Installation & Test - Elec. | (Steam System) Installation & Test - Elec. | 2008-10-31 | 2009-01-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3CF2510W74A12 (Steam System) Installation & Test - Elec. | Activity | 3CF2510W74A12 | (Steam System) Installation & Test - Elec. | 2008-10-31 00:00:00 | 2009-01-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3634 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3CF2510W90A13 | (Steam System) Installation & Test - I&C | (Steam System) Installation & Test - I&C | 2008-10-31 | 2009-01-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3CF2510W90A13 (Steam System) Installation & Test - I&C | Activity | 3CF2510W90A13 | (Steam System) Installation & Test - I&C | 2008-10-31 00:00:00 | 2009-01-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3635 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3CF2510W42A06 | (Silencer) Installation | (Silencer) Installation | 2008-10-31 | 2008-11-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3CF2510W42A06 (Silencer) Installation | Activity | 3CF2510W42A06 | (Silencer) Installation | 2008-10-31 00:00:00 | 2008-11-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3636 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3CF2510W62A11 | (Steam PIPING) Hydro Test | (Steam PIPING) Hydro Test | 2009-01-19 | 2009-02-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3CF2510W62A11 (Steam PIPING) Hydro Test | Activity | 3CF2510W62A11 | (Steam PIPING) Hydro Test | 2009-01-19 00:00:00 | 2009-02-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3637 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3SF2510W62A14 | (Steam System) Loop chek | (Steam System) Loop chek | 2009-02-19 | 2009-03-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3SF2510W62A14 (Steam System) Loop chek | Activity | 3SF2510W62A14 | (Steam System) Loop chek | 2009-02-19 00:00:00 | 2009-03-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3638 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3SF2510W62A15 | (Steam System) System Function Test | (Steam System) System Function Test | 2009-03-11 | 2009-03-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3SF2510W62A15 (Steam System) System Function Test | Activity | 3SF2510W62A15 | (Steam System) System Function Test | 2009-03-11 00:00:00 | 2009-03-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3639 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Steam System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Steam System |  | 3SF2510W62A16 | (Steam System) System Service | (Steam System) System Service | 2009-03-21 | 2009-03-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Steam System 3SF2510W62A16 (Steam System) System Service | Activity | 3SF2510W62A16 | (Steam System) System Service | 2009-03-21 00:00:00 | 2009-03-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3641 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Bypass System |  | 3EF2510W00A01.1 | (Bypass System) P&ID & System Design | (Bypass System) P&ID & System Design | 2007-04-02 | 2007-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Bypass System 3EF2510W00A01.1 (Bypass System) P&ID & System Design | Activity | 3EF2510W00A01.1 | (Bypass System) P&ID & System Design | 2007-04-02 00:00:00 | 2007-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3642 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Bypass System |  | 3PF2510W42A04.1P | (Bypass Valve) P.O & Procurement | (Bypass Valve) P.O & Procurement | 2007-08-20 | 2008-08-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Bypass System 3PF2510W42A04.1P (Bypass Valve) P.O & Procurement | Activity | 3PF2510W42A04.1P | (Bypass Valve) P.O & Procurement | 2007-08-20 00:00:00 | 2008-08-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3643 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Bypass System |  | 3PF2510W42A05.1T | (Bypass Valve) Transportation | (Bypass Valve) Transportation | 2008-08-30 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Bypass System 3PF2510W42A05.1T (Bypass Valve) Transportation | Activity | 3PF2510W42A05.1T | (Bypass Valve) Transportation | 2008-08-30 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3644 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Bypass System |  | 3CF2510W58A07.1 | (Bypass System) Piping Work | (Bypass System) Piping Work | 2008-10-15 | 2009-01-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Bypass System 3CF2510W58A07.1 (Bypass System) Piping Work | Activity | 3CF2510W58A07.1 | (Bypass System) Piping Work | 2008-10-15 00:00:00 | 2009-01-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3645 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Bypass System |  | 3CF2510W90A10.1 | (Bypass System) Installation & Test - I&C | (Bypass System) Installation & Test - I&C | 2008-10-15 | 2008-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Bypass System 3CF2510W90A10.1 (Bypass System) Installation & Test - I&C | Activity | 3CF2510W90A10.1 | (Bypass System) Installation & Test - I&C | 2008-10-15 00:00:00 | 2008-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3646 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Bypass System |  | 3CF2510W74A09.1 | (Bypass System) Installation & Test - Elec. | (Bypass System) Installation & Test - Elec. | 2008-10-15 | 2008-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Bypass System 3CF2510W74A09.1 (Bypass System) Installation & Test - Elec. | Activity | 3CF2510W74A09.1 | (Bypass System) Installation & Test - Elec. | 2008-10-15 00:00:00 | 2008-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3647 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Bypass System |  | 3CF2510W42A06.1 | (Bypass Valve) Installation | (Bypass Valve) Installation | 2008-10-15 | 2008-12-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Bypass System 3CF2510W42A06.1 (Bypass Valve) Installation | Activity | 3CF2510W42A06.1 | (Bypass Valve) Installation | 2008-10-15 00:00:00 | 2008-12-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3648 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Bypass System |  | 3CF2510W62A08.1 | (Bypass System) Hydro Test | (Bypass System) Hydro Test | 2009-01-14 | 2009-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Bypass System 3CF2510W62A08.1 (Bypass System) Hydro Test | Activity | 3CF2510W62A08.1 | (Bypass System) Hydro Test | 2009-01-14 00:00:00 | 2009-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3649 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Bypass System |  | 3SF2510W62A11.1 | (Bypass System) Loop check | (Bypass System) Loop check | 2009-01-31 | 2009-02-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Bypass System 3SF2510W62A11.1 (Bypass System) Loop check | Activity | 3SF2510W62A11.1 | (Bypass System) Loop check | 2009-01-31 00:00:00 | 2009-02-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3650 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Bypass System |  | 3SF2510W62A12.1 | (Bypass System) System Function Test | (Bypass System) System Function Test | 2009-02-14 | 2009-02-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Bypass System 3SF2510W62A12.1 (Bypass System) System Function Test | Activity | 3SF2510W62A12.1 | (Bypass System) System Function Test | 2009-02-14 00:00:00 | 2009-02-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3651 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Bypass System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Bypass System |  | 3SF2510W62A13.1 | (Bypass System) System Service | (Bypass System) System Service | 2009-02-24 | 2009-02-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Bypass System 3SF2510W62A13.1 (Bypass System) System Service | Activity | 3SF2510W62A13.1 | (Bypass System) System Service | 2009-02-24 00:00:00 | 2009-02-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3653 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | (Clean Drain System) P&ID & System Design | 2007-03-15 | 2008-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3EF3020W00A01.1 (Clean Drain System) P&ID & System Design | Activity | 3EF3020W00A01.1 | (Clean Drain System) P&ID & System Design | 2007-03-15 00:00:00 | 2008-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3654 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3PF3020W42A12.1P | (Clean Drain Tank) P.O & Procurement | (Clean Drain Tank) P.O & Procurement | 2007-10-01 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3PF3020W42A12.1P (Clean Drain Tank) P.O & Procurement | Activity | 3PF3020W42A12.1P | (Clean Drain Tank) P.O & Procurement | 2007-10-01 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3655 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3PF3020W42A06.1P | (Clean Drain Flash Vessel) P.O & Procurement | (Clean Drain Flash Vessel) P.O & Procurement | 2007-10-03 | 2008-06-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3PF3020W42A06.1P (Clean Drain Flash Vessel) P.O & Procurement | Activity | 3PF3020W42A06.1P | (Clean Drain Flash Vessel) P.O & Procurement | 2007-10-03 00:00:00 | 2008-06-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3656 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | (Clean Drain Flash Vessel) FDN Design | 2007-10-03 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3EF3020W16A03.1 (Clean Drain Flash Vessel) FDN Design | Activity | 3EF3020W16A03.1 | (Clean Drain Flash Vessel) FDN Design | 2007-10-03 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3657 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3EF3020W16A15.1 | (Clean Drain Pump) FDN Design | (Clean Drain Pump) FDN Design | 2007-10-03 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3EF3020W16A15.1 (Clean Drain Pump) FDN Design | Activity | 3EF3020W16A15.1 | (Clean Drain Pump) FDN Design | 2007-10-03 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3658 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3PF3020W42A18.1P | (Clean Drain Pump) P.O & Procurement | (Clean Drain Pump) P.O & Procurement | 2007-10-03 | 2008-09-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3PF3020W42A18.1P (Clean Drain Pump) P.O & Procurement | Activity | 3PF3020W42A18.1P | (Clean Drain Pump) P.O & Procurement | 2007-10-03 00:00:00 | 2008-09-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3659 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3EF3020W16A09.1 | (Clean Drain Tank) FDN Design | (Clean Drain Tank) FDN Design | 2007-12-06 | 2008-05-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3EF3020W16A09.1 (Clean Drain Tank) FDN Design | Activity | 3EF3020W16A09.1 | (Clean Drain Tank) FDN Design | 2007-12-06 00:00:00 | 2008-05-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3660 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3CF3020W16A04.1 | (Clean Drain Flash Vessel) FDN Work | (Clean Drain Flash Vessel) FDN Work | 2008-03-01 | 2008-04-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3CF3020W16A04.1 (Clean Drain Flash Vessel) FDN Work | Activity | 3CF3020W16A04.1 | (Clean Drain Flash Vessel) FDN Work | 2008-03-01 00:00:00 | 2008-04-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3661 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3CF3020W16A16.1 | (Clean Drain Pump) FDN Work | (Clean Drain Pump) FDN Work | 2008-03-01 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3CF3020W16A16.1 (Clean Drain Pump) FDN Work | Activity | 3CF3020W16A16.1 | (Clean Drain Pump) FDN Work | 2008-03-01 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3662 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3CF3020W16A10.1 | (Clean Drain Tank) FDN Work | (Clean Drain Tank) FDN Work | 2008-05-06 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3CF3020W16A10.1 (Clean Drain Tank) FDN Work | Activity | 3CF3020W16A10.1 | (Clean Drain Tank) FDN Work | 2008-05-06 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3663 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3PF3020W42A07.1T | (Clean Drain Flash Vessel) Transportation | (Clean Drain Flash Vessel) Transportation | 2008-06-04 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3PF3020W42A07.1T (Clean Drain Flash Vessel) Transportation | Activity | 3PF3020W42A07.1T | (Clean Drain Flash Vessel) Transportation | 2008-06-04 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3664 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3CF3020W42A08.1 | (Clean Drain Flash Vessel) Installation | (Clean Drain Flash Vessel) Installation | 2008-07-19 | 2008-08-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3CF3020W42A08.1 (Clean Drain Flash Vessel) Installation | Activity | 3CF3020W42A08.1 | (Clean Drain Flash Vessel) Installation | 2008-07-19 00:00:00 | 2008-08-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3665 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3PF3020W42A19.1T | (Clean Drain Pump) Transportation | (Clean Drain Pump) Transportation | 2008-09-18 | 2008-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3PF3020W42A19.1T (Clean Drain Pump) Transportation | Activity | 3PF3020W42A19.1T | (Clean Drain Pump) Transportation | 2008-09-18 00:00:00 | 2008-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3666 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3PF3020W42A13.1T | (Clean Drain Tank) Transportation | (Clean Drain Tank) Transportation | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3PF3020W42A13.1T (Clean Drain Tank) Transportation | Activity | 3PF3020W42A13.1T | (Clean Drain Tank) Transportation | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3667 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3CF3020W42A20.1 | (Clean Drain Pump) Installation | (Clean Drain Pump) Installation | 2008-11-03 | 2008-11-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3CF3020W42A20.1 (Clean Drain Pump) Installation | Activity | 3CF3020W42A20.1 | (Clean Drain Pump) Installation | 2008-11-03 00:00:00 | 2008-11-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3668 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3CF3020W58A21.1 | (Clean Drain System) Piping Work | (Clean Drain System) Piping Work | 2008-12-16 | 2009-03-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3CF3020W58A21.1 (Clean Drain System) Piping Work | Activity | 3CF3020W58A21.1 | (Clean Drain System) Piping Work | 2008-12-16 00:00:00 | 2009-03-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3669 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3CF3020W42A14.1 | (Clean Drain Tank) Installation | (Clean Drain Tank) Installation | 2008-12-16 | 2009-01-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3CF3020W42A14.1 (Clean Drain Tank) Installation | Activity | 3CF3020W42A14.1 | (Clean Drain Tank) Installation | 2008-12-16 00:00:00 | 2009-01-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3670 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3CF3020W74A23.1 | (Clean Drain System) Installation & Test - Elec. | (Clean Drain System) Installation & Test - Elec. | 2009-02-16 | 2009-03-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3CF3020W74A23.1 (Clean Drain System) Installation & Test - Elec. | Activity | 3CF3020W74A23.1 | (Clean Drain System) Installation & Test - Elec. | 2009-02-16 00:00:00 | 2009-03-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3671 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3CF3020W90A24.1 | (Clean Drain System) Installation & Test - I&C | (Clean Drain System) Installation & Test - I&C | 2009-02-16 | 2009-03-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3CF3020W90A24.1 (Clean Drain System) Installation & Test - I&C | Activity | 3CF3020W90A24.1 | (Clean Drain System) Installation & Test - I&C | 2009-02-16 00:00:00 | 2009-03-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3672 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3CF3020W62A22.1 | (Clean Drain System) Hydro Test | (Clean Drain System) Hydro Test | 2009-03-19 | 2009-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3CF3020W62A22.1 (Clean Drain System) Hydro Test | Activity | 3CF3020W62A22.1 | (Clean Drain System) Hydro Test | 2009-03-19 00:00:00 | 2009-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3673 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3SF3020W62A25.1 | (Clean Drain System) Loop chek | (Clean Drain System) Loop chek | 2009-04-17 | 2009-05-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3SF3020W62A25.1 (Clean Drain System) Loop chek | Activity | 3SF3020W62A25.1 | (Clean Drain System) Loop chek | 2009-04-17 00:00:00 | 2009-05-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3674 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3SF3020W62A26.1 | (Clean Drain System) System Function Test | (Clean Drain System) System Function Test | 2009-05-07 | 2009-05-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3SF3020W62A26.1 (Clean Drain System) System Function Test | Activity | 3SF3020W62A26.1 | (Clean Drain System) System Function Test | 2009-05-07 00:00:00 | 2009-05-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3675 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Combined Power Block Common > Clean Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Combined Power Block Common | Clean Drain System |  | 3SF3020W62A27.1 | (Clean Drain System) System Service | (Clean Drain System) System Service | 2009-05-10 | 2009-05-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Combined Power Block Common Clean Drain System 3SF3020W62A27.1 (Clean Drain System) System Service | Activity | 3SF3020W62A27.1 | (Clean Drain System) System Service | 2009-05-10 00:00:00 | 2009-05-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3678 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Gas Supply System (GTG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Gas Supply System (GTG) |  | 3CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | (Gas Supply System) Piping Work(Yard area) | 2008-07-19 | 2008-09-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Gas Supply System (GTG) 3CF3520W58A01 (Gas Supply System) Piping Work(Yard area) | Activity | 3CF3520W58A01 | (Gas Supply System) Piping Work(Yard area) | 2008-07-19 00:00:00 | 2008-09-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3680 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Oil Supply System (GTG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Oil Supply System (GTG) |  | 3CF3520W58A01.1 | (Oil Supply System) Piping Work(Yard area) | (Oil Supply System) Piping Work(Yard area) | 2008-03-03 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Oil Supply System (GTG) 3CF3520W58A01.1 (Oil Supply System) Piping Work(Yard area) | Activity | 3CF3520W58A01.1 | (Oil Supply System) Piping Work(Yard area) | 2008-03-03 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3681 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Oil Supply System (GTG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Oil Supply System (GTG) |  | 3CF3520W62A02 | (Oil Supply System) Hydro Test | (Oil Supply System) Hydro Test | 2008-05-03 | 2008-05-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Oil Supply System (GTG) 3CF3520W62A02 (Oil Supply System) Hydro Test | Activity | 3CF3520W62A02 | (Oil Supply System) Hydro Test | 2008-05-03 00:00:00 | 2008-05-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3683 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Make Up Wate Supply System (STG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Make Up Wate Supply System (STG) |  | 3CF3010W58A01 | (Make Up WTR Supply System) Piping Work(Block #3) | (Make Up WTR Supply System) Piping Work(Block #3) | 2008-05-19 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Make Up Wate Supply System (STG) 3CF3010W58A01 (Make Up WTR Supply System) Piping Work(Block #3) | Activity | 3CF3010W58A01 | (Make Up WTR Supply System) Piping Work(Block #3) | 2008-05-19 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3684 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Make Up Wate Supply System (STG) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Make Up Wate Supply System (STG) |  | 3CF3010W62A02 | (Make Up WTR Supply System) Hydro Test(Block #3) | (Make Up WTR Supply System) Hydro Test(Block #3) | 2008-07-19 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Make Up Wate Supply System (STG) 3CF3010W62A02 (Make Up WTR Supply System) Hydro Test(Block #3) | Activity | 3CF3010W62A02 | (Make Up WTR Supply System) Hydro Test(Block #3) | 2008-07-19 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3686 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Water Treatment Sytstem (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Water Treatment Sytstem (BOP) |  | 3CF3010W58A01.1 | (Water Treatment System) Piping Work(Block #3) | (Water Treatment System) Piping Work(Block #3) | 2008-10-17 | 2008-12-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Water Treatment Sytstem (BOP) 3CF3010W58A01.1 (Water Treatment System) Piping Work(Block #3) | Activity | 3CF3010W58A01.1 | (Water Treatment System) Piping Work(Block #3) | 2008-10-17 00:00:00 | 2008-12-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3687 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Water Treatment Sytstem (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Water Treatment Sytstem (BOP) |  | 3CF3010W62A02.1 | (Water Treatment System) Hydro Test(Block #3) | (Water Treatment System) Hydro Test(Block #3) | 2008-12-17 | 2009-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Water Treatment Sytstem (BOP) 3CF3010W62A02.1 (Water Treatment System) Hydro Test(Block #3) | Activity | 3CF3010W62A02.1 | (Water Treatment System) Hydro Test(Block #3) | 2008-12-17 00:00:00 | 2009-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3689 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Service Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Service Water System (BOP) |  | 3CF3035W58A01 | (SWS) Piping Work(Block #3) | (SWS) Piping Work(Block #3) | 2008-10-17 | 2008-12-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Service Water System (BOP) 3CF3035W58A01 (SWS) Piping Work(Block #3) | Activity | 3CF3035W58A01 | (SWS) Piping Work(Block #3) | 2008-10-17 00:00:00 | 2008-12-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3690 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Service Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Service Water System (BOP) |  | 3CF3035W62A02 | (SWS) Hydro Test(Block #3) | (SWS) Hydro Test(Block #3) | 2008-12-17 | 2009-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Service Water System (BOP) 3CF3035W62A02 (SWS) Hydro Test(Block #3) | Activity | 3CF3035W62A02 | (SWS) Hydro Test(Block #3) | 2008-12-17 00:00:00 | 2009-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3692 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Potable Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Potable Water System (BOP) |  | 3CF3035W58A01.1 | (PWS) Piping Work(Block #3) | (PWS) Piping Work(Block #3) | 2008-11-04 | 2009-01-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Potable Water System (BOP) 3CF3035W58A01.1 (PWS) Piping Work(Block #3) | Activity | 3CF3035W58A01.1 | (PWS) Piping Work(Block #3) | 2008-11-04 00:00:00 | 2009-01-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3693 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Potable Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Potable Water System (BOP) |  | 3CF3035W62A02.1 | (PWS) Hydro Test(Block #3) | (PWS) Hydro Test(Block #3) | 2009-01-03 | 2009-01-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Potable Water System (BOP) 3CF3035W62A02.1 (PWS) Hydro Test(Block #3) | Activity | 3CF3035W62A02.1 | (PWS) Hydro Test(Block #3) | 2009-01-03 00:00:00 | 2009-01-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3695 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Compressed Air System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Compressed Air System (BOP) |  | 3CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_(Block #3) | (COMP Air System) Piping Work(incl. Air blowing)_(Block #3) | 2008-09-02 | 2008-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Compressed Air System (BOP) 3CF3510W58A01 (COMP Air System) Piping Work(incl. Air blowing)_(Block #3) | Activity | 3CF3510W58A01 | (COMP Air System) Piping Work(incl. Air blowing)_(Block #3) | 2008-09-02 00:00:00 | 2008-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3697 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Waste Water Treatment System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Waste Water Treatment System (BOP) |  | 3CF4035W58A01.1 | (WWTS) Piping Work(Block #3) | (WWTS) Piping Work(Block #3) | 2008-10-17 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Waste Water Treatment System (BOP) 3CF4035W58A01.1 (WWTS) Piping Work(Block #3) | Activity | 3CF4035W58A01.1 | (WWTS) Piping Work(Block #3) | 2008-10-17 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3698 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Waste Water Treatment System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Waste Water Treatment System (BOP) |  | 3CF4035W62A02.1 | (WWTS) Hydro Test(Block #3) | (WWTS) Hydro Test(Block #3) | 2009-01-16 | 2009-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Waste Water Treatment System (BOP) 3CF4035W62A02.1 (WWTS) Hydro Test(Block #3) | Activity | 3CF4035W62A02.1 | (WWTS) Hydro Test(Block #3) | 2009-01-16 00:00:00 | 2009-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3700 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Sewage Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Sewage Water System (BOP) |  | 3CF4035W58A01 | (STS) Piping Work(Block #3) | (STS) Piping Work(Block #3) | 2008-10-17 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Sewage Water System (BOP) 3CF4035W58A01 (STS) Piping Work(Block #3) | Activity | 3CF4035W58A01 | (STS) Piping Work(Block #3) | 2008-10-17 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3701 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Sewage Water System (BOP) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Sewage Water System (BOP) |  | 3CF4035W62A02 | (STS) Hydro Test(Block #3) | (STS) Hydro Test(Block #3) | 2009-01-16 | 2009-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Sewage Water System (BOP) 3CF4035W62A02 (STS) Hydro Test(Block #3) | Activity | 3CF4035W62A02 | (STS) Hydro Test(Block #3) | 2009-01-16 00:00:00 | 2009-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3703 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > U/G Line | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | U/G Line |  | 3CF4035W22A01 | (STRS) Piping Work(Block #3) | (STRS) Piping Work(Block #3) | 2008-10-17 | 2009-01-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common U/G Line 3CF4035W22A01 (STRS) Piping Work(Block #3) | Activity | 3CF4035W22A01 | (STRS) Piping Work(Block #3) | 2008-10-17 00:00:00 | 2009-01-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3704 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > U/G Line | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | U/G Line |  | 3CF4035W22A02 | (SWS) Piping Work(Block #3) | (SWS) Piping Work(Block #3) | 2008-10-17 | 2009-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common U/G Line 3CF4035W22A02 (SWS) Piping Work(Block #3) | Activity | 3CF4035W22A02 | (SWS) Piping Work(Block #3) | 2008-10-17 00:00:00 | 2009-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3706 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Pipe Rack |  | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | (PipeRack) Pipe Rack Key Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Pipe Rack 3EF5550W00A01 (PipeRack) Pipe Rack Key Data | Activity | 3EF5550W00A01 | (PipeRack) Pipe Rack Key Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3707 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Pipe Rack |  | 3EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | (PipeRack) GA & Load Data to Civil Design | 2007-03-30 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Pipe Rack 3EF5550W00A02 (PipeRack) GA & Load Data to Civil Design | Activity | 3EF5550W00A02 | (PipeRack) GA & Load Data to Civil Design | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3708 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Pipe Rack |  | 3EF5550W20A05 | (PipeRack) Structure Design | (PipeRack) Structure Design | 2007-05-30 | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Pipe Rack 3EF5550W20A05 (PipeRack) Structure Design | Activity | 3EF5550W20A05 | (PipeRack) Structure Design | 2007-05-30 00:00:00 | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3709 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Pipe Rack |  | 3EF5550W16A03 | (PipeRack) FDN Design | (PipeRack) FDN Design | 2007-05-30 | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Pipe Rack 3EF5550W16A03 (PipeRack) FDN Design | Activity | 3EF5550W16A03 | (PipeRack) FDN Design | 2007-05-30 00:00:00 | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3710 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Pipe Rack |  | 3PF5550W46A08P | (PipeRack) P.O & Procurement | (PipeRack) P.O & Procurement | 2007-06-28 | 2008-03-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Pipe Rack 3PF5550W46A08P (PipeRack) P.O & Procurement | Activity | 3PF5550W46A08P | (PipeRack) P.O & Procurement | 2007-06-28 00:00:00 | 2008-03-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3711 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Pipe Rack |  | 3CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | (PipeRack) FDN Work Block #1 Area | 2007-09-01 | 2008-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Pipe Rack 3CF5550W16A04 (PipeRack) FDN Work Block #1 Area | Activity | 3CF5550W16A04 | (PipeRack) FDN Work Block #1 Area | 2007-09-01 00:00:00 | 2008-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3712 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Pipe Rack |  | 3PF5550W46A09T | (PipeRack) Trasnportation | (PipeRack) Trasnportation | 2008-03-05 | 2008-04-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Pipe Rack 3PF5550W46A09T (PipeRack) Trasnportation | Activity | 3PF5550W46A09T | (PipeRack) Trasnportation | 2008-03-05 00:00:00 | 2008-04-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3713 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > BOP Piping for Block #3 Common > Pipe Rack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | BOP Piping for Block #3 Common | Pipe Rack |  | 3CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | (PipeRack) Structure Work for Block #1 Area | 2008-04-19 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 BOP Piping for Block #3 Common Pipe Rack 3CF5550W46A06 (PipeRack) Structure Work for Block #1 Area | Activity | 3CF5550W46A06 | (PipeRack) Structure Work for Block #1 Area | 2008-04-19 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3716 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3EF1200W00A01 | (GTG #31/#32) GTG Process Data (FG, FO, CCW) | (GTG #31/#32) GTG Process Data (FG, FO, CCW) | 2007-03-01 | 2007-03-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3EF1200W00A01 (GTG #31/#32) GTG Process Data (FG, FO, CCW) | Activity | 3EF1200W00A01 | (GTG #31/#32) GTG Process Data (FG, FO, CCW) | 2007-03-01 00:00:00 | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3717 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3EF1200W00A02 | (GTG #31/#32) Instrument, Service Air, Aux steam Data | (GTG #31/#32) Instrument, Service Air, Aux steam Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3EF1200W00A02 (GTG #31/#32) Instrument, Service Air, Aux steam Data | Activity | 3EF1200W00A02 | (GTG #31/#32) Instrument, Service Air, Aux steam Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3718 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3EF1200W00A03 | (GTG #31/#32) Utility Consumption Data | (GTG #31/#32) Utility Consumption Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3EF1200W00A03 (GTG #31/#32) Utility Consumption Data | Activity | 3EF1200W00A03 | (GTG #31/#32) Utility Consumption Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3719 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3EF1200W00A04 | (GTG #31/#32) Emergency Load Data | (GTG #31/#32) Emergency Load Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3EF1200W00A04 (GTG #31/#32) Emergency Load Data | Activity | 3EF1200W00A04 | (GTG #31/#32) Emergency Load Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3720 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3EF1200W00A05 | (GTG #31/#32) Black Start Load Data | (GTG #31/#32) Black Start Load Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3EF1200W00A05 (GTG #31/#32) Black Start Load Data | Activity | 3EF1200W00A05 | (GTG #31/#32) Black Start Load Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3721 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | (GTG Common BLDG) GA & Load Data to Civil Design | 2007-03-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3EF1210W00A06 (GTG Common BLDG) GA & Load Data to Civil Design | Activity | 3EF1210W00A06 | (GTG Common BLDG) GA & Load Data to Civil Design | 2007-03-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3722 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3EF1210W16A07 | (GTG Common BLDG) FDN Design | (GTG Common BLDG) FDN Design | 2007-03-01 | 2007-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3EF1210W16A07 (GTG Common BLDG) FDN Design | Activity | 3EF1210W16A07 | (GTG Common BLDG) FDN Design | 2007-03-01 00:00:00 | 2007-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3723 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3EF1210W20A09 | (GTG Common BLDG) Structure Design | (GTG Common BLDG) Structure Design | 2007-03-01 | 2007-08-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3EF1210W20A09 (GTG Common BLDG) Structure Design | Activity | 3EF1210W20A09 | (GTG Common BLDG) Structure Design | 2007-03-01 00:00:00 | 2007-08-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3724 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | (GTG Common BLDG) P.O & Procurement(Steel Structure) | 2007-09-03 | 2008-03-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3PF1210W20A09P (GTG Common BLDG) P.O & Procurement(Steel Structure) | Activity | 3PF1210W20A09P | (GTG Common BLDG) P.O & Procurement(Steel Structure) | 2007-09-03 00:00:00 | 2008-03-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3725 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3CF1210W16A08 | (GTG Common BLDG) FDN Work | (GTG Common BLDG) FDN Work | 2007-11-01 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3CF1210W16A08 (GTG Common BLDG) FDN Work | Activity | 3CF1210W16A08 | (GTG Common BLDG) FDN Work | 2007-11-01 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3726 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | 2008-03-18 | 2008-07-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3CF1210W20A10 (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | Activity | 3CF1210W20A10 | (GTG Common BLDG) Structure Work(S/S, Cladding, Roof) | 2008-03-18 00:00:00 | 2008-07-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3727 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3CF1210W36A12 | (GTG Common BLDG) Installation & Test - HVAC | (GTG Common BLDG) Installation & Test - HVAC | 2008-05-15 | 2008-07-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3CF1210W36A12 (GTG Common BLDG) Installation & Test - HVAC | Activity | 3CF1210W36A12 | (GTG Common BLDG) Installation & Test - HVAC | 2008-05-15 00:00:00 | 2008-07-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3728 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3CF1210W38A11 | (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3CF1210W38A11 (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | Activity | 3CF1210W38A11 | (GTG Common BLDG) Installation & Test - Fire Fighting Sys. | 2008-05-31 00:00:00 | 2008-07-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3729 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3CF1210W90A14 | (GTG Common BLDG) Installation & Test - I&C | (GTG Common BLDG) Installation & Test - I&C | 2008-07-21 | 2008-09-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3CF1210W90A14 (GTG Common BLDG) Installation & Test - I&C | Activity | 3CF1210W90A14 | (GTG Common BLDG) Installation & Test - I&C | 2008-07-21 00:00:00 | 2008-09-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3730 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3CF1210W74A13 | (GTG Common BLDG) Installation & Test - Elec | (GTG Common BLDG) Installation & Test - Elec | 2008-07-21 | 2008-09-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3CF1210W74A13 (GTG Common BLDG) Installation & Test - Elec | Activity | 3CF1210W74A13 | (GTG Common BLDG) Installation & Test - Elec | 2008-07-21 00:00:00 | 2008-09-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3731 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG Common |  | 3CF1210W24A15 | (GTG Common BLDG) Building Finish | (GTG Common BLDG) Building Finish | 2008-07-26 | 2008-09-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG Common 3CF1210W24A15 (GTG Common BLDG) Building Finish | Activity | 3CF1210W24A15 | (GTG Common BLDG) Building Finish | 2008-07-26 00:00:00 | 2008-09-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3733 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 LEB |  | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | (GTG #31 LEB) GA & Load Data to Civil Design | 2007-05-31 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 LEB 3EF1200W00A01.1 (GTG #31 LEB) GA & Load Data to Civil Design | Activity | 3EF1200W00A01.1 | (GTG #31 LEB) GA & Load Data to Civil Design | 2007-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3734 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 LEB |  | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | (GTG #31 LEB) FDN Design | 2007-08-01 | 2007-11-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 LEB 3EF1200W16A02 (GTG #31 LEB) FDN Design | Activity | 3EF1200W16A02 | (GTG #31 LEB) FDN Design | 2007-08-01 00:00:00 | 2007-11-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3735 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 LEB |  | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | (GTG #31 LEB) Structure Design | 2007-08-01 | 2007-11-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 LEB 3EF1200W32A04 (GTG #31 LEB) Structure Design | Activity | 3EF1200W32A04 | (GTG #31 LEB) Structure Design | 2007-08-01 00:00:00 | 2007-11-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3736 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 LEB |  | 3CF1200W16A03 | (GTG #31 LEB) FDN Work | (GTG #31 LEB) FDN Work | 2007-11-28 | 2008-01-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 LEB 3CF1200W16A03 (GTG #31 LEB) FDN Work | Activity | 3CF1200W16A03 | (GTG #31 LEB) FDN Work | 2007-11-28 00:00:00 | 2008-01-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3737 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 LEB |  | 3CF1200W32A05 | (GTG #31 LEB) Structure Work | (GTG #31 LEB) Structure Work | 2008-01-25 | 2008-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 LEB 3CF1200W32A05 (GTG #31 LEB) Structure Work | Activity | 3CF1200W32A05 | (GTG #31 LEB) Structure Work | 2008-01-25 00:00:00 | 2008-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3738 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 LEB |  | 3CF1200W36A07 | (GTG #31 LEB) Installation & Test - HVAC | (GTG #31 LEB) Installation & Test - HVAC | 2008-05-15 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 LEB 3CF1200W36A07 (GTG #31 LEB) Installation & Test - HVAC | Activity | 3CF1200W36A07 | (GTG #31 LEB) Installation & Test - HVAC | 2008-05-15 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3739 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 LEB |  | 3CF1200W24A10 | (GTG #31 LEB) Building Finish | (GTG #31 LEB) Building Finish | 2008-05-27 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 LEB 3CF1200W24A10 (GTG #31 LEB) Building Finish | Activity | 3CF1200W24A10 | (GTG #31 LEB) Building Finish | 2008-05-27 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3740 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 LEB |  | 3CF1200W38A06 | (GTG #31 LEB) Installation & Test - Fire Fighting Sys. | (GTG #31 LEB) Installation & Test - Fire Fighting Sys. | 2008-05-31 | 2008-07-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 LEB 3CF1200W38A06 (GTG #31 LEB) Installation & Test - Fire Fighting Sys. | Activity | 3CF1200W38A06 | (GTG #31 LEB) Installation & Test - Fire Fighting Sys. | 2008-05-31 00:00:00 | 2008-07-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3741 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 LEB |  | 3CF1200W90A09 | (GTG #31 LEB) Installation & Test - I&C | (GTG #31 LEB) Installation & Test - I&C | 2008-06-04 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 LEB 3CF1200W90A09 (GTG #31 LEB) Installation & Test - I&C | Activity | 3CF1200W90A09 | (GTG #31 LEB) Installation & Test - I&C | 2008-06-04 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3742 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 LEB |  | 3CF1200W74A08 | (GTG #31 LEB) Installation & Test - Elec | (GTG #31 LEB) Installation & Test - Elec | 2008-06-04 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 LEB 3CF1200W74A08 (GTG #31 LEB) Installation & Test - Elec | Activity | 3CF1200W74A08 | (GTG #31 LEB) Installation & Test - Elec | 2008-06-04 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3745 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Main body | 3PF1213W42A08P | (GEN #31) P.O & Procurement | (GEN #31) P.O & Procurement | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Main body 3PF1213W42A08P (GEN #31) P.O & Procurement | Activity | 3PF1213W42A08P | (GEN #31) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3746 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Main body | 3EF1213W16A06 | (GEN #31) FDN Design | (GEN #31) FDN Design | 2007-04-30 | 2007-09-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Main body 3EF1213W16A06 (GEN #31) FDN Design | Activity | 3EF1213W16A06 | (GEN #31) FDN Design | 2007-04-30 00:00:00 | 2007-09-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3747 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Main body | 3PF1213W42A03P | (GT #31) P.O & Procurement | (GT #31) P.O & Procurement | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Main body 3PF1213W42A03P (GT #31) P.O & Procurement | Activity | 3PF1213W42A03P | (GT #31) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3748 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Main body | 3EF1213W16A01 | (GT #31) FDN Design | (GT #31) FDN Design | 2007-04-30 | 2007-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Main body 3EF1213W16A01 (GT #31) FDN Design | Activity | 3EF1213W16A01 | (GT #31) FDN Design | 2007-04-30 00:00:00 | 2007-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3749 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Main body | 3CF1213W16A07 | (GEN #31) FDN Work | (GEN #31) FDN Work | 2007-10-01 | 2008-02-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Main body 3CF1213W16A07 (GEN #31) FDN Work | Activity | 3CF1213W16A07 | (GEN #31) FDN Work | 2007-10-01 00:00:00 | 2008-02-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3750 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Main body | 3CF1213W16A02 | (GT #31) FDN Work | (GT #31) FDN Work | 2007-10-01 | 2008-02-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Main body 3CF1213W16A02 (GT #31) FDN Work | Activity | 3CF1213W16A02 | (GT #31) FDN Work | 2007-10-01 00:00:00 | 2008-02-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3751 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Main body | 3PF1213W42A09T | (GEN #31) Transportation | (GEN #31) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Main body 3PF1213W42A09T (GEN #31) Transportation | Activity | 3PF1213W42A09T | (GEN #31) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3752 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Main body | 3PF1213W42A04T | (GT #31) Transportation | (GT #31) Transportation | 2008-04-01 | 2008-05-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Main body 3PF1213W42A04T (GT #31) Transportation | Activity | 3PF1213W42A04T | (GT #31) Transportation | 2008-04-01 00:00:00 | 2008-05-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3753 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Main body | 3CF1213W42A05 | (GT #31) Installation(On FDN~Final Alignment) | (GT #31) Installation(On FDN~Final Alignment) | 2008-05-15 | 2008-09-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Main body 3CF1213W42A05 (GT #31) Installation(On FDN~Final Alignment) | Activity | 3CF1213W42A05 | (GT #31) Installation(On FDN~Final Alignment) | 2008-05-15 00:00:00 | 2008-09-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3754 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Main body | 3CF1213W42A10 | (GEN #31) Installation | (GEN #31) Installation | 2008-06-27 | 2008-10-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Main body 3CF1213W42A10 (GEN #31) Installation | Activity | 3CF1213W42A10 | (GEN #31) Installation | 2008-06-27 00:00:00 | 2008-10-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3755 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Main body | 3CF1213W52A11 | (GEN #31) Insulation | (GEN #31) Insulation | 2008-07-17 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Main body 3CF1213W52A11 (GEN #31) Insulation | Activity | 3CF1213W52A11 | (GEN #31) Insulation | 2008-07-17 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3757 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Electrical System | 3PF1255W70A01P | (GTG#31 Electrical) P.O & Procurement | (GTG#31 Electrical) P.O & Procurement | 2007-04-30 | 2008-05-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Electrical System 3PF1255W70A01P (GTG#31 Electrical) P.O & Procurement | Activity | 3PF1255W70A01P | (GTG#31 Electrical) P.O & Procurement | 2007-04-30 00:00:00 | 2008-05-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3758 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Electrical System | 3PF1255W70A02T | (GTG#31 Electrical) Transportation | (GTG#31 Electrical) Transportation | 2008-05-29 | 2008-07-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Electrical System 3PF1255W70A02T (GTG#31 Electrical) Transportation | Activity | 3PF1255W70A02T | (GTG#31 Electrical) Transportation | 2008-05-29 00:00:00 | 2008-07-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3759 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Electrical System | 3CF1255W70A03 | (GTG#31 Electrical) Installation- PCC | (GTG#31 Electrical) Installation- PCC | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Electrical System 3CF1255W70A03 (GTG#31 Electrical) Installation- PCC | Activity | 3CF1255W70A03 | (GTG#31 Electrical) Installation- PCC | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3760 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Electrical System | 3CF1255W70A04 | (GTG#31 Electrical) Installation- MCC | (GTG#31 Electrical) Installation- MCC | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Electrical System 3CF1255W70A04 (GTG#31 Electrical) Installation- MCC | Activity | 3CF1255W70A04 | (GTG#31 Electrical) Installation- MCC | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3761 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Electrical System | 3CF1255W70A05 | (GTG#31 Electrical) Installation- Protection Sys. | (GTG#31 Electrical) Installation- Protection Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Electrical System 3CF1255W70A05 (GTG#31 Electrical) Installation- Protection Sys. | Activity | 3CF1255W70A05 | (GTG#31 Electrical) Installation- Protection Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3762 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Electrical System | 3CF1255W70A07 | (GTG#31 Electrical) Installation- SEE&SFC Sys. | (GTG#31 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Electrical System 3CF1255W70A07 (GTG#31 Electrical) Installation- SEE&SFC Sys. | Activity | 3CF1255W70A07 | (GTG#31 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3763 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Electrical System | 3CF1255W70A08 | (GTG#31 Electrical) Installation- DC&UPS Sys. | (GTG#31 Electrical) Installation- DC&UPS Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Electrical System 3CF1255W70A08 (GTG#31 Electrical) Installation- DC&UPS Sys. | Activity | 3CF1255W70A08 | (GTG#31 Electrical) Installation- DC&UPS Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3764 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Electrical System | 3CF1255W74A09 | (GTG#31 Electrical) Cable work | (GTG#31 Electrical) Cable work | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Electrical System 3CF1255W74A09 (GTG#31 Electrical) Cable work | Activity | 3CF1255W74A09 | (GTG#31 Electrical) Cable work | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3765 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Electrical System | 3CF1255W86A06 | (GTG#31 Electrical) Installation- GT control Sys. | (GTG#31 Electrical) Installation- GT control Sys. | 2008-08-04 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Electrical System 3CF1255W86A06 (GTG#31 Electrical) Installation- GT control Sys. | Activity | 3CF1255W86A06 | (GTG#31 Electrical) Installation- GT control Sys. | 2008-08-04 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3766 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Electrical System | 3CF1255W62A10 | (GTG#31 Electrical) Electrical Function Test | (GTG#31 Electrical) Electrical Function Test | 2008-09-16 | 2008-09-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Electrical System 3CF1255W62A10 (GTG#31 Electrical) Electrical Function Test | Activity | 3CF1255W62A10 | (GTG#31 Electrical) Electrical Function Test | 2008-09-16 00:00:00 | 2008-09-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3767 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Electrical System | 3CF1255W62A11 | (GTG#31 Electrical) Loop Test | (GTG#31 Electrical) Loop Test | 2008-09-22 | 2008-09-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Electrical System 3CF1255W62A11 (GTG#31 Electrical) Loop Test | Activity | 3CF1255W62A11 | (GTG#31 Electrical) Loop Test | 2008-09-22 00:00:00 | 2008-09-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3769 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Starting System(Turning Device) | 3PF1265W42A01P | (Turning Gear) P.O & Procurement | (Turning Gear) P.O & Procurement | 2007-04-30 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Starting System(Turning Device) 3PF1265W42A01P (Turning Gear) P.O & Procurement | Activity | 3PF1265W42A01P | (Turning Gear) P.O & Procurement | 2007-04-30 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3770 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Starting System(Turning Device) | 3PF1265W42A02T | (Turning Gear) Transportation | (Turning Gear) Transportation | 2008-04-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Starting System(Turning Device) 3PF1265W42A02T (Turning Gear) Transportation | Activity | 3PF1265W42A02T | (Turning Gear) Transportation | 2008-04-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3771 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Starting System(Turning Device) | 3CF1265W42A03 | (Turning Gear) Installation | (Turning Gear) Installation | 2008-06-14 | 2008-06-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Starting System(Turning Device) 3CF1265W42A03 (Turning Gear) Installation | Activity | 3CF1265W42A03 | (Turning Gear) Installation | 2008-06-14 00:00:00 | 2008-06-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3772 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Starting System(Turning Device) | 3CF1265W74A04 | (Turning Gear) Installation- Elec. | (Turning Gear) Installation- Elec. | 2008-06-23 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Starting System(Turning Device) 3CF1265W74A04 (Turning Gear) Installation- Elec. | Activity | 3CF1265W74A04 | (Turning Gear) Installation- Elec. | 2008-06-23 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3773 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Starting System(Turning Device) | 3CF1265W90A05 | (Turning Gear) Installation- I&C | (Turning Gear) Installation- I&C | 2008-06-23 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Starting System(Turning Device) 3CF1265W90A05 (Turning Gear) Installation- I&C | Activity | 3CF1265W90A05 | (Turning Gear) Installation- I&C | 2008-06-23 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3774 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Starting System(Turning Device) | 3SF1265W62A06 | (Turning Gear) Loop check | (Turning Gear) Loop check | 2008-07-01 | 2008-07-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Starting System(Turning Device) 3SF1265W62A06 (Turning Gear) Loop check | Activity | 3SF1265W62A06 | (Turning Gear) Loop check | 2008-07-01 00:00:00 | 2008-07-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3775 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Starting System(Turning Device) | 3SF1265W62A07.0 | (Turning Gear) Function Test | (Turning Gear) Function Test | 2008-07-23 | 2008-07-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Starting System(Turning Device) 3SF1265W62A07.0 (Turning Gear) Function Test | Activity | 3SF1265W62A07.0 | (Turning Gear) Function Test | 2008-07-23 00:00:00 | 2008-07-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3777 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3PF1230W20A02P | (Air Intake) P.O & Procurement_Steel Sturucture | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3PF1230W20A02P (Air Intake) P.O & Procurement_Steel Sturucture | Activity | 3PF1230W20A02P | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3778 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3PF1230W64A05P | (Air Intake) P.O & Procurement_Inlet Duct | (Air Intake) P.O & Procurement_Inlet Duct | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3PF1230W64A05P (Air Intake) P.O & Procurement_Inlet Duct | Activity | 3PF1230W64A05P | (Air Intake) P.O & Procurement_Inlet Duct | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3779 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3PF1230W64A08P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3PF1230W64A08P (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 3PF1230W64A08P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3780 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3CF1230W16A01 | (Air Intake) FDN Work_Steel Sturucture | (Air Intake) FDN Work_Steel Sturucture | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3CF1230W16A01 (Air Intake) FDN Work_Steel Sturucture | Activity | 3CF1230W16A01 | (Air Intake) FDN Work_Steel Sturucture | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3781 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3PF1230W20A03T | (Air Intake) Transportation_Steel Sturucture | (Air Intake) Transportation_Steel Sturucture | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3PF1230W20A03T (Air Intake) Transportation_Steel Sturucture | Activity | 3PF1230W20A03T | (Air Intake) Transportation_Steel Sturucture | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3782 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3PF1230W64A06T | (Air Intake) Transportation_Inlet Duct | (Air Intake) Transportation_Inlet Duct | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3PF1230W64A06T (Air Intake) Transportation_Inlet Duct | Activity | 3PF1230W64A06T | (Air Intake) Transportation_Inlet Duct | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3783 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3PF1230W64A09T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3PF1230W64A09T (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 3PF1230W64A09T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3784 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3CF1230W20A04 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-05-16 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3CF1230W20A04 (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | Activity | 3CF1230W20A04 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-05-16 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3785 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3CF1230W64A07 | (Air Intake) Installation_Inlet Duct | (Air Intake) Installation_Inlet Duct | 2008-06-18 | 2008-06-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3CF1230W64A07 (Air Intake) Installation_Inlet Duct | Activity | 3CF1230W64A07 | (Air Intake) Installation_Inlet Duct | 2008-06-18 00:00:00 | 2008-06-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3786 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3CF1230W64A10 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-06-26 | 2008-07-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3CF1230W64A10 (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 3CF1230W64A10 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-06-26 00:00:00 | 2008-07-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3787 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3CF1230W74A11 | (Air Intake) Installation- Elec. | (Air Intake) Installation- Elec. | 2008-07-21 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3CF1230W74A11 (Air Intake) Installation- Elec. | Activity | 3CF1230W74A11 | (Air Intake) Installation- Elec. | 2008-07-21 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3788 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3CF1230W90A12 | (Air Intake) Installation- I&C | (Air Intake) Installation- I&C | 2008-07-21 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3CF1230W90A12 (Air Intake) Installation- I&C | Activity | 3CF1230W90A12 | (Air Intake) Installation- I&C | 2008-07-21 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3789 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3SF1230W62A13 | (Air Intake) Loop chek | (Air Intake) Loop chek | 2008-08-03 | 2008-08-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3SF1230W62A13 (Air Intake) Loop chek | Activity | 3SF1230W62A13 | (Air Intake) Loop chek | 2008-08-03 00:00:00 | 2008-08-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3790 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3SF1230W62A14 | (Air Intake) Function Test | (Air Intake) Function Test | 2008-08-10 | 2008-08-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3SF1230W62A14 (Air Intake) Function Test | Activity | 3SF1230W62A14 | (Air Intake) Function Test | 2008-08-10 00:00:00 | 2008-08-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3791 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air Intake System | 3SF1230W62A15 | (Air Intake) Load(Running) Test | (Air Intake) Load(Running) Test | 2008-08-13 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air Intake System 3SF1230W62A15 (Air Intake) Load(Running) Test | Activity | 3SF1230W62A15 | (Air Intake) Load(Running) Test | 2008-08-13 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3793 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air and Flue Gas System | 3PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air and Flue Gas System 3PF1265W64A01P (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | Activity | 3PF1265W64A01P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3794 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air and Flue Gas System | 3PF1265W64A02T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air and Flue Gas System 3PF1265W64A02T (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | Activity | 3PF1265W64A02T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3795 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air and Flue Gas System | 3CF1265W64A03 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-05-16 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air and Flue Gas System 3CF1265W64A03 (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | Activity | 3CF1265W64A03 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-05-16 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3796 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air and Flue Gas System | 3CF1265W64A04 | (Air&Flue Gas System) Duct work | (Air&Flue Gas System) Duct work | 2008-06-17 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air and Flue Gas System 3CF1265W64A04 (Air&Flue Gas System) Duct work | Activity | 3CF1265W64A04 | (Air&Flue Gas System) Duct work | 2008-06-17 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3797 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air and Flue Gas System | 3CF1265W74A05 | (Air&Flue Gas System) Installation- Elec. | (Air&Flue Gas System) Installation- Elec. | 2008-07-02 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air and Flue Gas System 3CF1265W74A05 (Air&Flue Gas System) Installation- Elec. | Activity | 3CF1265W74A05 | (Air&Flue Gas System) Installation- Elec. | 2008-07-02 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3798 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air and Flue Gas System | 3CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | (Air&Flue Gas System) Installation- I&C | 2008-07-02 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air and Flue Gas System 3CF1265W90A06 (Air&Flue Gas System) Installation- I&C | Activity | 3CF1265W90A06 | (Air&Flue Gas System) Installation- I&C | 2008-07-02 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3799 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air and Flue Gas System | 3SF1265W62A07 | (Air&Flue Gas System) Loop chek | (Air&Flue Gas System) Loop chek | 2008-07-13 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air and Flue Gas System 3SF1265W62A07 (Air&Flue Gas System) Loop chek | Activity | 3SF1265W62A07 | (Air&Flue Gas System) Loop chek | 2008-07-13 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3800 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Air and Flue Gas System | 3SF1265W62A08 | (Air&Flue Gas System) Function Test | (Air&Flue Gas System) Function Test | 2008-07-16 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Air and Flue Gas System 3SF1265W62A08 (Air&Flue Gas System) Function Test | Activity | 3SF1265W62A08 | (Air&Flue Gas System) Function Test | 2008-07-16 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3802 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3PF1250W42A02P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-04-30 | 2008-03-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3PF1250W42A02P (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | Activity | 3PF1250W42A02P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-04-30 00:00:00 | 2008-03-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3803 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-04-30 | 2008-03-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3PF1250W42A06P (Lube Oil System) P.O & Procurement_Lube oil functional Module | Activity | 3PF1250W42A06P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-04-30 00:00:00 | 2008-03-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3804 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3PF1250W42A10P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-04-30 | 2008-03-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3PF1250W42A10P (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | Activity | 3PF1250W42A10P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-04-30 00:00:00 | 2008-03-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3805 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3CF1250W16A01 | (Lube Oil System) FDN Work_Lube Oil Supply Module | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3CF1250W16A01 (Lube Oil System) FDN Work_Lube Oil Supply Module | Activity | 3CF1250W16A01 | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3806 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3CF1250W16A05 | (Lube Oil System) FDN Work_Lube oil functional Module | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3CF1250W16A05 (Lube Oil System) FDN Work_Lube oil functional Module | Activity | 3CF1250W16A05 | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3807 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3CF1250W16A09 | (Lube Oil System) FDN Work_Lube oil Mist Separator | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3CF1250W16A09 (Lube Oil System) FDN Work_Lube oil Mist Separator | Activity | 3CF1250W16A09 | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3808 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3PF1250W42A03T | (Lube Oil System) Transportation_Lube Oil Supply Module | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-03-29 | 2008-05-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3PF1250W42A03T (Lube Oil System) Transportation_Lube Oil Supply Module | Activity | 3PF1250W42A03T | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-03-29 00:00:00 | 2008-05-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3809 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3PF1250W42A07T | (Lube Oil System) Transportation_Lube oil functional Module | (Lube Oil System) Transportation_Lube oil functional Module | 2008-03-29 | 2008-05-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3PF1250W42A07T (Lube Oil System) Transportation_Lube oil functional Module | Activity | 3PF1250W42A07T | (Lube Oil System) Transportation_Lube oil functional Module | 2008-03-29 00:00:00 | 2008-05-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3810 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3PF1250W42A11T | (Lube Oil System) Transportation_Lube oil Mist Separator | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-03-29 | 2008-05-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3PF1250W42A11T (Lube Oil System) Transportation_Lube oil Mist Separator | Activity | 3PF1250W42A11T | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-03-29 00:00:00 | 2008-05-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3811 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3CF1250W42A04 | (Lube Oil System) Installation_Lube Oil Supply Module | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-05-14 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3CF1250W42A04 (Lube Oil System) Installation_Lube Oil Supply Module | Activity | 3CF1250W42A04 | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-05-14 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3812 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3CF1250W42A08 | (Lube Oil System) Installation_Lube oil functional Module | (Lube Oil System) Installation_Lube oil functional Module | 2008-05-14 | 2008-05-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3CF1250W42A08 (Lube Oil System) Installation_Lube oil functional Module | Activity | 3CF1250W42A08 | (Lube Oil System) Installation_Lube oil functional Module | 2008-05-14 00:00:00 | 2008-05-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3813 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3CF1250W42A12 | (Lube Oil System) Installation_Lube oil Mist Separator | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-05-14 | 2008-05-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3CF1250W42A12 (Lube Oil System) Installation_Lube oil Mist Separator | Activity | 3CF1250W42A12 | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-05-14 00:00:00 | 2008-05-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3814 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3CF1250W58A13 | (Lube Oil System) Piping work | (Lube Oil System) Piping work | 2008-05-30 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3CF1250W58A13 (Lube Oil System) Piping work | Activity | 3CF1250W58A13 | (Lube Oil System) Piping work | 2008-05-30 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3815 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3CF1250W62A16 | (GTG #11) Lube Oil Flushing | (GTG #11) Lube Oil Flushing | 2008-06-30 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3CF1250W62A16 (GTG #11) Lube Oil Flushing | Activity | 3CF1250W62A16 | (GTG #11) Lube Oil Flushing | 2008-06-30 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3816 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3CF1250W74A14 | (Lube Oil System) Installation- Elec. | (Lube Oil System) Installation- Elec. | 2008-07-01 | 2008-07-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3CF1250W74A14 (Lube Oil System) Installation- Elec. | Activity | 3CF1250W74A14 | (Lube Oil System) Installation- Elec. | 2008-07-01 00:00:00 | 2008-07-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3817 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3CF1250W90A15 | (Lube Oil System) Installation- I&C | (Lube Oil System) Installation- I&C | 2008-07-01 | 2008-07-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3CF1250W90A15 (Lube Oil System) Installation- I&C | Activity | 3CF1250W90A15 | (Lube Oil System) Installation- I&C | 2008-07-01 00:00:00 | 2008-07-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3818 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3SF1250W62A17 | (Lube Oil System) Loop chek | (Lube Oil System) Loop chek | 2008-07-15 | 2008-07-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3SF1250W62A17 (Lube Oil System) Loop chek | Activity | 3SF1250W62A17 | (Lube Oil System) Loop chek | 2008-07-15 00:00:00 | 2008-07-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3819 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3SF1250W62A18 | (Lube Oil System) Function Test | (Lube Oil System) Function Test | 2008-07-18 | 2008-07-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3SF1250W62A18 (Lube Oil System) Function Test | Activity | 3SF1250W62A18 | (Lube Oil System) Function Test | 2008-07-18 00:00:00 | 2008-07-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3820 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Lube Oil System | 3SF1250W62A19 | (Lube Oil System) Load Test | (Lube Oil System) Load Test | 2008-07-21 | 2008-07-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Lube Oil System 3SF1250W62A19 (Lube Oil System) Load Test | Activity | 3SF1250W62A19 | (Lube Oil System) Load Test | 2008-07-21 00:00:00 | 2008-07-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3822 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Generator Seal Oil System | 3PF1250W42A02.0P | (GEN Seal Oil Sys.) P.O & Procurement | (GEN Seal Oil Sys.) P.O & Procurement | 2007-04-30 | 2008-03-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Generator Seal Oil System 3PF1250W42A02.0P (GEN Seal Oil Sys.) P.O & Procurement | Activity | 3PF1250W42A02.0P | (GEN Seal Oil Sys.) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3823 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Generator Seal Oil System | 3CF1250W16A01.0 | (GEN Seal Oil Sys.) FDN Work | (GEN Seal Oil Sys.) FDN Work | 2007-11-30 | 2008-02-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Generator Seal Oil System 3CF1250W16A01.0 (GEN Seal Oil Sys.) FDN Work | Activity | 3CF1250W16A01.0 | (GEN Seal Oil Sys.) FDN Work | 2007-11-30 00:00:00 | 2008-02-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3824 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Generator Seal Oil System | 3PF1250W42A03.0T | (GEN Seal Oil Sys.) Transportation | (GEN Seal Oil Sys.) Transportation | 2008-03-29 | 2008-05-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Generator Seal Oil System 3PF1250W42A03.0T (GEN Seal Oil Sys.) Transportation | Activity | 3PF1250W42A03.0T | (GEN Seal Oil Sys.) Transportation | 2008-03-29 00:00:00 | 2008-05-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3825 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Generator Seal Oil System | 3CF1250W42A04.0 | (GEN Seal Oil Sys.) Installation | (GEN Seal Oil Sys.) Installation | 2008-05-14 | 2008-05-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Generator Seal Oil System 3CF1250W42A04.0 (GEN Seal Oil Sys.) Installation | Activity | 3CF1250W42A04.0 | (GEN Seal Oil Sys.) Installation | 2008-05-14 00:00:00 | 2008-05-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3826 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Generator Seal Oil System | 3CF1250W58A05 | (GEN Seal Oil Sys.) Piping Work | (GEN Seal Oil Sys.) Piping Work | 2008-05-29 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Generator Seal Oil System 3CF1250W58A05 (GEN Seal Oil Sys.) Piping Work | Activity | 3CF1250W58A05 | (GEN Seal Oil Sys.) Piping Work | 2008-05-29 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3827 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Generator Seal Oil System | 3CF1250W74A06 | (GEN Seal Oil Sys.) Installation- Elec. | (GEN Seal Oil Sys.) Installation- Elec. | 2008-06-30 | 2008-07-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Generator Seal Oil System 3CF1250W74A06 (GEN Seal Oil Sys.) Installation- Elec. | Activity | 3CF1250W74A06 | (GEN Seal Oil Sys.) Installation- Elec. | 2008-06-30 00:00:00 | 2008-07-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3828 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Generator Seal Oil System | 3CF1250W90A07 | (GEN Seal Oil Sys.) Installation- I&C | (GEN Seal Oil Sys.) Installation- I&C | 2008-06-30 | 2008-07-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Generator Seal Oil System 3CF1250W90A07 (GEN Seal Oil Sys.) Installation- I&C | Activity | 3CF1250W90A07 | (GEN Seal Oil Sys.) Installation- I&C | 2008-06-30 00:00:00 | 2008-07-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3829 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Generator Seal Oil System | 3SF1250W62A08 | (GEN Seal Oil Sys.) Oil Flushing | (GEN Seal Oil Sys.) Oil Flushing | 2008-06-30 | 2008-07-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Generator Seal Oil System 3SF1250W62A08 (GEN Seal Oil Sys.) Oil Flushing | Activity | 3SF1250W62A08 | (GEN Seal Oil Sys.) Oil Flushing | 2008-06-30 00:00:00 | 2008-07-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3830 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Generator Seal Oil System | 3SF1250W62A09 | (GEN Seal Oil Sys.) Loop chek | (GEN Seal Oil Sys.) Loop chek | 2008-07-13 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Generator Seal Oil System 3SF1250W62A09 (GEN Seal Oil Sys.) Loop chek | Activity | 3SF1250W62A09 | (GEN Seal Oil Sys.) Loop chek | 2008-07-13 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3831 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Generator Seal Oil System | 3SF1250W62A10 | (GEN Seal Oil Sys.) Function Test | (GEN Seal Oil Sys.) Function Test | 2008-07-16 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Generator Seal Oil System 3SF1250W62A10 (GEN Seal Oil Sys.) Function Test | Activity | 3SF1250W62A10 | (GEN Seal Oil Sys.) Function Test | 2008-07-16 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3833 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3PF1265W42A03P | (Gas Final Filter & Metering Skid) P.O & Procurement | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-04-30 | 2008-03-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3PF1265W42A03P (Gas Final Filter & Metering Skid) P.O & Procurement | Activity | 3PF1265W42A03P | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3834 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | (Gas Final Filter & Metering Skid) FDN Design | 2007-04-30 | 2007-10-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3EF1265W16A01 (Gas Final Filter & Metering Skid) FDN Design | Activity | 3EF1265W16A01 | (Gas Final Filter & Metering Skid) FDN Design | 2007-04-30 00:00:00 | 2007-10-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3835 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3PF1265W42A13P | (TCA Cooler) P.O & Procurement | (TCA Cooler) P.O & Procurement | 2007-04-30 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3PF1265W42A13P (TCA Cooler) P.O & Procurement | Activity | 3PF1265W42A13P | (TCA Cooler) P.O & Procurement | 2007-04-30 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3836 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3CF1265W16A02 | (Gas Final Filter & Metering Skid) FDN Work | (Gas Final Filter & Metering Skid) FDN Work | 2007-10-31 | 2008-01-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3CF1265W16A02 (Gas Final Filter & Metering Skid) FDN Work | Activity | 3CF1265W16A02 | (Gas Final Filter & Metering Skid) FDN Work | 2007-10-31 00:00:00 | 2008-01-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3837 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3CF1265W16A12 | (TCA Cooler) FDN Work | (TCA Cooler) FDN Work | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3CF1265W16A12 (TCA Cooler) FDN Work | Activity | 3CF1265W16A12 | (TCA Cooler) FDN Work | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3838 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3PF1265W42A04T | (Gas Final Filter & Metering Skid) Transportation | (Gas Final Filter & Metering Skid) Transportation | 2008-03-29 | 2008-05-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3PF1265W42A04T (Gas Final Filter & Metering Skid) Transportation | Activity | 3PF1265W42A04T | (Gas Final Filter & Metering Skid) Transportation | 2008-03-29 00:00:00 | 2008-05-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3839 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3PF1265W42A14T | (TCA Cooler) Transportation | (TCA Cooler) Transportation | 2008-04-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3PF1265W42A14T (TCA Cooler) Transportation | Activity | 3PF1265W42A14T | (TCA Cooler) Transportation | 2008-04-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3840 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3CF1265W42A05 | (Gas Final Filter & Metering Skid) Installation | (Gas Final Filter & Metering Skid) Installation | 2008-05-14 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3CF1265W42A05 (Gas Final Filter & Metering Skid) Installation | Activity | 3CF1265W42A05 | (Gas Final Filter & Metering Skid) Installation | 2008-05-14 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3841 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3CF1265W42A15 | (TCA Cooler) Installation | (TCA Cooler) Installation | 2008-06-14 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3CF1265W42A15 (TCA Cooler) Installation | Activity | 3CF1265W42A15 | (TCA Cooler) Installation | 2008-06-14 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3842 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3CF1265W58A06 | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | 2008-07-19 | 2008-09-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3CF1265W58A06 (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | Activity | 3CF1265W58A06 | (FGSS) Piping Work(incl. Airblowing Test)_Power block Area | 2008-07-19 00:00:00 | 2008-09-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3843 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3CF1265W74A07 | (FGSS) Installation- Elec. | (FGSS) Installation- Elec. | 2008-09-04 | 2008-09-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3CF1265W74A07 (FGSS) Installation- Elec. | Activity | 3CF1265W74A07 | (FGSS) Installation- Elec. | 2008-09-04 00:00:00 | 2008-09-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3844 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3CF1265W90A08 | (FGSS) Installation- I&C | (FGSS) Installation- I&C | 2008-09-04 | 2008-09-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3CF1265W90A08 (FGSS) Installation- I&C | Activity | 3CF1265W90A08 | (FGSS) Installation- I&C | 2008-09-04 00:00:00 | 2008-09-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3845 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3SF1265W62A09 | (FGSS) Loop chek | (FGSS) Loop chek | 2008-10-03 | 2008-10-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3SF1265W62A09 (FGSS) Loop chek | Activity | 3SF1265W62A09 | (FGSS) Loop chek | 2008-10-03 00:00:00 | 2008-10-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3846 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3SF1265W62A10.7 | (FGSS) Function Test | (FGSS) Function Test | 2008-10-13 | 2008-10-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3SF1265W62A10.7 (FGSS) Function Test | Activity | 3SF1265W62A10.7 | (FGSS) Function Test | 2008-10-13 00:00:00 | 2008-10-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3847 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Gas Supply System | 3SF1265W62A11.7 | (FGSS) Gas Receiving upto GT Final Control Valve | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-10-19 | 2008-10-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Gas Supply System 3SF1265W62A11.7 (FGSS) Gas Receiving upto GT Final Control Valve | Activity | 3SF1265W62A11.7 | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-10-19 00:00:00 | 2008-10-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3849 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Washing & Drain System | 3PF1265W42A02.0P | (Washing & Drain system Skid) P.O & Procurement | (Washing & Drain system Skid) P.O & Procurement | 2007-04-30 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Washing & Drain System 3PF1265W42A02.0P (Washing & Drain system Skid) P.O & Procurement | Activity | 3PF1265W42A02.0P | (Washing & Drain system Skid) P.O & Procurement | 2007-04-30 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3850 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Washing & Drain System | 3CF1265W16A01 | (Washing & Drain system Skid) FDN Work | (Washing & Drain system Skid) FDN Work | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Washing & Drain System 3CF1265W16A01 (Washing & Drain system Skid) FDN Work | Activity | 3CF1265W16A01 | (Washing & Drain system Skid) FDN Work | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3851 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Washing & Drain System | 3PF1265W42A03.0T | (Washing & Drain system Skid) Transportation | (Washing & Drain system Skid) Transportation | 2008-04-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Washing & Drain System 3PF1265W42A03.0T (Washing & Drain system Skid) Transportation | Activity | 3PF1265W42A03.0T | (Washing & Drain system Skid) Transportation | 2008-04-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3852 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Washing & Drain System | 3CF1265W42A04 | (Washing & Drain system Skid) Installation | (Washing & Drain system Skid) Installation | 2008-06-14 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Washing & Drain System 3CF1265W42A04 (Washing & Drain system Skid) Installation | Activity | 3CF1265W42A04 | (Washing & Drain system Skid) Installation | 2008-06-14 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3853 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Washing & Drain System | 3CF1265W58A05 | (Washing & Drain system Skid) Piping work | (Washing & Drain system Skid) Piping work | 2008-07-02 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Washing & Drain System 3CF1265W58A05 (Washing & Drain system Skid) Piping work | Activity | 3CF1265W58A05 | (Washing & Drain system Skid) Piping work | 2008-07-02 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3854 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Washing & Drain System | 3CF1265W74A06 | (Washing & Drain system Skid) Installation- Elec. | (Washing & Drain system Skid) Installation- Elec. | 2008-08-02 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Washing & Drain System 3CF1265W74A06 (Washing & Drain system Skid) Installation- Elec. | Activity | 3CF1265W74A06 | (Washing & Drain system Skid) Installation- Elec. | 2008-08-02 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3855 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Washing & Drain System | 3CF1265W90A07 | (Washing & Drain system Skid) Installation- I&C | (Washing & Drain system Skid) Installation- I&C | 2008-08-02 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Washing & Drain System 3CF1265W90A07 (Washing & Drain system Skid) Installation- I&C | Activity | 3CF1265W90A07 | (Washing & Drain system Skid) Installation- I&C | 2008-08-02 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3856 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Washing & Drain System | 3CF1265W62A08 | (Washing & Drain system Skid) Flushing | (Washing & Drain system Skid) Flushing | 2008-08-02 | 2008-08-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Washing & Drain System 3CF1265W62A08 (Washing & Drain system Skid) Flushing | Activity | 3CF1265W62A08 | (Washing & Drain system Skid) Flushing | 2008-08-02 00:00:00 | 2008-08-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3857 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Washing & Drain System | 3SF1265W62A09.0 | (Washing & Drain system Skid) Loop chek | (Washing & Drain system Skid) Loop chek | 2008-08-16 | 2008-08-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Washing & Drain System 3SF1265W62A09.0 (Washing & Drain system Skid) Loop chek | Activity | 3SF1265W62A09.0 | (Washing & Drain system Skid) Loop chek | 2008-08-16 00:00:00 | 2008-08-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3858 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Washing & Drain System | 3SF1265W62A10 | (Washing & Drain system Skid) Function Test | (Washing & Drain system Skid) Function Test | 2008-08-21 | 2008-08-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Washing & Drain System 3SF1265W62A10 (Washing & Drain system Skid) Function Test | Activity | 3SF1265W62A10 | (Washing & Drain system Skid) Function Test | 2008-08-21 00:00:00 | 2008-08-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3859 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Washing & Drain System | 3SF1265W62A11 | (Washing & Drain system Skid) Load(Running) Test | (Washing & Drain system Skid) Load(Running) Test | 2008-08-24 | 2008-08-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Washing & Drain System 3SF1265W62A11 (Washing & Drain system Skid) Load(Running) Test | Activity | 3SF1265W62A11 | (Washing & Drain system Skid) Load(Running) Test | 2008-08-24 00:00:00 | 2008-08-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3861 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3PF1265W42A02.8P | (Fuel oil injection System) P.O & Procurement | (Fuel oil injection System) P.O & Procurement | 2007-04-30 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3PF1265W42A02.8P (Fuel oil injection System) P.O & Procurement | Activity | 3PF1265W42A02.8P | (Fuel oil injection System) P.O & Procurement | 2007-04-30 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3862 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3PF1265W42A09P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3PF1265W42A09P (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | Activity | 3PF1265W42A09P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3863 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3PF1265W42A16P | (Water injection System) P.O & Procurement | (Water injection System) P.O & Procurement | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3PF1265W42A16P (Water injection System) P.O & Procurement | Activity | 3PF1265W42A16P | (Water injection System) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3864 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3CF1265W16A01.8 | (Fuel oil injection System) FDN Work | (Fuel oil injection System) FDN Work | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3CF1265W16A01.8 (Fuel oil injection System) FDN Work | Activity | 3CF1265W16A01.8 | (Fuel oil injection System) FDN Work | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3865 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3CF1265W16A08 | (Fuel oil injection Pump & actuator) FDN Work | (Fuel oil injection Pump & actuator) FDN Work | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3CF1265W16A08 (Fuel oil injection Pump & actuator) FDN Work | Activity | 3CF1265W16A08 | (Fuel oil injection Pump & actuator) FDN Work | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3866 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3CF1265W16A15 | (Water injection System) FDN Work | (Water injection System) FDN Work | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3CF1265W16A15 (Water injection System) FDN Work | Activity | 3CF1265W16A15 | (Water injection System) FDN Work | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3867 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3PF1265W42A10T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3PF1265W42A10T (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | Activity | 3PF1265W42A10T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3868 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3PF1265W42A17T | (Water injection System) Transportation | (Water injection System) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3PF1265W42A17T (Water injection System) Transportation | Activity | 3PF1265W42A17T | (Water injection System) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3869 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3PF1265W42A03.8T | (Fuel oil injection System) Transportation | (Fuel oil injection System) Transportation | 2008-04-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3PF1265W42A03.8T (Fuel oil injection System) Transportation | Activity | 3PF1265W42A03.8T | (Fuel oil injection System) Transportation | 2008-04-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3870 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3CF1265W42A11 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3CF1265W42A11 (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | Activity | 3CF1265W42A11 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3871 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3CF1265W42A18 | (Water injection System) Installation | (Water injection System) Installation | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3CF1265W42A18 (Water injection System) Installation | Activity | 3CF1265W42A18 | (Water injection System) Installation | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3872 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3CF1265W58A19 | (Water injection System) Piping work | (Water injection System) Piping work | 2008-05-31 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3CF1265W58A19 (Water injection System) Piping work | Activity | 3CF1265W58A19 | (Water injection System) Piping work | 2008-05-31 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3873 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3CF1265W42A04.8 | (Fuel oil injection System) Installation | (Fuel oil injection System) Installation | 2008-06-14 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3CF1265W42A04.8 (Fuel oil injection System) Installation | Activity | 3CF1265W42A04.8 | (Fuel oil injection System) Installation | 2008-06-14 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3874 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3CF1265W74A20 | (Water injection System) Installation- Elec. | (Water injection System) Installation- Elec. | 2008-06-16 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3CF1265W74A20 (Water injection System) Installation- Elec. | Activity | 3CF1265W74A20 | (Water injection System) Installation- Elec. | 2008-06-16 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3875 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3CF1265W90A21 | (Water injection System) Installation- I&C | (Water injection System) Installation- I&C | 2008-06-16 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3CF1265W90A21 (Water injection System) Installation- I&C | Activity | 3CF1265W90A21 | (Water injection System) Installation- I&C | 2008-06-16 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3876 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3SF1265W62A22 | (Water injection System) Loop chek | (Water injection System) Loop chek | 2008-06-29 | 2008-07-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3SF1265W62A22 (Water injection System) Loop chek | Activity | 3SF1265W62A22 | (Water injection System) Loop chek | 2008-06-29 00:00:00 | 2008-07-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3877 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3CF1265W58A05.8 | (Fuel oil injection System) Piping work | (Fuel oil injection System) Piping work | 2008-06-30 | 2008-07-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3CF1265W58A05.8 (Fuel oil injection System) Piping work | Activity | 3CF1265W58A05.8 | (Fuel oil injection System) Piping work | 2008-06-30 00:00:00 | 2008-07-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3878 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3SF1265W62A23 | (Water injection System) Function Test | (Water injection System) Function Test | 2008-07-04 | 2008-07-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3SF1265W62A23 (Water injection System) Function Test | Activity | 3SF1265W62A23 | (Water injection System) Function Test | 2008-07-04 00:00:00 | 2008-07-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3879 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3CF1265W74A06.8 | (Fuel oil injection System) Installation- Elec. | (Fuel oil injection System) Installation- Elec. | 2008-07-15 | 2008-07-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3CF1265W74A06.8 (Fuel oil injection System) Installation- Elec. | Activity | 3CF1265W74A06.8 | (Fuel oil injection System) Installation- Elec. | 2008-07-15 00:00:00 | 2008-07-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3880 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3CF1265W90A07.8 | (Fuel oil injection System) Installation- I&C | (Fuel oil injection System) Installation- I&C | 2008-07-15 | 2008-07-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3CF1265W90A07.8 (Fuel oil injection System) Installation- I&C | Activity | 3CF1265W90A07.8 | (Fuel oil injection System) Installation- I&C | 2008-07-15 00:00:00 | 2008-07-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3881 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3SF1265W62A12 | (Fuel oil injection System) Loop chek | (Fuel oil injection System) Loop chek | 2008-07-29 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3SF1265W62A12 (Fuel oil injection System) Loop chek | Activity | 3SF1265W62A12 | (Fuel oil injection System) Loop chek | 2008-07-29 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3882 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3SF1265W62A24 | (Water injection System) Load Test | (Water injection System) Load Test | 2008-08-12 | 2008-08-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3SF1265W62A24 (Water injection System) Load Test | Activity | 3SF1265W62A24 | (Water injection System) Load Test | 2008-08-12 00:00:00 | 2008-08-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3883 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3SF1265W62A13 | (Fuel oil injection System) Function Test | (Fuel oil injection System) Function Test | 2008-08-15 | 2008-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3SF1265W62A13 (Fuel oil injection System) Function Test | Activity | 3SF1265W62A13 | (Fuel oil injection System) Function Test | 2008-08-15 00:00:00 | 2008-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3884 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fuel Oil Injection System | 3SF1265W62A14 | (Fuel oil injection System) Flushing | (Fuel oil injection System) Flushing | 2008-08-30 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fuel Oil Injection System 3SF1265W62A14 (Fuel oil injection System) Flushing | Activity | 3SF1265W62A14 | (Fuel oil injection System) Flushing | 2008-08-30 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3886 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Vibration Monitoring System (VMS) | 3PF1260W86A02P | (VMS) P.O & Procurement for GT | (VMS) P.O & Procurement for GT | 2007-08-31 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Vibration Monitoring System (VMS) 3PF1260W86A02P (VMS) P.O & Procurement for GT | Activity | 3PF1260W86A02P | (VMS) P.O & Procurement for GT | 2007-08-31 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3887 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Vibration Monitoring System (VMS) | 3PF1260W86A03T | (VMS) Transportation for GT | (VMS) Transportation for GT | 2008-07-03 | 2008-08-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Vibration Monitoring System (VMS) 3PF1260W86A03T (VMS) Transportation for GT | Activity | 3PF1260W86A03T | (VMS) Transportation for GT | 2008-07-03 00:00:00 | 2008-08-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3888 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Vibration Monitoring System (VMS) | 3CF1260W86A04 | (VMS) Installation for GT | (VMS) Installation for GT | 2008-09-29 | 2008-10-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Vibration Monitoring System (VMS) 3CF1260W86A04 (VMS) Installation for GT | Activity | 3CF1260W86A04 | (VMS) Installation for GT | 2008-09-29 00:00:00 | 2008-10-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3889 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Vibration Monitoring System (VMS) | 3SF1260W62A05 | (VMS) Function Test for GT | (VMS) Function Test for GT | 2008-10-07 | 2008-10-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Vibration Monitoring System (VMS) 3SF1260W62A05 (VMS) Function Test for GT | Activity | 3SF1260W62A05 | (VMS) Function Test for GT | 2008-10-07 00:00:00 | 2008-10-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3891 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3EF1225W00A01 | (CCWS) CCW H/EX key data | (CCWS) CCW H/EX key data | 2007-04-30 | 2007-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3EF1225W00A01 (CCWS) CCW H/EX key data | Activity | 3EF1225W00A01 | (CCWS) CCW H/EX key data | 2007-04-30 00:00:00 | 2007-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3892 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3PF1225W42A18P | (EXP Head Tank) P.O & Procurement | (EXP Head Tank) P.O & Procurement | 2007-07-03 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3PF1225W42A18P (EXP Head Tank) P.O & Procurement | Activity | 3PF1225W42A18P | (EXP Head Tank) P.O & Procurement | 2007-07-03 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3893 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3EF1225W16A15 | (EXP Head Tank) FDN Design | (EXP Head Tank) FDN Design | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3EF1225W16A15 (EXP Head Tank) FDN Design | Activity | 3EF1225W16A15 | (EXP Head Tank) FDN Design | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3894 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3PF1225W42A12P | (CCWP) P.O & Procurement for GT | (CCWP) P.O & Procurement for GT | 2007-07-03 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3PF1225W42A12P (CCWP) P.O & Procurement for GT | Activity | 3PF1225W42A12P | (CCWP) P.O & Procurement for GT | 2007-07-03 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3895 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3EF1225W16A09 | (CCWP) FDN Design | (CCWP) FDN Design | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3EF1225W16A09 (CCWP) FDN Design | Activity | 3EF1225W16A09 | (CCWP) FDN Design | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3896 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3PF1225W42A05P (CCW H/EX) P.O & Procurement_Fin fan cooler | Activity | 3PF1225W42A05P | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3897 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3EF1225W16A02 (CCW H/EX) FDN Design_Fin fan cooler | Activity | 3EF1225W16A02 | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3898 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3CF1225W16A10 | (CCWP) FDN Work | (CCWP) FDN Work | 2007-11-30 | 2008-01-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3CF1225W16A10 (CCWP) FDN Work | Activity | 3CF1225W16A10 | (CCWP) FDN Work | 2007-11-30 00:00:00 | 2008-01-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3899 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3CF1225W16A03 | (CCW H/EX) FDN Work_Fin fan cooler | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 | 2008-02-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3CF1225W16A03 (CCW H/EX) FDN Work_Fin fan cooler | Activity | 3CF1225W16A03 | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 00:00:00 | 2008-02-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3900 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3CF1225W16A16 | (EXP Head Tank) FDN Work | (EXP Head Tank) FDN Work | 2008-02-01 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3CF1225W16A16 (EXP Head Tank) FDN Work | Activity | 3CF1225W16A16 | (EXP Head Tank) FDN Work | 2008-02-01 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3901 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3PF1225W42A19T | (EXP Head Tank) Transportation | (EXP Head Tank) Transportation | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3PF1225W42A19T (EXP Head Tank) Transportation | Activity | 3PF1225W42A19T | (EXP Head Tank) Transportation | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3902 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3PF1225W42A13T | (CCWP) Transportation for GT | (CCWP) Transportation for GT | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3PF1225W42A13T (CCWP) Transportation for GT | Activity | 3PF1225W42A13T | (CCWP) Transportation for GT | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3903 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3PF1225W42A06T | (CCW H/EX) Transportation_Fin fan cooler | (CCW H/EX) Transportation_Fin fan cooler | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3PF1225W42A06T (CCW H/EX) Transportation_Fin fan cooler | Activity | 3PF1225W42A06T | (CCW H/EX) Transportation_Fin fan cooler | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3904 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3CF1225W58A21 | (CCWS) Piping Work | (CCWS) Piping Work | 2008-06-26 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3CF1225W58A21 (CCWS) Piping Work | Activity | 3CF1225W58A21 | (CCWS) Piping Work | 2008-06-26 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3905 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3CF1225W42A20 | (EXP Head Tank) Installation | (EXP Head Tank) Installation | 2008-07-16 | 2008-08-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3CF1225W42A20 (EXP Head Tank) Installation | Activity | 3CF1225W42A20 | (EXP Head Tank) Installation | 2008-07-16 00:00:00 | 2008-08-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3906 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3CF1225W42A14 | (CCWP) Installation | (CCWP) Installation | 2008-07-16 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3CF1225W42A14 (CCWP) Installation | Activity | 3CF1225W42A14 | (CCWP) Installation | 2008-07-16 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3907 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | (CCW H/EX) Installation_Fin fan cooler | 2008-07-16 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3CF1225W42A07 (CCW H/EX) Installation_Fin fan cooler | Activity | 3CF1225W42A07 | (CCW H/EX) Installation_Fin fan cooler | 2008-07-16 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3908 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3CF1225W74A22 | (CCWS) Installation & Test - Elec. | (CCWS) Installation & Test - Elec. | 2008-07-30 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3CF1225W74A22 (CCWS) Installation & Test - Elec. | Activity | 3CF1225W74A22 | (CCWS) Installation & Test - Elec. | 2008-07-30 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3909 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3CF1225W90A23 | (CCWS) Installation & Test - I&C | (CCWS) Installation & Test - I&C | 2008-07-30 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3CF1225W90A23 (CCWS) Installation & Test - I&C | Activity | 3CF1225W90A23 | (CCWS) Installation & Test - I&C | 2008-07-30 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3910 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3SF1225W62A24 | (CCWS) Loop chek | (CCWS) Loop chek | 2008-08-30 | 2008-09-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3SF1225W62A24 (CCWS) Loop chek | Activity | 3SF1225W62A24 | (CCWS) Loop chek | 2008-08-30 00:00:00 | 2008-09-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3911 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3SF1225W62A25 | (CCWS) Function Test | (CCWS) Function Test | 2008-09-09 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3SF1225W62A25 (CCWS) Function Test | Activity | 3SF1225W62A25 | (CCWS) Function Test | 2008-09-09 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3912 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Closed Cooling Water System | 3SF1225W62A26 | (CCWS) Flushing | (CCWS) Flushing | 2008-09-14 | 2008-09-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Closed Cooling Water System 3SF1225W62A26 (CCWS) Flushing | Activity | 3SF1225W62A26 | (CCWS) Flushing | 2008-09-14 00:00:00 | 2008-09-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3914 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fire fighting System | 3PF1265W38A01P | (F/F GTG#31) P.O & Procurement_CO2 FF System | (F/F GTG#31) P.O & Procurement_CO2 FF System | 2007-04-30 | 2008-05-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fire fighting System 3PF1265W38A01P (F/F GTG#31) P.O & Procurement_CO2 FF System | Activity | 3PF1265W38A01P | (F/F GTG#31) P.O & Procurement_CO2 FF System | 2007-04-30 00:00:00 | 2008-05-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3915 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fire fighting System | 3PF1265W38A04P | (F/F GTG#31)P.O & Procurement_Clean Agent FF System | (F/F GTG#31)P.O & Procurement_Clean Agent FF System | 2007-04-30 | 2008-05-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fire fighting System 3PF1265W38A04P (F/F GTG#31)P.O & Procurement_Clean Agent FF System | Activity | 3PF1265W38A04P | (F/F GTG#31)P.O & Procurement_Clean Agent FF System | 2007-04-30 00:00:00 | 2008-05-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3916 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fire fighting System | 3PF1265W38A02T | (F/F GTG#31) Transportation_CO2 FF System | (F/F GTG#31) Transportation_CO2 FF System | 2008-05-14 | 2008-06-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fire fighting System 3PF1265W38A02T (F/F GTG#31) Transportation_CO2 FF System | Activity | 3PF1265W38A02T | (F/F GTG#31) Transportation_CO2 FF System | 2008-05-14 00:00:00 | 2008-06-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3917 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fire fighting System | 3PF1265W38A05T | (F/F GTG#31) Transportation_Clean Agent FF System | (F/F GTG#31) Transportation_Clean Agent FF System | 2008-05-14 | 2008-06-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fire fighting System 3PF1265W38A05T (F/F GTG#31) Transportation_Clean Agent FF System | Activity | 3PF1265W38A05T | (F/F GTG#31) Transportation_Clean Agent FF System | 2008-05-14 00:00:00 | 2008-06-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3918 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fire fighting System | 3CF1265W38A03 | (F/F GTG#31) Installation_CO2 FF System | (F/F GTG#31) Installation_CO2 FF System | 2008-06-28 | 2008-07-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fire fighting System 3CF1265W38A03 (F/F GTG#31) Installation_CO2 FF System | Activity | 3CF1265W38A03 | (F/F GTG#31) Installation_CO2 FF System | 2008-06-28 00:00:00 | 2008-07-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3919 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fire fighting System | 3CF1265W38A06 | (F/F GTG#31) Installation_Clean Agent FF System | (F/F GTG#31) Installation_Clean Agent FF System | 2008-06-28 | 2008-07-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fire fighting System 3CF1265W38A06 (F/F GTG#31) Installation_Clean Agent FF System | Activity | 3CF1265W38A06 | (F/F GTG#31) Installation_Clean Agent FF System | 2008-06-28 00:00:00 | 2008-07-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3920 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fire fighting System | 3CF1265W38A07 | (F/F GTG#31) Piping work | (F/F GTG#31) Piping work | 2008-07-14 | 2008-08-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fire fighting System 3CF1265W38A07 (F/F GTG#31) Piping work | Activity | 3CF1265W38A07 | (F/F GTG#31) Piping work | 2008-07-14 00:00:00 | 2008-08-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3921 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fire fighting System | 3SF1265W62A08.0 | (F/F GTG#31) Loop chek | (F/F GTG#31) Loop chek | 2008-08-07 | 2008-08-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fire fighting System 3SF1265W62A08.0 (F/F GTG#31) Loop chek | Activity | 3SF1265W62A08.0 | (F/F GTG#31) Loop chek | 2008-08-07 00:00:00 | 2008-08-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3922 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fire fighting System | 3SF1265W62A09.00 | (F/F GTG#31) Function Test(incl. Alarm Test) | (F/F GTG#31) Function Test(incl. Alarm Test) | 2008-08-14 | 2008-08-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fire fighting System 3SF1265W62A09.00 (F/F GTG#31) Function Test(incl. Alarm Test) | Activity | 3SF1265W62A09.00 | (F/F GTG#31) Function Test(incl. Alarm Test) | 2008-08-14 00:00:00 | 2008-08-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3923 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Fire fighting System | 3SF1265W62A10.0 | (F/F GTG#31) CO2 Discharge Test | (F/F GTG#31) CO2 Discharge Test | 2008-08-24 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Fire fighting System 3SF1265W62A10.0 (F/F GTG#31) CO2 Discharge Test | Activity | 3SF1265W62A10.0 | (F/F GTG#31) CO2 Discharge Test | 2008-08-24 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3925 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3PF1265W42A02.5P | (Purge Air System) P.O & Procurement | (Purge Air System) P.O & Procurement | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3PF1265W42A02.5P (Purge Air System) P.O & Procurement | Activity | 3PF1265W42A02.5P | (Purge Air System) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3926 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3PF1265W42A12P | (Control Oil) P.O & Procurement | (Control Oil) P.O & Procurement | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3PF1265W42A12P (Control Oil) P.O & Procurement | Activity | 3PF1265W42A12P | (Control Oil) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3927 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3CF1265W16A01.5 | (Purge Air System) FDN Work | (Purge Air System) FDN Work | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3CF1265W16A01.5 (Purge Air System) FDN Work | Activity | 3CF1265W16A01.5 | (Purge Air System) FDN Work | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3928 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3CF1265W16A11 | (Control Oil) FDN Work | (Control Oil) FDN Work | 2007-11-30 | 2008-01-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3CF1265W16A11 (Control Oil) FDN Work | Activity | 3CF1265W16A11 | (Control Oil) FDN Work | 2007-11-30 00:00:00 | 2008-01-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3929 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3PF1265W42A03.5T | (Purge Air System) Transportation | (Purge Air System) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3PF1265W42A03.5T (Purge Air System) Transportation | Activity | 3PF1265W42A03.5T | (Purge Air System) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3930 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3PF1265W42A13.0T | (Control Oil)Transportation | (Control Oil)Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3PF1265W42A13.0T (Control Oil)Transportation | Activity | 3PF1265W42A13.0T | (Control Oil)Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3931 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3CF1265W42A04.5 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3CF1265W42A04.5 (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | Activity | 3CF1265W42A04.5 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3932 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3CF1265W42A14 | (Control Oil) Installation | (Control Oil) Installation | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3CF1265W42A14 (Control Oil) Installation | Activity | 3CF1265W42A14 | (Control Oil) Installation | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3933 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3CF1265W58A05.5 | (Purge Air System) Piping work | (Purge Air System) Piping work | 2008-05-31 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3CF1265W58A05.5 (Purge Air System) Piping work | Activity | 3CF1265W58A05.5 | (Purge Air System) Piping work | 2008-05-31 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3934 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3CF1265W58A15 | (Control Oil) Piping work | (Control Oil) Piping work | 2008-05-31 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3CF1265W58A15 (Control Oil) Piping work | Activity | 3CF1265W58A15 | (Control Oil) Piping work | 2008-05-31 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3935 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3CF1265W74A06.5 | (Purge Air System) Installation- Elec. | (Purge Air System) Installation- Elec. | 2008-06-16 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3CF1265W74A06.5 (Purge Air System) Installation- Elec. | Activity | 3CF1265W74A06.5 | (Purge Air System) Installation- Elec. | 2008-06-16 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3936 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3CF1265W90A07.5 | (Purge Air System) Installation- I&C | (Purge Air System) Installation- I&C | 2008-06-16 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3CF1265W90A07.5 (Purge Air System) Installation- I&C | Activity | 3CF1265W90A07.5 | (Purge Air System) Installation- I&C | 2008-06-16 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3937 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3SF1265W62A08.5 | (Purge Air System) Loop chek | (Purge Air System) Loop chek | 2008-06-29 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3SF1265W62A08.5 (Purge Air System) Loop chek | Activity | 3SF1265W62A08.5 | (Purge Air System) Loop chek | 2008-06-29 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3938 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3SF1265W62A09.5 | (Purge Air System) Function Test | (Purge Air System) Function Test | 2008-07-02 | 2008-07-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3SF1265W62A09.5 (Purge Air System) Function Test | Activity | 3SF1265W62A09.5 | (Purge Air System) Function Test | 2008-07-02 00:00:00 | 2008-07-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3939 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3CF1265W74A16 | (Control Oil) Installation- Elec. | (Control Oil) Installation- Elec. | 2008-07-02 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3CF1265W74A16 (Control Oil) Installation- Elec. | Activity | 3CF1265W74A16 | (Control Oil) Installation- Elec. | 2008-07-02 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3940 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3CF1265W90A17 | (Control Oil) Installation- I&C | (Control Oil) Installation- I&C | 2008-07-02 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3CF1265W90A17 (Control Oil) Installation- I&C | Activity | 3CF1265W90A17 | (Control Oil) Installation- I&C | 2008-07-02 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3941 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3SF1265W62A10.5 | (Purge Air System) Load Test | (Purge Air System) Load Test | 2008-07-05 | 2008-07-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3SF1265W62A10.5 (Purge Air System) Load Test | Activity | 3SF1265W62A10.5 | (Purge Air System) Load Test | 2008-07-05 00:00:00 | 2008-07-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3942 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3SF1265W62A18 | (Control Oil) Loop chek | (Control Oil) Loop chek | 2008-07-16 | 2008-07-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3SF1265W62A18 (Control Oil) Loop chek | Activity | 3SF1265W62A18 | (Control Oil) Loop chek | 2008-07-16 00:00:00 | 2008-07-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3943 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3SF1265W62A19 | (Control Oil) Function Test | (Control Oil) Function Test | 2008-07-21 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3SF1265W62A19 (Control Oil) Function Test | Activity | 3SF1265W62A19 | (Control Oil) Function Test | 2008-07-21 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3944 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Auxiliary System | 3SF1265W62A20 | (Control Oil) Flushing | (Control Oil) Flushing | 2008-07-31 | 2008-08-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Auxiliary System 3SF1265W62A20 (Control Oil) Flushing | Activity | 3SF1265W62A20 | (Control Oil) Flushing | 2008-07-31 00:00:00 | 2008-08-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3946 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9011W62A01 | (GTG #31) Fuel Gas System Final Function Test | (GTG #31) Fuel Gas System Final Function Test | 2008-10-28 | 2008-10-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9011W62A01 (GTG #31) Fuel Gas System Final Function Test | Activity | 3SF9011W62A01 | (GTG #31) Fuel Gas System Final Function Test | 2008-10-28 00:00:00 | 2008-10-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3947 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9011W62A02 | (GTG #31) Turning Gear Operation | (GTG #31) Turning Gear Operation | 2008-10-31 | 2008-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9011W62A02 (GTG #31) Turning Gear Operation | Activity | 3SF9011W62A02 | (GTG #31) Turning Gear Operation | 2008-10-31 00:00:00 | 2008-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3948 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9011W62A03 | (GTG #31) Initial Firing with FSNL | (GTG #31) Initial Firing with FSNL | 2008-11-02 | 2008-11-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9011W62A03 (GTG #31) Initial Firing with FSNL | Activity | 3SF9011W62A03 | (GTG #31) Initial Firing with FSNL | 2008-11-02 00:00:00 | 2008-11-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3949 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9012W62A04 | (GTG #31) TBN & GEN Protection Test | (GTG #31) TBN & GEN Protection Test | 2008-11-03 | 2008-11-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9012W62A04 (GTG #31) TBN & GEN Protection Test | Activity | 3SF9012W62A04 | (GTG #31) TBN & GEN Protection Test | 2008-11-03 00:00:00 | 2008-11-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3950 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9012W62A05 | (GTG #31) 1st Synchronization | (GTG #31) 1st Synchronization | 2008-11-05 | 2008-11-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9012W62A05 (GTG #31) 1st Synchronization | Activity | 3SF9012W62A05 | (GTG #31) 1st Synchronization | 2008-11-05 00:00:00 | 2008-11-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3951 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9012W62A06 | (GTG #31) Optimization with Fuel Gas | (GTG #31) Optimization with Fuel Gas | 2008-11-07 | 2008-11-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9012W62A06 (GTG #31) Optimization with Fuel Gas | Activity | 3SF9012W62A06 | (GTG #31) Optimization with Fuel Gas | 2008-11-07 00:00:00 | 2008-11-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3952 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9012W62A07 | (GTG #31) Fuel Oil System Final Function Test | (GTG #31) Fuel Oil System Final Function Test | 2008-11-22 | 2008-12-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9012W62A07 (GTG #31) Fuel Oil System Final Function Test | Activity | 3SF9012W62A07 | (GTG #31) Fuel Oil System Final Function Test | 2008-11-22 00:00:00 | 2008-12-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3953 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9012W62A08 | (GTG #31) Optimization with Fuel Oil | (GTG #31) Optimization with Fuel Oil | 2008-12-02 | 2008-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9012W62A08 (GTG #31) Optimization with Fuel Oil | Activity | 3SF9012W62A08 | (GTG #31) Optimization with Fuel Oil | 2008-12-02 00:00:00 | 2008-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3954 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9012W62A09 | (GTG #31) Black start Test with GT | (GTG #31) Black start Test with GT | 2009-01-01 | 2009-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9012W62A09 (GTG #31) Black start Test with GT | Activity | 3SF9012W62A09 | (GTG #31) Black start Test with GT | 2009-01-01 00:00:00 | 2009-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3955 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9012W62A13 | (GTG #31) Fuel Change-Over Test | (GTG #31) Fuel Change-Over Test | 2009-01-01 | 2009-01-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9012W62A13 (GTG #31) Fuel Change-Over Test | Activity | 3SF9012W62A13 | (GTG #31) Fuel Change-Over Test | 2009-01-01 00:00:00 | 2009-01-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3956 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9012W62A10 | (GTG #31) Trial Run Test | (GTG #31) Trial Run Test | 2009-01-02 | 2009-01-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9012W62A10 (GTG #31) Trial Run Test | Activity | 3SF9012W62A10 | (GTG #31) Trial Run Test | 2009-01-02 00:00:00 | 2009-01-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3957 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9013W62A11 | (GTG #31) Reliability Test | (GTG #31) Reliability Test | 2009-01-03 | 2009-01-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9013W62A11 (GTG #31) Reliability Test | Activity | 3SF9013W62A11 | (GTG #31) Reliability Test | 2009-01-03 00:00:00 | 2009-01-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3958 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #31 > GTG #31 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #31 | GTG #31 Commissioning | 3SF9013W62A12 | (GTG #31) Performance Test (Fuel Gas & Fuel Oil) | (GTG #31) Performance Test (Fuel Gas & Fuel Oil) | 2009-01-18 | 2009-02-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #31 GTG #31 Commissioning 3SF9013W62A12 (GTG #31) Performance Test (Fuel Gas & Fuel Oil) | Activity | 3SF9013W62A12 | (GTG #31) Performance Test (Fuel Gas & Fuel Oil) | 2009-01-18 00:00:00 | 2009-02-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3961 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Main body | 3PF1213W42A08.1P | (Gen #32) P.O & Procurement | (Gen #32) P.O & Procurement | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Main body 3PF1213W42A08.1P (Gen #32) P.O & Procurement | Activity | 3PF1213W42A08.1P | (Gen #32) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3962 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Main body | 3EF1213W16A06.1 | (Gen #32) FDN Design | (Gen #32) FDN Design | 2007-04-30 | 2007-09-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Main body 3EF1213W16A06.1 (Gen #32) FDN Design | Activity | 3EF1213W16A06.1 | (Gen #32) FDN Design | 2007-04-30 00:00:00 | 2007-09-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3963 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Main body | 3PF1213W42A03.1P | (GT #32) P.O & Procurement | (GT #32) P.O & Procurement | 2007-04-30 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Main body 3PF1213W42A03.1P (GT #32) P.O & Procurement | Activity | 3PF1213W42A03.1P | (GT #32) P.O & Procurement | 2007-04-30 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3964 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Main body | 3EF1213W16A01.1 | (GT #32) FDN Design | (GT #32) FDN Design | 2007-04-30 | 2007-09-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Main body 3EF1213W16A01.1 (GT #32) FDN Design | Activity | 3EF1213W16A01.1 | (GT #32) FDN Design | 2007-04-30 00:00:00 | 2007-09-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3965 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Main body | 3CF1213W16A07.1 | (Gen #32) FDN Work | (Gen #32) FDN Work | 2007-09-28 | 2008-02-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Main body 3CF1213W16A07.1 (Gen #32) FDN Work | Activity | 3CF1213W16A07.1 | (Gen #32) FDN Work | 2007-09-28 00:00:00 | 2008-02-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3966 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Main body | 3CF1213W16A02.1 | (GT #32) FDN Work | (GT #32) FDN Work | 2007-09-28 | 2008-02-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Main body 3CF1213W16A02.1 (GT #32) FDN Work | Activity | 3CF1213W16A02.1 | (GT #32) FDN Work | 2007-09-28 00:00:00 | 2008-02-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3967 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Main body | 3PF1213W42A09.1T | (Gen #32) Transportation | (Gen #32) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Main body 3PF1213W42A09.1T (Gen #32) Transportation | Activity | 3PF1213W42A09.1T | (Gen #32) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3968 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Main body | 3PF1213W42A04.1T | (GT #32) Transportation | (GT #32) Transportation | 2008-04-30 | 2008-06-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Main body 3PF1213W42A04.1T (GT #32) Transportation | Activity | 3PF1213W42A04.1T | (GT #32) Transportation | 2008-04-30 00:00:00 | 2008-06-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3969 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Main body | 3CF1213W42A10.1 | (Gen #32) Installation | (Gen #32) Installation | 2008-05-16 | 2008-09-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Main body 3CF1213W42A10.1 (Gen #32) Installation | Activity | 3CF1213W42A10.1 | (Gen #32) Installation | 2008-05-16 00:00:00 | 2008-09-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3970 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Main body | 3CF1213W42A05.1 | (GT #32) Installation(On FDN~Final Alignment) | (GT #32) Installation(On FDN~Final Alignment) | 2008-06-13 | 2008-10-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Main body 3CF1213W42A05.1 (GT #32) Installation(On FDN~Final Alignment) | Activity | 3CF1213W42A05.1 | (GT #32) Installation(On FDN~Final Alignment) | 2008-06-13 00:00:00 | 2008-10-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3971 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Main body | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Main body | 3CF1213W52A11.1 | (GT #32) Insulation | (GT #32) Insulation | 2008-07-19 | 2008-08-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Main body 3CF1213W52A11.1 (GT #32) Insulation | Activity | 3CF1213W52A11.1 | (GT #32) Insulation | 2008-07-19 00:00:00 | 2008-08-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3973 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Electrical System | 3PF1255W70A01.1P | (GTG#32 Electrical) P.O & Procurement | (GTG#32 Electrical) P.O & Procurement | 2007-04-30 | 2008-05-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Electrical System 3PF1255W70A01.1P (GTG#32 Electrical) P.O & Procurement | Activity | 3PF1255W70A01.1P | (GTG#32 Electrical) P.O & Procurement | 2007-04-30 00:00:00 | 2008-05-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3974 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Electrical System | 3PF1255W70A02.1T | (GTG#32 Electrical) Transportation | (GTG#32 Electrical) Transportation | 2008-05-29 | 2008-07-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Electrical System 3PF1255W70A02.1T (GTG#32 Electrical) Transportation | Activity | 3PF1255W70A02.1T | (GTG#32 Electrical) Transportation | 2008-05-29 00:00:00 | 2008-07-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3975 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Electrical System | 3CF1255W70A03.1 | (GTG#32 Electrical) Installation- PCC | (GTG#32 Electrical) Installation- PCC | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Electrical System 3CF1255W70A03.1 (GTG#32 Electrical) Installation- PCC | Activity | 3CF1255W70A03.1 | (GTG#32 Electrical) Installation- PCC | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3976 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Electrical System | 3CF1255W70A04.1 | (GTG#32 Electrical) Installation- MCC | (GTG#32 Electrical) Installation- MCC | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Electrical System 3CF1255W70A04.1 (GTG#32 Electrical) Installation- MCC | Activity | 3CF1255W70A04.1 | (GTG#32 Electrical) Installation- MCC | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3977 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Electrical System | 3CF1255W70A05.1 | (GTG#32 Electrical) Installation- Protection Sys. | (GTG#32 Electrical) Installation- Protection Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Electrical System 3CF1255W70A05.1 (GTG#32 Electrical) Installation- Protection Sys. | Activity | 3CF1255W70A05.1 | (GTG#32 Electrical) Installation- Protection Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3978 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Electrical System | 3CF1255W70A07.1 | (GTG#32 Electrical) Installation- SEE&SFC Sys. | (GTG#32 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Electrical System 3CF1255W70A07.1 (GTG#32 Electrical) Installation- SEE&SFC Sys. | Activity | 3CF1255W70A07.1 | (GTG#32 Electrical) Installation- SEE&SFC Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3979 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Electrical System | 3CF1255W70A08.1 | (GTG#32 Electrical) Installation- DC&UPS Sys. | (GTG#32 Electrical) Installation- DC&UPS Sys. | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Electrical System 3CF1255W70A08.1 (GTG#32 Electrical) Installation- DC&UPS Sys. | Activity | 3CF1255W70A08.1 | (GTG#32 Electrical) Installation- DC&UPS Sys. | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3980 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Electrical System | 3CF1255W74A09.1 | (GTG#32 Electrical) Cable work | (GTG#32 Electrical) Cable work | 2008-08-01 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Electrical System 3CF1255W74A09.1 (GTG#32 Electrical) Cable work | Activity | 3CF1255W74A09.1 | (GTG#32 Electrical) Cable work | 2008-08-01 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3981 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Electrical System | 3CF1255W86A06.1 | (GTG#32 Electrical) Installation- GT control Sys. | (GTG#32 Electrical) Installation- GT control Sys. | 2008-08-04 | 2008-09-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Electrical System 3CF1255W86A06.1 (GTG#32 Electrical) Installation- GT control Sys. | Activity | 3CF1255W86A06.1 | (GTG#32 Electrical) Installation- GT control Sys. | 2008-08-04 00:00:00 | 2008-09-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3982 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Electrical System | 3CF1255W62A10.1 | (GTG#32 Electrical) Electrical Function Test | (GTG#32 Electrical) Electrical Function Test | 2008-09-16 | 2008-09-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Electrical System 3CF1255W62A10.1 (GTG#32 Electrical) Electrical Function Test | Activity | 3CF1255W62A10.1 | (GTG#32 Electrical) Electrical Function Test | 2008-09-16 00:00:00 | 2008-09-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3983 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Electrical System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Electrical System | 3CF1255W62A11.1 | (GTG#32 Electrical) Loop Test | (GTG#32 Electrical) Loop Test | 2008-09-22 | 2008-09-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Electrical System 3CF1255W62A11.1 (GTG#32 Electrical) Loop Test | Activity | 3CF1255W62A11.1 | (GTG#32 Electrical) Loop Test | 2008-09-22 00:00:00 | 2008-09-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3985 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Starting System(Turning Device) | 3PF1265W42A01.1P | (Turning Gear) P.O & Procurement | (Turning Gear) P.O & Procurement | 2007-04-30 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Starting System(Turning Device) 3PF1265W42A01.1P (Turning Gear) P.O & Procurement | Activity | 3PF1265W42A01.1P | (Turning Gear) P.O & Procurement | 2007-04-30 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3986 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Starting System(Turning Device) | 3PF1265W42A02.1T | (Turning Gear) Transportation | (Turning Gear) Transportation | 2008-04-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Starting System(Turning Device) 3PF1265W42A02.1T (Turning Gear) Transportation | Activity | 3PF1265W42A02.1T | (Turning Gear) Transportation | 2008-04-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3987 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Starting System(Turning Device) | 3CF1265W42A03.1 | (Turning Gear) Installation | (Turning Gear) Installation | 2008-06-14 | 2008-06-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Starting System(Turning Device) 3CF1265W42A03.1 (Turning Gear) Installation | Activity | 3CF1265W42A03.1 | (Turning Gear) Installation | 2008-06-14 00:00:00 | 2008-06-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3988 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Starting System(Turning Device) | 3CF1265W74A04.1 | (Turning Gear) Installation- Elec. | (Turning Gear) Installation- Elec. | 2008-06-23 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Starting System(Turning Device) 3CF1265W74A04.1 (Turning Gear) Installation- Elec. | Activity | 3CF1265W74A04.1 | (Turning Gear) Installation- Elec. | 2008-06-23 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3989 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Starting System(Turning Device) | 3CF1265W90A05.1 | (Turning Gear) Installation- I&C | (Turning Gear) Installation- I&C | 2008-06-23 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Starting System(Turning Device) 3CF1265W90A05.1 (Turning Gear) Installation- I&C | Activity | 3CF1265W90A05.1 | (Turning Gear) Installation- I&C | 2008-06-23 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3990 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Starting System(Turning Device) | 3SF1265W62A06.1 | (Turning Gear) Loop check | (Turning Gear) Loop check | 2008-07-01 | 2008-07-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Starting System(Turning Device) 3SF1265W62A06.1 (Turning Gear) Loop check | Activity | 3SF1265W62A06.1 | (Turning Gear) Loop check | 2008-07-01 00:00:00 | 2008-07-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3991 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Starting System(Turning Device) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Starting System(Turning Device) | 3SF1265W62A07.1 | (Turning Gear) Function Test | (Turning Gear) Function Test | 2008-07-25 | 2008-07-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Starting System(Turning Device) 3SF1265W62A07.1 (Turning Gear) Function Test | Activity | 3SF1265W62A07.1 | (Turning Gear) Function Test | 2008-07-25 00:00:00 | 2008-07-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3993 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3PF1230W20A02.1P | (Air Intake) P.O & Procurement_Steel Sturucture | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3PF1230W20A02.1P (Air Intake) P.O & Procurement_Steel Sturucture | Activity | 3PF1230W20A02.1P | (Air Intake) P.O & Procurement_Steel Sturucture | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3994 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3PF1230W64A05.1P | (Air Intake) P.O & Procurement_Inlet Duct | (Air Intake) P.O & Procurement_Inlet Duct | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3PF1230W64A05.1P (Air Intake) P.O & Procurement_Inlet Duct | Activity | 3PF1230W64A05.1P | (Air Intake) P.O & Procurement_Inlet Duct | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3995 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3PF1230W64A08.1P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3PF1230W64A08.1P (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 3PF1230W64A08.1P | (Air Intake) P.O & Procurement_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3996 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3CF1230W16A01.1 | (Air Intake) FDN Work_Steel Sturucture | (Air Intake) FDN Work_Steel Sturucture | 2007-11-28 | 2008-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3CF1230W16A01.1 (Air Intake) FDN Work_Steel Sturucture | Activity | 3CF1230W16A01.1 | (Air Intake) FDN Work_Steel Sturucture | 2007-11-28 00:00:00 | 2008-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3997 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3PF1230W20A03.1T | (Air Intake) Transportation_Steel Sturucture | (Air Intake) Transportation_Steel Sturucture | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3PF1230W20A03.1T (Air Intake) Transportation_Steel Sturucture | Activity | 3PF1230W20A03.1T | (Air Intake) Transportation_Steel Sturucture | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3998 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3PF1230W64A06.1T | (Air Intake) Transportation_Inlet Duct | (Air Intake) Transportation_Inlet Duct | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3PF1230W64A06.1T (Air Intake) Transportation_Inlet Duct | Activity | 3PF1230W64A06.1T | (Air Intake) Transportation_Inlet Duct | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 3999 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3PF1230W64A09.1T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3PF1230W64A09.1T (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 3PF1230W64A09.1T | (Air Intake) Transportation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4000 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3CF1230W20A04.1 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-06-02 | 2008-06-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3CF1230W20A04.1 (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | Activity | 3CF1230W20A04.1 | (Air Intake) Installation_Steel Sturucture(incl. Temp. Protection floor) | 2008-06-02 00:00:00 | 2008-06-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4001 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3CF1230W64A07.1 | (Air Intake) Installation_Inlet Duct | (Air Intake) Installation_Inlet Duct | 2008-06-19 | 2008-06-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3CF1230W64A07.1 (Air Intake) Installation_Inlet Duct | Activity | 3CF1230W64A07.1 | (Air Intake) Installation_Inlet Duct | 2008-06-19 00:00:00 | 2008-06-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4002 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3CF1230W64A10.1 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-06-27 | 2008-07-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3CF1230W64A10.1 (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | Activity | 3CF1230W64A10.1 | (Air Intake) Installation_Inlet Duct_Filter & Casing(incl. Anti-icing) | 2008-06-27 00:00:00 | 2008-07-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4003 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3CF1230W74A11.1 | (Air Intake) Installation- Elec. | (Air Intake) Installation- Elec. | 2008-07-22 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3CF1230W74A11.1 (Air Intake) Installation- Elec. | Activity | 3CF1230W74A11.1 | (Air Intake) Installation- Elec. | 2008-07-22 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4004 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3CF1230W90A12.1 | (Air Intake) Installation- I&C | (Air Intake) Installation- I&C | 2008-07-22 | 2008-08-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3CF1230W90A12.1 (Air Intake) Installation- I&C | Activity | 3CF1230W90A12.1 | (Air Intake) Installation- I&C | 2008-07-22 00:00:00 | 2008-08-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4005 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3SF1230W62A13.1 | (Air Intake) Loop chek | (Air Intake) Loop chek | 2008-08-05 | 2008-08-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3SF1230W62A13.1 (Air Intake) Loop chek | Activity | 3SF1230W62A13.1 | (Air Intake) Loop chek | 2008-08-05 00:00:00 | 2008-08-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4006 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3SF1230W62A14.1 | (Air Intake) Function Test | (Air Intake) Function Test | 2008-08-10 | 2008-08-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3SF1230W62A14.1 (Air Intake) Function Test | Activity | 3SF1230W62A14.1 | (Air Intake) Function Test | 2008-08-10 00:00:00 | 2008-08-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4007 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air Intake System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air Intake System | 3SF1230W62A15.1 | (Air Intake) Load(Running) Test | (Air Intake) Load(Running) Test | 2008-08-13 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air Intake System 3SF1230W62A15.1 (Air Intake) Load(Running) Test | Activity | 3SF1230W62A15.1 | (Air Intake) Load(Running) Test | 2008-08-13 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4009 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air and Flue Gas System | 3PF1265W64A01.1P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air and Flue Gas System 3PF1265W64A01.1P (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | Activity | 3PF1265W64A01.1P | (Air&Flue Gas System) P.O & Procurement_Expasion Joint & Exhaust Duct | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4010 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air and Flue Gas System | 3PF1265W64A02.1T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air and Flue Gas System 3PF1265W64A02.1T (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | Activity | 3PF1265W64A02.1T | (Air&Flue Gas System) Transportation_Expasion Joint & Exhaust Duct | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4011 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air and Flue Gas System | 3CF1265W64A03.1 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-05-16 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air and Flue Gas System 3CF1265W64A03.1 (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | Activity | 3CF1265W64A03.1 | (Air&Flue Gas System) Installation_Expasion Joint & Exhaust Duct | 2008-05-16 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4012 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air and Flue Gas System | 3CF1265W64A04.1 | (Air&Flue Gas System) Duct work | (Air&Flue Gas System) Duct work | 2008-06-17 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air and Flue Gas System 3CF1265W64A04.1 (Air&Flue Gas System) Duct work | Activity | 3CF1265W64A04.1 | (Air&Flue Gas System) Duct work | 2008-06-17 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4013 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air and Flue Gas System | 3CF1265W74A06.1 | (Air&Flue Gas System) Installation- Elec. | (Air&Flue Gas System) Installation- Elec. | 2008-07-02 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air and Flue Gas System 3CF1265W74A06.1 (Air&Flue Gas System) Installation- Elec. | Activity | 3CF1265W74A06.1 | (Air&Flue Gas System) Installation- Elec. | 2008-07-02 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4014 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air and Flue Gas System | 3CF1265W90A07.1 | (Air&Flue Gas System) Installation- I&C | (Air&Flue Gas System) Installation- I&C | 2008-07-02 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air and Flue Gas System 3CF1265W90A07.1 (Air&Flue Gas System) Installation- I&C | Activity | 3CF1265W90A07.1 | (Air&Flue Gas System) Installation- I&C | 2008-07-02 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4015 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air and Flue Gas System | 3SF1265W62A05.1 | (Air&Flue Gas System) Loop chek | (Air&Flue Gas System) Loop chek | 2008-07-13 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air and Flue Gas System 3SF1265W62A05.1 (Air&Flue Gas System) Loop chek | Activity | 3SF1265W62A05.1 | (Air&Flue Gas System) Loop chek | 2008-07-13 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4016 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Air and Flue Gas System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Air and Flue Gas System | 3SF1265W62A08.1 | (Air&Flue Gas System) Function Test | (Air&Flue Gas System) Function Test | 2008-07-16 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Air and Flue Gas System 3SF1265W62A08.1 (Air&Flue Gas System) Function Test | Activity | 3SF1265W62A08.1 | (Air&Flue Gas System) Function Test | 2008-07-16 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4018 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3PF1250W42A02.1P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3PF1250W42A02.1P (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | Activity | 3PF1250W42A02.1P | (Lube Oil System) P.O & Procurement_Lube Oil Supply Module | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4019 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3PF1250W42A06.1P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3PF1250W42A06.1P (Lube Oil System) P.O & Procurement_Lube oil functional Module | Activity | 3PF1250W42A06.1P | (Lube Oil System) P.O & Procurement_Lube oil functional Module | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4020 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3PF1250W42A10.1P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3PF1250W42A10.1P (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | Activity | 3PF1250W42A10.1P | (Lube Oil System) P.O & Procurement_Lube oil Mist Separator | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4021 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3CF1250W16A01.1 | (Lube Oil System) FDN Work_Lube Oil Supply Module | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-11-28 | 2008-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3CF1250W16A01.1 (Lube Oil System) FDN Work_Lube Oil Supply Module | Activity | 3CF1250W16A01.1 | (Lube Oil System) FDN Work_Lube Oil Supply Module | 2007-11-28 00:00:00 | 2008-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4022 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3CF1250W16A05.1 | (Lube Oil System) FDN Work_Lube oil functional Module | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-11-28 | 2008-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3CF1250W16A05.1 (Lube Oil System) FDN Work_Lube oil functional Module | Activity | 3CF1250W16A05.1 | (Lube Oil System) FDN Work_Lube oil functional Module | 2007-11-28 00:00:00 | 2008-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4023 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3CF1250W16A09.1 | (Lube Oil System) FDN Work_Lube oil Mist Separator | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-11-28 | 2008-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3CF1250W16A09.1 (Lube Oil System) FDN Work_Lube oil Mist Separator | Activity | 3CF1250W16A09.1 | (Lube Oil System) FDN Work_Lube oil Mist Separator | 2007-11-28 00:00:00 | 2008-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4024 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3PF1250W42A03.1T | (Lube Oil System) Transportation_Lube Oil Supply Module | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3PF1250W42A03.1T (Lube Oil System) Transportation_Lube Oil Supply Module | Activity | 3PF1250W42A03.1T | (Lube Oil System) Transportation_Lube Oil Supply Module | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4025 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3PF1250W42A07.1T | (Lube Oil System) Transportation_Lube oil functional Module | (Lube Oil System) Transportation_Lube oil functional Module | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3PF1250W42A07.1T (Lube Oil System) Transportation_Lube oil functional Module | Activity | 3PF1250W42A07.1T | (Lube Oil System) Transportation_Lube oil functional Module | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4026 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3PF1250W42A11.1T | (Lube Oil System) Transportation_Lube oil Mist Separator | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3PF1250W42A11.1T (Lube Oil System) Transportation_Lube oil Mist Separator | Activity | 3PF1250W42A11.1T | (Lube Oil System) Transportation_Lube oil Mist Separator | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4027 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3CF1250W42A04.1 | (Lube Oil System) Installation_Lube Oil Supply Module | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-05-16 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3CF1250W42A04.1 (Lube Oil System) Installation_Lube Oil Supply Module | Activity | 3CF1250W42A04.1 | (Lube Oil System) Installation_Lube Oil Supply Module | 2008-05-16 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4028 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3CF1250W42A08.1 | (Lube Oil System) Installation_Lube oil functional Module | (Lube Oil System) Installation_Lube oil functional Module | 2008-05-16 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3CF1250W42A08.1 (Lube Oil System) Installation_Lube oil functional Module | Activity | 3CF1250W42A08.1 | (Lube Oil System) Installation_Lube oil functional Module | 2008-05-16 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4029 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3CF1250W42A12.1 | (Lube Oil System) Installation_Lube oil Mist Separator | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-05-16 | 2008-05-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3CF1250W42A12.1 (Lube Oil System) Installation_Lube oil Mist Separator | Activity | 3CF1250W42A12.1 | (Lube Oil System) Installation_Lube oil Mist Separator | 2008-05-16 00:00:00 | 2008-05-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4030 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3CF1250W58A13.1 | (Lube Oil System) Piping work | (Lube Oil System) Piping work | 2008-06-02 | 2008-07-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3CF1250W58A13.1 (Lube Oil System) Piping work | Activity | 3CF1250W58A13.1 | (Lube Oil System) Piping work | 2008-06-02 00:00:00 | 2008-07-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4031 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3CF1250W62A16.1 | (GTG #32) Lube Oil Flushing | (GTG #32) Lube Oil Flushing | 2008-07-02 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3CF1250W62A16.1 (GTG #32) Lube Oil Flushing | Activity | 3CF1250W62A16.1 | (GTG #32) Lube Oil Flushing | 2008-07-02 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4032 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3CF1250W74A14.1 | (Lube Oil System) Installation- Elec. | (Lube Oil System) Installation- Elec. | 2008-07-03 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3CF1250W74A14.1 (Lube Oil System) Installation- Elec. | Activity | 3CF1250W74A14.1 | (Lube Oil System) Installation- Elec. | 2008-07-03 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4033 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3CF1250W90A15.1 | (Lube Oil System) Installation- I&C | (Lube Oil System) Installation- I&C | 2008-07-03 | 2008-07-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3CF1250W90A15.1 (Lube Oil System) Installation- I&C | Activity | 3CF1250W90A15.1 | (Lube Oil System) Installation- I&C | 2008-07-03 00:00:00 | 2008-07-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4034 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3SF1250W62A17.1 | (Lube Oil System) Loop chek | (Lube Oil System) Loop chek | 2008-07-17 | 2008-07-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3SF1250W62A17.1 (Lube Oil System) Loop chek | Activity | 3SF1250W62A17.1 | (Lube Oil System) Loop chek | 2008-07-17 00:00:00 | 2008-07-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4035 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3SF1250W62A18.1 | (Lube Oil System) Function Test | (Lube Oil System) Function Test | 2008-07-20 | 2008-07-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3SF1250W62A18.1 (Lube Oil System) Function Test | Activity | 3SF1250W62A18.1 | (Lube Oil System) Function Test | 2008-07-20 00:00:00 | 2008-07-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4036 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Lube Oil System | 3SF1250W62A19.1 | (Lube Oil System) Load Test | (Lube Oil System) Load Test | 2008-07-23 | 2008-07-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Lube Oil System 3SF1250W62A19.1 (Lube Oil System) Load Test | Activity | 3SF1250W62A19.1 | (Lube Oil System) Load Test | 2008-07-23 00:00:00 | 2008-07-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4038 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Generator Seal Oil System | 3PF1250W42A02.2P | (GEN Seal Oil Sys.) P.O & Procurement | (GEN Seal Oil Sys.) P.O & Procurement | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Generator Seal Oil System 3PF1250W42A02.2P (GEN Seal Oil Sys.) P.O & Procurement | Activity | 3PF1250W42A02.2P | (GEN Seal Oil Sys.) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4039 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Generator Seal Oil System | 3CF1250W16A01.2 | (GEN Seal Oil Sys.) FDN Work | (GEN Seal Oil Sys.) FDN Work | 2007-11-28 | 2008-02-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Generator Seal Oil System 3CF1250W16A01.2 (GEN Seal Oil Sys.) FDN Work | Activity | 3CF1250W16A01.2 | (GEN Seal Oil Sys.) FDN Work | 2007-11-28 00:00:00 | 2008-02-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4040 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Generator Seal Oil System | 3PF1250W42A03.2T | (GEN Seal Oil Sys.) Transportation | (GEN Seal Oil Sys.) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Generator Seal Oil System 3PF1250W42A03.2T (GEN Seal Oil Sys.) Transportation | Activity | 3PF1250W42A03.2T | (GEN Seal Oil Sys.) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4041 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Generator Seal Oil System | 3CF1250W42A04.2 | (GEN Seal Oil Sys.) Installation | (GEN Seal Oil Sys.) Installation | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Generator Seal Oil System 3CF1250W42A04.2 (GEN Seal Oil Sys.) Installation | Activity | 3CF1250W42A04.2 | (GEN Seal Oil Sys.) Installation | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4042 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Generator Seal Oil System | 3CF1250W58A05.2 | (GEN Seal Oil Sys.) Piping Work | (GEN Seal Oil Sys.) Piping Work | 2008-05-31 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Generator Seal Oil System 3CF1250W58A05.2 (GEN Seal Oil Sys.) Piping Work | Activity | 3CF1250W58A05.2 | (GEN Seal Oil Sys.) Piping Work | 2008-05-31 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4043 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Generator Seal Oil System | 3CF1250W74A07.2 | (GEN Seal Oil Sys.) Installation- Elec. | (GEN Seal Oil Sys.) Installation- Elec. | 2008-07-02 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Generator Seal Oil System 3CF1250W74A07.2 (GEN Seal Oil Sys.) Installation- Elec. | Activity | 3CF1250W74A07.2 | (GEN Seal Oil Sys.) Installation- Elec. | 2008-07-02 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4044 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Generator Seal Oil System | 3CF1250W90A08.2 | (GEN Seal Oil Sys.) Installation- I&C | (GEN Seal Oil Sys.) Installation- I&C | 2008-07-02 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Generator Seal Oil System 3CF1250W90A08.2 (GEN Seal Oil Sys.) Installation- I&C | Activity | 3CF1250W90A08.2 | (GEN Seal Oil Sys.) Installation- I&C | 2008-07-02 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4045 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Generator Seal Oil System | 3SF1250W62A06.2 | (GEN Seal Oil Sys.) Oil Flushing | (GEN Seal Oil Sys.) Oil Flushing | 2008-07-02 | 2008-07-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Generator Seal Oil System 3SF1250W62A06.2 (GEN Seal Oil Sys.) Oil Flushing | Activity | 3SF1250W62A06.2 | (GEN Seal Oil Sys.) Oil Flushing | 2008-07-02 00:00:00 | 2008-07-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4046 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Generator Seal Oil System | 3SF1250W62A09.2 | (GEN Seal Oil Sys.) Loop chek | (GEN Seal Oil Sys.) Loop chek | 2008-07-16 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Generator Seal Oil System 3SF1250W62A09.2 (GEN Seal Oil Sys.) Loop chek | Activity | 3SF1250W62A09.2 | (GEN Seal Oil Sys.) Loop chek | 2008-07-16 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4047 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Generator Seal Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Generator Seal Oil System | 3SF1250W62A10.2 | (GEN Seal Oil Sys.) Function Test | (GEN Seal Oil Sys.) Function Test | 2008-07-19 | 2008-07-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Generator Seal Oil System 3SF1250W62A10.2 (GEN Seal Oil Sys.) Function Test | Activity | 3SF1250W62A10.2 | (GEN Seal Oil Sys.) Function Test | 2008-07-19 00:00:00 | 2008-07-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4049 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3PF1265W42A03.1P | (Gas Final Filter & Metering Skid) P.O & Procurement | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3PF1265W42A03.1P (Gas Final Filter & Metering Skid) P.O & Procurement | Activity | 3PF1265W42A03.1P | (Gas Final Filter & Metering Skid) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4050 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3EF1265W16A01.1 | (Gas Final Filter & Metering Skid) FDN Design | (Gas Final Filter & Metering Skid) FDN Design | 2007-04-30 | 2007-10-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3EF1265W16A01.1 (Gas Final Filter & Metering Skid) FDN Design | Activity | 3EF1265W16A01.1 | (Gas Final Filter & Metering Skid) FDN Design | 2007-04-30 00:00:00 | 2007-10-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4051 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3PF1265W42A13.4P | (TCA Cooler) P.O & Procurement | (TCA Cooler) P.O & Procurement | 2007-04-30 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3PF1265W42A13.4P (TCA Cooler) P.O & Procurement | Activity | 3PF1265W42A13.4P | (TCA Cooler) P.O & Procurement | 2007-04-30 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4052 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3CF1265W16A02.1 | (Gas Final Filter & Metering Skid) FDN Work | (Gas Final Filter & Metering Skid) FDN Work | 2007-10-31 | 2008-01-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3CF1265W16A02.1 (Gas Final Filter & Metering Skid) FDN Work | Activity | 3CF1265W16A02.1 | (Gas Final Filter & Metering Skid) FDN Work | 2007-10-31 00:00:00 | 2008-01-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4053 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3CF1265W16A12.1 | (TCA Cooler) FDN Work | (TCA Cooler) FDN Work | 2007-11-28 | 2008-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3CF1265W16A12.1 (TCA Cooler) FDN Work | Activity | 3CF1265W16A12.1 | (TCA Cooler) FDN Work | 2007-11-28 00:00:00 | 2008-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4054 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3PF1265W42A04.1T | (Gas Final Filter & Metering Skid) Transportation | (Gas Final Filter & Metering Skid) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3PF1265W42A04.1T (Gas Final Filter & Metering Skid) Transportation | Activity | 3PF1265W42A04.1T | (Gas Final Filter & Metering Skid) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4055 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3PF1265W42A14.1T | (TCA Cooler) Transportation | (TCA Cooler) Transportation | 2008-04-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3PF1265W42A14.1T (TCA Cooler) Transportation | Activity | 3PF1265W42A14.1T | (TCA Cooler) Transportation | 2008-04-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4056 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3CF1265W42A05.1 | (Gas Final Filter & Metering Skid) Installation | (Gas Final Filter & Metering Skid) Installation | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3CF1265W42A05.1 (Gas Final Filter & Metering Skid) Installation | Activity | 3CF1265W42A05.1 | (Gas Final Filter & Metering Skid) Installation | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4057 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3CF1265W42A15.1 | (TCA Cooler) Installation | (TCA Cooler) Installation | 2008-06-14 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3CF1265W42A15.1 (TCA Cooler) Installation | Activity | 3CF1265W42A15.1 | (TCA Cooler) Installation | 2008-06-14 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4058 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3CF1265W58A06.1 | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | 2008-07-19 | 2008-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3CF1265W58A06.1 (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | Activity | 3CF1265W58A06.1 | (FGSS) Piping Work(incl. Airblowing Test)_Power Block Area | 2008-07-19 00:00:00 | 2008-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4059 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3CF1265W74A07.1 | (FGSS) Installation- Elec. | (FGSS) Installation- Elec. | 2008-08-20 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3CF1265W74A07.1 (FGSS) Installation- Elec. | Activity | 3CF1265W74A07.1 | (FGSS) Installation- Elec. | 2008-08-20 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4060 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3CF1265W90A08.1 | (FGSS) Installation- I&C | (FGSS) Installation- I&C | 2008-08-20 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3CF1265W90A08.1 (FGSS) Installation- I&C | Activity | 3CF1265W90A08.1 | (FGSS) Installation- I&C | 2008-08-20 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4061 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3SF1265W62A09.1 | (FGSS) Loop chek | (FGSS) Loop chek | 2008-10-03 | 2008-10-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3SF1265W62A09.1 (FGSS) Loop chek | Activity | 3SF1265W62A09.1 | (FGSS) Loop chek | 2008-10-03 00:00:00 | 2008-10-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4062 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3SF1265W62A10.4 | (FGSS) Function Test | (FGSS) Function Test | 2008-10-13 | 2008-10-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3SF1265W62A10.4 (FGSS) Function Test | Activity | 3SF1265W62A10.4 | (FGSS) Function Test | 2008-10-13 00:00:00 | 2008-10-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4063 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Gas Supply System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Gas Supply System | 3SF1265W62A11.4 | (FGSS) Gas Receiving upto GT Final Control Valve | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-10-19 | 2008-10-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Gas Supply System 3SF1265W62A11.4 (FGSS) Gas Receiving upto GT Final Control Valve | Activity | 3SF1265W62A11.4 | (FGSS) Gas Receiving upto GT Final Control Valve | 2008-10-19 00:00:00 | 2008-10-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4065 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Washing & Drain System | 3PF1265W42A02.2P | (Washing & Drain system Skid) P.O & Procurement | (Washing & Drain system Skid) P.O & Procurement | 2007-04-30 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Washing & Drain System 3PF1265W42A02.2P (Washing & Drain system Skid) P.O & Procurement | Activity | 3PF1265W42A02.2P | (Washing & Drain system Skid) P.O & Procurement | 2007-04-30 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4066 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Washing & Drain System | 3CF1265W16A01.2 | (Washing & Drain system Skid) FDN Work | (Washing & Drain system Skid) FDN Work | 2007-11-28 | 2008-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Washing & Drain System 3CF1265W16A01.2 (Washing & Drain system Skid) FDN Work | Activity | 3CF1265W16A01.2 | (Washing & Drain system Skid) FDN Work | 2007-11-28 00:00:00 | 2008-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4067 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Washing & Drain System | 3PF1265W42A03.2T | (Washing & Drain system Skid) Transportation | (Washing & Drain system Skid) Transportation | 2008-04-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Washing & Drain System 3PF1265W42A03.2T (Washing & Drain system Skid) Transportation | Activity | 3PF1265W42A03.2T | (Washing & Drain system Skid) Transportation | 2008-04-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4068 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Washing & Drain System | 3CF1265W42A04.2 | (Washing & Drain system Skid) Installation | (Washing & Drain system Skid) Installation | 2008-06-14 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Washing & Drain System 3CF1265W42A04.2 (Washing & Drain system Skid) Installation | Activity | 3CF1265W42A04.2 | (Washing & Drain system Skid) Installation | 2008-06-14 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4069 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Washing & Drain System | 3CF1265W58A05.2 | (Washing & Drain system Skid) Piping work | (Washing & Drain system Skid) Piping work | 2008-07-02 | 2008-08-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Washing & Drain System 3CF1265W58A05.2 (Washing & Drain system Skid) Piping work | Activity | 3CF1265W58A05.2 | (Washing & Drain system Skid) Piping work | 2008-07-02 00:00:00 | 2008-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4070 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Washing & Drain System | 3CF1265W74A07.2 | (Washing & Drain system Skid) Installation- Elec. | (Washing & Drain system Skid) Installation- Elec. | 2008-08-02 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Washing & Drain System 3CF1265W74A07.2 (Washing & Drain system Skid) Installation- Elec. | Activity | 3CF1265W74A07.2 | (Washing & Drain system Skid) Installation- Elec. | 2008-08-02 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4071 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Washing & Drain System | 3CF1265W90A08.2 | (Washing & Drain system Skid) Installation- I&C | (Washing & Drain system Skid) Installation- I&C | 2008-08-02 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Washing & Drain System 3CF1265W90A08.2 (Washing & Drain system Skid) Installation- I&C | Activity | 3CF1265W90A08.2 | (Washing & Drain system Skid) Installation- I&C | 2008-08-02 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4072 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Washing & Drain System | 3CF1265W62A06.2 | (Washing & Drain system Skid) Flushing | (Washing & Drain system Skid) Flushing | 2008-08-02 | 2008-08-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Washing & Drain System 3CF1265W62A06.2 (Washing & Drain system Skid) Flushing | Activity | 3CF1265W62A06.2 | (Washing & Drain system Skid) Flushing | 2008-08-02 00:00:00 | 2008-08-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4073 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Washing & Drain System | 3SF1265W62A09.2 | (Washing & Drain system Skid) Loop chek | (Washing & Drain system Skid) Loop chek | 2008-08-16 | 2008-08-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Washing & Drain System 3SF1265W62A09.2 (Washing & Drain system Skid) Loop chek | Activity | 3SF1265W62A09.2 | (Washing & Drain system Skid) Loop chek | 2008-08-16 00:00:00 | 2008-08-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4074 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Washing & Drain System | 3SF1265W62A10.2 | (Washing & Drain system Skid) Function Test | (Washing & Drain system Skid) Function Test | 2008-08-21 | 2008-08-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Washing & Drain System 3SF1265W62A10.2 (Washing & Drain system Skid) Function Test | Activity | 3SF1265W62A10.2 | (Washing & Drain system Skid) Function Test | 2008-08-21 00:00:00 | 2008-08-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4075 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Washing & Drain System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Washing & Drain System | 3SF1265W62A11.2 | (Washing & Drain system Skid) Load(Running) Test | (Washing & Drain system Skid) Load(Running) Test | 2008-08-24 | 2008-08-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Washing & Drain System 3SF1265W62A11.2 (Washing & Drain system Skid) Load(Running) Test | Activity | 3SF1265W62A11.2 | (Washing & Drain system Skid) Load(Running) Test | 2008-08-24 00:00:00 | 2008-08-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4077 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3PF1265W42A02.3P | (Fuel oil injection System) P.O & Procurement | (Fuel oil injection System) P.O & Procurement | 2007-04-30 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3PF1265W42A02.3P (Fuel oil injection System) P.O & Procurement | Activity | 3PF1265W42A02.3P | (Fuel oil injection System) P.O & Procurement | 2007-04-30 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4078 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3PF1265W42A12.1P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3PF1265W42A12.1P (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | Activity | 3PF1265W42A12.1P | (Fuel oil injection Pump & actuator) P.O & Procurement(incl. Main oil pump) | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4079 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3PF1265W42A15.1P | (Water injection System) P.O & Procurement | (Water injection System) P.O & Procurement | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3PF1265W42A15.1P (Water injection System) P.O & Procurement | Activity | 3PF1265W42A15.1P | (Water injection System) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4080 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3CF1265W16A01.3 | (Fuel oil injection System) FDN Work | (Fuel oil injection System) FDN Work | 2007-11-28 | 2008-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3CF1265W16A01.3 (Fuel oil injection System) FDN Work | Activity | 3CF1265W16A01.3 | (Fuel oil injection System) FDN Work | 2007-11-28 00:00:00 | 2008-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4081 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3CF1265W16A11.1 | (Fuel oil injection Pump & actuator) FDN Work | (Fuel oil injection Pump & actuator) FDN Work | 2007-11-28 | 2008-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3CF1265W16A11.1 (Fuel oil injection Pump & actuator) FDN Work | Activity | 3CF1265W16A11.1 | (Fuel oil injection Pump & actuator) FDN Work | 2007-11-28 00:00:00 | 2008-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4082 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3CF1265W16A15.1 | (Water injection System) FDN Work | (Water injection System) FDN Work | 2007-11-28 | 2008-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3CF1265W16A15.1 (Water injection System) FDN Work | Activity | 3CF1265W16A15.1 | (Water injection System) FDN Work | 2007-11-28 00:00:00 | 2008-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4083 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3PF1265W42A13.1T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3PF1265W42A13.1T (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | Activity | 3PF1265W42A13.1T | (Fuel oil injection Pump & actuator) Transportation(incl. Main oil pump) | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4084 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3PF1265W42A16.1T | (Water injection System) Transportation | (Water injection System) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3PF1265W42A16.1T (Water injection System) Transportation | Activity | 3PF1265W42A16.1T | (Water injection System) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4085 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3PF1265W42A03.3T | (Fuel oil injection System) Transportation | (Fuel oil injection System) Transportation | 2008-04-30 | 2008-06-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3PF1265W42A03.3T (Fuel oil injection System) Transportation | Activity | 3PF1265W42A03.3T | (Fuel oil injection System) Transportation | 2008-04-30 00:00:00 | 2008-06-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4086 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3CF1265W42A14.1 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3CF1265W42A14.1 (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | Activity | 3CF1265W42A14.1 | (Fuel oil injection Pump & actuator) Installation(incl. Main oil pump) | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4087 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3CF1265W42A17.1 | (Water injection System) Installation | (Water injection System) Installation | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3CF1265W42A17.1 (Water injection System) Installation | Activity | 3CF1265W42A17.1 | (Water injection System) Installation | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4088 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3CF1265W58A18.1 | (Water injection System) Piping work | (Water injection System) Piping work | 2008-05-31 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3CF1265W58A18.1 (Water injection System) Piping work | Activity | 3CF1265W58A18.1 | (Water injection System) Piping work | 2008-05-31 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4089 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3CF1265W42A04.3 | (Fuel oil injection System) Installation | (Fuel oil injection System) Installation | 2008-06-14 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3CF1265W42A04.3 (Fuel oil injection System) Installation | Activity | 3CF1265W42A04.3 | (Fuel oil injection System) Installation | 2008-06-14 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4090 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3CF1265W74A19.1 | (Water injection System) Installation- Elec. | (Water injection System) Installation- Elec. | 2008-06-16 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3CF1265W74A19.1 (Water injection System) Installation- Elec. | Activity | 3CF1265W74A19.1 | (Water injection System) Installation- Elec. | 2008-06-16 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4091 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3CF1265W90A20.1 | (Water injection System) Installation- I&C | (Water injection System) Installation- I&C | 2008-06-16 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3CF1265W90A20.1 (Water injection System) Installation- I&C | Activity | 3CF1265W90A20.1 | (Water injection System) Installation- I&C | 2008-06-16 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4092 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3SF1265W62A21.1 | (Water injection System) Loop chek | (Water injection System) Loop chek | 2008-06-29 | 2008-07-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3SF1265W62A21.1 (Water injection System) Loop chek | Activity | 3SF1265W62A21.1 | (Water injection System) Loop chek | 2008-06-29 00:00:00 | 2008-07-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4093 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3CF1265W58A05.3 | (Fuel oil injection System) Piping work | (Fuel oil injection System) Piping work | 2008-06-30 | 2008-07-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3CF1265W58A05.3 (Fuel oil injection System) Piping work | Activity | 3CF1265W58A05.3 | (Fuel oil injection System) Piping work | 2008-06-30 00:00:00 | 2008-07-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4094 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3SF1265W62A22.1 | (Water injection System) Function Test | (Water injection System) Function Test | 2008-07-04 | 2008-07-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3SF1265W62A22.1 (Water injection System) Function Test | Activity | 3SF1265W62A22.1 | (Water injection System) Function Test | 2008-07-04 00:00:00 | 2008-07-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4095 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3CF1265W74A06.3 | (Fuel oil injection System) Installation- Elec. | (Fuel oil injection System) Installation- Elec. | 2008-07-15 | 2008-07-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3CF1265W74A06.3 (Fuel oil injection System) Installation- Elec. | Activity | 3CF1265W74A06.3 | (Fuel oil injection System) Installation- Elec. | 2008-07-15 00:00:00 | 2008-07-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4096 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3CF1265W90A07.3 | (Fuel oil injection System) Installation- I&C | (Fuel oil injection System) Installation- I&C | 2008-07-15 | 2008-07-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3CF1265W90A07.3 (Fuel oil injection System) Installation- I&C | Activity | 3CF1265W90A07.3 | (Fuel oil injection System) Installation- I&C | 2008-07-15 00:00:00 | 2008-07-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4097 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3SF1265W62A08.3 | (Fuel oil injection System) Loop chek | (Fuel oil injection System) Loop chek | 2008-07-29 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3SF1265W62A08.3 (Fuel oil injection System) Loop chek | Activity | 3SF1265W62A08.3 | (Fuel oil injection System) Loop chek | 2008-07-29 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4098 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3SF1265W62A23.1 | (Water injection System) Load Test | (Water injection System) Load Test | 2008-08-12 | 2008-08-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3SF1265W62A23.1 (Water injection System) Load Test | Activity | 3SF1265W62A23.1 | (Water injection System) Load Test | 2008-08-12 00:00:00 | 2008-08-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4099 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3SF1265W62A09.3 | (Fuel oil injection System) Function Test | (Fuel oil injection System) Function Test | 2008-08-15 | 2008-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3SF1265W62A09.3 (Fuel oil injection System) Function Test | Activity | 3SF1265W62A09.3 | (Fuel oil injection System) Function Test | 2008-08-15 00:00:00 | 2008-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4100 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fuel Oil Injection System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fuel Oil Injection System | 3SF1265W62A10.3 | (Fuel oil injection System) Flushing | (Fuel oil injection System) Flushing | 2008-08-30 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fuel Oil Injection System 3SF1265W62A10.3 (Fuel oil injection System) Flushing | Activity | 3SF1265W62A10.3 | (Fuel oil injection System) Flushing | 2008-08-30 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4102 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Vibration Monitoring System (VMS) | 3PF1260W86A02.1P | (VMS) P.O & Procurement for GT | (VMS) P.O & Procurement for GT | 2007-08-31 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Vibration Monitoring System (VMS) 3PF1260W86A02.1P (VMS) P.O & Procurement for GT | Activity | 3PF1260W86A02.1P | (VMS) P.O & Procurement for GT | 2007-08-31 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4103 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Vibration Monitoring System (VMS) | 3PF1260W86A03.1T | (VMS) Transportation for GT | (VMS) Transportation for GT | 2008-07-31 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Vibration Monitoring System (VMS) 3PF1260W86A03.1T (VMS) Transportation for GT | Activity | 3PF1260W86A03.1T | (VMS) Transportation for GT | 2008-07-31 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4104 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Vibration Monitoring System (VMS) | 3CF1260W86A04.1 | (VMS) Installation for GT | (VMS) Installation for GT | 2008-10-15 | 2008-10-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Vibration Monitoring System (VMS) 3CF1260W86A04.1 (VMS) Installation for GT | Activity | 3CF1260W86A04.1 | (VMS) Installation for GT | 2008-10-15 00:00:00 | 2008-10-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4105 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Vibration Monitoring System (VMS) | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Vibration Monitoring System (VMS) | 3SF1260W62A05.1 | (VMS) Function Test for GT | (VMS) Function Test for GT | 2008-10-23 | 2008-10-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Vibration Monitoring System (VMS) 3SF1260W62A05.1 (VMS) Function Test for GT | Activity | 3SF1260W62A05.1 | (VMS) Function Test for GT | 2008-10-23 00:00:00 | 2008-10-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4107 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3EF1225W00A01.1 | (CCWS) CCW H/EX key data | (CCWS) CCW H/EX key data | 2007-04-30 | 2007-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3EF1225W00A01.1 (CCWS) CCW H/EX key data | Activity | 3EF1225W00A01.1 | (CCWS) CCW H/EX key data | 2007-04-30 00:00:00 | 2007-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4108 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3PF1225W42A12.1P | (EXP Head Tank) P.O & Procurement | (EXP Head Tank) P.O & Procurement | 2007-07-03 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3PF1225W42A12.1P (EXP Head Tank) P.O & Procurement | Activity | 3PF1225W42A12.1P | (EXP Head Tank) P.O & Procurement | 2007-07-03 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4109 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3EF1225W16A09.1 | (EXP Head Tank) FDN Design | (EXP Head Tank) FDN Design | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3EF1225W16A09.1 (EXP Head Tank) FDN Design | Activity | 3EF1225W16A09.1 | (EXP Head Tank) FDN Design | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4110 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3PF1225W42A06.1P | (CCWP) P.O & Procurement for GT | (CCWP) P.O & Procurement for GT | 2007-07-03 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3PF1225W42A06.1P (CCWP) P.O & Procurement for GT | Activity | 3PF1225W42A06.1P | (CCWP) P.O & Procurement for GT | 2007-07-03 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4111 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3EF1225W16A03.1 | (CCWP) FDN Design | (CCWP) FDN Design | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3EF1225W16A03.1 (CCWP) FDN Design | Activity | 3EF1225W16A03.1 | (CCWP) FDN Design | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4112 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3PF1225W42A18.1P | (CCW H/EX) P.O & Procurement_Fin fan cooler | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3PF1225W42A18.1P (CCW H/EX) P.O & Procurement_Fin fan cooler | Activity | 3PF1225W42A18.1P | (CCW H/EX) P.O & Procurement_Fin fan cooler | 2007-07-03 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4113 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3EF1225W16A15.1 | (CCW H/EX) FDN Design_Fin fan cooler | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 | 2007-11-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3EF1225W16A15.1 (CCW H/EX) FDN Design_Fin fan cooler | Activity | 3EF1225W16A15.1 | (CCW H/EX) FDN Design_Fin fan cooler | 2007-07-03 00:00:00 | 2007-11-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4114 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3CF1225W16A04.1 | (CCWP) FDN Work | (CCWP) FDN Work | 2007-11-30 | 2008-01-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3CF1225W16A04.1 (CCWP) FDN Work | Activity | 3CF1225W16A04.1 | (CCWP) FDN Work | 2007-11-30 00:00:00 | 2008-01-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4115 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3CF1225W16A16.1 | (CCW H/EX) FDN Work_Fin fan cooler | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 | 2008-02-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3CF1225W16A16.1 (CCW H/EX) FDN Work_Fin fan cooler | Activity | 3CF1225W16A16.1 | (CCW H/EX) FDN Work_Fin fan cooler | 2007-11-30 00:00:00 | 2008-02-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4116 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3CF1225W16A10.1 | (EXP Head Tank) FDN Work | (EXP Head Tank) FDN Work | 2008-02-01 | 2008-02-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3CF1225W16A10.1 (EXP Head Tank) FDN Work | Activity | 3CF1225W16A10.1 | (EXP Head Tank) FDN Work | 2008-02-01 00:00:00 | 2008-02-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4117 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3PF1225W42A13.1T | (EXP Head Tank) Transportation | (EXP Head Tank) Transportation | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3PF1225W42A13.1T (EXP Head Tank) Transportation | Activity | 3PF1225W42A13.1T | (EXP Head Tank) Transportation | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4118 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3PF1225W42A07.1T | (CCWP) Transportation for GT | (CCWP) Transportation for GT | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3PF1225W42A07.1T (CCWP) Transportation for GT | Activity | 3PF1225W42A07.1T | (CCWP) Transportation for GT | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4119 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3PF1225W42A19.1T | (CCW H/EX) Transportation_Fin fan cooler | (CCW H/EX) Transportation_Fin fan cooler | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3PF1225W42A19.1T (CCW H/EX) Transportation_Fin fan cooler | Activity | 3PF1225W42A19.1T | (CCW H/EX) Transportation_Fin fan cooler | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4120 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3CF1225W58A21.1 | (CCWS) Piping Work | (CCWS) Piping Work | 2008-07-09 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3CF1225W58A21.1 (CCWS) Piping Work | Activity | 3CF1225W58A21.1 | (CCWS) Piping Work | 2008-07-09 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4121 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3CF1225W42A14.1 | (EXP Head Tank) Installation | (EXP Head Tank) Installation | 2008-07-16 | 2008-08-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3CF1225W42A14.1 (EXP Head Tank) Installation | Activity | 3CF1225W42A14.1 | (EXP Head Tank) Installation | 2008-07-16 00:00:00 | 2008-08-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4122 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3CF1225W42A08.1 | (CCWP) Installation | (CCWP) Installation | 2008-07-16 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3CF1225W42A08.1 (CCWP) Installation | Activity | 3CF1225W42A08.1 | (CCWP) Installation | 2008-07-16 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4123 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3CF1225W42A20.1 | (CCW H/EX) Installation_Fin fan cooler | (CCW H/EX) Installation_Fin fan cooler | 2008-07-16 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3CF1225W42A20.1 (CCW H/EX) Installation_Fin fan cooler | Activity | 3CF1225W42A20.1 | (CCW H/EX) Installation_Fin fan cooler | 2008-07-16 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4124 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3CF1225W74A22.1 | (CCWS) Installation & Test - Elec. | (CCWS) Installation & Test - Elec. | 2008-07-30 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3CF1225W74A22.1 (CCWS) Installation & Test - Elec. | Activity | 3CF1225W74A22.1 | (CCWS) Installation & Test - Elec. | 2008-07-30 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4125 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3CF1225W90A23.1 | (CCWS) Installation & Test - I&C | (CCWS) Installation & Test - I&C | 2008-07-30 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3CF1225W90A23.1 (CCWS) Installation & Test - I&C | Activity | 3CF1225W90A23.1 | (CCWS) Installation & Test - I&C | 2008-07-30 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4126 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3SF1225W62A24.1 | (CCWS) Loop chek | (CCWS) Loop chek | 2008-08-30 | 2008-09-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3SF1225W62A24.1 (CCWS) Loop chek | Activity | 3SF1225W62A24.1 | (CCWS) Loop chek | 2008-08-30 00:00:00 | 2008-09-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4127 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3SF1225W62A25.1 | (CCWS) Function Test | (CCWS) Function Test | 2008-09-09 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3SF1225W62A25.1 (CCWS) Function Test | Activity | 3SF1225W62A25.1 | (CCWS) Function Test | 2008-09-09 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4128 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Closed Cooling Water System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Closed Cooling Water System | 3SF1225W62A26.1 | (CCWS) Flushing | (CCWS) Flushing | 2008-09-14 | 2008-09-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Closed Cooling Water System 3SF1225W62A26.1 (CCWS) Flushing | Activity | 3SF1225W62A26.1 | (CCWS) Flushing | 2008-09-14 00:00:00 | 2008-09-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4130 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fire fighting System | 3PF1265W38A01.2P | (F/F GTG#32) P.O & Procurement_CO2 FF System | (F/F GTG#32) P.O & Procurement_CO2 FF System | 2007-04-30 | 2008-05-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fire fighting System 3PF1265W38A01.2P (F/F GTG#32) P.O & Procurement_CO2 FF System | Activity | 3PF1265W38A01.2P | (F/F GTG#32) P.O & Procurement_CO2 FF System | 2007-04-30 00:00:00 | 2008-05-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4131 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fire fighting System | 3PF1265W38A04.2P | (F/F GTG#32) P.O & Procurement_Clean Agent FF System | (F/F GTG#32) P.O & Procurement_Clean Agent FF System | 2007-04-30 | 2008-05-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fire fighting System 3PF1265W38A04.2P (F/F GTG#32) P.O & Procurement_Clean Agent FF System | Activity | 3PF1265W38A04.2P | (F/F GTG#32) P.O & Procurement_Clean Agent FF System | 2007-04-30 00:00:00 | 2008-05-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4132 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fire fighting System | 3PF1265W38A02.2T | (F/F GTG#32) Transportation_CO2 FF System | (F/F GTG#32) Transportation_CO2 FF System | 2008-05-14 | 2008-06-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fire fighting System 3PF1265W38A02.2T (F/F GTG#32) Transportation_CO2 FF System | Activity | 3PF1265W38A02.2T | (F/F GTG#32) Transportation_CO2 FF System | 2008-05-14 00:00:00 | 2008-06-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4133 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fire fighting System | 3PF1265W38A05.2T | (F/F GTG#32)Transportation_Clean Agent FF System | (F/F GTG#32)Transportation_Clean Agent FF System | 2008-05-14 | 2008-06-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fire fighting System 3PF1265W38A05.2T (F/F GTG#32)Transportation_Clean Agent FF System | Activity | 3PF1265W38A05.2T | (F/F GTG#32)Transportation_Clean Agent FF System | 2008-05-14 00:00:00 | 2008-06-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4134 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fire fighting System | 3CF1265W38A03.2 | (F/F GTG#32) Installation_CO2 FF System | (F/F GTG#32) Installation_CO2 FF System | 2008-06-28 | 2008-07-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fire fighting System 3CF1265W38A03.2 (F/F GTG#32) Installation_CO2 FF System | Activity | 3CF1265W38A03.2 | (F/F GTG#32) Installation_CO2 FF System | 2008-06-28 00:00:00 | 2008-07-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4135 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fire fighting System | 3CF1265W38A06.2 | (F/F GTG#32) Installation_Clean Agent FF System | (F/F GTG#32) Installation_Clean Agent FF System | 2008-06-28 | 2008-07-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fire fighting System 3CF1265W38A06.2 (F/F GTG#32) Installation_Clean Agent FF System | Activity | 3CF1265W38A06.2 | (F/F GTG#32) Installation_Clean Agent FF System | 2008-06-28 00:00:00 | 2008-07-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4136 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fire fighting System | 3CF1265W38A07.2 | (F/F GTG#32) Piping work | (F/F GTG#32) Piping work | 2008-07-14 | 2008-08-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fire fighting System 3CF1265W38A07.2 (F/F GTG#32) Piping work | Activity | 3CF1265W38A07.2 | (F/F GTG#32) Piping work | 2008-07-14 00:00:00 | 2008-08-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4137 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fire fighting System | 3SF1265W62A08.2 | (F/F GTG#32) Loop chek | (F/F GTG#32) Loop chek | 2008-08-07 | 2008-08-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fire fighting System 3SF1265W62A08.2 (F/F GTG#32) Loop chek | Activity | 3SF1265W62A08.2 | (F/F GTG#32) Loop chek | 2008-08-07 00:00:00 | 2008-08-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4138 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fire fighting System | 3SF1265W62A09.20 | (F/F GTG#32) Function Test(incl. Alarm Test) | (F/F GTG#32) Function Test(incl. Alarm Test) | 2008-08-14 | 2008-08-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fire fighting System 3SF1265W62A09.20 (F/F GTG#32) Function Test(incl. Alarm Test) | Activity | 3SF1265W62A09.20 | (F/F GTG#32) Function Test(incl. Alarm Test) | 2008-08-14 00:00:00 | 2008-08-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4139 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Fire fighting System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Fire fighting System | 3SF1265W62A10.20 | (F/F GTG#32) CO2 Discharge Test | (F/F GTG#32) CO2 Discharge Test | 2008-08-24 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Fire fighting System 3SF1265W62A10.20 (F/F GTG#32) CO2 Discharge Test | Activity | 3SF1265W62A10.20 | (F/F GTG#32) CO2 Discharge Test | 2008-08-24 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4141 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3PF1265W42A02.6P | (Purge Air System) P.O & Procurement | (Purge Air System) P.O & Procurement | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3PF1265W42A02.6P (Purge Air System) P.O & Procurement | Activity | 3PF1265W42A02.6P | (Purge Air System) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4142 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3PF1265W42A12.6P | (Control Oil) P.O & Procurement | (Control Oil) P.O & Procurement | 2007-04-30 | 2008-03-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3PF1265W42A12.6P (Control Oil) P.O & Procurement | Activity | 3PF1265W42A12.6P | (Control Oil) P.O & Procurement | 2007-04-30 00:00:00 | 2008-03-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4143 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3CF1265W16A01.6 | (Purge Air System) FDN Work | (Purge Air System) FDN Work | 2007-11-28 | 2008-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3CF1265W16A01.6 (Purge Air System) FDN Work | Activity | 3CF1265W16A01.6 | (Purge Air System) FDN Work | 2007-11-28 00:00:00 | 2008-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4144 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3CF1265W16A11.6 | (Control Oil) FDN Work | (Control Oil) FDN Work | 2007-11-28 | 2008-01-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3CF1265W16A11.6 (Control Oil) FDN Work | Activity | 3CF1265W16A11.6 | (Control Oil) FDN Work | 2007-11-28 00:00:00 | 2008-01-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4145 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3PF1265W42A03.6T | (Purge Air System) Transportation | (Purge Air System) Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3PF1265W42A03.6T (Purge Air System) Transportation | Activity | 3PF1265W42A03.6T | (Purge Air System) Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4146 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3PF1265W42A13.6T | (Control Oil)Transportation | (Control Oil)Transportation | 2008-04-01 | 2008-05-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3PF1265W42A13.6T (Control Oil)Transportation | Activity | 3PF1265W42A13.6T | (Control Oil)Transportation | 2008-04-01 00:00:00 | 2008-05-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4147 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3CF1265W42A04.6 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3CF1265W42A04.6 (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | Activity | 3CF1265W42A04.6 | (Purge Air System) Installation(incl. Receiver TK, Air Comp.) | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4148 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3CF1265W42A14.6 | (Control Oil) Installation | (Control Oil) Installation | 2008-05-16 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3CF1265W42A14.6 (Control Oil) Installation | Activity | 3CF1265W42A14.6 | (Control Oil) Installation | 2008-05-16 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4149 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3CF1265W16A05.6 | (Purge Air System) Piping work | (Purge Air System) Piping work | 2008-05-31 | 2008-06-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3CF1265W16A05.6 (Purge Air System) Piping work | Activity | 3CF1265W16A05.6 | (Purge Air System) Piping work | 2008-05-31 00:00:00 | 2008-06-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4150 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3CF1265W16A15.6 | (Control Oil) Piping work | (Control Oil) Piping work | 2008-05-31 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3CF1265W16A15.6 (Control Oil) Piping work | Activity | 3CF1265W16A15.6 | (Control Oil) Piping work | 2008-05-31 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4151 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3CF1265W74A06.6 | (Purge Air System) Installation- Elec. | (Purge Air System) Installation- Elec. | 2008-06-16 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3CF1265W74A06.6 (Purge Air System) Installation- Elec. | Activity | 3CF1265W74A06.6 | (Purge Air System) Installation- Elec. | 2008-06-16 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4152 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3CF1265W90A07.6 | (Purge Air System) Installation- I&C | (Purge Air System) Installation- I&C | 2008-06-16 | 2008-06-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3CF1265W90A07.6 (Purge Air System) Installation- I&C | Activity | 3CF1265W90A07.6 | (Purge Air System) Installation- I&C | 2008-06-16 00:00:00 | 2008-06-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4153 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3SF1265W62A08.6 | (Purge Air System) Loop chek | (Purge Air System) Loop chek | 2008-06-29 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3SF1265W62A08.6 (Purge Air System) Loop chek | Activity | 3SF1265W62A08.6 | (Purge Air System) Loop chek | 2008-06-29 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4154 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3SF1265W62A09.6 | (Purge Air System) Function Test | (Purge Air System) Function Test | 2008-07-02 | 2008-07-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3SF1265W62A09.6 (Purge Air System) Function Test | Activity | 3SF1265W62A09.6 | (Purge Air System) Function Test | 2008-07-02 00:00:00 | 2008-07-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4155 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3CF1265W74A16.6 | (Control Oil) Installation- Elec. | (Control Oil) Installation- Elec. | 2008-07-02 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3CF1265W74A16.6 (Control Oil) Installation- Elec. | Activity | 3CF1265W74A16.6 | (Control Oil) Installation- Elec. | 2008-07-02 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4156 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3CF1265W90A17.6 | (Control Oil) Installation- I&C | (Control Oil) Installation- I&C | 2008-07-02 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3CF1265W90A17.6 (Control Oil) Installation- I&C | Activity | 3CF1265W90A17.6 | (Control Oil) Installation- I&C | 2008-07-02 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4157 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3SF1265W62A10.6 | (Purge Air System) Load Test | (Purge Air System) Load Test | 2008-07-05 | 2008-07-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3SF1265W62A10.6 (Purge Air System) Load Test | Activity | 3SF1265W62A10.6 | (Purge Air System) Load Test | 2008-07-05 00:00:00 | 2008-07-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4158 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3SF1265W62A18.6 | (Control Oil) Loop chek | (Control Oil) Loop chek | 2008-07-16 | 2008-07-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3SF1265W62A18.6 (Control Oil) Loop chek | Activity | 3SF1265W62A18.6 | (Control Oil) Loop chek | 2008-07-16 00:00:00 | 2008-07-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4159 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3SF1265W62A19.6 | (Control Oil) Function Test | (Control Oil) Function Test | 2008-07-21 | 2008-07-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3SF1265W62A19.6 (Control Oil) Function Test | Activity | 3SF1265W62A19.6 | (Control Oil) Function Test | 2008-07-21 00:00:00 | 2008-07-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4160 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Auxiliary System | 3SF1265W62A20.6 | (Control Oil) Flushing | (Control Oil) Flushing | 2008-07-31 | 2008-08-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Auxiliary System 3SF1265W62A20.6 (Control Oil) Flushing | Activity | 3SF1265W62A20.6 | (Control Oil) Flushing | 2008-07-31 00:00:00 | 2008-08-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4162 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9011W62A01.1 | (GTG #32) Fuel Gas System Final Function Test | (GTG #32) Fuel Gas System Final Function Test | 2008-10-28 | 2008-10-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9011W62A01.1 (GTG #32) Fuel Gas System Final Function Test | Activity | 3SF9011W62A01.1 | (GTG #32) Fuel Gas System Final Function Test | 2008-10-28 00:00:00 | 2008-10-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4163 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9011W62A02.1 | (GTG #32) Turning Gear Operation | (GTG #32) Turning Gear Operation | 2008-10-31 | 2008-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9011W62A02.1 (GTG #32) Turning Gear Operation | Activity | 3SF9011W62A02.1 | (GTG #32) Turning Gear Operation | 2008-10-31 00:00:00 | 2008-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4164 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9011W62A03.1 | (GTG #32) Initial Firing with FSNL | (GTG #32) Initial Firing with FSNL | 2008-11-02 | 2008-11-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9011W62A03.1 (GTG #32) Initial Firing with FSNL | Activity | 3SF9011W62A03.1 | (GTG #32) Initial Firing with FSNL | 2008-11-02 00:00:00 | 2008-11-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4165 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9012W62A04.1 | (GTG #32) TBN & GEN Protection Test | (GTG #32) TBN & GEN Protection Test | 2008-11-03 | 2008-11-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9012W62A04.1 (GTG #32) TBN & GEN Protection Test | Activity | 3SF9012W62A04.1 | (GTG #32) TBN & GEN Protection Test | 2008-11-03 00:00:00 | 2008-11-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4166 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9012W62A05.1 | (GTG #32) 1st Synchronization | (GTG #32) 1st Synchronization | 2008-11-05 | 2008-11-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9012W62A05.1 (GTG #32) 1st Synchronization | Activity | 3SF9012W62A05.1 | (GTG #32) 1st Synchronization | 2008-11-05 00:00:00 | 2008-11-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4167 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9012W62A06.1 | (GTG #32) Optimization with Fuel Gas | (GTG #32) Optimization with Fuel Gas | 2008-11-07 | 2008-11-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9012W62A06.1 (GTG #32) Optimization with Fuel Gas | Activity | 3SF9012W62A06.1 | (GTG #32) Optimization with Fuel Gas | 2008-11-07 00:00:00 | 2008-11-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4168 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9012W62A07.1 | (GTG #32) Fuel Oil System Final Function Test | (GTG #32) Fuel Oil System Final Function Test | 2008-11-22 | 2008-12-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9012W62A07.1 (GTG #32) Fuel Oil System Final Function Test | Activity | 3SF9012W62A07.1 | (GTG #32) Fuel Oil System Final Function Test | 2008-11-22 00:00:00 | 2008-12-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4169 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9012W62A08.1 | (GTG #32) Optimization with Fuel Oil | (GTG #32) Optimization with Fuel Oil | 2008-12-02 | 2008-12-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9012W62A08.1 (GTG #32) Optimization with Fuel Oil | Activity | 3SF9012W62A08.1 | (GTG #32) Optimization with Fuel Oil | 2008-12-02 00:00:00 | 2008-12-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4170 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9012W62A13.1 | (GTG #32) Fuel Change-Over Test | (GTG #32) Fuel Change-Over Test | 2009-01-01 | 2009-01-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9012W62A13.1 (GTG #32) Fuel Change-Over Test | Activity | 3SF9012W62A13.1 | (GTG #32) Fuel Change-Over Test | 2009-01-01 00:00:00 | 2009-01-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4171 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9012W62A09.1 | (GTG #32) Black start Test with GT | (GTG #32) Black start Test with GT | 2009-01-01 | 2009-01-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9012W62A09.1 (GTG #32) Black start Test with GT | Activity | 3SF9012W62A09.1 | (GTG #32) Black start Test with GT | 2009-01-01 00:00:00 | 2009-01-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4172 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9012W62A10.1 | (GTG #32) Trial Run Test | (GTG #32) Trial Run Test | 2009-01-02 | 2009-01-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9012W62A10.1 (GTG #32) Trial Run Test | Activity | 3SF9012W62A10.1 | (GTG #32) Trial Run Test | 2009-01-02 00:00:00 | 2009-01-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4173 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9013W62A11.1 | (GTG #32) Reliability Test | (GTG #32) Reliability Test | 2009-01-03 | 2009-01-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9013W62A11.1 (GTG #32) Reliability Test | Activity | 3SF9013W62A11.1 | (GTG #32) Reliability Test | 2009-01-03 00:00:00 | 2009-01-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4174 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Gas Turbine & Generator #31 & #32 > GTG #32 > GTG #32 Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Gas Turbine & Generator #31 & #32 | GTG #32 | GTG #32 Commissioning | 3SF9013W62A12.1 | (GTG #32) Performance Test (Fuel Gas & Fuel Oil) | (GTG #32) Performance Test (Fuel Gas & Fuel Oil) | 2009-01-18 | 2009-02-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Gas Turbine & Generator #31 & #32 GTG #32 GTG #32 Commissioning 3SF9013W62A12.1 (GTG #32) Performance Test (Fuel Gas & Fuel Oil) | Activity | 3SF9013W62A12.1 | (GTG #32) Performance Test (Fuel Gas & Fuel Oil) | 2009-01-18 00:00:00 | 2009-02-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4177 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG Common |  | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | (HRSG #31/#32) HRSG Process, GA Data | 2007-03-01 | 2007-03-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG Common 3EF1600W00A02 (HRSG #31/#32) HRSG Process, GA Data | Activity | 3EF1600W00A02 | (HRSG #31/#32) HRSG Process, GA Data | 2007-03-01 00:00:00 | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4178 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG Common |  | 3EF1600W00A03 | (HRSG #31/#32) Instrument, Service Air Data | (HRSG #31/#32) Instrument, Service Air Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG Common 3EF1600W00A03 (HRSG #31/#32) Instrument, Service Air Data | Activity | 3EF1600W00A03 | (HRSG #31/#32) Instrument, Service Air Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4179 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG Common |  | 3EF1600W00A04 | (HRSG #31/#32) Utility Consumption Data | (HRSG #31/#32) Utility Consumption Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG Common 3EF1600W00A04 (HRSG #31/#32) Utility Consumption Data | Activity | 3EF1600W00A04 | (HRSG #31/#32) Utility Consumption Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4180 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG Common |  | 3EF1600W00A05 | (HRSG #31/#32) Emergency Load Data | (HRSG #31/#32) Emergency Load Data | 2007-03-01 | 2007-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG Common 3EF1600W00A05 (HRSG #31/#32) Emergency Load Data | Activity | 3EF1600W00A05 | (HRSG #31/#32) Emergency Load Data | 2007-03-01 00:00:00 | 2007-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4181 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG Common | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG Common |  | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | (HRSG #31/#32) P&ID & System Design | 2007-05-18 | 2008-05-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG Common 3EF1600W00A01.0 (HRSG #31/#32) P&ID & System Design | Activity | 3EF1600W00A01.0 | (HRSG #31/#32) P&ID & System Design | 2007-05-18 00:00:00 | 2008-05-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4184 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | HRSG LEB | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | (HRSG #31 LEB) GA & Load Data to Civil Design | 2007-06-20 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 HRSG LEB 3EF1600W00A01 (HRSG #31 LEB) GA & Load Data to Civil Design | Activity | 3EF1600W00A01 | (HRSG #31 LEB) GA & Load Data to Civil Design | 2007-06-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4185 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | HRSG LEB | 3EF1600W32A02 | (HRSG #31 LEB) Building Design | (HRSG #31 LEB) Building Design | 2007-06-20 | 2007-11-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 HRSG LEB 3EF1600W32A02 (HRSG #31 LEB) Building Design | Activity | 3EF1600W32A02 | (HRSG #31 LEB) Building Design | 2007-06-20 00:00:00 | 2007-11-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4186 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | HRSG LEB | 3PF1600W90A10P | (HRSG #31 LEB) P.O & Procurement - I&C | (HRSG #31 LEB) P.O & Procurement - I&C | 2007-09-15 | 2008-08-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 HRSG LEB 3PF1600W90A10P (HRSG #31 LEB) P.O & Procurement - I&C | Activity | 3PF1600W90A10P | (HRSG #31 LEB) P.O & Procurement - I&C | 2007-09-15 00:00:00 | 2008-08-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4187 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | HRSG LEB | 3PF1600W74A06P | (HRSG #31 LEB) P.O & Procurement - Elec | (HRSG #31 LEB) P.O & Procurement - Elec | 2007-09-15 | 2008-08-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 HRSG LEB 3PF1600W74A06P (HRSG #31 LEB) P.O & Procurement - Elec | Activity | 3PF1600W74A06P | (HRSG #31 LEB) P.O & Procurement - Elec | 2007-09-15 00:00:00 | 2008-08-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4188 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | HRSG LEB | 3CF1600W16A03 | (HRSG #31 LEB) FDN Work | (HRSG #31 LEB) FDN Work | 2008-03-03 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 HRSG LEB 3CF1600W16A03 (HRSG #31 LEB) FDN Work | Activity | 3CF1600W16A03 | (HRSG #31 LEB) FDN Work | 2008-03-03 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4189 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | HRSG LEB | 3CF1600W32A04 | (HRSG #31 LEB) Structure Work | (HRSG #31 LEB) Structure Work | 2008-04-30 | 2008-07-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 HRSG LEB 3CF1600W32A04 (HRSG #31 LEB) Structure Work | Activity | 3CF1600W32A04 | (HRSG #31 LEB) Structure Work | 2008-04-30 00:00:00 | 2008-07-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4190 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | HRSG LEB | 3CF1600W36A14 | (HRSG #31 LEB) Installation & Test - HVAC | (HRSG #31 LEB) Installation & Test - HVAC | 2008-07-31 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 HRSG LEB 3CF1600W36A14 (HRSG #31 LEB) Installation & Test - HVAC | Activity | 3CF1600W36A14 | (HRSG #31 LEB) Installation & Test - HVAC | 2008-07-31 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4191 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | HRSG LEB | 3PF1600W90A11T | (HRSG #31 LEB) Transportataion - I&C | (HRSG #31 LEB) Transportataion - I&C | 2008-08-24 | 2008-10-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 HRSG LEB 3PF1600W90A11T (HRSG #31 LEB) Transportataion - I&C | Activity | 3PF1600W90A11T | (HRSG #31 LEB) Transportataion - I&C | 2008-08-24 00:00:00 | 2008-10-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4192 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | HRSG LEB | 3PF1600W74A07T | (HRSG #31 LEB) Transportataion - Elec | (HRSG #31 LEB) Transportataion - Elec | 2008-08-24 | 2008-10-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 HRSG LEB 3PF1600W74A07T (HRSG #31 LEB) Transportataion - Elec | Activity | 3PF1600W74A07T | (HRSG #31 LEB) Transportataion - Elec | 2008-08-24 00:00:00 | 2008-10-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4193 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | HRSG LEB | 3CF1600W90A12 | (HRSG #31 LEB) Installation & Test - I&C | (HRSG #31 LEB) Installation & Test - I&C | 2008-10-20 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 HRSG LEB 3CF1600W90A12 (HRSG #31 LEB) Installation & Test - I&C | Activity | 3CF1600W90A12 | (HRSG #31 LEB) Installation & Test - I&C | 2008-10-20 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4194 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | HRSG LEB | 3CF1600W74A08 | (HRSG #31 LEB) Installation & Test - Elec | (HRSG #31 LEB) Installation & Test - Elec | 2008-10-20 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 HRSG LEB 3CF1600W74A08 (HRSG #31 LEB) Installation & Test - Elec | Activity | 3CF1600W74A08 | (HRSG #31 LEB) Installation & Test - Elec | 2008-10-20 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4195 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | HRSG LEB | 3CF1600W38A13 | (HRSG #31 LEB) Installation & Test - Fire Fighting Sys. | (HRSG #31 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 HRSG LEB 3CF1600W38A13 (HRSG #31 LEB) Installation & Test - Fire Fighting Sys. | Activity | 3CF1600W38A13 | (HRSG #31 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4197 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Steel Structure & Casing | 3PF1610W20A03P | (HRSG #31 S/Structure & Casing) P.O & Procurement | (HRSG #31 S/Structure & Casing) P.O & Procurement | 2007-06-14 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Steel Structure & Casing 3PF1610W20A03P (HRSG #31 S/Structure & Casing) P.O & Procurement | Activity | 3PF1610W20A03P | (HRSG #31 S/Structure & Casing) P.O & Procurement | 2007-06-14 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4198 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Steel Structure & Casing | 3EF1610W20A01 | (HRSG #31 S/Structure & Casing) Design | (HRSG #31 S/Structure & Casing) Design | 2007-06-19 | 2008-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Steel Structure & Casing 3EF1610W20A01 (HRSG #31 S/Structure & Casing) Design | Activity | 3EF1610W20A01 | (HRSG #31 S/Structure & Casing) Design | 2007-06-19 00:00:00 | 2008-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4199 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Steel Structure & Casing | 3PF1610W20A04T | (HRSG #31 S/Structure & Casing) Transportation | (HRSG #31 S/Structure & Casing) Transportation | 2008-04-03 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Steel Structure & Casing 3PF1610W20A04T (HRSG #31 S/Structure & Casing) Transportation | Activity | 3PF1610W20A04T | (HRSG #31 S/Structure & Casing) Transportation | 2008-04-03 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4200 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Steel Structure & Casing | 3CF1610W20A05 | (HRSG #31 S/Structure & Casing) S/Structure Installation | (HRSG #31 S/Structure & Casing) S/Structure Installation | 2008-05-19 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Steel Structure & Casing 3CF1610W20A05 (HRSG #31 S/Structure & Casing) S/Structure Installation | Activity | 3CF1610W20A05 | (HRSG #31 S/Structure & Casing) S/Structure Installation | 2008-05-19 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4201 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Steel Structure & Casing | 3CF1610W20A06 | (HRSG #31 S/Structure & Casing) Casing Installation | (HRSG #31 S/Structure & Casing) Casing Installation | 2008-07-19 | 2008-09-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Steel Structure & Casing 3CF1610W20A06 (HRSG #31 S/Structure & Casing) Casing Installation | Activity | 3CF1610W20A06 | (HRSG #31 S/Structure & Casing) Casing Installation | 2008-07-19 00:00:00 | 2008-09-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4203 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3PF1615W64A14P | (HRSG #31 EXP Joint & Bellows) P.O & Procurement | (HRSG #31 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3PF1615W64A14P (HRSG #31 EXP Joint & Bellows) P.O & Procurement | Activity | 3PF1615W64A14P | (HRSG #31 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4204 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3PF1615W64A10P | (HRSG #31 Damper) P.O & Procurement | (HRSG #31 Damper) P.O & Procurement | 2007-06-13 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3PF1615W64A10P (HRSG #31 Damper) P.O & Procurement | Activity | 3PF1615W64A10P | (HRSG #31 Damper) P.O & Procurement | 2007-06-13 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4205 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3PF1615W64A06P | (HRSG #31 Duct) P.O & Procurement | (HRSG #31 Duct) P.O & Procurement | 2007-06-14 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3PF1615W64A06P (HRSG #31 Duct) P.O & Procurement | Activity | 3PF1615W64A06P | (HRSG #31 Duct) P.O & Procurement | 2007-06-14 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4206 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3EF1615W64A04 | (HRSG #31 Duct) Design | (HRSG #31 Duct) Design | 2007-06-18 | 2007-12-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3EF1615W64A04 (HRSG #31 Duct) Design | Activity | 3EF1615W64A04 | (HRSG #31 Duct) Design | 2007-06-18 00:00:00 | 2007-12-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4207 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | (HRSG #31 Duct) GA & Load Data to Civil Design | 2007-06-29 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3EF1615W00A01 (HRSG #31 Duct) GA & Load Data to Civil Design | Activity | 3EF1615W00A01 | (HRSG #31 Duct) GA & Load Data to Civil Design | 2007-06-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4208 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3EF1615W16A02 | (HRSG #31 Duct) FDN Design | (HRSG #31 Duct) FDN Design | 2007-10-03 | 2008-02-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3EF1615W16A02 (HRSG #31 Duct) FDN Design | Activity | 3EF1615W16A02 | (HRSG #31 Duct) FDN Design | 2007-10-03 00:00:00 | 2008-02-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4209 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3CF1615W16A03 | (HRSG #31 Duct) FDN Work | (HRSG #31 Duct) FDN Work | 2008-02-14 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3CF1615W16A03 (HRSG #31 Duct) FDN Work | Activity | 3CF1615W16A03 | (HRSG #31 Duct) FDN Work | 2008-02-14 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4210 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3PF1615W64A07T | (HRSG #31 Duct) Transportation | (HRSG #31 Duct) Transportation | 2008-04-03 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3PF1615W64A07T (HRSG #31 Duct) Transportation | Activity | 3PF1615W64A07T | (HRSG #31 Duct) Transportation | 2008-04-03 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4211 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3PF1615W64A11T | (HRSG #31(HRSG #11 Damper) Transportation | (HRSG #31(HRSG #11 Damper) Transportation | 2008-05-02 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3PF1615W64A11T (HRSG #31(HRSG #11 Damper) Transportation | Activity | 3PF1615W64A11T | (HRSG #31(HRSG #11 Damper) Transportation | 2008-05-02 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4212 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3PF1615W64A15T | (HRSG #31 EXP Joint & Bellows) Transportation | (HRSG #31 EXP Joint & Bellows) Transportation | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3PF1615W64A15T (HRSG #31 EXP Joint & Bellows) Transportation | Activity | 3PF1615W64A15T | (HRSG #31 EXP Joint & Bellows) Transportation | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4213 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3CF1615W64A12 | (HRSG #31 Damper) Installation | (HRSG #31 Damper) Installation | 2008-06-17 | 2008-08-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3CF1615W64A12 (HRSG #31 Damper) Installation | Activity | 3CF1615W64A12 | (HRSG #31 Damper) Installation | 2008-06-17 00:00:00 | 2008-08-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4214 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3CF1615W64A17 | (HRSG #31) Installation_Diverter Damper | (HRSG #31) Installation_Diverter Damper | 2008-07-02 | 2008-07-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3CF1615W64A17 (HRSG #31) Installation_Diverter Damper | Activity | 3CF1615W64A17 | (HRSG #31) Installation_Diverter Damper | 2008-07-02 00:00:00 | 2008-07-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4215 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3CF1615W64A20 | (HRSG #31) Installation_Guillotine Damper | (HRSG #31) Installation_Guillotine Damper | 2008-07-26 | 2008-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3CF1615W64A20 (HRSG #31) Installation_Guillotine Damper | Activity | 3CF1615W64A20 | (HRSG #31) Installation_Guillotine Damper | 2008-07-26 00:00:00 | 2008-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4216 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3CF1615W86A18 | (HRSG #31) Installation_Diverter Damper Control Unit | (HRSG #31) Installation_Diverter Damper Control Unit | 2008-07-26 | 2008-08-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3CF1615W86A18 (HRSG #31) Installation_Diverter Damper Control Unit | Activity | 3CF1615W86A18 | (HRSG #31) Installation_Diverter Damper Control Unit | 2008-07-26 00:00:00 | 2008-08-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4217 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3CF1615W62A19 | (HRSG #31) Diverter Damper Control Unit Flushing | (HRSG #31) Diverter Damper Control Unit Flushing | 2008-08-07 | 2008-08-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3CF1615W62A19 (HRSG #31) Diverter Damper Control Unit Flushing | Activity | 3CF1615W62A19 | (HRSG #31) Diverter Damper Control Unit Flushing | 2008-08-07 00:00:00 | 2008-08-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4218 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3SF1615W62A21 | (HRSG #31) Diverter Damper Function Test for GT #31 | (HRSG #31) Diverter Damper Function Test for GT #31 | 2008-09-02 | 2008-09-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3SF1615W62A21 (HRSG #31) Diverter Damper Function Test for GT #31 | Activity | 3SF1615W62A21 | (HRSG #31) Diverter Damper Function Test for GT #31 | 2008-09-02 00:00:00 | 2008-09-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4219 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3SF1615W62A22 | (HRSG #31) Guillotine Damper Function Test for GT #31 | (HRSG #31) Guillotine Damper Function Test for GT #31 | 2008-09-02 | 2008-09-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3SF1615W62A22 (HRSG #31) Guillotine Damper Function Test for GT #31 | Activity | 3SF1615W62A22 | (HRSG #31) Guillotine Damper Function Test for GT #31 | 2008-09-02 00:00:00 | 2008-09-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4220 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3CF1615W64A08 | (HRSG #31 Duct) Duct Installation | (HRSG #31 Duct) Duct Installation | 2008-11-18 | 2009-02-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3CF1615W64A08 (HRSG #31 Duct) Duct Installation | Activity | 3CF1615W64A08 | (HRSG #31 Duct) Duct Installation | 2008-11-18 00:00:00 | 2009-02-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4221 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Duct | 3CF1615W64A16 | (HRSG #31 EXP Joint & Bellows) Installation | (HRSG #31 EXP Joint & Bellows) Installation | 2009-01-20 | 2009-03-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Duct 3CF1615W64A16 (HRSG #31 EXP Joint & Bellows) Installation | Activity | 3CF1615W64A16 | (HRSG #31 EXP Joint & Bellows) Installation | 2009-01-20 00:00:00 | 2009-03-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4223 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Module | 3PF1610W42A02P | (HRSG #31 Module) P.O & Procurement | (HRSG #31 Module) P.O & Procurement | 2007-07-03 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Module 3PF1610W42A02P (HRSG #31 Module) P.O & Procurement | Activity | 3PF1610W42A02P | (HRSG #31 Module) P.O & Procurement | 2007-07-03 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4224 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Module | 3PF1610W42A03T | (HRSG #31 Module) Transportation | (HRSG #31 Module) Transportation | 2008-05-03 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Module 3PF1610W42A03T (HRSG #31 Module) Transportation | Activity | 3PF1610W42A03T | (HRSG #31 Module) Transportation | 2008-05-03 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4225 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Module | 3CF1610W42A04 | (HRSG #31 Module) Installation | (HRSG #31 Module) Installation | 2008-09-17 | 2008-11-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Module 3CF1610W42A04 (HRSG #31 Module) Installation | Activity | 3CF1610W42A04 | (HRSG #31 Module) Installation | 2008-09-17 00:00:00 | 2008-11-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4227 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Drum | 3PF1645W42A03P | (HRSG #31 Drum) P.O & Procurement | (HRSG #31 Drum) P.O & Procurement | 2007-06-13 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Drum 3PF1645W42A03P (HRSG #31 Drum) P.O & Procurement | Activity | 3PF1645W42A03P | (HRSG #31 Drum) P.O & Procurement | 2007-06-13 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4228 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Drum | 3EF1645W42A01 | (HRSG #31 Drum) Design | (HRSG #31 Drum) Design | 2007-06-18 | 2008-01-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Drum 3EF1645W42A01 (HRSG #31 Drum) Design | Activity | 3EF1645W42A01 | (HRSG #31 Drum) Design | 2007-06-18 00:00:00 | 2008-01-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4229 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Drum | 3PF1645W42A04T | (HRSG #31 Drum) Transportation | (HRSG #31 Drum) Transportation | 2008-07-02 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Drum 3PF1645W42A04T (HRSG #31 Drum) Transportation | Activity | 3PF1645W42A04T | (HRSG #31 Drum) Transportation | 2008-07-02 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4230 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Drum | 3CF1645W42A05 | (HRSG #31 Drum) Installation | (HRSG #31 Drum) Installation | 2008-11-18 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Drum 3CF1645W42A05 (HRSG #31 Drum) Installation | Activity | 3CF1645W42A05 | (HRSG #31 Drum) Installation | 2008-11-18 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4232 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Bypass Stack | 3PF1625W42A10P | (HRSG #31Bypass Stack Silencer) P.O & Procurement | (HRSG #31Bypass Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Bypass Stack 3PF1625W42A10P (HRSG #31Bypass Stack Silencer) P.O & Procurement | Activity | 3PF1625W42A10P | (HRSG #31Bypass Stack Silencer) P.O & Procurement | 2007-06-13 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4233 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Bypass Stack | 3EF1625W42A04 | (HRSG #31 Bypass Stack) Design | (HRSG #31 Bypass Stack) Design | 2007-06-18 | 2007-12-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Bypass Stack 3EF1625W42A04 (HRSG #31 Bypass Stack) Design | Activity | 3EF1625W42A04 | (HRSG #31 Bypass Stack) Design | 2007-06-18 00:00:00 | 2007-12-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4234 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Bypass Stack | 3PF1625W42A06P | (HRSG #31 Bypass Stack) P.O & Procurement | (HRSG #31 Bypass Stack) P.O & Procurement | 2007-07-03 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Bypass Stack 3PF1625W42A06P (HRSG #31 Bypass Stack) P.O & Procurement | Activity | 3PF1625W42A06P | (HRSG #31 Bypass Stack) P.O & Procurement | 2007-07-03 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4235 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Bypass Stack | 3EF1625W00A01 | (HRSG #31 Bypass Stack) GA & Load Data to Civil Design | (HRSG #31 Bypass Stack) GA & Load Data to Civil Design | 2007-08-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Bypass Stack 3EF1625W00A01 (HRSG #31 Bypass Stack) GA & Load Data to Civil Design | Activity | 3EF1625W00A01 | (HRSG #31 Bypass Stack) GA & Load Data to Civil Design | 2007-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4236 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Bypass Stack | 3EF1625W16A02 | (HRSG #31 Bypass Stack) FDN Design | (HRSG #31 Bypass Stack) FDN Design | 2007-11-05 | 2008-03-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Bypass Stack 3EF1625W16A02 (HRSG #31 Bypass Stack) FDN Design | Activity | 3EF1625W16A02 | (HRSG #31 Bypass Stack) FDN Design | 2007-11-05 00:00:00 | 2008-03-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4237 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Bypass Stack | 3CF1625W16A03 | (HRSG #31 Bypass Stack) FDN Work | (HRSG #31 Bypass Stack) FDN Work | 2008-03-13 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Bypass Stack 3CF1625W16A03 (HRSG #31 Bypass Stack) FDN Work | Activity | 3CF1625W16A03 | (HRSG #31 Bypass Stack) FDN Work | 2008-03-13 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4238 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Bypass Stack | 3PF1625W42A07T | (HRSG #31 Bypass Stack) Transportation | (HRSG #31 Bypass Stack) Transportation | 2008-04-02 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Bypass Stack 3PF1625W42A07T (HRSG #31 Bypass Stack) Transportation | Activity | 3PF1625W42A07T | (HRSG #31 Bypass Stack) Transportation | 2008-04-02 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4239 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Bypass Stack | 3PF1625W42A11T | (HRSG #31 Bypass Stack Silencer) Transportation | (HRSG #31 Bypass Stack Silencer) Transportation | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Bypass Stack 3PF1625W42A11T (HRSG #31 Bypass Stack Silencer) Transportation | Activity | 3PF1625W42A11T | (HRSG #31 Bypass Stack Silencer) Transportation | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4240 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Bypass Stack | 3CF1625W42A08 | (HRSG #31 Bypass Stack) Installation | (HRSG #31 Bypass Stack) Installation | 2008-05-31 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Bypass Stack 3CF1625W42A08 (HRSG #31 Bypass Stack) Installation | Activity | 3CF1625W42A08 | (HRSG #31 Bypass Stack) Installation | 2008-05-31 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4241 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Bypass Stack | 3CF1625W42A12 | (HRSG #31 Bypass Stack Silencer) Installation | (HRSG #31 Bypass Stack Silencer) Installation | 2008-08-01 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Bypass Stack 3CF1625W42A12 (HRSG #31 Bypass Stack Silencer) Installation | Activity | 3CF1625W42A12 | (HRSG #31 Bypass Stack Silencer) Installation | 2008-08-01 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4243 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Main Stack | 3PF1625W42A06.0P | (HRSG #31 Main Stack) P.O & Procurement | (HRSG #31 Main Stack) P.O & Procurement | 2007-06-04 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Main Stack 3PF1625W42A06.0P (HRSG #31 Main Stack) P.O & Procurement | Activity | 3PF1625W42A06.0P | (HRSG #31 Main Stack) P.O & Procurement | 2007-06-04 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4244 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Main Stack | 3EF1625W42A01 | (HRSG #31 Main Stack) Design | (HRSG #31 Main Stack) Design | 2007-06-18 | 2007-12-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Main Stack 3EF1625W42A01 (HRSG #31 Main Stack) Design | Activity | 3EF1625W42A01 | (HRSG #31 Main Stack) Design | 2007-06-18 00:00:00 | 2007-12-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4245 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Main Stack | 3PF1625W42A10.0P | (HRSG #31 Main Stack Silencer) P.O & Procurement | (HRSG #31 Main Stack Silencer) P.O & Procurement | 2007-07-27 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Main Stack 3PF1625W42A10.0P (HRSG #31 Main Stack Silencer) P.O & Procurement | Activity | 3PF1625W42A10.0P | (HRSG #31 Main Stack Silencer) P.O & Procurement | 2007-07-27 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4246 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Main Stack | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | (HRSG #31 Main Stack) GA & Load Data to Civil Design | 2007-08-06 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Main Stack 3EF1625W00A02 (HRSG #31 Main Stack) GA & Load Data to Civil Design | Activity | 3EF1625W00A02 | (HRSG #31 Main Stack) GA & Load Data to Civil Design | 2007-08-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4247 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Main Stack | 3EF1625W16A03 | (HRSG #31 Main Stack) FDN Design | (HRSG #31 Main Stack) FDN Design | 2007-11-08 | 2008-03-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Main Stack 3EF1625W16A03 (HRSG #31 Main Stack) FDN Design | Activity | 3EF1625W16A03 | (HRSG #31 Main Stack) FDN Design | 2007-11-08 00:00:00 | 2008-03-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4248 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Main Stack | 3CF1625W16A04 | (HRSG #31Main Stack) FDN Work | (HRSG #31Main Stack) FDN Work | 2008-03-18 | 2008-06-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Main Stack 3CF1625W16A04 (HRSG #31Main Stack) FDN Work | Activity | 3CF1625W16A04 | (HRSG #31Main Stack) FDN Work | 2008-03-18 00:00:00 | 2008-06-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4249 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Main Stack | 3PF1625W42A07.0T | (HRSG #31 Main Stack) Transportation | (HRSG #31 Main Stack) Transportation | 2008-04-03 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Main Stack 3PF1625W42A07.0T (HRSG #31 Main Stack) Transportation | Activity | 3PF1625W42A07.0T | (HRSG #31 Main Stack) Transportation | 2008-04-03 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4250 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Main Stack | 3PF1625W42A11.0T | (HRSG #31 Main Stack Silencer) Transportation | (HRSG #31 Main Stack Silencer) Transportation | 2008-07-16 | 2008-08-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Main Stack 3PF1625W42A11.0T (HRSG #31 Main Stack Silencer) Transportation | Activity | 3PF1625W42A11.0T | (HRSG #31 Main Stack Silencer) Transportation | 2008-07-16 00:00:00 | 2008-08-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4251 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Main Stack | 3CF1625W42A08.0 | (HRSG #31 Main Stack) Installation | (HRSG #31 Main Stack) Installation | 2009-01-14 | 2009-04-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Main Stack 3CF1625W42A08.0 (HRSG #31 Main Stack) Installation | Activity | 3CF1625W42A08.0 | (HRSG #31 Main Stack) Installation | 2009-01-14 00:00:00 | 2009-04-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4252 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Main Stack | 3CF1625W42A12.0 | (HRSG #31 Main Stack Silencer) Installation | (HRSG #31 Main Stack Silencer) Installation | 2009-03-25 | 2009-04-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Main Stack 3CF1625W42A12.0 (HRSG #31 Main Stack Silencer) Installation | Activity | 3CF1625W42A12.0 | (HRSG #31 Main Stack Silencer) Installation | 2009-03-25 00:00:00 | 2009-04-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4254 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Piping Work | 3PF1650W52A02P | (HRSG #31 Insulation) P.O & Procurement | (HRSG #31 Insulation) P.O & Procurement | 2008-01-09 | 2008-12-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Piping Work 3PF1650W52A02P (HRSG #31 Insulation) P.O & Procurement | Activity | 3PF1650W52A02P | (HRSG #31 Insulation) P.O & Procurement | 2008-01-09 00:00:00 | 2008-12-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4255 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Piping Work | 3CF1640W58A05 | (HRSG #31) Piping Work | (HRSG #31) Piping Work | 2008-12-01 | 2009-03-04 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Piping Work 3CF1640W58A05 (HRSG #31) Piping Work | Activity | 3CF1640W58A05 | (HRSG #31) Piping Work | 2008-12-01 00:00:00 | 2009-03-04 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4256 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Piping Work | 3PF1650W52A03T | (HRSG #31 Insulation) Transportation | (HRSG #31 Insulation) Transportation | 2008-12-02 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Piping Work 3PF1650W52A03T (HRSG #31 Insulation) Transportation | Activity | 3PF1650W52A03T | (HRSG #31 Insulation) Transportation | 2008-12-02 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4257 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Piping Work | 3CF1640W62A06 | (HRSG #31) Hydro Test | (HRSG #31) Hydro Test | 2009-03-05 | 2009-03-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Piping Work 3CF1640W62A06 (HRSG #31) Hydro Test | Activity | 3CF1640W62A06 | (HRSG #31) Hydro Test | 2009-03-05 00:00:00 | 2009-03-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4258 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Piping Work | 3CF1650W52A04 | (HRSG #31 Insulation) Installation | (HRSG #31 Insulation) Installation | 2009-03-19 | 2009-04-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Piping Work 3CF1650W52A04 (HRSG #31 Insulation) Installation | Activity | 3CF1650W52A04 | (HRSG #31 Insulation) Installation | 2009-03-19 00:00:00 | 2009-04-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4259 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Piping Work | 3CF1640W60A07 | (HRSG #31) Acid Cleaning | (HRSG #31) Acid Cleaning | 2009-03-30 | 2009-04-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Piping Work 3CF1640W60A07 (HRSG #31) Acid Cleaning | Activity | 3CF1640W60A07 | (HRSG #31) Acid Cleaning | 2009-03-30 00:00:00 | 2009-04-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4261 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | CEMS | 3PF1660W86A04P | (CEMS) P.O & Procurement | (CEMS) P.O & Procurement | 2007-08-29 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 CEMS 3PF1660W86A04P (CEMS) P.O & Procurement | Activity | 3PF1660W86A04P | (CEMS) P.O & Procurement | 2007-08-29 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4262 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | CEMS | 3EF1660W16A01 | (CEMS) FDN Design | (CEMS) FDN Design | 2007-10-30 | 2008-01-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 CEMS 3EF1660W16A01 (CEMS) FDN Design | Activity | 3EF1660W16A01 | (CEMS) FDN Design | 2007-10-30 00:00:00 | 2008-01-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4263 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | CEMS | 3CF1660W16A02 | (CEMS) FDN Work | (CEMS) FDN Work | 2008-01-26 | 2008-03-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 CEMS 3CF1660W16A02 (CEMS) FDN Work | Activity | 3CF1660W16A02 | (CEMS) FDN Work | 2008-01-26 00:00:00 | 2008-03-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4264 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | CEMS | 3PF1660W86A05T | (CEMS) Transportation | (CEMS) Transportation | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 CEMS 3PF1660W86A05T (CEMS) Transportation | Activity | 3PF1660W86A05T | (CEMS) Transportation | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4265 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | CEMS | 3CF1660W86A06 | (CEMS) Installation(incl. Elec, I&C) | (CEMS) Installation(incl. Elec, I&C) | 2008-07-16 | 2008-07-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 CEMS 3CF1660W86A06 (CEMS) Installation(incl. Elec, I&C) | Activity | 3CF1660W86A06 | (CEMS) Installation(incl. Elec, I&C) | 2008-07-16 00:00:00 | 2008-07-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4266 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | CEMS | 3CF1660W62A07 | (CEMS) Loop Test | (CEMS) Loop Test | 2008-08-01 | 2008-08-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 CEMS 3CF1660W62A07 (CEMS) Loop Test | Activity | 3CF1660W62A07 | (CEMS) Loop Test | 2008-08-01 00:00:00 | 2008-08-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4267 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | CEMS | 3SF1615W62A08 | (HRSG #31) CEMS Function Test for GT #31(Bypass stack) | (HRSG #31) CEMS Function Test for GT #31(Bypass stack) | 2008-09-02 | 2008-09-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 CEMS 3SF1615W62A08 (HRSG #31) CEMS Function Test for GT #31(Bypass stack) | Activity | 3SF1615W62A08 | (HRSG #31) CEMS Function Test for GT #31(Bypass stack) | 2008-09-02 00:00:00 | 2008-09-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4269 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Auxiliary System | 3PF1665W42A02P | (HRSG #31 MECH Vendor Equip) P.O & Procurement | (HRSG #31 MECH Vendor Equip) P.O & Procurement | 2007-09-10 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Auxiliary System 3PF1665W42A02P (HRSG #31 MECH Vendor Equip) P.O & Procurement | Activity | 3PF1665W42A02P | (HRSG #31 MECH Vendor Equip) P.O & Procurement | 2007-09-10 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4270 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Auxiliary System | 3PF1655W86A11P | (HRSG #31 I&C Vendor Equip) P.O & Procurement | (HRSG #31 I&C Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-10-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Auxiliary System 3PF1655W86A11P (HRSG #31 I&C Vendor Equip) P.O & Procurement | Activity | 3PF1655W86A11P | (HRSG #31 I&C Vendor Equip) P.O & Procurement | 2007-10-02 00:00:00 | 2008-10-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4271 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Auxiliary System | 3PF1655W70A06P | (HRSG #31 ELEC Vendor Equip) P.O & Procurement | (HRSG #31 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-10-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Auxiliary System 3PF1655W70A06P (HRSG #31 ELEC Vendor Equip) P.O & Procurement | Activity | 3PF1655W70A06P | (HRSG #31 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 00:00:00 | 2008-10-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4272 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Auxiliary System | 3PF1665W42A03T | (HRSG #31 MECH Vendor Equip) Transportation | (HRSG #31 MECH Vendor Equip) Transportation | 2008-10-03 | 2008-11-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Auxiliary System 3PF1665W42A03T (HRSG #31 MECH Vendor Equip) Transportation | Activity | 3PF1665W42A03T | (HRSG #31 MECH Vendor Equip) Transportation | 2008-10-03 00:00:00 | 2008-11-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4273 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Auxiliary System | 3PF1655W86A12T | (HRSG #31 I&C Vendor Equip) Transportation | (HRSG #31 I&C Vendor Equip) Transportation | 2008-10-04 | 2008-11-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Auxiliary System 3PF1655W86A12T (HRSG #31 I&C Vendor Equip) Transportation | Activity | 3PF1655W86A12T | (HRSG #31 I&C Vendor Equip) Transportation | 2008-10-04 00:00:00 | 2008-11-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4274 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Auxiliary System | 3PF1655W70A07T | (HRSG #31 ELEC Vendor Equip) Transportation | (HRSG #31 ELEC Vendor Equip) Transportation | 2008-10-04 | 2008-11-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Auxiliary System 3PF1655W70A07T (HRSG #31 ELEC Vendor Equip) Transportation | Activity | 3PF1655W70A07T | (HRSG #31 ELEC Vendor Equip) Transportation | 2008-10-04 00:00:00 | 2008-11-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4275 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Auxiliary System | 3CF1665W42A04 | (HRSG #31 MECH Vendor Equip) Installation | (HRSG #31 MECH Vendor Equip) Installation | 2008-11-18 | 2009-03-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Auxiliary System 3CF1665W42A04 (HRSG #31 MECH Vendor Equip) Installation | Activity | 3CF1665W42A04 | (HRSG #31 MECH Vendor Equip) Installation | 2008-11-18 00:00:00 | 2009-03-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4276 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Auxiliary System | 3CF1655W86A13 | (HRSG #31 I&C Vendor Equip) Installation | (HRSG #31 I&C Vendor Equip) Installation | 2008-11-19 | 2009-03-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Auxiliary System 3CF1655W86A13 (HRSG #31 I&C Vendor Equip) Installation | Activity | 3CF1655W86A13 | (HRSG #31 I&C Vendor Equip) Installation | 2008-11-19 00:00:00 | 2009-03-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4277 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Auxiliary System | 3CF1655W70A08 | (HRSG #31 ELEC Vendor Equip) Installation | (HRSG #31 ELEC Vendor Equip) Installation | 2008-11-19 | 2009-03-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Auxiliary System 3CF1655W70A08 (HRSG #31 ELEC Vendor Equip) Installation | Activity | 3CF1655W70A08 | (HRSG #31 ELEC Vendor Equip) Installation | 2008-11-19 00:00:00 | 2009-03-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4278 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Auxiliary System | 3CF1655W74A09 | (HRSG #31) Installation & Test - Elec. | (HRSG #31) Installation & Test - Elec. | 2008-12-30 | 2009-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Auxiliary System 3CF1655W74A09 (HRSG #31) Installation & Test - Elec. | Activity | 3CF1655W74A09 | (HRSG #31) Installation & Test - Elec. | 2008-12-30 00:00:00 | 2009-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4279 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Auxiliary System | 3CF1660W90A14 | (HRSG #31) Installation & Test - I&C | (HRSG #31) Installation & Test - I&C | 2008-12-30 | 2009-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Auxiliary System 3CF1660W90A14 (HRSG #31) Installation & Test - I&C | Activity | 3CF1660W90A14 | (HRSG #31) Installation & Test - I&C | 2008-12-30 00:00:00 | 2009-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4281 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Commissioning | 3SF1600W62A01 | (HRSG #31) Cold Commissioning for HRSG #31 | (HRSG #31) Cold Commissioning for HRSG #31 | 2009-04-23 | 2009-05-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Commissioning 3SF1600W62A01 (HRSG #31) Cold Commissioning for HRSG #31 | Activity | 3SF1600W62A01 | (HRSG #31) Cold Commissioning for HRSG #31 | 2009-04-23 00:00:00 | 2009-05-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4282 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #31 > Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #31 | Commissioning | 3SF1600W62A02 | (HRSG #31) Function Test for HRSG #31 | (HRSG #31) Function Test for HRSG #31 | 2009-05-13 | 2009-05-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #31 Commissioning 3SF1600W62A02 (HRSG #31) Function Test for HRSG #31 | Activity | 3SF1600W62A02 | (HRSG #31) Function Test for HRSG #31 | 2009-05-13 00:00:00 | 2009-05-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4285 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | HRSG LEB | 3EF1600W00A01.1 | (HRSG #32 LEB) GA & Load Data to Civil Design | (HRSG #32 LEB) GA & Load Data to Civil Design | 2007-06-20 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 HRSG LEB 3EF1600W00A01.1 (HRSG #32 LEB) GA & Load Data to Civil Design | Activity | 3EF1600W00A01.1 | (HRSG #32 LEB) GA & Load Data to Civil Design | 2007-06-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4286 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | HRSG LEB | 3EF1600W32A02.1 | (HRSG #32 LEB) Building Design | (HRSG #32 LEB) Building Design | 2007-06-20 | 2007-11-20 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 HRSG LEB 3EF1600W32A02.1 (HRSG #32 LEB) Building Design | Activity | 3EF1600W32A02.1 | (HRSG #32 LEB) Building Design | 2007-06-20 00:00:00 | 2007-11-20 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4287 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | HRSG LEB | 3PF1600W90A10.1P | (HRSG #32 LEB) P.O & Procurement - I&C | (HRSG #32 LEB) P.O & Procurement - I&C | 2007-09-15 | 2008-08-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 HRSG LEB 3PF1600W90A10.1P (HRSG #32 LEB) P.O & Procurement - I&C | Activity | 3PF1600W90A10.1P | (HRSG #32 LEB) P.O & Procurement - I&C | 2007-09-15 00:00:00 | 2008-08-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4288 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | HRSG LEB | 3PF1600W74A06.1P | (HRSG #32 LEB) P.O & Procurement - Elec | (HRSG #32 LEB) P.O & Procurement - Elec | 2007-09-15 | 2008-08-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 HRSG LEB 3PF1600W74A06.1P (HRSG #32 LEB) P.O & Procurement - Elec | Activity | 3PF1600W74A06.1P | (HRSG #32 LEB) P.O & Procurement - Elec | 2007-09-15 00:00:00 | 2008-08-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4289 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | HRSG LEB | 3CF1600W16A03.1 | (HRSG #32 LEB)FDN Work | (HRSG #32 LEB)FDN Work | 2008-03-03 | 2008-04-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 HRSG LEB 3CF1600W16A03.1 (HRSG #32 LEB)FDN Work | Activity | 3CF1600W16A03.1 | (HRSG #32 LEB)FDN Work | 2008-03-03 00:00:00 | 2008-04-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4290 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | HRSG LEB | 3CF1600W32A04.1 | (HRSG #32 LEB)Structure Work | (HRSG #32 LEB)Structure Work | 2008-04-30 | 2008-07-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 HRSG LEB 3CF1600W32A04.1 (HRSG #32 LEB)Structure Work | Activity | 3CF1600W32A04.1 | (HRSG #32 LEB)Structure Work | 2008-04-30 00:00:00 | 2008-07-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4291 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | HRSG LEB | 3CF1600W36A13.1 | (HRSG #32 LEB) Installation & Test - HVAC | (HRSG #32 LEB) Installation & Test - HVAC | 2008-07-31 | 2008-09-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 HRSG LEB 3CF1600W36A13.1 (HRSG #32 LEB) Installation & Test - HVAC | Activity | 3CF1600W36A13.1 | (HRSG #32 LEB) Installation & Test - HVAC | 2008-07-31 00:00:00 | 2008-09-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4292 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | HRSG LEB | 3PF1600W90A11.1T | (HRSG #32 LEB) Transportataion - I&C | (HRSG #32 LEB) Transportataion - I&C | 2008-08-24 | 2008-10-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 HRSG LEB 3PF1600W90A11.1T (HRSG #32 LEB) Transportataion - I&C | Activity | 3PF1600W90A11.1T | (HRSG #32 LEB) Transportataion - I&C | 2008-08-24 00:00:00 | 2008-10-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4293 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | HRSG LEB | 3PF1600W74A07.1T | (HRSG #32 LEB) Transportataion - Elec | (HRSG #32 LEB) Transportataion - Elec | 2008-08-24 | 2008-10-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 HRSG LEB 3PF1600W74A07.1T (HRSG #32 LEB) Transportataion - Elec | Activity | 3PF1600W74A07.1T | (HRSG #32 LEB) Transportataion - Elec | 2008-08-24 00:00:00 | 2008-10-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4294 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | HRSG LEB | 3CF1600W90A12.1 | (HRSG #32 LEB) Installation & Test - I&C | (HRSG #32 LEB) Installation & Test - I&C | 2008-10-20 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 HRSG LEB 3CF1600W90A12.1 (HRSG #32 LEB) Installation & Test - I&C | Activity | 3CF1600W90A12.1 | (HRSG #32 LEB) Installation & Test - I&C | 2008-10-20 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4295 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | HRSG LEB | 3CF1600W74A08.1 | (HRSG #32 LEB) Installation & Test - Elec | (HRSG #32 LEB) Installation & Test - Elec | 2008-10-20 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 HRSG LEB 3CF1600W74A08.1 (HRSG #32 LEB) Installation & Test - Elec | Activity | 3CF1600W74A08.1 | (HRSG #32 LEB) Installation & Test - Elec | 2008-10-20 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4296 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > HRSG LEB | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | HRSG LEB | 3CF1600W38A14.1 | (HRSG #32 LEB) Installation & Test - Fire Fighting Sys. | (HRSG #32 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 HRSG LEB 3CF1600W38A14.1 (HRSG #32 LEB) Installation & Test - Fire Fighting Sys. | Activity | 3CF1600W38A14.1 | (HRSG #32 LEB) Installation & Test - Fire Fighting Sys. | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4298 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Steel Structure & Casing | 3PF1610W20A03.1 | (HRSG #32 S/Structure & Casing) P.O & Procurement | (HRSG #32 S/Structure & Casing) P.O & Procurement | 2007-06-14 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Steel Structure & Casing 3PF1610W20A03.1 (HRSG #32 S/Structure & Casing) P.O & Procurement | Activity | 3PF1610W20A03.1 | (HRSG #32 S/Structure & Casing) P.O & Procurement | 2007-06-14 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4299 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Steel Structure & Casing | 3EF1610W20A01.1 | (HRSG #32 S/Structure & Casing) Design | (HRSG #32 S/Structure & Casing) Design | 2007-06-19 | 2008-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Steel Structure & Casing 3EF1610W20A01.1 (HRSG #32 S/Structure & Casing) Design | Activity | 3EF1610W20A01.1 | (HRSG #32 S/Structure & Casing) Design | 2007-06-19 00:00:00 | 2008-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4300 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Steel Structure & Casing | 3PF1610W20A04.1T | (HRSG #32 S/Structure & Casing) Transportation | (HRSG #32 S/Structure & Casing) Transportation | 2008-04-03 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Steel Structure & Casing 3PF1610W20A04.1T (HRSG #32 S/Structure & Casing) Transportation | Activity | 3PF1610W20A04.1T | (HRSG #32 S/Structure & Casing) Transportation | 2008-04-03 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4301 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Steel Structure & Casing | 3CF1610W20A05.1 | (HRSG #32 S/Structure & Casing) S/Structure Installation | (HRSG #32 S/Structure & Casing) S/Structure Installation | 2008-05-19 | 2008-07-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Steel Structure & Casing 3CF1610W20A05.1 (HRSG #32 S/Structure & Casing) S/Structure Installation | Activity | 3CF1610W20A05.1 | (HRSG #32 S/Structure & Casing) S/Structure Installation | 2008-05-19 00:00:00 | 2008-07-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4302 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Steel Structure & Casing | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Steel Structure & Casing | 3CF1610W20A06.1 | (HRSG #32 S/Structure & Casing) Casing Installation | (HRSG #32 S/Structure & Casing) Casing Installation | 2008-07-19 | 2008-09-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Steel Structure & Casing 3CF1610W20A06.1 (HRSG #32 S/Structure & Casing) Casing Installation | Activity | 3CF1610W20A06.1 | (HRSG #32 S/Structure & Casing) Casing Installation | 2008-07-19 00:00:00 | 2008-09-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4304 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3PF1665W64A14.1P | (HRSG #32 EXP Joint & Bellows) P.O & Procurement | (HRSG #32 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3PF1665W64A14.1P (HRSG #32 EXP Joint & Bellows) P.O & Procurement | Activity | 3PF1665W64A14.1P | (HRSG #32 EXP Joint & Bellows) P.O & Procurement | 2007-06-13 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4305 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3PF1615W64A10.1P | (HRSG #32 Damper) P.O & Procurement | (HRSG #32 Damper) P.O & Procurement | 2007-06-13 | 2008-05-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3PF1615W64A10.1P (HRSG #32 Damper) P.O & Procurement | Activity | 3PF1615W64A10.1P | (HRSG #32 Damper) P.O & Procurement | 2007-06-13 00:00:00 | 2008-05-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4306 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3PF1615W64A06.1P | (HRSG #32 Duct) P.O & Procurement | (HRSG #32 Duct) P.O & Procurement | 2007-06-14 | 2008-04-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3PF1615W64A06.1P (HRSG #32 Duct) P.O & Procurement | Activity | 3PF1615W64A06.1P | (HRSG #32 Duct) P.O & Procurement | 2007-06-14 00:00:00 | 2008-04-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4307 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3EF1615W64A01.1 | (HRSG #32 Duct) Design | (HRSG #32 Duct) Design | 2007-06-18 | 2007-12-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3EF1615W64A01.1 (HRSG #32 Duct) Design | Activity | 3EF1615W64A01.1 | (HRSG #32 Duct) Design | 2007-06-18 00:00:00 | 2007-12-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4308 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3EF1615W00A02.1 | (HRSG #32 Duct) GA & Load Data to Civil Design | (HRSG #32 Duct) GA & Load Data to Civil Design | 2007-06-29 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3EF1615W00A02.1 (HRSG #32 Duct) GA & Load Data to Civil Design | Activity | 3EF1615W00A02.1 | (HRSG #32 Duct) GA & Load Data to Civil Design | 2007-06-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4309 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3EF1615W16A03.1 | (HRSG #32 Duct) FDN Design | (HRSG #32 Duct) FDN Design | 2007-10-03 | 2008-02-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3EF1615W16A03.1 (HRSG #32 Duct) FDN Design | Activity | 3EF1615W16A03.1 | (HRSG #32 Duct) FDN Design | 2007-10-03 00:00:00 | 2008-02-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4310 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3CF1615W16A04.1 | (HRSG #32 Duct) FDN Work | (HRSG #32 Duct) FDN Work | 2008-02-14 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3CF1615W16A04.1 (HRSG #32 Duct) FDN Work | Activity | 3CF1615W16A04.1 | (HRSG #32 Duct) FDN Work | 2008-02-14 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4311 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3PF1615W64A07.1T | (HRSG #32 Duct) Transportation | (HRSG #32 Duct) Transportation | 2008-04-03 | 2008-05-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3PF1615W64A07.1T (HRSG #32 Duct) Transportation | Activity | 3PF1615W64A07.1T | (HRSG #32 Duct) Transportation | 2008-04-03 00:00:00 | 2008-05-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4312 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3PF1615W64A11.1T | (HRSG #32 Damper) Transportation | (HRSG #32 Damper) Transportation | 2008-05-02 | 2008-06-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3PF1615W64A11.1T (HRSG #32 Damper) Transportation | Activity | 3PF1615W64A11.1T | (HRSG #32 Damper) Transportation | 2008-05-02 00:00:00 | 2008-06-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4313 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3PF1665W64A15.1T | (HRSG #32 EXP Joint & Bellows) Transportation | (HRSG #32 EXP Joint & Bellows) Transportation | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3PF1665W64A15.1T (HRSG #32 EXP Joint & Bellows) Transportation | Activity | 3PF1665W64A15.1T | (HRSG #32 EXP Joint & Bellows) Transportation | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4314 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3CF1615W64A12.1 | (HRSG #32 Damper) Installation | (HRSG #32 Damper) Installation | 2008-06-17 | 2008-08-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3CF1615W64A12.1 (HRSG #32 Damper) Installation | Activity | 3CF1615W64A12.1 | (HRSG #32 Damper) Installation | 2008-06-17 00:00:00 | 2008-08-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4315 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3CF1615W64A17.1 | (HRSG #32) Installation_Diverter Damper | (HRSG #32) Installation_Diverter Damper | 2008-07-02 | 2008-07-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3CF1615W64A17.1 (HRSG #32) Installation_Diverter Damper | Activity | 3CF1615W64A17.1 | (HRSG #32) Installation_Diverter Damper | 2008-07-02 00:00:00 | 2008-07-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4316 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3CF1615W64A18.1 | (HRSG #32) Installation_Guillotine Damper | (HRSG #32) Installation_Guillotine Damper | 2008-07-26 | 2008-08-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3CF1615W64A18.1 (HRSG #32) Installation_Guillotine Damper | Activity | 3CF1615W64A18.1 | (HRSG #32) Installation_Guillotine Damper | 2008-07-26 00:00:00 | 2008-08-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4317 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3CF1615W86A19.1 | (HRSG #32) Installation_Diverter Damper Control Unit | (HRSG #32) Installation_Diverter Damper Control Unit | 2008-07-26 | 2008-08-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3CF1615W86A19.1 (HRSG #32) Installation_Diverter Damper Control Unit | Activity | 3CF1615W86A19.1 | (HRSG #32) Installation_Diverter Damper Control Unit | 2008-07-26 00:00:00 | 2008-08-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4318 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3CF1615W62A20.1 | (HRSG #32) Diverter Damper Control Unit Flushing | (HRSG #32) Diverter Damper Control Unit Flushing | 2008-08-07 | 2008-08-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3CF1615W62A20.1 (HRSG #32) Diverter Damper Control Unit Flushing | Activity | 3CF1615W62A20.1 | (HRSG #32) Diverter Damper Control Unit Flushing | 2008-08-07 00:00:00 | 2008-08-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4319 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3SF1615W62A21.1 | (HRSG #32) Diverter Damper Function Test for GT #32 | (HRSG #32) Diverter Damper Function Test for GT #32 | 2008-09-02 | 2008-09-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3SF1615W62A21.1 (HRSG #32) Diverter Damper Function Test for GT #32 | Activity | 3SF1615W62A21.1 | (HRSG #32) Diverter Damper Function Test for GT #32 | 2008-09-02 00:00:00 | 2008-09-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4320 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3SF1615W62A22.1 | (HRSG #32) Guillotine Damper Function Test for GT #32 | (HRSG #32) Guillotine Damper Function Test for GT #32 | 2008-09-02 | 2008-09-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3SF1615W62A22.1 (HRSG #32) Guillotine Damper Function Test for GT #32 | Activity | 3SF1615W62A22.1 | (HRSG #32) Guillotine Damper Function Test for GT #32 | 2008-09-02 00:00:00 | 2008-09-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4321 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3CF1615W64A08.1 | (HRSG #32 Duct) Duct Installation | (HRSG #32 Duct) Duct Installation | 2008-11-18 | 2009-02-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3CF1615W64A08.1 (HRSG #32 Duct) Duct Installation | Activity | 3CF1615W64A08.1 | (HRSG #32 Duct) Duct Installation | 2008-11-18 00:00:00 | 2009-02-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4322 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Duct | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Duct | 3CF1665W64A16.1 | (HRSG #32 EXP Joint & Bellows) Installation | (HRSG #32 EXP Joint & Bellows) Installation | 2009-01-20 | 2009-03-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Duct 3CF1665W64A16.1 (HRSG #32 EXP Joint & Bellows) Installation | Activity | 3CF1665W64A16.1 | (HRSG #32 EXP Joint & Bellows) Installation | 2009-01-20 00:00:00 | 2009-03-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4324 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Module | 3PF1610W42A02.1P | (HRSG #32 Module) P.O & Procurement | (HRSG #32 Module) P.O & Procurement | 2007-07-03 | 2008-05-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Module 3PF1610W42A02.1P (HRSG #32 Module) P.O & Procurement | Activity | 3PF1610W42A02.1P | (HRSG #32 Module) P.O & Procurement | 2007-07-03 00:00:00 | 2008-05-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4325 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Module | 3PF1610W42A03.1T | (HRSG #32 Module) Transportation | (HRSG #32 Module) Transportation | 2008-05-03 | 2008-06-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Module 3PF1610W42A03.1T (HRSG #32 Module) Transportation | Activity | 3PF1610W42A03.1T | (HRSG #32 Module) Transportation | 2008-05-03 00:00:00 | 2008-06-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4326 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Module | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Module | 3CF1610W42A04.1 | (HRSG #32 Module) Installation | (HRSG #32 Module) Installation | 2008-09-17 | 2008-11-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Module 3CF1610W42A04.1 (HRSG #32 Module) Installation | Activity | 3CF1610W42A04.1 | (HRSG #32 Module) Installation | 2008-09-17 00:00:00 | 2008-11-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4328 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Drum | 3PF1645W42A03.1P | (HRSG #32 Drum) P.O & Procurement | (HRSG #32 Drum) P.O & Procurement | 2007-06-13 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Drum 3PF1645W42A03.1P (HRSG #32 Drum) P.O & Procurement | Activity | 3PF1645W42A03.1P | (HRSG #32 Drum) P.O & Procurement | 2007-06-13 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4329 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Drum | 3EF1645W42A01.1 | (HRSG #32 Drum) Design | (HRSG #32 Drum) Design | 2007-06-18 | 2008-01-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Drum 3EF1645W42A01.1 (HRSG #32 Drum) Design | Activity | 3EF1645W42A01.1 | (HRSG #32 Drum) Design | 2007-06-18 00:00:00 | 2008-01-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4330 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Drum | 3PF1645W42A04.1T | (HRSG #32 Drum) Transportation | (HRSG #32 Drum) Transportation | 2008-07-02 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Drum 3PF1645W42A04.1T (HRSG #32 Drum) Transportation | Activity | 3PF1645W42A04.1T | (HRSG #32 Drum) Transportation | 2008-07-02 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4331 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Drum | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Drum | 3CF1645W42A05.1 | (HRSG #32 Drum) Installation | (HRSG #32 Drum) Installation | 2008-11-18 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Drum 3CF1645W42A05.1 (HRSG #32 Drum) Installation | Activity | 3CF1645W42A05.1 | (HRSG #32 Drum) Installation | 2008-11-18 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4333 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Bypass Stack | 3PF1625W42A10.1P | (HRSG #32 Bypass Stack Silencer) P.O & Procurement | (HRSG #32 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Bypass Stack 3PF1625W42A10.1P (HRSG #32 Bypass Stack Silencer) P.O & Procurement | Activity | 3PF1625W42A10.1P | (HRSG #32 Bypass Stack Silencer) P.O & Procurement | 2007-06-13 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4334 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Bypass Stack | 3EF1625W42A01.1 | (HRSG #32 Bypass Stack) Design | (HRSG #32 Bypass Stack) Design | 2007-06-18 | 2007-12-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Bypass Stack 3EF1625W42A01.1 (HRSG #32 Bypass Stack) Design | Activity | 3EF1625W42A01.1 | (HRSG #32 Bypass Stack) Design | 2007-06-18 00:00:00 | 2007-12-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4335 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Bypass Stack | 3PF1625W42A06.1P | (HRSG #32 Bypass Stack) P.O & Procurement | (HRSG #32 Bypass Stack) P.O & Procurement | 2007-07-03 | 2008-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Bypass Stack 3PF1625W42A06.1P (HRSG #32 Bypass Stack) P.O & Procurement | Activity | 3PF1625W42A06.1P | (HRSG #32 Bypass Stack) P.O & Procurement | 2007-07-03 00:00:00 | 2008-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4336 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Bypass Stack | 3EF1625W00A02.1 | (HRSG #32 Bypass Stack) GA & Load Data to Civil Design | (HRSG #32 Bypass Stack) GA & Load Data to Civil Design | 2007-08-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Bypass Stack 3EF1625W00A02.1 (HRSG #32 Bypass Stack) GA & Load Data to Civil Design | Activity | 3EF1625W00A02.1 | (HRSG #32 Bypass Stack) GA & Load Data to Civil Design | 2007-08-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4337 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Bypass Stack | 3EF1625W16A03.1 | (HRSG #32 Bypass Stack) FDN Design | (HRSG #32 Bypass Stack) FDN Design | 2007-11-05 | 2008-03-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Bypass Stack 3EF1625W16A03.1 (HRSG #32 Bypass Stack) FDN Design | Activity | 3EF1625W16A03.1 | (HRSG #32 Bypass Stack) FDN Design | 2007-11-05 00:00:00 | 2008-03-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4338 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Bypass Stack | 3CF1625W16A04.1 | (HRSG #32 Bypass Stack) FDN Work | (HRSG #32 Bypass Stack) FDN Work | 2008-03-13 | 2008-05-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Bypass Stack 3CF1625W16A04.1 (HRSG #32 Bypass Stack) FDN Work | Activity | 3CF1625W16A04.1 | (HRSG #32 Bypass Stack) FDN Work | 2008-03-13 00:00:00 | 2008-05-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4339 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Bypass Stack | 3PF1625W42A07.1T | (HRSG #32 Bypass Stack) Transportation | (HRSG #32 Bypass Stack) Transportation | 2008-04-02 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Bypass Stack 3PF1625W42A07.1T (HRSG #32 Bypass Stack) Transportation | Activity | 3PF1625W42A07.1T | (HRSG #32 Bypass Stack) Transportation | 2008-04-02 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4340 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Bypass Stack | 3PF1625W42A11.1T | (HRSG #32 Bypass Stack Silencer) Transportation | (HRSG #32 Bypass Stack Silencer) Transportation | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Bypass Stack 3PF1625W42A11.1T (HRSG #32 Bypass Stack Silencer) Transportation | Activity | 3PF1625W42A11.1T | (HRSG #32 Bypass Stack Silencer) Transportation | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4341 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Bypass Stack | 3CF1625W42A08.1 | (HRSG #32 Bypass Stack) Installation | (HRSG #32 Bypass Stack) Installation | 2008-05-31 | 2008-09-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Bypass Stack 3CF1625W42A08.1 (HRSG #32 Bypass Stack) Installation | Activity | 3CF1625W42A08.1 | (HRSG #32 Bypass Stack) Installation | 2008-05-31 00:00:00 | 2008-09-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4342 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Bypass Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Bypass Stack | 3CF1625W42A12.1 | (HRSG #32 Bypass Stack Silencer) Installation | (HRSG #32 Bypass Stack Silencer) Installation | 2008-08-01 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Bypass Stack 3CF1625W42A12.1 (HRSG #32 Bypass Stack Silencer) Installation | Activity | 3CF1625W42A12.1 | (HRSG #32 Bypass Stack Silencer) Installation | 2008-08-01 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4344 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Main Stack | 3PF1625W42A10.2P | (HRSG #32 Main Stack Silencer) P.O & Procurement | (HRSG #32 Main Stack Silencer) P.O & Procurement | 2007-06-13 | 2008-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Main Stack 3PF1625W42A10.2P (HRSG #32 Main Stack Silencer) P.O & Procurement | Activity | 3PF1625W42A10.2P | (HRSG #32 Main Stack Silencer) P.O & Procurement | 2007-06-13 00:00:00 | 2008-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4345 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Main Stack | 3EF1625W42A01.2 | (HRSG #32 Main Stack) Design | (HRSG #32 Main Stack) Design | 2007-06-18 | 2007-12-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Main Stack 3EF1625W42A01.2 (HRSG #32 Main Stack) Design | Activity | 3EF1625W42A01.2 | (HRSG #32 Main Stack) Design | 2007-06-18 00:00:00 | 2007-12-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4346 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Main Stack | 3PF1625W42A06.2P | (HRSG #32 Main Stack) P.O & Procurement | (HRSG #32 Main Stack) P.O & Procurement | 2007-07-18 | 2008-05-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Main Stack 3PF1625W42A06.2P (HRSG #32 Main Stack) P.O & Procurement | Activity | 3PF1625W42A06.2P | (HRSG #32 Main Stack) P.O & Procurement | 2007-07-18 00:00:00 | 2008-05-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4347 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Main Stack | 3EF1625W00A02.2 | (HRSG #32 Main Stack) GA & Load Data to Civil Design | (HRSG #32 Main Stack) GA & Load Data to Civil Design | 2007-08-06 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Main Stack 3EF1625W00A02.2 (HRSG #32 Main Stack) GA & Load Data to Civil Design | Activity | 3EF1625W00A02.2 | (HRSG #32 Main Stack) GA & Load Data to Civil Design | 2007-08-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4348 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Main Stack | 3EF1625W16A03.2 | (HRSG #32 Main Stack) FDN Design | (HRSG #32 Main Stack) FDN Design | 2007-11-08 | 2008-03-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Main Stack 3EF1625W16A03.2 (HRSG #32 Main Stack) FDN Design | Activity | 3EF1625W16A03.2 | (HRSG #32 Main Stack) FDN Design | 2007-11-08 00:00:00 | 2008-03-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4349 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Main Stack | 3CF1625W16A04.2 | (HRSG #32 Main Stack) FDN Work | (HRSG #32 Main Stack) FDN Work | 2008-03-18 | 2008-06-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Main Stack 3CF1625W16A04.2 (HRSG #32 Main Stack) FDN Work | Activity | 3CF1625W16A04.2 | (HRSG #32 Main Stack) FDN Work | 2008-03-18 00:00:00 | 2008-06-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4350 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Main Stack | 3PF1625W42A07.2T | (HRSG #32 Main Stack) Transportation | (HRSG #32 Main Stack) Transportation | 2008-05-17 | 2008-07-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Main Stack 3PF1625W42A07.2T (HRSG #32 Main Stack) Transportation | Activity | 3PF1625W42A07.2T | (HRSG #32 Main Stack) Transportation | 2008-05-17 00:00:00 | 2008-07-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4351 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Main Stack | 3PF1625W42A11.2T | (HRSG #32 Main Stack Silencer) Transportation | (HRSG #32 Main Stack Silencer) Transportation | 2008-05-31 | 2008-07-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Main Stack 3PF1625W42A11.2T (HRSG #32 Main Stack Silencer) Transportation | Activity | 3PF1625W42A11.2T | (HRSG #32 Main Stack Silencer) Transportation | 2008-05-31 00:00:00 | 2008-07-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4352 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Main Stack | 3CF1625W42A08.2 | (HRSG #32 Main Stack) Installation | (HRSG #32 Main Stack) Installation | 2009-01-14 | 2009-03-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Main Stack 3CF1625W42A08.2 (HRSG #32 Main Stack) Installation | Activity | 3CF1625W42A08.2 | (HRSG #32 Main Stack) Installation | 2009-01-14 00:00:00 | 2009-03-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4353 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Main Stack | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Main Stack | 3CF1625W42A12.2 | (HRSG #32 Main Stack Silencer) Installation | (HRSG #32 Main Stack Silencer) Installation | 2009-03-25 | 2009-04-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Main Stack 3CF1625W42A12.2 (HRSG #32 Main Stack Silencer) Installation | Activity | 3CF1625W42A12.2 | (HRSG #32 Main Stack Silencer) Installation | 2009-03-25 00:00:00 | 2009-04-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4355 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Piping Work | 3PF1650W52A02.1P | (HRSG #32 Insulation) P.O & Procurement | (HRSG #32 Insulation) P.O & Procurement | 2008-01-09 | 2008-12-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Piping Work 3PF1650W52A02.1P (HRSG #32 Insulation) P.O & Procurement | Activity | 3PF1650W52A02.1P | (HRSG #32 Insulation) P.O & Procurement | 2008-01-09 00:00:00 | 2008-12-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4356 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Piping Work | 3CF1640W58A05.1 | (HRSG #32) Piping Work | (HRSG #32) Piping Work | 2008-12-01 | 2009-02-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Piping Work 3CF1640W58A05.1 (HRSG #32) Piping Work | Activity | 3CF1640W58A05.1 | (HRSG #32) Piping Work | 2008-12-01 00:00:00 | 2009-02-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4357 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Piping Work | 3PF1650W52A03.1T | (HRSG #32 Insulation) Transportation | (HRSG #32 Insulation) Transportation | 2008-12-02 | 2009-01-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Piping Work 3PF1650W52A03.1T (HRSG #32 Insulation) Transportation | Activity | 3PF1650W52A03.1T | (HRSG #32 Insulation) Transportation | 2008-12-02 00:00:00 | 2009-01-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4358 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Piping Work | 3CF1640W62A06.1 | (HRSG #32) Hydro Test | (HRSG #32) Hydro Test | 2009-03-02 | 2009-03-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Piping Work 3CF1640W62A06.1 (HRSG #32) Hydro Test | Activity | 3CF1640W62A06.1 | (HRSG #32) Hydro Test | 2009-03-02 00:00:00 | 2009-03-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4359 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Piping Work | 3CF1650W52A04.1 | (HRSG #32 Insulation) Installation | (HRSG #32 Insulation) Installation | 2009-03-16 | 2009-04-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Piping Work 3CF1650W52A04.1 (HRSG #32 Insulation) Installation | Activity | 3CF1650W52A04.1 | (HRSG #32 Insulation) Installation | 2009-03-16 00:00:00 | 2009-04-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4360 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Piping Work | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Piping Work | 3CF1640W60A07.1 | (HRSG #32) Acid Cleaning | (HRSG #32) Acid Cleaning | 2009-03-26 | 2009-04-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Piping Work 3CF1640W60A07.1 (HRSG #32) Acid Cleaning | Activity | 3CF1640W60A07.1 | (HRSG #32) Acid Cleaning | 2009-03-26 00:00:00 | 2009-04-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4362 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | CEMS | 3PF1660W86A04.1P | (CEMS) P.O & Procurement | (CEMS) P.O & Procurement | 2007-08-29 | 2008-06-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 CEMS 3PF1660W86A04.1P (CEMS) P.O & Procurement | Activity | 3PF1660W86A04.1P | (CEMS) P.O & Procurement | 2007-08-29 00:00:00 | 2008-06-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4363 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | CEMS | 3EF1660W16A01.1 | (CEMS) FDN Design | (CEMS) FDN Design | 2007-10-30 | 2008-01-25 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 CEMS 3EF1660W16A01.1 (CEMS) FDN Design | Activity | 3EF1660W16A01.1 | (CEMS) FDN Design | 2007-10-30 00:00:00 | 2008-01-25 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4364 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | CEMS | 3CF1660W16A02.1 | (CEMS) FDN Work | (CEMS) FDN Work | 2008-01-26 | 2008-03-24 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 CEMS 3CF1660W16A02.1 (CEMS) FDN Work | Activity | 3CF1660W16A02.1 | (CEMS) FDN Work | 2008-01-26 00:00:00 | 2008-03-24 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4365 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | CEMS | 3PF1660W86A05.1T | (CEMS) Transportation | (CEMS) Transportation | 2008-07-01 | 2008-08-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 CEMS 3PF1660W86A05.1T (CEMS) Transportation | Activity | 3PF1660W86A05.1T | (CEMS) Transportation | 2008-07-01 00:00:00 | 2008-08-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4366 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | CEMS | 3CF1660W86A06.1 | (CEMS) Installation(incl. Elec, I&C) | (CEMS) Installation(incl. Elec, I&C) | 2008-08-15 | 2008-08-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 CEMS 3CF1660W86A06.1 (CEMS) Installation(incl. Elec, I&C) | Activity | 3CF1660W86A06.1 | (CEMS) Installation(incl. Elec, I&C) | 2008-08-15 00:00:00 | 2008-08-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4367 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | CEMS | 3CF1660W86A07.1 | (CEMS) Loop Test | (CEMS) Loop Test | 2008-09-01 | 2008-09-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 CEMS 3CF1660W86A07.1 (CEMS) Loop Test | Activity | 3CF1660W86A07.1 | (CEMS) Loop Test | 2008-09-01 00:00:00 | 2008-09-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4368 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > CEMS | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | CEMS | 3SF1660W62A08.1 | (HRSG #32) CEMS Function Test for GT #11(Bypass stack) | (HRSG #32) CEMS Function Test for GT #11(Bypass stack) | 2008-09-06 | 2008-09-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 CEMS 3SF1660W62A08.1 (HRSG #32) CEMS Function Test for GT #11(Bypass stack) | Activity | 3SF1660W62A08.1 | (HRSG #32) CEMS Function Test for GT #11(Bypass stack) | 2008-09-06 00:00:00 | 2008-09-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4370 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Auxiliary System | 3PF1665W42A12.1P | (HRSG #32 MECH Vendor Equip) P.O & Procurement | (HRSG #32 MECH Vendor Equip) P.O & Procurement | 2007-09-10 | 2008-10-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Auxiliary System 3PF1665W42A12.1P (HRSG #32 MECH Vendor Equip) P.O & Procurement | Activity | 3PF1665W42A12.1P | (HRSG #32 MECH Vendor Equip) P.O & Procurement | 2007-09-10 00:00:00 | 2008-10-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4371 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Auxiliary System | 3PF1655W86A07.1P | (HRSG #32 I&C Vendor Equip) P.O & Procurement | (HRSG #32 I&C Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-10-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Auxiliary System 3PF1655W86A07.1P (HRSG #32 I&C Vendor Equip) P.O & Procurement | Activity | 3PF1655W86A07.1P | (HRSG #32 I&C Vendor Equip) P.O & Procurement | 2007-10-02 00:00:00 | 2008-10-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4372 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Auxiliary System | 3PF1655W70A02.1P | (HRSG #32 ELEC Vendor Equip) P.O & Procurement | (HRSG #32 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 | 2008-10-03 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Auxiliary System 3PF1655W70A02.1P (HRSG #32 ELEC Vendor Equip) P.O & Procurement | Activity | 3PF1655W70A02.1P | (HRSG #32 ELEC Vendor Equip) P.O & Procurement | 2007-10-02 00:00:00 | 2008-10-03 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4373 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Auxiliary System | 3PF1665W42A13.1T | (HRSG #32 MECH Vendor Equip) Transportation | (HRSG #32 MECH Vendor Equip) Transportation | 2008-10-03 | 2008-11-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Auxiliary System 3PF1665W42A13.1T (HRSG #32 MECH Vendor Equip) Transportation | Activity | 3PF1665W42A13.1T | (HRSG #32 MECH Vendor Equip) Transportation | 2008-10-03 00:00:00 | 2008-11-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4374 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Auxiliary System | 3PF1655W86A08.1T | (HRSG #32 I&C Vendor Equip) Transportation | (HRSG #32 I&C Vendor Equip) Transportation | 2008-10-04 | 2008-11-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Auxiliary System 3PF1655W86A08.1T (HRSG #32 I&C Vendor Equip) Transportation | Activity | 3PF1655W86A08.1T | (HRSG #32 I&C Vendor Equip) Transportation | 2008-10-04 00:00:00 | 2008-11-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4375 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Auxiliary System | 3PF1655W70A03.1T | (HRSG #32 ELEC Vendor Equip) Transportation | (HRSG #32 ELEC Vendor Equip) Transportation | 2008-10-04 | 2008-11-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Auxiliary System 3PF1655W70A03.1T (HRSG #32 ELEC Vendor Equip) Transportation | Activity | 3PF1655W70A03.1T | (HRSG #32 ELEC Vendor Equip) Transportation | 2008-10-04 00:00:00 | 2008-11-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4376 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Auxiliary System | 3CF1665W42A14.1 | (HRSG #32 MECH Vendor Equip) Installation | (HRSG #32 MECH Vendor Equip) Installation | 2008-11-18 | 2009-03-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Auxiliary System 3CF1665W42A14.1 (HRSG #32 MECH Vendor Equip) Installation | Activity | 3CF1665W42A14.1 | (HRSG #32 MECH Vendor Equip) Installation | 2008-11-18 00:00:00 | 2009-03-02 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4377 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Auxiliary System | 3CF1655W86A09.1 | (HRSG #32 I&C Vendor Equip) Installation | (HRSG #32 I&C Vendor Equip) Installation | 2008-11-19 | 2009-03-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Auxiliary System 3CF1655W86A09.1 (HRSG #32 I&C Vendor Equip) Installation | Activity | 3CF1655W86A09.1 | (HRSG #32 I&C Vendor Equip) Installation | 2008-11-19 00:00:00 | 2009-03-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4378 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Auxiliary System | 3CF1655W70A04.1 | (HRSG #32 ELEC Vendor Equip) Installation | (HRSG #32 ELEC Vendor Equip) Installation | 2008-11-19 | 2009-03-13 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Auxiliary System 3CF1655W70A04.1 (HRSG #32 ELEC Vendor Equip) Installation | Activity | 3CF1655W70A04.1 | (HRSG #32 ELEC Vendor Equip) Installation | 2008-11-19 00:00:00 | 2009-03-13 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4379 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Auxiliary System | 3CF1655W74A05.1 | (HRSG #32) Installation & Test - Elec. | (HRSG #32) Installation & Test - Elec. | 2008-12-30 | 2009-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Auxiliary System 3CF1655W74A05.1 (HRSG #32) Installation & Test - Elec. | Activity | 3CF1655W74A05.1 | (HRSG #32) Installation & Test - Elec. | 2008-12-30 00:00:00 | 2009-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4380 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Auxiliary System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Auxiliary System | 3CF1660W90A10.1 | (HRSG #32) Installation & Test - I&C | (HRSG #32) Installation & Test - I&C | 2008-12-30 | 2009-04-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Auxiliary System 3CF1660W90A10.1 (HRSG #32) Installation & Test - I&C | Activity | 3CF1660W90A10.1 | (HRSG #32) Installation & Test - I&C | 2008-12-30 00:00:00 | 2009-04-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4382 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Commissioning | 3SF1600W62A01.1 | (HRSG #32)Cold Commissioning for HRSG #32 | (HRSG #32)Cold Commissioning for HRSG #32 | 2009-04-23 | 2009-05-12 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Commissioning 3SF1600W62A01.1 (HRSG #32)Cold Commissioning for HRSG #32 | Activity | 3SF1600W62A01.1 | (HRSG #32)Cold Commissioning for HRSG #32 | 2009-04-23 00:00:00 | 2009-05-12 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4383 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > HRSG #31 & #32 > HRSG #32 > Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | HRSG #31 & #32 | HRSG #32 | Commissioning | 3SF1600W62A02.1 | (HRSG #32) Function Test for HRSG #32 | (HRSG #32) Function Test for HRSG #32 | 2009-05-13 | 2009-05-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 HRSG #31 & #32 HRSG #32 Commissioning 3SF1600W62A02.1 (HRSG #32) Function Test for HRSG #32 | Activity | 3SF1600W62A02.1 | (HRSG #32) Function Test for HRSG #32 | 2009-05-13 00:00:00 | 2009-05-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4386 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Building |  | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | (STG #30 BLDG) GA & Load Data to Civil Design | 2007-03-01 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Building 3EF2010W00A01 (STG #30 BLDG) GA & Load Data to Civil Design | Activity | 3EF2010W00A01 | (STG #30 BLDG) GA & Load Data to Civil Design | 2007-03-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4387 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Building |  | 3EF2010W20A02 | (STG #30 BLDG) Buliding Design | (STG #30 BLDG) Buliding Design | 2007-03-01 | 2007-09-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Building 3EF2010W20A02 (STG #30 BLDG) Buliding Design | Activity | 3EF2010W20A02 | (STG #30 BLDG) Buliding Design | 2007-03-01 00:00:00 | 2007-09-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4388 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Building |  | 3PF2010W20A04P | (STG #30 BLDG) P.O & Procurement - Structure Work(S/S) | (STG #30 BLDG) P.O & Procurement - Structure Work(S/S) | 2007-09-19 | 2008-01-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Building 3PF2010W20A04P (STG #30 BLDG) P.O & Procurement - Structure Work(S/S) | Activity | 3PF2010W20A04P | (STG #30 BLDG) P.O & Procurement - Structure Work(S/S) | 2007-09-19 00:00:00 | 2008-01-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4389 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Building |  | 3CF2010W16A03 | (STG #30 BLDG) FDN Work | (STG #30 BLDG) FDN Work | 2007-12-15 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Building 3CF2010W16A03 (STG #30 BLDG) FDN Work | Activity | 3CF2010W16A03 | (STG #30 BLDG) FDN Work | 2007-12-15 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4390 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Building |  | 3PF2010W20A05T | (STG #30 BLDG) Transportation - Structure Work(S/S) | (STG #30 BLDG) Transportation - Structure Work(S/S) | 2008-02-01 | 2008-03-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Building 3PF2010W20A05T (STG #30 BLDG) Transportation - Structure Work(S/S) | Activity | 3PF2010W20A05T | (STG #30 BLDG) Transportation - Structure Work(S/S) | 2008-02-01 00:00:00 | 2008-03-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4391 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Building |  | 3CF2010W20A06 | (STG #30 BLDG) Structure Work(S/S) | (STG #30 BLDG) Structure Work(S/S) | 2008-04-16 | 2008-08-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Building 3CF2010W20A06 (STG #30 BLDG) Structure Work(S/S) | Activity | 3CF2010W20A06 | (STG #30 BLDG) Structure Work(S/S) | 2008-04-16 00:00:00 | 2008-08-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4392 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Building |  | 3CF2010W20A07 | (STG #30 BLDG) Cladding Work | (STG #30 BLDG) Cladding Work | 2008-06-25 | 2008-11-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Building 3CF2010W20A07 (STG #30 BLDG) Cladding Work | Activity | 3CF2010W20A07 | (STG #30 BLDG) Cladding Work | 2008-06-25 00:00:00 | 2008-11-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4393 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Building |  | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | (STG #30 BLDG) Roof Work | 2008-09-04 | 2008-12-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Building 3CF2010W20A08 (STG #30 BLDG) Roof Work | Activity | 3CF2010W20A08 | (STG #30 BLDG) Roof Work | 2008-09-04 00:00:00 | 2008-12-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4394 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Building |  | 3CF2010W38A09 | (STG #30 BLDG) Installation & Test - Fire Fighting Sys. | (STG #30 BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 | 2008-12-27 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Building 3CF2010W38A09 (STG #30 BLDG) Installation & Test - Fire Fighting Sys. | Activity | 3CF2010W38A09 | (STG #30 BLDG) Installation & Test - Fire Fighting Sys. | 2008-11-01 00:00:00 | 2008-12-27 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4395 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Building |  | 3CF2010W90A12 | (STG #30 BLDG) Installation & Test - I&C | (STG #30 BLDG) Installation & Test - I&C | 2008-11-12 | 2009-02-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Building 3CF2010W90A12 (STG #30 BLDG) Installation & Test - I&C | Activity | 3CF2010W90A12 | (STG #30 BLDG) Installation & Test - I&C | 2008-11-12 00:00:00 | 2009-02-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4396 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Building |  | 3CF2010W36A10 | (STG #30 BLDG) Installation & Test - HVAC | (STG #30 BLDG) Installation & Test - HVAC | 2008-11-12 | 2009-01-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Building 3CF2010W36A10 (STG #30 BLDG) Installation & Test - HVAC | Activity | 3CF2010W36A10 | (STG #30 BLDG) Installation & Test - HVAC | 2008-11-12 00:00:00 | 2009-01-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4397 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Building | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Building |  | 3CF2010W74A11 | (STG #30 BLDG) Installation & Test - Elec | (STG #30 BLDG) Installation & Test - Elec | 2008-11-12 | 2009-02-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Building 3CF2010W74A11 (STG #30 BLDG) Installation & Test - Elec | Activity | 3CF2010W74A11 | (STG #30 BLDG) Installation & Test - Elec | 2008-11-12 00:00:00 | 2009-02-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4399 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Unit Step-up Transformer |  | 3PF6500W70A07P | (STG #30 & UST Shelter) P.O & Procurement - Main TR | (STG #30 & UST Shelter) P.O & Procurement - Main TR | 2007-06-29 | 2008-08-05 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Unit Step-up Transformer 3PF6500W70A07P (STG #30 & UST Shelter) P.O & Procurement - Main TR | Activity | 3PF6500W70A07P | (STG #30 & UST Shelter) P.O & Procurement - Main TR | 2007-06-29 00:00:00 | 2008-08-05 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4400 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Unit Step-up Transformer |  | 3EF6500W00A01 | (STG #30 & UST Shelter) GA & Load Data to Civil Design | (STG #30 & UST Shelter) GA & Load Data to Civil Design | 2007-11-28 |  | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Unit Step-up Transformer 3EF6500W00A01 (STG #30 & UST Shelter) GA & Load Data to Civil Design | Activity | 3EF6500W00A01 | (STG #30 & UST Shelter) GA & Load Data to Civil Design | 2007-11-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4401 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Unit Step-up Transformer |  | 3EF6500W16A02 | (STG #30 & UST Shelter) FDN & Firewall Design | (STG #30 & UST Shelter) FDN & Firewall Design | 2007-11-28 | 2008-03-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Unit Step-up Transformer 3EF6500W16A02 (STG #30 & UST Shelter) FDN & Firewall Design | Activity | 3EF6500W16A02 | (STG #30 & UST Shelter) FDN & Firewall Design | 2007-11-28 00:00:00 | 2008-03-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4402 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Unit Step-up Transformer |  | 3EF6500W32A04 | (STG #30 & UST Shelter) Structure Design | (STG #30 & UST Shelter) Structure Design | 2007-11-28 | 2008-03-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Unit Step-up Transformer 3EF6500W32A04 (STG #30 & UST Shelter) Structure Design | Activity | 3EF6500W32A04 | (STG #30 & UST Shelter) Structure Design | 2007-11-28 00:00:00 | 2008-03-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4403 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Unit Step-up Transformer |  | 3CF6500W16A03 | (STG #30 & UST Shelter) FDN Work | (STG #30 & UST Shelter) FDN Work | 2008-03-11 | 2008-06-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Unit Step-up Transformer 3CF6500W16A03 (STG #30 & UST Shelter) FDN Work | Activity | 3CF6500W16A03 | (STG #30 & UST Shelter) FDN Work | 2008-03-11 00:00:00 | 2008-06-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4404 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Unit Step-up Transformer |  | 3CF6500W16A05 | (STG #30 & UST Shelter) Firewall Work | (STG #30 & UST Shelter) Firewall Work | 2008-06-10 | 2008-08-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Unit Step-up Transformer 3CF6500W16A05 (STG #30 & UST Shelter) Firewall Work | Activity | 3CF6500W16A05 | (STG #30 & UST Shelter) Firewall Work | 2008-06-10 00:00:00 | 2008-08-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4405 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Unit Step-up Transformer |  | 3PF6500W70A08T | (STG #30 & UST Shelter) Transportation - Main TR | (STG #30 & UST Shelter) Transportation - Main TR | 2008-08-06 | 2008-09-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Unit Step-up Transformer 3PF6500W70A08T (STG #30 & UST Shelter) Transportation - Main TR | Activity | 3PF6500W70A08T | (STG #30 & UST Shelter) Transportation - Main TR | 2008-08-06 00:00:00 | 2008-09-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4406 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Unit Step-up Transformer | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Unit Step-up Transformer |  | 3CF6500W70A09 | (STG #30 & UST Shelter) Installation - Main TR | (STG #30 & UST Shelter) Installation - Main TR | 2008-09-20 | 2008-11-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Unit Step-up Transformer 3CF6500W70A09 (STG #30 & UST Shelter) Installation - Main TR | Activity | 3CF6500W70A09 | (STG #30 & UST Shelter) Installation - Main TR | 2008-09-20 00:00:00 | 2008-11-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4408 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Steam Turbine |  | 3EF2020W00A01 | (ST #30) ST Process Data | (ST #30) ST Process Data | 2007-03-01 | 2007-03-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Steam Turbine 3EF2020W00A01 (ST #30) ST Process Data | Activity | 3EF2020W00A01 | (ST #30) ST Process Data | 2007-03-01 00:00:00 | 2007-03-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4409 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Steam Turbine |  | 3EF2020W00A02 | (ST #30) ST Aux' Steam Consumption Data | (ST #30) ST Aux' Steam Consumption Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Steam Turbine 3EF2020W00A02 (ST #30) ST Aux' Steam Consumption Data | Activity | 3EF2020W00A02 | (ST #30) ST Aux' Steam Consumption Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4410 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Steam Turbine |  | 3EF2020W00A03 | (ST #30) Instrument, Service Air Data | (ST #30) Instrument, Service Air Data | 2007-03-01 | 2007-03-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Steam Turbine 3EF2020W00A03 (ST #30) Instrument, Service Air Data | Activity | 3EF2020W00A03 | (ST #30) Instrument, Service Air Data | 2007-03-01 00:00:00 | 2007-03-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4411 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Steam Turbine |  | 3EF2020W00A04 | (ST #30) Utility Consumption Data | (ST #30) Utility Consumption Data | 2007-03-01 | 2007-04-26 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Steam Turbine 3EF2020W00A04 (ST #30) Utility Consumption Data | Activity | 3EF2020W00A04 | (ST #30) Utility Consumption Data | 2007-03-01 00:00:00 | 2007-04-26 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4412 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Steam Turbine |  | 3EF2020W00A05 | (ST #30) Emergency Load Data | (ST #30) Emergency Load Data | 2007-03-01 | 2007-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Steam Turbine 3EF2020W00A05 (ST #30) Emergency Load Data | Activity | 3EF2020W00A05 | (ST #30) Emergency Load Data | 2007-03-01 00:00:00 | 2007-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4413 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Steam Turbine |  | 3PF2020W42A10P | (ST #30) P.O & Procurement | (ST #30) P.O & Procurement | 2007-03-01 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Steam Turbine 3PF2020W42A10P (ST #30) P.O & Procurement | Activity | 3PF2020W42A10P | (ST #30) P.O & Procurement | 2007-03-01 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4414 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Steam Turbine |  | 3EF2020W16A06 | (ST #30) FDN Design | (ST #30) FDN Design | 2007-07-03 | 2007-11-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Steam Turbine 3EF2020W16A06 (ST #30) FDN Design | Activity | 3EF2020W16A06 | (ST #30) FDN Design | 2007-07-03 00:00:00 | 2007-11-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4415 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Steam Turbine |  | 3CF2020W16A07 | (ST #30) FDN Work | (ST #30) FDN Work | 2007-12-15 | 2008-04-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Steam Turbine 3CF2020W16A07 (ST #30) FDN Work | Activity | 3CF2020W16A07 | (ST #30) FDN Work | 2007-12-15 00:00:00 | 2008-04-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4416 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Steam Turbine |  | 3CF2020W16A08 | (ST #30) Pedestal & Top Slab Work | (ST #30) Pedestal & Top Slab Work | 2008-04-16 | 2008-10-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Steam Turbine 3CF2020W16A08 (ST #30) Pedestal & Top Slab Work | Activity | 3CF2020W16A08 | (ST #30) Pedestal & Top Slab Work | 2008-04-16 00:00:00 | 2008-10-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4417 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Steam Turbine |  | 3PF2020W42A11T | (ST #30) Transportation | (ST #30) Transportation | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Steam Turbine 3PF2020W42A11T (ST #30) Transportation | Activity | 3PF2020W42A11T | (ST #30) Transportation | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4418 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Steam Turbine | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Steam Turbine |  | 3CF2020W42A12 | (ST #30) Installation | (ST #30) Installation | 2008-12-16 | 2009-05-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Steam Turbine 3CF2020W42A12 (ST #30) Installation | Activity | 3CF2020W42A12 | (ST #30) Installation | 2008-12-16 00:00:00 | 2009-05-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4420 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > ST Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | ST Generator |  | 3PF2040W42A02P | (STG #30) P.O & Procurement | (STG #30) P.O & Procurement | 2007-03-01 | 2008-10-31 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 ST Generator 3PF2040W42A02P (STG #30) P.O & Procurement | Activity | 3PF2040W42A02P | (STG #30) P.O & Procurement | 2007-03-01 00:00:00 | 2008-10-31 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4421 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > ST Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | ST Generator |  | 3PF2040W42A03T | (STG #30) Transportation | (STG #30) Transportation | 2008-11-01 | 2008-12-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 ST Generator 3PF2040W42A03T (STG #30) Transportation | Activity | 3PF2040W42A03T | (STG #30) Transportation | 2008-11-01 00:00:00 | 2008-12-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4422 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > ST Generator | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | ST Generator |  | 3CF2040W42A04 | (STG #30) Installation | (STG #30) Installation | 2008-12-16 | 2009-04-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 ST Generator 3CF2040W42A04 (STG #30) Installation | Activity | 3CF2040W42A04 | (STG #30) Installation | 2008-12-16 00:00:00 | 2009-04-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4424 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Auxiliary Equipment |  | 3PF2070W42A04P | (STG #30 Aux. Equip) P.O & Procurement | (STG #30 Aux. Equip) P.O & Procurement | 2007-04-30 | 2008-10-01 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Auxiliary Equipment 3PF2070W42A04P (STG #30 Aux. Equip) P.O & Procurement | Activity | 3PF2070W42A04P | (STG #30 Aux. Equip) P.O & Procurement | 2007-04-30 00:00:00 | 2008-10-01 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4425 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Auxiliary Equipment |  | 3EF2070W16A01 | (STG #30 Aux. Equip) FDN Design | (STG #30 Aux. Equip) FDN Design | 2007-12-24 | 2008-05-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Auxiliary Equipment 3EF2070W16A01 (STG #30 Aux. Equip) FDN Design | Activity | 3EF2070W16A01 | (STG #30 Aux. Equip) FDN Design | 2007-12-24 00:00:00 | 2008-05-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4426 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Auxiliary Equipment |  | 3CF2070W16A02 | (STG #30 Aux. Equip) FDN Work | (STG #30 Aux. Equip) FDN Work | 2008-05-22 | 2008-08-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Auxiliary Equipment 3CF2070W16A02 (STG #30 Aux. Equip) FDN Work | Activity | 3CF2070W16A02 | (STG #30 Aux. Equip) FDN Work | 2008-05-22 00:00:00 | 2008-08-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4427 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Auxiliary Equipment |  | 3PF2070W42A05T | (STG #30 Aux. Equip) Transportation | (STG #30 Aux. Equip) Transportation | 2008-10-02 | 2008-11-15 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Auxiliary Equipment 3PF2070W42A05T (STG #30 Aux. Equip) Transportation | Activity | 3PF2070W42A05T | (STG #30 Aux. Equip) Transportation | 2008-10-02 00:00:00 | 2008-11-15 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4428 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > STG Auxiliary Equipment | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | STG Auxiliary Equipment |  | 3CF2070W42A06 | (STG #30 Aux. Equip) Installation | (STG #30 Aux. Equip) Installation | 2008-11-17 | 2009-03-11 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 STG Auxiliary Equipment 3CF2070W42A06 (STG #30 Aux. Equip) Installation | Activity | 3CF2070W42A06 | (STG #30 Aux. Equip) Installation | 2008-11-17 00:00:00 | 2009-03-11 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4430 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Piping & Etc. | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Piping & Etc. |  | 3CF2035W58A01 | (ST #30) Piping Work | (ST #30) Piping Work | 2008-08-16 | 2009-01-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Piping & Etc. 3CF2035W58A01 (ST #30) Piping Work | Activity | 3CF2035W58A01 | (ST #30) Piping Work | 2008-08-16 00:00:00 | 2009-01-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4431 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Piping & Etc. | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Piping & Etc. |  | 3CF2060W74A03 | (ST #30) Installation & Test - Elec. | (ST #30) Installation & Test - Elec. | 2009-01-16 | 2009-04-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Piping & Etc. 3CF2060W74A03 (ST #30) Installation & Test - Elec. | Activity | 3CF2060W74A03 | (ST #30) Installation & Test - Elec. | 2009-01-16 00:00:00 | 2009-04-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4432 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Piping & Etc. | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Piping & Etc. |  | 3CF2065W90A04 | (ST #30) Installation & Test - I&C | (ST #30) Installation & Test - I&C | 2009-01-16 | 2009-04-07 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Piping & Etc. 3CF2065W90A04 (ST #30) Installation & Test - I&C | Activity | 3CF2065W90A04 | (ST #30) Installation & Test - I&C | 2009-01-16 00:00:00 | 2009-04-07 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4433 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Piping & Etc. | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Piping & Etc. |  | 3CF2035W62A02 | (ST #30) Hydro Test | (ST #30) Hydro Test | 2009-01-17 | 2009-02-17 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Piping & Etc. 3CF2035W62A02 (ST #30) Hydro Test | Activity | 3CF2035W62A02 | (ST #30) Hydro Test | 2009-01-17 00:00:00 | 2009-02-17 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4435 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Lube Oil System |  | 3PF2030W42A04P | (Lube Oil Sys.) P.O & Procurement | (Lube Oil Sys.) P.O & Procurement | 2007-07-31 | 2008-09-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Lube Oil System 3PF2030W42A04P (Lube Oil Sys.) P.O & Procurement | Activity | 3PF2030W42A04P | (Lube Oil Sys.) P.O & Procurement | 2007-07-31 00:00:00 | 2008-09-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4436 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Lube Oil System |  | 3EF2030W16A01 | (Lube Oil Sys.) FDN Design | (Lube Oil Sys.) FDN Design | 2007-10-23 | 2008-01-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Lube Oil System 3EF2030W16A01 (Lube Oil Sys.) FDN Design | Activity | 3EF2030W16A01 | (Lube Oil Sys.) FDN Design | 2007-10-23 00:00:00 | 2008-01-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4437 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Lube Oil System |  | 3CF2030W16A02 | (Lube Oil Sys.) FDN Work | (Lube Oil Sys.) FDN Work | 2008-01-23 | 2008-05-23 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Lube Oil System 3CF2030W16A02 (Lube Oil Sys.) FDN Work | Activity | 3CF2030W16A02 | (Lube Oil Sys.) FDN Work | 2008-01-23 00:00:00 | 2008-05-23 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4438 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Lube Oil System |  | 3PF2030W42A05T | (Lube Oil Sys.) Transportation | (Lube Oil Sys.) Transportation | 2008-10-01 | 2008-11-14 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Lube Oil System 3PF2030W42A05T (Lube Oil Sys.) Transportation | Activity | 3PF2030W42A05T | (Lube Oil Sys.) Transportation | 2008-10-01 00:00:00 | 2008-11-14 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4439 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Lube Oil System |  | 3CF2030W42A06 | (Lube Oil Sys.) Equipment Installation | (Lube Oil Sys.) Equipment Installation | 2008-11-15 | 2008-12-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Lube Oil System 3CF2030W42A06 (Lube Oil Sys.) Equipment Installation | Activity | 3CF2030W42A06 | (Lube Oil Sys.) Equipment Installation | 2008-11-15 00:00:00 | 2008-12-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4440 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Lube Oil System |  | 3CF2030W58A07 | (Lube Oil Sys.) Pipe Installation | (Lube Oil Sys.) Pipe Installation | 2008-12-31 | 2009-03-18 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Lube Oil System 3CF2030W58A07 (Lube Oil Sys.) Pipe Installation | Activity | 3CF2030W58A07 | (Lube Oil Sys.) Pipe Installation | 2008-12-31 00:00:00 | 2009-03-18 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4441 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Lube Oil System |  | 3CF2030W62A08 | (Lube Oil Sys.) Lube oil flushing | (Lube Oil Sys.) Lube oil flushing | 2009-03-19 | 2009-04-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Lube Oil System 3CF2030W62A08 (Lube Oil Sys.) Lube oil flushing | Activity | 3CF2030W62A08 | (Lube Oil Sys.) Lube oil flushing | 2009-03-19 00:00:00 | 2009-04-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4442 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Lube Oil System | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Lube Oil System |  | 3CF2030W58A09 | (Lube Oil Sys.) Remove Temp. Pipe | (Lube Oil Sys.) Remove Temp. Pipe | 2009-04-17 | 2009-04-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Lube Oil System 3CF2030W58A09 (Lube Oil Sys.) Remove Temp. Pipe | Activity | 3CF2030W58A09 | (Lube Oil Sys.) Remove Temp. Pipe | 2009-04-17 00:00:00 | 2009-04-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4444 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Test & Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Test & Commissioning |  | 3SF2000W62A02 | (ST #30) Pre-Commissioning | (ST #30) Pre-Commissioning | 2009-04-29 | 2009-05-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Test & Commissioning 3SF2000W62A02 (ST #30) Pre-Commissioning | Activity | 3SF2000W62A02 | (ST #30) Pre-Commissioning | 2009-04-29 00:00:00 | 2009-05-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4445 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Test & Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Test & Commissioning |  | 3SF2000W62A01 | (ST #30) Aux. Equipment Function Test | (ST #30) Aux. Equipment Function Test | 2009-05-09 | 2009-05-28 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Test & Commissioning 3SF2000W62A01 (ST #30) Aux. Equipment Function Test | Activity | 3SF2000W62A01 | (ST #30) Aux. Equipment Function Test | 2009-05-09 00:00:00 | 2009-05-28 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4446 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Steam Turbine & Generator #30 > Test & Commissioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Steam Turbine & Generator #30 | Test & Commissioning |  | 3SF2000W62A03 | (ST #30) Turnning Gear Operation | (ST #30) Turnning Gear Operation | 2009-05-29 | 2009-05-30 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Steam Turbine & Generator #30 Test & Commissioning 3SF2000W62A03 (ST #30) Turnning Gear Operation | Activity | 3SF2000W62A03 | (ST #30) Turnning Gear Operation | 2009-05-29 00:00:00 | 2009-05-30 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4448 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9035W62A01 | (Comm'g) Steam Blowing | (Comm'g) Steam Blowing | 2009-05-31 | 2009-06-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9035W62A01 (Comm'g) Steam Blowing | Activity | 3SF9035W62A01 | (Comm'g) Steam Blowing | 2009-05-31 00:00:00 | 2009-06-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4449 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3CF9035W62A02 | (Comm'g) Temporary Piping Restoration | (Comm'g) Temporary Piping Restoration | 2009-06-20 | 2009-06-29 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3CF9035W62A02 (Comm'g) Temporary Piping Restoration | Activity | 3CF9035W62A02 | (Comm'g) Temporary Piping Restoration | 2009-06-20 00:00:00 | 2009-06-29 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4450 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9035W62A03 | (Comm'g) Bypass Operation | (Comm'g) Bypass Operation | 2009-06-30 | 2009-07-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9035W62A03 (Comm'g) Bypass Operation | Activity | 3SF9035W62A03 | (Comm'g) Bypass Operation | 2009-06-30 00:00:00 | 2009-07-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4451 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9035W62A04 | (Comm'g) Safety & Interlock Test | (Comm'g) Safety & Interlock Test | 2009-07-02 | 2009-07-06 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9035W62A04 (Comm'g) Safety & Interlock Test | Activity | 3SF9035W62A04 | (Comm'g) Safety & Interlock Test | 2009-07-02 00:00:00 | 2009-07-06 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4452 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9035W62A05 | (Comm'g) Steam Admission | (Comm'g) Steam Admission | 2009-07-07 | 2009-07-08 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9035W62A05 (Comm'g) Steam Admission | Activity | 3SF9035W62A05 | (Comm'g) Steam Admission | 2009-07-07 00:00:00 | 2009-07-08 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4453 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9040W62A06 | (Comm'g) TBN & GEN. Test | (Comm'g) TBN & GEN. Test | 2009-07-09 | 2009-07-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9040W62A06 (Comm'g) TBN & GEN. Test | Activity | 3SF9040W62A06 | (Comm'g) TBN & GEN. Test | 2009-07-09 00:00:00 | 2009-07-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4454 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9040W62A07 | (Comm'g) Synchronization Test | (Comm'g) Synchronization Test | 2009-07-22 | 2009-07-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9040W62A07 (Comm'g) Synchronization Test | Activity | 3SF9040W62A07 | (Comm'g) Synchronization Test | 2009-07-22 00:00:00 | 2009-07-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4455 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9040W62A08 | (Comm'g) Optimaization Test | (Comm'g) Optimaization Test | 2009-07-23 | 2009-08-09 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9040W62A08 (Comm'g) Optimaization Test | Activity | 3SF9040W62A08 | (Comm'g) Optimaization Test | 2009-07-23 00:00:00 | 2009-08-09 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4456 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9040W62A09 | (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | 2009-08-10 | 2009-08-10 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9040W62A09 (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | Activity | 3SF9040W62A09 | (Comm'g) Fuel Change-Over(Gas to Oil) and Optimaization | 2009-08-10 00:00:00 | 2009-08-10 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4457 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9040W62A10 | (Comm'g) Outage Period | (Comm'g) Outage Period | 2009-08-10 | 2009-08-16 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9040W62A10 (Comm'g) Outage Period | Activity | 3SF9040W62A10 | (Comm'g) Outage Period | 2009-08-10 00:00:00 | 2009-08-16 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4458 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9040W62A11 | (Comm'g) APS & Stability Guarantee Test | (Comm'g) APS & Stability Guarantee Test | 2009-08-17 | 2009-09-19 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9040W62A11 (Comm'g) APS & Stability Guarantee Test | Activity | 3SF9040W62A11 | (Comm'g) APS & Stability Guarantee Test | 2009-08-17 00:00:00 | 2009-09-19 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4459 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9040W62A12 | (Comm'g) Trial Run Test | (Comm'g) Trial Run Test | 2009-09-20 | 2009-09-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9040W62A12 (Comm'g) Trial Run Test | Activity | 3SF9040W62A12 | (Comm'g) Trial Run Test | 2009-09-20 00:00:00 | 2009-09-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4460 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9041W62A14 | (Comm'g) Reliability Test | (Comm'g) Reliability Test | 2009-09-22 | 2009-10-21 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9041W62A14 (Comm'g) Reliability Test | Activity | 3SF9041W62A14 | (Comm'g) Reliability Test | 2009-09-22 00:00:00 | 2009-10-21 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4461 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9040W62A13 | (Comm'g) Initial Operation Test | (Comm'g) Initial Operation Test | 2009-09-22 | 2009-09-22 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9040W62A13 (Comm'g) Initial Operation Test | Activity | 3SF9040W62A13 | (Comm'g) Initial Operation Test | 2009-09-22 00:00:00 | 2009-09-22 00:00:00
ccpp guide schedule_260527.xlsx | Sheet1 (2) | 4462 | activity |  | CCPP Project Standard Schedule_20181012_Idea > Power Plant Block #3 > Block #3 Commisssioning | CCPP Project Standard Schedule_20181012_Idea | Power Plant Block #3 | Block #3 Commisssioning |  |  | 3SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | 2009-10-22 | 2009-11-02 | CCPP Project Standard Schedule_20181012_Idea Power Plant Block #3 Block #3 Commisssioning 3SF9042W62A15 (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | Activity | 3SF9042W62A15 | (Comm'g) Performance Test (Fuel Gas & Fuel Oil) | 2009-10-22 00:00:00 | 2009-11-02 00:00:00