## Document for Owner
Scope | Team Code | Owner | Document No | Serial | Title | Pur | First Plan | Final Plan | DT Date(EM) | DT Date | DT No | DT Pur. | DT Rev. | Com. Date | Com. No | Com. Pur. | Com. Rev. | Com. Status | Discipline | PKG Code | First Actual | Final Actual
DHI | 배관기술 | 황계증 | MRT-UC07-P0ZEN-100001 | 1 | [Overall Arrange]_PLOT PLAN | FA | 2017-06-30 | 2018-09-28 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2020-11-04 | 134/T/MRT/REC/XI/2020 | FC | 6 | A | MECHANICAL | PLOT PLAN | 2017-06-30 | 2018-09-06
DHI | 배관기술 | 황계증 | MRT-UC08-P0ZEN-100002 | 2 | GENERAL ARRANGEMENT FOR POWER BLOCK | FA | 2017-07-28 | 2018-09-28 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2020-11-04 | 134/T/MRT/REC/XI/2020 | FC | 5 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-07-19
DHI | 배관기술 | 황계증 | MRT-UC08-P0ZEN-100003 | 3 | GENERAL ARRANGEMENT FOR POWER BLOCK GENERAL SECTION G-G | FA | 2017-07-28 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2020-11-04 | 134/T/MRT/REC/XI/2020 | FC | 5 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-03-09
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100004 | 4 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT GROUND FLOOR PLAN | FA | 2017-07-28 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 7 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-07-28
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100005 | 5 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT MEZZANINE FLOOR PLAN | FA | 2017-07-28 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 7 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-07-28
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100006 | 6 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT OPERATING FLOOR PLAN | FA | 2017-07-28 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 7 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-03-09
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100007 | 7 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT BASEMENT PLAN | FA | 2017-07-28 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 7 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-03-09
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100008 | 8 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT SECTION A-A | FA | 2017-07-28 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 6 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-07-28
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100009 | 9 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT SECTION B-B | FA | 2017-07-28 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 6 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-03-09
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100010 | 10 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT GROUND FLOOR PLAN | FA | 2017-07-28 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-03-09
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100011 | 11 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT MEZZANINE FLOOR PLAN | FA | 2017-07-28 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-03-09
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100012 | 12 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT OPERATING FLOOR PLAN | FA | 2017-07-28 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2017-12-21
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100013 | 13 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT BASEMENT PLAN | FA | 2017-07-28 | 2018-05-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-03-09
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100014 | 14 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT SECTION C-C | FA | 2017-07-28 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-07-28
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100015 | 15 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT SECTION D-D | FA | 2017-07-28 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN | 2017-07-28 | 2018-07-28
DHI | 배관기술 | 황계증 | MRT-UE00-P2ZEN-100016 | 16 | [Steam Turbine Building_GA (For Block 2)]_GENERAL ARRANGEMENT ROOF FLOOR PLAN | FA | 2018-02-16 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | 2020-11-13 | 137/T/MRT/REC/XI/2020 | FC | 5 | A | MECHANICAL | PLOT PLAN | 2018-02-12 | 2018-07-28
DHI | 배관기술 | 황계증 | MRT-UE00-P3ZEN-100017 | 17 | [Steam Turbine Building_GA (For BLOCK 3&4)]_GENERAL ARRANGEMENT ROOF FLOOR PLAN | FA | 2018-02-16 | 2018-07-30 | 2023-03-02 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | 2024-03-26 | MTW-AS-C-LT-24.5107.0 | AB | Z0 | A | MECHANICAL | PLOT PLAN | 2018-02-12 | 2020-11-04
DHI | EM | 김태환 | MRT-DA01-P0ZEN-020001 | 18 | DOCUMENT IDENTIFICATION | FI | 2017-05-30 |  | 2020-11-04 | 2020-11-04 | MRT-DS-REC-TT-200082-FC | FC | 2 | 2020-11-05 | 200082-FC STAMPED | FC | 2 | A | SUPPORT | GENERAL | 2017-06-30 | #VALUE!
DHI | EM | 김태환 | MRT-DA01-P0ZEN-020002 | 19 | EQUIPMENT AND SYSTEM IDENTIFICATION | FI | 2017-05-30 |  | 2017-08-21 | 2017-08-22 | MRT-DS-PLNE-TT-170016 | FI | 1 | 2017-09-15 | 15.018/E04/PLNE/IX/2017 | FI | 1 | I | SUPPORT | GENERAL | 2017-06-30 | 2020-08-24
DHI | EM | 장준태 | MRT-XV00-P0ZEN-020003 | 20 | EQUIPMENT LIST | FI | 2018-03-30 |  | 2020-08-24 | 2020-08-24 | MRT-DS-REC-TT-200067-FC | FC | 2 | 2020-08-24 | 200067-FC STAMPED | FC | 2 | A | SUPPORT | GENERAL | 2018-01-31 | 2017-11-24
DHI | EM | 장준태 | MRT-YK08-P0ZEN-020004 | 21 | TYPICAL NAMEPLATE DRAWING | FA | 2018-08-31 | 2018-11-30 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170100-FC | FC | 2 | 2018-09-21 | 170100-FC STAMPED | FC | 2 | A | SUPPORT | GENERAL | 2017-08-18 | #VALUE!
DHI | EM | 장준태 | MRT-BV02-P0ZEN-020005 | 22 | FLUE GAS DISPERSION STUDY | FI | 2017-11-24 |  | 2018-01-05 | 2018-01-11 | MRT-DS-PLNE-TT-180002 | FI | 1 | 2018-01-18 | 17.009/E04/PLNE/I/2018 | FI | 1 | A | SUPPORT | GENERAL | 2017-11-21 | #VALUE!
DHI | EM | 장준태 | MRT-DA05-P0ZEN-020006 | 23 | ABBREVIATION LIST | FI | 2017-11-30 |  | 2017-11-24 | 2017-12-05 | MRT-DS-PLNE-TT-170103 | FI | 0 | 2017-12-18 | 18.016/E04/PLNE/XII/2017 | FI | 0 | I | SUPPORT | GENERAL | 2017-11-24 | 2019-05-07
DHI | EM | 장준태 | MRT-YT01-P0QJA-110001 | 24 | Gas Cylinder (N2, CO2) Calculation | FA | 2019-04-26 | 2019-07-26 | 2019-05-07 | 2019-05-16 | MRT-DS-REC-TT-190114-FC | FC | 0 | 2019-05-16 | 190114-FC STAMPED | FC | 0 | A | MECHANICAL | N2 GAS SYSTEM | 2019-04-16 | 2017-12-11
DHI | 프로세스기술 | 김광희 | MRT-XG05-P0ZEN-110001 | 25 | [Plant Overall]_HEAT BALANCE DIAGRAMS | FA | 2017-05-31 | 2017-07-13 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170104-FC | FC | 3 | 2018-09-22 | 170104-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-07-26 | 2017-11-14
DHI | 프로세스기술 | 김광희 | MRT-XG02-P0ZEN-110002 | 26 | [Symbol & Legend]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170070-FC | FC | 2 | 2018-09-21 | 170070-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P0GHC-110002 | 27 | [Make-up Water System]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190191-FC STAMPED | FC | 7 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P0LBG-110004 | 28 | [Aux Steam system (For Common)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190191-FC STAMPED | FC | 6 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P0PA-110002 | 29 | [Cooling Water system (For Common)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190187-FC STAMPED | FC | 6 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2LA-110006 | 30 | [Feedwater system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190191-FC STAMPED | FC | 7 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2LBA-110003 | 31 | [Steam and Bypass system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2020-09-28 | 118-T-MRT-REC-IX-2020 | FC | 8 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2LBG-110004 | 32 | [AUX Steam system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2024-06-11 | 2024-06-11 | MRT-DS-REC-TT-240014 | AB | Z1 | 2024-09-30 | MTW-AS-C-LT-24.5780.0 | AB | Z1 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2LC-110007 | 33 | [Condensate system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190191-FC STAMPED | FC | 7 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2LCM-110005 | 34 | [Steam Drain System((For Block 2]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190191-FC STAMPED | FC | 7 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2PA-110002 | 35 | [Cooling Water system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2019-09-19 | 190187-FC STAMPED | FC | 7 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2PA-110008 | 36 | [Aux Cooling Water system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2020-12-04 | 140/T/MRT/REC/XII/2020 | FC | 6 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2PG-110009 | 37 | [Closed cooling water system (For Block 2)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2020-12-04 | 140/T/MRT/REC/XII/2020 | FC | 6 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3LA-110006 | 38 | [Feedwater system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3LBA-110003 | 39 | [Steam and Bypass system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3LBG-110004 | 40 | [Aux Steam system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2024-06-11 | 2024-06-11 | MRT-DS-REC-TT-240014 | AB | Z1 | 2024-06-25 | MTW-AS-C-LT-24.5422.0 | AB | Z1 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3LC-110007 | 41 | [Condensate system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3LCM-110005 | 42 | [Steam Drain System((For Block 3,4]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3PA-110002 | 43 | [Cooling Water system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3PA-110008 | 44 | [Aux Cooling Water system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3PG-110009 | 45 | [Closed cooling water system (For Block 3, 4)]_P&I DIAGRAM | FA | 2017-07-07 | 2017-12-09 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4969.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-10 | 2018-01-26
DHI | 프로세스기술 | 김광희 | MRT-XG07-P2LBA-110300 | 46 | [Steam, Feedwater & condensate system (For Block 2)]_PROCESS FLOW DIAGRAM | FA | 2017-10-19 | 2018-01-17 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180049-FC | FC | 2 | 2018-08-13 | 180049-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-10-13 | 2018-01-26
DHI | 프로세스기술 | 김광희 | MRT-XG07-P3LBA-110300 | 47 | [Steam, Feedwater & condensate system (For Block 3, 4)]_PROCESS FLOW DIAGRAM | FA | 2017-10-19 | 2018-01-17 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180049-FC | FC | 2 | 2018-08-13 | 180049-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-10-13 | 2018-01-26
DHI | 프로세스기술 | 김광희 | MRT-XG07-P2PA-110002 | 48 | [Cooling Water System (For Block 2)]_PROCESS FLOW DIAGRAM | FA | 2017-10-19 | 2018-01-17 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180049-FC | FC | 2 | 2018-08-13 | 180049-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-10-27 | 2018-01-26
DHI | 프로세스기술 | 김광희 | MRT-XG07-P3PA-110002 | 49 | [Cooling Water System (For Block 3, 4)]_PROCESS FLOW DIAGRAM | FA | 2017-10-19 | 2018-01-17 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180049-FC | FC | 2 | 2018-08-13 | 180049-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-10-27 | 2018-01-26
DHI | 프로세스기술 | 김광희 | MRT-XG07-P2PA-110304 | 50 | [Aux & Closed Cooling Water System (For Block 2)]_PROCESS FLOW DIAGRAM | FA | 2017-10-19 | 2018-01-17 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180049-FC | FC | 2 | 2018-08-13 | 180049-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-10-13 | 2018-01-26
DHI | 프로세스기술 | 김광희 | MRT-XG07-P3PA-110304 | 51 | [Aux & Closed Cooling Water System (For Block 3, 4)]_PROCESS FLOW DIAGRAM | FA | 2017-10-19 | 2018-01-17 | 2018-07-27 | 2018-09-10 | MRT-DS-REC-TT-180147-FC | FC | 3 | 2018-09-14 | 180147-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-10-13 | 2017-12-08
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2LBA-110400 | 52 | [Steam and Bypass system (For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-12-08
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3LBA-110400 | 53 | [Steam and Bypass system (For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-12-08
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2LBG-110401 | 54 | [Aux Steam System(For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-12-08
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3LBG-110401 | 55 | [Aux Steam System(For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-12-08
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2LA-110402 | 56 | [Feedwater system (For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-12-08
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3LA-110402 | 57 | [Feedwater system (For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-12-08
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2LC-110403 | 58 | [Condensate system (For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-12-08
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3LC-110403 | 59 | [Condensate system (For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 3 | 2018-09-22 | 170123-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-12-08
DHI | 프로세스기술 | 김광희 | MRT-XS00-P0GHC-110044 | 60 | [Make-up Water System]_SYSTEM DESCRIPTION | FA | 2017-10-25 | 2018-01-26 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 2 | 2018-09-22 | 170123-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-09-28 | 2017-12-08
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2PA-110400 | 61 | [Cooling Water System (For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 2 | 2018-09-22 | 170123-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-12-08
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3PA-110400 | 62 | [Cooling Water System (For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170123-FC | FC | 2 | 2018-09-22 | 170123-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-11-23
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2PA-110404 | 63 | [Aux Cooling Water System (For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170096-FC | FC | 2 | 2018-09-22 | 170096-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-11-23
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3PA-110404 | 64 | [Aux Cooling Water System (For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170096-FC | FC | 2 | 2018-09-22 | 170096-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-11-23
DHI | 프로세스기술 | 김광희 | MRT-XS00-P2PG-110405 | 65 | [Closed cooling water system (For Block 2)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-11-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170096-FC | FC | 2 | 2018-09-22 | 170096-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-11-23
DHI | 프로세스기술 | 김광희 | MRT-XS00-P3PG-110405 | 66 | [Closed cooling water system (For Block 3, 4)]_SYSTEM DESCRIPTION | FA | 2017-07-13 | 2017-12-15 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170096-FC | FC | 2 | 2018-09-22 | 170096-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-13 | 2017-12-11
DHI | 프로세스기술 | 김광희 | MRT-XW03-P2LA-110500 | 67 | [HP&LP Feed Water Pump_Design (For Block 2)]_sizing Calculation | FA | 2017-07-11 | 2017-11-24 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-24 | 2017-12-11
DHI | 프로세스기술 | 김광희 | MRT-XW03-P3LA-110500 | 68 | [HP&LP Feed Water Pump_Design (For Block 3, 4)]_sizing Calculation | FA | 2017-07-11 | 2017-12-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-24 | 2017-12-11
DHI | 프로세스기술 | 김광희 | MRT-XW03-P2LC-110501 | 69 | [Condensate Extraction Pump_Design (For Block 2)]_sizing Calculation | FA | 2017-07-11 | 2017-11-24 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-24 | 2017-12-11
DHI | 프로세스기술 | 김광희 | MRT-XW03-P3LC-110501 | 70 | [Condensate Extraction Pump_Design (For Block 3, 4)]_sizing Calculation | FA | 2017-07-11 | 2017-12-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-24 | 2017-12-11
DHI | 프로세스기술 | 김광희 | MRT-XW03-P0GHC-110051 | 71 | [Make-up Water Pump_Design]_SIZING CALCULATION | FA | 2017-10-25 | 2018-01-26 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-09-28 | 2017-12-11
DHI | 프로세스기술 | 김광희 | MRT-XW03-P2PAC-113500 | 72 | [Circulating Water Pump(DHI)_Design (For Block 2)]_sizing Calculation | FA | 2017-07-11 | 2017-11-24 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-08-22 | 2017-12-11
DHI | 프로세스기술 | 김광희 | MRT-XW03-P3PAC-113500 | 73 | [Circulating Water Pump(DHI)_Design (For Block 3, 4)]_sizing Calculation | FA | 2017-07-11 | 2017-12-10 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-08-22 | 2018-01-23
DHI | 프로세스기술 | 김광희 | MRT-XW03-P0MJ-110511 | 74 | [Diesel Generator_Design]_sizing Calculation | FA | 2017-08-14 | 2017-11-14 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-180036-FC | FC | 3 | 2018-09-21 | 180036-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-08-31 | 2018-06-15
DHI | 프로세스기술 | 김광희 | MRT-CN00-P2ZEN-110100 | 75 | [Plant Overall]_OPERATION PHILOSOPHY OF OVERALL PLANT (For Block 2) | FA | 2018-04-23 | 2018-08-31 | 2018-07-27 | 2018-09-17 | MRT-DS-REC-TT-180494-FC | FC | 1 | 2018-09-22 | 180494-FC STAMPED | FC | 1 | A | MECHANICAL | BOP SYSTEM | 2018-04-24 | 2018-07-13
DHI | 프로세스기술 | 김광희 | MRT-CN00-P3ZEN-110100 | 76 | [Plant Overall]_OPERATION PHILOSOPHY OF OVERALL PLANT (For Block 3, 4) | FA | 2018-05-23 | 2018-08-31 | 2018-07-27 | 2018-08-15 | MRT-DS-REC-TT-180603-FC | FC | 2 | 2018-09-01 | 180603-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2018-06-15 | 2018-12-21
DHI | 프로세스기술 | 김광희 | MRT-CN00-P2ZEN-110102 | 77 | [Plant Overall]_PLANT START-UP AND SHUT-DOWN PROCEDURE (For Block 2) | FA | 2018-11-14 | 2019-02-14 | 2018-12-21 | 2018-12-26 | MRT-DS-REC-TT-180917-FC | FC | 0 | 2018-12-27 | 180917-FC STAMPED | FC | 0 | A | MECHANICAL | BOP SYSTEM | 2018-12-04 | 2018-12-21
DHI | 프로세스기술 | 김광희 | MRT-CN00-P3ZEN-110102 | 78 | [Plant Overall]_PLANT START-UP AND SHUT-DOWN PROCEDURE (For Block 3,4) | FA | 2018-08-12 | 2018-12-10 | 2018-12-21 | 2018-12-26 | MRT-DS-REC-TT-180917-FC | FC | 2 | 2018-12-27 | 180917-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2018-08-10 | 2019-07-02
DHI | 프로세스기술 | 김광희 | MRT-YR01-P2ZEN-110103 | 79 | [Plant Overall]_STEAM BLOWING - OUT PROCEDURE (For Block 2) | FA | 2019-02-28 | 2019-06-21 | 2021-04-28 | 2021-04-28 | MRT-DS-REC-TT-210030 | FC | 2 | 2021-05-24 | 016/SER.00.01/LE/2021 | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2019-03-21 | 2019-07-02
DHI | 프로세스기술 | 김광희 | MRT-YR01-P3ZEN-110103 | 80 | [Plant Overall]_STEAM BLOWING - OUT PROCEDURE (For Block 3, 4) | FA | 2019-02-28 | 2019-06-21 | 2021-04-28 | 2021-04-28 | MRT-DS-REC-TT-210030 | FC | 2 | 2021-05-24 | 016/SER.00.01/LE/2021 | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2019-03-21 | 2018-05-25
DHI | 프로세스기술 | 김광희 | MRT-YK08-P2LB-111101 | 81 | [Bypass Valve & PRDS (For Block 2)]_OUTLINE DRAWING FOR BYPASS AND PRDS | FA | 2018-02-03 | 2018-05-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-15 | 180429-FC STAMPED | FC | 1 | A | MECHANICAL | BYPASS PRDS | 2018-02-14 | 2018-05-25
DHI | 프로세스기술 | 김광희 | MRT-YK08-P3LB-111101 | 82 | [Bypass Valve & PRDS (For Block 3, 4)]_OUTLINE DRAWING FOR BYPASS AND PRDS | FA | 2018-02-03 | 2018-07-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6017.0 | AB | Z0 | A | MECHANICAL | BYPASS PRDS | 2018-02-14 | 2018-05-25
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2LB-111102 | 83 | [Bypass Valve & PRDS (For Block 2)]_DATA SHEET FOR BYPASS AND PRDS | FA | 2018-02-03 | 2018-05-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-15 | 180429-FC STAMPED | FC | 1 | A | MECHANICAL | BYPASS PRDS | 2018-02-14 | 2018-05-25
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3LB-111102 | 84 | [Bypass Valve & PRDS (For Block 3, 4)]_DATA SHEET FOR BYPASS AND PRDS | FA | 2018-02-03 | 2018-07-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6017.0 | AB | Z0 | A | MECHANICAL | BYPASS PRDS | 2018-02-14 | 2018-05-25
DHI | 프로세스기술 | 김광희 | MRT-YK09-P2LB-111103 | 85 | [Bypass Valve & PRDS (For Block 2)]_Sectional drawing | FI | 2018-02-03 | 2018-05-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-15 | 180429-FC STAMPED | FC | 1 | A | MECHANICAL | BYPASS PRDS | 2018-02-14 | 2018-05-25
DHI | 프로세스기술 | 김광희 | MRT-YK09-P3LB-111103 | 86 | [Bypass Valve & PRDS (For Block 3, 4)]_Sectional drawing | FI | 2018-02-03 | 2018-07-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6017.0 | AB | Z0 | A | MECHANICAL | BYPASS PRDS | 2018-02-14 | 2018-07-27
DHI | 프로세스기술 | 김광희 | MRT-YL22-P2LB-111104 | 87 | [Bypass Valve & PRDS (For Block 2)]_Name Plate Drawing | FA | 2018-06-04 | 2018-09-04 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180457-FC | FC | 0 | 2018-10-09 | 180457-FC STAMPED | FC | 0 | A | MECHANICAL | BYPASS PRDS | 2018-06-01 | 2018-07-27
DHI | 프로세스기술 | 김광희 | MRT-YL22-P3LB-111104 | 88 | [Bypass Valve & PRDS (For Block 3, 4)]_Name Plate Drawing | FA | 2018-06-04 | 2018-09-04 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180457-FC | FC | 0 | 2018-10-09 | 180457-FC STAMPED | FC | 0 | A | MECHANICAL | BYPASS PRDS | 2018-06-01 | 2019-01-10
DHI | 프로세스기술 | 김광희 | MRT-YU04-P2LB-111105 | 89 | [Bypass Valve & PRDS (For Block 2)]_Pneumatic Diagram | FI | 2018-11-15 | 2019-02-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2019-01-12 | 180888-FC STAMPED | FC | 0 | A | I&C | BYPASS PRDS | 2018-11-16 | 2019-01-10
DHI | 프로세스기술 | 김광희 | MRT-YU04-P3LB-111105 | 90 | [Bypass Valve & PRDS (For Block 3, 4)]_Pneumatic Diagram | FI | 2018-11-15 | 2019-02-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-19 | MTW-AS-C-LT-24.4911.0 | AB | Z0 | A | I&C | BYPASS PRDS | 2018-11-16 | 2019-01-10
DHI | 프로세스기술 | 김광희 | MRT-YV02-P2LB-111106 | 91 | [Bypass Valve & PRDS (For Block 2)]_Wiring Diagram | FI | 2018-11-15 | 2019-02-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2019-01-12 | 180888-FC STAMPED | FC | 0 | A | ELECTRICAL | BYPASS PRDS | 2018-11-16 | 2019-01-10
DHI | 프로세스기술 | 김광희 | MRT-YV02-P3LB-111106 | 92 | [Bypass Valve & PRDS (For Block 3, 4)]_Wiring Diagram | FI | 2018-11-15 | 2019-02-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-19 | MTW-AS-C-LT-24.4911.0 | AB | Z0 | A | ELECTRICAL | BYPASS PRDS | 2018-11-16 | 2019-01-14
DHI | 프로세스기술 | 김광희 | MRT-DC04-P2LB-1111301 | 93 | [Bypass Valve & PRDS (For Block 2)]_O&M Manual | FI | 2018-11-30 | 2019-02-28 | 2019-01-14 | 2019-01-14 | MRT-DS-REC-TT-180940-FC | FC | 0 | 2019-01-15 | 180940-FC STAMPED | FC | 0 | A | SUPPORT | BYPASS PRDS | 2018-12-21 | 2019-01-14
DHI | 프로세스기술 | 김광희 | MRT-DC04-P3LB-1111301 | 94 | [Bypass Valve & PRDS (For Block 3, 4)]_O&M Manual | FI | 2018-11-30 | 2019-02-28 | 2019-01-14 | 2019-01-14 | MRT-DS-REC-TT-180940-FC | FC | 0 | 2019-01-15 | 180940-FC STAMPED | FC | 0 | A | SUPPORT | BYPASS PRDS | 2018-12-21 | 2018-07-05
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2PAB-113251 | 95 | [ASCS (For Block 2)]_GENERAL ARRANGEMENT DRAWING FOR AUTO SELF-CLEANING STRAINER | FA | 2018-03-09 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-12-10 | 180814-FC STAMPED | FC | 4 | A | MECHANICAL | CCW ASCS | 2018-03-14 | 2018-07-05
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3PAB-113251 | 96 | [ASCS (For Block 3, 4)]_GENERAL ARRANGEMENT DRAWING FOR AUTO SELF-CLEANING STRAINER | FA | 2018-03-09 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCW ASCS | 2018-03-14 | 2018-07-05
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2PAB-113252 | 97 | [ASCS (For Block 2)]_DATA SHEET FOR AUTO SELF-CLEANING STRAINER | FA | 2018-03-09 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-28 | 180576-FC STAMPED | FC | 3 | A | MECHANICAL | CCW ASCS | 2018-03-14 | 2018-07-05
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3PAB-113252 | 98 | [ASCS (For Block 3, 4)]_DATA SHEET FOR AUTO SELF-CLEANING STRAINER | FA | 2018-03-09 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCW ASCS | 2018-03-14 | 2018-07-05
DHI | 프로세스기술 | 김광희 | MRT-XG02-P2PAB-113253 | 99 | [ASCS (For Block 2)]_P&I DIAGRAM FOR AUTO SELF-CLEANING STRAINER | FA | 2018-03-09 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-12-10 | 180814-FC STAMPED | FC | 4 | A | MECHANICAL | CCW ASCS | 2018-03-14 | 2018-07-05
DHI | 프로세스기술 | 김광희 | MRT-XG02-P3PAB-113253 | 100 | [ASCS (For Block 3, 4)]_P&I DIAGRAM FOR AUTO SELF-CLEANING STRAINER | FA | 2018-03-09 | 2018-07-15 | 2024-10-23 | 2024-10-23 | MRT-DS-REC-TT-240019 | AB | Z1 | 2024-11-08 | MTW-AS-C-LT-24.5927.0 | AB | Z1 | A | MECHANICAL | CCW ASCS | 2018-03-14 | 2018-12-10
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2PAB-113263 | 101 | [ASCS (For Block 2)]_CONTROL PANEL OUTLINE AND WIRING DRAWING FOR AUTO SELF-CLEANING STRAINER | FI | 2018-11-07 | 2019-02-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-12-17 | 180868-FC STAMPED | FC | 0 | A | I&C | CCW ASCS | 2018-11-12 | 2018-12-10
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3PAB-113263 | 102 | [ASCS (For Block 3, 4)]_CONTROL PANEL OUTLINE AND WIRING DRAWING FOR AUTO SELF-CLEANING STRAINER | FI | 2018-11-07 | 2019-02-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-07-01 | MTW-AS-C-LT-24.5459.0 | AB | Z0 | A | I&C | CCW ASCS | 2018-11-12 | 2018-12-10
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P2PAB-113267 | 103 | [ASCS (For Block 2)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-07 | 2019-02-07 | 2018-12-10 | 2018-12-11 | MRT-DS-REC-TT-180868-FC | FC | 0 | 2018-12-17 | 180868-FC STAMPED | FC | 0 | A | SUPPORT | CCW ASCS | 2018-11-12 | 2018-12-10
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P3PAB-113267 | 104 | [ASCS (For Block 3, 4)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-07 | 2019-02-07 | 2018-12-10 | 2018-12-11 | MRT-DS-REC-TT-180868-FC | FC | 0 | 2018-12-17 | 180868-FC STAMPED | FC | 0 | A | SUPPORT | CCW ASCS | 2018-11-12 | 2018-03-21
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2PGB-113200 | 105 | [CCW Heat Exchanger (For Block 2)]_DATA SHEET FOR PLATE TYPE HEAT EXCHANGER | FA | 2018-02-01 | 2018-05-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-08-13 | 180212-FC STAMPED | FC | 2 | A | MECHANICAL | CCW HX | 2018-02-02 | 2018-03-21
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3PGB-113200 | 106 | [CCW Heat Exchanger (For Block 3, 4)]_DATA SHEET FOR PLATE TYPE HEAT EXCHANGER | FA | 2018-02-01 | 2018-07-03 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCW HX | 2018-02-02 | 2018-05-11
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2PGB-113201 | 107 | [CCW Heat Exchanger (For Block 2)]_OUTLINE DRAWING FOR PLATE TYPE HEAT EXCHANGER | FI | 2018-02-01 | 2018-05-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-08-29 | 180385-FC STAMPED | FC | 3 | A | MECHANICAL | CCW HX | 2018-02-02 | 2018-05-11
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3PGB-113201 | 108 | [CCW Heat Exchanger (For Block 3, 4)]_OUTLINE DRAWING FOR PLATE TYPE HEAT EXCHANGER | FI | 2018-02-01 | 2018-07-03 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCW HX | 2018-02-02 | 2018-12-10
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P2PGB-113203 | 109 | [CCW Heat Exchanger (For Block 2)]_Installation & O&M MANUAL | FI | 2018-11-07 | 2019-02-07 | 2018-12-10 | 2018-12-11 | MRT-DS-REC-TT-180868-FC | FC | 0 | 2018-12-17 | 180868-FC STAMPED | FC | 0 | A | SUPPORT | CCW HX | 2018-11-12 | 2018-12-10
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P3PGB-113203 | 110 | [CCW Heat Exchanger (For Block 3, 4)]_Installation & O&M MANUAL | FI | 2018-11-07 | 2019-02-07 | 2018-12-10 | 2018-12-11 | MRT-DS-REC-TT-180868-FC | FC | 0 | 2018-12-17 | 180868-FC STAMPED | FC | 0 | A | SUPPORT | CCW HX | 2018-11-12 | 2018-03-29
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2PGB-113101 | 111 | [CCWP (For Block 2)]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | FA | 2018-02-04 | 2018-05-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-28 | 180577-FC STAMPED | FC | 2 | A | MECHANICAL | CCWP | 2018-02-07 | 2018-03-29
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3PGB-113101 | 112 | [CCWP (For Block 3, 4)]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | FA | 2018-02-04 | 2018-07-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCWP | 2018-02-07 | 2018-03-29
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2PGB-113102 | 113 | [CCWP (For Block 2)]_DATA SHEET FOR CLOSED COOLING WATER PUMP | FA | 2018-02-04 | 2018-05-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-03 | 180252-FC STAMPED | FC | 1 | A | MECHANICAL | CCWP | 2018-02-07 | 2018-03-29
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3PGB-113102 | 114 | [CCWP (For Block 3, 4)]_DATA SHEET FOR CLOSED COOLING WATER PUMP | FA | 2018-02-04 | 2018-07-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCWP | 2018-02-07 | 2018-05-11
DHI | 프로세스기술 | 김광희 | MRT-YK10-P2PGB-113103 | 115 | [CCWP (For Block 2)]_Pump Sectional Drawing | FI | 2018-03-06 | 2018-06-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-08-25 | 180386-FC STAMPED | FC | 1 | A | MECHANICAL | CCWP | 2018-03-07 | 2018-05-11
DHI | 프로세스기술 | 김광희 | MRT-YK10-P3PGB-113103 | 116 | [CCWP (For Block 3, 4)]_Pump Sectional Drawing | FI | 2018-03-06 | 2018-08-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | MECHANICAL | CCWP | 2018-03-07 | 2018-04-18
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2PGB-113104 | 117 | [CCWP (For Block 2)]_DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2018-03-06 | 2018-06-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-23 | 180787-FC STAMPED | FC | 3 | A | ELECTRICAL | CCWP | 2018-03-07 | 2018-04-18
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3PGB-113104 | 118 | [CCWP (For Block 3, 4)]_DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2018-03-06 | 2018-08-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | ELECTRICAL | CCWP | 2018-03-07 | 2018-04-18
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2PGB-113105 | 119 | [CCWP (For Block 2)]_OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2018-03-06 | 2018-06-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-23 | 180787-FC STAMPED | FC | 3 | A | ELECTRICAL | CCWP | 2018-03-07 | 2018-04-18
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3PGB-113105 | 120 | [CCWP (For Block 3, 4)]_OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FA | 2018-03-06 | 2018-08-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4980.0 | AB | Z0 | A | ELECTRICAL | CCWP | 2018-03-07 | 2018-11-12
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2PGB-113107 | 121 | [CCWP (For Block 2)]_MAIN TERNINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FI | 2018-10-31 | 2019-01-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2019-01-31 | 180889-FC STAMPED | FC | 1 | A | ELECTRICAL | CCWP | 2018-10-31 | 2018-11-12
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3PGB-113107 | 122 | [CCWP (For Block 3, 4)]_MAIN TERNINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | FI | 2018-10-31 | 2019-01-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-07-01 | MTW-AS-C-LT-24.5459.0 | AB | Z0 | A | ELECTRICAL | CCWP | 2018-10-31 | 2017-12-11
DHI | 프로세스기술 | 김광희 | MRT-XW03-P2PGB-113110 | 123 | [CCWP (For Block 2)]_SIZING CALCULATION FOR CLOSED COOLING WATER PUMP | FA | 2017-08-01 | 2017-11-01 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | CCWP | 2017-08-21 | 2017-12-11
DHI | 프로세스기술 | 김광희 | MRT-XW03-P3PGB-113110 | 124 | [CCWP (For Block 3, 4)]_SIZING CALCULATION FOR CLOSED COOLING WATER PUMP | FA | 2017-08-01 | 2017-12-31 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170127-FC | FC | 2 | 2018-09-22 | 170127-FC STAMPED | FC | 2 | A | MECHANICAL | CCWP | 2017-08-21 | 2018-11-12
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P2PGB-113116 | 125 | [CCWP (For Block 2)]_INSTALLATION MANUAL | FI | 2018-10-31 | 2019-01-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180851-FC | FC | 0 | 2018-12-07 | 180851-FC STAMPED | FC | 0 | A | SUPPORT | CCWP | 2018-10-31 | 2018-11-12
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P3PGB-113116 | 126 | [CCWP (For Block 3, 4)]_INSTALLATION MANUAL | FI | 2018-10-31 | 2019-01-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180851-FC | FC | 0 | 2018-12-07 | 180851-FC STAMPED | FC | 0 | A | SUPPORT | CCWP | 2018-10-31 | 2018-11-12
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P2PGB-113117 | 127 | [CCWP (For Block 2)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-10-31 | 2019-01-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180851-FC | FC | 0 | 2018-12-07 | 180851-FC STAMPED | FC | 0 | A | SUPPORT | CCWP | 2018-10-31 | 2018-11-12
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P3PGB-113117 | 128 | [CCWP (For Block 3, 4)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-10-31 | 2019-01-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180851-FC | FC | 0 | 2018-12-07 | 180851-FC STAMPED | FC | 0 | A | SUPPORT | CCWP | 2018-10-31 | 2018-11-12
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P2PGB-113118 | 129 | [CCWP (For Block 2)]_COMMISSIONING MANUAL | FI | 2018-10-31 | 2019-01-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180851-FC | FC | 0 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 0 | I | SUPPORT | CCWP | 2018-10-31 | 2018-11-12
DHI | 프로세스기술 | 김광희 | MRT-CQ02-P3PGB-113118 | 130 | [CCWP (For Block 3, 4)]_COMMISSIONING MANUAL | FI | 2018-10-31 | 2019-01-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180851-FC | FC | 0 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 0 | I | SUPPORT | CCWP | 2018-10-31 | 2018-07-17
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2ZEN-113300 | 133 | [MOV (Gate & Globe)(DHI) (For Block 2)]_OUTLINE DRAWING FOR MOV (G&G) | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-22 | 180618-FC STAMPED | FC | 2 | A | MECHANICAL | MOV | 2018-03-05 | 2018-07-17
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3ZEN-113300 | 134 | [MOV (Gate & Globe)(DHI) (For Block 3, 4)]_OUTLINE DRAWING FOR MOV (G&G) | FA | 2018-06-20 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-07-01 | MTW-AS-C-LT-24.5459.0 | AB | Z0 | A | MECHANICAL | MOV | 2018-03-05 | 2018-07-27
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2ZEN-113301 | 135 | [MOV (Gate & Globe)(DHI) (For Block 2)]_DATA SHEET FOR MOV (G&G) | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-09-12 | 180619-FC STAMPED | FC | 2 | A | MECHANICAL | MOV | 2018-03-05 | 2018-07-27
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3ZEN-113301 | 136 | [MOV (Gate & Globe)(DHI) (For Block 3, 4)]_DATA SHEET FOR MOV (G&G) | FA | 2018-06-20 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-07-01 | MTW-AS-C-LT-24.5459.0 | AB | Z0 | A | MECHANICAL | MOV | 2018-03-05 | 2018-12-04
DHI | 프로세스기술 | 김광희 | MRT-CT00-P2ZEN-113300 | 137 | [MOV (GATE & GLOBE)(DHI) (For Block 2)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-15 | 2019-02-15 | 2018-12-04 | 2018-12-04 | MRT-DS-REC-TT-180859-FC | FC | 0 | 2018-12-12 | 180859-FC STAMPED | FC | 0 | A | SUPPORT | MOV | 2018-11-05 | 2018-12-04
DHI | 프로세스기술 | 김광희 | MRT-CT00-P3ZEN-113300 | 138 | [MOV (GATE & GLOBE)(DHI) (For Block 3, 4)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-15 | 2019-02-15 | 2018-12-04 | 2018-12-04 | MRT-DS-REC-TT-180859-FC | FC | 0 | 2018-12-12 | 180859-FC STAMPED | FC | 0 | A | SUPPORT | MOV | 2018-11-05 | 2018-04-04
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2ZEN-113400 | 139 | [MOV (Butterfly)(DHI) (For Block 2)]_OUTLINE DRAWING FOR MOV (BUTTERFLY) | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-16 | 180736-FC STAMPED | FC | 2 | A | MECHANICAL | MOV | 2018-02-14 | 2018-04-04
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3ZEN-113400 | 140 | [MOV (Butterfly)(DHI) (For Block 3, 4)]_OUTLINE DRAWING FOR MOV (BUTTERFLY) | FA | 2018-06-20 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-07-01 | MTW-AS-C-LT-24.5459.0 | AB | Z0 | A | MECHANICAL | MOV | 2018-02-14 | 2018-04-04
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2ZEN-113401 | 141 | [MOV (Butterfly)(DHI) (For Block 2)]_DATA SHEET FOR MOV (BUTTERFLY) | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-16 | 180736-FC STAMPED | FC | 2 | A | MECHANICAL | MOV | 2018-02-14 | 2018-04-04
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3ZEN-113401 | 142 | [MOV (Butterfly)(DHI) (For Block 3, 4)]_DATA SHEET FOR MOV (BUTTERFLY) | FA | 2018-06-20 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-07-01 | MTW-AS-C-LT-24.5459.0 | AB | Z0 | A | MECHANICAL | MOV | 2018-02-14 | 2018-12-04
DHI | 프로세스기술 | 김광희 | MRT-CT00-P2ZEN-113400 | 143 | [MOV (Butterfly)(DHI) (For Block 2)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-15 | 2019-02-15 | 2018-12-04 | 2018-12-04 | MRT-DS-REC-TT-180860-FC | FC | 0 | 2018-12-12 | 180860-FC STAMPED | FC | 0 | A | SUPPORT | MOV | 2018-11-05 | 2018-12-04
DHI | 프로세스기술 | 김광희 | MRT-CT00-P3ZEN-113400 | 144 | [MOV (Butterfly)(DHI) (For Block 3, 4)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-15 | 2019-02-15 | 2018-12-04 | 2018-12-04 | MRT-DS-REC-TT-180860-FC | FC | 0 | 2018-12-12 | 180860-FC STAMPED | FC | 0 | A | SUPPORT | MOV | 2018-11-05 | 2017-12-13
DHI | 프로세스기술 | 김광희 | MRT-XG02-P0QJA-110010 | 145 | [N2 Gas system]_P&ID | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | 2020-12-04 | 140/T/MRT/REC/XII/2020 | FC | 5 | A | MECHANICAL | N2 GAS SYSTEM | 2017-07-10 | 2018-07-27
DHI | 프로세스기술 | 김광희 | MRT-YD00-P0QJA-111101 | 146 | [N2 Gas System]_General Arrangement Drawing | FA | 2018-06-26 | 2018-09-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-05 | 180544-FC STAMPED | FC | 0 | A | MECHANICAL | N2 GAS SYSTEM | 2018-06-27 | 2018-11-29
DHI | 프로세스기술 | 김광희 | MRT-YD00-P0QJA-111601 | 147 | [N2 Gas system] O&M Manual | FI | 2018-11-02 | 2019-02-08 | 2018-11-29 | 2018-12-07 | MRT-DS-REC-TT-180862-FC | FC | 0 | 2018-12-11 | 180862-FC STAMPED | FC | 0 | A | SUPPORT | N2 GAS SYSTEM | 2018-11-06 | 2018-04-04
DHI | 프로세스기술 | 김광희 | MRT-YD00-P2ZEN-113500 | 148 | [COMBINED NONRETURN VALVE(DHI) (For Block 2)]_OUTLINE DRAWING FOR C-NRV | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-31 | 180737-FC STAMPED | FC | 2 | A | MECHANICAL | NRV | 2018-02-14 | 2018-04-04
DHI | 프로세스기술 | 김광희 | MRT-YD00-P3ZEN-113500 | 149 | [COMBINED NONRETURN VALVE(DHI) (For Block 3, 4)]_OUTLINE DRAWING FOR C-NRV | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-06-24 | MTW-AS-C-LT-24.5412.0 | AB | Z0 | A | MECHANICAL | NRV | 2018-02-14 | 2018-04-04
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2ZEN-113501 | 150 | [COMBINED NONRETURN VALVE(DHI) (For Block 2)]_DATA SHEET FOR C-NRV | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-31 | 180737-FC STAMPED | FC | 2 | A | MECHANICAL | NRV | 2018-02-14 | 2018-04-04
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3ZEN-113501 | 151 | [COMBINED NONRETURN VALVE(DHI) (For Block 3, 4)]_DATA SHEET FOR C-NRV | FA | 2018-06-20 | 2018-09-20 | 2024-10-23 | 2024-10-23 | MRT-DS-REC-TT-240019 | AB | Z1 | 2024-11-08 | MTW-AS-C-LT-24.5927.0 | AB | Z1 | A | MECHANICAL | NRV | 2018-02-14 | 2018-11-29
DHI | 프로세스기술 | 김광희 | MRT-CT00-P2ZEN-113500 | 152 | [COMBINED NONRETURN VALVE(DHI) (For Block 2)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-15 | 2019-02-15 | 2018-11-29 | 2018-12-07 | MRT-DS-REC-TT-180861-FC | FC | 0 | 2018-12-13 | 180861-FC STAMPED | FC | 0 | A | SUPPORT | NRV | 2018-11-05 | 2018-11-29
DHI | 프로세스기술 | 김광희 | MRT-CT00-P3ZEN-113500 | 153 | [COMBINED NONRETURN VALVE(DHI) (For Block 3, 4)]_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-15 | 2019-02-15 | 2018-11-29 | 2018-12-07 | MRT-DS-REC-TT-180861-FC | FC | 0 | 2018-12-13 | 180861-FC STAMPED | FC | 0 | A | SUPPORT | NRV | 2018-11-05 | 2018-06-26
DHI | 프로세스기술 | 김광희 | MRT-YK08-P2LBG-111300 | 154 | [Silencer (For Block 2)]_OUTLINE DRAWING FOR Silencer | FI | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2020-03-02 | 200023-FC STAMPED | FC | 3 | I | MECHANICAL | SILENCER | 2018-05-18 | 2018-06-26
DHI | 프로세스기술 | 김광희 | MRT-YK08-P3LBG-111300 | 155 | [Silencer (For Block 3, 4)]_OUTLINE DRAWING FOR Silencer | FI | 2018-06-20 | 2018-11-19 | 2024-10-23 | 2024-10-23 | MRT-DS-REC-TT-240019 | AB | Z1 | 2024-11-08 | MTW-AS-C-LT-24.5927.0 | AB | Z1 | A | MECHANICAL | SILENCER | 2018-05-18 | 2018-06-26
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2LBG-111301 | 156 | [Silencer (For Block 2)]_DATA SHEET FOR Silencer | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-10-05 | 180536-FC STAMPED | FC | 1 | A | MECHANICAL | SILENCER | 2018-05-18 | 2018-06-26
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3LBG-111301 | 157 | [Silencer (For Block 3, 4)]_DATA SHEET FOR Silencer | FA | 2018-06-20 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-06-24 | MTW-AS-C-LT-24.5412.0 | AB | Z0 | A | MECHANICAL | SILENCER | 2018-05-18 | 2018-05-10
DHI | 프로세스기술 | 김광희 | MRT-YK08-P2ZEN-111200 | 158 | [Safety Relief Valve(DHI) (For Block 2)]_OUTLINE DRAWING FOR SAFETY AND RELIEF VALVE | FI | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-08-25 | 180370-FC STAMPED | FC | 1 | A | MECHANICAL | SRV | 2018-03-19 | 2018-05-10
DHI | 프로세스기술 | 김광희 | MRT-YK08-P3ZEN-111200 | 159 | [Safety Relief Valve(DHI) (For Block 3, 4)]_OUTLINE DRAWING FOR SAFETY AND RELIEF VALVE | FI | 2018-06-20 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2024-06-24 | MTW-AS-C-LT-24.5412.0 | AB | Z0 | A | MECHANICAL | SRV | 2018-03-19 | 2018-05-10
DHI | 프로세스기술 | 김광희 | MRT-YT01-P2ZEN-111201 | 160 | [Safety Relief Valve(DHI) (For Block 2)]_DATA SHEET FOR SAFETY AND RELIEF VALVE | FA | 2018-06-20 | 2018-09-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | 2018-08-25 | 180370-FC STAMPED | FC | 1 | A | MECHANICAL | SRV | 2018-03-19 | 2018-05-10
DHI | 프로세스기술 | 김광희 | MRT-YT01-P3ZEN-111201 | 161 | [Safety Relief Valve(DHI) (For Block 3, 4)]_DATA SHEET FOR SAFETY AND RELIEF VALVE | FA | 2018-06-20 | 2018-11-19 | 2024-11-11 | 2024-11-11 | MRT-DS-REC-TT-240025 | AB | Z2 | 2024-11-21 | MTW-AS-C-LT-24.5975.0 | AB | Z2 | A | MECHANICAL | SRV | 2018-03-19 | 2017-12-19
DHI | 플랜트기술 | 류두현 | MRT-XG02-P2SCA-120004 | 162 | [Compressed air system (DHI for Block 2)]_P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | FA | 2017-07-07 | 2017-11-05 | 2024-11-19 | 2024-11-19 | MRT-DS-REC-TT-240036 | AB | Z1 | 2024-11-29 | MTW-AS-C-LT-24.6005.0 | AB | Z1 | A | MECHANICAL | BOP SYSTEM | 2017-07-11 | 2017-12-19
DHI | 플랜트기술 | 류두현 | MRT-XG02-P3SCA-120004 | 163 | [Compressed air system (DHI for Block 3, 4)]_P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | FA | 2017-07-07 | 2017-12-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-11 | 2017-12-19
DHI | 플랜트기술 | 류두현 | MRT-XG02-P2SCA-120005 | 164 | [Compressed air system (DHI for Block 2)]_P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | FA | 2017-07-07 | 2017-11-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-11 | 2017-12-19
DHI | 플랜트기술 | 류두현 | MRT-XG02-P3SCA-120005 | 165 | [Compressed air system (DHI for Block 3, 4)]_P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | FA | 2017-07-07 | 2017-12-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-11 | 2017-12-19
DHI | 플랜트기술 | 류두현 | MRT-XG02-P2SCA-120006 | 166 | [Compressed air system (DHI for Block 2)]_P&I DIAGRAM FOR SERVICE AIR SYSTEM | FA | 2017-07-07 | 2017-11-05 | 2025-02-07 | 2025-02-07 | MRT-DS-REC-TT-250006 | AB | Z3 | 2025-02-17 | MTW-AS-C-LT-25.6202.0 | AB | Z3 | A | MECHANICAL | BOP SYSTEM | 2017-07-11 | 2017-12-19
DHI | 플랜트기술 | 류두현 | MRT-XG02-P3SCA-120006 | 167 | [Compressed air system (DHI for Block 3, 4)]_P&I DIAGRAM FOR SERVICE AIR SYSTEM | FA | 2017-07-07 | 2017-12-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-11 | 2017-11-22
DHI | 플랜트기술 | 류두현 | MRT-XS00-P2SCA-120015 | 168 | [Compressed air system (DHI for Block 2)]_SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | FA | 2017-07-07 | 2017-11-05 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170090-FC | FC | 2 | 2018-09-22 | 170090-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-19 | 2017-11-22
DHI | 플랜트기술 | 류두현 | MRT-XS00-P3SCA-120015 | 169 | [Compressed air system (DHI for Block 3,4)]_SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | FA | 2017-07-07 | 2017-12-05 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170090-FC | FC | 2 | 2018-09-22 | 170090-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-19 | 2017-11-28
DHI | 플랜트기술 | 류두현 | MRT-XW03-P2SCA-120017 | 170 | [Compressed air system (DHI for Block 2)]_SIZING CALCULATION_COMPRESSED AIR SYSTEM | FA | 2017-08-07 | 2017-11-05 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170111-FC | FC | 2 | 2018-09-22 | 170111-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-08-28 | 2017-11-28
DHI | 플랜트기술 | 류두현 | MRT-XW03-P3SCA-120017 | 171 | [Compressed air system (DHI for Block 3, 4)]_SIZING CALCULATION_COMPRESSED AIR SYSTEM | FA | 2017-08-07 | 2018-01-04 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170111-FC | FC | 2 | 2018-09-22 | 170111-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-08-28 | 2018-01-19
DHI | 플랜트기술 | 오광일 | MRT-XS00-P2MAV-120053 | 172 | [Clean & Dirty Oil Storage System(For Block 2)]_System Description | FA | 2017-07-07 | 2017-11-07 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-180032-FC | FC | 3 | 2018-09-24 | 180032-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-07-19 | 2018-01-19
DHI | 플랜트기술 | 오광일 | MRT-XS00-P3MAV-120053 | 173 | [Clean & Dirty Oil Storage System(For Block 3,4)]_System Description | FA | 2017-07-07 | 2017-12-07 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-180032-FC | FC | 3 | 2018-09-24 | 180032-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-07-19 | 2018-01-19
DHI | 플랜트기술 | 오광일 | MRT-XG02-P2MAV-120054 | 174 | [Clean & Dirty Oil Storage System(For Block 2)]_P&ID | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-11 | 2018-01-19
DHI | 플랜트기술 | 오광일 | MRT-XG02-P3MAV-120054 | 175 | [Clean & Dirty Oil Storage System(For Block 3,4)]_P&ID | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-11 | 2017-12-08
DHI | 플랜트기술 | 이태훈 | MRT-XG02-P0GHD-120001 | 176 | [Service water distribution system]_P&ID | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-11 | 2017-11-23
DHI | 플랜트기술 | 이태훈 | MRT-XG02-P0GKC-120001 | 177 | [Potable water distribution system]_P&ID | FA | 2017-07-07 | 2017-11-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | 2024-11-18 | MTW-AS-C-LT-23.4183.0 | AB | Z0 | A | MECHANICAL | BOP SYSTEM | 2017-07-11 | 2017-11-21
DHI | 플랜트기술 | 이태훈 | MRT-XS00-P0GHD-120001 | 178 | [Service water distribution system]_system description | FA | 2017-07-07 | 2017-11-07 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170089-FC | FC | 2 | 2018-10-02 | 170089-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-19 | 2017-11-21
DHI | 플랜트기술 | 이태훈 | MRT-XS00-P0GKC-120001 | 179 | [Potable water distribution system]_system description | FA | 2017-07-07 | 2017-11-07 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170089-FC | FC | 2 | 2018-10-02 | 170089-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-07-19 | 2018-04-20
DHI | 플랜트기술 | 오광일 | MRT-XW03-P2MAV-120001 | 180 | [General Service Pump (oil) DHI for Block 2_Design]_sizing Calculation | FA | 2018-02-28 | 2018-05-29 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180329-FC | FC | 1 | 2018-09-06 | 180329-FC STAMPED | FC | 1 | A | MECHANICAL | BOP SYSTEM | 2018-03-09 | 2018-04-20
DHI | 플랜트기술 | 오광일 | MRT-XW03-P3MAV-130001 | 181 | [General Service Pump (oil) DHI for Block 3, 4_Design]_sizing Calculation | FA | 2018-02-28 | 2018-07-29 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180329-FC | FC | 1 | 2018-09-06 | 180329-FC STAMPED | FC | 1 | A | MECHANICAL | BOP SYSTEM | 2018-03-09 | 2018-03-06
DHI | 플랜트기술 | 이태훈 | MRT-XW03-P3GHD-120001 | 182 | [Service Water Pump (DHI for Block 3,4)]_SIZING CALCULATION | FA | 2017-11-30 | 2018-02-28 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180149-FC | FC | 2 | 2018-08-13 | 180149-FC STAMPED | FC | 2 | A | MECHANICAL | BOP SYSTEM | 2017-12-13 | 2018-06-27
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P2GM-128508 | 183 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_Sizing Calculation | FA | 2017-11-24 | 2018-03-24 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180547-FC | FC | 3 | 2018-10-23 | 180547-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-12-21 | 2018-06-27
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P3GM-128508 | 184 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_Sizing Calculation | FA | 2017-11-24 | 2018-03-24 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180547-FC | FC | 3 | 2018-10-23 | 180547-FC STAMPED | FC | 3 | A | MECHANICAL | BOP SYSTEM | 2017-12-21 | 2017-12-08
DHI | 플랜트기술 | 이태훈 | MRT-XG07-P0ZEN-120050 | 185 | [Plant Overall]_WATER BALANCE DIAGRAM | FA | 2017-06-09 | 2017-09-07 | 2018-09-14 | 2018-10-10 | MRT-DS-REC-TT-180733-FC | FC | 4 | 2018-10-16 | 180733-FC STAMPED | FC | 4 | A | MECHANICAL | BOP SYSTEM | 2017-06-30 | 2018-04-17
DHI | 플랜트기술 | 오슬기 | MRT-YQ03-P2LB-122088 | 186 | [HRSG(For Block 2)]_HRSG_PERFORMANCE AND OPERATIONAL DATA | FA | 2017-11-01 | 2018-01-30 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180320-FC | FC | 3 | 2018-09-10 | 180320-FC STAMPED | FC | 3 | A | MECHANICAL | HRSG | 2017-11-09 | 2018-04-17
DHI | 플랜트기술 | 오슬기 | MRT-YQ03-P3LB-122088 | 187 | [HRSG(For Block 3, 4)]_HRSG_PERFORMANCE AND OPERATIONAL DATA | FA | 2017-11-01 | 2018-01-30 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180320-FC | FC | 2 | 2018-09-10 | 180320-FC STAMPED | FC | 2 | A | MECHANICAL | HRSG | 2018-02-21 | 2018-04-05
DHI | 플랜트기술 | 오슬기 | MRT-XG02-P2LB-122022 | 188 | [HRSG(For Block 2)]_HRSG_P&I DIAGRAM | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2017-07-10 | 2018-04-05
DHI | 플랜트기술 | 오슬기 | MRT-XG02-P3LB-122022 | 189 | [HRSG(for Block 3, 4)]_HRSG_P&I DIAGRAM | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-08 | 2018-01-19
DHI | 플랜트기술 | 오슬기 | MRT-XS00-P2LB-122035 | 190 | [HRSG(For Block 2)]_HRSG_SYSTEM DESCRIPTION | FA | 2018-01-01 | 2018-04-01 | 2018-07-27 | 2018-09-19 | MRT-DS-REC-TT-180160-FC | FC | 2 | 2018-09-28 | 180160-FC STAMPED | FC | 2 | A | MECHANICAL | HRSG | 2017-12-21 | 2018-04-02
DHI | 플랜트기술 | 오슬기 | MRT-XS00-P3LB-122035 | 191 | [HRSG(for Block 3, 4)]_HRSG_SYSTEM DESCRIPTION | FA | 2018-01-01 | 2018-04-01 | 2018-07-27 | 2018-08-20 | MRT-DS-REC-TT-180262-FC | FC | 2 | 2018-09-10 | 180262-FC STAMPED | FC | 2 | A | MECHANICAL | HRSG | 2018-01-19 | #VALUE!
DHI | 플랜트기술 | 오슬기 | MRT-XS00-P2LB-122037 | 192 | [HRSG(For Block 2)]_HRSG_BLOWDOWN SYSTEM SUMMARY | FI | 2017-12-01 |  | 2018-07-28 | 2018-07-28 | MRT-DS-REC-TT-180687 | FI | 2 | 2018-08-03 | 685/T/MRT/REC/VIII/2018 | FI | 2 | I | MECHANICAL | HRSG | 2017-12-07 | #VALUE!
DHI | 플랜트기술 | 오슬기 | MRT-XS00-P3LB-122037 | 193 | [HRSG(For Block 3, 4)]_HRSG_BLOWDOWN SYSTEM SUMMARY | FI | 2017-12-01 |  | 2018-07-28 | 2018-07-28 | MRT-DS-REC-TT-180687 | FI | 1 | 2018-08-03 | 685/T/MRT/REC/VIII/2018 | FI | 1 | I | MECHANICAL | HRSG | 2018-03-05 | 2018-03-21
DHI | 플랜트기술 | 오슬기 | MRT-UE00-P2LB-122007 | 194 | [HRSG(For Block 2)]_HRSG_GENERAL ARRANGEMENT | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2017-11-17 | 2018-03-21
DHI | 플랜트기술 | 오슬기 | MRT-UE00-P3LB-122007 | 195 | [HRSG(For Block 3, 4)]_HRSG_GENERAL ARRANGEMENT | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-21 | #VALUE!
DHI | 플랜트기술 | 오슬기 | MRT-XV00-P2LB-122039 | 196 | [HRSG(For Block 2)]_HRSG_EQUIPMENT LIST | FI | 2018-03-01 |  | 2018-08-16 | 2018-08-16 | MRT-DS-REC-TT-180705 | FI | 1 | 2018-08-28 | 752/T/MRT/REC/VIII/2018 | FI | 1 | I | MECHANICAL | HRSG | 2018-02-28 | #VALUE!
DHI | 플랜트기술 | 오슬기 | MRT-XV00-P3LB-122039 | 197 | [HRSG(For Block 3, 4)]_HRSG_EQUIPMENT LIST | FI | 2018-03-01 |  | 2018-08-16 | 2018-08-16 | MRT-DS-REC-TT-180705 | FI | 1 | 2018-08-28 | 752/T/MRT/REC/VIII/2018 | FI | 1 | I | MECHANICAL | HRSG | 2018-02-28 | 2018-03-14
DHI | 플랜트기술 | 오슬기 | MRT-UE00-P2LB-122008 | 198 | [HRSG(For Block 2)]_HRSG_ARRANGEMENT OF CASING & FIELD ERECTION | FI | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2017-11-09 | 2018-03-14
DHI | 플랜트기술 | 오슬기 | MRT-UE00-P3LB-122008 | 199 | [HRSG(for Block 3, 4)]_HRSG_ARRANGEMENT OF CASING & FIELD ERECTION | FI | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-21 | 2018-03-21
DHI | 플랜트기술 | 오슬기 | MRT-UE00-P2LB-122010 | 200 | [HRSG(For Block 2)]_HRSG_ARRANGEMENT OF MAIN STACK & FIELD ERECTION | FI | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-01-08 | 2018-03-21
DHI | 플랜트기술 | 오슬기 | MRT-UE00-P3LB-122010 | 201 | [HRSG(for Block 3, 4)]_HRSG_ARRANGEMENT OF MAIN STACK & FIELD ERECTION | FI | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-01-08 | 2018-07-12
DHI | 플랜트기술 | 오슬기 | MRT-VN03-P2LB-122015 | 202 | [HRSG(For Block 2)]_HRSG_ARRANGEMENT FOR PLATFORM STRUCTURE | FI | 2018-02-01 | 2018-05-02 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-08 | 2018-07-12
DHI | 플랜트기술 | 오슬기 | MRT-VN03-P3LB-122015 | 203 | [HRSG(For Block 3, 4)]_HRSG_ARRANGEMENT FOR PLATFORM STRUCTURE | FI | 2018-02-01 | 2018-05-02 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-08 | #VALUE!
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P2LB-122022 | 204 | [HRSG(for Block 2, 3 & 4)]_HRSG_PRESSURE PARTS DESIGN REPORT | FI | 2018-03-20 |  | 2018-11-07 | 2018-11-07 | MRT-DS-REC-TT-180863 | FI | 1 | 2019-01-02 | 1169/T/MRT/REC/XII/2018 | FI | 1 | I | MECHANICAL | HRSG | 2018-03-20 | 2018-01-16
DHI | 플랜트기술 | 오슬기 | MRT-YB03-P2LB-122048 | 205 | [HRSG(For Block 2)]_HRSG_PRESSURE PART ARRANGEMENT | FI | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2017-12-07 | 2018-03-14
DHI | 플랜트기술 | 오슬기 | MRT-YB03-P3LB-122048 | 206 | [HRSG(for Block 3, 4)]_HRSG_PRESSURE PART ARRANGEMENT | FI | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-01-16 | 2018-07-03
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122049 | 207 | [HRSG(For Block 2)]_HRSG_SPEC. & DRAWING FOR STEAM DRUM | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-01 | 2018-07-03
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122049 | 208 | [HRSG(for Block 3, 4)]_HRSG_SPEC. & DRAWING FOR STEAM DRUM | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-01 | 2018-06-14
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122050 | 209 | [HRSG(For Block 2)]_HRSG_SPEC. & DRAWING FOR BLOWDOWN PUMP | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2018-06-14
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122050 | 210 | [HRSG(For Block 3, 4)]_HRSG_SPEC. & DRAWING FOR BLOWDOWN PUMP | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2018-06-14
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P2LB-122051 | 211 | [HRSG(For Block 2)]_HRSG_SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2018-06-14
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P3LB-122051 | 212 | [HRSG(For Block 3, 4)]_HRSG_SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2018-06-14
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122052 | 213 | [HRSG(For Block 2)]_HRSG_SPEC. & DRAWING FOR STACK DAMPER | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2018-06-14
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122052 | 214 | [HRSG(For Block 3, 4)]_HRSG_SPEC. & DRAWING FOR STACK DAMPER | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2018-06-14
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122053 | 215 | [HRSG(For Block 2)]_HRSG_SPEC. & DRAWING FOR SILENCER | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2018-06-14
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122053 | 216 | [HRSG(For Block 3, 4)]_HRSG_SPEC. & DRAWING FOR SILENCER | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2018-08-06
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122055 | 217 | [HRSG(For Block 2)]_HRSG_EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | FI | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2018-08-06
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122055 | 218 | [HRSG(For Block 3, 4)]_HRSG_EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | FI | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2018-10-31
DHI | 플랜트기술 | 오슬기 | MRT-YB03-P2LB-122113 | 219 | [HRSG(for Block 2, 3&4)]_ HRSG_PRESSURE PART DETAIL FOR INSTALLATION | FI | 2018-10-24 | 2018-11-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-10-24 | 2018-11-26
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122120 | 220 | [HRSG(for Block 2, 3&4)]_HRSG_CASING EXPANSION JOINT DRAWINGS FOR INSTALLATION | FI | 2018-11-22 | 2019-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-11-22 | 2018-04-24
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P2LB-122106 | 221 | [HRSG(For Block 2)]_HRSG_DIVERTER & GUILLOTINE DAMPER DOCUMENT PACKAGE | FA | 2017-12-15 | 2018-02-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2017-12-15 | 2018-04-24
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P3LB-122106 | 222 | [HRSG(For Block 3, 4)]_HRSG_DIVERTER & GUILLOTINE DAMPER DOCUMENT PACKAGE | FA | 2017-12-15 | 2018-02-01 | 2024-11-14 | 2024-11-14 | MRT-DS-REC-TT-240028 | AB | Z1 | 2024-11-26 | MTW-AS-C-LT-24.5992.0 | AB | Z1 | A | MECHANICAL | HRSG | 2017-12-15 | 2018-11-09
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P2LB-122117 | 223 | [HRSG(for Block 2, 3&4)]_HRSG_DIVERTER DAMPER DRAWINGS FOR INSTALLATION | FI | 2018-11-12 | 2019-01-11 | 2018-11-09 | 2018-11-12 | MRT-DS-REC-TT-180869-FC | FC | 0 | 2018-11-13 | 180869-FC STAMPED | FC | 0 | A | MECHANICAL | HRSG | 2018-11-09 | 2018-06-01
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122107 | 224 | [HRSG(For Block 2)]_HRSG_SPEC. & DRAWING FOR RECIRCULATION PUMP | FA | 2018-01-31 | 2018-04-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-01 | 2018-06-01
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122107 | 225 | [HRSG(For Block 3, 4)]_HRSG_SPEC. & DRAWING FOR RECIRCULATION PUMP | FA | 2018-01-31 | 2018-04-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-01 | 2019-01-24
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122114 | 226 | [HRSG(for Block 2)]_HRSG_SPEC. & DRAWING FOR SUMP PUMP | FA | 2018-10-30 | 2018-11-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-10-29 | 2019-01-24
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122114 | 227 | [HRSG(for Block 3, 4)]_HRSG_SPEC. & DRAWING FOR SUMP PUMP | FA | 2018-10-30 | 2018-11-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-10-29 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-YK08-P2LB-122115 | 228 | [HRSG(for Block 2)]_HRSG_NAMEPLATE DRAWING | FI | 2018-11-07 | 2019-03-07 | 2019-05-24 | 2019-05-27 | MRT-DS-REC-TT-180857-FC | FC | 0 | 2019-05-29 | 180857-FC STAMPED | FC | 0 | A | MECHANICAL | HRSG | 2018-11-05 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-YK08-P3LB-122115 | 229 | [HRSG(for Block 3, 4)]_HRSG_ NAMEPLATE DRAWING | FI | 2018-11-07 | 2019-03-07 | 2019-05-24 | 2019-05-27 | MRT-DS-REC-TT-180857-FC | FC | 0 | 2019-05-29 | 180857-FC STAMPED | FC | 0 | A | MECHANICAL | HRSG | 2018-11-05 | 2019-03-28
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P2LB-122122 | 230 | [HRSG(for Block 2)]_HRSG_ELEVATOR DOCUMENT PACKAGE | FA | 2019-03-11 | 2019-06-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2019-03-08 | 2019-03-28
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P3LB-122122 | 231 | [HRSG(for Block 3, 4)]_HRSG_ELEVATOR DOCUMENT PACKAGE | FA | 2019-03-11 | 2019-06-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | MECHANICAL | HRSG | 2019-03-08 | 2019-05-08
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P2LB-122123 | 232 | [HRSG(for Block 2)]_HRSG_HOIST DOCUMENT PACKAGE | FI | 2019-04-03 | 2019-06-03 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2019-04-15 | 2019-05-08
DHI | 플랜트기술 | 오슬기 | MRT-DP00-P3LB-122123 | 233 | [HRSG(for Block 3, 4)]_HRSG_HOIST DOCUMENT PACKAGE | FI | 2019-04-03 | 2019-06-03 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | MECHANICAL | HRSG | 2019-04-15 | #VALUE!
DHI | 플랜트기술 | 오슬기 | MRT-YT02-P2LB-122104 | 234 | [HRSG(For Block 2)]_HRSG_PIPING MATERIAL CLASSIFICATION | FI | 2018-02-01 |  | 2018-11-16 | 2018-11-16 | MRT-DS-REC-TT-180885 | FI | 1 | 2018-12-20 | 1148/T/MRT/REC/XII/2018 | FI | 1 | I | MECHANICAL | HRSG | 2018-02-01 | #VALUE!
DHI | 플랜트기술 | 오슬기 | MRT-YT02-P3LB-122104 | 235 | [HRSG(for Block 3, 4)]_HRSG_PIPING MATERIAL CLASSIFICATION | FI | 2018-02-01 |  | 2018-11-16 | 2018-11-16 | MRT-DS-REC-TT-180885 | FI | 1 | 2018-12-20 | 1148/T/MRT/REC/XII/2018 | FI | 1 | I | MECHANICAL | HRSG | 2018-02-01 | 2018-07-27
DHI | 플랜트기술 | 오슬기 | MRT-XG01-P2LB-122021 | 236 | [HRSG(For Block 2)]_HRSG_PIPING ARRANGEMENT | FI | 2018-06-01 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-06-14 | 2018-08-06
DHI | 플랜트기술 | 오슬기 | MRT-XG01-P3LB-122021 | 237 | [HRSG(For Block 3, 4)]_HRSG_PIPING ARRANGEMENT | FI | 2018-06-01 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-07-18 | 2018-07-27
DHI | 플랜트기술 | 오슬기 | MRT-YK01-P2LB-122074 | 238 | [HRSG(For Block 2)]_HRSG_MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | FI | 2018-06-01 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2018-07-27
DHI | 플랜트기술 | 오슬기 | MRT-YK01-P3LB-122074 | 239 | [HRSG(For Block 3, 4)]_HRSG_MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | FI | 2018-06-01 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2018-07-09
DHI | 플랜트기술 | 오슬기 | MRT-XL00-P2LB-122030 | 240 | [HRSG(For Block 2)]_HRSG_LINE LIST | FA | 2018-01-01 | 2018-04-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2017-12-21 | 2018-07-09
DHI | 플랜트기술 | 오슬기 | MRT-XL00-P3LB-122030 | 241 | [HRSG(For Block 3, 4)]_HRSG_LINE LIST | FA | 2018-01-01 | 2018-04-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-08 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-XN00-P2LB-122032 | 242 | [HRSG(For Block 2)]_HRSG_VALVE LIST | FI | 2018-01-01 | 2018-05-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2017-12-21 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-XN00-P3LB-122032 | 243 | [HRSG(For Block 3, 4)]_HRSG_VALVE LIST | FI | 2018-01-01 | 2018-05-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-08 | 2018-07-27
DHI | 플랜트기술 | 오슬기 | MRT-XJ00-P2LB-122027 | 244 | [HRSG(For Block 2)]_HRSG_LARGE BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | FI | 2018-06-01 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-03-21 | 2018-07-27
DHI | 플랜트기술 | 오슬기 | MRT-XJ00-P3LB-122027 | 245 | [HRSG(For Block 3, 4)]_HRSG_LARGE BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | FI | 2018-06-01 | 2018-08-30 | 2024-03-12 | 2024-03-12 | MRT-DS-REC-TT-240007 | AB | Z1 | 2024-03-20 | MTW-AS-C-LT-24.5077.0 | AB | Z1 | A | MECHANICAL | HRSG | 2018-03-21 | 2018-07-16
DHI | 플랜트기술 | 오슬기 | MRT-XJ00-P2LB-122028 | 246 | [HRSG(For Block 2)]_HRSG_SMALL BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | FI | 2018-02-01 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-08 | 2018-07-16
DHI | 플랜트기술 | 오슬기 | MRT-XJ00-P3LB-122028 | 247 | [HRSG(For Block 3, 4)]_HRSG_SMALL BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | FI | 2018-02-01 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-08 | 2018-07-27
DHI | 플랜트기술 | 오슬기 | MRT-XH01-P2LB-122026 | 248 | [HRSG(For Block 2)]_HRSG_PIPE SUPPORT DRAWINGS | FI | 2018-06-30 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-06-27 | 2018-07-27
DHI | 플랜트기술 | 오슬기 | MRT-XH01-P3LB-122026 | 249 | [HRSG(For Block 3, 4)]_HRSG_PIPE SUPPORT DRAWINGS | FI | 2018-06-30 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-06-27 | 2018-07-27
DHI | 플랜트기술 | 오슬기 | MRT-XH01-P2LB-122025 | 250 | [HRSG(For Block 2)]_HRSG_TYPICAL SUPPORT DRAWING FOR SMALL BORE PIPING | FI | 2018-06-30 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-06-27 | 2018-07-27
DHI | 플랜트기술 | 오슬기 | MRT-XH01-P3LB-122025 | 251 | [HRSG(For Block 3, 4)]_HRSG_TYPICAL SUPPORT DRAWING FOR SMALL BORE PIPING | FI | 2018-06-30 | 2018-08-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-06-27 | 2018-10-24
DHI | 플랜트기술 | 오슬기 | MRT-XH01-P2LB-122112 | 252 | [HRSG(for Block 2)]_HRSG_PIPE SUPPORT DRAWINGS FOR INSTALLATION | FI | 2018-10-19 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-10-19 | 2018-10-24
DHI | 플랜트기술 | 오슬기 | MRT-XH01-P3LB-122112 | 253 | [HRSG(for Block 3, 4)]_HRSG_PIPE SUPPORT DRAWINGS FOR INSTALLATION | FI | 2018-10-19 | 2018-11-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-10-19 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-YQ03-P2LB-122086 | 254 | [HRSG(For Block 2)]_HRSG_DATA & BOM OF INSULATION | FI | 2018-03-01 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-YQ03-P3LB-122086 | 255 | [HRSG(For Block 3, 4)]_HRSG_DATA & BOM OF INSULATION | FI | 2018-03-01 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | MECHANICAL | HRSG | 2018-02-28 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P2LB-122100 | 256 | [HRSG(For Block 2)]_HRSG_ELECTRICAL SINGLE LINE DIAGRAMS | FI | 2018-02-01 | 2018-06-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-02-01 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P3LB-122100 | 257 | [HRSG(for Block 3, 4)]_HRSG_ELECTRICAL SINGLE LINE DIAGRAMS | FI | 2018-02-01 | 2018-06-01 | 2024-11-14 | 2024-11-14 | MRT-DS-REC-TT-240028 | AB | Z0 | 2024-11-21 | MTW-AS-C-LT-24.5978.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-02-01 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122109 | 258 | [HRSG(for Block 2)]_HRSG_ELECTRICAL USER LOCATION | FI | 2018-04-06 | 2018-08-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-04-02 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122109 | 259 | [HRSG(for Block 3, 4)]_HRSG_ELECTRICAL USER LOCATION | FI | 2018-04-06 | 2018-08-04 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-04-02 | 2018-09-03
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122056 | 260 | [HRSG(For Block 2)]_HRSG_POWER DISTRIBUTION PANEL DRAWINGS | FA | 2018-05-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-02-28 | 2018-09-03
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122056 | 261 | [HRSG(For Block 3, 4)]_HRSG_POWER DISTRIBUTION PANEL DRAWINGS | FA | 2018-05-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-02-28 | 2018-07-03
DHI | 플랜트기술 | 오슬기 | MRT-YQ01-P2LB-122085 | 262 | [HRSG(For Block 2)]_HRSG_WIRING & SCHEMATIC DIAGRAM | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-03-27 | 2018-07-03
DHI | 플랜트기술 | 오슬기 | MRT-YQ01-P3LB-122085 | 263 | [HRSG(For Block 3, 4)]_HRSG_WIRING & SCHEMATIC DIAGRAM | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-03-27 | 2018-11-22
DHI | 플랜트기술 | 오슬기 | MRT-YE00-P2LB-122116 | 264 | [HRSG(for Block 2)]_HRSG_LIGHTING SYSTEM | FA | 2018-11-07 | 2018-12-21 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-11-05 | 2018-11-22
DHI | 플랜트기술 | 오슬기 | MRT-YE00-P3LB-122116 | 265 | [HRSG(for Block 3, 4)]_HRSG_LIGHTING SYSTEM | FA | 2018-11-07 | 2018-12-21 | 2024-11-14 | 2024-11-14 | MRT-DS-REC-TT-240028 | AB | Z0 | 2024-11-21 | MTW-AS-C-LT-24.5978.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-11-05 | 2018-10-04
DHI | 플랜트기술 | 오슬기 | MRT-YS00-P2LB-122092 | 266 | [HRSG(For Block 2)]_HRSG_AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | FA | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-03-27 | 2018-10-04
DHI | 플랜트기술 | 오슬기 | MRT-YS00-P3LB-122092 | 267 | [HRSG(For Block 3, 4)]_HRSG_AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | FA | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-03-27 | 2018-07-23
DHI | 플랜트기술 | 오슬기 | MRT-XW01-P2LB-122043 | 268 | [HRSG(For Block 2)]_HRSG_TECHNICAL SPECIFICATION FOR CABLING ACCESSORIES | FA | 2018-05-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-06-14 | 2018-07-23
DHI | 플랜트기술 | 오슬기 | MRT-XW01-P3LB-122043 | 269 | [HRSG(For Block 3, 4)]_HRSG_TECHNICAL SPECIFICATION FOR CABLING ACCESSORIES | FA | 2018-06-01 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5520.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-06-14 | 2018-08-06
DHI | 플랜트기술 | 오슬기 | MRT-YL16-P2LB-122078 | 270 | [HRSG(For Block 2)]_HRSG_CABLE SCHEDULE | FA | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-04-02 | 2018-08-06
DHI | 플랜트기술 | 오슬기 | MRT-YL16-P3LB-122078 | 271 | [HRSG(For Block 3, 4)]_HRSG_CABLE SCHEDULE | FA | 2018-04-01 | 2018-06-30 | 2024-11-14 | 2024-11-14 | MRT-DS-REC-TT-240028 | AB | Z0 | 2024-11-21 | MTW-AS-C-LT-24.5978.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-04-02 | 2018-09-10
DHI | 플랜트기술 | 오슬기 | MRT-YD02-P2LB-122063 | 272 | [HRSG(For Block 2)]_HRSG_CONDUIT LAYOUT DRAWING | FI | 2018-06-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-07-28 | 2018-09-10
DHI | 플랜트기술 | 오슬기 | MRT-YD02-P3LB-122063 | 273 | [HRSG(For Block 3, 4)]_HRSG_CONDUIT LAYOUT DRAWING | FI | 2018-06-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-12-06 | MTW-AS-C-LT-23.4676.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-07-28 | 2018-07-26
DHI | 플랜트기술 | 오슬기 | MRT-YD02-P2LB-122064 | 274 | [HRSG(For Block 2)]_HRSG_CABLE TRAY & RACEWAY LAYOUT DIAGRAM | FI | 2018-06-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-06-01 | 2018-10-24
DHI | 플랜트기술 | 오슬기 | MRT-YD02-P3LB-122064 | 275 | [HRSG(For Block 3, 4)]_HRSG_CABLE TRAY & RACEWAY LAYOUT DIAGRAM | FI | 2018-06-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-12-06 | MTW-AS-C-LT-23.4676.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-07-18 | 2018-07-26
DHI | 플랜트기술 | 오슬기 | MRT-YD02-P2LB-122065 | 276 | [HRSG(For Block 2)]_HRSG_GROUNDING AND LIGHTNING PLAN DIAGRAMS | FI | 2018-05-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-06-01 | 2018-08-06
DHI | 플랜트기술 | 오슬기 | MRT-YD02-P3LB-122065 | 277 | [HRSG(For Block 3, 4)]_HRSG_GROUNDING AND LIGHTNING PLAN DIAGRAMS | FI | 2018-06-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-08-09 | MTW-AS-C-LT-24.5626.0 | AB | Z0 | A | ELECTRICAL | HRSG | 2018-07-18 | #VALUE!
DHI | 플랜트기술 | 오슬기 | MRT-XS01-P2LB-122111 | 278 | [HRSG(For Block 2, 3&4)]_HRSG_CONTROL AND AUTOMATION DESCRIPTION | FI | 2018-10-12 |  | 2019-01-24 | 2019-01-24 | MRT-DS-REC-TT-190018 | FI | 1 | 2019-03-29 | 187/T/MRT/REC/III/2019 | FI | 1 | I | I&C | HRSG | 2018-10-12 | 2018-06-14
DHI | 플랜트기술 | 오슬기 | MRT-VN02-P2LB-122089 | 279 | [HRSG(For Block 2)]_HRSG_MOV DATASHEET & DRAWINGS | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2018-02-28 | 2018-06-14
DHI | 플랜트기술 | 오슬기 | MRT-VN02-P3LB-122089 | 280 | [HRSG(For Block 3, 4)]_HRSG_MOV DATASHEET & DRAWINGS | FA | 2018-03-01 | 2018-05-30 | 2024-10-17 | 2024-10-17 | MRT-DS-REC-TT-240015 | AB | Z2 | 2024-12-05 | MTW-AS-C-LT-24.6039.0 | AB | Z2 | A | I&C | HRSG | 2018-02-28 | 2018-07-13
DHI | 플랜트기술 | 오슬기 | MRT-VN02-P2LB-122090 | 281 | [HRSG(For Block 2)]_HRSG_CV DATASHEET & DRAWINGS | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2018-02-28 | 2018-07-13
DHI | 플랜트기술 | 오슬기 | MRT-VN02-P3LB-122090 | 282 | [HRSG(For Block 3, 4)]_HRSG_CV DATASHEET & DRAWINGS | FA | 2018-03-01 | 2018-05-30 | 2024-02-23 | 2024-02-23 | MRT-DS-REC-TT-240004 | AB | Z2 | 2024-04-02 | MTW-AS-C-LT-24.5134.0 | AB | Z2 | A | I&C | HRSG | 2018-02-28 | 2018-07-23
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P2LB-122093 | 283 | [HRSG(For Block 2)]_HRSG_CEMS DATASHEET & DRAWINGS | FA | 2018-05-10 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2018-06-14 | 2018-07-23
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P3LB-122093 | 284 | [HRSG(For Block 3, 4)]_HRSG_CEMS DATASHEET & DRAWINGS | FA | 2018-06-20 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2025-02-20 | MTW-AS-C-LT-25.6214.0 | AB | Z0 | A | I&C | HRSG | 2018-06-27 | 2018-07-13
DHI | 플랜트기술 | 오슬기 | MRT-YF00-P2LB-122066 | 285 | [HRSG(For Block 2)]_HRSG_CONTROL AND AUTOMATION DIAGRAM | FA | 2018-02-01 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2018-02-01 | 2019-02-25
DHI | 플랜트기술 | 오슬기 | MRT-YF00-P3LB-122066 | 286 | [HRSG(For Block 3, 4)]_HRSG_CONTROL AND AUTOMATION DIAGRAM | FA | 2018-09-20 | 2018-11-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2025-02-20 | MTW-AS-C-LT-25.6214.0 | AB | Z0 | A | I&C | HRSG | 2018-12-21 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-YL00-P2LB-122075 | 287 | [HRSG(For Block 2, 3&4)]_HRSG_INSTRUMENT LIST | FI | 2018-01-01 | 2018-05-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2017-12-21 | 2018-07-03
DHI | 플랜트기술 | 오슬기 | MRT-YT02-P2LB-122094 | 288 | [HRSG(For Block 2)]_HRSG_LOCAL INSTRUMENT DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2018-03-27 | 2018-07-03
DHI | 플랜트기술 | 오슬기 | MRT-YT02-P3LB-122094 | 289 | [HRSG(For Block 3, 4)]_HRSG_LOCAL INSTRUMENT DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2024-03-05 | 2024-03-05 | MRT-DS-REC-TT-240006 | AB | Z1 | 2024-03-28 | MTW-AS-C-LT-24.5129.0 | AB | Z1 | A | I&C | HRSG | 2018-03-27 | 2018-07-03
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P2LB-122095 | 290 | [HRSG(For Block 2)]_HRSG_TRANSMITTER DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2018-03-27 | 2018-07-03
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P3LB-122095 | 291 | [HRSG(For Block 3, 4)]_HRSG_TRANSMITTER DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6018.0 | AB | Z0 | A | I&C | HRSG | 2018-03-27 | 2018-07-03
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P2LB-122096 | 292 | [HRSG(For Block 2)]_HRSG_DRUM LEVEL GAUGE DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2018-03-27 | 2018-07-03
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P3LB-122096 | 293 | [HRSG(For Block 3, 4)]_HRSG_DRUM LEVEL GAUGE DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2024-03-05 | 2024-03-05 | MRT-DS-REC-TT-240006 | AB | Z1 | 2024-03-28 | MTW-AS-C-LT-24.5129.0 | AB | Z1 | A | I&C | HRSG | 2018-03-27 | 2018-07-03
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P2LB-122097 | 294 | [HRSG(For Block 2)]_HRSG_FLOW ELEMENT DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2018-03-27 | 2018-07-03
DHI | 플랜트기술 | 오슬기 | MRT-YT01-P3LB-122097 | 295 | [HRSG(For Block 3, 4)]_HRSG_FLOW ELEMENT DATASHEET & DRAWINGS | FI | 2018-04-01 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | I&C | HRSG | 2018-03-27 | 2018-07-05
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P2LB-122108 | 296 | [HRSG(For Block 2)]_HRSG_I&C LOCAL PANEL DRAWINGS | FA | 2018-03-05 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2018-02-28 | 2018-07-05
DHI | 플랜트기술 | 오슬기 | MRT-YD00-P3LB-122108 | 297 | [HRSG(For Block 3, 4)]_HRSG_I&C LOCAL PANEL DRAWINGS | FA | 2018-03-05 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-02-27 | MTW-AS-C-LT-24.4968.0 | AB | Z0 | A | I&C | HRSG | 2018-02-28 | 2018-07-23
DHI | 플랜트기술 | 오슬기 | MRT-YM03-P2LB-122069 | 298 | [HRSG(For Block 2)]_HRSG_INSTRUMENT LOCATION | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2018-02-28 | 2018-07-23
DHI | 플랜트기술 | 오슬기 | MRT-YM03-P3LB-122069 | 299 | [HRSG(For Block 3, 4)]_HRSG_INSTRUMENT LOCATION | FA | 2018-03-01 | 2018-05-30 | 2024-03-05 | 2024-03-05 | MRT-DS-REC-TT-240006 | AB | Z1 | 2024-03-28 | MTW-AS-C-LT-24.5129.0 | AB | Z1 | A | I&C | HRSG | 2018-02-28 | 2018-03-21
DHI | 플랜트기술 | 오슬기 | MRT-YK00-P2LB-122072 | 300 | [HRSG(For Block 2)]_HRSG_INSTRUMENT INSTALLATION DETAIL DRAWINGS | FA | 2018-03-01 | 2018-05-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2018-02-28 | 2018-03-21
DHI | 플랜트기술 | 오슬기 | MRT-YK00-P3LB-122072 | 301 | [HRSG(For Block 3, 4)]_HRSG_INSTRUMENT INSTALLATION DETAIL DRAWINGS | FA | 2018-03-01 | 2018-05-30 | 2024-02-23 | 2024-02-23 | MRT-DS-REC-TT-240004 | AB | Z2 | 2024-04-02 | MTW-AS-C-LT-24.5134.0 | AB | Z2 | A | I&C | HRSG | 2018-02-28 | 2018-10-24
DHI | 플랜트기술 | 오슬기 | MRT-YK00-P2LB-122076 | 302 | [HRSG(for Block 2)]_HRSG_HOOK UP DRAWING | FI | 2018-05-30 | 2018-10-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | I&C | HRSG | 2018-07-13 | 2018-10-24
DHI | 플랜트기술 | 오슬기 | MRT-YK00-P3LB-122076 | 303 | [HRSG(for Block 3, 4)]_HRSG_HOOK UP DRAWING | FI | 2018-06-30 | 2018-11-23 | 2024-12-09 | 2024-12-09 | MRT-DS-REC-TT-240043 | AB | Z3 | 2024-12-16 | MTW-AS-C-LT-24.6072.0 | AB | Z3 | A | I&C | HRSG | 2018-07-13 | 2018-03-28
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P2LB-122021 | 304 | [HRSG(For Block 2, 3&4)]_HRSG_MAIN FRAMES DESIGN REPORT | FA | 2017-12-04 | 2018-04-30 | 2018-10-01 | 2018-11-23 | MRT-DS-REC-TT-180774-FC | FC | 3 | 2018-12-03 | 180774-FC STAMPED | FC | 3 | A | CIVIL | HRSG | 2017-12-07 | 2018-03-23
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P2LB-122016 | 305 | [HRSG(For Block 2)]_HRSG_COLUMN LOCATION FOR STEEL STRUCTURE AND STACK (WITH PLAN VIEW) | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | CIVIL | HRSG | 2017-11-17 | 2018-03-23
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P3LB-122016 | 306 | [HRSG(for Block 3, 4)]_HRSG_COLUMN LOCATION FOR STEEL STRUCTURE AND STACK (WITH PLAN VIEW) | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-03-20 | MTW-AS-C-LT-24.5076.0 | AB | Z0 | A | CIVIL | HRSG | 2018-01-19 | 2018-02-21
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P2LB-122017 | 307 | [HRSG(For Block 2)]_HRSG_FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | FA | 2017-11-01 | 2018-01-30 | 2018-07-27 | 2018-08-20 | MRT-DS-REC-TT-180257-FC | FC | 3 | 2018-09-03 | 180257-FC STAMPED | FC | 3 | A | CIVIL | HRSG | 2017-11-09 | 2018-02-21
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P3LB-122017 | 308 | [HRSG(for Block 3, 4)]_HRSG_FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | FA | 2017-11-01 | 2018-01-30 | 2018-07-27 | 2018-08-20 | MRT-DS-REC-TT-180257-FC | FC | 2 | 2018-09-03 | 180257-FC STAMPED | FC | 2 | A | CIVIL | HRSG | 2018-01-24 | 2018-03-21
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P2LB-122018 | 309 | [HRSG(For Block 2)]_HRSG_BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2023-07-14 | MTW-AS-C-LT-23.4184.0 | AB | Z0 | A | CIVIL | HRSG | 2017-11-17 | 2018-03-21
DHI | 플랜트기술 | 오슬기 | MRT-XB02-P3LB-122018 | 310 | [HRSG(For Block 3, 4)]_HRSG_BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | FA | 2017-11-01 | 2018-01-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | 2024-03-20 | MTW-AS-C-LT-24.5076.0 | AB | Z0 | A | CIVIL | HRSG | 2018-01-08 | 2018-11-28
DHI | 플랜트기술 | 오슬기 | MRT-UC02-P2LB-122121 | 311 | [HRSG(for Block 2, 3&4)]_HRSG_ERECTION MANUAL FOR INSTALLATION | FI | 2018-11-27 | 2019-01-30 | 2019-08-20 | 2019-08-20 | MRT-DS-REC-TT-190180-FC | FC | 1 | 2019-08-20 | 190180-FC STAMPED | FC | 1 | A | SUPPORT | HRSG | 2018-11-27 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-YR01-P2LB-122082 | 312 | [HRSG(For Block 2, 3&4)]_HRSG_CHEMICAL CLEANING PROCEDURE | FI | 2018-07-06 | 2018-11-03 | 2019-05-24 | 2019-06-14 | MRT-DS-REC-TT-180595-FC | FC | 0 | 2019-06-14 | 180595-FC STAMPED | FC | 0 | A | SUPPORT | HRSG | 2018-07-12 | 2019-05-24
DHI | 플랜트기술 | 오슬기 | MRT-YL08-P2LB-122083 | 313 | [HRSG(For Block 2, 3&4)]_HRSG_CONSERVATION PROCEDURE | FI | 2018-06-01 | 2018-09-29 | 2019-05-24 | 2019-06-17 | MRT-DS-REC-TT-180487-FC | FC | 0 | 2019-06-17 | 180487-FC STAMPED | FC | 0 | A | SUPPORT | HRSG | 2018-06-14 | 2019-02-22
DHI | 플랜트기술 | 오슬기 | MRT-DN05-P2LB-122119 | 314 | [HRSG(for Block 2, 3&4)]_HRSG_COMMISSIONING MANUAL | FA | 2018-11-30 | 2019-02-28 | 2022-12-12 | 2022-12-12 | MRT-DS-REC-TT-220026 | FC | 0 | 2023-01-11 | DEEMED APPROVAL | FC | 0 | A | SUPPORT | HRSG | 2018-11-27 | 2018-07-27
DHI | 플랜트기술 | 오슬기 | MRT-DN05-P2LB-122110 | 315 | [HRSG(For Block 2, 3&4)]_COMMISSIONING PROCEDURE FOR DIVERTER DAMPER, GUILLOTTINE | FA | 2018-07-09 | 2018-10-09 | 2018-07-27 | 2018-09-24 | MRT-DS-REC-TT-180561-FC | FC | 0 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 0 | A | SUPPORT | HRSG | 2018-07-03 | 2019-02-22
DHI | 플랜트기술 | 오슬기 | MRT-CQ02-P2LB-122118 | 316 | [HRSG(for Block 2, 3&4)]_HRSG_OPERATION & MAINTENANCE MANUAL | FI | 2018-11-30 | 2019-02-28 | 2019-08-23 | 2019-08-24 | MRT-DS-REC-TT-190185-FC | FC | 1 | 2019-08-26 | 190185-FC STAMPED | FC | 1 | A | SUPPORT | HRSG | 2018-11-27 | 2018-04-09
DHI | 플랜트기술 | 류두현 | MRT-XG02-P2SCA-127502 | 317 | [Air compressor (DHI for Block 2)]_P&I DIAGRAM FOR AIR COMPRESSOR PACKAGE | FA | 2018-01-21 | 2018-04-21 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | MECHANICAL | AIR COMPRESSOR | 2018-02-01 | 2018-04-09
DHI | 플랜트기술 | 류두현 | MRT-XG02-P3SCA-127502 | 318 | [Air compressor (DHI for Block 3, 4)]_P&I DIAGRAM FOR AIR COMPRESSOR PACKAGE | FA | 2018-01-21 | 2018-06-20 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2018-10-23 | 180711-FC STAMPED | FC | 2 | A | MECHANICAL | AIR COMPRESSOR | 2018-02-01 | 2018-07-23
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LCB-127501 | 319 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSORS PACKAGE | FA | 2018-03-21 | 2018-06-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | MECHANICAL | AIR COMPRESSOR | 2018-03-15 | 2018-07-23
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LCB-127501 | 320 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_GENERAL ARRANGEMENT DRAWING FOR AIR COMPRESSORS PACKAGE | FA | 2018-03-21 | 2018-08-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2018-10-22 | 180638-FC STAMPED | FC | 2 | A | MECHANICAL | AIR COMPRESSOR | 2018-03-15 | 2018-06-11
DHI | 플랜트기술 | 류두현 | MRT-XW01-P2SCA-127503 | 321 | [Air compressor (DHI for Block 2)]_EQUIPMENT SPECIFICATION FOR COMPRESSED AIR SYSTEM | FA | 2018-01-21 | 2018-04-21 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | MECHANICAL | AIR COMPRESSOR | 2018-02-01 | 2018-06-11
DHI | 플랜트기술 | 류두현 | MRT-XW01-P3SCA-127503 | 322 | [Air compressor (DHI for Block 3, 4)]_EQUIPMENT SPECIFICATION FOR COMPRESSED AIR SYSTEM | FA | 2018-01-21 | 2018-06-20 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2018-10-10 | 180474-FC STAMPED | FC | 2 | A | MECHANICAL | AIR COMPRESSOR | 2018-02-01 | 2018-07-27
DHI | 플랜트기술 | 류두현 | MRT-XF00-P2SCA-127524 | 323 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_NAME PLATE DRAWING | FI | 2018-05-21 | 2018-08-19 | 2018-08-29 | 2018-10-02 | MRT-DS-REC-TT-180710-FC | FC | 1 | 2018-10-22 | 180710-FC STAMPED | FC | 1 | A | MECHANICAL | AIR COMPRESSOR | 2018-06-04 | 2018-07-27
DHI | 플랜트기술 | 류두현 | MRT-XF00-P3SCA-127524 | 324 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_NAME PLATE DRAWING | FI | 2018-05-21 | 2018-10-18 | 2018-08-29 | 2018-10-02 | MRT-DS-REC-TT-180710-FC | FC | 1 | 2018-10-22 | 180710-FC STAMPED | FC | 1 | A | MECHANICAL | AIR COMPRESSOR | 2018-06-04 | 2018-03-22
DHI | 플랜트기술 | 류두현 | MRT-YF02-P2SCA-127514 | 325 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_CONTROL DESCRIPTION (PHILOSOPHY) | FA | 2018-02-20 | 2018-05-21 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180209-FC | FC | 1 | 2018-08-13 | 180209-FC STAMPED | FC | 1 | A | MECHANICAL | AIR COMPRESSOR | 2018-02-27 | 2018-03-22
DHI | 플랜트기술 | 류두현 | MRT-YF02-P3SCA-127514 | 326 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_CONTROL DESCRIPTION (PHILOSOPHY) | FA | 2018-02-20 | 2018-07-20 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180209-FC | FC | 1 | 2018-08-13 | 180209-FC STAMPED | FC | 1 | A | MECHANICAL | AIR COMPRESSOR | 2018-02-27 | 2018-05-03
DHI | 플랜트기술 | 류두현 | MRT-XW01-P2SCA-127504 | 327 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_MOTOR SPECIFICATION | FA | 2018-03-21 | 2018-05-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR | 2018-04-09 | 2018-05-03
DHI | 플랜트기술 | 류두현 | MRT-XW01-P3SCA-127504 | 328 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_MOTOR SPECIFICATION | FA | 2018-03-21 | 2018-05-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2018-11-29 | 180699-FC STAMPED | FC | 2 | A | ELECTRICAL | AIR COMPRESSOR | 2018-04-09 | 2018-07-23
DHI | 플랜트기술 | 류두현 | MRT-YU02-P2SCA-127510 | 329 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_SINGLE LINE DIAGRAM | FA | 2018-03-21 | 2018-06-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR | 2018-03-28 | 2018-07-23
DHI | 플랜트기술 | 류두현 | MRT-YU02-P3SCA-127510 | 330 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_SINGLE LINE DIAGRAM | FA | 2018-03-21 | 2018-08-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5526.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR | 2018-03-28 | 2018-07-23
DHI | 플랜트기술 | 류두현 | MRT-YS01-P2SCA-127511 | 331 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_SCHEMATIC DIAGRAM FOR AIR COMPRESSOR PACKAGE | FI | 2018-04-21 | 2018-07-20 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR | 2018-05-03 | 2018-07-23
DHI | 플랜트기술 | 류두현 | MRT-YS01-P3SCA-127511 | 332 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_SCHEMATIC DIAGRAM FOR AIR COMPRESSOR PACKAGE | FI | 2018-04-21 | 2018-09-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5526.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR | 2018-05-03 | 2018-10-29
DHI | 플랜트기술 | 류두현 | MRT-YV02-P2SCA-127532 | 333 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_INTERCONNECTION WIRING DIAGRAM | FI | 2018-09-19 | 2018-11-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR | 2018-10-04 | 2018-10-29
DHI | 플랜트기술 | 류두현 | MRT-YV02-P3SCA-127532 | 334 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_INTERCONNECTION WIRING DIAGRAM | FI | 2018-09-19 | 2018-11-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5526.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR | 2018-10-04 | 2018-07-06
DHI | 플랜트기술 | 류두현 | MRT-YD16-P2SCA-127531 | 335 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_EMBEDDED CONDUIT DRAWING | FA | 2018-04-13 | 2018-06-13 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR | 2018-04-17 | 2018-07-06
DHI | 플랜트기술 | 류두현 | MRT-YD16-P3SCA-127531 | 336 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_EMBEDDED CONDUIT DRAWING | FA | 2018-04-13 | 2018-06-13 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5526.0 | AB | Z0 | A | ELECTRICAL | AIR COMPRESSOR | 2018-04-17 | 2018-07-27
DHI | 플랜트기술 | 류두현 | MRT-YR05-P2SCA-127523 | 337 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_PLC PANEL & EQUIPMENT LCP DRAWING | FA | 2018-05-21 | 2018-08-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | I&C | AIR COMPRESSOR | 2018-05-25 | 2018-07-27
DHI | 플랜트기술 | 류두현 | MRT-YR05-P3SCA-127523 | 338 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_PLC PANEL & EQUIPMENT LCP DRAWING | FA | 2018-05-21 | 2018-10-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5825.0 | AB | Z0 | A | I&C | AIR COMPRESSOR | 2018-05-25 | 2018-08-06
DHI | 플랜트기술 | 류두현 | MRT-YD05-P2SCA-127515 | 339 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_PLC HMI GRAPHICS | FA | 2018-05-11 | 2018-07-20 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | I&C | AIR COMPRESSOR | 2018-05-15 | 2018-08-06
DHI | 플랜트기술 | 류두현 | MRT-YD05-P3SCA-127515 | 340 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_PLC HMI GRAPHICS | FA | 2018-05-11 | 2018-09-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5526.0 | AB | Z0 | A | I&C | AIR COMPRESSOR | 2018-05-15 | 2018-07-23
DHI | 플랜트기술 | 류두현 | MRT-YF00-P2SCA-127518 | 341 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_CONTROL LOGIC & LOOP DIAGRAM | FA | 2018-05-25 | 2018-07-20 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | I&C | AIR COMPRESSOR | 2018-06-11 | 2018-07-23
DHI | 플랜트기술 | 류두현 | MRT-YF00-P3SCA-127518 | 342 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_CONTROL LOGIC & LOOP DIAGRAM | FA | 2018-05-25 | 2018-09-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5825.0 | AB | Z0 | A | I&C | AIR COMPRESSOR | 2018-06-11 | 2018-07-27
DHI | 플랜트기술 | 류두현 | MRT-YL00-P2SCA-127520 | 343 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_INSTRUMENT LIST AND DATA SHEET | FI | 2018-05-21 | 2018-08-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | I&C | AIR COMPRESSOR | 2018-06-08 | 2018-07-27
DHI | 플랜트기술 | 류두현 | MRT-YL00-P3SCA-127520 | 344 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_INSTRUMENT LIST AND DATA SHEET | FI | 2018-05-21 | 2018-10-18 | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240030 | AB | Z1 | 2024-12-04 | MTW-AS-C-LT-24.6031.0 | AB | Z1 | A | I&C | AIR COMPRESSOR | 2018-06-08 | 2018-09-05
DHI | 플랜트기술 | 류두현 | MRT-YK00-P2SCA-127521 | 345 | [Air compressor (DHI for Block 2)]_HOOK UP DRAWING | FI | 2018-05-18 | 2018-07-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | I&C | AIR COMPRESSOR | 2018-05-17 | 2018-09-05
DHI | 플랜트기술 | 류두현 | MRT-YK00-P3SCA-127521 | 346 | [Air compressor (DHI for Block 3, 4)]_HOOK UP DRAWING | FI | 2018-05-18 | 2018-07-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5825.0 | AB | Z0 | A | I&C | AIR COMPRESSOR | 2018-05-17 | 2018-07-11
DHI | 플랜트기술 | 류두현 | MRT-XB00-P2SCA-127509 | 347 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_FOUNDATION DRAWINGS | FI | 2018-04-07 | 2018-07-06 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3689.0 | AB | Z0 | A | CIVIL | AIR COMPRESSOR | 2018-03-15 | 2018-07-11
DHI | 플랜트기술 | 류두현 | MRT-XB00-P3SCA-127509 | 348 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_FOUNDATION DRAWINGS | FI | 2018-04-07 | 2018-09-04 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | 2024-03-20 | MTW-AS-C-LT-24.5075.0 | AB | Z0 | A | CIVIL | AIR COMPRESSOR | 2018-03-15 | 2018-08-06
DHI | 플랜트기술 | 류두현 | MRT-CQ02-P2SCA-127529 | 349 | [Air compressor (DHI for Block 2)]_AIR COMPRESSOR_O & M MANUAL | FI | 2018-07-24 | 2018-10-22 | 2018-08-06 | 2018-11-19 | MRT-DS-REC-TT-180632-FC | FC | 0 | 2018-11-28 | 180632-FC STAMPED | FC | 0 | A | SUPPORT | AIR COMPRESSOR | 2018-07-20 | 2018-08-06
DHI | 플랜트기술 | 류두현 | MRT-CQ02-P3SCA-127529 | 350 | [Air compressor (DHI for Block 3, 4)]_AIR COMPRESSOR_O & M MANUAL | FI | 2018-07-24 | 2018-12-21 | 2018-08-06 | 2018-11-19 | MRT-DS-REC-TT-180632-FC | FC | 0 | 2018-11-28 | 180632-FC STAMPED | FC | 0 | A | SUPPORT | AIR COMPRESSOR | 2018-07-20 | 2018-06-01
DHI | 플랜트기술 | 류두현 | MRT-XG02-P2LAC-126003 | 351 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_P&I DIAGRAM | FA | 2018-01-09 | 2018-06-08 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-12-17 | 180906-FC STAMPED | FC | 3 | A | MECHANICAL | BFP HP | 2018-02-12 | 2018-06-01
DHI | 플랜트기술 | 류두현 | MRT-XG02-P3LAC-126003 | 352 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_P&I DIAGRAM | FA | 2018-01-09 | 2018-06-08 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP HP | 2018-02-12 | 2018-04-20
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126001 | 353 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_GENERAL ARRANGEMENT DRAWING | FA | 2018-01-09 | 2018-04-09 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-09-10 | 180327-FC STAMPED | FC | 1 | A | MECHANICAL | BFP HP | 2018-02-12 | 2018-04-20
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126001 | 354 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_GENERAL ARRANGEMENT DRAWING | FA | 2018-01-09 | 2018-06-08 | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240031 | AB | Z1 | 2024-11-22 | MTW-AS-C-LT-24.5983.0 | AB | Z1 | A | MECHANICAL | BFP HP | 2018-02-12 | 2018-04-20
DHI | 플랜트기술 | 류두현 | MRT-YT01-P2LAC-126004 | 355 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | FA | 2018-01-09 | 2018-04-09 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-09-10 | 180327-FC STAMPED | FC | 1 | A | MECHANICAL | BFP HP | 2018-02-12 | 2018-04-20
DHI | 플랜트기술 | 류두현 | MRT-YT01-P3LAC-126004 | 356 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | FA | 2018-01-09 | 2018-06-08 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP HP | 2018-02-12 | 2018-06-22
DHI | 플랜트기술 | 류두현 | MRT-YT01-P2LAC-126005 | 357 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | FA | 2018-02-10 | 2018-05-11 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-10-23 | 180712-FC STAMPED | FC | 4 | A | ELECTRICAL | BFP HP | 2018-03-15 | 2018-06-22
DHI | 플랜트기술 | 류두현 | MRT-YT01-P3LAC-126005 | 358 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | FA | 2018-02-10 | 2018-07-10 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | ELECTRICAL | BFP HP | 2018-03-15 | 2018-05-10
DHI | 플랜트기술 | 류두현 | MRT-YK01-P2LAC-126006 | 359 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_SECTIONAL DRAWING FOR PUMP | FI | 2018-02-10 | 2018-05-11 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-08-29 | 180380-FC STAMPED | FC | 1 | A | MECHANICAL | BFP HP | 2018-03-06 | 2018-05-10
DHI | 플랜트기술 | 류두현 | MRT-YK01-P3LAC-126006 | 360 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_SECTIONAL DRAWING FOR PUMP | FI | 2018-02-10 | 2018-07-10 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP HP | 2018-03-06 | 2018-09-07
DHI | 플랜트기술 | 류두현 | MRT-YT02-P2LAC-126011 | 361 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_LIST AND DATA SHEET FOR INSTRUMENT | FI | 2018-05-27 | 2018-08-25 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-11-29 | 180748-FC STAMPED | FC | 3 | A | I&C | BFP HP | 2018-05-04 | 2018-09-07
DHI | 플랜트기술 | 류두현 | MRT-YT02-P3LAC-126011 | 362 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_LIST AND DATA SHEET FOR INSTRUMENT | FI | 2018-05-27 | 2018-10-24 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5834.0 | AB | Z0 | A | I&C | BFP HP | 2018-05-04 | 2019-05-24
DHI | 플랜트기술 | 류두현 | MRT-XK00-P2LAC-126013 | 363 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_FLEXIBLE COUPLING DRAWING | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2019-05-29 | 180556-FC STAMPED | FC | 0 | A | MECHANICAL | BFP HP | 2018-07-02 | 2019-05-24
DHI | 플랜트기술 | 류두현 | MRT-XK00-P3LAC-126013 | 364 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_FLEXIBLE COUPLING DRAWING | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP HP | 2018-07-02 | 2018-07-24
DHI | 플랜트기술 | 류두현 | MRT-XK00-P2LAC-126014 | 365 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_DATA AND OUTLINE DRAWING FOR LUBE OIL UNIT | FA | 2018-05-31 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-11-05 | 180657-FC STMAPED | FC | 1 | A | MECHANICAL | BFP HP | 2018-05-24 | 2018-07-24
DHI | 플랜트기술 | 류두현 | MRT-XK00-P3LAC-126014 | 366 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_DATA AND OUTLINE DRAWING FOR LUBE OIL UNIT | FA | 2018-05-31 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP HP | 2018-05-24 | 2019-05-24
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126016 | 367 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_MECHANICAL SEAL OUTLINE DRAWING & DATA SHEET | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2019-06-14 | 180422-FC STAMPED | FC | 0 | A | MECHANICAL | BFP HP | 2018-05-25 | 2019-05-24
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126016 | 368 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_MECHANICAL SEAL OUTLINE DRAWING & DATA SHEET | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP HP | 2018-05-25 | 2018-07-27
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126017 | 369 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_SUCTION STRAINER DRAWING & DATA SHEET | FA | 2018-05-31 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-10-31 | 180676-FC STAMPED | FC | 1 | A | MECHANICAL | BFP HP | 2018-05-11 | 2018-07-27
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126017 | 370 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_SUCTION STRAINER DRAWING & DATA SHEET | FA | 2018-05-31 | 2018-08-31 | 2024-04-09 | 2024-04-09 | MRT-DS-REC-TT-240009 | AB | Z1 | 2024-05-20 | MTW-AS-C-LT-24.5267.0 | AB | Z1 | A | MECHANICAL | BFP HP | 2018-05-11 | 2018-05-10
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126007 | 371 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_NAME PLATE DRAWING | FI | 2018-05-27 | 2018-08-25 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180378-FC | FC | 1 | 2018-08-31 | 180378-FC STAMPED | FC | 1 | A | MECHANICAL | BFP HP | 2018-03-14 | 2018-05-10
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126007 | 372 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_NAME PLATE DRAWING | FI | 2018-03-25 | 2018-08-22 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180378-FC | FC | 1 | 2018-08-31 | 180378-FC STAMPED | FC | 1 | A | MECHANICAL | BFP HP | 2018-03-14 | 2018-09-14
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126049 | 373 | [HP Feed Water pump (DHI for Block 2)]_I&C JUNCTION BOX OUTLINE & INTERNAL LAYOUT DRAWING | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2019-02-18 | 190008-FC STAMPED | FC | 3 | A | I&C | BFP HP | 2018-06-18 | 2018-09-14
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126049 | 374 | [HP Feed Water pump (DHI for Block 3,4)]_I&C JUNCTION BOX OUTLINE & INTERNAL LAYOUT DRAWING | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5834.0 | AB | Z0 | A | I&C | BFP HP | 2018-06-18 | 2018-09-14
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126050 | 375 | [HP Feed Water pump (DHI for Block 2)]_CABLE INTERCONNECTION WIRING DIAGRAM | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2019-02-18 | 190008-FC STAMPED | FC | 3 | A | ELECTRICAL | BFP HP | 2018-06-18 | 2018-09-14
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126050 | 376 | [HP Feed Water pump (DHI for Block 3,4)]_CABLE INTERCONNECTION WIRING DIAGRAM | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5527.0 | AB | Z0 | A | ELECTRICAL | BFP HP | 2018-06-18 | 2018-05-15
DHI | 플랜트기술 | 류두현 | MRT-XB00-P2LAC-126022 | 377 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_FOUNDATION DRAWING | FI | 2018-02-28 | 2018-06-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-08-31 | 180396-FC STAMPED | FC | 1 | A | CIVIL | BFP HP | 2018-02-22 | 2018-05-15
DHI | 플랜트기술 | 류두현 | MRT-XB00-P3LAC-126022 | 378 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_FOUNDATION DRAWING | FI | 2018-02-28 | 2018-06-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-20 | MTW-AS-C-LT-24.5073.0 | AB | Z0 | A | CIVIL | BFP HP | 2018-02-22 | 2018-11-28
DHI | 플랜트기술 | 류두현 | MRT-CH01-P2LAC-126037 | 379 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_ERECTION MANUAL | FI | 2018-12-18 | 2019-02-15 | 2018-11-28 | 2018-11-29 | MRT-DS-REC-TT-180907-FC | FC | 0 | 2018-12-06 | 180907-FC STAMPED | FC | 0 | A | SUPPORT | BFP HP | 2018-11-26 | 2018-11-28
DHI | 플랜트기술 | 류두현 | MRT-CH01-P3LAC-126037 | 380 | [HP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_ERECTION MANUAL | FI | 2018-12-18 | 2019-02-15 | 2018-11-28 | 2018-11-29 | MRT-DS-REC-TT-180907-FC | FC | 0 | 2018-12-06 | 180907-FC STAMPED | FC | 0 | A | SUPPORT | BFP HP | 2018-11-26 | 2018-12-19
DHI | 플랜트기술 | 류두현 | MRT-CQ02-P2LAC-126038 | 381 | [HP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_O&M MANUAL | FI | 2019-03-30 | 2019-05-30 | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180911-FC | FC | 0 | 2018-12-22 | 180911-FC STAMPED | FC | 0 | A | SUPPORT | BFP HP | 2018-11-29 | 2018-12-19
DHI | 플랜트기술 | 류두현 | MRT-CQ02-P3LAC-126038 | 382 | [HP Feed Water pump (DHI for Block 3,4)]_FEEDWATER PUMP_O&M MANUAL | FI | 2019-03-30 | 2019-05-30 | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180911-FC | FC | 0 | 2018-12-22 | 180911-FC STAMPED | FC | 0 | A | SUPPORT | BFP HP | 2018-11-29 | 2018-06-01
DHI | 플랜트기술 | 류두현 | MRT-XG02-P2LAC-126053 | 383 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_P&I DIAGRAM | FA | 2018-01-09 | 2018-06-08 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-12-17 | 180906-FC STAMPED | FC | 3 | A | MECHANICAL | BFP LP | 2018-02-12 | 2018-06-01
DHI | 플랜트기술 | 류두현 | MRT-XG02-P3LAC-126053 | 384 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_P&I DIAGRAM | FA | 2018-01-09 | 2018-06-08 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-05-17 | MTW-AS-C-LT-24.5260.0 | AB | Z0 | A | MECHANICAL | BFP LP | 2018-02-12 | 2018-04-20
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126051 | 385 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_GENERAL ARRANGEMENT DRAWING | FA | 2018-01-09 | 2018-04-09 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-09-10 | 180327-FC STAMPED | FC | 1 | A | MECHANICAL | BFP LP | 2018-02-12 | 2018-04-20
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126051 | 386 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_GENERAL ARRANGEMENT DRAWING | FA | 2018-01-09 | 2018-06-08 | 2024-04-09 | 2024-04-09 | MRT-DS-REC-TT-240009 | AB | Z1 | 2024-05-20 | MTW-AS-C-LT-24.5267.0 | AB | Z1 | A | MECHANICAL | BFP LP | 2018-02-12 | 2018-04-20
DHI | 플랜트기술 | 류두현 | MRT-YT01-P2LAC-126054 | 387 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | FA | 2018-01-09 | 2018-04-09 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-09-10 | 180327-FC STAMPED | FC | 1 | A | MECHANICAL | BFP LP | 2018-02-12 | 2018-04-20
DHI | 플랜트기술 | 류두현 | MRT-YT01-P3LAC-126054 | 388 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | FA | 2018-01-09 | 2018-06-08 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP LP | 2018-02-12 | 2018-04-25
DHI | 플랜트기술 | 류두현 | MRT-YT01-P2LAC-126055 | 389 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | FA | 2018-02-10 | 2018-05-11 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-10-23 | 180712-FC STAMPED | FC | 2 | A | ELECTRICAL | BFP LP | 2018-03-15 | 2018-04-25
DHI | 플랜트기술 | 류두현 | MRT-YT01-P3LAC-126055 | 390 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | FA | 2018-02-10 | 2018-07-10 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | ELECTRICAL | BFP LP | 2018-03-15 | 2018-05-10
DHI | 플랜트기술 | 류두현 | MRT-YK01-P2LAC-126056 | 391 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_SECTIONAL DRAWING FOR PUMP | FI | 2018-02-10 | 2018-05-11 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-08-29 | 180380-FC STAMPED | FC | 1 | A | MECHANICAL | BFP LP | 2018-03-06 | 2018-05-10
DHI | 플랜트기술 | 류두현 | MRT-YK01-P3LAC-126056 | 392 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_SECTIONAL DRAWING FOR PUMP | FI | 2018-02-10 | 2018-07-10 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP LP | 2018-03-06 | 2018-05-10
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126057 | 393 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_NAME PLATE DRAWING | FI | 2018-05-27 | 2018-08-25 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180378-FC | FC | 1 | 2018-08-31 | 180378-FC STAMPED | FC | 1 | A | MECHANICAL | BFP LP | 2018-03-14 | 2018-05-10
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126057 | 394 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_NAME PLATE DRAWING | FI | 2018-03-25 | 2018-08-22 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180378-FC | FC | 1 | 2018-08-31 | 180378-FC STAMPED | FC | 1 | A | MECHANICAL | BFP LP | 2018-03-14 | 2018-09-07
DHI | 플랜트기술 | 류두현 | MRT-YT02-P2LAC-126061 | 395 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_LIST AND DATA SHEET FOR INSTRUMENT | FI | 2018-05-27 | 2018-08-25 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-11-29 | 180748-FC STAMPED | FC | 3 | A | I&C | BFP LP | 2018-05-04 | 2018-09-07
DHI | 플랜트기술 | 류두현 | MRT-YT02-P3LAC-126061 | 396 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_LIST AND DATA SHEET FOR INSTRUMENT | FI | 2018-05-27 | 2018-10-24 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5834.0 | AB | Z0 | A | I&C | BFP LP | 2018-05-04 | 2019-05-24
DHI | 플랜트기술 | 류두현 | MRT-XK00-P2LAC-126063 | 397 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_FLEXIBLE COUPLING DRAWING | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2019-05-29 | 180556-FC STAMPED | FC | 0 | A | MECHANICAL | BFP LP | 2018-07-02 | 2019-05-24
DHI | 플랜트기술 | 류두현 | MRT-XK00-P3LAC-126063 | 398 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_FLEXIBLE COUPLING DRAWING | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP LP | 2018-07-02 | 2019-05-24
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126064 | 399 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_MECHANICAL SEAL OUTLINE DRAWING & DATA SHEET | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2019-06-14 | 180422-FC STAMPED | FC | 0 | A | MECHANICAL | BFP LP | 2018-05-25 | 2019-05-24
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126064 | 400 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_MECHANICAL SEAL OUTLINE DRAWING & DATA SHEET | FI | 2018-06-30 | 2018-10-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5086.0 | AB | Z0 | A | MECHANICAL | BFP LP | 2018-05-25 | 2018-07-27
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126065 | 401 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_SUCTION STRAINER DRAWING & DATA SHEET | FA | 2018-05-31 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-10-31 | 180676-FC STAMPED | FC | 1 | A | MECHANICAL | BFP LP | 2018-05-11 | 2018-07-27
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126065 | 402 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_SUCTION STRAINER & DATA SHEET | FA | 2018-05-31 | 2018-08-31 | 2024-11-25 | 2024-11-25 | MRT-DS-REC-TT-240040 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6028.0 | AB | Z1 | A | MECHANICAL | BFP LP | 2018-05-11 | 2018-09-14
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126096 | 403 | [LP Feed Water pump (DHI for Block 2)]_I&C JUNCTION BOX OUTLINE & INTERNAL LAYOUT DRAWING | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-12-08 | 180867-FC STAMPED | FC | 2 | A | I&C | BFP LP | 2018-06-18 | 2018-09-14
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126096 | 404 | [LP Feed Water pump (DHI for Block 3,4)]_I&C JUNCTION BOX OUTLINE & INTERNAL LAYOUT DRAWING | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5834.0 | AB | Z0 | A | I&C | BFP LP | 2018-06-18 | 2018-09-14
DHI | 플랜트기술 | 류두현 | MRT-YD00-P2LAC-126097 | 405 | [LP Feed Water pump (DHI for Block 2)]_CABLE INTERCONNECTION WIRING DAIGRAM | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-12-08 | 180867-FC STAMPED | FC | 2 | A | ELECTRICAL | BFP LP | 2018-06-18 | 2018-09-14
DHI | 플랜트기술 | 류두현 | MRT-YD00-P3LAC-126097 | 406 | [LP Feed Water pump (DHI for Block 3,4)]_CABLE INTERCONNECTION WIRING DAIGRAM | FI | 2018-06-15 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5527.0 | AB | Z0 | A | ELECTRICAL | BFP LP | 2018-06-18 | 2018-05-15
DHI | 플랜트기술 | 류두현 | MRT-XB00-P2LAC-126070 | 407 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_FOUNDATION DRAWING | FI | 2018-02-28 | 2018-06-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2018-08-31 | 180396-FC STAMPED | FC | 1 | A | CIVIL | BFP LP | 2018-02-22 | 2018-05-15
DHI | 플랜트기술 | 류두현 | MRT-XB00-P3LAC-126070 | 408 | [LP Feed Water pump (DHI for Block 3, 4)]_FEEDWATER PUMP_FOUNDATION DRAWING | FI | 2018-02-28 | 2018-06-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | 2024-03-20 | MTW-AS-C-LT-24.5073.0 | AB | Z0 | A | CIVIL | BFP LP | 2018-02-22 | 2018-11-28
DHI | 플랜트기술 | 류두현 | MRT-CH01-P2LAC-126085 | 409 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_ERECTION MANUAL | FI | 2018-12-18 | 2019-02-15 | 2018-11-28 | 2018-11-29 | MRT-DS-REC-TT-180907-FC | FC | 0 | 2018-12-06 | 180907-FC STAMPED | FC | 0 | A | SUPPORT | BFP LP | 2018-11-26 | 2018-11-28
DHI | 플랜트기술 | 류두현 | MRT-CH01-P3LAC-126085 | 410 | [LP Feed Water pump (DHI for Block 3,4)]_FEEDWATER PUMP_ERECTION MANUAL | FI | 2018-12-18 | 2019-02-15 | 2018-11-28 | 2018-11-29 | MRT-DS-REC-TT-180907-FC | FC | 0 | 2018-12-06 | 180907-FC STAMPED | FC | 0 | A | SUPPORT | BFP LP | 2018-11-26 | 2018-12-19
DHI | 플랜트기술 | 류두현 | MRT-CQ02-P2LAC-126086 | 411 | [LP Feed Water pump (DHI for Block 2)]_FEEDWATER PUMP_O&M MANUAL | FI | 2019-03-30 | 2019-05-30 | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180911-FC | FC | 0 | 2018-12-22 | 180911-FC STAMPED | FC | 0 | A | SUPPORT | BFP LP | 2018-11-29 | 2018-12-19
DHI | 플랜트기술 | 류두현 | MRT-CQ02-P3LAC-126086 | 412 | [LP Feed Water pump (DHI for Block 3,4)]_FEEDWATER PUMP_O&M MANUAL | FI | 2019-03-30 | 2019-05-30 | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180911-FC | FC | 0 | 2018-12-22 | 180911-FC STAMPED | FC | 0 | A | SUPPORT | BFP LP | 2018-11-29 | 2018-08-09
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P2LCB-127031 | 413 | [Condensate Extraction pump (DHI for Block 2)]_CEP_GENERAL ARRANGEMENT DRAWING | FA | 2018-03-10 | 2018-06-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-01-05 | 180923-FC STAMPED | FC | 2 | A | MECHANICAL | CEP | 2018-03-27 | 2018-06-27
DHI | 플랜트기술 | 이태훈 | MRT-XG02-P2LCB-127032 | 413 | [Condensate Extraction pump (DHI for Block 2)]_CEP_P&I DIAGRAM | FA | 2018-03-10 | 2018-06-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2020-01-10 | 190244-FC STAMPED | FC | 4 | A | MECHANICAL | CEP | 2018-04-03 | 2018-06-27
DHI | 플랜트기술 | 이태훈 | MRT-XG02-P3LCB-127032 | 413 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_P&I DIAGRAM | FA | 2018-03-10 | 2018-08-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP | 2018-04-03 | 2018-08-09
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P3LCB-127031 | 414 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_GENERAL ARRANGEMENT DRAWING | FA | 2018-03-10 | 2018-08-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP | 2018-03-27 | 2018-07-17
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2LCB-127033 | 415 | [Condensate Extraction pump (DHI for Block 2)]_CEP_DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-03-10 | 2018-06-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-12-17 | 180874-FC STAMPED | FC | 3 | A | MECHANICAL | CEP | 2018-03-27 | 2018-07-17
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3LCB-127033 | 416 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-03-10 | 2018-08-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP | 2018-03-27 | 2018-07-27
DHI | 플랜트기술 | 이태훈 | MRT-YK09-P2LCB-127034 | 417 | [Condensate Extraction pump (DHI for Block 2)]_CEP_PUMP SECTIONAL DRAWING | FI | 2018-05-28 | 2018-08-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-01-05 | 180923-FC STAMPED | FC | 1 | A | MECHANICAL | CEP | 2018-04-03 | 2018-07-27
DHI | 플랜트기술 | 이태훈 | MRT-YK09-P3LCB-127034 | 418 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_PUMP SECTIONAL DRAWING | FI | 2018-05-28 | 2018-10-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP | 2018-04-03 | 2018-07-27
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2LCB-127035 | 419 | [Condensate Extraction pump (DHI for Block 2)]_CEP_MECHANICAL SEAL SPECIFICATION | FI | 2018-05-28 | 2018-08-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-09-13 | 180470-FC STAMPED | FC | 0 | A | MECHANICAL | CEP | 2018-06-08 | 2018-07-27
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3LCB-127035 | 420 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_MECHANICAL SEAL SPECIFICATION | FI | 2018-05-28 | 2018-10-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP | 2018-06-08 | 2018-08-14
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2LCB-127036 | 421 | [Condensate Extraction pump (DHI for Block 2)]_CEP_COUPLING SPECIFICATION | FA | 2018-07-28 | 2018-10-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-11-29 | 180684-FC STAMPED | FC | 0 | A | MECHANICAL | CEP | 2018-07-27 | 2018-08-14
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3LCB-127036 | 422 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_COUPLING SPECIFICATION | FA | 2018-07-28 | 2018-12-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP | 2018-07-27 | 2018-08-06
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2LCB-127037 | 423 | [Condensate Extraction pump (DHI for Block 2)]_CEP_SUCTION STRAINER SPECIFICATION | FA | 2018-07-28 | 2018-10-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-10-06 | 180668-FC STAMPED | FC | 0 | A | MECHANICAL | CEP | 2018-07-26 | 2018-08-06
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3LCB-127037 | 424 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_SUCTION STRAINER SPECIFICATION | FA | 2018-07-28 | 2018-12-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | CEP | 2018-07-26 | 2018-08-06
DHI | 플랜트기술 | 이태훈 | MRT-YL22-P2LCB-127042 | 425 | [Condensate Extraction pump (DHI for Block 2)]_CEP_NAME PLATE DRAWING | FI | 2018-07-28 | 2018-10-26 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180923-FC | FC | 1 | 2019-01-05 | 180923-FC STAMPED | FC | 1 | A | MECHANICAL | CEP | 2018-07-26 | 2018-08-06
DHI | 플랜트기술 | 이태훈 | MRT-YL22-P3LCB-127042 | 426 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_NAME PLATE DRAWING | FI | 2018-07-28 | 2018-12-25 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180923-FC | FC | 1 | 2019-01-05 | 180923-FC STAMPED | FC | 1 | A | MECHANICAL | CEP | 2018-07-26 | 2018-08-09
DHI | 플랜트기술 | 이태훈 | MRT-YM01-P2LCB-127039 | 427 | [Condensate Extraction pump (DHI for Block 2)]_CEP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-07-28 | 2018-10-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2020-09-01 | 200070-FC STAMPED | FC | 3 | A | ELECTRICAL | CEP | 2018-07-27 | 2018-08-09
DHI | 플랜트기술 | 이태훈 | MRT-YM01-P3LCB-127039 | 428 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-07-28 | 2018-12-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | ELECTRICAL | CEP | 2018-07-27 | 2018-08-14
DHI | 플랜트기술 | 이태훈 | MRT-YL00-P2LCB-127040 | 429 | [Condensate Extraction pump (DHI for Block 2)]_CEP_INSTRUMENT LIST AND DATA SHEET | FI | 2018-07-28 | 2018-10-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-11-29 | 180684-FC STAMPED | FC | 0 | A | I&C | CEP | 2018-07-27 | 2018-08-14
DHI | 플랜트기술 | 이태훈 | MRT-YL00-P3LCB-127040 | 430 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_INSTRUMENT LIST AND DATA SHEET | FI | 2018-07-28 | 2018-12-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-08-12 | MTW-AS-C-LT-24.5630.0 | AB | Z0 | A | I&C | CEP | 2018-07-27 | 2018-08-06
DHI | 플랜트기술 | 이태훈 | MRT-CQ02-P2LCB-127043 | 431 | [Condensate Extraction pump (DHI for Block 2)]_CEP_O&M MANUAL | FI | 2018-07-30 | 2018-10-28 | 2018-08-06 | 2018-09-27 | MRT-DS-REC-TT-180637-FC | FC | 0 | 2018-10-05 | 180637-FC STAMPED | FC | 0 | A | SUPPORT | CEP | 2018-07-23 | 2018-08-06
DHI | 플랜트기술 | 이태훈 | MRT-CQ02-P3LCB-127043 | 432 | [Condensate Extraction pump (DHI for Block 3, 4)]_CEP_O&M MANUAL | FI | 2018-07-30 | 2018-12-27 | 2018-08-06 | 2018-09-27 | MRT-DS-REC-TT-180637-FC | FC | 0 | 2018-10-05 | 180637-FC STAMPED | FC | 0 | A | SUPPORT | CEP | 2018-07-23 | 2018-04-16
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P2GHC-129001 | 433 | [General Service Pump (DHI for Block 2)]_GSP_GENERAL ARRANGEMENT DRAWING | FA | 2018-02-28 | 2018-05-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-09-13 | 180460-FC STAMPED | FC | 3 | A | MECHANICAL | GSP | 2018-02-05 | 2018-04-16
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P3GHC-129001 | 434 | [General Service Pump (DHI for Block 3, 4)]_GSP_GENERAL ARRANGEMENT DRAWING | FA | 2018-02-28 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | GSP | 2018-02-05 | 2018-05-25
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2GHC-129002 | 435 | [General Service Pump (DHI for Block 2)]_GSP_DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-02-28 | 2018-05-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-08-23 | 180427-FC STAMPED | FC | 2 | A | MECHANICAL | GSP | 2018-02-23 | 2018-05-25
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3GHC-129002 | 436 | [General Service Pump (DHI for Block 3, 4)]_GSP_DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-02-28 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | GSP | 2018-02-23 | 2019-05-24
DHI | 플랜트기술 | 이태훈 | MRT-YK09-P2GHC-129003 | 437 | [General Service Pump (DHI for Block 2)]_GSP_PUMP SECTIONAL DRAWING | FI | 2018-03-15 | 2018-07-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-05-29 | 180190-FC STAMPED | FC | 0 | A | MECHANICAL | GSP | 2018-03-21 | 2019-05-24
DHI | 플랜트기술 | 이태훈 | MRT-YK09-P3GHC-129003 | 438 | [General Service Pump (DHI for Block 3, 4)]_GSP_PUMP SECTIONAL DRAWING | FI | 2018-03-15 | 2018-07-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | GSP | 2018-03-21 | 2019-05-24
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2GHC-129004 | 439 | [General Service Pump (DHI for Block 2)]_GSP_MECHANICAL SEAL SPECIFICATION | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-05-29 | 180277-FC STAMPED | FC | 0 | A | MECHANICAL | GSP | 2018-04-04 | 2019-05-24
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3GHC-129004 | 440 | [General Service Pump (DHI for Block 3, 4)]_GSP_MECHANICAL SEAL SPECIFICATION | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | GSP | 2018-04-04 | 2019-05-24
DHI | 플랜트기술 | 이태훈 | MRT-YL22-P2GHC-129014 | 441 | [General Service Pump (DHI for Block 2)]_GSP_NAME PLATE DRAWING | FI | 2018-05-31 | 2018-09-28 | 2019-05-24 | 2019-05-28 | MRT-DS-REC-TT-180502-FC | FC | 0 | 2019-06-11 | 180502-FC STAMPED | FC | 0 | A | MECHANICAL | GSP | 2018-06-15 | 2019-05-24
DHI | 플랜트기술 | 이태훈 | MRT-YL22-P3GHC-129014 | 442 | [General Service Pump (DHI for Block 3, 4)]_GSP_NAME PLATE DRAWING | FI | 2018-05-31 | 2018-09-28 | 2019-05-24 | 2019-05-28 | MRT-DS-REC-TT-180502-FC | FC | 0 | 2019-06-11 | 180502-FC STAMPED | FC | 0 | A | MECHANICAL | GSP | 2018-06-15 | 2018-05-25
DHI | 플랜트기술 | 이태훈 | MRT-YM01-P2GHC-129008 | 443 | [General Service Pump (DHI for Block 2)]_GSP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-03-31 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-09-27 | 180428-FC STAMPED | FC | 2 | A | ELECTRICAL | GSP | 2018-03-22 | 2018-05-25
DHI | 플랜트기술 | 이태훈 | MRT-YM01-P3GHC-129008 | 444 | [General Service Pump (DHI for Block 3, 4)]_GSP_MOTOR DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-03-31 | 2018-08-28 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | ELECTRICAL | GSP | 2018-03-22 | 2019-05-24
DHI | 플랜트기술 | 이태훈 | MRT-YL00-P2GHC-129011 | 445 | [General Service Pump (DHI for Block 2)]_GSP_INSTRUMENT LIST AND DATA SHEET | FI | 2018-04-30 | 2018-08-28 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-05-29 | 180382-FC STAMPED | FC | 0 | A | I&C | GSP | 2018-05-11 | 2019-05-24
DHI | 플랜트기술 | 이태훈 | MRT-YL00-P3GHC-129011 | 446 | [General Service Pump (DHI for Block 3, 4)]_GSP_INSTRUMENT LIST AND DATA SHEET | FI | 2018-04-30 | 2018-08-28 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240018 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6022.0 | AB | Z1 | A | I&C | GSP | 2018-05-11 | 2018-07-27
DHI | 플랜트기술 | 이태훈 | MRT-CQ02-P2GHC-129016 | 447 | [General Service Pump (DHI for Block 2)]_GSP_O&M MANUAL | FI | 2018-07-15 | 2018-10-13 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180587-FC | FC | 0 | 2018-10-05 | 180587-FC STAMPED | FC | 0 | A | SUPPORT | GSP | 2018-07-11 | 2018-07-27
DHI | 플랜트기술 | 이태훈 | MRT-CQ02-P3GHC-129016 | 448 | [General Service Pump (DHI for Block 3, 4)]_GSP_O&M MANUAL | FI | 2018-07-15 | 2018-12-12 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180587-FC | FC | 0 | 2018-10-05 | 180587-FC STAMPED | FC | 0 | A | SUPPORT | GSP | 2018-07-11 | 2018-04-26
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P2GM-128507 | 449 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_P&ID | FA | 2017-11-16 | 2018-03-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-09-11 | 489/T/MRT/REC/IX/2019 | FC | 4 | A | MECHANICAL | SUMP PUMP | 2017-12-19 | 2018-04-26
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P3GM-128507 | 450 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_P&ID | FA | 2017-11-16 | 2018-03-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | SUMP PUMP | 2017-12-19 | 2018-06-20
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P2GM-128501 | 451 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_PUMP OUTLINE DRAWING | FA | 2018-03-10 | 2018-06-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-01-12 | 180943-FC STAMPED | FC | 2 | A | MECHANICAL | SUMP PUMP | 2018-04-26 | 2018-06-20
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P3GM-128501 | 452 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_PUMP OUTLINE DRAWING | FA | 2018-03-10 | 2018-08-07 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | SUMP PUMP | 2018-04-26 | 2018-08-09
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P2GM-128502 | 453 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-03-26 | 2018-06-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-01-12 | 180943-FC STAMPED | FC | 2 | A | MECHANICAL | SUMP PUMP | 2018-04-26 | 2018-08-09
DHI | 플랜트기술 | 이태훈 | MRT-YT01-P3GM-128502 | 454 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_DATA SHEET & CHARACTERISTIC CURVE | FA | 2018-03-26 | 2018-08-23 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | SUMP PUMP | 2018-04-26 | 2018-07-24
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P2GM-128503 | 455 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_PUMP SECTIONAL DRAWING | FI | 2018-04-26 | 2018-07-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-10-26 | 180656-FC STAMPED | FC | 1 | A | MECHANICAL | SUMP PUMP | 2018-05-02 | 2018-07-24
DHI | 플랜트기술 | 이태훈 | MRT-YD00-P3GM-128503 | 456 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_PUMP SECTIONAL DRAWING | FI | 2018-04-26 | 2018-09-23 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | SUMP PUMP | 2018-05-02 | 2018-07-27
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P2GM-128504 | 457 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_MECHANICAL SEAL SPECIFICATION | FI | 2018-05-15 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-08-25 | 180395-FC STAMPED | FC | 0 | A | MECHANICAL | SUMP PUMP | 2018-05-15 | 2018-07-27
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P3GM-128504 | 458 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_MECHANICAL SEAL SPECIFICATION | FI | 2018-05-15 | 2018-10-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | SUMP PUMP | 2018-05-15 | 2018-07-24
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P2GM-128505 | 459 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_COUPLING SPECIFICATION | FA | 2018-04-16 | 2018-07-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-10-26 | 180656-FC STAMPED | FC | 1 | A | MECHANICAL | SUMP PUMP | 2018-04-26 | 2018-07-24
DHI | 플랜트기술 | 이태훈 | MRT-XK00-P3GM-128505 | 460 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_COUPLING SPECIFICATION | FA | 2018-04-16 | 2018-09-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | SUMP PUMP | 2018-04-26 | 2019-05-24
DHI | 플랜트기술 | 이태훈 | MRT-XF00-P2GM-128510 | 461 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_NAME PLATE DRAWING | FI | 2018-05-26 | 2018-09-23 | 2019-05-24 | 2019-05-27 | MRT-DS-REC-TT-180442-FC | FC | 0 | 2019-05-29 | 180442-FC STAMPED | FC | 0 | A | MECHANICAL | SUMP PUMP | 2018-05-31 | 2019-05-24
DHI | 플랜트기술 | 이태훈 | MRT-XF00-P3GM-128510 | 462 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_NAME PLATE DRAWING | FI | 2018-05-26 | 2018-09-23 | 2019-05-24 | 2019-05-27 | MRT-DS-REC-TT-180442-FC | FC | 0 | 2019-12-06 | 180442-FC STAMPED | FC | 0 | A | MECHANICAL | SUMP PUMP | 2018-05-31 | 2018-08-06
DHI | 플랜트기술 | 이태훈 | MRT-XW01-P2GM-128507 | 463 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_MOTOR SPECIFICATION | FA | 2018-05-26 | 2018-08-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-01-12 | 180943-FC STAMPED | FC | 2 | A | ELECTRICAL | SUMP PUMP | 2018-05-31 | 2018-08-06
DHI | 플랜트기술 | 이태훈 | MRT-XW01-P3GM-128507 | 464 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_MOTOR SPECIFICATION | FA | 2018-05-26 | 2018-10-23 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | ELECTRICAL | SUMP PUMP | 2018-05-31 | 2018-09-13
DHI | 플랜트기술 | 이태훈 | MRT-YR05-P2GM-128511 | 465 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_SCHEMATIC AND WIRING DIAGRAM WITH CONTROL PANEL LAYOUT DRAWING | FI | 2018-05-26 | 2018-08-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-01-12 | 180943-FC STAMPED | FC | 2 | A | ELECTRICAL | SUMP PUMP | 2018-05-31 | 2018-09-13
DHI | 플랜트기술 | 이태훈 | MRT-YR05-P3GM-128511 | 466 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_SCHEMATIC AND WIRING DIAGRAM WITH CONTROL PANEL LAYOUT DRAWING | FI | 2018-05-26 | 2018-10-23 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240018 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6022.0 | AB | Z1 | A | ELECTRICAL | SUMP PUMP | 2018-05-31 | 2018-10-11
DHI | 플랜트기술 | 이태훈 | MRT-YL00-P2GM-128512 | 467 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_INSTRUMENT LIST AND DATA SHEET | FI | 2018-05-26 | 2018-08-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-08-12 | 190176-FC STAMPED | FC | 3 | A | I&C | SUMP PUMP | 2018-07-27 | 2018-10-11
DHI | 플랜트기술 | 이태훈 | MRT-YL00-P3GM-128512 | 468 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_INSTRUMENT LIST AND DATA SHEET | FI | 2018-05-26 | 2018-10-23 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240018 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6022.0 | AB | Z1 | A | I&C | SUMP PUMP | 2018-07-27 | 2018-08-06
DHI | 플랜트기술 | 이태훈 | MRT-XB00-P2GM-128506 | 469 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_FOUNDATION DRAWINGS | FI | 2018-05-26 | 2018-08-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-04-29 | 190118-FC STAMPED | FC | 2 | A | CIVIL | SUMP PUMP | 2018-07-04 | 2018-08-06
DHI | 플랜트기술 | 이태훈 | MRT-XB00-P3GM-128506 | 470 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_FOUNDATION DRAWINGS | FI | 2018-05-26 | 2018-10-23 | 2024-11-15 | 2024-11-15 | MRT-DS-REC-TT-240029 | AB | Z0 | 2025-02-20 | MTW-AS-C-LT-25.6213.0 | AB | Z0 | A | CIVIL | SUMP PUMP | 2018-07-04 | 2018-11-14
DHI | 플랜트기술 | 이태훈 | MRT-CQ02-P2GM-128515 | 471 | [Sump Pump (DHI for Block 2)]_SUMP PUMP_O&M MANUAL | FI | 2018-08-10 | 2019-01-31 | 2018-11-14 | 2018-12-03 | MRT-DS-REC-TT-180839-FC | FC | 1 | 2018-12-08 | 180839-FC STAMPED | FC | 1 | A | SUPPORT | SUMP PUMP | 2018-08-29 | 2018-11-14
DHI | 플랜트기술 | 이태훈 | MRT-CQ02-P3GM-128515 | 472 | [Sump Pump (DHI for Block 3, 4)]_SUMP PUMP_O&M MANUAL | FI | 2018-08-10 | 2019-01-31 | 2018-11-14 | 2018-12-03 | MRT-DS-REC-TT-180839-FC | FC | 1 | 2018-12-08 | 180839-FC STAMPED | FC | 1 | A | SUPPORT | SUMP PUMP | 2018-08-29 | 2018-04-09
DHI | 플랜트기술 | 안성훈 | MRT-YD00-P0SMM-128001 | 473 | [Crane & Hoist(DHI)]_CRANE_GA DRAWING FOR STEAM TURBINE BUILDING CRANE | FA | 2018-01-05 | 2018-04-05 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-12-23 | 190223-FC STAMPED | FC | 4 | A | MECHANICAL | CRANE | 2018-01-11 | 2018-04-09
DHI | 플랜트기술 | 안성훈 | MRT-YT01-P0SMM-128004 | 474 | [Crane & Hoist(DHI)]_CRANE_DATA SHEETS FOR STEAM TURBINE BUILDING CRANE | FA | 2018-01-05 | 2018-04-05 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180446-FC | FC | 3 | 2018-09-12 | 180446-FC STAMPED | FC | 3 | A | MECHANICAL | CRANE | 2018-01-11 | 2018-05-15
DHI | 플랜트기술 | 안성훈 | MRT-YK09-P0SMM-128007 | 475 | [Crane & Hoist(DHI)]_CRANE_MECHNICAL DETAIL FOR STEAM TURBINE BUILDING CRANE | FA | 2018-03-26 | 2018-06-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2020-01-02 | 190232-FC STAMPED | FC | 4 | A | MECHANICAL | CRANE | 2018-04-03 | 2019-05-24
DHI | 플랜트기술 | 안성훈 | MRT-YK08-P0SMM-128001 | 476 | [Crane & Hoist(DHI)]_CRANE_NAMEPLATE DRAWING FOR STEAM TURBINE BUILDING CRANE | FI | 2018-03-20 | 2018-07-18 | 2019-05-24 | 2019-05-27 | MRT-DS-REC-TT-180232-FC | FC | 0 | 2019-05-29 | 180232-FC STAMPED | FC | 0 | A | MECHANICAL | CRANE | 2018-03-26 | 2019-05-24
DHI | 플랜트기술 | 안성훈 | MRT-YS18-P0SMM-128010 | 477 | [Crane & Hoist(DHI)]_CRANE_ELECTRICAL DETAIL FOR STEAM TURBINE BUILDING CRANE | FI | 2018-03-26 | 2018-07-24 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2020-01-10 | 190242-FC STAMPED | FC | 2 | A | ELECTRICAL | CRANE | 2018-03-27 | 2018-11-22
DHI | 플랜트기술 | 안성훈 | MRT-DM02-P0SMM-128001 | 478 | [Crane & Hoist(DHI)]_CRANE_INSTALLATION & ERECTION MANUAL FOR STEAM TURBINE BUILDING CRANE | FI | 2018-11-06 | 2019-01-06 | 2018-11-22 | 2018-11-22 | MRT-DS-REC-TT-180848-FC | FC | 0 | 2018-12-13 | 180848-FC STAMPED | FC | 0 | A | SUPPORT | CRANE | 2018-10-29 | 2018-11-22
DHI | 플랜트기술 | 안성훈 | MRT-CT00-P0SMM-128001 | 479 | [Crane & Hoist(DHI)]_CRANE_OPERATION & MAINTENANCE MANUAL FOR STEAM TURBINE BUILDING CRANE | FI | 2018-11-06 | 2019-01-06 | 2018-11-22 | 2018-11-22 | MRT-DS-REC-TT-180848-FC | FC | 0 | 2018-12-13 | 180848-FC STAMPED | FC | 0 | A | SUPPORT | CRANE | 2018-10-29 | 2018-07-05
DHI | 플랜트기술 | 박대영 | MRT-YD00-P2SM-128020 | 480 | [Crane & Hoist(DHI)]_HOIST_GA DRAWING (FOR BLOCK 2) | FI | 2018-04-30 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2018-12-07 | 180838-FC STAMPED | FC | 2 | A | MECHANICAL | HOIST | 2018-05-17 | 2018-07-05
DHI | 플랜트기술 | 박대영 | MRT-YD00-P3SM-128020 | 481 | [Crane & Hoist(DHI)]_HOIST_GA DRAWING (FOR BLOCK 3, 4) | FI | 2018-04-30 | 2018-06-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | HOIST | 2018-05-17 | 2019-03-18
DHI | 플랜트기술 | 박대영 | MRT-YK09-P2SM-128040 | 482 | [Crane & Hoist(DHI)]_HOIST_MECHANICAL DETAIL (FOR BLOCK 2) | FI | 2018-04-30 | 2019-03-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-03-18 | 180841-FC STAMPED | FC | 1 | A | MECHANICAL | HOIST | 2018-05-17 | 2019-03-18
DHI | 플랜트기술 | 박대영 | MRT-YK09-P3SM-128040 | 483 | [Crane & Hoist(DHI)]_HOIST_MECHANICAL DETAIL (FOR BLOCK 3, 4) | FI | 2018-04-30 | 2019-03-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | HOIST | 2018-05-17 | 2019-03-18
DHI | 플랜트기술 | 박대영 | MRT-YT01-P2SM-128030 | 484 | [Crane & Hoist(DHI)]_HOIST_DATA SHEET (FOR BLOCK 2) | FI | 2018-04-30 | 2019-03-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-03-18 | 180420-FC STAMPED | FC | 0 | A | MECHANICAL | HOIST | 2018-05-17 | 2019-03-18
DHI | 플랜트기술 | 박대영 | MRT-YT01-P3SM-128030 | 485 | [Crane & Hoist(DHI)]_HOIST_DATA SHEET (FOR BLOCK 3, 4) | FI | 2018-04-30 | 2019-03-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-03-04 | MTW-AS-C-LT-24.4985.0 | AB | Z0 | A | MECHANICAL | HOIST | 2018-05-17 | 2019-03-18
DHI | 플랜트기술 | 박대영 | MRT-YS18-P2SM-128050 | 486 | [Crane & Hoist(DHI)]_HOIST_ELECTRICAL DETAIL (FOR BLOCK 2) | FI | 2018-04-30 | 2019-03-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2019-03-18 | 180420-FC STAMPED | FC | 0 | A | ELECTRICAL | HOIST | 2018-05-24 | 2019-03-18
DHI | 플랜트기술 | 박대영 | MRT-YS18-P3SM-128050 | 487 | [Crane & Hoist(DHI)]_HOIST_ELECTRICAL DETAIL (FOR BLOCK 3, 4) | FI | 2018-04-30 | 2019-03-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | 2024-07-12 | MTW-AS-C-LT-24.5518.0 | AB | Z0 | A | ELECTRICAL | HOIST | 2018-05-24 | 2018-12-24
DHI | 플랜트기술 | 박대영 | MRT-CQ02-P2SM-128060 | 488 | [Crane & Hoist(DHI)]_HOIST_ O&M Manual (FOR BLOCK 2) | FI | 2018-11-30 | 2019-01-31 | 2018-12-24 | 2018-12-26 | MRT-DS-REC-TT-180918-FC | FC | 0 | 2018-12-27 | 180918-FC STAMPED | FC | 0 | A | SUPPORT | HOIST | 2018-12-06 | 2018-12-24
DHI | 플랜트기술 | 박대영 | MRT-CQ02-P3SM-128060 | 489 | [Crane & Hoist(DHI)]_HOIST_ O&M Manual (FOR BLOCK 3, 4) | FI | 2018-11-30 | 2019-01-31 | 2018-12-24 | 2018-12-26 | MRT-DS-REC-TT-180918-FC | FC | 0 | 2018-12-27 | 180918-FC STAMPED | FC | 0 | A | SUPPORT | HOIST | 2018-12-06 | 2018-06-05
DHI | 기계기술 | 김희정 | MRT-XG02-P2QC-130001 | 490 | [Chemical Dosing System For Block 2]_P&ID | FA | 2018-02-01 | 2018-05-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-23 | 180749-FC STMAPED | FC | 3 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-02-12 | 2018-06-05
DHI | 기계기술 | 김희정 | MRT-XG02-P3QC-130001 | 491 | [Chemical Dosing system For Block 3, 4]_P&ID | FA | 2018-02-01 | 2018-05-16 | 2024-05-20 | 2024-05-20 | MRT-DS-REC-TT-240012 | AB | Z1 | 2024-06-08 | MTW-AS-C-LT-24.5327.0 | AB | Z1 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-02-12 | 2018-06-29
DHI | 기계기술 | 김희정 | MRT-XA00-P2QC-130002 | 492 | [Chemical Dosing System For Block 2]_GENERAL ARRANGEMENT DRAWING | FA | 2018-02-01 | 2018-05-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-20 | 180760-FC STAMPED | FC | 3 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-02-07 | 2018-06-29
DHI | 기계기술 | 김희정 | MRT-XA00-P3QC-130002 | 493 | [Chemical Dosing system For Block 3, 4]_GENERAL ARRANGEMENT DRAWING | FA | 2018-02-01 | 2018-05-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-20 | 180760-FC STAMPED | FC | 3 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-02-07 | 2018-06-05
DHI | 기계기술 | 김희정 | MRT-XS00-P2QC-130003 | 494 | [Chemical Dosing System For Block 2]_SYSTEM DESCRIPTION | FA | 2018-02-01 | 2018-05-16 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180463-FC | FC | 2 | 2018-09-13 | 180463-FC STAMPED | FC | 2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-02-12 | 2018-06-05
DHI | 기계기술 | 김희정 | MRT-XS00-P3QC-130003 | 495 | [Chemical Dosing system For Block 3, 4]_SYSTEM DESCRIPTION | FA | 2018-02-01 | 2018-05-16 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180463-FC | FC | 2 | 2018-09-13 | 180463-FC STAMPED | FC | 2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-02-12 | 2018-06-05
DHI | 기계기술 | 김희정 | MRT-CC07-P2QC-130004 | 496 | [Chemical Dosing System For Block 2]_CALCULATION SHEET | FA | 2018-02-01 | 2018-05-16 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180463-FC | FC | 2 | 2018-09-13 | 180463-FC STAMPED | FC | 2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-02-12 | 2018-06-05
DHI | 기계기술 | 김희정 | MRT-CC07-P3QC-130004 | 497 | [Chemical Dosing system For Block 3, 4]_CALCULATION SHEET | FA | 2018-02-01 | 2018-05-16 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180463-FC | FC | 2 | 2018-09-13 | 180463-FC STAMPED | FC | 2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-02-12 | 2018-06-15
DHI | 기계기술 | 김희정 | MRT-YD00-P2QC-130005 | 498 | [Chemical Dosing System For Block 2]_CONTROL PANEL ARRANGEMENT DRAWING | FI | 2018-03-01 | 2018-06-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-16 | 180750-FC STAMPED | FC | 3 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-03-27 | 2018-06-15
DHI | 기계기술 | 김희정 | MRT-YD00-P3QC-130005 | 499 | [Chemical Dosing system For Block 3, 4]_CONTROL PANEL ARRANGEMENT DRAWING | FI | 2018-03-01 | 2018-06-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5936.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-03-27 | 2018-07-04
DHI | 기계기술 | 김희정 | MRT-YF02-P2QC-130006 | 500 | [Chemical Dosing System For Block 2]_CONTROL CONFIGURATION DIAGRAM | FA | 2018-03-01 | 2018-06-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-12-10 | 180831-FC STAMPED | FC | 4 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-03-27 | 2018-07-04
DHI | 기계기술 | 김희정 | MRT-YF02-P3QC-130006 | 501 | [Chemical Dosing system For Block 3, 4]_CONTROL CONFIGURATION DIAGRAM | FA | 2018-03-01 | 2018-06-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-03-27 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YL00-P2QC-130007 | 502 | [Chemical Dosing System For Block 2]_INSTRUMENT LIST | FI | 2018-03-01 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-11 | 180694-FC STAMPED | FC | 2 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-03-13 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YL00-P3QC-130007 | 503 | [Chemical Dosing system For Block 3, 4]_INSTRUMENT LIST | FI | 2018-03-01 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-03-13 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-XN00-P2QC-130008 | 504 | [Chemical Dosing System For Block 2]_VALVE LIST | FI | 2018-03-01 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180519-FC STAMPED | FC | 1 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-03-12 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-XN00-P3QC-130008 | 505 | [Chemical Dosing system For Block 3, 4]_VALVE LIST | FI | 2018-03-01 | 2018-06-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180519-FC STAMPED | FC | 1 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-03-12 | 2018-06-25
DHI | 기계기술 | 김희정 | MRT-XB02-P2QC-130009 | 506 | [Chemical Dosing System For Block 2]_FOUNDATION AND LOADING DATA | FI | 2018-04-01 | 2018-07-14 | 2018-09-18 | 2018-10-10 | MRT-DS-REC-TT-180752-FC | FC | 2 | 2018-10-16 | 180752-FC STAMPED | FC | 2 | A | CIVIL | CHEMICAL DOSING SYSTEM | 2018-04-06 | 2018-06-25
DHI | 기계기술 | 김희정 | MRT-XB02-P3QC-130009 | 507 | [Chemical Dosing system For Block 3, 4]_FOUNDATION AND LOADING DATA | FI | 2018-04-01 | 2018-07-14 | 2018-09-18 | 2018-10-10 | MRT-DS-REC-TT-180752-FC | FC | 2 | 2018-10-16 | 180752-FC STAMPED | FC | 2 | A | CIVIL | CHEMICAL DOSING SYSTEM | 2018-04-06 | 2018-06-25
DHI | 기계기술 | 김희정 | MRT-YK10-P2QC-130010 | 508 | [Chemical Dosing System For Block 2]_EQUIPMENT ASSEMBLY DRAWING | FI | 2018-04-01 | 2018-07-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-23 | 180698-FC STAMPED | FC | 2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-05-10 | 2018-06-25
DHI | 기계기술 | 김희정 | MRT-YK10-P3QC-130010 | 509 | [Chemical Dosing system For Block 3, 4]_EQUIPMENT ASSEMBLY DRAWING | FI | 2018-04-01 | 2018-07-14 | 2025-01-21 | 2025-01-21 | MRT-DS-REC-TT-250005 | AB | Z2 | 2025-01-24 | MTW-AS-C-LT-25.6148.0 | AB | Z2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-05-10 | 2018-06-25
DHI | 기계기술 | 김희정 | MRT-XH01-P2QC-130011 | 510 | [Chemical Dosing System For Block 2]_PIPING ARRANGEMENT DRAWING | FI | 2018-04-01 | 2018-07-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-11 | 180761-FC STAMPED | FC | 2 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-04-05 | 2018-06-25
DHI | 기계기술 | 김희정 | MRT-XH01-P3QC-130011 | 511 | [Chemical Dosing system For Block 3, 4]_PIPING ARRANGEMENT DRAWING | FI | 2018-04-01 | 2018-07-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-05-17 | MTW-AS-C-LT-24.5261.0 | AB | Z0 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-04-05 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P2QC-130012 | 512 | [Chemical Dosing System For Block 2]_TECHNICAL DATASHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-17 | 180697-FC STAMPED | FC | 1 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-04-23 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P3QC-130012 | 513 | [Chemical Dosing system For Block 3, 4]_TECHNICAL DATASHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-17 | 180697-FC STAMPED | FC | 1 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-04-23 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P2QC-130013 | 514 | [Chemical Dosing System For Block 2]_MOTOR DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180563-FC STAMPED | FC | 1 | A | ELECTRICAL | CHEMICAL DOSING SYSTEM | 2018-05-16 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P3QC-130013 | 515 | [Chemical Dosing system For Block 3, 4]_MOTOR DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180563-FC STAMPED | FC | 1 | A | ELECTRICAL | CHEMICAL DOSING SYSTEM | 2018-05-16 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P2QC-130014 | 516 | [Chemical Dosing System For Block 2]_PUMP DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180511-FC STAMPED | FC | 1 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-04-03 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P3QC-130014 | 517 | [Chemical Dosing system For Block 3, 4]_PUMP DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-10-31 | MRT-YT01-P3QC-130014 | AB | Z0 | A | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-04-03 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P2QC-130016 | 518 | [Chemical Dosing System For Block 2]_INSTRUMENT DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-14 | 180695-FC STAMPED | FC | 2 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-05-16 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P3QC-130016 | 519 | [Chemical Dosing system For Block 3, 4]_INSTRUMENT DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2025-01-21 | 2025-01-21 | MRT-DS-REC-TT-250005 | AB | Z1 | 2025-02-12 | MTW-AS-C-LT-25.6191.0 | AB | Z1 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-05-16 | 2018-07-16
DHI | 기계기술 | 김희정 | MRT-YV02-P2QC-130017 | 520 | [Chemical Dosing System For Block 2]_INTERCONNECTION WIRING DIAGRAM | FI | 2018-05-01 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-22 | 180615-FC STAMPED | FC | 2 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-05-10 | 2018-07-16
DHI | 기계기술 | 김희정 | MRT-YV02-P3QC-130017 | 521 | [Chemical Dosing system For Block 3, 4]_INTERCONNECTION WIRING DIAGRAM | FI | 2018-05-01 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5936.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-05-10 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YL22-P2QC-130018 | 522 | [Chemical Dosing System For Block 2]_NAME PLATE DRAWING | FI | 2018-05-01 | 2018-08-29 | 2019-05-24 | 2019-06-17 | MRT-DS-REC-TT-180753-FC | FC | 1 | 2018-10-17 | 921/T/MRT/REC/X/2018 | FI | 1 | I | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-05-15 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YL22-P3QC-130018 | 523 | [Chemical Dosing system For Block 3, 4]_NAME PLATE DRAWING | FI | 2018-05-01 | 2018-08-29 | 2019-05-24 | 2019-06-17 | MRT-DS-REC-TT-180753-FC | FC | 1 | 2018-10-17 | 921/T/MRT/REC/X/2018 | FI | 1 | I | MECHANICAL | CHEMICAL DOSING SYSTEM | 2018-05-15 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YF00-P2QC-130019 | 524 | [Chemical Dosing System For Block 2]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-14 | 180520-FC STAMPED | FC | 1 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-05-16 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YF00-P3QC-130019 | 525 | [Chemical Dosing system For Block 3, 4]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-05-16 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YS01-P2QC-130020 | 526 | [Chemical Dosing System For Block 2]_SCHEMATIC DIAGRAM | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-19 | 180811-FC STAMPED | FC | 2 | A | ELECTRICAL | CHEMICAL DOSING SYSTEM | 2018-05-15 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YS01-P3QC-130020 | 527 | [Chemical Dosing system For Block 3, 4]_SCHEMATIC DIAGRAM | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | ELECTRICAL | CHEMICAL DOSING SYSTEM | 2018-05-15 | 2018-06-25
DHI | 기계기술 | 김희정 | MRT-YE00-P2QC-130021 | 528 | [Chemical Dosing System For Block 2]_CABLE TRAY LAYOUT DRAWING | FI | 2018-05-01 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-26 | 180754-FC STAMPED | FC | 3 | A | ELECTRICAL | CHEMICAL DOSING SYSTEM | 2018-05-11 | 2018-06-25
DHI | 기계기술 | 김희정 | MRT-YE00-P3QC-130021 | 529 | [Chemical Dosing system For Block 3, 4]_CABLE TRAY LAYOUT DRAWING | FI | 2018-05-01 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5936.0 | AB | Z0 | A | ELECTRICAL | CHEMICAL DOSING SYSTEM | 2018-05-11 | 2018-06-22
DHI | 기계기술 | 김희정 | MRT-YK00-P2QC-130022 | 530 | [Chemical Dosing System For Block 2]_HOOK UP DRAWING | FI | 2018-05-01 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-23 | 180762-FC STAMPED | FC | 3 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-05-15 | 2018-06-22
DHI | 기계기술 | 김희정 | MRT-YK00-P3QC-130022 | 531 | [Chemical Dosing system For Block 3, 4]_HOOK UP DRAWING | FI | 2018-05-01 | 2018-08-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-05-15 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P2QC-130033 | 532 | [Chemical Dosing System For Block 2]_PLC DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-14 | 180509-FC STAMPED | FC | 1 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-04-05 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P3QC-130033 | 533 | [Chemical Dosing system For Block 3, 4]_PLC DATA SHEET | FI | 2018-04-01 | 2018-07-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-04-05 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YL01-P2QC-130034 | 534 | [Chemical Dosing System For Block 2]_PLC IO LIST | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-28 | 180891-FC STAMPED | FC | 3 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-05-15 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YL01-P3QC-130034 | 535 | [Chemical Dosing system For Block 3, 4]_PLC IO LIST | FI | 2018-05-01 | 2018-08-29 | 2025-01-21 | 2025-01-21 | MRT-DS-REC-TT-250005 | AB | Z1 | 2025-02-12 | MTW-AS-C-LT-25.6191.0 | AB | Z1 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-05-15 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YD05-P2QC-130035 | 536 | [Chemical Dosing System For Block 2]_HMI GRAPHICS | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-19 | 180904-FC STAMPED | FC | 3 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-05-10 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YD05-P3QC-130035 | 537 | [Chemical Dosing system For Block 3, 4]_HMI GRAPHICS | FI | 2018-05-01 | 2018-08-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5936.0 | AB | Z0 | A | I&C | CHEMICAL DOSING SYSTEM | 2018-05-10 | 2018-12-19
DHI | 기계기술 | 김희정 | MRT-CQ02-P2QC-130036 | 538 | [Chemical Dosing System For Block 2]_Installation & Erection Manual | FI | 2018-11-30 | 2019-02-28 | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180925-FC | FC | 0 | 2018-12-22 | 180925-FC STAMPED | FC | 0 | A | SUPPORT | CHEMICAL DOSING SYSTEM | 2018-12-10 | 2018-12-19
DHI | 기계기술 | 김희정 | MRT-CQ02-P3QC-130036 | 539 | [Chemical Dosing System For Block 3,4]_Installation & Erection Manual | FI | 2018-11-30 | 2019-02-28 | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180925-FC | FC | 0 | 2018-12-22 | 180925-FC STAMPED | FC | 0 | A | SUPPORT | CHEMICAL DOSING SYSTEM | 2018-12-10 | 2019-01-02
DHI | 기계기술 | 김희정 | MRT-DN05-P2QC-130001 | 540 | [Chemical Dosing System For Block 2]_Commissioning Manual | FA | 2018-11-30 | 2019-02-28 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180924-FC | FC | 0 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 0 | A | SUPPORT | CHEMICAL DOSING SYSTEM | 2018-12-10 | 2019-01-02
DHI | 기계기술 | 김희정 | MRT-DN05-P3QC-130001 | 541 | [Chemical dosing system For Block 3, 4]_Commissioning Manual | FA | 2018-11-30 | 2019-02-28 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180924-FC | FC | 0 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 0 | A | SUPPORT | CHEMICAL DOSING SYSTEM | 2018-12-10 | 2018-11-15
DHI | 기계기술 | 김희정 | MRT-CQ02-P2QC-130023 | 542 | [Chemical Dosing System For Block 2]_O&M MANUAL | FI | 2018-06-29 | 2018-11-30 | 2018-11-15 | 2018-12-04 | MRT-DS-REC-TT-180581-FC | FC | 0 | 2018-12-11 | 180581-FC STAMPED | FC | 0 | A | SUPPORT | CHEMICAL DOSING SYSTEM | 2018-07-06 | 2018-11-15
DHI | 기계기술 | 김희정 | MRT-CQ02-P3QC-130023 | 543 | [Chemical Dosing system For Block 3, 4]_O&M MANUAL | FI | 2018-06-29 | 2018-11-30 | 2018-11-15 | 2018-12-04 | MRT-DS-REC-TT-180581-FC | FC | 0 | 2018-12-11 | 180581-FC STAMPED | FC | 0 | A | SUPPORT | CHEMICAL DOSING SYSTEM | 2018-07-06 | 2018-05-31
DHI | 기계기술 | 김희정 | MRT-XG02-P2QU-130024 | 544 | [Sampling System_For Block 2]_P&ID | FA | 2018-01-31 | 2018-05-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-09-13 | 180449-FC STAMPED | FC | 2 | A | MECHANICAL | SAMPLING SYSTEM | 2018-02-08 | 2018-05-31
DHI | 기계기술 | 김희정 | MRT-XG02-P3QU-130024 | 545 | [Sampling System_For Block 3,4]_P&ID | FA | 2018-01-31 | 2018-05-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-05-17 | MTW-AS-C-LT-24.5261.0 | AB | Z0 | A | MECHANICAL | SAMPLING SYSTEM | 2018-02-08 | 2018-05-30
DHI | 기계기술 | 김희정 | MRT-XA00-P2QU-130025 | 546 | [Sampling System_For Block 2]_GENERAL ARRANGEMENT DRAWING | FA | 2018-01-31 | 2018-05-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-12-17 | 180870-FC STAMPED | FC | 6 | A | MECHANICAL | SAMPLING SYSTEM | 2018-02-08 | 2018-05-30
DHI | 기계기술 | 김희정 | MRT-XA00-P3QU-130025 | 547 | [Sampling System_For Block 3,4]_GENERAL ARRANGEMENT DRAWING | FA | 2018-01-31 | 2018-05-15 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-12-07 | 180842-FC STAMPED | FC | 5 | A | MECHANICAL | SAMPLING SYSTEM | 2018-02-08 | 2018-05-30
DHI | 기계기술 | 김희정 | MRT-XS00-P2QU-130026 | 548 | [Sampling System_For Block 2]_SYSTEM DESCRIPTION | FA | 2018-01-31 | 2018-05-15 | 2018-11-07 | 2018-12-03 | MRT-DS-REC-TT-180832-FC | FC | 3 | 2018-12-07 | 180832-FC STAMPED | FC | 3 | A | MECHANICAL | SAMPLING SYSTEM | 2018-02-08 | 2018-05-30
DHI | 기계기술 | 김희정 | MRT-XS00-P3QU-130026 | 549 | [Sampling System_For Block 3,4]_SYSTEM DESCRIPTION | FA | 2018-01-31 | 2018-05-15 | 2018-11-07 | 2018-12-03 | MRT-DS-REC-TT-180832-FC | FC | 3 | 2018-12-07 | 180832-FC STAMPED | FC | 3 | A | MECHANICAL | SAMPLING SYSTEM | 2018-02-08 | 2018-06-15
DHI | 기계기술 | 김희정 | MRT-YF02-P2QU-130027 | 550 | [Sampling System_For Block 2]_CONTROL CONFIGURATION DIAGRAM | FA | 2018-02-28 | 2018-06-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-09-21 | 180499-FC STAMPED | FC | 2 | A | I&C | SAMPLING SYSTEM | 2018-03-06 | 2018-06-15
DHI | 기계기술 | 김희정 | MRT-YF02-P3QU-130027 | 551 | [Sampling System_For Block 3,4]_CONTROL CONFIGURATION DIAGRAM | FA | 2018-02-28 | 2018-06-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | SAMPLING SYSTEM | 2018-03-06 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YL00-P2QU-130028 | 552 | [Sampling System_For Block 2]_INSTRUMENT LIST | FI | 2018-02-28 | 2018-06-28 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180424-FC STAMPED | FC | 1 | A | I&C | SAMPLING SYSTEM | 2018-03-06 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YL00-P3QU-130028 | 553 | [Sampling System_For Block 3,4]_INSTRUMENT LIST | FI | 2018-02-28 | 2018-06-28 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | SAMPLING SYSTEM | 2018-03-06 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-XN00-P2QU-130029 | 554 | [Sampling System_For Block 2]_VALVE LIST | FI | 2018-02-28 | 2018-06-28 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180152-FC STAMPED | FC | 0 | A | MECHANICAL | SAMPLING SYSTEM | 2018-03-06 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-XN00-P3QU-130029 | 555 | [Sampling System_For Block 3,4]_VALVE LIST | FI | 2018-02-28 | 2018-06-28 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180152-FC STAMPED | FC | 0 | A | MECHANICAL | SAMPLING SYSTEM | 2018-03-06 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P2QU-130030 | 556 | [Sampling System_For Block 2]_TECHNICAL DATASHEET | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180423-FC STAMPED | FC | 1 | A | MECHANICAL | SAMPLING SYSTEM | 2018-04-06 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P3QU-130030 | 557 | [Sampling System_For Block 3,4]_TECHNICAL DATASHEET | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-05-29 | 180293-FC STAMPED | FC | 0 | A | MECHANICAL | SAMPLING SYSTEM | 2018-04-06 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P2QU-130031 | 558 | [Sampling System_For Block 2]_INSTRUMENT DATA SHEET | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-19 | 180757-FC STAMPED | FC | 3 | A | I&C | SAMPLING SYSTEM | 2018-04-06 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YT01-P3QU-130031 | 559 | [Sampling System_For Block 3,4]_INSTRUMENT DATA SHEET | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | SAMPLING SYSTEM | 2018-04-06 | 2018-07-16
DHI | 기계기술 | 김희정 | MRT-YV02-P2QU-130032 | 560 | [Sampling System_For Block 2]_INTERCONNECTION WIRING DIAGRAM | FI | 2018-03-31 | 2018-07-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2018-10-05 | 180612-FC STAMPED | FC | 2 | A | ELECTRICAL | SAMPLING SYSTEM | 2018-04-06 | 2018-07-16
DHI | 기계기술 | 김희정 | MRT-YV02-P3QU-130032 | 561 | [Sampling System_For Block 3,4]_INTERCONNECTION WIRING DIAGRAM | FI | 2018-03-31 | 2018-07-13 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | ELECTRICAL | SAMPLING SYSTEM | 2018-04-06 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YF00-P2QU-130033 | 562 | [Sampling System_For Block 2]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-19 | 180757-FC STAMPED | FC | 3 | A | I&C | SAMPLING SYSTEM | 2018-04-06 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YF00-P3QU-130033 | 563 | [Sampling System_For Block 3,4]_CONTROL LOOP & LOGIC DIAGRAM | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | I&C | SAMPLING SYSTEM | 2018-04-06 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YS01-P2QU-130034 | 564 | [Sampling System_For Block 2]_SCHEMATIC DIAGRAM | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2019-06-19 | 180715-FC STAMPED | FC | 3 | A | ELECTRICAL | SAMPLING SYSTEM | 2018-04-06 | 2019-05-24
DHI | 기계기술 | 김희정 | MRT-YS01-P3QU-130034 | 565 | [Sampling System_For Block 3,4]_SCHEMATIC DIAGRAM | FI | 2018-03-31 | 2018-07-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | 2024-12-03 | MTW-AS-C-LT-24.6021.0 | AB | Z0 | A | ELECTRICAL | SAMPLING SYSTEM | 2018-04-06 | 2018-11-26
DHI | 기계기술 | 김희정 | MRT-CQ02-P2QU-130036 | 566 | [Sampling System For Block 2]_Installation & Erection Manual | FI | 2018-11-23 | 2019-02-23 | 2018-11-26 | 2018-11-26 | MRT-DS-REC-TT-180901-FC | FC | 0 | 2018-12-03 | 180901-FC STAMPED | FC | 0 | A | SUPPORT | SAMPLING SYSTEM | 2018-11-22 | 2018-11-26
DHI | 기계기술 | 김희정 | MRT-CQ02-P3QU-130036 | 567 | [Sampling System For Block 3,4]_Installation & Erection Manual | FI | 2018-11-23 | 2019-02-23 | 2018-11-26 | 2018-11-26 | MRT-DS-REC-TT-180901-FC | FC | 0 | 2018-12-03 | 180901-FC STAMPED | FC | 0 | A | SUPPORT | SAMPLING SYSTEM | 2018-11-22 | 2018-12-13
DHI | 기계기술 | 김희정 | MRT-DN05-P2QU-130001 | 568 | [Sampling System For Block 2]_Commissioning Manual | FA | 2018-11-23 | 2019-02-23 | 2021-02-09 | 2021-02-09 | MRT-DS-REC-TT-210003 | FC | 1 | 2021-03-11 | DEEMED APPROVAL | FC | 1 | A | SUPPORT | SAMPLING SYSTEM | 2018-11-22 | 2018-12-13
DHI | 기계기술 | 김희정 | MRT-DN05-P3QU-130001 | 569 | [Sampling system For Block 3, 4]_Commissioning Manual | FA | 2018-11-23 | 2019-02-23 | 2021-02-09 | 2021-02-09 | MRT-DS-REC-TT-210003 | FC | 1 | 2021-03-11 | DEEMED APPROVAL | FC | 1 | A | SUPPORT | SAMPLING SYSTEM | 2018-11-22 | 2018-11-15
DHI | 기계기술 | 김희정 | MRT-CQ02-P2QU-130035 | 570 | [Sampling System_For Block 2]_O&M MANUAL | FI | 2018-04-30 | 2018-11-30 | 2018-11-15 | 2018-12-03 | MRT-DS-REC-TT-180373-FC | FC | 0 | 2018-12-07 | 180373-FC STAMPED | FC | 0 | A | SUPPORT | SAMPLING SYSTEM | 2018-05-10 | 2018-11-15
DHI | 기계기술 | 김희정 | MRT-CQ02-P3QU-130035 | 571 | [Sampling System_For Block 3,4]_O&M MANUAL | FI | 2018-04-30 | 2018-11-30 | 2018-11-15 | 2018-12-03 | MRT-DS-REC-TT-180373-FC | FC | 0 | 2018-12-07 | 180373-FC STAMPED | FC | 0 | A | SUPPORT | SAMPLING SYSTEM | 2018-05-10 | 2017-12-07
DHI | 배관기술 | 김근유 | MRT-DE00-P0ZEN-140001 | 572 | [Piping General]_Piping material specification | FA | 2017-08-31 | 2017-11-30 | 2019-01-14 | 2019-01-14 | MRT-DS-REC-TT-180939-FC | FC | 3 | 2019-01-15 | 180939-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING | 2017-08-31 | 2017-12-07
DHI | 배관기술 | 김근유 | MRT-CV03-P0ZEN-140002 | 573 | [Piping General]_Piping Insulation Specification | FA | 2017-08-31 | 2017-11-30 | 2019-03-28 | 2019-03-29 | MRT-DS-REC-TT-190060-FC | FC | 3 | 2019-03-30 | 190060-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING | 2017-08-31 | 2019-01-02
DHI | 배관기술 | 김근유 | MRT-DE00-P0ZEN-140002 | 574 | [Piping General]_Material Specification for GRP | FA | 2018-12-31 | 2019-01-31 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180934-FC | FC | 0 | 2019-01-05 | 180934-FC STAMPED | FC | 0 | A | MECHANICAL | BOP PIPING | 2018-12-20 | 2019-01-02
DHI | 배관기술 | 김근유 | MRT-CC05-P0ZEN-140001 | 575 | [Piping General]_Product Detail Drawing for GRP | FA | 2018-12-31 | 2019-01-31 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180934-FC | FC | 0 | 2019-01-05 | 180934-FC STAMPED | FC | 0 | A | MECHANICAL | BOP PIPING | 2018-12-20 | 2019-01-02
DHI | 배관기술 | 김근유 | MRT-CC07-P0ZEN-140001 | 576 | [Piping General]_Wall thickness calculation for GRP | FA | 2018-12-31 | 2019-01-31 | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180934-FC | FC | 0 | 2019-01-05 | 180934-FC STAMPED | FC | 0 | A | MECHANICAL | BOP PIPING | 2018-12-20 | 2019-04-12
DHI | 배관기술 | 김근유 | MRT-DL03-P0ZEN-140001 | 577 | [Piping General]_Transporting, Handling & Storage Procedure for GRP Installation | FI | 2019-02-21 | 2019-04-21 | 2019-04-12 | 2019-04-15 | MRT-DS-REC-TT-190050-FC | FC | 0 | 2019-04-15 | 190050-FC STAMPED | FC | 0 | A | SUPPORT | BOP PIPING | 2019-02-21 | 2019-02-11
DHI | 배관기술 | 김근유 | MRT-DM01-P0ZEN-140001 | 578 | [Piping General]_Installation Manual for GRP | FI | 2019-02-01 | 2019-04-01 | 2019-02-11 | 2019-02-12 | MRT-DS-REC-TT-190027-FC | FC | 0 | 2019-02-14 | 190027-FC STAMPED | FC | 0 | A | SUPPORT | BOP PIPING | 2019-02-01 | 2019-05-30
DHI | 배관기술 | 김근유 | MRT-DM01-P0ZEN-140002 | 579 | [Piping General]_Hydrotest procedure for GRP installation | FI | 2019-02-21 | 2019-04-21 | 2019-05-30 | 2019-06-14 | MRT-DS-REC-TT-190123-FC | FC | 1 | 2019-06-17 | 190123-FC STAMPED | FC | 1 | A | SUPPORT | BOP PIPING | 2019-02-21 | #VALUE!
DHI | 배관기술 | 김근유 | MRT-DF04-P2ZEN-142001 | 580 | [Piping General]_Stress Analysis Report for HP & CRH Steam system Block #2 | FI | 2018-03-31 |  | 2018-04-03 | 2018-04-03 | MRT-DS-REC-TT-180274 | FI | 0 | 2018-04-16 | 213/T/MRT/REC/IV/2018 | FI | 0 | I | MECHANICAL | BOP PIPING | 2018-04-03 | #VALUE!
DHI | 배관기술 | 김근유 | MRT-DF04-P2ZEN-142002 | 581 | [Piping General]_Stress Analysis Report for HRH Steam system Block #2 | FI | 2018-03-31 |  | 2018-04-03 | 2018-04-03 | MRT-DS-REC-TT-180274 | FI | 0 | 2018-04-16 | 213/T/MRT/REC/IV/2018 | FI | 0 | I | MECHANICAL | BOP PIPING | 2018-04-03 | #VALUE!
DHI | 배관기술 | 김근유 | MRT-DF04-P2ZEN-142003 | 582 | [Piping General]_Stress Analysis Report for LP Steam system Block #2 | FI | 2018-04-30 |  | 2018-06-18 | 2018-06-18 | MRT-DS-REC-TT-180512 | FI | 1 | 2018-07-02 | 469/T/MRT/REC/VII/2018 | FI | 1 | I | MECHANICAL | BOP PIPING | 2018-04-24 | #VALUE!
DHI | 배관기술 | 김근유 | MRT-DF04-P2ZEN-142004 | 583 | [Piping General]_Stress Analysis Report for Feed water system Block #2 | FI | 2018-04-30 |  | 2018-06-18 | 2018-06-18 | MRT-DS-REC-TT-180512 | FI | 1 | 2018-07-02 | 469/T/MRT/REC/VII/2018 | FI | 1 | I | MECHANICAL | BOP PIPING | 2018-05-08 | #VALUE!
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-143001 | 584 | [Piping General]_Stress Analysis Report for HP & CRH Steam system Block #3 | FI | 2018-05-10 |  | 2018-05-29 | 2018-05-29 | MRT-DS-REC-TT-180439 | FI | 0 | 2018-06-29 | 445/T/MRT/REC/VI/2018 | FI | 0 | I | MECHANICAL | BOP PIPING | 2018-05-29 | #VALUE!
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-143002 | 585 | [Piping General]_Stress Analysis Report for HRH Steam system Block #3 | FI | 2018-05-10 |  | 2018-06-05 | 2018-06-05 | MRT-DS-REC-TT-180466 | FI | 0 | 2018-06-29 | 456/T/MRT/REC/VI/2018 | FI | 0 | I | MECHANICAL | BOP PIPING | 2018-06-05 | #VALUE!
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-143003 | 586 | [Piping General]_Stress Analysis Report for LP Steam system Block #3 | FI | 2018-05-10 |  | 2018-05-29 | 2018-05-29 | MRT-DS-REC-TT-180439 | FI | 0 | 2018-06-29 | 445/T/MRT/REC/VI/2018 | FI | 0 | I | MECHANICAL | BOP PIPING | 2018-05-29 | #VALUE!
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-143004 | 587 | [Piping General]_Stress Analysis Report for Feed water system Block #3 | FI | 2018-05-10 |  | 2018-06-05 | 2018-06-05 | MRT-DS-REC-TT-180466 | FI | 0 | 2018-06-29 | 456/T/MRT/REC/VI/2018 | FI | 0 | I | MECHANICAL | BOP PIPING | 2018-06-05 | #VALUE!
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-144001 | 588 | [Piping General]_Stress Analysis Report for HP & CRH Steam system Block #4 | FI | 2018-05-31 |  | 2018-09-19 | 2018-09-19 | MRT-DS-REC-TT-180790 | FI | 1 | 2018-11-14 | 1014/T/MRT/REC/XI/2018 | FI | 1 | I | MECHANICAL | BOP PIPING | 2018-06-12 | #VALUE!
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-144002 | 589 | [Piping General]_Stress Analysis Report for HRH Steam system Block #4 | FI | 2018-05-31 |  | 2018-09-19 | 2018-09-19 | MRT-DS-REC-TT-180790 | FI | 1 | 2018-11-14 | 1014/T/MRT/REC/XI/2018 | FI | 1 | I | MECHANICAL | BOP PIPING | 2018-06-19 | #VALUE!
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-144003 | 590 | [Piping General]_Stress Analysis Report for LP Steam system Block #4 | FI | 2018-05-31 |  | 2018-06-18 | 2018-06-18 | MRT-DS-REC-TT-180513 | FI | 0 | 2018-07-03 | 495/T/MRT/REC/VII/2018 | FI | 0 | I | MECHANICAL | BOP PIPING | 2018-06-18 | #VALUE!
DHI | 배관기술 | 김근유 | MRT-DF04-P3ZEN-144004 | 591 | [Piping General]_Stress Analysis Report for Feed water system Block #4 | FI | 2018-05-31 |  | 2018-09-19 | 2018-09-19 | MRT-DS-REC-TT-180790 | FI | 1 | 2018-11-14 | 1014/T/MRT/REC/XI/2018 | FI | 1 | I | MECHANICAL | BOP PIPING | 2018-06-19 | 2018-02-13
DHI | 배관기술 | 김근유 | MRT-XN00-P0ZEN-140001 | 592 | [Piping General]_Manual Valve List | FA | 2017-10-30 | 2018-02-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-01-22 | 180932-FC STAMPED | FC | 4 | A | MECHANICAL | BOP PIPING | 2017-11-01 | 2018-03-23
DHI | 배관기술 | 김근유 | MRT-XL00-P0ZEN-140001 | 593 | [Piping General]_Piping Line List | FA | 2017-10-30 | 2018-02-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2018-08-03 | 180225-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING | 2017-10-30 | 2018-02-13
DHI | 배관기술 | 김근유 | MRT-XL00-P0ZEN-140002 | 594 | [Piping General]_Piping Specialty List | FA | 2017-11-30 | 2018-02-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-01-22 | 180932-FC STAMPED | FC | 4 | A | MECHANICAL | BOP PIPING | 2017-12-07 | 2018-04-27
DHI | 배관기술 | 김근유 | MRT-XK00-P0ZEN-140001 | 595 | [Piping General]_Typical Installation Drawing for Pipe Support | FA | 2018-02-28 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2018-08-25 | 180355-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING | 2018-02-28 | 2018-04-13
DHI | 배관기술 | 김근유 | MRT-XH01-P0UZT-140001 | 596 | [Yard_Piping]_Key Plan for Piping Arrangement Drawing | FA | 2017-12-30 | 2018-03-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2018-09-05 | 180310-FC STAMPED | FC | 2 | A | MECHANICAL | BOP PIPING | 2017-12-21 | 2018-04-27
DHI | 배관기술 | 김근유 | MRT-XH01-P0UZT-140000 | 597 | [Yard_Piping]_Piping Arrangement Drawing for Yard area | FA | 2018-02-28 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-03-12 | 190031-FC STAMPED | FC | 2 | A | MECHANICAL | BOP PIPING | 2018-02-28 | 2018-07-26
DHI | 배관기술 | 김근유 | MRT-XH01-P2UMA-142000 | 598 | [Steam Turbine Building_Piping]_Piping Arrangement Drawing for Block 2 STG Building Area | FA | 2018-02-28 | 2018-05-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2018-08-03 | 681/T/MRT/REC/VII/2018 | FC | 1 | A | MECHANICAL | BOP PIPING | 2018-04-13 | 2018-11-21
DHI | 배관기술 | 김근유 | MRT-XH01-P3UMA-143000 | 599 | [Steam Turbine Building_Piping]_Piping Arrangement Drawing for Block 3 STG Building Area | FA | 2018-06-15 | 2018-08-14 | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240032 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6019.0 | AB | Z1 | A | MECHANICAL | BOP PIPING | 2018-07-26 | 2018-11-09
DHI | 배관기술 | 김근유 | MRT-XH01-P3UMA-144000 | 600 | [Steam Turbine Building_Piping]_Piping Arrangement Drawing for Block 4 STG Building Area | FA | 2018-07-20 | 2018-09-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2024-02-29 | MTW-AS-C-LT-24.4987.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-09-04 | 2018-04-13
DHI | 배관기술 | 김근유 | MRT-XH01-P2ULY-142000 | 601 | [Pipe Rack_Piping]_Piping Arrangement Drawing for Block 2 Piperack area | FA | 2017-12-30 | 2018-03-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-11-25 | 190216-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING | 2017-12-21 | 2018-04-13
DHI | 배관기술 | 김근유 | MRT-XH01-P3ULY-143000 | 602 | [Pipe Rack_Piping]_Piping Arrangement Drawing for Block 3 Piperack area | FA | 2017-12-30 | 2018-03-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2024-02-29 | MTW-AS-C-LT-24.4987.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2017-12-21 | 2018-04-13
DHI | 배관기술 | 김근유 | MRT-XH01-P3ULY-144000 | 603 | [Pipe Rack_Piping]_Piping Arrangement Drawing for Block 4 Piperack area | FA | 2017-12-30 | 2018-03-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2024-02-29 | MTW-AS-C-LT-24.4987.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2017-12-21 | 2018-11-19
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2LBA-142000 | 604 | [Steam and Bypass system(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-04-30 |  | 2024-05-14 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | 2024-05-20 | MTW-AS-C-LT-24.5268.0 | AB | Z1 | C | MECHANICAL | BOP PIPING | 2018-04-27 | 2019-03-25
DHI | 배관기술 | 김근유 | MRT-XJ00-P2LBA-145000 | 605 | [Steam and Bypass system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2024-05-14 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | 2024-05-20 | MTW-AS-C-LT-24.5268.0 | AB | Z1 | C | MECHANICAL | BOP PIPING | 2019-02-20 | 2019-03-08
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LBA-143000 | 606 | [Steam and Bypass system(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-05-31 |  | 2024-05-14 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | 2024-09-20 | MTW-AS-C-LT-24.5759.0 | AB | Z1 | A | MECHANICAL | BOP PIPING | 2018-06-21 | 2019-03-26
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LBA-146000 | 607 | [Steam and Bypass system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2024-10-18 | 2024-10-18 | MRT-DS-REC-TT-240016 | AB | Z1 | 2024-12-13 | MTW-AS-C-LT-24.6064.0 | AB | Z1 | A | MECHANICAL | BOP PIPING | 2019-02-22 | 2019-04-19
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LBA-144000 | 608 | [Steam and Bypass system(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-06-30 |  | 2024-05-14 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | 2024-09-20 | MTW-AS-C-LT-24.5759.0 | AB | Z1 | A | MECHANICAL | BOP PIPING | 2018-07-24 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LBA-147000 | 609 | [Steam and Bypass system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-15 | 2019-05-15 | 2024-10-18 | 2024-10-18 | MRT-DS-REC-TT-240016 | AB | Z1 | 2024-12-13 | MTW-AS-C-LT-24.6064.0 | AB | Z1 | A | MECHANICAL | BOP PIPING | 2019-03-29 | 2018-11-30
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2LCM-142000 | 610 | [Steam Drain System(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-05-25 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-01-24 | 200009-FC STAMPED | FC | 2A | A | MECHANICAL | BOP PIPING | 2018-05-31 | 2019-03-26
DHI | 배관기술 | 김근유 | MRT-XJ00-P2LCM-145000 | 611 | [Steam Drain System(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-12-07 | 200088-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING | 2019-02-22 | 2019-03-13
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LCM-143000 | 612 | [Steam Drain System(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-06-25 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-07-27 | 2019-03-26
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LCM-146000 | 613 | [Steam Drain System(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-02-22 | 2019-04-19
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LCM-144000 | 614 | [Steam Drain System(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-08-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-08-29 | 2019-04-09
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LCM-147000 | 615 | [Steam Drain System(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-15 | 2019-05-15 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-15 | 2019-05-30
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2MAA-142000 | 616 | [ST Misc system(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2019-04-30 | 2019-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-02-19 | 200017-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING | 2019-05-17 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P2MAA-145000 | 617 | [ST Misc system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-12-07 | 200088-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING | 2019-03-25 | 2019-05-30
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3MAA-143000 | 618 | [ST Misc system(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2019-04-30 | 2019-05-31 | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-05-17 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3MAA-146000 | 619 | [ST Misc system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-01 | 2019-05-30
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3MAA-144000 | 620 | [ST Misc system(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2019-04-30 | 2019-05-31 | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-05-17 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3MAA-147000 | 621 | [ST Misc system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-01 | 2019-07-17
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P0LBG-141000 | 622 | [Aux Steam System(Common)_Piping]_Piping ISO drawing_LB | FI | 2018-08-31 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-09-07 | 2019-03-25
DHI | 배관기술 | 김근유 | MRT-XJ00-P0LBG-140000 | 623 | [Aux Steam System(Common)_Piping]_Piping ISO drawing_SB | FI | 2019-02-28 | 2019-03-29 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2019-12-17 | 190238-FC STAMPED | FC | 1A | A | MECHANICAL | BOP PIPING | 2019-02-22 | 2018-11-30
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2LBG-142000 | 624 | [Aux Steam System(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-05-18 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-01-24 | 200009-FC STAMPED | FC | 2A | A | MECHANICAL | BOP PIPING | 2018-05-31 | 2019-03-25
DHI | 배관기술 | 김근유 | MRT-XJ00-P2LBG-145000 | 625 | [Aux Steam System(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-08-15 | 190178-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING | 2019-02-22 | 2019-02-21
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LBG-143000 | 626 | [Aux Steam System(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-06-18 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-08-30 | 2019-03-26
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LBG-146000 | 627 | [Aux Steam System(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2024-10-18 | 2024-10-18 | MRT-DS-REC-TT-240016 | AB | Z1 | 2024-12-13 | MTW-AS-C-LT-24.6064.0 | AB | Z1 | A | MECHANICAL | BOP PIPING | 2019-02-22 | 2019-04-19
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LBG-144000 | 628 | [Aux Steam System(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-07-18 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-08-30 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LBG-147000 | 629 | [Aux Steam System(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-15 | 2019-05-15 | 2024-10-18 | 2024-10-18 | MRT-DS-REC-TT-240016 | AB | Z1 | 2024-12-13 | MTW-AS-C-LT-24.6064.0 | AB | Z1 | A | MECHANICAL | BOP PIPING | 2019-03-25 | 2018-11-30
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2LCA-142000 | 630 | [Condensate system(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-05-31 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-01-24 | 200009-FC STAMPED | FC | 2C | A | MECHANICAL | BOP PIPING | 2018-06-27 | 2019-03-28
DHI | 배관기술 | 김근유 | MRT-XJ00-P2LCA-145000 | 631 | [Condensate system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-12-07 | 200088-FC STAMPED | FC | 2B | A | MECHANICAL | BOP PIPING | 2019-03-05 | 2019-02-28
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LCA-143000 | 632 | [Condensate system(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-06-30 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-07-27 | 2019-03-28
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LCA-146000 | 633 | [Condensate system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2025-01-17 | 2025-01-17 | MRT-DS-REC-TT-250004 | AB | Z0 | 2025-01-23 | MTW-AS-C-LT-25.6149.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-04 | 2019-04-19
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LCA-144000 | 634 | [Condensate system(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-08-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-08-29 | 2019-05-28
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LCA-147000 | 635 | [Condensate system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-15 | 2019-05-15 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-08 | 2018-11-30
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2LAB-142000 | 636 | [Feedwater system(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-05-18 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-01-24 | 200009-FC STAMPED | FC | 2A | A | MECHANICAL | BOP PIPING | 2018-05-31 | 2019-01-24
DHI | 배관기술 | 김근유 | MRT-XJ00-P2LAB-145000 | 637 | [Feedwater system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-08-15 | 190177-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING | 2018-12-21 | 2019-02-25
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LAB-143000 | 638 | [Feedwater system(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-06-18 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-06-27 | 2019-03-25
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LAB-146000 | 639 | [Feedwater system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-02-21 | 2019-04-19
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3LAB-144000 | 640 | [Feedwater system(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-07-18 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-07-25 | 2019-04-04
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LAB-147000 | 641 | [Feedwater system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-15 | 2019-05-15 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-02-26 | 2019-07-17
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P0GHC-140001 | 642 | [Make-up Water System_Piping]_Piping ISO drawing_LB | FI | 2018-05-30 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-07-16 | 2019-03-28
DHI | 배관기술 | 김근유 | MRT-XJ00-P0GHC-141000 | 643 | [Make-up Water System_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2021-03-26 | 210018-FC STAMPED | FC | 1D | 1 | MECHANICAL | BOP PIPING | 2019-03-08 | 2018-06-12
DHI | 배관기술 | 김근유 | MRT-XJ00-P2PAB-140001 | 644 | [Cooling Water System(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-01-31 | 2018-05-04 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-09-27 | 190198-FC STAMPED | FC | 4A | A | MECHANICAL | BOP PIPING | 2018-01-25 | 2019-04-01
DHI | 배관기술 | 김근유 | MRT-XJ00-P2PAB-145000 | 645 | [Cooling Water System(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-09-17 | 190171-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING | 2019-02-01 | 2018-06-12
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-140001 | 646 | [Cooling Water System(For Block 3, 4)_Piping]_Piping ISO drawing_LB | FI | 2018-01-31 | 2018-05-04 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-01-25 | 2019-04-01
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-146000 | 647 | [Cooling Water System(For Block 3, 4)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-02-01 | 2019-04-01
DHI | 배관기술 | 김근유 | MRT-XJ00-P2PAB-142200 | 648 | [Cooling Water Miscellaneous System(For Block 2)_Piping]_Piping ISO drawing | FI | 2019-02-01 | 2019-02-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2021-03-26 | 210018-FC STAMPED | FC | 1B | 1 | MECHANICAL | BOP PIPING | 2019-02-01 | 2019-04-01
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-143200 | 649 | [Cooling Water Miscellaneous System(For Block 3)_Piping]_Piping ISO drawing | FI | 2019-02-01 | 2019-02-28 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-02-01 | 2019-04-01
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-144200 | 650 | [Cooling Water Miscellaneous System(For Block 4)_Piping]_Piping ISO drawing | FI | 2019-02-01 | 2019-02-28 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-02-01 | 2018-06-21
DHI | 배관기술 | 김근유 | MRT-XJ00-P2PAB-142100 | 651 | [Aux Cooling Water System(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-02-28 | 2018-05-04 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-11-15 | 190226-FC STAMPED | FC | 3B | A | MECHANICAL | BOP PIPING | 2018-03-12 | 2019-03-25
DHI | 배관기술 | 김근유 | MRT-XJ00-P2PAB-145100 | 652 | [Aux Cooling Water System(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-09-17 | 190171-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING | 2019-02-15 | 2018-06-21
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-143100 | 653 | [Aux Cooling Water System(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-02-28 | 2018-05-04 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-03-12 | 2019-03-25
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-146100 | 654 | [Aux Cooling Water System(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-02-15 | 2018-06-21
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-144100 | 655 | [Aux Cooling Water System(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-02-28 | 2018-05-04 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-03-12 | 2019-03-25
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PAB-147100 | 656 | [Aux Cooling Water System(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-02-28 | 2019-05-15 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-02-15 | 2018-11-30
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P2PGB-142000 | 657 | [Closed cooling water system(For Block 2)_Piping]_Piping ISO drawing_LB | FI | 2018-05-18 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2022-11-25 | 220023-FC STAMPED | FC | 2C | A | MECHANICAL | BOP PIPING | 2018-05-31 | 2019-04-04
DHI | 배관기술 | 김근유 | MRT-XJ00-P2PGB-145000 | 658 | [Closed cooling water system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2018-12-21 | 2019-03-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-11-19 | 200083-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING | 2019-02-28 | 2019-02-26
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3PGB-143000 | 659 | [Closed cooling water system(For Block 3)_Piping]_Piping ISO drawing_LB | FI | 2018-06-18 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-07-27 | 2019-03-28
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PGB-146000 | 660 | [Closed cooling water system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-01-31 | 2019-03-29 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-04 | 2019-04-19
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P3PGB-144000 | 661 | [Closed cooling water system(For Block 4)_Piping]_Piping ISO drawing_LB | FI | 2018-07-18 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-08-31 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3PGB-147000 | 662 | [Closed cooling water system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-15 | 2019-05-15 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-01 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P2QC-145000 | 663 | [Chemical dosing system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2021-03-26 | 210018-FC STAMPED | FC | 1B | 1 | MECHANICAL | BOP PIPING | 2019-03-29 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3QC-146000 | 664 | [Chemical dosing system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-29 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3QC-147000 | 665 | [Chemical dosing system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-29 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P2QU-145000 | 666 | [Sampling system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2024-01-03 | MTW-AS-C-LT-24.4759.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-25 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3QU-146000 | 667 | [Sampling system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-25 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3QU-147000 | 668 | [Sampling system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-25 | 2019-07-11
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P0GKB-140001 | 669 | [Potable water system_Piping]_Piping ISO drawing_LB | FI | 2018-05-30 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-05-31 | 2019-04-09
DHI | 배관기술 | 김근유 | MRT-XJ00-P0GKB-141000 | 670 | [Potable water system_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2021-07-01 | 210044-FC STAMPED | FC | 1E | A | MECHANICAL | BOP PIPING | 2019-03-15 | 2019-07-11
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P0GHD-140001 | 671 | [Service water system_Piping]_Piping ISO drawing_LB | FI | 2018-05-30 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-06-05 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P0GHD-141000 | 672 | [Service water system_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2021-07-01 | 210044-FC STAMPED | FC | 1E | A | MECHANICAL | BOP PIPING | 2019-03-25 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P2SCA-145000 | 673 | [Compressed air system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-09-19 | 190196-FC STAMPED | FC | 1 | A | MECHANICAL | BOP PIPING | 2019-04-01 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3SCA-146000 | 674 | [Compressed air system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-01 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3SCA-147000 | 675 | [Compressed air system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-01 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P2QFB-145000 | 676 | [Instrument air system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2021-03-26 | 210018-FC STAMPED | FC | 1C | 1 | MECHANICAL | BOP PIPING | 2019-03-29 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3QFB-146000 | 677 | [Instrument air system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-29 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3QFB-147000 | 678 | [Instrument air system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-29 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P2SCB-145000 | 679 | [Service air system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2021-11-23 | 210059-FC STAMP | FC | 1E | A | MECHANICAL | BOP PIPING | 2019-03-21 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3SCB-146000 | 680 | [Service air system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-01 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P3SCB-147000 | 681 | [Service air system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-29 | 2019-05-28
DHI | 배관기술 | 김근유 | MRT-XJ00-P2MAV-145000 | 682 | [Clean & Dirty oil system(For Block 2)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2021-06-21 | 210042-FC STAMPED | FC | 1C | A | MECHANICAL | BOP PIPING | 2019-04-08 | 2019-05-28
DHI | 배관기술 | 김근유 | MRT-XJ00-P3MAV-146000 | 683 | [Clean & Dirty oil system(For Block 3)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-08 | 2019-05-28
DHI | 배관기술 | 김근유 | MRT-XJ00-P3MAV-147000 | 684 | [Clean & Dirty oil system(For Block 4)_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5396.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-08 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P0QJA-141000 | 685 | [N2 Gas system_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2020-03-07 | 200027-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING | 2019-03-25 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P0EKG-141000 | 686 | [Fuel gas supply system_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2020-03-07 | 200027-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING | 2019-03-29 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P0EGD-141000 | 687 | [Fuel oil supply system_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2020-03-07 | 200027-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING | 2019-03-29 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P0MKG-141000 | 688 | [H2 Gas system_Piping]_Piping ISO drawing_SB | FI | 2019-04-30 | 2019-05-31 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2020-12-07 | 200088-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING | 2019-03-29 | 2019-07-11
DHI | 보일러생산설계 | 김건휘 | MRT-XJ00-P0GMA-140001 | 689 | [Waste Water Transfer system_Piping]_Piping ISO drawing_LB | FI | 2018-08-31 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-12-08 | MTW-AS-C-LT-23.4681.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2018-09-06 | 2019-04-29
DHI | 배관기술 | 김근유 | MRT-XJ00-P0GMA-141000 | 690 | [Waste Water Transfer system_Piping]_Piping ISO drawing_SB | FI | 2019-03-29 | 2019-04-30 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2021-03-26 | 210018-FC STAMPED | FC | 1D | 1 | MECHANICAL | BOP PIPING | 2019-04-02 | 2019-06-21
DHI | 배관기술 | 김근유 | MRT-XJ00-P0QCH-140000 | 691 | [Electro Chlorination_Piping]_Piping ISO drawing | FI | 2019-05-17 | 2019-06-21 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2022-04-16 | 220005-FC STAMP | FC | 1B | 1 | MECHANICAL | BOP PIPING | 2019-05-28 | 2019-05-31
DHI | 배관기술 | 김근유 | MRT-XJ00-P0LAA-140000 | 692 | [Aux Boiler Miscellaneous System_Piping]_Piping ISO drawing | FI | 2019-05-24 | 2019-06-30 | 2023-03-15 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | 2020-03-07 | 200027-FC STAMPED | FC | 1B | A | MECHANICAL | BOP PIPING | 2019-05-21 | 2020-01-16
DHI | 배관기술 | 김근유 | MRT-XJ00-P2LB-142000 | 693 | [Steam Blowing(For Blcok2)_Piping]_Piping ISO drawing_LB | FI | 2019-11-15 |  | 2022-05-23 | 2022-05-23 | MRT-DS-REC-TT-220006 | FC | 1C | 2022-05-23 | 220006-FC STAMP | FC | 1C | A | MECHANICAL | BOP PIPING | 2019-11-11 | 2020-01-16
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LB-143000 | 694 | [Steam Blowing(For Blcok3)_Piping]_Piping ISO drawing_LB | FI | 2019-11-15 |  | 2020-04-09 |  | MRT-DS-REC-TT-200035-FC | FC | 1A | 2019-11-11 | 190224-FC STAMPED | FI | 0 | A | MECHANICAL | BOP PIPING | 2019-11-11 | 2020-01-16
DHI | 배관기술 | 김근유 | MRT-XJ00-P3LB-144000 | 695 | [Steam Blowing(For Blcok4)_Piping]_Piping ISO drawing_LB | FI | 2019-11-15 |  | 2020-04-09 |  | MRT-DS-REC-TT-200035-FC | FC | 1A | 2019-11-11 | 190224-FC STAMPED | FI | 0 | A | MECHANICAL | BOP PIPING | 2019-11-11 | 2019-04-05
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LBA-142000 | 696 | Pipe Support for Steam and Bypass System (Block 2) | FI | 2019-03-21 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-03-09 | 200025-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING | 2019-03-21 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LBA-143000 | 697 | Pipe Support for Steam and Bypass System (Block 3) | FI | 2019-04-17 |  | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240034 | AB | Z1 | 2024-11-22 | MTW-AS-C-LT-24.5985.0 | AB | Z1 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LBA-144000 | 698 | Pipe Support for Steam and Bypass System (Block 4) | FI | 2019-04-17 |  | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240034 | AB | Z1 | 2024-11-22 | MTW-AS-C-LT-24.5985.0 | AB | Z1 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LCM-142000 | 699 | Pipe Support for Steam Drain System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-10-20 | 200077-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LCM-143000 | 700 | Pipe Support for Steam Drain System (Block 3) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LCM-144000 | 701 | Pipe Support for Steam Drain System (Block 4) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LCA-142000 | 702 | Pipe Support for Condensate System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-12-16 | 190239-FC STAMPED | FC | 2 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LCA-143000 | 703 | Pipe Support for Condensate System (Block 3) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LCA-144000 | 704 | Pipe Support for Condensate System (Block 4) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LAB-142000 | 705 | Pipe Support for Feedwater System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-03-09 | 200025-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LAB-143000 | 706 | Pipe Support for Feedwater System (Block 3) | FI | 2019-04-17 |  | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240034 | AB | Z1 | 2024-11-22 | MTW-AS-C-LT-24.5985.0 | AB | Z1 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LAB-144000 | 707 | Pipe Support for Feedwater System (Block 4) | FI | 2019-04-17 |  | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240034 | AB | Z1 | 2024-11-22 | MTW-AS-C-LT-24.5985.0 | AB | Z1 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LBG-142000 | 708 | Pipe Support for Aux Steam System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-12-16 | 190239-FC STAMPED | FC | 2 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LBG-143000 | 709 | Pipe Support for Aux Steam System (Block 3) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LBG-144000 | 710 | Pipe Support for Aux Steam System (Block 4) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-09-02
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P0LBG-141000 | 711 | Pipe Support for AUX Steam System_Common | FI | 2019-07-01 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-07-01 | 2019-09-02
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P0GHC-140001 | 712 | Pipe Support for Make-up Water System | FI | 2019-07-01 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-07-01 | 2019-04-05
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2PAB-142000 | 713 | Pipe Support for Cooling Water System (Block 2) | FI | 2019-03-22 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2021-04-27 | 050/T/MRT/REC/IV/2021 | FC | 4 | I | MECHANICAL | BOP PIPING | 2019-03-22 | 2019-04-05
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3PAB-143000 | 714 | Pipe Support for Cooling Water System (Block 3) | FI | 2019-03-22 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-22 | 2019-04-05
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4PAB-144000 | 715 | Pipe Support for Cooling Water System (Block 4) | FI | 2019-03-22 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-03-22 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2ACW-142000 | 716 | Pipe Support for Aux Cooling Water System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2020-03-09 | 200025-FC STAMPED | FC | 3 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3ACW-143000 | 717 | Pipe Support for Aux Cooling Water System (Block 3) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4ACW-144000 | 718 | Pipe Support for Aux Cooling Water System (Block 4) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-09-02
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2PGB-142000 | 719 | Pipe Support for Closed Cooling Water System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-12-16 | 190239-FC STAMPED | FC | 2 | A | MECHANICAL | BOP PIPING | 2019-06-19 | 2019-09-02
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3PGB-143000 | 720 | Pipe Support for Closed Cooling Water System (Block 3) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-06-19 | 2019-09-02
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4PGB-144000 | 721 | Pipe Support for Closed Cooling Water System (Block 4) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-06-19 | 2019-09-02
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P0GHD-140001 | 722 | Pipe Support for Service water system | FI | 2019-07-01 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-07-01 | 2019-09-02
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P0GMA-140001 | 723 | Pipe Support for Waste Water Transfer system | FI | 2019-07-01 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-07-01 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P0QCH-140001 | 724 | Pipe Support for Electro Chlorniation System (Common) | FI | 2020-03-03 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2020-03-04 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2MAM-142000 | 725 | Pipe Support for Miscellinious System (Block 2) | FI | 2019-04-17 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | 2019-12-16 | 190239-FC STAMPED | FC | 2 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3MAM-142000 | 726 | Pipe Support for Miscellinious System (Block 3) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-23 | 2019-05-08
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4MAM-142000 | 727 | Pipe Support for Miscellinious System (Block 4) | FI | 2019-04-17 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-04-23 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LB0-140001 | 728 | Pipe Support for Steam blowing (Block 2) | FI | 2020-01-17 |  | 2020-01-20 | 2020-01-22 | MRT-DS-REC-TT-200005-FC | FI | 0 | 2020-01-22 | 200005-FC STAMPED | FI | 0 | A | MECHANICAL | BOP PIPING | 2020-01-20 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LB0-140001 | 729 | Pipe Support for Steam blowing (Block 3) | FI | 2020-01-21 |  | 2020-01-21 | 2020-01-22 | MRT-DS-REC-TT-200006-FC | FI | 0 | 2020-01-22 | 200006-FC STAMPED | FI | 0 | A | MECHANICAL | BOP PIPING | 2020-01-21 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LB0-140001 | 730 | Pipe Support for Steam blowing (Block 4) | FI | 2020-01-21 |  | 2020-01-21 | 2020-01-22 | MRT-DS-REC-TT-200006-FC | FI | 0 | 2020-01-22 | 200006-FC STAMPED | FI | 0 | A | MECHANICAL | BOP PIPING | 2020-01-21 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LBA-141000 | 731 | Small Bore Pipe Support for Steam and Bypass System (Block 2) | FI | 2019-12-06 |  | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220053 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3771.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-12-05 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LBA-141000 | 732 | Small Bore Pipe Support for Steam and Bypass System (Block 3) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-12-05 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LBA-141100 | 733 | Small Bore Pipe Support for Steam and Bypass System (Block 4) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-12-05 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LBA-141100 | 734 | Small Bore Pipe Support for Steam Drain System (Block 2) | FI | 2019-12-06 |  | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220053 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3771.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-12-05 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LBA-141100 | 735 | Small Bore Pipe Support for Steam Drain System (Block 3) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-12-05 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LBA-141200 | 736 | Small Bore Pipe Support for Steam Drain System (Block 4) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-12-05 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LBG-141000 | 737 | Small Bore Pipe Support for Aux Steam System (Block 2) | FI | 2019-12-06 |  | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220053 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3771.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-12-05 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P2LCA-141000 | 738 | Small Bore Pipe Support for Condensate System (Block 2) | FI | 2019-12-06 |  | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220053 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3771.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-12-05 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LCE-141000 | 739 | Small Bore Pipe Support for Condensate System (Block 3) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-12-05 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P4LCE-142000 | 740 | Small Bore Pipe Support for Condensate System (Block 4) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-12-05 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P3LAB-141100 | 741 | Small Bore Pipe Support for Feed water System (Block 3) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2024-06-19 | MTW-AS-C-LT-24.5398.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-12-05 | #VALUE!
DHI | 보일러생산설계 | 김건휘 | MRT-XK00-P0EGD-141000 | 742 | Small Bore Pipe Support for Fuel Oil Supply System (Common) | FI | 2019-12-06 |  | 2023-05-31 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | 2023-11-17 | MTW-AS-C-LT-23.4620.0 | AB | Z0 | A | MECHANICAL | BOP PIPING | 2019-12-05 | 2018-02-13
DHI | 계측제어기술 | 최민석 | MRT-XW01-P0ZEN-161001 | 743 | I&C General Design Criteria | FA | 2017-11-01 | 2018-02-02 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180218-FC | FC | 5 | 2018-09-03 | 180218-FC STAMPED | FC | 5 | A | I&C | BOP I&C | 2017-09-29 | 2018-07-27
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2ZEN-161601 | 744 | Plant Master Control Diagram(For Block 2) | FA | 2018-05-11 | 2018-07-31 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-05-30 | 2018-07-27
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3ZEN-161601 | 745 | Plant Master Control Diagram(For Block 3, 4) | FA | 2018-05-11 | 2018-07-31 | 2024-10-24 | 2024-10-24 | MRT-DS-REC-TT-240021 | AB | Z0 | 2024-12-04 | MTW-AS-C-LT-24.6034.0 | AB | Z0 | A | I&C | BOP I&C | 2018-05-30 | 2018-04-06
DHI | 계측제어기술 | 최민석 | MRT-YU04-P0ZEN-161012 | 746 | Plant Control Block Diagram(For Block 2, 3 & 4) | FA | 2017-11-24 | 2018-03-23 | 2018-07-27 | 2018-08-21 | MRT-DS-REC-TT-180289-FC | FC | 4 | 2018-09-07 | 180289-FC STAMPED | FC | 4 | A | I&C | BOP I&C | 2017-11-27 | 2018-03-21
DHI | 계측제어기술 | 최민석 | MRT-MA01-P2ZEN-161011 | 747 | Plant Control System Configuration Diagram(For Block 2) | FA | 2017-12-01 | 2018-03-02 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-08-13 | 180200-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-09-29 | 2018-03-21
DHI | 계측제어기술 | 최민석 | MRT-MA01-P3ZEN-161011 | 748 | Plant Control System Configuration Diagram(For Block 3, 4) | FA | 2017-12-01 | 2018-03-02 | 2024-10-25 | 2024-10-25 | MRT-DS-REC-TT-240022 | AB | Z0 | 2024-12-04 | MTW-AS-C-LT-24.6033.0 | AB | Z0 | A | I&C | BOP I&C | 2017-09-29 | 2018-03-27
DHI | 계측제어기술 | 최민석 | MRT-YF01-P2ZEN-161013 | 749 | Plant Protection & Interlock Diagram(For Block 2) | FA | 2017-12-21 | 2018-03-22 | 2018-07-27 | 2018-07-30 | MRT-DS-REC-TT-180226-FC | FC | 3 | 2018-08-03 | 180226-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-12-22 | 2018-03-27
DHI | 계측제어기술 | 최민석 | MRT-YF01-P3ZEN-161013 | 750 | Plant Protection & Interlock Diagram(For Block 3, 4) | FA | 2017-12-21 | 2018-03-22 | 2018-07-27 | 2018-07-30 | MRT-DS-REC-TT-180226-FC | FC | 3 | 2018-08-03 | 180226-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-12-22 | 2018-03-22
DHI | 계측제어기술 | 고경환 | MRT-YR05-P0ZEN-161016 | 751 | Master & Slave Clock Concept Diagram (For Block 2, 3&4) | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-20 | MRT-DS-REC-TT-180206-FC | FC | 2 | 2018-09-05 | 180206-FC STAMPED | FC | 2 | A | I&C | BOP I&C | 2017-11-15 | 2018-07-27
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CJD-161401 | 752 | Plant Start-up & Shutdown Sequence Diagram - Symbol & Legend | FA | 2018-05-20 | 2018-09-21 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-05-18 | 2018-07-27
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CJD-161402 | 753 | Plant Start-up & Shutdown Sequence Diagram for Start-up(For Block 2) | FA | 2018-05-20 | 2018-09-21 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-05-18 | 2018-07-27
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CJD-161402 | 754 | Plant Start-up & Shutdown Sequence Diagram for Start-up(For Block 3, 4) | FA | 2018-05-20 | 2018-09-21 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-05-18 | 2018-07-27
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CJD-161403 | 755 | Plant Start-up & Shutdown Sequence Diagram for Shutdown(For Block 2) | FA | 2018-05-20 | 2018-09-21 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-05-18 | 2018-07-27
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CJD-161403 | 756 | Plant Start-up & Shutdown Sequence Diagram for Shutdown(For Block 3, 4) | FA | 2018-05-20 | 2018-09-21 | 2024-10-24 | 2024-10-24 | MRT-DS-REC-TT-240021 | AB | Z0 | 2024-12-04 | MTW-AS-C-LT-24.6034.0 | AB | Z0 | A | I&C | BOP I&C | 2018-05-18 | 2018-03-21
DHI | 계측제어기술 | 최민석 | MRT-MA02-P2ZEN-161015 | 757 | 3rd Party Data-link Interface Concept Diagram(For Block 2) | FA | 2017-11-15 | 2018-03-16 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-08-13 | 180200-FC STAMPED | FC | 2 | A | I&C | BOP I&C | 2017-11-16 | 2018-03-21
DHI | 계측제어기술 | 최민석 | MRT-MA02-P3ZEN-161015 | 758 | 3rd Party Data-link Interface Concept Diagram(For Block 3, 4) | FA | 2017-11-15 | 2018-03-16 | 2024-10-25 | 2024-10-25 | MRT-DS-REC-TT-240022 | AB | Z0 | 2024-12-04 | MTW-AS-C-LT-24.6033.0 | AB | Z0 | A | I&C | BOP I&C | 2017-11-16 | 2018-05-11
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CBA-161201 | 759 | Control Logic Diagram - Symbol & Legend(For Block 2,3&4) | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-09-15 | 180376-FC STAMPED | FC | 1 | A | I&C | BOP I&C | 2018-01-31 | 2018-05-11
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CBA-161202 | 760 | Control Logic Diagram - Typical Function(For Block 2,3&4) | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2019-01-22 | 180376-FC STAMPED | FC | 1 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161203 | 761 | [HP&IP&LP Steam System(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-12-03 | 180582-FC STAMPED | FC | 2 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161203 | 762 | [HP&IP&LP Steam System(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161204 | 763 | [Aux Steam System(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-12-03 | 180582-FC STAMPED | FC | 2 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161204 | 764 | [Aux Steam System(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161205 | 765 | [Feedwater system(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161205 | 766 | [Feedwater system(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161206 | 767 | [Condensate system(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161206 | 768 | [Condensate system(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161207 | 769 | [Cooling Water System(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161207 | 770 | [Cooling Water System(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161208 | 771 | [Steam Drain System(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161208 | 772 | [Steam Drain System(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161209 | 773 | [Closed cooling water system(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161209 | 774 | [Closed cooling water system(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161210 | 775 | [Condensate Vacuum System(For Block 2)] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161210 | 776 | [Condensate Vacuum System(For Block 3, 4)] Control Logic Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161211 | 777 | [Miscellaneous System(For Block 2)] Control Logic Diagram | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161211 | 778 | [Miscellaneous System(For Block 3, 4)] Control Logic Diagram | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CBA-161212 | 779 | [Interface with GT & ST Control System(For Block 2)] Control Logic Diagram | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CBA-161212 | 780 | [Interface with GT & ST Control System(For Block 3, 4)] Control Logic Diagram | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CBA-161221 | 781 | [Make-up Water System] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-12-03 | 180582-FC STAMPED | FC | 2 | A | I&C | BOP I&C | 2018-01-31 | 2018-09-06
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CBA-161222 | 782 | [Service water system] Control Logic Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-05-11
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CGA-161301 | 783 | Control Loop Diagram - Symbol & Legend(For Block 2,3&4) | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-09-15 | 180376-FC STAMPED | FC | 1 | A | I&C | BOP I&C | 2018-01-31 | 2018-05-11
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CGA-161302 | 784 | Control Loop Diagram - Typical Function(For Block 2,3&4) | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-09-15 | 180376-FC STAMPED | FC | 1 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161303 | 785 | [HP&IP&LP Steam System(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161303 | 786 | [HP&IP&LP Steam System(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161304 | 787 | [Aux Steam System(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161304 | 788 | [Aux Steam System(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161305 | 789 | [Feedwater system(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161305 | 790 | [Feedwater system(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161306 | 791 | [Condensate system(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161306 | 792 | [Condensate system(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161307 | 793 | [Cooling Water System(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161307 | 794 | [Cooling Water System(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161308 | 795 | [Steam Drain System(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161308 | 796 | [Steam Drain System(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161309 | 797 | [Closed cooling water system(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161309 | 798 | [Closed cooling water system(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161310 | 799 | [Condensate Vacuum System(For Block 2)] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161310 | 800 | [Condensate Vacuum System(For Block 3, 4)] Control Loop Diagram for BOP | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161311 | 801 | [Miscellaneous System(For Block 2)] Control Loop Diagram | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161311 | 802 | [Miscellaneous System(For Block 3, 4)] Control Loop Diagram | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P2CGA-161312 | 803 | [Interface with GT & ST Control System(For Block 2)] Control Loop Diagram | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P3CGA-161312 | 804 | [Interface with GT & ST Control System(For Block 3, 4)] Control Loop Diagram | FA | 2018-01-19 | 2018-06-29 | 2024-10-21 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6040.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CGA-161321 | 805 | [Make-up Water System] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-12-03 | 180582-FC STAMPED | FC | 2 | A | I&C | BOP I&C | 2018-01-31 | 2018-07-12
DHI | 계측제어기술 | 최민석 | MRT-YF00-P0CGA-161322 | 806 | [Service water system] Control Loop Diagram for BOP | FA | 2018-01-05 | 2018-06-29 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3769.0 | AB | Z0 | A | I&C | BOP I&C | 2018-01-31 | 2018-04-03
DHI | 계측제어기술 | 최민석 | MRT-CV03-P2ZEN-165201 | 807 | [Control Valves(DHI For Block 2)] Technical Specification & Datasheet for Control Valve - BOP | FA | 2018-03-30 | 2018-06-30 | 2023-01-02 | 2023-01-02 | MRT-DS-REC-TT-220052 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3770.0 | AB | Z0 | A | I&C | BOP I&C | 2017-12-21 | 2018-04-03
DHI | 계측제어기술 | 최민석 | MRT-CV03-P3ZEN-165201 | 808 | [Control Valves(DHI For Block 3, 4)] Technical Specification & Datasheet for Control Valve - BOP | FA | 2018-03-30 | 2018-06-30 | 2024-11-12 | 2024-11-12 | MRT-DS-REC-TT-240026 | AB | Z0 | 2018-12-17 | 180802-FC STAMPED | FC | 4 | A | I&C | BOP I&C | 2017-12-21 | 2020-03-11
DHI | 계측제어기술 | 최민석 | MRT-GT00-P2ZEN-167001 | 809 | TECHNICAL SPECIFICATION FOR GAS TURBINE CONTROL SYSTEM (BLOCK 2 ABB MODIFICATION) | FA | 2020-02-20 | 2020-06-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2021-06-23 | DEEMED APPROVAL | FC | 1 | A | I&C | BOP I&C | 2020-02-06 | 2020-10-14
DHI | 계측제어기술 | 최민석 | MRT-GT00-P3ZEN-167001 | 810 | TECHNICAL SPECIFICATION FOR GAS TURBINE CONTROL SYSTEM (BLOCK 3,4 SIEMENS MODIFICATION) | FA | 2020-04-20 | 2020-08-28 | 2025-02-17 | 2025-02-17 | MRT-DS-REC-TT-250007 | AB | Z1 | 2025-02-13 | MTW-AS-C-LT-25.6199.0 | AB | Z0 | B | I&C | BOP I&C | 2020-09-04 | #VALUE!
DHI | 계측제어기술 | 최민석 | MRT-YR00-P0ZEN-163001 | 810 | TECHNICAL SPECIFICATION FOR STG CABLE | FA | 2023-04-14 | 2023-08-11 | 2023-04-11 | 2023-04-11 | MRT-DS-REC-TT-230009 | FA | A | [5 empty] | I&C | BOP I&C | 2023-04-11 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162101 | 811 | Typical Elementary Wiring Diagram - Index | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162102 | 812 | Typical Elementary Wiring Diagram for Motor Operated Valve (Internal MCC) | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162103 | 813 | Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Double Coil SOV) | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162104 | 814 | Typical Elementary Wiring Diagram for Pneumatic Shut-off Valve (Single Coil SOV) | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162105 | 815 | Typical Elementary Wiring Diagram for Modulating Control Actuator | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162106 | 816 | Typical Elementary Wiring Diagram for Analog Input | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162107 | 817 | Typical Elementary Wiring Diagram for Analog Output | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162108 | 818 | Typical Elementary Wiring Diagram for Binary Input | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162109 | 819 | Typical Elementary Wiring Diagram for Binary Output | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162110 | 820 | Typical Elementary Wiring Diagram for MV SWGR BUS TIE-1 | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162111 | 821 | Typical Elementary Wiring Diagram for MV SWGR BUS TIE-2 | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162112 | 822 | Typical Elementary Wiring Diagram for MV SWGR INCOMER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162113 | 823 | Typical Elementary Wiring Diagram for MV SWGR MOTOR FEEDER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162114 | 824 | Typical Elementary Wiring Diagram for MV SWGR NON MOTOR FEEDER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162115 | 825 | Typical Elementary Wiring Diagram for LV SWGR BUS TIE-1 | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162116 | 826 | Typical Elementary Wiring Diagram for LV SWGR BUS TIE-2 | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162117 | 827 | Typical Elementary Wiring Diagram for LV SWGR INCOMER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162118 | 828 | Typical Elementary Wiring Diagram for LV SWGR MCC MOTOR FEEDER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162119 | 829 | Typical Elementary Wiring Diagram for LV SWGR NON MOTOR FEEDER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-03-23
DHI | 계측제어기술 | 최민석 | MRT-YS00-P0ZEN-162120 | 830 | Typical Elementary Wiring Diagram for MCC INCOMER | FA | 2017-11-15 | 2018-03-16 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180205-FC | FC | 3 | 2018-08-13 | 180205-FC STAMPED | FC | 3 | A | I&C | BOP I&C | 2017-11-17 | 2018-07-06
DHI | 계측제어기술 | 최민석 | MRT-YL01-P2ZEN-161051 | 831 | DCS IO Database(For Block 2) | FA | 2017-12-01 | 2018-05-01 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | 2018-09-28 | 180574-FC STAMPED | FC | 3 | A | I&C | DCS | 2017-12-15 | 2018-07-06
DHI | 계측제어기술 | 최민석 | MRT-YL01-P3ZEN-161051 | 832 | DCS IO Database(For Block 3, 4) | FA | 2017-12-14 | 2018-05-01 | 2024-11-14 | 2024-11-14 | MRT-DS-REC-TT-240027 | AB | Z0 | 2024-12-04 | MTW-AS-C-LT-24.6032.0 | AB | Z0 | A | I&C | DCS | 2017-12-15 | 2018-02-13
DHI | 계측제어기술 | 고경환 | MRT-YD06-P2ZEN-161014 | 833 | DCS Power Distribution Concept Diagram(For Block 2) | FA | 2017-11-10 | 2018-02-09 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180103-FC | FC | 1 | 2018-09-05 | 180103-FC STAMPED | FC | 1 | A | I&C | DCS | 2017-11-13 | 2018-02-13
DHI | 계측제어기술 | 고경환 | MRT-YD06-P3ZEN-161014 | 834 | DCS Power Distribution Concept Diagram(For Block 3, 4) | FA | 2017-11-10 | 2018-02-09 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180103-FC | FC | 1 | 2018-09-05 | 180103-FC STAMPED | FC | 1 | A | I&C | DCS | 2017-11-13 | 2018-06-12
DHI | 계측제어기술 | 고경환 | MRT-CV03-P0ZEN-163101 | 835 | [DCS(For Block 2,3&4)] Functional Design Specification for Graphic | FA | 2018-02-21 | 2018-05-22 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2018-10-15 | 180484-FC STAMPED | FC | 1 | A | I&C | DCS | 2018-02-23 | 2018-06-04
DHI | 계측제어기술 | 고경환 | MRT-CV03-P0ZEN-163102 | 836 | [DCS(For Block 2,3&4)] Functional Design Specification for Hardware | FA | 2018-02-21 | 2018-05-22 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2018-09-29 | 180461-FC STAMPED | FC | 1 | A | I&C | DCS | 2018-02-23 | 2018-06-04
DHI | 계측제어기술 | 고경환 | MRT-CV03-P0ZEN-163103 | 837 | [DCS(For Block 2,3&4)] Functional Design Specification for Software | FA | 2018-02-21 | 2018-05-22 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2018-09-29 | 180461-FC STAMPED | FC | 1 | A | I&C | DCS | 2018-02-23 | 2018-06-07
DHI | 계측제어기술 | 고경환 | MRT-YE03-P2ZEN-163104 | 838 | [DCS(For Block 2)] Grounding Concept & Detail Drawing | FA | 2018-02-21 | 2018-05-22 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS | 2018-03-23 | 2018-06-22
DHI | 계측제어기술 | 고경환 | MRT-YE03-P3ZEN-163104 | 839 | [DCS(For Block 3, 4)] Grounding Concept & Detail Drawing | FA | 2018-03-23 | 2018-06-21 | 2024-11-18 | 2024-11-18 | MRT-DS-REC-TT-240035 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6024.0 | AB | Z1 | A | I&C | DCS | 2018-03-27 | 2018-06-22
DHI | 계측제어기술 | 고경환 | MRT-MA02-P2ZEN-163105 | 840 | [DCS(For Block 2)] LAN Configuration Diagram | FA | 2018-02-21 | 2018-05-22 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS | 2018-03-23 | 2018-06-22
DHI | 계측제어기술 | 고경환 | MRT-MA02-P3ZEN-163105 | 841 | [DCS(For Block 3, 4)] LAN Configuration Diagram | FA | 2018-03-23 | 2018-06-21 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS | 2018-03-27 | 2018-06-07
DHI | 계측제어기술 | 고경환 | MRT-YD06-P2ZEN-163106 | 842 | [DCS(For Block 2)] Equipment Power Distribution Diagram | FA | 2018-02-28 | 2018-05-29 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS | 2018-03-23 | 2018-08-22
DHI | 계측제어기술 | 고경환 | MRT-YD06-P3ZEN-163106 | 843 | [DCS(For Block 3, 4)] Equipment Power Distribution Diagram | FA | 2018-03-30 | 2018-06-28 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5824.0 | AB | Z0 | A | I&C | DCS | 2018-04-04 | 2018-07-06
DHI | 계측제어기술 | 고경환 | MRT-CV03-P0ZEN-163107 | 844 | [DCS(For Block 2,3&4)] Specification & Drawing for CCR Emergency Push Button | FA | 2018-03-04 | 2018-06-02 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS | 2018-03-23 | 2018-06-12
DHI | 계측제어기술 | 고경환 | MRT-CV03-P0ZEN-163108 | 845 | [DCS(For Block 2,3&4)] Technical Specification for Time Synchronization | FA | 2018-03-04 | 2018-06-02 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS | 2018-03-23 | 2018-07-17
DHI | 계측제어기술 | 고경환 | MRT-YD07-P2ZEN-163109 | 846 | [DCS(For Block 2)] IO & Module Allocation | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS | 2018-04-26 | 2018-07-17
DHI | 계측제어기술 | 고경환 | MRT-YD07-P3ZEN-163109 | 847 | [DCS(For Block 3, 4)] IO & Module Allocation | FA | 2018-05-12 | 2018-08-10 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS | 2018-04-26 | 2018-07-17
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163110 | 848 | [DCS(For Block 2)] Outline & Detail Drawing for Console, Computer, Printer Desk | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-12-15 | 142/T/MRT/REC/XII/2020 | FC | 3 | A | I&C | DCS | 2018-04-26 | 2018-07-17
DHI | 계측제어기술 | 고경환 | MRT-YR05-P3ZEN-163110 | 849 | [DCS(For Block 3&4)] Outline & Detail Drawing for Console, Computer, Printer Desk | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS | 2018-04-26 | 2018-07-17
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163111 | 850 | [DCS(For Block 2)] Outline & Detail Drawing for Network Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS | 2018-04-26 | 2018-07-17
DHI | 계측제어기술 | 고경환 | MRT-YR05-P3ZEN-163111 | 851 | [DCS(For Block 3&4)] Outline & Detail Drawing for Network Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS | 2018-04-26 | 2018-07-17
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163112 | 852 | [DCS(For Block 2)] Outline & Detail Drawing for Marshalling and Relay Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS | 2018-04-26 | 2018-07-17
DHI | 계측제어기술 | 고경환 | MRT-YR05-P3ZEN-163112 | 853 | [DCS(For Block 3&4)] Outline & Detail Drawing for Marshalling and Relay Cabinet | FA | 2018-04-12 | 2018-07-11 | 2023-05-09 | 2023-05-09 | MRT-DS-REC-TT-230010 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5833.0 | AB | Z0 | A | I&C | DCS | 2018-04-26 | 2018-07-17
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163113 | 854 | [DCS(For Block 2)] Outline & Detail Drawing for Power Distribution Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-12-15 | 142/T/MRT/REC/XII/2020 | FC | 3 | A | I&C | DCS | 2018-04-26 | 2018-07-17
DHI | 계측제어기술 | 고경환 | MRT-YR05-P3ZEN-163113 | 855 | [DCS(For Block 3&4)] Outline & Detail Drawing for Power Distribution Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5824.0 | AB | Z0 | A | I&C | DCS | 2018-04-26 | 2018-07-17
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163114 | 856 | [DCS(For Block 2)] Outline & Detail Drawing for System Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2020-05-15 | 085/T/MRT/REC/V/2020 | FC | 2 | A | I&C | DCS | 2018-04-26 | 2018-07-17
DHI | 계측제어기술 | 고경환 | MRT-YR05-P3ZEN-163114 | 857 | [DCS(For Block 3&4)] Outline & Detail Drawing for System Cabinet | FA | 2018-04-12 | 2018-07-11 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS | 2018-04-26 | 2018-07-27
DHI | 계측제어기술 | 고경환 | MRT-YR05-P0ZEN-163115 | 858 | [DCS(For Block 2, 3&4)] HMI Graphic Drawing | FA | 2018-06-08 | 2018-09-06 | 2023-05-09 | 2023-05-09 | MRT-DS-REC-TT-230010 | AB | Z0 | 2018-10-06 | 180535-FC STAMPED | FC | 0 | A | I&C | DCS | 2018-06-25 | 2018-07-27
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163116 | 859 | [DCS(For Block 2)] Internal Cable Connection Diagram | FI | 2018-06-21 | 2018-09-19 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2018-09-28 | 180553-FC STAMPED | FC | 0 | A | I&C | DCS | 2018-06-29 | 2018-09-10
DHI | 계측제어기술 | 고경환 | MRT-YV02-P3ZEN-163116 | 860 | [DCS(For Block 3, 4)] Internal Cable Connection Diagram | FI | 2018-07-21 | 2018-10-19 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS | 2018-07-18 | 2018-07-06
DHI | 계측제어기술 | 고경환 | MRT-CV03-P3ZEN-163118 | 861 | [DCS(For Block 3, 4)] Specification & Drawings for Large Screen Display | FA | 2018-04-03 | 2018-07-02 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5835.0 | AB | Z0 | A | I&C | DCS | 2018-04-26 | 2018-09-10
DHI | 계측제어기술 | 고경환 | MRT-YL15-P3ZEN-163117 | 862 | [DCS(For Block 3, 4)] Cable list | FI | 2018-07-21 | 2018-10-19 | 2018-09-10 | 2018-11-21 | MRT-DS-REC-TT-180625-FC | FC | 0 | 2018-11-26 | 180625-FC STAMPED | FC | 0 | A | I&C | DCS | 2018-07-18 | 2018-07-27
DHI | 계측제어기술 | 고경환 | MRT-YR05-P2ZEN-163117 | 863 | [DCS(For Block 2)] Cable List | FI | 2018-06-21 | 2018-09-19 | 2018-07-27 | 2018-09-24 | MRT-DS-REC-TT-180553-FC | FC | 0 | 2018-09-28 | 180553-FC STAMPED | FC | 0 | A | I&C | DCS | 2018-06-29 | 2018-09-06
DHI | 계측제어기술 | 신동인 | MRT-YL00-P2ZEN-165101 | 864 | [Field Instrument(DHI For Block 2)] Field Instrument List for BOP | FA | 2018-03-30 | 2018-06-30 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220049 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3768.0 | AB | Z0 | A | I&C | FIELD INSTRUMENT | 2018-04-13 | 2018-09-06
DHI | 계측제어기술 | 신동인 | MRT-YL00-P3ZEN-165101 | 865 | [Field Instrument(DHI For Block 3, 4)] Field Instrument List for BOP | FA | 2018-03-30 | 2018-06-30 | 2024-11-26 | 2024-11-26 | MRT-DS-REC-TT-240041 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6027.0 | AB | Z1 | A | I&C | FIELD INSTRUMENT | 2018-04-13 | 2018-07-04
DHI | 계측제어기술 | 신동인 | MRT-CV03-P2ZEN-165102 | 866 | [Field Instrument(DHI For Block 2)] Technical Specification & Datasheet for Process Transmitter - BOP | FA | 2018-03-30 | 2018-06-30 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220049 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3768.0 | AB | Z0 | A | I&C | FIELD INSTRUMENT | 2018-04-06 | 2018-07-04
DHI | 계측제어기술 | 신동인 | MRT-CV03-P3ZEN-165102 | 867 | [Field Instrument(DHI For Block 3, 4)] Technical Specification & Datasheet for Process Transmitter - BOP | FA | 2018-03-30 | 2018-06-30 | 2024-11-26 | 2024-11-26 | MRT-DS-REC-TT-240041 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6027.0 | AB | Z1 | A | I&C | FIELD INSTRUMENT | 2018-04-06 | 2018-09-21
DHI | 계측제어기술 | 신동인 | MRT-CV03-P2ZEN-165103 | 868 | [Field Instrument(DHI For Block 2)] Technical Specification & Datasheet for Local Instrument - BOP | FA | 2018-03-30 | 2018-06-30 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220049 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3768.0 | AB | Z0 | A | I&C | FIELD INSTRUMENT | 2018-04-06 | 2018-09-21
DHI | 계측제어기술 | 신동인 | MRT-CV03-P3ZEN-165103 | 869 | [Field Instrument(DHI For Block 3, 4)] Technical Specification & Datasheet for Local Instrument - BOP | FA | 2018-03-30 | 2018-06-30 | 2024-11-26 | 2024-11-26 | MRT-DS-REC-TT-240041 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6027.0 | AB | Z1 | A | I&C | FIELD INSTRUMENT | 2018-04-06 | 2018-07-04
DHI | 계측제어기술 | 신동인 | MRT-CV03-P2ZEN-165104 | 870 | [Field Instrument(DHI For Block 2)] Technical Specification & Datasheet for Flow Element - BOP | FA | 2018-03-30 | 2018-06-30 | 2022-12-27 | 2022-12-27 | MRT-DS-REC-TT-220049 | AB | Z0 | 2023-03-07 | MTW-AS-C-LT-23.3768.0 | AB | Z0 | A | I&C | FIELD INSTRUMENT | 2018-04-06 | 2018-07-04
DHI | 계측제어기술 | 신동인 | MRT-CV03-P3ZEN-165104 | 871 | [Field Instrument(DHI For Block 3, 4)] Technical Specification & Datasheet for Flow Element - BOP | FA | 2018-03-30 | 2018-06-30 | 2024-01-08 | 2024-01-08 | MRT-DS-REC-TT-240002 | AB | Z0 | 2024-02-07 | MTW-AS-C-LT-24.4898.0 | AB | Z0 | A | I&C | FIELD INSTRUMENT | 2018-04-06 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA06-P0UCA-180101 | 872 | [Central control building]_Calculation Sheet | FA | 2017-10-18 | 2017-12-31 | 2018-09-13 | 2018-09-17 | MRT-DS-REC-TT-170157-FC | FC | 2 | 2018-10-23 | 170757-FC STAMPED | FC | 2 | A | CIVIL | CONTROL BUILDING | 2017-09-29 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-XB02-P0UCA-180102 | 873 | [Central control building]_Pile Arrangement Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-09-29 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180103 | 874 | [Central control building]_Foundation & Column Arrangement Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-09-29 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA02-P0UCA-180104 | 875 | [Central control building]_Foundation Re-Bar Schedule | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-09-29 | 2018-01-08
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180105 | 876 | [Central control building]_Interior Finish Schedule | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-09-29 | 2018-03-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180106 | 877 | [Central control building]_Door & Window Schedule | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-11-27 | 2018-01-08
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180107 | 878 | [Central control building]_Ground & First Floor Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-09-29 | 2018-01-08
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180108 | 879 | [Central control building]_Second & Roof Floor Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-09-29 | 2018-01-08
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180112 | 880 | [Central control building]_Main Section | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-09-29 | 2018-01-08
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180113 | 881 | [Central control building]_Side Elevation | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-09-29 | 2018-03-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180114 | 882 | [Central control building]_Enlarged Staircase Plan & Section | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-11-27 | 2018-03-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180115 | 883 | [Central control building]_Enlarged Toilet Plan & Elevation | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-11-27 | 2018-03-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180116 | 884 | [Central control building]_Enlarged Locker, Kitchen and Ablution Room Plan & Elevation | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-11-27 | 2018-03-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180117 | 885 | [Central control building]_Wall Section | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-11-27 | 2018-08-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180119 | 886 | [Central control building]_Ceiling Plan | FA | 2018-04-01 | 2018-09-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2018-03-22 | 2018-07-05
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UCA-180120 | 887 | [Central control building]_Architectural Misc. Detail | FA | 2018-04-01 | 2018-09-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2018-03-22 | 2018-02-27
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180122 | 888 | [Central control building]_Ground & First Floor Framing Plan | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-10-27 | 2018-02-27
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180123 | 889 | [Central control building]_Second & Roof Floor Framing Plan | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-10-27 | 2018-02-27
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180127 | 890 | [Central control building]_Line Framing Elevation | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-10-27 | 2018-02-27
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180128 | 891 | [Central control building]_Row Framing Elevation | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-10-27 | 2018-02-27
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180129 | 892 | [Central control building]_Staircase Framing Plan & Elevation | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-12-22 | 2018-07-19
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UCA-180132 | 893 | [Central control building]_Panel Support Frame Layout & Detail | FA | 2018-02-01 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2018-01-24 | 2018-07-19
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UCA-180133 | 894 | [Central control building]_Structual Misc. Detail | FA | 2018-02-01 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2018-01-24 | 2018-02-27
DHI | 건축기술 | 정윤철 | MRT-CA02-P0UCA-180134 | 895 | [Central control building]_Column Re-Bar Schedule | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-10-27 | 2018-02-27
DHI | 건축기술 | 정윤철 | MRT-CA02-P0UCA-180135 | 896 | [Central control building]_Beam & Girder Re-Bar Schedule | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-10-27 | 2018-02-27
DHI | 건축기술 | 정윤철 | MRT-CA02-P0UCA-180136 | 897 | [Central control building]_Slab & Misc. Re-Bar Schedule | FA | 2017-12-27 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-10-27 | 2018-02-14
DHI | 건축기술 | 정윤철 | MRT-CA05-P0UCA-180161 | 898 | [Central control building_Plumbing]_Plumbing Equipment Schedule | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-11-24 | 2018-02-14
DHI | 건축기술 | 정윤철 | MRT-CA05-P0UCA-180162 | 899 | [Central control building_Plumbing]_Plumbing Schematic Diagram | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-11-24 | 2018-02-14
DHI | 건축기술 | 정윤철 | MRT-CA05-P0UCA-180163 | 900 | [Central control building_Plumbing]_Plumbing Plan | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-11-24 | 2018-02-14
DHI | 건축기술 | 정윤철 | MRT-CA05-P0UCA-180164 | 901 | [Central control building_Plumbing]_Enlarged Plumbing Plan | FA | 2017-12-01 | 2018-03-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | CONTROL BUILDING | 2017-11-24 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA06-P0UMA-180001 | 902 | [Steam Turbine Building]_Calculation of Piling & Foundation | FA | 2017-10-18 | 2017-12-31 | 2018-07-27 | 2018-08-21 | MRT-DS-REC-TT-180307-FC | FC | 3 | 2018-09-10 | 180307-FC STAMPED | FC | 3 | A | CIVIL | STG BUILDING | 2017-09-28 | 2018-02-14
DHI | 건축기술 | 정윤철 | MRT-CA06-P0UMA-180002 | 903 | [Steam Turbine Building]_Calculation of Super Structure | FA | 2017-11-02 | 2018-01-16 | 2018-07-27 | 2018-11-01 | MRT-DS-REC-TT-180255-FC | FC | 4 | 2018-11-09 | 180255-FC STAMPED | FC | 4 | A | CIVIL | STG BUILDING | 2017-10-27 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA06-P0UMA-180003 | 904 | [Steam Turbine Building]_Loading Data for Super Structure | FA | 2017-10-18 | 2017-12-31 | 2018-07-27 | 2018-11-01 | MRT-DS-REC-TT-180255-FC | FC | 3 | 2018-11-09 | 180255-FC STAMPED | FC | 3 | A | CIVIL | STG BUILDING | 2017-09-28 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-XB02-P0UMA-180004 | 905 | [Steam Turbine Building]_Pile Arrangement Plan | FI | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-09-28 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UMA-180005 | 906 | [Steam Turbine Building]_Foundation Arrangement Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-09-28 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UMA-180006 | 907 | [Steam Turbine Building]_Foundation Longitudinal Section | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-09-28 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UMA-180007 | 908 | [Steam Turbine Building]_Foundation Rebar Detail | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-09-28 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180008 | 909 | [Steam Turbine Building]_Interior Finish Schedule | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-09-28 | 2018-02-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180009 | 910 | [Steam Turbine Building]_Door & Window Schedule | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-11-14 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180010 | 911 | [Steam Turbine Building]_Ground & Mezzanine Floor Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-09-28 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180011 | 912 | [Steam Turbine Building]_Operating & Roof Floor Plan | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-09-28 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180013 | 913 | [Steam Turbine Building]_Main Section | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-09-28 | 2017-12-22
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180014 | 914 | [Steam Turbine Building]_Side Elevation | FA | 2017-10-18 | 2017-12-31 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-09-28 | 2018-02-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180015 | 915 | [Steam Turbine Building]_Ground Floor Plan (Enlarged) | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-11-14 | 2018-02-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180016 | 916 | [Steam Turbine Building]_Mezzanine Floor Plan (Enlarged) | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-11-14 | 2018-02-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180017 | 917 | [Steam Turbine Building]_Operating Floor Plan (Enlarged) | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-11-14 | 2018-02-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180019 | 918 | [Steam Turbine Building]_Roof Floor Plan (Enlarged) | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-11-14 | 2018-02-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180021 | 919 | [Steam Turbine Building]_Wall Section | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-11-14 | 2018-02-06
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180022 | 920 | [Steam Turbine Building]_Stair Plan & Section | FA | 2017-11-15 | 2018-01-29 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-11-14 | 2018-07-10
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180023 | 921 | [Steam Turbine Building]_Misc. Platform Plan & Section | FA | 2018-03-01 | 2018-07-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2018-02-21 | 2018-07-10
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180024 | 922 | [Steam Turbine Building]_Architectural Misc. Detail | FA | 2018-03-01 | 2018-07-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2018-02-21 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180025 | 923 | [Steam Turbine Building]_Column Arrangement Plan | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180026 | 924 | [Steam Turbine Building]_Column Schedule | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UMA-180027 | 925 | [Steam Turbine Building]_Ground Floor Framing Plan (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180028 | 926 | [Steam Turbine Building]_Mezzanine Floor Framing Plan (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180029 | 927 | [Steam Turbine Building]_Operating Floor Framing Plan (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180030 | 928 | [Steam Turbine Building]_Lower Roof Floor Framing Plan (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180031 | 929 | [Steam Turbine Building]_Crane Floor Framing Plan (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180032 | 930 | [Steam Turbine Building]_Roof Floor Framing Plan (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180033 | 931 | [Steam Turbine Building]_Line Framing Elevation (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180034 | 932 | [Steam Turbine Building]_Row Framing Elevation (Enlarged) | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-02-14
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180035 | 933 | [Steam Turbine Building]_Girt Arrangement Plan | FA | 2017-12-01 | 2018-02-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-11-28 | 2018-02-14
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180036 | 934 | [Steam Turbine Building]_Girt Line Elevation (Enlarged) | FA | 2017-12-01 | 2018-02-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-11-28 | 2018-02-14
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180037 | 935 | [Steam Turbine Building]_Girt Row Elevation (Enlarged) | FA | 2017-12-01 | 2018-02-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-11-28 | 2018-02-14
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180039 | 936 | [Steam Turbine Building]_Misc. Platform Framing Plan & Elevation | FA | 2017-12-01 | 2018-02-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-11-28 | 2018-02-14
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180040 | 937 | [Steam Turbine Building]_Stair Framing Plan & Elevation | FA | 2017-12-01 | 2018-02-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-11-28 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180042 | 938 | [Steam Turbine Building]_Crane Girder Detail | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180043 | 939 | [Steam Turbine Building]_Connection Detail | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-05-25
DHI | 건축기술 | 정윤철 | MRT-CA01-P0UMA-180044 | 940 | [Steam Turbine Building]_Equipment Foundation & Slab Outline Plan | FA | 2018-02-01 | 2018-05-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2018-01-30 | 2018-05-25
DHI | 건축기술 | 정윤철 | MRT-CA02-P0UMA-180045 | 941 | [Steam Turbine Building]_Equipment Foundation Rebar Detail | FA | 2018-02-01 | 2018-05-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2018-01-30 | 2018-01-23
DHI | 건축기술 | 정윤철 | MRT-CA03-P0UMA-180046 | 942 | [Steam Turbine Building]_Structural Misc. Detail | FA | 2018-02-01 | 2018-05-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-10-27 | 2018-07-13
DHI | 건축기술 | 정윤철 | MRT-CA00-P0UMA-180047 | 943 | [Steam Turbine Building]_Floor Opening Schedule | FA | 2018-02-01 | 2018-07-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2018-01-30 | 2018-05-24
DHI | 건축기술 | 정윤철 | MRT-CA05-P0UMA-180061 | 944 | [Steam Turbine Building_Plumbing]_Equipment drain Schematic Diagram | FA | 2017-12-15 | 2018-05-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-12-15 | 2018-05-24
DHI | 건축기술 | 정윤철 | MRT-CA05-P0UMA-180062 | 945 | [Steam Turbine Building_Plumbing]_Equipment drain Plan | FA | 2017-12-15 | 2018-05-18 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | 2023-02-16 | MTW-AS-C-LT-23.3690.0 | AB | Z0 | A | CIVIL | STG BUILDING | 2017-12-15 | 2018-07-27
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170801 | 946 | [Air Receiver Tank Foundation(For Block 2)]_Calculation | FA | 2018-01-05 | 2018-08-26 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180367-FC | FC | 2 | 2018-08-23 | 180367-FC STAMPED | FC | 2 | A | CIVIL | AIR TANK FDN | 2018-01-08 | 2018-07-27
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170801 | 947 | [Air Receiver Tank Foundation(For Block 3, 4)]_Calculation | FA | 2018-01-05 | 2018-09-26 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180367-FC | FC | 2 | 2018-08-23 | 180367-FC STAMPED | FC | 2 | A | CIVIL | AIR TANK FDN | 2018-01-08 | 2018-07-27
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170803 | 948 | [Air Receiver Tank Foundation(For Block 2)]_Plan & Section drawing | FA | 2018-01-05 | 2018-08-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-08-23 | 180367-FC STAMPED | FC | 2 | A | CIVIL | AIR TANK FDN | 2018-01-08 | 2018-07-27
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170803 | 949 | [Air Receiver Tank Foundation(For Block 3, 4)]_Plan & Section drawing | FA | 2018-01-05 | 2018-09-26 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-08-23 | 180367-FC STAMPED | FC | 2 | A | CIVIL | AIR TANK FDN | 2018-01-08 | 2018-07-27
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UMA-170806 | 950 | [Air Receiver Tank Foundation(For Block 2)]_Re-bar Arrangement | FA | 2018-01-05 | 2018-08-26 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-08-23 | 180367-FC STAMPED | FC | 2 | A | CIVIL | AIR TANK FDN | 2018-01-08 | 2018-07-27
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UMA-170806 | 951 | [Air Receiver Tank Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2018-01-05 | 2018-09-26 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-08-23 | 180367-FC STAMPED | FC | 2 | A | CIVIL | AIR TANK FDN | 2018-01-08 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170501 | 952 | [BFP Foundation(For Block 2)]_Calculation | FA | 2017-11-02 | 2018-01-16 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180364-FC | FC | 3 | 2018-09-07 | 180364-FC STAMPED | FC | 3 | A | CIVIL | BFP FDN | 2017-12-08 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170501 | 953 | [BFP Foundation(For Block 3, 4)]_Calculation | FA | 2017-11-02 | 2018-02-11 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180364-FC | FC | 3 | 2018-09-07 | 180364-FC STAMPED | FC | 3 | A | CIVIL | BFP FDN | 2017-12-08 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UMA-170502 | 954 | [BFP Foundation(For Block 2, 3&4)] Foundation Layout | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-10-15 | 180720-FC STAMPED | FC | 4 | A | CIVIL | BFP FDN | 2017-12-08 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170503 | 955 | [BFP Foundation(For Block 2)]_Pile Arrangement Drawing | FA | 2017-11-02 | 2018-01-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-08-03 | 180219-FC STAMPED | FC | 2 | A | CIVIL | BFP FDN | 2017-12-08 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170503 | 956 | [BFP Foundation(For Block 3, 4)]_Pile Arrangement Drawing | FA | 2017-11-02 | 2018-02-11 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-08-03 | 180219-FC STAMPED | FC | 2 | A | CIVIL | BFP FDN | 2017-12-08 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170507 | 957 | [BFP Foundation(For Block 2)]_Plan drawing | FA | 2017-11-02 | 2018-08-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2020-04-06 | 200016-FC STAMPED | FC | 5 | A | CIVIL | BFP FDN | 2017-12-08 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170507 | 958 | [BFP Foundation(For Block 3, 4)]_Plan drawing | FA | 2017-11-02 | 2018-09-20 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2020-04-06 | 200016-FC STAMPED | FC | 5 | A | CIVIL | BFP FDN | 2017-12-08 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UMA-170510 | 959 | [BFP Foundation(For Block 2)]_Re-bar Arrangement | FA | 2017-11-02 | 2018-08-20 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2020-04-06 | 200016-FC STAMPED | FC | 5 | A | CIVIL | BFP FDN | 2017-12-19 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UMA-170510 | 960 | [BFP Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2017-11-02 | 2018-09-20 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2020-04-06 | 200016-FC STAMPED | FC | 5 | A | CIVIL | BFP FDN | 2017-12-19 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170601 | 961 | [CEP PIT Foundation(For Block 2)]_Calculation | FA | 2017-11-12 | 2018-01-25 | 2018-07-27 | 2018-08-15 | MRT-DS-REC-TT-180221-FC | FC | 2 | 2018-08-31 | 180221-FC STAMPED | FC | 2 | A | CIVIL | CEP FDN | 2018-01-05 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170601 | 962 | [CEP PIT Foundation(For Block 3, 4)]_Calculation | FA | 2017-11-12 | 2018-02-22 | 2018-07-27 | 2018-08-15 | MRT-DS-REC-TT-180221-FC | FC | 2 | 2018-08-31 | 180221-FC STAMPED | FC | 2 | A | CIVIL | CEP FDN | 2018-01-05 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UMA-170602 | 963 | [CEP PIT FOUNDATION]_FOUNDATION LAYOUT | FA | 2018-02-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-10-15 | 180476-FC STAMPED | FC | 2 | A | CIVIL | CEP FDN | 2018-02-12 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170603 | 964 | [CEP PIT Foundation(For Block 2)]_Pile Arrangement Drawing | FA | 2017-11-12 | 2018-01-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-08-31 | 180221-FC STAMPED | FC | 2 | A | CIVIL | CEP FDN | 2018-01-05 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170603 | 965 | [CEP PIT Foundation(For Block 3, 4)]_Pile Arrangement Drawing | FA | 2017-11-12 | 2018-02-22 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-08-31 | 180221-FC STAMPED | FC | 2 | A | CIVIL | CEP FDN | 2018-01-05 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170607 | 966 | [CEP PIT Foundation(For Block 2)]_Plan drawing | FA | 2017-11-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-22 | 231/T/MRT/REC/IV/2019 | FC | 5 | A | CIVIL | CEP FDN | 2018-01-05 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170607 | 967 | [CEP PIT Foundation(For Block 3, 4)]_Plan drawing | FA | 2017-11-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-22 | 231/T/MRT/REC/IV/2019 | FC | 5 | A | CIVIL | CEP FDN | 2018-01-05 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170608 | 968 | [CEP PIT Foundation(For Block 2)]_Sectional drawing | FA | 2017-11-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-22 | 231/T/MRT/REC/IV/2019 | FC | 5 | A | CIVIL | CEP FDN | 2018-01-05 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170608 | 969 | [CEP PIT Foundation(For Block 3, 4)]_Sectional drawing | FA | 2017-11-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-22 | 231/T/MRT/REC/IV/2019 | FC | 5 | A | CIVIL | CEP FDN | 2018-01-05 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170609 | 970 | [CEP PIT Foundation(For Block 2)]_Detail drawing | FA | 2018-01-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-08-12 | 190150-FC STAMPED | FC | 5 | A | CIVIL | CEP FDN | 2018-01-05 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170609 | 971 | [CEP PIT Foundation(For Block 3, 4)]_Detail drawing | FA | 2018-01-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-10-15 | 180701-FC STAMPED | FC | 4 | A | CIVIL | CEP FDN | 2018-01-05 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UMA-170610 | 972 | [CEP PIT Foundation(For Block 2)]_Re-bar Arrangement | FA | 2017-11-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-10-15 | 180701-FC STAMPED | FC | 3 | A | CIVIL | CEP FDN | 2018-01-31 | 2018-03-23
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UMA-170610 | 973 | [CEP PIT Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2017-11-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-10-15 | 180701-FC STAMPED | FC | 3 | A | CIVIL | CEP FDN | 2018-01-31 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170701 | 974 | [CW PIT Foundation(For Block 2)]_Calculation | FA | 2017-11-12 | 2018-01-25 | 2018-07-27 | 2018-09-14 | MRT-DS-REC-TT-180213-FC | FC | 2 | 2018-09-18 | 180213-FC STAMPED | FC | 2 | A | CIVIL | CW PIT FDN | 2018-01-05 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170701 | 975 | [CW PIT Foundation(For Block 3, 4)]_Calculation | FA | 2017-11-12 | 2018-02-22 | 2018-07-27 | 2018-09-14 | MRT-DS-REC-TT-180213-FC | FC | 2 | 2018-09-18 | 180213-FC STAMPED | FC | 2 | A | CIVIL | CW PIT FDN | 2018-01-05 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UMA-170702 | 976 | [CW PIT Foundation]_Foundation Layout | FA | 2018-02-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-28 | 180558-FC STAMPED | FC | 2 | A | CIVIL | CW PIT FDN | 2018-02-12 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170703 | 977 | [CW PIT Foundation(For Block 2)]_Pile Arrangement Drawing | FA | 2017-11-12 | 2018-01-25 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-18 | 180213-FC STAMPED | FC | 2 | A | CIVIL | CW PIT FDN | 2018-01-05 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170703 | 978 | [CW PIT Foundation(For Block 3, 4)]_Pile Arrangement Drawing | FA | 2017-11-12 | 2018-02-22 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-09-18 | 180213-FC STAMPED | FC | 2 | A | CIVIL | CW PIT FDN | 2018-01-05 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170707 | 979 | [CW PIT Foundation(For Block 2)]_Plan drawing | FA | 2017-11-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-23 | 190109-FC STAMPED | FC | 5 | A | CIVIL | CW PIT FDN | 2018-01-05 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170707 | 980 | [CW PIT Foundation(For Block 3, 4)]_Plan drawing | FA | 2017-11-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-23 | 190109-FC STAMPED | FC | 6 | A | CIVIL | CW PIT FDN | 2018-01-05 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170708 | 981 | [CW PIT Foundation(For Block 2)]_Sectional drawing | FA | 2017-11-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-23 | 190109-FC STAMPED | FC | 5 | A | CIVIL | CW PIT FDN | 2018-01-05 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170708 | 982 | [CW PIT Foundation(For Block 3, 4)]_Sectional drawing | FA | 2017-11-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-23 | 190109-FC STAMPED | FC | 6 | A | CIVIL | CW PIT FDN | 2018-01-05 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170709 | 983 | [CW PIT Foundation(For Block 2)]_Detail drawing | FA | 2018-01-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-23 | 190109-FC STAMPED | FC | 6 | A | CIVIL | CW PIT FDN | 2018-01-05 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170709 | 984 | [CW PIT Foundation(For Block 3, 4)]_Detail drawing | FA | 2018-01-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-23 | 190109-FC STAMPED | FC | 6 | A | CIVIL | CW PIT FDN | 2018-01-05 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UMA-170710 | 985 | [CW PIT Foundation(For Block 2)]_Re-bar Arrangement | FA | 2017-11-12 | 2018-03-06 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-28 | 180558-FC STAMPED | FC | 2 | A | CIVIL | CW PIT FDN | 2018-01-31 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UMA-170710 | 986 | [CW PIT Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2017-11-12 | 2018-03-06 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-03-18 | 190064-FC STAMPED | FC | 4 | A | CIVIL | CW PIT FDN | 2018-01-31 | 2017-12-08
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UHA-170001 | 987 | [HRSG Foundation(For Block 2)]_Pile calculation | FA | 2017-10-20 | 2017-12-30 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180202-FC | FC | 3 | 2018-09-05 | 180202-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN | 2017-10-23 | 2017-12-08
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UHA-170001 | 988 | [HRSG Foundation(For Block 3, 4)]_Pile calculation | FA | 2017-10-20 | 2018-01-30 | 2018-07-27 | 2018-08-03 | MRT-DS-REC-TT-180202-FC | FC | 3 | 2018-09-05 | 180202-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN | 2017-10-23 | 2017-12-08
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UHA-170002 | 989 | [HRSG Foundation]_Layout | FA | 2017-10-20 | 2017-12-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-05 | 180202-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN | 2017-10-23 | 2017-12-08
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170003 | 990 | [HRSG Foundation(For Block 2)]_Pile Arrangement Drawing | FA | 2017-10-20 | 2017-12-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-05 | 180202-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN | 2017-10-23 | 2017-12-08
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170003 | 991 | [HRSG Foundation(For Block 3, 4)]_Pile Arrangement Drawing | FA | 2017-10-20 | 2018-01-30 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-09-05 | 180202-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN | 2017-10-23 | 2017-12-08
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170004 | 992 | [HRSG Foundation(For Block 2)]_Pile Schedule | FA | 2017-10-20 | 2017-12-30 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-05 | 180202-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN | 2017-10-23 | 2017-12-08
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170004 | 993 | [HRSG Foundation(For Block 3, 4)]_Pile Schedule | FA | 2017-10-20 | 2018-01-30 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-09-05 | 180202-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN | 2017-10-23 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UHA-170005 | 994 | [HRSG Foundation(For Block 2)]_Calculation | FA | 2017-11-05 | 2018-02-16 | 2018-07-27 | 2018-09-04 | MRT-DS-REC-TT-180333-FC | FC | 3 | 2018-09-13 | 180333-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN | 2017-11-20 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UHA-170005 | 995 | [HRSG Foundation(For Block 3, 4)]_Calculation | FA | 2017-11-05 | 2018-03-16 | 2018-07-27 | 2018-09-04 | MRT-DS-REC-TT-180333-FC | FC | 3 | 2018-09-13 | 180333-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN | 2017-11-20 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170007 | 996 | [HRSG Foundation(For Block 2)]_Plan drawing | FA | 2017-11-05 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-02-02 | 190022-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN | 2017-11-20 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170007 | 997 | [HRSG Foundation(For Block 3, 4)]_Plan drawing | FA | 2017-11-05 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-02-02 | 190022-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN | 2017-11-20 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170008 | 998 | [HRSG Foundation(For Block 2)]_Sectional drawing | FA | 2017-11-05 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-08-13 | 180203-FC STAMPED | FC | 2 | A | CIVIL | HRSG FDN | 2017-11-20 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170008 | 999 | [HRSG Foundation(For Block 3, 4)]_Sectional drawing | FA | 2017-11-05 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-08-13 | 180203-FC STAMPED | FC | 2 | A | CIVIL | HRSG FDN | 2017-11-20 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170009 | 1000 | [HRSG Foundation(For Block 2)]_Detail drawing | FA | 2017-12-05 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-03-11 | 190055-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN | 2017-11-29 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170009 | 1001 | [HRSG Foundation(For Block 3, 4)]_Detail drawing | FA | 2017-12-05 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-03-11 | 190055-FC STAMPED | FC | 4 | A | CIVIL | HRSG FDN | 2017-11-29 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UHA-170010 | 1002 | [HRSG Foundation(For Block 2)]_Re-bar Arrangement | FA | 2017-11-05 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-02-02 | 190022-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN | 2017-12-15 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UHA-170010 | 1003 | [HRSG Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2017-11-05 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-02-02 | 190022-FC STAMPED | FC | 3 | A | CIVIL | HRSG FDN | 2017-12-15 | 2018-01-29
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UHA-170101 | 1004 | [HRSG MISCELLANEOUS Foundation(For Block 2)]_Calculation | FA | 2017-10-20 | 2018-02-16 | 2018-11-01 | 2018-11-09 | MRT-DS-REC-TT-180815-FC | FC | 3 | 2018-11-09 | 180815-FC STAMPED | FC | 3 | A | CIVIL | HRSG MISC FDN | 2017-11-29 | 2018-01-29
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UHA-170101 | 1005 | [HRSG MISCELLANEOUS Foundation(For Block 3, 4)]_Calculation | FA | 2017-10-20 | 2018-03-16 | 2018-11-01 | 2018-11-09 | MRT-DS-REC-TT-180815-FC | FC | 3 | 2018-11-09 | 180815-FC STAMPED | FC | 3 | A | CIVIL | HRSG MISC FDN | 2017-11-29 | 2018-01-29
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170103 | 1006 | [HRSG MISCELLANEOUS Foundation(For Block 2)]_Plan drawing | FA | 2017-10-20 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-08-12 | 190159-FC STAMPED | FC | 11 | A | CIVIL | HRSG MISC FDN | 2017-11-29 | 2018-01-29
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170103 | 1007 | [HRSG MISCELLANEOUS Foundation(For Block 3, 4)]_Plan drawing | FA | 2017-10-20 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-08-12 | 190159-FC STAMPED | FC | 11 | A | CIVIL | HRSG MISC FDN | 2017-11-29 | 2018-01-29
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UHA-170104 | 1008 | [HRSG MISCELLANEOUS Foundation(For Block 2)]_Sectional drawing | FA | 2017-10-20 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-06-19 | 190142-FC STAMPED | FC | 7 | A | CIVIL | HRSG MISC FDN | 2017-11-29 | 2018-01-29
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UHA-170104 | 1009 | [HRSG MISCELLANEOUS Foundation(For Block 3, 4)]_Sectional drawing | FA | 2017-10-20 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-06-19 | 190142-FC STAMPED | FC | 7 | A | CIVIL | HRSG MISC FDN | 2017-11-29 | 2018-01-29
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UHA-170106 | 1010 | [HRSG MISCELLANEOUS Foundation(For Block 2)]_Re-bar Arrangement | FA | 2017-10-20 | 2018-02-16 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-11 | 190095-FC STMAPED | FC | 8 | A | CIVIL | HRSG MISC FDN | 2017-12-15 | 2018-01-29
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UHA-170106 | 1011 | [HRSG MISCELLANEOUS Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2017-10-20 | 2018-03-16 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-11 | 190095-FC STMAPED | FC | 8 | A | CIVIL | HRSG MISC FDN | 2017-12-15 | 2018-10-26
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UMA-171003 | 1012 | [N2 Gas System Foundation]_Plan & Section drawing | FA | 2018-10-12 | 2018-12-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-02-11 | 190023-FC STAMPED | FC | 1 | A | CIVIL | N2 FDN | 2018-10-10 | 2018-10-26
DHI | 토목기술 | 박찬웅 | MRT-VK02-P0UMA-171006 | 1013 | [N2 Gas System Foundation]_Re-bar Arrangement | FA | 2018-10-12 | 2018-12-14 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-02-11 | 190023-FC STAMPED | FC | 1 | A | CIVIL | N2 FDN | 2018-10-10 | 2018-07-24
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UEJ-170901 | 1014 | [Clean and Dirty Oil Tank Foundation(For Block 2)]_Calculation | FA | 2018-04-27 | 2018-07-27 | 2018-08-09 | 2018-10-02 | MRT-DS-REC-TT-180650-FC | FC | 1 | 2018-10-22 | 180650-FC STAMPED | FC | 1 | A | CIVIL | OIL TANK FDN | 2018-05-03 | 2018-07-24
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UEJ-170901 | 1015 | [Clean and Dirty Oil Tank Foundation(For Block 3, 4)]_Calculation | FA | 2018-04-27 | 2018-07-27 | 2018-08-09 | 2018-10-02 | MRT-DS-REC-TT-180650-FC | FC | 1 | 2018-10-22 | 180650-FC STAMPED | FC | 1 | A | CIVIL | OIL TANK FDN | 2018-05-03 | 2018-07-24
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UEJ-170907 | 1016 | [Clean and Dirty Oil Tank Foundation(For Block 2)]_Plan & Section drawing | FA | 2018-04-27 | 2018-07-27 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2020-08-13 | 200059-FC STAMPED | FC | 3 | A | CIVIL | OIL TANK FDN | 2018-05-03 | 2018-07-24
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UEJ-170907 | 1017 | [Clean and Dirty Oil Tank Foundation(For Block 3, 4)]_Plan & Section drawing | FA | 2018-04-27 | 2018-07-27 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2020-08-13 | 200059-FC STAMPED | FC | 3 | A | CIVIL | OIL TANK FDN | 2018-05-03 | 2018-07-24
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UEJ-170910 | 1018 | [Clean and Dirty Oil Tank Foundation(For Block 2)]_Re-bar Arrangement | FA | 2018-04-27 | 2018-07-27 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-23 | 190108-FC STAMPED | FC | 2 | A | CIVIL | OIL TANK FDN | 2018-05-03 | 2018-07-24
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UEJ-170910 | 1019 | [Clean and Dirty Oil Tank Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2018-04-27 | 2018-07-27 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-23 | 190108-FC STAMPED | FC | 2 | A | CIVIL | OIL TANK FDN | 2018-05-03 | 2019-07-31
DHI | 토목기술 | 박찬웅 | MRT-CC07-P0UMA-171201 | 1020 | [Sampling System Foundation]_Calculation | FA | 2019-07-19 | 2019-09-19 | 2019-07-31 | 2019-08-02 | MRT-DS-REC-TT-190160-FC | FC | 0 | 2019-08-02 | 190160-FC STAMPED | FC | 0 | A | CIVIL | SAMPLING FDN | 2019-07-16 | 2019-08-27
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UMA-171203 | 1021 | [Sampling System Foundation]_Plan & Section & Rebar Drawing | FA | 2019-07-19 | 2019-09-19 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-08-27 | 190174-FC STAMPED | FC | 1 | A | CIVIL | SAMPLING FDN | 2019-07-16 | 2018-01-08
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170201 | 1022 | [Steam Turbine Generator Foundation(For Block 2)]_Pile calculation | FA | 2017-10-20 | 2018-01-01 | 2018-08-09 | 2018-11-15 | MRT-DS-REC-TT-180636-FC | FC | 2 | 2018-11-24 | 180636-FC STAMPED | FC | 2 | A | CIVIL | STG FDN | 2017-10-20 | 2018-01-08
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170201 | 1023 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Pile calculation | FA | 2017-10-20 | 2018-02-01 | 2018-08-09 | 2018-11-15 | MRT-DS-REC-TT-180636-FC | FC | 2 | 2018-11-24 | 180636-FC STAMPED | FC | 2 | A | CIVIL | STG FDN | 2017-10-20 | 2018-01-08
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170203 | 1024 | [Steam Turbine Generator Foundation(For Block 2)]_Pile Arrangement Drawing | FA | 2017-10-20 | 2018-01-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-07 | 180318-FC STAMPED | FC | 2 | A | CIVIL | STG FDN | 2017-10-20 | 2018-01-08
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170203 | 1025 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Pile Arrangement Drawing | FA | 2017-10-20 | 2018-02-01 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-09-07 | 180318-FC STAMPED | FC | 2 | A | CIVIL | STG FDN | 2017-10-20 | 2018-01-08
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170204 | 1026 | [Steam Turbine Generator Foundation(For Block 2)]_Pile Schedule | FA | 2017-10-20 | 2018-01-01 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-07 | 180318-FC STAMPED | FC | 2 | A | CIVIL | STG FDN | 2017-10-20 | 2018-01-08
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170204 | 1027 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Pile Schedule | FA | 2017-10-20 | 2018-02-01 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-09-07 | 180318-FC STAMPED | FC | 2 | A | CIVIL | STG FDN | 2017-10-20 | 2018-02-19
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170205 | 1028 | [Steam Turbine Generator Foundation(For Block 2)]_Calculation | FA | 2017-11-05 | 2018-02-12 | 2018-08-09 | 2018-11-15 | MRT-DS-REC-TT-180636-FC | FC | 2 | 2018-11-24 | 180636-FC STAMPED | FC | 2 | A | CIVIL | STG FDN | 2017-11-22 | 2018-02-19
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170205 | 1029 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Calculation | FA | 2017-11-05 | 2018-03-12 | 2018-08-09 | 2018-11-15 | MRT-DS-REC-TT-180636-FC | FC | 2 | 2018-11-24 | 180636-FC STAMPED | FC | 2 | A | CIVIL | STG FDN | 2017-12-12 | 2018-02-19
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170207 | 1030 | [Steam Turbine Generator Foundation(For Block 2)]_Plan drawing | FA | 2017-11-05 | 2018-02-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-08-27 | 190175-FC STAMPED | FC | 7 | A | CIVIL | STG FDN | 2017-11-22 | 2018-02-19
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170207 | 1031 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Plan drawing | FA | 2017-11-05 | 2018-03-12 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-08-27 | 190175-FC STAMPED | FC | 7 | A | CIVIL | STG FDN | 2017-12-12 | 2018-02-19
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170208 | 1032 | [Steam Turbine Generator Foundation(For Block 2)]_Sectional drawing | FA | 2017-11-05 | 2018-02-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-12-22 | 180821-FC STAMPED | FC | 4 | A | CIVIL | STG FDN | 2017-11-22 | 2018-02-19
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170208 | 1033 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Sectional drawing | FA | 2017-11-05 | 2018-03-12 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-05-28 | 324/T/MRT/REC/V/2019 | FC | 5 | A | CIVIL | STG FDN | 2017-12-12 | 2018-02-19
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UMA-170209 | 1034 | [Steam Turbine Generator Foundation(For Block 2)]_Detail drawing | FA | 2018-01-05 | 2018-03-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-15 | 190100-FC STAMPED | FC | 4 | A | CIVIL | STG FDN | 2017-11-22 | 2018-02-19
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UMA-170209 | 1035 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Detail drawing | FA | 2018-01-05 | 2018-04-12 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-15 | 190100-FC STAMPED | FC | 4 | A | CIVIL | STG FDN | 2017-12-12 | 2018-03-22
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UMA-170210 | 1036 | [Steam Turbine Generator Foundation(For Block 2)]_Re-bar Arrangement | FA | 2017-11-05 | 2018-02-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-15 | 190100-FC STAMPED | FC | 4 | A | CIVIL | STG FDN | 2018-01-12 | 2018-06-29
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UMA-170210 | 1037 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2017-11-05 | 2018-06-01 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-04-15 | 190100-FC STAMPED | FC | 4 | A | CIVIL | STG FDN | 2018-01-29 | 2018-02-19
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UMA-170211 | 1038 | [Steam Turbine Generator Foundation(For Block 2)]_Dynamic Analysis for TG Pedestal | FA | 2017-11-05 | 2018-02-12 | 2018-08-09 | 2018-11-15 | MRT-DS-REC-TT-180636-FC | FC | 2 | 2018-11-24 | 180636-FC STAMPED | FC | 2 | A | CIVIL | STG FDN | 2017-11-22 | 2018-02-19
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UMA-170211 | 1039 | [Steam Turbine Generator Foundation(For Block 3, 4)]_Dynamic Analysis for TG Pedestal | FA | 2017-11-05 | 2018-03-12 | 2018-08-09 | 2018-11-15 | MRT-DS-REC-TT-180636-FC | FC | 2 | 2018-11-24 | 180636-FC STAMPED | FC | 2 | A | CIVIL | STG FDN | 2017-12-12 | 2019-01-23
DHI | 토목기술 | 박찬웅 | MRT-CC02-P0UMA-171103 | 1040 | [Sump Pump Pit]_Plan & Section drawing | FA | 2018-11-12 | 2019-01-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-04-15 | 190098-FC STAMPED | FC | 2 | A | CIVIL | SUMP PIT | 2018-12-18 | 2018-12-24
DHI | 토목기술 | 박찬웅 | MRT-VK02-P0UMA-171106 | 1041 | [Sump Pump Pit]_Re-bar Arrangement | FA | 2018-11-12 | 2019-01-12 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-12-27 | 180927-FC STAMPED | FC | 0 | A | CIVIL | SUMP PIT | 2018-12-18 | 2018-08-09
DHI | 토목기술 | 박찬웅 | MRT-CC07-P2UAG-170301 | 1042 | [TR Foundation(For Block 2)]_Calculation | FA | 2018-07-13 | 2018-09-08 | 2018-08-09 | 2018-08-28 | MRT-DS-REC-TT-180660-FC | FC | 1 | 2018-09-13 | 180660-FC STAMPED | FC | 1 | A | CIVIL | TR FDN | 2018-07-17 | 2018-08-09
DHI | 토목기술 | 박찬웅 | MRT-CC07-P3UAG-170301 | 1043 | [TR Foundation(For Block 3, 4)]_Calculation | FA | 2018-07-13 | 2018-09-08 | 2018-08-09 | 2018-08-28 | MRT-DS-REC-TT-180660-FC | FC | 1 | 2018-09-13 | 180660-FC STAMPED | FC | 1 | A | CIVIL | TR FDN | 2018-07-17 | 2018-08-09
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UAG-170303 | 1044 | [TR Foundation(For Block 2)]_Pile Arrangement Drawing | FA | 2018-07-13 | 2018-09-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2018-09-13 | 180660-FC STAMPED | FC | 1 | A | CIVIL | TR FDN | 2018-07-17 | 2018-08-09
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UAG-170303 | 1045 | [TR Foundation(For Block 3, 4)]_Pile Arrangement Drawing | FA | 2018-07-13 | 2018-09-08 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-09-13 | 180660-FC STAMPED | FC | 1 | A | CIVIL | TR FDN | 2018-07-17 | 2018-07-27
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UAG-170307 | 1046 | [TR Foundation(For Block 2)]_Plan drawing | FA | 2018-07-13 | 2018-09-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-11-25 | 190220-FC STAMPED | FC | 4 | A | CIVIL | TR FDN | 2018-07-17 | 2018-07-27
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UAG-170307 | 1047 | [TR Foundation(For Block 3, 4)]_Plan drawing | FA | 2018-07-13 | 2018-09-08 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-11-25 | 190220-FC STAMPED | FC | 3 | A | CIVIL | TR FDN | 2018-07-17 | 2018-09-12
DHI | 토목기술 | 박찬웅 | MRT-CC02-P2UAG-170308 | 1048 | [TR Foundation(For Block 2)]_Sectional drawing | FA | 2018-07-13 | 2018-09-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-11-25 | 190220-FC STAMPED | FC | 5 | A | CIVIL | TR FDN | 2018-07-17 | 2018-09-12
DHI | 토목기술 | 박찬웅 | MRT-CC02-P3UAG-170308 | 1049 | [TR Foundation(For Block 3, 4)]_Sectional drawing | FA | 2018-07-13 | 2018-09-08 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2019-11-25 | 190220-FC STAMPED | FC | 4 | A | CIVIL | TR FDN | 2018-07-17 | 2018-08-09
DHI | 토목기술 | 박찬웅 | MRT-VK02-P2UAG-170310 | 1050 | [TR Foundation(For Block 2)]_Re-bar Arrangement | FA | 2018-07-13 | 2018-09-08 | 2022-12-14 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | 2019-03-30 | 190081-FC STAMPED | FC | 2 | A | CIVIL | TR FDN | 2018-07-25 | 2018-08-09
DHI | 토목기술 | 박찬웅 | MRT-VK02-P3UAG-170310 | 1051 | [TR Foundation(For Block 3, 4)]_Re-bar Arrangement | FA | 2018-07-13 | 2018-09-08 | 2023-02-20 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | 2018-12-12 | 180890-FC STAMPED | FC | 1 | A | CIVIL | TR FDN | 2018-07-25 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220014 | 1052 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT +3.10MM (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220015 | 1053 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT +9.10MM (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220016 | 1054 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT +14.60MM (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220017 | 1055 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT LONGGITUDINAL SECTION AA (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220018 | 1056 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT LONGGITUDINAL SECTION BB (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220020 | 1057 | [STEAM TURBINE] TURBINE CROSS SECTION 1-1 (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220021 | 1058 | [STEAM TURBINE] TURBINE CROSS SECTION 2-2 (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P2MAA-220022 | 1059 | [STEAM TURBINE] TURBINE CROSS SECTION 3-3 (BLOCK #2) | FA | 2017-11-26 | 2018-01-12 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-12 | 190139-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220014 | 1060 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT +3.10MM (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220015 | 1061 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT +9.10MM (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220016 | 1062 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT +14.60MM (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220017 | 1063 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT LONGGITUDINAL SECTION AA (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220018 | 1064 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT LONGGITUDINAL SECTION BB (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220019 | 1065 | [STEAM TURBINE] GENERAL ARRANGEMENT DRAWING - LAYOUT LONGGITUDINAL SECTION CC (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220020 | 1066 | [STEAM TURBINE] TURBINE CROSS SECTION 1-1 (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220021 | 1067 | [STEAM TURBINE] TURBINE CROSS SECTION 2-2 (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-07-16
DHI | TG_SKODA | 백운홍 | MRT-XA00-P3MAA-220022 | 1068 | [STEAM TURBINE] TURBINE CROSS SECTION 3-3 (BLOCK #3,4) | FA | 2017-12-24 | 2018-01-28 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2017-11-28 | 2018-10-01
DHI | TG_SKODA | 백운홍 | MRT-XG02-P2MAA-220005 | 1069 | [STEAM TURBINE] P&I DIAGRAM STEAM-WATER (BLOCK #2) | FA | 2017-12-03 | 2018-04-22 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-11-01 | 190208-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM TURBINE | 2018-01-17 | 2018-10-01
DHI | TG_SKODA | 백운홍 | MRT-XG02-P3MAA-220005 | 1070 | [STEAM TURBINE] P&I DIAGRAM STEAM-WATER (BLOCK #3, 4) | FA | 2017-12-03 | 2018-04-22 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2018-01-17 | 2018-10-17
DHI | TG_SKODA | 백운홍 | MRT-XG02-P2MAV-220006 | 1071 | [STEAM TURBINE] P&I DIAGRAM LUBRICATION OIL (BLOCK #2) | FA | 2017-12-03 | 2018-04-22 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2018-12-03 | 180797-FC STAMPED | FC | 2 | A | MECHANICAL | STEAM TURBINE | 2018-01-17 | 2018-10-01
DHI | TG_SKODA | 백운홍 | MRT-XG02-P3MAV-220006 | 1072 | [STEAM TURBINE] P&I DIAGRAM LUBRICATION OIL (BLOCK #3,4) | FA | 2017-12-03 | 2018-04-22 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2018-01-17 | 2018-10-01
DHI | TG_SKODA | 백운홍 | MRT-XG02-P2MAX-220007 | 1073 | [STEAM TURBINE] P&I DIAGRAM HPH (BLOCK #2) | FA | 2017-12-03 | 2018-04-22 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2018-10-23 | 180788-FC STAMPED | FC | 1 | A | MECHANICAL | STEAM TURBINE | 2018-01-17 | 2018-10-01
DHI | TG_SKODA | 백운홍 | MRT-XG02-P3MAX-220007 | 1074 | [STEAM TURBINE] P&I DIAGRAM HPH (BLOCK #3,4) | FA | 2017-12-03 | 2018-04-22 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2018-01-17 | 2019-06-26
DHI | TG_SKODA | 백운홍 | MRT-XK00-P2MAA-220207 | 1075 | [STEAM TURBINE] DRAWINGS AND PARTS LISTS OF TURBINE (BLOCK #2) | FI | 2019-04-18 |  | 2019-06-26 | 2019-07-01 | MRT-DS-REC-TT-190117-FC | FC | 0 | 2019-07-01 | 190117-FC STAMPED | FC | 0 | A | MECHANICAL | STEAM TURBINE | 2019-04-18 | 2019-04-05
DHI | TG_SKODA | 백운홍 | MRT-XK00-P3MAA-220207 | 1076 | [STEAM TURBINE] DRAWINGS AND PARTS LISTS OF TURBINE (BLOCK #3,4) | FI | 2019-03-14 |  | 2020-05-08 | 2020-06-10 | MRT-DS-REC-TT-200041-FC | FC | 1 | 2020-06-10 | 200041-FC STAMPED | FC | 1 | A | MECHANICAL | STEAM TURBINE | 2019-03-14 | 2019-03-14
DHI | TG_SKODA | 백운홍 | MRT-XR00-P2MAA-220040 | 1077 | [STEAM TURBINE] LIST OF EQUIPMENTS (BLOCK #2) | FI | 2018-10-25 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-03-18 | 180843-FC STAMPED | FC | 0 | A | MECHANICAL | STEAM TURBINE | 2018-10-25 | 2019-03-14
DHI | TG_SKODA | 백운홍 | MRT-XR00-P3MAA-220040 | 1078 | [STEAM TURBINE] LIST OF EQUIPMENTS (BLOCK #3,4) | FI | 2018-11-07 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2018-11-07 | 2019-03-14
DHI | TG_SKODA | 백운홍 | MRT-XR00-P2MAV-220041 | 1079 | [STEAM TURBINE] LIST OF OIL SYSTEM EQUIPMENTS (BLOCK #2) | FI | 2018-10-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-03-18 | 180816-FC STAMPED | FC | 0 | A | MECHANICAL | STEAM TURBINE | 2018-10-12 | 2019-04-05
DHI | TG_SKODA | 백운홍 | MRT-XR00-P3MAV-220041 | 1080 | [STEAM TURBINE] LIST OF OIL SYSTEM EQUIPMENTS (BLOCK #3,4) | FI | 2019-03-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2019-03-14 | 2019-03-11
DHI | TG_SKODA | 백운홍 | MRT-XN00-P2MAV-220039 | 1081 | [STEAM TURBINE] LIST OF VALVES - OIL SYSTEM (BLOCK #2) | FI | 2019-02-18 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-03-12 | 190037-FC STAMPED | FC | 0 | A | MECHANICAL | STEAM TURBINE | 2019-02-18 | 2019-03-11
DHI | TG_SKODA | 백운홍 | MRT-XN00-P3MAV-220039 | 1082 | [STEAM TURBINE] LIST OF VALVES - OIL SYSTEM (BLOCK #3,4) | FI | 2019-02-18 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2019-02-18 | 2019-03-11
DHI | TG_SKODA | 백운홍 | MRT-XN00-P2MAA-220038 | 1083 | [STEAM TURBINE] LIST OF VALVES - STEAM AND WATER (BLOCK #2) | FI | 2019-02-18 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2021-08-27 | 210048-FC STAMPED | FC | 1 | A | MECHANICAL | STEAM TURBINE | 2019-02-18 | 2019-03-11
DHI | TG_SKODA | 백운홍 | MRT-XN00-P3MAA-220038 | 1084 | [STEAM TURBINE] LIST OF VALVES - STEAM AND WATER (BLOCK #3,4) | FI | 2019-02-18 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2019-02-18 | 2019-10-18
DHI | TG_SKODA | 백운홍 | MRT-XM00-P2MAA-220012 | 1085 | [STEAM TURBINE] STEAM TURBINE LAYDOWN PLAN (BLOCK #2) | FI | 2017-12-03 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-10-18 | 190211-FC STAMPED | FC | 1 | A | MECHANICAL | STEAM TURBINE | 2018-01-17 | 2019-10-18
DHI | TG_SKODA | 백운홍 | MRT-XM00-P3MAA-220012 | 1086 | [STEAM TURBINE] STEAM TURBINE LAYDOWN PLAN (BLOCK #3, 4) | FI | 2017-12-03 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2018-01-17 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YV02-P3MAK-230077 | 1087 | [STEAM TURBINE] FREQUENCY CONVERTER FOR TURNING GEAR (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2019-02-12 | 2018-07-17
DHI | TG_SKODA | 백운홍 | MRT-XV00-P2MAA-220036 | 1088 | [STEAM TURBINE] PIPING LINE LIST - STEAM-WATER (BLOCK #2) | FA | 2018-01-10 | 2018-04-10 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2018-10-16 | 180621-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM TURBINE | 2018-01-05 | 2018-07-17
DHI | TG_SKODA | 백운홍 | MRT-XV00-P3MAA-220036 | 1089 | [STEAM TURBINE] PIPING LINE LIST - STEAM-WATER (BLOCK #3, 4) | FA | 2018-01-10 | 2018-04-10 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2018-01-05 | 2018-07-17
DHI | TG_SKODA | 백운홍 | MRT-XV00-P2MAV-220037 | 1090 | [STEAM TURBINE] PIPING LINE LIST - LUBRICATION OIL (BLOCK #2) | FA | 2018-01-10 | 2018-04-10 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-12-04 | 141/T/MRT/REC/XII/2020 | FC | 4 | A | MECHANICAL | STEAM TURBINE | 2018-01-05 | 2018-07-17
DHI | TG_SKODA | 백운홍 | MRT-XV00-P3MAV-220037 | 1091 | [STEAM TURBINE] PIPING LINE LIST - LUBRICATION OIL (BLOCK #3, 4) | FA | 2018-01-10 | 2018-04-10 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2018-01-05 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2MAA-220214 | 1092 | [STEAM TURBINE] ISOMETRIC DRAWINGS OF PIPELINES FOR SMALL BORE PIPING (BLOCK #2) | FI | 2020-02-25 | 2020-04-25 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-02-25 | 200019-FC STAMPED | FI | 0 | A | MECHANICAL | STEAM TURBINE | 2020-02-25 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3MAA-220214 | 1093 | [STEAM TURBINE] ISOMETRIC DRAWINGS OF PIPELINES FOR SMALL BORE PIPING (BLOCK #3,4) | FI | 2019-09-01 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-VE01-P2MAA-220044 | 1094 | [STEAM TURBINE] ALLOWABLE FORCES AND MOMENTS (BLOCK #2) | FI | 2018-01-28 |  | 2019-04-08 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | 2019-04-10 | 211/T/MRT/REC/IV/2019 | FI | 1 | I | MECHANICAL | STEAM TURBINE | 2018-01-30 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-VE01-P3MAA-220044 | 1095 | [STEAM TURBINE] ALLOWABLE FORCES AND MOMENTS (BLOCK #3, 4) | FI | 2018-01-28 |  | 2019-04-08 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | 2019-04-10 | 211/T/MRT/REC/IV/2019 | FI | 1 | I | MECHANICAL | STEAM TURBINE | 2018-01-30 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-XG01-P2MAA-220045 | 1096 | [STEAM TURBINE] DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM (BLOCK #2) | FI | 2018-07-08 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-06-29 | 200052-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM TURBINE | 2018-07-27 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-XG01-P3MAA-220045 | 1097 | [STEAM TURBINE] DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM (BLOCK #3, 4) | FI | 2018-07-08 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | MECHANICAL | STEAM TURBINE | 2018-07-27 | 2019-01-11
DHI | TG_SKODA | 백운홍 | MRT-XT00-P2MAA-220208 | 1098 | [STEAM TURBINE] FOUNDATION BOLT ASSEMBLY AND PART LIST (BLOCK #2) FOR INSTALLATION | FI | 2019-01-10 |  | 2019-01-11 | 2019-01-11 | MRT-DS-REC-TT-190009-FC | FC | 0 | 2019-01-12 | 190009-FC STAMPED | FC | 0 | A | MECHANICAL | STEAM TURBINE | 2019-01-10 | 2019-01-11
DHI | TG_SKODA | 백운홍 | MRT-XT00-P3MAA-220208 | 1099 | [STEAM TURBINE] FOUNDATION BOLT ASSEMBLY AND PART LIST (BLOCK #3,4) FOR INSTALLATION | FI | 2019-01-10 |  | 2019-01-11 | 2019-01-11 | MRT-DS-REC-TT-190009-FC | FC | 0 | 2019-01-12 | 190009-FC STAMPED | FC | 0 | A | MECHANICAL | STEAM TURBINE | 2019-01-10 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YV02-P2MAK-230077 | 1100 | [STEAM TURBINE] STARTER FOR TURNING GEAR (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | ELECTRICAL | STEAM TURBINE | 2019-02-12 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YV02-P2MAV-230078 | 1101 | [STEAM TURBINE] DC MOTOR STARTER (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | ELECTRICAL | STEAM TURBINE | 2019-02-12 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YV02-P3MAV-230078 | 1102 | [STEAM TURBINE] DC MOTOR STARTER (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5541.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE | 2019-02-12 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YL15-P2CJJ-240072 | 1103 | [STEAM TURBINE] CABLE LIST (BLOCK #2) | FA | 2019-02-20 | 2019-04-20 | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | ELECTRICAL | STEAM TURBINE | 2019-02-20 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YL15-P3CJJ-240072 | 1104 | [STEAM TURBINE] CABLE LIST (BLOCK #3,4) | FA | 2019-02-20 | 2019-04-20 | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | ELECTRICAL | STEAM TURBINE | 2019-02-20 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YL15-P2CJJ-240122 | 1105 | [STEAM TURBINE] CABLE LIST FOR FIELD INSTALLATION (BLOCK #2) | FI | 2020-07-09 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-09 | 200058-FC STAMPED | FI | 0 | A | ELECTRICAL | STEAM TURBINE | 2020-07-09 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YL15-P3CJJ-240114 | 1106 | [STEAM TURBINE] CABLE LIST FOR FIELD INSTALLATION (BLOCK #3,4) | FI | 2019-02-20 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE | 2019-02-20 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YL15-P2MAD-240171 | 1107 | [STEAM TURBINE] VIBRATION MONITORING SYSTEM - CABLE LIST (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | ELECTRICAL | STEAM TURBINE | 2019-02-12 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YL15-P3MAD-240181 | 1108 | [STEAM TURBINE] VIBRATION MONITORING SYSTEM - CABLE LIST (BLOCK #3,4) | FI | 2019-02-20 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE | 2019-02-20 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YV02-P2CJJ-240121 | 1109 | [STEAM TURBINE] WIRING DIAGRAMS, LOOP DIAGRAMS (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-03-07 | 200022-FC STAMPED | FC | 2 | A | ELECTRICAL | STEAM TURBINE | 2019-02-12 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YV02-P3CJJ-240113 | 1110 | [STEAM TURBINE] WIRING DIAGRAMS, LOOP DIAGRAMS (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE | 2019-02-12 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YV02-P2MAX-220095 | 1111 | [STEAM TURBINE] WIRING DIAGRAMS, HIGH-PRESSURE HYDRAULIC (BLOCK #2) | FI | 2020-04-08 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-04-08 | 200033-FC STAMPED | FI | 0 | A | ELECTRICAL | STEAM TURBINE | 2020-04-08 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YV02-P3MAX-220144 | 1112 | [STEAM TURBINE] WIRING DIAGRAMS, HIGH-PRESSURE HYDRAULIC (BLOCK #3,4) | FI | 2020-04-29 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE | 2020-04-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YD05-P3MAA-240157 | 1113 | [STEAM TURBINE] WIRING DIAGRAMS, LOOP DIAGRAMS for Synchr. System of Turning gear (BLOCK #3,4) | FI | 2020-08-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE | 2020-08-25 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YV02-P2MAD-240170 | 1114 | [STEAM TURBINE] VIBRATION MONITORING SYSTEM - WIRING DIAGRAMS (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | ELECTRICAL | STEAM TURBINE | 2019-02-12 | 2019-04-29
DHI | TG_SKODA | 백운홍 | MRT-YV02-P3MAD-240180 | 1115 | [STEAM TURBINE] VIBRATION MONITORING SYSTEM - WIRING DIAGRAMS (BLOCK #3,4) | FI | 2019-04-04 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5541.0 | AB | Z0 | A | ELECTRICAL | STEAM TURBINE | 2019-04-04 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-XS01-P2CJJ-240060 | 1116 | [STEAM TURBINE] CONTROL SYSTEM FUNCTIONS PHILOSOPHY (BLOCK #2) | FI | 2018-03-11 |  | 2019-02-22 | 2019-02-22 | MRT-DS-REC-TT-190053 | FI | 1 | 2019-03-27 | 164/T/MRT/REC/III/2019 | FI | 1 | I | I&C | STEAM TURBINE | 2018-06-07 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-XS01-P3CJJ-240060 | 1117 | [STEAM TURBINE] CONTROL SYSTEM FUNCTIONS PHILOSOPHY (BLOCK #3, 4) | FI | 2018-03-11 |  | 2019-03-14 | 2019-03-14 | MRT-DS-REC-TT-190077 | FI | 1 | 2019-04-04 | 194/T/MRT/REC/IV/2019 | FI | 1 | I | I&C | STEAM TURBINE | 2018-10-17 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-XR00-P2MAA-220086 | 1118 | [STEAM TURBINE] FUNCTIONAL DESCRIPTION (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE | 2019-02-20 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-XR00-P3MAA-220082 | 1119 | [STEAM TURBINE] FUNCTIONAL DESCRIPTION (BLOCK #3,4) | FI | 2019-02-12 |  | 2019-04-01 | 2019-04-08 | MRT-DS-REC-TT-190032-FC | FC | 0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE | 2019-02-12 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YF00-P2CJJ-240064 | 1120 | [STEAM TURBINE] LOGIC DIAGRAMS (BLOCK #2) | FI | 2018-07-15 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-07-09 | 377/T/MRT/REC/VII/2019 | FI | 1 | I | I&C | STEAM TURBINE | 2018-10-19 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YF00-P3CJJ-240064 | 1121 | [STEAM TURBINE] LOGIC DIAGRAMS (BLOCK #3, 4) | FI | 2018-07-15 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2025-01-14 | MTW-G-C-LT-25.6118.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2019-05-31 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YF00-P2CJJ-240213 | 1122 | [STEAM TURBINE] LOGIC DIAGRAMS FOR CONTROL SYSTEM (BLOCK #2) | FI | 2020-07-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE | 2020-07-14 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YK00-P2CJJ-240065 | 1123 | [STEAM TURBINE] PROTECTION DIAGRAM FOR I&C (BLOCK #2) | FI | 2020-07-14 |  | 2020-07-14 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE | 2020-07-14 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YK00-P3CJJ-240065 | 1124 | [STEAM TURBINE] PROTECTION DIAGRAM FOR I&C (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE | 2020-08-25 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YD05-P2CJJ-240069 | 1125 | [STEAM TURBINE] HMI DESIGN (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE | 2019-02-12 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YD05-P3CJJ-240069 | 1126 | [STEAM TURBINE] HMI DESIGN (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2019-02-12 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YV02-P2CJJ-240113 | 1127 | [STEAM TURBINE] HMI DESIGN FOR CONTROL SYSTEM (BLOCK #2) | FI | 2020-07-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE | 2020-07-14 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YV02-P3CJJ-240105 | 1128 | [STEAM TURBINE] HMI DESIGN FOR CONTROL SYSTEM (BLOCK #3,4) | FI | 2020-08-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2020-08-25 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YL01-P2CJJ-240073 | 1129 | [STEAM TURBINE] LIST OF CABINETS AND JB (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE | 2019-02-12 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YL01-P3CJJ-240073 | 1130 | [STEAM TURBINE] LIST OF CABINETS AND JB (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2019-02-12 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YR00-P2CJJ-240055 | 1131 | [STEAM TURBINE] CONTROL SYSTEM ARCHITECTURE (BLOCK #2) | FI | 2018-02-11 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-04 | 193/T/MRT/REC/IV/2019 | FI | 1 | I | I&C | STEAM TURBINE | 2018-02-14 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YR00-P3CJJ-240055 | 1132 | [STEAM TURBINE] CONTROL SYSTEM ARCHITECTURE (BLOCK #3, 4) | FI | 2018-02-11 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2018-02-14 | 2019-01-02
DHI | TG_SKODA | 백운홍 | MRT-YF02-P2CJJ-240112 | 1133 | [STEAM TURBINE] CONTROL SYSTEM HARDWARE SPECIFICATION (BLOCK #2) | FI | 2018-05-06 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-05-20 | 200041-FC STAMPED | FC | 1 | A | I&C | STEAM TURBINE | 2018-12-07 | 2019-05-24
DHI | TG_SKODA | 백운홍 | MRT-YF02-P3CJJ-240104 | 1134 | [STEAM TURBINE] CONTROL SYSTEM HARDWARE SPECIFICATION (BLOCK #3, 4) | FI | 2018-05-06 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2019-01-09 | 2019-04-05
DHI | TG_SKODA | 백운홍 | MRT-YF02-P2MAD-240168 | 1135 | [STEAM TURBINE] CONTROL SYSTEM HARDWARE SPECIFICATION FOR VMS (BLOCK #2) | FI | 2019-02-18 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-11 | 190037-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE | 2019-02-18 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YF02-P3MAD-240178 | 1136 | [STEAM TURBINE] CONTROL SYSTEM HARDWARE SPECIFICATION FOR VMS (BLOCK #3,4) | FI | 2019-09-01 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YF02-P2MAX-220094 | 1137 | [STEAM TURBINE] CONTROL SYSTEM. HARDWARE SPECIFICATION FOR HPH OIL SYSTEM (BLOCK #2) | FI | 2020-07-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE | 2020-07-14 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAX-220143 | 1138 | [STEAM TURBINE] CONTROL SYSTEM. HARDWARE SPECIFICATION FOR HPH OIL SYSTEM (BLOCK #3,4) | FI | 2020-08-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2020-08-25 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YF02-P3MAA-240156 | 1139 | [STEAM TURBINE] CONTROL SYSTEM. HARDWARE SPECIFICATION FOR Synchr. SYSTEM OF TURNING GEAR (BLOCK #3,4) | FI | 2020-08-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2020-08-25 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YL01-P2CJJ-240070 | 1140 | [STEAM TURBINE] I/O LIST (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-12-16 | 190241-FC STAMPED | FC | 1 | A | I&C | STEAM TURBINE | 2019-02-12 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YL01-P3CJJ-240070 | 1141 | [STEAM TURBINE] I/O LIST (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2019-02-12 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YL01-P2MAD-240169 | 1142 | [STEAM TURBINE] I/O LIST FOR VMS (BLOCK #2) | FI | 2020-07-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE | 2020-07-14 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YL01-P3MAD-240179 | 1143 | [STEAM TURBINE] I/O LIST FOR VMS (BLOCK #3,4) | FI | 2020-08-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2025-01-14 | MTW-G-C-LT-25.6118.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2020-08-25 | 2018-08-29
DHI | TG_SKODA | 백운홍 | MRT-YL13-P2CJJ-240061 | 1144 | [STEAM TURBINE] SIGNAL TRANSFER LIST BETWEEN TCS AND DCS - HARDWIRE (BLOCK #2) | FI | 2018-03-11 |  | 2018-08-29 | 2018-10-19 | MRT-DS-REC-TT-180592-FC | FC | 0 | 2018-10-26 | 180592-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE | 2018-07-11 | 2018-08-29
DHI | TG_SKODA | 백운홍 | MRT-YL13-P3CJJ-240061 | 1145 | [STEAM TURBINE] SIGNAL TRANSFER LIST BETWEEN TCS AND DCS (BLOCK #3, 4) | FI | 2018-03-11 |  | 2018-08-29 | 2018-10-19 | MRT-DS-REC-TT-180592-FC | FC | 0 | 2018-10-26 | 180592-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE | 2018-07-11 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YS01-P2CJJ-240051 | 1146 | [STEAM TURBINE] CONSUMER SCHEMES FOR I&C (BLOCK #2) | FI | 2020-07-14 |  | 2020-07-14 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE | 2020-07-14 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YS01-P3CJJ-240051 | 1147 | [STEAM TURBINE] CONSUMER SCHEMES FOR I&C (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE | 2020-08-25 | 2019-04-05
DHI | TG_SKODA | 백운홍 | MRT-YL00-P2CJJ-240052 | 1148 | [STEAM TURBINE] MEASUREMENT LIST (BLOCK #2) | FI | 2019-02-18 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-11 | 190037-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE | 2019-02-18 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YL00-P3CJJ-240052 | 1149 | [STEAM TURBINE] MEASUREMENT LIST (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5069.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2019-02-12 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YL00-P2CJJ-240053 | 1150 | [STEAM TURBINE] CONSUMER LIST FOR I&C (BLOCK #2) | FI | 2020-07-14 |  | 2020-07-14 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE | 2020-07-14 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YL00-P3CJJ-240053 | 1151 | [STEAM TURBINE] CONSUMER LIST FOR I&C (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE | 2020-08-25 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YL08-P2CJJ-240068 | 1152 | [STEAM TURBINE] TRIPS & ALARMS SETTING (BLOCK #2) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-12-03 | 200084-FC STAMPED | FC | 1 | A | I&C | STEAM TURBINE | 2019-02-12 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YL08-P3CJJ-240068 | 1153 | [STEAM TURBINE] TRIPS & ALARMS SETTING (BLOCK #3,4) | FI | 2019-02-12 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2019-02-12 | 2019-03-14
DHI | TG_SKODA | 백운홍 | MRT-YT02-P2CJJ-240120 | 1154 | [STEAM TURBINE] INSTRUMENTATION DATA SHEETS (BLOCK #2) | FI | 2018-06-03 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-03-18 | 180759-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE | 2018-11-09 | 2019-03-14
DHI | TG_SKODA | 백운홍 | MRT-YT02-P3CJJ-240112 | 1155 | [STEAM TURBINE] INSTRUMENTATION DATA SHEETS (BLOCK #3, 4) | FI | 2018-06-03 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2018-11-09 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YT02-P2MAD-240167 | 1156 | [STEAM TURBINE] INSTRUMENTATION DATA SHEETS FOR VMS (BLOCK #2) | FI | 2020-07-09 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-09 | 200058-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE | 2020-07-09 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YT02-P3MAD-240177 | 1157 | [STEAM TURBINE] INSTRUMENTATION DATA SHEETS FOR VMS (BLOCK #3,4) | FI | 2019-09-01 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2019-11-28 | 2019-03-18
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2CJA-240057 | 1158 | [STEAM TURBINE] I&C LAYOUTS +3.10M (BLOCK #2) | FI | 2018-08-30 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-08-23 | 19019-FC STAMPED | FC | 3 | A | I&C | STEAM TURBINE | 2018-08-29 | 2019-03-18
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2CJA-240058 | 1159 | [STEAM TURBINE] I&C LAYOUTS +9.10M (BLOCK #2) | FI | 2018-08-30 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-08-23 | 19019-FC STAMPED | FC | 3 | A | I&C | STEAM TURBINE | 2018-08-29 | 2019-03-18
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2CJA-240059 | 1160 | [STEAM TURBINE] I&C LAYOUTS +14.60M (BLOCK #2) | FI | 2018-08-30 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-08-23 | 19019-FC STAMPED | FC | 3 | A | I&C | STEAM TURBINE | 2018-08-29 | 2019-03-18
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3CJA-240057 | 1161 | [STEAM TURBINE] I&C LAYOUTS +3.10M (BLOCK #3,4) | FI | 2018-08-30 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2018-08-29 | 2019-03-18
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3CJA-240058 | 1162 | [STEAM TURBINE] I&C LAYOUTS +9.10M (BLOCK #3,4) | FI | 2018-08-30 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2018-08-29 | 2019-03-18
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3CJA-240059 | 1163 | [STEAM TURBINE] I&C LAYOUTS +14.60M (BLOCK #3,4) | FI | 2018-08-30 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2025-01-14 | MTW-G-C-LT-25.6118.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2018-08-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YK00-P2CJJ-240049 | 1164 | [STEAM TURBINE] HOOK-UPS FOR I&C (BLOCK #2) | FI | 2020-07-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | I&C | STEAM TURBINE | 2020-07-14 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YK00-P2CJJ-240119 | 1165 | [STEAM TURBINE] HOOK-UPS FOR FIELD INSTRUMENTATION (BLOCK #2) | FA | 2019-02-12 | 2019-04-30 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2019-04-08 | 190032-FC STAMPED | FC | 0 | A | I&C | STEAM TURBINE | 2019-02-12 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YK00-P3CJJ-240049 | 1166 | [STEAM TURBINE] HOOK-UPS FOR I&C (BLOCK #3,4) | FI | 2020-08-14 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2020-08-25 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-YK00-P3CJJ-240111 | 1167 | [STEAM TURBINE] HOOK-UPS FOR FIELD INSTRUMENTATION (BLOCK #3,4) | FA | 2019-02-12 | 2019-04-30 | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-11-12 | MTW-AS-C-LT-24.5938.0 | AB | Z0 | A | I&C | STEAM TURBINE | 2019-02-12 | 2019-01-07
DHI | TG_SKODA | 백운홍 | MRT-XT00-P2MAA-220002 | 1168 | [STEAM TURBINE] STEAM TURBINE FOUNDATION EMBEDDED ELEMENTS FOR INSTALLATION (BLOCK #2) | FI | 2017-11-19 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | 2020-06-10 | 200049-FC STAMPED | FC | 2 | A | CIVIL | STEAM TURBINE | 2017-11-27 | 2019-01-14
DHI | TG_SKODA | 백운홍 | MRT-XT00-P3MAA-220002 | 1169 | [STEAM TURBINE] STEAM TURBINE FOUNDATION EMBEDDED ELEMENTS FOR INSTALLATION (BLOCK #3,4) | FI | 2017-11-19 |  | 2022-12-20 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | 2024-03-21 | MTW-AS-C-LT-24.5089.0 | AB | Z0 | A | CIVIL | STEAM TURBINE | 2017-11-27 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CA07-P2MAA-220003 | 1170 | [STEAM TURBINE] STG FOUNDATION - DESIGN CRITERIA (BLOCK #2) | FI | 2017-10-22 |  | 2017-10-31 | 2017-11-03 | MRT-DS-PLNE-TT-170052 | FI | 0 | 2017-11-21 | 20.027/E04/PLNE/XI/2017 | FI | 0 | I | CIVIL | STEAM TURBINE | 2017-10-31 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CA07-P3MAA-220003 | 1171 | [STEAM TURBINE] STG FOUNDATION - DESIGN CRITERIA (BLOCK #3, 4) | FI | 2017-11-19 |  | 2017-11-07 | 2017-11-09 | MRT-DS-PLNE-TT-170060 | FI | 0 | 2017-11-20 | 20.005/E04/PLNE/XI/2017 | FI | 0 | I | CIVIL | STEAM TURBINE | 2017-11-07 | 2019-01-07
DHI | TG_SKODA | 백운홍 | MRT-VL00-P2MAA-220001 | 1172 | [STEAM TURBINE] STG FOUNDATION SHAPE - PLANS PART1 FOR INSTALLATION (BLOCK #2) | FI | 2017-10-08 |  | 2019-02-22 | 2019-02-26 | MRT-DS-REC-TT-190033-FC | FC | 2 | 2019-02-26 | 190033-FC STAMPED | FC | 2 | A | CIVIL | STEAM TURBINE | 2017-11-02 | 2019-01-14
DHI | TG_SKODA | 백운홍 | MRT-VL00-P3MAA-220001 | 1173 | [STEAM TURBINE] STG FOUNDATION SHAPE - PLANS FOR INSTALLATION (BLOCK #3, 4) | FI | 2017-11-05 |  | 2019-02-22 | 2019-02-26 | MRT-DS-REC-TT-190033-FC | FC | 2 | 2019-02-26 | 190033-FC STAMPED | FC | 2 | A | CIVIL | STEAM TURBINE | 2017-11-03 | 2019-01-07
DHI | TG_SKODA | 백운홍 | MRT-VL00-P2MAA-220009 | 1174 | [STEAM TURBINE] STG FOUNDATION SHAPE - SECTIONS FOR INSTALLATION (BLOCK #2) | FI | 2017-10-08 |  | 2019-01-07 | 2019-01-07 | MRT-DS-REC-TT-190003-FC | FC | 1 | 2019-01-07 | 190003-FC STAMPED | FC | 1 | A | CIVIL | STEAM TURBINE | 2017-11-02 | 2019-01-14
DHI | TG_SKODA | 백운홍 | MRT-VL00-P3MAA-220009 | 1175 | [STEAM TURBINE] STG FOUNDATION SHAPE - SECTIONS FOR INSTALLATION (BLOCK #3,4) | FI | 2017-11-05 |  | 2019-01-14 | 2019-01-14 | MRT-DS-REC-TT-190005-FC | FC | 1 | 2019-01-14 | 190005-FC STAMPED | FC | 1 | A | CIVIL | STEAM TURBINE | 2017-11-03 | 2019-01-07
DHI | TG_SKODA | 백운홍 | MRT-VL00-P2MAA-220010 | 1176 | [STEAM TURBINE] STG FOUNDATION - DIRECTIVES FOR CIVIL WORK FOR INSTALLATION (BLOCK #2) | FI | 2017-10-08 |  | 2019-01-07 | 2019-01-07 | MRT-DS-REC-TT-190003-FC | FC | 1 | 2019-01-07 | 190003-FC STAMPED | FC | 1 | A | CIVIL | STEAM TURBINE | 2017-10-31 | 2019-01-14
DHI | TG_SKODA | 백운홍 | MRT-VL00-P3MAA-220010 | 1177 | [STEAM TURBINE] STG FOUNDATION - DIRECTIVES FOR CIVIL WORK FOR INSTALLATION (BLOCK #3,4) | FI | 2017-11-05 |  | 2019-01-14 | 2019-01-14 | MRT-DS-REC-TT-190005-FC | FC | 1 | 2019-01-14 | 190005-FC STAMPED | FC | 1 | A | CIVIL | STEAM TURBINE | 2017-11-07 | 2020-12-03
DHI | TG_SKODA | 백운홍 | MRT-UF00-P2MAA-220023 | 1178 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN (BLOCK #2) | FI | 2017-10-08 |  | 2020-12-03 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FC | 1 | 2020-12-03 | 200084-FC STAMPED | FC | 1 | A | CIVIL | STEAM TURBINE | 2017-11-03 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-UF00-P3MAA-220023 | 1179 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN (BLOCK #3, 4) | FI | 2017-11-05 |  | 2019-03-04 | 2019-03-04 | MRT-DS-REC-TT-190062 | FI | 1 | 2019-04-04 | 193/T/MRT/REC/IV/2019 | FI | 1 | I | CIVIL | STEAM TURBINE | 2017-11-03 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2MAA-220025 | 1180 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - EQUIPMENT - LEVELS +3,10M (BLOCK #2) | FI | 2018-01-15 |  | 2018-04-16 | 2018-04-16 | MRT-DS-REC-TT-180312 | FI | 0 | 2018-06-29 | 452/T/MRT/REC/VI/2018 | FI | 0 | I | CIVIL | STEAM TURBINE | 2018-04-16 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3MAA-220025 | 1181 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - EQUIPMENT - LEVELS +3,10M (BLOCK #3,4) | FI | 2018-01-15 |  | 2018-04-16 | 2018-04-16 | MRT-DS-REC-TT-180312 | FI | 0 | 2018-06-29 | 452/T/MRT/REC/VI/2018 | FI | 0 | I | CIVIL | STEAM TURBINE | 2018-04-16 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2MAA-220026 | 1182 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - EQUIPMENT - LEVELS +9,10M (BLOCK #2) | FI | 2018-01-15 |  | 2019-04-08 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | 2019-04-10 | 211/T/MRT/REC/IV/2019 | FI | 1 | I | CIVIL | STEAM TURBINE | 2018-04-16 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3MAA-220026 | 1183 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - EQUIPMENT - LEVELS +9,10M (BLOCK #3,4) | FI | 2018-01-15 |  | 2019-04-08 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | 2019-04-10 | 211/T/MRT/REC/IV/2019 | FI | 1 | I | CIVIL | STEAM TURBINE | 2018-04-16 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2MAA-220027 | 1184 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - EQUIPMENT - LEVELS +14,60M (BLOCK #2) | FI | 2018-01-15 |  | 2019-04-08 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | 2019-04-10 | 211/T/MRT/REC/IV/2019 | FI | 1 | I | CIVIL | STEAM TURBINE | 2018-04-16 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3MAA-220027 | 1185 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - EQUIPMENT - LEVELS +14,60M (BLOCK #3,4) | FI | 2018-01-15 |  | 2019-04-08 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | 2019-04-10 | 211/T/MRT/REC/IV/2019 | FI | 1 | I | CIVIL | STEAM TURBINE | 2018-04-16 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2MAA-220030 | 1186 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - PENETRATION PLAN - LEVELS +9,10M (BLOCK #2) | FI | 2017-10-08 |  | 2019-02-01 | 2019-02-01 | MRT-DS-REC-TT-190028 | FI | 1 | 2019-03-06 | 104/T/MRT/REC/III/2019 | FI | 1 | I | CIVIL | STEAM TURBINE | 2017-10-31 | 2019-10-28
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3MAA-220031 | 1187 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - PENETRATION PLAN - LEVELS +9,10M (BLOCK #3,4) | FI | 2017-11-05 |  | 2019-10-28 | 2019-10-28 | MRT-DS-REC-TT-190217-FC | FC | 2 | 2019-10-28 | 190217-FC STAMPED | FC | 2 | A | CIVIL | STEAM TURBINE | 2017-11-07 | 2020-12-03
DHI | TG_SKODA | 백운홍 | MRT-YD00-P2MAA-220031 | 1188 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - PENETRATION PLAN - LEVELS +14,60M (BLOCK #2) | FI | 2017-10-08 |  | 2020-12-03 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FC | 2 | 2020-12-03 | 200084-FC STAMPED | FC | 2 | A | CIVIL | STEAM TURBINE | 2017-10-31 | 2019-10-28
DHI | TG_SKODA | 백운홍 | MRT-YD00-P3MAA-220030 | 1189 | [STEAM TURBINE] STG FOUNDATION LOAD PLAN - PENETRATION PLAN - LEVELS +14,60M (BLOCK #3,4) | FI | 2017-11-05 |  | 2019-10-28 | 2019-10-28 | MRT-DS-REC-TT-190217-FC | FC | 2 | 2019-10-28 | 190217-FC STAMPED | FC | 2 | A | CIVIL | STEAM TURBINE | 2017-11-07 | 2019-01-07
DHI | TG_SKODA | 백운홍 | MRT-VL00-P2MAA-220079 | 1190 | [STEAM TURBINE] STG FOUNDATION SHAPE - PLANS PART2 FOR INSTALLATION (BLOCK #2) | FI | 2019-01-04 |  | 2019-01-07 | 2019-01-07 | MRT-DS-REC-TT-190003-FC | FC | 0 | 2019-01-07 | 190003-FC STAMPED | FC | 0 | A | CIVIL | STEAM TURBINE | 2019-01-04 | 2018-12-19
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220134 | 1191 | [STEAM TURBINE] INITIAL SPECIFICATION FOR STEAM TURBINE INSTALLATION (BLOCK 2) | FI | 2018-11-23 |  | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180921-FC | FC | 0 | 2018-12-22 | 180921-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2018-12-07 | 2018-12-19
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220133 | 1192 | [STEAM TURBINE] INITIAL SPECIFICATION FOR STEAM TURBINE INSTALLATION (BLOCK 3,4) | FI | 2018-11-23 |  | 2018-12-19 | 2018-12-19 | MRT-DS-REC-TT-180921-FC | FC | 0 | 2018-12-22 | 180921-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2018-12-07 | 2019-06-26
DHI | TG_SKODA | 백운홍 | MRT-QA00-P2MAA-220210 | 1193 | [STEAM TURBINE] MEASUREMENT PROTOCOLS FOR TURBINE FOR INSTALLATION (BLOCK #2) | FI | 2019-05-29 |  | 2019-06-26 | 2019-06-27 | MRT-DS-REC-TT-190138-FC | FC | 0 | 2019-06-27 | 190138-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-05-29 | 2019-06-26
DHI | TG_SKODA | 백운홍 | MRT-QA00-P3MAA-220210 | 1194 | [STEAM TURBINE] MEASUREMENT PROTOCOLS FOR TURBINE FOR INSTALLATION (BLOCK #3,4) | FI | 2019-05-29 |  | 2019-06-26 | 2019-06-27 | MRT-DS-REC-TT-190138-FC | FC | 0 | 2019-06-27 | 190138-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-05-29 | 2019-01-02
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220165 | 1195 | [STEAM TURBINE] INSTRUCTION FOR STEAM TURBINE ASSEMBLY (BLOCK 2) | FI | 2018-11-23 |  | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180920-FC | FC | 0 | 2019-01-07 | 180920-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2018-12-07 | 2019-04-05
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220174 | 1196 | [STEAM TURBINE] INSTRUCTION FOR STEAM TURBINE ASSEMBLY (BLOCK 3,4) | FI | 2018-12-14 |  | 2019-05-31 | 2019-06-18 | MRT-DS-REC-TT-190131-FC | FC | I | 2019-06-19 | 190131-FC STAMPED | FC | I | A | SUPPORT | STEAM TURBINE | 2019-03-04 | 2019-01-02
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220166 | 1197 | [STEAM TURBINE] MAIN ASSEMBLY MANUAL (BLOCK 2) | FI | 2018-11-23 |  | 2019-01-02 | 2019-01-03 | MRT-DS-REC-TT-180920-FC | FC | 0 | 2019-01-07 | 180920-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2018-12-07 | 2019-06-26
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220175 | 1198 | [STEAM TURBINE] MAIN ASSEMBLY MANUAL (BLOCK 3,4) | FI | 2018-12-14 |  | 2019-06-26 | 2019-07-01 | MRT-DS-REC-TT-190130-FC | FC | 0 | 2019-07-01 | 190130-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-05-21 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220193 | 1199 | [STEAM TURBINE] ASSEMBLY MANUAL FOR AUXILIARY STEEL STRUCTURES (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | 2019-09-09
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220193 | 1200 | [STEAM TURBINE] ASSEMBLY MANUAL FOR AUXILIARY STEEL STRUCTURES (BLOCK #3,4) | FI | 2019-07-24 |  | 2019-09-09 | 2019-09-09 | MRT-DS-REC-TT-190166-FC | FC | 0 | 2019-09-09 | 190166-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-07-24 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2LBS-220087 | 1201 | [STEAM TURBINE] ASSEMBLY MANUAL FOR BUTTERFLY VALVE (BLOCK #2) | FI | 2019-02-20 |  | 2019-05-31 | 2019-06-18 | MRT-DS-REC-TT-190131-FC | FC | I | 2019-06-19 | 190131-FC STAMPED | FC | I | A | SUPPORT | STEAM TURBINE | 2019-02-20 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3LBA-220083 | 1202 | [STEAM TURBINE] ASSEMBLY MANUAL FOR BUTTERFLY VALVE (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2CJJ-240114 | 1203 | [STEAM TURBINE] ASSEMBLY MANUAL FOR CONTROL SYSTEM (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-02-20 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3CJJ-240106 | 1204 | [STEAM TURBINE] ASSEMBLY MANUAL FOR CONTROL SYSTEM (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220152 | 1205 | [STEAM TURBINE] ASSEMBLY MANUAL FOR EXPANDERS HEX (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-02-20 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220161 | 1206 | [STEAM TURBINE] ASSEMBLY MANUAL FOR EXPANDERS HEX (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053 | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAV-220105 | 1207 | [STEAM TURBINE] ASSEMBLY MANUAL FOR EXPANSION JOINT (BLOCK #2) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | 2019-04-05
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAV-220097 | 1208 | [STEAM TURBINE] ASSEMBLY MANUAL FOR EXPANSION JOINT (BLOCK #3,4) | FI | 2019-03-04 |  | 2019-04-05 | 2019-04-11 | MRT-DS-REC-TT-190062-FC | FC | 0 | 2019-04-11 | 190062-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-03-04 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2CJJ-240123 | 1209 | [STEAM TURBINE] ASSEMBLY MANUAL FOR FIELD INSTRUMENTATION (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-02-20 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3CJJ-240115 | 1210 | [STEAM TURBINE] ASSEMBLY MANUAL FOR FIELD INSTRUMENTATION (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAK-220082 | 1211 | [STEAM TURBINE] ASSEMBLY MANUAL FOR GEARBOX (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAX-220096 | 1212 | [STEAM TURBINE] ASSEMBLY MANUAL FOR HPH OIL SYSTEM (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | 2019-04-05
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAX-220145 | 1213 | [STEAM TURBINE] ASSEMBLY MANUAL FOR HPH OIL SYSTEM (BLOCK #3,4) | FI | 2019-03-04 |  | 2019-04-05 | 2019-04-11 | MRT-DS-REC-TT-190062-FC | FC | 0 | 2019-04-11 | 190062-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-03-04 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAV-220161 | 1214 | [STEAM TURBINE] ASSEMBLY MANUAL FOR HYDRAULIC BLOCK OF JACKING OIL (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAV-220170 | 1215 | [STEAM TURBINE] ASSEMBLY MANUAL FOR HYDRAULIC BLOCK OF JACKING OIL (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAV-240136 | 1216 | [STEAM TURBINE] ASSEMBLY MANUAL FOR INTEGRATED OIL SYSTEM (BLOCK #2) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAV-240135 | 1217 | [STEAM TURBINE] ASSEMBLY MANUAL FOR INTEGRATED OIL SYSTEM (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2LBA-220130 | 1218 | [STEAM TURBINE] ASSEMBLY MANUAL FOR LP STRAINER (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-02-20 | 2019-04-05
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3LBA-220129 | 1219 | [STEAM TURBINE] ASSEMBLY MANUAL FOR LP STRAINER (BLOCK #3,4) | FI | 2019-03-04 |  | 2019-04-05 | 2019-04-11 | MRT-DS-REC-TT-190062-FC | FC | 0 | 2019-04-11 | 190062-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-03-04 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2LBS-220090 | 1220 | [STEAM TURBINE] ASSEMBLY MANUAL FOR NON RETURN EXTRACTION FLAPS (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-02-20 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3LBC-220086 | 1221 | [STEAM TURBINE] ASSEMBLY MANUAL FOR NON RETURN EXTRACTION FLAPS (BLOCK #3,4) | FI | 2020-08-25 |  | 2020-08-26 | 2020-09-03 | MRT-DS-REC-TT-200068-FC | FI | 0 | 2020-09-03 | 200068-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-08-26 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAV-220101 | 1222 | [STEAM TURBINE] ASSEMBLY MANUAL FOR OIL CLEANING UNIT (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAV-220093 | 1223 | [STEAM TURBINE] ASSEMBLY MANUAL FOR OIL CLEANING UNIT (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220178 | 1224 | [STEAM TURBINE] ASSEMBLY MANUAL FOR PIPELINE SUPPORTS (BLOCK #2) | FI | 2020-06-22 |  | 2020-06-22 | 2020-06-24 | MRT-DS-REC-TT-200050 | FI | 0 | 2020-06-24 | 200050-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-22 | 2020-06-22
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220189 | 1225 | [STEAM TURBINE] ASSEMBLY MANUAL FOR PIPELINE SUPPORTS (BLOCK #3,4) | FI | 2019-09-01 |  | 2020-06-22 | 2020-06-24 | MRT-DS-REC-TT-200050 | FC | 1 | 2020-06-24 | 200050-FC STAMPED | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-230180 | 1226 | [STEAM TURBINE] ASSEMBLY MANUAL FOR ROTOR GROUNDING (BLOCK #2) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-230191 | 1227 | [STEAM TURBINE] ASSEMBLY MANUAL FOR ROTOR GROUNDING (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAW-220158 | 1228 | [STEAM TURBINE] ASSEMBLY MANUAL FOR STEAM COOLERS (BLOCK #2) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAW-220167 | 1229 | [STEAM TURBINE] ASSEMBLY MANUAL FOR STEAM COOLERS (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220155 | 1230 | [STEAM TURBINE] ASSEMBLY MANUAL FOR STEAM TRAPS (BLOCK #2) | FI | 2019-02-20 |  | 2019-04-01 | 2019-04-12 | MRT-DS-REC-TT-190042-FC | FC | 0 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-02-20 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220164 | 1231 | [STEAM TURBINE] ASSEMBLY MANUAL FOR STEAM TRAPS (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220131 | 1232 | [STEAM TURBINE] ASSEMBLY MANUAL FOR STEAM WATER VALVES (BLOCK #2) | FI | 2019-02-20 |  | 2021-08-24 | 2021-08-24 | MRT-DS-REC-TT-210048 | FC | 1 | 2019-04-12 | 190042-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-02-20 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220130 | 1233 | [STEAM TURBINE] ASSEMBLY MANUAL FOR STEAM WATER VALVES (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-240158 | 1234 | [STEAM TURBINE] ASSEMBLY MANUAL FOR SYNCHR. SYSTEM OF TURNING GEAR (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | 2020-05-08
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAA-220199 | 1235 | [STEAM TURBINE] ASSEMBLY MANUAL FOR THERMAL INSULATION OF TURBINE (BLOCK #2) | FI | 2019-03-14 |  | 2020-05-08 | 2020-05-20 | MRT-DS-REC-TT-200041-FC | FC | 1 | 2020-05-20 | 200041-FC STAMPED | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-03-21 | 2020-05-08
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAA-220199 | 1236 | [STEAM TURBINE] ASSEMBLY MANUAL FOR THERMAL INSULATION OF TURBINE (BLOCK #3,4) | FI | 2019-03-14 |  | 2020-05-08 | 2020-05-20 | MRT-DS-REC-TT-200041-FC | FC | 1 | 2020-05-20 | 200041-FC STAMPED | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-03-21 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAW-220108 | 1237 | [STEAM TURBINE] ASSEMBLY MANUAL FOR VALVES - CONTROL (BLOCK #2) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAW-220100 | 1238 | [STEAM TURBINE] ASSEMBLY MANUAL FOR VALVES - CONTROL (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAD-240172 | 1239 | [STEAM TURBINE] ASSEMBLY MANUAL FOR VMS (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAD-240182 | 1240 | [STEAM TURBINE] ASSEMBLY MANUAL FOR VMS (BLOCK #3,4) | FI | 2019-09-01 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P2MAM-220141 | 1241 | [STEAM TURBINE] ASSEMBLY MANUAL FOR VSC - HEX (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DM02-P3MAM-220139 | 1242 | [STEAM TURBINE] ASSEMBLY MANUAL FOR VSC - HEX (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | 2020-04-02
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2CJJ-240115 | 1243 | [STEAM TURBINE] COMMISSIONING MANUAL FOR CONTROL SYSTEM (BLOCK #2) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | 2020-04-02
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3CJJ-240107 | 1244 | [STEAM TURBINE] COMMISSIONING MANUAL FOR CONTROL SYSTEM (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | 2020-04-02
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2CJJ-240124 | 1245 | [STEAM TURBINE] COMMISSIONING MANUAL FOR FIELD INSTRUMENTATION (BLOCK #2) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | 2020-04-02
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3CJJ-240116 | 1246 | [STEAM TURBINE] COMMISSIONING MANUAL FOR FIELD INSTRUMENTATION (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAX-220097 | 1247 | [STEAM TURBINE] COMMISSIONING MANUAL FOR HPH OIL SYSTEM (BLOCK #2) | FA | 2020-06-30 |  | 2020-06-29 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | 2023-01-30 | MTW-CS-OM-LT-23.3598.0 | FA | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | 2020-04-02
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAX-220146 | 1248 | [STEAM TURBINE] COMMISSIONING MANUAL FOR HPH OIL SYSTEM (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2023-10-19 | 2023-10-19 | MRT-DS-REC-TT-230015 | FC | 2 | 2023-11-19 | DEEMED APPROVAL | FC | 2 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAV-220162 | 1249 | [STEAM TURBINE] COMMISSIONING MANUAL FOR HYDRAULIC BLOCK OF JACKING OIL (BLOCK #2) | FA | 2020-06-30 |  | 2020-06-29 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | 2023-01-30 | MTW-CS-OM-LT-23.3598.0 | FA | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | 2020-04-02
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAV-220171 | 1250 | [STEAM TURBINE] COMMISSIONING MANUAL FOR HYDRAULIC BLOCK OF JACKING OIL (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2023-10-19 | 2023-10-19 | MRT-DS-REC-TT-230015 | FC | 1 | 2023-11-19 | DEEMED APPROVAL | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | 2020-04-02
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAV-240137 | 1251 | [STEAM TURBINE] COMMISSIONING MANUAL FOR INTEGRATED OIL SYSTEM (BLOCK #2) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | 2020-04-02
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAV-240136 | 1252 | [STEAM TURBINE] COMMISSIONING MANUAL FOR INTEGRATED OIL SYSTEM (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAV-220102 | 1253 | [STEAM TURBINE] COMMISSIONING MANUAL FOR OIL CLEANING UNIT (BLOCK #2) | FA | 2020-06-30 |  | 2020-06-29 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | 2023-01-30 | MTW-CS-OM-LT-23.3598.0 | FA | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | 2020-04-02
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAV-220094 | 1254 | [STEAM TURBINE] COMMISSIONING MANUAL FOR OIL CLEANING UNIT (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2023-10-19 | 2023-10-19 | MRT-DS-REC-TT-230015 | FC | 2 | 2023-11-19 | DEEMED APPROVAL | FC | 2 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | 2019-04-01
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAA-220205 | 1255 | [STEAM TURBINE] COMMISSIONING MANUAL FOR STEAM TURBINE AND ACCESSORIES (BLOCK 2) | FA | 2018-12-14 | 2019-02-15 | 2019-07-09 | 2019-07-12 | MRT-DS-REC-TT-190139-FC | FC | 1 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-02-12 | 2019-07-26
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAA-220205 | 1256 | [STEAM TURBINE] COMMISSIONING MANUAL FOR STEAM TURBINE AND ACCESSORIES (BLOCK 3,4) | FA | 2019-02-15 | 2019-04-12 | 2019-07-26 | 2019-08-02 | MRT-DS-REC-TT-190157-FC | FC | 0 | 2021-01-14 | 001/SER.00.01/LE/2021 | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-07-11 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAD-240173 | 1257 | [STEAM TURBINE] COMMISSIONING MANUAL FOR VMS (BLOCK #2) | FA | 2020-06-30 |  | 2020-06-29 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | 2023-01-30 | MTW-CS-OM-LT-23.3598.0 | FA | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | 2020-04-02
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAD-240183 | 1258 | [STEAM TURBINE] COMMISSIONING MANUAL FOR VMS (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-05 | MTW-CS-OM-LT-23.3450.0 | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-DN05-P2MAM-220142 | 1259 | [STEAM TURBINE] COMMISSIONING MANUAL FOR VSC - HEX (BLOCK #2) | FA | 2020-06-30 |  | 2020-06-29 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | 2023-01-30 | MTW-CS-OM-LT-23.3598.0 | FA | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | 2020-04-02
DHI | TG_SKODA | 백운홍 | MRT-DN05-P3MAM-220140 | 1260 | [STEAM TURBINE] COMMISSIONING MANUAL FOR VSC - HEX (BLOCK #3,4) | FA | 2019-12-31 | 2020-02-29 | 2020-04-02 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | 2023-01-30 | MTW-CS-OM-LT-23.3599.0 | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | 2019-04-05
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220201 | 1261 | [STEAM TURBINE] OPERATION INSTRUCTION FOR STEAM TURBINE (BLOCK 2) | FI | 2018-12-14 |  | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220045 | FC | 3 | 2023-01-21 | DEEMED APPROVAL | FC | 3 | A | SUPPORT | STEAM TURBINE | 2019-03-04 | 2019-07-26
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220201 | 1262 | [STEAM TURBINE] OPERATION INSTRUCTION FOR STEAM TURBINE (BLOCK 3,4) | FI | 2019-02-15 |  | 2020-12-03 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FC | 1 | 2020-12-03 | 200084-FC STAMPED | FC | 1 | A | SUPPORT | STEAM TURBINE | 2019-07-11 | 2019-07-26
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220202 | 1263 | [STEAM TURBINE] MAINTENANCE INSTRUCTION FOR STEAM TURBINE (BLOCK 2) | FI | 2018-12-14 |  | 2019-07-26 | 2019-08-02 | MRT-DS-REC-TT-190157-FC | FC | 0 | 2019-08-02 | 190157-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-07-11 | 2019-09-09
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220202 | 1264 | [STEAM TURBINE] MAINTENANCE INSTRUCTION FOR STEAM TURBINE (BLOCK 3,4) | FI | 2019-02-15 |  | 2019-09-09 | 2019-09-09 | MRT-DS-REC-TT-190166-FC | FC | 0 | 2019-09-09 | 190166-FC STAMPED | FC | 0 | A | SUPPORT | STEAM TURBINE | 2019-07-24 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220203 | 1265 | [STEAM TURBINE] SUMMARY OPERATION AND MAINTENANCE INSTRUCTIONS (BLOCK #2) | FI | 2020-07-14 |  | 2020-07-14 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | 2020-07-20 | 200060-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-07-14 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220203 | 1266 | [STEAM TURBINE] SUMMARY OPERATION AND MAINTENANCE INSTRUCTIONS (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-08-25 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2CJJ-240116 | 1267 | [STEAM TURBINE] O&M MANUAL FOR CONTROL SYSTEM (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3CJJ-240108 | 1268 | [STEAM TURBINE] O&M MANUAL FOR CONTROL SYSTEM (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-08-25 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220153 | 1269 | [STEAM TURBINE] O&M MANUAL FOR EXPANDERS HEX (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220162 | 1270 | [STEAM TURBINE] O&M MANUAL FOR EXPANDERS HEX (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-08-25 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAV-220106 | 1271 | [STEAM TURBINE] O&M MANUAL FOR EXPANSION JOINT (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAV-220098 | 1272 | [STEAM TURBINE] O&M MANUAL FOR EXPANSION JOINT (BLOCK #3,4) | FI | 2020-11-26 |  | 2020-12-03 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FI | 0 | 2020-12-03 | 200084-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-12-03 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2CJJ-240125 | 1273 | [STEAM TURBINE] O&M MANUAL FOR FIELD INSTRUMENTATION (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3CJJ-240117 | 1274 | [STEAM TURBINE] O&M MANUAL FOR FIELD INSTRUMENTATION (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAK-220084 | 1275 | [STEAM TURBINE] O&M MANUAL FOR GEARBOX (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAX-220098 | 1276 | [STEAM TURBINE] O&M MANUAL FOR HPH OIL SYSTEM (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAX-220147 | 1277 | [STEAM TURBINE] O&M MANUAL FOR HPH OIL SYSTEM (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAV-220163 | 1278 | [STEAM TURBINE] O&M MANUAL FOR HYDRAULIC BLOCK OF JACKING OIL (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAV-220172 | 1279 | [STEAM TURBINE] O&M MANUAL FOR HYDRAULIC BLOCK OF JACKING OIL (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAV-240138 | 1280 | [STEAM TURBINE] O&M MANUAL FOR INTEGRATED OIL SYSTEM (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAV-240137 | 1281 | [STEAM TURBINE] O&M MANUAL FOR INTEGRATED OIL SYSTEM (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAV-220103 | 1282 | [STEAM TURBINE] O&M MANUAL FOR OIL CLEANING UNIT (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAV-220095 | 1283 | [STEAM TURBINE] O&M MANUAL FOR OIL CLEANING UNIT (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-08-25 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-240145 | 1284 | [STEAM TURBINE] O&M MANUAL FOR OVER SPEED PROTECTION (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220194 | 1285 | [STEAM TURBINE] O&M MANUAL FOR POK POD DN40 (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220194 | 1286 | [STEAM TURBINE] O&M MANUAL FOR POK POD DN40 (BLOCK #3,4) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-230181 | 1287 | [STEAM TURBINE] O&M MANUAL FOR ROTOR GROUNDING (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAW-220159 | 1288 | [STEAM TURBINE] O&M MANUAL FOR STEAM COOLERS (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAW-220168 | 1289 | [STEAM TURBINE] O&M MANUAL FOR STEAM COOLERS (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-08-25 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220156 | 1290 | [STEAM TURBINE] O&M MANUAL FOR STEAM TRAPS (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220165 | 1291 | [STEAM TURBINE] O&M MANUAL FOR STEAM TRAPS (BLOCK #3,4) | FI | 2020-08-25 |  | 2020-08-26 | 2020-09-03 | MRT-DS-REC-TT-200068-FC | FI | 0 | 2020-09-03 | 200068-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-08-26 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-240159 | 1292 | [STEAM TURBINE] O&M MANUAL FOR SYNCHR. SYSTEM OF TURNING GEAR (BLOCK #3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-08-25 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2LBS-220088 | 1293 | [STEAM TURBINE] O&M MANUAL FOR VALVES - BUTTERFLY VALVES FOR ISOLATION AND CONTROL (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3LBA-220084 | 1294 | [STEAM TURBINE] O&M MANUAL FOR VALVES - BUTTERFLY VALVES FOR ISOLATION AND CONTROL (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAW-220109 | 1295 | [STEAM TURBINE] O&M MANUAL FOR VALVES - CONTROL (BLOCK #2) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAW-220101 | 1296 | [STEAM TURBINE] O&M MANUAL FOR VALVES - CONTROL (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAA-220132 | 1297 | [STEAM TURBINE] O&M MANUAL FOR VALVES - STEAM & WATER (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAA-220131 | 1298 | [STEAM TURBINE] O&M MANUAL FOR VALVES - STEAM & WATER (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAD-240174 | 1299 | [STEAM TURBINE] O&M MANUAL FOR VMS (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAD-240184 | 1300 | [STEAM TURBINE] O&M MANUAL FOR VMS (BLOCK #3,4) | FI | 2019-12-31 |  | 2019-11-28 | 2019-12-07 | MRT-DS-REC-TT-190234-FC | FI | 0 | 2019-12-09 | 190234-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2019-11-28 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P2MAM-220143 | 1301 | [STEAM TURBINE] O&M MANUAL FOR VSC - HEX (BLOCK #2) | FI | 2020-06-30 |  | 2020-06-29 | 2020-06-30 | MRT-DS-REC-TT-200053-FC | FI | 0 | 2020-06-30 | 200053-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-06-29 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CQ02-P3MAM-220141 | 1302 | [STEAM TURBINE] O&M MANUAL FOR VSC - HEX (BLOCK#3,4) | FI | 2020-08-14 |  | 2020-08-25 | 2020-08-26 | MRT-DS-REC-TT-200066-FC | FI | 0 | 2020-08-26 | 200066-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-08-25 | #VALUE!
DHI | TG_SKODA | 백운홍 | MRT-CY05-P3CJJ-240109 | 1303 | [STEAM TURBINE] TRAINING MANUAL FOR CONTROL SYSTEM (BLOCK #3,4) | FI | 2020-08-25 |  | 2020-08-26 | 2020-09-03 | MRT-DS-REC-TT-200068-FC | FI | 0 | 2020-09-03 | 200068-FC STAMPED | FI | 0 | A | SUPPORT | STEAM TURBINE | 2020-08-26 | 2018-02-19
DHI | HEX | 이승찬 | MRT-YD00-P0PGB-606000 | 1304 | [CCW HEAD TANK]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER HEAD TANK | FA | 2017-09-29 | 2017-12-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-04 | 180599-FC STAMPED | FC | 3 | A | MECHANICAL | CCW HEAD TANK | 2017-09-29 | 2018-02-19
DHI | HEX | 이승찬 | MRT-YD00-P0PGB-606001 | 1305 | [CCW HEAD TANK]_GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER CHEMICAL DOSING TANK | FA | 2017-09-29 | 2017-12-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-23 | 180785-FC STAMPED | FC | 4 | A | MECHANICAL | CCW HEAD TANK | 2017-09-29 | 2018-06-15
DHI | HEX | 이승찬 | MRT-YK08-P2MAG-601001 | 1306 | Condenser #2_General Layout | FA | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-21 | 180500-FC STAMPED | FC | 4 | A | MECHANICAL | CONDENSER | 2017-08-21 | 2018-05-28
DHI | HEX | 이승찬 | MRT-YK08-P2MAG-601002 | 1307 | Condenser #2_General Arrangement | FA | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-15 | 180434-FC STAMPED | FC | 3 | A | MECHANICAL | CONDENSER | 2017-08-29 | 2018-06-15
DHI | HEX | 이승찬 | MRT-XL00-P2MAG-601003 | 1308 | Condenser #2_Connection List | FI | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-21 | 180501-FC STAMPED | FC | 4 | A | MECHANICAL | CONDENSER | 2017-08-29 | 2018-06-15
DHI | HEX | 이승찬 | MRT-XL00-P2MAG-601004 | 1309 | Condenser #2_Connection Detail | FI | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-21 | 180501-FC STAMPED | FC | 3 | A | MECHANICAL | CONDENSER | 2017-08-29 | 2018-03-09
DHI | HEX | 이승찬 | MRT-VL00-P2MAG-601005 | 1310 | Condenser #2_Foundation Assembly | FA | 2017-08-31 | 2017-12-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-13 | 180168-FC STAMPED | FC | 2 | A | CIVIL | CONDENSER | 2017-08-31 | 2018-03-09
DHI | HEX | 이승찬 | MRT-VL00-P2MAG-601006 | 1311 | Condenser #2_Foundation Detail | FA | 2017-08-31 | 2017-12-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-13 | 180168-FC STAMPED | FC | 2 | A | CIVIL | CONDENSER | 2017-08-31 | 2018-07-02
DHI | HEX | 이승찬 | MRT-YT01-P2MAG-601007 | 1312 | Condenser #2_Data Sheet | FA | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-24 | 180557-FC STAMPED | FC | 4 | A | MECHANICAL | CONDENSER | 2017-09-26 | #VALUE!
DHI | HEX | 이승찬 | MRT-YT01-P2MAG-601008 | 1313 | Condenser #2_Nozzle Force and Moment | FI | 2017-08-31 |  | 2018-03-09 | 2018-03-09 | MRT-DS-REC-TT-180167 | FI | 2 | 2018-04-03 | 151/T/MRT/REC/IV/2018 | FI | 2 | I | MECHANICAL | CONDENSER | 2017-09-26 | #VALUE!
DHI | HEX | 이승찬 | MRT-YT01-P2MAG-601009 | 1314 | Condenser #2_Performance Curves | FI | 2017-08-31 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-02-02 | 02.012/E04/PLNE/II/2018 | FI | 1 | A | MECHANICAL | CONDENSER | 2017-09-26 | 2018-09-14
DHI | HEX | 이승찬 | MRT-YL00-P2MAG-601010 | 1315 | Condenser #2_Instrument list and Datasheet for Condenser #2 | FA | 2018-05-30 | 2018-07-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-16 | 180738-FC STAMPED | FC | 1 | A | I&C | CONDENSER | 2018-07-02 | 2018-08-27
DHI | HEX | 이승찬 | MRT-CQ02-P2MAG-601011 | 1316 | Condenser #2_Instruction Manuals for Erection, Installation, Operation and Maintenance | FI | 2018-07-31 | 2018-09-30 | 2018-08-27 | 2018-11-09 | MRT-DS-REC-TT-180651-FC | FC | 0 | 2018-11-09 | 180651-FC STAMPED | FC | 0 | A | SUPPORT | CONDENSER | 2018-07-24 | 2018-06-15
DHI | HEX | 이승찬 | MRT-YK08-P3MAG-602001 | 1317 | Condenser #3,4_General Layout | FA | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER | 2017-08-21 | 2018-05-28
DHI | HEX | 이승찬 | MRT-YK08-P3MAG-602002 | 1318 | Condenser #3,4_General Arrangement | FA | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER | 2017-08-29 | 2018-06-15
DHI | HEX | 이승찬 | MRT-XL00-P3MAG-602003 | 1319 | Condenser #3,4_Connection List | FI | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER | 2017-08-29 | 2018-06-15
DHI | HEX | 이승찬 | MRT-XL00-P3MAG-602004 | 1320 | Condenser #3,4_Connection Detail | FI | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER | 2017-08-29 | 2018-03-09
DHI | HEX | 이승찬 | MRT-VL00-P3MAG-602005 | 1321 | Condenser #3,4_Foundation Assembly | FA | 2017-08-31 | 2017-12-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-13 | 180168-FC STAMPED | FC | 2 | A | CIVIL | CONDENSER | 2017-08-31 | 2018-03-09
DHI | HEX | 이승찬 | MRT-VL00-P3MAG-602006 | 1322 | Condenser #3,4_Foundation Detail | FA | 2017-08-31 | 2017-12-29 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-13 | 180168-FC STAMPED | FC | 2 | A | CIVIL | CONDENSER | 2017-08-31 | 2018-07-02
DHI | HEX | 이승찬 | MRT-YT01-P3MAG-602007 | 1323 | Condenser #3,4_Data Sheet | FA | 2017-08-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER | 2017-09-26 | #VALUE!
DHI | HEX | 이승찬 | MRT-YT01-P3MAG-602008 | 1324 | Condenser #3,4_Nozzle Force and Moment | FI | 2017-08-31 |  | 2018-03-09 | 2018-03-09 | MRT-DS-REC-TT-180167 | FI | 2 | 2018-04-03 | 151/T/MRT/REC/IV/2018 | FI | 2 | I | MECHANICAL | CONDENSER | 2017-09-26 | #VALUE!
DHI | HEX | 이승찬 | MRT-YT01-P3MAG-602009 | 1325 | Condenser #3,4_Performance Curves | FI | 2017-08-31 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER | 2017-09-26 | 2018-09-14
DHI | HEX | 이승찬 | MRT-YL00-P3MAG-602010 | 1326 | Condenser #3,4_Instrument list and Datasheet for Condenser #3,4 | FA | 2018-05-30 | 2018-07-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | I&C | CONDENSER | 2018-07-02 | 2018-11-12
DHI | HEX | 이승찬 | MRT-CQ02-P3MAG-602011 | 1327 | Condenser #3,4_Instruction Manuals for Erection, Installation, Operation and Maintenance | FI | 2018-08-31 | 2018-10-31 | 2018-11-12 | 2018-12-03 | MRT-DS-REC-TT-180807-FC | FC | 0 | 2018-12-08 | 180807-FC STAMPED | FC | 0 | A | SUPPORT | CONDENSER | 2018-10-05 | 2018-05-11
DHI | HEX | 이승찬 | MRT-YT01-P2PAH-604101 | 1328 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_Technical Data Sheet | FA | 2017-11-17 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-27 | 180392-FC STAMPED | FC | 2 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-11-21 | 2018-05-11
DHI | HEX | 이승찬 | MRT-XG02-P2PAH-604102 | 1329 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_P & I Diagram | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-23 | 180391-FC STAMPRED | FC | 2 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-10-13 | 2018-05-11
DHI | HEX | 이승찬 | MRT-YK08-P2PAH-604103 | 1330 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_Outline Drawing | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-23 | 180391-FC STAMPRED | FC | 2 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-10-13 | 2018-05-11
DHI | HEX | 이승찬 | MRT-YK08-P2PAH-604104 | 1331 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_Outline Drawing for Ball Recirculation unit | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2021-04-27 | 051/T/MRT/REC/IV/2021 | FC | 3 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-10-13 | 2019-01-24
DHI | HEX | 이승찬 | MRT-CQ02-P2PAH-604105 | 1332 | [CTCS & Debris Filter]_O&M Manual For Condenser Tube Cleaning System #2 | FI | 2018-12-14 | 2019-01-14 | 2019-01-24 | 2019-01-24 | MRT-DS-REC-TT-180937-FC | FC | 0 | 2019-01-25 | 180937-FC STAMPED | FC | 0 | A | SUPPORT | CONDENSER TUBE CLEANING | 2018-12-21 | 2018-05-11
DHI | HEX | 이승찬 | MRT-YT01-P2PBB-604111 | 1333 | [CTCS & Debris Filter]_Debris Filter_Technical Data Sheet | FA | 2017-11-17 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-27 | 180392-FC STAMPED | FC | 2 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-11-21 | 2018-05-11
DHI | HEX | 이승찬 | MRT-XG02-P2PBB-604112 | 1334 | [CTCS & Debris Filter]_Debris Filter_P & I Diagram for Block 2 | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-12-10 | 180794-FC STAMPED | FC | 3 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-10-13 | 2018-05-11
DHI | HEX | 이승찬 | MRT-YK08-P2PBB-604113 | 1335 | [CTCS & Debris Filter]_Debris Filter_Outline Drawing | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-23 | 180391-FC STAMPRED | FC | 2 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-10-13 | 2019-01-24
DHI | HEX | 이승찬 | MRT-CQ02-P2PBB-604114 | 1336 | [CTCS & Debris Filter]_O&M Manual For Debris Filter #2 | FI | 2018-12-14 | 2019-01-14 | 2019-01-24 | 2019-01-24 | MRT-DS-REC-TT-180937-FC | FC | 0 | 2019-01-25 | 180937-FC STAMPED | FC | 0 | A | SUPPORT | CONDENSER TUBE CLEANING | 2018-12-21 | 2018-03-26
DHI | HEX | 이승찬 | MRT-YF00-P2PAH-604121 | 1337 | [CTCS & Debris Filter]_Control Logic for CTCS & Debris Filter | FI | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-01 | 180772-FC STAMPED | FC | 2 | A | I&C | CONDENSER TUBE CLEANING | 2018-01-26 | 2018-03-26
DHI | HEX | 이승찬 | MRT-YV02-P2PAH-604122 | 1338 | [CTCS & Debris Filter]_Cable Connection & Wiring Diagram for CTCS & Debris Filter | FI | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-01 | 180772-FC STAMPED | FC | 3 | A | ELECTRICAL | CONDENSER TUBE CLEANING | 2018-01-26 | 2018-05-11
DHI | HEX | 이승찬 | MRT-YB03-P2PAH-604123 | 1339 | [CTCS & Debris Filter]_Configuration Diagram of Package System for CTCS & Debris Filter | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-01 | 180772-FC STAMPED | FC | 4 | A | I&C | CONDENSER TUBE CLEANING | 2018-01-26 | 2018-03-26
DHI | HEX | 이승찬 | MRT-YK08-P2PAH-604124 | 1340 | [CTCS & Debris Filter]_Outline Drawing for Control Panel of CTCS & Debris Filter | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-01 | 180772-FC STAMPED | FC | 5 | A | I&C | CONDENSER TUBE CLEANING | 2018-01-26 | 2018-05-11
DHI | HEX | 이승찬 | MRT-YT01-P3PAH-604501 | 1341 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_Technical Data Sheet | FA | 2017-11-17 | 2018-04-30 | 2024-11-25 | 2024-11-25 | MRT-DS-REC-TT-240039 | AB | Z2 | 2024-11-29 | MTW-AS-C-LT-24.6004.0 | AB | Z2 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-11-21 | 2018-05-11
DHI | HEX | 이승찬 | MRT-XG02-P3PAH-604502 | 1342 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_P & I Diagram | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-06-21 | MTW-AS-C-LT-24.5406.0 | AB | Z0 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-10-13 | 2018-05-11
DHI | HEX | 이승찬 | MRT-YK08-P3PAH-604503 | 1343 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_Outline Drawing | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-10-13 | 2018-05-11
DHI | HEX | 이승찬 | MRT-YK08-P3PAH-604504 | 1344 | [CTCS & Debris Filter]_Condenser Tube Cleaning System_Outline Drawing for Ball Recirculation unit | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-10-13 | 2019-01-24
DHI | HEX | 이승찬 | MRT-CQ02-P2PAH-604505 | 1345 | [CTCS & Debris Filter]_O&M Manual For Condenser Tube Cleaning System #3, 4 | FI | 2018-12-14 | 2019-01-14 | 2019-01-24 | 2019-01-24 | MRT-DS-REC-TT-180937-FC | FC | 0 | 2019-01-25 | 180937-FC STAMPED | FC | 0 | A | SUPPORT | CONDENSER TUBE CLEANING | 2018-12-21 | 2018-05-11
DHI | HEX | 이승찬 | MRT-YT01-P3PBB-604511 | 1346 | [CTCS & Debris Filter]_Debris Filter_Technical Data Sheet | FA | 2017-11-17 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-11-21 | 2018-05-11
DHI | HEX | 이승찬 | MRT-XG02-P3PBB-604512 | 1347 | [CTCS & Debris Filter]_Debris Filter_P & I Diagram for Block 3,4 | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-06-21 | MTW-AS-C-LT-24.5406.0 | AB | Z0 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-10-13 | 2018-05-11
DHI | HEX | 이승찬 | MRT-YK08-P3PBB-604513 | 1348 | [CTCS & Debris Filter]_Debris Filter_Outline Drawing | FA | 2017-10-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | CONDENSER TUBE CLEANING | 2017-10-13 | 2019-01-24
DHI | HEX | 이승찬 | MRT-CQ02-P2PBB-604514 | 1349 | [CTCS & Debris Filter]_O&M Manual For Debris Filter #3, 4 | FI | 2018-12-14 | 2019-01-14 | 2019-01-24 | 2019-01-24 | MRT-DS-REC-TT-180937-FC | FC | 0 | 2019-01-25 | 180937-FC STAMPED | FC | 0 | A | SUPPORT | CONDENSER TUBE CLEANING | 2018-12-21 | 2018-03-26
DHI | HEX | 이승찬 | MRT-YF00-P3PAH-604521 | 1350 | [CTCS & Debris Filter]_Control Logic for CTCS & Debris Filter | FI | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | I&C | CONDENSER TUBE CLEANING | 2018-01-26 | 2018-03-26
DHI | HEX | 이승찬 | MRT-YV02-P3PAH-604522 | 1351 | [CTCS & Debris Filter]_Cable Connection & Wiring Diagram for CTCS & Debris Filter | FI | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-15 | MTW-AS-C-LT-24.5844.0 | AB | Z0 | A | ELECTRICAL | CONDENSER TUBE CLEANING | 2018-01-26 | 2018-04-18
DHI | HEX | 이승찬 | MRT-YB03-P3PAH-604523 | 1352 | [CTCS & Debris Filter]_Configuration Diagram of Package System for CTCS & Debris Filter | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | I&C | CONDENSER TUBE CLEANING | 2018-01-26 | 2018-03-26
DHI | HEX | 이승찬 | MRT-YK08-P3PAH-604524 | 1353 | [CTCS & Debris Filter]_Outline Drawing for Control Panel of CTCS & Debris Filter | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | I&C | CONDENSER TUBE CLEANING | 2018-01-26 | 2018-05-10
DHI | HEX | 곽주영 | MRT-YK08-P2LAA-605100 | 1354 | Outline Drawing for Deaerator & Storage Tank #2 | FA | 2017-09-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-29 | 180384-FC STAMPED | FC | 4 | A | MECHANICAL | DEAERATOR | 2017-09-29 | 2018-05-10
DHI | HEX | 곽주영 | MRT-YT01-P2LAA-605101 | 1355 | Datasheet for Deaerator & Storage Tank #2 | FA | 2017-09-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-08-25 | 180383-FC STAMPED | FC | 4 | A | MECHANICAL | DEAERATOR | 2017-09-29 | 2018-06-18
DHI | HEX | 곽주영 | MRT-YK08-P2LAA-605102 | 1356 | Insulation Support Detail for Deaerator & Storage Tank #2 | FI | 2017-12-22 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-21 | 180514-FC STAMPED | FC | 4 | A | MECHANICAL | DEAERATOR | 2017-10-19 | 2018-07-27
DHI | HEX | 곽주영 | MRT-CQ02-P2LAA-605103 | 1357 | Installation and O&M Manual For Deaerator & Feedwater Storage Tank #2 | FI | 2018-06-29 | 2018-09-28 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180598-FC | FC | 0 | 2018-10-05 | 180598-FC STAMPED | FC | 0 | A | SUPPORT | DEAERATOR | 2018-07-13 | 2018-05-10
DHI | HEX | 곽주영 | MRT-YK08-P3LAA-605500 | 1358 | Outline Drawing for Deaerator & Storage Tank #3,4 | FA | 2017-09-29 | 2018-04-30 | 2024-04-08 | 2024-04-08 | MRT-DS-REC-TT-240008 | AB | Z1 | 2024-04-25 | MTW-AS-C-LT-24.5184.0 | AB | Z1 | A | MECHANICAL | DEAERATOR | 2017-09-29 | 2018-05-10
DHI | HEX | 곽주영 | MRT-YT01-P3LAA-605501 | 1359 | Datasheet for Deaerator & Storage Tank #3,4 | FA | 2017-09-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | DEAERATOR | 2017-09-29 | 2018-06-18
DHI | HEX | 곽주영 | MRT-YK08-P3LAA-605502 | 1360 | Insulation Support Detail for Deaerator & Storage Tank #3,4 | FI | 2017-12-22 | 2018-05-31 | 2024-04-08 | 2024-04-08 | MRT-DS-REC-TT-240008 | AB | Z1 | 2024-04-25 | MTW-AS-C-LT-24.5184.0 | AB | Z1 | A | MECHANICAL | DEAERATOR | 2017-10-19 | 2018-07-27
DHI | HEX | 곽주영 | MRT-CQ02-P3LAA-605503 | 1361 | Installation and O&M Manual For Deaerator & Feedwater Storage Tank #3,4 | FI | 2018-06-29 | 2018-09-28 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180598-FC | FC | 0 | 2018-10-05 | 180598-FC STAMPED | FC | 0 | A | SUPPORT | DEAERATOR | 2018-07-13 | 2018-04-26
DHI | HEX | 이승찬 | MRT-YD00-P0QHE-606001 | 1362 | [FLASH TANK]_GENERAL ARRANGEMENT DRAWING FOR ATMOSPHERIC FLASH TANK | FA | 2017-11-10 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-23 | 180785-FC STAMPED | FC | 4 | A | MECHANICAL | FLASH TANK | 2017-11-10 | 2018-06-15
DHI | HEX | 이승찬 | MRT-YD00-P2QHE-606003 | 1363 | [FLASH TANK]_GENERAL ARRANGEMENT DRAWING FOR VACUUM FLASH TANK (For Block 2) | FA | 2017-12-13 | 2018-05-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-23 | 180785-FC STAMPED | FC | 3 | A | MECHANICAL | FLASH TANK | 2017-12-07 | 2018-06-15
DHI | HEX | 이승찬 | MRT-YD00-P3QHE-606003 | 1364 | [FLASH TANK]_GENERAL ARRANGEMENT DRAWING FOR VACUUM FLASH TANK (For Block 3, 4) | FA | 2017-12-13 | 2018-05-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | FLASH TANK | 2017-12-07 | 2018-06-15
DHI | HEX | 이승찬 | MRT-YD00-P0ERB-606001 | 1365 | [C&D TANK]_GENERAL ARRANGEMENT DRAWING FOR CLEAN OIL TANK | FA | 2017-12-13 | 2018-05-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2020-02-25 | 200003-FC STAMPED | FC | 4 | A | MECHANICAL | OIL TANK | 2017-12-07 | 2018-06-15
DHI | HEX | 이승찬 | MRT-YD00-P0ERB-606002 | 1366 | [C&D TANK]_GENERAL ARRANGEMENT DRAWING FOR DIRTY OIL TANK | FA | 2017-12-13 | 2018-05-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2020-02-25 | 200003-FC STAMPED | FC | 4 | A | MECHANICAL | OIL TANK | 2017-12-07 | 2018-04-26
DHI | HEX | 이진재 | MRT-YL00-P2MAJ-603107 | 1367 | Steam Jet Air Ejector #2 - System Description | FA | 2017-10-31 | 2018-05-31 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180344-FC | FC | 3 | 2018-09-08 | 180344-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-11-09 | 2018-03-08
DHI | HEX | 이진재 | MRT-YT01-P2MAJ-603100 | 1368 | Steam Jet Air Ejector #2 - Technical Data Sheet | FA | 2017-10-31 | 2018-02-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-29 | 180713-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-11-09 | 2018-04-26
DHI | HEX | 이진재 | MRT-XG02-P2MAJ-603101 | 1369 | Steam Jet Air Ejector #2 - P&I Diagram | FA | 2017-10-31 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-29 | 180713-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-11-09 | 2018-03-14
DHI | HEX | 이진재 | MRT-YK08-P2MAJ-603102 | 1370 | Steam Jet Air Ejector #2 - Outline drawing | FA | 2017-10-31 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-29 | 180713-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-11-09 | 2018-03-14
DHI | HEX | 이진재 | MRT-YT01-P2MAJ-603103 | 1371 | Steam Jet Air Ejector #2 - Heat Exchanger Data & Drawing | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-05 | 180593-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-12-23 | #VALUE!
DHI | HEX | 이진재 | MRT-YT01-P2MAJ-603104 | 1372 | Steam Jet Air Ejector #2 - Performance Curves | FI | 2017-10-31 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-02-26 | 025/T/MRT/REC/II/2018 | FI | 1 | I | MECHANICAL | STEAM JET AIR EJECTOR | 2017-11-09 | 2018-07-12
DHI | HEX | 이진재 | MRT-YL00-P2MAJ-603105 | 1373 | Steam Jet Air Ejector #2 - Instrument List and Data Sheet | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-12-11 | 180714-FC STAMPED | FC | 5 | A | I&C | STEAM JET AIR EJECTOR | 2017-12-23 | 2018-04-26
DHI | HEX | 이진재 | MRT-XN00-P2MAJ-603106 | 1374 | Steam Jet Air Ejector #2 - Valve List and Data Sheet | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-29 | 180713-FC STAMPED | FC | 4 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-12-23 | 2018-07-17
DHI | HEX | 이진재 | MRT-YV02-P2MAJ-603108 | 1375 | Steam Jet Air Ejector #2 - Wiring Diagram | FI | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-12-11 | 180714-FC STAMPED | FC | 5 | A | ELECTRICAL | STEAM JET AIR EJECTOR | 2017-12-23 | 2018-07-27
DHI | HEX | 이진재 | MRT-CQ02-P2MAJ-603109 | 1376 | Steam Jet Air Ejector #2 - Instruction manual | FI | 2018-07-31 | 2018-10-31 | 2018-07-27 | 2018-08-20 | MRT-DS-REC-TT-180281-FC | FC | 0 | 2018-09-03 | 180281-FC STAMPED | FC | 0 | A | SUPPORT | STEAM JET AIR EJECTOR | 2018-04-05 | 2018-04-26
DHI | HEX | 이진재 | MRT-YL00-P3MAJ-604107 | 1377 | Steam Jet Air Ejector #3,4 - System Description | FA | 2017-10-31 | 2018-05-31 | 2018-07-27 | 2018-08-27 | MRT-DS-REC-TT-180344-FC | FC | 3 | 2018-09-08 | 180344-FC STAMPED | FC | 3 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-11-09 | 2018-03-08
DHI | HEX | 이진재 | MRT-YT01-P3MAJ-604100 | 1378 | Steam Jet Air Ejector #3,4 - Technical Data Sheet | FA | 2017-10-31 | 2018-02-28 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-11-09 | 2018-04-26
DHI | HEX | 이진재 | MRT-XG02-P3MAJ-604101 | 1379 | Steam Jet Air Ejector #3,4 - P&I Diagram | FA | 2017-10-31 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-06-21 | MTW-AS-C-LT-24.5406.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-11-09 | 2018-03-14
DHI | HEX | 이진재 | MRT-YK08-P3MAJ-604102 | 1380 | Steam Jet Air Ejector #3,4 - Outline drawing | FA | 2017-10-31 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-11-09 | 2018-03-14
DHI | HEX | 이진재 | MRT-YT01-P3MAJ-604103 | 1381 | Steam Jet Air Ejector #3,4 - Heat Exchanger Data & Drawing | FA | 2017-12-29 | 2018-04-30 | 2024-11-20 | 2024-11-20 | MRT-DS-REC-TT-240038 | AB | Z1 | 2024-11-28 | MTW-AS-C-LT-24.5999.0 | AB | Z1 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-12-23 | #VALUE!
DHI | HEX | 이진재 | MRT-YT01-P3MAJ-604104 | 1382 | Steam Jet Air Ejector #3,4 - Performance Curves | FI | 2017-10-31 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-11-09 | 2018-07-12
DHI | HEX | 이진재 | MRT-YL00-P3MAJ-604105 | 1383 | Steam Jet Air Ejector #3,4 - Instrument List and Data Sheet | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | I&C | STEAM JET AIR EJECTOR | 2017-12-23 | 2018-04-26
DHI | HEX | 이진재 | MRT-XN00-P3MAJ-604106 | 1384 | Steam Jet Air Ejector #3,4 - Valve List and Data Sheet | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2017-12-23 | 2018-07-17
DHI | HEX | 이진재 | MRT-YV02-P3MAJ-604108 | 1385 | Steam Jet Air Ejector #3,4 - Wiring Diagram | FI | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | ELECTRICAL | STEAM JET AIR EJECTOR | 2017-12-23 | 2018-07-27
DHI | HEX | 이진재 | MRT-CQ02-P3MAJ-603109 | 1386 | Steam Jet Air Ejector #3,4 - Instruction manual | FI | 2018-07-31 | 2018-10-31 | 2018-07-27 | 2018-08-20 | MRT-DS-REC-TT-180281-FC | FC | 0 | 2018-09-03 | 180281-FC STAMPED | FC | 0 | A | SUPPORT | STEAM JET AIR EJECTOR | 2018-04-05 | 2018-06-15
DHI | HEX | 이승찬 | MRT-YT01-P2MAJ-603110 | 1387 | Steam Jet Air Ejector #2 - Data Sheet for Silencer | FI | 2018-01-12 | 2018-06-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-24 | 180505-FC STAMPED | FC | 2 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2018-01-19 | 2018-04-26
DHI | HEX | 이승찬 | MRT-YK08-P2MAJ-603308 | 1388 | Steam Jet Air Ejector #2 - Silencer Drawing | FA | 2018-01-12 | 2018-06-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-08 | 180344-FC STAMPED | FC | 1 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2018-01-19 | 2018-06-15
DHI | HEX | 이승찬 | MRT-YT01-P3MAJ-604110 | 1389 | Steam Jet Air Ejector #3,4 - Data Sheet for Silencer | FI | 2018-01-12 | 2018-06-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2018-01-19 | 2018-04-26
DHI | HEX | 이승찬 | MRT-YK08-P3MAJ-604308 | 1390 | Steam Jet Air Ejector #3,4 - Silencer Drawing | FA | 2018-01-12 | 2018-06-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | STEAM JET AIR EJECTOR | 2018-01-19 | 2018-04-19
DHI | HEX | 이진재 | MRT-YK08-P2MAJ-603200 | 1391 | Waterbox Vacuum Pump #2 - Outline Drawing | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-16 | 180658-FC STAMPED | FC | 3 | A | MECHANICAL | WATERBOX VACUUM PUMP | 2018-03-06 | 2018-06-01
DHI | HEX | 이진재 | MRT-XG02-P2MAJ-603201 | 1392 | Waterbox Vacuum Pump #2 - P & I Diagram | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-16 | 180658-FC STAMPED | FC | 4 | A | MECHANICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2018-05-15
DHI | HEX | 이진재 | MRT-YV02-P2MAJ-603202 | 1393 | Waterbox Vacuum Pump #2 - Wiring Diargam | FI | 2018-01-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2021-07-12 | 210045-FC STAMPED | FC | 3 | A | ELECTRICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2018-05-15
DHI | HEX | 이진재 | MRT-YK08-P2MAJ-603203 | 1394 | Waterbox Vacuum Pump #2 - Terminal Box | FI | 2018-01-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-10-05 | 180537-FC STAMPED | FC | 2 | A | ELECTRICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2018-04-19
DHI | HEX | 이진재 | MRT-YT01-P2MAJ-603204 | 1395 | Waterbox Vacuum Pump #2 - Technical Datasheet | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-09-13 | 180448-FC STAMPED | FC | 3 | A | MECHANICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2019-05-24
DHI | HEX | 이진재 | MRT-YK08-P2MAJ-603205 | 1396 | Waterbox Vacuum Pump #2 - Motor Datasheet & Drawings | FI | 2018-01-31 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2019-05-29 | 180269-FC STAMPED | FC | 1 | A | ELECTRICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2019-05-24
DHI | HEX | 이진재 | MRT-YT01-P2MAJ-603206 | 1397 | Waterbox Vacuum Pump #2 - Heat Exchanger Data Sheet& Drawings | FI | 2018-01-31 | 2018-05-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2019-05-29 | 180448-FC STAMPED | FC | 1 | A | MECHANICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2018-07-11
DHI | HEX | 이진재 | MRT-YL00-P2MAJ-603207 | 1398 | Waterbox Vacuum Pump #2_Instrument list with drawing | FA | 2018-01-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2018-11-29 | 180724-FC STAMPED | FC | 4 | A | I&C | WATERBOX VACUUM PUMP | 2018-03-06 | 2018-07-05
DHI | HEX | 이진재 | MRT-CQ02-P2MAJ-603208 | 1399 | Waterbox Vacuum Pump #2_Instruction manual | FI | 2018-04-30 | 2018-06-29 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180569-FC | FC | 1 | 2018-10-10 | 180569-FC STAMPED | FC | 1 | A | SUPPORT | WATERBOX VACUUM PUMP | 2018-05-18 | 2018-06-01
DHI | HEX | 이진재 | MRT-XS00-P2MAJ-603209 | 1400 | Waterbox Vacuum Pump #2 - System Description & Control Philosophy | FA | 2018-01-31 | 2018-04-30 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180448-FC | FC | 2 | 2018-09-13 | 180448-FC STAMPED | FC | 2 | A | MECHANICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2018-04-19
DHI | HEX | 이진재 | MRT-YK08-P3MAJ-604200 | 1401 | Waterbox Vacuum Pump #3,4 - Outline Drawing | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-04-04 | MTW-AS-C-LT-24.5144.0 | AB | Z0 | A | MECHANICAL | WATERBOX VACUUM PUMP | 2018-03-06 | 2018-06-01
DHI | HEX | 이진재 | MRT-XG02-P3MAJ-604201 | 1402 | Waterbox Vacuum Pump #3,4 - P & I Diagram | FA | 2017-12-29 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-06-21 | MTW-AS-C-LT-24.5406.0 | AB | Z0 | A | MECHANICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2018-05-15
DHI | HEX | 이진재 | MRT-YV02-P3MAJ-604202 | 1403 | Waterbox Vacuum Pump #3,4 - Wiring Diargam | FI | 2018-01-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | ELECTRICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2018-05-15
DHI | HEX | 이진재 | MRT-YK08-P3MAJ-604203 | 1404 | Waterbox Vacuum Pump #3,4 - Terminal Box | FI | 2018-01-31 | 2018-04-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5839.0 | AB | Z0 | A | ELECTRICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2018-04-19
DHI | HEX | 이진재 | MRT-YT01-P3MAJ-604204 | 1405 | Waterbox Vacuum Pump #3,4 - Technical Datasheet | FA | 2017-12-29 | 2018-04-30 | 2024-11-20 | 2024-11-20 | MRT-DS-REC-TT-240038 | AB | Z1 | 2024-11-28 | MTW-AS-C-LT-24.5999.0 | AB | Z1 | A | MECHANICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2019-05-24
DHI | HEX | 이진재 | MRT-YK08-P3MAJ-604205 | 1406 | Waterbox Vacuum Pump #3,4 - Motor Datasheet & Drawings | FI | 2018-01-31 | 2018-05-31 | 2024-11-20 | 2024-11-20 | MRT-DS-REC-TT-240038 | AB | Z1 | 2024-11-28 | MTW-AS-C-LT-24.5999.0 | AB | Z1 | A | ELECTRICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2019-05-24
DHI | HEX | 이진재 | MRT-YT01-P3MAJ-604206 | 1407 | Waterbox Vacuum Pump #3,4 - Heat Exchanger Data Sheet& Drawings | FI | 2018-01-31 | 2018-05-31 | 2024-12-02 | 2024-12-02 | MRT-DS-REC-TT-240042 | AB | Z2 | 2024-12-05 | MTW-AS-C-LT-24.6041.0 | AB | Z2 | A | MECHANICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2018-07-11
DHI | HEX | 이진재 | MRT-YL00-P3MAJ-604207 | 1408 | Waterbox Vacuum Pump #3,4_Instrument list with drawing | FA | 2018-01-31 | 2018-04-30 | 2024-11-20 | 2024-11-20 | MRT-DS-REC-TT-240037 | AB | Z1 | 2024-12-03 | MTW-AS-C-LT-24.6026.0 | AB | Z1 | A | I&C | WATERBOX VACUUM PUMP | 2018-03-06 | 2018-07-05
DHI | HEX | 이진재 | MRT-CQ02-P3MAJ-604208 | 1409 | Waterbox Vacuum Pump #3,4_Instruction manual | FI | 2018-04-30 | 2018-06-29 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180569-FC | FC | 1 | 2018-10-10 | 180569-FC STAMPED | FC | 1 | A | SUPPORT | WATERBOX VACUUM PUMP | 2018-05-18 | 2018-06-01
DHI | HEX | 이진재 | MRT-XS00-P3MAJ-604209 | 1410 | Waterbox Vacuum Pump #3,4 - System Description & Control Philosophy | FA | 2018-01-31 | 2018-04-30 | 2018-07-27 | 2018-08-29 | MRT-DS-REC-TT-180448-FC | FC | 2 | 2018-09-13 | 180448-FC STAMPED | FC | 2 | A | MECHANICAL | WATERBOX VACUUM PUMP | 2018-02-12 | 2018-07-27
DHI | TG_SYSTEM | 구태모 | MRT-XW03-P3MKA-210001 | 1411 | HAZARDOUS AREA CLASSIFICATION FOR GENERATOR (Block #3,4) | FI | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | SUPPORT | GENERATOR AUXILIARY | 2018-05-04 | 2018-07-27
DHI | TG_SYSTEM | 구태모 | MRT-XS00-P3MKG-210001 | 1412 | SYSTEM DESCRIPTION FOR H2 & CO2 CONTROL SYSTEM (Block #3,4) | FI | 2018-02-19 | 2018-06-19 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180591-FC | FC | 1 | 2018-10-05 | 180591-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-02-26 | 2018-07-27
DHI | TG_SYSTEM | 구태모 | MRT-XS00-P3MKW-210001 | 1413 | SYSTEM DESCRIPTION FOR GENERATOR SEAL OIL SYSTEM (Block #3,4) | FI | 2018-02-19 | 2018-06-19 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180591-FC | FC | 1 | 2018-10-05 | 180591-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-02-26 | 2018-07-27
DHI | TG_SYSTEM | 구태모 | MRT-XG02-P2MKJ-210001 | 1414 | GENERATOR PIPING DIAGRAM FOR LIQUID LEVEL DETECTOR (Block #2) | FI | 2018-02-18 | 2018-06-18 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-10-05 | 180591-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-02-26 | 2018-07-27
DHI | TG_SYSTEM | 구태모 | MRT-XG02-P3MKW-210001 | 1415 | GENERATOR SEAL OIL SYSTEM P & ID (Block #3,4) | FA | 2018-02-19 | 2018-06-19 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-02-26 | 2018-07-27
DHI | TG_SYSTEM | 구태모 | MRT-XG02-P3MKG-210001 | 1416 | H2 & CO2 CONTROL SYSTEM P & ID (Block #3,4) | FA | 2018-02-19 | 2018-06-19 | 2023-07-19 | 2023-07-19 | MRT-DS-REC-TT-230012 | AB | Z0 | 2024-10-14 | MTW-AS-C-LT-24.5831.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-02-26 | 2018-08-23
DHI | TG_SYSTEM | 구태모 | MRT-XL00-P3MKA-210001 | 1417 | LINE LIST FOR GENERATOR (Block #3,4) | FI | 2018-04-02 | 2018-08-02 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-04-13 | 2018-08-23
DHI | TG_SYSTEM | 구태모 | MRT-XN00-P3MKA-210001 | 1418 | VALVE LIST FOR GENERATOR (Block #3,4) | FI | 2018-04-02 | 2018-08-02 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-04-13 | 2019-09-02
DHI | TG_SYSTEM | 구태모 | MRT-CN00-P3MKG-210001 | 1419 | COMMISSIONING PROCEDURE FOR H2 & CO2 CONTROL SYSTEM (Block #3,4) | FA | 2018-12-31 | 2019-02-28 | 2021-09-03 | 2021-09-03 | MRT-DS-REC-TT-210050 | FC | 2 | 2021-10-03 | DEEMED APPROVAL | FC | 2 | A | SUPPORT | GENERATOR AUXILIARY | 2019-07-19 | 2019-09-02
DHI | TG_SYSTEM | 구태모 | MRT-CN00-P3MKW-210001 | 1420 | COMMISSIONING PROCEDURE FOR GENERATOR SHAFT SEAL SYSTEM (Block #3,4) | FA | 2018-12-31 | 2019-02-28 | 2021-09-03 | 2021-09-03 | MRT-DS-REC-TT-210050 | FC | 2 | 2021-10-03 | DEEMED APPROVAL | FC | 2 | A | SUPPORT | GENERATOR AUXILIARY | 2019-07-19 | 2018-07-27
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKW-220002 | 1421 | GENERATOR SEAL OIL SUPPLY UNIT OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-06-05 | 2018-07-27
DHI | TG_SYSTEM | 유정운 | MRT-YV02-P3MKW-230001 | 1422 | GENERATOR SEAL OIL ELECTRICAL CONNECTION DIAGRAM (Block #3,4) | FI | 2018-05-30 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5067.0 | AB | Z0 | A | ELECTRICAL | GENERATOR AUXILIARY | 2018-06-01 | 2018-07-27
DHI | TG_SYSTEM | 유정운 | MRT-YT01-P3MKA-240002 | 1423 | GENERATOR PUMP AND MOTOR LIST, DRAWING AND DATA SHEET (Block #3,4) | FI | 2018-05-30 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | ELECTRICAL | GENERATOR AUXILIARY | 2018-06-01 | 2018-07-27
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKW-220004 | 1424 | FLOAT TRAP OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-04-27 | 2018-07-27
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P2MKJ-220001 | 1425 | LIQUID DETECTOR OUTLINE (Block #2) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-10-10 | 180728-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-04-27 | 2018-07-27
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKW-220003 | 1426 | LIQUID DETECTOR OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-04-27 | 2020-08-31
DHI | TG_SYSTEM | 유정운 | MRT-YT01-P3MKA-240003 | 1427 | GENERATOR AUX SYSTEM INSTRUMENT DATA SHEET (Block #3,4) | FI | 2018-05-30 |  | 2024-11-05 | 2024-11-05 | MRT-DS-REC-TT-240024 | AB | Z0 | 2024-12-05 | MTW-AS-C-LT-24.6044.0 | AB | Z0 | A | I&C | GENERATOR AUXILIARY | 2018-06-12 | 2018-07-27
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKG-220004 | 1428 | H2 & CO2 CONTROL SYSTEM_CO2 MANIFOLD OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-04-27 | 2018-07-27
DHI | TG_SYSTEM | 유정운 | MRT-YV02-P3MKW-230002 | 1429 | H2 & CO2 CONTROL SYSTEM_ELECTRICAL CONNECTION DIAGRAM (Block #3,4) | FI | 2018-05-31 |  | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5067.0 | AB | Z0 | A | ELECTRICAL | GENERATOR AUXILIARY | 2018-06-01 | 2018-07-27
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKG-220006 | 1430 | H2 & CO2 CONTROL SYSTEM_GENERATOR GAS MONITORING SYSTEM OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-04-27 | 2018-07-27
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKG-220005 | 1431 | H2 & CO2 CONTROL SYSTEM_H2 CONTROL CABINET OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5067.0 | AB | Z0 | A | I&C | GENERATOR AUXILIARY | 2018-04-27 | 2018-07-27
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKG-220001 | 1432 | H2 & CO2 CONTROL SYSTEM_H2 GAS DRYER OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-04-27 | 2018-07-27
DHI | TG_SYSTEM | 유정운 | MRT-YD00-P3MKG-220003 | 1433 | H2 & CO2 CONTROL SYSTEM_H2 MANIFOLD OUTLINE (Block #3,4) | FA | 2018-04-30 | 2018-08-31 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUXILIARY | 2018-04-27 | 2019-03-06
DHI | TG_SYSTEM | 유정운 | MRT-CQ02-P3MKG-260001 | 1434 | O&M MANUAL FOR HYDROGEN CONTROL SYSTEM (Block #3,4) | FI | 2018-12-31 |  | 2019-03-06 | 2019-03-08 | MRT-DS-REC-TT-190020-FC | FC | 0 | 2019-03-11 | 190020-FC STAMPED | FC | 0 | A | SUPPORT | GENERATOR AUXILIARY | 2019-01-24 | 2019-03-06
DHI | TG_SYSTEM | 유정운 | MRT-CQ02-P3MKW-260001 | 1435 | O&M MANUAL FOR GENERATOR SHAFT SEAL SYSTEM (Block #3,4) | FI | 2018-12-31 |  | 2019-03-06 | 2019-03-08 | MRT-DS-REC-TT-190020-FC | FC | 0 | 2019-03-11 | 190020-FC STAMPED | FC | 0 | A | SUPPORT | GENERATOR AUXILIARY | 2019-01-24 | 2018-06-07
DHI | TG_GEN | 허명구 | MRT-YT01-P2MKA-240001 | 1436 | GENERATOR DATA SHEET (Block #2) | FI | 2018-03-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-09-21 | 180468-FC STAMPED | FC | 1 | A | ELECTRICAL | GENERATOR | 2018-03-12 | 2018-06-07
DHI | TG_GEN | 허명구 | MRT-YT01-P3MKA-240001 | 1437 | GENERATOR DATA SHEET (Block #3,4) | FI | 2018-03-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | ELECTRICAL | GENERATOR | 2018-03-12 | 2018-07-27
DHI | TG_GEN | 허명구 | MRT-YK08-P2MKJ-220001 | 1438 | GENERATOR UNIT AIR COOLER OUTLINE (Block #2) | FA | 2018-01-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-08-13 | 180210-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-03-21 | 2018-07-27
DHI | TG_GEN | 허명구 | MRT-YK08-P3MKA-220001 | 1439 | GENERATOR UNIT HYDROGEN COOLER OUTLINE (Block #3,4) | FA | 2018-03-01 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR | 2018-03-21 | 2018-02-06
DHI | TG_GEN | 어민혁 | MRT-YD00-P2MKA-220003 | 1440 | GENERATOR MECHANICAL OUTLINE (Block #2) | FA | 2017-11-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-08-28 | 180368-FC STAMPED | FC | 3 | A | MECHANICAL | GENERATOR | 2017-11-08 | 2018-02-06
DHI | TG_GEN | 어민혁 | MRT-YD00-P3MKA-220003 | 1441 | GENERATOR MECHANICAL OUTLINE (Block #3,4) | FA | 2017-12-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR | 2017-11-08 | 2019-03-22
DHI | TG_GEN | 어민혁 | MRT-YK08-P2MKA-220002 | 1442 | GENERATOR NAME PLATE (Block #2) | FI | 2018-04-30 | 2019-03-22 | 2019-03-22 | 2019-03-22 | MRT-DS-REC-TT-180264-FC | FC | 0 | 2019-03-22 | 180264-FC STAMPED | FC | 0 | A | ELECTRICAL | GENERATOR | 2018-04-02 | 2019-03-22
DHI | TG_GEN | 어민혁 | MRT-YK08-P3MKA-220002 | 1443 | GENERATOR NAME PLATE (Block #3,4) | FI | 2018-04-30 | 2019-03-22 | 2019-03-22 | 2019-03-22 | MRT-DS-REC-TT-180264-FC | FC | 0 | 2019-03-22 | 180264-FC STAMPED | FC | 0 | A | ELECTRICAL | GENERATOR | 2018-04-02 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-YD00-P2MKA-220001 | 1444 | GENERATOR PIPING CONNECTION (Block #2) | FI | 2018-03-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-09-05 | 180249-FC STAMPED | FC | 3 | A | MECHANICAL | GENERATOR | 2017-11-08 | 2018-09-13
DHI | TG_GEN | 어민혁 | MRT-YD00-P3MKA-220001 | 1445 | GENERATOR PIPING CONNECTION (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR | 2017-11-08 | 2019-03-22
DHI | TG_GEN | 어민혁 | MRT-YK10-P2MKA-220003 | 1446 | GENERATOR COOLER ROOF ASSY(Block #2) | FI | 2018-04-30 | 2019-03-22 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2019-03-22 | 180829-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR | 2018-04-27 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-YD00-P2MKA-220005 | 1447 | GENERATOR ENCLOSURE ARRANGEMENT(Block #2) | FI | 2018-03-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2019-01-05 | 180929-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR | 2018-03-30 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-YK10-P2MKA-220001 | 1448 | GENERATOR END SHIELD ASSY CE(Block #2) | FI | 2018-03-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-08-14 | 180211-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-03-21 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-YK10-P3MKA-220001 | 1449 | GENERATOR END SHIELD ASSY CE (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR | 2018-03-21 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-YK10-P2MKA-220002 | 1450 | GENERATOR END SHIELD ASSY TE(Block #2) | FI | 2018-03-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-08-14 | 180211-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-03-21 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-YK10-P3MKA-220002 | 1451 | GENERATOR END SHIELD ASSY TE (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR | 2018-03-21 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-YD00-P3MKA-220005 | 1452 | GENERATOR LAGGING LAYOUT (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR | 2018-05-25 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-DM01-P3MKA-220001 | 1453 | TERMINAL BOX BOLTING AND WELDING PROCEDURE | FI | 2018-10-30 | 2018-09-30 | 2018-07-27 | 2018-08-08 | MRT-DS-REC-TT-180191-FC | FC | 0 | 2018-08-14 | 180191-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-03-16 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-YK10-P3MKA-220003 | 1454 | GENERATOR TERMINAL BOX ASSEMBLY (Block #3,4) | FI | 2018-03-30 | 2018-09-30 | 2018-07-27 | 2018-08-08 | MRT-DS-REC-TT-180191-FC | FC | 0 | 2018-08-14 | 180191-FC STAMPED | FC | 0 | A | ELECTRICAL | GENERATOR | 2018-03-16 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-YD00-P2MKA-220002 | 1455 | GENERATOR STATOR HANDLING AND SHIPPING DIMENSION (Block #2) | FI | 2018-03-30 | 2018-08-30 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180068-FC | FC | 0 | 2018-08-13 | 180068-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-02-02 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-YD00-P3MKA-220002 | 1456 | GENERATOR STATOR HANDLING AND SHIPPING DIMENSION (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2018-07-27 | 2018-08-01 | MRT-DS-REC-TT-180068-FC | FC | 0 | 2018-08-13 | 180068-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-02-02 | 2018-02-14
DHI | TG_GEN | 어민혁 | MRT-XB00-P2MKA-220001 | 1457 | GENERATOR FOUNDATION ARRANGEMENT DRAWING (Block #2) | FA | 2017-11-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-08-13 | 180111-FC STAMPED | FC | 3 | A | CIVIL | GENERATOR | 2017-11-08 | 2018-02-14
DHI | TG_GEN | 어민혁 | MRT-XB00-P3MKA-220001 | 1458 | GENERATOR FOUNDATION ARRANGEMENT DRAWING (Block #3,4) | FA | 2017-12-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-01 | MTW-AS-C-LT-24.5000.0 | AB | Z0 | A | CIVIL | GENERATOR | 2017-11-08 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-YD00-P2MKA-220004 | 1459 | GENERATOR FOUNDATION PLATE ASSY (Block #2) | FI | 2018-03-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-08-14 | 180186-FC STAMPED | FC | 0 | A | CIVIL | GENERATOR | 2018-03-15 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-YD00-P3MKA-220004 | 1460 | GENERATOR FOUNDATION PLATE ASSY (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-01 | MTW-AS-C-LT-24.5000.0 | AB | Z0 | A | CIVIL | GENERATOR | 2018-03-15 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-DM02-P2MKA-220001 | 1461 | GENERATOR FOUNDATION INSTALLATION DETAIL(Block #2) | FI | 2018-03-30 | 2018-08-30 | 2018-07-27 | 2018-08-08 | MRT-DS-REC-TT-180187-FC | FC | 0 | 2018-08-14 | 180187-FC STAMPED | FC | 0 | A | CIVIL | GENERATOR | 2018-03-15 | 2018-07-27
DHI | TG_GEN | 어민혁 | MRT-DM02-P3MKA-220001 | 1462 | GENERATOR FOUNDATION INSTALLATION DETAIL | FI | 2018-04-30 | 2018-09-30 | 2018-07-27 | 2018-08-08 | MRT-DS-REC-TT-180187-FC | FC | 0 | 2018-08-14 | 180187-FC STAMPED | FC | 0 | A | CIVIL | GENERATOR | 2018-03-15 | #VALUE!
DHI | TG_GEN | 어민혁 | MRT-UF00-P2MKA-220001 | 1463 | GENERATOR FOUNDATION LOADING (Block #2) | FI | 2018-03-30 |  | 2017-12-15 | 2017-12-22 | MRT-DS-PLNE-TT-170136 | FI | 1 | 2017-12-29 | 27.025/E04/PLNE/XII/2017 | FI | 1 | A | CIVIL | GENERATOR | 2017-11-08 | #VALUE!
DHI | TG_GEN | 어민혁 | MRT-UF00-P3MKA-220001 | 1464 | GENERATOR FOUNDATION LOADING (Block #3,4) | FI | 2018-04-30 |  | 2017-12-15 | 2017-12-22 | MRT-DS-PLNE-TT-170136 | FI | 1 | 2017-12-29 | 27.025/E04/PLNE/XII/2017 | FI | 1 | A | CIVIL | GENERATOR | 2017-11-08 | 2018-07-27
DHI | TG_GEN | 김충목 | MRT-YK10-P2MKB-230001 | 1465 | BRUSH HOLDER RIGGING ASSEMBLY (Block #2) | FI | 2018-06-30 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-10-31 | 180575-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-07-05 | 2018-07-27
DHI | TG_GEN | 김충목 | MRT-YK10-P3MKB-230001 | 1466 | BRUSH HOLDER RIGGING ASSEMBLY (Block #3,4) | FI | 2018-07-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR | 2018-07-12 | 2018-07-27
DHI | TG_GEN | 김충목 | MRT-XF00-P2MKA-230001 | 1467 | GENERATOR ROTOR HANDLING DIMENSION (Block #2) | FI | 2018-06-30 | 2018-08-30 | 2018-07-27 | 2018-09-24 | MRT-DS-REC-TT-180575-FC | FC | 0 | 2018-10-31 | 180575-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-07-05 | 2018-07-27
DHI | TG_GEN | 김충목 | MRT-XF00-P3MKA-220001 | 1468 | GENERATOR ROTOR HANDLING DIMENSION (Block #3,4) | FI | 2018-07-30 | 2018-09-30 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180596-FC | FC | 0 | 2018-10-05 | 180596-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-07-12 | 2018-07-27
DHI | TG_GEN | 김충목 | MRT-YK10-P2MKA-230002 | 1469 | FIELD CLEARANCE DIAGRAM (Block #2) | FI | 2018-06-30 | 2018-08-30 | 2019-01-03 | 2019-01-03 | MRT-DS-REC-TT-180928-FC | FC | 1 | 2019-01-05 | 180928-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR | 2018-07-05 | 2018-07-27
DHI | TG_GEN | 김충목 | MRT-YK10-P3MKA-230002 | 1470 | FIELD CLEARANCE DIAGRAM (Block #3,4) | FI | 2018-07-30 | 2018-09-30 | 2018-07-27 | 2018-09-27 | MRT-DS-REC-TT-180596-FC | FC | 0 | 2018-10-05 | 180596-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-07-12 | 2018-07-27
DHI | TG_GEN | 김충목 | MRT-YK10-P2MKA-230003 | 1471 | ROTOR ASSEMBLY AND DISASSEMBLY NOTE (Block #2) | FI | 2018-03-30 | 2018-08-30 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180227-FC | FC | 0 | 2018-08-27 | 180227-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-03-26 | 2018-07-27
DHI | TG_GEN | 김충목 | MRT-YK10-P3MKA-230003 | 1472 | ROTOR ASSEMBLY AND DISASSEMBLY NOTE (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180351-FC | FC | 0 | 2018-08-28 | 180351-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-04-27 | 2018-07-27
DHI | TG_GEN | 김충목 | MRT-YK10-P2MKA-230004 | 1473 | ROTOR ASSEMBLY AND DISASSEMBLY DIAGRAM (Block #2) | FI | 2018-03-30 | 2018-08-30 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180227-FC | FC | 0 | 2018-08-27 | 180227-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-03-26 | 2018-07-27
DHI | TG_GEN | 김충목 | MRT-YK10-P3MKA-230004 | 1474 | ROTOR ASSEMBLY AND DISASSEMBLY DIAGRAM (Block #3,4) | FI | 2018-04-30 | 2018-09-30 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180351-FC | FC | 0 | 2018-08-28 | 180351-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-04-27 | 2018-07-27
DHI | TG_GEN | 최성찬 | MRT-YE00-P2MKA-230001 | 1475 | GENERATOR ELECTRICAL CONNECTION OUTLINE WITH PACKAGE WIRING AND TERMINAL (Block #2) | FA | 2018-03-01 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2019-03-26 | 180942-FC STAMPED | FC | 2 | A | ELECTRICAL | GENERATOR | 2018-04-12 | 2018-07-27
DHI | TG_GEN | 최성찬 | MRT-YE00-P3MKA-230001 | 1476 | GENERATOR ELECTRICAL CONNECTION OUTLINE WITH PACKAGE WIRING AND TERMINAL (Block #3,4) | FA | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-19 | MTW-AS-C-LT-24.5067.0 | AB | Z0 | A | ELECTRICAL | GENERATOR | 2018-05-18 | 2018-07-27
DHI | TG_GEN | 최성찬 | MRT-YE00-P2MKA-230002 | 1477 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (Block #2) | FA | 2018-03-01 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2019-01-25 | 190010-FC STAMPED | FC | 3 | A | ELECTRICAL | GENERATOR | 2018-02-13 | 2018-07-27
DHI | TG_GEN | 최성찬 | MRT-YE00-P3MKA-230002 | 1478 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (Block #3,4) | FA | 2018-04-30 | 2018-09-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-03-01 | MTW-AS-C-LT-24.5000.0 | AB | Z0 | A | ELECTRICAL | GENERATOR | 2018-02-13 | 2018-07-27
DHI | TG_GEN | 최성찬 | MRT-YK00-P2BAT-240001 | 1479 | CURRENT TRANSFORMER CONFIGURATION (Block #2) | FA | 2018-03-01 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-12-08 | 180741-FC STAMPED | FC | 1 | A | ELECTRICAL | GENERATOR | 2018-04-12 | 2018-07-27
DHI | TG_GEN | 최성찬 | MRT-UC02-P2BAT-240001 | 1480 | GENERATOR NEUTRAL ENCLOSURE INSTALLATION (Block #2) | FA | 2018-03-01 | 2018-08-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2019-03-26 | 180942-FC STAMPED | FC | 2 | A | MECHANICAL | GENERATOR | 2018-04-12 | 2018-07-27
DHI | TG_GEN | 최성찬 | MRT-YK00-P3BAT-240001 | 1481 | CURRENT TRANSFORMER ASSEMBLY (Block #3,4) | FA | 2018-04-30 | 2018-09-30 | 2018-07-27 | 2018-08-13 | MRT-DS-REC-TT-180352-FC | FC | 0 | 2018-08-28 | 180352-FC STAMPED | FC | 0 | A | MECHANICAL | GENERATOR | 2018-04-27 | 2019-02-11
DHI | TG_GEN | 허명구 | MRT-CM02-P2MKA-220001 | 1482 | GENERATOR O&M MANUAL (Block #2) | FI | 2019-01-31 | 2019-03-31 | 2019-02-11 | 2019-02-11 | MRT-DS-REC-TT-190013-FC | FC | 0 | 2019-02-11 | 190013-FC STAMPED | FC | 0 | A | SUPPORT | GENERATOR | 2019-01-16 | 2019-02-11
DHI | TG_GEN | 허명구 | MRT-CM02-P3MKA-220001 | 1483 | GENERATOR O&M MANUAL (Block #3,4) | FI | 2019-01-31 | 2019-03-31 | 2019-02-11 | 2019-02-11 | MRT-DS-REC-TT-190013-FC | FC | 0 | 2019-02-11 | 190013-FC STAMPED | FC | 0 | A | SUPPORT | GENERATOR | 2019-01-16 | 2018-06-20
DHI | TG_SYSTEM | 이동혁 | MRT-XH01-P2MKJ-220001 | 1484 | GENERATOR AUXILIARIES PIPING ARRANGEMENT (Block #2) | FA | 2018-03-15 | 2018-05-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-09-21 | 180516-FC STAMPED | FC | 1 | A | MECHANICAL | GENERATOR AUX PIPING | 2018-03-20 | 2018-07-20
DHI | TG_SYSTEM | 이동혁 | MRT-XH01-P3MKA-220001 | 1485 | GENERATOR AUXILIARIES PIPING ARRANGEMENT (Block #3,4) | FA | 2018-05-15 | 2018-07-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUX PIPING | 2018-06-26 | 2018-06-15
DHI | TG_SYSTEM | 이동혁 | MRT-XJ00-P2MKJ-220001 | 1486 | GENERATOR AUXILIARIES PIPING ISO (Block #2) | FA | 2018-03-15 | 2018-05-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-10-23 | 180778-FC STAMPED | FC | 3 | A | MECHANICAL | GENERATOR AUX PIPING | 2018-03-16 | 2018-07-20
DHI | TG_SYSTEM | 이동혁 | MRT-XJ00-P3MKA-220001 | 1487 | GENERATOR AUXILIARIES PIPING ISO (Block #3,4) | FA | 2018-05-15 | 2018-07-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUX PIPING | 2018-06-15 | 2018-06-20
DHI | TG_SYSTEM | 이동혁 | MRT-XK00-P2MKJ-220001 | 1488 | GENERATOR AUXILIARIES PIPING SUPPORT (Block #2) | FA | 2018-03-15 | 2018-05-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2018-10-23 | 180779-FC STAMPED | FC | 2 | A | MECHANICAL | GENERATOR AUX PIPING | 2018-03-20 | 2018-07-25
DHI | TG_SYSTEM | 이동혁 | MRT-XK00-P3MKA-220001 | 1489 | GENERATOR AUXILIARIES PIPING SUPPORT (Block #3,4) | FA | 2018-05-30 | 2018-07-30 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUX PIPING | 2018-05-31 | 2018-06-26
DHI | TG_SYSTEM | 이동혁 | MRT-YD00-P3MKW-220001 | 1490 | GENERATOR BEARING OIL DRAIN ENLARGEMENT OUTLINE (Block #3,4) | FA | 2018-04-15 | 2018-06-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUX PIPING | 2018-05-11 | 2018-06-26
DHI | TG_SYSTEM | 이동혁 | MRT-YD00-P3MKW-220005 | 1491 | GENERATOR SEAL OIL DRAIN ENLARGEMENT OUTLINE (Block #3,4) | FA | 2018-04-15 | 2018-06-15 | 2022-12-15 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | 2024-02-28 | MTW-AS-C-LT-24.4979.0 | AB | Z0 | A | MECHANICAL | GENERATOR AUX PIPING | 2018-05-11 | 2019-03-25
DHI | TG_ELEC&INC | 김강현 | MRT-YR02-P2MKC-230001 | 1492 | DATA FOR POWER SYSTEM STABILITY ANALYSIS #2 | FI | 2019-03-02 | 2019-07-02 | 2019-03-25 | 2019-03-26 | MRT-DS-REC-TT-190068-FC | FC | 0 | 2019-03-26 | 190068-FC STAMPED | FC | 0 | A | ELECTRICAL | STG ELECTRICAL | 2019-03-07 | 2019-03-25
DHI | TG_ELEC&INC | 김강현 | MRT-YR02-P3MKC-230001 | 1493 | DATA FOR POWER SYSTEM STABILITY ANALYSIS #3,4 | FI | 2019-03-02 | 2019-07-02 | 2019-03-25 | 2019-03-26 | MRT-DS-REC-TT-190068-FC | FC | 0 | 2019-03-26 | 190068-FC STAMPED | FC | 0 | A | ELECTRICAL | STG ELECTRICAL | 2019-03-07 | 2018-06-27
DHI | TG_ELEC&INC | 김강현 | MRT-YK09-P2MKC-230001 | 1494 | EXCITATION CUBICLE OUTLINE DRAWING #2 | FA | 2018-03-20 | 2018-06-20 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-10-05 | 180545-FC STAMPED | FC | 1 | A | ELECTRICAL | STG ELECTRICAL | 2018-03-28 | 2018-06-27
DHI | TG_ELEC&INC | 김강현 | MRT-YK09-P3MKC-230001 | 1495 | EXCITATION CUBICLE OUTLINE DRAWING #3,4 | FA | 2018-03-20 | 2018-06-20 | 2024-01-08 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5537.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL | 2018-03-28 | 2018-07-23
DHI | TG_ELEC&INC | 김강현 | MRT-YK09-P2MKC-230006 | 1496 | EXCITATION SYSTEM ELEMENTARY DIAGRAM #2 | FA | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-10-05 | 180644-FC STAMPED | FC | 1 | A | ELECTRICAL | STG ELECTRICAL | 2018-05-10 | 2018-07-23
DHI | TG_ELEC&INC | 김강현 | MRT-YK09-P3MKC-230006 | 1497 | EXCITATION SYSTEM ELEMENTARY DIAGRAM #3,4 | FA | 2018-04-30 | 2018-07-30 | 2024-01-08 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5537.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL | 2018-05-10 | 2019-05-09
DHI | TG_ELEC&INC | 김강현 | MRT-CQ03-P0MKC-230001 | 1498 | O&M MANUAL FOR EXCITATION SYSTEM | FI | 2019-04-30 | 2019-06-28 | 2019-05-09 | 2019-05-17 | MRT-DS-REC-TT-190120-FC | FC | 0 | 2019-05-17 | 190120-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL | 2019-04-26 | 2018-07-27
DHI | TG_ELEC&INC | 정창수 | MRT-YK09-P2MKC-230002 | 1499 | DRAWINGS OF EXCITATION TRANSFORMER FOR ST #2 | FA | 2018-03-20 | 2018-06-20 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-12-14 | 180897-FC STAMPED | FC | 4 | A | ELECTRICAL | STG ELECTRICAL | 2018-04-18 | 2018-07-27
DHI | TG_ELEC&INC | 정창수 | MRT-YK09-P3MKC-230002 | 1500 | DRAWINGS OF EXCITATION TRANSFORMER FOR ST #3,4 | FA | 2018-03-20 | 2018-06-20 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5529.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL | 2018-04-18 | 2018-10-01
DHI | TG_ELEC&INC | 정창수 | MRT-YK09-P2MKC-230003 | 1501 | AC & DC BUSDUCT LAYOUT DRAWINGS #2 | FA | 2018-03-20 | 2018-06-20 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2019-02-02 | 190011-FC STAMPED | FC | 2 | A | ELECTRICAL | STG ELECTRICAL | 2018-03-30 | 2018-11-13
DHI | TG_ELEC&INC | 정창수 | MRT-YK09-P3MKC-230003 | 1502 | AC & DC BUSDUCT LAYOUT DRAWINGS #3,4 | FA | 2018-03-20 | 2018-06-20 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5529.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL | 2018-03-30 | 2018-09-10
DHI | TG_ELEC&INC | 정창수 | MRT-YU01-P2MKC-230010 | 1503 | SINGLE LINE DIAGRAMS INCLUDING GENERATOR CONTROL & PROTECTION #2 | FA | 2018-03-20 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-10-10 | 180723-FC STAMPED | FC | 1 | A | ELECTRICAL | STG ELECTRICAL | 2018-04-18 | 2018-09-10
DHI | TG_ELEC&INC | 정창수 | MRT-YU01-P3MKC-230010 | 1504 | SINGLE LINE DIAGRAMS INCLUDING GENERATOR CONTROL & PROTECTION #3,4 | FA | 2018-03-20 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5529.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL | 2018-04-18 | 2018-07-27
DHI | TG_ELEC&INC | 정창수 | MRT-YF00-P2MKC-230011 | 1505 | LOGIC DIAGRAMS OF GENERATOR PROTECTION PANEL FOR STG #2 | FI | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-08-31 | 180360-FC STAMPED | FC | 0 | A | I&C | STG ELECTRICAL | 2018-05-03 | 2018-07-27
DHI | TG_ELEC&INC | 정창수 | MRT-YF00-P3MKC-230011 | 1506 | LOGIC DIAGRAMS OF GENERATOR PROTECTION PANEL FOR STG #3,4 | FI | 2018-04-30 | 2018-07-30 | 2024-01-08 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5537.0 | AB | Z0 | A | I&C | STG ELECTRICAL | 2018-05-03 | 2018-07-27
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P2MKC-230012 | 1507 | SCHEMATIC DIAGRAMS FOR GENERATOR PROTECTION RELAY FOR STG #2 | FA | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-12-17 | 180909-FC STAMPED | FC | 2 | A | ELECTRICAL | STG ELECTRICAL | 2018-05-03 | 2018-07-27
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P3MKC-230012 | 1508 | SCHEMATIC DIAGRAMS FOR GENERATOR PROTECTION RELAY FOR STG #3,4 | FA | 2018-04-30 | 2018-07-30 | 2024-01-08 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5537.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL | 2018-05-03 | 2018-07-27
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P2MKC-230013 | 1509 | SCHEMATIC DIAGRAMS FOR GENERATOR METERING & SYNCHRO PANEL #2 | FA | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-12-17 | 180909-FC STAMPED | FC | 2 | A | ELECTRICAL | STG ELECTRICAL | 2018-05-03 | 2018-07-27
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P3MKC-230013 | 1510 | SCHEMATIC DIAGRAMS FOR GENERATOR METERING & SYNCHRO PANEL #3,4 | FA | 2018-04-30 | 2018-07-30 | 2024-01-08 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | 2024-07-18 | MTW-AS-C-LT-24.5537.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL | 2018-05-03 | 2018-10-23
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P2MKC-230014 | 1511 | SCHEMATIC DIAGRAMS FOR NGR AND NGTR PANEL FOR STG #2 | FA | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-12-17 | 180910-FC STAMPED | FC | 3 | A | ELECTRICAL | STG ELECTRICAL | 2018-05-03 | 2018-10-23
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P3MKC-230014 | 1512 | SCHEMATIC DIAGRAMS FOR NGR AND NGTR PANEL FOR STG #3,4 | FA | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5529.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL | 2018-05-03 | 2018-07-27
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P2MKC-230015 | 1513 | SCHEMATIC DIAGRAMS FOR PT SA PANEL FOR STG #2 | FA | 2018-05-17 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2018-12-17 | 180910-FC STAMPED | FC | 2 | A | ELECTRICAL | STG ELECTRICAL | 2018-05-25 | 2018-07-27
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P3MKC-230015 | 1514 | SCHEMATIC DIAGRAMS FOR PT SA PANEL FOR STG #3,4 | FA | 2018-05-17 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5529.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL | 2018-05-25 | 2018-07-27
DHI | TG_ELEC&INC | 정창수 | MRT-YS01-P3MKC-230017 | 1515 | SCHEMATIC DIAGRAMS FOR EMERGENCY SEAL OIL DC MOTOR STARTER PANEL #3,4 | FA | 2018-04-30 | 2018-07-30 | 2022-12-22 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | 2024-07-16 | MTW-AS-C-LT-24.5529.0 | AB | Z0 | A | ELECTRICAL | STG ELECTRICAL | 2018-04-24 | 2019-05-10
DHI | TG_ELEC&INC | 정창수 | MRT-CQ03-P0MKC-230002 | 1516 | O&M MANUAL FOR EXCITATION TRANSFORMER | FI | 2019-04-30 | 2019-06-28 | 2019-05-10 | 2019-05-21 | MRT-DS-REC-TT-190122-FC | FC | 0 | 2019-05-21 | 190122-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL | 2019-05-07 | 2019-05-31
DHI | TG_ELEC&INC | 정창수 | MRT-CQ03-P0MKC-230012 | 1517 | O&M MANUAL FOR GENERATOR PROTECTION RELAY | FI | 2019-04-30 | 2019-06-28 | 2019-05-31 | 2019-06-22 | MRT-DS-REC-TT-190126-FC | FC | 0 | 2019-06-24 | 190126-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL | 2019-05-15 | 2019-05-31
DHI | TG_ELEC&INC | 정창수 | MRT-CQ03-P0MKC-230013 | 1518 | O&M MANUAL FOR GENERATOR METERING & SYNCHRO PANEL | FI | 2019-04-30 | 2019-06-28 | 2019-05-31 | 2019-06-22 | MRT-DS-REC-TT-190126-FC | FC | 0 | 2019-06-24 | 190126-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL | 2019-05-15 | 2019-05-10
DHI | TG_ELEC&INC | 정창수 | MRT-CQ03-P0MKC-230014 | 1519 | O&M MANUAL FOR NGTR PANEL | FI | 2019-04-30 | 2019-06-28 | 2019-05-10 | 2019-05-21 | MRT-DS-REC-TT-190122-FC | FC | 0 | 2019-05-21 | 190122-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL | 2019-05-07 | 2019-05-10
DHI | TG_ELEC&INC | 정창수 | MRT-CQ03-P0MKC-230015 | 1520 | O&M MANUAL FOR PTSA PANEL | FI | 2019-04-30 | 2019-06-28 | 2019-05-10 | 2019-05-21 | MRT-DS-REC-TT-190122-FC | FC | 0 | 2019-05-21 | 190122-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL | 2019-05-07 | 2019-02-11
DHI | TG_ELEC&INC | 정창수 | MRT-YT10-P2MKC-230016 | 1521 | PROTECTION RELAY SETTING DATA AND CALCULATION FOR STG #2 | FA | 2018-12-30 | 2019-04-30 | 2022-09-15 | 2022-09-15 | MRT-DS-REC-TT-220015 | FC | 1 | 2019-02-14 | 190014-FC STAMPED | FC | 0 | A | ELECTRICAL | STG ELECTRICAL | 2019-01-16 | 2019-02-11
DHI | TG_ELEC&INC | 정창수 | MRT-YT10-P3MKC-230016 | 1522 | PROTECTION RELAY SETTING DATA AND CALCULATION FOR STG #3,4 | FA | 2018-12-30 | 2019-04-30 | 2019-02-11 | 2019-02-12 | MRT-DS-REC-TT-190014-FC | FC | 0 | 2019-02-14 | 190014-FC STAMPED | FC | 0 | A | ELECTRICAL | STG ELECTRICAL | 2019-01-16 | 2019-05-10
DHI | TG_ELEC&INC | 정창수 | MRT-CQ03-P0MKC-230017 | 1523 | O&M MANUAL FOR ESOP MOTOR STARTER PANEL | FI | 2019-04-30 | 2019-06-28 | 2019-05-10 | 2019-05-21 | MRT-DS-REC-TT-190122-FC | FC | 0 | 2019-05-21 | 190122-FC STAMPED | FC | 0 | A | SUPPORT | STG ELECTRICAL | 2019-05-07 | #VALUE!
Formulas:
First Actual = CHOOSECOLS(CHOOSEROWS(_xlws.FILTER(표1[], (표1[DT_DOC_NO] = [Document No]),""),1),3)
Final Actual = CHOOSECOLS(CHOOSEROWS(_xlws.FILTER(표1[], (표1[DT_DOC_NO] = [Document No, row below])*(표1[DT_DOC_PUR] = "FC"),""),1),3)

## Sheet1
ID | DT_DOC_NO | DT_SUBM_DATE_EM | DT_NO | DT_DOC_PUR | DT_DOC_REV | DT_ATT_DOC | DT_ATT_REP | DT_CHK_BOX_1
6 | MRT-DA01-P0ZEN-020001 | 2017-06-30 | MRT-DS-PLN-DT-170002 | FA | 0 | TRUE | FALSE | FALSE
7 | MRT-DA01-P0ZEN-020002 | 2017-06-30 | MRT-DS-PLN-DT-170002 | FA | 0 | TRUE | FALSE | FALSE
8 | MRT-XG07-P0ZEN-120050 | 2017-06-30 | MRT-DS-PLN-DT-170003 | FA | 0 | TRUE | FALSE | FALSE
9 | MRT-UC07-P0ZEN-100001 | 2017-06-30 | MRT-DS-PLN-DT-170004 | FA | 0 | TRUE | FALSE | FALSE
10 | MRT-XG02-P0ZEN-110002 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
11 | MRT-XG02-P2LBA-110003 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
12 | MRT-XG02-P2LBG-110004 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
13 | MRT-XG02-P0LBG-110004 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
14 | MRT-XG02-P2LCM-110005 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
15 | MRT-XG02-P2LA-110006 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
16 | MRT-XG02-P2LC-110007 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
17 | MRT-XG02-P2PA-110002 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
18 | MRT-XG02-P0PA-110002 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
19 | MRT-XG02-P2PA-110008 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
20 | MRT-XG02-P0GHC-110002 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
21 | MRT-XG02-P2PG-110009 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
22 | MRT-XG02-P0QJA-110010 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
23 | MRT-XG02-P3LBA-110003 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
24 | MRT-XG02-P3LBG-110004 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
25 | MRT-XG02-P3LCM-110005 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
26 | MRT-XG02-P3LA-110006 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
27 | MRT-XG02-P3LC-110007 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
28 | MRT-XG02-P3PA-110002 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
29 | MRT-XG02-P3PA-110008 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
30 | MRT-XG02-P3PG-110009 | 2017-07-10 | MRT-DS-PLN-DT-170005 | FA | 0 | TRUE | FALSE | FALSE
31 | MRT-XG02-P2LB-122022 | 2017-07-10 | MRT-DS-PLN-DT-170006 | FA | 0 | TRUE | FALSE | FALSE
32 | MRT-XG02-P2SCA-120004 | 2017-07-11 | MRT-DS-PLN-DT-170007 | FA | 0 | TRUE | FALSE | FALSE
33 | MRT-XG02-P2SCA-120005 | 2017-07-11 | MRT-DS-PLN-DT-170007 | FA | 0 | TRUE | FALSE | FALSE
34 | MRT-XG02-P2SCA-120006 | 2017-07-11 | MRT-DS-PLN-DT-170007 | FA | 0 | TRUE | FALSE | FALSE
35 | MRT-XG02-P3SCA-120004 | 2017-07-11 | MRT-DS-PLN-DT-170007 | FA | 0 | TRUE | FALSE | FALSE
36 | MRT-XG02-P3SCA-120005 | 2017-07-11 | MRT-DS-PLN-DT-170007 | FA | 0 | TRUE | FALSE | FALSE
37 | MRT-XG02-P3SCA-120006 | 2017-07-11 | MRT-DS-PLN-DT-170007 | FA | 0 | TRUE | FALSE | FALSE
38 | MRT-XG02-P0GKC-120001 | 2017-07-11 | MRT-DS-PLN-DT-170007 | FA | 0 | TRUE | FALSE | FALSE
39 | MRT-XG02-P0GHD-120001 | 2017-07-11 | MRT-DS-PLN-DT-170007 | FA | 0 | TRUE | FALSE | FALSE
40 | MRT-XG02-P2MAV-120054 | 2017-07-11 | MRT-DS-PLN-DT-170007 | FA | 0 | TRUE | FALSE | FALSE
41 | MRT-XG02-P3MAV-120054 | 2017-07-11 | MRT-DS-PLN-DT-170007 | FA | 0 | TRUE | FALSE | FALSE
42 | MRT-XS00-P2LBA-110400 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
43 | MRT-XS00-P2LBG-110401 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
44 | MRT-XS00-P2LA-110402 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
45 | MRT-XS00-P2LC-110403 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
46 | MRT-XS00-P2PA-110400 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
47 | MRT-XS00-P2PA-110404 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
48 | MRT-XS00-P2PG-110405 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
49 | MRT-XS00-P3LBA-110400 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
50 | MRT-XS00-P3LBG-110401 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
51 | MRT-XS00-P3LA-110402 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
52 | MRT-XS00-P3LC-110403 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
53 | MRT-XS00-P3PA-110400 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
54 | MRT-XS00-P3PA-110404 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
55 | MRT-XS00-P3PG-110405 | 2017-07-13 | MRT-DS-PLN-DT-170008 | FA | 0 | TRUE | FALSE | FALSE
56 | MRT-QM01-P0ZEN-040002 | 2017-07-19 | MRT-DS-PLN-TT-170009 | FA | 0 | TRUE | FALSE | FALSE
57 | MRT-QM01-P0ZEN-040003 | 2017-07-19 | MRT-DS-PLN-TT-170009 | FA | 0 | TRUE | FALSE | FALSE
58 | MRT-XS00-P2MAV-120053 | 2017-07-19 | MRT-DS-PLN-DT-170010 | FA | 0 | TRUE | FALSE | FALSE
59 | MRT-XS00-P3MAV-120053 | 2017-07-19 | MRT-DS-PLN-DT-170010 | FA | 0 | TRUE | FALSE | FALSE
60 | MRT-XS00-P2SCA-120015 | 2017-07-19 | MRT-DS-PLN-DT-170010 | FA | 0 | TRUE | FALSE | FALSE
61 | MRT-XS00-P3SCA-120015 | 2017-07-19 | MRT-DS-PLN-DT-170010 | FA | 0 | TRUE | FALSE | FALSE
62 | MRT-XS00-P0GKC-120001 | 2017-07-19 | MRT-DS-PLN-DT-170010 | FA | 0 | TRUE | FALSE | FALSE
63 | MRT-XS00-P0GHD-120001 | 2017-07-19 | MRT-DS-PLN-DT-170010 | FA | 0 | TRUE | FALSE | FALSE
64 | MRT-XW03-P2LC-110501 | 2017-07-24 | MRT-DS-PLN-DT-170011 | FA | 0 | TRUE | FALSE | FALSE
65 | MRT-XW03-P2LA-110500 | 2017-07-24 | MRT-DS-PLN-DT-170011 | FA | 0 | TRUE | FALSE | FALSE
66 | MRT-XW03-P3LC-110501 | 2017-07-24 | MRT-DS-PLN-DT-170011 | FA | 0 | TRUE | FALSE | FALSE
67 | MRT-XW03-P3LA-110500 | 2017-07-24 | MRT-DS-PLN-DT-170011 | FA | 0 | TRUE | FALSE | FALSE
114 | MRT-XS00-P3GC-135100 | 2017-07-25 | MRT-HK-PLNE-DT-170001 | FA | 0 | TRUE | FALSE | FALSE
115 | MRT-XS00-P0GA-125200 | 2017-07-25 | MRT-HK-PLNE-DT-170001 | FA | 0 | TRUE | FALSE | FALSE
116 | MRT-XW01-P00SA-135500 | 2017-07-25 | MRT-HK-PLNE-DT-170001 | FA | 0 | TRUE | FALSE | FALSE
117 | MRT-XW01-P3MKG-125301 | 2017-07-25 | MRT-HK-PLNE-DT-170001 | FA | 0 | TRUE | FALSE | FALSE
118 | MRT-XG08-P3MKG-125302 | 2017-07-25 | MRT-HK-PLNE-DT-170001 | FA | 0 | TRUE | FALSE | FALSE
119 | MRT-XW01-P0GAA-135000 | 2017-07-25 | MRT-HK-PLNE-DT-170001 | FA | 0 | TRUE | FALSE | FALSE
120 | MRT-XG08-P0GAA-135001 | 2017-07-25 | MRT-HK-PLNE-DT-170001 | FA | 0 | TRUE | FALSE | FALSE
121 | MRT-XW01-P0SMU-125001 | 2017-07-25 | MRT-HK-PLNE-DT-170001 | FA | 0 | TRUE | FALSE | FALSE
68 | MRT-XG05-P0ZEN-110001 | 2017-07-26 | MRT-DS-PLN-TT-170012 | FA | 1 | TRUE | TRUE | FALSE
122 | MRT-XS00-P0GN-135200 | 2017-07-26 | MRT-HK-PLNE-TT-170002 | FA | 0 | TRUE | FALSE | FALSE
123 | MRT-CY03-P0SGA-135402 | 2017-07-26 | MRT-HK-PLNE-TT-170002 | FA | 0 | TRUE | FALSE | FALSE
69 | MRT-UC07-P0ZEN-100001 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
70 | MRT-UC08-P0ZEN-100002 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
71 | MRT-UC08-P0ZEN-100003 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
72 | MRT-UE00-P2ZEN-100004 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
73 | MRT-UE00-P2ZEN-100005 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
74 | MRT-UE00-P2ZEN-100006 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
75 | MRT-UE00-P2ZEN-100007 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
76 | MRT-UE00-P2ZEN-100008 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
77 | MRT-UE00-P2ZEN-100009 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
78 | MRT-UE00-P3ZEN-100010 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
79 | MRT-UE00-P3ZEN-100011 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
80 | MRT-UE00-P3ZEN-100012 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
81 | MRT-UE00-P3ZEN-100013 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
82 | MRT-UE00-P3ZEN-100014 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
83 | MRT-UE00-P3ZEN-100015 | 2017-07-28 | MRT-DS-PLN-TT-170013 | FA | 0 | TRUE | FALSE | FALSE
124 | MRT-YD00-P3CWA-165003 | 2017-08-10 | MRT-HK-PLNE-TT-170004 | FA | 0 | TRUE | FALSE | FALSE
125 | MRT-YS01-P0ZEN-165004 | 2017-08-10 | MRT-HK-PLNE-TT-170004 | FA | 0 | TRUE | FALSE | FALSE
126 | MRT-YU01-P0ABA-150024 | 2017-08-15 | MRT-HK-PLNE-TT-170005 | FA | 0 | TRUE | FALSE | FALSE
127 | MRT-XW03-P3GC-135101 | 2017-08-15 | MRT-HK-PLNE-TT-170005 | FA | 0 | TRUE | FALSE | FALSE
128 | MRT-XW03-P0GEN-135301 | 2017-08-15 | MRT-HK-PLNE-TT-170005 | FA | 0 | TRUE | FALSE | FALSE
129 | MRT-XG02-P0GEN-135302 | 2017-08-15 | MRT-HK-PLNE-TT-170005 | FA | 0 | TRUE | FALSE | FALSE
130 | MRT-CV03-P0SGA-135400 | 2017-08-15 | MRT-HK-PLNE-TT-170005 | FA | 0 | TRUE | FALSE | FALSE
84 | MRT-YK08-P0ZEN-020004 | 2017-08-18 | MRT-DS-PLNE-TT-170014 | FA | 0 | TRUE | FALSE | FALSE
85 | MRT-YK08-P2MAG-601001 | 2017-08-21 | MRT-DS-PLNE-TT-170015 | FA | 0 | TRUE | FALSE | FALSE
86 | MRT-YK08-P3MAG-602001 | 2017-08-21 | MRT-DS-PLNE-TT-170015 | FA | 0 | TRUE | FALSE | FALSE
87 | MRT-DA01-P0ZEN-020001 | 2017-08-21 | MRT-DS-PLNE-TT-170016 | FI | 1 | TRUE | TRUE | FALSE
88 | MRT-DA01-P0ZEN-020002 | 2017-08-21 | MRT-DS-PLNE-TT-170016 | FI | 1 | TRUE | TRUE | FALSE
89 | MRT-XW03-P2PGB-113110 | 2017-08-21 | MRT-DS-PLNE-TT-170017 | FA | 0 | TRUE | FALSE | FALSE
90 | MRT-XW03-P3PGB-113110 | 2017-08-21 | MRT-DS-PLNE-TT-170017 | FA | 0 | TRUE | FALSE | FALSE
131 | MRT-XW03-P0GN-135201 | 2017-08-21 | MRT-HK-PLNE-TT-170006 | FA | 0 | TRUE | FALSE | FALSE
132 | MRT-DE00-P0ZEN-145000 | 2017-08-21 | MRT-HK-PLNE-TT-170006 | FA | 0 | TRUE | FALSE | FALSE
91 | MRT-XG07-P0ZEN-120050 | 2017-08-22 | MRT-DS-PLNE-TT-170018 | FA | 1 | TRUE | TRUE | FALSE
92 | MRT-XW03-P2PAC-113500 | 2017-08-22 | MRT-DS-PLNE-TT-170019 | FA | 0 | TRUE | FALSE | FALSE
93 | MRT-XW03-P3PAC-113500 | 2017-08-22 | MRT-DS-PLNE-TT-170019 | FA | 0 | TRUE | FALSE | FALSE
133 | MRT-YR04-P0ZEN-165001 | 2017-08-25 | MRT-HK-PLNE-TT-170008 | FA | 0 | TRUE | FALSE | FALSE
134 | MRT-CA07-P0ZEN-175001 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
135 | MRT-CC05-P0ZEN-175021 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
136 | MRT-CC05-P0ZEN-175022 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
137 | MRT-CC05-P0ZEN-175023 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
138 | MRT-CC05-P0ZEN-175024 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
139 | MRT-CC05-P0ZEN-175025 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
140 | MRT-CC05-P0ZEN-175026 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
141 | MRT-CC05-P0ZEN-175027 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
142 | MRT-CC05-P0ZEN-175028 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
143 | MRT-CC05-P0ZEN-175029 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
144 | MRT-CC05-P0ZEN-175030 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
145 | MRT-CC05-P0ZEN-175031 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
146 | MRT-CC05-P0ZEN-175032 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
147 | MRT-CC05-P0ZEN-175033 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
148 | MRT-CC05-P0ZEN-175034 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
149 | MRT-CC05-P0ZEN-175035 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
150 | MRT-CC05-P0ZEN-175036 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
151 | MRT-CC05-P0ZEN-175037 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
152 | MRT-CC05-P0ZEN-175041 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
153 | MRT-CC05-P0ZEN-175042 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
154 | MRT-CC05-P0ZEN-175043 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
155 | MRT-CC05-P0ZEN-175044 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
156 | MRT-CC05-P0ZEN-175045 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
157 | MRT-CC05-P0ZEN-175046 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
158 | MRT-CC05-P0ZEN-175047 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
159 | MRT-CC05-P0ZEN-175048 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
160 | MRT-CC05-P0ZEN-175049 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
161 | MRT-CC05-P0ZEN-175051 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
162 | MRT-CC05-P0ZEN-175052 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
163 | MRT-CC05-P0ZEN-175053 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
164 | MRT-CC05-P0ZEN-175054 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
165 | MRT-CC05-P0ZEN-175061 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
166 | MRT-CC05-P0ZEN-175062 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
167 | MRT-CC05-P0ZEN-175063 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
168 | MRT-CC05-P0ZEN-175064 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
169 | MRT-CC05-P0ZEN-175065 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
170 | MRT-CC05-P0ZEN-175066 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
171 | MRT-CC05-P0ZEN-175067 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
172 | MRT-CC05-P0ZEN-175068 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
173 | MRT-CC05-P0ZEN-175069 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
174 | MRT-CC05-P0ZEN-175070 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
175 | MRT-CC05-P0ZEN-175071 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
176 | MRT-CC05-P0ZEN-175072 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
177 | MRT-CC05-P0ZEN-175073 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
178 | MRT-XS01-P0ABA-150001 | 2017-08-28 | MRT-HK-PLNE-TT-170010 | FA | 0 | TRUE | FALSE | FALSE
326 | MRT-XW03-P2SCA-120017 | 2017-08-28 | MRT-DS-PLNE-TT-170021 | FA | 0 | TRUE | FALSE | FALSE
327 | MRT-XW03-P3SCA-120017 | 2017-08-28 | MRT-DS-PLNE-TT-170021 | FA | 0 | TRUE | FALSE | FALSE
94 | MRT-YK08-P2MAG-601002 | 2017-08-29 | MRT-DS-PLNE-TT-170020 | FA | 0 | TRUE | FALSE | FALSE
95 | MRT-XL00-P2MAG-601003 | 2017-08-29 | MRT-DS-PLNE-TT-170020 | FI | 0 | TRUE | FALSE | FALSE
96 | MRT-XL00-P2MAG-601004 | 2017-08-29 | MRT-DS-PLNE-TT-170020 | FI | 0 | TRUE | FALSE | FALSE
97 | MRT-YK08-P3MAG-602002 | 2017-08-29 | MRT-DS-PLNE-TT-170020 | FA | 0 | TRUE | FALSE | FALSE
98 | MRT-XL00-P3MAG-602003 | 2017-08-29 | MRT-DS-PLNE-TT-170020 | FI | 0 | TRUE | FALSE | FALSE
99 | MRT-XL00-P3MAG-602004 | 2017-08-29 | MRT-DS-PLNE-TT-170020 | FI | 0 | TRUE | FALSE | FALSE
100 | MRT-VL00-P2MAG-601005 | 2017-08-31 | MRT-DS-PLNE-TT-170022 | FA | 0 | TRUE | FALSE | FALSE
101 | MRT-VL00-P2MAG-601006 | 2017-08-31 | MRT-DS-PLNE-TT-170022 | FA | 0 | TRUE | FALSE | FALSE
102 | MRT-VL00-P3MAG-602005 | 2017-08-31 | MRT-DS-PLNE-TT-170022 | FA | 0 | TRUE | FALSE | FALSE
103 | MRT-VL00-P3MAG-602006 | 2017-08-31 | MRT-DS-PLNE-TT-170022 | FA | 0 | TRUE | FALSE | FALSE
104 | MRT-DE00-P0ZEN-140001 | 2017-08-31 | MRT-DS-PLNE-TT-170023 | FA | 0 | TRUE | FALSE | FALSE
105 | MRT-CV03-P0ZEN-140002 | 2017-08-31 | MRT-DS-PLNE-TT-170024 | FA | 0 | TRUE | FALSE | FALSE
106 | MRT-XW03-P0MJ-110511 | 2017-08-31 | MRT-DS-PLNE-TT-170025 | FA | 0 | TRUE | FALSE | FALSE
179 | MRT-BF05-P0ZEN-175000 | 2017-08-31 | MRT-HK-PLNE-TT-170011 | FI | 0 | TRUE | FALSE | FALSE
180 | MRT-FF01-P0SGA-135404 | 2017-08-31 | MRT-HK-PLNE-TT-170011 | FA | 0 | TRUE | FALSE | FALSE
328 | MRT-YU01-P0ABA-150024 | 2017-09-06 | MRT-DS-PLNE-TT-170012 | FA | 1 | TRUE | TRUE | FALSE
329 | MRT-XS00-P3GC-135100 | 2017-09-06 | MRT-DS-PLNE-TT-170012 | FA | 1 | TRUE | TRUE | FALSE
330 | MRT-XS00-P0GA-125200 | 2017-09-06 | MRT-DS-PLNE-TT-170012 | FA | 1 | TRUE | TRUE | FALSE
331 | MRT-XW01-P00SA-135500 | 2017-09-06 | MRT-DS-PLNE-TT-170012 | FA | 1 | TRUE | TRUE | FALSE
181 | MRT-CC05-P0ZEN-175021 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
182 | MRT-CC05-P0ZEN-175022 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
183 | MRT-CC05-P0ZEN-175023 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
184 | MRT-CC05-P0ZEN-175024 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
185 | MRT-CC05-P0ZEN-175025 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
186 | MRT-CC05-P0ZEN-175026 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
187 | MRT-CC05-P0ZEN-175027 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
188 | MRT-CC05-P0ZEN-175028 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
189 | MRT-CC05-P0ZEN-175029 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
190 | MRT-CC05-P0ZEN-175030 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
191 | MRT-CC05-P0ZEN-175031 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
192 | MRT-CC05-P0ZEN-175032 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
193 | MRT-CC05-P0ZEN-175033 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
194 | MRT-CC05-P0ZEN-175034 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
195 | MRT-CC05-P0ZEN-175035 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
196 | MRT-CC05-P0ZEN-175036 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
197 | MRT-CC05-P0ZEN-175037 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
198 | MRT-CC05-P0ZEN-175041 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
199 | MRT-CC05-P0ZEN-175042 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
200 | MRT-CC05-P0ZEN-175043 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
201 | MRT-CC05-P0ZEN-175044 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
202 | MRT-CC05-P0ZEN-175045 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
203 | MRT-CC05-P0ZEN-175046 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
204 | MRT-CC05-P0ZEN-175047 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
205 | MRT-CC05-P0ZEN-175048 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
206 | MRT-CC05-P0ZEN-175049 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
207 | MRT-CC05-P0ZEN-175051 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
208 | MRT-CC05-P0ZEN-175052 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
209 | MRT-CC05-P0ZEN-175053 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
210 | MRT-CC05-P0ZEN-175054 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
211 | MRT-CC05-P0ZEN-175061 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
212 | MRT-CC05-P0ZEN-175062 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
213 | MRT-CC05-P0ZEN-175063 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
214 | MRT-CC05-P0ZEN-175064 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
215 | MRT-CC05-P0ZEN-175065 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
216 | MRT-CC05-P0ZEN-175066 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
217 | MRT-CC05-P0ZEN-175067 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
218 | MRT-CC05-P0ZEN-175068 | 2017-09-14 | MRT-HK-PLNE-TT-170013 | FA | 1 | TRUE | TRUE | FALSE
219 | MRT-XW01-P3MKG-125301 | 2017-09-19 | MRT-HK-PLNE-TT-170014 | FA | 1 | TRUE | TRUE | FALSE
220 | MRT-XG08-P3MKG-125302 | 2017-09-19 | MRT-HK-PLNE-TT-170014 | FA | 1 | TRUE | TRUE | FALSE
221 | MRT-XW01-P0GAA-135000 | 2017-09-19 | MRT-HK-PLNE-TT-170014 | FA | 1 | TRUE | TRUE | FALSE
222 | MRT-XG08-P0GAA-135001 | 2017-09-19 | MRT-HK-PLNE-TT-170014 | FA | 1 | TRUE | TRUE | FALSE
223 | MRT-CA07-P0ZEN-175001 | 2017-09-19 | MRT-HK-PLNE-TT-170014 | FA | 1 | TRUE | TRUE | FALSE
224 | MRT-CC05-P0ZEN-175069 | 2017-09-19 | MRT-HK-PLNE-TT-170014 | FA | 1 | TRUE | TRUE | FALSE
225 | MRT-CC05-P0ZEN-175070 | 2017-09-19 | MRT-HK-PLNE-TT-170014 | FA | 1 | TRUE | TRUE | FALSE
226 | MRT-CC05-P0ZEN-175071 | 2017-09-19 | MRT-HK-PLNE-TT-170014 | FA | 1 | TRUE | TRUE | FALSE
227 | MRT-CC05-P0ZEN-175072 | 2017-09-19 | MRT-HK-PLNE-TT-170014 | FA | 1 | TRUE | TRUE | FALSE
228 | MRT-CC05-P0ZEN-175073 | 2017-09-19 | MRT-HK-PLNE-TT-170014 | FA | 1 | TRUE | TRUE | FALSE
229 | MRT-CC07-P0ZEN-175075 | 2017-09-19 | MRT-HK-PLNE-TT-170014 | FA | 0 | TRUE | FALSE | FALSE
230 | MRT-XG02-P0GN-135202 | 2017-09-19 | MRT-HK-PLNE-TT-170014 | FA | 0 | TRUE | TRUE | FALSE
107 | MRT-QM01-P0ZEN-040001 | 2017-09-26 | MRT-DS-PLNE-TT-170026 | FA | 0 | TRUE | FALSE | FALSE
108 | MRT-YT01-P2MAG-601007 | 2017-09-26 | MRT-DS-PLNE-TT-170027 | FA | 0 | TRUE | FALSE | FALSE
109 | MRT-YT01-P2MAG-601008 | 2017-09-26 | MRT-DS-PLNE-TT-170027 | FI | 0 | TRUE | FALSE | FALSE
110 | MRT-YT01-P2MAG-601009 | 2017-09-26 | MRT-DS-PLNE-TT-170027 | FI | 0 | TRUE | FALSE | FALSE
111 | MRT-YT01-P3MAG-602007 | 2017-09-26 | MRT-DS-PLNE-TT-170027 | FA | 0 | TRUE | FALSE | FALSE
112 | MRT-YT01-P3MAG-602008 | 2017-09-26 | MRT-DS-PLNE-TT-170027 | FI | 0 | TRUE | FALSE | FALSE
113 | MRT-YT01-P3MAG-602009 | 2017-09-26 | MRT-DS-PLNE-TT-170027 | FI | 0 | TRUE | FALSE | FALSE
231 | MRT-XS00-P0GHC-110044 | 2017-09-28 | MRT-DS-PLNE-TT-170030 | FA | 0 | TRUE | FALSE | FALSE
232 | MRT-XW03-P0GHC-110051 | 2017-09-28 | MRT-DS-PLNE-TT-170030 | FA | 0 | TRUE | FALSE | FALSE
233 | MRT-CA06-P0UMA-180001 | 2017-09-28 | MRT-DS-PLNE-TT-170028 | FA | 0 | TRUE | FALSE | FALSE
234 | MRT-CA06-P0UMA-180003 | 2017-09-28 | MRT-DS-PLNE-TT-170028 | FA | 0 | TRUE | FALSE | FALSE
235 | MRT-XB02-P0UMA-180004 | 2017-09-28 | MRT-DS-PLNE-TT-170028 | FA | 0 | TRUE | FALSE | FALSE
236 | MRT-CA01-P0UMA-180005 | 2017-09-28 | MRT-DS-PLNE-TT-170028 | FA | 0 | TRUE | FALSE | FALSE
237 | MRT-CA01-P0UMA-180006 | 2017-09-28 | MRT-DS-PLNE-TT-170028 | FA | 0 | TRUE | FALSE | FALSE
238 | MRT-CA01-P0UMA-180007 | 2017-09-28 | MRT-DS-PLNE-TT-170028 | FA | 0 | TRUE | FALSE | FALSE
239 | MRT-CA00-P0UMA-180008 | 2017-09-28 | MRT-DS-PLNE-TT-170028 | FA | 0 | TRUE | FALSE | FALSE
240 | MRT-CA00-P0UMA-180010 | 2017-09-28 | MRT-DS-PLNE-TT-170028 | FA | 0 | TRUE | FALSE | FALSE
241 | MRT-CA00-P0UMA-180011 | 2017-09-28 | MRT-DS-PLNE-TT-170028 | FA | 0 | TRUE | FALSE | FALSE
242 | MRT-CA00-P0UMA-180013 | 2017-09-28 | MRT-DS-PLNE-TT-170028 | FA | 0 | TRUE | FALSE | FALSE
243 | MRT-CA00-P0UMA-180014 | 2017-09-28 | MRT-DS-PLNE-TT-170028 | FA | 0 | TRUE | FALSE | FALSE
244 | MRT-CA06-P0UCA-180101 | 2017-09-29 | MRT-DS-PLNE-TT-170029 | FA | 0 | TRUE | FALSE | FALSE
245 | MRT-XB02-P0UCA-180102 | 2017-09-29 | MRT-DS-PLNE-TT-170029 | FA | 0 | TRUE | FALSE | FALSE
246 | MRT-CA01-P0UCA-180103 | 2017-09-29 | MRT-DS-PLNE-TT-170029 | FA | 0 | TRUE | FALSE | FALSE
247 | MRT-CA02-P0UCA-180104 | 2017-09-29 | MRT-DS-PLNE-TT-170029 | FA | 0 | TRUE | FALSE | FALSE
248 | MRT-CA00-P0UCA-180105 | 2017-09-29 | MRT-DS-PLNE-TT-170029 | FA | 0 | TRUE | FALSE | FALSE
249 | MRT-CA00-P0UCA-180107 | 2017-09-29 | MRT-DS-PLNE-TT-170029 | FA | 0 | TRUE | FALSE | FALSE
250 | MRT-CA00-P0UCA-180108 | 2017-09-29 | MRT-DS-PLNE-TT-170029 | FA | 0 | TRUE | FALSE | FALSE
251 | MRT-CA00-P0UCA-180112 | 2017-09-29 | MRT-DS-PLNE-TT-170029 | FA | 0 | TRUE | FALSE | FALSE
252 | MRT-CA00-P0UCA-180113 | 2017-09-29 | MRT-DS-PLNE-TT-170029 | FA | 0 | TRUE | FALSE | FALSE
253 | MRT-XS00-P2LBA-110400 | 2017-09-29 | MRT-DS-PLNE-TT-170034 | FA | 1 | TRUE | TRUE | FALSE
254 | MRT-XS00-P2LBG-110401 | 2017-09-29 | MRT-DS-PLNE-TT-170034 | FA | 1 | TRUE | TRUE | FALSE
255 | MRT-XS00-P2LA-110402 | 2017-09-29 | MRT-DS-PLNE-TT-170034 | FA | 1 | TRUE | TRUE | FALSE
256 | MRT-XS00-P2LC-110403 | 2017-09-29 | MRT-DS-PLNE-TT-170034 | FA | 1 | TRUE | TRUE | FALSE
257 | MRT-XS00-P2PA-110404 | 2017-09-29 | MRT-DS-PLNE-TT-170034 | FA | 1 | TRUE | TRUE | FALSE
258 | MRT-XS00-P2PG-110405 | 2017-09-29 | MRT-DS-PLNE-TT-170034 | FA | 1 | TRUE | TRUE | FALSE
259 | MRT-XS00-P3LBA-110400 | 2017-09-29 | MRT-DS-PLNE-TT-170034 | FA | 1 | TRUE | TRUE | FALSE
260 | MRT-XS00-P3LBG-110401 | 2017-09-29 | MRT-DS-PLNE-TT-170034 | FA | 1 | TRUE | TRUE | FALSE
261 | MRT-XS00-P3LA-110402 | 2017-09-29 | MRT-DS-PLNE-TT-170034 | FA | 1 | TRUE | TRUE | FALSE
262 | MRT-XS00-P3LC-110403 | 2017-09-29 | MRT-DS-PLNE-TT-170034 | FA | 1 | TRUE | TRUE | FALSE
263 | MRT-XS00-P3PA-110404 | 2017-09-29 | MRT-DS-PLNE-TT-170034 | FA | 1 | TRUE | TRUE | FALSE
264 | MRT-XS00-P3PG-110405 | 2017-09-29 | MRT-DS-PLNE-TT-170034 | FA | 1 | TRUE | TRUE | FALSE
265 | MRT-YK08-P2LAA-605100 | 2017-09-29 | MRT-DS-PLNE-TT-170032 | FA | 0 | TRUE | FALSE | FALSE
266 | MRT-YK08-P3LAA-605500 | 2017-09-29 | MRT-DS-PLNE-TT-170032 | FA | 0 | TRUE | FALSE | FALSE
267 | MRT-YT01-P2LAA-605101 | 2017-09-29 | MRT-DS-PLNE-TT-170033 | FA | 0 | TRUE | FALSE | FALSE
268 | MRT-YT01-P3LAA-605501 | 2017-09-29 | MRT-DS-PLNE-TT-170033 | FA | 0 | TRUE | FALSE | FALSE
269 | MRT-YD00-P0PGB-606001 | 2017-09-29 | MRT-DS-PLNE-TT-170036 | FA | 0 | TRUE | FALSE | FALSE
270 | MRT-YD00-P0PGB-606000 | 2017-09-29 | MRT-DS-PLNE-TT-170036 | FA | 0 | TRUE | FALSE | FALSE
271 | MRT-XG02-P0ZEN-110002 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
272 | MRT-XG02-P2LBA-110003 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
273 | MRT-XG02-P2LBG-110004 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
274 | MRT-XG02-P0LBG-110004 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
275 | MRT-XG02-P2LCM-110005 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
276 | MRT-XG02-P2LA-110006 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
277 | MRT-XG02-P2LC-110007 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
278 | MRT-XG02-P2PA-110002 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
279 | MRT-XG02-P0PA-110002 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
280 | MRT-XG02-P2PA-110008 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
281 | MRT-XG02-P0GHC-110002 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
282 | MRT-XG02-P2PG-110009 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
283 | MRT-XG02-P0QJA-110010 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
284 | MRT-XG02-P3LBA-110003 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
285 | MRT-XG02-P3LBG-110004 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
286 | MRT-XG02-P3LCM-110005 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
287 | MRT-XG02-P3LA-110006 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
288 | MRT-XG02-P3LC-110007 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
289 | MRT-XG02-P3PA-110002 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
290 | MRT-XG02-P3PA-110008 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
291 | MRT-XG02-P3PG-110009 | 2017-09-29 | MRT-DS-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
292 | MRT-XG02-P2SCA-120004 | 2017-09-29 | MRT-DS-PLNE-TT-170031 | FA | 1 | TRUE | TRUE | FALSE
293 | MRT-XG02-P2SCA-120005 | 2017-09-29 | MRT-DS-PLNE-TT-170031 | FA | 1 | TRUE | TRUE | FALSE
294 | MRT-XG02-P2SCA-120006 | 2017-09-29 | MRT-DS-PLNE-TT-170031 | FA | 1 | TRUE | TRUE | FALSE
295 | MRT-XS00-P2SCA-120015 | 2017-09-29 | MRT-DS-PLNE-TT-170031 | FA | 1 | TRUE | TRUE | FALSE
296 | MRT-XG02-P3SCA-120004 | 2017-09-29 | MRT-DS-PLNE-TT-170031 | FA | 1 | TRUE | TRUE | FALSE
297 | MRT-XG02-P3SCA-120005 | 2017-09-29 | MRT-DS-PLNE-TT-170031 | FA | 1 | TRUE | TRUE | FALSE
298 | MRT-XG02-P3SCA-120006 | 2017-09-29 | MRT-DS-PLNE-TT-170031 | FA | 1 | TRUE | TRUE | FALSE
299 | MRT-XS00-P3SCA-120015 | 2017-09-29 | MRT-DS-PLNE-TT-170031 | FA | 1 | TRUE | TRUE | FALSE
300 | MRT-XG02-P0GKC-120001 | 2017-09-29 | MRT-DS-PLNE-TT-170031 | FA | 1 | TRUE | TRUE | FALSE
301 | MRT-XG02-P0GHD-120001 | 2017-09-29 | MRT-DS-PLNE-TT-170031 | FA | 1 | TRUE | TRUE | FALSE
302 | MRT-XW01-P0ZEN-161001 | 2017-09-29 | MRT-DS-PLNE-TT-170037 | FA | 0 | TRUE | FALSE | FALSE
303 | MRT-MA01-P2ZEN-161011 | 2017-09-29 | MRT-DS-PLNE-TT-170037 | FA | 0 | TRUE | FALSE | FALSE
304 | MRT-MA01-P3ZEN-161011 | 2017-09-29 | MRT-DS-PLNE-TT-170037 | FA | 0 | TRUE | FALSE | FALSE
305 | MRT-XG02-P2PAH-604102 | 2017-10-13 | MRT-DS-PLNE-TT-170039 | FA | 0 | TRUE | FALSE | FALSE
306 | MRT-YK08-P2PAH-604103 | 2017-10-13 | MRT-DS-PLNE-TT-170039 | FA | 0 | TRUE | FALSE | FALSE
307 | MRT-YK08-P2PAH-604104 | 2017-10-13 | MRT-DS-PLNE-TT-170039 | FA | 0 | TRUE | FALSE | FALSE
308 | MRT-XG02-P2PBB-604112 | 2017-10-13 | MRT-DS-PLNE-TT-170039 | FA | 0 | TRUE | FALSE | FALSE
309 | MRT-YK08-P2PBB-604113 | 2017-10-13 | MRT-DS-PLNE-TT-170039 | FA | 0 | TRUE | FALSE | FALSE
310 | MRT-XG02-P3PAH-604502 | 2017-10-13 | MRT-DS-PLNE-TT-170039 | FA | 0 | TRUE | FALSE | FALSE
311 | MRT-YK08-P3PAH-604503 | 2017-10-13 | MRT-DS-PLNE-TT-170039 | FA | 0 | TRUE | FALSE | FALSE
312 | MRT-YK08-P3PAH-604504 | 2017-10-13 | MRT-DS-PLNE-TT-170039 | FA | 0 | TRUE | FALSE | FALSE
313 | MRT-XG02-P3PBB-604512 | 2017-10-13 | MRT-DS-PLNE-TT-170039 | FA | 0 | TRUE | FALSE | FALSE
314 | MRT-YK08-P3PBB-604513 | 2017-10-13 | MRT-DS-PLNE-TT-170039 | FA | 0 | TRUE | FALSE | FALSE
315 | MRT-XG07-P2LBA-110300 | 2017-10-13 | MRT-DS-PLNE-TT-170040 | FA | 0 | TRUE | FALSE | FALSE
316 | MRT-XG07-P2PA-110304 | 2017-10-13 | MRT-DS-PLNE-TT-170040 | FA | 0 | TRUE | FALSE | FALSE
317 | MRT-XG07-P3LBA-110300 | 2017-10-13 | MRT-DS-PLNE-TT-170040 | FA | 0 | TRUE | FALSE | FALSE
318 | MRT-XG07-P3PA-110304 | 2017-10-13 | MRT-DS-PLNE-TT-170040 | FA | 0 | TRUE | FALSE | FALSE
319 | MRT-YK08-P0ZEN-020004 | 2017-10-16 | MRT-DS-PLNE-TT-170041 | FA | 1 | TRUE | TRUE | FALSE
320 | MRT-XG02-P0GA-125201 | 2017-10-16 | MRT-HK-PLNE-TT-170016 | FA | 0 | TRUE | FALSE | FALSE
321 | MRT-XA00-P3GC-135105 | 2017-10-16 | MRT-HK-PLNE-TT-170016 | FA | 0 | TRUE | FALSE | FALSE
322 | MRT-CV03-P0SGA-135400 | 2017-10-16 | MRT-HK-PLNE-TT-170016 | FA | 1 | TRUE | TRUE | FALSE
323 | MRT-CY03-P0SGA-135402 | 2017-10-16 | MRT-HK-PLNE-TT-170016 | FA | 1 | TRUE | TRUE | FALSE
324 | MRT-FF01-P0SGA-135404 | 2017-10-16 | MRT-HK-PLNE-TT-170016 | FA | 1 | TRUE | TRUE | FALSE
325 | MRT-XW03-P0SMU-125002 | 2017-10-16 | MRT-HK-PLNE-TT-170016 | FA | 0 | TRUE | FALSE | FALSE
332 | MRT-YK08-P2LAA-605102 | 2017-10-19 | MRT-DS-PLNE-TT-170042 | FI | 0 | TRUE | FALSE | FALSE
333 | MRT-YK08-P3LAA-605502 | 2017-10-19 | MRT-DS-PLNE-TT-170042 | FI | 0 | TRUE | FALSE | FALSE
334 | MRT-XG05-P0ZEN-110001 | 2017-10-20 | MRT-DS-PLNE-TT-170038 | FA | 2 | TRUE | TRUE | FALSE
335 | MRT-CC07-P2UMA-170201 | 2017-10-20 | MRT-DS-PLNE-TT-170043 | FA | 0 | TRUE | FALSE | FALSE
336 | MRT-CC02-P2UMA-170203 | 2017-10-20 | MRT-DS-PLNE-TT-170043 | FA | 0 | TRUE | FALSE | FALSE
337 | MRT-CC02-P2UMA-170204 | 2017-10-20 | MRT-DS-PLNE-TT-170043 | FA | 0 | TRUE | FALSE | FALSE
338 | MRT-CC07-P3UMA-170201 | 2017-10-20 | MRT-DS-PLNE-TT-170043 | FA | 0 | TRUE | FALSE | FALSE
339 | MRT-CC02-P3UMA-170203 | 2017-10-20 | MRT-DS-PLNE-TT-170043 | FA | 0 | TRUE | FALSE | FALSE
340 | MRT-CC02-P3UMA-170204 | 2017-10-20 | MRT-DS-PLNE-TT-170043 | FA | 0 | TRUE | FALSE | FALSE
341 | MRT-XG02-P2LB-122022 | 2017-10-20 | MRT-DS-PLNE-TT-170044 | FA | 1 | TRUE | TRUE | FALSE
342 | MRT-CC07-P2UHA-170001 | 2017-10-23 | MRT-DS-PLNE-TT-170045 | FA | 0 | TRUE | FALSE | FALSE
343 | MRT-CC02-P2UHA-170003 | 2017-10-23 | MRT-DS-PLNE-TT-170045 | FA | 0 | TRUE | FALSE | FALSE
344 | MRT-CC02-P2UHA-170004 | 2017-10-23 | MRT-DS-PLNE-TT-170045 | FA | 0 | TRUE | FALSE | FALSE
345 | MRT-CC07-P3UHA-170001 | 2017-10-23 | MRT-DS-PLNE-TT-170045 | FA | 0 | TRUE | FALSE | FALSE
346 | MRT-CC02-P3UHA-170003 | 2017-10-23 | MRT-DS-PLNE-TT-170045 | FA | 0 | TRUE | FALSE | FALSE
347 | MRT-CC02-P3UHA-170004 | 2017-10-23 | MRT-DS-PLNE-TT-170045 | FA | 0 | TRUE | FALSE | FALSE
348 | MRT-CC02-P0UHA-170002 | 2017-10-23 | MRT-DS-PLNE-TT-170045 | FA | 0 | TRUE | FALSE | FALSE
349 | MRT-XG02-P3GC-135102 | 2017-10-23 | MRT-HK-PLNE-TT-170019 | FA | 0 | TRUE | FALSE | FALSE
350 | MRT-XA00-P3GC-135105 | 2017-10-23 | MRT-HK-PLNE-TT-170019 | FA | 0 | TRUE | FALSE | FALSE
351 | MRT-XA00-P0GEN-135305 | 2017-10-23 | MRT-HK-PLNE-TT-170019 | FA | 0 | TRUE | FALSE | FALSE
352 | MRT-XH00-P0GH-145001 | 2017-10-23 | MRT-HK-PLNE-TT-170019 | FA | 0 | TRUE | FALSE | FALSE
353 | MRT-XA00-P3MKG-125305 | 2017-10-23 | MRT-HK-PLNE-TT-170019 | FI | 0 | TRUE | FALSE | FALSE
354 | MRT-XA00-P0GAA-135004 | 2017-10-23 | MRT-HK-PLNE-TT-170019 | FI | 0 | TRUE | FALSE | FALSE
355 | MRT-XA00-P0QHA-125402 | 2017-10-23 | MRT-HK-PLNE-TT-170019 | FI | 0 | TRUE | FALSE | FALSE
356 | MRT-XA00-P0MJA-125502 | 2017-10-23 | MRT-HK-PLNE-TT-170019 | FI | 0 | TRUE | FALSE | FALSE
357 | MRT-XW01-P0SMU-125001 | 2017-10-23 | MRT-HK-PLNE-TT-170019 | FA | 2 | TRUE | TRUE | FALSE
358 | MRT-XS00-P2PA-110400 | 2017-10-24 | MRT-DS-PLNE-TT-170046 | FA | 1 | TRUE | TRUE | FALSE
359 | MRT-XS00-P3PA-110400 | 2017-10-24 | MRT-DS-PLNE-TT-170046 | FA | 1 | TRUE | TRUE | FALSE
360 | MRT-XS00-P0GKC-120001 | 2017-10-25 | MRT-DS-PLNE-TT-170047 | FA | 1 | TRUE | TRUE | FALSE
361 | MRT-XS00-P0GHD-120001 | 2017-10-25 | MRT-DS-PLNE-TT-170047 | FA | 1 | TRUE | TRUE | FALSE
369 | MRT-XS00-P2MAV-120053 | 2017-10-26 | MRT-DS-PLNE-TT-170048 | FA | 1 | TRUE | TRUE | FALSE
370 | MRT-XS00-P3MAV-120053 | 2017-10-26 | MRT-DS-PLNE-TT-170048 | FA | 1 | TRUE | TRUE | FALSE
371 | MRT-XG02-P2MAV-120054 | 2017-10-26 | MRT-DS-PLNE-TT-170048 | FA | 1 | TRUE | TRUE | FALSE
372 | MRT-XG02-P3MAV-120054 | 2017-10-26 | MRT-DS-PLNE-TT-170048 | FA | 1 | TRUE | TRUE | FALSE
445 | MRT-XS01-P0ABA-150002 | 2017-10-26 | MRT-HK-PLNE-TT-170022 | FA | 1 | TRUE | TRUE | FALSE
446 | MRT-YR04-P0ZEN-165001 | 2017-10-26 | MRT-HK-PLNE-TT-170022 | FA | 1 | TRUE | TRUE | FALSE
362 | MRT-CA01-P0UCA-180122 | 2017-10-27 | MRT-DS-PLNE-TT-170049 | FA | 0 | TRUE | FALSE | FALSE
363 | MRT-CA01-P0UCA-180123 | 2017-10-27 | MRT-DS-PLNE-TT-170049 | FA | 0 | TRUE | FALSE | FALSE
364 | MRT-CA01-P0UCA-180127 | 2017-10-27 | MRT-DS-PLNE-TT-170049 | FA | 0 | TRUE | FALSE | FALSE
365 | MRT-CA01-P0UCA-180128 | 2017-10-27 | MRT-DS-PLNE-TT-170049 | FA | 0 | TRUE | FALSE | FALSE
366 | MRT-CA02-P0UCA-180134 | 2017-10-27 | MRT-DS-PLNE-TT-170049 | FA | 0 | TRUE | FALSE | FALSE
367 | MRT-CA02-P0UCA-180135 | 2017-10-27 | MRT-DS-PLNE-TT-170049 | FA | 0 | TRUE | FALSE | FALSE
368 | MRT-CA02-P0UCA-180136 | 2017-10-27 | MRT-DS-PLNE-TT-170049 | FA | 0 | TRUE | FALSE | FALSE
373 | MRT-CA06-P0UMA-180002 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
374 | MRT-CA03-P0UMA-180025 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
375 | MRT-CA03-P0UMA-180026 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
376 | MRT-CA01-P0UMA-180027 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
377 | MRT-CA03-P0UMA-180028 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
378 | MRT-CA03-P0UMA-180029 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
379 | MRT-CA03-P0UMA-180031 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
380 | MRT-CA03-P0UMA-180032 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
381 | MRT-CA03-P0UMA-180033 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
382 | MRT-CA03-P0UMA-180034 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
383 | MRT-CA03-P0UMA-180042 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
384 | MRT-CA03-P0UMA-180043 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
385 | MRT-CA03-P0UMA-180046 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
386 | MRT-CA03-P0UMA-180030 | 2017-10-27 | MRT-DS-PLNE-TT-170050 | FA | 0 | TRUE | FALSE | FALSE
387 | MRT-CA00-P0UQA-186522 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 0 | TRUE | FALSE | FALSE
388 | MRT-CA00-P0UQA-186520 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 0 | TRUE | FALSE | FALSE
389 | MRT-CA00-P0UQA-186515 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 0 | TRUE | FALSE | FALSE
390 | MRT-CA00-P0UQA-186512 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 0 | TRUE | FALSE | FALSE
391 | MRT-CA00-P0UQA-186511 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 0 | TRUE | FALSE | FALSE
392 | MRT-CC01-P0ZEN-175019 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 0 | TRUE | FALSE | FALSE
393 | MRT-CA07-P0ZEN-175001 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 2 | TRUE | TRUE | FALSE
394 | MRT-CC05-P0ZEN-175069 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 2 | TRUE | TRUE | FALSE
395 | MRT-CC05-P0ZEN-175070 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 2 | TRUE | TRUE | FALSE
396 | MRT-CC05-P0ZEN-175071 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 2 | TRUE | TRUE | FALSE
397 | MRT-CC05-P0ZEN-175072 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 2 | TRUE | TRUE | FALSE
398 | MRT-CC05-P0ZEN-175073 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 2 | TRUE | TRUE | FALSE
399 | MRT-CC07-P0ZEN-175075 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 1 | TRUE | TRUE | FALSE
400 | MRT-CC07-P0UPC-175701 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 0 | TRUE | TRUE | FALSE
401 | MRT-CC02-P0UPC-175705 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 0 | TRUE | FALSE | FALSE
402 | MRT-CA00-P0UQA-186510 | 2017-10-27 | MRT-HK-PLNE-TT-170020 | FA | 0 | TRUE | FALSE | FALSE
403 | MRT-XG07-P2PA-110002 | 2017-10-27 | MRT-DS-PLNE-TT-170051 | FA | 0 | TRUE | FALSE | FALSE
404 | MRT-XG07-P3PA-110002 | 2017-10-27 | MRT-DS-PLNE-TT-170051 | FA | 0 | TRUE | FALSE | FALSE
405 | MRT-XL00-P0ZEN-140001 | 2017-10-30 | MRT-DS-PLNE-TT-170054 | FA | 0 | TRUE | FALSE | FALSE
406 | MRT-UC07-P0ZEN-100001 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 2 | TRUE | TRUE | FALSE
407 | MRT-UC08-P0ZEN-100002 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
408 | MRT-UC08-P0ZEN-100003 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
409 | MRT-UE00-P2ZEN-100004 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
410 | MRT-UE00-P2ZEN-100005 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
411 | MRT-UE00-P2ZEN-100006 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
412 | MRT-UE00-P2ZEN-100007 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
413 | MRT-UE00-P2ZEN-100008 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
414 | MRT-UE00-P2ZEN-100009 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
415 | MRT-UE00-P3ZEN-100010 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
416 | MRT-UE00-P3ZEN-100011 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
417 | MRT-UE00-P3ZEN-100012 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
418 | MRT-UE00-P3ZEN-100013 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
419 | MRT-UE00-P3ZEN-100014 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
420 | MRT-UE00-P3ZEN-100015 | 2017-10-31 | MRT-DS-PLNE-TT-170053 | FA | 1 | TRUE | TRUE | FALSE
421 | MRT-CA07-P2MAA-220003 | 2017-10-31 | MRT-DS-PLNE-TT-170052 | FI | 0 | TRUE | FALSE | FALSE
422 | MRT-VL00-P2MAA-220010 | 2017-10-31 | MRT-DS-PLNE-TT-170052 | FI | 0 | TRUE | FALSE | FALSE
423 | MRT-YD00-P2MAA-220030 | 2017-10-31 | MRT-DS-PLNE-TT-170052 | FI | 0 | TRUE | FALSE | FALSE
424 | MRT-YD00-P2MAA-220031 | 2017-10-31 | MRT-DS-PLNE-TT-170052 | FI | 0 | TRUE | FALSE | FALSE
425 | MRT-XW03-P2LC-110501 | 2017-10-31 | MRT-DS-PLNE-TT-170056 | FA | 1 | TRUE | TRUE | FALSE
426 | MRT-XW03-P2LA-110500 | 2017-10-31 | MRT-DS-PLNE-TT-170056 | FA | 1 | TRUE | TRUE | FALSE
427 | MRT-XW03-P3LC-110501 | 2017-10-31 | MRT-DS-PLNE-TT-170056 | FA | 1 | TRUE | TRUE | FALSE
428 | MRT-XW03-P3LA-110500 | 2017-10-31 | MRT-DS-PLNE-TT-170056 | FA | 1 | TRUE | TRUE | FALSE
429 | MRT-QM01-P0ZEN-040002 | 2017-10-31 | MRT-DS-PLNE-TT-170057 | FA | 1 | TRUE | TRUE | FALSE
430 | MRT-QM01-P0ZEN-040003 | 2017-10-31 | MRT-DS-PLNE-TT-170057 | FA | 1 | TRUE | TRUE | FALSE
431 | MRT-XN00-P0ZEN-140001 | 2017-11-01 | MRT-DS-PLNE-TT-170055 | FA | 0 | TRUE | FALSE | FALSE
432 | MRT-QM03-P0ZEN-045002 | 2017-11-01 | MRT-HK-PLNE-TT-170024 | FA | 0 | TRUE | FALSE | FALSE
433 | MRT-DD00-P0ZEN-045001 | 2017-11-01 | MRT-HK-PLNE-TT-170024 | FA | 0 | TRUE | FALSE | FALSE
434 | MRT-XS00-P0GN-135200 | 2017-11-01 | MRT-HK-PLNE-TT-170024 | FA | 1 | TRUE | FALSE | FALSE
435 | MRT-XW03-P0GN-135201 | 2017-11-01 | MRT-HK-PLNE-TT-170024 | FA | 1 | TRUE | FALSE | FALSE
436 | MRT-XA00-P0PAC-125102 | 2017-11-01 | MRT-HK-PLNE-TT-170024 | FA | 0 | TRUE | FALSE | FALSE
437 | MRT-VL00-P2MAA-220001 | 2017-11-02 | MRT-DS-PLNE-TT-170058 | FI | 0 | TRUE | FALSE | FALSE
438 | MRT-VL00-P2MAA-220009 | 2017-11-02 | MRT-DS-PLNE-TT-170058 | FI | 0 | TRUE | FALSE | FALSE
439 | MRT-VL00-P3MAA-220009 | 2017-11-03 | MRT-DS-PLNE-TT-170059 | FI | 0 | TRUE | FALSE | FALSE
440 | MRT-UF00-P2MAA-220023 | 2017-11-03 | MRT-DS-PLNE-TT-170059 | FI | 0 | TRUE | FALSE | FALSE
441 | MRT-VL00-P3MAA-220001 | 2017-11-03 | MRT-DS-PLNE-TT-170059 | FI | 0 | TRUE | FALSE | FALSE
442 | MRT-UF00-P3MAA-220023 | 2017-11-03 | MRT-DS-PLNE-TT-170059 | FI | 0 | TRUE | FALSE | FALSE
447 | MRT-DS00-P0ZEN-175000 | 2017-11-03 | MRT-HK-PLNE-TT-170026 | FA | 0 | TRUE | FALSE | FALSE
450 | MRT-CC02-P0UPC-175705 | 2017-11-03 | MRT-HK-PLNE-TT-170025 | FA | 1 | TRUE | FALSE | FALSE
443 | MRT-DE00-P0ZEN-140001 | 2017-11-06 | MRT-DS-PLNE-TT-170061 | FA | 1 | TRUE | TRUE | FALSE
444 | MRT-CV03-P0ZEN-140002 | 2017-11-06 | MRT-DS-PLNE-TT-170061 | FA | 1 | TRUE | TRUE | FALSE
448 | MRT-XW03-P2PGB-113110 | 2017-11-06 | MRT-DS-PLNE-TT-170062 | FA | 1 | TRUE | TRUE | FALSE
449 | MRT-XW03-P3PGB-113110 | 2017-11-06 | MRT-DS-PLNE-TT-170062 | FA | 1 | TRUE | TRUE | FALSE
451 | MRT-CA07-P3MAA-220003 | 2017-11-07 | MRT-DS-PLNE-TT-170060 | FI | 0 | TRUE | FALSE | FALSE
452 | MRT-VL00-P3MAA-220010 | 2017-11-07 | MRT-DS-PLNE-TT-170060 | FI | 0 | TRUE | FALSE | FALSE
453 | MRT-YD00-P3MAA-220030 | 2017-11-07 | MRT-DS-PLNE-TT-170060 | FI | 0 | TRUE | FALSE | FALSE
454 | MRT-YD00-P3MAA-220031 | 2017-11-07 | MRT-DS-PLNE-TT-170060 | FI | 0 | TRUE | FALSE | FALSE
455 | MRT-XB00-P2MKA-220001 | 2017-11-08 | MRT-DS-PLNE-TT-170063 | FA | 0 | TRUE | FALSE | FALSE
456 | MRT-UF00-P2MKA-220001 | 2017-11-08 | MRT-DS-PLNE-TT-170063 | FI | 0 | TRUE | FALSE | FALSE
457 | MRT-YD00-P2MKA-220001 | 2017-11-08 | MRT-DS-PLNE-TT-170063 | FI | 0 | TRUE | FALSE | FALSE
458 | MRT-YD00-P2MKA-220003 | 2017-11-08 | MRT-DS-PLNE-TT-170063 | FA | 0 | TRUE | FALSE | FALSE
459 | MRT-XB00-P3MKA-220001 | 2017-11-08 | MRT-DS-PLNE-TT-170063 | FA | 0 | TRUE | FALSE | FALSE
460 | MRT-UF00-P3MKA-220001 | 2017-11-08 | MRT-DS-PLNE-TT-170063 | FI | 0 | TRUE | FALSE | FALSE
461 | MRT-YD00-P3MKA-220001 | 2017-11-08 | MRT-DS-PLNE-TT-170063 | FI | 0 | TRUE | FALSE | FALSE
462 | MRT-YD00-P3MKA-220003 | 2017-11-08 | MRT-DS-PLNE-TT-170063 | FA | 0 | TRUE | FALSE | FALSE
555 | MRT-XS00-P3GC-135100 | 2017-11-08 | MRT-HK-PLNE-TT-170027 | FA | 2 | TRUE | TRUE | FALSE
556 | MRT-XS00-P0GA-125200 | 2017-11-08 | MRT-HK-PLNE-TT-170027 | FA | 2 | TRUE | TRUE | FALSE
557 | MRT-XW03-P3GC-135101 | 2017-11-08 | MRT-HK-PLNE-TT-170027 | FA | 1 | TRUE | TRUE | FALSE
558 | MRT-XW01-P00SA-135500 | 2017-11-08 | MRT-HK-PLNE-TT-170027 | FA | 2 | TRUE | TRUE | FALSE
559 | MRT-XW01-P0GAA-135000 | 2017-11-08 | MRT-HK-PLNE-TT-170027 | FA | 2 | TRUE | TRUE | FALSE
463 | MRT-UE00-P2LB-122008 | 2017-11-09 | MRT-DS-PLNE-TT-170065 | FI | 0 | TRUE | FALSE | FALSE
464 | MRT-XB02-P2LB-122017 | 2017-11-09 | MRT-DS-PLNE-TT-170065 | FA | 0 | TRUE | FALSE | FALSE
465 | MRT-YQ03-P2LB-122088 | 2017-11-09 | MRT-DS-PLNE-TT-170065 | FA | 0 | TRUE | FALSE | FALSE
466 | MRT-YT01-P2MAJ-603100 | 2017-11-09 | MRT-DS-PLNE-TT-170064 | FA | 0 | TRUE | FALSE | FALSE
467 | MRT-XG02-P2MAJ-603101 | 2017-11-09 | MRT-DS-PLNE-TT-170064 | FA | 0 | TRUE | FALSE | FALSE
468 | MRT-YK08-P2MAJ-603102 | 2017-11-09 | MRT-DS-PLNE-TT-170064 | FA | 0 | TRUE | FALSE | FALSE
469 | MRT-YT01-P2MAJ-603104 | 2017-11-09 | MRT-DS-PLNE-TT-170064 | FI | 0 | TRUE | FALSE | FALSE
470 | MRT-YL00-P2MAJ-603107 | 2017-11-09 | MRT-DS-PLNE-TT-170064 | FA | 0 | TRUE | FALSE | FALSE
471 | MRT-YT01-P3MAJ-604100 | 2017-11-09 | MRT-DS-PLNE-TT-170064 | FA | 0 | TRUE | FALSE | FALSE
472 | MRT-XG02-P3MAJ-604101 | 2017-11-09 | MRT-DS-PLNE-TT-170064 | FA | 0 | TRUE | FALSE | FALSE
473 | MRT-YK08-P3MAJ-604102 | 2017-11-09 | MRT-DS-PLNE-TT-170064 | FA | 0 | TRUE | FALSE | FALSE
474 | MRT-YT01-P3MAJ-604104 | 2017-11-09 | MRT-DS-PLNE-TT-170064 | FI | 0 | TRUE | FALSE | FALSE
475 | MRT-YL00-P3MAJ-604107 | 2017-11-09 | MRT-DS-PLNE-TT-170064 | FA | 0 | TRUE | FALSE | FALSE
476 | MRT-XW03-P0GEN-135301 | 2017-11-09 | MRT-HK-PLNE-TT-170028 | FA | 1 | TRUE | TRUE | FALSE
477 | MRT-FF01-P0SGA-135403 | 2017-11-09 | MRT-HK-PLNE-TT-170028 | FA | 0 | TRUE | FALSE | FALSE
478 | MRT-YD00-P0QHE-606001 | 2017-11-10 | MRT-DS-PLNE-TT-170066 | FA | 0 | TRUE | FALSE | FALSE
479 | MRT-YD06-P2ZEN-161014 | 2017-11-13 | MRT-DS-PLNE-TT-170068 | FA | 0 | TRUE | FALSE | FALSE
480 | MRT-YD06-P3ZEN-161014 | 2017-11-13 | MRT-DS-PLNE-TT-170068 | FA | 0 | TRUE | FALSE | FALSE
481 | MRT-XW03-P2SCA-120017 | 2017-11-13 | MRT-DS-PLNE-TT-170067 | FA | 1 | TRUE | TRUE | FALSE
482 | MRT-XW03-P3SCA-120017 | 2017-11-13 | MRT-DS-PLNE-TT-170067 | FA | 1 | TRUE | TRUE | FALSE
483 | MRT-CA00-P0UMA-180009 | 2017-11-14 | MRT-DS-PLNE-TT-170069 | FA | 0 | TRUE | FALSE | FALSE
484 | MRT-CA00-P0UMA-180015 | 2017-11-14 | MRT-DS-PLNE-TT-170069 | FA | 0 | TRUE | FALSE | FALSE
485 | MRT-CA00-P0UMA-180016 | 2017-11-14 | MRT-DS-PLNE-TT-170069 | FA | 0 | TRUE | FALSE | FALSE
486 | MRT-CA00-P0UMA-180017 | 2017-11-14 | MRT-DS-PLNE-TT-170069 | FA | 0 | TRUE | FALSE | FALSE
487 | MRT-CA00-P0UMA-180019 | 2017-11-14 | MRT-DS-PLNE-TT-170069 | FA | 0 | TRUE | FALSE | FALSE
488 | MRT-CA00-P0UMA-180021 | 2017-11-14 | MRT-DS-PLNE-TT-170069 | FA | 0 | TRUE | FALSE | FALSE
489 | MRT-CA00-P0UMA-180022 | 2017-11-14 | MRT-DS-PLNE-TT-170069 | FA | 0 | TRUE | FALSE | FALSE
490 | MRT-XG02-P0ZEN-110002 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FC | 2 | TRUE | TRUE | FALSE
491 | MRT-XG02-P2LBA-110003 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
492 | MRT-XG02-P2LBG-110004 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
493 | MRT-XG02-P0LBG-110004 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
494 | MRT-XG02-P2LCM-110005 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
495 | MRT-XG02-P2LA-110006 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
496 | MRT-XG02-P2LC-110007 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
497 | MRT-XG02-P2PA-110002 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
498 | MRT-XG02-P0PA-110002 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
499 | MRT-XG02-P2PA-110008 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
500 | MRT-XG02-P0GHC-110002 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
501 | MRT-XG02-P2PG-110009 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
502 | MRT-XG02-P0QJA-110010 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
503 | MRT-XG02-P3LBA-110003 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
504 | MRT-XG02-P3LBG-110004 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
505 | MRT-XG02-P3LCM-110005 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
506 | MRT-XG02-P3LA-110006 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
507 | MRT-XG02-P3LC-110007 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
508 | MRT-XG02-P3PA-110002 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
509 | MRT-XG02-P3PA-110008 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
510 | MRT-XG02-P3PG-110009 | 2017-11-14 | MRT-DS-PLNE-TT-170070 | FA | 2 | TRUE | TRUE | FALSE
511 | MRT-YR05-P0ZEN-161016 | 2017-11-15 | MRT-DS-PLNE-TT-170071 | FA | 0 | TRUE | FALSE | FALSE
512 | MRT-XW03-P2PAC-113500 | 2017-11-16 | MRT-DS-PLNE-TT-170072 | FA | 1 | TRUE | TRUE | FALSE
513 | MRT-XW03-P3PAC-113500 | 2017-11-16 | MRT-DS-PLNE-TT-170072 | FA | 1 | TRUE | TRUE | FALSE
514 | MRT-MA02-P2ZEN-161015 | 2017-11-16 | MRT-DS-PLNE-TT-170074 | FA | 0 | TRUE | FALSE | FALSE
515 | MRT-MA02-P3ZEN-161015 | 2017-11-16 | MRT-DS-PLNE-TT-170074 | FA | 0 | TRUE | FALSE | FALSE
516 | MRT-YS00-P0ZEN-162120 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
517 | MRT-YS00-P0ZEN-162119 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
518 | MRT-YS00-P0ZEN-162118 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
519 | MRT-YS00-P0ZEN-162117 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
520 | MRT-YS00-P0ZEN-162116 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
521 | MRT-YS00-P0ZEN-162115 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
522 | MRT-YS00-P0ZEN-162114 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
523 | MRT-YS00-P0ZEN-162113 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
524 | MRT-YS00-P0ZEN-162112 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
525 | MRT-YS00-P0ZEN-162111 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
526 | MRT-YS00-P0ZEN-162110 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
527 | MRT-YS00-P0ZEN-162101 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
528 | MRT-YS00-P0ZEN-162102 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
529 | MRT-YS00-P0ZEN-162103 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
530 | MRT-YS00-P0ZEN-162104 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
531 | MRT-YS00-P0ZEN-162105 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
532 | MRT-YS00-P0ZEN-162106 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
533 | MRT-YS00-P0ZEN-162107 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
534 | MRT-YS00-P0ZEN-162108 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
535 | MRT-YS00-P0ZEN-162109 | 2017-11-17 | MRT-DS-PLNE-TT-170076 | FA | 0 | TRUE | FALSE | FALSE
536 | MRT-YL19-P0ABA-150003 | 2017-11-17 | MRT-HK-PLNE-TT-170029 | FA | 0 | TRUE | FALSE | FALSE
537 | MRT-XW03-P0BAA-150018 | 2017-11-17 | MRT-HK-PLNE-TT-170029 | FA | 0 | TRUE | FALSE | FALSE
538 | MRT-XW03-P0BAA-150019 | 2017-11-17 | MRT-HK-PLNE-TT-170029 | FA | 0 | TRUE | FALSE | FALSE
539 | MRT-YU01-P0ABA-150024 | 2017-11-17 | MRT-HK-PLNE-TT-170029 | FA | 2 | TRUE | FALSE | FALSE
540 | MRT-CA06-P0UMA-180001 | 2017-11-17 | MRT-DS-PLNE-TT-170078 | FA | 1 | TRUE | TRUE | FALSE
541 | MRT-CA06-P0UMA-180003 | 2017-11-17 | MRT-DS-PLNE-TT-170078 | FA | 1 | TRUE | TRUE | FALSE
542 | MRT-XB02-P0UMA-180004 | 2017-11-17 | MRT-DS-PLNE-TT-170078 | FA | 1 | TRUE | TRUE | FALSE
543 | MRT-CA01-P0UMA-180005 | 2017-11-17 | MRT-DS-PLNE-TT-170078 | FA | 1 | TRUE | TRUE | FALSE
544 | MRT-CA01-P0UMA-180006 | 2017-11-17 | MRT-DS-PLNE-TT-170078 | FA | 1 | TRUE | TRUE | FALSE
545 | MRT-CA01-P0UMA-180007 | 2017-11-17 | MRT-DS-PLNE-TT-170078 | FA | 1 | TRUE | TRUE | FALSE
546 | MRT-CA00-P0UMA-180008 | 2017-11-17 | MRT-DS-PLNE-TT-170078 | FA | 1 | TRUE | TRUE | FALSE
547 | MRT-CA00-P0UMA-180010 | 2017-11-17 | MRT-DS-PLNE-TT-170078 | FA | 1 | TRUE | TRUE | FALSE
548 | MRT-CA00-P0UMA-180011 | 2017-11-17 | MRT-DS-PLNE-TT-170078 | FA | 1 | TRUE | TRUE | FALSE
549 | MRT-CA00-P0UMA-180013 | 2017-11-17 | MRT-DS-PLNE-TT-170078 | FA | 1 | TRUE | TRUE | FALSE
550 | MRT-CA00-P0UMA-180014 | 2017-11-17 | MRT-DS-PLNE-TT-170078 | FA | 1 | TRUE | TRUE | FALSE
551 | MRT-XG07-P0ZEN-120050 | 2017-11-17 | MRT-DS-PLNE-TT-170079 | FA | 2 | TRUE | TRUE | FALSE
552 | MRT-XB02-P2LB-122018 | 2017-11-17 | MRT-DS-PLNE-TT-170075 | FA | 0 | TRUE | FALSE | FALSE
553 | MRT-XB02-P2LB-122016 | 2017-11-17 | MRT-DS-PLNE-TT-170075 | FA | 0 | TRUE | FALSE | FALSE
554 | MRT-UE00-P2LB-122007 | 2017-11-17 | MRT-DS-PLNE-TT-170075 | FA | 0 | TRUE | FALSE | FALSE
560 | MRT-XS00-P0GHC-110044 | 2017-11-20 | MRT-DS-PLNE-TT-170077 | FA | 1 | TRUE | TRUE | FALSE
561 | MRT-XW03-P0GHC-110051 | 2017-11-20 | MRT-DS-PLNE-TT-170077 | FA | 1 | TRUE | TRUE | FALSE
562 | MRT-YK08-P2MAG-601001 | 2017-11-20 | MRT-DS-PLNE-TT-170082 | FA | 1 | TRUE | TRUE | FALSE
563 | MRT-YK08-P3MAG-602001 | 2017-11-20 | MRT-DS-PLNE-TT-170082 | FA | 1 | TRUE | TRUE | FALSE
564 | MRT-YK08-P2MAG-601002 | 2017-11-20 | MRT-DS-PLNE-TT-170083 | FA | 1 | TRUE | TRUE | FALSE
565 | MRT-XL00-P2MAG-601003 | 2017-11-20 | MRT-DS-PLNE-TT-170083 | FI | 1 | TRUE | TRUE | FALSE
566 | MRT-XL00-P2MAG-601004 | 2017-11-20 | MRT-DS-PLNE-TT-170083 | FI | 1 | TRUE | TRUE | FALSE
567 | MRT-YK08-P3MAG-602002 | 2017-11-20 | MRT-DS-PLNE-TT-170083 | FA | 1 | TRUE | TRUE | FALSE
568 | MRT-XL00-P3MAG-602003 | 2017-11-20 | MRT-DS-PLNE-TT-170083 | FI | 1 | TRUE | TRUE | FALSE
569 | MRT-XL00-P3MAG-602004 | 2017-11-20 | MRT-DS-PLNE-TT-170083 | FI | 1 | TRUE | TRUE | FALSE
570 | MRT-VL00-P2MAG-601005 | 2017-11-20 | MRT-DS-PLNE-TT-170084 | FA | 1 | TRUE | TRUE | FALSE
571 | MRT-VL00-P2MAG-601006 | 2017-11-20 | MRT-DS-PLNE-TT-170084 | FA | 1 | TRUE | TRUE | FALSE
572 | MRT-VL00-P3MAG-602005 | 2017-11-20 | MRT-DS-PLNE-TT-170084 | FA | 1 | TRUE | TRUE | FALSE
573 | MRT-VL00-P3MAG-602006 | 2017-11-20 | MRT-DS-PLNE-TT-170084 | FA | 1 | TRUE | TRUE | FALSE
574 | MRT-XS00-P0GEN-135300 | 2017-11-20 | MRT-HK-PLNE-TT-170031 | FA | 1 | TRUE | TRUE | FALSE
575 | MRT-XA00-P0PAC-125102 | 2017-11-20 | MRT-HK-PLNE-TT-170031 | FA | 1 | TRUE | TRUE | FALSE
583 | MRT-CC07-P2UHA-170005 | 2017-11-20 | MRT-DS-PLNE-TT-170087 | FA | 0 | TRUE | FALSE | FALSE
584 | MRT-CC02-P2UHA-170007 | 2017-11-20 | MRT-DS-PLNE-TT-170087 | FA | 0 | TRUE | FALSE | FALSE
585 | MRT-CC02-P2UHA-170008 | 2017-11-20 | MRT-DS-PLNE-TT-170087 | FA | 0 | TRUE | FALSE | FALSE
586 | MRT-CC07-P3UHA-170005 | 2017-11-20 | MRT-DS-PLNE-TT-170087 | FA | 0 | TRUE | FALSE | FALSE
587 | MRT-CC02-P3UHA-170007 | 2017-11-20 | MRT-DS-PLNE-TT-170087 | FA | 0 | TRUE | FALSE | FALSE
588 | MRT-CC02-P3UHA-170008 | 2017-11-20 | MRT-DS-PLNE-TT-170087 | FA | 0 | TRUE | FALSE | FALSE
589 | MRT-BV02-P0ZEN-020005 | 2017-11-21 | MRT-DS-PLNE-TT-170088 | FI | 0 | TRUE | FALSE | FALSE
590 | MRT-XS00-P0GKC-120001 | 2017-11-21 | MRT-DS-PLNE-TT-170089 | FC | 2 | TRUE | TRUE | FALSE
591 | MRT-XS00-P0GHD-120001 | 2017-11-21 | MRT-DS-PLNE-TT-170089 | FC | 2 | TRUE | TRUE | FALSE
592 | MRT-YT01-P2PAH-604101 | 2017-11-21 | MRT-DS-PLNE-TT-170092 | FA | 0 | TRUE | FALSE | FALSE
593 | MRT-YT01-P2PBB-604111 | 2017-11-21 | MRT-DS-PLNE-TT-170092 | FA | 0 | TRUE | FALSE | FALSE
594 | MRT-YT01-P3PAH-604501 | 2017-11-21 | MRT-DS-PLNE-TT-170092 | FA | 0 | TRUE | FALSE | FALSE
595 | MRT-YT01-P3PBB-604511 | 2017-11-21 | MRT-DS-PLNE-TT-170092 | FA | 0 | TRUE | FALSE | FALSE
596 | MRT-XS00-P0GN-135200 | 2017-11-21 | MRT-HK-PLNE-TT-170030 | FA | 2 | TRUE | TRUE | FALSE
597 | MRT-XG02-P0GEN-135302 | 2017-11-21 | MRT-HK-PLNE-TT-170030 | FA | 1 | TRUE | TRUE | FALSE
598 | MRT-XG02-P0GA-125201 | 2017-11-21 | MRT-HK-PLNE-TT-170030 | FA | 1 | TRUE | TRUE | FALSE
599 | MRT-XA00-P0GN-135205 | 2017-11-21 | MRT-HK-PLNE-TT-170030 | FA | 1 | TRUE | TRUE | FALSE
600 | MRT-XH00-P0GH-145001 | 2017-11-21 | MRT-HK-PLNE-TT-170030 | FA | 1 | TRUE | TRUE | FALSE
601 | MRT-CV03-P0SGA-135400 | 2017-11-21 | MRT-HK-PLNE-TT-170030 | FA | 2 | TRUE | TRUE | FALSE
602 | MRT-XA00-P0MJA-125502 | 2017-11-21 | MRT-HK-PLNE-TT-170030 | FI | 1 | TRUE | TRUE | FALSE
603 | MRT-CA06-P0UCA-180101 | 2017-11-22 | MRT-DS-PLNE-TT-170093 | FA | 1 | TRUE | TRUE | FALSE
604 | MRT-XB02-P0UCA-180102 | 2017-11-22 | MRT-DS-PLNE-TT-170093 | FA | 1 | TRUE | TRUE | FALSE
605 | MRT-CA01-P0UCA-180103 | 2017-11-22 | MRT-DS-PLNE-TT-170093 | FA | 1 | TRUE | TRUE | FALSE
606 | MRT-CA02-P0UCA-180104 | 2017-11-22 | MRT-DS-PLNE-TT-170093 | FA | 1 | TRUE | TRUE | FALSE
607 | MRT-XW03-P0MJ-110511 | 2017-11-22 | MRT-DS-PLNE-TT-170091 | FA | 1 | TRUE | TRUE | FALSE
608 | MRT-XS00-P2SCA-120015 | 2017-11-22 | MRT-DS-PLNE-TT-170090 | FC | 2 | TRUE | TRUE | FALSE
609 | MRT-XS00-P3SCA-120015 | 2017-11-22 | MRT-DS-PLNE-TT-170090 | FC | 2 | TRUE | TRUE | FALSE
610 | MRT-CC07-P2UMA-170205 | 2017-11-22 | MRT-DS-PLNE-TT-170094 | FA | 0 | TRUE | FALSE | FALSE
611 | MRT-CC02-P2UMA-170207 | 2017-11-22 | MRT-DS-PLNE-TT-170094 | FA | 0 | TRUE | FALSE | FALSE
612 | MRT-CC02-P2UMA-170208 | 2017-11-22 | MRT-DS-PLNE-TT-170094 | FA | 0 | TRUE | FALSE | FALSE
613 | MRT-CC02-P2UMA-170209 | 2017-11-22 | MRT-DS-PLNE-TT-170094 | FA | 0 | TRUE | FALSE | FALSE
614 | MRT-CC07-P2UMA-170211 | 2017-11-22 | MRT-DS-PLNE-TT-170094 | FA | 0 | TRUE | FALSE | FALSE
576 | MRT-CC07-P2UHA-170001 | 2017-11-23 | MRT-DS-PLNE-TT-170085 | FA | 1 | TRUE | TRUE | FALSE
577 | MRT-CC02-P2UHA-170003 | 2017-11-23 | MRT-DS-PLNE-TT-170085 | FA | 1 | TRUE | TRUE | FALSE
578 | MRT-CC02-P2UHA-170004 | 2017-11-23 | MRT-DS-PLNE-TT-170085 | FA | 1 | TRUE | TRUE | FALSE
579 | MRT-CC07-P3UHA-170001 | 2017-11-23 | MRT-DS-PLNE-TT-170085 | FA | 1 | TRUE | TRUE | FALSE
580 | MRT-CC02-P3UHA-170003 | 2017-11-23 | MRT-DS-PLNE-TT-170085 | FA | 1 | TRUE | TRUE | FALSE
581 | MRT-CC02-P3UHA-170004 | 2017-11-23 | MRT-DS-PLNE-TT-170085 | FA | 1 | TRUE | TRUE | FALSE
582 | MRT-CC02-P0UHA-170002 | 2017-11-23 | MRT-DS-PLNE-TT-170085 | FA | 1 | TRUE | TRUE | FALSE
615 | MRT-YK08-P2LAA-605100 | 2017-11-23 | MRT-DS-PLNE-TT-170080 | FA | 1 | TRUE | TRUE | FALSE
616 | MRT-YK08-P3LAA-605500 | 2017-11-23 | MRT-DS-PLNE-TT-170080 | FA | 1 | TRUE | TRUE | FALSE
617 | MRT-YT01-P2LAA-605101 | 2017-11-23 | MRT-DS-PLNE-TT-170081 | FA | 1 | TRUE | TRUE | FALSE
618 | MRT-YT01-P3LAA-605501 | 2017-11-23 | MRT-DS-PLNE-TT-170081 | FA | 1 | TRUE | TRUE | FALSE
619 | MRT-XS00-P2LBA-110400 | 2017-11-23 | MRT-DS-PLNE-TT-170095 | FA | 2 | TRUE | TRUE | FALSE
620 | MRT-XS00-P2LBG-110401 | 2017-11-23 | MRT-DS-PLNE-TT-170095 | FA | 2 | TRUE | TRUE | FALSE
621 | MRT-XS00-P2LA-110402 | 2017-11-23 | MRT-DS-PLNE-TT-170095 | FA | 2 | TRUE | TRUE | FALSE
622 | MRT-XS00-P2LC-110403 | 2017-11-23 | MRT-DS-PLNE-TT-170095 | FA | 2 | TRUE | TRUE | FALSE
623 | MRT-XS00-P3LBA-110400 | 2017-11-23 | MRT-DS-PLNE-TT-170095 | FA | 2 | TRUE | TRUE | FALSE
624 | MRT-XS00-P3LBG-110401 | 2017-11-23 | MRT-DS-PLNE-TT-170095 | FA | 2 | TRUE | TRUE | FALSE
625 | MRT-XS00-P3LA-110402 | 2017-11-23 | MRT-DS-PLNE-TT-170095 | FA | 2 | TRUE | TRUE | FALSE
626 | MRT-XS00-P3LC-110403 | 2017-11-23 | MRT-DS-PLNE-TT-170095 | FA | 2 | TRUE | TRUE | FALSE
627 | MRT-XS00-P2PA-110404 | 2017-11-23 | MRT-DS-PLNE-TT-170096 | FC | 2 | TRUE | TRUE | FALSE
628 | MRT-XS00-P2PG-110405 | 2017-11-23 | MRT-DS-PLNE-TT-170096 | FC | 2 | TRUE | TRUE | FALSE
629 | MRT-XS00-P3PA-110404 | 2017-11-23 | MRT-DS-PLNE-TT-170096 | FC | 2 | TRUE | TRUE | FALSE
630 | MRT-XS00-P3PG-110405 | 2017-11-23 | MRT-DS-PLNE-TT-170096 | FC | 2 | TRUE | TRUE | FALSE
631 | MRT-YD00-P0PGB-606000 | 2017-11-23 | MRT-DS-PLNE-TT-170097 | FA | 1 | TRUE | TRUE | FALSE
632 | MRT-YD00-P0PGB-606001 | 2017-11-23 | MRT-DS-PLNE-TT-170097 | FA | 1 | TRUE | TRUE | FALSE
633 | MRT-XG02-P0GKC-120001 | 2017-11-23 | MRT-DS-PLNE-TT-170098 | FC | 2 | TRUE | FALSE | FALSE
634 | MRT-XG02-P0GHD-120001 | 2017-11-23 | MRT-DS-PLNE-TT-170098 | FA | 2 | TRUE | TRUE | FALSE
635 | MRT-XG02-P2SCA-120004 | 2017-11-23 | MRT-DS-PLNE-TT-170099 | FA | 2 | TRUE | TRUE | FALSE
636 | MRT-XG02-P2SCA-120005 | 2017-11-23 | MRT-DS-PLNE-TT-170099 | FA | 2 | TRUE | TRUE | FALSE
637 | MRT-XG02-P2SCA-120006 | 2017-11-23 | MRT-DS-PLNE-TT-170099 | FA | 2 | TRUE | TRUE | FALSE
638 | MRT-XG02-P3SCA-120004 | 2017-11-23 | MRT-DS-PLNE-TT-170099 | FA | 2 | TRUE | TRUE | FALSE
639 | MRT-XG02-P3SCA-120005 | 2017-11-23 | MRT-DS-PLNE-TT-170099 | FA | 2 | TRUE | TRUE | FALSE
640 | MRT-XG02-P3SCA-120006 | 2017-11-23 | MRT-DS-PLNE-TT-170099 | FA | 2 | TRUE | TRUE | FALSE
749 | MRT-UC08-P0ZEN-750009 | 2017-11-23 | MRT-HK-PLNE-TT-170032 | FA | 0 | TRUE | FALSE | FALSE
750 | MRT-UC08-P0ZEN-750008 | 2017-11-23 | MRT-HK-PLNE-TT-170032 | FA | 0 | TRUE | FALSE | FALSE
751 | MRT-UC08-P0ZEN-750007 | 2017-11-23 | MRT-HK-PLNE-TT-170032 | FA | 0 | TRUE | FALSE | FALSE
752 | MRT-UC08-P0ZEN-750006 | 2017-11-23 | MRT-HK-PLNE-TT-170032 | FA | 0 | TRUE | FALSE | FALSE
753 | MRT-UC08-P0ZEN-750005 | 2017-11-23 | MRT-HK-PLNE-TT-170032 | FA | 0 | TRUE | FALSE | FALSE
754 | MRT-UC08-P0ZEN-750004 | 2017-11-23 | MRT-HK-PLNE-TT-170032 | FA | 0 | TRUE | FALSE | FALSE
755 | MRT-UC08-P0ZEN-750003 | 2017-11-23 | MRT-HK-PLNE-TT-170032 | FA | 0 | TRUE | FALSE | FALSE
641 | MRT-YK08-P0ZEN-020004 | 2017-11-24 | MRT-DS-PLNE-TT-170100 | FC | 2 | TRUE | FALSE | FALSE
642 | MRT-DA05-P0ZEN-020006 | 2017-11-24 | MRT-DS-PLNE-TT-170103 | FI | 0 | TRUE | FALSE | FALSE
643 | MRT-CA05-P0UCA-180161 | 2017-11-24 | MRT-DS-PLNE-TT-170101 | FA | 0 | TRUE | FALSE | FALSE
644 | MRT-CA05-P0UCA-180162 | 2017-11-24 | MRT-DS-PLNE-TT-170101 | FA | 0 | TRUE | FALSE | FALSE
645 | MRT-CA05-P0UCA-180163 | 2017-11-24 | MRT-DS-PLNE-TT-170101 | FA | 0 | TRUE | FALSE | FALSE
646 | MRT-CA05-P0UCA-180164 | 2017-11-24 | MRT-DS-PLNE-TT-170101 | FA | 0 | TRUE | FALSE | FALSE
647 | MRT-XT00-P2MAA-220002 | 2017-11-27 | MRT-DS-PLNE-TT-170086 | FI | 0 | TRUE | FALSE | FALSE
648 | MRT-XT00-P3MAA-220002 | 2017-11-27 | MRT-DS-PLNE-TT-170086 | FI | 0 | TRUE | FALSE | FALSE
649 | MRT-CA00-P0UCA-180105 | 2017-11-27 | MRT-DS-PLNE-TT-170102 | FA | 1 | TRUE | TRUE | FALSE
650 | MRT-CA00-P0UCA-180106 | 2017-11-27 | MRT-DS-PLNE-TT-170102 | FA | 0 | TRUE | FALSE | FALSE
651 | MRT-CA00-P0UCA-180107 | 2017-11-27 | MRT-DS-PLNE-TT-170102 | FA | 1 | TRUE | TRUE | FALSE
652 | MRT-CA00-P0UCA-180108 | 2017-11-27 | MRT-DS-PLNE-TT-170102 | FA | 1 | TRUE | TRUE | FALSE
653 | MRT-CA00-P0UCA-180112 | 2017-11-27 | MRT-DS-PLNE-TT-170102 | FA | 1 | TRUE | TRUE | FALSE
654 | MRT-CA00-P0UCA-180113 | 2017-11-27 | MRT-DS-PLNE-TT-170102 | FA | 1 | TRUE | TRUE | FALSE
655 | MRT-CA00-P0UCA-180114 | 2017-11-27 | MRT-DS-PLNE-TT-170102 | FA | 0 | TRUE | FALSE | FALSE
656 | MRT-CA00-P0UCA-180115 | 2017-11-27 | MRT-DS-PLNE-TT-170102 | FA | 0 | TRUE | FALSE | FALSE
657 | MRT-CA00-P0UCA-180116 | 2017-11-27 | MRT-DS-PLNE-TT-170102 | FA | 0 | TRUE | FALSE | FALSE
658 | MRT-CA00-P0UCA-180117 | 2017-11-27 | MRT-DS-PLNE-TT-170102 | FA | 0 | TRUE | FALSE | FALSE
659 | MRT-XS00-P0GA-125200 | 2017-11-27 | MRT-HK-PLNE-TT-170032 | FA | 3 | TRUE | TRUE | FALSE
660 | MRT-XA00-P0GEN-135305 | 2017-11-27 | MRT-HK-PLNE-TT-170032 | FA | 1 | TRUE | TRUE | FALSE
661 | MRT-XA00-P3MKG-125305 | 2017-11-27 | MRT-HK-PLNE-TT-170032 | FI | 1 | TRUE | TRUE | FALSE
662 | MRT-DP00-P0ZEN-070001 | 2017-11-27 | MRT-DS-PLNE-TT-170105 | FA | 0 | TRUE | FALSE | FALSE
663 | MRT-YU04-P0ZEN-161012 | 2017-11-27 | MRT-DS-PLNE-TT-170106 | FA | 0 | TRUE | FALSE | FALSE
664 | MRT-YS01-P0ZEN-165013 | 2017-11-27 | MRT-HK-PLNE-TT-170033 | FA | 0 | TRUE | FALSE | FALSE
665 | MRT-XG02-P3GC-135102 | 2017-11-27 | MRT-HK-PLNE-TT-170033 | FA | 1 | TRUE | TRUE | FALSE
666 | MRT-XG02-P0GN-135202 | 2017-11-27 | MRT-HK-PLNE-TT-170033 | FA | 1 | TRUE | TRUE | FALSE
667 | MRT-XA00-P3GC-135105 | 2017-11-27 | MRT-HK-PLNE-TT-170033 | FA | 1 | TRUE | TRUE | FALSE
668 | MRT-XA00-P0GAA-135004 | 2017-11-27 | MRT-HK-PLNE-TT-170033 | FA | 1 | TRUE | TRUE | FALSE
669 | MRT-XA00-P0QHA-125402 | 2017-11-27 | MRT-HK-PLNE-TT-170033 | FI | 1 | TRUE | TRUE | FALSE
670 | MRT-XA00-P2MAA-220013 | 2017-11-28 | MRT-DS-PLNE-TT-170107 | FA | 0 | TRUE | FALSE | FALSE
671 | MRT-XA00-P2MAA-220014 | 2017-11-28 | MRT-DS-PLNE-TT-170107 | FA | 0 | TRUE | FALSE | FALSE
672 | MRT-XA00-P2MAA-220015 | 2017-11-28 | MRT-DS-PLNE-TT-170107 | FA | 0 | TRUE | FALSE | FALSE
673 | MRT-XA00-P2MAA-220016 | 2017-11-28 | MRT-DS-PLNE-TT-170107 | FA | 0 | TRUE | FALSE | FALSE
674 | MRT-XA00-P2MAA-220017 | 2017-11-28 | MRT-DS-PLNE-TT-170107 | FA | 0 | TRUE | FALSE | FALSE
675 | MRT-XA00-P2MAA-220018 | 2017-11-28 | MRT-DS-PLNE-TT-170107 | FA | 0 | TRUE | FALSE | FALSE
676 | MRT-XA00-P2MAA-220020 | 2017-11-28 | MRT-DS-PLNE-TT-170107 | FA | 0 | TRUE | FALSE | FALSE
677 | MRT-XA00-P2MAA-220021 | 2017-11-28 | MRT-DS-PLNE-TT-170107 | FA | 0 | TRUE | FALSE | FALSE
678 | MRT-XA00-P2MAA-220022 | 2017-11-28 | MRT-DS-PLNE-TT-170107 | FA | 0 | TRUE | FALSE | FALSE
679 | MRT-XA00-P3MAA-220016 | 2017-11-28 | MRT-DS-PLNE-TT-170109 | FA | 0 | TRUE | FALSE | FALSE
680 | MRT-XA00-P3MAA-220013 | 2017-11-28 | MRT-DS-PLNE-TT-170109 | FA | 0 | TRUE | FALSE | FALSE
681 | MRT-XA00-P3MAA-220014 | 2017-11-28 | MRT-DS-PLNE-TT-170109 | FA | 0 | TRUE | FALSE | FALSE
682 | MRT-XA00-P3MAA-220015 | 2017-11-28 | MRT-DS-PLNE-TT-170109 | FA | 0 | TRUE | FALSE | FALSE
683 | MRT-XA00-P3MAA-220017 | 2017-11-28 | MRT-DS-PLNE-TT-170109 | FA | 0 | TRUE | FALSE | FALSE
684 | MRT-XA00-P3MAA-220018 | 2017-11-28 | MRT-DS-PLNE-TT-170109 | FA | 0 | TRUE | FALSE | FALSE
685 | MRT-XA00-P3MAA-220019 | 2017-11-28 | MRT-DS-PLNE-TT-170109 | FA | 0 | TRUE | FALSE | FALSE
686 | MRT-XA00-P3MAA-220020 | 2017-11-28 | MRT-DS-PLNE-TT-170109 | FA | 0 | TRUE | FALSE | FALSE
687 | MRT-XA00-P3MAA-220021 | 2017-11-28 | MRT-DS-PLNE-TT-170109 | FA | 0 | TRUE | FALSE | FALSE
688 | MRT-XA00-P3MAA-220022 | 2017-11-28 | MRT-DS-PLNE-TT-170109 | FA | 0 | TRUE | FALSE | FALSE
689 | MRT-XW03-P2SCA-120017 | 2017-11-28 | MRT-DS-PLNE-TT-170111 | FC | 2 | TRUE | FALSE | FALSE
690 | MRT-XW03-P3SCA-120017 | 2017-11-28 | MRT-DS-PLNE-TT-170111 | FC | 2 | TRUE | FALSE | FALSE
691 | MRT-CA03-P0UMA-180035 | 2017-11-28 | MRT-DS-PLNE-TT-170108 | FA | 0 | TRUE | FALSE | FALSE
692 | MRT-CA03-P0UMA-180036 | 2017-11-28 | MRT-DS-PLNE-TT-170108 | FA | 0 | TRUE | FALSE | FALSE
693 | MRT-CA03-P0UMA-180037 | 2017-11-28 | MRT-DS-PLNE-TT-170108 | FA | 0 | TRUE | FALSE | FALSE
694 | MRT-CA03-P0UMA-180039 | 2017-11-28 | MRT-DS-PLNE-TT-170108 | FA | 0 | TRUE | FALSE | FALSE
695 | MRT-CA03-P0UMA-180040 | 2017-11-28 | MRT-DS-PLNE-TT-170108 | FA | 0 | TRUE | FALSE | FALSE
696 | MRT-CC02-P2UHA-170009 | 2017-11-29 | MRT-DS-PLNE-TT-170113 | FA | 0 | TRUE | FALSE | FALSE
697 | MRT-CC02-P3UHA-170009 | 2017-11-29 | MRT-DS-PLNE-TT-170113 | FA | 0 | TRUE | FALSE | FALSE
698 | MRT-CC07-P2UHA-170101 | 2017-11-29 | MRT-DS-PLNE-TT-170113 | FA | 0 | TRUE | FALSE | FALSE
699 | MRT-CC02-P2UHA-170103 | 2017-11-29 | MRT-DS-PLNE-TT-170113 | FA | 0 | TRUE | FALSE | FALSE
700 | MRT-CC02-P2UHA-170104 | 2017-11-29 | MRT-DS-PLNE-TT-170113 | FA | 0 | TRUE | FALSE | FALSE
701 | MRT-CC07-P3UHA-170101 | 2017-11-29 | MRT-DS-PLNE-TT-170113 | FA | 0 | TRUE | FALSE | FALSE
702 | MRT-CC02-P3UHA-170103 | 2017-11-29 | MRT-DS-PLNE-TT-170113 | FA | 0 | TRUE | FALSE | FALSE
703 | MRT-CC02-P3UHA-170104 | 2017-11-29 | MRT-DS-PLNE-TT-170113 | FA | 0 | TRUE | FALSE | FALSE
704 | MRT-XW01-P0ZEN-161001 | 2017-12-01 | MRT-DS-PLNE-TT-170114 | FA | 1 | TRUE | TRUE | FALSE
705 | MRT-MA01-P2ZEN-161011 | 2017-12-01 | MRT-DS-PLNE-TT-170114 | FA | 1 | TRUE | TRUE | FALSE
706 | MRT-MA01-P3ZEN-161011 | 2017-12-01 | MRT-DS-PLNE-TT-170114 | FA | 1 | TRUE | TRUE | FALSE
707 | MRT-DS00-P0ZEN-175000 | 2017-12-04 | MRT-HK-PLNE-TT-170034 | FA | 1 | TRUE | FALSE | FALSE
748 | MRT-BF05-P0ZEN-175004 | 2017-12-04 | MRT-HK-PLNE-TT-170034 | FA | 0 | TRUE | FALSE | FALSE
708 | MRT-XS00-P0GA-125200 | 2017-12-05 | MRT-HK-PLNE-TT-170035 | FA | 3 | TRUE | TRUE | FALSE
709 | MRT-FF01-P0SGA-135403 | 2017-12-05 | MRT-HK-PLNE-TT-170035 | FA | 1 | TRUE | TRUE | FALSE
710 | MRT-DE00-P0ZEN-140001 | 2017-12-07 | MRT-DS-PLNE-TT-170117 | FC | 2 | TRUE | TRUE | FALSE
711 | MRT-CV03-P0ZEN-140002 | 2017-12-07 | MRT-DS-PLNE-TT-170117 | FC | 2 | TRUE | TRUE | FALSE
712 | MRT-XS00-P2LB-122037 | 2017-12-07 | MRT-DS-PLNE-TT-170116 | FI | 0 | TRUE | FALSE | FALSE
713 | MRT-YB03-P2LB-122048 | 2017-12-07 | MRT-DS-PLNE-TT-170116 | FI | 0 | TRUE | FALSE | FALSE
714 | MRT-XB02-P2LB-122021 | 2017-12-07 | MRT-DS-PLNE-TT-170116 | FA | 0 | TRUE | FALSE | FALSE
715 | MRT-YD00-P3QHE-606003 | 2017-12-07 | MRT-DS-PLNE-TT-170120 | FA | 0 | TRUE | FALSE | FALSE
716 | MRT-YD00-P2QHE-606003 | 2017-12-07 | MRT-DS-PLNE-TT-170120 | FA | 0 | TRUE | FALSE | FALSE
717 | MRT-YD00-P0ERB-606001 | 2017-12-07 | MRT-DS-PLNE-TT-170120 | FA | 0 | TRUE | FALSE | FALSE
718 | MRT-YD00-P0ERB-606002 | 2017-12-07 | MRT-DS-PLNE-TT-170120 | FA | 0 | TRUE | FALSE | FALSE
719 | MRT-XL00-P0ZEN-140002 | 2017-12-07 | MRT-DS-PLNE-TT-170118 | FA | 0 | TRUE | FALSE | FALSE
720 | MRT-BF05-P0ZEN-195000 | 2017-12-07 | MRT-HK-PLNE-TT-170036 | FA | 0 | TRUE | FALSE | FALSE
721 | MRT-CC07-P2UHA-170001 | 2017-12-08 | MRT-DS-PLNE-TT-170122 | FC | 2 | TRUE | TRUE | FALSE
722 | MRT-CC02-P2UHA-170003 | 2017-12-08 | MRT-DS-PLNE-TT-170122 | FC | 2 | TRUE | TRUE | FALSE
723 | MRT-CC02-P2UHA-170004 | 2017-12-08 | MRT-DS-PLNE-TT-170122 | FC | 2 | TRUE | TRUE | FALSE
724 | MRT-CC07-P3UHA-170001 | 2017-12-08 | MRT-DS-PLNE-TT-170122 | FC | 2 | TRUE | TRUE | FALSE
725 | MRT-CC02-P3UHA-170003 | 2017-12-08 | MRT-DS-PLNE-TT-170122 | FC | 2 | TRUE | TRUE | FALSE
726 | MRT-CC02-P3UHA-170004 | 2017-12-08 | MRT-DS-PLNE-TT-170122 | FC | 2 | TRUE | TRUE | FALSE
727 | MRT-CC02-P0UHA-170002 | 2017-12-08 | MRT-DS-PLNE-TT-170122 | FC | 2 | TRUE | TRUE | FALSE
728 | MRT-XG07-P0ZEN-120050 | 2017-12-08 | MRT-DS-PLNE-TT-170121 | FC | 3 | TRUE | TRUE | FALSE
729 | MRT-XG02-P0GHD-120001 | 2017-12-08 | MRT-DS-PLNE-TT-170121 | FC | 3 | TRUE | TRUE | FALSE
730 | MRT-XS00-P2LBA-110400 | 2017-12-08 | MRT-DS-PLNE-TT-170123 | FC | 3 | TRUE | TRUE | FALSE
731 | MRT-XS00-P2LBG-110401 | 2017-12-08 | MRT-DS-PLNE-TT-170123 | FC | 3 | TRUE | TRUE | FALSE
732 | MRT-XS00-P2LA-110402 | 2017-12-08 | MRT-DS-PLNE-TT-170123 | FC | 3 | TRUE | TRUE | FALSE
733 | MRT-XS00-P2LC-110403 | 2017-12-08 | MRT-DS-PLNE-TT-170123 | FC | 3 | TRUE | TRUE | FALSE
734 | MRT-XS00-P2PA-110400 | 2017-12-08 | MRT-DS-PLNE-TT-170123 | FC | 2 | TRUE | TRUE | FALSE
735 | MRT-XS00-P3LBA-110400 | 2017-12-08 | MRT-DS-PLNE-TT-170123 | FC | 3 | TRUE | TRUE | FALSE
736 | MRT-XS00-P3LBG-110401 | 2017-12-08 | MRT-DS-PLNE-TT-170123 | FC | 3 | TRUE | TRUE | FALSE
737 | MRT-XS00-P3LA-110402 | 2017-12-08 | MRT-DS-PLNE-TT-170123 | FC | 3 | TRUE | TRUE | FALSE
738 | MRT-XS00-P3LC-110403 | 2017-12-08 | MRT-DS-PLNE-TT-170123 | FC | 3 | TRUE | TRUE | FALSE
739 | MRT-XS00-P3PA-110400 | 2017-12-08 | MRT-DS-PLNE-TT-170123 | FC | 2 | TRUE | TRUE | FALSE
740 | MRT-XS00-P0GHC-110044 | 2017-12-08 | MRT-DS-PLNE-TT-170123 | FC | 2 | TRUE | TRUE | FALSE
741 | MRT-CC07-P2UMA-170501 | 2017-12-08 | MRT-DS-PLNE-TT-170126 | FA | 0 | TRUE | FALSE | FALSE
742 | MRT-CC02-P2UMA-170503 | 2017-12-08 | MRT-DS-PLNE-TT-170126 | FA | 0 | TRUE | FALSE | FALSE
743 | MRT-CC02-P2UMA-170507 | 2017-12-08 | MRT-DS-PLNE-TT-170126 | FA | 0 | TRUE | FALSE | FALSE
744 | MRT-CC07-P3UMA-170501 | 2017-12-08 | MRT-DS-PLNE-TT-170126 | FA | 0 | TRUE | FALSE | FALSE
745 | MRT-CC02-P3UMA-170503 | 2017-12-08 | MRT-DS-PLNE-TT-170126 | FA | 0 | TRUE | FALSE | FALSE
746 | MRT-CC02-P3UMA-170507 | 2017-12-08 | MRT-DS-PLNE-TT-170126 | FA | 0 | TRUE | FALSE | FALSE
747 | MRT-CC02-P0UMA-170502 | 2017-12-08 | MRT-DS-PLNE-TT-170126 | FA | 0 | TRUE | FALSE | FALSE
756 | MRT-XW03-P2PAC-113500 | 2017-12-11 | MRT-DS-PLNE-TT-170127 | FC | 2 | TRUE | TRUE | FALSE
757 | MRT-XW03-P2PGB-113110 | 2017-12-11 | MRT-DS-PLNE-TT-170127 | FC | 2 | TRUE | TRUE | FALSE
758 | MRT-XW03-P2LC-110501 | 2017-12-11 | MRT-DS-PLNE-TT-170127 | FC | 2 | TRUE | TRUE | FALSE
759 | MRT-XW03-P2LA-110500 | 2017-12-11 | MRT-DS-PLNE-TT-170127 | FC | 2 | TRUE | TRUE | FALSE
760 | MRT-XW03-P3PAC-113500 | 2017-12-11 | MRT-DS-PLNE-TT-170127 | FC | 2 | TRUE | TRUE | FALSE
761 | MRT-XW03-P3PGB-113110 | 2017-12-11 | MRT-DS-PLNE-TT-170127 | FC | 2 | TRUE | TRUE | FALSE
762 | MRT-XW03-P3LC-110501 | 2017-12-11 | MRT-DS-PLNE-TT-170127 | FC | 2 | TRUE | TRUE | FALSE
763 | MRT-XW03-P3LA-110500 | 2017-12-11 | MRT-DS-PLNE-TT-170127 | FC | 2 | TRUE | TRUE | FALSE
764 | MRT-XW03-P0GHC-110051 | 2017-12-11 | MRT-DS-PLNE-TT-170127 | FC | 2 | TRUE | TRUE | FALSE
765 | MRT-XG05-P0ZEN-110001 | 2017-12-11 | MRT-DS-PLNE-TT-170104 | FC | 3 | TRUE | TRUE | FALSE
766 | MRT-CC07-P3UMA-170205 | 2017-12-12 | MRT-DS-PLNE-TT-170129 | FA | 0 | TRUE | FALSE | FALSE
767 | MRT-CC02-P3UMA-170207 | 2017-12-12 | MRT-DS-PLNE-TT-170129 | FA | 0 | TRUE | FALSE | FALSE
768 | MRT-CC02-P3UMA-170208 | 2017-12-12 | MRT-DS-PLNE-TT-170129 | FA | 0 | TRUE | FALSE | FALSE
769 | MRT-CC02-P3UMA-170209 | 2017-12-12 | MRT-DS-PLNE-TT-170129 | FA | 0 | TRUE | FALSE | FALSE
770 | MRT-CC07-P3UMA-170211 | 2017-12-12 | MRT-DS-PLNE-TT-170129 | FA | 0 | TRUE | FALSE | FALSE
771 | MRT-XW03-P3GHD-120001 | 2017-12-13 | MRT-DS-PLNE-TT-170119 | FA | 0 | TRUE | FALSE | FALSE
772 | MRT-XG02-P2LBA-110003 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
773 | MRT-XG02-P2LBG-110004 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
774 | MRT-XG02-P0LBG-110004 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
775 | MRT-XG02-P2LCM-110005 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
776 | MRT-XG02-P2LA-110006 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
777 | MRT-XG02-P2LC-110007 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
778 | MRT-XG02-P2PA-110002 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
779 | MRT-XG02-P0PA-110002 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
780 | MRT-XG02-P2PA-110008 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
781 | MRT-XG02-P0GHC-110002 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
782 | MRT-XG02-P2PG-110009 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
783 | MRT-XG02-P0QJA-110010 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
784 | MRT-XG02-P3LBA-110003 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
785 | MRT-XG02-P3LBG-110004 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
786 | MRT-XG02-P3LCM-110005 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
787 | MRT-XG02-P3LA-110006 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
788 | MRT-XG02-P3LC-110007 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
789 | MRT-XG02-P3PA-110002 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
790 | MRT-XG02-P3PA-110008 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
791 | MRT-XG02-P3PG-110009 | 2017-12-13 | MRT-DS-PLNE-TT-170131 | FC | 3 | TRUE | FALSE | FALSE
792 | MRT-YK08-P2LAA-605102 | 2017-12-14 | MRT-DS-PLNE-TT-170132 | FI | 1 | TRUE | TRUE | FALSE
793 | MRT-YK08-P3LAA-605502 | 2017-12-14 | MRT-DS-PLNE-TT-170132 | FI | 1 | TRUE | TRUE | FALSE
794 | MRT-XS00-P0GN-135200 | 2017-12-14 | MRT-HK-PLNE-TT-170037 | FA | 2 | TRUE | TRUE | FALSE
795 | MRT-XA00-P0GEN-135305 | 2017-12-14 | MRT-HK-PLNE-TT-170037 | FA | 1 | TRUE | TRUE | FALSE
796 | MRT-XA00-P0PAC-125102 | 2017-12-14 | MRT-HK-PLNE-TT-170037 | FA | 1 | TRUE | TRUE | FALSE
797 | MRT-XH00-P0GH-145001 | 2017-12-14 | MRT-HK-PLNE-TT-170037 | FA | 1 | TRUE | TRUE | FALSE
798 | MRT-CV03-P0SGA-135400 | 2017-12-14 | MRT-HK-PLNE-TT-170037 | FA | 2 | TRUE | TRUE | FALSE
799 | MRT-XA00-P3MKG-125305 | 2017-12-14 | MRT-HK-PLNE-TT-170037 | FI | 1 | TRUE | TRUE | FALSE
800 | MRT-XA00-P0GAA-135004 | 2017-12-14 | MRT-HK-PLNE-TT-170037 | FA | 1 | TRUE | TRUE | FALSE
801 | MRT-XA00-P0QHA-125402 | 2017-12-14 | MRT-HK-PLNE-TT-170037 | FI | 1 | TRUE | TRUE | FALSE
802 | MRT-XA00-P0MJA-125502 | 2017-12-14 | MRT-HK-PLNE-TT-170037 | FI | 1 | TRUE | TRUE | FALSE
840 | MRT-XA00-P0GN-135205 | 2017-12-14 | MRT-HK-PLNE-TT-170037 | FA | 1 | TRUE | TRUE | FALSE
803 | MRT-CA05-P0UMA-180061 | 2017-12-15 | MRT-DS-PLNE-TT-170135 | FA | 0 | TRUE | FALSE | FALSE
804 | MRT-CA05-P0UMA-180062 | 2017-12-15 | MRT-DS-PLNE-TT-170135 | FA | 0 | TRUE | FALSE | FALSE
805 | MRT-VK02-P2UHA-170010 | 2017-12-15 | MRT-DS-PLNE-TT-170128 | FA | 0 | TRUE | FALSE | FALSE
806 | MRT-VK02-P3UHA-170010 | 2017-12-15 | MRT-DS-PLNE-TT-170128 | FA | 0 | TRUE | FALSE | FALSE
807 | MRT-XB00-P2MKA-220001 | 2017-12-15 | MRT-DS-PLNE-TT-170136 | FA | 1 | TRUE | TRUE | FALSE
808 | MRT-UF00-P2MKA-220001 | 2017-12-15 | MRT-DS-PLNE-TT-170136 | FI | 1 | TRUE | TRUE | FALSE
809 | MRT-YD00-P2MKA-220001 | 2017-12-15 | MRT-DS-PLNE-TT-170136 | FI | 1 | TRUE | TRUE | FALSE
810 | MRT-YD00-P2MKA-220003 | 2017-12-15 | MRT-DS-PLNE-TT-170136 | FA | 1 | TRUE | TRUE | FALSE
811 | MRT-XB00-P3MKA-220001 | 2017-12-15 | MRT-DS-PLNE-TT-170136 | FA | 1 | TRUE | TRUE | FALSE
812 | MRT-UF00-P3MKA-220001 | 2017-12-15 | MRT-DS-PLNE-TT-170136 | FI | 1 | TRUE | TRUE | FALSE
813 | MRT-YD00-P3MKA-220001 | 2017-12-15 | MRT-DS-PLNE-TT-170136 | FI | 1 | TRUE | TRUE | FALSE
814 | MRT-YD00-P3MKA-220003 | 2017-12-15 | MRT-DS-PLNE-TT-170136 | FA | 1 | TRUE | TRUE | FALSE
815 | MRT-VK02-P2UHA-170106 | 2017-12-15 | MRT-DS-PLNE-TT-170137 | FA | 0 | TRUE | FALSE | FALSE
816 | MRT-VK02-P3UHA-170106 | 2017-12-15 | MRT-DS-PLNE-TT-170137 | FA | 0 | TRUE | FALSE | FALSE
817 | MRT-YL01-P2ZEN-161051 | 2017-12-15 | MRT-DS-PLNE-TT-170138 | FA | 0 | TRUE | FALSE | FALSE
818 | MRT-YL01-P3ZEN-161051 | 2017-12-15 | MRT-DS-PLNE-TT-170138 | FA | 0 | TRUE | FALSE | FALSE
819 | MRT-DP00-P2LB-122106 | 2017-12-15 | MRT-DS-PLNE-TT-170134 | FA | 0 | TRUE | FALSE | FALSE
820 | MRT-DP00-P3LB-122106 | 2017-12-15 | MRT-DS-PLNE-TT-170134 | FA | 0 | TRUE | FALSE | FALSE
825 | MRT-XA00-P3GC-135105 | 2017-12-15 | MRT-HK-PLNE-TT-170038 | FA | 2 | TRUE | TRUE | FALSE
821 | MRT-XS00-P2MAV-120053 | 2017-12-18 | MRT-DS-PLNE-TT-170130 | FA | 2 | TRUE | TRUE | FALSE
822 | MRT-XS00-P3MAV-120053 | 2017-12-18 | MRT-DS-PLNE-TT-170130 | FA | 2 | TRUE | TRUE | FALSE
823 | MRT-XG02-P2MAV-120054 | 2017-12-18 | MRT-DS-PLNE-TT-170130 | FA | 2 | TRUE | TRUE | FALSE
824 | MRT-XG02-P3MAV-120054 | 2017-12-18 | MRT-DS-PLNE-TT-170130 | FA | 2 | TRUE | TRUE | FALSE
826 | MRT-XG02-P2SCA-120004 | 2017-12-19 | MRT-DS-PLNE-TT-170139 | FC | 3 | TRUE | TRUE | FALSE
827 | MRT-XG02-P2SCA-120005 | 2017-12-19 | MRT-DS-PLNE-TT-170139 | FC | 3 | TRUE | TRUE | FALSE
828 | MRT-XG02-P2SCA-120006 | 2017-12-19 | MRT-DS-PLNE-TT-170139 | FC | 3 | TRUE | TRUE | FALSE
829 | MRT-XG02-P3SCA-120004 | 2017-12-19 | MRT-DS-PLNE-TT-170139 | FC | 3 | TRUE | TRUE | FALSE
830 | MRT-XG02-P3SCA-120005 | 2017-12-19 | MRT-DS-PLNE-TT-170139 | FC | 3 | TRUE | TRUE | FALSE
831 | MRT-XG02-P3SCA-120006 | 2017-12-19 | MRT-DS-PLNE-TT-170139 | FC | 3 | TRUE | TRUE | FALSE
832 | MRT-XK00-P2GM-128507 | 2017-12-19 | MRT-DS-PLNE-TT-170141 | FA | 0 | TRUE | FALSE | FALSE
833 | MRT-XK00-P3GM-128507 | 2017-12-19 | MRT-DS-PLNE-TT-170141 | FA | 0 | TRUE | FALSE | FALSE
834 | MRT-CC07-P0UPC-175012 | 2017-12-19 | MRT-HK-PLNE-TT-170039 | FA | 0 | TRUE | FALSE | FALSE
835 | MRT-CC02-P0ZEN-175011 | 2017-12-19 | MRT-HK-PLNE-TT-170039 | FA | 0 | TRUE | FALSE | FALSE
836 | MRT-CC07-P0UPC-175701 | 2017-12-19 | MRT-HK-PLNE-TT-170039 | FA | 2 | TRUE | TRUE | FALSE
837 | MRT-CC02-P0UPC-175705 | 2017-12-19 | MRT-HK-PLNE-TT-170039 | FA | 3 | TRUE | TRUE | FALSE
838 | MRT-VK02-P2UMA-170510 | 2017-12-19 | MRT-DS-PLNE-TT-170143 | FA | 0 | TRUE | FALSE | FALSE
839 | MRT-VK02-P3UMA-170510 | 2017-12-19 | MRT-DS-PLNE-TT-170143 | FA | 0 | TRUE | FALSE | FALSE
841 | MRT-CA06-P0UMA-180002 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
842 | MRT-CA03-P0UMA-180025 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
843 | MRT-CA03-P0UMA-180026 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
844 | MRT-CA01-P0UMA-180027 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
845 | MRT-CA03-P0UMA-180028 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
846 | MRT-CA03-P0UMA-180029 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
847 | MRT-CA03-P0UMA-180031 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
848 | MRT-CA03-P0UMA-180032 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
849 | MRT-CA03-P0UMA-180033 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
850 | MRT-CA03-P0UMA-180034 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
851 | MRT-CA03-P0UMA-180042 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
852 | MRT-CA03-P0UMA-180043 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
853 | MRT-CA03-P0UMA-180046 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
854 | MRT-CA03-P0UMA-180030 | 2017-12-21 | MRT-DS-PLNE-TT-170144 | FA | 1 | TRUE | TRUE | FALSE
855 | MRT-XG07-P2LBA-110300 | 2017-12-21 | MRT-DS-PLNE-TT-170148 | FA | 1 | TRUE | TRUE | FALSE
856 | MRT-XG07-P2PA-110304 | 2017-12-21 | MRT-DS-PLNE-TT-170148 | FA | 1 | TRUE | TRUE | FALSE
857 | MRT-XG07-P3LBA-110300 | 2017-12-21 | MRT-DS-PLNE-TT-170148 | FA | 1 | TRUE | TRUE | FALSE
858 | MRT-XG07-P3PA-110304 | 2017-12-21 | MRT-DS-PLNE-TT-170148 | FA | 1 | TRUE | TRUE | FALSE
859 | MRT-XG07-P2PA-110002 | 2017-12-21 | MRT-DS-PLNE-TT-170148 | FA | 1 | TRUE | TRUE | FALSE
860 | MRT-XG07-P3PA-110002 | 2017-12-21 | MRT-DS-PLNE-TT-170148 | FA | 1 | TRUE | TRUE | FALSE
861 | MRT-CV03-P2ZEN-165201 | 2017-12-21 | MRT-DS-PLNE-TT-170152 | FA | 0 | TRUE | FALSE | FALSE
862 | MRT-CV03-P3ZEN-165201 | 2017-12-21 | MRT-DS-PLNE-TT-170152 | FA | 0 | TRUE | FALSE | FALSE
863 | MRT-XH01-P0UZT-140001 | 2017-12-21 | MRT-DS-PLNE-TT-170150 | FA | 0 | TRUE | FALSE | FALSE
864 | MRT-XH01-P2ULY-142000 | 2017-12-21 | MRT-DS-PLNE-TT-170150 | FA | 0 | TRUE | FALSE | FALSE
865 | MRT-XH01-P3ULY-143000 | 2017-12-21 | MRT-DS-PLNE-TT-170150 | FA | 0 | TRUE | FALSE | FALSE
866 | MRT-XH01-P3ULY-144000 | 2017-12-21 | MRT-DS-PLNE-TT-170150 | FA | 0 | TRUE | FALSE | FALSE
867 | MRT-YL00-P2LB-122075 | 2017-12-21 | MRT-DS-PLNE-TT-170145 | FI | 0 | TRUE | FALSE | FALSE
868 | MRT-XL00-P2LB-122030 | 2017-12-21 | MRT-DS-PLNE-TT-170145 | FA | 0 | TRUE | FALSE | FALSE
869 | MRT-XN00-P2LB-122032 | 2017-12-21 | MRT-DS-PLNE-TT-170145 | FI | 0 | TRUE | FALSE | FALSE
870 | MRT-XS00-P2LB-122035 | 2017-12-21 | MRT-DS-PLNE-TT-170145 | FA | 0 | TRUE | FALSE | FALSE
871 | MRT-XL00-P0ZEN-140001 | 2017-12-21 | MRT-DS-PLNE-TT-170153 | FA | 1 | TRUE | TRUE | FALSE
872 | MRT-UC07-P0ZEN-100001 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 3 | TRUE | TRUE | FALSE
873 | MRT-UC08-P0ZEN-100002 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
874 | MRT-UC08-P0ZEN-100003 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
875 | MRT-UE00-P2ZEN-100004 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
876 | MRT-UE00-P2ZEN-100005 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
877 | MRT-UE00-P2ZEN-100006 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
878 | MRT-UE00-P2ZEN-100007 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
879 | MRT-UE00-P2ZEN-100008 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
880 | MRT-UE00-P2ZEN-100009 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
881 | MRT-UE00-P3ZEN-100010 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
882 | MRT-UE00-P3ZEN-100011 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
883 | MRT-UE00-P3ZEN-100012 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
884 | MRT-UE00-P3ZEN-100013 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FC | 2 | TRUE | TRUE | FALSE
885 | MRT-UE00-P3ZEN-100014 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
886 | MRT-UE00-P3ZEN-100015 | 2017-12-21 | MRT-DS-PLNE-TT-170149 | FA | 2 | TRUE | TRUE | FALSE
887 | MRT-XG02-P2LB-122022 | 2017-12-21 | MRT-DS-PLNE-TT-170155 | FA | 2 | TRUE | TRUE | FALSE
888 | MRT-XK00-P2GM-128508 | 2017-12-21 | MRT-DS-PLNE-TT-170154 | FA | 0 | TRUE | FALSE | FALSE
889 | MRT-XK00-P3GM-128508 | 2017-12-21 | MRT-DS-PLNE-TT-170154 | FA | 0 | TRUE | FALSE | FALSE
890 | MRT-CA01-P0UCA-180129 | 2017-12-22 | MRT-DS-PLNE-TT-170156 | FA | 0 | TRUE | FALSE | FALSE
891 | MRT-CA06-P0UCA-180101 | 2017-12-22 | MRT-DS-PLNE-TT-170157 | FC | 2 | TRUE | TRUE | FALSE
892 | MRT-XB02-P0UCA-180102 | 2017-12-22 | MRT-DS-PLNE-TT-170157 | FC | 2 | TRUE | TRUE | FALSE
893 | MRT-CA01-P0UCA-180103 | 2017-12-22 | MRT-DS-PLNE-TT-170157 | FC | 2 | TRUE | TRUE | FALSE
894 | MRT-CA02-P0UCA-180104 | 2017-12-22 | MRT-DS-PLNE-TT-170157 | FC | 2 | TRUE | TRUE | FALSE
895 | MRT-CA06-P0UMA-180001 | 2017-12-22 | MRT-DS-PLNE-TT-170158 | FC | 2 | TRUE | TRUE | FALSE
896 | MRT-CA06-P0UMA-180003 | 2017-12-22 | MRT-DS-PLNE-TT-170158 | FC | 2 | TRUE | TRUE | FALSE
897 | MRT-XB02-P0UMA-180004 | 2017-12-22 | MRT-DS-PLNE-TT-170158 | FC | 2 | TRUE | TRUE | FALSE
898 | MRT-CA01-P0UMA-180005 | 2017-12-22 | MRT-DS-PLNE-TT-170158 | FC | 2 | TRUE | TRUE | FALSE
899 | MRT-CA01-P0UMA-180006 | 2017-12-22 | MRT-DS-PLNE-TT-170158 | FC | 2 | TRUE | TRUE | FALSE
900 | MRT-CA01-P0UMA-180007 | 2017-12-22 | MRT-DS-PLNE-TT-170158 | FC | 2 | TRUE | TRUE | FALSE
901 | MRT-CA00-P0UMA-180008 | 2017-12-22 | MRT-DS-PLNE-TT-170158 | FC | 2 | TRUE | TRUE | FALSE
902 | MRT-CA00-P0UMA-180010 | 2017-12-22 | MRT-DS-PLNE-TT-170158 | FC | 2 | TRUE | TRUE | FALSE
903 | MRT-CA00-P0UMA-180011 | 2017-12-22 | MRT-DS-PLNE-TT-170158 | FC | 2 | TRUE | TRUE | FALSE
904 | MRT-CA00-P0UMA-180013 | 2017-12-22 | MRT-DS-PLNE-TT-170158 | FC | 2 | TRUE | TRUE | FALSE
905 | MRT-CA00-P0UMA-180014 | 2017-12-22 | MRT-DS-PLNE-TT-170158 | FC | 2 | TRUE | TRUE | FALSE
906 | MRT-YF01-P2ZEN-161013 | 2017-12-22 | MRT-DS-PLNE-TT-170160 | FA | 0 | TRUE | FALSE | FALSE
907 | MRT-YF01-P3ZEN-161013 | 2017-12-22 | MRT-DS-PLNE-TT-170160 | FA | 0 | TRUE | FALSE | FALSE
916 | MRT-QM03-P0ZEN-045002 | 2017-12-22 | MRT-HK-PLNE-TT-170040 | FA | 1 | TRUE | TRUE | FALSE
919 | MRT-QM00-P0H-040001 | 2017-12-22 | MRT-DS-PLNE-TT-170147 | FA | 0 | TRUE | TRUE | FALSE
920 | MRT-QM00-P0H-040002 | 2017-12-22 | MRT-DS-PLNE-TT-170147 | FA | 0 | TRUE | TRUE | FALSE
921 | MRT-QM01-P0ZEN-040002 | 2017-12-22 | MRT-DS-PLNE-TT-170142 | FA | 2 | TRUE | TRUE | FALSE
922 | MRT-QM01-P0ZEN-040003 | 2017-12-22 | MRT-DS-PLNE-TT-170142 | FA | 2 | TRUE | TRUE | FALSE
923 | MRT-QM01-P0ZEN-040001 | 2017-12-22 | MRT-DS-PLNE-TT-170133 | FA | 1 | TRUE | TRUE | FALSE
924 | MRT-QM01-P0ZEN-040001 | 2017-12-22 | MRT-DS-PLNE-TT-170133 | FA | 1 | TRUE | TRUE | FALSE
908 | MRT-YT01-P2MAJ-603103 | 2017-12-23 | MRT-DS-PLNE-TT-170159 | FI | 0 | TRUE | FALSE | FALSE
909 | MRT-YL00-P2MAJ-603105 | 2017-12-23 | MRT-DS-PLNE-TT-170159 | FA | 0 | TRUE | FALSE | FALSE
910 | MRT-XN00-P2MAJ-603106 | 2017-12-23 | MRT-DS-PLNE-TT-170159 | FA | 0 | TRUE | FALSE | FALSE
911 | MRT-YV02-P2MAJ-603108 | 2017-12-23 | MRT-DS-PLNE-TT-170159 | FI | 0 | TRUE | FALSE | FALSE
912 | MRT-YT01-P3MAJ-604103 | 2017-12-23 | MRT-DS-PLNE-TT-170159 | FI | 0 | TRUE | FALSE | FALSE
913 | MRT-YL00-P3MAJ-604105 | 2017-12-23 | MRT-DS-PLNE-TT-170159 | FA | 0 | TRUE | FALSE | FALSE
914 | MRT-XN00-P3MAJ-604106 | 2017-12-23 | MRT-DS-PLNE-TT-170159 | FA | 0 | TRUE | FALSE | FALSE
915 | MRT-YV02-P3MAJ-604108 | 2017-12-23 | MRT-DS-PLNE-TT-170159 | FI | 0 | TRUE | FALSE | FALSE
917 | MRT-XS00-P0GEN-135300 | 2017-12-29 | MRT-HK-PLNE-TT-170041 | FA | 1 | TRUE | TRUE | FALSE
918 | MRT-XW03-P0GEN-135301 | 2017-12-29 | MRT-HK-PLNE-TT-170041 | FA | 1 | TRUE | TRUE | FALSE
926 | MRT-BF05-P0ZEN-195001 | 2018-01-02 | MRT-HK-PLNE-TT-170042 | FA | 0 | TRUE | TRUE | FALSE
925 | MRT-BV02-P0ZEN-020005 | 2018-01-05 | MRT-DS-PLNE-TT-180002 | FI | 1 | TRUE | TRUE | FALSE
927 | MRT-CC07-P2UMA-170601 | 2018-01-05 | MRT-DS-PLNE-TT-170146 | FA | 0 | TRUE | TRUE | FALSE
928 | MRT-CC02-P2UMA-170603 | 2018-01-05 | MRT-DS-PLNE-TT-170146 | FA | 0 | TRUE | TRUE | FALSE
929 | MRT-CC02-P2UMA-170607 | 2018-01-05 | MRT-DS-PLNE-TT-170146 | FA | 0 | TRUE | TRUE | FALSE
930 | MRT-CC02-P2UMA-170608 | 2018-01-05 | MRT-DS-PLNE-TT-170146 | FA | 0 | TRUE | TRUE | FALSE
931 | MRT-CC02-P2UMA-170609 | 2018-01-05 | MRT-DS-PLNE-TT-170146 | FA | 0 | TRUE | TRUE | FALSE
932 | MRT-CC07-P3UMA-170601 | 2018-01-05 | MRT-DS-PLNE-TT-170146 | FA | 0 | TRUE | TRUE | FALSE
933 | MRT-CC02-P3UMA-170603 | 2018-01-05 | MRT-DS-PLNE-TT-170146 | FA | 0 | TRUE | TRUE | FALSE
934 | MRT-CC02-P3UMA-170607 | 2018-01-05 | MRT-DS-PLNE-TT-170146 | FA | 0 | TRUE | TRUE | FALSE
935 | MRT-CC02-P3UMA-170608 | 2018-01-05 | MRT-DS-PLNE-TT-170146 | FA | 0 | TRUE | TRUE | FALSE
936 | MRT-CC02-P3UMA-170609 | 2018-01-05 | MRT-DS-PLNE-TT-170146 | FA | 0 | TRUE | TRUE | FALSE
937 | MRT-CC07-P2UMA-170701 | 2018-01-05 | MRT-DS-PLNE-TT-170151 | FA | 0 | TRUE | TRUE | FALSE
938 | MRT-CC02-P2UMA-170703 | 2018-01-05 | MRT-DS-PLNE-TT-170151 | FA | 0 | TRUE | TRUE | FALSE
939 | MRT-CC02-P2UMA-170707 | 2018-01-05 | MRT-DS-PLNE-TT-170151 | FA | 0 | TRUE | TRUE | FALSE
940 | MRT-CC02-P2UMA-170708 | 2018-01-05 | MRT-DS-PLNE-TT-170151 | FA | 0 | TRUE | TRUE | FALSE
941 | MRT-CC02-P2UMA-170709 | 2018-01-05 | MRT-DS-PLNE-TT-170151 | FA | 0 | TRUE | TRUE | FALSE
942 | MRT-CC07-P3UMA-170701 | 2018-01-05 | MRT-DS-PLNE-TT-170151 | FA | 0 | TRUE | TRUE | FALSE
943 | MRT-CC02-P3UMA-170703 | 2018-01-05 | MRT-DS-PLNE-TT-170151 | FA | 0 | TRUE | TRUE | FALSE
944 | MRT-CC02-P3UMA-170707 | 2018-01-05 | MRT-DS-PLNE-TT-170151 | FA | 0 | TRUE | TRUE | FALSE
945 | MRT-CC02-P3UMA-170708 | 2018-01-05 | MRT-DS-PLNE-TT-170151 | FA | 0 | TRUE | TRUE | FALSE
946 | MRT-CC02-P3UMA-170709 | 2018-01-05 | MRT-DS-PLNE-TT-170151 | FA | 0 | TRUE | TRUE | FALSE
947 | MRT-XV00-P2MAA-220036 | 2018-01-05 | MRT-DS-PLNE-TT-180005 | FA | 0 | TRUE | TRUE | FALSE
948 | MRT-XV00-P2MAV-220037 | 2018-01-05 | MRT-DS-PLNE-TT-180005 | FA | 0 | TRUE | TRUE | FALSE
949 | MRT-XV00-P3MAA-220036 | 2018-01-05 | MRT-DS-PLNE-TT-180005 | FA | 0 | TRUE | TRUE | FALSE
950 | MRT-XV00-P3MAV-220037 | 2018-01-05 | MRT-DS-PLNE-TT-180005 | FA | 0 | TRUE | TRUE | FALSE
951 | MRT-XW03-P0MJ-110511 | 2018-01-05 | MRT-DS-PLNE-TT-180006 | FA | 2 | TRUE | TRUE | FALSE
952 | MRT-CC07-P2UMA-170201 | 2018-01-08 | MRT-DS-PLNE-TT-170110 | FC | 1 | TRUE | TRUE | FALSE
953 | MRT-CC02-P2UMA-170203 | 2018-01-08 | MRT-DS-PLNE-TT-170110 | FC | 1 | TRUE | TRUE | FALSE
954 | MRT-CC02-P2UMA-170204 | 2018-01-08 | MRT-DS-PLNE-TT-170110 | FC | 1 | TRUE | TRUE | FALSE
955 | MRT-CC07-P3UMA-170201 | 2018-01-08 | MRT-DS-PLNE-TT-170110 | FC | 1 | TRUE | TRUE | FALSE
956 | MRT-CC02-P3UMA-170203 | 2018-01-08 | MRT-DS-PLNE-TT-170110 | FC | 1 | TRUE | TRUE | FALSE
957 | MRT-CC02-P3UMA-170204 | 2018-01-08 | MRT-DS-PLNE-TT-170110 | FC | 1 | TRUE | TRUE | FALSE
958 | MRT-DP00-P2LB-122106 | 2018-01-08 | MRT-DS-PLNE-TT-180004 | FA | 1 | TRUE | TRUE | FALSE
959 | MRT-DP00-P3LB-122106 | 2018-01-08 | MRT-DS-PLNE-TT-180004 | FA | 1 | TRUE | TRUE | FALSE
960 | MRT-YS00-P0ZEN-162101 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
961 | MRT-YS00-P0ZEN-162102 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
962 | MRT-YS00-P0ZEN-162103 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
963 | MRT-YS00-P0ZEN-162104 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
964 | MRT-YS00-P0ZEN-162105 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
965 | MRT-YS00-P0ZEN-162106 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
966 | MRT-YS00-P0ZEN-162107 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
967 | MRT-YS00-P0ZEN-162108 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
968 | MRT-YS00-P0ZEN-162109 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
969 | MRT-YS00-P0ZEN-162110 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
970 | MRT-YS00-P0ZEN-162111 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
971 | MRT-YS00-P0ZEN-162112 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
972 | MRT-YS00-P0ZEN-162113 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
973 | MRT-YS00-P0ZEN-162114 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
974 | MRT-YS00-P0ZEN-162115 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
975 | MRT-YS00-P0ZEN-162116 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
976 | MRT-YS00-P0ZEN-162117 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
977 | MRT-YS00-P0ZEN-162118 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
978 | MRT-YS00-P0ZEN-162119 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
979 | MRT-YS00-P0ZEN-162120 | 2018-01-08 | MRT-DS-PLNE-TT-180011 | FA | 1 | TRUE | TRUE | FALSE
980 | MRT-XB02-P2LB-122018 | 2018-01-08 | MRT-DS-PLNE-TT-180003 | FA | 1 | TRUE | TRUE | FALSE
981 | MRT-XB02-P3LB-122018 | 2018-01-08 | MRT-DS-PLNE-TT-180003 | FA | 0 | TRUE | TRUE | FALSE
982 | MRT-UE00-P2LB-122010 | 2018-01-08 | MRT-DS-PLNE-TT-180008 | FI | 0 | TRUE | TRUE | FALSE
983 | MRT-UE00-P3LB-122010 | 2018-01-08 | MRT-DS-PLNE-TT-180008 | FI | 0 | TRUE | TRUE | FALSE
984 | MRT-XW03-P3GHD-120001 | 2018-01-08 | MRT-DS-PLNE-TT-180012 | FA | 1 | TRUE | TRUE | FALSE
985 | MRT-CA00-P0UCA-180105 | 2018-01-08 | MRT-DS-PLNE-TT-180009 | FC | 2 | TRUE | TRUE | FALSE
986 | MRT-CA00-P0UCA-180107 | 2018-01-08 | MRT-DS-PLNE-TT-180009 | FC | 2 | TRUE | TRUE | FALSE
987 | MRT-CA00-P0UCA-180108 | 2018-01-08 | MRT-DS-PLNE-TT-180009 | FC | 2 | TRUE | TRUE | FALSE
988 | MRT-CA00-P0UCA-180112 | 2018-01-08 | MRT-DS-PLNE-TT-180009 | FC | 2 | TRUE | TRUE | FALSE
989 | MRT-CA00-P0UCA-180113 | 2018-01-08 | MRT-DS-PLNE-TT-180009 | FC | 2 | TRUE | TRUE | FALSE
990 | MRT-CA01-P0UCA-180122 | 2018-01-08 | MRT-DS-PLNE-TT-180010 | FA | 1 | TRUE | TRUE | FALSE
991 | MRT-CA01-P0UCA-180123 | 2018-01-08 | MRT-DS-PLNE-TT-180010 | FA | 1 | TRUE | TRUE | FALSE
992 | MRT-CA01-P0UCA-180127 | 2018-01-08 | MRT-DS-PLNE-TT-180010 | FA | 1 | TRUE | TRUE | FALSE
993 | MRT-CA01-P0UCA-180128 | 2018-01-08 | MRT-DS-PLNE-TT-180010 | FA | 1 | TRUE | TRUE | FALSE
994 | MRT-CA02-P0UCA-180134 | 2018-01-08 | MRT-DS-PLNE-TT-180010 | FA | 1 | TRUE | TRUE | FALSE
995 | MRT-CA02-P0UCA-180135 | 2018-01-08 | MRT-DS-PLNE-TT-180010 | FA | 1 | TRUE | TRUE | FALSE
996 | MRT-CA02-P0UCA-180136 | 2018-01-08 | MRT-DS-PLNE-TT-180010 | FA | 1 | TRUE | TRUE | FALSE
997 | MRT-CC07-P2UMA-170801 | 2018-01-08 | MRT-DS-PLNE-TT-180014 | FA | 0 | TRUE | TRUE | FALSE
998 | MRT-CC02-P2UMA-170803 | 2018-01-08 | MRT-DS-PLNE-TT-180014 | FA | 0 | TRUE | TRUE | FALSE
999 | MRT-VK02-P2UMA-170806 | 2018-01-08 | MRT-DS-PLNE-TT-180014 | FA | 0 | TRUE | TRUE | FALSE
1000 | MRT-CC07-P3UMA-170801 | 2018-01-08 | MRT-DS-PLNE-TT-180014 | FA | 0 | TRUE | TRUE | FALSE
1001 | MRT-CC02-P3UMA-170803 | 2018-01-08 | MRT-DS-PLNE-TT-180014 | FA | 0 | TRUE | TRUE | FALSE
1002 | MRT-VK02-P3UMA-170806 | 2018-01-08 | MRT-DS-PLNE-TT-180014 | FA | 0 | TRUE | TRUE | FALSE
1003 | MRT-XB00-P2MKA-220001 | 2018-01-09 | MRT-DS-PLNE-TT-180013 | FA | 2 | TRUE | TRUE | FALSE
1004 | MRT-XB00-P3MKA-220001 | 2018-01-09 | MRT-DS-PLNE-TT-180013 | FA | 2 | TRUE | TRUE | FALSE
1005 | MRT-YD00-P0SMM-128001 | 2018-01-11 | MRT-DS-PLNE-TT-180017 | FA | 0 | TRUE | TRUE | FALSE
1006 | MRT-YT01-P0SMM-128004 | 2018-01-11 | MRT-DS-PLNE-TT-180018 | FA | 0 | TRUE | TRUE | FALSE
1040 | MRT-QM00-P0H-040003 | 2018-01-11 | MRT-DS-PLNE-TT-180019 | FA | 0 | TRUE | TRUE | FALSE
1041 | MRT-QM00-P0H-040004 | 2018-01-11 | MRT-DS-PLNE-TT-180019 | FA | 0 | TRUE | TRUE | FALSE
1007 | MRT-CA00-P0UMA-180009 | 2018-01-12 | MRT-DS-PLNE-TT-180022 | FA | 1 | TRUE | TRUE | FALSE
1008 | MRT-CA00-P0UMA-180015 | 2018-01-12 | MRT-DS-PLNE-TT-180022 | FA | 1 | TRUE | TRUE | FALSE
1009 | MRT-CA00-P0UMA-180016 | 2018-01-12 | MRT-DS-PLNE-TT-180022 | FA | 1 | TRUE | TRUE | FALSE
1010 | MRT-CA00-P0UMA-180017 | 2018-01-12 | MRT-DS-PLNE-TT-180022 | FA | 1 | TRUE | TRUE | FALSE
1011 | MRT-CA00-P0UMA-180019 | 2018-01-12 | MRT-DS-PLNE-TT-180022 | FA | 1 | TRUE | TRUE | FALSE
1012 | MRT-CA00-P0UMA-180021 | 2018-01-12 | MRT-DS-PLNE-TT-180022 | FA | 1 | TRUE | TRUE | FALSE
1013 | MRT-CA00-P0UMA-180022 | 2018-01-12 | MRT-DS-PLNE-TT-180022 | FA | 1 | TRUE | TRUE | FALSE
1014 | MRT-XA00-P2MAA-220013 | 2018-01-12 | MRT-DS-PLNE-TT-180015 | FA | 1 | TRUE | TRUE | FALSE
1015 | MRT-XA00-P2MAA-220014 | 2018-01-12 | MRT-DS-PLNE-TT-180015 | FA | 1 | TRUE | TRUE | FALSE
1016 | MRT-XA00-P2MAA-220015 | 2018-01-12 | MRT-DS-PLNE-TT-180015 | FA | 1 | TRUE | TRUE | FALSE
1017 | MRT-XA00-P2MAA-220016 | 2018-01-12 | MRT-DS-PLNE-TT-180015 | FA | 1 | TRUE | TRUE | FALSE
1018 | MRT-XA00-P2MAA-220017 | 2018-01-12 | MRT-DS-PLNE-TT-180015 | FA | 1 | TRUE | TRUE | FALSE
1019 | MRT-XA00-P2MAA-220018 | 2018-01-12 | MRT-DS-PLNE-TT-180015 | FA | 1 | TRUE | TRUE | FALSE
1020 | MRT-XA00-P2MAA-220020 | 2018-01-12 | MRT-DS-PLNE-TT-180015 | FA | 1 | TRUE | TRUE | FALSE
1021 | MRT-XA00-P2MAA-220021 | 2018-01-12 | MRT-DS-PLNE-TT-180015 | FA | 1 | TRUE | TRUE | FALSE
1022 | MRT-XA00-P2MAA-220022 | 2018-01-12 | MRT-DS-PLNE-TT-180015 | FA | 1 | TRUE | TRUE | FALSE
1023 | MRT-XA00-P3MAA-220016 | 2018-01-12 | MRT-DS-PLNE-TT-180016 | FA | 1 | TRUE | TRUE | FALSE
1024 | MRT-XA00-P3MAA-220013 | 2018-01-12 | MRT-DS-PLNE-TT-180016 | FA | 1 | TRUE | TRUE | FALSE
1025 | MRT-XA00-P3MAA-220014 | 2018-01-12 | MRT-DS-PLNE-TT-180016 | FA | 1 | TRUE | TRUE | FALSE
1026 | MRT-XA00-P3MAA-220015 | 2018-01-12 | MRT-DS-PLNE-TT-180016 | FA | 1 | TRUE | TRUE | FALSE
1027 | MRT-XA00-P3MAA-220017 | 2018-01-12 | MRT-DS-PLNE-TT-180016 | FA | 1 | TRUE | TRUE | FALSE
1028 | MRT-XA00-P3MAA-220018 | 2018-01-12 | MRT-DS-PLNE-TT-180016 | FA | 1 | TRUE | TRUE | FALSE
1029 | MRT-XA00-P3MAA-220019 | 2018-01-12 | MRT-DS-PLNE-TT-180016 | FA | 1 | TRUE | TRUE | FALSE
1030 | MRT-XA00-P3MAA-220020 | 2018-01-12 | MRT-DS-PLNE-TT-180016 | FA | 1 | TRUE | TRUE | FALSE
1031 | MRT-XA00-P3MAA-220021 | 2018-01-12 | MRT-DS-PLNE-TT-180016 | FA | 1 | TRUE | TRUE | FALSE
1032 | MRT-XA00-P3MAA-220022 | 2018-01-12 | MRT-DS-PLNE-TT-180016 | FA | 1 | TRUE | TRUE | FALSE
1033 | MRT-VK02-P2UMA-170210 | 2018-01-12 | MRT-DS-PLNE-TT-180023 | FA | 0 | TRUE | TRUE | FALSE
1034 | MRT-XW01-P0ZEN-161001 | 2018-01-12 | MRT-DS-PLNE-TT-180020 | FA | 2 | TRUE | TRUE | FALSE
1083 | MRT-QM03-P0ZEN-045002 | 2018-01-15 | MRT-HK-PLNE-TT-170044 | FA | 2 | TRUE | TRUE | FALSE
1035 | MRT-CA03-P0UMA-180035 | 2018-01-16 | MRT-DS-PLNE-TT-180024 | FA | 1 | TRUE | TRUE | FALSE
1036 | MRT-CA03-P0UMA-180036 | 2018-01-16 | MRT-DS-PLNE-TT-180024 | FA | 1 | TRUE | TRUE | FALSE
1037 | MRT-CA03-P0UMA-180037 | 2018-01-16 | MRT-DS-PLNE-TT-180024 | FA | 1 | TRUE | TRUE | FALSE
1038 | MRT-CA03-P0UMA-180039 | 2018-01-16 | MRT-DS-PLNE-TT-180024 | FA | 1 | TRUE | TRUE | FALSE
1039 | MRT-CA03-P0UMA-180040 | 2018-01-16 | MRT-DS-PLNE-TT-180024 | FA | 1 | TRUE | TRUE | FALSE
1042 | MRT-YB03-P3LB-122048 | 2018-01-16 | MRT-DS-PLNE-TT-180025 | FI | 0 | TRUE | TRUE | FALSE
1043 | MRT-YB03-P2LB-122048 | 2018-01-16 | MRT-DS-PLNE-TT-180025 | FC | 1 | TRUE | TRUE | FALSE
1044 | MRT-CA05-P0UCA-180161 | 2018-01-17 | MRT-DS-PLNE-TT-180026 | FA | 1 | TRUE | TRUE | FALSE
1045 | MRT-CA05-P0UCA-180162 | 2018-01-17 | MRT-DS-PLNE-TT-180026 | FA | 1 | TRUE | TRUE | FALSE
1046 | MRT-CA05-P0UCA-180163 | 2018-01-17 | MRT-DS-PLNE-TT-180026 | FA | 1 | TRUE | TRUE | FALSE
1047 | MRT-CA05-P0UCA-180164 | 2018-01-17 | MRT-DS-PLNE-TT-180026 | FA | 1 | TRUE | TRUE | FALSE
1048 | MRT-XG02-P2MAA-220005 | 2018-01-17 | MRT-DS-PLNE-TT-170112 | FA | 0 | TRUE | TRUE | FALSE
1049 | MRT-XG02-P3MAA-220005 | 2018-01-17 | MRT-DS-PLNE-TT-170112 | FA | 0 | TRUE | TRUE | FALSE
1050 | MRT-XG02-P2MAV-220006 | 2018-01-17 | MRT-DS-PLNE-TT-170112 | FA | 0 | TRUE | TRUE | FALSE
1051 | MRT-XG02-P3MAV-220006 | 2018-01-17 | MRT-DS-PLNE-TT-170112 | FA | 0 | TRUE | TRUE | FALSE
1052 | MRT-XG02-P2MAX-220007 | 2018-01-17 | MRT-DS-PLNE-TT-170112 | FA | 0 | TRUE | TRUE | FALSE
1053 | MRT-XG02-P3MAX-220007 | 2018-01-17 | MRT-DS-PLNE-TT-170112 | FA | 0 | TRUE | TRUE | FALSE
1054 | MRT-YU04-P0ZEN-161012 | 2018-01-17 | MRT-DS-PLNE-TT-180021 | FA | 1 | TRUE | TRUE | FALSE
1055 | MRT-XM00-P2MAA-220012 | 2018-01-17 | MRT-DS-PLNE-TT-180027 | FI | 0 | TRUE | TRUE | FALSE
1056 | MRT-XM00-P3MAA-220012 | 2018-01-17 | MRT-DS-PLNE-TT-180027 | FI | 0 | TRUE | TRUE | FALSE
1057 | MRT-XG02-P2SCA-120004 | 2018-01-18 | MRT-DS-PLNE-TT-180007 | FC | 4 | TRUE | TRUE | FALSE
1058 | MRT-XG02-P2SCA-120005 | 2018-01-18 | MRT-DS-PLNE-TT-180007 | FC | 4 | TRUE | TRUE | FALSE
1059 | MRT-XG02-P2SCA-120006 | 2018-01-18 | MRT-DS-PLNE-TT-180007 | FC | 4 | TRUE | TRUE | FALSE
1060 | MRT-XG02-P3SCA-120004 | 2018-01-18 | MRT-DS-PLNE-TT-180007 | FC | 4 | TRUE | TRUE | FALSE
1061 | MRT-XG02-P3SCA-120005 | 2018-01-18 | MRT-DS-PLNE-TT-180007 | FC | 4 | TRUE | TRUE | FALSE
1062 | MRT-XG02-P3SCA-120006 | 2018-01-18 | MRT-DS-PLNE-TT-180007 | FC | 4 | TRUE | TRUE | FALSE
1063 | MRT-CA00-P0UCA-180106 | 2018-01-19 | MRT-DS-PLNE-TT-180030 | FA | 1 | TRUE | TRUE | FALSE
1064 | MRT-CA00-P0UCA-180114 | 2018-01-19 | MRT-DS-PLNE-TT-180030 | FA | 1 | TRUE | TRUE | FALSE
1065 | MRT-CA00-P0UCA-180115 | 2018-01-19 | MRT-DS-PLNE-TT-180030 | FA | 1 | TRUE | TRUE | FALSE
1066 | MRT-CA00-P0UCA-180116 | 2018-01-19 | MRT-DS-PLNE-TT-180030 | FA | 1 | TRUE | TRUE | FALSE
1067 | MRT-CA00-P0UCA-180117 | 2018-01-19 | MRT-DS-PLNE-TT-180030 | FA | 1 | TRUE | TRUE | FALSE
1068 | MRT-XB02-P3LB-122016 | 2018-01-19 | MRT-DS-PLNE-TT-180028 | FA | 0 | TRUE | TRUE | FALSE
1069 | MRT-XB02-P2LB-122016 | 2018-01-19 | MRT-DS-PLNE-TT-180028 | FA | 1 | TRUE | TRUE | FALSE
1070 | MRT-XS00-P2LB-122035 | 2018-01-19 | MRT-DS-PLNE-TT-180029 | FC | 1 | TRUE | TRUE | FALSE
1071 | MRT-XS00-P3LB-122035 | 2018-01-19 | MRT-DS-PLNE-TT-180029 | FA | 0 | TRUE | TRUE | FALSE
1072 | MRT-XS00-P2MAV-120053 | 2018-01-19 | MRT-DS-PLNE-TT-180032 | FC | 3 | TRUE | TRUE | FALSE
1073 | MRT-XS00-P3MAV-120053 | 2018-01-19 | MRT-DS-PLNE-TT-180032 | FC | 3 | TRUE | TRUE | FALSE
1074 | MRT-XG02-P2MAV-120054 | 2018-01-19 | MRT-DS-PLNE-TT-180032 | FC | 3 | TRUE | TRUE | FALSE
1075 | MRT-XG02-P3MAV-120054 | 2018-01-19 | MRT-DS-PLNE-TT-180032 | FC | 3 | TRUE | TRUE | FALSE
1076 | MRT-YK08-P2MAJ-603308 | 2018-01-19 | MRT-DS-PLNE-TT-180031 | FA | 0 | TRUE | TRUE | FALSE
1077 | MRT-YK08-P3MAJ-604308 | 2018-01-19 | MRT-DS-PLNE-TT-180031 | FA | 0 | TRUE | TRUE | FALSE
1078 | MRT-YT01-P2MAJ-603110 | 2018-01-19 | MRT-DS-PLNE-TT-180031 | FI | 0 | TRUE | TRUE | FALSE
1079 | MRT-YT01-P3MAJ-604110 | 2018-01-19 | MRT-DS-PLNE-TT-180031 | FI | 0 | TRUE | TRUE | FALSE
1080 | MRT-YF01-P2ZEN-161013 | 2018-01-22 | MRT-DS-PLNE-TT-180033 | FA | 1 | TRUE | TRUE | FALSE
1081 | MRT-YF01-P3ZEN-161013 | 2018-01-22 | MRT-DS-PLNE-TT-180033 | FA | 1 | TRUE | TRUE | FALSE
1082 | MRT-XN00-P0ZEN-140001 | 2018-01-22 | MRT-DS-PLNE-TT-180034 | FA | 1 | TRUE | TRUE | FALSE
1084 | MRT-QM03-P0ZEN-045003 | 2018-01-22 | MRT-HK-PLNE-TT-170045 | FA | 0 | TRUE | TRUE | FALSE
1085 | MRT-XG02-P0GEN-135302 | 2018-01-22 | MRT-HK-PLNE-TT-170045 | FA | 2 | TRUE | TRUE | FALSE
1086 | MRT-XW03-P0MJ-110511 | 2018-01-23 | MRT-DS-PLNE-TT-180036 | FC | 3 | TRUE | TRUE | FALSE
1087 | MRT-CA06-P0UMA-180002 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FA | 2 | TRUE | TRUE | FALSE
1088 | MRT-CA03-P0UMA-180025 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1089 | MRT-CA03-P0UMA-180026 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1090 | MRT-CA01-P0UMA-180027 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1091 | MRT-CA03-P0UMA-180028 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1092 | MRT-CA03-P0UMA-180029 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1093 | MRT-CA03-P0UMA-180031 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1094 | MRT-CA03-P0UMA-180032 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1095 | MRT-CA03-P0UMA-180033 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1096 | MRT-CA03-P0UMA-180034 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1097 | MRT-CA03-P0UMA-180042 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1098 | MRT-CA03-P0UMA-180043 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1099 | MRT-CA03-P0UMA-180046 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1100 | MRT-CA03-P0UMA-180030 | 2018-01-23 | MRT-DS-PLNE-TT-180035 | FC | 2 | TRUE | TRUE | FALSE
1109 | MRT-YS05-P0ZEN-165014 | 2018-01-23 | MRT-HK-PLNE-TT-180046 | FI | 0 | TRUE | TRUE | FALSE
1101 | MRT-YT01-P2MAG-601007 | 2018-01-24 | MRT-DS-PLNE-TT-180039 | FA | 1 | TRUE | TRUE | FALSE
1102 | MRT-YT01-P2MAG-601008 | 2018-01-24 | MRT-DS-PLNE-TT-180039 | FI | 1 | TRUE | TRUE | FALSE
1103 | MRT-YT01-P2MAG-601009 | 2018-01-24 | MRT-DS-PLNE-TT-180039 | FI | 1 | TRUE | TRUE | FALSE
1104 | MRT-YT01-P3MAG-602007 | 2018-01-24 | MRT-DS-PLNE-TT-180039 | FA | 1 | TRUE | TRUE | FALSE
1105 | MRT-YT01-P3MAG-602008 | 2018-01-24 | MRT-DS-PLNE-TT-180039 | FI | 1 | TRUE | TRUE | FALSE
1106 | MRT-YT01-P3MAG-602009 | 2018-01-24 | MRT-DS-PLNE-TT-180039 | FI | 1 | TRUE | TRUE | FALSE
1107 | MRT-CA03-P0UCA-180132 | 2018-01-24 | MRT-DS-PLNE-TT-180040 | FA | 0 | TRUE | TRUE | FALSE
1108 | MRT-CA01-P0UCA-180133 | 2018-01-24 | MRT-DS-PLNE-TT-180040 | FA | 0 | TRUE | TRUE | FALSE
1110 | MRT-XB02-P3LB-122017 | 2018-01-24 | MRT-DS-PLNE-TT-180041 | FA | 0 | TRUE | TRUE | FALSE
1111 | MRT-XB02-P2LB-122017 | 2018-01-24 | MRT-DS-PLNE-TT-180041 | FA | 1 | TRUE | TRUE | FALSE
1112 | MRT-XJ00-P2PAB-140001 | 2018-01-25 | MRT-DS-PLNE-TT-180042 | FI | 0 | TRUE | TRUE | FALSE
1113 | MRT-XJ00-P3PAB-140001 | 2018-01-25 | MRT-DS-PLNE-TT-180042 | FI | 0 | TRUE | TRUE | FALSE
1114 | MRT-XL00-P0ZEN-140002 | 2018-01-25 | MRT-DS-PLNE-TT-180043 | FA | 1 | TRUE | TRUE | FALSE
1121 | MRT-QM01-P0ZEN-040002 | 2018-01-25 | MRT-DS-PLNE-TT-180037 | FA | 3 | TRUE | TRUE | FALSE
1122 | MRT-QM01-P0ZEN-040003 | 2018-01-25 | MRT-DS-PLNE-TT-180037 | FC | 3 | TRUE | TRUE | FALSE
1123 | MRT-QM00-P0H-040001 | 2018-01-25 | MRT-DS-PLNE-TT-180038 | FC | 1 | TRUE | TRUE | FALSE
1124 | MRT-QM00-P0H-040002 | 2018-01-25 | MRT-DS-PLNE-TT-180038 | FC | 1 | TRUE | TRUE | FALSE
1115 | MRT-XG07-P2LBA-110300 | 2018-01-26 | MRT-DS-PLNE-TT-180049 | FC | 2 | TRUE | TRUE | FALSE
1116 | MRT-XG07-P2PA-110304 | 2018-01-26 | MRT-DS-PLNE-TT-180049 | FC | 2 | TRUE | TRUE | FALSE
1117 | MRT-XG07-P3LBA-110300 | 2018-01-26 | MRT-DS-PLNE-TT-180049 | FC | 2 | TRUE | TRUE | FALSE
1118 | MRT-XG07-P3PA-110304 | 2018-01-26 | MRT-DS-PLNE-TT-180049 | FC | 2 | TRUE | TRUE | FALSE
1119 | MRT-XG07-P2PA-110002 | 2018-01-26 | MRT-DS-PLNE-TT-180049 | FC | 2 | TRUE | TRUE | FALSE
1120 | MRT-XG07-P3PA-110002 | 2018-01-26 | MRT-DS-PLNE-TT-180049 | FC | 2 | TRUE | TRUE | FALSE
1125 | MRT-CC07-P2UHA-170005 | 2018-01-26 | MRT-DS-PLNE-TT-180045 | FA | 1 | TRUE | TRUE | FALSE
1126 | MRT-CC02-P2UHA-170007 | 2018-01-26 | MRT-DS-PLNE-TT-180045 | FA | 1 | TRUE | TRUE | FALSE
1127 | MRT-CC02-P2UHA-170008 | 2018-01-26 | MRT-DS-PLNE-TT-180045 | FA | 1 | TRUE | TRUE | FALSE
1128 | MRT-CC02-P2UHA-170009 | 2018-01-26 | MRT-DS-PLNE-TT-180045 | FA | 1 | TRUE | TRUE | FALSE
1129 | MRT-CC07-P3UHA-170005 | 2018-01-26 | MRT-DS-PLNE-TT-180045 | FA | 1 | TRUE | TRUE | FALSE
1130 | MRT-CC02-P3UHA-170007 | 2018-01-26 | MRT-DS-PLNE-TT-180045 | FA | 1 | TRUE | TRUE | FALSE
1131 | MRT-CC02-P3UHA-170008 | 2018-01-26 | MRT-DS-PLNE-TT-180045 | FA | 1 | TRUE | TRUE | FALSE
1132 | MRT-CC02-P3UHA-170009 | 2018-01-26 | MRT-DS-PLNE-TT-180045 | FA | 1 | TRUE | TRUE | FALSE
1133 | MRT-CC02-P2UHA-170003 | 2018-01-26 | MRT-DS-PLNE-TT-180046 | FC | 3 | TRUE | TRUE | FALSE
1134 | MRT-CC02-P2UHA-170004 | 2018-01-26 | MRT-DS-PLNE-TT-180046 | FC | 3 | TRUE | TRUE | FALSE
1135 | MRT-CC02-P3UHA-170003 | 2018-01-26 | MRT-DS-PLNE-TT-180046 | FC | 3 | TRUE | TRUE | FALSE
1136 | MRT-CC02-P3UHA-170004 | 2018-01-26 | MRT-DS-PLNE-TT-180046 | FC | 3 | TRUE | TRUE | FALSE
1137 | MRT-CC02-P0UHA-170002 | 2018-01-26 | MRT-DS-PLNE-TT-180046 | FC | 3 | TRUE | TRUE | FALSE
1138 | MRT-VK02-P2UHA-170010 | 2018-01-26 | MRT-DS-PLNE-TT-180047 | FA | 1 | TRUE | TRUE | FALSE
1139 | MRT-VK02-P3UHA-170010 | 2018-01-26 | MRT-DS-PLNE-TT-180047 | FA | 1 | TRUE | TRUE | FALSE
1140 | MRT-YF00-P2PAH-604121 | 2018-01-26 | MRT-DS-PLNE-TT-180050 | FI | 0 | TRUE | TRUE | FALSE
1141 | MRT-YV02-P2PAH-604122 | 2018-01-26 | MRT-DS-PLNE-TT-180050 | FI | 0 | TRUE | TRUE | FALSE
1142 | MRT-YB03-P2PAH-604123 | 2018-01-26 | MRT-DS-PLNE-TT-180050 | FA | 0 | TRUE | TRUE | FALSE
1143 | MRT-YK08-P2PAH-604124 | 2018-01-26 | MRT-DS-PLNE-TT-180050 | FA | 0 | TRUE | TRUE | FALSE
1144 | MRT-YF00-P3PAH-604521 | 2018-01-26 | MRT-DS-PLNE-TT-180051 | FI | 0 | TRUE | TRUE | FALSE
1145 | MRT-YV02-P3PAH-604522 | 2018-01-26 | MRT-DS-PLNE-TT-180051 | FI | 0 | TRUE | TRUE | FALSE
1146 | MRT-YB03-P3PAH-604523 | 2018-01-26 | MRT-DS-PLNE-TT-180051 | FA | 0 | TRUE | TRUE | FALSE
1147 | MRT-YK08-P3PAH-604524 | 2018-01-26 | MRT-DS-PLNE-TT-180051 | FA | 0 | TRUE | TRUE | FALSE
1148 | MRT-CA07-P0ZEN-175016 | 2018-01-26 | MRT-HK-PLNE-TT-180047 | FA | 0 | TRUE | TRUE | FALSE
1149 | MRT-CA07-P0ZEN-175018 | 2018-01-26 | MRT-HK-PLNE-TT-180047 | FA | 0 | TRUE | TRUE | FALSE
1150 | MRT-XW03-P0ANA-150015 | 2018-01-26 | MRT-HK-PLNE-TT-180047 | FA | 0 | TRUE | TRUE | FALSE
1151 | MRT-YQ01-P0BHT-150177 | 2018-01-26 | MRT-HK-PLNE-TT-180047 | FA | 0 | TRUE | TRUE | FALSE
1152 | MRT-XG02-P3GC-135102 | 2018-01-26 | MRT-HK-PLNE-TT-180047 | FA | 2 | TRUE | TRUE | FALSE
1153 | MRT-XG02-P0GA-125201 | 2018-01-26 | MRT-HK-PLNE-TT-180047 | FA | 2 | TRUE | TRUE | FALSE
1154 | MRT-YT01-P2LAA-605101 | 2018-01-29 | MRT-DS-PLNE-TT-180052 | FA | 2 | TRUE | TRUE | FALSE
1155 | MRT-YT01-P3LAA-605501 | 2018-01-29 | MRT-DS-PLNE-TT-180052 | FA | 2 | TRUE | TRUE | FALSE
1156 | MRT-YK08-P2LAA-605100 | 2018-01-29 | MRT-DS-PLNE-TT-180053 | FA | 2 | TRUE | TRUE | FALSE
1157 | MRT-YK08-P3LAA-605500 | 2018-01-29 | MRT-DS-PLNE-TT-180053 | FA | 2 | TRUE | TRUE | FALSE
1158 | MRT-CC07-P2UHA-170101 | 2018-01-29 | MRT-DS-PLNE-TT-180048 | FC | 1 | TRUE | TRUE | FALSE
1159 | MRT-CC02-P2UHA-170103 | 2018-01-29 | MRT-DS-PLNE-TT-180048 | FC | 1 | TRUE | TRUE | FALSE
1160 | MRT-CC02-P2UHA-170104 | 2018-01-29 | MRT-DS-PLNE-TT-180048 | FC | 1 | TRUE | TRUE | FALSE
1161 | MRT-CC07-P3UHA-170101 | 2018-01-29 | MRT-DS-PLNE-TT-180048 | FC | 1 | TRUE | TRUE | FALSE
1162 | MRT-CC02-P3UHA-170103 | 2018-01-29 | MRT-DS-PLNE-TT-180048 | FC | 1 | TRUE | TRUE | FALSE
1163 | MRT-CC02-P3UHA-170104 | 2018-01-29 | MRT-DS-PLNE-TT-180048 | FC | 1 | TRUE | TRUE | FALSE
1164 | MRT-VK02-P2UHA-170106 | 2018-01-29 | MRT-DS-PLNE-TT-180054 | FC | 1 | TRUE | TRUE | FALSE
1165 | MRT-VK02-P3UHA-170106 | 2018-01-29 | MRT-DS-PLNE-TT-180054 | FC | 1 | TRUE | TRUE | FALSE
1166 | MRT-VK02-P3UMA-170210 | 2018-01-29 | MRT-DS-PLNE-TT-180055 | FA | 0 | TRUE | TRUE | FALSE
1167 | MRT-CA01-P0UMA-180044 | 2018-01-30 | MRT-DS-PLNE-TT-180056 | FA | 0 | TRUE | TRUE | FALSE
1168 | MRT-CA02-P0UMA-180045 | 2018-01-30 | MRT-DS-PLNE-TT-180056 | FA | 0 | TRUE | TRUE | FALSE
1169 | MRT-CA00-P0UMA-180047 | 2018-01-30 | MRT-DS-PLNE-TT-180056 | FA | 0 | TRUE | TRUE | FALSE
1170 | MRT-VE01-P2MAA-220044 | 2018-01-30 | MRT-DS-PLNE-TT-180057 | FI | 0 | TRUE | TRUE | FALSE
1171 | MRT-VE01-P3MAA-220044 | 2018-01-30 | MRT-DS-PLNE-TT-180057 | FI | 0 | TRUE | TRUE | FALSE
1172 | MRT-YF00-P2CBA-161203 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1173 | MRT-YF00-P2CGA-161303 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1174 | MRT-YF00-P3CBA-161203 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1175 | MRT-YF00-P3CGA-161303 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1176 | MRT-YF00-P2CBA-161204 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1177 | MRT-YF00-P2CGA-161304 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1178 | MRT-YF00-P3CBA-161204 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1179 | MRT-YF00-P3CGA-161304 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1180 | MRT-YF00-P2CBA-161205 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1181 | MRT-YF00-P2CGA-161305 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1182 | MRT-YF00-P3CBA-161205 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1183 | MRT-YF00-P3CGA-161305 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1184 | MRT-YF00-P2CBA-161206 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1185 | MRT-YF00-P2CGA-161306 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1186 | MRT-YF00-P3CBA-161206 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1187 | MRT-YF00-P3CGA-161306 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1188 | MRT-YF00-P2CBA-161207 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1189 | MRT-YF00-P2CGA-161307 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1190 | MRT-YF00-P3CBA-161207 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1191 | MRT-YF00-P3CGA-161307 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1192 | MRT-YF00-P2CBA-161208 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1193 | MRT-YF00-P2CGA-161308 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1194 | MRT-YF00-P3CBA-161208 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1195 | MRT-YF00-P3CGA-161308 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1196 | MRT-YF00-P0CBA-161221 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1197 | MRT-YF00-P0CGA-161321 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1198 | MRT-YF00-P2CBA-161209 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1199 | MRT-YF00-P2CGA-161309 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1200 | MRT-YF00-P3CBA-161209 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1201 | MRT-YF00-P3CGA-161309 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1202 | MRT-YF00-P0CBA-161222 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1203 | MRT-YF00-P0CGA-161322 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1204 | MRT-YF00-P2CBA-161211 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1205 | MRT-YF00-P2CBA-161212 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1206 | MRT-YF00-P2CBA-161210 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1207 | MRT-YF00-P2CGA-161311 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1208 | MRT-YF00-P2CGA-161312 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1209 | MRT-YF00-P2CGA-161310 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1210 | MRT-YF00-P3CBA-161211 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1211 | MRT-YF00-P3CBA-161212 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1212 | MRT-YF00-P3CBA-161210 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1213 | MRT-YF00-P3CGA-161311 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1214 | MRT-YF00-P3CGA-161312 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1215 | MRT-YF00-P3CGA-161310 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1216 | MRT-YF00-P0CBA-161201 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1217 | MRT-YF00-P0CBA-161202 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1218 | MRT-YF00-P0CGA-161301 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1219 | MRT-YF00-P0CGA-161302 | 2018-01-31 | MRT-DS-PLNE-TT-180044 | FA | 0 | TRUE | TRUE | FALSE
1220 | MRT-XV00-P0ZEN-020003 | 2018-01-31 | MRT-DS-PLNE-TT-180058 | FI | 0 | TRUE | TRUE | FALSE
1221 | MRT-VK02-P2UMA-170610 | 2018-01-31 | MRT-DS-PLNE-TT-180059 | FA | 0 | TRUE | TRUE | FALSE
1222 | MRT-VK02-P3UMA-170610 | 2018-01-31 | MRT-DS-PLNE-TT-180059 | FA | 0 | TRUE | TRUE | FALSE
1223 | MRT-VK02-P2UMA-170710 | 2018-01-31 | MRT-DS-PLNE-TT-180059 | FA | 0 | TRUE | TRUE | FALSE
1224 | MRT-VK02-P3UMA-170710 | 2018-01-31 | MRT-DS-PLNE-TT-180059 | FA | 0 | TRUE | TRUE | FALSE
1225 | MRT-MA01-P2ZEN-161011 | 2018-01-31 | MRT-DS-PLNE-TT-180061 | FA | 2 | TRUE | TRUE | FALSE
1226 | MRT-MA01-P3ZEN-161011 | 2018-01-31 | MRT-DS-PLNE-TT-180061 | FA | 2 | TRUE | TRUE | FALSE
1227 | MRT-XW01-P2SCA-127503 | 2018-02-01 | MRT-DS-PLNE-TT-180060 | FA | 0 | TRUE | TRUE | FALSE
1228 | MRT-XG02-P2SCA-127502 | 2018-02-01 | MRT-DS-PLNE-TT-180060 | FA | 0 | TRUE | TRUE | FALSE
1229 | MRT-XW01-P3SCA-127503 | 2018-02-01 | MRT-DS-PLNE-TT-180060 | FA | 0 | TRUE | TRUE | FALSE
1230 | MRT-XG02-P3SCA-127502 | 2018-02-01 | MRT-DS-PLNE-TT-180060 | FA | 0 | TRUE | TRUE | FALSE
1231 | MRT-DP00-P0ZEN-070001 | 2018-02-01 | MRT-DS-PLNE-TT-180066 | FA | 1 | TRUE | TRUE | FALSE
1232 | MRT-YF00-P2LB-122066 | 2018-02-01 | MRT-DS-PLNE-TT-180063 | FA | 0 | TRUE | TRUE | FALSE
1233 | MRT-YT01-P3LB-122100 | 2018-02-01 | MRT-DS-PLNE-TT-180064 | FI | 0 | TRUE | TRUE | FALSE
1234 | MRT-YT01-P2LB-122100 | 2018-02-01 | MRT-DS-PLNE-TT-180064 | FI | 0 | TRUE | TRUE | FALSE
1235 | MRT-YD00-P3LB-122049 | 2018-02-01 | MRT-DS-PLNE-TT-180065 | FI | 0 | TRUE | TRUE | FALSE
1236 | MRT-YT02-P3LB-122104 | 2018-02-01 | MRT-DS-PLNE-TT-180065 | FI | 0 | TRUE | TRUE | FALSE
1237 | MRT-YT02-P2LB-122104 | 2018-02-01 | MRT-DS-PLNE-TT-180065 | FI | 0 | TRUE | TRUE | FALSE
1238 | MRT-YD00-P2LB-122049 | 2018-02-01 | MRT-DS-PLNE-TT-180065 | FI | 0 | TRUE | TRUE | FALSE
1239 | MRT-YD00-P2LB-122107 | 2018-02-01 | MRT-DS-PLNE-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1240 | MRT-YD00-P3LB-122107 | 2018-02-01 | MRT-DS-PLNE-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1262 | MRT-XS01-P0ABA-150002 | 2018-02-01 | MRT-HK-PLNE-TT-180048 | FA | 1 | TRUE | TRUE | FALSE
1263 | MRT-XH00-P0GH-145001 | 2018-02-01 | MRT-HK-PLNE-TT-180048 | FA | 2 | TRUE | TRUE | FALSE
1241 | MRT-YT01-P2PGB-113200 | 2018-02-02 | MRT-DS-PLNE-TT-180067 | FA | 0 | TRUE | TRUE | FALSE
1242 | MRT-YD00-P2PGB-113201 | 2018-02-02 | MRT-DS-PLNE-TT-180067 | FI | 0 | TRUE | TRUE | FALSE
1243 | MRT-YT01-P3PGB-113200 | 2018-02-02 | MRT-DS-PLNE-TT-180067 | FA | 0 | TRUE | TRUE | FALSE
1244 | MRT-YD00-P3PGB-113201 | 2018-02-02 | MRT-DS-PLNE-TT-180067 | FI | 0 | TRUE | TRUE | FALSE
1245 | MRT-YD00-P2MKA-220002 | 2018-02-02 | MRT-DS-PLNE-TT-180068 | FI | 0 | TRUE | TRUE | FALSE
1246 | MRT-YD00-P3MKA-220002 | 2018-02-02 | MRT-DS-PLNE-TT-180068 | FI | 0 | TRUE | TRUE | FALSE
1247 | MRT-YD00-P2MKA-220001 | 2018-02-02 | MRT-DS-PLNE-TT-180069 | FI | 2 | TRUE | TRUE | FALSE
1248 | MRT-YT01-P2MAJ-603100 | 2018-02-02 | MRT-DS-PLNE-TT-180072 | FA | 1 | TRUE | TRUE | FALSE
1249 | MRT-XG02-P2MAJ-603101 | 2018-02-02 | MRT-DS-PLNE-TT-180072 | FA | 1 | TRUE | TRUE | FALSE
1250 | MRT-YK08-P2MAJ-603102 | 2018-02-02 | MRT-DS-PLNE-TT-180072 | FA | 1 | TRUE | TRUE | FALSE
1251 | MRT-YT01-P2MAJ-603104 | 2018-02-02 | MRT-DS-PLNE-TT-180072 | FI | 1 | TRUE | TRUE | FALSE
1252 | MRT-YL00-P2MAJ-603107 | 2018-02-02 | MRT-DS-PLNE-TT-180072 | FA | 1 | TRUE | TRUE | FALSE
1253 | MRT-YT01-P3MAJ-604100 | 2018-02-02 | MRT-DS-PLNE-TT-180072 | FA | 1 | TRUE | TRUE | FALSE
1254 | MRT-XG02-P3MAJ-604101 | 2018-02-02 | MRT-DS-PLNE-TT-180072 | FA | 1 | TRUE | TRUE | FALSE
1255 | MRT-YK08-P3MAJ-604102 | 2018-02-02 | MRT-DS-PLNE-TT-180072 | FA | 1 | TRUE | TRUE | FALSE
1256 | MRT-YT01-P3MAJ-604104 | 2018-02-02 | MRT-DS-PLNE-TT-180072 | FI | 1 | TRUE | TRUE | FALSE
1257 | MRT-YL00-P3MAJ-604107 | 2018-02-02 | MRT-DS-PLNE-TT-180072 | FA | 1 | TRUE | TRUE | FALSE
1260 | MRT-CA05-P0UMA-180061 | 2018-02-02 | MRT-DS-PLNE-TT-180070 | FA | 1 | TRUE | TRUE | FALSE
1261 | MRT-CA05-P0UMA-180062 | 2018-02-02 | MRT-DS-PLNE-TT-180070 | FA | 1 | TRUE | TRUE | FALSE
1264 | MRT-YD00-P2GHC-129001 | 2018-02-05 | MRT-DS-PLNE-TT-180073 | FA | 0 | TRUE | TRUE | FALSE
1265 | MRT-YD00-P3GHC-129001 | 2018-02-05 | MRT-DS-PLNE-TT-180073 | FA | 0 | TRUE | TRUE | FALSE
1266 | MRT-BF05-P0ZEN-175004 | 2018-02-05 | MRT-HK-PLNE-TT-180049 | FA | 1 | TRUE | TRUE | FALSE
1258 | MRT-YD00-P2MKA-220003 | 2018-02-06 | MRT-DS-PLNE-TT-180071 | FC | 2 | TRUE | TRUE | FALSE
1259 | MRT-YD00-P3MKA-220003 | 2018-02-06 | MRT-DS-PLNE-TT-180071 | FC | 2 | TRUE | TRUE | FALSE
1267 | MRT-CA00-P0UMA-180009 | 2018-02-06 | MRT-DS-PLNE-TT-180075 | FC | 2 | TRUE | TRUE | FALSE
1268 | MRT-CA00-P0UMA-180015 | 2018-02-06 | MRT-DS-PLNE-TT-180075 | FC | 2 | TRUE | TRUE | FALSE
1269 | MRT-CA00-P0UMA-180016 | 2018-02-06 | MRT-DS-PLNE-TT-180075 | FC | 2 | TRUE | TRUE | FALSE
1270 | MRT-CA00-P0UMA-180017 | 2018-02-06 | MRT-DS-PLNE-TT-180075 | FC | 2 | TRUE | TRUE | FALSE
1271 | MRT-CA00-P0UMA-180019 | 2018-02-06 | MRT-DS-PLNE-TT-180075 | FC | 2 | TRUE | TRUE | FALSE
1272 | MRT-CA00-P0UMA-180021 | 2018-02-06 | MRT-DS-PLNE-TT-180075 | FC | 2 | TRUE | TRUE | FALSE
1273 | MRT-CA00-P0UMA-180022 | 2018-02-06 | MRT-DS-PLNE-TT-180075 | FC | 2 | TRUE | TRUE | FALSE
1274 | MRT-MA02-P2ZEN-161015 | 2018-02-06 | MRT-DS-PLNE-TT-180076 | FA | 1 | TRUE | TRUE | FALSE
1275 | MRT-MA02-P3ZEN-161015 | 2018-02-06 | MRT-DS-PLNE-TT-180076 | FA | 1 | TRUE | TRUE | FALSE
1276 | MRT-XG02-P2LBA-110003 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1277 | MRT-XG02-P2LBG-110004 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1278 | MRT-XG02-P0LBG-110004 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1279 | MRT-XG02-P2LCM-110005 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1280 | MRT-XG02-P2LA-110006 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1281 | MRT-XG02-P2LC-110007 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1282 | MRT-XG02-P2PA-110002 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1283 | MRT-XG02-P0PA-110002 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1284 | MRT-XG02-P2PA-110008 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1285 | MRT-XG02-P0GHC-110002 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1286 | MRT-XG02-P2PG-110009 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1287 | MRT-XG02-P3LBA-110003 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1288 | MRT-XG02-P3LBG-110004 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1289 | MRT-XG02-P3LCM-110005 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1290 | MRT-XG02-P3LA-110006 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1291 | MRT-XG02-P3LC-110007 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1292 | MRT-XG02-P3PA-110002 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1293 | MRT-XG02-P3PA-110008 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1294 | MRT-XG02-P3PG-110009 | 2018-02-06 | MRT-DS-PLNE-TT-180074 | FC | 4 | TRUE | TRUE | FALSE
1295 | MRT-YD00-P2PGB-113101 | 2018-02-07 | MRT-DS-PLNE-TT-180077 | FA | 0 | TRUE | TRUE | FALSE
1296 | MRT-YT01-P2PGB-113102 | 2018-02-07 | MRT-DS-PLNE-TT-180077 | FA | 0 | TRUE | TRUE | FALSE
1297 | MRT-YD00-P3PGB-113101 | 2018-02-07 | MRT-DS-PLNE-TT-180077 | FA | 0 | TRUE | TRUE | FALSE
1298 | MRT-YT01-P3PGB-113102 | 2018-02-07 | MRT-DS-PLNE-TT-180077 | FA | 0 | TRUE | TRUE | FALSE
1299 | MRT-XA00-P2QC-130002 | 2018-02-07 | MRT-DS-PLNE-TT-180078 | FA | 0 | TRUE | TRUE | FALSE
1300 | MRT-XA00-P3QC-130002 | 2018-02-07 | MRT-DS-PLNE-TT-180078 | FA | 0 | TRUE | TRUE | FALSE
1301 | MRT-XG02-P3LB-122022 | 2018-02-08 | MRT-DS-PLNE-TT-180079 | FA | 0 | TRUE | TRUE | FALSE
1302 | MRT-XG02-P2LB-122022 | 2018-02-08 | MRT-DS-PLNE-TT-180079 | FA | 3 | TRUE | TRUE | FALSE
1303 | MRT-XL00-P3LB-122030 | 2018-02-08 | MRT-DS-PLNE-TT-180080 | FA | 0 | TRUE | TRUE | FALSE
1304 | MRT-XL00-P2LB-122030 | 2018-02-08 | MRT-DS-PLNE-TT-180080 | FA | 1 | TRUE | TRUE | FALSE
1305 | MRT-XN00-P3LB-122032 | 2018-02-08 | MRT-DS-PLNE-TT-180081 | FI | 0 | TRUE | TRUE | FALSE
1306 | MRT-XN00-P2LB-122032 | 2018-02-08 | MRT-DS-PLNE-TT-180081 | FI | 1 | TRUE | TRUE | FALSE
1307 | MRT-XB02-P2LB-122021 | 2018-02-08 | MRT-DS-PLNE-TT-180082 | FA | 1 | TRUE | TRUE | FALSE
1308 | MRT-VN03-P2LB-122015 | 2018-02-08 | MRT-DS-PLNE-TT-180083 | FI | 0 | TRUE | TRUE | FALSE
1309 | MRT-XJ00-P2LB-122028 | 2018-02-08 | MRT-DS-PLNE-TT-180083 | FI | 0 | TRUE | TRUE | FALSE
1310 | MRT-VN03-P3LB-122015 | 2018-02-08 | MRT-DS-PLNE-TT-180083 | FI | 0 | TRUE | TRUE | FALSE
1311 | MRT-XJ00-P3LB-122028 | 2018-02-08 | MRT-DS-PLNE-TT-180083 | FI | 0 | TRUE | TRUE | FALSE
1312 | MRT-XG02-P2QU-130024 | 2018-02-08 | MRT-DS-PLNE-TT-180084 | FA | 0 | TRUE | TRUE | FALSE
1313 | MRT-XA00-P2QU-130025 | 2018-02-08 | MRT-DS-PLNE-TT-180084 | FA | 0 | TRUE | TRUE | FALSE
1314 | MRT-XS00-P2QU-130026 | 2018-02-08 | MRT-DS-PLNE-TT-180084 | FA | 0 | TRUE | TRUE | FALSE
1315 | MRT-XG02-P3QU-130024 | 2018-02-08 | MRT-DS-PLNE-TT-180084 | FA | 0 | TRUE | TRUE | FALSE
1316 | MRT-XA00-P3QU-130025 | 2018-02-08 | MRT-DS-PLNE-TT-180084 | FA | 0 | TRUE | TRUE | FALSE
1317 | MRT-XS00-P3QU-130026 | 2018-02-08 | MRT-DS-PLNE-TT-180084 | FA | 0 | TRUE | TRUE | FALSE
1318 | MRT-UE00-P2ZEN-100016 | 2018-02-12 | MRT-DS-PLNE-TT-180085 | FA | 0 | TRUE | TRUE | FALSE
1319 | MRT-UE00-P3ZEN-100017 | 2018-02-12 | MRT-DS-PLNE-TT-180085 | FA | 0 | TRUE | TRUE | FALSE
1320 | MRT-CV03-P2ZEN-165201 | 2018-02-12 | MRT-DS-PLNE-TT-180086 | FA | 1 | TRUE | TRUE | FALSE
1321 | MRT-CV03-P3ZEN-165201 | 2018-02-12 | MRT-DS-PLNE-TT-180086 | FA | 1 | TRUE | TRUE | FALSE
1322 | MRT-YT01-P2LAC-126004 | 2018-02-12 | MRT-DS-PLNE-TT-180087 | FA | 0 | TRUE | TRUE | FALSE
1323 | MRT-YD00-P2LAC-126001 | 2018-02-12 | MRT-DS-PLNE-TT-180087 | FA | 0 | TRUE | TRUE | FALSE
1324 | MRT-XG02-P2LAC-126003 | 2018-02-12 | MRT-DS-PLNE-TT-180087 | FA | 0 | TRUE | TRUE | FALSE
1325 | MRT-YT01-P3LAC-126004 | 2018-02-12 | MRT-DS-PLNE-TT-180087 | FA | 0 | TRUE | TRUE | FALSE
1326 | MRT-YD00-P3LAC-126001 | 2018-02-12 | MRT-DS-PLNE-TT-180087 | FA | 0 | TRUE | TRUE | FALSE
1327 | MRT-XG02-P3LAC-126003 | 2018-02-12 | MRT-DS-PLNE-TT-180087 | FA | 0 | TRUE | TRUE | FALSE
1328 | MRT-YT01-P2LAC-126054 | 2018-02-12 | MRT-DS-PLNE-TT-180087 | FA | 0 | TRUE | TRUE | FALSE
1329 | MRT-YD00-P2LAC-126051 | 2018-02-12 | MRT-DS-PLNE-TT-180087 | FA | 0 | TRUE | TRUE | FALSE
1330 | MRT-XG02-P2LAC-126053 | 2018-02-12 | MRT-DS-PLNE-TT-180087 | FA | 0 | TRUE | TRUE | FALSE
1331 | MRT-YT01-P3LAC-126054 | 2018-02-12 | MRT-DS-PLNE-TT-180087 | FA | 0 | TRUE | TRUE | FALSE
1332 | MRT-YD00-P3LAC-126051 | 2018-02-12 | MRT-DS-PLNE-TT-180087 | FA | 0 | TRUE | TRUE | FALSE
1333 | MRT-XG02-P3LAC-126053 | 2018-02-12 | MRT-DS-PLNE-TT-180087 | FA | 0 | TRUE | TRUE | FALSE
1334 | MRT-XG02-P2MAJ-603201 | 2018-02-12 | MRT-DS-PLNE-TT-180089 | FA | 0 | TRUE | TRUE | FALSE
1335 | MRT-YT01-P2MAJ-603204 | 2018-02-12 | MRT-DS-PLNE-TT-180089 | FA | 0 | TRUE | TRUE | FALSE
1336 | MRT-YT01-P2MAJ-603206 | 2018-02-12 | MRT-DS-PLNE-TT-180089 | FI | 0 | TRUE | TRUE | FALSE
1337 | MRT-XS00-P2MAJ-603209 | 2018-02-12 | MRT-DS-PLNE-TT-180089 | FA | 0 | TRUE | TRUE | FALSE
1338 | MRT-XG02-P3MAJ-604201 | 2018-02-12 | MRT-DS-PLNE-TT-180089 | FA | 0 | TRUE | TRUE | FALSE
1339 | MRT-YT01-P3MAJ-604204 | 2018-02-12 | MRT-DS-PLNE-TT-180089 | FA | 0 | TRUE | TRUE | FALSE
1340 | MRT-YT01-P3MAJ-604206 | 2018-02-12 | MRT-DS-PLNE-TT-180089 | FI | 0 | TRUE | TRUE | FALSE
1341 | MRT-XS00-P3MAJ-604209 | 2018-02-12 | MRT-DS-PLNE-TT-180089 | FA | 0 | TRUE | TRUE | FALSE
1342 | MRT-YV02-P2MAJ-603202 | 2018-02-12 | MRT-DS-PLNE-TT-180090 | FI | 0 | TRUE | TRUE | FALSE
1343 | MRT-YK08-P2MAJ-603203 | 2018-02-12 | MRT-DS-PLNE-TT-180090 | FI | 0 | TRUE | TRUE | FALSE
1344 | MRT-YK08-P2MAJ-603205 | 2018-02-12 | MRT-DS-PLNE-TT-180090 | FI | 0 | TRUE | TRUE | FALSE
1345 | MRT-YV02-P3MAJ-604202 | 2018-02-12 | MRT-DS-PLNE-TT-180090 | FI | 0 | TRUE | TRUE | FALSE
1346 | MRT-YK08-P3MAJ-604203 | 2018-02-12 | MRT-DS-PLNE-TT-180090 | FI | 0 | TRUE | TRUE | FALSE
1347 | MRT-YK08-P3MAJ-604205 | 2018-02-12 | MRT-DS-PLNE-TT-180090 | FI | 0 | TRUE | TRUE | FALSE
1348 | MRT-DP00-P2LB-122106 | 2018-02-12 | MRT-DS-PLNE-TT-180091 | FA | 2 | TRUE | TRUE | FALSE
1349 | MRT-DP00-P3LB-122106 | 2018-02-12 | MRT-DS-PLNE-TT-180091 | FA | 2 | TRUE | TRUE | FALSE
1350 | MRT-CC07-P2UMA-170701 | 2018-02-12 | MRT-DS-PLNE-TT-180093 | FA | 1 | TRUE | TRUE | FALSE
1351 | MRT-CC02-P2UMA-170703 | 2018-02-12 | MRT-DS-PLNE-TT-180093 | FA | 1 | TRUE | TRUE | FALSE
1352 | MRT-CC02-P2UMA-170707 | 2018-02-12 | MRT-DS-PLNE-TT-180093 | FA | 1 | TRUE | TRUE | FALSE
1353 | MRT-CC02-P2UMA-170708 | 2018-02-12 | MRT-DS-PLNE-TT-180093 | FA | 1 | TRUE | TRUE | FALSE
1354 | MRT-CC02-P2UMA-170709 | 2018-02-12 | MRT-DS-PLNE-TT-180093 | FA | 1 | TRUE | TRUE | FALSE
1355 | MRT-CC07-P3UMA-170701 | 2018-02-12 | MRT-DS-PLNE-TT-180093 | FA | 1 | TRUE | TRUE | FALSE
1356 | MRT-CC02-P3UMA-170703 | 2018-02-12 | MRT-DS-PLNE-TT-180093 | FA | 1 | TRUE | TRUE | FALSE
1357 | MRT-CC02-P3UMA-170707 | 2018-02-12 | MRT-DS-PLNE-TT-180093 | FA | 1 | TRUE | TRUE | FALSE
1358 | MRT-CC02-P3UMA-170708 | 2018-02-12 | MRT-DS-PLNE-TT-180093 | FA | 1 | TRUE | TRUE | FALSE
1359 | MRT-CC02-P3UMA-170709 | 2018-02-12 | MRT-DS-PLNE-TT-180093 | FA | 1 | TRUE | TRUE | FALSE
1360 | MRT-CC02-P0UMA-170702 | 2018-02-12 | MRT-DS-PLNE-TT-180093 | FA | 0 | TRUE | TRUE | FALSE
1361 | MRT-XG02-P2QC-130001 | 2018-02-12 | MRT-DS-PLNE-TT-180092 | FA | 0 | TRUE | TRUE | FALSE
1362 | MRT-XS00-P2QC-130003 | 2018-02-12 | MRT-DS-PLNE-TT-180092 | FA | 0 | TRUE | TRUE | FALSE
1363 | MRT-CC07-P2QC-130004 | 2018-02-12 | MRT-DS-PLNE-TT-180092 | FA | 0 | TRUE | TRUE | FALSE
1364 | MRT-XG02-P3QC-130001 | 2018-02-12 | MRT-DS-PLNE-TT-180092 | FA | 0 | TRUE | TRUE | FALSE
1365 | MRT-XS00-P3QC-130003 | 2018-02-12 | MRT-DS-PLNE-TT-180092 | FA | 0 | TRUE | TRUE | FALSE
1366 | MRT-CC07-P3QC-130004 | 2018-02-12 | MRT-DS-PLNE-TT-180092 | FA | 0 | TRUE | TRUE | FALSE
1367 | MRT-YD00-P3CWA-165003 | 2018-02-12 | MRT-HK-RE-TT-180050 | FA | 0 | TRUE | TRUE | FALSE
1368 | MRT-YS01-P0ZEN-165013 | 2018-02-12 | MRT-HK-RE-TT-180050 | FA | 1 | TRUE | TRUE | FALSE
1369 | MRT-CC07-P2UMA-170601 | 2018-02-12 | MRT-DS-PLNE-TT-180096 | FA | 1 | TRUE | TRUE | FALSE
1370 | MRT-CC02-P2UMA-170603 | 2018-02-12 | MRT-DS-PLNE-TT-180096 | FA | 1 | TRUE | TRUE | FALSE
1371 | MRT-CC02-P2UMA-170607 | 2018-02-12 | MRT-DS-PLNE-TT-180096 | FA | 1 | TRUE | TRUE | FALSE
1372 | MRT-CC02-P2UMA-170608 | 2018-02-12 | MRT-DS-PLNE-TT-180096 | FA | 1 | TRUE | TRUE | FALSE
1373 | MRT-CC02-P2UMA-170609 | 2018-02-12 | MRT-DS-PLNE-TT-180096 | FA | 1 | TRUE | TRUE | FALSE
1374 | MRT-CC07-P3UMA-170601 | 2018-02-12 | MRT-DS-PLNE-TT-180096 | FA | 1 | TRUE | TRUE | FALSE
1375 | MRT-CC02-P3UMA-170603 | 2018-02-12 | MRT-DS-PLNE-TT-180096 | FA | 1 | TRUE | TRUE | FALSE
1376 | MRT-CC02-P3UMA-170607 | 2018-02-12 | MRT-DS-PLNE-TT-180096 | FA | 1 | TRUE | TRUE | FALSE
1377 | MRT-CC02-P3UMA-170608 | 2018-02-12 | MRT-DS-PLNE-TT-180096 | FA | 1 | TRUE | TRUE | FALSE
1378 | MRT-CC02-P3UMA-170609 | 2018-02-12 | MRT-DS-PLNE-TT-180096 | FA | 1 | TRUE | TRUE | FALSE
1379 | MRT-CC02-P0UMA-170602 | 2018-02-12 | MRT-DS-PLNE-TT-180096 | FA | 0 | TRUE | TRUE | FALSE
1380 | MRT-QM03-P0ZEN-045009 | 2018-02-13 | MRT-HK-RE-TT-180051 | FA | 0 | TRUE | TRUE | FALSE
1381 | MRT-QM03-P0ZEN-045008 | 2018-02-13 | MRT-HK-RE-TT-180051 | FA | 1 | TRUE | TRUE | FALSE
1382 | MRT-XW01-P0ZEN-161001 | 2018-02-13 | MRT-DS-PLNE-TT-180088 | FC | 3 | TRUE | TRUE | FALSE
1383 | MRT-YU04-P0ZEN-161012 | 2018-02-13 | MRT-DS-PLNE-TT-180101 | FA | 2 | TRUE | TRUE | FALSE
1384 | MRT-YD06-P2ZEN-161014 | 2018-02-13 | MRT-DS-PLNE-TT-180103 | FC | 1 | TRUE | TRUE | FALSE
1385 | MRT-YD06-P3ZEN-161014 | 2018-02-13 | MRT-DS-PLNE-TT-180103 | FC | 1 | TRUE | TRUE | FALSE
1386 | MRT-YE00-P2MKA-230002 | 2018-02-13 | MRT-DS-PLNE-TT-180097 | FA | 0 | TRUE | TRUE | FALSE
1387 | MRT-XL00-P0ZEN-140001 | 2018-02-13 | MRT-DS-PLNE-TT-180104 | FA | 2 | TRUE | TRUE | FALSE
1388 | MRT-XL00-P0ZEN-140002 | 2018-02-13 | MRT-DS-PLNE-TT-180104 | FC | 2 | TRUE | TRUE | FALSE
1389 | MRT-XN00-P0ZEN-140001 | 2018-02-13 | MRT-DS-PLNE-TT-180104 | FC | 2 | TRUE | TRUE | FALSE
1390 | MRT-YE00-P3MKA-230002 | 2018-02-13 | MRT-DS-PLNE-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
1391 | MRT-YL00-P2MAJ-603105 | 2018-02-13 | MRT-DS-PLNE-TT-180099 | FA | 1 | TRUE | TRUE | FALSE
1392 | MRT-YL00-P3MAJ-604105 | 2018-02-13 | MRT-DS-PLNE-TT-180099 | FA | 1 | TRUE | TRUE | FALSE
1393 | MRT-YT01-P2MAJ-603103 | 2018-02-13 | MRT-DS-PLNE-TT-180100 | FA | 1 | TRUE | TRUE | FALSE
1394 | MRT-XN00-P2MAJ-603106 | 2018-02-13 | MRT-DS-PLNE-TT-180100 | FA | 1 | TRUE | TRUE | FALSE
1395 | MRT-YT01-P3MAJ-604103 | 2018-02-13 | MRT-DS-PLNE-TT-180100 | FA | 1 | TRUE | TRUE | FALSE
1396 | MRT-XN00-P3MAJ-604106 | 2018-02-13 | MRT-DS-PLNE-TT-180100 | FA | 1 | TRUE | TRUE | FALSE
1397 | MRT-YU02-P0ABA-150026 | 2018-02-13 | MRT-HK-RE-TT-180052 | FA | 0 | TRUE | TRUE | FALSE
1398 | MRT-CA03-P0UMA-180035 | 2018-02-14 | MRT-DS-PLNE-TT-180094 | FC | 2 | TRUE | TRUE | FALSE
1399 | MRT-CA03-P0UMA-180036 | 2018-02-14 | MRT-DS-PLNE-TT-180094 | FC | 2 | TRUE | TRUE | FALSE
1400 | MRT-CA03-P0UMA-180037 | 2018-02-14 | MRT-DS-PLNE-TT-180094 | FC | 2 | TRUE | TRUE | FALSE
1401 | MRT-CA03-P0UMA-180039 | 2018-02-14 | MRT-DS-PLNE-TT-180094 | FC | 2 | TRUE | TRUE | FALSE
1402 | MRT-CA03-P0UMA-180040 | 2018-02-14 | MRT-DS-PLNE-TT-180094 | FC | 2 | TRUE | TRUE | FALSE
1403 | MRT-CA05-P0UCA-180161 | 2018-02-14 | MRT-DS-PLNE-TT-180105 | FC | 2 | TRUE | TRUE | FALSE
1404 | MRT-CA05-P0UCA-180162 | 2018-02-14 | MRT-DS-PLNE-TT-180105 | FC | 2 | TRUE | TRUE | FALSE
1405 | MRT-CA05-P0UCA-180163 | 2018-02-14 | MRT-DS-PLNE-TT-180105 | FC | 2 | TRUE | TRUE | FALSE
1406 | MRT-CA05-P0UCA-180164 | 2018-02-14 | MRT-DS-PLNE-TT-180105 | FC | 2 | TRUE | TRUE | FALSE
1407 | MRT-CC07-P2UMA-170501 | 2018-02-14 | MRT-DS-PLNE-TT-180106 | FA | 1 | TRUE | TRUE | FALSE
1408 | MRT-CC02-P2UMA-170503 | 2018-02-14 | MRT-DS-PLNE-TT-180106 | FA | 1 | TRUE | TRUE | FALSE
1409 | MRT-CC02-P2UMA-170507 | 2018-02-14 | MRT-DS-PLNE-TT-180106 | FA | 1 | TRUE | TRUE | FALSE
1410 | MRT-VK02-P2UMA-170510 | 2018-02-14 | MRT-DS-PLNE-TT-180106 | FA | 1 | TRUE | TRUE | FALSE
1411 | MRT-CC07-P3UMA-170501 | 2018-02-14 | MRT-DS-PLNE-TT-180106 | FA | 1 | TRUE | TRUE | FALSE
1412 | MRT-CC02-P3UMA-170503 | 2018-02-14 | MRT-DS-PLNE-TT-180106 | FA | 1 | TRUE | TRUE | FALSE
1413 | MRT-CC02-P3UMA-170507 | 2018-02-14 | MRT-DS-PLNE-TT-180106 | FA | 1 | TRUE | TRUE | FALSE
1414 | MRT-VK02-P3UMA-170510 | 2018-02-14 | MRT-DS-PLNE-TT-180106 | FA | 1 | TRUE | TRUE | FALSE
1415 | MRT-CC02-P0UMA-170502 | 2018-02-14 | MRT-DS-PLNE-TT-180106 | FA | 1 | TRUE | TRUE | FALSE
1416 | MRT-YF01-P2ZEN-161013 | 2018-02-14 | MRT-DS-PLNE-TT-180102 | FA | 2 | TRUE | TRUE | FALSE
1417 | MRT-YF01-P3ZEN-161013 | 2018-02-14 | MRT-DS-PLNE-TT-180102 | FA | 2 | TRUE | TRUE | FALSE
1418 | MRT-CA06-P0UMA-180002 | 2018-02-14 | MRT-DS-PLNE-TT-180109 | FC | 3 | TRUE | TRUE | FALSE
1419 | MRT-YR00-P2CJJ-240055 | 2018-02-14 | MRT-DS-PLNE-TT-180110 | FI | 0 | TRUE | TRUE | FALSE
1420 | MRT-YR00-P3CJJ-240055 | 2018-02-14 | MRT-DS-PLNE-TT-180110 | FI | 0 | TRUE | TRUE | FALSE
1421 | MRT-YT01-P2LB-111102 | 2018-02-14 | MRT-DS-PLNE-TT-180108 | FA | 0 | TRUE | TRUE | FALSE
1422 | MRT-YK08-P2LB-111101 | 2018-02-14 | MRT-DS-PLNE-TT-180108 | FA | 0 | TRUE | TRUE | FALSE
1423 | MRT-YK09-P2LB-111103 | 2018-02-14 | MRT-DS-PLNE-TT-180108 | FI | 0 | TRUE | TRUE | FALSE
1424 | MRT-YT01-P3LB-111102 | 2018-02-14 | MRT-DS-PLNE-TT-180108 | FA | 0 | TRUE | TRUE | FALSE
1425 | MRT-YK08-P3LB-111101 | 2018-02-14 | MRT-DS-PLNE-TT-180108 | FA | 0 | TRUE | TRUE | FALSE
1426 | MRT-YK09-P3LB-111103 | 2018-02-14 | MRT-DS-PLNE-TT-180108 | FI | 0 | TRUE | TRUE | FALSE
1427 | MRT-YS00-P0ZEN-162101 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1428 | MRT-YS00-P0ZEN-162102 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1429 | MRT-YS00-P0ZEN-162103 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1430 | MRT-YS00-P0ZEN-162104 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1431 | MRT-YS00-P0ZEN-162105 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1432 | MRT-YS00-P0ZEN-162106 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1433 | MRT-YS00-P0ZEN-162107 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1434 | MRT-YS00-P0ZEN-162108 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1435 | MRT-YS00-P0ZEN-162109 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1436 | MRT-YS00-P0ZEN-162110 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1437 | MRT-YS00-P0ZEN-162111 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1438 | MRT-YS00-P0ZEN-162112 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1439 | MRT-YS00-P0ZEN-162113 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1440 | MRT-YS00-P0ZEN-162114 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1441 | MRT-YS00-P0ZEN-162115 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1442 | MRT-YS00-P0ZEN-162116 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1443 | MRT-YS00-P0ZEN-162117 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1444 | MRT-YS00-P0ZEN-162118 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1445 | MRT-YS00-P0ZEN-162119 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1446 | MRT-YS00-P0ZEN-162120 | 2018-02-14 | MRT-DS-PLNE-TT-180107 | FA | 2 | TRUE | TRUE | FALSE
1447 | MRT-YD00-P2ZEN-113400 | 2018-02-14 | MRT-DS-PLNE-TT-180114 | FA | 0 | TRUE | TRUE | FALSE
1448 | MRT-YT01-P2ZEN-113401 | 2018-02-14 | MRT-DS-PLNE-TT-180114 | FA | 0 | TRUE | TRUE | FALSE
1449 | MRT-YD00-P3ZEN-113400 | 2018-02-14 | MRT-DS-PLNE-TT-180114 | FA | 0 | TRUE | TRUE | FALSE
1450 | MRT-YT01-P3ZEN-113401 | 2018-02-14 | MRT-DS-PLNE-TT-180114 | FA | 0 | TRUE | TRUE | FALSE
1451 | MRT-YT01-P3ZEN-113501 | 2018-02-14 | MRT-DS-PLNE-TT-180112 | FA | 0 | TRUE | TRUE | FALSE
1452 | MRT-YT01-P2ZEN-113501 | 2018-02-14 | MRT-DS-PLNE-TT-180112 | FA | 0 | TRUE | TRUE | FALSE
1453 | MRT-YD00-P3ZEN-113500 | 2018-02-14 | MRT-DS-PLNE-TT-180112 | FA | 0 | TRUE | TRUE | FALSE
1454 | MRT-YD00-P2ZEN-113500 | 2018-02-14 | MRT-DS-PLNE-TT-180112 | FA | 0 | TRUE | TRUE | FALSE
1455 | MRT-QM03-P0ZEN-145002 | 2018-02-14 | MRT-HK-RE-TT-180053 | FA | 0 | TRUE | TRUE | FALSE
1456 | MRT-XB00-P2MKA-220001 | 2018-02-14 | MRT-DS-PLNE-TT-180111 | FC | 3 | TRUE | TRUE | FALSE
1457 | MRT-XB00-P3MKA-220001 | 2018-02-14 | MRT-DS-PLNE-TT-180111 | FC | 3 | TRUE | TRUE | FALSE
1458 | MRT-XG02-P0GN-135202 | 2018-02-14 | MRT-HK-RE-TT-180054 | FA | 2 | TRUE | TRUE | FALSE
1459 | MRT-YL25-P0ZEN-145301 | 2018-02-14 | MRT-HK-RE-TT-180054 | FA | 0 | TRUE | TRUE | FALSE
1460 | MRT-CC07-P2UMA-170205 | 2018-02-19 | MRT-DS-PLNE-TT-180113 | FC | 1 | TRUE | TRUE | FALSE
1461 | MRT-CC02-P2UMA-170207 | 2018-02-19 | MRT-DS-PLNE-TT-180113 | FC | 1 | TRUE | TRUE | FALSE
1462 | MRT-CC02-P2UMA-170208 | 2018-02-19 | MRT-DS-PLNE-TT-180113 | FC | 1 | TRUE | TRUE | FALSE
1463 | MRT-CC02-P2UMA-170209 | 2018-02-19 | MRT-DS-PLNE-TT-180113 | FC | 1 | TRUE | TRUE | FALSE
1464 | MRT-CC07-P2UMA-170211 | 2018-02-19 | MRT-DS-PLNE-TT-180113 | FC | 1 | TRUE | TRUE | FALSE
1465 | MRT-CC07-P3UMA-170205 | 2018-02-19 | MRT-DS-PLNE-TT-180113 | FC | 1 | TRUE | TRUE | FALSE
1466 | MRT-CC02-P3UMA-170207 | 2018-02-19 | MRT-DS-PLNE-TT-180113 | FC | 1 | TRUE | TRUE | FALSE
1467 | MRT-CC02-P3UMA-170208 | 2018-02-19 | MRT-DS-PLNE-TT-180113 | FC | 1 | TRUE | TRUE | FALSE
1468 | MRT-CC02-P3UMA-170209 | 2018-02-19 | MRT-DS-PLNE-TT-180113 | FC | 1 | TRUE | TRUE | FALSE
1469 | MRT-CC07-P3UMA-170211 | 2018-02-19 | MRT-DS-PLNE-TT-180113 | FC | 1 | TRUE | TRUE | FALSE
1470 | MRT-YD00-P0PGB-606000 | 2018-02-19 | MRT-DS-PLNE-TT-180115 | FC | 2 | TRUE | TRUE | FALSE
1471 | MRT-YD00-P0PGB-606001 | 2018-02-19 | MRT-DS-PLNE-TT-180115 | FC | 2 | TRUE | TRUE | FALSE
1472 | MRT-XW03-P0BAU-150016 | 2018-02-20 | MRT-HK-REC-TT-180055 | FA | 0 | TRUE | TRUE | FALSE
1473 | MRT-YE06-P0BAU-150160 | 2018-02-20 | MRT-HK-REC-TT-180055 | FA | 0 | TRUE | TRUE | FALSE
1474 | MRT-CA00-P0UMA-180023 | 2018-02-21 | MRT-DS-PLNE-TT-180095 | FA | 0 | TRUE | TRUE | FALSE
1475 | MRT-CA00-P0UMA-180024 | 2018-02-21 | MRT-DS-PLNE-TT-180095 | FA | 0 | TRUE | TRUE | FALSE
1476 | MRT-UE00-P3LB-122008 | 2018-02-21 | MRT-DS-PLNE-TT-180116 | FI | 0 | TRUE | TRUE | FALSE
1477 | MRT-UE00-P2LB-122008 | 2018-02-21 | MRT-DS-PLNE-TT-180116 | FI | 1 | TRUE | TRUE | FALSE
1478 | MRT-UE00-P2LB-122010 | 2018-02-21 | MRT-DS-PLNE-TT-180117 | FI | 1 | TRUE | TRUE | FALSE
1479 | MRT-UE00-P3LB-122010 | 2018-02-21 | MRT-DS-PLNE-TT-180117 | FI | 1 | TRUE | TRUE | FALSE
1480 | MRT-XB02-P2LB-122017 | 2018-02-21 | MRT-DS-PLNE-TT-180118 | FC | 2 | TRUE | TRUE | FALSE
1481 | MRT-XB02-P3LB-122017 | 2018-02-21 | MRT-DS-PLNE-TT-180118 | FC | 1 | TRUE | TRUE | FALSE
1482 | MRT-UE00-P3LB-122007 | 2018-02-21 | MRT-DS-PLNE-TT-180119 | FA | 0 | TRUE | TRUE | FALSE
1483 | MRT-UE00-P2LB-122007 | 2018-02-21 | MRT-DS-PLNE-TT-180119 | FA | 1 | TRUE | TRUE | FALSE
1484 | MRT-YQ03-P3LB-122088 | 2018-02-21 | MRT-DS-PLNE-TT-180120 | FA | 0 | TRUE | TRUE | FALSE
1485 | MRT-YQ03-P2LB-122088 | 2018-02-21 | MRT-DS-PLNE-TT-180120 | FA | 1 | TRUE | TRUE | FALSE
1486 | MRT-XB02-P0UMA-180004 | 2018-02-22 | MRT-DS-PLNE-TT-180121 | FC | 3 | TRUE | TRUE | FALSE
1487 | MRT-CA01-P0UMA-180005 | 2018-02-22 | MRT-DS-PLNE-TT-180121 | FC | 3 | TRUE | TRUE | FALSE
1488 | MRT-CA01-P0UMA-180006 | 2018-02-22 | MRT-DS-PLNE-TT-180121 | FC | 3 | TRUE | TRUE | FALSE
1489 | MRT-CA01-P0UMA-180007 | 2018-02-22 | MRT-DS-PLNE-TT-180121 | FC | 3 | TRUE | TRUE | FALSE
1490 | MRT-XB02-P0UCA-180102 | 2018-02-22 | MRT-DS-PLNE-TT-180122 | FC | 3 | TRUE | TRUE | FALSE
1491 | MRT-CA01-P0UCA-180103 | 2018-02-22 | MRT-DS-PLNE-TT-180122 | FC | 3 | TRUE | TRUE | FALSE
1492 | MRT-CA02-P0UCA-180104 | 2018-02-22 | MRT-DS-PLNE-TT-180122 | FC | 3 | TRUE | TRUE | FALSE
1493 | MRT-XW03-P0BAA-150006 | 2018-02-22 | MRT-HK-RE-TT-180056 | FA | 0 | TRUE | TRUE | FALSE
1494 | MRT-XW03-P0BAC-150007 | 2018-02-22 | MRT-HK-RE-TT-180056 | FA | 0 | TRUE | TRUE | FALSE
1495 | MRT-XB00-P2LAC-126022 | 2018-02-22 | MRT-DS-PLNE-TT-180123 | FI | 0 | TRUE | TRUE | FALSE
1496 | MRT-XB00-P3LAC-126022 | 2018-02-22 | MRT-DS-PLNE-TT-180123 | FI | 0 | TRUE | TRUE | FALSE
1497 | MRT-XB00-P2LAC-126070 | 2018-02-22 | MRT-DS-PLNE-TT-180123 | FI | 0 | TRUE | TRUE | FALSE
1498 | MRT-XB00-P3LAC-126070 | 2018-02-22 | MRT-DS-PLNE-TT-180123 | FI | 0 | TRUE | TRUE | FALSE
1499 | MRT-CV03-P0ZEN-163101 | 2018-02-23 | MRT-DS-PLNE-TT-180124 | FA | 0 | TRUE | TRUE | FALSE
1500 | MRT-CV03-P0ZEN-163102 | 2018-02-23 | MRT-DS-PLNE-TT-180124 | FA | 0 | TRUE | TRUE | FALSE
1501 | MRT-CV03-P0ZEN-163103 | 2018-02-23 | MRT-DS-PLNE-TT-180124 | FA | 0 | TRUE | TRUE | FALSE
1502 | MRT-CC07-P2UMA-170801 | 2018-02-23 | MRT-DS-PLNE-TT-180125 | FA | 1 | TRUE | TRUE | FALSE
1503 | MRT-CC02-P2UMA-170803 | 2018-02-23 | MRT-DS-PLNE-TT-180125 | FA | 1 | TRUE | TRUE | FALSE
1504 | MRT-VK02-P2UMA-170806 | 2018-02-23 | MRT-DS-PLNE-TT-180125 | FA | 1 | TRUE | TRUE | FALSE
1505 | MRT-CC07-P3UMA-170801 | 2018-02-23 | MRT-DS-PLNE-TT-180125 | FA | 1 | TRUE | TRUE | FALSE
1506 | MRT-CC02-P3UMA-170803 | 2018-02-23 | MRT-DS-PLNE-TT-180125 | FA | 1 | TRUE | TRUE | FALSE
1507 | MRT-VK02-P3UMA-170806 | 2018-02-23 | MRT-DS-PLNE-TT-180125 | FA | 1 | TRUE | TRUE | FALSE
1508 | MRT-YT01-P2GHC-129002 | 2018-02-23 | MRT-DS-PLNE-TT-180126 | FA | 0 | TRUE | TRUE | FALSE
1509 | MRT-YT01-P3GHC-129002 | 2018-02-23 | MRT-DS-PLNE-TT-180126 | FA | 0 | TRUE | TRUE | FALSE
1510 | MRT-YR05-P0ZEN-161016 | 2018-02-23 | MRT-DS-PLNE-TT-180127 | FA | 1 | TRUE | TRUE | FALSE
1511 | MRT-QM03-P0ZEN-045003 | 2018-02-26 | MRT-HK-REC-TT-180058 | FA | 1 | TRUE | TRUE | FALSE
1512 | MRT-XG02-P2MKJ-210001 | 2018-02-26 | MRT-DS-PLNE-TT-180128 | FI | 0 | TRUE | TRUE | FALSE
1513 | MRT-XG02-P3MKW-210001 | 2018-02-26 | MRT-DS-PLNE-TT-180128 | FA | 0 | TRUE | TRUE | FALSE
1514 | MRT-XG02-P3MKG-210001 | 2018-02-26 | MRT-DS-PLNE-TT-180128 | FA | 0 | TRUE | TRUE | FALSE
1515 | MRT-XS00-P3MKW-210001 | 2018-02-26 | MRT-DS-PLNE-TT-180128 | FI | 0 | TRUE | TRUE | FALSE
1516 | MRT-XS00-P3MKG-210001 | 2018-02-26 | MRT-DS-PLNE-TT-180128 | FI | 0 | TRUE | TRUE | FALSE
1517 | MRT-CC02-P0PUPC-175750 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1518 | MRT-CC02-P0PUPC-175751 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1519 | MRT-CC02-P0PUPC-175752 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1520 | MRT-CC02-P0PUPC-175753 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1521 | MRT-CC02-P0PUPC-175755 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1522 | MRT-CC02-P0PUPC-175756 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1523 | MRT-CC02-P0PUPC-175757 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1524 | MRT-CC02-P0PUPC-175758 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1525 | MRT-CC02-P0PUPC-175759 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1526 | MRT-CC02-P0PUPC-175760 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1527 | MRT-CC02-P0PUPC-175761 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1528 | MRT-CC02-P0PUPC-175762 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1529 | MRT-CC02-P0PUPC-175763 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1530 | MRT-CC02-P0PUPC-175764 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1531 | MRT-CC02-P0PUPC-175765 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1532 | MRT-CC02-P0PUPC-175766 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1533 | MRT-CC02-P0PUPC-175767 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1534 | MRT-CC02-P0PUPC-175768 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1535 | MRT-CC02-P0PUPC-175769 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1536 | MRT-CC02-P0PUPC-175770 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1537 | MRT-CC02-P0PUPC-175771 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1538 | MRT-CC02-P0PUPC-175754 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1539 | MRT-CC02-P0PUPC-175772 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1540 | MRT-CC02-P0PUPC-175773 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1541 | MRT-CC02-P0PUPC-175774 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1542 | MRT-CC02-P0PUPC-175775 | 2018-02-26 | MRT-HK-REC-TT-180057 | FA | 0 | TRUE | TRUE | FALSE
1543 | MRT-CA01-P0UCA-180129 | 2018-02-27 | MRT-DS-REC-TT-180129 | FC | 1 | TRUE | TRUE | FALSE
1544 | MRT-CA01-P0UCA-180122 | 2018-02-27 | MRT-DS-REC-TT-180130 | FC | 2 | TRUE | TRUE | FALSE
1545 | MRT-CA01-P0UCA-180123 | 2018-02-27 | MRT-DS-REC-TT-180130 | FC | 2 | TRUE | TRUE | FALSE
1546 | MRT-CA01-P0UCA-180127 | 2018-02-27 | MRT-DS-REC-TT-180130 | FC | 2 | TRUE | TRUE | FALSE
1547 | MRT-CA01-P0UCA-180128 | 2018-02-27 | MRT-DS-REC-TT-180130 | FC | 2 | TRUE | TRUE | FALSE
1548 | MRT-CA02-P0UCA-180134 | 2018-02-27 | MRT-DS-REC-TT-180130 | FC | 2 | TRUE | TRUE | FALSE
1549 | MRT-CA02-P0UCA-180135 | 2018-02-27 | MRT-DS-REC-TT-180130 | FC | 2 | TRUE | TRUE | FALSE
1550 | MRT-CA02-P0UCA-180136 | 2018-02-27 | MRT-DS-REC-TT-180130 | FC | 2 | TRUE | TRUE | FALSE
1551 | MRT-YF02-P2SCA-127514 | 2018-02-27 | MRT-DS-REC-TT-180131 | FA | 0 | TRUE | TRUE | FALSE
1552 | MRT-YF02-P3SCA-127514 | 2018-02-27 | MRT-DS-REC-TT-180131 | FA | 0 | TRUE | TRUE | FALSE
1553 | MRT-DP01-P0ZEN-070002 | 2018-02-27 | MRT-DS-REC-TT-180132 | FI | 0 | TRUE | TRUE | FALSE
1554 | MRT-YU01-P0ABA-150025 | 2018-02-27 | MRT-HK-REC-TT-180059 | FA | 0 | TRUE | TRUE | FALSE
1555 | MRT-YE04-P0BAU-150175 | 2018-02-27 | MRT-HK-REC-TT-180059 | FA | 0 | TRUE | TRUE | FALSE
1556 | MRT-XW03-P0ABA-150192 | 2018-02-27 | MRT-HK-REC-TT-180059 | FA | 0 | TRUE | TRUE | FALSE
1557 | MRT-YE01-P0BAU-150207 | 2018-02-27 | MRT-HK-REC-TT-180059 | FA | 0 | TRUE | TRUE | FALSE
8020 | MRT-CC07-P0UGA-176231 | 2018-02-27 | MRT-HK-REC-TT-180060 | FA | 0 | TRUE | FALSE | FALSE
8021 | MRT-CC07-P0UGA-176271 | 2018-02-27 | MRT-HK-REC-TT-180060 | FA | 0 | TRUE | FALSE | FALSE
1558 | MRT-XB02-P2LB-122018 | 2018-02-28 | MRT-DS-REC-TT-180133 | FA | 2 | TRUE | TRUE | FALSE
1559 | MRT-XB02-P3LB-122018 | 2018-02-28 | MRT-DS-REC-TT-180133 | FA | 1 | TRUE | TRUE | FALSE
1560 | MRT-QM03-P0ZEN-045010 | 2018-02-28 | MRT-HK-REC-TT-180061 | FA | 0 | TRUE | TRUE | FALSE
1561 | MRT-QM03-P0ZEN-045007 | 2018-02-28 | MRT-HK-REC-TT-180061 | FA | 0 | TRUE | TRUE | FALSE
1562 | MRT-XH01-P0UZT-140001 | 2018-02-28 | MRT-DS-REC-TT-180137 | FA | 1 | TRUE | TRUE | FALSE
1563 | MRT-XH01-P2ULY-142000 | 2018-02-28 | MRT-DS-REC-TT-180137 | FA | 1 | TRUE | TRUE | FALSE
1564 | MRT-XH01-P3ULY-143000 | 2018-02-28 | MRT-DS-REC-TT-180137 | FA | 1 | TRUE | TRUE | FALSE
1565 | MRT-XH01-P3ULY-144000 | 2018-02-28 | MRT-DS-REC-TT-180137 | FA | 1 | TRUE | TRUE | FALSE
1566 | MRT-YK08-P2LAA-605100 | 2018-02-28 | MRT-DS-REC-TT-180138 | FA | 3 | TRUE | TRUE | FALSE
1567 | MRT-YK08-P3LAA-605500 | 2018-02-28 | MRT-DS-REC-TT-180138 | FA | 3 | TRUE | TRUE | FALSE
1568 | MRT-YT01-P2LAA-605101 | 2018-02-28 | MRT-DS-REC-TT-180139 | FA | 3 | TRUE | TRUE | FALSE
1569 | MRT-YT01-P3LAA-605501 | 2018-02-28 | MRT-DS-REC-TT-180139 | FA | 3 | TRUE | TRUE | FALSE
1570 | MRT-YQ03-P2LB-122086 | 2018-02-28 | MRT-DS-REC-TT-180134 | FI | 0 | TRUE | FALSE | FALSE
1571 | MRT-XV00-P2LB-122039 | 2018-02-28 | MRT-DS-REC-TT-180134 | FI | 0 | TRUE | FALSE | FALSE
1572 | MRT-YD00-P2LB-122055 | 2018-02-28 | MRT-DS-REC-TT-180134 | FI | 0 | TRUE | FALSE | FALSE
1573 | MRT-YK01-P2LB-122074 | 2018-02-28 | MRT-DS-REC-TT-180134 | FI | 0 | TRUE | FALSE | FALSE
1574 | MRT-VN02-P2LB-122089 | 2018-02-28 | MRT-DS-REC-TT-180134 | FA | 0 | TRUE | FALSE | FALSE
1575 | MRT-YD00-P2LB-122050 | 2018-02-28 | MRT-DS-REC-TT-180134 | FA | 0 | TRUE | FALSE | FALSE
1576 | MRT-YT01-P2LB-122051 | 2018-02-28 | MRT-DS-REC-TT-180134 | FA | 0 | TRUE | FALSE | FALSE
1577 | MRT-YD00-P2LB-122053 | 2018-02-28 | MRT-DS-REC-TT-180134 | FA | 0 | TRUE | FALSE | FALSE
1578 | MRT-YD00-P2LB-122052 | 2018-02-28 | MRT-DS-REC-TT-180134 | FA | 0 | TRUE | FALSE | FALSE
1579 | MRT-YQ03-P3LB-122086 | 2018-02-28 | MRT-DS-REC-TT-180134 | FI | 0 | TRUE | FALSE | FALSE
1580 | MRT-XV00-P3LB-122039 | 2018-02-28 | MRT-DS-REC-TT-180134 | FI | 0 | TRUE | FALSE | FALSE
1581 | MRT-YD00-P3LB-122050 | 2018-02-28 | MRT-DS-REC-TT-180134 | FA | 0 | TRUE | FALSE | FALSE
1582 | MRT-YT01-P3LB-122051 | 2018-02-28 | MRT-DS-REC-TT-180134 | FA | 0 | TRUE | FALSE | FALSE
1583 | MRT-YD00-P3LB-122052 | 2018-02-28 | MRT-DS-REC-TT-180134 | FA | 0 | TRUE | FALSE | FALSE
1584 | MRT-YD00-P3LB-122053 | 2018-02-28 | MRT-DS-REC-TT-180134 | FA | 0 | TRUE | FALSE | FALSE
1585 | MRT-YD00-P3LB-122055 | 2018-02-28 | MRT-DS-REC-TT-180134 | FI | 0 | TRUE | FALSE | FALSE
1586 | MRT-YK01-P3LB-122074 | 2018-02-28 | MRT-DS-REC-TT-180134 | FI | 0 | TRUE | FALSE | FALSE
1587 | MRT-VN02-P3LB-122089 | 2018-02-28 | MRT-DS-REC-TT-180134 | FA | 0 | TRUE | FALSE | FALSE
1588 | MRT-YD00-P2LB-122056 | 2018-02-28 | MRT-DS-REC-TT-180135 | FA | 0 | TRUE | FALSE | FALSE
1589 | MRT-YD00-P3LB-122056 | 2018-02-28 | MRT-DS-REC-TT-180135 | FA | 0 | TRUE | FALSE | FALSE
1590 | MRT-VN02-P2LB-122090 | 2018-02-28 | MRT-DS-REC-TT-180136 | FA | 0 | TRUE | FALSE | FALSE
1591 | MRT-YK00-P2LB-122072 | 2018-02-28 | MRT-DS-REC-TT-180136 | FA | 0 | TRUE | FALSE | FALSE
1592 | MRT-YM03-P2LB-122069 | 2018-02-28 | MRT-DS-REC-TT-180136 | FA | 0 | TRUE | FALSE | FALSE
1593 | MRT-YD00-P2LB-122108 | 2018-02-28 | MRT-DS-REC-TT-180136 | FA | 0 | TRUE | FALSE | FALSE
1594 | MRT-YD00-P3LB-122108 | 2018-02-28 | MRT-DS-REC-TT-180136 | FA | 0 | TRUE | FALSE | FALSE
1595 | MRT-YM03-P3LB-122069 | 2018-02-28 | MRT-DS-REC-TT-180136 | FA | 0 | TRUE | FALSE | FALSE
1596 | MRT-YK00-P3LB-122072 | 2018-02-28 | MRT-DS-REC-TT-180136 | FA | 0 | TRUE | FALSE | FALSE
1597 | MRT-VN02-P3LB-122090 | 2018-02-28 | MRT-DS-REC-TT-180136 | FA | 0 | TRUE | FALSE | FALSE
1598 | MRT-XH01-P0UZT-140000 | 2018-02-28 | MRT-DS-REC-TT-180140 | FA | 0 | TRUE | FALSE | FALSE
1599 | MRT-XK00-P0ZEN-140001 | 2018-02-28 | MRT-DS-REC-TT-180141 | FA | 0 | TRUE | FALSE | FALSE
1614 | MRT-CA00-P0USG-186863 | 2018-02-28 | MRT-HK-REC-TT-180063 | FA | 0 | TRUE | TRUE | FALSE
1615 | MRT-CA00-P0USG-186857 | 2018-02-28 | MRT-HK-REC-TT-180063 | FA | 0 | TRUE | TRUE | FALSE
1616 | MRT-CA00-P0UGA-186624 | 2018-02-28 | MRT-HK-REC-TT-180063 | FA | 0 | TRUE | TRUE | FALSE
1617 | MRT-CA06-P0USG-186851 | 2018-02-28 | MRT-HK-REC-TT-180063 | FA | 0 | TRUE | TRUE | FALSE
1618 | MRT-CA01-P0USG-186852 | 2018-02-28 | MRT-HK-REC-TT-180063 | FA | 0 | TRUE | TRUE | FALSE
1619 | MRT-CA00-P0USG-186858 | 2018-02-28 | MRT-HK-REC-TT-180063 | FA | 0 | TRUE | TRUE | FALSE
1620 | MRT-CA00-P0USG-186862 | 2018-02-28 | MRT-HK-REC-TT-180063 | FA | 0 | TRUE | TRUE | FALSE
1621 | MRT-CA00-P0USG-186864 | 2018-02-28 | MRT-HK-REC-TT-180063 | FA | 0 | TRUE | TRUE | FALSE
1837 | MRT-YR08-P0ABA-150034 | 2018-02-28 | MRT-HK-REC-TT-180062 | FA | 0 | TRUE | FALSE | FALSE
2111 | MRT-CC02-P0UPC-175787 | 2018-02-28 | MRT-HK-REC-TT-180060 | FA | 0 | TRUE | FALSE | FALSE
2112 | MRT-CC02-P0UPC-175786 | 2018-02-28 | MRT-HK-REC-TT-180060 | FA | 0 | TRUE | FALSE | FALSE
2113 | MRT-CC02-P0UPC-175783 | 2018-02-28 | MRT-HK-REC-TT-180060 | FA | 0 | TRUE | FALSE | FALSE
2114 | MRT-CC02-P0UPC-175781 | 2018-02-28 | MRT-HK-REC-TT-180060 | FA | 0 | TRUE | FALSE | FALSE
2115 | MRT-CC07-P0UPC-175792 | 2018-02-28 | MRT-HK-REC-TT-180060 | FA | 0 | TRUE | FALSE | FALSE
2116 | MRT-CC07-P0UPC-175791 | 2018-02-28 | MRT-HK-REC-TT-180060 | FA | 0 | TRUE | FALSE | FALSE
1622 | MRT-CA06-P0UGA-186601 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1623 | MRT-CA06-P0UGA-186599 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1624 | MRT-CA01-P0UGA-186603 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1625 | MRT-CA00-P0UGX-186963 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1626 | MRT-CA00-P0UGX-186961 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1627 | MRT-CA00-P0UGA-186625 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1628 | MRT-CA00-P0UGA-186617 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1629 | MRT-CA00-P0UGA-186616 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1630 | MRT-CA00-P0UGA-186614 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1631 | MRT-CA00-P0UGA-186613 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1632 | MRT-CA00-P0UGA-186612 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1633 | MRT-CA00-P0UGA-186611 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1634 | MRT-CA00-P0UGX-186957 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1635 | MRT-CA06-P0UGA-186600 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1636 | MRT-CA01-P0UGA-186602 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1637 | MRT-CA00-P0UGA-186610 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1638 | MRT-CA00-P0UGA-186615 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1639 | MRT-CA01-P0UGX-186722 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1640 | MRT-CA06-P0UGX-186951 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1641 | MRT-CA01-P0UGX-186952 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1642 | MRT-CA00-P0UGX-186956 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1643 | MRT-CA00-P0UGX-186960 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1644 | MRT-CA00-P0UGX-186966 | 2018-03-01 | MRT-HK-REC-TT-180064 | FA | 0 | TRUE | TRUE | FALSE
1645 | MRT-CC02-P0ULY-176108 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1646 | MRT-CC02-P0ULY-176107 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1647 | MRT-CC02-P0ULY-176106 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1648 | MRT-CA00-P0UST-186917 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1649 | MRT-CA00-P0UST-186911 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1650 | MRT-CA00-P0UST-186909 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1651 | MRT-CA00-P0UPB-187009 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1652 | MRT-CA00-P0UPB-187007 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1653 | MRT-CC07-P0ULY-176101 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1654 | MRT-CC02-P0ULY-176105 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1655 | MRT-CA01-P0UST-186902 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1656 | MRT-CA00-P0UST-186906 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1657 | MRT-CA00-P0UST-186912 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1658 | MRT-CA00-P0UST-186914 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1659 | MRT-CA06-P0UPB-187001 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1660 | MRT-CA01-P0UPB-187002 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1661 | MRT-CA00-P0UPB-187006 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1662 | MRT-CA00-P0UPB-187012 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1663 | MRT-CA00-P0UPB-187014 | 2018-03-01 | MRT-HK-REC-TT-180065 | FA | 0 | TRUE | TRUE | FALSE
1664 | MRT-HM05-P00SA-135504 | 2018-03-01 | MRT-HK-REC-TT-180066 | FA | 0 | TRUE | TRUE | FALSE
1665 | MRT-HM01-P0SAK-135565 | 2018-03-01 | MRT-HK-REC-TT-180067 | FA | 0 | TRUE | TRUE | FALSE
1666 | MRT-HM01-P0SAK-135564 | 2018-03-01 | MRT-HK-REC-TT-180067 | FA | 0 | TRUE | TRUE | FALSE
1667 | MRT-HM01-P00SA-135573 | 2018-03-01 | MRT-HK-REC-TT-180067 | FA | 0 | TRUE | TRUE | FALSE
1668 | MRT-HM01-P00SA-135572 | 2018-03-01 | MRT-HK-REC-TT-180067 | FA | 0 | TRUE | TRUE | FALSE
1669 | MRT-HM01-P00SA-135571 | 2018-03-01 | MRT-HK-REC-TT-180067 | FA | 0 | TRUE | TRUE | FALSE
1670 | MRT-HM01-P00SA-135568 | 2018-03-01 | MRT-HK-REC-TT-180067 | FA | 0 | TRUE | TRUE | FALSE
1671 | MRT-HM01-P00SA-135566 | 2018-03-01 | MRT-HK-REC-TT-180067 | FA | 0 | TRUE | TRUE | FALSE
1672 | MRT-HM01-P00SA-135563 | 2018-03-01 | MRT-HK-REC-TT-180067 | FA | 0 | TRUE | TRUE | FALSE
1673 | MRT-XW03-P0BBT-150009 | 2018-03-02 | MRT-HK-REC-TT-180068 | FA | 0 | TRUE | TRUE | FALSE
1674 | MRT-YU02-P0ABA-150026 | 2018-03-02 | MRT-HK-REC-TT-180068 | FA | 1 | TRUE | TRUE | FALSE
1600 | MRT-YD00-P2ZEN-113300 | 2018-03-05 | MRT-DS-REC-TT-180142 | FA | 0 | TRUE | TRUE | FALSE
1601 | MRT-YT01-P2ZEN-113301 | 2018-03-05 | MRT-DS-REC-TT-180142 | FA | 0 | TRUE | TRUE | FALSE
1602 | MRT-YD00-P3ZEN-113300 | 2018-03-05 | MRT-DS-REC-TT-180142 | FA | 0 | TRUE | TRUE | FALSE
1603 | MRT-YT01-P3ZEN-113301 | 2018-03-05 | MRT-DS-REC-TT-180142 | FA | 0 | TRUE | TRUE | FALSE
1604 | MRT-YD00-P0SMM-128001 | 2018-03-05 | MRT-DS-REC-TT-180143 | FA | 1 | TRUE | TRUE | FALSE
1605 | MRT-YT01-P0SMM-128004 | 2018-03-05 | MRT-DS-REC-TT-180144 | FA | 1 | TRUE | TRUE | FALSE
1606 | MRT-XS00-P2LB-122037 | 2018-03-05 | MRT-DS-REC-TT-180145 | FI | 1 | TRUE | TRUE | FALSE
1607 | MRT-XS00-P3LB-122037 | 2018-03-05 | MRT-DS-REC-TT-180145 | FI | 0 | TRUE | TRUE | FALSE
1608 | MRT-DP00-P0ZEN-070001 | 2018-03-05 | MRT-DS-REC-TT-180146 | FA | 2 | TRUE | TRUE | FALSE
1609 | MRT-XG07-P3PA-110304 | 2018-03-05 | MRT-DS-REC-TT-180147 | FC | 3 | TRUE | TRUE | FALSE
1610 | MRT-YT01-P2PGB-113200 | 2018-03-05 | MRT-DS-REC-TT-180148 | FA | 1 | TRUE | TRUE | FALSE
1611 | MRT-YD00-P2PGB-113201 | 2018-03-05 | MRT-DS-REC-TT-180148 | FI | 1 | TRUE | TRUE | FALSE
1612 | MRT-YT01-P3PGB-113200 | 2018-03-05 | MRT-DS-REC-TT-180148 | FA | 1 | TRUE | TRUE | FALSE
1613 | MRT-YD00-P3PGB-113201 | 2018-03-05 | MRT-DS-REC-TT-180148 | FI | 1 | TRUE | TRUE | FALSE
1675 | MRT-XW03-P3GHD-120001 | 2018-03-06 | MRT-DS-REC-TT-180149 | FC | 2 | TRUE | TRUE | FALSE
1676 | MRT-CA00-P0UCA-180106 | 2018-03-06 | MRT-DS-REC-TT-180150 | FC | 2 | TRUE | TRUE | FALSE
1677 | MRT-CA00-P0UCA-180114 | 2018-03-06 | MRT-DS-REC-TT-180150 | FC | 2 | TRUE | TRUE | FALSE
1678 | MRT-CA00-P0UCA-180115 | 2018-03-06 | MRT-DS-REC-TT-180150 | FC | 2 | TRUE | TRUE | FALSE
1679 | MRT-CA00-P0UCA-180116 | 2018-03-06 | MRT-DS-REC-TT-180150 | FC | 2 | TRUE | TRUE | FALSE
1680 | MRT-CA00-P0UCA-180117 | 2018-03-06 | MRT-DS-REC-TT-180150 | FC | 2 | TRUE | TRUE | FALSE
1681 | MRT-YK01-P2LAC-126006 | 2018-03-06 | MRT-DS-REC-TT-180151 | FI | 0 | TRUE | TRUE | FALSE
1682 | MRT-YK01-P3LAC-126006 | 2018-03-06 | MRT-DS-REC-TT-180151 | FI | 0 | TRUE | TRUE | FALSE
1683 | MRT-YK01-P2LAC-126056 | 2018-03-06 | MRT-DS-REC-TT-180151 | FI | 0 | TRUE | TRUE | FALSE
1684 | MRT-YK01-P3LAC-126056 | 2018-03-06 | MRT-DS-REC-TT-180151 | FI | 0 | TRUE | TRUE | FALSE
1685 | MRT-XN00-P2QU-130029 | 2018-03-06 | MRT-DS-REC-TT-180152 | FI | 0 | TRUE | TRUE | FALSE
1686 | MRT-XN00-P3QU-130029 | 2018-03-06 | MRT-DS-REC-TT-180152 | FI | 0 | TRUE | TRUE | FALSE
1687 | MRT-YF02-P2QU-130027 | 2018-03-06 | MRT-DS-REC-TT-180153 | FA | 0 | TRUE | TRUE | FALSE
1688 | MRT-YL00-P2QU-130028 | 2018-03-06 | MRT-DS-REC-TT-180153 | FI | 0 | TRUE | TRUE | FALSE
1689 | MRT-YF02-P3QU-130027 | 2018-03-06 | MRT-DS-REC-TT-180153 | FA | 0 | TRUE | TRUE | FALSE
1690 | MRT-YL00-P3QU-130028 | 2018-03-06 | MRT-DS-REC-TT-180153 | FI | 0 | TRUE | TRUE | FALSE
1691 | MRT-YK08-P2MAJ-603200 | 2018-03-06 | MRT-DS-REC-TT-180155 | FA | 0 | TRUE | TRUE | FALSE
1692 | MRT-YK08-P3MAJ-604200 | 2018-03-06 | MRT-DS-REC-TT-180155 | FA | 0 | TRUE | TRUE | FALSE
1693 | MRT-YL00-P2MAJ-603207 | 2018-03-06 | MRT-DS-REC-TT-180156 | FA | 0 | TRUE | TRUE | FALSE
1694 | MRT-YL00-P3MAJ-604207 | 2018-03-06 | MRT-DS-REC-TT-180156 | FA | 0 | TRUE | TRUE | FALSE
1695 | MRT-QM00-P0H-040001 | 2018-03-06 | MRT-DS-REC-TT-180154 | FC | 2 | TRUE | TRUE | FALSE
1696 | MRT-QM00-P0H-040002 | 2018-03-06 | MRT-DS-REC-TT-180154 | FC | 2 | TRUE | TRUE | FALSE
1697 | MRT-YK10-P2PGB-113103 | 2018-03-07 | MRT-DS-REC-TT-180157 | FI | 0 | TRUE | TRUE | FALSE
1698 | MRT-YT01-P2PGB-113104 | 2018-03-07 | MRT-DS-REC-TT-180157 | FA | 0 | TRUE | TRUE | FALSE
1699 | MRT-YD00-P2PGB-113105 | 2018-03-07 | MRT-DS-REC-TT-180157 | FA | 0 | TRUE | TRUE | FALSE
1700 | MRT-YK10-P3PGB-113103 | 2018-03-07 | MRT-DS-REC-TT-180157 | FI | 0 | TRUE | TRUE | FALSE
1701 | MRT-YT01-P3PGB-113104 | 2018-03-07 | MRT-DS-REC-TT-180157 | FA | 0 | TRUE | TRUE | FALSE
1702 | MRT-YD00-P3PGB-113105 | 2018-03-07 | MRT-DS-REC-TT-180157 | FA | 0 | TRUE | TRUE | FALSE
1703 | MRT-YD00-P2BAC-150352 | 2018-03-07 | MRT-HK-REC-TT-180069 | FA | 0 | TRUE | TRUE | FALSE
1704 | MRT-XW03-P0BBT-150009 | 2018-03-07 | MRT-HK-REC-TT-180069 | FA | 0 | TRUE | TRUE | FALSE
1705 | MRT-XW03-P0ANA-150015 | 2018-03-07 | MRT-HK-REC-TT-180069 | FA | 1 | TRUE | TRUE | FALSE
1706 | MRT-XW03-P0BFA-150299 | 2018-03-07 | MRT-HK-REC-TT-180069 | FA | 0 | TRUE | TRUE | FALSE
1707 | MRT-XW03-P0BAA-150019 | 2018-03-07 | MRT-HK-REC-TT-180069 | FA | 0 | TRUE | TRUE | FALSE
1708 | MRT-XW03-P0BAA-150020 | 2018-03-07 | MRT-HK-REC-TT-180069 | FA | 0 | TRUE | TRUE | FALSE
1709 | MRT-YD00-P2BAC-150362 | 2018-03-07 | MRT-HK-REC-TT-180069 | FA | 0 | TRUE | TRUE | FALSE
1710 | MRT-YS01-P2BAC-150355 | 2018-03-07 | MRT-HK-REC-TT-180069 | FA | 0 | TRUE | TRUE | FALSE
1711 | MRT-YS01-P3BAC-150365 | 2018-03-07 | MRT-HK-REC-TT-180069 | FA | 0 | TRUE | TRUE | FALSE
8070 | MRT-YD00-P3BAC-150362 | 2018-03-07 | MRT-HK-REC-TT-180069 | FA | 0 | TRUE | FALSE | FALSE
1712 | MRT-CA07-P0ZEN-175018 | 2018-03-08 | MRT-HK-REC-TT-180077 | FA | 0 | TRUE | TRUE | FALSE
1713 | MRT-XG02-P3GC-135102 | 2018-03-08 | MRT-HK-REC-TT-180077 | FA | 2 | TRUE | TRUE | FALSE
1714 | MRT-XG02-P0GA-125201 | 2018-03-08 | MRT-HK-REC-TT-180077 | FA | 2 | TRUE | TRUE | FALSE
1715 | MRT-YT01-P2MAJ-603100 | 2018-03-08 | MRT-DS-REC-TT-180159 | FC | 2 | TRUE | TRUE | FALSE
1716 | MRT-XG02-P2MAJ-603101 | 2018-03-08 | MRT-DS-REC-TT-180159 | FA | 2 | TRUE | TRUE | FALSE
1717 | MRT-XN00-P2MAJ-603106 | 2018-03-08 | MRT-DS-REC-TT-180159 | FA | 2 | TRUE | TRUE | FALSE
1718 | MRT-YL00-P2MAJ-603107 | 2018-03-08 | MRT-DS-REC-TT-180159 | FA | 2 | TRUE | TRUE | FALSE
1719 | MRT-YT01-P3MAJ-604100 | 2018-03-08 | MRT-DS-REC-TT-180159 | FC | 2 | TRUE | TRUE | FALSE
1720 | MRT-XG02-P3MAJ-604101 | 2018-03-08 | MRT-DS-REC-TT-180159 | FA | 2 | TRUE | TRUE | FALSE
1721 | MRT-XN00-P3MAJ-604106 | 2018-03-08 | MRT-DS-REC-TT-180159 | FA | 2 | TRUE | TRUE | FALSE
1722 | MRT-YL00-P3MAJ-604107 | 2018-03-08 | MRT-DS-REC-TT-180159 | FA | 2 | TRUE | TRUE | FALSE
1781 | MRT-XW03-P0BBT-150013 | 2018-03-08 | MRT-HK-REC-TT-180071 | FA | 0 | TRUE | TRUE | FALSE
1782 | MRT-XW03-P0BAT-150005 | 2018-03-08 | MRT-HK-REC-TT-180071 | FA | 0 | TRUE | TRUE | FALSE
1783 | MRT-XW03-P0BFT-150010 | 2018-03-08 | MRT-HK-REC-TT-180071 | FA | 0 | TRUE | TRUE | FALSE
1784 | MRT-XW03-P0BAA-150018 | 2018-03-08 | MRT-HK-REC-TT-180071 | FA | 1 | TRUE | TRUE | FALSE
1723 | MRT-XS00-P2LB-122035 | 2018-03-09 | MRT-DS-REC-TT-180160 | FC | 2 | TRUE | TRUE | FALSE
1724 | MRT-XS00-P3LB-122035 | 2018-03-09 | MRT-DS-REC-TT-180160 | FA | 1 | TRUE | TRUE | FALSE
1725 | MRT-YD00-P0QHE-606001 | 2018-03-09 | MRT-DS-REC-TT-180158 | FA | 1 | TRUE | TRUE | FALSE
1726 | MRT-YD00-P2GHC-129001 | 2018-03-09 | MRT-DS-REC-TT-180161 | FA | 1 | TRUE | TRUE | FALSE
1727 | MRT-YD00-P3GHC-129001 | 2018-03-09 | MRT-DS-REC-TT-180161 | FA | 1 | TRUE | TRUE | FALSE
1728 | MRT-UE00-P2ZEN-100004 | 2018-03-09 | MRT-DS-REC-TT-180162 | FC | 3 | TRUE | TRUE | FALSE
1729 | MRT-UE00-P2ZEN-100005 | 2018-03-09 | MRT-DS-REC-TT-180162 | FA | 3 | TRUE | TRUE | FALSE
1730 | MRT-UE00-P2ZEN-100006 | 2018-03-09 | MRT-DS-REC-TT-180162 | FA | 3 | TRUE | TRUE | FALSE
1731 | MRT-UE00-P2ZEN-100007 | 2018-03-09 | MRT-DS-REC-TT-180162 | FC | 3 | TRUE | TRUE | FALSE
1732 | MRT-UE00-P2ZEN-100008 | 2018-03-09 | MRT-DS-REC-TT-180162 | FC | 3 | TRUE | TRUE | FALSE
1733 | MRT-UE00-P2ZEN-100009 | 2018-03-09 | MRT-DS-REC-TT-180162 | FA | 3 | TRUE | TRUE | FALSE
1734 | MRT-UE00-P3ZEN-100010 | 2018-03-09 | MRT-DS-REC-TT-180162 | FC | 3 | TRUE | TRUE | FALSE
1735 | MRT-UE00-P3ZEN-100011 | 2018-03-09 | MRT-DS-REC-TT-180162 | FC | 3 | TRUE | TRUE | FALSE
1736 | MRT-UE00-P3ZEN-100012 | 2018-03-09 | MRT-DS-REC-TT-180162 | FC | 3 | TRUE | TRUE | FALSE
1737 | MRT-UE00-P3ZEN-100013 | 2018-03-09 | MRT-DS-REC-TT-180162 | FC | 3 | TRUE | TRUE | FALSE
1738 | MRT-UE00-P3ZEN-100014 | 2018-03-09 | MRT-DS-REC-TT-180162 | FC | 3 | TRUE | TRUE | FALSE
1739 | MRT-UE00-P3ZEN-100015 | 2018-03-09 | MRT-DS-REC-TT-180162 | FA | 3 | TRUE | TRUE | FALSE
1740 | MRT-YK08-P2LAA-605102 | 2018-03-09 | MRT-DS-REC-TT-180163 | FI | 2 | TRUE | TRUE | FALSE
1741 | MRT-YK08-P3LAA-605502 | 2018-03-09 | MRT-DS-REC-TT-180163 | FI | 2 | TRUE | TRUE | FALSE
1742 | MRT-XW03-P2MAV-120001 | 2018-03-09 | MRT-DS-REC-TT-180170 | FA | 0 | TRUE | TRUE | FALSE
1743 | MRT-XW03-P3MAV-130001 | 2018-03-09 | MRT-DS-REC-TT-180170 | FA | 0 | TRUE | TRUE | FALSE
1744 | MRT-QM01-P0ZEN-040002 | 2018-03-09 | MRT-DS-REC-TT-180164 | FA | 4 | TRUE | TRUE | FALSE
1745 | MRT-YK08-P2MAG-601001 | 2018-03-09 | MRT-DS-REC-TT-180165 | FA | 2 | TRUE | TRUE | FALSE
1746 | MRT-YK08-P3MAG-602001 | 2018-03-09 | MRT-DS-REC-TT-180165 | FA | 2 | TRUE | TRUE | FALSE
1747 | MRT-YK08-P2MAG-601002 | 2018-03-09 | MRT-DS-REC-TT-180166 | FA | 2 | TRUE | TRUE | FALSE
1748 | MRT-XL00-P2MAG-601003 | 2018-03-09 | MRT-DS-REC-TT-180166 | FI | 2 | TRUE | TRUE | FALSE
1749 | MRT-XL00-P2MAG-601004 | 2018-03-09 | MRT-DS-REC-TT-180166 | FI | 2 | TRUE | TRUE | FALSE
1750 | MRT-YK08-P3MAG-602002 | 2018-03-09 | MRT-DS-REC-TT-180166 | FA | 2 | TRUE | TRUE | FALSE
1751 | MRT-XL00-P3MAG-602003 | 2018-03-09 | MRT-DS-REC-TT-180166 | FI | 2 | TRUE | TRUE | FALSE
1752 | MRT-XL00-P3MAG-602004 | 2018-03-09 | MRT-DS-REC-TT-180166 | FI | 2 | TRUE | TRUE | FALSE
1753 | MRT-VL00-P2MAG-601005 | 2018-03-09 | MRT-DS-REC-TT-180168 | FC | 2 | TRUE | TRUE | FALSE
1754 | MRT-VL00-P2MAG-601006 | 2018-03-09 | MRT-DS-REC-TT-180168 | FC | 2 | TRUE | TRUE | FALSE
1755 | MRT-VL00-P3MAG-602005 | 2018-03-09 | MRT-DS-REC-TT-180168 | FC | 2 | TRUE | TRUE | FALSE
1756 | MRT-VL00-P3MAG-602006 | 2018-03-09 | MRT-DS-REC-TT-180168 | FC | 2 | TRUE | TRUE | FALSE
1757 | MRT-YT01-P2MAG-601007 | 2018-03-09 | MRT-DS-REC-TT-180167 | FA | 2 | TRUE | TRUE | FALSE
1758 | MRT-YT01-P2MAG-601008 | 2018-03-09 | MRT-DS-REC-TT-180167 | FI | 2 | TRUE | TRUE | FALSE
1759 | MRT-YT01-P3MAG-602007 | 2018-03-09 | MRT-DS-REC-TT-180167 | FA | 2 | TRUE | TRUE | FALSE
1760 | MRT-YT01-P3MAG-602008 | 2018-03-09 | MRT-DS-REC-TT-180167 | FI | 2 | TRUE | TRUE | FALSE
1761 | MRT-YF01-P0CYA-150122 | 2018-03-09 | MRT-HK-REC-TT-180072 | FA | 0 | TRUE | TRUE | FALSE
1785 | MRT-P0ZEN-DD08-075000 | 2018-03-10 | MRT-HK-REC-TT-180074 | FA | 0 | TRUE | TRUE | FALSE
1762 | MRT-XG02-P2PAH-604102 | 2018-03-12 | MRT-DS-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
1763 | MRT-YK08-P2PAH-604103 | 2018-03-12 | MRT-DS-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
1764 | MRT-YK08-P2PAH-604104 | 2018-03-12 | MRT-DS-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
1765 | MRT-XG02-P2PBB-604112 | 2018-03-12 | MRT-DS-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
1766 | MRT-YK08-P2PBB-604113 | 2018-03-12 | MRT-DS-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
1767 | MRT-XG02-P3PAH-604502 | 2018-03-12 | MRT-DS-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
1768 | MRT-YK08-P3PAH-604503 | 2018-03-12 | MRT-DS-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
1769 | MRT-YK08-P3PAH-604504 | 2018-03-12 | MRT-DS-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
1770 | MRT-XG02-P3PBB-604512 | 2018-03-12 | MRT-DS-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
1771 | MRT-YK08-P3PBB-604513 | 2018-03-12 | MRT-DS-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
1772 | MRT-YT01-P2PAH-604101 | 2018-03-12 | MRT-DS-REC-TT-180172 | FA | 1 | TRUE | TRUE | FALSE
1773 | MRT-YT01-P2PBB-604111 | 2018-03-12 | MRT-DS-REC-TT-180172 | FA | 1 | TRUE | TRUE | FALSE
1774 | MRT-YT01-P3PAH-604501 | 2018-03-12 | MRT-DS-REC-TT-180172 | FA | 1 | TRUE | TRUE | FALSE
1775 | MRT-YT01-P3PBB-604511 | 2018-03-12 | MRT-DS-REC-TT-180172 | FA | 1 | TRUE | TRUE | FALSE
1776 | MRT-YT01-P2MKA-240001 | 2018-03-12 | MRT-DS-REC-TT-180173 | FI | 0 | TRUE | TRUE | FALSE
1777 | MRT-YT01-P3MKA-240001 | 2018-03-12 | MRT-DS-REC-TT-180173 | FI | 0 | TRUE | TRUE | FALSE
1778 | MRT-CH05-P0ZEN-040001 | 2018-03-12 | MRT-DS-REC-TT-180169 | FI | 0 | TRUE | TRUE | FALSE
1779 | MRT-XN00-P2QC-130008 | 2018-03-12 | MRT-DS-REC-TT-180174 | FI | 0 | TRUE | TRUE | FALSE
1780 | MRT-XN00-P3QC-130008 | 2018-03-12 | MRT-DS-REC-TT-180174 | FI | 0 | TRUE | TRUE | FALSE
1786 | MRT-XJ00-P2PAB-142100 | 2018-03-12 | MRT-DS-REC-TT-180175 | FI | 0 | TRUE | TRUE | FALSE
1787 | MRT-XJ00-P3PAB-143100 | 2018-03-12 | MRT-DS-REC-TT-180175 | FI | 0 | TRUE | TRUE | FALSE
1788 | MRT-XJ00-P3PAB-144100 | 2018-03-12 | MRT-DS-REC-TT-180175 | FI | 0 | TRUE | TRUE | FALSE
1789 | MRT-YL00-P2QC-130007 | 2018-03-13 | MRT-DS-REC-TT-180179 | FI | 0 | TRUE | TRUE | FALSE
1790 | MRT-YL00-P3QC-130007 | 2018-03-13 | MRT-DS-REC-TT-180179 | FI | 0 | TRUE | TRUE | FALSE
1791 | MRT-XW01-P0ZEN-161001 | 2018-03-13 | MRT-DS-REC-TT-180180 | FC | 4 | TRUE | TRUE | FALSE
1792 | MRT-YB03-P3LB-122048 | 2018-03-14 | MRT-DS-REC-TT-180176 | FC | 1 | TRUE | TRUE | FALSE
1793 | MRT-UE00-P2LB-122008 | 2018-03-14 | MRT-DS-REC-TT-180177 | FC | 2 | TRUE | TRUE | FALSE
1794 | MRT-UE00-P3LB-122008 | 2018-03-14 | MRT-DS-REC-TT-180177 | FC | 1 | TRUE | TRUE | FALSE
1795 | MRT-YD00-P2LAC-126007 | 2018-03-14 | MRT-DS-REC-TT-180181 | FI | 0 | TRUE | TRUE | FALSE
1796 | MRT-YD00-P3LAC-126007 | 2018-03-14 | MRT-DS-REC-TT-180181 | FI | 0 | TRUE | TRUE | FALSE
1797 | MRT-YD00-P2LAC-126057 | 2018-03-14 | MRT-DS-REC-TT-180181 | FI | 0 | TRUE | TRUE | FALSE
1798 | MRT-YD00-P3LAC-126057 | 2018-03-14 | MRT-DS-REC-TT-180181 | FI | 0 | TRUE | TRUE | FALSE
1799 | MRT-YK08-P2MAJ-603102 | 2018-03-14 | MRT-DS-REC-TT-180182 | FC | 2 | TRUE | TRUE | FALSE
1800 | MRT-YT01-P2MAJ-603103 | 2018-03-14 | MRT-DS-REC-TT-180182 | FC | 2 | TRUE | TRUE | FALSE
1801 | MRT-YK08-P3MAJ-604102 | 2018-03-14 | MRT-DS-REC-TT-180182 | FC | 2 | TRUE | TRUE | FALSE
1802 | MRT-YT01-P3MAJ-604103 | 2018-03-14 | MRT-DS-REC-TT-180182 | FC | 2 | TRUE | TRUE | FALSE
1803 | MRT-YL00-P2MAJ-603105 | 2018-03-14 | MRT-DS-REC-TT-180183 | FA | 2 | TRUE | TRUE | FALSE
1804 | MRT-YL00-P3MAJ-604105 | 2018-03-14 | MRT-DS-REC-TT-180183 | FA | 2 | TRUE | TRUE | FALSE
1805 | MRT-YD00-P2PAB-113251 | 2018-03-14 | MRT-DS-REC-TT-180184 | FA | 0 | TRUE | TRUE | FALSE
1806 | MRT-YT01-P2PAB-113252 | 2018-03-14 | MRT-DS-REC-TT-180184 | FA | 0 | TRUE | TRUE | FALSE
1807 | MRT-XG02-P2PAB-113253 | 2018-03-14 | MRT-DS-REC-TT-180184 | FA | 0 | TRUE | TRUE | FALSE
1808 | MRT-YD00-P3PAB-113251 | 2018-03-14 | MRT-DS-REC-TT-180184 | FA | 0 | TRUE | TRUE | FALSE
1809 | MRT-YT01-P3PAB-113252 | 2018-03-14 | MRT-DS-REC-TT-180184 | FA | 0 | TRUE | TRUE | FALSE
1810 | MRT-XG02-P3PAB-113253 | 2018-03-14 | MRT-DS-REC-TT-180184 | FA | 0 | TRUE | TRUE | FALSE
1811 | MRT-XB00-P2SCA-127509 | 2018-03-15 | MRT-DS-REC-TT-180185 | FA | 0 | TRUE | TRUE | FALSE
1812 | MRT-YD00-P2LCB-127501 | 2018-03-15 | MRT-DS-REC-TT-180185 | FA | 0 | TRUE | TRUE | FALSE
1813 | MRT-XB00-P3SCA-127509 | 2018-03-15 | MRT-DS-REC-TT-180185 | FA | 0 | TRUE | TRUE | FALSE
1814 | MRT-YD00-P3LCB-127501 | 2018-03-15 | MRT-DS-REC-TT-180185 | FA | 0 | TRUE | TRUE | FALSE
1815 | MRT-CA05-P0UMA-180061 | 2018-03-15 | MRT-DS-REC-TT-180178 | FA | 2 | TRUE | TRUE | FALSE
1816 | MRT-CA05-P0UMA-180062 | 2018-03-15 | MRT-DS-REC-TT-180178 | FA | 2 | TRUE | TRUE | FALSE
1817 | MRT-YD00-P2MKA-220004 | 2018-03-15 | MRT-DS-REC-TT-180186 | FI | 0 | TRUE | TRUE | FALSE
1818 | MRT-YD00-P3MKA-220004 | 2018-03-15 | MRT-DS-REC-TT-180186 | FI | 0 | TRUE | TRUE | FALSE
1819 | MRT-DM02-P2MKA-220001 | 2018-03-15 | MRT-DS-REC-TT-180187 | FI | 0 | TRUE | TRUE | FALSE
1820 | MRT-DM02-P3MKA-220001 | 2018-03-15 | MRT-DS-REC-TT-180187 | FI | 0 | TRUE | TRUE | FALSE
1821 | MRT-YT01-P2GHC-129002 | 2018-03-15 | MRT-DS-REC-TT-180188 | FA | 1 | TRUE | TRUE | FALSE
1822 | MRT-YT01-P3GHC-129002 | 2018-03-15 | MRT-DS-REC-TT-180188 | FA | 1 | TRUE | TRUE | FALSE
1823 | MRT-YT01-P2LAC-126005 | 2018-03-15 | MRT-DS-REC-TT-180189 | FA | 0 | TRUE | TRUE | FALSE
1824 | MRT-YT01-P3LAC-126005 | 2018-03-15 | MRT-DS-REC-TT-180189 | FA | 0 | TRUE | TRUE | FALSE
1825 | MRT-YT01-P2LAC-126055 | 2018-03-15 | MRT-DS-REC-TT-180189 | FA | 0 | TRUE | TRUE | FALSE
1826 | MRT-YT01-P3LAC-126055 | 2018-03-15 | MRT-DS-REC-TT-180189 | FA | 0 | TRUE | TRUE | FALSE
1827 | MRT-YK10-P3MKA-220003 | 2018-03-16 | MRT-DS-REC-TT-180191 | FI | 0 | TRUE | TRUE | FALSE
1828 | MRT-DM01-P3MKA-220001 | 2018-03-16 | MRT-DS-REC-TT-180191 | FI | 0 | TRUE | TRUE | FALSE
1829 | MRT-XJ00-P2MKJ-220001 | 2018-03-16 | MRT-DS-REC-TT-180192 | FA | 0 | TRUE | TRUE | FALSE
1830 | MRT-XA01-P0ABA-150503 | 2018-03-16 | MRT-HK-REC-TT-180075 | FA | 0 | TRUE | TRUE | FALSE
1831 | MRT-XA01-P0ABA-150502 | 2018-03-16 | MRT-HK-REC-TT-180075 | FA | 0 | TRUE | TRUE | FALSE
1832 | MRT-XW03-P0ASR-150196 | 2018-03-16 | MRT-HK-REC-TT-180075 | FA | 0 | TRUE | TRUE | FALSE
1833 | MRT-YK08-P2ZEN-111200 | 2018-03-19 | MRT-DS-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
1834 | MRT-YT01-P2ZEN-111201 | 2018-03-19 | MRT-DS-REC-TT-180194 | FA | 0 | TRUE | TRUE | FALSE
1835 | MRT-YK08-P3ZEN-111200 | 2018-03-19 | MRT-DS-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
1836 | MRT-YT01-P3ZEN-111201 | 2018-03-19 | MRT-DS-REC-TT-180194 | FA | 0 | TRUE | TRUE | FALSE
1838 | MRT-QM01-P0ZEN-040001 | 2018-03-20 | MRT-DS-REC-TT-180193 | FA | 2 | TRUE | TRUE | FALSE
1839 | MRT-XB02-P2LB-122022 | 2018-03-20 | MRT-DS-REC-TT-180199 | FI | 0 | TRUE | FALSE | FALSE
1840 | MRT-XH01-P2MKJ-220001 | 2018-03-20 | MRT-DS-REC-TT-180201 | FA | 0 | TRUE | FALSE | FALSE
1841 | MRT-XK00-P2MKJ-220001 | 2018-03-20 | MRT-DS-REC-TT-180201 | FA | 0 | TRUE | FALSE | FALSE
1842 | MRT-UE00-P2LB-122010 | 2018-03-21 | MRT-DS-REC-TT-180195 | FC | 2 | TRUE | TRUE | FALSE
1843 | MRT-UE00-P3LB-122010 | 2018-03-21 | MRT-DS-REC-TT-180195 | FC | 2 | TRUE | TRUE | FALSE
1844 | MRT-XB02-P2LB-122018 | 2018-03-21 | MRT-DS-REC-TT-180196 | FC | 3 | TRUE | TRUE | FALSE
1845 | MRT-XB02-P3LB-122018 | 2018-03-21 | MRT-DS-REC-TT-180196 | FC | 2 | TRUE | TRUE | FALSE
1846 | MRT-UE00-P2LB-122007 | 2018-03-21 | MRT-DS-REC-TT-180197 | FC | 2 | TRUE | TRUE | FALSE
1847 | MRT-UE00-P3LB-122007 | 2018-03-21 | MRT-DS-REC-TT-180197 | FC | 1 | TRUE | TRUE | FALSE
1848 | MRT-YK00-P2LB-122072 | 2018-03-21 | MRT-DS-REC-TT-180198 | FC | 1 | TRUE | TRUE | FALSE
1849 | MRT-YK00-P3LB-122072 | 2018-03-21 | MRT-DS-REC-TT-180198 | FC | 1 | TRUE | TRUE | FALSE
1850 | MRT-YK09-P2GHC-129003 | 2018-03-21 | MRT-DS-REC-TT-180190 | FI | 0 | TRUE | FALSE | FALSE
1851 | MRT-YK09-P3GHC-129003 | 2018-03-21 | MRT-DS-REC-TT-180190 | FI | 0 | TRUE | FALSE | FALSE
1852 | MRT-QM01-P0ZEN-045001 | 2018-03-21 | MRT-HK-REC-TT-180077 | FA | 0 | TRUE | FALSE | FALSE
1853 | MRT-XJ00-P2LB-122027 | 2018-03-21 | MRT-DS-REC-TT-180208 | FI | 0 | TRUE | FALSE | FALSE
1854 | MRT-XJ00-P3LB-122027 | 2018-03-21 | MRT-DS-REC-TT-180208 | FI | 0 | TRUE | FALSE | FALSE
1855 | MRT-YK08-P2MKJ-220001 | 2018-03-21 | MRT-DS-REC-TT-180210 | FA | 0 | TRUE | FALSE | FALSE
1856 | MRT-YK08-P3MKA-220001 | 2018-03-21 | MRT-DS-REC-TT-180210 | FA | 0 | TRUE | FALSE | FALSE
1857 | MRT-YK10-P2MKA-220001 | 2018-03-21 | MRT-DS-REC-TT-180211 | FI | 0 | TRUE | FALSE | FALSE
1858 | MRT-YK10-P2MKA-220002 | 2018-03-21 | MRT-DS-REC-TT-180211 | FI | 0 | TRUE | FALSE | FALSE
1859 | MRT-YK10-P3MKA-220001 | 2018-03-21 | MRT-DS-REC-TT-180211 | FI | 0 | TRUE | FALSE | FALSE
1860 | MRT-YK10-P3MKA-220002 | 2018-03-21 | MRT-DS-REC-TT-180211 | FI | 0 | TRUE | FALSE | FALSE
1861 | MRT-YT01-P2PGB-113200 | 2018-03-21 | MRT-DS-REC-TT-180212 | FC | 2 | TRUE | TRUE | FALSE
1862 | MRT-YT01-P3PGB-113200 | 2018-03-21 | MRT-DS-REC-TT-180212 | FC | 2 | TRUE | TRUE | FALSE
1863 | MRT-MA02-P2ZEN-161015 | 2018-03-21 | MRT-DS-REC-TT-180200 | FC | 2 | TRUE | TRUE | FALSE
1864 | MRT-MA02-P3ZEN-161015 | 2018-03-21 | MRT-DS-REC-TT-180200 | FC | 2 | TRUE | TRUE | FALSE
1865 | MRT-MA01-P2ZEN-161011 | 2018-03-21 | MRT-DS-REC-TT-180200 | FC | 3 | TRUE | TRUE | FALSE
1866 | MRT-MA01-P3ZEN-161011 | 2018-03-21 | MRT-DS-REC-TT-180200 | FC | 3 | TRUE | TRUE | FALSE
1867 | MRT-XG02-P0GN-135202 | 2018-03-22 | MRT-HK-REC-TT-180078 | FA | 3 | TRUE | TRUE | FALSE
1868 | MRT-CC07-P0UZT-175990 | 2018-03-22 | MRT-HK-REC-TT-180079 | FA | 0 | TRUE | FALSE | FALSE
1869 | MRT-CC02-P0UZT-175991 | 2018-03-22 | MRT-HK-REC-TT-180079 | FA | 0 | TRUE | FALSE | FALSE
1870 | MRT-YM01-P2GHC-129008 | 2018-03-22 | MRT-DS-REC-TT-180204 | FA | 0 | TRUE | FALSE | FALSE
1871 | MRT-YM01-P3GHC-129008 | 2018-03-22 | MRT-DS-REC-TT-180204 | FA | 0 | TRUE | FALSE | FALSE
1872 | MRT-CC07-P2UHA-170001 | 2018-03-22 | MRT-DS-REC-TT-180202 | FC | 3 | TRUE | TRUE | FALSE
1873 | MRT-CC02-P2UHA-170003 | 2018-03-22 | MRT-DS-REC-TT-180202 | FC | 4 | TRUE | TRUE | FALSE
1874 | MRT-CC02-P2UHA-170004 | 2018-03-22 | MRT-DS-REC-TT-180202 | FC | 4 | TRUE | TRUE | FALSE
1875 | MRT-CC07-P3UHA-170001 | 2018-03-22 | MRT-DS-REC-TT-180202 | FC | 3 | TRUE | TRUE | FALSE
1876 | MRT-CC02-P3UHA-170003 | 2018-03-22 | MRT-DS-REC-TT-180202 | FC | 4 | TRUE | TRUE | FALSE
1877 | MRT-CC02-P3UHA-170004 | 2018-03-22 | MRT-DS-REC-TT-180202 | FC | 4 | TRUE | TRUE | FALSE
1878 | MRT-CC02-P0UHA-170002 | 2018-03-22 | MRT-DS-REC-TT-180202 | FC | 4 | TRUE | TRUE | FALSE
1879 | MRT-CC07-P2UHA-170005 | 2018-03-22 | MRT-DS-REC-TT-180203 | FC | 2 | TRUE | TRUE | FALSE
1880 | MRT-CC02-P2UHA-170007 | 2018-03-22 | MRT-DS-REC-TT-180203 | FC | 2 | TRUE | TRUE | FALSE
1881 | MRT-CC02-P2UHA-170008 | 2018-03-22 | MRT-DS-REC-TT-180203 | FC | 2 | TRUE | TRUE | FALSE
1882 | MRT-CC02-P2UHA-170009 | 2018-03-22 | MRT-DS-REC-TT-180203 | FC | 2 | TRUE | TRUE | FALSE
1883 | MRT-VK02-P2UHA-170010 | 2018-03-22 | MRT-DS-REC-TT-180203 | FC | 2 | TRUE | TRUE | FALSE
1884 | MRT-CC07-P3UHA-170005 | 2018-03-22 | MRT-DS-REC-TT-180203 | FC | 2 | TRUE | TRUE | FALSE
1885 | MRT-CC02-P3UHA-170007 | 2018-03-22 | MRT-DS-REC-TT-180203 | FC | 2 | TRUE | TRUE | FALSE
1886 | MRT-CC02-P3UHA-170008 | 2018-03-22 | MRT-DS-REC-TT-180203 | FC | 2 | TRUE | TRUE | FALSE
1887 | MRT-CC02-P3UHA-170009 | 2018-03-22 | MRT-DS-REC-TT-180203 | FC | 2 | TRUE | TRUE | FALSE
1888 | MRT-VK02-P3UHA-170010 | 2018-03-22 | MRT-DS-REC-TT-180203 | FC | 2 | TRUE | TRUE | FALSE
1889 | MRT-VK02-P2UMA-170210 | 2018-03-22 | MRT-DS-REC-TT-180207 | FC | 1 | TRUE | TRUE | FALSE
1890 | MRT-YR05-P0ZEN-161016 | 2018-03-22 | MRT-DS-REC-TT-180206 | FC | 2 | TRUE | TRUE | FALSE
1891 | MRT-YF02-P2SCA-127514 | 2018-03-22 | MRT-DS-REC-TT-180209 | FC | 1 | TRUE | TRUE | FALSE
1892 | MRT-YF02-P3SCA-127514 | 2018-03-22 | MRT-DS-REC-TT-180209 | FC | 1 | TRUE | TRUE | FALSE
1893 | MRT-CC07-P2UMA-170701 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 2 | TRUE | TRUE | FALSE
1894 | MRT-CC02-P2UMA-170703 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 2 | TRUE | TRUE | FALSE
1895 | MRT-CC02-P2UMA-170707 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 2 | TRUE | TRUE | FALSE
1896 | MRT-CC02-P2UMA-170708 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 2 | TRUE | TRUE | FALSE
1897 | MRT-CC02-P2UMA-170709 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 2 | TRUE | TRUE | FALSE
1898 | MRT-VK02-P2UMA-170710 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 1 | TRUE | TRUE | FALSE
1899 | MRT-CC07-P3UMA-170701 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 2 | TRUE | TRUE | FALSE
1900 | MRT-CC02-P3UMA-170703 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 2 | TRUE | TRUE | FALSE
1901 | MRT-CC02-P3UMA-170707 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 2 | TRUE | TRUE | FALSE
1902 | MRT-CC02-P3UMA-170708 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 2 | TRUE | TRUE | FALSE
1903 | MRT-CC02-P3UMA-170709 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 2 | TRUE | TRUE | FALSE
1904 | MRT-VK02-P3UMA-170710 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 1 | TRUE | TRUE | FALSE
1905 | MRT-CC02-P0UMA-170702 | 2018-03-22 | MRT-DS-REC-TT-180213 | FC | 1 | TRUE | TRUE | FALSE
1906 | MRT-YV02-P2MAJ-603108 | 2018-03-22 | MRT-DS-REC-TT-180215 | FA | 1 | TRUE | TRUE | FALSE
1907 | MRT-YV02-P3MAJ-604108 | 2018-03-22 | MRT-DS-REC-TT-180215 | FA | 1 | TRUE | TRUE | FALSE
1908 | MRT-CA00-P0UCA-180119 | 2018-03-22 | MRT-DS-REC-TT-180216 | FA | 0 | TRUE | FALSE | FALSE
1909 | MRT-CA00-P0UCA-180120 | 2018-03-22 | MRT-DS-REC-TT-180216 | FA | 0 | TRUE | FALSE | FALSE
1910 | MRT-CC07-P2UMA-170501 | 2018-03-22 | MRT-DS-REC-TT-180219 | FC | 2 | TRUE | TRUE | FALSE
1911 | MRT-CC02-P2UMA-170503 | 2018-03-22 | MRT-DS-REC-TT-180219 | FC | 2 | TRUE | TRUE | FALSE
1912 | MRT-CC02-P2UMA-170507 | 2018-03-22 | MRT-DS-REC-TT-180219 | FC | 2 | TRUE | TRUE | FALSE
1913 | MRT-VK02-P2UMA-170510 | 2018-03-22 | MRT-DS-REC-TT-180219 | FC | 2 | TRUE | TRUE | FALSE
1914 | MRT-CC07-P3UMA-170501 | 2018-03-22 | MRT-DS-REC-TT-180219 | FC | 2 | TRUE | TRUE | FALSE
1915 | MRT-CC02-P3UMA-170503 | 2018-03-22 | MRT-DS-REC-TT-180219 | FC | 2 | TRUE | TRUE | FALSE
1916 | MRT-CC02-P3UMA-170507 | 2018-03-22 | MRT-DS-REC-TT-180219 | FC | 2 | TRUE | TRUE | FALSE
1917 | MRT-VK02-P3UMA-170510 | 2018-03-22 | MRT-DS-REC-TT-180219 | FC | 2 | TRUE | TRUE | FALSE
1918 | MRT-CC02-P0UMA-170502 | 2018-03-22 | MRT-DS-REC-TT-180219 | FC | 2 | TRUE | TRUE | FALSE
1919 | MRT-XG02-P2LB-122022 | 2018-03-23 | MRT-DS-REC-TT-180222 | FA | 4 | TRUE | TRUE | FALSE
1920 | MRT-XG02-P3LB-122022 | 2018-03-23 | MRT-DS-REC-TT-180222 | FA | 1 | TRUE | TRUE | FALSE
1921 | MRT-XL00-P2LB-122030 | 2018-03-23 | MRT-DS-REC-TT-180223 | FA | 2 | TRUE | TRUE | FALSE
1922 | MRT-XL00-P3LB-122030 | 2018-03-23 | MRT-DS-REC-TT-180223 | FA | 1 | TRUE | TRUE | FALSE
1923 | MRT-XB02-P2LB-122016 | 2018-03-23 | MRT-DS-REC-TT-180224 | FC | 2 | TRUE | TRUE | FALSE
1924 | MRT-XB02-P3LB-122016 | 2018-03-23 | MRT-DS-REC-TT-180224 | FC | 1 | TRUE | TRUE | FALSE
1925 | MRT-CC07-P2UMA-170601 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 2 | TRUE | TRUE | FALSE
1926 | MRT-CC02-P2UMA-170603 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 2 | TRUE | TRUE | FALSE
1927 | MRT-CC02-P2UMA-170607 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 2 | TRUE | TRUE | FALSE
1928 | MRT-CC02-P2UMA-170608 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 2 | TRUE | TRUE | FALSE
1929 | MRT-CC02-P2UMA-170609 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 2 | TRUE | TRUE | FALSE
1930 | MRT-VK02-P2UMA-170610 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 1 | TRUE | TRUE | FALSE
1931 | MRT-CC07-P3UMA-170601 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 2 | TRUE | TRUE | FALSE
1932 | MRT-CC02-P3UMA-170603 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 2 | TRUE | TRUE | FALSE
1933 | MRT-CC02-P3UMA-170607 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 2 | TRUE | TRUE | FALSE
1934 | MRT-CC02-P3UMA-170608 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 2 | TRUE | TRUE | FALSE
1935 | MRT-CC02-P3UMA-170609 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 2 | TRUE | TRUE | FALSE
1936 | MRT-VK02-P3UMA-170610 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 1 | TRUE | TRUE | FALSE
1937 | MRT-CC02-P0UMA-170602 | 2018-03-23 | MRT-DS-REC-TT-180221 | FC | 1 | TRUE | TRUE | FALSE
1938 | MRT-YE03-P2ZEN-163104 | 2018-03-23 | MRT-DS-REC-TT-180217 | FA | 0 | TRUE | FALSE | FALSE
1939 | MRT-MA02-P2ZEN-163105 | 2018-03-23 | MRT-DS-REC-TT-180217 | FA | 0 | TRUE | FALSE | FALSE
1940 | MRT-YD06-P2ZEN-163106 | 2018-03-23 | MRT-DS-REC-TT-180217 | FA | 0 | TRUE | FALSE | FALSE
1941 | MRT-CV03-P0ZEN-163107 | 2018-03-23 | MRT-DS-REC-TT-180217 | FA | 0 | TRUE | FALSE | FALSE
1942 | MRT-CV03-P0ZEN-163108 | 2018-03-23 | MRT-DS-REC-TT-180217 | FA | 0 | TRUE | FALSE | FALSE
1943 | MRT-YS00-P0ZEN-162101 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1944 | MRT-YS00-P0ZEN-162102 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1945 | MRT-YS00-P0ZEN-162103 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1946 | MRT-YS00-P0ZEN-162104 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1947 | MRT-YS00-P0ZEN-162105 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1948 | MRT-YS00-P0ZEN-162106 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1949 | MRT-YS00-P0ZEN-162107 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1950 | MRT-YS00-P0ZEN-162108 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1951 | MRT-YS00-P0ZEN-162109 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1952 | MRT-YS00-P0ZEN-162110 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1953 | MRT-YS00-P0ZEN-162111 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1954 | MRT-YS00-P0ZEN-162112 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1955 | MRT-YS00-P0ZEN-162113 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1956 | MRT-YS00-P0ZEN-162114 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1957 | MRT-YS00-P0ZEN-162115 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1958 | MRT-YS00-P0ZEN-162116 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1959 | MRT-YS00-P0ZEN-162117 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1960 | MRT-YS00-P0ZEN-162118 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1961 | MRT-YS00-P0ZEN-162119 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1962 | MRT-YS00-P0ZEN-162120 | 2018-03-23 | MRT-DS-REC-TT-180205 | FC | 3 | TRUE | TRUE | FALSE
1963 | MRT-XL00-P0ZEN-140001 | 2018-03-23 | MRT-DS-REC-TT-180225 | FC | 3 | TRUE | TRUE | FALSE
1964 | MRT-YF00-P2PAH-604121 | 2018-03-26 | MRT-DS-REC-TT-180229 | FC | 1 | TRUE | TRUE | FALSE
1965 | MRT-YV02-P2PAH-604122 | 2018-03-26 | MRT-DS-REC-TT-180229 | FC | 1 | TRUE | TRUE | FALSE
1966 | MRT-YB03-P2PAH-604123 | 2018-03-26 | MRT-DS-REC-TT-180229 | FA | 1 | TRUE | TRUE | FALSE
1967 | MRT-YK08-P2PAH-604124 | 2018-03-26 | MRT-DS-REC-TT-180229 | FC | 1 | TRUE | TRUE | FALSE
1968 | MRT-YF00-P3PAH-604521 | 2018-03-26 | MRT-DS-REC-TT-180230 | FC | 1 | TRUE | TRUE | FALSE
1969 | MRT-YV02-P3PAH-604522 | 2018-03-26 | MRT-DS-REC-TT-180230 | FC | 1 | TRUE | TRUE | FALSE
1970 | MRT-YB03-P3PAH-604523 | 2018-03-26 | MRT-DS-REC-TT-180230 | FA | 1 | TRUE | TRUE | FALSE
1971 | MRT-YK08-P3PAH-604524 | 2018-03-26 | MRT-DS-REC-TT-180230 | FC | 1 | TRUE | TRUE | FALSE
1972 | MRT-YK10-P2MKA-230003 | 2018-03-26 | MRT-DS-REC-TT-180227 | FI | 0 | TRUE | TRUE | FALSE
1973 | MRT-YK10-P2MKA-230004 | 2018-03-26 | MRT-DS-REC-TT-180227 | FI | 0 | TRUE | TRUE | FALSE
1974 | MRT-YK08-P0SMM-128001 | 2018-03-26 | MRT-DS-REC-TT-180232 | FI | 0 | TRUE | FALSE | FALSE
1975 | MRT-XV00-P2MAA-220036 | 2018-03-26 | MRT-DS-REC-TT-180220 | FA | 1 | TRUE | TRUE | FALSE
1976 | MRT-XV00-P3MAA-220036 | 2018-03-26 | MRT-DS-REC-TT-180220 | FA | 1 | TRUE | TRUE | FALSE
1977 | MRT-XV00-P2MAV-220037 | 2018-03-26 | MRT-DS-REC-TT-180228 | FA | 1 | TRUE | TRUE | FALSE
1978 | MRT-XV00-P3MAV-220037 | 2018-03-26 | MRT-DS-REC-TT-180228 | FA | 1 | TRUE | TRUE | FALSE
1979 | MRT-YE00-P2MKA-230002 | 2018-03-26 | MRT-DS-REC-TT-180231 | FA | 1 | TRUE | TRUE | FALSE
1980 | MRT-YE00-P3MKA-230002 | 2018-03-26 | MRT-DS-REC-TT-180231 | FA | 1 | TRUE | TRUE | FALSE
1981 | MRT-YF01-P2ZEN-161013 | 2018-03-27 | MRT-DS-REC-TT-180226 | FC | 3 | TRUE | TRUE | FALSE
1982 | MRT-YF01-P3ZEN-161013 | 2018-03-27 | MRT-DS-REC-TT-180226 | FC | 3 | TRUE | TRUE | FALSE
1983 | MRT-YD00-P2QHE-606003 | 2018-03-27 | MRT-DS-REC-TT-180214 | FA | 1 | TRUE | TRUE | FALSE
1984 | MRT-YD00-P3QHE-606003 | 2018-03-27 | MRT-DS-REC-TT-180214 | FA | 1 | TRUE | TRUE | FALSE
1985 | MRT-YD00-P2QC-130005 | 2018-03-27 | MRT-DS-REC-TT-180235 | FI | 0 | TRUE | FALSE | FALSE
1986 | MRT-YF02-P2QC-130006 | 2018-03-27 | MRT-DS-REC-TT-180235 | FA | 0 | TRUE | FALSE | FALSE
1987 | MRT-YD00-P3QC-130005 | 2018-03-27 | MRT-DS-REC-TT-180235 | FI | 0 | TRUE | FALSE | FALSE
1988 | MRT-YF02-P3QC-130006 | 2018-03-27 | MRT-DS-REC-TT-180235 | FA | 0 | TRUE | FALSE | FALSE
1989 | MRT-XB02-P0UMA-180004 | 2018-03-27 | MRT-DS-REC-TT-180236 | FC | 4 | TRUE | TRUE | FALSE
1990 | MRT-YU04-P0ZEN-161012 | 2018-03-27 | MRT-DS-REC-TT-180238 | FA | 3 | TRUE | TRUE | FALSE
1991 | MRT-YS18-P0SMM-128010 | 2018-03-27 | MRT-DS-REC-TT-180240 | FI | 0 | TRUE | FALSE | FALSE
1992 | MRT-XB02-P0UCA-180102 | 2018-03-27 | MRT-DS-REC-TT-180237 | FC | 4 | TRUE | TRUE | FALSE
1993 | MRT-YE03-P3ZEN-163104 | 2018-03-27 | MRT-DS-REC-TT-180239 | FA | 0 | TRUE | FALSE | FALSE
1994 | MRT-MA02-P3ZEN-163105 | 2018-03-27 | MRT-DS-REC-TT-180239 | FA | 0 | TRUE | FALSE | FALSE
1995 | MRT-YT01-P2LB-122096 | 2018-03-27 | MRT-DS-REC-TT-180241 | FI | 0 | TRUE | FALSE | FALSE
1996 | MRT-YT01-P2LB-122097 | 2018-03-27 | MRT-DS-REC-TT-180241 | FI | 0 | TRUE | FALSE | FALSE
1997 | MRT-YT02-P2LB-122094 | 2018-03-27 | MRT-DS-REC-TT-180241 | FI | 0 | TRUE | FALSE | FALSE
1998 | MRT-YT01-P2LB-122095 | 2018-03-27 | MRT-DS-REC-TT-180241 | FI | 0 | TRUE | FALSE | FALSE
1999 | MRT-YQ01-P2LB-122085 | 2018-03-27 | MRT-DS-REC-TT-180241 | FI | 0 | TRUE | FALSE | FALSE
2000 | MRT-YQ01-P3LB-122085 | 2018-03-27 | MRT-DS-REC-TT-180241 | FI | 0 | TRUE | FALSE | FALSE
2001 | MRT-YT02-P3LB-122094 | 2018-03-27 | MRT-DS-REC-TT-180241 | FI | 0 | TRUE | FALSE | FALSE
2002 | MRT-YT01-P3LB-122095 | 2018-03-27 | MRT-DS-REC-TT-180241 | FI | 0 | TRUE | FALSE | FALSE
2003 | MRT-YT01-P3LB-122096 | 2018-03-27 | MRT-DS-REC-TT-180241 | FI | 0 | TRUE | FALSE | FALSE
2004 | MRT-YT01-P3LB-122097 | 2018-03-27 | MRT-DS-REC-TT-180241 | FI | 0 | TRUE | FALSE | FALSE
2005 | MRT-YS00-P2LB-122092 | 2018-03-27 | MRT-DS-REC-TT-180242 | FA | 0 | TRUE | FALSE | FALSE
2006 | MRT-YS00-P3LB-122092 | 2018-03-27 | MRT-DS-REC-TT-180242 | FA | 0 | TRUE | FALSE | FALSE
2007 | MRT-YT01-P2LCB-127033 | 2018-03-27 | MRT-DS-REC-TT-180243 | FA | 0 | TRUE | FALSE | FALSE
2008 | MRT-YD00-P2LCB-127031 | 2018-03-27 | MRT-DS-REC-TT-180243 | FA | 0 | TRUE | FALSE | FALSE
2009 | MRT-YT01-P3LCB-127033 | 2018-03-27 | MRT-DS-REC-TT-180243 | FA | 0 | TRUE | FALSE | FALSE
2010 | MRT-YD00-P3LCB-127031 | 2018-03-27 | MRT-DS-REC-TT-180243 | FA | 0 | TRUE | FALSE | FALSE
2011 | MRT-XW01-P0ZEN-161001 | 2018-03-27 | MRT-DS-REC-TT-180218 | FA | 5 | TRUE | TRUE | FALSE
2012 | MRT-YU02-P2SCA-127510 | 2018-03-28 | MRT-DS-REC-TT-180244 | FA | 0 | TRUE | FALSE | FALSE
2013 | MRT-YU02-P3SCA-127510 | 2018-03-28 | MRT-DS-REC-TT-180244 | FA | 0 | TRUE | FALSE | FALSE
2014 | MRT-YK09-P2MKC-230001 | 2018-03-28 | MRT-DS-REC-TT-180246 | FA | 0 | TRUE | FALSE | FALSE
2015 | MRT-YK09-P3MKC-230001 | 2018-03-28 | MRT-DS-REC-TT-180246 | FA | 0 | TRUE | FALSE | FALSE
2016 | MRT-XB02-P2LB-122021 | 2018-03-28 | MRT-DS-REC-TT-180247 | FC | 2 | TRUE | TRUE | FALSE
2017 | MRT-QM00-P0H-040005 | 2018-03-29 | MRT-DS-REC-TT-180248 | FA | 0 | TRUE | FALSE | FALSE
2018 | MRT-YD00-P2PGB-113101 | 2018-03-29 | MRT-DS-REC-TT-180252 | FC | 1 | TRUE | TRUE | FALSE
2019 | MRT-YT01-P2PGB-113102 | 2018-03-29 | MRT-DS-REC-TT-180252 | FC | 1 | TRUE | TRUE | FALSE
2020 | MRT-YD00-P3PGB-113101 | 2018-03-29 | MRT-DS-REC-TT-180252 | FC | 1 | TRUE | TRUE | FALSE
2021 | MRT-YT01-P3PGB-113102 | 2018-03-29 | MRT-DS-REC-TT-180252 | FC | 1 | TRUE | TRUE | FALSE
2022 | MRT-YD00-P2MKA-220005 | 2018-03-30 | MRT-DS-REC-TT-180253 | FI | 0 | TRUE | FALSE | FALSE
2023 | MRT-QM01-P0ZEN-040002 | 2018-03-30 | MRT-DS-REC-TT-180254 | FC | 5 | TRUE | TRUE | FALSE
2024 | MRT-YK09-P2MKC-230003 | 2018-03-30 | MRT-DS-REC-TT-180251 | FA | 0 | TRUE | FALSE | FALSE
2025 | MRT-YK09-P3MKC-230003 | 2018-03-30 | MRT-DS-REC-TT-180251 | FA | 0 | TRUE | FALSE | FALSE
2026 | MRT-XW01-P2SCA-127503 | 2018-03-30 | MRT-DS-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
2027 | MRT-XW01-P3SCA-127503 | 2018-03-30 | MRT-DS-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
2028 | MRT-YD00-P2MKA-220001 | 2018-03-30 | MRT-DS-REC-TT-180249 | FI | 3 | TRUE | TRUE | FALSE
2029 | MRT-XB02-P2LB-122017 | 2018-03-30 | MRT-DS-REC-TT-180257 | FC | 3 | TRUE | TRUE | FALSE
2030 | MRT-XB02-P3LB-122017 | 2018-03-30 | MRT-DS-REC-TT-180257 | FC | 2 | TRUE | TRUE | FALSE
2031 | MRT-YD00-P2LB-122108 | 2018-03-30 | MRT-DS-REC-TT-180258 | FA | 1 | TRUE | TRUE | FALSE
2032 | MRT-YD00-P3LB-122108 | 2018-03-30 | MRT-DS-REC-TT-180258 | FA | 1 | TRUE | TRUE | FALSE
2033 | MRT-YQ03-P2LB-122088 | 2018-03-30 | MRT-DS-REC-TT-180259 | FA | 2 | TRUE | TRUE | FALSE
2034 | MRT-YQ03-P3LB-122088 | 2018-03-30 | MRT-DS-REC-TT-180259 | FA | 1 | TRUE | TRUE | FALSE
2035 | MRT-YD00-P2LB-122056 | 2018-03-30 | MRT-DS-REC-TT-180260 | FA | 1 | TRUE | TRUE | FALSE
2036 | MRT-YD00-P3LB-122056 | 2018-03-30 | MRT-DS-REC-TT-180260 | FA | 1 | TRUE | TRUE | FALSE
2037 | MRT-CA06-P0UMA-180002 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 4 | TRUE | TRUE | FALSE
2038 | MRT-CA06-P0UMA-180003 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 3 | TRUE | TRUE | FALSE
2039 | MRT-CA03-P0UMA-180025 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 3 | TRUE | TRUE | FALSE
2040 | MRT-CA03-P0UMA-180026 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 3 | TRUE | TRUE | FALSE
2041 | MRT-CA01-P0UMA-180027 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 3 | TRUE | TRUE | FALSE
2042 | MRT-CA03-P0UMA-180028 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 3 | TRUE | TRUE | FALSE
2043 | MRT-CA03-P0UMA-180029 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 3 | TRUE | TRUE | FALSE
2044 | MRT-CA03-P0UMA-180031 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 3 | TRUE | TRUE | FALSE
2045 | MRT-CA03-P0UMA-180032 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 3 | TRUE | TRUE | FALSE
2046 | MRT-CA03-P0UMA-180033 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 3 | TRUE | TRUE | FALSE
2047 | MRT-CA03-P0UMA-180034 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 3 | TRUE | TRUE | FALSE
2048 | MRT-CA03-P0UMA-180042 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 3 | TRUE | TRUE | FALSE
2049 | MRT-CA03-P0UMA-180030 | 2018-03-30 | MRT-DS-REC-TT-180255 | FC | 3 | TRUE | TRUE | FALSE
2050 | MRT-CC02-P2UHA-170103 | 2018-03-30 | MRT-DS-REC-TT-180256 | FC | 2 | TRUE | TRUE | FALSE
2051 | MRT-CC02-P2UHA-170104 | 2018-03-30 | MRT-DS-REC-TT-180256 | FC | 2 | TRUE | TRUE | FALSE
2052 | MRT-VK02-P2UHA-170106 | 2018-03-30 | MRT-DS-REC-TT-180256 | FC | 2 | TRUE | TRUE | FALSE
2053 | MRT-CC02-P3UHA-170103 | 2018-03-30 | MRT-DS-REC-TT-180256 | FC | 2 | TRUE | TRUE | FALSE
2054 | MRT-CC02-P3UHA-170104 | 2018-03-30 | MRT-DS-REC-TT-180256 | FC | 2 | TRUE | TRUE | FALSE
2055 | MRT-VK02-P3UHA-170106 | 2018-03-30 | MRT-DS-REC-TT-180256 | FC | 2 | TRUE | TRUE | FALSE
2056 | MRT-CA00-P0UGA-186610 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2057 | MRT-CA00-P0UGA-186615 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2058 | MRT-CA00-P0UGA-186624 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2059 | MRT-CA00-P0UGA-186611 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2060 | MRT-CA00-P0UGA-186612 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2061 | MRT-CA00-P0UGA-186613 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2062 | MRT-CA00-P0UGA-186614 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2063 | MRT-CA00-P0UGA-186616 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2064 | MRT-CA00-P0UGA-186617 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2065 | MRT-CC02-P0UGA-176235 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2066 | MRT-CC02-P0UGA-176275 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2067 | MRT-CA06-P0UGA-186600 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2068 | MRT-CA01-P0UGA-186602 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2069 | MRT-CA00-P0UGX-186726 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2070 | MRT-CA00-P0UGX-186730 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2071 | MRT-CA00-P0UGX-186732 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2072 | MRT-CA00-P0UGX-186734 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2073 | MRT-CA00-P0UGX-186736 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2074 | MRT-CA00-P0UST-186906 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2075 | MRT-CA00-P0UST-186912 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2076 | MRT-CA00-P0UST-186914 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2077 | MRT-CA00-P0UGA-186625 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2078 | MRT-CA01-P0UGA-186603 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2079 | MRT-CA06-P0UGA-186599 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2080 | MRT-CA00-P0UST-186909 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2081 | MRT-CA00-P0UST-186911 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2082 | MRT-CA06-P0USG-186851 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2083 | MRT-CA01-P0USG-186852 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2084 | MRT-CA00-P0USG-186856 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2085 | MRT-CA00-P0USG-186858 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2086 | MRT-CA00-P0USG-186862 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2087 | MRT-CA00-P0USG-186864 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2088 | MRT-CA06-P0UST-186901 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2089 | MRT-CA01-P0UST-186902 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2090 | MRT-CA00-P0UGX-186956 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2091 | MRT-CA01-P0UPB-187002 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2092 | MRT-CA00-P0UPB-187006 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2093 | MRT-CA00-P0UPB-187012 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2094 | MRT-CA00-P0UPB-187014 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2095 | MRT-CA00-P0USG-186857 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2096 | MRT-CA00-P0USG-186863 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2097 | MRT-CA00-P0UPB-187007 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2098 | MRT-CA00-P0UPB-187009 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2099 | MRT-CA00-P0UST-186917 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2100 | MRT-CA00-P0UPB-187013 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2101 | MRT-CC02-P0ULY-176105 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2102 | MRT-CA01-P0UGX-186952 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2103 | MRT-CA00-P0UGX-186960 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2104 | MRT-CA00-P0UGX-186966 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2105 | MRT-CA00-P0UGX-186957 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2106 | MRT-CA00-P0UGX-186961 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2107 | MRT-CA00-P0UGX-186963 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2108 | MRT-CC02-P0ULY-176106 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2109 | MRT-CC02-P0ULY-176107 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2110 | MRT-CC02-P0ULY-176108 | 2018-03-31 | MRT-HK-REC-TT-180081 | FA | 1 | TRUE | TRUE | FALSE
2117 | MRT-CA07-P0ZEN-175018 | 2018-04-02 | MRT-HK-REC-TT-180083 | FI | 1 | TRUE | TRUE | FALSE
2118 | MRT-QM03-P0ZEN-045004 | 2018-04-02 | MRT-HK-REC-TT-180082 | FA | 0 | TRUE | FALSE | FALSE
2119 | MRT-YK00-P2LB-122072 | 2018-04-02 | MRT-DS-REC-TT-180261 | FC | 2 | TRUE | TRUE | FALSE
2120 | MRT-YK00-P3LB-122072 | 2018-04-02 | MRT-DS-REC-TT-180261 | FC | 2 | TRUE | TRUE | FALSE
2121 | MRT-XS00-P3LB-122035 | 2018-04-02 | MRT-DS-REC-TT-180262 | FC | 2 | TRUE | TRUE | FALSE
2122 | MRT-YL16-P2LB-122078 | 2018-04-02 | MRT-DS-REC-TT-180263 | FA | 0 | TRUE | FALSE | FALSE
2123 | MRT-YL16-P3LB-122078 | 2018-04-02 | MRT-DS-REC-TT-180263 | FA | 0 | TRUE | FALSE | FALSE
2124 | MRT-YK08-P3MKA-220002 | 2018-04-02 | MRT-DS-REC-TT-180264 | FI | 0 | TRUE | FALSE | FALSE
2125 | MRT-YK08-P2MKA-220002 | 2018-04-02 | MRT-DS-REC-TT-180264 | FI | 0 | TRUE | FALSE | FALSE
2126 | MRT-YD00-P2LB-122049 | 2018-04-02 | MRT-DS-REC-TT-180265 | FI | 1 | TRUE | TRUE | FALSE
2127 | MRT-YD00-P2LB-122107 | 2018-04-02 | MRT-DS-REC-TT-180265 | FA | 1 | TRUE | TRUE | FALSE
2128 | MRT-YD00-P3LB-122107 | 2018-04-02 | MRT-DS-REC-TT-180265 | FA | 1 | TRUE | TRUE | FALSE
2129 | MRT-YD00-P3LB-122049 | 2018-04-02 | MRT-DS-REC-TT-180265 | FI | 1 | TRUE | TRUE | FALSE
2130 | MRT-YD00-P2LB-122109 | 2018-04-02 | MRT-DS-REC-TT-180266 | FI | 0 | TRUE | FALSE | FALSE
2131 | MRT-YD00-P3LB-122109 | 2018-04-02 | MRT-DS-REC-TT-180266 | FI | 0 | TRUE | FALSE | FALSE
2132 | MRT-XG02-P2LCB-127032 | 2018-04-03 | MRT-DS-REC-TT-180267 | FA | 0 | TRUE | FALSE | FALSE
2133 | MRT-XG02-P3LCB-127032 | 2018-04-03 | MRT-DS-REC-TT-180267 | FA | 0 | TRUE | FALSE | FALSE
2134 | MRT-YK09-P2LCB-127034 | 2018-04-03 | MRT-DS-REC-TT-180267 | FI | 0 | TRUE | FALSE | FALSE
2135 | MRT-YK09-P3LCB-127034 | 2018-04-03 | MRT-DS-REC-TT-180267 | FI | 0 | TRUE | FALSE | FALSE
2136 | MRT-XG02-P2LCB-127032 | 2018-04-03 | MRT-DS-REC-TT-180267 | FA | 0 | TRUE | FALSE | FALSE
2137 | MRT-YK09-P2LCB-127034 | 2018-04-03 | MRT-DS-REC-TT-180267 | FI | 0 | TRUE | FALSE | FALSE
2138 | MRT-XG02-P3LCB-127032 | 2018-04-03 | MRT-DS-REC-TT-180267 | FA | 0 | TRUE | FALSE | FALSE
2139 | MRT-YK09-P3LCB-127034 | 2018-04-03 | MRT-DS-REC-TT-180267 | FI | 0 | TRUE | FALSE | FALSE
2140 | MRT-YV02-P2MAJ-603202 | 2018-04-03 | MRT-DS-REC-TT-180269 | FI | 1 | TRUE | TRUE | FALSE
2141 | MRT-YK08-P2MAJ-603205 | 2018-04-03 | MRT-DS-REC-TT-180269 | FI | 1 | TRUE | TRUE | FALSE
2142 | MRT-YV02-P3MAJ-604202 | 2018-04-03 | MRT-DS-REC-TT-180269 | FI | 1 | TRUE | TRUE | FALSE
2143 | MRT-YK08-P3MAJ-604205 | 2018-04-03 | MRT-DS-REC-TT-180269 | FI | 1 | TRUE | TRUE | FALSE
2144 | MRT-YL00-P2MAJ-603207 | 2018-04-03 | MRT-DS-REC-TT-180270 | FA | 1 | TRUE | TRUE | FALSE
2145 | MRT-YL00-P3MAJ-604207 | 2018-04-03 | MRT-DS-REC-TT-180270 | FA | 1 | TRUE | TRUE | FALSE
2146 | MRT-YK09-P0SMM-128007 | 2018-04-03 | MRT-DS-REC-TT- | FA | 0 | TRUE | FALSE | FALSE
2147 | MRT-YK09-P0SMM-128007 | 2018-04-03 | MRT-DS-REC-TT-180271 | FA | 0 | TRUE | FALSE | FALSE
2148 | MRT-YT01-P2QC-130014 | 2018-04-03 | MRT-DS-REC-TT-180272 | FI | 0 | TRUE | FALSE | FALSE
2149 | MRT-YT01-P3QC-130014 | 2018-04-03 | MRT-DS-REC-TT-180272 | FI | 0 | TRUE | FALSE | FALSE
2150 | MRT-YM03-P2LB-122069 | 2018-04-03 | MRT-DS-REC-TT-180273 | FA | 1 | TRUE | TRUE | FALSE
2151 | MRT-YM03-P3LB-122069 | 2018-04-03 | MRT-DS-REC-TT-180273 | FA | 1 | TRUE | TRUE | FALSE
2152 | MRT-DF04-P2ZEN-142001 | 2018-04-03 | MRT-DS-REC-TT-180274 | FI | 0 | TRUE | FALSE | FALSE
2153 | MRT-DF04-P2ZEN-142002 | 2018-04-03 | MRT-DS-REC-TT-180274 | FI | 0 | TRUE | FALSE | FALSE
2154 | MRT-XN00-P0ZEN-140001 | 2018-04-03 | MRT-DS-REC-TT-180276 | FC | 3 | TRUE | TRUE | FALSE
2155 | MRT-CV03-P2ZEN-165201 | 2018-04-03 | MRT-DS-REC-TT-180286 | FC | 2 | TRUE | TRUE | FALSE
2156 | MRT-CV03-P3ZEN-165201 | 2018-04-03 | MRT-DS-REC-TT-180286 | FC | 2 | TRUE | TRUE | FALSE
2173 | MRT-CC02-P0UQQ-175829 | 2018-04-03 | MRT-HK-REC-TT-180085 | FA | 1 | TRUE | TRUE | FALSE
2174 | MRT-CC02-P0UQQ-175828 | 2018-04-03 | MRT-HK-REC-TT-180085 | FA | 1 | TRUE | TRUE | FALSE
2175 | MRT-CC02-P0UQQ-175827 | 2018-04-03 | MRT-HK-REC-TT-180085 | FA | 1 | TRUE | TRUE | FALSE
2176 | MRT-CC02-P0UQQ-175826 | 2018-04-03 | MRT-HK-REC-TT-180085 | FA | 1 | TRUE | TRUE | FALSE
2177 | MRT-CC07-P0UQQ-175801 | 2018-04-03 | MRT-HK-REC-TT-180085 | FA | 1 | TRUE | TRUE | FALSE
2178 | MRT-CC02-P0UQQ-175805 | 2018-04-03 | MRT-HK-REC-TT-180085 | FA | 1 | TRUE | TRUE | FALSE
2179 | MRT-CC02-P0UQQ-175810 | 2018-04-03 | MRT-HK-REC-TT-180085 | FA | 1 | TRUE | TRUE | FALSE
2180 | MRT-CC07-P0UQQ-175815 | 2018-04-03 | MRT-HK-REC-TT-180085 | FA | 1 | TRUE | TRUE | FALSE
2181 | MRT-CC02-P0UQQ-175830 | 2018-04-03 | MRT-HK-REC-TT-180085 | FA | 1 | TRUE | TRUE | FALSE
2157 | MRT-YT01-P2GHC-129004 | 2018-04-04 | MRT-DS-REC-TT-180277 | FI | 0 | TRUE | FALSE | FALSE
2158 | MRT-YT01-P3GHC-129004 | 2018-04-04 | MRT-DS-REC-TT-180277 | FI | 0 | TRUE | FALSE | FALSE
2159 | MRT-YD00-P2ZEN-113500 | 2018-04-04 | MRT-DS-REC-TT-180278 | FC | 1 | TRUE | TRUE | FALSE
2160 | MRT-YD00-P3ZEN-113500 | 2018-04-04 | MRT-DS-REC-TT-180278 | FC | 1 | TRUE | TRUE | FALSE
2161 | MRT-YT01-P2ZEN-113501 | 2018-04-04 | MRT-DS-REC-TT-180278 | FC | 1 | TRUE | TRUE | FALSE
2162 | MRT-YT01-P3ZEN-113501 | 2018-04-04 | MRT-DS-REC-TT-180278 | FC | 1 | TRUE | TRUE | FALSE
2163 | MRT-YD00-P2ZEN-113400 | 2018-04-04 | MRT-DS-REC-TT-180279 | FC | 1 | TRUE | TRUE | FALSE
2164 | MRT-YT01-P2ZEN-113401 | 2018-04-04 | MRT-DS-REC-TT-180279 | FC | 1 | TRUE | TRUE | FALSE
2165 | MRT-YD00-P3ZEN-113400 | 2018-04-04 | MRT-DS-REC-TT-180279 | FC | 1 | TRUE | TRUE | FALSE
2166 | MRT-YT01-P3ZEN-113401 | 2018-04-04 | MRT-DS-REC-TT-180279 | FC | 1 | TRUE | TRUE | FALSE
2167 | MRT-YL01-P2ZEN-161051 | 2018-04-04 | MRT-DS-REC-TT-180280 | FA | 1 | TRUE | TRUE | FALSE
2168 | MRT-YL01-P3ZEN-161051 | 2018-04-04 | MRT-DS-REC-TT-180280 | FA | 1 | TRUE | TRUE | FALSE
2169 | MRT-YD06-P3ZEN-163106 | 2018-04-04 | MRT-DS-REC-TT-180283 | FA | 0 | TRUE | FALSE | FALSE
2170 | MRT-XN00-P2LB-122032 | 2018-04-04 | MRT-DS-REC-TT-180275 | FI | 2 | TRUE | TRUE | FALSE
2171 | MRT-XN00-P3LB-122032 | 2018-04-04 | MRT-DS-REC-TT-180275 | FI | 1 | TRUE | TRUE | FALSE
2172 | MRT-XL00-P0ZEN-140002 | 2018-04-05 | MRT-DS-REC-TT-180282 | FC | 3 | TRUE | TRUE | FALSE
2182 | MRT-CQ02-P2MAJ-603109 | 2018-04-05 | MRT-DS-REC-TT-180281 | FI | 0 | TRUE | FALSE | FALSE
2183 | MRT-CQ02-P3MAJ-603109 | 2018-04-05 | MRT-DS-REC-TT-180281 | FI | 0 | TRUE | FALSE | FALSE
2184 | MRT-YT01-P2MAJ-603110 | 2018-04-05 | MRT-DS-REC-TT-180281 | FI | 1 | TRUE | TRUE | FALSE
2185 | MRT-YT01-P3MAJ-604110 | 2018-04-05 | MRT-DS-REC-TT-180281 | FI | 1 | TRUE | TRUE | FALSE
2186 | MRT-XH01-P2QC-130011 | 2018-04-05 | MRT-DS-REC-TT-180284 | FI | 0 | TRUE | FALSE | FALSE
2187 | MRT-XH01-P3QC-130011 | 2018-04-05 | MRT-DS-REC-TT-180284 | FI | 0 | TRUE | FALSE | FALSE
2188 | MRT-YT01-P2QC-130033 | 2018-04-05 | MRT-DS-REC-TT-180285 | FI | 0 | TRUE | FALSE | FALSE
2189 | MRT-YT01-P3QC-130033 | 2018-04-05 | MRT-DS-REC-TT-180285 | FI | 0 | TRUE | FALSE | FALSE
2190 | MRT-XK00-P2GM-128508 | 2018-04-05 | MRT-DS-REC-TT-180287 | FA | 1 | TRUE | TRUE | FALSE
2191 | MRT-XK00-P3GM-128508 | 2018-04-05 | MRT-DS-REC-TT-180287 | FA | 1 | TRUE | TRUE | FALSE
2192 | MRT-XG02-P2LB-122022 | 2018-04-05 | MRT-DS-REC-TT-180288 | FC | 5 | TRUE | TRUE | FALSE
2193 | MRT-XG02-P3LB-122022 | 2018-04-05 | MRT-DS-REC-TT-180288 | FC | 2 | TRUE | TRUE | FALSE
2194 | MRT-XB02-P2QC-130009 | 2018-04-06 | MRT-DS-REC-TT-180268 | FI | 0 | TRUE | FALSE | FALSE
2195 | MRT-XB02-P3QC-130009 | 2018-04-06 | MRT-DS-REC-TT-180268 | FI | 0 | TRUE | FALSE | FALSE
2196 | MRT-YU04-P0ZEN-161012 | 2018-04-06 | MRT-DS-REC-TT-180289 | FC | 4 | TRUE | TRUE | FALSE
2197 | MRT-YT01-P2QU-130031 | 2018-04-06 | MRT-DS-REC-TT-180292 | FI | 0 | TRUE | FALSE | FALSE
2198 | MRT-YF00-P2QU-130033 | 2018-04-06 | MRT-DS-REC-TT-180292 | FI | 0 | TRUE | FALSE | FALSE
2199 | MRT-YT01-P3QU-130031 | 2018-04-06 | MRT-DS-REC-TT-180292 | FI | 0 | TRUE | FALSE | FALSE
2200 | MRT-YF00-P3QU-130033 | 2018-04-06 | MRT-DS-REC-TT-180292 | FI | 0 | TRUE | FALSE | FALSE
2201 | MRT-YT01-P2QU-130030 | 2018-04-06 | MRT-DS-REC-TT-180293 | FI | 0 | TRUE | FALSE | FALSE
2202 | MRT-YT01-P3QU-130030 | 2018-04-06 | MRT-DS-REC-TT-180293 | FI | 0 | TRUE | FALSE | FALSE
2203 | MRT-YV02-P2QU-130032 | 2018-04-06 | MRT-DS-REC-TT-180294 | FI | 0 | TRUE | FALSE | FALSE
2204 | MRT-YS01-P2QU-130034 | 2018-04-06 | MRT-DS-REC-TT-180294 | FI | 0 | TRUE | FALSE | FALSE
2205 | MRT-YV02-P3QU-130032 | 2018-04-06 | MRT-DS-REC-TT-180294 | FI | 0 | TRUE | FALSE | FALSE
2206 | MRT-YS01-P3QU-130034 | 2018-04-06 | MRT-DS-REC-TT-180294 | FI | 0 | TRUE | FALSE | FALSE
2207 | MRT-CV03-P2ZEN-165102 | 2018-04-06 | MRT-DS-REC-TT-180291 | FA | 0 | TRUE | FALSE | FALSE
2208 | MRT-CV03-P2ZEN-165103 | 2018-04-06 | MRT-DS-REC-TT-180291 | FA | 0 | TRUE | FALSE | FALSE
2209 | MRT-CV03-P2ZEN-165104 | 2018-04-06 | MRT-DS-REC-TT-180291 | FA | 0 | TRUE | FALSE | FALSE
2210 | MRT-CV03-P3ZEN-165102 | 2018-04-06 | MRT-DS-REC-TT-180291 | FA | 0 | TRUE | FALSE | FALSE
2211 | MRT-CV03-P3ZEN-165103 | 2018-04-06 | MRT-DS-REC-TT-180291 | FA | 0 | TRUE | FALSE | FALSE
2212 | MRT-CV03-P3ZEN-165104 | 2018-04-06 | MRT-DS-REC-TT-180291 | FA | 0 | TRUE | FALSE | FALSE
2213 | MRT-XW01-P2SCA-127504 | 2018-04-09 | MRT-DS-REC-TT-180295 | FA | 0 | TRUE | FALSE | FALSE
2214 | MRT-XW01-P3SCA-127504 | 2018-04-09 | MRT-DS-REC-TT-180295 | FA | 0 | TRUE | FALSE | FALSE
2215 | MRT-XG02-P2SCA-127502 | 2018-04-09 | MRT-DS-REC-TT-180296 | FC | 1 | TRUE | TRUE | FALSE
2216 | MRT-XG02-P3SCA-127502 | 2018-04-09 | MRT-DS-REC-TT-180296 | FC | 1 | TRUE | TRUE | FALSE
2217 | MRT-XK00-P2GM-128507 | 2018-04-09 | MRT-DS-REC-TT-180297 | FA | 1 | TRUE | TRUE | FALSE
2218 | MRT-XK00-P3GM-128507 | 2018-04-09 | MRT-DS-REC-TT-180297 | FA | 1 | TRUE | TRUE | FALSE
2219 | MRT-YD00-P0SMM-128001 | 2018-04-09 | MRT-DS-REC-TT-180298 | FC | 2 | TRUE | TRUE | FALSE
2220 | MRT-QM01-P0ZEN-045001 | 2018-04-09 | MRT-HK-REC-TT-180086 | FA | 1 | TRUE | TRUE | FALSE
2221 | MRT-UE00-P2ZEN-100016 | 2018-04-09 | MRT-DS-REC-TT-180290 | FA | 1 | TRUE | TRUE | FALSE
2222 | MRT-UE00-P3ZEN-100017 | 2018-04-09 | MRT-DS-REC-TT-180290 | FA | 1 | TRUE | TRUE | FALSE
2223 | MRT-YT01-P0SMM-128004 | 2018-04-09 | MRT-DS-REC-TT-180299 | FC | 2 | TRUE | TRUE | FALSE
2224 | MRT-YU02-P2BFA-150035 | 2018-04-10 | MRT-HK-REC-TT-180087 | FA | 0 | TRUE | FALSE | FALSE
2225 | MRT-YU02-P3BFC-150036 | 2018-04-10 | MRT-HK-REC-TT-180087 | FA | 0 | TRUE | FALSE | FALSE
2226 | MRT-YU02-P3BFE-150037 | 2018-04-10 | MRT-HK-REC-TT-180087 | FA | 0 | TRUE | FALSE | FALSE
2227 | MRT-YL25-P0ZEN-145301 | 2018-04-10 | MRT-HK-REC-TT-180088 | FA | 1 | TRUE | TRUE | FALSE
2228 | MRT-XW03-P0SMU-125002 | 2018-04-11 | MRT-HK-REC-TT-180089 | FA | 1 | TRUE | TRUE | FALSE
2229 | MRT-CC02-P2UHA-170103 | 2018-04-12 | MRT-DS-REC-TT-180302 | FC | 3 | TRUE | TRUE | FALSE
2230 | MRT-CC02-P2UHA-170104 | 2018-04-12 | MRT-DS-REC-TT-180302 | FC | 3 | TRUE | TRUE | FALSE
2231 | MRT-VK02-P2UHA-170106 | 2018-04-12 | MRT-DS-REC-TT-180302 | FC | 3 | TRUE | TRUE | FALSE
2232 | MRT-CC02-P3UHA-170103 | 2018-04-12 | MRT-DS-REC-TT-180302 | FC | 3 | TRUE | TRUE | FALSE
2233 | MRT-CC02-P3UHA-170104 | 2018-04-12 | MRT-DS-REC-TT-180302 | FC | 3 | TRUE | TRUE | FALSE
2234 | MRT-VK02-P3UHA-170106 | 2018-04-12 | MRT-DS-REC-TT-180302 | FC | 3 | TRUE | TRUE | FALSE
2235 | MRT-YE00-P2MKA-230001 | 2018-04-12 | MRT-DS-REC-TT-180300 | FA | 0 | TRUE | FALSE | FALSE
2236 | MRT-YK00-P2BAT-240001 | 2018-04-12 | MRT-DS-REC-TT-180300 | FA | 0 | TRUE | FALSE | FALSE
2237 | MRT-UC02-P2BAT-240001 | 2018-04-12 | MRT-DS-REC-TT-180300 | FA | 0 | TRUE | FALSE | FALSE
2238 | MRT-YV02-P2MAJ-603108 | 2018-04-12 | MRT-DS-REC-TT-180304 | FA | 2 | TRUE | TRUE | FALSE
2239 | MRT-YV02-P3MAJ-604108 | 2018-04-12 | MRT-DS-REC-TT-180304 | FA | 2 | TRUE | TRUE | FALSE
2240 | MRT-CC02-P2UMA-170207 | 2018-04-13 | MRT-DS-REC-TT-180305 | FC | 2 | TRUE | TRUE | FALSE
2241 | MRT-CC02-P2UMA-170208 | 2018-04-13 | MRT-DS-REC-TT-180305 | FC | 2 | TRUE | TRUE | FALSE
2242 | MRT-CC02-P2UMA-170209 | 2018-04-13 | MRT-DS-REC-TT-180305 | FC | 2 | TRUE | TRUE | FALSE
2243 | MRT-XH01-P2UMA-142000 | 2018-04-13 | MRT-DS-REC-TT-180308 | FA | 0 | TRUE | TRUE | FALSE
2244 | MRT-XH01-P0UZT-140001 | 2018-04-13 | MRT-DS-REC-TT-180310 | FC | 2 | TRUE | TRUE | FALSE
2245 | MRT-XH01-P2ULY-142000 | 2018-04-13 | MRT-DS-REC-TT-180310 | FC | 2 | TRUE | TRUE | FALSE
2246 | MRT-XH01-P3ULY-143000 | 2018-04-13 | MRT-DS-REC-TT-180310 | FC | 2 | TRUE | TRUE | FALSE
2247 | MRT-XH01-P3ULY-144000 | 2018-04-13 | MRT-DS-REC-TT-180310 | FC | 2 | TRUE | TRUE | FALSE
2248 | MRT-XL00-P3MKA-210001 | 2018-04-13 | MRT-DS-REC-TT-180303 | FI | 0 | TRUE | FALSE | FALSE
2249 | MRT-XN00-P3MKA-210001 | 2018-04-13 | MRT-DS-REC-TT-180303 | FI | 0 | TRUE | FALSE | FALSE
2250 | MRT-YD00-P2ZEN-113300 | 2018-04-13 | MRT-DS-REC-TT-180309 | FA | 1 | TRUE | TRUE | FALSE
2251 | MRT-YT01-P2ZEN-113301 | 2018-04-13 | MRT-DS-REC-TT-180309 | FA | 1 | TRUE | TRUE | FALSE
2252 | MRT-YD00-P3ZEN-113300 | 2018-04-13 | MRT-DS-REC-TT-180309 | FA | 1 | TRUE | TRUE | FALSE
2253 | MRT-YT01-P3ZEN-113301 | 2018-04-13 | MRT-DS-REC-TT-180309 | FA | 1 | TRUE | TRUE | FALSE
2254 | MRT-YL00-P2ZEN-165101 | 2018-04-13 | MRT-DS-REC-TT-180311 | FA | 0 | TRUE | FALSE | FALSE
2255 | MRT-YL00-P3ZEN-165101 | 2018-04-13 | MRT-DS-REC-TT-180311 | FA | 0 | TRUE | FALSE | FALSE
2256 | MRT-CC02-P0UBX-176007 | 2018-04-16 | MRT-HK-REC-TT-180090 | FA | 0 | TRUE | FALSE | FALSE
2257 | MRT-CC02-P0UBX-176006 | 2018-04-16 | MRT-HK-REC-TT-180090 | FA | 0 | TRUE | FALSE | FALSE
2258 | MRT-CC07-P0UBX-176001 | 2018-04-16 | MRT-HK-REC-TT-180090 | FA | 0 | TRUE | FALSE | FALSE
2259 | MRT-CC02-P0UBX-176005 | 2018-04-16 | MRT-HK-REC-TT-180090 | FA | 0 | TRUE | FALSE | FALSE
2260 | MRT-HM05-P00SA-135504 | 2018-04-16 | MRT-HK-REC-TT-180091 | FA | 1 | TRUE | TRUE | FALSE
2261 | MRT-YD00-P2GHC-129001 | 2018-04-16 | MRT-DS-REC-TT-180314 | FC | 2 | TRUE | TRUE | FALSE
2262 | MRT-YD00-P3GHC-129001 | 2018-04-16 | MRT-DS-REC-TT-180314 | FC | 2 | TRUE | TRUE | FALSE
2263 | MRT-YD00-P3MAA-220025 | 2018-04-16 | MRT-DS-REC-TT-180312 | FI | 0 | TRUE | FALSE | FALSE
2264 | MRT-YD00-P3MAA-220026 | 2018-04-16 | MRT-DS-REC-TT-180312 | FI | 0 | TRUE | FALSE | FALSE
2265 | MRT-YD00-P3MAA-220027 | 2018-04-16 | MRT-DS-REC-TT-180312 | FI | 0 | TRUE | FALSE | FALSE
2266 | MRT-YD00-P2MAA-220025 | 2018-04-16 | MRT-DS-REC-TT-180312 | FI | 0 | TRUE | FALSE | FALSE
2267 | MRT-YD00-P2MAA-220026 | 2018-04-16 | MRT-DS-REC-TT-180312 | FI | 0 | TRUE | FALSE | FALSE
2268 | MRT-YD00-P2MAA-220027 | 2018-04-16 | MRT-DS-REC-TT-180312 | FI | 0 | TRUE | FALSE | FALSE
2269 | MRT-XA01-P0ABA-150505 | 2018-04-17 | MRT-HK-REC-TT-180092 | FA | 0 | TRUE | FALSE | FALSE
2270 | MRT-CA05-P0UCA-180161 | 2018-04-17 | MRT-DS-REC-TT-180313 | FC | 3 | TRUE | TRUE | FALSE
2271 | MRT-CA05-P0UCA-180162 | 2018-04-17 | MRT-DS-REC-TT-180313 | FC | 3 | TRUE | TRUE | FALSE
2272 | MRT-CA05-P0UCA-180163 | 2018-04-17 | MRT-DS-REC-TT-180313 | FC | 3 | TRUE | TRUE | FALSE
2273 | MRT-CA05-P0UCA-180164 | 2018-04-17 | MRT-DS-REC-TT-180313 | FC | 3 | TRUE | TRUE | FALSE
2274 | MRT-CC02-P0UZT-175991 | 2018-04-17 | MRT-HK-REC-TT-180093 | FA | 1 | TRUE | TRUE | FALSE
2275 | MRT-YD16-P2SCA-127531 | 2018-04-17 | MRT-DS-REC-TT-180316 | FA | 0 | TRUE | FALSE | FALSE
2276 | MRT-YD16-P3SCA-127531 | 2018-04-17 | MRT-DS-REC-TT-180316 | FA | 0 | TRUE | FALSE | FALSE
2277 | MRT-QM01-P0ZEN-040001 | 2018-04-17 | MRT-DS-REC-TT-180317 | FA | 3 | TRUE | TRUE | FALSE
2278 | MRT-CC02-P2UMA-170203 | 2018-04-17 | MRT-DS-REC-TT-180318 | FC | 2 | TRUE | TRUE | FALSE
2279 | MRT-CC02-P2UMA-170204 | 2018-04-17 | MRT-DS-REC-TT-180318 | FC | 2 | TRUE | TRUE | FALSE
2280 | MRT-CC02-P3UMA-170203 | 2018-04-17 | MRT-DS-REC-TT-180318 | FC | 2 | TRUE | TRUE | FALSE
2281 | MRT-CC02-P3UMA-170204 | 2018-04-17 | MRT-DS-REC-TT-180318 | FC | 2 | TRUE | TRUE | FALSE
2282 | MRT-YQ03-P2LB-122088 | 2018-04-17 | MRT-DS-REC-TT-180320 | FC | 3 | TRUE | TRUE | FALSE
2283 | MRT-YQ03-P3LB-122088 | 2018-04-17 | MRT-DS-REC-TT-180320 | FC | 2 | TRUE | TRUE | FALSE
2284 | MRT-YU01-P2MKC-230010 | 2018-04-18 | MRT-DS-REC-TT-180315 | FA | 0 | TRUE | FALSE | FALSE
2285 | MRT-YU01-P3MKC-230010 | 2018-04-18 | MRT-DS-REC-TT-180315 | FA | 0 | TRUE | FALSE | FALSE
2286 | MRT-YK09-P2MKC-230002 | 2018-04-18 | MRT-DS-REC-TT-180319 | FA | 0 | TRUE | FALSE | FALSE
2287 | MRT-YK09-P3MKC-230002 | 2018-04-18 | MRT-DS-REC-TT-180319 | FA | 0 | TRUE | FALSE | FALSE
2288 | MRT-YB03-P3PAH-604523 | 2018-04-18 | MRT-DS-REC-TT-180325 | FC | 2 | TRUE | TRUE | FALSE
2289 | MRT-YK08-P3PAH-604524 | 2018-04-18 | MRT-DS-REC-TT-180325 | FC | 2 | TRUE | TRUE | FALSE
2290 | MRT-YD00-P2PAB-113251 | 2018-04-18 | MRT-DS-REC-TT-180321 | FA | 1 | TRUE | TRUE | FALSE
2291 | MRT-YT01-P2PAB-113252 | 2018-04-18 | MRT-DS-REC-TT-180321 | FA | 1 | TRUE | TRUE | FALSE
2292 | MRT-XG02-P2PAB-113253 | 2018-04-18 | MRT-DS-REC-TT-180321 | FA | 1 | TRUE | TRUE | FALSE
2293 | MRT-YD00-P3PAB-113251 | 2018-04-18 | MRT-DS-REC-TT-180321 | FA | 1 | TRUE | TRUE | FALSE
2294 | MRT-YT01-P3PAB-113252 | 2018-04-18 | MRT-DS-REC-TT-180321 | FA | 1 | TRUE | TRUE | FALSE
2295 | MRT-XG02-P3PAB-113253 | 2018-04-18 | MRT-DS-REC-TT-180321 | FA | 1 | TRUE | TRUE | FALSE
2296 | MRT-YD00-P2PGB-113201 | 2018-04-18 | MRT-DS-REC-TT-180323 | FI | 2 | TRUE | TRUE | FALSE
2297 | MRT-YD00-P3PGB-113201 | 2018-04-18 | MRT-DS-REC-TT-180323 | FI | 2 | TRUE | TRUE | FALSE
2298 | MRT-YT01-P2PGB-113104 | 2018-04-18 | MRT-DS-REC-TT-180322 | FC | 1 | TRUE | TRUE | FALSE
2299 | MRT-YD00-P2PGB-113105 | 2018-04-18 | MRT-DS-REC-TT-180322 | FC | 1 | TRUE | TRUE | FALSE
2300 | MRT-YT01-P3PGB-113104 | 2018-04-18 | MRT-DS-REC-TT-180322 | FC | 1 | TRUE | TRUE | FALSE
2301 | MRT-YD00-P3PGB-113105 | 2018-04-18 | MRT-DS-REC-TT-180322 | FC | 1 | TRUE | TRUE | FALSE
2302 | MRT-YB03-P2PAH-604123 | 2018-04-18 | MRT-DS-REC-TT-180324 | FA | 2 | TRUE | TRUE | FALSE
2303 | MRT-YK08-P2PAH-604124 | 2018-04-18 | MRT-DS-REC-TT-180324 | FC | 2 | TRUE | TRUE | FALSE
2304 | MRT-CA06-P0UMA-180001 | 2018-04-18 | MRT-DS-REC-TT-180307 | FC | 3 | TRUE | TRUE | FALSE
2305 | MRT-XB02-P0UMA-180004 | 2018-04-18 | MRT-DS-REC-TT-180307 | FC | 5 | TRUE | TRUE | FALSE
2306 | MRT-CA01-P0UMA-180005 | 2018-04-18 | MRT-DS-REC-TT-180307 | FC | 4 | TRUE | TRUE | FALSE
2307 | MRT-CA01-P0UMA-180006 | 2018-04-18 | MRT-DS-REC-TT-180307 | FC | 4 | TRUE | TRUE | FALSE
2308 | MRT-CA01-P0UMA-180007 | 2018-04-18 | MRT-DS-REC-TT-180307 | FC | 4 | TRUE | TRUE | FALSE
2309 | MRT-CA03-P0UQA-186559 | 2018-04-19 | MRT-HK-REC-TT-180094 | FA | 0 | TRUE | FALSE | FALSE
2310 | MRT-CA06-P0UQA-186506 | 2018-04-19 | MRT-HK-REC-TT-180094 | FA | 0 | TRUE | FALSE | FALSE
2311 | MRT-CA03-P0UQA-186550 | 2018-04-19 | MRT-HK-REC-TT-180094 | FA | 0 | TRUE | FALSE | FALSE
2312 | MRT-CA03-P0UQA-186552 | 2018-04-19 | MRT-HK-REC-TT-180094 | FA | 0 | TRUE | FALSE | FALSE
2313 | MRT-CA03-P0UQA-186554 | 2018-04-19 | MRT-HK-REC-TT-180094 | FA | 0 | TRUE | FALSE | FALSE
2314 | MRT-CA03-P0UQA-186556 | 2018-04-19 | MRT-HK-REC-TT-180094 | FA | 0 | TRUE | FALSE | FALSE
2315 | MRT-CA03-P0UQA-186558 | 2018-04-19 | MRT-HK-REC-TT-180094 | FA | 0 | TRUE | FALSE | FALSE
2316 | MRT-CA03-P0UQA-186562 | 2018-04-19 | MRT-HK-REC-TT-180094 | FA | 0 | TRUE | FALSE | FALSE
2317 | MRT-CA03-P0UQA-186564 | 2018-04-19 | MRT-HK-REC-TT-180094 | FA | 0 | TRUE | FALSE | FALSE
2318 | MRT-CA03-P0UQA-186566 | 2018-04-19 | MRT-HK-REC-TT-180094 | FA | 0 | TRUE | FALSE | FALSE
2319 | MRT-CA03-P0UQA-186568 | 2018-04-19 | MRT-HK-REC-TT-180094 | FA | 0 | TRUE | FALSE | FALSE
2320 | MRT-XW03-P0BBT-150009 | 2018-04-19 | MRT-HK-REC-TT-180095 | FA | 1 | TRUE | TRUE | FALSE
2321 | MRT-XW03-P0BBT-150013 | 2018-04-19 | MRT-HK-REC-TT-180095 | FA | 1 | TRUE | TRUE | FALSE
2322 | MRT-YK08-P2MAJ-603200 | 2018-04-19 | MRT-DS-REC-TT-180326 | FC | 1 | TRUE | TRUE | FALSE
2323 | MRT-XG02-P2MAJ-603201 | 2018-04-19 | MRT-DS-REC-TT-180326 | FA | 1 | TRUE | TRUE | FALSE
2324 | MRT-YT01-P2MAJ-603204 | 2018-04-19 | MRT-DS-REC-TT-180326 | FC | 1 | TRUE | TRUE | FALSE
2325 | MRT-YK08-P3MAJ-604200 | 2018-04-19 | MRT-DS-REC-TT-180326 | FC | 1 | TRUE | TRUE | FALSE
2326 | MRT-XG02-P3MAJ-604201 | 2018-04-19 | MRT-DS-REC-TT-180326 | FA | 1 | TRUE | TRUE | FALSE
2327 | MRT-YT01-P3MAJ-604204 | 2018-04-19 | MRT-DS-REC-TT-180326 | FC | 1 | TRUE | TRUE | FALSE
2328 | MRT-YT01-P2LAC-126004 | 2018-04-20 | MRT-DS-REC-TT-180327 | FC | 1 | TRUE | TRUE | FALSE
2329 | MRT-YD00-P2LAC-126001 | 2018-04-20 | MRT-DS-REC-TT-180327 | FC | 1 | TRUE | TRUE | FALSE
2330 | MRT-YT01-P3LAC-126004 | 2018-04-20 | MRT-DS-REC-TT-180327 | FC | 1 | TRUE | TRUE | FALSE
2331 | MRT-YD00-P3LAC-126001 | 2018-04-20 | MRT-DS-REC-TT-180327 | FC | 1 | TRUE | TRUE | FALSE
2332 | MRT-YT01-P2LAC-126054 | 2018-04-20 | MRT-DS-REC-TT-180327 | FC | 1 | TRUE | TRUE | FALSE
2333 | MRT-YD00-P2LAC-126051 | 2018-04-20 | MRT-DS-REC-TT-180327 | FC | 1 | TRUE | TRUE | FALSE
2334 | MRT-YT01-P3LAC-126054 | 2018-04-20 | MRT-DS-REC-TT-180327 | FC | 1 | TRUE | TRUE | FALSE
2335 | MRT-YD00-P3LAC-126051 | 2018-04-20 | MRT-DS-REC-TT-180327 | FC | 1 | TRUE | TRUE | FALSE
2336 | MRT-YD00-P2MKA-220003 | 2018-04-20 | MRT-DS-REC-TT-180328 | FC | 3 | TRUE | TRUE | FALSE
2337 | MRT-XW03-P2MAV-120001 | 2018-04-20 | MRT-DS-REC-TT-180329 | FC | 1 | TRUE | TRUE | FALSE
2338 | MRT-XW03-P3MAV-130001 | 2018-04-20 | MRT-DS-REC-TT-180329 | FC | 1 | TRUE | TRUE | FALSE
2339 | MRT-HM01-P0SAC-135562 | 2018-04-23 | MRT-HK-REC-TT-180096 | FA | 0 | TRUE | FALSE | FALSE
2340 | MRT-HM01-P0SAH-135561 | 2018-04-23 | MRT-HK-REC-TT-180096 | FA | 0 | TRUE | FALSE | FALSE
2341 | MRT-YK08-P2LAA-605102 | 2018-04-23 | MRT-DS-REC-TT-180331 | FI | 3 | TRUE | TRUE | FALSE
2342 | MRT-YK08-P3LAA-605502 | 2018-04-23 | MRT-DS-REC-TT-180331 | FI | 3 | TRUE | TRUE | FALSE
2343 | MRT-CC07-P2UHA-170005 | 2018-04-23 | MRT-DS-REC-TT-180333 | FC | 3 | TRUE | TRUE | FALSE
2344 | MRT-CC07-P3UHA-170005 | 2018-04-23 | MRT-DS-REC-TT-180333 | FC | 3 | TRUE | TRUE | FALSE
2345 | MRT-CC02-P2UHA-170103 | 2018-04-23 | MRT-DS-REC-TT-180332 | FC | 4 | TRUE | TRUE | FALSE
2346 | MRT-CC02-P2UHA-170104 | 2018-04-23 | MRT-DS-REC-TT-180332 | FC | 4 | TRUE | TRUE | FALSE
2347 | MRT-VK02-P2UHA-170106 | 2018-04-23 | MRT-DS-REC-TT-180332 | FC | 4 | TRUE | TRUE | FALSE
2348 | MRT-CC02-P3UHA-170103 | 2018-04-23 | MRT-DS-REC-TT-180332 | FC | 4 | TRUE | TRUE | FALSE
2349 | MRT-CC02-P3UHA-170104 | 2018-04-23 | MRT-DS-REC-TT-180332 | FC | 4 | TRUE | TRUE | FALSE
2350 | MRT-VK02-P3UHA-170106 | 2018-04-23 | MRT-DS-REC-TT-180332 | FC | 4 | TRUE | TRUE | FALSE
2351 | MRT-YT01-P2QC-130012 | 2018-04-23 | MRT-DS-REC-TT-180335 | FI | 0 | TRUE | FALSE | FALSE
2352 | MRT-YT01-P3QC-130012 | 2018-04-23 | MRT-DS-REC-TT-180335 | FI | 0 | TRUE | FALSE | FALSE
2353 | MRT-YQ01-P0BHT-150177 | 2018-04-24 | MRT-HK-REC-TT-180097 | FA | 1 | TRUE | TRUE | FALSE
2354 | MRT-CA03-P0UCA-180132 | 2018-04-24 | MRT-DS-REC-TT-180334 | FA | 1 | TRUE | TRUE | FALSE
2355 | MRT-CA01-P0UCA-180133 | 2018-04-24 | MRT-DS-REC-TT-180334 | FA | 1 | TRUE | TRUE | FALSE
2356 | MRT-CN00-P2ZEN-110100 | 2018-04-24 | MRT-DS-REC-TT-180330 | FA | 0 | TRUE | FALSE | FALSE
2357 | MRT-DF04-P2ZEN-142003 | 2018-04-24 | MRT-DS-REC-TT-180338 | FI | 0 | TRUE | FALSE | FALSE
2358 | MRT-YS01-P3MKC-230017 | 2018-04-24 | MRT-DS-REC-TT-180339 | FA | 0 | TRUE | FALSE | FALSE
2359 | MRT-DP00-P2LB-122106 | 2018-04-24 | MRT-DS-REC-TT-180341 | FC | 3 | TRUE | TRUE | FALSE
2360 | MRT-DP00-P3LB-122106 | 2018-04-24 | MRT-DS-REC-TT-180341 | FC | 3 | TRUE | TRUE | FALSE
2403 | MRT-CA06-P0UGA-186605 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2404 | MRT-CA01-P0UGA-186628 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2405 | MRT-CA02-P0UGA-186634 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2406 | MRT-CA03-P0UGA-186636 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2407 | MRT-CA03-P0UGA-186638 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2408 | MRT-CA03-P0UGA-186640 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2409 | MRT-CA03-P0UGA-186644 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2410 | MRT-CA03-P0UGA-186646 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2411 | MRT-CA01-P0UGA-186631 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2412 | MRT-CA02-P0UGA-186633 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2413 | MRT-CA03-P0UGA-186635 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2414 | MRT-CA03-P0UGA-186637 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2415 | MRT-CA03-P0UGA-186639 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2416 | MRT-CA03-P0UGA-186641 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2417 | MRT-CA03-P0UGA-186643 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2418 | MRT-CA03-P0UGA-186645 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2419 | MRT-CA06-P0UGA-186604 | 2018-04-24 | MRT-HK-REC-TT-180098 | FA | 0 | TRUE | TRUE | FALSE
2361 | MRT-YD00-P0ERB-606001 | 2018-04-25 | MRT-DS-REC-TT-180340 | FA | 1 | TRUE | TRUE | FALSE
2362 | MRT-YD00-P0ERB-606002 | 2018-04-25 | MRT-DS-REC-TT-180340 | FA | 1 | TRUE | TRUE | FALSE
2363 | MRT-XG02-P2LAC-126003 | 2018-04-25 | MRT-DS-REC-TT-180342 | FA | 1 | TRUE | TRUE | FALSE
2364 | MRT-XG02-P3LAC-126003 | 2018-04-25 | MRT-DS-REC-TT-180342 | FA | 1 | TRUE | TRUE | FALSE
2365 | MRT-XG02-P2LAC-126053 | 2018-04-25 | MRT-DS-REC-TT-180342 | FA | 1 | TRUE | TRUE | FALSE
2366 | MRT-XG02-P3LAC-126053 | 2018-04-25 | MRT-DS-REC-TT-180342 | FA | 1 | TRUE | TRUE | FALSE
2367 | MRT-YT01-P2LAC-126005 | 2018-04-25 | MRT-DS-REC-TT-180343 | FA | 1 | TRUE | TRUE | FALSE
2368 | MRT-YT01-P3LAC-126005 | 2018-04-25 | MRT-DS-REC-TT-180343 | FA | 1 | TRUE | TRUE | FALSE
2369 | MRT-YT01-P2LAC-126055 | 2018-04-25 | MRT-DS-REC-TT-180343 | FC | 1 | TRUE | TRUE | FALSE
2370 | MRT-YT01-P3LAC-126055 | 2018-04-25 | MRT-DS-REC-TT-180343 | FC | 1 | TRUE | TRUE | FALSE
2371 | MRT-YM01-P2GHC-129008 | 2018-04-25 | MRT-DS-REC-TT-180337 | FA | 1 | TRUE | TRUE | FALSE
2372 | MRT-YM01-P3GHC-129008 | 2018-04-25 | MRT-DS-REC-TT-180337 | FA | 1 | TRUE | TRUE | FALSE
2373 | MRT-XG02-P2MAJ-603101 | 2018-04-26 | MRT-DS-REC-TT-180344 | FC | 3 | TRUE | TRUE | FALSE
2374 | MRT-XN00-P2MAJ-603106 | 2018-04-26 | MRT-DS-REC-TT-180344 | FC | 3 | TRUE | TRUE | FALSE
2375 | MRT-YL00-P2MAJ-603107 | 2018-04-26 | MRT-DS-REC-TT-180344 | FC | 3 | TRUE | TRUE | FALSE
2376 | MRT-XG02-P3MAJ-604101 | 2018-04-26 | MRT-DS-REC-TT-180344 | FC | 3 | TRUE | TRUE | FALSE
2377 | MRT-XN00-P3MAJ-604106 | 2018-04-26 | MRT-DS-REC-TT-180344 | FC | 3 | TRUE | TRUE | FALSE
2378 | MRT-YL00-P3MAJ-604107 | 2018-04-26 | MRT-DS-REC-TT-180344 | FC | 3 | TRUE | TRUE | FALSE
2379 | MRT-YK08-P2MAJ-603308 | 2018-04-26 | MRT-DS-REC-TT-180344 | FC | 1 | TRUE | TRUE | FALSE
2380 | MRT-YK08-P3MAJ-604308 | 2018-04-26 | MRT-DS-REC-TT-180344 | FC | 1 | TRUE | TRUE | FALSE
2381 | MRT-YD00-P0QHE-606001 | 2018-04-26 | MRT-DS-REC-TT-180346 | FC | 2 | TRUE | TRUE | FALSE
2382 | MRT-XK00-P2GM-128507 | 2018-04-26 | MRT-DS-REC-TT-180336 | FC | 2 | TRUE | TRUE | FALSE
2383 | MRT-XK00-P3GM-128507 | 2018-04-26 | MRT-DS-REC-TT-180336 | FC | 2 | TRUE | TRUE | FALSE
2384 | MRT-XK00-P2GM-128505 | 2018-04-26 | MRT-DS-REC-TT-180347 | FA | 0 | TRUE | FALSE | FALSE
2385 | MRT-YT01-P2GM-128502 | 2018-04-26 | MRT-DS-REC-TT-180347 | FA | 0 | TRUE | FALSE | FALSE
2386 | MRT-YD00-P2GM-128501 | 2018-04-26 | MRT-DS-REC-TT-180347 | FA | 0 | TRUE | FALSE | FALSE
2387 | MRT-XK00-P3GM-128505 | 2018-04-26 | MRT-DS-REC-TT-180347 | FA | 0 | TRUE | FALSE | FALSE
2388 | MRT-YT01-P3GM-128502 | 2018-04-26 | MRT-DS-REC-TT-180347 | FA | 0 | TRUE | FALSE | FALSE
2389 | MRT-YD00-P3GM-128501 | 2018-04-26 | MRT-DS-REC-TT-180347 | FA | 0 | TRUE | FALSE | FALSE
2390 | MRT-YD07-P2ZEN-163109 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2391 | MRT-YR05-P2ZEN-163110 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2392 | MRT-YR05-P2ZEN-163111 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2393 | MRT-YR05-P2ZEN-163112 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2394 | MRT-YR05-P2ZEN-163113 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2395 | MRT-YR05-P2ZEN-163114 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2396 | MRT-CV03-P3ZEN-163118 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2397 | MRT-YD07-P3ZEN-163109 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2398 | MRT-YR05-P3ZEN-163110 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2399 | MRT-YR05-P3ZEN-163111 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2400 | MRT-YR05-P3ZEN-163112 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2401 | MRT-YR05-P3ZEN-163113 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2402 | MRT-YR05-P3ZEN-163114 | 2018-04-26 | MRT-DS-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
2420 | MRT-YK10-P2MKA-220003 | 2018-04-27 | MRT-DS-REC-TT-180350 | FI | 0 | TRUE | FALSE | FALSE
2421 | MRT-YK10-P3MKA-230003 | 2018-04-27 | MRT-DS-REC-TT-180351 | FI | 0 | TRUE | FALSE | FALSE
2422 | MRT-YK10-P3MKA-230004 | 2018-04-27 | MRT-DS-REC-TT-180351 | FI | 0 | TRUE | FALSE | FALSE
2423 | MRT-XG02-P2LBA-110003 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2424 | MRT-XG02-P2LBG-110004 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2425 | MRT-XG02-P0LBG-110004 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2426 | MRT-XG02-P2LCM-110005 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2427 | MRT-XG02-P2LA-110006 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2428 | MRT-XG02-P2LC-110007 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2429 | MRT-XG02-P2PA-110002 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2430 | MRT-XG02-P0PA-110002 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2431 | MRT-XG02-P2PA-110008 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2432 | MRT-XG02-P0GHC-110002 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2433 | MRT-XG02-P2PG-110009 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2434 | MRT-XG02-P3LBA-110003 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2435 | MRT-XG02-P3LBG-110004 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2436 | MRT-XG02-P3LCM-110005 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2437 | MRT-XG02-P3LA-110006 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2438 | MRT-XG02-P3LC-110007 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2439 | MRT-XG02-P3PA-110002 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2440 | MRT-XG02-P3PA-110008 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2441 | MRT-XG02-P3PG-110009 | 2018-04-27 | MRT-DS-REC-TT-180348 | FC | 5 | TRUE | TRUE | FALSE
2442 | MRT-YK00-P3BAT-240001 | 2018-04-27 | MRT-DS-REC-TT-180352 | FA | 0 | TRUE | FALSE | FALSE
2443 | MRT-XH01-P0UZT-140000 | 2018-04-27 | MRT-DS-REC-TT-180354 | FC | 1 | TRUE | TRUE | FALSE
2444 | MRT-XK00-P0ZEN-140001 | 2018-04-27 | MRT-DS-REC-TT-180355 | FC | 1 | TRUE | TRUE | FALSE
2445 | MRT-XJ00-P2LBA-142000 | 2018-04-27 | MRT-DS-REC-TT-180356 | FI | 0 | TRUE | FALSE | FALSE
2446 | MRT-YD00-P2MKJ-220001 | 2018-04-27 | MRT-DS-REC-TT-180353 | FA | 0 | TRUE | FALSE | FALSE
2447 | MRT-YD00-P3MKW-220003 | 2018-04-27 | MRT-DS-REC-TT-180353 | FA | 0 | TRUE | FALSE | FALSE
2448 | MRT-YD00-P3MKW-220004 | 2018-04-27 | MRT-DS-REC-TT-180353 | FA | 0 | TRUE | FALSE | FALSE
2449 | MRT-YD00-P3MKG-220001 | 2018-04-27 | MRT-DS-REC-TT-180353 | FA | 0 | TRUE | FALSE | FALSE
2450 | MRT-YD00-P3MKG-220003 | 2018-04-27 | MRT-DS-REC-TT-180353 | FA | 0 | TRUE | FALSE | FALSE
2451 | MRT-YD00-P3MKG-220004 | 2018-04-27 | MRT-DS-REC-TT-180353 | FA | 0 | TRUE | FALSE | FALSE
2452 | MRT-YD00-P3MKG-220005 | 2018-04-27 | MRT-DS-REC-TT-180353 | FA | 0 | TRUE | FALSE | FALSE
2453 | MRT-YD00-P3MKG-220006 | 2018-04-27 | MRT-DS-REC-TT-180353 | FA | 0 | TRUE | FALSE | FALSE
2477 | MRT-CC04-P0ULY-176187 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2478 | MRT-CC04-P0ULY-176186 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2479 | MRT-CC04-P0ULY-176185 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2480 | MRT-CC04-P0ULY-176184 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2481 | MRT-CC04-P0ULY-176183 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2482 | MRT-CC04-P0ULY-176182 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2483 | MRT-CC04-P0ULY-176181 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2484 | MRT-CC04-P0ULY-176180 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2485 | MRT-CC04-P0ULY-176172 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2486 | MRT-CC04-P0ULY-176171 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2487 | MRT-CC04-P0ULY-176170 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2488 | MRT-CC04-P0ULY-176169 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2489 | MRT-CC04-P0ULY-176168 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2490 | MRT-CC04-P0ULY-176167 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2491 | MRT-CC04-P0ULY-176166 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2492 | MRT-CC04-P0ULY-176165 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2493 | MRT-CC04-P0ULY-176164 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2494 | MRT-CC04-P0ULY-176163 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2495 | MRT-CC04-P0ULY-176162 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2496 | MRT-CC04-P0ULY-176161 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2497 | MRT-CC04-P0ULY-176157 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2498 | MRT-CC04-P0ULY-176156 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2499 | MRT-CC04-P0ULY-176154 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2500 | MRT-CC04-P0ULY-176153 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2501 | MRT-CC04-P0ULY-176138 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2502 | MRT-CC04-P0ULY-176137 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2503 | MRT-CC04-P0ULY-176136 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2504 | MRT-CC04-P0ULY-176128 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2505 | MRT-CC04-P0ULY-176127 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2506 | MRT-CC04-P0ULY-176126 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2507 | MRT-CC04-P0ULY-176123 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2508 | MRT-CC04-P0ULY-176122 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2509 | MRT-CC04-P0ULY-176121 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2510 | MRT-CC07-P0ULY-176115 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2511 | MRT-CC02-P0ULY-176120 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2512 | MRT-CC02-P0ULY-176125 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2513 | MRT-CC04-P0ULY-176135 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2514 | MRT-CC04-P0ULY-176140 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2515 | MRT-CC04-P0ULY-176145 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2516 | MRT-CC04-P0ULY-176150 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2517 | MRT-CC04-P0ULY-176155 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2518 | MRT-CC04-P0ULY-176160 | 2018-04-28 | MRT-HK-REC-TT-180099 | FA | 0 | TRUE | TRUE | FALSE
2454 | MRT-CC07-P0UQQ-175801 | 2018-05-02 | MRT-HK-REC-TT-180100 | FA | 2 | TRUE | TRUE | FALSE
2455 | MRT-CC02-P0UQQ-175805 | 2018-05-02 | MRT-HK-REC-TT-180100 | FA | 2 | TRUE | TRUE | FALSE
2456 | MRT-CC02-P0UQQ-175810 | 2018-05-02 | MRT-HK-REC-TT-180100 | FA | 2 | TRUE | TRUE | FALSE
2457 | MRT-CC07-P0UQQ-175815 | 2018-05-02 | MRT-HK-REC-TT-180100 | FA | 2 | TRUE | TRUE | FALSE
2458 | MRT-CC07-P0UPC-175791 | 2018-05-02 | MRT-HK-REC-TT-180100 | FA | 1 | TRUE | TRUE | FALSE
2459 | MRT-CC07-P0UPC-175792 | 2018-05-02 | MRT-HK-REC-TT-180100 | FA | 1 | TRUE | TRUE | FALSE
2460 | MRT-CC02-P0UPC-175781 | 2018-05-02 | MRT-HK-REC-TT-180100 | FA | 1 | TRUE | TRUE | FALSE
2461 | MRT-YD00-P2GM-128503 | 2018-05-02 | MRT-DS-REC-TT-180359 | FI | 0 | TRUE | FALSE | FALSE
2462 | MRT-YD00-P3GM-128503 | 2018-05-02 | MRT-DS-REC-TT-180359 | FI | 0 | TRUE | FALSE | FALSE
2463 | MRT-YD00-P0SMM-128001 | 2018-05-02 | MRT-DS-REC-TT-180358 | FC | 3 | TRUE | TRUE | FALSE
2464 | MRT-YF00-P2MKC-230011 | 2018-05-03 | MRT-DS-REC-TT-180360 | FI | 0 | TRUE | FALSE | FALSE
2465 | MRT-YS01-P2MKC-230012 | 2018-05-03 | MRT-DS-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
2466 | MRT-YS01-P2MKC-230013 | 2018-05-03 | MRT-DS-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
2467 | MRT-YF00-P3MKC-230011 | 2018-05-03 | MRT-DS-REC-TT-180360 | FI | 0 | TRUE | FALSE | FALSE
2468 | MRT-YS01-P3MKC-230012 | 2018-05-03 | MRT-DS-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
2469 | MRT-YS01-P3MKC-230013 | 2018-05-03 | MRT-DS-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
2470 | MRT-YS01-P2MKC-230014 | 2018-05-03 | MRT-DS-REC-TT-180361 | FA | 0 | TRUE | FALSE | FALSE
2471 | MRT-YS01-P3MKC-230014 | 2018-05-03 | MRT-DS-REC-TT-180361 | FA | 0 | TRUE | FALSE | FALSE
2472 | MRT-XW01-P2SCA-127504 | 2018-05-03 | MRT-DS-REC-TT-180349 | FC | 1 | TRUE | TRUE | FALSE
2473 | MRT-YS01-P2SCA-127511 | 2018-05-03 | MRT-DS-REC-TT-180349 | FI | 0 | TRUE | FALSE | FALSE
2474 | MRT-XW01-P3SCA-127504 | 2018-05-03 | MRT-DS-REC-TT-180349 | FC | 1 | TRUE | TRUE | FALSE
2475 | MRT-YS01-P3SCA-127511 | 2018-05-03 | MRT-DS-REC-TT-180349 | FI | 0 | TRUE | FALSE | FALSE
2476 | MRT-YU02-P0ABA-150026 | 2018-05-03 | MRT-HK-REC-TT-180101 | FA | 2 | TRUE | TRUE | FALSE
2519 | MRT-CC07-P2UEJ-170901 | 2018-05-03 | MRT-DS-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
2520 | MRT-CC02-P2UEJ-170907 | 2018-05-03 | MRT-DS-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
2521 | MRT-VK02-P2UEJ-170910 | 2018-05-03 | MRT-DS-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
2522 | MRT-CC07-P3UEJ-170901 | 2018-05-03 | MRT-DS-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
2523 | MRT-CC02-P3UEJ-170907 | 2018-05-03 | MRT-DS-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
2524 | MRT-VK02-P3UEJ-170910 | 2018-05-03 | MRT-DS-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
2525 | MRT-XW03-P3MKA-210001 | 2018-05-04 | MRT-DS-REC-TT-180363 | FI | 0 | TRUE | FALSE | FALSE
2526 | MRT-CC07-P2UMA-170501 | 2018-05-04 | MRT-DS-REC-TT-180364 | FC | 3 | TRUE | TRUE | FALSE
2527 | MRT-CC02-P2UMA-170507 | 2018-05-04 | MRT-DS-REC-TT-180364 | FC | 3 | TRUE | TRUE | FALSE
2528 | MRT-VK02-P2UMA-170510 | 2018-05-04 | MRT-DS-REC-TT-180364 | FC | 3 | TRUE | TRUE | FALSE
2529 | MRT-CC07-P3UMA-170501 | 2018-05-04 | MRT-DS-REC-TT-180364 | FC | 3 | TRUE | TRUE | FALSE
2530 | MRT-CC02-P3UMA-170507 | 2018-05-04 | MRT-DS-REC-TT-180364 | FC | 3 | TRUE | TRUE | FALSE
2531 | MRT-VK02-P3UMA-170510 | 2018-05-04 | MRT-DS-REC-TT-180364 | FC | 3 | TRUE | TRUE | FALSE
2532 | MRT-CC02-P0UMA-170502 | 2018-05-04 | MRT-DS-REC-TT-180364 | FC | 3 | TRUE | TRUE | FALSE
2533 | MRT-YT02-P2LAC-126011 | 2018-05-04 | MRT-DS-REC-TT-180365 | FI | 0 | TRUE | FALSE | FALSE
2534 | MRT-YT02-P3LAC-126011 | 2018-05-04 | MRT-DS-REC-TT-180365 | FI | 0 | TRUE | FALSE | FALSE
2535 | MRT-YT02-P2LAC-126061 | 2018-05-04 | MRT-DS-REC-TT-180365 | FI | 0 | TRUE | FALSE | FALSE
2536 | MRT-YT02-P3LAC-126061 | 2018-05-04 | MRT-DS-REC-TT-180365 | FI | 0 | TRUE | FALSE | FALSE
2537 | MRT-DF04-P2ZEN-142004 | 2018-05-08 | MRT-DS-REC-TT-180366 | FI | 0 | TRUE | FALSE | FALSE
2538 | MRT-YL01-P2ZEN-165021 | 2018-05-08 | MRT-HK-REC-TT-180102 | FA | 0 | TRUE | FALSE | FALSE
2539 | MRT-YL01-P3ZEN-165022 | 2018-05-08 | MRT-HK-REC-TT-180102 | FA | 0 | TRUE | FALSE | FALSE
2540 | MRT-CC07-P2UMA-170801 | 2018-05-08 | MRT-DS-REC-TT-180367 | FA | 2 | TRUE | TRUE | FALSE
2541 | MRT-CC02-P2UMA-170803 | 2018-05-08 | MRT-DS-REC-TT-180367 | FA | 2 | TRUE | TRUE | FALSE
2542 | MRT-VK02-P2UMA-170806 | 2018-05-08 | MRT-DS-REC-TT-180367 | FA | 2 | TRUE | TRUE | FALSE
2543 | MRT-CC07-P3UMA-170801 | 2018-05-08 | MRT-DS-REC-TT-180367 | FA | 2 | TRUE | TRUE | FALSE
2544 | MRT-CC02-P3UMA-170803 | 2018-05-08 | MRT-DS-REC-TT-180367 | FA | 2 | TRUE | TRUE | FALSE
2545 | MRT-VK02-P3UMA-170806 | 2018-05-08 | MRT-DS-REC-TT-180367 | FA | 2 | TRUE | TRUE | FALSE
2546 | MRT-YS01-P0ZEN-165013 | 2018-05-08 | MRT-HK-REC-TT-180103 | FA | 2 | TRUE | TRUE | FALSE
2547 | MRT-YD00-P2MKA-220003 | 2018-05-08 | MRT-DS-REC-TT-180368 | FC | 3 | TRUE | TRUE | FALSE
2548 | MRT-XA01-P0ABA-150502 | 2018-05-09 | MRT-HK-REC-TT-180104 | FA | 1 | TRUE | TRUE | FALSE
2549 | MRT-YL15-P0ZEN-165025 | 2018-05-09 | MRT-HK-REC-TT-180105 | FA | 0 | TRUE | FALSE | FALSE
2550 | MRT-XA01-P0ABA-150503 | 2018-05-10 | MRT-HK-REC-TT-180104 | FA | 1 | TRUE | TRUE | FALSE
2551 | MRT-XG02-P2QU-130024 | 2018-05-10 | MRT-DS-REC-TT-180357 | FA | 1 | TRUE | TRUE | FALSE
2552 | MRT-XA00-P2QU-130025 | 2018-05-10 | MRT-DS-REC-TT-180357 | FA | 1 | TRUE | TRUE | FALSE
2553 | MRT-XS00-P2QU-130026 | 2018-05-10 | MRT-DS-REC-TT-180357 | FA | 1 | TRUE | TRUE | FALSE
2554 | MRT-XG02-P3QU-130024 | 2018-05-10 | MRT-DS-REC-TT-180357 | FA | 1 | TRUE | TRUE | FALSE
2555 | MRT-XA00-P3QU-130025 | 2018-05-10 | MRT-DS-REC-TT-180357 | FA | 1 | TRUE | TRUE | FALSE
2556 | MRT-XS00-P3QU-130026 | 2018-05-10 | MRT-DS-REC-TT-180357 | FA | 1 | TRUE | TRUE | FALSE
2557 | MRT-YK09-P2MKC-230006 | 2018-05-10 | MRT-DS-REC-TT-180374 | FA | 0 | TRUE | FALSE | FALSE
2558 | MRT-YK09-P3MKC-230006 | 2018-05-10 | MRT-DS-REC-TT-180374 | FA | 0 | TRUE | FALSE | FALSE
2559 | MRT-CQ02-P2QU-130035 | 2018-05-10 | MRT-DS-REC-TT-180373 | FI | 0 | TRUE | FALSE | FALSE
2560 | MRT-CQ02-P3QU-130035 | 2018-05-10 | MRT-DS-REC-TT-180373 | FI | 0 | TRUE | FALSE | FALSE
2561 | MRT-YK10-P2QC-130010 | 2018-05-10 | MRT-DS-REC-TT-180375 | FI | 0 | TRUE | FALSE | FALSE
2562 | MRT-YK10-P3QC-130010 | 2018-05-10 | MRT-DS-REC-TT-180375 | FI | 0 | TRUE | FALSE | FALSE
2563 | MRT-YV02-P2QC-130017 | 2018-05-10 | MRT-DS-REC-TT-180377 | FI | 0 | TRUE | FALSE | FALSE
2564 | MRT-YV02-P3QC-130017 | 2018-05-10 | MRT-DS-REC-TT-180377 | FI | 0 | TRUE | FALSE | FALSE
2565 | MRT-YK08-P2ZEN-111200 | 2018-05-10 | MRT-DS-REC-TT-180370 | FC | 1 | TRUE | TRUE | FALSE
2566 | MRT-YT01-P2ZEN-111201 | 2018-05-10 | MRT-DS-REC-TT-180370 | FC | 1 | TRUE | TRUE | FALSE
2567 | MRT-YK08-P3ZEN-111200 | 2018-05-10 | MRT-DS-REC-TT-180370 | FC | 1 | TRUE | TRUE | FALSE
2568 | MRT-YT01-P3ZEN-111201 | 2018-05-10 | MRT-DS-REC-TT-180370 | FC | 1 | TRUE | TRUE | FALSE
2569 | MRT-YD00-P2LAC-126007 | 2018-05-10 | MRT-DS-REC-TT-180378 | FC | 1 | TRUE | TRUE | FALSE
2570 | MRT-YD00-P3LAC-126007 | 2018-05-10 | MRT-DS-REC-TT-180378 | FC | 1 | TRUE | TRUE | FALSE
2571 | MRT-YD00-P2LAC-126057 | 2018-05-10 | MRT-DS-REC-TT-180378 | FC | 1 | TRUE | TRUE | FALSE
2572 | MRT-YD00-P3LAC-126057 | 2018-05-10 | MRT-DS-REC-TT-180378 | FC | 1 | TRUE | TRUE | FALSE
2573 | MRT-YK01-P2LAC-126006 | 2018-05-10 | MRT-DS-REC-TT-180380 | FC | 1 | TRUE | TRUE | FALSE
2574 | MRT-YK01-P3LAC-126006 | 2018-05-10 | MRT-DS-REC-TT-180380 | FC | 1 | TRUE | TRUE | FALSE
2575 | MRT-YK01-P2LAC-126056 | 2018-05-10 | MRT-DS-REC-TT-180380 | FC | 1 | TRUE | TRUE | FALSE
2576 | MRT-YK01-P3LAC-126056 | 2018-05-10 | MRT-DS-REC-TT-180380 | FC | 1 | TRUE | TRUE | FALSE
2577 | MRT-YD05-P2QC-130035 | 2018-05-10 | MRT-DS-REC-TT-180381 | FI | 0 | TRUE | FALSE | FALSE
2578 | MRT-YD05-P3QC-130035 | 2018-05-10 | MRT-DS-REC-TT-180381 | FI | 0 | TRUE | FALSE | FALSE
2579 | MRT-YK08-P2LAA-605100 | 2018-05-10 | MRT-DS-REC-TT-180384 | FC | 4 | TRUE | TRUE | FALSE
2580 | MRT-YK08-P3LAA-605500 | 2018-05-10 | MRT-DS-REC-TT-180384 | FC | 4 | TRUE | TRUE | FALSE
2581 | MRT-XK00-P2GM-128508 | 2018-05-10 | MRT-DS-REC-TT-180371 | FA | 2 | TRUE | TRUE | FALSE
2582 | MRT-XK00-P3GM-128508 | 2018-05-10 | MRT-DS-REC-TT-180371 | FA | 2 | TRUE | TRUE | FALSE
2583 | MRT-YT01-P2LAA-605101 | 2018-05-10 | MRT-DS-REC-TT-180383 | FC | 4 | TRUE | TRUE | FALSE
2584 | MRT-YT01-P3LAA-605501 | 2018-05-10 | MRT-DS-REC-TT-180383 | FC | 4 | TRUE | TRUE | FALSE
2585 | MRT-YD00-P2PGB-113201 | 2018-05-11 | MRT-DS-REC-TT-180385 | FC | 3 | TRUE | TRUE | FALSE
2586 | MRT-YD00-P3PGB-113201 | 2018-05-11 | MRT-DS-REC-TT-180385 | FC | 3 | TRUE | TRUE | FALSE
2587 | MRT-YK10-P2PGB-113103 | 2018-05-11 | MRT-DS-REC-TT-180386 | FC | 1 | TRUE | TRUE | FALSE
2588 | MRT-YK10-P3PGB-113103 | 2018-05-11 | MRT-DS-REC-TT-180386 | FC | 1 | TRUE | TRUE | FALSE
2589 | MRT-YD00-P3MKW-220001 | 2018-05-11 | MRT-DS-REC-TT-180372 | FA | 0 | TRUE | FALSE | FALSE
2590 | MRT-YD00-P3MKW-220005 | 2018-05-11 | MRT-DS-REC-TT-180372 | FA | 0 | TRUE | FALSE | FALSE
2591 | MRT-YL00-P2GHC-129011 | 2018-05-11 | MRT-DS-REC-TT-180382 | FI | 0 | TRUE | FALSE | FALSE
2592 | MRT-YL00-P3GHC-129011 | 2018-05-11 | MRT-DS-REC-TT-180382 | FI | 0 | TRUE | FALSE | FALSE
2593 | MRT-YE00-P2QC-130021 | 2018-05-11 | MRT-DS-REC-TT-180387 | FI | 0 | TRUE | FALSE | FALSE
2594 | MRT-YE00-P3QC-130021 | 2018-05-11 | MRT-DS-REC-TT-180387 | FI | 0 | TRUE | FALSE | FALSE
2595 | MRT-YD00-P3LAC-126017 | 2018-05-11 | MRT-DS-REC-TT-180388 | FA | 0 | TRUE | FALSE | FALSE
2596 | MRT-YD00-P2LAC-126017 | 2018-05-11 | MRT-DS-REC-TT-180388 | FA | 0 | TRUE | FALSE | FALSE
2597 | MRT-YD00-P2LAC-126065 | 2018-05-11 | MRT-DS-REC-TT-180388 | FA | 0 | TRUE | FALSE | FALSE
2598 | MRT-YD00-P3LAC-126065 | 2018-05-11 | MRT-DS-REC-TT-180388 | FA | 0 | TRUE | FALSE | FALSE
2599 | MRT-YB03-P2PAH-604123 | 2018-05-11 | MRT-DS-REC-TT-180390 | FC | 3 | TRUE | TRUE | FALSE
2600 | MRT-XG02-P2PAH-604102 | 2018-05-11 | MRT-DS-REC-TT-180391 | FC | 2 | TRUE | TRUE | FALSE
2601 | MRT-YK08-P2PAH-604103 | 2018-05-11 | MRT-DS-REC-TT-180391 | FC | 2 | TRUE | TRUE | FALSE
2602 | MRT-YK08-P2PAH-604104 | 2018-05-11 | MRT-DS-REC-TT-180391 | FC | 2 | TRUE | TRUE | FALSE
2603 | MRT-XG02-P2PBB-604112 | 2018-05-11 | MRT-DS-REC-TT-180391 | FC | 2 | TRUE | TRUE | FALSE
2604 | MRT-YK08-P2PBB-604113 | 2018-05-11 | MRT-DS-REC-TT-180391 | FC | 2 | TRUE | TRUE | FALSE
2605 | MRT-XG02-P3PAH-604502 | 2018-05-11 | MRT-DS-REC-TT-180391 | FC | 2 | TRUE | TRUE | FALSE
2606 | MRT-YK08-P3PAH-604503 | 2018-05-11 | MRT-DS-REC-TT-180391 | FC | 2 | TRUE | TRUE | FALSE
2607 | MRT-YK08-P3PAH-604504 | 2018-05-11 | MRT-DS-REC-TT-180391 | FC | 2 | TRUE | TRUE | FALSE
2608 | MRT-XG02-P3PBB-604512 | 2018-05-11 | MRT-DS-REC-TT-180391 | FC | 2 | TRUE | TRUE | FALSE
2609 | MRT-YK08-P3PBB-604513 | 2018-05-11 | MRT-DS-REC-TT-180391 | FC | 2 | TRUE | TRUE | FALSE
2610 | MRT-YT01-P2PAH-604101 | 2018-05-11 | MRT-DS-REC-TT-180392 | FC | 2 | TRUE | TRUE | FALSE
2611 | MRT-YT01-P2PBB-604111 | 2018-05-11 | MRT-DS-REC-TT-180392 | FC | 2 | TRUE | TRUE | FALSE
2612 | MRT-YT01-P3PAH-604501 | 2018-05-11 | MRT-DS-REC-TT-180392 | FC | 2 | TRUE | TRUE | FALSE
2613 | MRT-YT01-P3PBB-604511 | 2018-05-11 | MRT-DS-REC-TT-180392 | FC | 2 | TRUE | TRUE | FALSE
2614 | MRT-YF00-P2CBA-161203 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2615 | MRT-YF00-P2CGA-161303 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2616 | MRT-YF00-P3CBA-161203 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2617 | MRT-YF00-P3CGA-161303 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2618 | MRT-YF00-P2CBA-161204 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2619 | MRT-YF00-P2CGA-161304 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2620 | MRT-YF00-P3CBA-161204 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2621 | MRT-YF00-P3CGA-161304 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2622 | MRT-YF00-P2CBA-161205 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2623 | MRT-YF00-P2CGA-161305 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2624 | MRT-YF00-P3CBA-161205 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2625 | MRT-YF00-P3CGA-161305 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2626 | MRT-YF00-P2CBA-161206 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2627 | MRT-YF00-P2CGA-161306 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2628 | MRT-YF00-P3CBA-161206 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2629 | MRT-YF00-P3CGA-161306 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2630 | MRT-YF00-P2CBA-161207 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2631 | MRT-YF00-P2CGA-161307 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2632 | MRT-YF00-P3CBA-161207 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2633 | MRT-YF00-P3CGA-161307 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2634 | MRT-YF00-P2CBA-161208 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2635 | MRT-YF00-P2CGA-161308 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2636 | MRT-YF00-P3CBA-161208 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2637 | MRT-YF00-P3CGA-161308 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2638 | MRT-YF00-P0CBA-161221 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2639 | MRT-YF00-P0CGA-161321 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2640 | MRT-YF00-P2CBA-161209 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2641 | MRT-YF00-P2CGA-161309 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2642 | MRT-YF00-P3CBA-161209 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2643 | MRT-YF00-P3CGA-161309 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2644 | MRT-YF00-P0CBA-161222 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2645 | MRT-YF00-P0CGA-161322 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2646 | MRT-YF00-P2CBA-161211 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2647 | MRT-YF00-P2CBA-161212 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2648 | MRT-YF00-P2CBA-161210 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2649 | MRT-YF00-P2CGA-161311 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2650 | MRT-YF00-P2CGA-161312 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2651 | MRT-YF00-P2CGA-161310 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2652 | MRT-YF00-P3CBA-161211 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2653 | MRT-YF00-P3CBA-161212 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2654 | MRT-YF00-P3CBA-161210 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2655 | MRT-YF00-P3CGA-161311 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2656 | MRT-YF00-P3CGA-161312 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2657 | MRT-YF00-P3CGA-161310 | 2018-05-11 | MRT-DS-REC-TT-180376 | FA | 1 | TRUE | TRUE | FALSE
2658 | MRT-YF00-P0CBA-161201 | 2018-05-11 | MRT-DS-REC-TT-180376 | FC | 1 | TRUE | TRUE | FALSE
2659 | MRT-YF00-P0CBA-161202 | 2018-05-11 | MRT-DS-REC-TT-180376 | FC | 1 | TRUE | TRUE | FALSE
2660 | MRT-YF00-P0CGA-161301 | 2018-05-11 | MRT-DS-REC-TT-180376 | FC | 1 | TRUE | TRUE | FALSE
2661 | MRT-YF00-P0CGA-161302 | 2018-05-11 | MRT-DS-REC-TT-180376 | FC | 1 | TRUE | TRUE | FALSE
2662 | MRT-CC02-P0UQQ-175805 | 2018-05-14 | MRT-HK-REC-TT-180106 | FA | 2 | TRUE | TRUE | FALSE
2663 | MRT-XK00-P2GM-128504 | 2018-05-15 | MRT-DS-REC-TT-180395 | FI | 0 | TRUE | FALSE | FALSE
2664 | MRT-XK00-P3GM-128504 | 2018-05-15 | MRT-DS-REC-TT-180395 | FI | 0 | TRUE | FALSE | FALSE
2665 | MRT-XB00-P2LAC-126022 | 2018-05-15 | MRT-DS-REC-TT-180396 | FC | 1 | TRUE | TRUE | FALSE
2666 | MRT-XB00-P3LAC-126022 | 2018-05-15 | MRT-DS-REC-TT-180396 | FC | 1 | TRUE | TRUE | FALSE
2667 | MRT-XB00-P2LAC-126070 | 2018-05-15 | MRT-DS-REC-TT-180396 | FC | 1 | TRUE | TRUE | FALSE
2668 | MRT-XB00-P3LAC-126070 | 2018-05-15 | MRT-DS-REC-TT-180396 | FC | 1 | TRUE | TRUE | FALSE
2669 | MRT-YV02-P2MAJ-603202 | 2018-05-15 | MRT-DS-REC-TT-180393 | FC | 2 | TRUE | TRUE | FALSE
2670 | MRT-YK08-P2MAJ-603203 | 2018-05-15 | MRT-DS-REC-TT-180393 | FC | 1 | TRUE | TRUE | FALSE
2671 | MRT-YV02-P3MAJ-604202 | 2018-05-15 | MRT-DS-REC-TT-180393 | FC | 2 | TRUE | TRUE | FALSE
2672 | MRT-YK08-P3MAJ-604203 | 2018-05-15 | MRT-DS-REC-TT-180393 | FC | 1 | TRUE | TRUE | FALSE
2673 | MRT-CC02-P0UZT-175992 | 2018-05-15 | MRT-HK-REC-TT-180107 | FA | 0 | TRUE | FALSE | FALSE
2674 | MRT-YL22-P2QC-130018 | 2018-05-15 | MRT-DS-REC-TT-180397 | FI | 0 | TRUE | FALSE | FALSE
2675 | MRT-YL22-P3QC-130018 | 2018-05-15 | MRT-DS-REC-TT-180397 | FI | 0 | TRUE | FALSE | FALSE
2676 | MRT-YL01-P2QC-130034 | 2018-05-15 | MRT-DS-REC-TT-180398 | FI | 0 | TRUE | FALSE | FALSE
2677 | MRT-YL01-P3QC-130034 | 2018-05-15 | MRT-DS-REC-TT-180398 | FI | 0 | TRUE | FALSE | FALSE
2678 | MRT-YK00-P2QC-130022 | 2018-05-15 | MRT-DS-REC-TT-180399 | FI | 0 | TRUE | FALSE | FALSE
2679 | MRT-YK00-P3QC-130022 | 2018-05-15 | MRT-DS-REC-TT-180399 | FI | 0 | TRUE | FALSE | FALSE
2680 | MRT-YK09-P0SMM-128007 | 2018-05-15 | MRT-DS-REC-TT-180400 | FC | 1 | TRUE | TRUE | FALSE
2681 | MRT-YD05-P2SCA-127515 | 2018-05-15 | MRT-DS-REC-TT-180389 | FA | 0 | TRUE | FALSE | FALSE
2682 | MRT-YD05-P3SCA-127515 | 2018-05-15 | MRT-DS-REC-TT-180389 | FA | 0 | TRUE | FALSE | FALSE
2683 | MRT-YS01-P2QC-130020 | 2018-05-15 | MRT-DS-REC-TT-180379 | FI | 0 | TRUE | FALSE | FALSE
2684 | MRT-YS01-P3QC-130020 | 2018-05-15 | MRT-DS-REC-TT-180379 | FI | 0 | TRUE | FALSE | FALSE
2685 | MRT-YT01-P2QC-130013 | 2018-05-16 | MRT-DS-REC-TT-180403 | FI | 0 | TRUE | FALSE | FALSE
2686 | MRT-YT01-P3QC-130013 | 2018-05-16 | MRT-DS-REC-TT-180403 | FI | 0 | TRUE | FALSE | FALSE
2687 | MRT-YT01-P2QC-130016 | 2018-05-16 | MRT-DS-REC-TT-180404 | FI | 0 | TRUE | FALSE | FALSE
2688 | MRT-YT01-P3QC-130016 | 2018-05-16 | MRT-DS-REC-TT-180404 | FI | 0 | TRUE | FALSE | FALSE
2689 | MRT-YS18-P0SMM-128010 | 2018-05-16 | MRT-DS-REC-TT-180401 | FI | 1 | TRUE | TRUE | FALSE
2690 | MRT-YF00-P2QC-130019 | 2018-05-16 | MRT-DS-REC-TT-180405 | FI | 0 | TRUE | FALSE | FALSE
2691 | MRT-YF00-P3QC-130019 | 2018-05-16 | MRT-DS-REC-TT-180405 | FI | 0 | TRUE | FALSE | FALSE
2692 | MRT-XW03-P0BAT-150005 | 2018-05-16 | MRT-HK-REC-TT-180108 | FA | 1 | TRUE | TRUE | FALSE
2693 | MRT-XW03-P0BAA-150006 | 2018-05-16 | MRT-HK-REC-TT-180108 | FA | 1 | TRUE | TRUE | FALSE
2694 | MRT-YD00-P2SM-128020 | 2018-05-17 | MRT-DS-REC-TT-180402 | FI | 0 | TRUE | TRUE | FALSE
2695 | MRT-YD00-P3SM-128020 | 2018-05-17 | MRT-DS-REC-TT-180402 | FI | 0 | TRUE | TRUE | FALSE
2696 | MRT-YT01-P2SM-128030 | 2018-05-17 | MRT-DS-REC-TT-180402 | FI | 0 | TRUE | TRUE | FALSE
2697 | MRT-YT01-P3SM-128030 | 2018-05-17 | MRT-DS-REC-TT-180402 | FI | 0 | TRUE | TRUE | FALSE
2698 | MRT-YK09-P2SM-128040 | 2018-05-17 | MRT-DS-REC-TT-180402 | FI | 0 | TRUE | TRUE | FALSE
2699 | MRT-YK09-P3SM-128040 | 2018-05-17 | MRT-DS-REC-TT-180402 | FI | 0 | TRUE | TRUE | FALSE
2700 | MRT-YD16-P2SCA-127531 | 2018-05-17 | MRT-DS-REC-TT-180407 | FA | 1 | TRUE | TRUE | FALSE
2701 | MRT-YD16-P3SCA-127531 | 2018-05-17 | MRT-DS-REC-TT-180407 | FA | 1 | TRUE | TRUE | FALSE
2702 | MRT-YK00-P2SCA-127521 | 2018-05-17 | MRT-DS-REC-TT-180406 | FI | 0 | TRUE | FALSE | FALSE
2703 | MRT-YK00-P3SCA-127521 | 2018-05-17 | MRT-DS-REC-TT-180406 | FI | 0 | TRUE | FALSE | FALSE
2704 | MRT-YK08-P2MAJ-603200 | 2018-05-17 | MRT-DS-REC-TT-180394 | FC | 2 | TRUE | TRUE | FALSE
2705 | MRT-XG02-P2MAJ-603201 | 2018-05-17 | MRT-DS-REC-TT-180394 | FA | 2 | TRUE | TRUE | FALSE
2706 | MRT-YT01-P2MAJ-603204 | 2018-05-17 | MRT-DS-REC-TT-180394 | FC | 2 | TRUE | TRUE | FALSE
2707 | MRT-XS00-P2MAJ-603209 | 2018-05-17 | MRT-DS-REC-TT-180394 | FI | 1 | TRUE | TRUE | FALSE
2708 | MRT-YK08-P3MAJ-604200 | 2018-05-17 | MRT-DS-REC-TT-180394 | FC | 2 | TRUE | TRUE | FALSE
2709 | MRT-XG02-P3MAJ-604201 | 2018-05-17 | MRT-DS-REC-TT-180394 | FA | 2 | TRUE | TRUE | FALSE
2710 | MRT-YT01-P3MAJ-604204 | 2018-05-17 | MRT-DS-REC-TT-180394 | FC | 2 | TRUE | TRUE | FALSE
2711 | MRT-XS00-P3MAJ-604209 | 2018-05-17 | MRT-DS-REC-TT-180394 | FI | 1 | TRUE | TRUE | FALSE
2712 | MRT-YS05-P0ZEN-165014 | 2018-05-18 | MRT-HK-REC-TT-180109 | FA | 1 | TRUE | TRUE | FALSE
2713 | MRT-CQ02-P2MAJ-603208 | 2018-05-18 | MRT-DS-REC-TT-180408 | FI | 0 | TRUE | FALSE | FALSE
2714 | MRT-CQ02-P3MAJ-604208 | 2018-05-18 | MRT-DS-REC-TT-180408 | FI | 0 | TRUE | FALSE | FALSE
2715 | MRT-YE00-P3MKA-230001 | 2018-05-18 | MRT-DS-REC-TT-180409 | FA | 0 | TRUE | FALSE | FALSE
2716 | MRT-YF00-P0CJD-161401 | 2018-05-18 | MRT-DS-REC-TT-180410 | FA | 0 | TRUE | FALSE | FALSE
2717 | MRT-YF00-P2CJD-161402 | 2018-05-18 | MRT-DS-REC-TT-180410 | FA | 0 | TRUE | FALSE | FALSE
2718 | MRT-YF00-P2CJD-161403 | 2018-05-18 | MRT-DS-REC-TT-180410 | FA | 0 | TRUE | FALSE | FALSE
2719 | MRT-YF00-P3CJD-161402 | 2018-05-18 | MRT-DS-REC-TT-180410 | FA | 0 | TRUE | FALSE | FALSE
2720 | MRT-YF00-P3CJD-161403 | 2018-05-18 | MRT-DS-REC-TT-180410 | FA | 0 | TRUE | FALSE | FALSE
2721 | MRT-YK08-P2LBG-111300 | 2018-05-18 | MRT-DS-REC-TT-180413 | FI | 0 | TRUE | FALSE | FALSE
2722 | MRT-YT01-P2LBG-111301 | 2018-05-18 | MRT-DS-REC-TT-180413 | FA | 0 | TRUE | FALSE | FALSE
2723 | MRT-YK08-P3LBG-111300 | 2018-05-18 | MRT-DS-REC-TT-180413 | FI | 0 | TRUE | FALSE | FALSE
2724 | MRT-YT01-P3LBG-111301 | 2018-05-18 | MRT-DS-REC-TT-180413 | FA | 0 | TRUE | FALSE | FALSE
2725 | MRT-CC02-P0UPC-175750 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2726 | MRT-CC02-P0UPC-175751 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2727 | MRT-CC02-P0UPC-175752 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2728 | MRT-CC02-P0UPC-175753 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2729 | MRT-CC02-P0UPC-175755 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2730 | MRT-CC02-P0UPC-175756 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2731 | MRT-CC02-P0UPC-175757 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2732 | MRT-CC02-P0UPC-175758 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2733 | MRT-CC02-P0UPC-175759 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2734 | MRT-CC02-P0UPC-175760 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2735 | MRT-CC02-P0UPC-175761 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2736 | MRT-CC02-P0UPC-175762 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2737 | MRT-CC02-P0UPC-175763 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2738 | MRT-CC02-P0UPC-175764 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2739 | MRT-CC02-P0UPC-175765 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2740 | MRT-CC02-P0UPC-175766 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2741 | MRT-CC02-P0UPC-175767 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2742 | MRT-CC02-P0UPC-175768 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2743 | MRT-CC02-P0UPC-175769 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2744 | MRT-CC02-P0UPC-175770 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2745 | MRT-CC02-P0UPC-175771 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2746 | MRT-CC02-P0UPC-175754 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2747 | MRT-CC02-P0UPC-175772 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2748 | MRT-CC02-P0UPC-175773 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2749 | MRT-CC02-P0UPC-175774 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2750 | MRT-CC02-P0UPC-175775 | 2018-05-23 | MRT-HK-REC-TT-180111 | FA | 1 | TRUE | TRUE | FALSE
2751 | MRT-CC02-P3UMA-170207 | 2018-05-23 | MRT-DS-REC-TT-180411 | FC | 2 | TRUE | TRUE | FALSE
2752 | MRT-CC02-P3UMA-170208 | 2018-05-23 | MRT-DS-REC-TT-180411 | FC | 2 | TRUE | TRUE | FALSE
2753 | MRT-CC02-P3UMA-170209 | 2018-05-23 | MRT-DS-REC-TT-180411 | FC | 2 | TRUE | TRUE | FALSE
2754 | MRT-VK02-P3UMA-170210 | 2018-05-23 | MRT-DS-REC-TT-180412 | FA | 1 | TRUE | TRUE | FALSE
2755 | MRT-CC07-P0UQQ-175801 | 2018-05-23 | MRT-HK-REC-TT-180113 | FA | 3 | TRUE | TRUE | FALSE
2756 | MRT-CC02-P0UQQ-175805 | 2018-05-23 | MRT-HK-REC-TT-180113 | FA | 3 | TRUE | TRUE | FALSE
2757 | MRT-CC07-P0UQQ-175815 | 2018-05-23 | MRT-HK-REC-TT-180113 | FA | 3 | TRUE | TRUE | FALSE
2758 | MRT-QM03-P0ZEN-045005 | 2018-05-23 | MRT-HK-REC-TT-180110 | FA | 0 | TRUE | FALSE | FALSE
2759 | MRT-QMO3-P0ZEN-185003 | 2018-05-23 | MRT-HK-REC-TT-180112 | FA | 0 | TRUE | FALSE | FALSE
2760 | MRT-QMO3-P0ZEN-185002 | 2018-05-23 | MRT-HK-REC-TT-180112 | FA | 0 | TRUE | FALSE | FALSE
2761 | MRT-QM03-P0ZEN-185004 | 2018-05-23 | MRT-HK-REC-TT-180112 | FA | 0 | TRUE | FALSE | FALSE
2762 | MRT-QM03-P0ZEN-185001 | 2018-05-23 | MRT-HK-REC-TT-180112 | FA | 0 | TRUE | FALSE | FALSE
2763 | MRT-XA01-P0ASA-150504 | 2018-05-23 | MRT-HK-REC-TT-180115 | FA | 0 | TRUE | FALSE | FALSE
2764 | MRT-VN03-P2LB-122015 | 2018-05-24 | MRT-DS-REC-TT-180414 | FI | 1 | TRUE | TRUE | FALSE
2765 | MRT-VN03-P3LB-122015 | 2018-05-24 | MRT-DS-REC-TT-180414 | FI | 1 | TRUE | TRUE | FALSE
2766 | MRT-CA05-P0UMA-180061 | 2018-05-24 | MRT-DS-REC-TT-180415 | FC | 3 | TRUE | TRUE | FALSE
2767 | MRT-CA05-P0UMA-180062 | 2018-05-24 | MRT-DS-REC-TT-180415 | FC | 3 | TRUE | TRUE | FALSE
2768 | MRT-XG02-P2QC-130001 | 2018-05-24 | MRT-DS-REC-TT-180418 | FA | 1 | TRUE | TRUE | FALSE
2769 | MRT-XS00-P2QC-130003 | 2018-05-24 | MRT-DS-REC-TT-180418 | FI | 1 | TRUE | TRUE | FALSE
2770 | MRT-CC07-P2QC-130004 | 2018-05-24 | MRT-DS-REC-TT-180418 | FI | 1 | TRUE | TRUE | FALSE
2771 | MRT-XG02-P3QC-130001 | 2018-05-24 | MRT-DS-REC-TT-180418 | FA | 1 | TRUE | TRUE | FALSE
2772 | MRT-XS00-P3QC-130003 | 2018-05-24 | MRT-DS-REC-TT-180418 | FI | 1 | TRUE | TRUE | FALSE
2773 | MRT-CC07-P3QC-130004 | 2018-05-24 | MRT-DS-REC-TT-180418 | FI | 1 | TRUE | TRUE | FALSE
2774 | MRT-XK00-P2LAC-126014 | 2018-05-24 | MRT-DS-REC-TT-180417 | FA | 0 | TRUE | FALSE | FALSE
2775 | MRT-XK00-P3LAC-126014 | 2018-05-24 | MRT-DS-REC-TT-180417 | FA | 0 | TRUE | FALSE | FALSE
2776 | MRT-YS18-P2SM-128050 | 2018-05-24 | MRT-DS-REC-TT-180420 | FI | 0 | TRUE | FALSE | FALSE
2777 | MRT-YS18-P3SM-128050 | 2018-05-24 | MRT-DS-REC-TT-180420 | FI | 0 | TRUE | FALSE | FALSE
2778 | MRT-QM00-P0H-040003 | 2018-05-24 | MRT-DS-REC-TT-180419 | FA | 0 | TRUE | FALSE | FALSE
2779 | MRT-QM00-P0H-040004 | 2018-05-24 | MRT-DS-REC-TT-180419 | FA | 0 | TRUE | FALSE | FALSE
2780 | MRT-XA00-P0GAA-135004 | 2018-05-24 | MRT-HK-REC-TT-180117 | FA | 2 | TRUE | TRUE | FALSE
2781 | MRT-YS01-P2MKC-230015 | 2018-05-25 | MRT-DS-REC-TT-180421 | FA | 0 | TRUE | FALSE | FALSE
2782 | MRT-YS01-P3MKC-230015 | 2018-05-25 | MRT-DS-REC-TT-180421 | FA | 0 | TRUE | FALSE | FALSE
2783 | MRT-YK00-P0ZEN-165023 | 2018-05-25 | MRT-HK-REC-TT-180116 | FA | 0 | TRUE | FALSE | FALSE
2784 | MRT-YE00-P2MKA-230002 | 2018-05-25 | MRT-DS-REC-TT-180425 | FA | 2 | TRUE | TRUE | FALSE
2785 | MRT-YE00-P3MKA-230002 | 2018-05-25 | MRT-DS-REC-TT-180425 | FA | 2 | TRUE | TRUE | FALSE
2786 | MRT-YT01-P2QU-130030 | 2018-05-25 | MRT-DS-REC-TT-180423 | FI | 1 | TRUE | TRUE | FALSE
2787 | MRT-YF02-P2QU-130027 | 2018-05-25 | MRT-DS-REC-TT-180424 | FA | 1 | TRUE | TRUE | FALSE
2788 | MRT-YL00-P2QU-130028 | 2018-05-25 | MRT-DS-REC-TT-180424 | FI | 1 | TRUE | TRUE | FALSE
2789 | MRT-YF02-P3QU-130027 | 2018-05-25 | MRT-DS-REC-TT-180424 | FA | 1 | TRUE | TRUE | FALSE
2790 | MRT-YT01-P2GHC-129002 | 2018-05-25 | MRT-DS-REC-TT-180427 | FC | 2 | TRUE | TRUE | FALSE
2791 | MRT-YT01-P3GHC-129002 | 2018-05-25 | MRT-DS-REC-TT-180427 | FC | 2 | TRUE | TRUE | FALSE
2792 | MRT-YM01-P2GHC-129008 | 2018-05-25 | MRT-DS-REC-TT-180428 | FC | 2 | TRUE | TRUE | FALSE
2793 | MRT-YM01-P3GHC-129008 | 2018-05-25 | MRT-DS-REC-TT-180428 | FC | 2 | TRUE | TRUE | FALSE
2794 | MRT-YD00-P2LAC-126016 | 2018-05-25 | MRT-DS-REC-TT-180422 | FI | 0 | TRUE | FALSE | FALSE
2795 | MRT-YD00-P3LAC-126016 | 2018-05-25 | MRT-DS-REC-TT-180422 | FI | 0 | TRUE | FALSE | FALSE
2796 | MRT-YD00-P2LAC-126064 | 2018-05-25 | MRT-DS-REC-TT-180422 | FI | 0 | TRUE | FALSE | FALSE
2797 | MRT-YD00-P3LAC-126064 | 2018-05-25 | MRT-DS-REC-TT-180422 | FI | 0 | TRUE | FALSE | FALSE
2798 | MRT-CA01-P0UMA-180044 | 2018-05-25 | MRT-DS-REC-TT-180426 | FC | 1 | TRUE | TRUE | FALSE
2799 | MRT-CA02-P0UMA-180045 | 2018-05-25 | MRT-DS-REC-TT-180426 | FC | 1 | TRUE | TRUE | FALSE
2800 | MRT-CA00-P0UMA-180047 | 2018-05-25 | MRT-DS-REC-TT-180426 | FA | 1 | TRUE | TRUE | FALSE
2801 | MRT-YD00-P3MKA-220005 | 2018-05-25 | MRT-DS-REC-TT-180430 | FI | 0 | TRUE | FALSE | FALSE
2802 | MRT-YT01-P2LB-111102 | 2018-05-25 | MRT-DS-REC-TT-180429 | FC | 1 | TRUE | TRUE | FALSE
2803 | MRT-YK08-P2LB-111101 | 2018-05-25 | MRT-DS-REC-TT-180429 | FC | 1 | TRUE | TRUE | FALSE
2804 | MRT-YK09-P2LB-111103 | 2018-05-25 | MRT-DS-REC-TT-180429 | FC | 1 | TRUE | TRUE | FALSE
2805 | MRT-YT01-P3LB-111102 | 2018-05-25 | MRT-DS-REC-TT-180429 | FC | 1 | TRUE | TRUE | FALSE
2806 | MRT-YK08-P3LB-111101 | 2018-05-25 | MRT-DS-REC-TT-180429 | FC | 1 | TRUE | TRUE | FALSE
2807 | MRT-YK09-P3LB-111103 | 2018-05-25 | MRT-DS-REC-TT-180429 | FC | 1 | TRUE | TRUE | FALSE
2808 | MRT-YR05-P2SCA-127523 | 2018-05-25 | MRT-DS-REC-TT-180432 | FA | 0 | TRUE | FALSE | FALSE
2809 | MRT-YR05-P3SCA-127523 | 2018-05-25 | MRT-DS-REC-TT-180432 | FA | 0 | TRUE | FALSE | FALSE
2810 | MRT-YL25-P0ZEN-145301 | 2018-05-25 | MRT-HK-REC-TT-180118 | FA | 2 | TRUE | TRUE | FALSE
2811 | MRT-QM03-P0ZEN-185007 | 2018-05-25 | MRT-HK-REC-TT-180119 | FA | 0 | TRUE | FALSE | FALSE
2812 | MRT-QM03-P0ZEN-185006 | 2018-05-25 | MRT-HK-REC-TT-180119 | FA | 0 | TRUE | FALSE | FALSE
2813 | MRT-QM03-P0ZEN-185005 | 2018-05-25 | MRT-HK-REC-TT-180119 | FA | 0 | TRUE | FALSE | FALSE
2814 | MRT-YT01-P2LAC-126005 | 2018-05-28 | MRT-DS-REC-TT-180431 | FA | 2 | TRUE | TRUE | FALSE
2815 | MRT-YT01-P3LAC-126005 | 2018-05-28 | MRT-DS-REC-TT-180431 | FA | 2 | TRUE | TRUE | FALSE
2816 | MRT-YK08-P2MAG-601001 | 2018-05-28 | MRT-DS-REC-TT-180433 | FA | 3 | TRUE | TRUE | FALSE
2817 | MRT-YK08-P3MAG-602001 | 2018-05-28 | MRT-DS-REC-TT-180433 | FA | 3 | TRUE | TRUE | FALSE
2818 | MRT-YT01-P2PGB-113104 | 2018-05-28 | MRT-DS-REC-TT-180436 | FC | 2 | TRUE | TRUE | FALSE
2819 | MRT-YT01-P3PGB-113104 | 2018-05-28 | MRT-DS-REC-TT-180436 | FC | 2 | TRUE | TRUE | FALSE
2820 | MRT-YK08-P2MAG-601002 | 2018-05-28 | MRT-DS-REC-TT-180434 | FC | 3 | TRUE | TRUE | FALSE
2821 | MRT-XL00-P2MAG-601003 | 2018-05-28 | MRT-DS-REC-TT-180434 | FI | 3 | TRUE | TRUE | FALSE
2822 | MRT-YK08-P3MAG-602002 | 2018-05-28 | MRT-DS-REC-TT-180434 | FC | 3 | TRUE | TRUE | FALSE
2823 | MRT-XL00-P3MAG-602003 | 2018-05-28 | MRT-DS-REC-TT-180434 | FI | 3 | TRUE | TRUE | FALSE
2824 | MRT-YT01-P2MAG-601007 | 2018-05-28 | MRT-DS-REC-TT-180435 | FA | 3 | TRUE | TRUE | FALSE
2825 | MRT-YT01-P3MAG-602007 | 2018-05-28 | MRT-DS-REC-TT-180435 | FA | 3 | TRUE | TRUE | FALSE
2826 | 1HC0134924 | 2018-05-28 | MRT-HK-REC-TT-180120 | FA | 0 | TRUE | FALSE | FALSE
2827 | 1HC0134768 | 2018-05-28 | MRT-HK-REC-TT-180120 | FA | 0 | TRUE | FALSE | FALSE
2828 | MRT-XA00-P2QC-130002 | 2018-05-28 | MRT-DS-REC-TT-180438 | FA | 1 | TRUE | TRUE | FALSE
2829 | MRT-XA00-P3QC-130002 | 2018-05-28 | MRT-DS-REC-TT-180438 | FA | 1 | TRUE | TRUE | FALSE
2830 | MRT-DF04-P3ZEN-143001 | 2018-05-29 | MRT-DS-REC-TT-180439 | FI | 0 | TRUE | FALSE | FALSE
2831 | MRT-DF04-P3ZEN-143003 | 2018-05-29 | MRT-DS-REC-TT-180439 | FI | 0 | TRUE | FALSE | FALSE
2832 | MRT-YS01-P0ZEN-165013 | 2018-05-29 | MRT-HK-REC-TT-180122 | FA | 3 | TRUE | TRUE | FALSE
2833 | MRT-XG02-P0GHD-120001 | 2018-05-29 | MRT-DS-REC-TT-180440 | FC | 4 | TRUE | TRUE | FALSE
2834 | MRT-XG02-P0GKC-120001 | 2018-05-29 | MRT-DS-REC-TT-180441 | FC | 3 | TRUE | TRUE | FALSE
2835 | MRT-YF00-P2ZEN-161601 | 2018-05-30 | MRT-DS-REC-TT-180437 | FA | 0 | TRUE | FALSE | FALSE
2836 | MRT-YF00-P3ZEN-161601 | 2018-05-30 | MRT-DS-REC-TT-180437 | FA | 0 | TRUE | FALSE | FALSE
2837 | MRT-XA00-P2QU-130025 | 2018-05-30 | MRT-DS-REC-TT-180445 | FC | 2 | TRUE | TRUE | FALSE
2838 | MRT-XS00-P2QU-130026 | 2018-05-30 | MRT-DS-REC-TT-180445 | FC | 2 | TRUE | TRUE | FALSE
2839 | MRT-XA00-P3QU-130025 | 2018-05-30 | MRT-DS-REC-TT-180445 | FC | 2 | TRUE | TRUE | FALSE
2840 | MRT-XS00-P3QU-130026 | 2018-05-30 | MRT-DS-REC-TT-180445 | FC | 2 | TRUE | TRUE | FALSE
2841 | MRT-CA03-P0UXA-186704 | 2018-05-30 | MRT-HK-REC-TT-180121 | FA | 0 | TRUE | FALSE | FALSE
2842 | MRT-CA06-P0UXA-186702 | 2018-05-30 | MRT-HK-REC-TT-180121 | FA | 0 | TRUE | FALSE | FALSE
2843 | MRT-YL00-P2MAJ-603105 | 2018-05-30 | MRT-DS-REC-TT-180369 | FA | 3 | TRUE | TRUE | FALSE
2844 | MRT-YV02-P2MAJ-603108 | 2018-05-30 | MRT-DS-REC-TT-180369 | FA | 3 | TRUE | TRUE | FALSE
2845 | MRT-YL00-P3MAJ-604105 | 2018-05-30 | MRT-DS-REC-TT-180369 | FA | 3 | TRUE | TRUE | FALSE
2846 | MRT-YV02-P3MAJ-604108 | 2018-05-30 | MRT-DS-REC-TT-180369 | FA | 3 | TRUE | TRUE | FALSE
2847 | MRT-YT01-P0SMM-128004 | 2018-05-30 | MRT-DS-REC-TT-180446 | FC | 3 | TRUE | TRUE | FALSE
2848 | MRT-YD00-P0UAA-150207 | 2018-05-30 | MRT-HK-REC-TT-180123 | FA | 0 | TRUE | FALSE | FALSE
2849 | MRT-XA01-P0ABA-150507 | 2018-05-30 | MRT-HK-REC-TT-180123 | FA | 0 | TRUE | FALSE | FALSE
2850 | MRT-XW01-P2GM-128507 | 2018-05-31 | MRT-DS-REC-TT-180442 | FA | 0 | TRUE | FALSE | FALSE
2851 | MRT-XF00-P2GM-128510 | 2018-05-31 | MRT-DS-REC-TT-180442 | FI | 0 | TRUE | FALSE | FALSE
2852 | MRT-XW01-P3GM-128507 | 2018-05-31 | MRT-DS-REC-TT-180442 | FA | 0 | TRUE | FALSE | FALSE
2853 | MRT-XF00-P3GM-128510 | 2018-05-31 | MRT-DS-REC-TT-180442 | FI | 0 | TRUE | FALSE | FALSE
2854 | MRT-XJ00-P2LBG-142000 | 2018-05-31 | MRT-DS-REC-TT-180443 | FI | 0 | TRUE | FALSE | FALSE
2855 | MRT-XJ00-P2LAB-142000 | 2018-05-31 | MRT-DS-REC-TT-180443 | FI | 0 | TRUE | FALSE | FALSE
2856 | MRT-XJ00-P2PGB-142000 | 2018-05-31 | MRT-DS-REC-TT-180443 | FI | 0 | TRUE | FALSE | FALSE
2857 | MRT-XJ00-P2LCM-142000 | 2018-05-31 | MRT-DS-REC-TT-180443 | FI | 0 | TRUE | FALSE | FALSE
2858 | MRT-YR05-P2GM-128511 | 2018-05-31 | MRT-DS-REC-TT-180444 | FI | 0 | TRUE | FALSE | FALSE
2859 | MRT-YR05-P3GM-128511 | 2018-05-31 | MRT-DS-REC-TT-180444 | FI | 0 | TRUE | FALSE | FALSE
2860 | MRT-XG02-P2QU-130024 | 2018-05-31 | MRT-DS-REC-TT-180449 | FC | 2 | TRUE | TRUE | FALSE
2861 | MRT-XG02-P3QU-130024 | 2018-05-31 | MRT-DS-REC-TT-180449 | FC | 2 | TRUE | TRUE | FALSE
2862 | MRT-XK00-P3MKA-220001 | 2018-05-31 | MRT-DS-REC-TT-180451 | FA | 0 | TRUE | FALSE | FALSE
2863 | MRT-XJ00-P0GKB-140001 | 2018-05-31 | MRT-DS-REC-TT-180450 | FI | 0 | TRUE | FALSE | FALSE
2864 | MRT-YL00-P2MAJ-603207 | 2018-05-31 | MRT-DS-REC-TT-180447 | FA | 2 | TRUE | TRUE | FALSE
2865 | MRT-YL00-P3MAJ-604207 | 2018-05-31 | MRT-DS-REC-TT-180447 | FA | 2 | TRUE | TRUE | FALSE
2866 | MRT-YU02-P0BAY-150027 | 2018-05-31 | MRT-HK-REC-TT-180124 | FA | 0 | TRUE | FALSE | FALSE
2867 | MRT-XG02-P2MAJ-603201 | 2018-06-01 | MRT-DS-REC-TT-180448 | FC | 3 | TRUE | TRUE | FALSE
2868 | MRT-YT01-P2MAJ-603204 | 2018-06-01 | MRT-DS-REC-TT-180448 | FC | 3 | TRUE | TRUE | FALSE
2869 | MRT-YT01-P2MAJ-603206 | 2018-06-01 | MRT-DS-REC-TT-180448 | FI | 1 | TRUE | TRUE | FALSE
2870 | MRT-XS00-P2MAJ-603209 | 2018-06-01 | MRT-DS-REC-TT-180448 | FC | 2 | TRUE | TRUE | FALSE
2871 | MRT-XG02-P3MAJ-604201 | 2018-06-01 | MRT-DS-REC-TT-180448 | FC | 3 | TRUE | TRUE | FALSE
2872 | MRT-YT01-P3MAJ-604204 | 2018-06-01 | MRT-DS-REC-TT-180448 | FC | 3 | TRUE | TRUE | FALSE
2873 | MRT-YT01-P3MAJ-604206 | 2018-06-01 | MRT-DS-REC-TT-180448 | FI | 1 | TRUE | TRUE | FALSE
2874 | MRT-XS00-P3MAJ-604209 | 2018-06-01 | MRT-DS-REC-TT-180448 | FC | 2 | TRUE | TRUE | FALSE
2875 | MRT-YV02-P3MKW-230001 | 2018-06-01 | MRT-DS-REC-TT-180452 | FI | 0 | TRUE | FALSE | FALSE
2876 | MRT-YV02-P3MKW-230002 | 2018-06-01 | MRT-DS-REC-TT-180452 | FI | 0 | TRUE | FALSE | FALSE
2877 | MRT-YT01-P3MKA-240002 | 2018-06-01 | MRT-DS-REC-TT-180452 | FI | 0 | TRUE | FALSE | FALSE
2878 | MRT-YD00-P2LB-122107 | 2018-06-01 | MRT-DS-REC-TT-180453 | FC | 2 | TRUE | TRUE | FALSE
2879 | MRT-YD00-P3LB-122107 | 2018-06-01 | MRT-DS-REC-TT-180453 | FC | 2 | TRUE | TRUE | FALSE
2880 | MRT-YD02-P2LB-122064 | 2018-06-01 | MRT-DS-REC-TT-180455 | FI | 0 | TRUE | FALSE | FALSE
2881 | MRT-YD02-P2LB-122065 | 2018-06-01 | MRT-DS-REC-TT-180455 | FI | 0 | TRUE | FALSE | FALSE
2882 | MRT-XG02-P2LAC-126003 | 2018-06-01 | MRT-DS-REC-TT-180454 | FC | 2 | TRUE | TRUE | FALSE
2883 | MRT-XG02-P3LAC-126003 | 2018-06-01 | MRT-DS-REC-TT-180454 | FC | 2 | TRUE | TRUE | FALSE
2884 | MRT-XG02-P2LAC-126053 | 2018-06-01 | MRT-DS-REC-TT-180454 | FC | 2 | TRUE | TRUE | FALSE
2885 | MRT-XG02-P3LAC-126053 | 2018-06-01 | MRT-DS-REC-TT-180454 | FC | 2 | TRUE | TRUE | FALSE
2886 | MRT-YL22-P2LB-111104 | 2018-06-01 | MRT-DS-REC-TT-180457 | FA | 0 | TRUE | FALSE | FALSE
2887 | MRT-YL22-P3LB-111104 | 2018-06-01 | MRT-DS-REC-TT-180457 | FA | 0 | TRUE | FALSE | FALSE
2888 | MRT-XF00-P2SCA-127524 | 2018-06-04 | MRT-DS-REC-TT-180458 | FI | 0 | TRUE | FALSE | FALSE
2889 | MRT-XF00-P3SCA-127524 | 2018-06-04 | MRT-DS-REC-TT-180458 | FI | 0 | TRUE | FALSE | FALSE
2890 | MRT-QM03-P0ZEN-155001 | 2018-06-04 | MRT-HK-REC-TT-180125 | FI | 0 | TRUE | FALSE | FALSE
2891 | MRT-XB00-P2SCA-127509 | 2018-06-04 | MRT-DS-REC-TT-180459 | FA | 1 | TRUE | TRUE | FALSE
2892 | MRT-XB00-P3SCA-127509 | 2018-06-04 | MRT-DS-REC-TT-180459 | FA | 1 | TRUE | TRUE | FALSE
2893 | MRT-YD00-P2GHC-129001 | 2018-06-04 | MRT-DS-REC-TT-180460 | FC | 3 | TRUE | TRUE | FALSE
2894 | MRT-YD00-P3GHC-129001 | 2018-06-04 | MRT-DS-REC-TT-180460 | FC | 3 | TRUE | TRUE | FALSE
2895 | MRT-CV03-P0ZEN-163102 | 2018-06-04 | MRT-DS-REC-TT-180461 | FC | 1 | TRUE | TRUE | FALSE
2896 | MRT-CV03-P0ZEN-163103 | 2018-06-04 | MRT-DS-REC-TT-180461 | FC | 1 | TRUE | TRUE | FALSE
2897 | MRT-YT01-P3BAT-150398 | 2018-06-05 | MRT-HK-REC-TT-180126 | FA | 0 | TRUE | FALSE | FALSE
2898 | MRT-YT01-P3BAT-150397 | 2018-06-05 | MRT-HK-REC-TT-180126 | FA | 0 | TRUE | FALSE | FALSE
2899 | MRT-UBM-P3BAT-150406 | 2018-06-05 | MRT-HK-REC-TT-180126 | FA | 0 | TRUE | FALSE | FALSE
2900 | MRT-YD00-P3BAT-150396 | 2018-06-05 | MRT-HK-REC-TT-180126 | FA | 0 | TRUE | FALSE | FALSE
2901 | MRT-XM00-P3BAT-150409 | 2018-06-05 | MRT-HK-REC-TT-180126 | FA | 0 | TRUE | FALSE | FALSE
2902 | MRT-BAB-P3BAT-150395 | 2018-06-05 | MRT-HK-REC-TT-180126 | FA | 0 | TRUE | FALSE | FALSE
2903 | MRT-YT01-P2BAT-150375 | 2018-06-05 | MRT-HK-REC-TT-180126 | FA | 0 | TRUE | FALSE | FALSE
2904 | MRT-YT01-P2BAT-150374 | 2018-06-05 | MRT-HK-REC-TT-180126 | FA | 0 | TRUE | FALSE | FALSE
2905 | MRT-YD00-P2BAT-150383 | 2018-06-05 | MRT-HK-REC-TT-180126 | FA | 0 | TRUE | FALSE | FALSE
2906 | MRT-YD00-P2BAT-150373 | 2018-06-05 | MRT-HK-REC-TT-180126 | FA | 0 | TRUE | FALSE | FALSE
2907 | MRT-BAB-P2BAT-150372 | 2018-06-05 | MRT-HK-REC-TT-180126 | FA | 0 | TRUE | FALSE | FALSE
2908 | MRT-CC07-P0UPC-175715 | 2018-06-05 | MRT-HK-REC-TT-180127 | FA | 1 | TRUE | TRUE | FALSE
2909 | MRT-CC07-P0UQQ-175801 | 2018-06-05 | MRT-HK-REC-TT-180127 | FA | 4 | TRUE | TRUE | FALSE
2910 | MRT-CC02-P0UQQ-175805 | 2018-06-05 | MRT-HK-REC-TT-180127 | FA | 4 | TRUE | TRUE | FALSE
2911 | MRT-XJ00-P0GHD-140001 | 2018-06-05 | MRT-DS-REC-TT-180462 | FI | 0 | TRUE | FALSE | FALSE
2912 | MRT-XG02-P2QC-130001 | 2018-06-05 | MRT-DS-REC-TT-180463 | FC | 2 | TRUE | TRUE | FALSE
2913 | MRT-XS00-P2QC-130003 | 2018-06-05 | MRT-DS-REC-TT-180463 | FC | 2 | TRUE | TRUE | FALSE
2914 | MRT-CC07-P2QC-130004 | 2018-06-05 | MRT-DS-REC-TT-180463 | FC | 2 | TRUE | TRUE | FALSE
2915 | MRT-XG02-P3QC-130001 | 2018-06-05 | MRT-DS-REC-TT-180463 | FC | 2 | TRUE | TRUE | FALSE
2916 | MRT-XS00-P3QC-130003 | 2018-06-05 | MRT-DS-REC-TT-180463 | FC | 2 | TRUE | TRUE | FALSE
2917 | MRT-CC07-P3QC-130004 | 2018-06-05 | MRT-DS-REC-TT-180463 | FC | 2 | TRUE | TRUE | FALSE
2918 | MRT-YD00-P3MKW-220002 | 2018-06-05 | MRT-DS-REC-TT-180464 | FA | 0 | TRUE | FALSE | FALSE
2919 | MRT-YT01-P2QU-130031 | 2018-06-05 | MRT-DS-REC-TT-180465 | FI | 1 | TRUE | TRUE | FALSE
2920 | MRT-YF00-P2QU-130033 | 2018-06-05 | MRT-DS-REC-TT-180465 | FI | 1 | TRUE | TRUE | FALSE
2921 | MRT-YT01-P3QU-130031 | 2018-06-05 | MRT-DS-REC-TT-180465 | FI | 1 | TRUE | TRUE | FALSE
2922 | MRT-DF04-P3ZEN-143002 | 2018-06-05 | MRT-DS-REC-TT-180466 | FI | 0 | TRUE | FALSE | FALSE
2923 | MRT-DF04-P3ZEN-143004 | 2018-06-05 | MRT-DS-REC-TT-180466 | FI | 0 | TRUE | FALSE | FALSE
2924 | MRT-CA06-P0UXA-186660 | 2018-06-07 | MRT-HK-REC-TT-180128 | FA | 0 | TRUE | FALSE | FALSE
2925 | MRT-CA01-P0UXA-186662 | 2018-06-07 | MRT-HK-REC-TT-180128 | FA | 0 | TRUE | FALSE | FALSE
2926 | MRT-CA06-P0UVH-187051 | 2018-06-07 | MRT-HK-REC-TT-180128 | FA | 0 | TRUE | FALSE | FALSE
2927 | MRT-CA01-P0UVH-187052 | 2018-06-07 | MRT-HK-REC-TT-180128 | FA | 0 | TRUE | FALSE | FALSE
2928 | MRT-CA06-P0UYX-187151 | 2018-06-07 | MRT-HK-REC-TT-180128 | FA | 0 | TRUE | FALSE | FALSE
2929 | MRT-CA01-P0UYX-187152 | 2018-06-07 | MRT-HK-REC-TT-180128 | FA | 0 | TRUE | FALSE | FALSE
2930 | MRT-CA06-P0UYX-187311 | 2018-06-07 | MRT-HK-REC-TT-180128 | FA | 0 | TRUE | FALSE | FALSE
2931 | MRT-CA01-P0UYX-187312 | 2018-06-07 | MRT-HK-REC-TT-180128 | FA | 0 | TRUE | FALSE | FALSE
2932 | MRT-CC03-P0UQQ-175837 | 2018-06-07 | MRT-HK-REC-TT-180129 | FA | 1 | TRUE | TRUE | FALSE
2933 | MRT-CC03-P0UQQ-175836 | 2018-06-07 | MRT-HK-REC-TT-180129 | FA | 1 | TRUE | TRUE | FALSE
2934 | MRT-CC02-P0UQQ-175810 | 2018-06-07 | MRT-HK-REC-TT-180129 | FA | 3 | TRUE | TRUE | FALSE
2935 | MRT-CC07-P0UQQ-175815 | 2018-06-07 | MRT-HK-REC-TT-180129 | FA | 4 | TRUE | TRUE | FALSE
2936 | MRT-CC02-P0UQQ-175820 | 2018-06-07 | MRT-HK-REC-TT-180129 | FA | 2 | TRUE | TRUE | FALSE
2937 | MRT-CC02-P0UQQ-175825 | 2018-06-07 | MRT-HK-REC-TT-180129 | FA | 2 | TRUE | TRUE | FALSE
2938 | MRT-CC02-P0UQQ-175830 | 2018-06-07 | MRT-HK-REC-TT-180129 | FA | 2 | TRUE | TRUE | FALSE
2939 | MRT-CC03-P0UQQ-175835 | 2018-06-07 | MRT-HK-REC-TT-180129 | FA | 1 | TRUE | TRUE | FALSE
2940 | MRT-CC02-P0UQQ-175826 | 2018-06-07 | MRT-HK-REC-TT-180129 | FA | 2 | TRUE | TRUE | FALSE
2941 | MRT-CC02-P0UQQ-175827 | 2018-06-07 | MRT-HK-REC-TT-180129 | FA | 2 | TRUE | TRUE | FALSE
2942 | MRT-CC02-P0UQQ-175828 | 2018-06-07 | MRT-HK-REC-TT-180129 | FA | 2 | TRUE | TRUE | FALSE
2943 | MRT-CC02-P0UQQ-175829 | 2018-06-07 | MRT-HK-REC-TT-180129 | FA | 2 | TRUE | TRUE | FALSE
2944 | MRT-CC04-P0ULY-176130 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 0 | TRUE | TRUE | FALSE
2945 | MRT-CC04-P0ULY-176129 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 0 | TRUE | TRUE | FALSE
2946 | MRT-CC04-P0ULY-176132 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 0 | TRUE | TRUE | FALSE
2947 | MRT-CC04-P0ULY-176131 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 0 | TRUE | TRUE | FALSE
2948 | MRT-CC07-P0ULY-176101 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 2 | TRUE | TRUE | FALSE
2949 | MRT-CC07-P0ULY-176115 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 2 | TRUE | TRUE | FALSE
2950 | MRT-CC02-P0ULY-176120 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2951 | MRT-CC02-P0ULY-176125 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2952 | MRT-CC04-P0ULY-176145 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2953 | MRT-CC04-P0ULY-176150 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2954 | MRT-CC04-P0ULY-176155 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2955 | MRT-CC04-P0ULY-176160 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2956 | MRT-CC02-P0ULY-176108 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 2 | TRUE | TRUE | FALSE
2957 | MRT-CC04-P0ULY-176121 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2958 | MRT-CC04-P0ULY-176122 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2959 | MRT-CC04-P0ULY-176123 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2960 | MRT-CC04-P0ULY-176126 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2961 | MRT-CC04-P0ULY-176127 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2962 | MRT-CC04-P0ULY-176128 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2963 | MRT-CC04-P0ULY-176136 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2964 | MRT-CC04-P0ULY-176137 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2965 | MRT-CC04-P0ULY-176138 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2966 | MRT-CC04-P0ULY-176153 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2967 | MRT-CC04-P0ULY-176154 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2968 | MRT-CC04-P0ULY-176156 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2969 | MRT-CC04-P0ULY-176157 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2970 | MRT-CC04-P0ULY-176161 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2971 | MRT-CC04-P0ULY-176162 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2972 | MRT-CC04-P0ULY-176163 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2973 | MRT-CC04-P0ULY-176164 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2974 | MRT-CC04-P0ULY-176165 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2975 | MRT-CC04-P0ULY-176166 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2976 | MRT-CC04-P0ULY-176167 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2977 | MRT-CC04-P0ULY-176168 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2978 | MRT-CC04-P0ULY-176169 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2979 | MRT-CC04-P0ULY-176170 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2980 | MRT-CC04-P0ULY-176171 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2981 | MRT-CC04-P0ULY-176172 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2982 | MRT-CC04-P0ULY-176180 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2983 | MRT-CC04-P0ULY-176181 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2984 | MRT-CC04-P0ULY-176182 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2985 | MRT-CC04-P0ULY-176183 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2986 | MRT-CC04-P0ULY-176184 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2987 | MRT-CC04-P0ULY-176185 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2988 | MRT-CC04-P0ULY-176186 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2989 | MRT-CC04-P0ULY-176187 | 2018-06-07 | MRT-HK-REC-TT-180130 | FA | 1 | TRUE | TRUE | FALSE
2990 | MRT-YD00-P3CWA-165003 | 2018-06-07 | MRT-HK-REC-TT-180131 | FA | 1 | TRUE | TRUE | FALSE
2991 | MRT-YD00-P0UAA-150204 | 2018-06-07 | MRT-HK-REC-TT-180133 | FA | 0 | TRUE | FALSE | FALSE
2992 | MRT-CA00-P0UYX-187157 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
2993 | MRT-CA00-P0UYX-187184 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
2994 | MRT-CA00-P0UYX-187159 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
2995 | MRT-CA00-P0UXA-186674 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
2996 | MRT-CA00-P0UXA-186673 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
2997 | MRT-CA00-P0UXA-186672 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
2998 | MRT-CA00-P0UXA-186671 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
2999 | MRT-CA00-P0UVH-187086 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3000 | MRT-CA00-P0UVH-187059 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3001 | MRT-CA00-P0UVH-187057 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3002 | MRT-CA00-P0UAB-187339 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3003 | MRT-CA00-P0UAB-187337 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3004 | MRT-CA00-P0UAB-187322 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3005 | MRT-CA00-P0UAB-187320 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3006 | MRT-CA00-P0UAB-187319 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3007 | MRT-CA00-P0UAB-187318 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3008 | MRT-CA00-P0UXA-186670 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3009 | MRT-CA00-P0UXA-186684 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3010 | MRT-CA00-P0UVH-187056 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3011 | MRT-CA00-P0UVH-187058 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3012 | MRT-CA00-P0UVH-187062 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3013 | MRT-CA00-P0UYX-187156 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3014 | MRT-CA00-P0UYX-187158 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3015 | MRT-CA00-P0UYX-187162 | 2018-06-07 | MRT-HK-REC-TT-180132 | FA | 0 | TRUE | FALSE | FALSE
3016 | MRT-XS01-P2CJJ-240060 | 2018-06-07 | MRT-DS-REC-TT-180467 | FI | 0 | TRUE | FALSE | FALSE
3017 | MRT-YT01-P2MKA-240001 | 2018-06-07 | MRT-DS-REC-TT-180468 | FC | 1 | TRUE | TRUE | FALSE
3018 | MRT-YT01-P3MKA-240001 | 2018-06-07 | MRT-DS-REC-TT-180468 | FC | 1 | TRUE | TRUE | FALSE
3019 | MRT-YE03-P2ZEN-163104 | 2018-06-07 | MRT-DS-REC-TT-180469 | FC | 1 | TRUE | TRUE | FALSE
3020 | MRT-YD06-P2ZEN-163106 | 2018-06-07 | MRT-DS-REC-TT-180469 | FC | 1 | TRUE | TRUE | FALSE
3021 | MRT-YL00-P2SCA-127520 | 2018-06-08 | MRT-DS-REC-TT-180471 | FI | 0 | TRUE | FALSE | FALSE
3022 | MRT-YL00-P3SCA-127520 | 2018-06-08 | MRT-DS-REC-TT-180471 | FI | 0 | TRUE | FALSE | FALSE
3023 | MRT-YD00-P2LCB-127501 | 2018-06-08 | MRT-DS-REC-TT-180472 | FA | 1 | TRUE | TRUE | FALSE
3024 | MRT-YD00-P3LCB-127501 | 2018-06-08 | MRT-DS-REC-TT-180472 | FA | 1 | TRUE | TRUE | FALSE
3025 | MRT-YT01-P2LCB-127035 | 2018-06-08 | MRT-DS-REC-TT-180470 | FI | 0 | TRUE | FALSE | FALSE
3026 | MRT-YT01-P3LCB-127035 | 2018-06-08 | MRT-DS-REC-TT-180470 | FI | 0 | TRUE | FALSE | FALSE
3027 | MRT-CV03-P2ZEN-165201 | 2018-06-08 | MRT-DS-REC-TT-180473 | FC | 3 | TRUE | TRUE | FALSE
3028 | MRT-CV03-P3ZEN-165201 | 2018-06-08 | MRT-DS-REC-TT-180473 | FC | 3 | TRUE | TRUE | FALSE
7944 | MRT-CC02-P0UGA-176255 | 2018-06-08 | MRT-HK-REC-TT-180137 | FA | 0 | TRUE | FALSE | FALSE
7945 | MRT-CC07-P0UGA-176285 | 2018-06-08 | MRT-HK-REC-TT-180137 | FA | 0 | TRUE | FALSE | FALSE
3029 | MRT-XW01-P2SCA-127503 | 2018-06-11 | MRT-DS-REC-TT-180474 | FC | 2 | TRUE | TRUE | FALSE
3030 | MRT-XW01-P3SCA-127503 | 2018-06-11 | MRT-DS-REC-TT-180474 | FC | 2 | TRUE | TRUE | FALSE
3031 | MRT-YF00-P2SCA-127518 | 2018-06-11 | MRT-DS-REC-TT-180475 | FI | 0 | TRUE | FALSE | FALSE
3032 | MRT-YD05-P2SCA-127515 | 2018-06-11 | MRT-DS-REC-TT-180475 | FA | 1 | TRUE | TRUE | FALSE
3033 | MRT-YF00-P3SCA-127518 | 2018-06-11 | MRT-DS-REC-TT-180475 | FI | 0 | TRUE | FALSE | FALSE
3034 | MRT-YD05-P3SCA-127515 | 2018-06-11 | MRT-DS-REC-TT-180475 | FA | 1 | TRUE | TRUE | FALSE
3035 | MRT-CA03-P0UST-186927 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3036 | MRT-CA03-P0UST-186949 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3037 | MRT-CA03-P0UST-186948 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3038 | MRT-CA03-P0UST-186947 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3039 | MRT-CA03-P0UST-186937 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3040 | MRT-CA02-P0UST-186922 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3041 | MRT-CA02-P0UGX-186993 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3042 | MRT-CA02-P0UGX-186992 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3043 | MRT-CA02-P0UGX-186991 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3044 | MRT-CA02-P0UGX-186985 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3045 | MRT-CA02-P0UGX-186983 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3046 | MRT-CA02-P0UGX-186974 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3047 | MRT-CA01-P0UGX-186986 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3048 | MRT-CA01-P0UGX-186973 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3049 | MRT-CA06-P0UST-186904 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3050 | MRT-CA02-P0UST-186924 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3051 | MRT-CA03-P0UST-186928 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3052 | MRT-CA03-P0UST-186930 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3053 | MRT-CA03-P0UST-186932 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3054 | MRT-CA03-P0UST-186934 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3055 | MRT-CA03-P0UST-186936 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3056 | MRT-CA06-P0UGX-186954 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3057 | MRT-CA01-P0UGX-186976 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3058 | MRT-CA01-P0UGX-186978 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3059 | MRT-CA02-P0UGX-186982 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3060 | MRT-CA01-P0UGX-186988 | 2018-06-11 | MRT-HK-REC-TT-180134 | FA | 0 | TRUE | TRUE | FALSE
3061 | MRT-CA03-P0USG-186885 | 2018-06-12 | MRT-HK-REC-TT-180135 | FA | 0 | TRUE | TRUE | FALSE
3062 | MRT-CA01-P0USG-186869 | 2018-06-12 | MRT-HK-REC-TT-180135 | FA | 0 | TRUE | TRUE | FALSE
3063 | MRT-CA06-P0USG-186854 | 2018-06-12 | MRT-HK-REC-TT-180135 | FA | 0 | TRUE | TRUE | FALSE
3064 | MRT-CA01-P0USG-186868 | 2018-06-12 | MRT-HK-REC-TT-180135 | FA | 0 | TRUE | TRUE | FALSE
3065 | MRT-CA02-P0USG-186874 | 2018-06-12 | MRT-HK-REC-TT-180135 | FA | 0 | TRUE | TRUE | FALSE
3066 | MRT-CA03-P0USG-186876 | 2018-06-12 | MRT-HK-REC-TT-180135 | FA | 0 | TRUE | TRUE | FALSE
3067 | MRT-CA03-P0USG-186878 | 2018-06-12 | MRT-HK-REC-TT-180135 | FA | 0 | TRUE | TRUE | FALSE
3068 | MRT-CA03-P0USG-186880 | 2018-06-12 | MRT-HK-REC-TT-180135 | FA | 0 | TRUE | TRUE | FALSE
3069 | MRT-CA03-P0USG-186882 | 2018-06-12 | MRT-HK-REC-TT-180135 | FA | 0 | TRUE | TRUE | FALSE
3070 | MRT-CA03-P0USG-186884 | 2018-06-12 | MRT-HK-REC-TT-180135 | FA | 0 | TRUE | TRUE | FALSE
3071 | MRT-CCO7-P0UGA-176285 | 2018-06-12 | MRT-HK-REC-TT-180137 | FA | 0 | TRUE | FALSE | FALSE
3072 | MRT-CA02-P0UGA-176265 | 2018-06-12 | MRT-HK-REC-TT-180137 | FA | 0 | TRUE | FALSE | FALSE
3073 | MRT-CA02-P0UGA-176260 | 2018-06-12 | MRT-HK-REC-TT-180137 | FA | 0 | TRUE | FALSE | FALSE
3074 | MRT-CA02-P0UGA-176300 | 2018-06-12 | MRT-HK-REC-TT-180137 | FA | 0 | TRUE | FALSE | FALSE
3075 | MRT-CC07-P0UGA-176245 | 2018-06-12 | MRT-HK-REC-TT-180137 | FA | 0 | TRUE | FALSE | FALSE
3076 | MRT-CC02-P0UGA-176250 | 2018-06-12 | MRT-HK-REC-TT-180137 | FA | 0 | TRUE | FALSE | FALSE
3077 | MRT-CC02-P0UGA-176290 | 2018-06-12 | MRT-HK-REC-TT-180137 | FA | 0 | TRUE | FALSE | FALSE
3078 | MRT-CC02-P0UGA-176295 | 2018-06-12 | MRT-HK-REC-TT-180137 | FA | 0 | TRUE | FALSE | FALSE
3079 | MRT-CA02-P0UGA-176305 | 2018-06-12 | MRT-HK-REC-TT-180137 | FA | 0 | TRUE | FALSE | FALSE
3080 | MRT-CC02-P2UMA-170607 | 2018-06-12 | MRT-DS-REC-TT-180476 | FC | 3 | TRUE | TRUE | FALSE
3081 | MRT-CC02-P2UMA-170608 | 2018-06-12 | MRT-DS-REC-TT-180476 | FC | 3 | TRUE | TRUE | FALSE
3082 | MRT-CC02-P2UMA-170609 | 2018-06-12 | MRT-DS-REC-TT-180476 | FC | 3 | TRUE | TRUE | FALSE
3083 | MRT-VK02-P2UMA-170610 | 2018-06-12 | MRT-DS-REC-TT-180476 | FC | 2 | TRUE | TRUE | FALSE
3084 | MRT-CC02-P3UMA-170607 | 2018-06-12 | MRT-DS-REC-TT-180476 | FC | 3 | TRUE | TRUE | FALSE
3085 | MRT-CC02-P3UMA-170608 | 2018-06-12 | MRT-DS-REC-TT-180476 | FC | 3 | TRUE | TRUE | FALSE
3086 | MRT-CC02-P3UMA-170609 | 2018-06-12 | MRT-DS-REC-TT-180476 | FC | 3 | TRUE | TRUE | FALSE
3087 | MRT-VK02-P3UMA-170610 | 2018-06-12 | MRT-DS-REC-TT-180476 | FC | 2 | TRUE | TRUE | FALSE
3088 | MRT-CC02-P0UMA-170602 | 2018-06-12 | MRT-DS-REC-TT-180476 | FC | 2 | TRUE | TRUE | FALSE
3089 | MRT-YT01-P3MKA-240003 | 2018-06-12 | MRT-DS-REC-TT-180477 | FI | 0 | TRUE | FALSE | FALSE
3090 | MRT-DF04-P3ZEN-144001 | 2018-06-12 | MRT-DS-REC-TT-180478 | FI | 0 | TRUE | FALSE | FALSE
3091 | MRT-XJ00-P2PAB-140001 | 2018-06-12 | MRT-DS-REC-TT-180479 | FC | 1 | TRUE | TRUE | FALSE
3092 | MRT-XJ00-P3PAB-140001 | 2018-06-12 | MRT-DS-REC-TT-180479 | FC | 1 | TRUE | TRUE | FALSE
3093 | MRT-CA01-P0UPB-187037 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3094 | MRT-CA01-P0UPB-187036 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3095 | MRT-CA01-P0UGX-186741 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3096 | MRT-CA06-P0UGA-186605 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3097 | MRT-CA02-P0UGA-186634 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3098 | MRT-CA03-P0UGA-186640 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3099 | MRT-CA01-P0UGX-186742 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3100 | MRT-CA03-P0UGX-186748 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3101 | MRT-CA03-P0UGX-186750 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3102 | MRT-CA03-P0UGX-186752 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3103 | MRT-CA03-P0UGX-186754 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3104 | MRT-CA03-P0UGX-186756 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3105 | MRT-CA06-P0UPB-187004 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3106 | MRT-CA01-P0UPB-187016 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3107 | MRT-CA02-P0UPB-187018 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3108 | MRT-CA01-P0UPB-187020 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3109 | MRT-CA01-P0UPB-187022 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3110 | MRT-CA01-P0UPB-187024 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3111 | MRT-CA02-P0UPB-187026 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3112 | MRT-CA02-P0UPB-187028 | 2018-06-12 | MRT-HK-REC-TT-180136 | FA | 0 | TRUE | TRUE | FALSE
3113 | MRT-YT01-P3BAC-150361 | 2018-06-12 | MRT-HK-REC-TT-180138 | FI | 0 | TRUE | FALSE | FALSE
3114 | MRT-YT01-P2BAC-150354 | 2018-06-12 | MRT-HK-REC-TT-180138 | FI | 0 | TRUE | FALSE | FALSE
3115 | MRT-YD00-P0UAA-150204 | 2018-06-12 | MRT-HK-REC-TT-180139 | FA | 2 | TRUE | FALSE | FALSE
3116 | MRT-CV03-P0ZEN-163101 | 2018-06-12 | MRT-DS-REC-TT-180484 | FC | 1 | TRUE | TRUE | FALSE
3117 | MRT-CV03-P0ZEN-163108 | 2018-06-12 | MRT-DS-REC-TT-180484 | FC | 1 | TRUE | TRUE | FALSE
3118 | MRT-YL01-P2ZEN-161051 | 2018-06-14 | MRT-DS-REC-TT-180486 | FA | 2 | TRUE | TRUE | FALSE
3119 | MRT-YL01-P3ZEN-161051 | 2018-06-14 | MRT-DS-REC-TT-180486 | FA | 2 | TRUE | TRUE | FALSE
3120 | MRT-XL00-P2LB-122030 | 2018-06-14 | MRT-DS-REC-TT-180480 | FA | 3 | TRUE | TRUE | FALSE
3121 | MRT-XL00-P3LB-122030 | 2018-06-14 | MRT-DS-REC-TT-180480 | FA | 2 | TRUE | TRUE | FALSE
3122 | MRT-VN02-P2LB-122090 | 2018-06-14 | MRT-DS-REC-TT-180481 | FA | 1 | TRUE | TRUE | FALSE
3123 | MRT-VN02-P3LB-122090 | 2018-06-14 | MRT-DS-REC-TT-180481 | FA | 1 | TRUE | TRUE | FALSE
3124 | MRT-YF00-P2LB-122066 | 2018-06-14 | MRT-DS-REC-TT-180482 | FA | 1 | TRUE | TRUE | FALSE
3125 | MRT-YD00-P2LB-122108 | 2018-06-14 | MRT-DS-REC-TT-180483 | FA | 2 | TRUE | TRUE | FALSE
3126 | MRT-YD00-P3LB-122108 | 2018-06-14 | MRT-DS-REC-TT-180483 | FA | 2 | TRUE | TRUE | FALSE
3127 | MRT-VN02-P2LB-122089 | 2018-06-14 | MRT-DS-REC-TT-180485 | FC | 1 | TRUE | TRUE | FALSE
3128 | MRT-YD00-P2LB-122050 | 2018-06-14 | MRT-DS-REC-TT-180485 | FC | 1 | TRUE | TRUE | FALSE
3129 | MRT-YT01-P2LB-122051 | 2018-06-14 | MRT-DS-REC-TT-180485 | FC | 1 | TRUE | TRUE | FALSE
3130 | MRT-YD00-P2LB-122053 | 2018-06-14 | MRT-DS-REC-TT-180485 | FC | 1 | TRUE | TRUE | FALSE
3131 | MRT-YD00-P2LB-122052 | 2018-06-14 | MRT-DS-REC-TT-180485 | FC | 1 | TRUE | TRUE | FALSE
3132 | MRT-YD00-P3LB-122050 | 2018-06-14 | MRT-DS-REC-TT-180485 | FC | 1 | TRUE | TRUE | FALSE
3133 | MRT-YT01-P3LB-122051 | 2018-06-14 | MRT-DS-REC-TT-180485 | FC | 1 | TRUE | TRUE | FALSE
3134 | MRT-YD00-P3LB-122052 | 2018-06-14 | MRT-DS-REC-TT-180485 | FC | 1 | TRUE | TRUE | FALSE
3135 | MRT-YD00-P3LB-122053 | 2018-06-14 | MRT-DS-REC-TT-180485 | FC | 1 | TRUE | TRUE | FALSE
3136 | MRT-VN02-P3LB-122089 | 2018-06-14 | MRT-DS-REC-TT-180485 | FC | 1 | TRUE | TRUE | FALSE
3137 | MRT-YL08-P2LB-122083 | 2018-06-14 | MRT-DS-REC-TT-180487 | FI | 0 | TRUE | FALSE | FALSE
3138 | MRT-XG01-P2LB-122021 | 2018-06-14 | MRT-DS-REC-TT-180487 | FI | 0 | TRUE | FALSE | FALSE
3139 | MRT-YT01-P2LB-122093 | 2018-06-14 | MRT-DS-REC-TT-180488 | FA | 0 | TRUE | FALSE | FALSE
3140 | MRT-XW01-P2LB-122043 | 2018-06-14 | MRT-DS-REC-TT-180488 | FA | 0 | TRUE | FALSE | FALSE
3141 | MRT-XW01-P3LB-122043 | 2018-06-14 | MRT-DS-REC-TT-180488 | FA | 0 | TRUE | FALSE | FALSE
3142 | MRT-YV02-P2QU-130032 | 2018-06-15 | MRT-DS-REC-TT-180492 | FI | 1 | TRUE | TRUE | FALSE
3143 | MRT-YS01-P2QU-130034 | 2018-06-15 | MRT-DS-REC-TT-180492 | FI | 1 | TRUE | TRUE | FALSE
3144 | MRT-YV02-P3QU-130032 | 2018-06-15 | MRT-DS-REC-TT-180492 | FI | 1 | TRUE | TRUE | FALSE
3145 | MRT-YS01-P3QU-130034 | 2018-06-15 | MRT-DS-REC-TT-180492 | FI | 1 | TRUE | TRUE | FALSE
3146 | MRT-YD00-P2QC-130005 | 2018-06-15 | MRT-DS-REC-TT-180489 | FC | 1 | TRUE | TRUE | FALSE
3147 | MRT-YF02-P2QC-130006 | 2018-06-15 | MRT-DS-REC-TT-180489 | FA | 1 | TRUE | TRUE | FALSE
3148 | MRT-YD00-P3QC-130005 | 2018-06-15 | MRT-DS-REC-TT-180489 | FC | 1 | TRUE | TRUE | FALSE
3149 | MRT-YF02-P3QC-130006 | 2018-06-15 | MRT-DS-REC-TT-180489 | FA | 1 | TRUE | TRUE | FALSE
3150 | MRT-YF02-P2QU-130027 | 2018-06-15 | MRT-DS-REC-TT-180499 | FC | 2 | TRUE | TRUE | FALSE
3151 | MRT-YF02-P3QU-130027 | 2018-06-15 | MRT-DS-REC-TT-180499 | FC | 2 | TRUE | TRUE | FALSE
3152 | MRT-YD00-P2PAB-113251 | 2018-06-15 | MRT-DS-REC-TT-180498 | FA | 2 | TRUE | TRUE | FALSE
3153 | MRT-YT01-P2PAB-113252 | 2018-06-15 | MRT-DS-REC-TT-180498 | FA | 2 | TRUE | TRUE | FALSE
3154 | MRT-XG02-P2PAB-113253 | 2018-06-15 | MRT-DS-REC-TT-180498 | FA | 2 | TRUE | TRUE | FALSE
3155 | MRT-YD00-P3PAB-113251 | 2018-06-15 | MRT-DS-REC-TT-180498 | FA | 2 | TRUE | TRUE | FALSE
3156 | MRT-YT01-P3PAB-113252 | 2018-06-15 | MRT-DS-REC-TT-180498 | FA | 2 | TRUE | TRUE | FALSE
3157 | MRT-XG02-P3PAB-113253 | 2018-06-15 | MRT-DS-REC-TT-180498 | FA | 2 | TRUE | TRUE | FALSE
3158 | MRT-YK08-P2MAG-601001 | 2018-06-15 | MRT-DS-REC-TT-180500 | FC | 4 | TRUE | TRUE | FALSE
3159 | MRT-YK08-P3MAG-602001 | 2018-06-15 | MRT-DS-REC-TT-180500 | FC | 4 | TRUE | TRUE | FALSE
3160 | MRT-YD00-P2QHE-606003 | 2018-06-15 | MRT-DS-REC-TT-180495 | FC | 2 | TRUE | TRUE | FALSE
3161 | MRT-YD00-P3QHE-606003 | 2018-06-15 | MRT-DS-REC-TT-180495 | FC | 2 | TRUE | TRUE | FALSE
3162 | MRT-YD00-P0ERB-606001 | 2018-06-15 | MRT-DS-REC-TT-180496 | FC | 2 | TRUE | TRUE | FALSE
3163 | MRT-YD00-P0ERB-606002 | 2018-06-15 | MRT-DS-REC-TT-180496 | FC | 2 | TRUE | TRUE | FALSE
3164 | MRT-CN00-P2ZEN-110100 | 2018-06-15 | MRT-DS-REC-TT-180494 | FC | 1 | TRUE | TRUE | FALSE
3165 | MRT-CN00-P3ZEN-110100 | 2018-06-15 | MRT-DS-REC-TT-180494 | FA | 0 | TRUE | FALSE | FALSE
3166 | MRT-XV00-P0ZEN-020003 | 2018-06-15 | MRT-DS-REC-TT-180504 | FI | 1 | TRUE | TRUE | FALSE
3167 | MRT-XL00-P2MAG-601003 | 2018-06-15 | MRT-DS-REC-TT-180501 | FC | 4 | TRUE | TRUE | FALSE
3168 | MRT-XL00-P2MAG-601004 | 2018-06-15 | MRT-DS-REC-TT-180501 | FC | 3 | TRUE | TRUE | FALSE
3169 | MRT-XL00-P3MAG-602003 | 2018-06-15 | MRT-DS-REC-TT-180501 | FC | 4 | TRUE | TRUE | FALSE
3170 | MRT-XL00-P3MAG-602004 | 2018-06-15 | MRT-DS-REC-TT-180501 | FC | 3 | TRUE | TRUE | FALSE
3171 | MRT-XJ00-P2MKJ-220001 | 2018-06-15 | MRT-DS-REC-TT-180497 | FC | 1 | TRUE | TRUE | FALSE
3172 | MRT-YL22-P2GHC-129014 | 2018-06-15 | MRT-DS-REC-TT-180502 | FI | 0 | TRUE | FALSE | FALSE
3173 | MRT-YL22-P3GHC-129014 | 2018-06-15 | MRT-DS-REC-TT-180502 | FI | 0 | TRUE | FALSE | FALSE
3174 | MRT-XJ00-P3MKA-220001 | 2018-06-15 | MRT-DS-REC-TT-180503 | FA | 0 | TRUE | FALSE | FALSE
3175 | MRT-YT01-P2MAJ-603110 | 2018-06-15 | MRT-DS-REC-TT-180505 | FC | 2 | TRUE | TRUE | FALSE
3176 | MRT-YT01-P3MAJ-604110 | 2018-06-15 | MRT-DS-REC-TT-180505 | FC | 2 | TRUE | TRUE | FALSE
3177 | MRT-YD00-P2LAC-126049 | 2018-06-18 | MRT-DS-REC-TT-180506 | FI | 0 | TRUE | FALSE | FALSE
3178 | MRT-YD00-P3LAC-126049 | 2018-06-18 | MRT-DS-REC-TT-180506 | FI | 0 | TRUE | FALSE | FALSE
3179 | MRT-YD00-P2LAC-126096 | 2018-06-18 | MRT-DS-REC-TT-180506 | FI | 0 | TRUE | FALSE | FALSE
3180 | MRT-YD00-P3LAC-126096 | 2018-06-18 | MRT-DS-REC-TT-180506 | FI | 0 | TRUE | FALSE | FALSE
3181 | MRT-YD00-P2LAC-126050 | 2018-06-18 | MRT-DS-REC-TT-180506 | FI | 0 | TRUE | FALSE | FALSE
3182 | MRT-YD00-P3LAC-126050 | 2018-06-18 | MRT-DS-REC-TT-180506 | FI | 0 | TRUE | FALSE | FALSE
3183 | MRT-YD00-P2LAC-126097 | 2018-06-18 | MRT-DS-REC-TT-180506 | FI | 0 | TRUE | FALSE | FALSE
3184 | MRT-YD00-P3LAC-126097 | 2018-06-18 | MRT-DS-REC-TT-180506 | FI | 0 | TRUE | FALSE | FALSE
3185 | MRT-YT01-P2QC-130016 | 2018-06-18 | MRT-DS-REC-TT-180507 | FI | 1 | TRUE | TRUE | FALSE
3186 | MRT-YT01-P3QC-130016 | 2018-06-18 | MRT-DS-REC-TT-180507 | FI | 1 | TRUE | TRUE | FALSE
3187 | MRT-YV02-P2QC-130017 | 2018-06-18 | MRT-DS-REC-TT-180508 | FI | 1 | TRUE | TRUE | FALSE
3188 | MRT-YV02-P3QC-130017 | 2018-06-18 | MRT-DS-REC-TT-180508 | FI | 1 | TRUE | TRUE | FALSE
3189 | MRT-YT01-P2QC-130033 | 2018-06-18 | MRT-DS-REC-TT-180509 | FI | 1 | TRUE | TRUE | FALSE
3190 | MRT-YT01-P3QC-130033 | 2018-06-18 | MRT-DS-REC-TT-180509 | FI | 1 | TRUE | TRUE | FALSE
3191 | MRT-YL01-P2QC-130034 | 2018-06-18 | MRT-DS-REC-TT-180510 | FI | 1 | TRUE | TRUE | FALSE
3192 | MRT-YL01-P3QC-130034 | 2018-06-18 | MRT-DS-REC-TT-180510 | FI | 1 | TRUE | TRUE | FALSE
3193 | MRT-YT01-P2QC-130014 | 2018-06-18 | MRT-DS-REC-TT-180511 | FI | 1 | TRUE | TRUE | FALSE
3194 | MRT-YT01-P3QC-130014 | 2018-06-18 | MRT-DS-REC-TT-180511 | FI | 1 | TRUE | TRUE | FALSE
3195 | MRT-DF04-P3ZEN-144003 | 2018-06-18 | MRT-DS-REC-TT-180513 | FI | 0 | TRUE | FALSE | FALSE
3196 | MRT-DF04-P2ZEN-142003 | 2018-06-18 | MRT-DS-REC-TT-180512 | FI | 1 | TRUE | TRUE | FALSE
3197 | MRT-DF04-P2ZEN-142004 | 2018-06-18 | MRT-DS-REC-TT-180512 | FI | 1 | TRUE | TRUE | FALSE
3198 | MRT-YK08-P2LAA-605102 | 2018-06-18 | MRT-DS-REC-TT-180514 | FC | 4 | TRUE | TRUE | FALSE
3199 | MRT-YK08-P3LAA-605502 | 2018-06-18 | MRT-DS-REC-TT-180514 | FC | 4 | TRUE | TRUE | FALSE
3200 | MRT-DF04-P3ZEN-144002 | 2018-06-19 | MRT-DS-REC-TT-180515 | FI | 0 | TRUE | FALSE | FALSE
3201 | MRT-DF04-P3ZEN-144004 | 2018-06-19 | MRT-DS-REC-TT-180515 | FI | 0 | TRUE | FALSE | FALSE
3202 | MRT-XH01-P2MKJ-220001 | 2018-06-20 | MRT-DS-REC-TT-180516 | FC | 1 | TRUE | TRUE | FALSE
3203 | MRT-YD00-P2GM-128501 | 2018-06-20 | MRT-DS-REC-TT-180517 | FC | 1 | TRUE | TRUE | FALSE
3204 | MRT-YD00-P3GM-128501 | 2018-06-20 | MRT-DS-REC-TT-180517 | FC | 1 | TRUE | TRUE | FALSE
3205 | MRT-YL00-P2QC-130007 | 2018-06-20 | MRT-DS-REC-TT-180518 | FI | 1 | TRUE | TRUE | FALSE
3206 | MRT-YL00-P3QC-130007 | 2018-06-20 | MRT-DS-REC-TT-180518 | FI | 1 | TRUE | TRUE | FALSE
3207 | MRT-XN00-P2QC-130008 | 2018-06-20 | MRT-DS-REC-TT-180519 | FI | 1 | TRUE | TRUE | FALSE
3208 | MRT-XN00-P3QC-130008 | 2018-06-20 | MRT-DS-REC-TT-180519 | FI | 1 | TRUE | TRUE | FALSE
3209 | MRT-YF00-P2QC-130019 | 2018-06-20 | MRT-DS-REC-TT-180520 | FI | 1 | TRUE | TRUE | FALSE
3210 | MRT-YF00-P3QC-130019 | 2018-06-20 | MRT-DS-REC-TT-180520 | FI | 1 | TRUE | TRUE | FALSE
3211 | MRT-YT02-P2LAC-126011 | 2018-06-20 | MRT-DS-REC-TT-180522 | FI | 1 | TRUE | TRUE | FALSE
3212 | MRT-YT02-P3LAC-126011 | 2018-06-20 | MRT-DS-REC-TT-180522 | FI | 1 | TRUE | TRUE | FALSE
3213 | MRT-YT02-P2LAC-126061 | 2018-06-20 | MRT-DS-REC-TT-180522 | FI | 1 | TRUE | TRUE | FALSE
3214 | MRT-YT02-P3LAC-126061 | 2018-06-20 | MRT-DS-REC-TT-180522 | FI | 1 | TRUE | TRUE | FALSE
3215 | MRT-XK00-P2MKJ-220001 | 2018-06-20 | MRT-DS-REC-TT-180521 | FC | 1 | TRUE | TRUE | FALSE
3216 | MRT-XJ00-P2PAB-142100 | 2018-06-21 | MRT-DS-REC-TT-180523 | FC | 1 | TRUE | TRUE | FALSE
3217 | MRT-XJ00-P3PAB-143100 | 2018-06-21 | MRT-DS-REC-TT-180523 | FC | 1 | TRUE | TRUE | FALSE
3218 | MRT-XJ00-P3PAB-144100 | 2018-06-21 | MRT-DS-REC-TT-180523 | FC | 1 | TRUE | TRUE | FALSE
3219 | MRT-XJ00-P3LBA-143000 | 2018-06-21 | MRT-DS-REC-TT-180524 | FI | 0 | TRUE | FALSE | FALSE
3220 | MRT-YT01-P2LAC-126005 | 2018-06-22 | MRT-DS-REC-TT-180525 | FC | 3 | TRUE | TRUE | FALSE
3221 | MRT-YT01-P3LAC-126005 | 2018-06-22 | MRT-DS-REC-TT-180525 | FC | 3 | TRUE | TRUE | FALSE
3222 | MRT-YK00-P2QC-130022 | 2018-06-22 | MRT-DS-REC-TT-180526 | FC | 1 | TRUE | TRUE | FALSE
3223 | MRT-YK00-P3QC-130022 | 2018-06-22 | MRT-DS-REC-TT-180526 | FC | 1 | TRUE | TRUE | FALSE
3224 | MRT-MA02-P2ZEN-163105 | 2018-06-22 | MRT-DS-REC-TT-180528 | FC | 1 | TRUE | TRUE | FALSE
3225 | MRT-YE03-P3ZEN-163104 | 2018-06-22 | MRT-DS-REC-TT-180528 | FC | 1 | TRUE | TRUE | FALSE
3226 | MRT-MA02-P3ZEN-163105 | 2018-06-22 | MRT-DS-REC-TT-180528 | FC | 1 | TRUE | TRUE | FALSE
3227 | MRT-CC02-P2UHA-170103 | 2018-06-22 | MRT-DS-REC-TT-180527 | FC | 5 | TRUE | TRUE | FALSE
3228 | MRT-VK02-P2UHA-170106 | 2018-06-22 | MRT-DS-REC-TT-180527 | FC | 5 | TRUE | TRUE | FALSE
3229 | MRT-CC02-P3UHA-170103 | 2018-06-22 | MRT-DS-REC-TT-180527 | FC | 5 | TRUE | TRUE | FALSE
3230 | MRT-VK02-P3UHA-170106 | 2018-06-22 | MRT-DS-REC-TT-180527 | FC | 5 | TRUE | TRUE | FALSE
3231 | MRT-YE00-P2QC-130021 | 2018-06-25 | MRT-DS-REC-TT-180529 | FC | 1 | TRUE | TRUE | FALSE
3232 | MRT-YE00-P3QC-130021 | 2018-06-25 | MRT-DS-REC-TT-180529 | FC | 1 | TRUE | TRUE | FALSE
3233 | MRT-XH01-P2QC-130011 | 2018-06-25 | MRT-DS-REC-TT-180530 | FC | 1 | TRUE | TRUE | FALSE
3234 | MRT-XH01-P3QC-130011 | 2018-06-25 | MRT-DS-REC-TT-180530 | FC | 1 | TRUE | TRUE | FALSE
3235 | MRT-YK10-P2QC-130010 | 2018-06-25 | MRT-DS-REC-TT-180531 | FC | 1 | TRUE | TRUE | FALSE
3236 | MRT-YK10-P3QC-130010 | 2018-06-25 | MRT-DS-REC-TT-180531 | FC | 1 | TRUE | TRUE | FALSE
3237 | MRT-XB02-P2QC-130009 | 2018-06-25 | MRT-DS-REC-TT-180532 | FC | 1 | TRUE | TRUE | FALSE
3238 | MRT-XB02-P3QC-130009 | 2018-06-25 | MRT-DS-REC-TT-180532 | FC | 1 | TRUE | TRUE | FALSE
3239 | MRT-XG02-P2LCM-110005 | 2018-06-25 | MRT-DS-REC-TT-180533 | FC | 6 | TRUE | TRUE | FALSE
3240 | MRT-XG02-P0QJA-110010 | 2018-06-25 | MRT-DS-REC-TT-180533 | FC | 4 | TRUE | TRUE | FALSE
3241 | MRT-XG02-P3LCM-110005 | 2018-06-25 | MRT-DS-REC-TT-180533 | FC | 6 | TRUE | TRUE | FALSE
3242 | MRT-HM01-P0SAH-135531 | 2018-06-25 | MRT-HK-REC-TT-180140 | FA | 0 | TRUE | FALSE | FALSE
3243 | MRT-HM01-P0SAL-135569 | 2018-06-25 | MRT-HK-REC-TT-180140 | FA | 0 | TRUE | FALSE | FALSE
3244 | MRT-HM01-P00SA-135575 | 2018-06-25 | MRT-HK-REC-TT-180140 | FA | 0 | TRUE | FALSE | FALSE
3245 | MRT-HM05-P00SA-135504 | 2018-06-25 | MRT-HK-REC-TT-180140 | FA | 2 | TRUE | TRUE | FALSE
3246 | MRT-HM01-P00SA-135572 | 2018-06-25 | MRT-HK-REC-TT-180140 | FA | 1 | TRUE | TRUE | FALSE
3247 | MRT-YS01-P2MKC-230012 | 2018-06-25 | MRT-DS-REC-TT-180534 | FA | 1 | TRUE | TRUE | FALSE
3248 | MRT-YS01-P3MKC-230012 | 2018-06-25 | MRT-DS-REC-TT-180534 | FA | 1 | TRUE | TRUE | FALSE
3249 | MRT-YR05-P0ZEN-163115 | 2018-06-25 | MRT-DS-REC-TT-180535 | FA | 0 | TRUE | FALSE | FALSE
3250 | MRT-YK08-P2LBG-111300 | 2018-06-26 | MRT-DS-REC-TT-180536 | FC | 1 | TRUE | TRUE | FALSE
3251 | MRT-YT01-P2LBG-111301 | 2018-06-26 | MRT-DS-REC-TT-180536 | FC | 1 | TRUE | TRUE | FALSE
3252 | MRT-YK08-P3LBG-111300 | 2018-06-26 | MRT-DS-REC-TT-180536 | FC | 1 | TRUE | TRUE | FALSE
3253 | MRT-YT01-P3LBG-111301 | 2018-06-26 | MRT-DS-REC-TT-180536 | FC | 1 | TRUE | TRUE | FALSE
3254 | MRT-YD00-P2BBT-150423 | 2018-06-26 | MRT-HK-REC-TT-180141 | FA | 0 | TRUE | FALSE | FALSE
3255 | MRT-YD00-P3BBT-150441 | 2018-06-26 | MRT-HK-REC-TT-180141 | FA | 0 | TRUE | FALSE | FALSE
3256 | MRT-YD00-P2BBT-150424 | 2018-06-26 | MRT-HK-REC-TT-180141 | FA | 0 | TRUE | FALSE | FALSE
3257 | MRT-YD00-P3BBT-150440 | 2018-06-26 | MRT-HK-REC-TT-180141 | FA | 0 | TRUE | FALSE | FALSE
3258 | MRT-YT01-P3BBT-150438 | 2018-06-26 | MRT-HK-REC-TT-180141 | FA | 0 | TRUE | FALSE | FALSE
3259 | MRT-YT01-P2BBT-150421 | 2018-06-26 | MRT-HK-REC-TT-180141 | FA | 0 | TRUE | FALSE | FALSE
3260 | MRT-UBE-P3BBT-150435 | 2018-06-26 | MRT-HK-REC-TT-180141 | FA | 0 | TRUE | FALSE | FALSE
3261 | MRT-UBE-P2BBT-150418 | 2018-06-26 | MRT-HK-REC-TT-180141 | FA | 0 | TRUE | FALSE | FALSE
3262 | MRT-CC03-P0UQQ-175838 | 2018-06-26 | MRT-HK-REC-TT-180142 | FA | 1 | TRUE | TRUE | FALSE
3263 | MRT-CC02-P0UBX-176035 | 2018-06-26 | MRT-HK-REC-TT-180142 | FA | 0 | TRUE | TRUE | FALSE
3264 | MRT-CC02-P0UBX-176005 | 2018-06-26 | MRT-HK-REC-TT-180142 | FA | 2 | TRUE | TRUE | FALSE
3265 | MRT-CC07-P0UBX-176015 | 2018-06-26 | MRT-HK-REC-TT-180142 | FA | 0 | TRUE | TRUE | FALSE
3266 | MRT-CC02-P0UBX-176020 | 2018-06-26 | MRT-HK-REC-TT-180142 | FA | 0 | TRUE | TRUE | FALSE
3267 | MRT-CC02-P0UBX-176025 | 2018-06-26 | MRT-HK-REC-TT-180142 | FA | 0 | TRUE | TRUE | FALSE
3268 | MRT-CC02-P0UBX-176030 | 2018-06-26 | MRT-HK-REC-TT-180142 | FA | 0 | TRUE | TRUE | FALSE
3269 | MRT-CC02-P0UBX-176006 | 2018-06-26 | MRT-HK-REC-TT-180142 | FA | 2 | TRUE | TRUE | FALSE
3270 | MRT-CC02-P0UBX-176007 | 2018-06-26 | MRT-HK-REC-TT-180142 | FA | 2 | TRUE | TRUE | FALSE
3271 | MRT-CA02-P0UYX-187177 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3272 | MRT-CA02-P0UVH-187080 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3273 | MRT-CA01-P0UYX-187187 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3274 | MRT-CA01-P0UVH-187088 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3275 | MRT-CA01-P0UYX-187186 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3276 | MRT-CA01-P0UYX-187171 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3277 | MRT-CA01-P0UVH-187073 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3278 | MRT-CA06-P0UVH-187054 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3279 | MRT-CA01-P0UVH-187066 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3280 | MRT-CA02-P0UVH-187068 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3281 | MRT-CA01-P0UVH-187070 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3282 | MRT-CA01-P0UVH-187072 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3283 | MRT-CA01-P0UVH-187074 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3284 | MRT-CA02-P0UVH-187076 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3285 | MRT-CA02-P0UVH-187078 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3286 | MRT-CA06-P0UYX-187154 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3287 | MRT-CA01-P0UYX-187164 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3288 | MRT-CA02-P0UYX-187166 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3289 | MRT-CA01-P0UYX-187168 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3290 | MRT-CA01-P0UYX-187170 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3291 | MRT-CA01-P0UYX-187172 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3292 | MRT-CA02-P0UYX-187174 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3293 | MRT-CA02-P0UYX-187176 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3294 | MRT-CA02-P0UYX-187178 | 2018-06-26 | MRT-HK-REC-TT-180143 | FA | 0 | TRUE | TRUE | FALSE
3295 | MRT-YD06-P3ZEN-163106 | 2018-06-26 | MRT-DS-REC-TT-180540 | FA | 1 | TRUE | TRUE | FALSE
3296 | MRT-YK08-P2MAJ-603203 | 2018-06-26 | MRT-DS-REC-TT-180537 | FC | 2 | TRUE | TRUE | FALSE
3297 | MRT-YK08-P3MAJ-604203 | 2018-06-26 | MRT-DS-REC-TT-180537 | FC | 2 | TRUE | TRUE | FALSE
3298 | MRT-XH01-P3MKA-220001 | 2018-06-26 | MRT-DS-REC-TT-180538 | FA | 0 | TRUE | FALSE | FALSE
3299 | MRT-YD00-P3MKW-220001 | 2018-06-26 | MRT-DS-REC-TT-180539 | FC | 1 | TRUE | TRUE | FALSE
3300 | MRT-YD00-P3MKW-220005 | 2018-06-26 | MRT-DS-REC-TT-180539 | FC | 1 | TRUE | TRUE | FALSE
3301 | MRT-YT01-P3LB-122093 | 2018-06-27 | MRT-DS-REC-TT-180541 | FA | 0 | TRUE | FALSE | FALSE
3302 | MRT-XH01-P2LB-122026 | 2018-06-27 | MRT-DS-REC-TT-180542 | FI | 0 | TRUE | FALSE | FALSE
3303 | MRT-XH01-P2LB-122025 | 2018-06-27 | MRT-DS-REC-TT-180542 | FI | 0 | TRUE | FALSE | FALSE
3304 | MRT-XH01-P3LB-122025 | 2018-06-27 | MRT-DS-REC-TT-180542 | FI | 0 | TRUE | FALSE | FALSE
3305 | MRT-XH01-P3LB-122026 | 2018-06-27 | MRT-DS-REC-TT-180542 | FI | 0 | TRUE | FALSE | FALSE
3306 | MRT-YT01-P3LB-122093 | 2018-06-27 | MRT-DS-REC-TT-180541 | FA | 0 | TRUE | FALSE | FALSE
3307 | MRT-XH01-P2LB-122026 | 2018-06-27 | MRT-DS-REC-TT-180542 | FI | 0 | TRUE | FALSE | FALSE
3308 | MRT-XH01-P2LB-122025 | 2018-06-27 | MRT-DS-REC-TT-180542 | FI | 0 | TRUE | FALSE | FALSE
3309 | MRT-XH01-P3LB-122025 | 2018-06-27 | MRT-DS-REC-TT-180542 | FI | 0 | TRUE | FALSE | FALSE
3310 | MRT-XH01-P3LB-122026 | 2018-06-27 | MRT-DS-REC-TT-180542 | FI | 0 | TRUE | FALSE | FALSE
3311 | MRT-YK09-P2MKC-230001 | 2018-06-27 | MRT-DS-REC-TT-180545 | FC | 1 | TRUE | TRUE | FALSE
3312 | MRT-YK09-P3MKC-230001 | 2018-06-27 | MRT-DS-REC-TT-180545 | FC | 1 | TRUE | TRUE | FALSE
3313 | MRT-XG02-P2LCB-127032 | 2018-06-27 | MRT-DS-REC-TT-180546 | FC | 1 | TRUE | TRUE | FALSE
3314 | MRT-XG02-P3LCB-127032 | 2018-06-27 | MRT-DS-REC-TT-180546 | FC | 1 | TRUE | TRUE | FALSE
3315 | MRT-YD00-P0QJA-111101 | 2018-06-27 | MRT-DS-REC-TT-180544 | FA | 0 | TRUE | FALSE | FALSE
3316 | MRT-XK00-P2GM-128508 | 2018-06-27 | MRT-DS-REC-TT-180547 | FC | 3 | TRUE | TRUE | FALSE
3317 | MRT-XK00-P3GM-128508 | 2018-06-27 | MRT-DS-REC-TT-180547 | FC | 3 | TRUE | TRUE | FALSE
3318 | MRT-XJ00-P2LCA-142000 | 2018-06-27 | MRT-DS-REC-TT-180543 | FI | 0 | TRUE | FALSE | FALSE
3319 | MRT-XJ00-P3LAB-143000 | 2018-06-27 | MRT-DS-REC-TT-180543 | FI | 0 | TRUE | FALSE | FALSE
3320 | MRT-QM03-POZEN-145005 | 2018-06-27 | MRT-HK-REC-TT-180144 | FA | 0 | TRUE | FALSE | FALSE
3321 | MRT-QM03-P0ZEN-185008 | 2018-06-27 | MRT-HK-REC-TT-180145 | FA | 0 | TRUE | TRUE | FALSE
3322 | MRT-QM03-P0ZEN-185003 | 2018-06-27 | MRT-HK-REC-TT-180145 | FA | 3 | TRUE | TRUE | FALSE
3323 | MRT-XA00-P2QC-130002 | 2018-06-29 | MRT-DS-REC-TT-180550 | FC | 2 | TRUE | TRUE | FALSE
3324 | MRT-XA00-P3QC-130002 | 2018-06-29 | MRT-DS-REC-TT-180550 | FC | 2 | TRUE | TRUE | FALSE
3325 | MRT-CC02-P2UMA-170207 | 2018-06-29 | MRT-DS-REC-TT-180549 | FC | 3 | TRUE | TRUE | FALSE
3326 | MRT-CC02-P2UMA-170208 | 2018-06-29 | MRT-DS-REC-TT-180549 | FC | 3 | TRUE | TRUE | FALSE
3327 | MRT-VK02-P2UMA-170210 | 2018-06-29 | MRT-DS-REC-TT-180549 | FC | 2 | TRUE | TRUE | FALSE
3328 | MRT-CC02-P3UMA-170207 | 2018-06-29 | MRT-DS-REC-TT-180549 | FC | 3 | TRUE | TRUE | FALSE
3329 | MRT-CC02-P3UMA-170208 | 2018-06-29 | MRT-DS-REC-TT-180549 | FC | 3 | TRUE | TRUE | FALSE
3330 | MRT-VK02-P3UMA-170210 | 2018-06-29 | MRT-DS-REC-TT-180549 | FC | 2 | TRUE | TRUE | FALSE
3331 | MRT-CC02-P0ZEN-175011 | 2018-06-29 | MRT-HK-REC-TT-180147 | FA | 1 | TRUE | TRUE | FALSE
3332 | MRT-CC07-P0UPC-175012 | 2018-06-29 | MRT-HK-REC-TT-180147 | FA | 1 | TRUE | TRUE | FALSE
3333 | MRT-CH04-P3BAC-150366 | 2018-06-29 | MRT-HK-REC-TT-180146 | FA | 0 | TRUE | TRUE | FALSE
3334 | MRT-XW03-P0BTA-150014 | 2018-06-29 | MRT-HK-REC-TT-180146 | FA | 1 | TRUE | TRUE | FALSE
3335 | MRT-YR05-P2ZEN-163116 | 2018-06-29 | MRT-DS-REC-TT-180553 | FI | 0 | TRUE | FALSE | FALSE
3336 | MRT-YR05-P2ZEN-163117 | 2018-06-29 | MRT-DS-REC-TT-180553 | FI | 0 | TRUE | FALSE | FALSE
3337 | MRT-YL00-P2ZEN-165101 | 2018-06-29 | MRT-DS-REC-TT-180554 | FA | 1 | TRUE | TRUE | FALSE
3338 | MRT-YL00-P3ZEN-165101 | 2018-06-29 | MRT-DS-REC-TT-180554 | FA | 1 | TRUE | TRUE | FALSE
3339 | MRT-XA00-P2MAA-220014 | 2018-06-29 | MRT-DS-REC-TT-180551 | FA | 2 | TRUE | TRUE | FALSE
3340 | MRT-XA00-P2MAA-220015 | 2018-06-29 | MRT-DS-REC-TT-180551 | FA | 2 | TRUE | TRUE | FALSE
3341 | MRT-XA00-P2MAA-220016 | 2018-06-29 | MRT-DS-REC-TT-180551 | FA | 2 | TRUE | TRUE | FALSE
3342 | MRT-XA00-P2MAA-220017 | 2018-06-29 | MRT-DS-REC-TT-180551 | FA | 2 | TRUE | TRUE | FALSE
3343 | MRT-XA00-P2MAA-220018 | 2018-06-29 | MRT-DS-REC-TT-180551 | FA | 2 | TRUE | TRUE | FALSE
3344 | MRT-XA00-P2MAA-220020 | 2018-06-29 | MRT-DS-REC-TT-180551 | FA | 2 | TRUE | TRUE | FALSE
3345 | MRT-XA00-P2MAA-220021 | 2018-06-29 | MRT-DS-REC-TT-180551 | FA | 2 | TRUE | TRUE | FALSE
3346 | MRT-XA00-P2MAA-220022 | 2018-06-29 | MRT-DS-REC-TT-180551 | FA | 2 | TRUE | TRUE | FALSE
3347 | MRT-YL00-P2MAG-601010 | 2018-07-02 | MRT-DS-REC-TT-180555 | FA | 0 | TRUE | FALSE | FALSE
3348 | MRT-YL00-P3MAG-602010 | 2018-07-02 | MRT-DS-REC-TT-180555 | FA | 0 | TRUE | FALSE | FALSE
3349 | MRT-YT01-P2MAG-601007 | 2018-07-02 | MRT-DS-REC-TT-180557 | FC | 4 | TRUE | TRUE | FALSE
3350 | MRT-YT01-P3MAG-602007 | 2018-07-02 | MRT-DS-REC-TT-180557 | FC | 4 | TRUE | TRUE | FALSE
3351 | MRT-XA01-P0ABA-150502 | 2018-07-02 | MRT-HK-REC-TT-180148 | FA | 2 | TRUE | TRUE | FALSE
3352 | MRT-YU02-P2BJA-150041 | 2018-07-02 | MRT-HK-REC-TT-180149 | FA | 0 | TRUE | FALSE | FALSE
3353 | MRT-YU02-P3BJA-150042 | 2018-07-02 | MRT-HK-REC-TT-180149 | FA | 0 | TRUE | FALSE | FALSE
3354 | MRT-YU02-P3BJC-150043 | 2018-07-02 | MRT-HK-REC-TT-180149 | FA | 0 | TRUE | FALSE | FALSE
3355 | MRT-YU02-P0BJJ-150052 | 2018-07-02 | MRT-HK-REC-TT-180149 | FA | 0 | TRUE | FALSE | FALSE
3356 | MRT-XK00-P2LAC-126013 | 2018-07-02 | MRT-DS-REC-TT-180556 | FI | 0 | TRUE | FALSE | FALSE
3357 | MRT-XK00-P3LAC-126013 | 2018-07-02 | MRT-DS-REC-TT-180556 | FI | 0 | TRUE | FALSE | FALSE
3358 | MRT-XK00-P2LAC-126063 | 2018-07-02 | MRT-DS-REC-TT-180556 | FI | 0 | TRUE | FALSE | FALSE
3359 | MRT-XK00-P3LAC-126063 | 2018-07-02 | MRT-DS-REC-TT-180556 | FI | 0 | TRUE | FALSE | FALSE
3360 | MRT-XA00-P3MAA-220016 | 2018-07-02 | MRT-DS-REC-TT-180552 | FA | 2 | TRUE | TRUE | FALSE
3361 | MRT-XA00-P3MAA-220014 | 2018-07-02 | MRT-DS-REC-TT-180552 | FA | 2 | TRUE | TRUE | FALSE
3362 | MRT-XA00-P3MAA-220015 | 2018-07-02 | MRT-DS-REC-TT-180552 | FA | 2 | TRUE | TRUE | FALSE
3363 | MRT-XA00-P3MAA-220017 | 2018-07-02 | MRT-DS-REC-TT-180552 | FA | 2 | TRUE | TRUE | FALSE
3364 | MRT-XA00-P3MAA-220018 | 2018-07-02 | MRT-DS-REC-TT-180552 | FA | 2 | TRUE | TRUE | FALSE
3365 | MRT-XA00-P3MAA-220019 | 2018-07-02 | MRT-DS-REC-TT-180552 | FA | 2 | TRUE | TRUE | FALSE
3366 | MRT-XA00-P3MAA-220020 | 2018-07-02 | MRT-DS-REC-TT-180552 | FA | 2 | TRUE | TRUE | FALSE
3367 | MRT-XA00-P3MAA-220021 | 2018-07-02 | MRT-DS-REC-TT-180552 | FA | 2 | TRUE | TRUE | FALSE
3368 | MRT-XA00-P3MAA-220022 | 2018-07-02 | MRT-DS-REC-TT-180552 | FA | 2 | TRUE | TRUE | FALSE
3369 | MRT-CC02-P2UMA-170707 | 2018-07-02 | MRT-DS-REC-TT-180558 | FC | 3 | TRUE | TRUE | FALSE
3370 | MRT-CC02-P2UMA-170708 | 2018-07-02 | MRT-DS-REC-TT-180558 | FC | 3 | TRUE | TRUE | FALSE
3371 | MRT-CC02-P2UMA-170709 | 2018-07-02 | MRT-DS-REC-TT-180558 | FC | 3 | TRUE | TRUE | FALSE
3372 | MRT-VK02-P2UMA-170710 | 2018-07-02 | MRT-DS-REC-TT-180558 | FC | 2 | TRUE | TRUE | FALSE
3373 | MRT-CC02-P3UMA-170707 | 2018-07-02 | MRT-DS-REC-TT-180558 | FC | 3 | TRUE | TRUE | FALSE
3374 | MRT-CC02-P3UMA-170708 | 2018-07-02 | MRT-DS-REC-TT-180558 | FC | 3 | TRUE | TRUE | FALSE
3375 | MRT-CC02-P3UMA-170709 | 2018-07-02 | MRT-DS-REC-TT-180558 | FC | 3 | TRUE | TRUE | FALSE
3376 | MRT-VK02-P3UMA-170710 | 2018-07-02 | MRT-DS-REC-TT-180558 | FC | 2 | TRUE | TRUE | FALSE
3377 | MRT-CC02-P0UMA-170702 | 2018-07-02 | MRT-DS-REC-TT-180558 | FC | 2 | TRUE | TRUE | FALSE
3378 | MRT-YD00-P2LB-122049 | 2018-07-03 | MRT-DS-REC-TT-180559 | FC | 2 | TRUE | TRUE | FALSE
3379 | MRT-YD00-P3LB-122049 | 2018-07-03 | MRT-DS-REC-TT-180559 | FC | 2 | TRUE | TRUE | FALSE
3380 | MRT-YT01-P2LB-122096 | 2018-07-03 | MRT-DS-REC-TT-180560 | FC | 1 | TRUE | TRUE | FALSE
3381 | MRT-YT01-P2LB-122097 | 2018-07-03 | MRT-DS-REC-TT-180560 | FC | 1 | TRUE | TRUE | FALSE
3382 | MRT-YT02-P2LB-122094 | 2018-07-03 | MRT-DS-REC-TT-180560 | FC | 1 | TRUE | TRUE | FALSE
3383 | MRT-YT01-P2LB-122095 | 2018-07-03 | MRT-DS-REC-TT-180560 | FC | 1 | TRUE | TRUE | FALSE
3384 | MRT-YQ01-P2LB-122085 | 2018-07-03 | MRT-DS-REC-TT-180560 | FC | 1 | TRUE | TRUE | FALSE
3385 | MRT-YQ01-P3LB-122085 | 2018-07-03 | MRT-DS-REC-TT-180560 | FC | 1 | TRUE | TRUE | FALSE
3386 | MRT-YT02-P3LB-122094 | 2018-07-03 | MRT-DS-REC-TT-180560 | FC | 1 | TRUE | TRUE | FALSE
3387 | MRT-YT01-P3LB-122095 | 2018-07-03 | MRT-DS-REC-TT-180560 | FC | 1 | TRUE | TRUE | FALSE
3388 | MRT-YT01-P3LB-122096 | 2018-07-03 | MRT-DS-REC-TT-180560 | FC | 1 | TRUE | TRUE | FALSE
3389 | MRT-YT01-P3LB-122097 | 2018-07-03 | MRT-DS-REC-TT-180560 | FC | 1 | TRUE | TRUE | FALSE
3390 | MRT-DN05-P2LB-122110 | 2018-07-03 | MRT-DS-REC-TT-180561 | FA | 0 | TRUE | FALSE | FALSE
3391 | MRT-YF02-P2QC-130006 | 2018-07-04 | MRT-DS-REC-TT-180562 | FC | 2 | TRUE | TRUE | FALSE
3392 | MRT-YF02-P3QC-130006 | 2018-07-04 | MRT-DS-REC-TT-180562 | FC | 2 | TRUE | TRUE | FALSE
3393 | MRT-YT01-P2QC-130013 | 2018-07-04 | MRT-DS-REC-TT-180563 | FI | 1 | TRUE | TRUE | FALSE
3394 | MRT-YT01-P3QC-130013 | 2018-07-04 | MRT-DS-REC-TT-180563 | FI | 1 | TRUE | TRUE | FALSE
3395 | MRT-CV03-P2ZEN-165102 | 2018-07-04 | MRT-DS-REC-TT-180566 | FC | 1 | TRUE | TRUE | FALSE
3396 | MRT-CV03-P2ZEN-165104 | 2018-07-04 | MRT-DS-REC-TT-180566 | FC | 1 | TRUE | TRUE | FALSE
3397 | MRT-CV03-P3ZEN-165102 | 2018-07-04 | MRT-DS-REC-TT-180566 | FC | 1 | TRUE | TRUE | FALSE
3398 | MRT-CV03-P3ZEN-165104 | 2018-07-04 | MRT-DS-REC-TT-180566 | FC | 1 | TRUE | TRUE | FALSE
3399 | MRT-XB00-P2GM-128506 | 2018-07-04 | MRT-DS-REC-TT-180567 | FI | 0 | TRUE | FALSE | FALSE
3400 | MRT-XB00-P3GM-128506 | 2018-07-04 | MRT-DS-REC-TT-180567 | FI | 0 | TRUE | FALSE | FALSE
3401 | MRT-YT01-P2BAC-150354 | 2018-07-04 | MRT-HK-REC-TT-180151 | FI | 1 | TRUE | TRUE | FALSE
3402 | MRT-YT01-P3BAC-150361 | 2018-07-04 | MRT-HK-REC-TT-180151 | FI | 1 | TRUE | TRUE | FALSE
3403 | MRT-CA00-P0UCA-180105 | 2018-07-05 | MRT-DS-REC-TT-180565 | FC | 3 | TRUE | TRUE | FALSE
3404 | MRT-CA00-P0UCA-180107 | 2018-07-05 | MRT-DS-REC-TT-180565 | FC | 3 | TRUE | TRUE | FALSE
3405 | MRT-CA00-P0UCA-180108 | 2018-07-05 | MRT-DS-REC-TT-180565 | FC | 3 | TRUE | TRUE | FALSE
3406 | MRT-CA00-P0UCA-180112 | 2018-07-05 | MRT-DS-REC-TT-180565 | FC | 3 | TRUE | TRUE | FALSE
3407 | MRT-CA00-P0UCA-180113 | 2018-07-05 | MRT-DS-REC-TT-180565 | FC | 3 | TRUE | TRUE | FALSE
3408 | MRT-CA00-P0UCA-180119 | 2018-07-05 | MRT-DS-REC-TT-180565 | FA | 1 | TRUE | TRUE | FALSE
3409 | MRT-CA00-P0UCA-180120 | 2018-07-05 | MRT-DS-REC-TT-180565 | FC | 1 | TRUE | TRUE | FALSE
3410 | MRT-CA01-P0UCA-180122 | 2018-07-05 | MRT-DS-REC-TT-180565 | FC | 3 | TRUE | TRUE | FALSE
3411 | MRT-CA01-P0UCA-180123 | 2018-07-05 | MRT-DS-REC-TT-180565 | FC | 3 | TRUE | TRUE | FALSE
3412 | MRT-CA01-P0UCA-180127 | 2018-07-05 | MRT-DS-REC-TT-180565 | FC | 3 | TRUE | TRUE | FALSE
3413 | MRT-CA01-P0UCA-180128 | 2018-07-05 | MRT-DS-REC-TT-180565 | FC | 3 | TRUE | TRUE | FALSE
3414 | MRT-CA02-P0UCA-180134 | 2018-07-05 | MRT-DS-REC-TT-180565 | FC | 3 | TRUE | TRUE | FALSE
3415 | MRT-CA02-P0UCA-180135 | 2018-07-05 | MRT-DS-REC-TT-180565 | FC | 3 | TRUE | TRUE | FALSE
3416 | MRT-YD00-P2LB-122108 | 2018-07-05 | MRT-DS-REC-TT-180564 | FC | 3 | TRUE | TRUE | FALSE
3417 | MRT-YD00-P3LB-122108 | 2018-07-05 | MRT-DS-REC-TT-180564 | FC | 3 | TRUE | TRUE | FALSE
3418 | MRT-XW03-P0BBA-150285 | 2018-07-05 | MRT-HK-REC-TT-180150 | FA | 1 | TRUE | TRUE | FALSE
3419 | MRT-YK09-P0SMM-128007 | 2018-07-05 | MRT-DS-REC-TT-180572 | FC | 2 | TRUE | TRUE | FALSE
3420 | MRT-YD00-P2SM-128020 | 2018-07-05 | MRT-DS-REC-TT-180568 | FC | 1 | TRUE | TRUE | FALSE
3421 | MRT-YD00-P3SM-128020 | 2018-07-05 | MRT-DS-REC-TT-180568 | FC | 1 | TRUE | TRUE | FALSE
3422 | MRT-CQ02-P2MAJ-603208 | 2018-07-05 | MRT-DS-REC-TT-180569 | FC | 1 | TRUE | TRUE | FALSE
3423 | MRT-CQ02-P3MAJ-604208 | 2018-07-05 | MRT-DS-REC-TT-180569 | FC | 1 | TRUE | TRUE | FALSE
3424 | MRT-YK10-P2MKB-230001 | 2018-07-05 | MRT-DS-REC-TT-180575 | FI | 0 | TRUE | FALSE | FALSE
3425 | MRT-XF00-P2MKA-230001 | 2018-07-05 | MRT-DS-REC-TT-180575 | FI | 0 | TRUE | FALSE | FALSE
3426 | MRT-YK10-P2MKA-230002 | 2018-07-05 | MRT-DS-REC-TT-180575 | FI | 0 | TRUE | FALSE | FALSE
3427 | MRT-YD00-P2PAB-113251 | 2018-07-05 | MRT-DS-REC-TT-180576 | FC | 3 | TRUE | TRUE | FALSE
3428 | MRT-YT01-P2PAB-113252 | 2018-07-05 | MRT-DS-REC-TT-180576 | FC | 3 | TRUE | TRUE | FALSE
3429 | MRT-XG02-P2PAB-113253 | 2018-07-05 | MRT-DS-REC-TT-180576 | FC | 3 | TRUE | TRUE | FALSE
3430 | MRT-YD00-P3PAB-113251 | 2018-07-05 | MRT-DS-REC-TT-180576 | FC | 3 | TRUE | TRUE | FALSE
3431 | MRT-YT01-P3PAB-113252 | 2018-07-05 | MRT-DS-REC-TT-180576 | FC | 3 | TRUE | TRUE | FALSE
3432 | MRT-XG02-P3PAB-113253 | 2018-07-05 | MRT-DS-REC-TT-180576 | FC | 3 | TRUE | TRUE | FALSE
3433 | MRT-YM01-P3PAC-130001 | 2018-07-06 | MRT-HK-REC-TT-180153 | FA | 0 | TRUE | FALSE | FALSE
3434 | MRT-YM01-P2PAC-130001 | 2018-07-06 | MRT-HK-REC-TT-180153 | FA | 0 | TRUE | FALSE | FALSE
3435 | MRT-YD00-P2PGB-113101 | 2018-07-06 | MRT-DS-REC-TT-180577 | FC | 2 | TRUE | TRUE | FALSE
3436 | MRT-YD00-P3PGB-113101 | 2018-07-06 | MRT-DS-REC-TT-180577 | FC | 2 | TRUE | TRUE | FALSE
3437 | MRT-YD00-P2PGB-113105 | 2018-07-06 | MRT-DS-REC-TT-180578 | FC | 2 | TRUE | TRUE | FALSE
3438 | MRT-YD00-P3PGB-113105 | 2018-07-06 | MRT-DS-REC-TT-180578 | FC | 2 | TRUE | TRUE | FALSE
3439 | MRT-YL01-P2ZEN-161051 | 2018-07-06 | MRT-DS-REC-TT-180574 | FC | 3 | TRUE | TRUE | FALSE
3440 | MRT-YL01-P3ZEN-161051 | 2018-07-06 | MRT-DS-REC-TT-180574 | FC | 3 | TRUE | TRUE | FALSE
3441 | MRT-YD16-P2SCA-127531 | 2018-07-06 | MRT-DS-REC-TT-180579 | FC | 2 | TRUE | TRUE | FALSE
3442 | MRT-YD16-P3SCA-127531 | 2018-07-06 | MRT-DS-REC-TT-180579 | FC | 2 | TRUE | TRUE | FALSE
3443 | MRT-CV03-P0ZEN-163107 | 2018-07-06 | MRT-DS-REC-TT-180573 | FC | 1 | TRUE | TRUE | FALSE
3444 | MRT-CV03-P3ZEN-163118 | 2018-07-06 | MRT-DS-REC-TT-180573 | FC | 1 | TRUE | TRUE | FALSE
3445 | MRT-XA00-P2QU-130025 | 2018-07-06 | MRT-DS-REC-TT-180580 | FC | 3 | TRUE | TRUE | FALSE
3446 | MRT-XA00-P3QU-130025 | 2018-07-06 | MRT-DS-REC-TT-180580 | FC | 3 | TRUE | TRUE | FALSE
3447 | MRT-CQ02-P2QC-130023 | 2018-07-06 | MRT-DS-REC-TT-180581 | FI | 0 | TRUE | FALSE | FALSE
3448 | MRT-CQ02-P3QC-130023 | 2018-07-06 | MRT-DS-REC-TT-180581 | FI | 0 | TRUE | FALSE | FALSE
3449 | MRT-XJ00-P2PAB-140001 | 2018-07-06 | MRT-DS-REC-TT-180583 | FC | 2 | TRUE | TRUE | FALSE
3450 | MRT-XJ00-P3PAB-140001 | 2018-07-06 | MRT-DS-REC-TT-180583 | FC | 2 | TRUE | TRUE | FALSE
3451 | MRT-XL00-P2LB-122030 | 2018-07-09 | MRT-DS-REC-TT-180570 | FC | 4 | TRUE | TRUE | FALSE
3452 | MRT-XL00-P3LB-122030 | 2018-07-09 | MRT-DS-REC-TT-180570 | FC | 3 | TRUE | TRUE | FALSE
3453 | MRT-CC02-P0UPC-175746 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3454 | MRT-CC02-P0UPC-175744 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3455 | MRT-CC02-P0UPC-175743 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3456 | MRT-CC02-P0UPC-175742 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3457 | MRT-CC02-P0UPC-175741 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3458 | MRT-CC02-P0UPC-175737 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3459 | MRT-CC02-P0UPC-175736 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3460 | MRT-CC02-P0UPC-175733 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3461 | MRT-CC02-P0UPC-175732 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3462 | MRT-CC02-P0UPC-175731 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3463 | MRT-CC02-P0UPC-175729 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3464 | MRT-CC02-P0UPC-175728 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3465 | MRT-CC02-P0UPC-175727 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3466 | MRT-CC02-P0UPC-175726 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 1 | TRUE | TRUE | FALSE
3467 | MRT-CC02-P0UPC-175723 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3468 | MRT-CC02-P0UPC-175722 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3469 | MRT-CC02-P0UPC-175721 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3470 | MRT-CC02-P0UPC-175705 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 4 | TRUE | TRUE | FALSE
3471 | MRT-CC02-P0UPC-175720 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 1 | TRUE | TRUE | FALSE
3472 | MRT-CC02-P0UPC-175725 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 1 | TRUE | TRUE | FALSE
3473 | MRT-CC02-P0UPC-175730 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 1 | TRUE | TRUE | FALSE
3474 | MRT-CC02-P0UPC-175740 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3475 | MRT-CC02-P0UPC-175745 | 2018-07-09 | MRT-HK-REC-TT-180154 | FA | 0 | TRUE | TRUE | FALSE
3476 | MRT-CA00-P0UMA-180023 | 2018-07-10 | MRT-DS-REC-TT-180585 | FC | 1 | TRUE | TRUE | FALSE
3477 | MRT-CA00-P0UMA-180024 | 2018-07-10 | MRT-DS-REC-TT-180585 | FC | 1 | TRUE | TRUE | FALSE
3478 | MRT-XA01-P0ASA-150501 | 2018-07-10 | MRT-HK-REC-TT-180156 | FA | 0 | TRUE | FALSE | FALSE
3479 | MRT-YE06-P0BAU-150160 | 2018-07-10 | MRT-HK-REC-TT-180157 | FA | 1 | TRUE | TRUE | FALSE
3480 | MRT-XA00-P2MAA-220013 | 2018-07-10 | MRT-DS-REC-TT-180584 | FA | 2 | TRUE | TRUE | FALSE
3481 | MRT-XA00-P3MAA-220013 | 2018-07-10 | MRT-DS-REC-TT-180584 | FA | 2 | TRUE | TRUE | FALSE
3482 | MRT-XV00-P2MAA-220036 | 2018-07-10 | MRT-DS-REC-TT-180584 | FA | 2 | TRUE | TRUE | FALSE
3483 | MRT-XV00-P2MAV-220037 | 2018-07-10 | MRT-DS-REC-TT-180584 | FA | 2 | TRUE | TRUE | FALSE
3484 | MRT-XV00-P2MAV-220037 | 2018-07-10 | MRT-DS-REC-TT-180584 | FA | 2 | TRUE | TRUE | FALSE
3485 | MRT-XV00-P3MAA-220036 | 2018-07-10 | MRT-DS-REC-TT-180584 | FA | 2 | TRUE | TRUE | FALSE
3486 | MRT-XV00-P3MAV-220037 | 2018-07-10 | MRT-DS-REC-TT-180584 | FA | 2 | TRUE | TRUE | FALSE
3487 | MRT-CA03-P0UCA-180132 | 2018-07-10 | MRT-DS-REC-TT-180586 | FA | 2 | TRUE | TRUE | FALSE
3488 | MRT-CA01-P0UCA-180133 | 2018-07-10 | MRT-DS-REC-TT-180586 | FA | 2 | TRUE | TRUE | FALSE
3837 | MRT-BAB-P2BAT-150372 | 2018-07-10 | MRT-HK-REC-TT-180158 | FA | 1 | TRUE | TRUE | FALSE
3838 | MRT-YT01-P2BAT-150371 | 2018-07-10 | MRT-HK-REC-TT-180158 | FA | 0 | TRUE | FALSE | FALSE
3839 | MRT-YD00-P2BAT-150373 | 2018-07-10 | MRT-HK-REC-TT-180158 | FA | 1 | TRUE | TRUE | FALSE
3840 | MRT-YD00-P2BAT-150383 | 2018-07-10 | MRT-HK-REC-TT-180158 | FA | 1 | TRUE | TRUE | FALSE
3841 | MRT-YT01-P2BAT-150375 | 2018-07-10 | MRT-HK-REC-TT-180158 | FA | 1 | TRUE | TRUE | FALSE
3842 | MRT-YT01-P3BAT-150397 | 2018-07-10 | MRT-HK-REC-TT-180158 | FA | 1 | TRUE | TRUE | FALSE
3489 | MRT-XB00-P2SCA-127509 | 2018-07-11 | MRT-DS-REC-TT-180588 | FC | 2 | TRUE | TRUE | FALSE
3490 | MRT-XB00-P3SCA-127509 | 2018-07-11 | MRT-DS-REC-TT-180588 | FC | 2 | TRUE | TRUE | FALSE
3491 | MRT-YT01-P2LCB-127033 | 2018-07-11 | MRT-DS-REC-TT-180589 | FA | 1 | TRUE | TRUE | FALSE
3492 | MRT-YT01-P3LCB-127033 | 2018-07-11 | MRT-DS-REC-TT-180589 | FA | 1 | TRUE | TRUE | FALSE
3493 | MRT-CQ02-P2GHC-129016 | 2018-07-11 | MRT-DS-REC-TT-180587 | FI | 0 | TRUE | FALSE | FALSE
3494 | MRT-CQ02-P3GHC-129016 | 2018-07-11 | MRT-DS-REC-TT-180587 | FI | 0 | TRUE | FALSE | FALSE
3495 | MRT-YL00-P2MAJ-603207 | 2018-07-11 | MRT-DS-REC-TT-180590 | FC | 3 | TRUE | TRUE | FALSE
3496 | MRT-YL00-P3MAJ-604207 | 2018-07-11 | MRT-DS-REC-TT-180590 | FC | 3 | TRUE | TRUE | FALSE
3497 | MRT-YL13-P3CJJ-240061 | 2018-07-11 | MRT-DS-REC-TT-180592 | FI | 0 | TRUE | FALSE | FALSE
3498 | MRT-YL13-P2CJJ-240061 | 2018-07-11 | MRT-DS-REC-TT-180592 | FI | 0 | TRUE | FALSE | FALSE
3499 | MRT-YF00-P2CBA-161203 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3500 | MRT-YF00-P2CGA-161303 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3501 | MRT-YF00-P3CBA-161203 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3502 | MRT-YF00-P3CGA-161303 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3503 | MRT-YF00-P2CBA-161204 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3504 | MRT-YF00-P2CGA-161304 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3505 | MRT-YF00-P3CBA-161204 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3506 | MRT-YF00-P3CGA-161304 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3507 | MRT-YF00-P2CBA-161205 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3508 | MRT-YF00-P2CGA-161305 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3509 | MRT-YF00-P3CBA-161205 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3510 | MRT-YF00-P3CGA-161305 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3511 | MRT-YF00-P2CBA-161206 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3512 | MRT-YF00-P2CGA-161306 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3513 | MRT-YF00-P3CGA-161306 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3514 | MRT-YF00-P2CBA-161207 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3515 | MRT-YF00-P2CGA-161307 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3516 | MRT-YF00-P3CBA-161207 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3517 | MRT-YF00-P3CGA-161307 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3518 | MRT-YF00-P2CBA-161208 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3519 | MRT-YF00-P2CGA-161308 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3520 | MRT-YF00-P3CBA-161208 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3521 | MRT-YF00-P3CGA-161308 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3522 | MRT-YF00-P0CBA-161221 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3523 | MRT-YF00-P0CGA-161321 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3524 | MRT-YF00-P2CBA-161209 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3525 | MRT-YF00-P2CGA-161309 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3526 | MRT-YF00-P3CBA-161209 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3527 | MRT-YF00-P3CGA-161309 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3528 | MRT-YF00-P0CBA-161222 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3529 | MRT-YF00-P0CGA-161322 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3530 | MRT-YF00-P2CBA-161211 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3531 | MRT-YF00-P2CBA-161212 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3532 | MRT-YF00-P2CBA-161210 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3533 | MRT-YF00-P2CGA-161311 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3534 | MRT-YF00-P2CGA-161312 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3535 | MRT-YF00-P2CGA-161310 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3536 | MRT-YF00-P3CBA-161211 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3537 | MRT-YF00-P3CBA-161212 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3538 | MRT-YF00-P3CBA-161210 | 2018-07-12 | MRT-DS-REC-TT-180582 | FA | 2 | TRUE | TRUE | FALSE
3539 | MRT-YF00-P3CGA-161311 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3540 | MRT-YF00-P3CGA-161312 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3541 | MRT-YF00-P3CGA-161310 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3542 | MRT-VN03-P2LB-122015 | 2018-07-12 | MRT-DS-REC-TT-180594 | FC | 2 | TRUE | TRUE | FALSE
3543 | MRT-VN03-P3LB-122015 | 2018-07-12 | MRT-DS-REC-TT-180594 | FC | 2 | TRUE | TRUE | FALSE
3544 | MRT-YR01-P2LB-122082 | 2018-07-12 | MRT-DS-REC-TT-180595 | FI | 0 | TRUE | FALSE | FALSE
3545 | MRT-XF00-P3MKA-220001 | 2018-07-12 | MRT-DS-REC-TT-180596 | FI | 0 | TRUE | FALSE | FALSE
3546 | MRT-YK10-P3MKB-230001 | 2018-07-12 | MRT-DS-REC-TT-180596 | FI | 0 | TRUE | FALSE | FALSE
3547 | MRT-YK10-P3MKA-230002 | 2018-07-12 | MRT-DS-REC-TT-180596 | FI | 0 | TRUE | FALSE | FALSE
3548 | MRT-YF00-P3CBA-161206 | 2018-07-12 | MRT-DS-REC-TT-180582 | FC | 2 | TRUE | TRUE | FALSE
3549 | MRT-XG02-P2MKJ-210001 | 2018-07-12 | MRT-DS-REC-TT-180591 | FI | 1 | TRUE | TRUE | FALSE
3550 | MRT-XG02-P3MKW-210001 | 2018-07-12 | MRT-DS-REC-TT-180591 | FA | 1 | TRUE | TRUE | FALSE
3551 | MRT-XG02-P3MKG-210001 | 2018-07-12 | MRT-DS-REC-TT-180591 | FA | 1 | TRUE | TRUE | FALSE
3552 | MRT-XS00-P3MKW-210001 | 2018-07-12 | MRT-DS-REC-TT-180591 | FI | 1 | TRUE | TRUE | FALSE
3553 | MRT-XS00-P3MKG-210001 | 2018-07-12 | MRT-DS-REC-TT-180591 | FI | 1 | TRUE | TRUE | FALSE
3554 | MRT-YL00-P2MAJ-603105 | 2018-07-12 | MRT-DS-REC-TT-180597 | FC | 4 | TRUE | TRUE | FALSE
3555 | MRT-YL00-P3MAJ-604105 | 2018-07-12 | MRT-DS-REC-TT-180597 | FC | 4 | TRUE | TRUE | FALSE
3556 | MRT-YT01-P2MAJ-603100 | 2018-07-12 | MRT-DS-REC-TT-180593 | FC | 3 | TRUE | TRUE | FALSE
3557 | MRT-YT01-P2MAJ-603103 | 2018-07-12 | MRT-DS-REC-TT-180593 | FC | 3 | TRUE | TRUE | FALSE
3558 | MRT-YT01-P3MAJ-604100 | 2018-07-12 | MRT-DS-REC-TT-180593 | FC | 3 | TRUE | TRUE | FALSE
3559 | MRT-YT01-P3MAJ-604103 | 2018-07-12 | MRT-DS-REC-TT-180593 | FC | 3 | TRUE | TRUE | FALSE
3560 | MRT-CQ02-P2LAA-605103 | 2018-07-13 | MRT-DS-REC-TT-180598 | FI | 0 | TRUE | FALSE | FALSE
3561 | MRT-CQ02-P3LAA-605503 | 2018-07-13 | MRT-DS-REC-TT-180598 | FI | 0 | TRUE | FALSE | FALSE
3562 | MRT-YD00-P0PGB-606000 | 2018-07-13 | MRT-DS-REC-TT-180599 | FC | 3 | TRUE | TRUE | FALSE
3563 | MRT-YD00-P0PGB-606001 | 2018-07-13 | MRT-DS-REC-TT-180599 | FC | 3 | TRUE | TRUE | FALSE
3564 | MRT-YD00-P0QHE-606001 | 2018-07-13 | MRT-DS-REC-TT-180600 | FC | 3 | TRUE | TRUE | FALSE
3565 | MRT-YD00-P0UAA-150206 | 2018-07-13 | MRTHK-REC-TT-180162 | FA | 0 | TRUE | TRUE | FALSE
3566 | MRT-CC00-P0ZEN-145401 | 2018-07-13 | MRT-HK-REC-TT-180159 | FA | 0 | TRUE | FALSE | FALSE
3567 | MRT-CN00-P3ZEN-110100 | 2018-07-13 | MRT-DS-REC-TT-180603 | FC | 2 | TRUE | TRUE | FALSE
3568 | MRT-YD00-P3BAT-150401 | 2018-07-13 | MRT-HK-REC-TT-180160 | FA | 0 | TRUE | FALSE | FALSE
3569 | MRT-YD00-P2BAT-150378 | 2018-07-13 | MRT-HK-REC-TT-180160 | FA | 0 | TRUE | FALSE | FALSE
3570 | MRT-YD00-P2BAT-150382 | 2018-07-13 | MRT-HK-REC-TT-180160 | FA | 0 | TRUE | FALSE | FALSE
3571 | MRT-YD00-P3BAT-150405 | 2018-07-13 | MRT-HK-REC-TT-180160 | FA | 0 | TRUE | FALSE | FALSE
3572 | MRT-YD00-P2BAT-150381 | 2018-07-13 | MRT-HK-REC-TT-180160 | FA | 0 | TRUE | FALSE | FALSE
3573 | MRT-YD00-P3BAT-150404 | 2018-07-13 | MRT-HK-REC-TT-180160 | FA | 0 | TRUE | FALSE | FALSE
3574 | MRT-YU02-P3BJN-150054 | 2018-07-13 | MRT-HK-REC-TT-180161 | FA | 0 | TRUE | TRUE | FALSE
3575 | MRT-YU02-P0BJL-150055 | 2018-07-13 | MRT-HK-REC-TT-180161 | FA | 0 | TRUE | TRUE | FALSE
3576 | MRT-YK00-P2LB-122076 | 2018-07-13 | MRT-DS-REC-TT-180604 | FI | 0 | TRUE | FALSE | FALSE
3577 | MRT-YK00-P3LB-122076 | 2018-07-13 | MRT-DS-REC-TT-180604 | FI | 0 | TRUE | FALSE | FALSE
3578 | MRT-VN02-P2LB-122090 | 2018-07-13 | MRT-DS-REC-TT-180605 | FC | 2 | TRUE | TRUE | FALSE
3579 | MRT-VN02-P3LB-122090 | 2018-07-13 | MRT-DS-REC-TT-180605 | FC | 2 | TRUE | TRUE | FALSE
3580 | MRT-CA00-P0UMA-180047 | 2018-07-13 | MRT-DS-REC-TT-180606 | FC | 2 | TRUE | TRUE | FALSE
3581 | MRT-YF00-P2LB-122066 | 2018-07-13 | MRT-DS-REC-TT-180607 | FC | 2 | TRUE | TRUE | FALSE
3582 | MRT-CV03-P2ZEN-165103 | 2018-07-16 | MRT-DS-REC-TT-180609 | FA | 1 | TRUE | TRUE | FALSE
3583 | MRT-CV03-P3ZEN-165103 | 2018-07-16 | MRT-DS-REC-TT-180609 | FA | 1 | TRUE | TRUE | FALSE
3584 | MRT-XJ00-P0GHC-140001 | 2018-07-16 | MRT-DS-REC-TT-180610 | FI | 0 | TRUE | FALSE | FALSE
3585 | MRT-XJ00-P2LB-122028 | 2018-07-16 | MRT-DS-REC-TT-180608 | FC | 1 | TRUE | TRUE | FALSE
3586 | MRT-XJ00-P3LB-122028 | 2018-07-16 | MRT-DS-REC-TT-180608 | FC | 1 | TRUE | TRUE | FALSE
3587 | MRT-YS01-P2QU-130034 | 2018-07-16 | MRT-DS-REC-TT-180611 | FI | 2 | TRUE | TRUE | FALSE
3588 | MRT-YS01-P3QU-130034 | 2018-07-16 | MRT-DS-REC-TT-180611 | FI | 2 | TRUE | TRUE | FALSE
3589 | MRT-YV02-P2QU-130032 | 2018-07-16 | MRT-DS-REC-TT-180612 | FC | 2 | TRUE | TRUE | FALSE
3590 | MRT-YV02-P3QU-130032 | 2018-07-16 | MRT-DS-REC-TT-180612 | FC | 2 | TRUE | TRUE | FALSE
3591 | MRT-DB00-P2PAC-130001 | 2018-07-16 | MRT-HK-REC-TT-180163 | FA | 0 | TRUE | FALSE | FALSE
3592 | MRT-DB00-P3PAC-130001 | 2018-07-16 | MRT-HK-REC-TT-180163 | FA | 0 | TRUE | FALSE | FALSE
3593 | MRT-XA00-P2PAC-130001 | 2018-07-16 | MRT-HK-REC-TT-180163 | FA | 0 | TRUE | FALSE | FALSE
3594 | MRT-XA00-P3PAC-130001 | 2018-07-16 | MRT-HK-REC-TT-180163 | FA | 0 | TRUE | FALSE | FALSE
3595 | MRT-YT01-P2PAC-130001 | 2018-07-16 | MRT-HK-REC-TT-180163 | FA | 0 | TRUE | FALSE | FALSE
3596 | MRT-YT01-P3PAC-130001 | 2018-07-16 | MRT-HK-REC-TT-180163 | FA | 0 | TRUE | FALSE | FALSE
3597 | MRT-QM03-P0ZEN-155002 | 2018-07-16 | MRT-HK-REC-TT-180164 | FA | 0 | TRUE | FALSE | FALSE
3598 | MRT-QM03-P0ZEN-155003 | 2018-07-16 | MRT-HK-REC-TT-180164 | FA | 0 | TRUE | FALSE | FALSE
3599 | MRT-QM03-P0ZEN-155004 | 2018-07-16 | MRT-HK-REC-TT-180164 | FA | 0 | TRUE | FALSE | FALSE
3600 | MRT-QM03-P0ZEN-045006 | 2018-07-16 | MRT-HK-REC-TT-180164 | FA | 0 | TRUE | FALSE | FALSE
3601 | MRT-XA00-P3MAA-220016 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3602 | MRT-XA00-P2MAA-220014 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3603 | MRT-XA00-P2MAA-220015 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3604 | MRT-XA00-P2MAA-220016 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3605 | MRT-XA00-P2MAA-220017 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3606 | MRT-XA00-P2MAA-220018 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3607 | MRT-XA00-P3MAA-220014 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3608 | MRT-XA00-P3MAA-220015 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3609 | MRT-XA00-P3MAA-220017 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3610 | MRT-XA00-P3MAA-220018 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3611 | MRT-XA00-P3MAA-220019 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3612 | MRT-XA00-P2MAA-220020 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3613 | MRT-XA00-P3MAA-220020 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3614 | MRT-XA00-P2MAA-220021 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3615 | MRT-XA00-P3MAA-220021 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3616 | MRT-XA00-P2MAA-220022 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3617 | MRT-XA00-P3MAA-220022 | 2018-07-16 | MRT-DS-REC-TT-180613 | FC | 3 | TRUE | TRUE | FALSE
3618 | MRT-YV02-P2QC-130017 | 2018-07-16 | MRT-DS-REC-TT-180615 | FC | 2 | TRUE | TRUE | FALSE
3619 | MRT-YV02-P3QC-130017 | 2018-07-16 | MRT-DS-REC-TT-180615 | FC | 2 | TRUE | TRUE | FALSE
3620 | MRT-DS00-P2PAC-130001 | 2018-07-16 | MRT-HK-REC-TT-180165 | FA | 0 | TRUE | FALSE | FALSE
3621 | MRT-YT01-P2LCB-127033 | 2018-07-17 | MRT-DS-REC-TT-180617 | FC | 2 | TRUE | TRUE | FALSE
3622 | MRT-YT01-P3LCB-127033 | 2018-07-17 | MRT-DS-REC-TT-180617 | FC | 2 | TRUE | TRUE | FALSE
3623 | MRT-YD07-P2ZEN-163109 | 2018-07-17 | MRT-DS-REC-TT-180614 | FC | 1 | TRUE | TRUE | FALSE
3624 | MRT-YR05-P2ZEN-163110 | 2018-07-17 | MRT-DS-REC-TT-180614 | FC | 1 | TRUE | TRUE | FALSE
3625 | MRT-YR05-P2ZEN-163111 | 2018-07-17 | MRT-DS-REC-TT-180614 | FC | 1 | TRUE | TRUE | FALSE
3626 | MRT-YR05-P2ZEN-163112 | 2018-07-17 | MRT-DS-REC-TT-180614 | FC | 1 | TRUE | TRUE | FALSE
3627 | MRT-YR05-P2ZEN-163113 | 2018-07-17 | MRT-DS-REC-TT-180614 | FC | 1 | TRUE | TRUE | FALSE
3628 | MRT-YR05-P2ZEN-163114 | 2018-07-17 | MRT-DS-REC-TT-180614 | FC | 1 | TRUE | TRUE | FALSE
3629 | MRT-YD07-P3ZEN-163109 | 2018-07-17 | MRT-DS-REC-TT-180614 | FC | 1 | TRUE | TRUE | FALSE
3630 | MRT-YR05-P3ZEN-163110 | 2018-07-17 | MRT-DS-REC-TT-180614 | FC | 1 | TRUE | TRUE | FALSE
3631 | MRT-YR05-P3ZEN-163111 | 2018-07-17 | MRT-DS-REC-TT-180614 | FC | 1 | TRUE | TRUE | FALSE
3632 | MRT-YR05-P3ZEN-163112 | 2018-07-17 | MRT-DS-REC-TT-180614 | FC | 1 | TRUE | TRUE | FALSE
3633 | MRT-YR05-P3ZEN-163113 | 2018-07-17 | MRT-DS-REC-TT-180614 | FC | 1 | TRUE | TRUE | FALSE
3634 | MRT-YR05-P3ZEN-163114 | 2018-07-17 | MRT-DS-REC-TT-180614 | FC | 1 | TRUE | TRUE | FALSE
3635 | MRT-CC07-P2UAG-170301 | 2018-07-17 | MRT-DS-REC-TT-180616 | FA | 0 | TRUE | FALSE | FALSE
3636 | MRT-CC02-P2UAG-170303 | 2018-07-17 | MRT-DS-REC-TT-180616 | FA | 0 | TRUE | FALSE | FALSE
3637 | MRT-CC02-P2UAG-170307 | 2018-07-17 | MRT-DS-REC-TT-180616 | FA | 0 | TRUE | FALSE | FALSE
3638 | MRT-CC02-P2UAG-170308 | 2018-07-17 | MRT-DS-REC-TT-180616 | FA | 0 | TRUE | FALSE | FALSE
3639 | MRT-CC07-P3UAG-170301 | 2018-07-17 | MRT-DS-REC-TT-180616 | FA | 0 | TRUE | FALSE | FALSE
3640 | MRT-CC02-P3UAG-170303 | 2018-07-17 | MRT-DS-REC-TT-180616 | FA | 0 | TRUE | FALSE | FALSE
3641 | MRT-CC02-P3UAG-170307 | 2018-07-17 | MRT-DS-REC-TT-180616 | FA | 0 | TRUE | FALSE | FALSE
3642 | MRT-CC02-P3UAG-170308 | 2018-07-17 | MRT-DS-REC-TT-180616 | FA | 0 | TRUE | FALSE | FALSE
3643 | MRT-YK00-P2SCA-127521 | 2018-07-17 | MRT-DS-REC-TT-180602 | FI | 1 | TRUE | TRUE | FALSE
3644 | MRT-YK00-P3SCA-127521 | 2018-07-17 | MRT-DS-REC-TT-180602 | FI | 1 | TRUE | TRUE | FALSE
3645 | MRT-YD00-P2ZEN-113300 | 2018-07-17 | MRT-DS-REC-TT-180618 | FC | 2 | TRUE | TRUE | FALSE
3646 | MRT-YD00-P3ZEN-113300 | 2018-07-17 | MRT-DS-REC-TT-180618 | FC | 2 | TRUE | TRUE | FALSE
3647 | MRT-YT01-P2ZEN-113301 | 2018-07-17 | MRT-DS-REC-TT-180619 | FA | 2 | TRUE | TRUE | FALSE
3648 | MRT-YT01-P3ZEN-113301 | 2018-07-17 | MRT-DS-REC-TT-180619 | FA | 2 | TRUE | TRUE | FALSE
3649 | MRT-YV02-P2MAJ-603108 | 2018-07-17 | MRT-DS-REC-TT-180620 | FC | 4 | TRUE | TRUE | FALSE
3650 | MRT-YV02-P3MAJ-604108 | 2018-07-17 | MRT-DS-REC-TT-180620 | FC | 4 | TRUE | TRUE | FALSE
3651 | MRT-XV00-P2MAA-220036 | 2018-07-17 | MRT-DS-REC-TT-180621 | FC | 3 | TRUE | TRUE | FALSE
3652 | MRT-XV00-P2MAV-220037 | 2018-07-17 | MRT-DS-REC-TT-180621 | FC | 3 | TRUE | TRUE | FALSE
3653 | MRT-XV00-P3MAA-220036 | 2018-07-17 | MRT-DS-REC-TT-180621 | FC | 3 | TRUE | TRUE | FALSE
3654 | MRT-XV00-P3MAV-220037 | 2018-07-17 | MRT-DS-REC-TT-180621 | FC | 3 | TRUE | TRUE | FALSE
3655 | MRT-YE04-P0UAA-150219 | 2018-07-18 | MRT-HK-REC-TT-180152 | FA | 0 | TRUE | FALSE | FALSE
3656 | MRT-YS01-P0UAA-150218 | 2018-07-18 | MRT-HK-REC-TT-180152 | FA | 0 | TRUE | FALSE | FALSE
3657 | MRT-YD00-P0UAA-150217 | 2018-07-18 | MRT-HK-REC-TT-180152 | FA | 0 | TRUE | FALSE | FALSE
3658 | MRT-XG01-P3LB-122021 | 2018-07-18 | MRT-DS-REC-TT-180622 | FI | 0 | TRUE | FALSE | FALSE
3659 | MRT-YD02-P3LB-122064 | 2018-07-18 | MRT-DS-REC-TT-180623 | FI | 0 | TRUE | FALSE | FALSE
3660 | MRT-YD02-P3LB-122065 | 2018-07-18 | MRT-DS-REC-TT-180623 | FI | 0 | TRUE | FALSE | FALSE
3661 | MRT-YU02-P2BBA-150458 | 2018-07-18 | MRT-HK-REC-TT-180168 | FA | 0 | TRUE | FALSE | FALSE
3662 | MRT-YM02-P2BBA-150459 | 2018-07-18 | MRT-HK-REC-TT-180168 | FA | 0 | TRUE | FALSE | FALSE
3663 | MRT-YV02-P3ZEN-163116 | 2018-07-18 | MRT-DS-REC-TT-180625 | FI | 0 | TRUE | FALSE | FALSE
3664 | MRT-YL15-P3ZEN-163117 | 2018-07-18 | MRT-DS-REC-TT-180625 | FI | 0 | TRUE | FALSE | FALSE
3665 | MRT-CA06-P0UST-186901 | 2018-07-18 | MRT-HK-REC-TT-180169 | FA | 2 | TRUE | TRUE | FALSE
3666 | MRT-CA01-P0UST-186902 | 2018-07-18 | MRT-HK-REC-TT-180169 | FA | 2 | TRUE | TRUE | FALSE
3670 | MRT-CA03-P0UCA-180132 | 2018-07-19 | MRT-DS-REC-TT-180629 | FC | 3 | TRUE | TRUE | FALSE
3671 | MRT-CA01-P0UCA-180133 | 2018-07-19 | MRT-DS-REC-TT-180629 | FC | 3 | TRUE | TRUE | FALSE
3672 | MRT-YL00-P2ZEN-165101 | 2018-07-19 | MRT-DS-REC-TT-180628 | FA | 2 | TRUE | TRUE | FALSE
3673 | MRT-YL00-P3ZEN-165101 | 2018-07-19 | MRT-DS-REC-TT-180628 | FA | 2 | TRUE | TRUE | FALSE
3674 | MRT-HM01-P00SA-135575 | 2018-07-19 | MRT-HK-REC-TT-180167 | FA | 0 | TRUE | FALSE | FALSE
3675 | MRT-HM01-P0SAL-135569 | 2018-07-19 | MRT-HK-REC-TT-180167 | FA | 0 | TRUE | FALSE | FALSE
3676 | MRT-HM01-P00SA-135574 | 2018-07-19 | MRT-HK-REC-TT-180167 | FA | 0 | TRUE | FALSE | FALSE
3677 | MRT-XA00-P0GAA-135004 | 2018-07-19 | MRT-HK-REC-TT-180167 | FA | 3 | TRUE | FALSE | FALSE
3678 | MRT-QM01-P0ZEN-040001 | 2018-07-19 | MRT-DS-REC-TT-180630 | FC | 4 | TRUE | TRUE | FALSE
3679 | MRT-UC07-P0ZEN-100001 | 2018-07-19 | MRT-DS-REC-TT-180626 | FA | 4 | TRUE | TRUE | FALSE
3680 | MRT-UC08-P0ZEN-100002 | 2018-07-19 | MRT-DS-REC-TT-180626 | FA | 3 | TRUE | TRUE | FALSE
3681 | MRT-UC08-P0ZEN-100003 | 2018-07-19 | MRT-DS-REC-TT-180627 | FC | 3 | TRUE | TRUE | FALSE
3958 | MRT-XA00-P0GAA-135004 | 2018-07-19 | MRT-HK-REC-TT-180167 | FA | 3 | TRUE | TRUE | FALSE
4963 | MRT-QM00-P0H-040003 | 2018-07-19 | MRT-DS-REC-TT-180419-FC | FC | 0 | TRUE | TRUE | FALSE
4964 | MRT-QM00-P0H-040004 | 2018-07-19 | MRT-DS-REC-TT-180419-FC | FC | 0 | TRUE | TRUE | FALSE
4965 | MRT-QM00-P0H-040005 | 2018-07-19 | MRT-DS-REC-TT-180419-FC | FC | 0 | TRUE | TRUE | FALSE
3682 | MRT-YD05-P2SCA-127515 | 2018-07-20 | MRT-DS-REC-TT-180631 | FA | 2 | TRUE | TRUE | FALSE
3683 | MRT-YD05-P3SCA-127515 | 2018-07-20 | MRT-DS-REC-TT-180631 | FA | 2 | TRUE | TRUE | FALSE
3684 | MRT-CQ02-P2SCA-127529 | 2018-07-20 | MRT-DS-REC-TT-180632 | FI | 0 | TRUE | FALSE | FALSE
3685 | MRT-CQ02-P3SCA-127529 | 2018-07-20 | MRT-DS-REC-TT-180632 | FI | 0 | TRUE | FALSE | FALSE
3686 | MRT-BAB-P3BAT-150395 | 2018-07-20 | MRT-HK-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
3687 | MRT-YD00-P3BAT-150396 | 2018-07-20 | MRT-HK-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
3688 | MRT-UBM-P3BAT-150406 | 2018-07-20 | MRT-HK-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
3689 | MRT-YT01-P3BAT-150397 | 2018-07-20 | MRT-HK-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
3690 | MRT-YT01-P3BAT-150398 | 2018-07-20 | MRT-HK-REC-TT-180171 | FA | 1 | TRUE | TRUE | FALSE
3691 | MRT-YT01-P3BAT-150394 | 2018-07-20 | MRT-HK-REC-TT-180171 | FA | 0 | TRUE | FALSE | FALSE
3692 | MRT-QM03-P0ZEN-185009 | 2018-07-20 | MRT-HK-REC-TT-180172 | FA | 0 | TRUE | FALSE | FALSE
3693 | MRT-XJ00-P2MKJ-220001 | 2018-07-20 | MRT-DS-REC-TT-180633 | FC | 2 | TRUE | TRUE | FALSE
3694 | MRT-XH01-P3MKA-220001 | 2018-07-20 | MRT-DS-REC-TT-180634 | FC | 1 | TRUE | TRUE | FALSE
3695 | MRT-XJ00-P3MKA-220001 | 2018-07-20 | MRT-DS-REC-TT-180635 | FC | 1 | TRUE | TRUE | FALSE
3696 | MRT-CC07-P2UMA-170201 | 2018-07-20 | MRT-DS-REC-TT-180636 | FC | 2 | TRUE | TRUE | FALSE
3697 | MRT-CC07-P2UMA-170205 | 2018-07-20 | MRT-DS-REC-TT-180636 | FC | 2 | TRUE | TRUE | FALSE
3698 | MRT-CC07-P2UMA-170211 | 2018-07-20 | MRT-DS-REC-TT-180636 | FC | 2 | TRUE | TRUE | FALSE
3699 | MRT-CC07-P3UMA-170201 | 2018-07-20 | MRT-DS-REC-TT-180636 | FC | 2 | TRUE | TRUE | FALSE
3700 | MRT-CC07-P3UMA-170205 | 2018-07-20 | MRT-DS-REC-TT-180636 | FC | 2 | TRUE | TRUE | FALSE
3701 | MRT-CC07-P3UMA-170211 | 2018-07-20 | MRT-DS-REC-TT-180636 | FC | 2 | TRUE | TRUE | FALSE
4078 | MRT-XA01-P0ABA-150507 | 2018-07-20 | MRT-HK-REC-TT-180155 | FA | 0 | TRUE | FALSE | FALSE
3702 | MRT-YT01-P2QU-130031 | 2018-07-23 | MRT-DS-REC-TT-180642 | FI | 2 | TRUE | TRUE | FALSE
3703 | MRT-YF00-P2QU-130033 | 2018-07-23 | MRT-DS-REC-TT-180642 | FI | 2 | TRUE | TRUE | FALSE
3704 | MRT-YT01-P3QU-130031 | 2018-07-23 | MRT-DS-REC-TT-180642 | FI | 2 | TRUE | TRUE | FALSE
3705 | MRT-YF00-P3QU-130033 | 2018-07-23 | MRT-DS-REC-TT-180642 | FI | 1 | TRUE | TRUE | FALSE
3706 | MRT-CQ02-P2LCB-127043 | 2018-07-23 | MRT-DS-REC-TT-180637 | FI | 0 | TRUE | FALSE | FALSE
3707 | MRT-CQ02-P3LCB-127043 | 2018-07-23 | MRT-DS-REC-TT-180637 | FI | 0 | TRUE | FALSE | FALSE
3708 | MRT-YU02-P2SCA-127510 | 2018-07-23 | MRT-DS-REC-TT-180639 | FC | 1 | TRUE | TRUE | FALSE
3709 | MRT-YU02-P3SCA-127510 | 2018-07-23 | MRT-DS-REC-TT-180639 | FC | 1 | TRUE | TRUE | FALSE
3710 | MRT-YS01-P2SCA-127511 | 2018-07-23 | MRT-DS-REC-TT-180640 | FC | 1 | TRUE | TRUE | FALSE
3711 | MRT-YS01-P3SCA-127511 | 2018-07-23 | MRT-DS-REC-TT-180640 | FC | 1 | TRUE | TRUE | FALSE
3712 | MRT-YF00-P2SCA-127518 | 2018-07-23 | MRT-DS-REC-TT-180641 | FC | 1 | TRUE | TRUE | FALSE
3713 | MRT-YF00-P3SCA-127518 | 2018-07-23 | MRT-DS-REC-TT-180641 | FC | 1 | TRUE | TRUE | FALSE
3714 | MRT-YD00-P2LCB-127501 | 2018-07-23 | MRT-DS-REC-TT-180638 | FC | 2 | TRUE | TRUE | FALSE
3715 | MRT-YD00-P3LCB-127501 | 2018-07-23 | MRT-DS-REC-TT-180638 | FC | 2 | TRUE | TRUE | FALSE
3716 | MRT-YT01-P2LB-122093 | 2018-07-23 | MRT-DS-REC-TT-180643 | FC | 1 | TRUE | TRUE | FALSE
3717 | MRT-XW01-P2LB-122043 | 2018-07-23 | MRT-DS-REC-TT-180643 | FC | 1 | TRUE | TRUE | FALSE
3718 | MRT-XW01-P3LB-122043 | 2018-07-23 | MRT-DS-REC-TT-180643 | FC | 1 | TRUE | TRUE | FALSE
3719 | MRT-YT01-P3LB-122093 | 2018-07-23 | MRT-DS-REC-TT-180645 | FC | 1 | TRUE | TRUE | FALSE
3720 | MRT-YM03-P2LB-122069 | 2018-07-23 | MRT-DS-REC-TT-180646 | FC | 2 | TRUE | TRUE | FALSE
3721 | MRT-YM03-P3LB-122069 | 2018-07-23 | MRT-DS-REC-TT-180646 | FC | 2 | TRUE | TRUE | FALSE
3722 | MRT-YK09-P2MKC-230006 | 2018-07-23 | MRT-DS-REC-TT-180644 | FC | 1 | TRUE | TRUE | FALSE
3723 | MRT-YK09-P3MKC-230006 | 2018-07-23 | MRT-DS-REC-TT-180644 | FC | 1 | TRUE | TRUE | FALSE
3724 | MRT-YD06-P3ZEN-163106 | 2018-07-23 | MRT-DS-REC-TT-180647 | FA | 2 | TRUE | TRUE | FALSE
3725 | MRT-QM03-P0ZEN-145007 | 2018-07-23 | MRT-HK-REC-TT-180173 | FA | 0 | TRUE | FALSE | FALSE
3726 | MRT-QM03-P0ZEN-145012 | 2018-07-23 | MRT-HK-REC-TT-180173 | FA | 0 | TRUE | FALSE | FALSE
3727 | MRT-YE16-P3UCB-150135 | 2018-07-23 | MRT-HK-REC-TT-180174 | FA | 0 | TRUE | FALSE | FALSE
3728 | MRT-YE00-P0UCB-150161 | 2018-07-23 | MRT-HK-REC-TT-180174 | FA | 0 | TRUE | FALSE | FALSE
3667 | MRT-QM00-P0H-040003 | 2018-07-24 | MRT-DS-REC-TT-180624 | FC | 1 | TRUE | TRUE | FALSE
3668 | MRT-QM00-P0H-040004 | 2018-07-24 | MRT-DS-REC-TT-180624 | FC | 1 | TRUE | TRUE | FALSE
3669 | MRT-QM00-P0H-040005 | 2018-07-24 | MRT-DS-REC-TT-180624 | FC | 1 | TRUE | TRUE | FALSE
3729 | MRT-CA00-P0UCA-180106 | 2018-07-24 | MRT-DS-REC-TT-180649 | FC | 3 | TRUE | TRUE | FALSE
3730 | MRT-CA00-P0UCA-180114 | 2018-07-24 | MRT-DS-REC-TT-180649 | FC | 3 | TRUE | TRUE | FALSE
3731 | MRT-CA00-P0UCA-180115 | 2018-07-24 | MRT-DS-REC-TT-180649 | FC | 3 | TRUE | TRUE | FALSE
3732 | MRT-CA00-P0UCA-180116 | 2018-07-24 | MRT-DS-REC-TT-180649 | FC | 3 | TRUE | TRUE | FALSE
3733 | MRT-CA00-P0UCA-180117 | 2018-07-24 | MRT-DS-REC-TT-180649 | FC | 3 | TRUE | TRUE | FALSE
3734 | MRT-CA01-P0UCA-180129 | 2018-07-24 | MRT-DS-REC-TT-180649 | FC | 2 | TRUE | TRUE | FALSE
3735 | MRT-CQ02-P2MAG-601011 | 2018-07-24 | MRT-DS-REC-TT-180651 | FI | 0 | TRUE | FALSE | FALSE
3736 | MRT-XB02-P0UMA-180004 | 2018-07-24 | MRT-DS-REC-TT-180648 | FC | 6 | TRUE | TRUE | FALSE
3737 | MRT-CA01-P0UMA-180005 | 2018-07-24 | MRT-DS-REC-TT-180648 | FC | 5 | TRUE | TRUE | FALSE
3738 | MRT-XJ00-P3LBA-144000 | 2018-07-24 | MRT-DS-REC-TT-180652 | FI | 0 | TRUE | FALSE | FALSE
3739 | MRT-CC07-P2UEJ-170901 | 2018-07-24 | MRT-DS-REC-TT-180650 | FC | 1 | TRUE | TRUE | FALSE
3740 | MRT-CC02-P2UEJ-170907 | 2018-07-24 | MRT-DS-REC-TT-180650 | FC | 1 | TRUE | TRUE | FALSE
3741 | MRT-VK02-P2UEJ-170910 | 2018-07-24 | MRT-DS-REC-TT-180650 | FC | 1 | TRUE | TRUE | FALSE
3742 | MRT-CC07-P3UEJ-170901 | 2018-07-24 | MRT-DS-REC-TT-180650 | FC | 1 | TRUE | TRUE | FALSE
3743 | MRT-CC02-P3UEJ-170907 | 2018-07-24 | MRT-DS-REC-TT-180650 | FC | 1 | TRUE | TRUE | FALSE
3744 | MRT-VK02-P3UEJ-170910 | 2018-07-24 | MRT-DS-REC-TT-180650 | FC | 1 | TRUE | TRUE | FALSE
3745 | MRT-CA00-P0UMA-180009 | 2018-07-24 | MRT-DS-REC-TT-180654 | FC | 3 | TRUE | TRUE | FALSE
3746 | MRT-CA00-P0UMA-180015 | 2018-07-24 | MRT-DS-REC-TT-180654 | FC | 3 | TRUE | TRUE | FALSE
3747 | MRT-CA00-P0UMA-180016 | 2018-07-24 | MRT-DS-REC-TT-180654 | FC | 3 | TRUE | TRUE | FALSE
3748 | MRT-CA00-P0UMA-180017 | 2018-07-24 | MRT-DS-REC-TT-180654 | FC | 3 | TRUE | TRUE | FALSE
3749 | MRT-CA00-P0UMA-180019 | 2018-07-24 | MRT-DS-REC-TT-180654 | FC | 3 | TRUE | TRUE | FALSE
3750 | MRT-CA00-P0UMA-180021 | 2018-07-24 | MRT-DS-REC-TT-180654 | FC | 3 | TRUE | TRUE | FALSE
3751 | MRT-CA00-P0UMA-180022 | 2018-07-24 | MRT-DS-REC-TT-180654 | FC | 3 | TRUE | TRUE | FALSE
3752 | MRT-YV02-P2PAH-604122 | 2018-07-24 | MRT-DS-REC-TT-180655 | FC | 2 | TRUE | TRUE | FALSE
3753 | MRT-YK08-P2PAH-604124 | 2018-07-24 | MRT-DS-REC-TT-180655 | FC | 3 | TRUE | TRUE | FALSE
3754 | MRT-YT01-P2GM-128502 | 2018-07-24 | MRT-DS-REC-TT-180653 | FA | 1 | TRUE | TRUE | FALSE
3755 | MRT-YT01-P3GM-128502 | 2018-07-24 | MRT-DS-REC-TT-180653 | FA | 1 | TRUE | TRUE | FALSE
3756 | MRT-XK00-P2GM-128505 | 2018-07-24 | MRT-DS-REC-TT-180656 | FC | 1 | TRUE | TRUE | FALSE
3757 | MRT-YD00-P2GM-128503 | 2018-07-24 | MRT-DS-REC-TT-180656 | FC | 1 | TRUE | TRUE | FALSE
3758 | MRT-XK00-P3GM-128505 | 2018-07-24 | MRT-DS-REC-TT-180656 | FC | 1 | TRUE | TRUE | FALSE
3759 | MRT-YD00-P3GM-128503 | 2018-07-24 | MRT-DS-REC-TT-180656 | FC | 1 | TRUE | TRUE | FALSE
3760 | MRT-XK00-P2LAC-126014 | 2018-07-24 | MRT-DS-REC-TT-180657 | FC | 1 | TRUE | TRUE | FALSE
3761 | MRT-XK00-P3LAC-126014 | 2018-07-24 | MRT-DS-REC-TT-180657 | FC | 1 | TRUE | TRUE | FALSE
3762 | MRT-CC02-P0UPC-175781 | 2018-07-24 | MRT-HK-REC-TT-180175 | FA | 2 | TRUE | TRUE | FALSE
3763 | MRT-CC02-P0UPC-175783 | 2018-07-24 | MRT-HK-REC-TT-180175 | FA | 1 | TRUE | TRUE | FALSE
3764 | MRT-CC02-P0UPC-175786 | 2018-07-24 | MRT-HK-REC-TT-180175 | FA | 1 | TRUE | TRUE | FALSE
3765 | MRT-CC02-P0UPC-175787 | 2018-07-24 | MRT-HK-REC-TT-180175 | FA | 1 | TRUE | TRUE | FALSE
3766 | MRT-CC02-P0UPC-175782 | 2018-07-24 | MRT-HK-REC-TT-180175 | FA | 0 | TRUE | TRUE | FALSE
3767 | MRT-CC03-P0UPC-175788 | 2018-07-24 | MRT-HK-REC-TT-180175 | FA | 0 | TRUE | TRUE | FALSE
3768 | MRT-CC03-P0UPC-175789 | 2018-07-24 | MRT-HK-REC-TT-180175 | FA | 0 | TRUE | TRUE | FALSE
3769 | MRT-YD00-P2BAT-150379 | 2018-07-24 | MRT-HK-REC-TT-180177 | FA | 0 | TRUE | FALSE | FALSE
3770 | MRT-YD00-P3BAT-150402 | 2018-07-24 | MRT-HK-REC-TT-180177 | FA | 0 | TRUE | FALSE | FALSE
3771 | MRT-YV02-P2BAT-150380 | 2018-07-24 | MRT-HK-REC-TT-180177 | FA | 0 | TRUE | FALSE | FALSE
3772 | MRT-YV02-P3BAT-150403 | 2018-07-24 | MRT-HK-REC-TT-180177 | FA | 0 | TRUE | FALSE | FALSE
3822 | MRT-XB00-P2SCA-127509 | 2018-07-24 | MRT-DS-REC-TT-180588-FC | FC | 2 | TRUE | TRUE | FALSE
3823 | MRT-XB00-P3SCA-127509 | 2018-07-24 | MRT-DS-REC-TT-180588-FC | FC | 2 | TRUE | TRUE | FALSE
3824 | MRT-YF02-P2QC-130006 | 2018-07-24 | MRT-DS-REC-TT-180562-FC | FC | 2 | TRUE | TRUE | FALSE
3825 | MRT-YF02-P3QC-130006 | 2018-07-24 | MRT-DS-REC-TT-180562-FC | FC | 2 | TRUE | TRUE | FALSE
3773 | MRT-DD02-P0ZEN-175013 | 2018-07-25 | MRT-HK-REC-TT-180175 | FI | 0 | TRUE | FALSE | FALSE
3774 | MRT-XJ00-P3LAB-144000 | 2018-07-25 | MRT-DS-REC-TT-180659 | FI | 0 | TRUE | FALSE | FALSE
3775 | MRT-YK08-P2MAJ-603200 | 2018-07-25 | MRT-DS-REC-TT-180658 | FC | 3 | TRUE | TRUE | FALSE
3776 | MRT-XG02-P2MAJ-603201 | 2018-07-25 | MRT-DS-REC-TT-180658 | FC | 4 | TRUE | TRUE | FALSE
3777 | MRT-YK08-P3MAJ-604200 | 2018-07-25 | MRT-DS-REC-TT-180658 | FC | 3 | TRUE | TRUE | FALSE
3778 | MRT-XG02-P3MAJ-604201 | 2018-07-25 | MRT-DS-REC-TT-180658 | FC | 4 | TRUE | TRUE | FALSE
3779 | MRT-CC07-P2UAG-170301 | 2018-07-25 | MRT-DS-REC-TT-180660 | FA | 1 | TRUE | TRUE | FALSE
3780 | MRT-CC02-P2UAG-170303 | 2018-07-25 | MRT-DS-REC-TT-180660 | FA | 1 | TRUE | TRUE | FALSE
3781 | MRT-VK02-P2UAG-170310 | 2018-07-25 | MRT-DS-REC-TT-180660 | FA | 0 | TRUE | FALSE | FALSE
3782 | MRT-CC07-P3UAG-170301 | 2018-07-25 | MRT-DS-REC-TT-180660 | FA | 1 | TRUE | TRUE | FALSE
3783 | MRT-CC02-P3UAG-170303 | 2018-07-25 | MRT-DS-REC-TT-180660 | FA | 1 | TRUE | TRUE | FALSE
3784 | MRT-VK02-P3UAG-170310 | 2018-07-25 | MRT-DS-REC-TT-180660 | FA | 0 | TRUE | FALSE | FALSE
3785 | MRT-XK00-P3MKA-220001 | 2018-07-25 | MRT-DS-REC-TT-180663 | FC | 1 | TRUE | TRUE | FALSE
3786 | MRT-YT02-P2LAC-126011 | 2018-07-25 | MRT-DS-REC-TT-180661 | FI | 2 | TRUE | TRUE | FALSE
3787 | MRT-YT02-P3LAC-126011 | 2018-07-25 | MRT-DS-REC-TT-180661 | FI | 2 | TRUE | TRUE | FALSE
3788 | MRT-YT02-P2LAC-126061 | 2018-07-25 | MRT-DS-REC-TT-180661 | FI | 2 | TRUE | TRUE | FALSE
3789 | MRT-YT02-P3LAC-126061 | 2018-07-25 | MRT-DS-REC-TT-180661 | FI | 2 | TRUE | TRUE | FALSE
3790 | MRT-CA03-P0UMA-180025 | 2018-07-26 | MRT-DS-REC-TT-180662 | FC | 4 | TRUE | TRUE | FALSE
3791 | MRT-CA03-P0UMA-180026 | 2018-07-26 | MRT-DS-REC-TT-180662 | FC | 4 | TRUE | TRUE | FALSE
3792 | MRT-CA01-P0UMA-180027 | 2018-07-26 | MRT-DS-REC-TT-180662 | FC | 4 | TRUE | TRUE | FALSE
3793 | MRT-CA03-P0UMA-180028 | 2018-07-26 | MRT-DS-REC-TT-180662 | FC | 4 | TRUE | TRUE | FALSE
3794 | MRT-CA03-P0UMA-180029 | 2018-07-26 | MRT-DS-REC-TT-180662 | FC | 4 | TRUE | TRUE | FALSE
3795 | MRT-CA03-P0UMA-180031 | 2018-07-26 | MRT-DS-REC-TT-180662 | FC | 4 | TRUE | TRUE | FALSE
3796 | MRT-CA03-P0UMA-180032 | 2018-07-26 | MRT-DS-REC-TT-180662 | FC | 4 | TRUE | TRUE | FALSE
3797 | MRT-CA03-P0UMA-180033 | 2018-07-26 | MRT-DS-REC-TT-180662 | FC | 4 | TRUE | TRUE | FALSE
3798 | MRT-CA03-P0UMA-180034 | 2018-07-26 | MRT-DS-REC-TT-180662 | FC | 4 | TRUE | TRUE | FALSE
3799 | MRT-CA03-P0UMA-180040 | 2018-07-26 | MRT-DS-REC-TT-180662 | FC | 3 | TRUE | TRUE | FALSE
3800 | MRT-CA03-P0UMA-180042 | 2018-07-26 | MRT-DS-REC-TT-180662 | FC | 4 | TRUE | TRUE | FALSE
3801 | MRT-CA03-P0UMA-180030 | 2018-07-26 | MRT-DS-REC-TT-180662 | FC | 4 | TRUE | TRUE | FALSE
3802 | MRT-XH01-P2UMA-142000 | 2018-07-26 | MRT-DS-REC-TT-180664 | FC | 1 | TRUE | TRUE | FALSE
3803 | MRT-YD02-P2LB-122064 | 2018-07-26 | MRT-DS-REC-TT-180665 | FC | 1 | TRUE | TRUE | FALSE
3804 | MRT-YD02-P2LB-122065 | 2018-07-26 | MRT-DS-REC-TT-180665 | FC | 1 | TRUE | TRUE | FALSE
3805 | MRT-XH01-P3UMA-143000 | 2018-07-26 | MRT-DS-REC-TT-180667 | FA | 0 | TRUE | FALSE | FALSE
3806 | MRT-YL22-P2LCB-127042 | 2018-07-26 | MRT-DS-REC-TT-180668 | FI | 0 | TRUE | FALSE | FALSE
3807 | MRT-YT01-P2LCB-127037 | 2018-07-26 | MRT-DS-REC-TT-180668 | FA | 0 | TRUE | FALSE | FALSE
3808 | MRT-YL22-P3LCB-127042 | 2018-07-26 | MRT-DS-REC-TT-180668 | FI | 0 | TRUE | FALSE | FALSE
3809 | MRT-YT01-P3LCB-127037 | 2018-07-26 | MRT-DS-REC-TT-180668 | FA | 0 | TRUE | FALSE | FALSE
3810 | MRT-XW01-P2GM-128507 | 2018-07-26 | MRT-DS-REC-TT-180669 | FA | 1 | TRUE | TRUE | FALSE
3811 | MRT-XW01-P3GM-128507 | 2018-07-26 | MRT-DS-REC-TT-180669 | FA | 1 | TRUE | TRUE | FALSE
3812 | MRT-XA00-P3PBB-135231 | 2018-07-26 | MRT-HK-REC-TT-180178 | FA | 0 | TRUE | FALSE | FALSE
3813 | MRT-XA00-P2PBB-135230 | 2018-07-26 | MRT-HK-REC-TT-180178 | FA | 0 | TRUE | FALSE | FALSE
3814 | MRT-XM00-P3PBB-135222 | 2018-07-26 | MRT-HK-REC-TT-180178 | FA | 0 | TRUE | FALSE | FALSE
3815 | MRT-XM00-P2PBB-135219 | 2018-07-26 | MRT-HK-REC-TT-180178 | FA | 0 | TRUE | FALSE | FALSE
3816 | MRT-XA00-P3PBB-135221 | 2018-07-26 | MRT-HK-REC-TT-180178 | FA | 0 | TRUE | FALSE | FALSE
3817 | MRT-XA00-P2PBB-135218 | 2018-07-26 | MRT-HK-REC-TT-180178 | FA | 0 | TRUE | FALSE | FALSE
3818 | MRT-XA00-P3PBB-135220 | 2018-07-26 | MRT-HK-REC-TT-180178 | FA | 0 | TRUE | FALSE | FALSE
3819 | MRT-XA00-P2PBB-135217 | 2018-07-26 | MRT-HK-REC-TT-180178 | FA | 0 | TRUE | FALSE | FALSE
3820 | MRT-XM00-P0PBB-135229 | 2018-07-26 | MRT-HK-REC-TT-180178 | FA | 0 | TRUE | FALSE | FALSE
3821 | MRT-XA00-P0PBB-135228 | 2018-07-26 | MRT-HK-REC-TT-180178 | FA | 0 | TRUE | FALSE | FALSE
3826 | MRT-QM01-P0ZEN-040001 | 2018-07-27 | MRT-DS-REC-TT-180630-FC | FC | 4 | TRUE | TRUE | FALSE
3827 | MRT-CC02-P2UMA-170207 | 2018-07-27 | MRT-DS-REC-TT-180549-FC | FC | 3 | TRUE | TRUE | FALSE
3828 | MRT-CC02-P2UMA-170208 | 2018-07-27 | MRT-DS-REC-TT-180549-FC | FC | 3 | TRUE | TRUE | FALSE
3829 | MRT-VK02-P2UMA-170210 | 2018-07-27 | MRT-DS-REC-TT-180549-FC | FC | 2 | TRUE | TRUE | FALSE
3830 | MRT-CC02-P3UMA-170207 | 2018-07-27 | MRT-DS-REC-TT-180549-FC | FC | 3 | TRUE | TRUE | FALSE
3831 | MRT-CC02-P3UMA-170208 | 2018-07-27 | MRT-DS-REC-TT-180549-FC | FC | 3 | TRUE | TRUE | FALSE
3832 | MRT-VK02-P3UMA-170210 | 2018-07-27 | MRT-DS-REC-TT-180549-FC | FC | 2 | TRUE | TRUE | FALSE
3833 | MRT-CA00-P0UMA-180023 | 2018-07-27 | MRT-DS-REC-TT-180585-FC | FC | 1 | TRUE | TRUE | FALSE
3834 | MRT-CA00-P0UMA-180024 | 2018-07-27 | MRT-DS-REC-TT-180585-FC | FC | 1 | TRUE | TRUE | FALSE
3835 | MRT-XJ00-P3LCA-143000 | 2018-07-27 | MRT-DS-REC-TT-180666 | FI | 0 | TRUE | FALSE | FALSE
3836 | MRT-XJ00-P3LCM-143000 | 2018-07-27 | MRT-DS-REC-TT-180666 | FI | 0 | TRUE | FALSE | FALSE
3843 | MRT-CA05-P0UCA-180161 | 2018-07-27 | MRT-DS-REC-TT-180670 | FC | 4 | TRUE | TRUE | FALSE
3844 | MRT-CA05-P0UCA-180162 | 2018-07-27 | MRT-DS-REC-TT-180670 | FC | 4 | TRUE | TRUE | FALSE
3845 | MRT-CA05-P0UCA-180163 | 2018-07-27 | MRT-DS-REC-TT-180670 | FC | 4 | TRUE | TRUE | FALSE
3846 | MRT-CA05-P0UCA-180164 | 2018-07-27 | MRT-DS-REC-TT-180670 | FC | 4 | TRUE | TRUE | FALSE
3847 | MRT-YD00-P2LCB-127031 | 2018-07-27 | MRT-DS-REC-TT-180675 | FA | 1 | TRUE | TRUE | FALSE
3848 | MRT-YM01-P2LCB-127039 | 2018-07-27 | MRT-DS-REC-TT-180675 | FA | 0 | TRUE | FALSE | FALSE
3849 | MRT-YD00-P3LCB-127031 | 2018-07-27 | MRT-DS-REC-TT-180675 | FA | 1 | TRUE | TRUE | FALSE
3850 | MRT-YM01-P3LCB-127039 | 2018-07-27 | MRT-DS-REC-TT-180675 | FA | 0 | TRUE | FALSE | FALSE
3851 | MRT-XG01-P2MAA-220045 | 2018-07-27 | MRT-DS-REC-TT-180673 | FI | 0 | TRUE | FALSE | FALSE
3852 | MRT-XG01-P3MAA-220045 | 2018-07-27 | MRT-DS-REC-TT-180673 | FI | 0 | TRUE | FALSE | FALSE
3853 | MRT-YE00-P2QC-130021 | 2018-07-27 | MRT-DS-REC-TT-180679 | FC | 2 | TRUE | TRUE | FALSE
3854 | MRT-YE00-P3QC-130021 | 2018-07-27 | MRT-DS-REC-TT-180679 | FC | 2 | TRUE | TRUE | FALSE
3855 | MRT-YD00-P2QC-130005 | 2018-07-27 | MRT-DS-REC-TT-180677 | FC | 2 | TRUE | TRUE | FALSE
3856 | MRT-YD00-P3QC-130005 | 2018-07-27 | MRT-DS-REC-TT-180677 | FC | 2 | TRUE | TRUE | FALSE
3857 | MRT-YL00-P2GM-128512 | 2018-07-27 | MRT-DS-REC-TT-180678 | FI | 0 | TRUE | FALSE | FALSE
3858 | MRT-YL00-P3GM-128512 | 2018-07-27 | MRT-DS-REC-TT-180678 | FI | 0 | TRUE | FALSE | FALSE
3859 | MRT-YD00-P2LAC-126017 | 2018-07-27 | MRT-DS-REC-TT-180676 | FC | 1 | TRUE | TRUE | FALSE
3860 | MRT-YD00-P2LAC-126065 | 2018-07-27 | MRT-DS-REC-TT-180676 | FC | 1 | TRUE | TRUE | FALSE
3861 | MRT-YD00-P3LAC-126065 | 2018-07-27 | MRT-DS-REC-TT-180676 | FC | 1 | TRUE | TRUE | FALSE
3862 | MRT-YD00-P3LAC-126017 | 2018-07-27 | MRT-DS-REC-TT-180676 | FC | 1 | TRUE | TRUE | FALSE
3863 | MRT-XJ00-P3PGB-143000 | 2018-07-27 | MRT-DS-REC-TT-180683 | FI | 0 | TRUE | FALSE | FALSE
3864 | MRT-YF00-P2ZEN-161601 | 2018-07-27 | MRT-DS-REC-TT-180672 | FC | 1 | TRUE | TRUE | FALSE
3865 | MRT-YF00-P3ZEN-161601 | 2018-07-27 | MRT-DS-REC-TT-180672 | FC | 1 | TRUE | TRUE | FALSE
3866 | MRT-YS01-P3MKC-230017 | 2018-07-27 | MRT-DS-REC-TT-180682 | FC | 1 | TRUE | TRUE | FALSE
3867 | MRT-YK09-P2MKC-230002 | 2018-07-27 | MRT-DS-REC-TT-180680 | FC | 1 | TRUE | TRUE | FALSE
3868 | MRT-YK09-P3MKC-230002 | 2018-07-27 | MRT-DS-REC-TT-180680 | FC | 1 | TRUE | TRUE | FALSE
3869 | MRT-YL16-P2LB-122078 | 2018-07-27 | MRT-DS-REC-TT-180671 | FA | 1 | TRUE | TRUE | FALSE
3870 | MRT-YL16-P3LB-122078 | 2018-07-27 | MRT-DS-REC-TT-180671 | FA | 1 | TRUE | TRUE | FALSE
3871 | MRT-YS01-P2MKC-230015 | 2018-07-27 | MRT-DS-REC-TT-180681 | FC | 1 | TRUE | TRUE | FALSE
3872 | MRT-YS01-P3MKC-230015 | 2018-07-27 | MRT-DS-REC-TT-180681 | FC | 1 | TRUE | TRUE | FALSE
3873 | MRT-YT01-P2LCB-127036 | 2018-07-27 | MRT-DS-REC-TT-180684 | FA | 0 | TRUE | FALSE | FALSE
3874 | MRT-YL00-P2LCB-127040 | 2018-07-27 | MRT-DS-REC-TT-180684 | FI | 0 | TRUE | FALSE | FALSE
3875 | MRT-YT01-P3LCB-127036 | 2018-07-27 | MRT-DS-REC-TT-180684 | FA | 0 | TRUE | FALSE | FALSE
3876 | MRT-YL00-P3LCB-127040 | 2018-07-27 | MRT-DS-REC-TT-180684 | FI | 0 | TRUE | FALSE | FALSE
3877 | MRT-XG02-P2LCB-127032 | 2018-07-27 | MRT-DS-REC-TT-180685 | FC | 2 | TRUE | TRUE | FALSE
3878 | MRT-XG02-P3LCB-127032 | 2018-07-27 | MRT-DS-REC-TT-180685 | FC | 2 | TRUE | TRUE | FALSE
4190 | MRT-YT01-P2PGB-113200 | 2018-07-27 | MRT-DS-REC-TT-180212-FC | FC | 2 | TRUE | TRUE | FALSE
4191 | MRT-YT01-P3PGB-113200 | 2018-07-27 | MRT-DS-REC-TT-180212-FC | FC | 2 | TRUE | TRUE | FALSE
4192 | MRT-YD00-P2MKA-220002 | 2018-07-27 | MRT-DS-REC-TT-180068-FC | FC | 0 | TRUE | TRUE | FALSE
4193 | MRT-YD00-P3MKA-220002 | 2018-07-27 | MRT-DS-REC-TT-180068-FC | FC | 0 | TRUE | TRUE | FALSE
4194 | MRT-YF02-P2SCA-127514 | 2018-07-27 | MRT-DS-REC-TT-180209-FC | FC | 1 | TRUE | TRUE | FALSE
4195 | MRT-YF02-P3SCA-127514 | 2018-07-27 | MRT-DS-REC-TT-180209-FC | FC | 1 | TRUE | TRUE | FALSE
4196 | MRT-YK08-P2MKJ-220001 | 2018-07-27 | MRT-DS-REC-TT-180210-FC | FC | 0 | TRUE | FALSE | FALSE
4197 | MRT-YK08-P3MKA-220001 | 2018-07-27 | MRT-DS-REC-TT-180210-FC | FC | 0 | TRUE | FALSE | FALSE
4198 | MRT-XB00-P2MKA-220001 | 2018-07-27 | MRT-DS-REC-TT-180111-FC | FC | 3 | TRUE | TRUE | FALSE
4199 | MRT-XB00-P3MKA-220001 | 2018-07-27 | MRT-DS-REC-TT-180111-FC | FC | 3 | TRUE | TRUE | FALSE
4200 | MRT-YB03-P3LB-122048 | 2018-07-27 | MRT-DS-REC-TT-180176-FC | FC | 1 | TRUE | TRUE | FALSE
4201 | MRT-XW03-P3GHD-120001 | 2018-07-27 | MRT-DS-REC-TT-180149-FC | FC | 2 | TRUE | TRUE | FALSE
4202 | MRT-UE00-P2LB-122007 | 2018-07-27 | MRT-DS-REC-TT-180197-FC | FC | 2 | TRUE | TRUE | FALSE
4203 | MRT-UE00-P3LB-122007 | 2018-07-27 | MRT-DS-REC-TT-180197-FC | FC | 1 | TRUE | TRUE | FALSE
4204 | MRT-VL00-P2MAG-601005 | 2018-07-27 | MRT-DS-REC-TT-180168-FC | FC | 2 | TRUE | TRUE | FALSE
4205 | MRT-VL00-P2MAG-601006 | 2018-07-27 | MRT-DS-REC-TT-180168-FC | FC | 2 | TRUE | TRUE | FALSE
4206 | MRT-VL00-P3MAG-602005 | 2018-07-27 | MRT-DS-REC-TT-180168-FC | FC | 2 | TRUE | TRUE | FALSE
4207 | MRT-VL00-P3MAG-602006 | 2018-07-27 | MRT-DS-REC-TT-180168-FC | FC | 2 | TRUE | TRUE | FALSE
4208 | MRT-CC02-P2UHA-170007 | 2018-07-27 | MRT-DS-REC-TT-180203-FC | FC | 2 | TRUE | TRUE | FALSE
4209 | MRT-CC02-P2UHA-170008 | 2018-07-27 | MRT-DS-REC-TT-180203-FC | FC | 2 | TRUE | TRUE | FALSE
4210 | MRT-CC02-P2UHA-170009 | 2018-07-27 | MRT-DS-REC-TT-180203-FC | FC | 2 | TRUE | TRUE | FALSE
4211 | MRT-VK02-P2UHA-170010 | 2018-07-27 | MRT-DS-REC-TT-180203-FC | FC | 2 | TRUE | TRUE | FALSE
4212 | MRT-CC02-P3UHA-170007 | 2018-07-27 | MRT-DS-REC-TT-180203-FC | FC | 2 | TRUE | TRUE | FALSE
4213 | MRT-CC02-P3UHA-170008 | 2018-07-27 | MRT-DS-REC-TT-180203-FC | FC | 2 | TRUE | TRUE | FALSE
4214 | MRT-CC02-P3UHA-170009 | 2018-07-27 | MRT-DS-REC-TT-180203-FC | FC | 2 | TRUE | TRUE | FALSE
4215 | MRT-VK02-P3UHA-170010 | 2018-07-27 | MRT-DS-REC-TT-180203-FC | FC | 2 | TRUE | TRUE | FALSE
4216 | MRT-MA02-P2ZEN-161015 | 2018-07-27 | MRT-DS-REC-TT-180200-FC | FC | 2 | TRUE | TRUE | FALSE
4217 | MRT-MA02-P3ZEN-161015 | 2018-07-27 | MRT-DS-REC-TT-180200-FC | FC | 2 | TRUE | TRUE | FALSE
4218 | MRT-MA01-P2ZEN-161011 | 2018-07-27 | MRT-DS-REC-TT-180200-FC | FC | 3 | TRUE | TRUE | FALSE
4219 | MRT-MA01-P3ZEN-161011 | 2018-07-27 | MRT-DS-REC-TT-180200-FC | FC | 3 | TRUE | TRUE | FALSE
4220 | MRT-UE00-P2LB-122010 | 2018-07-27 | MRT-DS-REC-TT-180195-FC | FC | 2 | TRUE | TRUE | FALSE
4221 | MRT-UE00-P3LB-122010 | 2018-07-27 | MRT-DS-REC-TT-180195-FC | FC | 2 | TRUE | TRUE | FALSE
4222 | MRT-UE00-P2LB-122008 | 2018-07-27 | MRT-DS-REC-TT-180177-FC | FC | 2 | TRUE | TRUE | FALSE
4223 | MRT-UE00-P3LB-122008 | 2018-07-27 | MRT-DS-REC-TT-180177-FC | FC | 1 | TRUE | TRUE | FALSE
4224 | MRT-XB02-P2LB-122018 | 2018-07-27 | MRT-DS-REC-TT-180196-FC | FC | 3 | TRUE | TRUE | FALSE
4225 | MRT-XB02-P3LB-122018 | 2018-07-27 | MRT-DS-REC-TT-180196-FC | FC | 2 | TRUE | TRUE | FALSE
4226 | MRT-XG07-P2LBA-110300 | 2018-07-27 | MRT-DS-REC-TT-180049-FC | FC | 2 | TRUE | TRUE | FALSE
4227 | MRT-XG07-P2PA-110304 | 2018-07-27 | MRT-DS-REC-TT-180049-FC | FC | 2 | TRUE | TRUE | FALSE
4228 | MRT-XG07-P3LBA-110300 | 2018-07-27 | MRT-DS-REC-TT-180049-FC | FC | 2 | TRUE | TRUE | FALSE
4229 | MRT-XG07-P2PA-110002 | 2018-07-27 | MRT-DS-REC-TT-180049-FC | FC | 2 | TRUE | TRUE | FALSE
4230 | MRT-XG07-P3PA-110002 | 2018-07-27 | MRT-DS-REC-TT-180049-FC | FC | 2 | TRUE | TRUE | FALSE
4231 | MRT-QM00-P0H-040001 | 2018-07-27 | MRT-DS-REC-TT-180154-FC | FC | 2 | TRUE | TRUE | FALSE
4232 | MRT-QM00-P0H-040002 | 2018-07-27 | MRT-DS-REC-TT-180154-FC | FC | 2 | TRUE | TRUE | FALSE
4233 | MRT-YS00-P0ZEN-162101 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4234 | MRT-YS00-P0ZEN-162102 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4235 | MRT-YS00-P0ZEN-162103 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4236 | MRT-YS00-P0ZEN-162104 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4237 | MRT-YS00-P0ZEN-162105 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4238 | MRT-YS00-P0ZEN-162106 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4239 | MRT-YS00-P0ZEN-162107 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4240 | MRT-YS00-P0ZEN-162108 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4241 | MRT-YS00-P0ZEN-162109 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4242 | MRT-YS00-P0ZEN-162110 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4243 | MRT-YS00-P0ZEN-162111 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4244 | MRT-YS00-P0ZEN-162112 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4245 | MRT-YS00-P0ZEN-162113 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4246 | MRT-YS00-P0ZEN-162114 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4247 | MRT-YS00-P0ZEN-162115 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4248 | MRT-YS00-P0ZEN-162116 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4249 | MRT-YS00-P0ZEN-162117 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4250 | MRT-YS00-P0ZEN-162118 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4251 | MRT-YS00-P0ZEN-162119 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4252 | MRT-YS00-P0ZEN-162120 | 2018-07-27 | MRT-DS-REC-TT-180205-FC | FC | 3 | TRUE | TRUE | FALSE
4253 | MRT-YK10-P2MKA-220001 | 2018-07-27 | MRT-DS-REC-TT-180211-FC | FC | 0 | TRUE | TRUE | FALSE
4254 | MRT-YK10-P2MKA-220002 | 2018-07-27 | MRT-DS-REC-TT-180211-FC | FC | 0 | TRUE | TRUE | FALSE
4255 | MRT-YK10-P3MKA-220001 | 2018-07-27 | MRT-DS-REC-TT-180211-FC | FC | 0 | TRUE | TRUE | FALSE
4256 | MRT-YK10-P3MKA-220002 | 2018-07-27 | MRT-DS-REC-TT-180211-FC | FC | 0 | TRUE | TRUE | FALSE
4257 | MRT-DM02-P2MKA-220001 | 2018-07-27 | MRT-DS-REC-TT-180187-FC | FC | 0 | TRUE | TRUE | FALSE
4258 | MRT-DM02-P3MKA-220001 | 2018-07-27 | MRT-DS-REC-TT-180187-FC | FC | 0 | TRUE | TRUE | FALSE
4259 | MRT-YK10-P3MKA-220003 | 2018-07-27 | MRT-DS-REC-TT-180191-FC | FC | 0 | TRUE | TRUE | FALSE
4260 | MRT-DM01-P3MKA-220001 | 2018-07-27 | MRT-DS-REC-TT-180191-FC | FC | 0 | TRUE | TRUE | FALSE
4261 | MRT-YD00-P2MKA-220004 | 2018-07-27 | MRT-DS-REC-TT-180186-FC | FC | 0 | TRUE | TRUE | FALSE
4262 | MRT-YD00-P3MKA-220004 | 2018-07-27 | MRT-DS-REC-TT-180186-FC | FC | 0 | TRUE | TRUE | FALSE
4291 | MRT-CC02-P2UMA-170503 | 2018-07-27 | MRT-DS-REC-TT-180219-FC | FC | 2 | TRUE | TRUE | FALSE
4292 | MRT-CC02-P3UMA-170503 | 2018-07-27 | MRT-DS-REC-TT-180219-FC | FC | 2 | TRUE | TRUE | FALSE
4293 | MRT-XB02-P2LB-122016 | 2018-07-27 | MRT-DS-REC-TT-180224-FC | FC | 2 | TRUE | TRUE | FALSE
4294 | MRT-XB02-P3LB-122016 | 2018-07-27 | MRT-DS-REC-TT-180224-FC | FC | 1 | TRUE | TRUE | FALSE
4295 | MRT-YF01-P2ZEN-161013 | 2018-07-27 | MRT-DS-REC-TT-180226-FC | FC | 3 | TRUE | TRUE | FALSE
4296 | MRT-YF01-P3ZEN-161013 | 2018-07-27 | MRT-DS-REC-TT-180226-FC | FC | 3 | TRUE | TRUE | FALSE
4297 | MRT-CV03-P0ZEN-163107 | 2018-07-27 | MRT-DS-REC-TT-180573-FC | FC | 1 | TRUE | TRUE | FALSE
4298 | MRT-CV03-P3ZEN-163118 | 2018-07-27 | MRT-DS-REC-TT-180573-FC | FC | 1 | TRUE | TRUE | FALSE
4299 | MRT-XL00-P0ZEN-140001 | 2018-07-27 | MRT-DS-REC-TT-180225-FC | FC | 3 | TRUE | TRUE | FALSE
4300 | MRT-YF00-P2PAH-604121 | 2018-07-27 | MRT-DS-REC-TT-180229-FC | FC | 1 | TRUE | TRUE | FALSE
4301 | MRT-YF00-P3PAH-604521 | 2018-07-27 | MRT-DS-REC-TT-180230-FC | FC | 1 | TRUE | TRUE | FALSE
4302 | MRT-YV02-P3PAH-604522 | 2018-07-27 | MRT-DS-REC-TT-180230-FC | FC | 1 | TRUE | TRUE | FALSE
4364 | MRT-YD06-P2ZEN-161014 | 2018-07-27 | MRT-DS-REC-TT-180103-FC | FC | 1 | TRUE | TRUE | FALSE
4365 | MRT-YD06-P3ZEN-161014 | 2018-07-27 | MRT-DS-REC-TT-180103-FC | FC | 1 | TRUE | TRUE | FALSE
4366 | MRT-YK01-P2LB-122074 | 2018-07-27 | MRT-DS-REC-TT-180134-FC | FC | 0 | TRUE | TRUE | FALSE
4367 | MRT-YK01-P3LB-122074 | 2018-07-27 | MRT-DS-REC-TT-180134-FC | FC | 0 | TRUE | TRUE | FALSE
4368 | MRT-CC07-P2UHA-170001 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 3 | TRUE | TRUE | FALSE
4369 | MRT-CC02-P2UHA-170003 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 4 | TRUE | TRUE | FALSE
4370 | MRT-CC02-P2UHA-170004 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 4 | TRUE | TRUE | FALSE
4371 | MRT-CC07-P3UHA-170001 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 3 | TRUE | TRUE | FALSE
4372 | MRT-CC02-P3UHA-170003 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 4 | TRUE | TRUE | FALSE
4373 | MRT-CC02-P3UHA-170004 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 4 | TRUE | TRUE | FALSE
4374 | MRT-CC02-P0UHA-170002 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 4 | TRUE | TRUE | FALSE
4375 | MRT-XJ00-P2LB-122027 | 2018-07-27 | MRT-DS-REC-TT-180208-FC | FC | 0 | TRUE | TRUE | FALSE
4376 | MRT-XJ00-P3LB-122027 | 2018-07-27 | MRT-DS-REC-TT-180208-FC | FC | 0 | TRUE | TRUE | FALSE
4377 | MRT-CC07-P2UMA-170601 | 2018-07-27 | MRT-DS-REC-TT-180221-FC | FC | 2 | TRUE | TRUE | FALSE
4378 | MRT-CC02-P2UMA-170603 | 2018-07-27 | MRT-DS-REC-TT-180221-FC | FC | 2 | TRUE | TRUE | FALSE
4379 | MRT-CC07-P3UMA-170601 | 2018-07-27 | MRT-DS-REC-TT-180221-FC | FC | 2 | TRUE | TRUE | FALSE
4380 | MRT-CC02-P3UMA-170603 | 2018-07-27 | MRT-DS-REC-TT-180221-FC | FC | 2 | TRUE | TRUE | FALSE
4381 | MRT-YK10-P2MKA-230003 | 2018-07-27 | MRT-DS-REC-TT-180227-FC | FC | 0 | TRUE | TRUE | FALSE
4382 | MRT-YK10-P2MKA-230004 | 2018-07-27 | MRT-DS-REC-TT-180227-FC | FC | 0 | TRUE | TRUE | FALSE
4383 | MRT-YK10-P3MKA-230003 | 2018-07-27 | MRT-DS-REC-TT-180351-FC | FC | 0 | TRUE | TRUE | FALSE
4384 | MRT-YK10-P3MKA-230004 | 2018-07-27 | MRT-DS-REC-TT-180351-FC | FC | 0 | TRUE | TRUE | FALSE
4385 | MRT-YK00-P3BAT-240001 | 2018-07-27 | MRT-DS-REC-TT-180352-FC | FC | 0 | TRUE | TRUE | FALSE
4386 | MRT-YD00-P2MKJ-220001 | 2018-07-27 | MRT-DS-REC-TT-180353-FC | FC | 0 | TRUE | TRUE | FALSE
4387 | MRT-YD00-P3MKW-220003 | 2018-07-27 | MRT-DS-REC-TT-180353-FC | FC | 0 | TRUE | TRUE | FALSE
4388 | MRT-YD00-P3MKW-220004 | 2018-07-27 | MRT-DS-REC-TT-180353-FC | FC | 0 | TRUE | TRUE | FALSE
4389 | MRT-YD00-P3MKG-220001 | 2018-07-27 | MRT-DS-REC-TT-180353-FC | FC | 0 | TRUE | TRUE | FALSE
4390 | MRT-YD00-P3MKG-220003 | 2018-07-27 | MRT-DS-REC-TT-180353-FC | FC | 0 | TRUE | TRUE | FALSE
4391 | MRT-YD00-P3MKG-220004 | 2018-07-27 | MRT-DS-REC-TT-180353-FC | FC | 0 | TRUE | TRUE | FALSE
4392 | MRT-YD00-P3MKG-220005 | 2018-07-27 | MRT-DS-REC-TT-180353-FC | FC | 0 | TRUE | TRUE | FALSE
4393 | MRT-YD00-P3MKG-220006 | 2018-07-27 | MRT-DS-REC-TT-180353-FC | FC | 0 | TRUE | TRUE | FALSE
4394 | MRT-XK00-P0ZEN-140001 | 2018-07-27 | MRT-DS-REC-TT-180355-FC | FC | 1 | TRUE | TRUE | FALSE
4395 | MRT-YD00-P0SMM-128001 | 2018-07-27 | MRT-DS-REC-TT-180358-FC | FC | 3 | TRUE | TRUE | FALSE
4396 | MRT-YF00-P2MKC-230011 | 2018-07-27 | MRT-DS-REC-TT-180360-FC | FC | 0 | TRUE | TRUE | FALSE
4397 | MRT-YS01-P2MKC-230013 | 2018-07-27 | MRT-DS-REC-TT-180360-FC | FC | 0 | TRUE | TRUE | FALSE
4398 | MRT-YF00-P3MKC-230011 | 2018-07-27 | MRT-DS-REC-TT-180360-FC | FC | 0 | TRUE | TRUE | FALSE
4399 | MRT-YS01-P3MKC-230013 | 2018-07-27 | MRT-DS-REC-TT-180360-FC | FC | 0 | TRUE | TRUE | FALSE
4400 | MRT-XW03-P3MKA-210001 | 2018-07-27 | MRT-DS-REC-TT-180363-FC | FC | 0 | TRUE | TRUE | FALSE
4401 | MRT-CC07-P2UMA-170801 | 2018-07-27 | MRT-DS-REC-TT-180367-FC | FC | 2 | TRUE | TRUE | FALSE
4402 | MRT-CC02-P2UMA-170803 | 2018-07-27 | MRT-DS-REC-TT-180367-FC | FC | 2 | TRUE | TRUE | FALSE
4403 | MRT-VK02-P2UMA-170806 | 2018-07-27 | MRT-DS-REC-TT-180367-FC | FC | 2 | TRUE | TRUE | FALSE
4404 | MRT-CC07-P3UMA-170801 | 2018-07-27 | MRT-DS-REC-TT-180367-FC | FC | 2 | TRUE | TRUE | FALSE
4405 | MRT-CC02-P3UMA-170803 | 2018-07-27 | MRT-DS-REC-TT-180367-FC | FC | 2 | TRUE | TRUE | FALSE
4406 | MRT-VK02-P3UMA-170806 | 2018-07-27 | MRT-DS-REC-TT-180367-FC | FC | 2 | TRUE | TRUE | FALSE
4407 | MRT-YD00-P2MKA-220003 | 2018-07-27 | MRT-DS-REC-TT-180368-FC | FC | 3 | TRUE | TRUE | FALSE
4408 | MRT-YK08-P2ZEN-111200 | 2018-07-27 | MRT-DS-REC-TT-180370-FC | FC | 1 | TRUE | TRUE | FALSE
4409 | MRT-YT01-P2ZEN-111201 | 2018-07-27 | MRT-DS-REC-TT-180370-FC | FC | 1 | TRUE | TRUE | FALSE
4410 | MRT-YK08-P3ZEN-111200 | 2018-07-27 | MRT-DS-REC-TT-180370-FC | FC | 1 | TRUE | TRUE | FALSE
4411 | MRT-YT01-P3ZEN-111201 | 2018-07-27 | MRT-DS-REC-TT-180370-FC | FC | 1 | TRUE | TRUE | FALSE
4412 | MRT-YD00-P2LAC-126007 | 2018-07-27 | MRT-DS-REC-TT-180378-FC | FC | 1 | TRUE | TRUE | FALSE
4413 | MRT-YD00-P3LAC-126007 | 2018-07-27 | MRT-DS-REC-TT-180378-FC | FC | 1 | TRUE | TRUE | FALSE
4414 | MRT-YD00-P2LAC-126057 | 2018-07-27 | MRT-DS-REC-TT-180378-FC | FC | 1 | TRUE | TRUE | FALSE
4415 | MRT-YD00-P3LAC-126057 | 2018-07-27 | MRT-DS-REC-TT-180378-FC | FC | 1 | TRUE | TRUE | FALSE
4416 | MRT-YK01-P2LAC-126006 | 2018-07-27 | MRT-DS-REC-TT-180380-FC | FC | 1 | TRUE | TRUE | FALSE
4417 | MRT-YK01-P3LAC-126006 | 2018-07-27 | MRT-DS-REC-TT-180380-FC | FC | 1 | TRUE | TRUE | FALSE
4418 | MRT-YK01-P2LAC-126056 | 2018-07-27 | MRT-DS-REC-TT-180380-FC | FC | 1 | TRUE | TRUE | FALSE
4419 | MRT-YK01-P3LAC-126056 | 2018-07-27 | MRT-DS-REC-TT-180380-FC | FC | 1 | TRUE | TRUE | FALSE
4420 | MRT-YT01-P2LAA-605101 | 2018-07-27 | MRT-DS-REC-TT-180383-FC | FC | 4 | TRUE | TRUE | FALSE
4421 | MRT-YT01-P3LAA-605501 | 2018-07-27 | MRT-DS-REC-TT-180383-FC | FC | 4 | TRUE | TRUE | FALSE
4422 | MRT-YK08-P2LAA-605100 | 2018-07-27 | MRT-DS-REC-TT-180384-FC | FC | 4 | TRUE | TRUE | FALSE
4423 | MRT-YK08-P3LAA-605500 | 2018-07-27 | MRT-DS-REC-TT-180384-FC | FC | 4 | TRUE | TRUE | FALSE
4424 | MRT-YD00-P2PGB-113201 | 2018-07-27 | MRT-DS-REC-TT-180385-FC | FC | 3 | TRUE | TRUE | FALSE
4425 | MRT-YD00-P3PGB-113201 | 2018-07-27 | MRT-DS-REC-TT-180385-FC | FC | 3 | TRUE | TRUE | FALSE
4426 | MRT-YK10-P2PGB-113103 | 2018-07-27 | MRT-DS-REC-TT-180386-FC | FC | 1 | TRUE | TRUE | FALSE
4427 | MRT-YK10-P3PGB-113103 | 2018-07-27 | MRT-DS-REC-TT-180386-FC | FC | 1 | TRUE | TRUE | FALSE
4428 | MRT-YD00-P2LAC-126017 | 2018-07-27 | MRT-DS-REC-TT-180388-FC | FC | 0 | TRUE | TRUE | FALSE
4429 | MRT-YD00-P2LAC-126065 | 2018-07-27 | MRT-DS-REC-TT-180388-FC | FC | 0 | TRUE | TRUE | FALSE
4430 | MRT-YD00-P3LAC-126065 | 2018-07-27 | MRT-DS-REC-TT-180388-FC | FC | 0 | TRUE | TRUE | FALSE
4431 | MRT-YD00-P3LAC-126017 | 2018-07-27 | MRT-DS-REC-TT-180388-FC | FC | 0 | TRUE | TRUE | FALSE
4432 | MRT-YB03-P2PAH-604123 | 2018-07-27 | MRT-DS-REC-TT-180390-FC | FC | 3 | TRUE | TRUE | FALSE
4433 | MRT-XG02-P2PAH-604102 | 2018-07-27 | MRT-DS-REC-TT-180391-FC | FC | 2 | TRUE | TRUE | FALSE
4434 | MRT-YK08-P2PAH-604103 | 2018-07-27 | MRT-DS-REC-TT-180391-FC | FC | 2 | TRUE | TRUE | FALSE
4435 | MRT-YK08-P2PAH-604104 | 2018-07-27 | MRT-DS-REC-TT-180391-FC | FC | 2 | TRUE | TRUE | FALSE
4436 | MRT-XG02-P2PBB-604112 | 2018-07-27 | MRT-DS-REC-TT-180391-FC | FC | 2 | TRUE | TRUE | FALSE
4437 | MRT-YK08-P2PBB-604113 | 2018-07-27 | MRT-DS-REC-TT-180391-FC | FC | 2 | TRUE | TRUE | FALSE
4438 | MRT-XG02-P3PAH-604502 | 2018-07-27 | MRT-DS-REC-TT-180391-FC | FC | 2 | TRUE | TRUE | FALSE
4439 | MRT-YK08-P3PAH-604503 | 2018-07-27 | MRT-DS-REC-TT-180391-FC | FC | 2 | TRUE | TRUE | FALSE
4440 | MRT-YK08-P3PAH-604504 | 2018-07-27 | MRT-DS-REC-TT-180391-FC | FC | 2 | TRUE | TRUE | FALSE
4441 | MRT-XG02-P3PBB-604512 | 2018-07-27 | MRT-DS-REC-TT-180391-FC | FC | 2 | TRUE | TRUE | FALSE
4442 | MRT-YK08-P3PBB-604513 | 2018-07-27 | MRT-DS-REC-TT-180391-FC | FC | 2 | TRUE | TRUE | FALSE
4443 | MRT-YT01-P2PAH-604101 | 2018-07-27 | MRT-DS-REC-TT-180392-FC | FC | 2 | TRUE | TRUE | FALSE
4444 | MRT-YT01-P2PBB-604111 | 2018-07-27 | MRT-DS-REC-TT-180392-FC | FC | 2 | TRUE | TRUE | FALSE
4445 | MRT-YT01-P3PAH-604501 | 2018-07-27 | MRT-DS-REC-TT-180392-FC | FC | 2 | TRUE | TRUE | FALSE
4446 | MRT-YT01-P3PBB-604511 | 2018-07-27 | MRT-DS-REC-TT-180392-FC | FC | 2 | TRUE | TRUE | FALSE
4447 | MRT-YV02-P2MAJ-603202 | 2018-07-27 | MRT-DS-REC-TT-180393-FC | FC | 2 | TRUE | TRUE | FALSE
4448 | MRT-YV02-P3MAJ-604202 | 2018-07-27 | MRT-DS-REC-TT-180393-FC | FC | 2 | TRUE | TRUE | FALSE
4449 | MRT-XK00-P2GM-128504 | 2018-07-27 | MRT-DS-REC-TT-180395-FC | FC | 0 | TRUE | TRUE | FALSE
4450 | MRT-XK00-P3GM-128504 | 2018-07-27 | MRT-DS-REC-TT-180395-FC | FC | 0 | TRUE | TRUE | FALSE
4451 | MRT-XB00-P2LAC-126022 | 2018-07-27 | MRT-DS-REC-TT-180396-FC | FC | 1 | TRUE | TRUE | FALSE
4452 | MRT-XB00-P3LAC-126022 | 2018-07-27 | MRT-DS-REC-TT-180396-FC | FC | 1 | TRUE | TRUE | FALSE
4453 | MRT-XB00-P2LAC-126070 | 2018-07-27 | MRT-DS-REC-TT-180396-FC | FC | 1 | TRUE | TRUE | FALSE
4454 | MRT-XB00-P3LAC-126070 | 2018-07-27 | MRT-DS-REC-TT-180396-FC | FC | 1 | TRUE | TRUE | FALSE
4455 | MRT-YE00-P3MKA-230001 | 2018-07-27 | MRT-DS-REC-TT-180409-FC | FC | 0 | TRUE | TRUE | FALSE
4456 | MRT-YF00-P0CJD-161401 | 2018-07-27 | MRT-DS-REC-TT-180410-FC | FC | 0 | TRUE | TRUE | FALSE
4457 | MRT-YF00-P2CJD-161402 | 2018-07-27 | MRT-DS-REC-TT-180410-FC | FC | 0 | TRUE | TRUE | FALSE
4458 | MRT-YF00-P2CJD-161403 | 2018-07-27 | MRT-DS-REC-TT-180410-FC | FC | 0 | TRUE | TRUE | FALSE
4459 | MRT-YF00-P3CJD-161402 | 2018-07-27 | MRT-DS-REC-TT-180410-FC | FC | 0 | TRUE | TRUE | FALSE
4460 | MRT-YF00-P3CJD-161403 | 2018-07-27 | MRT-DS-REC-TT-180410-FC | FC | 0 | TRUE | TRUE | FALSE
4461 | MRT-CC02-P3UMA-170209 | 2018-07-27 | MRT-DS-REC-TT-180411-FC | FC | 2 | TRUE | TRUE | FALSE
4462 | MRT-YE00-P2MKA-230002 | 2018-07-27 | MRT-DS-REC-TT-180425-FC | FC | 2 | TRUE | TRUE | FALSE
4463 | MRT-YE00-P3MKA-230002 | 2018-07-27 | MRT-DS-REC-TT-180425-FC | FC | 2 | TRUE | TRUE | FALSE
4464 | MRT-YT01-P2GHC-129002 | 2018-07-27 | MRT-DS-REC-TT-180427-FC | FC | 2 | TRUE | TRUE | FALSE
4465 | MRT-YT01-P3GHC-129002 | 2018-07-27 | MRT-DS-REC-TT-180427-FC | FC | 2 | TRUE | TRUE | FALSE
4466 | MRT-YM01-P2GHC-129008 | 2018-07-27 | MRT-DS-REC-TT-180428-FC | FC | 2 | TRUE | TRUE | FALSE
4467 | MRT-YM01-P3GHC-129008 | 2018-07-27 | MRT-DS-REC-TT-180428-FC | FC | 2 | TRUE | TRUE | FALSE
4468 | MRT-YD00-P3MKA-220005 | 2018-07-27 | MRT-DS-REC-TT-180430-FC | FC | 0 | TRUE | TRUE | FALSE
4469 | MRT-YR05-P2SCA-127523 | 2018-07-27 | MRT-DS-REC-TT-180432-FC | FC | 0 | TRUE | TRUE | FALSE
4470 | MRT-YR05-P3SCA-127523 | 2018-07-27 | MRT-DS-REC-TT-180432-FC | FC | 0 | TRUE | TRUE | FALSE
4471 | MRT-YT01-P2PGB-113104 | 2018-07-27 | MRT-DS-REC-TT-180436-FC | FC | 2 | TRUE | TRUE | FALSE
4472 | MRT-YT01-P3PGB-113104 | 2018-07-27 | MRT-DS-REC-TT-180436-FC | FC | 2 | TRUE | TRUE | FALSE
4473 | MRT-XA00-P2QC-130002 | 2018-07-27 | MRT-DS-REC-TT-180550-FC | FC | 2 | TRUE | TRUE | FALSE
4474 | MRT-XA00-P3QC-130002 | 2018-07-27 | MRT-DS-REC-TT-180550-FC | FC | 2 | TRUE | TRUE | FALSE
4475 | MRT-YT01-P2MAG-601007 | 2018-07-27 | MRT-DS-REC-TT-180557-FC | FC | 4 | TRUE | TRUE | FALSE
4476 | MRT-YT01-P3MAG-602007 | 2018-07-27 | MRT-DS-REC-TT-180557-FC | FC | 4 | TRUE | TRUE | FALSE
4477 | MRT-YD00-P2LB-122049 | 2018-07-27 | MRT-DS-REC-TT-180559-FC | FC | 2 | TRUE | TRUE | FALSE
4478 | MRT-YD00-P3LB-122049 | 2018-07-27 | MRT-DS-REC-TT-180559-FC | FC | 2 | TRUE | TRUE | FALSE
4479 | MRT-YT01-P2LB-122097 | 2018-07-27 | MRT-DS-REC-TT-180560-FC | FC | 1 | TRUE | TRUE | FALSE
4480 | MRT-YT01-P3LB-122097 | 2018-07-27 | MRT-DS-REC-TT-180560-FC | FC | 1 | TRUE | TRUE | FALSE
4481 | MRT-YD00-P0PGB-606000 | 2018-07-27 | MRT-DS-REC-TT-180599-FC | FC | 3 | TRUE | TRUE | FALSE
4482 | MRT-YD00-P0PGB-606001 | 2018-07-27 | MRT-DS-REC-TT-180599-FC | FC | 3 | TRUE | TRUE | FALSE
4483 | MRT-YD00-P0QHE-606001 | 2018-07-27 | MRT-DS-REC-TT-180600-FC | FC | 3 | TRUE | TRUE | FALSE
4484 | MRT-CN00-P3ZEN-110100 | 2018-07-27 | MRT-DS-REC-TT-180603-FC | FC | 2 | TRUE | TRUE | FALSE
4485 | MRT-CC02-P2UAG-170307 | 2018-07-27 | MRT-DS-REC-TT-180616-FC | FC | 0 | TRUE | TRUE | FALSE
4486 | MRT-CC02-P3UAG-170307 | 2018-07-27 | MRT-DS-REC-TT-180616-FC | FC | 0 | TRUE | TRUE | FALSE
4487 | MRT-YT01-P2ZEN-113301 | 2018-07-27 | MRT-DS-REC-TT-180619-FC | FC | 2 | TRUE | TRUE | FALSE
4488 | MRT-YT01-P3ZEN-113301 | 2018-07-27 | MRT-DS-REC-TT-180619-FC | FC | 2 | TRUE | TRUE | FALSE
4531 | MRT-DP01-P0ZEN-070002 | 2018-07-27 | MRT-DS-REC-TT-180132-FC | FC | 0 | TRUE | TRUE | FALSE
4532 | MRT-YU04-P0ZEN-161012 | 2018-07-27 | MRT-DS-REC-TT-180289-FC | FC | 4 | TRUE | TRUE | FALSE
4533 | MRT-XG02-P2SCA-127502 | 2018-07-27 | MRT-DS-REC-TT-180296-FC | FC | 1 | TRUE | TRUE | FALSE
4534 | MRT-XG02-P3SCA-127502 | 2018-07-27 | MRT-DS-REC-TT-180296-FC | FC | 1 | TRUE | TRUE | FALSE
4535 | MRT-YE00-P2MKA-230001 | 2018-07-27 | MRT-DS-REC-TT-180300-FC | FC | 0 | TRUE | TRUE | FALSE
4536 | MRT-YK00-P2BAT-240001 | 2018-07-27 | MRT-DS-REC-TT-180300-FC | FC | 0 | TRUE | TRUE | FALSE
4537 | MRT-UC02-P2BAT-240001 | 2018-07-27 | MRT-DS-REC-TT-180300-FC | FC | 0 | TRUE | TRUE | FALSE
4540 | MRT-CC02-P2UMA-170209 | 2018-07-27 | MRT-DS-REC-TT-180305-FC | FC | 2 | TRUE | TRUE | FALSE
4541 | MRT-CA06-P0UMA-180001 | 2018-07-27 | MRT-DS-REC-TT-180307-FC | FC | 3 | TRUE | TRUE | FALSE
4542 | MRT-CA01-P0UMA-180006 | 2018-07-27 | MRT-DS-REC-TT-180307-FC | FC | 4 | TRUE | TRUE | FALSE
4543 | MRT-CA01-P0UMA-180007 | 2018-07-27 | MRT-DS-REC-TT-180307-FC | FC | 4 | TRUE | TRUE | FALSE
4544 | MRT-YD00-P3MKA-220003 | 2018-07-27 | MRT-DS-REC-TT-180071-FC | FC | 2 | TRUE | TRUE | FALSE
4545 | MRT-CA03-P0UMA-180035 | 2018-07-27 | MRT-DS-REC-TT-180094-FC | FC | 2 | TRUE | TRUE | FALSE
4546 | MRT-CA03-P0UMA-180036 | 2018-07-27 | MRT-DS-REC-TT-180094-FC | FC | 2 | TRUE | TRUE | FALSE
4547 | MRT-CA03-P0UMA-180037 | 2018-07-27 | MRT-DS-REC-TT-180094-FC | FC | 2 | TRUE | TRUE | FALSE
4548 | MRT-CA01-P0UCA-180103 | 2018-07-27 | MRT-DS-REC-TT-180122-FC | FC | 3 | TRUE | TRUE | FALSE
4549 | MRT-CA02-P0UCA-180104 | 2018-07-27 | MRT-DS-REC-TT-180122-FC | FC | 3 | TRUE | TRUE | FALSE
4550 | MRT-CA02-P0UCA-180136 | 2018-07-27 | MRT-DS-REC-TT-180130-FC | FC | 2 | TRUE | TRUE | FALSE
4551 | MRT-XG07-P3PA-110304 | 2018-07-27 | MRT-DS-REC-TT-180147-FC | FC | 3 | TRUE | TRUE | FALSE
4552 | MRT-XS00-P2LB-122035 | 2018-07-27 | MRT-DS-REC-TT-180160-FC | FC | 2 | TRUE | TRUE | FALSE
4553 | MRT-YK08-P2MAJ-603102 | 2018-07-27 | MRT-DS-REC-TT-180182-FC | FC | 2 | TRUE | TRUE | FALSE
4554 | MRT-YK08-P3MAJ-604102 | 2018-07-27 | MRT-DS-REC-TT-180182-FC | FC | 2 | TRUE | TRUE | FALSE
4555 | MRT-YR05-P0ZEN-161016 | 2018-07-27 | MRT-DS-REC-TT-180206-FC | FC | 2 | TRUE | TRUE | FALSE
4556 | MRT-CC02-P2UMA-170703 | 2018-07-27 | MRT-DS-REC-TT-180213-FC | FC | 2 | TRUE | TRUE | FALSE
4557 | MRT-CC02-P3UMA-170703 | 2018-07-27 | MRT-DS-REC-TT-180213-FC | FC | 2 | TRUE | TRUE | FALSE
4558 | MRT-CC07-P2UMA-170701 | 2018-07-27 | MRT-DS-REC-TT-180213-FC | FC | 2 | TRUE | TRUE | FALSE
4559 | MRT-CC07-P3UMA-170701 | 2018-07-27 | MRT-DS-REC-TT-180213-FC | FC | 2 | TRUE | TRUE | FALSE
4560 | MRT-XW01-P0ZEN-161001 | 2018-07-27 | MRT-DS-REC-TT-180218-FC | FC | 5 | TRUE | TRUE | FALSE
4561 | MRT-XB02-P0UCA-180102 | 2018-07-27 | MRT-DS-REC-TT-180237-FC | FC | 4 | TRUE | TRUE | FALSE
4562 | MRT-XB02-P2LB-122021 | 2018-07-27 | MRT-DS-REC-TT-180247-FC | FC | 2 | TRUE | TRUE | FALSE
4563 | MRT-YD00-P2MKA-220001 | 2018-07-27 | MRT-DS-REC-TT-180249-FC | FC | 3 | TRUE | TRUE | FALSE
4564 | MRT-YT01-P2PGB-113102 | 2018-07-27 | MRT-DS-REC-TT-180252-FC | FC | 1 | TRUE | TRUE | FALSE
4565 | MRT-YT01-P3PGB-113102 | 2018-07-27 | MRT-DS-REC-TT-180252-FC | FC | 1 | TRUE | TRUE | FALSE
4566 | MRT-YD00-P2MKA-220005 | 2018-07-27 | MRT-DS-REC-TT-180253-FC | FC | 0 | TRUE | TRUE | FALSE
4567 | MRT-QM01-P0ZEN-040002 | 2018-07-27 | MRT-DS-REC-TT-180254-FC | FC | 5 | TRUE | TRUE | FALSE
4568 | MRT-CA06-P0UMA-180002 | 2018-07-27 | MRT-DS-REC-TT-180255-FC | FC | 4 | TRUE | TRUE | FALSE
4569 | MRT-CA06-P0UMA-180003 | 2018-07-27 | MRT-DS-REC-TT-180255-FC | FC | 3 | TRUE | TRUE | FALSE
4570 | MRT-XB02-P2LB-122017 | 2018-07-27 | MRT-DS-REC-TT-180257-FC | FC | 3 | TRUE | TRUE | FALSE
4571 | MRT-XB02-P3LB-122017 | 2018-07-27 | MRT-DS-REC-TT-180257-FC | FC | 2 | TRUE | TRUE | FALSE
4572 | MRT-YK00-P2LB-122072 | 2018-07-27 | MRT-DS-REC-TT-180261-FC | FC | 2 | TRUE | TRUE | FALSE
4573 | MRT-YK00-P3LB-122072 | 2018-07-27 | MRT-DS-REC-TT-180261-FC | FC | 2 | TRUE | TRUE | FALSE
4574 | MRT-XS00-P3LB-122035 | 2018-07-27 | MRT-DS-REC-TT-180262-FC | FC | 2 | TRUE | TRUE | FALSE
4575 | MRT-YK09-P2LCB-127034 | 2018-07-27 | MRT-DS-REC-TT-180267-FC | FC | 0 | TRUE | TRUE | FALSE
4576 | MRT-YK09-P3LCB-127034 | 2018-07-27 | MRT-DS-REC-TT-180267-FC | FC | 0 | TRUE | TRUE | FALSE
4577 | MRT-XN00-P0ZEN-140001 | 2018-07-27 | MRT-DS-REC-TT-180276-FC | FC | 3 | TRUE | TRUE | FALSE
4578 | MRT-YD00-P2ZEN-113500 | 2018-07-27 | MRT-DS-REC-TT-180278-FC | FC | 1 | TRUE | TRUE | FALSE
4579 | MRT-YD00-P3ZEN-113500 | 2018-07-27 | MRT-DS-REC-TT-180278-FC | FC | 1 | TRUE | TRUE | FALSE
4580 | MRT-YT01-P2ZEN-113501 | 2018-07-27 | MRT-DS-REC-TT-180278-FC | FC | 1 | TRUE | TRUE | FALSE
4581 | MRT-YT01-P3ZEN-113501 | 2018-07-27 | MRT-DS-REC-TT-180278-FC | FC | 1 | TRUE | TRUE | FALSE
4582 | MRT-YD00-P2ZEN-113400 | 2018-07-27 | MRT-DS-REC-TT-180279-FC | FC | 1 | TRUE | TRUE | FALSE
4583 | MRT-YD00-P3ZEN-113400 | 2018-07-27 | MRT-DS-REC-TT-180279-FC | FC | 1 | TRUE | TRUE | FALSE
4584 | MRT-YT01-P2ZEN-113401 | 2018-07-27 | MRT-DS-REC-TT-180279-FC | FC | 1 | TRUE | TRUE | FALSE
4585 | MRT-YT01-P3ZEN-113401 | 2018-07-27 | MRT-DS-REC-TT-180279-FC | FC | 1 | TRUE | TRUE | FALSE
4586 | MRT-CQ02-P2MAJ-603109 | 2018-07-27 | MRT-DS-REC-TT-180281-FC | FC | 0 | TRUE | TRUE | FALSE
4587 | MRT-CQ02-P3MAJ-603109 | 2018-07-27 | MRT-DS-REC-TT-180281-FC | FC | 0 | TRUE | TRUE | FALSE
4588 | MRT-XL00-P0ZEN-140002 | 2018-07-27 | MRT-DS-REC-TT-180282-FC | FC | 3 | TRUE | TRUE | FALSE
4589 | MRT-XG02-P2LB-122022 | 2018-07-27 | MRT-DS-REC-TT-180288-FC | FC | 5 | TRUE | TRUE | FALSE
4590 | MRT-XG02-P3LB-122022 | 2018-07-27 | MRT-DS-REC-TT-180288-FC | FC | 2 | TRUE | TRUE | FALSE
4591 | MRT-XH01-P0UZT-140001 | 2018-07-27 | MRT-DS-REC-TT-180310-FC | FC | 2 | TRUE | TRUE | FALSE
4592 | MRT-XH01-P2ULY-142000 | 2018-07-27 | MRT-DS-REC-TT-180310-FC | FC | 2 | TRUE | TRUE | FALSE
4593 | MRT-XH01-P3ULY-143000 | 2018-07-27 | MRT-DS-REC-TT-180310-FC | FC | 2 | TRUE | TRUE | FALSE
4594 | MRT-XH01-P3ULY-144000 | 2018-07-27 | MRT-DS-REC-TT-180310-FC | FC | 2 | TRUE | TRUE | FALSE
4595 | MRT-CC02-P2UMA-170203 | 2018-07-27 | MRT-DS-REC-TT-180318-FC | FC | 2 | TRUE | TRUE | FALSE
4596 | MRT-CC02-P2UMA-170204 | 2018-07-27 | MRT-DS-REC-TT-180318-FC | FC | 2 | TRUE | TRUE | FALSE
4597 | MRT-CC02-P3UMA-170203 | 2018-07-27 | MRT-DS-REC-TT-180318-FC | FC | 2 | TRUE | TRUE | FALSE
4598 | MRT-CC02-P3UMA-170204 | 2018-07-27 | MRT-DS-REC-TT-180318-FC | FC | 2 | TRUE | TRUE | FALSE
4599 | MRT-YK09-P2MKC-230002 | 2018-07-27 | MRT-DS-REC-TT-180319-FC | FC | 0 | TRUE | TRUE | FALSE
4600 | MRT-YK09-P3MKC-230002 | 2018-07-27 | MRT-DS-REC-TT-180319-FC | FC | 0 | TRUE | TRUE | FALSE
4601 | MRT-YQ03-P2LB-122088 | 2018-07-27 | MRT-DS-REC-TT-180320-FC | FC | 3 | TRUE | TRUE | FALSE
4602 | MRT-YQ03-P3LB-122088 | 2018-07-27 | MRT-DS-REC-TT-180320-FC | FC | 2 | TRUE | TRUE | FALSE
4603 | MRT-YB03-P3PAH-604523 | 2018-07-27 | MRT-DS-REC-TT-180325-FC | FC | 2 | TRUE | TRUE | FALSE
4604 | MRT-YK08-P3PAH-604524 | 2018-07-27 | MRT-DS-REC-TT-180325-FC | FC | 2 | TRUE | TRUE | FALSE
4605 | MRT-YD00-P2LAC-126001 | 2018-07-27 | MRT-DS-REC-TT-180327-FC | FC | 1 | TRUE | TRUE | FALSE
4606 | MRT-YD00-P2LAC-126051 | 2018-07-27 | MRT-DS-REC-TT-180327-FC | FC | 1 | TRUE | TRUE | FALSE
4607 | MRT-YD00-P3LAC-126001 | 2018-07-27 | MRT-DS-REC-TT-180327-FC | FC | 1 | TRUE | TRUE | FALSE
4608 | MRT-YD00-P3LAC-126051 | 2018-07-27 | MRT-DS-REC-TT-180327-FC | FC | 1 | TRUE | TRUE | FALSE
4609 | MRT-YT01-P2LAC-126004 | 2018-07-27 | MRT-DS-REC-TT-180327-FC | FC | 1 | TRUE | TRUE | FALSE
4610 | MRT-YT01-P2LAC-126054 | 2018-07-27 | MRT-DS-REC-TT-180327-FC | FC | 1 | TRUE | TRUE | FALSE
4611 | MRT-YT01-P3LAC-126004 | 2018-07-27 | MRT-DS-REC-TT-180327-FC | FC | 1 | TRUE | TRUE | FALSE
4612 | MRT-YT01-P3LAC-126054 | 2018-07-27 | MRT-DS-REC-TT-180327-FC | FC | 1 | TRUE | TRUE | FALSE
4613 | MRT-XW03-P2MAV-120001 | 2018-07-27 | MRT-DS-REC-TT-180329-FC | FC | 1 | TRUE | TRUE | FALSE
4614 | MRT-XW03-P3MAV-130001 | 2018-07-27 | MRT-DS-REC-TT-180329-FC | FC | 1 | TRUE | TRUE | FALSE
4615 | MRT-CC02-P2UHA-170104 | 2018-07-27 | MRT-DS-REC-TT-180332-FC | FC | 4 | TRUE | TRUE | FALSE
4616 | MRT-CC02-P3UHA-170104 | 2018-07-27 | MRT-DS-REC-TT-180332-FC | FC | 4 | TRUE | TRUE | FALSE
4617 | MRT-CC07-P2UHA-170005 | 2018-07-27 | MRT-DS-REC-TT-180333-FC | FC | 3 | TRUE | TRUE | FALSE
4618 | MRT-CC07-P3UHA-170005 | 2018-07-27 | MRT-DS-REC-TT-180333-FC | FC | 3 | TRUE | TRUE | FALSE
4619 | MRT-XK00-P2GM-128507 | 2018-07-27 | MRT-DS-REC-TT-180336-FC | FC | 2 | TRUE | TRUE | FALSE
4620 | MRT-XK00-P3GM-128507 | 2018-07-27 | MRT-DS-REC-TT-180336-FC | FC | 2 | TRUE | TRUE | FALSE
4621 | MRT-YS01-P3MKC-230017 | 2018-07-27 | MRT-DS-REC-TT-180339-FC | FC | 0 | TRUE | TRUE | FALSE
4622 | MRT-DP00-P2LB-122106 | 2018-07-27 | MRT-DS-REC-TT-180341-FC | FC | 3 | TRUE | TRUE | FALSE
4623 | MRT-DP00-P3LB-122106 | 2018-07-27 | MRT-DS-REC-TT-180341-FC | FC | 3 | TRUE | TRUE | FALSE
4624 | MRT-YT01-P2LAC-126055 | 2018-07-27 | MRT-DS-REC-TT-180343-FC | FC | 1 | TRUE | TRUE | FALSE
4625 | MRT-YT01-P3LAC-126055 | 2018-07-27 | MRT-DS-REC-TT-180343-FC | FC | 1 | TRUE | TRUE | FALSE
4626 | MRT-XG02-P2MAJ-603101 | 2018-07-27 | MRT-DS-REC-TT-180344-FC | FC | 3 | TRUE | TRUE | FALSE
4627 | MRT-XG02-P3MAJ-604101 | 2018-07-27 | MRT-DS-REC-TT-180344-FC | FC | 3 | TRUE | TRUE | FALSE
4628 | MRT-XN00-P2MAJ-603106 | 2018-07-27 | MRT-DS-REC-TT-180344-FC | FC | 3 | TRUE | TRUE | FALSE
4629 | MRT-XN00-P3MAJ-604106 | 2018-07-27 | MRT-DS-REC-TT-180344-FC | FC | 3 | TRUE | TRUE | FALSE
4630 | MRT-YK08-P2MAJ-603308 | 2018-07-27 | MRT-DS-REC-TT-180344-FC | FC | 1 | TRUE | TRUE | FALSE
4631 | MRT-YK08-P3MAJ-604308 | 2018-07-27 | MRT-DS-REC-TT-180344-FC | FC | 1 | TRUE | TRUE | FALSE
4632 | MRT-YL00-P2MAJ-603107 | 2018-07-27 | MRT-DS-REC-TT-180344-FC | FC | 3 | TRUE | TRUE | FALSE
4633 | MRT-YL00-P3MAJ-604107 | 2018-07-27 | MRT-DS-REC-TT-180344-FC | FC | 3 | TRUE | TRUE | FALSE
4634 | MRT-XG02-P0GHC-110002 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4635 | MRT-XG02-P0LBG-110004 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4636 | MRT-XG02-P0PA-110002 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4637 | MRT-XG02-P2LA-110006 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4638 | MRT-XG02-P2LBA-110003 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4639 | MRT-XG02-P2LBG-110004 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4640 | MRT-XG02-P2LC-110007 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4641 | MRT-XG02-P2PA-110002 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4642 | MRT-XG02-P2PA-110008 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4643 | MRT-XG02-P2PG-110009 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4644 | MRT-XG02-P3LA-110006 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4645 | MRT-XG02-P3LBA-110003 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4646 | MRT-XG02-P3LBG-110004 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4647 | MRT-XG02-P3LC-110007 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4648 | MRT-XG02-P3PA-110002 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4649 | MRT-XG02-P3PA-110008 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4650 | MRT-XG02-P3PG-110009 | 2018-07-27 | MRT-DS-REC-TT-180348-FC | FC | 5 | TRUE | TRUE | FALSE
4651 | MRT-XW01-P2SCA-127504 | 2018-07-27 | MRT-DS-REC-TT-180349-FC | FC | 1 | TRUE | TRUE | FALSE
4652 | MRT-XW01-P3SCA-127504 | 2018-07-27 | MRT-DS-REC-TT-180349-FC | FC | 1 | TRUE | TRUE | FALSE
4653 | MRT-CC02-P0UMA-170502 | 2018-07-27 | MRT-DS-REC-TT-180364-FC | FC | 3 | TRUE | TRUE | FALSE
4654 | MRT-CC02-P2UMA-170507 | 2018-07-27 | MRT-DS-REC-TT-180364-FC | FC | 3 | TRUE | TRUE | FALSE
4655 | MRT-CC02-P3UMA-170507 | 2018-07-27 | MRT-DS-REC-TT-180364-FC | FC | 3 | TRUE | TRUE | FALSE
4656 | MRT-CC07-P2UMA-170501 | 2018-07-27 | MRT-DS-REC-TT-180364-FC | FC | 3 | TRUE | TRUE | FALSE
4657 | MRT-CC07-P3UMA-170501 | 2018-07-27 | MRT-DS-REC-TT-180364-FC | FC | 3 | TRUE | TRUE | FALSE
4658 | MRT-VK02-P2UMA-170510 | 2018-07-27 | MRT-DS-REC-TT-180364-FC | FC | 3 | TRUE | TRUE | FALSE
4659 | MRT-VK02-P3UMA-170510 | 2018-07-27 | MRT-DS-REC-TT-180364-FC | FC | 3 | TRUE | TRUE | FALSE
4660 | MRT-YF00-P0CBA-161201 | 2018-07-27 | MRT-DS-REC-TT-180376-FC | FC | 1 | TRUE | TRUE | FALSE
4661 | MRT-YF00-P0CGA-161301 | 2018-07-27 | MRT-DS-REC-TT-180376-FC | FC | 1 | TRUE | TRUE | FALSE
4662 | MRT-YF00-P0CGA-161302 | 2018-07-27 | MRT-DS-REC-TT-180376-FC | FC | 1 | TRUE | TRUE | FALSE
4663 | MRT-YS01-P2MKC-230015 | 2018-07-27 | MRT-DS-REC-TT-180421-FC | FC | 0 | TRUE | TRUE | FALSE
4664 | MRT-YS01-P3MKC-230015 | 2018-07-27 | MRT-DS-REC-TT-180421-FC | FC | 0 | TRUE | TRUE | FALSE
4665 | MRT-CA01-P0UMA-180044 | 2018-07-27 | MRT-DS-REC-TT-180426-FC | FC | 1 | TRUE | TRUE | FALSE
4666 | MRT-CA02-P0UMA-180045 | 2018-07-27 | MRT-DS-REC-TT-180426-FC | FC | 1 | TRUE | TRUE | FALSE
4667 | MRT-YK08-P2LB-111101 | 2018-07-27 | MRT-DS-REC-TT-180429-FC | FC | 1 | TRUE | TRUE | FALSE
4668 | MRT-YK08-P3LB-111101 | 2018-07-27 | MRT-DS-REC-TT-180429-FC | FC | 1 | TRUE | TRUE | FALSE
4669 | MRT-YK09-P2LB-111103 | 2018-07-27 | MRT-DS-REC-TT-180429-FC | FC | 1 | TRUE | TRUE | FALSE
4670 | MRT-YK09-P3LB-111103 | 2018-07-27 | MRT-DS-REC-TT-180429-FC | FC | 1 | TRUE | TRUE | FALSE
4671 | MRT-YT01-P2LB-111102 | 2018-07-27 | MRT-DS-REC-TT-180429-FC | FC | 1 | TRUE | TRUE | FALSE
4672 | MRT-YT01-P3LB-111102 | 2018-07-27 | MRT-DS-REC-TT-180429-FC | FC | 1 | TRUE | TRUE | FALSE
4673 | MRT-YK08-P2MAG-601002 | 2018-07-27 | MRT-DS-REC-TT-180434-FC | FC | 3 | TRUE | TRUE | FALSE
4674 | MRT-YK08-P3MAG-602002 | 2018-07-27 | MRT-DS-REC-TT-180434-FC | FC | 3 | TRUE | TRUE | FALSE
4675 | MRT-XG02-P0GKC-120001 | 2018-07-27 | MRT-DS-REC-TT-180441-FC | FC | 3 | TRUE | TRUE | FALSE
4676 | MRT-XS00-P2QU-130026 | 2018-07-27 | MRT-DS-REC-TT-180445-FC | FC | 2 | TRUE | TRUE | FALSE
4677 | MRT-XS00-P3QU-130026 | 2018-07-27 | MRT-DS-REC-TT-180445-FC | FC | 2 | TRUE | TRUE | FALSE
4678 | MRT-YT01-P0SMM-128004 | 2018-07-27 | MRT-DS-REC-TT-180446-FC | FC | 3 | TRUE | TRUE | FALSE
4679 | MRT-XS00-P2MAJ-603209 | 2018-07-27 | MRT-DS-REC-TT-180448-FC | FC | 2 | TRUE | TRUE | FALSE
4680 | MRT-XS00-P3MAJ-604209 | 2018-07-27 | MRT-DS-REC-TT-180448-FC | FC | 2 | TRUE | TRUE | FALSE
4681 | MRT-YT01-P2MAJ-603204 | 2018-07-27 | MRT-DS-REC-TT-180448-FC | FC | 3 | TRUE | TRUE | FALSE
4682 | MRT-YT01-P3MAJ-604204 | 2018-07-27 | MRT-DS-REC-TT-180448-FC | FC | 3 | TRUE | TRUE | FALSE
4683 | MRT-XG02-P2QU-130024 | 2018-07-27 | MRT-DS-REC-TT-180449-FC | FC | 2 | TRUE | TRUE | FALSE
4684 | MRT-XG02-P3QU-130024 | 2018-07-27 | MRT-DS-REC-TT-180449-FC | FC | 2 | TRUE | TRUE | FALSE
4685 | MRT-YT01-P3MKA-240002 | 2018-07-27 | MRT-DS-REC-TT-180452-FC | FC | 0 | TRUE | TRUE | FALSE
4686 | MRT-YV02-P3MKW-230001 | 2018-07-27 | MRT-DS-REC-TT-180452-FC | FC | 0 | TRUE | TRUE | FALSE
4687 | MRT-YV02-P3MKW-230002 | 2018-07-27 | MRT-DS-REC-TT-180452-FC | FC | 0 | TRUE | TRUE | FALSE
4688 | MRT-YD00-P2LB-122107 | 2018-07-27 | MRT-DS-REC-TT-180453-FC | FC | 2 | TRUE | TRUE | FALSE
4689 | MRT-YD00-P3LB-122107 | 2018-07-27 | MRT-DS-REC-TT-180453-FC | FC | 2 | TRUE | TRUE | FALSE
4690 | MRT-XG02-P2LAC-126003 | 2018-07-27 | MRT-DS-REC-TT-180454-FC | FC | 2 | TRUE | TRUE | FALSE
4691 | MRT-XG02-P2LAC-126053 | 2018-07-27 | MRT-DS-REC-TT-180454-FC | FC | 2 | TRUE | TRUE | FALSE
4692 | MRT-XG02-P3LAC-126003 | 2018-07-27 | MRT-DS-REC-TT-180454-FC | FC | 2 | TRUE | TRUE | FALSE
4693 | MRT-XG02-P3LAC-126053 | 2018-07-27 | MRT-DS-REC-TT-180454-FC | FC | 2 | TRUE | TRUE | FALSE
4694 | MRT-YL22-P2LB-111104 | 2018-07-27 | MRT-DS-REC-TT-180457-FC | FC | 0 | TRUE | TRUE | FALSE
4695 | MRT-YL22-P3LB-111104 | 2018-07-27 | MRT-DS-REC-TT-180457-FC | FC | 0 | TRUE | TRUE | FALSE
4696 | MRT-XF00-P2SCA-127524 | 2018-07-27 | MRT-DS-REC-TT-180458-FC | FC | 0 | TRUE | TRUE | FALSE
4697 | MRT-XF00-P3SCA-127524 | 2018-07-27 | MRT-DS-REC-TT-180458-FC | FC | 0 | TRUE | TRUE | FALSE
4698 | MRT-YD00-P2GHC-129001 | 2018-07-27 | MRT-DS-REC-TT-180460-FC | FC | 3 | TRUE | TRUE | FALSE
4699 | MRT-YD00-P3GHC-129001 | 2018-07-27 | MRT-DS-REC-TT-180460-FC | FC | 3 | TRUE | TRUE | FALSE
4700 | MRT-CV03-P0ZEN-163102 | 2018-07-27 | MRT-DS-REC-TT-180461-FC | FC | 1 | TRUE | TRUE | FALSE
4701 | MRT-CV03-P0ZEN-163103 | 2018-07-27 | MRT-DS-REC-TT-180461-FC | FC | 1 | TRUE | TRUE | FALSE
4702 | MRT-CC07-P2QC-130004 | 2018-07-27 | MRT-DS-REC-TT-180463-FC | FC | 2 | TRUE | TRUE | FALSE
4703 | MRT-CC07-P3QC-130004 | 2018-07-27 | MRT-DS-REC-TT-180463-FC | FC | 2 | TRUE | TRUE | FALSE
4704 | MRT-XG02-P2QC-130001 | 2018-07-27 | MRT-DS-REC-TT-180463-FC | FC | 2 | TRUE | TRUE | FALSE
4705 | MRT-XG02-P3QC-130001 | 2018-07-27 | MRT-DS-REC-TT-180463-FC | FC | 2 | TRUE | TRUE | FALSE
4706 | MRT-XS00-P2QC-130003 | 2018-07-27 | MRT-DS-REC-TT-180463-FC | FC | 2 | TRUE | TRUE | FALSE
4707 | MRT-XS00-P3QC-130003 | 2018-07-27 | MRT-DS-REC-TT-180463-FC | FC | 2 | TRUE | TRUE | FALSE
4708 | MRT-YD00-P3MKW-220002 | 2018-07-27 | MRT-DS-REC-TT-180464-FC | FC | 0 | TRUE | TRUE | FALSE
4709 | MRT-YT01-P2MKA-240001 | 2018-07-27 | MRT-DS-REC-TT-180468-FC | FC | 1 | TRUE | TRUE | FALSE
4710 | MRT-YT01-P3MKA-240001 | 2018-07-27 | MRT-DS-REC-TT-180468-FC | FC | 1 | TRUE | TRUE | FALSE
4711 | MRT-YD06-P2ZEN-163106 | 2018-07-27 | MRT-DS-REC-TT-180469-FC | FC | 1 | TRUE | TRUE | FALSE
4712 | MRT-YE03-P2ZEN-163104 | 2018-07-27 | MRT-DS-REC-TT-180469-FC | FC | 1 | TRUE | TRUE | FALSE
4713 | MRT-YT01-P2LCB-127035 | 2018-07-27 | MRT-DS-REC-TT-180470-FC | FC | 0 | TRUE | TRUE | FALSE
4714 | MRT-YT01-P3LCB-127035 | 2018-07-27 | MRT-DS-REC-TT-180470-FC | FC | 0 | TRUE | TRUE | FALSE
4715 | MRT-YL00-P2SCA-127520 | 2018-07-27 | MRT-DS-REC-TT-180471-FC | FC | 0 | TRUE | TRUE | FALSE
4716 | MRT-YL00-P3SCA-127520 | 2018-07-27 | MRT-DS-REC-TT-180471-FC | FC | 0 | TRUE | TRUE | FALSE
4717 | MRT-CV03-P2ZEN-165201 | 2018-07-27 | MRT-DS-REC-TT-180473-FC | FC | 3 | TRUE | TRUE | FALSE
4718 | MRT-CV03-P3ZEN-165201 | 2018-07-27 | MRT-DS-REC-TT-180473-FC | FC | 3 | TRUE | TRUE | FALSE
4719 | MRT-VN02-P2LB-122089 | 2018-07-27 | MRT-DS-REC-TT-180485-FC | FC | 1 | TRUE | TRUE | FALSE
4720 | MRT-VN02-P3LB-122089 | 2018-07-27 | MRT-DS-REC-TT-180485-FC | FC | 1 | TRUE | TRUE | FALSE
4721 | MRT-YD00-P2LB-122050 | 2018-07-27 | MRT-DS-REC-TT-180485-FC | FC | 1 | TRUE | TRUE | FALSE
4722 | MRT-YD00-P2LB-122052 | 2018-07-27 | MRT-DS-REC-TT-180485-FC | FC | 1 | TRUE | TRUE | FALSE
4723 | MRT-YD00-P2LB-122053 | 2018-07-27 | MRT-DS-REC-TT-180485-FC | FC | 1 | TRUE | TRUE | FALSE
4724 | MRT-YD00-P3LB-122050 | 2018-07-27 | MRT-DS-REC-TT-180485-FC | FC | 1 | TRUE | TRUE | FALSE
4725 | MRT-YD00-P3LB-122052 | 2018-07-27 | MRT-DS-REC-TT-180485-FC | FC | 1 | TRUE | TRUE | FALSE
4726 | MRT-YD00-P3LB-122053 | 2018-07-27 | MRT-DS-REC-TT-180485-FC | FC | 1 | TRUE | TRUE | FALSE
4727 | MRT-YT01-P2LB-122051 | 2018-07-27 | MRT-DS-REC-TT-180485-FC | FC | 1 | TRUE | TRUE | FALSE
4728 | MRT-YT01-P3LB-122051 | 2018-07-27 | MRT-DS-REC-TT-180485-FC | FC | 1 | TRUE | TRUE | FALSE
4729 | MRT-XG01-P2LB-122021 | 2018-07-27 | MRT-DS-REC-TT-180487-FC | FC | 0 | TRUE | TRUE | FALSE
4730 | MRT-YD00-P2QC-130005 | 2018-07-27 | MRT-DS-REC-TT-180489-FC | FC | 1 | TRUE | TRUE | FALSE
4731 | MRT-YD00-P3QC-130005 | 2018-07-27 | MRT-DS-REC-TT-180489-FC | FC | 1 | TRUE | TRUE | FALSE
4732 | MRT-CN00-P2ZEN-110100 | 2018-07-27 | MRT-DS-REC-TT-180494-FC | FC | 1 | TRUE | TRUE | FALSE
4733 | MRT-YD00-P2QHE-606003 | 2018-07-27 | MRT-DS-REC-TT-180495-FC | FC | 2 | TRUE | TRUE | FALSE
4734 | MRT-YD00-P3QHE-606003 | 2018-07-27 | MRT-DS-REC-TT-180495-FC | FC | 2 | TRUE | TRUE | FALSE
4735 | MRT-YD00-P0ERB-606001 | 2018-07-27 | MRT-DS-REC-TT-180496-FC | FC | 2 | TRUE | TRUE | FALSE
4736 | MRT-YD00-P0ERB-606002 | 2018-07-27 | MRT-DS-REC-TT-180496-FC | FC | 2 | TRUE | TRUE | FALSE
4737 | MRT-YF02-P2QU-130027 | 2018-07-27 | MRT-DS-REC-TT-180499-FC | FC | 2 | TRUE | TRUE | FALSE
4738 | MRT-YF02-P3QU-130027 | 2018-07-27 | MRT-DS-REC-TT-180499-FC | FC | 2 | TRUE | TRUE | FALSE
4739 | MRT-YK08-P2MAG-601001 | 2018-07-27 | MRT-DS-REC-TT-180500-FC | FC | 4 | TRUE | TRUE | FALSE
4740 | MRT-YK08-P3MAG-602001 | 2018-07-27 | MRT-DS-REC-TT-180500-FC | FC | 4 | TRUE | TRUE | FALSE
4741 | MRT-XL00-P2MAG-601003 | 2018-07-27 | MRT-DS-REC-TT-180501-FC | FC | 4 | TRUE | TRUE | FALSE
4742 | MRT-XL00-P2MAG-601004 | 2018-07-27 | MRT-DS-REC-TT-180501-FC | FC | 3 | TRUE | TRUE | FALSE
4743 | MRT-XL00-P3MAG-602003 | 2018-07-27 | MRT-DS-REC-TT-180501-FC | FC | 4 | TRUE | TRUE | FALSE
4744 | MRT-XL00-P3MAG-602004 | 2018-07-27 | MRT-DS-REC-TT-180501-FC | FC | 3 | TRUE | TRUE | FALSE
4745 | MRT-YT01-P2MAJ-603110 | 2018-07-27 | MRT-DS-REC-TT-180505-FC | FC | 2 | TRUE | TRUE | FALSE
4746 | MRT-YT01-P3MAJ-604110 | 2018-07-27 | MRT-DS-REC-TT-180505-FC | FC | 2 | TRUE | TRUE | FALSE
4747 | MRT-YK08-P2LAA-605102 | 2018-07-27 | MRT-DS-REC-TT-180514-FC | FC | 4 | TRUE | TRUE | FALSE
4748 | MRT-YK08-P3LAA-605502 | 2018-07-27 | MRT-DS-REC-TT-180514-FC | FC | 4 | TRUE | TRUE | FALSE
4749 | MRT-XH01-P2MKJ-220001 | 2018-07-27 | MRT-DS-REC-TT-180516-FC | FC | 1 | TRUE | TRUE | FALSE
4750 | MRT-YD00-P2GM-128501 | 2018-07-27 | MRT-DS-REC-TT-180517-FC | FC | 1 | TRUE | TRUE | FALSE
4751 | MRT-YD00-P3GM-128501 | 2018-07-27 | MRT-DS-REC-TT-180517-FC | FC | 1 | TRUE | TRUE | FALSE
4752 | MRT-XK00-P2MKJ-220001 | 2018-07-27 | MRT-DS-REC-TT-180521-FC | FC | 1 | TRUE | TRUE | FALSE
4753 | MRT-YT01-P2LAC-126005 | 2018-07-27 | MRT-DS-REC-TT-180525-FC | FC | 3 | TRUE | TRUE | FALSE
4754 | MRT-YT01-P3LAC-126005 | 2018-07-27 | MRT-DS-REC-TT-180525-FC | FC | 3 | TRUE | TRUE | FALSE
4755 | MRT-YK00-P2QC-130022 | 2018-07-27 | MRT-DS-REC-TT-180526-FC | FC | 1 | TRUE | TRUE | FALSE
4756 | MRT-YK00-P3QC-130022 | 2018-07-27 | MRT-DS-REC-TT-180526-FC | FC | 1 | TRUE | TRUE | FALSE
4757 | MRT-CC02-P2UHA-170103 | 2018-07-27 | MRT-DS-REC-TT-180527-FC | FC | 5 | TRUE | TRUE | FALSE
4758 | MRT-CC02-P3UHA-170103 | 2018-07-27 | MRT-DS-REC-TT-180527-FC | FC | 5 | TRUE | TRUE | FALSE
4759 | MRT-VK02-P2UHA-170106 | 2018-07-27 | MRT-DS-REC-TT-180527-FC | FC | 5 | TRUE | TRUE | FALSE
4760 | MRT-VK02-P3UHA-170106 | 2018-07-27 | MRT-DS-REC-TT-180527-FC | FC | 5 | TRUE | TRUE | FALSE
4761 | MRT-MA02-P2ZEN-163105 | 2018-07-27 | MRT-DS-REC-TT-180528-FC | FC | 1 | TRUE | TRUE | FALSE
4762 | MRT-MA02-P3ZEN-163105 | 2018-07-27 | MRT-DS-REC-TT-180528-FC | FC | 1 | TRUE | TRUE | FALSE
4763 | MRT-YE03-P3ZEN-163104 | 2018-07-27 | MRT-DS-REC-TT-180528-FC | FC | 1 | TRUE | TRUE | FALSE
4764 | MRT-YE00-P2QC-130021 | 2018-07-27 | MRT-DS-REC-TT-180529-FC | FC | 1 | TRUE | TRUE | FALSE
4765 | MRT-YE00-P3QC-130021 | 2018-07-27 | MRT-DS-REC-TT-180529-FC | FC | 1 | TRUE | TRUE | FALSE
4766 | MRT-XH01-P2QC-130011 | 2018-07-27 | MRT-DS-REC-TT-180530-FC | FC | 1 | TRUE | TRUE | FALSE
4767 | MRT-XH01-P3QC-130011 | 2018-07-27 | MRT-DS-REC-TT-180530-FC | FC | 1 | TRUE | TRUE | FALSE
4768 | MRT-YK10-P2QC-130010 | 2018-07-27 | MRT-DS-REC-TT-180531-FC | FC | 1 | TRUE | TRUE | FALSE
4769 | MRT-YK10-P3QC-130010 | 2018-07-27 | MRT-DS-REC-TT-180531-FC | FC | 1 | TRUE | TRUE | FALSE
4770 | MRT-XG02-P0QJA-110010 | 2018-07-27 | MRT-DS-REC-TT-180533-FC | FC | 4 | TRUE | TRUE | FALSE
4771 | MRT-XG02-P2LCM-110005 | 2018-07-27 | MRT-DS-REC-TT-180533-FC | FC | 6 | TRUE | TRUE | FALSE
4772 | MRT-XG02-P3LCM-110005 | 2018-07-27 | MRT-DS-REC-TT-180533-FC | FC | 6 | TRUE | TRUE | FALSE
4773 | MRT-YS01-P2MKC-230012 | 2018-07-27 | MRT-DS-REC-TT-180534-FC | FC | 1 | TRUE | TRUE | FALSE
4774 | MRT-YS01-P3MKC-230012 | 2018-07-27 | MRT-DS-REC-TT-180534-FC | FC | 1 | TRUE | TRUE | FALSE
4775 | MRT-YR05-P0ZEN-163115 | 2018-07-27 | MRT-DS-REC-TT-180535-FC | FC | 0 | TRUE | TRUE | FALSE
4776 | MRT-YK08-P2LBG-111300 | 2018-07-27 | MRT-DS-REC-TT-180536-FC | FC | 1 | TRUE | TRUE | FALSE
4777 | MRT-YK08-P3LBG-111300 | 2018-07-27 | MRT-DS-REC-TT-180536-FC | FC | 1 | TRUE | TRUE | FALSE
4778 | MRT-YT01-P2LBG-111301 | 2018-07-27 | MRT-DS-REC-TT-180536-FC | FC | 1 | TRUE | TRUE | FALSE
4779 | MRT-YT01-P3LBG-111301 | 2018-07-27 | MRT-DS-REC-TT-180536-FC | FC | 1 | TRUE | TRUE | FALSE
4780 | MRT-YK08-P2MAJ-603203 | 2018-07-27 | MRT-DS-REC-TT-180537-FC | FC | 2 | TRUE | TRUE | FALSE
4781 | MRT-YK08-P3MAJ-604203 | 2018-07-27 | MRT-DS-REC-TT-180537-FC | FC | 2 | TRUE | TRUE | FALSE
4782 | MRT-YD00-P3MKW-220001 | 2018-07-27 | MRT-DS-REC-TT-180539-FC | FC | 1 | TRUE | TRUE | FALSE
4783 | MRT-YD00-P3MKW-220005 | 2018-07-27 | MRT-DS-REC-TT-180539-FC | FC | 1 | TRUE | TRUE | FALSE
4784 | MRT-XH01-P2LB-122025 | 2018-07-27 | MRT-DS-REC-TT-180542-FC | FC | 0 | TRUE | TRUE | FALSE
4785 | MRT-XH01-P2LB-122026 | 2018-07-27 | MRT-DS-REC-TT-180542-FC | FC | 0 | TRUE | TRUE | FALSE
4786 | MRT-XH01-P3LB-122025 | 2018-07-27 | MRT-DS-REC-TT-180542-FC | FC | 0 | TRUE | TRUE | FALSE
4787 | MRT-XH01-P3LB-122026 | 2018-07-27 | MRT-DS-REC-TT-180542-FC | FC | 0 | TRUE | TRUE | FALSE
4788 | MRT-YD00-P0QJA-111101 | 2018-07-27 | MRT-DS-REC-TT-180544-FC | FC | 0 | TRUE | TRUE | FALSE
4789 | MRT-YK09-P2MKC-230001 | 2018-07-27 | MRT-DS-REC-TT-180545-FC | FC | 1 | TRUE | TRUE | FALSE
4790 | MRT-YK09-P3MKC-230001 | 2018-07-27 | MRT-DS-REC-TT-180545-FC | FC | 1 | TRUE | TRUE | FALSE
4791 | MRT-XG02-P2LCB-127032 | 2018-07-27 | MRT-DS-REC-TT-180546-FC | FC | 1 | TRUE | TRUE | FALSE
4792 | MRT-XG02-P3LCB-127032 | 2018-07-27 | MRT-DS-REC-TT-180546-FC | FC | 1 | TRUE | TRUE | FALSE
4793 | MRT-XK00-P2GM-128508 | 2018-07-27 | MRT-DS-REC-TT-180547-FC | FC | 3 | TRUE | TRUE | FALSE
4794 | MRT-XK00-P3GM-128508 | 2018-07-27 | MRT-DS-REC-TT-180547-FC | FC | 3 | TRUE | TRUE | FALSE
4795 | MRT-YR05-P2ZEN-163116 | 2018-07-27 | MRT-DS-REC-TT-180553-FC | FC | 0 | TRUE | TRUE | FALSE
4796 | MRT-YR05-P2ZEN-163117 | 2018-07-27 | MRT-DS-REC-TT-180553-FC | FC | 0 | TRUE | TRUE | FALSE
4797 | MRT-CC02-P0UMA-170702 | 2018-07-27 | MRT-DS-REC-TT-180558-FC | FC | 2 | TRUE | TRUE | FALSE
4798 | MRT-CC02-P2UMA-170707 | 2018-07-27 | MRT-DS-REC-TT-180558-FC | FC | 3 | TRUE | TRUE | FALSE
4799 | MRT-CC02-P2UMA-170708 | 2018-07-27 | MRT-DS-REC-TT-180558-FC | FC | 3 | TRUE | TRUE | FALSE
4800 | MRT-CC02-P2UMA-170709 | 2018-07-27 | MRT-DS-REC-TT-180558-FC | FC | 3 | TRUE | TRUE | FALSE
4801 | MRT-CC02-P3UMA-170707 | 2018-07-27 | MRT-DS-REC-TT-180558-FC | FC | 3 | TRUE | TRUE | FALSE
4802 | MRT-CC02-P3UMA-170708 | 2018-07-27 | MRT-DS-REC-TT-180558-FC | FC | 3 | TRUE | TRUE | FALSE
4803 | MRT-CC02-P3UMA-170709 | 2018-07-27 | MRT-DS-REC-TT-180558-FC | FC | 3 | TRUE | TRUE | FALSE
4804 | MRT-VK02-P2UMA-170710 | 2018-07-27 | MRT-DS-REC-TT-180558-FC | FC | 2 | TRUE | TRUE | FALSE
4805 | MRT-VK02-P3UMA-170710 | 2018-07-27 | MRT-DS-REC-TT-180558-FC | FC | 2 | TRUE | TRUE | FALSE
4806 | MRT-DN05-P2LB-122110 | 2018-07-27 | MRT-DS-REC-TT-180561-FC | FC | 0 | TRUE | TRUE | FALSE
4807 | MRT-YD00-P2LB-122108 | 2018-07-27 | MRT-DS-REC-TT-180564-FC | FC | 3 | TRUE | TRUE | FALSE
4808 | MRT-YD00-P3LB-122108 | 2018-07-27 | MRT-DS-REC-TT-180564-FC | FC | 3 | TRUE | TRUE | FALSE
4809 | MRT-YD00-P2SM-128020 | 2018-07-27 | MRT-DS-REC-TT-180568-FC | FC | 1 | TRUE | TRUE | FALSE
4810 | MRT-YD00-P3SM-128020 | 2018-07-27 | MRT-DS-REC-TT-180568-FC | FC | 1 | TRUE | TRUE | FALSE
4811 | MRT-CQ02-P2MAJ-603208 | 2018-07-27 | MRT-DS-REC-TT-180569-FC | FC | 1 | TRUE | TRUE | FALSE
4812 | MRT-CQ02-P3MAJ-604208 | 2018-07-27 | MRT-DS-REC-TT-180569-FC | FC | 1 | TRUE | TRUE | FALSE
4813 | MRT-XL00-P2LB-122030 | 2018-07-27 | MRT-DS-REC-TT-180570-FC | FC | 4 | TRUE | TRUE | FALSE
4814 | MRT-XL00-P3LB-122030 | 2018-07-27 | MRT-DS-REC-TT-180570-FC | FC | 3 | TRUE | TRUE | FALSE
4815 | MRT-YK09-P0SMM-128007 | 2018-07-27 | MRT-DS-REC-TT-180572-FC | FC | 2 | TRUE | TRUE | FALSE
4816 | MRT-YL01-P2ZEN-161051 | 2018-07-27 | MRT-DS-REC-TT-180574-FC | FC | 3 | TRUE | TRUE | FALSE
4817 | MRT-YL01-P3ZEN-161051 | 2018-07-27 | MRT-DS-REC-TT-180574-FC | FC | 3 | TRUE | TRUE | FALSE
4818 | MRT-XF00-P2MKA-230001 | 2018-07-27 | MRT-DS-REC-TT-180575-FC | FC | 0 | TRUE | TRUE | FALSE
4819 | MRT-YK10-P2MKA-230002 | 2018-07-27 | MRT-DS-REC-TT-180575-FC | FC | 0 | TRUE | TRUE | FALSE
4820 | MRT-YK10-P2MKB-230001 | 2018-07-27 | MRT-DS-REC-TT-180575-FC | FC | 0 | TRUE | TRUE | FALSE
4821 | MRT-XG02-P2PAB-113253 | 2018-07-27 | MRT-DS-REC-TT-180576-FC | FC | 3 | TRUE | TRUE | FALSE
4822 | MRT-XG02-P3PAB-113253 | 2018-07-27 | MRT-DS-REC-TT-180576-FC | FC | 3 | TRUE | TRUE | FALSE
4823 | MRT-YD00-P2PAB-113251 | 2018-07-27 | MRT-DS-REC-TT-180576-FC | FC | 3 | TRUE | TRUE | FALSE
4824 | MRT-YD00-P3PAB-113251 | 2018-07-27 | MRT-DS-REC-TT-180576-FC | FC | 3 | TRUE | TRUE | FALSE
4825 | MRT-YT01-P2PAB-113252 | 2018-07-27 | MRT-DS-REC-TT-180576-FC | FC | 3 | TRUE | TRUE | FALSE
4826 | MRT-YT01-P3PAB-113252 | 2018-07-27 | MRT-DS-REC-TT-180576-FC | FC | 3 | TRUE | TRUE | FALSE
4827 | MRT-YD00-P2PGB-113101 | 2018-07-27 | MRT-DS-REC-TT-180577-FC | FC | 2 | TRUE | TRUE | FALSE
4828 | MRT-YD00-P3PGB-113101 | 2018-07-27 | MRT-DS-REC-TT-180577-FC | FC | 2 | TRUE | TRUE | FALSE
4829 | MRT-YD00-P2PGB-113105 | 2018-07-27 | MRT-DS-REC-TT-180578-FC | FC | 2 | TRUE | TRUE | FALSE
4830 | MRT-YD00-P3PGB-113105 | 2018-07-27 | MRT-DS-REC-TT-180578-FC | FC | 2 | TRUE | TRUE | FALSE
4831 | MRT-YD16-P2SCA-127531 | 2018-07-27 | MRT-DS-REC-TT-180579-FC | FC | 2 | TRUE | TRUE | FALSE
4832 | MRT-YD16-P3SCA-127531 | 2018-07-27 | MRT-DS-REC-TT-180579-FC | FC | 2 | TRUE | TRUE | FALSE
4833 | MRT-XA00-P2QU-130025 | 2018-07-27 | MRT-DS-REC-TT-180580-FC | FC | 3 | TRUE | TRUE | FALSE
4834 | MRT-XA00-P3QU-130025 | 2018-07-27 | MRT-DS-REC-TT-180580-FC | FC | 3 | TRUE | TRUE | FALSE
4835 | MRT-CQ02-P2GHC-129016 | 2018-07-27 | MRT-DS-REC-TT-180587-FC | FC | 0 | TRUE | TRUE | FALSE
4836 | MRT-CQ02-P3GHC-129016 | 2018-07-27 | MRT-DS-REC-TT-180587-FC | FC | 0 | TRUE | TRUE | FALSE
4837 | MRT-YL00-P2MAJ-603207 | 2018-07-27 | MRT-DS-REC-TT-180590-FC | FC | 3 | TRUE | TRUE | FALSE
4838 | MRT-YL00-P3MAJ-604207 | 2018-07-27 | MRT-DS-REC-TT-180590-FC | FC | 3 | TRUE | TRUE | FALSE
4839 | MRT-XG02-P2MKJ-210001 | 2018-07-27 | MRT-DS-REC-TT-180591-FC | FC | 1 | TRUE | TRUE | FALSE
4840 | MRT-XG02-P3MKG-210001 | 2018-07-27 | MRT-DS-REC-TT-180591-FC | FC | 1 | TRUE | TRUE | FALSE
4841 | MRT-XG02-P3MKW-210001 | 2018-07-27 | MRT-DS-REC-TT-180591-FC | FC | 1 | TRUE | TRUE | FALSE
4842 | MRT-XS00-P3MKG-210001 | 2018-07-27 | MRT-DS-REC-TT-180591-FC | FC | 1 | TRUE | TRUE | FALSE
4843 | MRT-XS00-P3MKW-210001 | 2018-07-27 | MRT-DS-REC-TT-180591-FC | FC | 1 | TRUE | TRUE | FALSE
4844 | MRT-YT01-P2MAJ-603100 | 2018-07-27 | MRT-DS-REC-TT-180593-FC | FC | 3 | TRUE | TRUE | FALSE
4845 | MRT-YT01-P2MAJ-603103 | 2018-07-27 | MRT-DS-REC-TT-180593-FC | FC | 3 | TRUE | TRUE | FALSE
4846 | MRT-YT01-P3MAJ-604100 | 2018-07-27 | MRT-DS-REC-TT-180593-FC | FC | 3 | TRUE | TRUE | FALSE
4847 | MRT-YT01-P3MAJ-604103 | 2018-07-27 | MRT-DS-REC-TT-180593-FC | FC | 3 | TRUE | TRUE | FALSE
4848 | MRT-VN03-P2LB-122015 | 2018-07-27 | MRT-DS-REC-TT-180594-FC | FC | 2 | TRUE | TRUE | FALSE
4849 | MRT-VN03-P3LB-122015 | 2018-07-27 | MRT-DS-REC-TT-180594-FC | FC | 2 | TRUE | TRUE | FALSE
4850 | MRT-XF00-P3MKA-220001 | 2018-07-27 | MRT-DS-REC-TT-180596-FC | FC | 0 | TRUE | TRUE | FALSE
4851 | MRT-YK10-P3MKA-230002 | 2018-07-27 | MRT-DS-REC-TT-180596-FC | FC | 0 | TRUE | TRUE | FALSE
4852 | MRT-YK10-P3MKB-230001 | 2018-07-27 | MRT-DS-REC-TT-180596-FC | FC | 0 | TRUE | TRUE | FALSE
4853 | MRT-CQ02-P2LAA-605103 | 2018-07-27 | MRT-DS-REC-TT-180598-FC | FC | 0 | TRUE | TRUE | FALSE
4854 | MRT-CQ02-P3LAA-605503 | 2018-07-27 | MRT-DS-REC-TT-180598-FC | FC | 0 | TRUE | TRUE | FALSE
5453 | MRT-YD06-P2ZEN-161014 | 2018-07-27 | MRT-DS-REC-TT-180103-FC | FC | 1 | TRUE | TRUE | FALSE
5454 | MRT-YD06-P3ZEN-161014 | 2018-07-27 | MRT-DS-REC-TT-180103-FC | FC | 1 | TRUE | TRUE | FALSE
5455 | MRT-YK01-P2LB-122074 | 2018-07-27 | MRT-DS-REC-TT-180134-FC | FC | 0 | TRUE | TRUE | FALSE
5456 | MRT-YK01-P3LB-122074 | 2018-07-27 | MRT-DS-REC-TT-180134-FC | FC | 0 | TRUE | TRUE | FALSE
5457 | MRT-CC07-P2UHA-170001 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 3 | TRUE | TRUE | FALSE
5458 | MRT-CC02-P2UHA-170003 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 4 | TRUE | TRUE | FALSE
5459 | MRT-CC02-P2UHA-170004 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 4 | TRUE | TRUE | FALSE
5460 | MRT-CC07-P3UHA-170001 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 3 | TRUE | TRUE | FALSE
5461 | MRT-CC02-P3UHA-170003 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 4 | TRUE | TRUE | FALSE
5462 | MRT-CC02-P3UHA-170004 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 4 | TRUE | TRUE | FALSE
5463 | MRT-CC02-P0UHA-170002 | 2018-07-27 | MRT-DS-REC-TT-180202-FC | FC | 4 | TRUE | TRUE | FALSE
5464 | MRT-XJ00-P2LB-122027 | 2018-07-27 | MRT-DS-REC-TT-180208-FC | FC | 0 | TRUE | TRUE | FALSE
5465 | MRT-XJ00-P3LB-122027 | 2018-07-27 | MRT-DS-REC-TT-180208-FC | FC | 0 | TRUE | TRUE | FALSE
5466 | MRT-CC07-P2UMA-170601 | 2018-07-27 | MRT-DS-REC-TT-180221-FC | FC | 2 | TRUE | TRUE | FALSE
5467 | MRT-CC02-P2UMA-170603 | 2018-07-27 | MRT-DS-REC-TT-180221-FC | FC | 2 | TRUE | TRUE | FALSE
5468 | MRT-CC07-P3UMA-170601 | 2018-07-27 | MRT-DS-REC-TT-180221-FC | FC | 2 | TRUE | TRUE | FALSE
5469 | MRT-CC02-P3UMA-170603 | 2018-07-27 | MRT-DS-REC-TT-180221-FC | FC | 2 | TRUE | TRUE | FALSE
5470 | MRT-YK10-P2MKA-230003 | 2018-07-27 | MRT-DS-REC-TT-180227-FC | FC | 0 | TRUE | TRUE | FALSE
5471 | MRT-YK10-P2MKA-230004 | 2018-07-27 | MRT-DS-REC-TT-180227-FC | FC | 0 | TRUE | TRUE | FALSE
5472 | MRT-YK10-P3MKA-230003 | 2018-07-27 | MRT-DS-REC-TT-180351-FC | FC | 0 | TRUE | TRUE | FALSE
5473 | MRT-YK10-P3MKA-230004 | 2018-07-27 | MRT-DS-REC-TT-180351-FC | FC | 0 | TRUE | TRUE | FALSE
5474 | MRT-YK00-P3BAT-240001 | 2018-07-27 | MRT-DS-REC-TT-180352-FC | FC | 0 | TRUE | TRUE | FALSE
5475 | MRT-YD00-P0SMM-128001 | 2018-07-27 | MRT-DS-REC-TT-180358-FC | FC | 3 | TRUE | TRUE | FALSE
5476 | MRT-YF00-P2MKC-230011 | 2018-07-27 | MRT-DS-REC-TT-180360-FC | FC | 0 | TRUE | TRUE | FALSE
5477 | MRT-YS01-P2MKC-230013 | 2018-07-27 | MRT-DS-REC-TT-180360-FC | FC | 0 | TRUE | TRUE | FALSE
5478 | MRT-YF00-P3MKC-230011 | 2018-07-27 | MRT-DS-REC-TT-180360-FC | FC | 0 | TRUE | TRUE | FALSE
5479 | MRT-YS01-P3MKC-230013 | 2018-07-27 | MRT-DS-REC-TT-180360-FC | FC | 0 | TRUE | TRUE | FALSE
5480 | MRT-XW03-P3MKA-210001 | 2018-07-27 | MRT-DS-REC-TT-180363-FC | FC | 0 | TRUE | TRUE | FALSE
5481 | MRT-CC07-P2UMA-170801 | 2018-07-27 | MRT-DS-REC-TT-180367-FC | FC | 2 | TRUE | TRUE | FALSE
5482 | MRT-CC02-P2UMA-170803 | 2018-07-27 | MRT-DS-REC-TT-180367-FC | FC | 2 | TRUE | TRUE | FALSE
5483 | MRT-VK02-P2UMA-170806 | 2018-07-27 | MRT-DS-REC-TT-180367-FC | FC | 2 | TRUE | TRUE | FALSE
5484 | MRT-CC07-P3UMA-170801 | 2018-07-27 | MRT-DS-REC-TT-180367-FC | FC | 2 | TRUE | TRUE | FALSE
5485 | MRT-CC02-P3UMA-170803 | 2018-07-27 | MRT-DS-REC-TT-180367-FC | FC | 2 | TRUE | TRUE | FALSE
5486 | MRT-VK02-P3UMA-170806 | 2018-07-27 | MRT-DS-REC-TT-180367-FC | FC | 2 | TRUE | TRUE | FALSE
5487 | MRT-YD00-P2MKA-220003 | 2018-07-27 | MRT-DS-REC-TT-180368-FC | FC | 3 | TRUE | TRUE | FALSE
5488 | MRT-YK08-P2ZEN-111200 | 2018-07-27 | MRT-DS-REC-TT-180370-FC | FC | 1 | TRUE | TRUE | FALSE
5489 | MRT-YT01-P2ZEN-111201 | 2018-07-27 | MRT-DS-REC-TT-180370-FC | FC | 1 | TRUE | TRUE | FALSE
5490 | MRT-YK08-P3ZEN-111200 | 2018-07-27 | MRT-DS-REC-TT-180370-FC | FC | 1 | TRUE | TRUE | FALSE
5491 | MRT-YT01-P3ZEN-111201 | 2018-07-27 | MRT-DS-REC-TT-180370-FC | FC | 1 | TRUE | TRUE | FALSE
5492 | MRT-YD00-P2LAC-126007 | 2018-07-27 | MRT-DS-REC-TT-180378-FC | FC | 1 | TRUE | TRUE | FALSE
5493 | MRT-YD00-P2LAC-126057 | 2018-07-27 | MRT-DS-REC-TT-180378-FC | FC | 1 | TRUE | TRUE | FALSE
5494 | MRT-YD00-P3LAC-126057 | 2018-07-27 | MRT-DS-REC-TT-180378-FC | FC | 1 | TRUE | TRUE | FALSE
5495 | MRT-YK01-P2LAC-126006 | 2018-07-27 | MRT-DS-REC-TT-180380-FC | FC | 1 | TRUE | TRUE | FALSE
5496 | MRT-YK01-P3LAC-126006 | 2018-07-27 | MRT-DS-REC-TT-180380-FC | FC | 1 | TRUE | TRUE | FALSE
5497 | MRT-YK01-P2LAC-126056 | 2018-07-27 | MRT-DS-REC-TT-180380-FC | FC | 1 | TRUE | TRUE | FALSE
5498 | MRT-YK01-P3LAC-126056 | 2018-07-27 | MRT-DS-REC-TT-180380-FC | FC | 1 | TRUE | TRUE | FALSE
5499 | MRT-YT01-P2LAA-605101 | 2018-07-27 | MRT-DS-REC-TT-180383-FC | FC | 4 | TRUE | TRUE | FALSE
5500 | MRT-YT01-P3LAA-605501 | 2018-07-27 | MRT-DS-REC-TT-180383-FC | FC | 4 | TRUE | TRUE | FALSE
5501 | MRT-YK08-P2LAA-605100 | 2018-07-27 | MRT-DS-REC-TT-180384-FC | FC | 4 | TRUE | TRUE | FALSE
5502 | MRT-YK08-P3LAA-605500 | 2018-07-27 | MRT-DS-REC-TT-180384-FC | FC | 4 | TRUE | TRUE | FALSE
3879 | MRT-UE00-P2ZEN-100004 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 4 | TRUE | TRUE | FALSE
3880 | MRT-UE00-P2ZEN-100005 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 4 | TRUE | TRUE | FALSE
3881 | MRT-UE00-P2ZEN-100006 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 4 | TRUE | TRUE | FALSE
3882 | MRT-UE00-P2ZEN-100007 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 4 | TRUE | TRUE | FALSE
3883 | MRT-UE00-P2ZEN-100008 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 4 | TRUE | TRUE | FALSE
3884 | MRT-UE00-P2ZEN-100009 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 4 | TRUE | TRUE | FALSE
3885 | MRT-UE00-P3ZEN-100010 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 4 | TRUE | TRUE | FALSE
3886 | MRT-UE00-P3ZEN-100011 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 4 | TRUE | TRUE | FALSE
3887 | MRT-UE00-P3ZEN-100012 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 4 | TRUE | TRUE | FALSE
3888 | MRT-UE00-P3ZEN-100013 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 4 | TRUE | TRUE | FALSE
3889 | MRT-UE00-P3ZEN-100014 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 4 | TRUE | TRUE | FALSE
3890 | MRT-UE00-P3ZEN-100015 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 4 | TRUE | TRUE | FALSE
3891 | MRT-UE00-P2ZEN-100016 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 2 | TRUE | TRUE | FALSE
3892 | MRT-UE00-P3ZEN-100017 | 2018-07-28 | MRT-DS-REC-TT-180674 | FC | 2 | TRUE | TRUE | FALSE
3893 | MRT-YD02-P2LB-122063 | 2018-07-28 | MRT-DS-REC-TT-180686 | FI | 0 | TRUE | FALSE | FALSE
3894 | MRT-YD02-P3LB-122063 | 2018-07-28 | MRT-DS-REC-TT-180686 | FI | 0 | TRUE | FALSE | FALSE
3895 | MRT-XS00-P2LB-122037 | 2018-07-28 | MRT-DS-REC-TT-180687 | FI | 2 | TRUE | TRUE | FALSE
3896 | MRT-YD00-P2LB-122055 | 2018-07-28 | MRT-DS-REC-TT-180687 | FI | 1 | TRUE | TRUE | FALSE
3897 | MRT-XS00-P3LB-122037 | 2018-07-28 | MRT-DS-REC-TT-180687 | FI | 1 | TRUE | TRUE | FALSE
3898 | MRT-YD00-P3LB-122055 | 2018-07-28 | MRT-DS-REC-TT-180687 | FI | 1 | TRUE | TRUE | FALSE
4916 | MRT-XA01-P0ABA-150512 | 2018-08-01 | MRT-HK-REC-TT-180183 | FA | 0 | TRUE | FALSE | FALSE
4917 | MRT-XA01-P0ABA-150511 | 2018-08-01 | MRT-HK-REC-TT-180183 | FA | 0 | TRUE | FALSE | FALSE
4270 | MRT-CC07-P0UBX-176001 | 2018-08-04 | MRT-HK-REC-TT-180187 | FA | 2 | TRUE | TRUE | FALSE
4271 | MRT-CC02-P0UBX-176005 | 2018-08-04 | MRT-HK-REC-TT-180187 | FA | 3 | TRUE | TRUE | FALSE
4272 | MRT-CC07-P0UBX-176015 | 2018-08-04 | MRT-HK-REC-TT-180187 | FA | 1 | TRUE | TRUE | FALSE
4273 | MRT-CC02-P0UBX-176020 | 2018-08-04 | MRT-HK-REC-TT-180187 | FA | 1 | TRUE | TRUE | FALSE
4274 | MRT-CC02-P0UBX-176025 | 2018-08-04 | MRT-HK-REC-TT-180187 | FA | 1 | TRUE | TRUE | FALSE
4275 | MRT-CC02-P0UBX-176030 | 2018-08-04 | MRT-HK-REC-TT-180187 | FA | 1 | TRUE | TRUE | FALSE
4276 | MRT-CC02-P0UBX-176006 | 2018-08-04 | MRT-HK-REC-TT-180187 | FA | 3 | TRUE | TRUE | FALSE
4277 | MRT-CC02-P0UBX-176007 | 2018-08-04 | MRT-HK-REC-TT-180187 | FA | 3 | TRUE | TRUE | FALSE
4278 | MRT-CC02-P0UBX-176035 | 2018-08-04 | MRT-HK-REC-TT-180187 | FA | 1 | TRUE | TRUE | FALSE
4279 | MRT-CC02-P0UBX-176036 | 2018-08-04 | MRT-HK-REC-TT-180187 | FA | 1 | TRUE | TRUE | FALSE
3899 | MRT-CA00-P0UCA-180105 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 3 | TRUE | TRUE | FALSE
3900 | MRT-CA00-P0UCA-180107 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 3 | TRUE | TRUE | FALSE
3901 | MRT-CA00-P0UCA-180108 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 3 | TRUE | TRUE | FALSE
3902 | MRT-CA00-P0UCA-180112 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 3 | TRUE | TRUE | FALSE
3903 | MRT-CA00-P0UCA-180113 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 3 | TRUE | TRUE | FALSE
3904 | MRT-CA00-P0UCA-180119 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 1 | TRUE | TRUE | FALSE
3905 | MRT-CA00-P0UCA-180120 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 1 | TRUE | TRUE | FALSE
3906 | MRT-CA01-P0UCA-180122 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 3 | TRUE | TRUE | FALSE
3907 | MRT-CA01-P0UCA-180123 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 3 | TRUE | TRUE | FALSE
3908 | MRT-CA01-P0UCA-180127 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 3 | TRUE | TRUE | FALSE
3909 | MRT-CA01-P0UCA-180128 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 3 | TRUE | TRUE | FALSE
3910 | MRT-CA02-P0UCA-180134 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 3 | TRUE | TRUE | FALSE
3911 | MRT-CA02-P0UCA-180135 | 2018-08-06 | MRT-DS-REC-TT-180565-FC | FC | 3 | TRUE | TRUE | FALSE
3912 | MRT-XB00-P2GM-128506 | 2018-08-06 | MRT-DS-REC-TT-180567-FC | FC | 0 | TRUE | TRUE | FALSE
3913 | MRT-XB00-P3GM-128506 | 2018-08-06 | MRT-DS-REC-TT-180567-FC | FC | 0 | TRUE | TRUE | FALSE
3914 | MRT-CA00-P0UMA-180047 | 2018-08-06 | MRT-DS-REC-TT-180606-FC | FC | 2 | TRUE | TRUE | FALSE
3915 | MRT-YV02-P2QU-130032 | 2018-08-06 | MRT-DS-REC-TT-180612-FC | FC | 2 | TRUE | TRUE | FALSE
3916 | MRT-YV02-P3QU-130032 | 2018-08-06 | MRT-DS-REC-TT-180612-FC | FC | 2 | TRUE | TRUE | FALSE
3917 | MRT-YU02-P2SCA-127510 | 2018-08-06 | MRT-DS-REC-TT-180639-FC | FC | 1 | TRUE | TRUE | FALSE
3918 | MRT-YU02-P3SCA-127510 | 2018-08-06 | MRT-DS-REC-TT-180639-FC | FC | 1 | TRUE | TRUE | FALSE
3919 | MRT-XG01-P3LB-122021 | 2018-08-06 | MRT-DS-REC-TT-180622-FC | FC | 0 | TRUE | TRUE | FALSE
3920 | MRT-YS01-P2SCA-127511 | 2018-08-06 | MRT-DS-REC-TT-180640-FC | FC | 1 | TRUE | TRUE | FALSE
3921 | MRT-YS01-P3SCA-127511 | 2018-08-06 | MRT-DS-REC-TT-180640-FC | FC | 1 | TRUE | TRUE | FALSE
3922 | MRT-XW01-P2GM-128507 | 2018-08-06 | MRT-DS-REC-TT-180669-FC | FC | 1 | TRUE | TRUE | FALSE
3923 | MRT-XW01-P3GM-128507 | 2018-08-06 | MRT-DS-REC-TT-180669-FC | FC | 1 | TRUE | TRUE | FALSE
3924 | MRT-YS01-P3MKC-230017 | 2018-08-06 | MRT-DS-REC-TT-180682-FC | FC | 1 | TRUE | TRUE | FALSE
3925 | MRT-YS01-P2MKC-230015 | 2018-08-06 | MRT-DS-REC-TT-180681-FC | FC | 1 | TRUE | TRUE | FALSE
3926 | MRT-YS01-P3MKC-230015 | 2018-08-06 | MRT-DS-REC-TT-180681-FC | FC | 1 | TRUE | TRUE | FALSE
3927 | MRT-YK09-P2MKC-230002 | 2018-08-06 | MRT-DS-REC-TT-180680-FC | FC | 1 | TRUE | TRUE | FALSE
3928 | MRT-YK09-P3MKC-230002 | 2018-08-06 | MRT-DS-REC-TT-180680-FC | FC | 1 | TRUE | TRUE | FALSE
3929 | MRT-YD02-P2LB-122064 | 2018-08-06 | MRT-DS-REC-TT-180665-FC | FC | 1 | TRUE | TRUE | FALSE
3930 | MRT-YD02-P2LB-122065 | 2018-08-06 | MRT-DS-REC-TT-180665-FC | FC | 1 | TRUE | TRUE | FALSE
3931 | MRT-YM03-P2LB-122069 | 2018-08-06 | MRT-DS-REC-TT-180646-FC | FC | 2 | TRUE | TRUE | FALSE
3932 | MRT-YM03-P3LB-122069 | 2018-08-06 | MRT-DS-REC-TT-180646-FC | FC | 2 | TRUE | TRUE | FALSE
3933 | MRT-YD02-P3LB-122065 | 2018-08-06 | MRT-DS-REC-TT-180623-FC | FC | 0 | TRUE | TRUE | FALSE
3934 | MRT-YK09-P2MKC-230006 | 2018-08-06 | MRT-DS-REC-TT-180644-FC | FC | 1 | TRUE | TRUE | FALSE
3935 | MRT-YK09-P3MKC-230006 | 2018-08-06 | MRT-DS-REC-TT-180644-FC | FC | 1 | TRUE | TRUE | FALSE
3936 | MRT-YT01-P3LB-122093 | 2018-08-06 | MRT-DS-REC-TT-180645-FC | FC | 1 | TRUE | TRUE | FALSE
3937 | MRT-YD00-P2LAC-126017 | 2018-08-06 | MRT-DS-REC-TT-180676-FC | FC | 1 | TRUE | TRUE | FALSE
3938 | MRT-YD00-P2LAC-126065 | 2018-08-06 | MRT-DS-REC-TT-180676-FC | FC | 1 | TRUE | TRUE | FALSE
3939 | MRT-YD00-P3LAC-126065 | 2018-08-06 | MRT-DS-REC-TT-180676-FC | FC | 1 | TRUE | TRUE | FALSE
3940 | MRT-YD00-P3LAC-126017 | 2018-08-06 | MRT-DS-REC-TT-180676-FC | FC | 1 | TRUE | TRUE | FALSE
3941 | MRT-XG02-P2LCB-127032 | 2018-08-06 | MRT-DS-REC-TT-180685-FC | FC | 2 | TRUE | TRUE | FALSE
3942 | MRT-XG02-P3LCB-127032 | 2018-08-06 | MRT-DS-REC-TT-180685-FC | FC | 2 | TRUE | TRUE | FALSE
3943 | MRT-CQ02-P2LCB-127043 | 2018-08-06 | MRT-DS-REC-TT-180637-FC | FC | 0 | TRUE | TRUE | FALSE
3944 | MRT-CQ02-P3LCB-127043 | 2018-08-06 | MRT-DS-REC-TT-180637-FC | FC | 0 | TRUE | TRUE | FALSE
3945 | MRT-CQ02-P2SCA-127529 | 2018-08-06 | MRT-DS-REC-TT-180632-FC | FC | 0 | TRUE | TRUE | FALSE
3946 | MRT-CQ02-P3SCA-127529 | 2018-08-06 | MRT-DS-REC-TT-180632-FC | FC | 0 | TRUE | TRUE | FALSE
3947 | MRT-YD00-P2LB-122055 | 2018-08-06 | MRT-DS-REC-TT-180687-FC | FC | 1 | TRUE | TRUE | FALSE
3948 | MRT-YD00-P3LB-122055 | 2018-08-06 | MRT-DS-REC-TT-180687-FC | FC | 1 | TRUE | TRUE | FALSE
3949 | MRT-YD05-P2SCA-127515 | 2018-08-06 | MRT-DS-REC-TT-180631-FC | FC | 2 | TRUE | TRUE | FALSE
3950 | MRT-YD05-P3SCA-127515 | 2018-08-06 | MRT-DS-REC-TT-180631-FC | FC | 2 | TRUE | TRUE | FALSE
3951 | MRT-YL22-P2LCB-127042 | 2018-08-06 | MRT-DS-REC-TT-180668-FC | FC | 0 | TRUE | TRUE | FALSE
3952 | MRT-YT01-P2LCB-127037 | 2018-08-06 | MRT-DS-REC-TT-180668-FC | FC | 0 | TRUE | TRUE | FALSE
3953 | MRT-YL22-P3LCB-127042 | 2018-08-06 | MRT-DS-REC-TT-180668-FC | FC | 0 | TRUE | TRUE | FALSE
3954 | MRT-YT01-P3LCB-127037 | 2018-08-06 | MRT-DS-REC-TT-180668-FC | FC | 0 | TRUE | TRUE | FALSE
3955 | MRT-YL16-P2LB-122078 | 2018-08-06 | MRT-DS-REC-TT-180671-FC | FC | 1 | TRUE | TRUE | FALSE
3956 | MRT-YL16-P3LB-122078 | 2018-08-06 | MRT-DS-REC-TT-180671-FC | FC | 1 | TRUE | TRUE | FALSE
3957 | MRT-YT01-P2LB-122093 | 2018-08-06 | MRT-DS-REC-TT-180643-FC | FC | 1 | TRUE | TRUE | FALSE
3959 | MRT-CC07-P0UPC-175715 | 2018-08-07 | MRT-HK-REC-TT-180179 | FA | 2 | TRUE | TRUE | FALSE
3960 | MRT-CC03-P0UPC-176350 | 2018-08-07 | MRT-HK-REC-TT-180179 | FA | 0 | TRUE | TRUE | FALSE
3961 | MRT-CC03-P0UPC-176351 | 2018-08-07 | MRT-HK-REC-TT-180179 | FA | 0 | TRUE | TRUE | FALSE
3962 | MRT-CC03-P0UPC-176352 | 2018-08-07 | MRT-HK-REC-TT-180179 | FA | 0 | TRUE | TRUE | FALSE
3963 | MRT-CC03-P0UPC-176360 | 2018-08-07 | MRT-HK-REC-TT-180179 | FA | 0 | TRUE | TRUE | FALSE
3964 | MRT-CC03-P0UPC-176361 | 2018-08-07 | MRT-HK-REC-TT-180179 | FA | 0 | TRUE | TRUE | FALSE
3965 | MRT-CC03-P0UPC-176362 | 2018-08-07 | MRT-HK-REC-TT-180179 | FA | 0 | TRUE | TRUE | FALSE
3966 | MRT-CC03-P0UPC-176363 | 2018-08-07 | MRT-HK-REC-TT-180179 | FA | 0 | TRUE | TRUE | FALSE
3967 | MRT-CC03-P0UPC-175776 | 2018-08-07 | MRT-HK-REC-TT-180179 | FA | 0 | TRUE | TRUE | FALSE
3968 | MRT-DD04-P3CYP-020001 | 2018-08-07 | MRT-HK-REC-TT-180180 | FA | 0 | TRUE | FALSE | FALSE
3969 | MRT-CA06-P0UGG-187278 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3970 | MRT-CA06-P0UGG-187274 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3971 | MRT-CA03-P0UGG-187294 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3972 | MRT-CA03-P0UGG-187292 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3973 | MRT-CA03-P0UGG-187270 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3974 | MRT-CA03-P0UGG-187268 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3975 | MRT-CA03-P0UGG-187266 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3976 | MRT-CA01-P0UGG-187286 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3977 | MRT-CA01-P0UGG-187262 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3978 | MRT-CA00-P0UGG-187282 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3979 | MRT-CA00-P0UGG-187280 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3980 | MRT-CA06-P0UGG-187251 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3981 | MRT-CA01-P0UGG-187252 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3982 | MRT-CA06-P0UGG-187254 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3983 | MRT-CA00-P0UGG-187256 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3984 | MRT-CA00-P0UGG-187258 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3985 | MRT-CA03-P0UGG-187276 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3986 | MRT-CA03-P0UGG-187290 | 2018-08-07 | MRT-HK-REC-TT-180181 | FA | 0 | TRUE | FALSE | FALSE
3987 | MRT-YD00-P0UCB-150283 | 2018-08-07 | MRT-HK-REC-TT-180182 | FA | 0 | TRUE | FALSE | FALSE
3988 | MRT-YU02-P2BJA-150041 | 2018-08-07 | MRT-HK-REC-TT-180182 | FA | 1 | TRUE | TRUE | FALSE
3989 | MRT-YS05-P0UZT-150176 | 2018-08-07 | MRT-HK-REC-TT-180182 | FA | 0 | TRUE | FALSE | FALSE
3990 | MRT-YT01-P3ASQ-150854 | 2018-08-07 | MRT-HK-REC-TT-180170 | FA | 0 | TRUE | FALSE | FALSE
3991 | MRT-YS01-P3ASQ-150856 | 2018-08-07 | MRT-HK-REC-TT-180170 | FA | 0 | TRUE | FALSE | FALSE
3992 | MRT-YM02-P3ASQ-150855 | 2018-08-07 | MRT-HK-REC-TT-180170 | FA | 0 | TRUE | FALSE | FALSE
3993 | MRT-US02-P3ASQ-150857 | 2018-08-07 | MRT-HK-REC-TT-180170 | FA | 0 | TRUE | FALSE | FALSE
3994 | MRT-QM03-P0ZEN-145015 | 2018-08-07 | MRT-HK-REC-TT-180184 | FA | 0 | TRUE | FALSE | FALSE
3995 | MRT-QM03-P0ZEN-145011 | 2018-08-07 | MRT-HK-REC-TT-180184 | FA | 0 | TRUE | FALSE | FALSE
3996 | MRT-QM03-P0ZEN-145010 | 2018-08-07 | MRT-HK-REC-TT-180184 | FA | 0 | TRUE | FALSE | FALSE
3997 | MRT-CC03-P0UAA-176080 | 2018-08-07 | MRT-HK-REC-TT-180185 | FA | 0 | TRUE | FALSE | FALSE
3998 | MRT-CC02-P0UAA-176077 | 2018-08-07 | MRT-HK-REC-TT-180185 | FA | 0 | TRUE | FALSE | FALSE
3999 | MRT-CC02-P0UAA-176076 | 2018-08-07 | MRT-HK-REC-TT-180185 | FA | 0 | TRUE | FALSE | FALSE
4000 | MRT-CC02-P0UAA-176074 | 2018-08-07 | MRT-HK-REC-TT-180185 | FA | 0 | TRUE | FALSE | FALSE
4001 | MRT-CC02-P0UAA-176073 | 2018-08-07 | MRT-HK-REC-TT-180185 | FA | 0 | TRUE | FALSE | FALSE
4002 | MRT-CC02-P0UAA-176072 | 2018-08-07 | MRT-HK-REC-TT-180185 | FA | 0 | TRUE | FALSE | FALSE
4003 | MRT-CC02-P0UAA-176071 | 2018-08-07 | MRT-HK-REC-TT-180185 | FA | 0 | TRUE | FALSE | FALSE
4004 | MRT-CC07-P0UAA-176065 | 2018-08-07 | MRT-HK-REC-TT-180185 | FA | 0 | TRUE | FALSE | FALSE
4005 | MRT-CC02-P0UAA-176070 | 2018-08-07 | MRT-HK-REC-TT-180185 | FA | 0 | TRUE | FALSE | FALSE
4006 | MRT-CC02-P0UAA-176075 | 2018-08-07 | MRT-HK-REC-TT-180185 | FA | 0 | TRUE | FALSE | FALSE
4007 | MRT-CC03-P0UAA-176085 | 2018-08-07 | MRT-HK-REC-TT-180185 | FA | 0 | TRUE | FALSE | FALSE
4008 | MRT-CA01-P0UST-186902 | 2018-08-07 | MRT-HK-REC-TT-180188 | FA | 3 | TRUE | TRUE | FALSE
4009 | MRT-CA06-P0UXA-186706 | 2018-08-07 | MRT-HK-REC-TT-180186 | FA | 0 | TRUE | FALSE | FALSE
4010 | MRT-CA01-P0UXA-186719 | 2018-08-07 | MRT-HK-REC-TT-180186 | FA | 0 | TRUE | FALSE | FALSE
4011 | MRT-CA01-P0UXA-186718 | 2018-08-07 | MRT-HK-REC-TT-180186 | FA | 0 | TRUE | FALSE | FALSE
4012 | MRT-CA01-P0UXA-186713 | 2018-08-07 | MRT-HK-REC-TT-180186 | FA | 0 | TRUE | FALSE | FALSE
4013 | MRT-CA01-P0UXA-186710 | 2018-08-07 | MRT-HK-REC-TT-180186 | FA | 0 | TRUE | FALSE | FALSE
4014 | MRT-CA01-P0UXA-186708 | 2018-08-07 | MRT-HK-REC-TT-180186 | FA | 0 | TRUE | FALSE | FALSE
4015 | MRT-CA03-P0UXA-186704 | 2018-08-07 | MRT-HK-REC-TT-180186 | FA | 1 | TRUE | TRUE | FALSE
4016 | MRT-CA06-P0UXA-186702 | 2018-08-07 | MRT-HK-REC-TT-180186 | FA | 1 | TRUE | TRUE | FALSE
4017 | MRT-CA01-P0UXA-186712 | 2018-08-07 | MRT-HK-REC-TT-180186 | FA | 0 | TRUE | FALSE | FALSE
4018 | MRT-CA01-P0UXA-186714 | 2018-08-07 | MRT-HK-REC-TT-180186 | FA | 0 | TRUE | FALSE | FALSE
4019 | MRT-CA01-P0UXA-186716 | 2018-08-07 | MRT-HK-REC-TT-180186 | FA | 0 | TRUE | FALSE | FALSE
4020 | MRT-CA00-P0UMA-180008 | 2018-08-07 | MRT-DS-REC-TT-180688 | FC | 3 | TRUE | TRUE | FALSE
4021 | MRT-CA00-P0UMA-180010 | 2018-08-07 | MRT-DS-REC-TT-180688 | FC | 3 | TRUE | TRUE | FALSE
4022 | MRT-CA00-P0UMA-180011 | 2018-08-07 | MRT-DS-REC-TT-180688 | FC | 3 | TRUE | TRUE | FALSE
4023 | MRT-CA00-P0UMA-180013 | 2018-08-07 | MRT-DS-REC-TT-180688 | FC | 3 | TRUE | TRUE | FALSE
4024 | MRT-CA00-P0UMA-180014 | 2018-08-07 | MRT-DS-REC-TT-180688 | FC | 3 | TRUE | TRUE | FALSE
4025 | MRT-CA03-P0UST-186951 | 2018-08-08 | MRT-HK-REC-TT-180189 | FA | 0 | TRUE | FALSE | FALSE
4026 | MRT-CA03-P0UST-186950 | 2018-08-08 | MRT-HK-REC-TT-180189 | FA | 0 | TRUE | FALSE | FALSE
4027 | MRT-CA03-P0UST-186933 | 2018-08-08 | MRT-HK-REC-TT-180189 | FA | 0 | TRUE | FALSE | FALSE
4028 | MRT-CA03-P0UST-186938 | 2018-08-08 | MRT-HK-REC-TT-180189 | FA | 0 | TRUE | FALSE | FALSE
4029 | MRT-CA02-P0UGX-186984 | 2018-08-08 | MRT-HK-REC-TT-180189 | FA | 0 | TRUE | FALSE | FALSE
4030 | MRT-CA01-P0UPB-187023 | 2018-08-08 | MRT-HK-REC-TT-180189 | FA | 0 | TRUE | FALSE | FALSE
4031 | MRT-YU02-P3BJL-150053 | 2018-08-08 | MRT-HK-REC-TT-180190 | FA | 0 | TRUE | FALSE | FALSE
4032 | MRT-YU02-P0BJN-150056 | 2018-08-08 | MRT-HK-REC-TT-180190 | FA | 0 | TRUE | FALSE | FALSE
4033 | MRT-CA00-P3CYP-160002 | 2018-08-08 | MRT-HK-REC-TT-180191 | FA | 0 | TRUE | FALSE | FALSE
4035 | MRT-YR05-P2SCA-127523 | 2018-08-08 | MRT-DS-REC-TT-180691 | FC | 1 | TRUE | TRUE | FALSE
4036 | MRT-YR05-P3SCA-127523 | 2018-08-08 | MRT-DS-REC-TT-180691 | FC | 1 | TRUE | TRUE | FALSE
4133 | MRT-YD00-P2BBT-150419 | 2018-08-08 | MRT-HK-REC-TT-180192 | FA | 0 | TRUE | FALSE | FALSE
4134 | MRT-YD00-P3BBT-150436 | 2018-08-08 | MRT-HK-REC-TT-180192 | FA | 0 | TRUE | FALSE | FALSE
4135 | MRT-YT01-P2BBT-150417 | 2018-08-08 | MRT-HK-REC-TT-180192 | FA | 0 | TRUE | FALSE | FALSE
4136 | MRT-YT01-P3BBT-150434 | 2018-08-08 | MRT-HK-REC-TT-180192 | FA | 0 | TRUE | FALSE | FALSE
4037 | MRT-CV03-P2ZEN-165104 | 2018-08-09 | MRT-DS-REC-TT-180566-FC | FC | 1 | TRUE | TRUE | FALSE
4038 | MRT-CV03-P3ZEN-165104 | 2018-08-09 | MRT-DS-REC-TT-180566-FC | FC | 1 | TRUE | TRUE | FALSE
4039 | MRT-CC07-P2UMA-170201 | 2018-08-09 | MRT-DS-REC-TT-180636-FC | FC | 2 | TRUE | TRUE | FALSE
4040 | MRT-CC07-P2UMA-170205 | 2018-08-09 | MRT-DS-REC-TT-180636-FC | FC | 2 | TRUE | TRUE | FALSE
4041 | MRT-CC07-P2UMA-170211 | 2018-08-09 | MRT-DS-REC-TT-180636-FC | FC | 2 | TRUE | TRUE | FALSE
4042 | MRT-CC07-P3UMA-170201 | 2018-08-09 | MRT-DS-REC-TT-180636-FC | FC | 2 | TRUE | TRUE | FALSE
4043 | MRT-CC07-P3UMA-170205 | 2018-08-09 | MRT-DS-REC-TT-180636-FC | FC | 2 | TRUE | TRUE | FALSE
4044 | MRT-CC07-P3UMA-170211 | 2018-08-09 | MRT-DS-REC-TT-180636-FC | FC | 2 | TRUE | TRUE | FALSE
4045 | MRT-CA03-P0UCA-180132 | 2018-08-09 | MRT-DS-REC-TT-180629-FC | FC | 3 | TRUE | TRUE | FALSE
4046 | MRT-CA01-P0UCA-180133 | 2018-08-09 | MRT-DS-REC-TT-180629-FC | FC | 3 | TRUE | TRUE | FALSE
4047 | MRT-XB02-P0UMA-180004 | 2018-08-09 | MRT-DS-REC-TT-180648-FC | FC | 6 | TRUE | TRUE | FALSE
4048 | MRT-CA01-P0UMA-180005 | 2018-08-09 | MRT-DS-REC-TT-180648-FC | FC | 5 | TRUE | TRUE | FALSE
4049 | MRT-CA00-P0UCA-180106 | 2018-08-09 | MRT-DS-REC-TT-180649-FC | FC | 3 | TRUE | TRUE | FALSE
4050 | MRT-CA00-P0UCA-180114 | 2018-08-09 | MRT-DS-REC-TT-180649-FC | FC | 3 | TRUE | TRUE | FALSE
4051 | MRT-CA00-P0UCA-180115 | 2018-08-09 | MRT-DS-REC-TT-180649-FC | FC | 3 | TRUE | TRUE | FALSE
4052 | MRT-CA00-P0UCA-180116 | 2018-08-09 | MRT-DS-REC-TT-180649-FC | FC | 3 | TRUE | TRUE | FALSE
4053 | MRT-CA00-P0UCA-180117 | 2018-08-09 | MRT-DS-REC-TT-180649-FC | FC | 3 | TRUE | TRUE | FALSE
4054 | MRT-CA01-P0UCA-180129 | 2018-08-09 | MRT-DS-REC-TT-180649-FC | FC | 2 | TRUE | TRUE | FALSE
4055 | MRT-CC07-P2UEJ-170901 | 2018-08-09 | MRT-DS-REC-TT-180650-FC | FC | 1 | TRUE | TRUE | FALSE
4056 | MRT-CC02-P2UEJ-170907 | 2018-08-09 | MRT-DS-REC-TT-180650-FC | FC | 1 | TRUE | TRUE | FALSE
4057 | MRT-VK02-P2UEJ-170910 | 2018-08-09 | MRT-DS-REC-TT-180650-FC | FC | 1 | TRUE | TRUE | FALSE
4058 | MRT-CC07-P3UEJ-170901 | 2018-08-09 | MRT-DS-REC-TT-180650-FC | FC | 1 | TRUE | TRUE | FALSE
4059 | MRT-CC02-P3UEJ-170907 | 2018-08-09 | MRT-DS-REC-TT-180650-FC | FC | 1 | TRUE | TRUE | FALSE
4060 | MRT-VK02-P3UEJ-170910 | 2018-08-09 | MRT-DS-REC-TT-180650-FC | FC | 1 | TRUE | TRUE | FALSE
4061 | MRT-CA00-P0UMA-180009 | 2018-08-09 | MRT-DS-REC-TT-180654-FC | FC | 3 | TRUE | TRUE | FALSE
4062 | MRT-CA00-P0UMA-180015 | 2018-08-09 | MRT-DS-REC-TT-180654-FC | FC | 3 | TRUE | TRUE | FALSE
4063 | MRT-CA00-P0UMA-180016 | 2018-08-09 | MRT-DS-REC-TT-180654-FC | FC | 3 | TRUE | TRUE | FALSE
4064 | MRT-CA00-P0UMA-180017 | 2018-08-09 | MRT-DS-REC-TT-180654-FC | FC | 3 | TRUE | TRUE | FALSE
4065 | MRT-CA00-P0UMA-180019 | 2018-08-09 | MRT-DS-REC-TT-180654-FC | FC | 3 | TRUE | TRUE | FALSE
4066 | MRT-CA00-P0UMA-180021 | 2018-08-09 | MRT-DS-REC-TT-180654-FC | FC | 3 | TRUE | TRUE | FALSE
4067 | MRT-CA00-P0UMA-180022 | 2018-08-09 | MRT-DS-REC-TT-180654-FC | FC | 3 | TRUE | TRUE | FALSE
4068 | MRT-CC07-P2UAG-170301 | 2018-08-09 | MRT-DS-REC-TT-180660-FC | FC | 1 | TRUE | TRUE | FALSE
4069 | MRT-CC02-P2UAG-170303 | 2018-08-09 | MRT-DS-REC-TT-180660-FC | FC | 1 | TRUE | TRUE | FALSE
4070 | MRT-VK02-P2UAG-170310 | 2018-08-09 | MRT-DS-REC-TT-180660-FC | FC | 0 | TRUE | TRUE | FALSE
4071 | MRT-CC07-P3UAG-170301 | 2018-08-09 | MRT-DS-REC-TT-180660-FC | FC | 1 | TRUE | TRUE | FALSE
4072 | MRT-CC02-P3UAG-170303 | 2018-08-09 | MRT-DS-REC-TT-180660-FC | FC | 1 | TRUE | TRUE | FALSE
4073 | MRT-VK02-P3UAG-170310 | 2018-08-09 | MRT-DS-REC-TT-180660-FC | FC | 0 | TRUE | TRUE | FALSE
4074 | MRT-YD00-P2LCB-127031 | 2018-08-09 | MRT-DS-REC-TT-180675-FC | FC | 1 | TRUE | TRUE | FALSE
4075 | MRT-YM01-P2LCB-127039 | 2018-08-09 | MRT-DS-REC-TT-180675-FC | FC | 0 | TRUE | TRUE | FALSE
4076 | MRT-YD00-P3LCB-127031 | 2018-08-09 | MRT-DS-REC-TT-180675-FC | FC | 1 | TRUE | TRUE | FALSE
4077 | MRT-YM01-P3LCB-127039 | 2018-08-09 | MRT-DS-REC-TT-180675-FC | FC | 0 | TRUE | TRUE | FALSE
4079 | MRT-XA00-P2PAC-130001 | 2018-08-09 | MRT-HK-REC-TT-180193 | FA | 0 | TRUE | FALSE | FALSE
4080 | MRT-XA00-P3PAC-130001 | 2018-08-09 | MRT-HK-REC-TT-180193 | FA | 0 | TRUE | FALSE | FALSE
4081 | MRT-YT01-P2PAC-130001 | 2018-08-09 | MRT-HK-REC-TT-180193 | FA | 0 | TRUE | FALSE | FALSE
4082 | MRT-YT01-P3PAC-130001 | 2018-08-09 | MRT-HK-REC-TT-180193 | FA | 0 | TRUE | FALSE | FALSE
4083 | MRT-YD07-P2ZEN-163109 | 2018-08-09 | MRT-DS-REC-TT-180614-FC | FC | 1 | TRUE | TRUE | FALSE
4084 | MRT-YR05-P2ZEN-163110 | 2018-08-09 | MRT-DS-REC-TT-180614-FC | FC | 1 | TRUE | TRUE | FALSE
4085 | MRT-YR05-P2ZEN-163111 | 2018-08-09 | MRT-DS-REC-TT-180614-FC | FC | 1 | TRUE | TRUE | FALSE
4086 | MRT-YR05-P2ZEN-163112 | 2018-08-09 | MRT-DS-REC-TT-180614-FC | FC | 1 | TRUE | TRUE | FALSE
4087 | MRT-YR05-P2ZEN-163113 | 2018-08-09 | MRT-DS-REC-TT-180614-FC | FC | 1 | TRUE | TRUE | FALSE
4088 | MRT-YR05-P2ZEN-163114 | 2018-08-09 | MRT-DS-REC-TT-180614-FC | FC | 1 | TRUE | TRUE | FALSE
4089 | MRT-YD07-P3ZEN-163109 | 2018-08-09 | MRT-DS-REC-TT-180614-FC | FC | 1 | TRUE | TRUE | FALSE
4090 | MRT-YR05-P3ZEN-163110 | 2018-08-09 | MRT-DS-REC-TT-180614-FC | FC | 1 | TRUE | TRUE | FALSE
4091 | MRT-YR05-P3ZEN-163111 | 2018-08-09 | MRT-DS-REC-TT-180614-FC | FC | 1 | TRUE | TRUE | FALSE
4092 | MRT-YR05-P3ZEN-163112 | 2018-08-09 | MRT-DS-REC-TT-180614-FC | FC | 1 | TRUE | TRUE | FALSE
4093 | MRT-YR05-P3ZEN-163113 | 2018-08-09 | MRT-DS-REC-TT-180614-FC | FC | 1 | TRUE | TRUE | FALSE
4094 | MRT-YR05-P3ZEN-163114 | 2018-08-09 | MRT-DS-REC-TT-180614-FC | FC | 1 | TRUE | TRUE | FALSE
4095 | MRT-VN02-P2LB-122090 | 2018-08-09 | MRT-DS-REC-TT-180605-FC | FC | 2 | TRUE | TRUE | FALSE
4096 | MRT-VN02-P3LB-122090 | 2018-08-09 | MRT-DS-REC-TT-180605-FC | FC | 2 | TRUE | TRUE | FALSE
4097 | MRT-YT01-P2LCB-127033 | 2018-08-09 | MRT-DS-REC-TT-180617-FC | FC | 2 | TRUE | TRUE | FALSE
4098 | MRT-YT01-P3LCB-127033 | 2018-08-09 | MRT-DS-REC-TT-180617-FC | FC | 2 | TRUE | TRUE | FALSE
4099 | MRT-YD00-P2ZEN-113300 | 2018-08-09 | MRT-DS-REC-TT-180618-FC | FC | 2 | TRUE | TRUE | FALSE
4100 | MRT-YD00-P3ZEN-113300 | 2018-08-09 | MRT-DS-REC-TT-180618-FC | FC | 2 | TRUE | TRUE | FALSE
4101 | MRT-YT01-P2GM-128502 | 2018-08-09 | MRT-DS-REC-TT-180653-FC | FC | 1 | TRUE | TRUE | FALSE
4102 | MRT-YT01-P3GM-128502 | 2018-08-09 | MRT-DS-REC-TT-180653-FC | FC | 1 | TRUE | TRUE | FALSE
4103 | MRT-XM00-P2BAT-150386 | 2018-08-09 | MRT-HK-REC-TT-180195 | FA | 0 | TRUE | FALSE | FALSE
4104 | MRT-XA01-P0ABA-150514 | 2018-08-09 | MRT-HK-REC-TT-180195 | FA | 0 | TRUE | FALSE | FALSE
4034 | MRT-CA03-P0UMA-180039 | 2018-08-10 | MRT-DS-REC-TT-180690 | FC | 3 | TRUE | TRUE | FALSE
4105 | MRT-UC08-P0ZEN-100003 | 2018-08-10 | MRT-DS-REC-TT-180627-FC | FC | 3 | TRUE | TRUE | FALSE
4106 | MRT-YV02-P2PAH-604122 | 2018-08-10 | MRT-DS-REC-TT-180655-FC | FC | 2 | TRUE | TRUE | FALSE
4107 | MRT-YK10-P2MAA-185101 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4108 | MRT-CA03-P2UMA-185125 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4109 | MRT-CA03-P2UMA-185124 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4110 | MRT-CA03-P2UMA-185123 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4111 | MRT-CA03-P2UMA-185122 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4112 | MRT-CA03-P2UMA-185121 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4113 | MRT-CA03-P2UMA-185120 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4114 | MRT-CA03-P2UMA-185119 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4115 | MRT-CA03-P2UMA-185118 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4116 | MRT-CA03-P2UMA-185117 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4117 | MRT-CA03-P2UMA-185116 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4118 | MRT-CA03-P2UMA-185115 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4119 | MRT-CA03-P2UMA-185114 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4120 | MRT-CA03-P2UMA-185113 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4121 | MRT-CA03-P2UMA-185112 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4122 | MRT-CA03-P2UMA-185111 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4123 | MRT-CA03-P2UMA-185110 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4124 | MRT-CA03-P2UMA-185109 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4125 | MRT-CA03-P2UMA-185108 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4126 | MRT-CA03-P2UMA-185107 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4127 | MRT-CA03-P2UMA-185106 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4128 | MRT-CA03-P2UMA-185105 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4129 | MRT-CA03-P2UMA-185104 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4130 | MRT-CA03-P2UMA-185103 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4131 | MRT-CA03-P2UMA-185102 | 2018-08-10 | MRT-HK-REC-TT-180194 | FI | 0 | TRUE | TRUE | FALSE
4132 | MRT-CN00-P3ZEN-110102 | 2018-08-10 | MRT-DS-REC-TT-180693 | FA | 0 | TRUE | FALSE | FALSE
4137 | MRT-CA06-P0UMX-187201 | 2018-08-11 | MRT-HK-REC-TT-180197 | FA | 0 | TRUE | FALSE | FALSE
4138 | MRT-CA01-P0UMX-187202 | 2018-08-11 | MRT-HK-REC-TT-180197 | FA | 0 | TRUE | FALSE | FALSE
4139 | MRT-CA06-P0UMX-187204 | 2018-08-11 | MRT-HK-REC-TT-180197 | FA | 0 | TRUE | FALSE | FALSE
4140 | MRT-CA01-P0UMX-187214 | 2018-08-11 | MRT-HK-REC-TT-180197 | FA | 0 | TRUE | FALSE | FALSE
4141 | MRT-CA02-P0UMX-187220 | 2018-08-11 | MRT-HK-REC-TT-180197 | FA | 0 | TRUE | FALSE | FALSE
4142 | MRT-CA03-P0UMX-187222 | 2018-08-11 | MRT-HK-REC-TT-180197 | FA | 0 | TRUE | FALSE | FALSE
4143 | MRT-CA06-P0UYX-187151 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4144 | MRT-CA01-P0UYX-187152 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4145 | MRT-CA06-P0UYX-187154 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4146 | MRT-CA00-P0UYX-187156 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4147 | MRT-CA00-P0UYX-187158 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4148 | MRT-CA00-P0UYX-187162 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4149 | MRT-CA01-P0UYX-187164 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4150 | MRT-CA02-P0UYX-187166 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4151 | MRT-CA01-P0UYX-187168 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4152 | MRT-CA01-P0UYX-187170 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4153 | MRT-CA01-P0UYX-187172 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4154 | MRT-CA02-P0UYX-187174 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4155 | MRT-CA02-P0UYX-187176 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4156 | MRT-CA02-P0UYX-187178 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4157 | MRT-CA00-P0UYX-187159 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4158 | MRT-CA00-P0UYX-187184 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4159 | MRT-CA00-P0UYX-187157 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4160 | MRT-CA01-P0UYX-187171 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4161 | MRT-CA01-P0UYX-187186 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4162 | MRT-CA01-P0UYX-187187 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4163 | MRT-CA02-P0UYX-187177 | 2018-08-11 | MRT-HK-REC-TT-180198 | FA | 1 | TRUE | TRUE | FALSE
4164 | MRT-YL00-P2QC-130007 | 2018-08-13 | MRT-DS-REC-TT-180694 | FI | 2 | TRUE | TRUE | FALSE
4165 | MRT-YL00-P3QC-130007 | 2018-08-13 | MRT-DS-REC-TT-180694 | FI | 2 | TRUE | TRUE | FALSE
4166 | MRT-YK00-P2QC-130022 | 2018-08-13 | MRT-DS-REC-TT-180696 | FC | 2 | TRUE | TRUE | FALSE
4167 | MRT-YK00-P3QC-130022 | 2018-08-13 | MRT-DS-REC-TT-180696 | FC | 2 | TRUE | TRUE | FALSE
4168 | MRT-YT01-P2QC-130016 | 2018-08-13 | MRT-DS-REC-TT-180695 | FI | 2 | TRUE | TRUE | FALSE
4169 | MRT-YT01-P3QC-130016 | 2018-08-13 | MRT-DS-REC-TT-180695 | FI | 2 | TRUE | TRUE | FALSE
4170 | MRT-YT01-P2QC-130012 | 2018-08-13 | MRT-DS-REC-TT-180697 | FI | 1 | TRUE | FALSE | FALSE
4171 | MRT-YT01-P3QC-130012 | 2018-08-13 | MRT-DS-REC-TT-180697 | FI | 1 | TRUE | FALSE | FALSE
4172 | MRT-YK10-P2QC-130010 | 2018-08-13 | MRT-DS-REC-TT-180698 | FC | 2 | TRUE | TRUE | FALSE
4173 | MRT-YK10-P3QC-130010 | 2018-08-13 | MRT-DS-REC-TT-180698 | FC | 2 | TRUE | TRUE | FALSE
4174 | MRT-XW01-P2SCA-127504 | 2018-08-13 | MRT-DS-REC-TT-180699 | FC | 2 | TRUE | TRUE | FALSE
4175 | MRT-XW01-P3SCA-127504 | 2018-08-13 | MRT-DS-REC-TT-180699 | FC | 2 | TRUE | TRUE | FALSE
4176 | MRT-DP00-P0ZEN-070416 | 2018-08-13 | MRT-HK-REC-TT-180200 | FA | 0 | TRUE | FALSE | FALSE
4177 | MRT-YD00-P2CWA-165002 | 2018-08-13 | MRT-HK-REC-TT-180200 | FA | 0 | TRUE | FALSE | FALSE
6494 | MRT-QM03-POZEN-155001 | 2018-08-13 | MRT-HK-REC-TT-180202 | FA | 1 | TRUE | FALSE | FALSE
10626 | MRT-QM03-P0ZEN-155001 | 2018-08-13 | MRT-HK-REC-TT-180202 | FI | 1 | TRUE | FALSE | FALSE
4178 | MRT-CA03-P0UMA-180025 | 2018-08-14 | MRT-DS-REC-TT-180662-FC | FC | 4 | TRUE | TRUE | FALSE
4179 | MRT-CA03-P0UMA-180026 | 2018-08-14 | MRT-DS-REC-TT-180662-FC | FC | 4 | TRUE | TRUE | FALSE
4180 | MRT-CA01-P0UMA-180027 | 2018-08-14 | MRT-DS-REC-TT-180662-FC | FC | 4 | TRUE | TRUE | FALSE
4181 | MRT-CA03-P0UMA-180028 | 2018-08-14 | MRT-DS-REC-TT-180662-FC | FC | 4 | TRUE | TRUE | FALSE
4182 | MRT-CA03-P0UMA-180029 | 2018-08-14 | MRT-DS-REC-TT-180662-FC | FC | 4 | TRUE | TRUE | FALSE
4183 | MRT-CA03-P0UMA-180031 | 2018-08-14 | MRT-DS-REC-TT-180662-FC | FC | 4 | TRUE | TRUE | FALSE
4184 | MRT-CA03-P0UMA-180032 | 2018-08-14 | MRT-DS-REC-TT-180662-FC | FC | 4 | TRUE | TRUE | FALSE
4185 | MRT-CA03-P0UMA-180033 | 2018-08-14 | MRT-DS-REC-TT-180662-FC | FC | 4 | TRUE | TRUE | FALSE
4186 | MRT-CA03-P0UMA-180034 | 2018-08-14 | MRT-DS-REC-TT-180662-FC | FC | 4 | TRUE | TRUE | FALSE
4187 | MRT-CA03-P0UMA-180040 | 2018-08-14 | MRT-DS-REC-TT-180662-FC | FC | 3 | TRUE | TRUE | FALSE
4188 | MRT-CA03-P0UMA-180042 | 2018-08-14 | MRT-DS-REC-TT-180662-FC | FC | 4 | TRUE | TRUE | FALSE
4189 | MRT-CA03-P0UMA-180030 | 2018-08-14 | MRT-DS-REC-TT-180662-FC | FC | 4 | TRUE | TRUE | FALSE
4263 | MRT-YK08-P2PAH-604124 | 2018-08-14 | MRT-DS-REC-TT-180700 | FC | 4 | TRUE | TRUE | FALSE
4264 | MRT-YT01-P2LCB-127036 | 2018-08-14 | MRT-DS-REC-TT-180684-FC | FC | 0 | TRUE | TRUE | FALSE
4265 | MRT-YL00-P2LCB-127040 | 2018-08-14 | MRT-DS-REC-TT-180684-FC | FC | 0 | TRUE | TRUE | FALSE
4266 | MRT-YT01-P3LCB-127036 | 2018-08-14 | MRT-DS-REC-TT-180684-FC | FC | 0 | TRUE | TRUE | FALSE
4267 | MRT-YL00-P3LCB-127040 | 2018-08-14 | MRT-DS-REC-TT-180684-FC | FC | 0 | TRUE | TRUE | FALSE
4268 | MRT-YV02-P2QC-130017 | 2018-08-14 | MRT-DS-REC-TT-180615-FC | FC | 2 | TRUE | TRUE | FALSE
4269 | MRT-YV02-P3QC-130017 | 2018-08-14 | MRT-DS-REC-TT-180615-FC | FC | 2 | TRUE | TRUE | FALSE
4290 | MRT-XW03-P3GC-135111 | 2018-08-14 | MRT-HK-REC-TT-180203 | FA | 0 | TRUE | FALSE | FALSE
4341 | MRT-CA06-P0USX-186801 | 2018-08-14 | MRT-HK-REC-TT-180201 | FA | 0 | TRUE | FALSE | FALSE
4342 | MRT-CA01-P0USX-186802 | 2018-08-14 | MRT-HK-REC-TT-180201 | FA | 0 | TRUE | FALSE | FALSE
4343 | MRT-CA00-P0USX-186806 | 2018-08-14 | MRT-HK-REC-TT-180201 | FA | 0 | TRUE | FALSE | FALSE
4344 | MRT-CA00-P0USX-186808 | 2018-08-14 | MRT-HK-REC-TT-180201 | FA | 0 | TRUE | FALSE | FALSE
4345 | MRT-CA00-P0USX-186814 | 2018-08-14 | MRT-HK-REC-TT-180201 | FA | 0 | TRUE | FALSE | FALSE
4346 | MRT-CA00-P0USX-186807 | 2018-08-14 | MRT-HK-REC-TT-180201 | FA | 0 | TRUE | TRUE | FALSE
4280 | MRT-CA06-P0UGG-187251 | 2018-08-15 | MRT-HK-REC-TT-180204 | FA | 1 | TRUE | TRUE | FALSE
4281 | MRT-CA01-P0UGG-187252 | 2018-08-15 | MRT-HK-REC-TT-180204 | FA | 1 | TRUE | TRUE | FALSE
4282 | MRT-CC02-P2UMA-170607 | 2018-08-16 | MRT-DS-REC-TT-180701 | FC | 4 | TRUE | TRUE | FALSE
4283 | MRT-CC02-P2UMA-170608 | 2018-08-16 | MRT-DS-REC-TT-180701 | FC | 4 | TRUE | TRUE | FALSE
4284 | MRT-CC02-P2UMA-170609 | 2018-08-16 | MRT-DS-REC-TT-180701 | FC | 4 | TRUE | TRUE | FALSE
4285 | MRT-VK02-P2UMA-170610 | 2018-08-16 | MRT-DS-REC-TT-180701 | FC | 3 | TRUE | TRUE | FALSE
4286 | MRT-CC02-P3UMA-170607 | 2018-08-16 | MRT-DS-REC-TT-180701 | FC | 4 | TRUE | TRUE | FALSE
4287 | MRT-CC02-P3UMA-170608 | 2018-08-16 | MRT-DS-REC-TT-180701 | FC | 4 | TRUE | TRUE | FALSE
4288 | MRT-CC02-P3UMA-170609 | 2018-08-16 | MRT-DS-REC-TT-180701 | FC | 4 | TRUE | TRUE | FALSE
4289 | MRT-VK02-P3UMA-170610 | 2018-08-16 | MRT-DS-REC-TT-180701 | FC | 3 | TRUE | TRUE | FALSE
4303 | MRT-CC02-P2UMA-170707 | 2018-08-16 | MRT-DS-REC-TT-180702 | FC | 4 | TRUE | TRUE | FALSE
4304 | MRT-CC02-P2UMA-170708 | 2018-08-16 | MRT-DS-REC-TT-180702 | FC | 4 | TRUE | TRUE | FALSE
4305 | MRT-CC02-P2UMA-170709 | 2018-08-16 | MRT-DS-REC-TT-180702 | FC | 4 | TRUE | TRUE | FALSE
4306 | MRT-CC02-P3UMA-170707 | 2018-08-16 | MRT-DS-REC-TT-180702 | FC | 4 | TRUE | TRUE | FALSE
4307 | MRT-CC02-P3UMA-170708 | 2018-08-16 | MRT-DS-REC-TT-180702 | FC | 4 | TRUE | TRUE | FALSE
4308 | MRT-CC02-P3UMA-170709 | 2018-08-16 | MRT-DS-REC-TT-180702 | FC | 4 | TRUE | TRUE | FALSE
4309 | MRT-VK02-P3UMA-170710 | 2018-08-16 | MRT-DS-REC-TT-180702 | FC | 3 | TRUE | TRUE | FALSE
4310 | MRT-YD00-P2LAC-126049 | 2018-08-16 | MRT-DS-REC-TT-180703 | FI | 1 | TRUE | TRUE | FALSE
4311 | MRT-YD00-P3LAC-126049 | 2018-08-16 | MRT-DS-REC-TT-180703 | FI | 1 | TRUE | TRUE | FALSE
4312 | MRT-YD00-P2LAC-126096 | 2018-08-16 | MRT-DS-REC-TT-180703 | FI | 1 | TRUE | TRUE | FALSE
4313 | MRT-YD00-P3LAC-126096 | 2018-08-16 | MRT-DS-REC-TT-180703 | FI | 1 | TRUE | TRUE | FALSE
4314 | MRT-YD00-P2LAC-126050 | 2018-08-16 | MRT-DS-REC-TT-180703 | FI | 1 | TRUE | TRUE | FALSE
4315 | MRT-YD00-P3LAC-126050 | 2018-08-16 | MRT-DS-REC-TT-180703 | FI | 1 | TRUE | TRUE | FALSE
4316 | MRT-YD00-P2LAC-126097 | 2018-08-16 | MRT-DS-REC-TT-180703 | FI | 1 | TRUE | TRUE | FALSE
4317 | MRT-YD00-P3LAC-126097 | 2018-08-16 | MRT-DS-REC-TT-180703 | FI | 1 | TRUE | TRUE | FALSE
4318 | MRT-YL00-P2LB-122075 | 2018-08-16 | MRT-DS-REC-TT-180704 | FI | 1 | TRUE | TRUE | FALSE
4319 | MRT-XV00-P2LB-122039 | 2018-08-16 | MRT-DS-REC-TT-180705 | FI | 1 | TRUE | TRUE | FALSE
4320 | MRT-XV00-P3LB-122039 | 2018-08-16 | MRT-DS-REC-TT-180705 | FI | 1 | TRUE | TRUE | FALSE
4352 | MRT-CC07-P0UZT-175901 | 2018-08-16 | MRT-HK-REC-TT-180205 | FA | 0 | TRUE | FALSE | FALSE
4353 | MRT-CC02-P0UZT-175905 | 2018-08-16 | MRT-HK-REC-TT-180205 | FA | 0 | TRUE | FALSE | FALSE
4354 | MRT-CC02-P0UZT-175907 | 2018-08-16 | MRT-HK-REC-TT-180205 | FA | 0 | TRUE | FALSE | FALSE
4355 | MRT-CC02-P0UZT-175908 | 2018-08-16 | MRT-HK-REC-TT-180205 | FA | 0 | TRUE | FALSE | FALSE
4356 | MRT-CC02-P0UZT-175909 | 2018-08-16 | MRT-HK-REC-TT-180205 | FA | 0 | TRUE | FALSE | FALSE
4321 | MRT-XJ00-P2MKJ-220001 | 2018-08-17 | MRT-DS-REC-TT-180633-FC | FC | 2 | TRUE | TRUE | FALSE
4322 | MRT-XH01-P3MKA-220001 | 2018-08-17 | MRT-DS-REC-TT-180634-FC | FC | 1 | TRUE | TRUE | FALSE
4323 | MRT-XJ00-P3MKA-220001 | 2018-08-17 | MRT-DS-REC-TT-180635-FC | FC | 1 | TRUE | TRUE | FALSE
4324 | MRT-XK00-P2LAC-126014 | 2018-08-17 | MRT-DS-REC-TT-180657-FC | FC | 1 | TRUE | TRUE | FALSE
4325 | MRT-XK00-P3LAC-126014 | 2018-08-17 | MRT-DS-REC-TT-180657-FC | FC | 1 | TRUE | TRUE | FALSE
4326 | MRT-CA05-P0UCA-180161 | 2018-08-17 | MRT-DS-REC-TT-180670-FC | FC | 4 | TRUE | TRUE | FALSE
4327 | MRT-CA05-P0UCA-180162 | 2018-08-17 | MRT-DS-REC-TT-180670-FC | FC | 4 | TRUE | TRUE | FALSE
4328 | MRT-CA05-P0UCA-180163 | 2018-08-17 | MRT-DS-REC-TT-180670-FC | FC | 4 | TRUE | TRUE | FALSE
4329 | MRT-CA05-P0UCA-180164 | 2018-08-17 | MRT-DS-REC-TT-180670-FC | FC | 4 | TRUE | TRUE | FALSE
4330 | MRT-CA00-P0UMA-180008 | 2018-08-17 | MRT-DS-REC-TT-180688-FC | FC | 3 | TRUE | TRUE | FALSE
4331 | MRT-CA00-P0UMA-180010 | 2018-08-17 | MRT-DS-REC-TT-180688-FC | FC | 3 | TRUE | TRUE | FALSE
4332 | MRT-CA00-P0UMA-180011 | 2018-08-17 | MRT-DS-REC-TT-180688-FC | FC | 3 | TRUE | TRUE | FALSE
4333 | MRT-CA00-P0UMA-180013 | 2018-08-17 | MRT-DS-REC-TT-180688-FC | FC | 3 | TRUE | TRUE | FALSE
4334 | MRT-CA00-P0UMA-180014 | 2018-08-17 | MRT-DS-REC-TT-180688-FC | FC | 3 | TRUE | TRUE | FALSE
4335 | MRT-YR05-P2SCA-127523 | 2018-08-17 | MRT-DS-REC-TT-180691-FC | FC | 1 | TRUE | TRUE | FALSE
4336 | MRT-YR05-P3SCA-127523 | 2018-08-17 | MRT-DS-REC-TT-180691-FC | FC | 1 | TRUE | TRUE | FALSE
4337 | MRT-YD00-P2LB-122056 | 2018-08-17 | MRT-DS-REC-TT-180706 | FA | 2 | TRUE | TRUE | FALSE
4338 | MRT-YD00-P3LB-122056 | 2018-08-17 | MRT-DS-REC-TT-180706 | FA | 2 | TRUE | TRUE | FALSE
4339 | MRT-YD00-P2LB-122053 | 2018-08-17 | MRT-DS-REC-TT-180707 | FC | 2 | TRUE | TRUE | FALSE
4340 | MRT-YD00-P3LB-122053 | 2018-08-17 | MRT-DS-REC-TT-180707 | FC | 2 | TRUE | TRUE | FALSE
4347 | MRT-YT01-P3MKA-240003 | 2018-08-20 | MRT-DS-REC-TT-180708 | FI | 1 | TRUE | TRUE | FALSE
4348 | MRT-YK00-P2SCA-127521 | 2018-08-20 | MRT-DS-REC-TT-180709 | FI | 2 | TRUE | TRUE | FALSE
4349 | MRT-YK00-P3SCA-127521 | 2018-08-20 | MRT-DS-REC-TT-180709 | FI | 2 | TRUE | TRUE | FALSE
4350 | MRT-XF00-P2SCA-127524 | 2018-08-20 | MRT-DS-REC-TT-180710 | FC | 1 | TRUE | TRUE | FALSE
4351 | MRT-XF00-P3SCA-127524 | 2018-08-20 | MRT-DS-REC-TT-180710 | FC | 1 | TRUE | TRUE | FALSE
4357 | MRT-CC00-P0ZEN-145401 | 2018-08-20 | MRT-HK-REC-TT-180206 | FA | 1 | TRUE | TRUE | FALSE
4358 | MRT-YU02-P0BHA-150038 | 2018-08-20 | MRT-HK-REC-TT-180207 | FA | 0 | TRUE | FALSE | FALSE
4359 | MRT-YD00-P0GQA-150132 | 2018-08-20 | MRT-HK-REC-TT-180207 | FA | 0 | TRUE | FALSE | FALSE
4360 | MRT-XA00-P2PBB-135217 | 2018-08-20 | MRT-HK-REC-TT-180208 | FA | 0 | TRUE | TRUE | FALSE
4361 | MRT-XA00-P3PBB-135220 | 2018-08-20 | MRT-HK-REC-TT-180208 | FA | 0 | TRUE | TRUE | FALSE
4362 | MRT-XA00-P2PBB-135218 | 2018-08-20 | MRT-HK-REC-TT-180208 | FA | 0 | TRUE | TRUE | FALSE
4363 | MRT-XA00-P3PBB-135221 | 2018-08-20 | MRT-HK-REC-TT-180208 | FA | 0 | TRUE | TRUE | FALSE
4489 | MRT-XW01-P2SCA-127504 | 2018-08-22 | MRT-DS-REC-TT-180699-FC | FC | 2 | TRUE | TRUE | FALSE
4490 | MRT-XW01-P3SCA-127504 | 2018-08-22 | MRT-DS-REC-TT-180699-FC | FC | 2 | TRUE | TRUE | FALSE
4491 | MRT-CA03-P0UMA-180039 | 2018-08-22 | MRT-DS-REC-TT-180690-FC | FC | 3 | TRUE | TRUE | FALSE
4492 | MRT-YD06-P3ZEN-163106 | 2018-08-22 | MRT-DS-REC-TT-180647-FC | FC | 2 | TRUE | TRUE | FALSE
4493 | MRT-XW03-P0BBA-150285 | 2018-08-22 | MRT-HK-REC-TT-180209 | FA | 1 | TRUE | TRUE | FALSE
4494 | MRT-CA06-P0UGA-186600 | 2018-08-22 | MRT-HK-REC-TT-180210 | FA | 2 | TRUE | TRUE | FALSE
4495 | MRT-CA01-P0UGA-186602 | 2018-08-22 | MRT-HK-REC-TT-180210 | FA | 2 | TRUE | TRUE | FALSE
4496 | MRT-CA01-P0UGA-186603 | 2018-08-22 | MRT-HK-REC-TT-180210 | FA | 2 | TRUE | TRUE | FALSE
4497 | MRT-CA06-P0UGA-186599 | 2018-08-22 | MRT-HK-REC-TT-180210 | FA | 2 | TRUE | TRUE | FALSE
4498 | MRT-CC04-P0ULY-176109 | 2018-08-22 | MRT-HK-REC-TT-180211 | FA | 0 | TRUE | FALSE | FALSE
4499 | MRT-CC07-P0ULY-176112 | 2018-08-22 | MRT-HK-REC-TT-180211 | FA | 0 | TRUE | FALSE | FALSE
4500 | MRT-CA01-P0USG-186852 | 2018-08-22 | MRT-HK-REC-TT-180212 | FA | 2 | TRUE | TRUE | FALSE
4501 | MRT-CA06-P0UGX-186951 | 2018-08-22 | MRT-HK-REC-TT-180212 | FA | 1 | TRUE | TRUE | FALSE
4502 | MRT-CA01-P0UGX-186952 | 2018-08-22 | MRT-HK-REC-TT-180212 | FA | 2 | TRUE | TRUE | FALSE
4503 | MRT-CC02-P0UGA-176250 | 2018-08-22 | MRT-HK-REC-TT-180213 | FA | 1 | TRUE | TRUE | FALSE
4504 | MRT-CC02-P0UGA-176290 | 2018-08-22 | MRT-HK-REC-TT-180213 | FA | 1 | TRUE | TRUE | FALSE
4505 | MRT-CA06-P0UGX-186720 | 2018-08-22 | MRT-HK-REC-TT-180214 | FA | 1 | TRUE | TRUE | FALSE
4506 | MRT-CA01-P0UGX-186722 | 2018-08-22 | MRT-HK-REC-TT-180214 | FA | 1 | TRUE | TRUE | FALSE
4507 | MRT-CA06-P0UPB-187001 | 2018-08-22 | MRT-HK-REC-TT-180214 | FA | 1 | TRUE | TRUE | FALSE
4508 | MRT-CA01-P0UPB-187002 | 2018-08-22 | MRT-HK-REC-TT-180214 | FA | 2 | TRUE | TRUE | FALSE
4509 | MRT-CA01-P0UXA-186662 | 2018-08-22 | MRT-HK-REC-TT-180214 | FA | 1 | TRUE | TRUE | FALSE
4510 | MRT-CA06-P0UXA-186660 | 2018-08-22 | MRT-HK-REC-TT-180214 | FA | 1 | TRUE | TRUE | FALSE
4511 | MRT-CA06-P0UGX-186721 | 2018-08-22 | MRT-HK-REC-TT-180214 | FA | 1 | TRUE | TRUE | FALSE
4512 | MRT-YT01-P2LAC-126005 | 2018-08-22 | MRT-DS-REC-TT-180712 | FC | 4 | TRUE | TRUE | FALSE
4513 | MRT-YT01-P3LAC-126005 | 2018-08-22 | MRT-DS-REC-TT-180712 | FC | 4 | TRUE | TRUE | FALSE
4514 | MRT-YT01-P2LAC-126055 | 2018-08-22 | MRT-DS-REC-TT-180712 | FC | 2 | TRUE | TRUE | FALSE
4515 | MRT-YT01-P3LAC-126055 | 2018-08-22 | MRT-DS-REC-TT-180712 | FC | 2 | TRUE | TRUE | FALSE
4516 | MRT-YL00-P2MAJ-603105 | 2018-08-22 | MRT-DS-REC-TT-180714 | FC | 5 | TRUE | TRUE | FALSE
4517 | MRT-YV02-P2MAJ-603108 | 2018-08-22 | MRT-DS-REC-TT-180714 | FC | 5 | TRUE | TRUE | FALSE
4518 | MRT-YL00-P3MAJ-604105 | 2018-08-22 | MRT-DS-REC-TT-180714 | FC | 5 | TRUE | TRUE | FALSE
4519 | MRT-YV02-P3MAJ-604108 | 2018-08-22 | MRT-DS-REC-TT-180714 | FC | 5 | TRUE | TRUE | FALSE
4520 | MRT-YS01-P2QU-130034 | 2018-08-22 | MRT-DS-REC-TT-180715 | FI | 3 | TRUE | TRUE | FALSE
4521 | MRT-XG02-P2SCA-127502 | 2018-08-23 | MRT-DS-REC-TT-180711 | FC | 2 | TRUE | TRUE | FALSE
4522 | MRT-XG02-P3SCA-127502 | 2018-08-23 | MRT-DS-REC-TT-180711 | FC | 2 | TRUE | TRUE | FALSE
4523 | MRT-YT01-P2MAJ-603100 | 2018-08-23 | MRT-DS-REC-TT-180713 | FC | 4 | TRUE | TRUE | FALSE
4524 | MRT-XG02-P2MAJ-603101 | 2018-08-23 | MRT-DS-REC-TT-180713 | FC | 4 | TRUE | TRUE | FALSE
4525 | MRT-YK08-P2MAJ-603102 | 2018-08-23 | MRT-DS-REC-TT-180713 | FC | 3 | TRUE | TRUE | FALSE
4526 | MRT-XN00-P2MAJ-603106 | 2018-08-23 | MRT-DS-REC-TT-180713 | FC | 4 | TRUE | TRUE | FALSE
4527 | MRT-YT01-P3MAJ-604100 | 2018-08-23 | MRT-DS-REC-TT-180713 | FC | 4 | TRUE | TRUE | FALSE
4528 | MRT-XG02-P3MAJ-604101 | 2018-08-23 | MRT-DS-REC-TT-180713 | FC | 4 | TRUE | TRUE | FALSE
4529 | MRT-YK08-P3MAJ-604102 | 2018-08-23 | MRT-DS-REC-TT-180713 | FC | 3 | TRUE | TRUE | FALSE
4530 | MRT-XN00-P3MAJ-604106 | 2018-08-23 | MRT-DS-REC-TT-180713 | FC | 4 | TRUE | TRUE | FALSE
4538 | MRT-XL00-P3MKA-210001 | 2018-08-23 | MRT-DS-REC-TT-180303-FC | FC | 0 | TRUE | TRUE | FALSE
4539 | MRT-XN00-P3MKA-210001 | 2018-08-23 | MRT-DS-REC-TT-180303-FC | FC | 0 | TRUE | TRUE | FALSE
4855 | MRT-YU02-P3BBA-150460 | 2018-08-24 | MRT-HK-REC-TT-180215 | FA | 0 | TRUE | FALSE | FALSE
4856 | MRT-YU02-P3BBA-150118 | 2018-08-24 | MRT-HK-REC-TT-180215 | FA | 0 | TRUE | FALSE | FALSE
4857 | MRT-YU02-P0BBA-150462 | 2018-08-24 | MRT-HK-REC-TT-180215 | FA | 0 | TRUE | FALSE | FALSE
4858 | MRT-YM02-P3BBA-150461 | 2018-08-24 | MRT-HK-REC-TT-180215 | FA | 0 | TRUE | FALSE | FALSE
4859 | MRT-YM02-P3BBA-150119 | 2018-08-24 | MRT-HK-REC-TT-180215 | FA | 0 | TRUE | FALSE | FALSE
4860 | MRT-YM02-P0BBA-150463 | 2018-08-24 | MRT-HK-REC-TT-180215 | FA | 0 | TRUE | FALSE | FALSE
4861 | MRT-YU02-P0BCA-150028 | 2018-08-24 | MRT-HK-REC-TT-180215 | FA | 0 | TRUE | FALSE | FALSE
4862 | MRT-YU02-P2BBA-150029 | 2018-08-24 | MRT-HK-REC-TT-180215 | FA | 0 | TRUE | FALSE | FALSE
4863 | MRT-YU02-P3BBC-150030 | 2018-08-24 | MRT-HK-REC-TT-180215 | FA | 0 | TRUE | FALSE | FALSE
4864 | MRT-YD00-P0UGA-150126 | 2018-08-24 | MRT-HK-REC-TT-180215 | FA | 0 | TRUE | FALSE | FALSE
4865 | MRT-YU02-P0BJJ-150052 | 2018-08-24 | MRT-HK-REC-TT-180216 | FA | 1 | TRUE | TRUE | FALSE
4866 | MRT-YD00-P0BJQ-150131 | 2018-08-24 | MRT-HK-REC-TT-180216 | FA | 0 | TRUE | FALSE | FALSE
4867 | MRT-CC02-P2UHA-170103 | 2018-08-24 | MRT-DS-REC-TT-180716 | FC | 6 | TRUE | TRUE | FALSE
4868 | MRT-CC02-P2UHA-170104 | 2018-08-24 | MRT-DS-REC-TT-180716 | FC | 5 | TRUE | TRUE | FALSE
4869 | MRT-VK02-P2UHA-170106 | 2018-08-24 | MRT-DS-REC-TT-180716 | FC | 6 | TRUE | TRUE | FALSE
4870 | MRT-CC02-P3UHA-170103 | 2018-08-24 | MRT-DS-REC-TT-180716 | FC | 6 | TRUE | TRUE | FALSE
4871 | MRT-CC02-P3UHA-170104 | 2018-08-24 | MRT-DS-REC-TT-180716 | FC | 5 | TRUE | TRUE | FALSE
4872 | MRT-VK02-P3UHA-170106 | 2018-08-24 | MRT-DS-REC-TT-180716 | FC | 6 | TRUE | TRUE | FALSE
4873 | MRT-YK10-P2MAA-185126 | 2018-08-24 | MRT-HK-REC-TT-180217 | FI | 0 | TRUE | FALSE | FALSE
4874 | MRT-CC07-P0ULY-176115 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 2 | TRUE | TRUE | FALSE
4875 | MRT-CC04-P0ULY-176140 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 1 | TRUE | TRUE | FALSE
4876 | MRT-CC04-P0ULY-176141 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4877 | MRT-CC04-P0ULY-176142 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4878 | MRT-CC04-P0ULY-176143 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4879 | MRT-CC04-P0ULY-176144 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4880 | MRT-CC04-P0ULY-176146 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4881 | MRT-CC04-P0ULY-176147 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4882 | MRT-CC04-P0ULY-176148 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4883 | MRT-CC04-P0ULY-176149 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4884 | MRT-CC04-P0ULY-176173 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4885 | MRT-CC04-P0ULY-176174 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4886 | MRT-CC04-P0ULY-176175 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4887 | MRT-CC04-P0ULY-176177 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4888 | MRT-CC04-P0ULY-176178 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4889 | MRT-CC04-P0ULY-176179 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4890 | MRT-CC04-P0ULY-176197 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4891 | MRT-CC04-P0ULY-176198 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4892 | MRT-CC04-P0ULY-176199 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4893 | MRT-CC04-P0ULY-176193 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4894 | MRT-CC04-P0ULY-176194 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4895 | MRT-CC04-P0ULY-176195 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4896 | MRT-CC04-P0ULY-176196 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4897 | MRT-CC04-P0ULY-176176 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4898 | MRT-CC07-P0ULY-176114 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4899 | MRT-CC04-P0ULY-176189 | 2018-08-27 | MRT-HK-REC-TT-180218 | FA | 0 | TRUE | TRUE | FALSE
4900 | MRT-XK00-P2GM-128505 | 2018-08-27 | MRT-DS-REC-TT-180656-FC | FC | 1 | TRUE | TRUE | FALSE
4901 | MRT-YD00-P2GM-128503 | 2018-08-27 | MRT-DS-REC-TT-180656-FC | FC | 1 | TRUE | TRUE | FALSE
4902 | MRT-XK00-P3GM-128505 | 2018-08-27 | MRT-DS-REC-TT-180656-FC | FC | 1 | TRUE | TRUE | FALSE
4903 | MRT-YD00-P3GM-128503 | 2018-08-27 | MRT-DS-REC-TT-180656-FC | FC | 1 | TRUE | TRUE | FALSE
4904 | MRT-YD00-P2BAT-150377 | 2018-08-27 | MRT-HK-REC-TT-180219 | FA | 0 | TRUE | FALSE | FALSE
4905 | MRT-YD00-P3BAT-150400 | 2018-08-27 | MRT-HK-REC-TT-180219 | FA | 0 | TRUE | FALSE | FALSE
4906 | MRT-YT01-P2PAC-130001 | 2018-08-27 | MRT-HK-REC-TT-180220 | FA | 1 | TRUE | TRUE | FALSE
4907 | MRT-YT01-P3PAC-130001 | 2018-08-27 | MRT-HK-REC-TT-180220 | FA | 1 | TRUE | TRUE | FALSE
4908 | MRT-XG02-P2PAC-130001 | 2018-08-27 | MRT-HK-REC-TT-180220 | FA | 0 | TRUE | FALSE | FALSE
4909 | MRT-XG02-P3PAC-130001 | 2018-08-27 | MRT-HK-REC-TT-180220 | FA | 0 | TRUE | FALSE | FALSE
4910 | MRT-BV02-P2PAC-130001 | 2018-08-27 | MRT-HK-REC-TT-180220 | FA | 0 | TRUE | FALSE | FALSE
4911 | MRT-QM03-P0ZEN-145016 | 2018-08-27 | MRT-HK-REC-TT-180221 | FA | 0 | TRUE | FALSE | FALSE
4912 | MRT-YD00-P0UBN-150134 | 2018-08-27 | MRT-HK-REC-TT-180222 | FA | 0 | TRUE | FALSE | FALSE
4913 | MRT-XA01-P0ABA-150513 | 2018-08-27 | MRT-HK-REC-TT-180222 | FA | 1 | TRUE | TRUE | FALSE
4914 | MRT-XA01-P0ABA-150510 | 2018-08-27 | MRT-HK-REC-TT-180222 | FA | 1 | TRUE | TRUE | FALSE
4915 | MRT-CQ02-P2MAG-601011 | 2018-08-27 | MRT-DS-REC-TT-180651-FC | FC | 0 | TRUE | TRUE | FALSE
4918 | MRT-XG02-P0GKC-120001 | 2018-08-28 | MRT-DS-REC-TT-180719 | FC | 4 | TRUE | TRUE | FALSE
4919 | MRT-YS01-P2MKC-230014 | 2018-08-28 | MRT-DS-REC-TT-180718 | FA | 1 | TRUE | TRUE | FALSE
4920 | MRT-YS01-P3MKC-230014 | 2018-08-28 | MRT-DS-REC-TT-180718 | FA | 1 | TRUE | TRUE | FALSE
4921 | MRT-CC02-P2UMA-170507 | 2018-08-28 | MRT-DS-REC-TT-180720 | FC | 4 | TRUE | TRUE | FALSE
4922 | MRT-VK02-P2UMA-170510 | 2018-08-28 | MRT-DS-REC-TT-180720 | FC | 4 | TRUE | TRUE | FALSE
4923 | MRT-CC02-P3UMA-170507 | 2018-08-28 | MRT-DS-REC-TT-180720 | FC | 4 | TRUE | TRUE | FALSE
4924 | MRT-VK02-P3UMA-170510 | 2018-08-28 | MRT-DS-REC-TT-180720 | FC | 4 | TRUE | TRUE | FALSE
4925 | MRT-CC02-P0UMA-170502 | 2018-08-28 | MRT-DS-REC-TT-180720 | FC | 4 | TRUE | TRUE | FALSE
4926 | MRT-XF00-P2SCA-127524 | 2018-08-29 | MRT-DS-REC-TT-180710-FC | FC | 1 | TRUE | TRUE | FALSE
4927 | MRT-XF00-P3SCA-127524 | 2018-08-29 | MRT-DS-REC-TT-180710-FC | FC | 1 | TRUE | TRUE | FALSE
4928 | MRT-YL00-P2ZEN-165101 | 2018-08-29 | MRT-DS-REC-TT-180721 | FA | 3 | TRUE | TRUE | FALSE
4929 | MRT-YL00-P3ZEN-165101 | 2018-08-29 | MRT-DS-REC-TT-180721 | FA | 3 | TRUE | TRUE | FALSE
4930 | MRT-YU01-P2MKC-230010 | 2018-08-29 | MRT-DS-REC-TT-180723 | FA | 1 | TRUE | TRUE | FALSE
4931 | MRT-YU01-P3MKC-230010 | 2018-08-29 | MRT-DS-REC-TT-180723 | FA | 1 | TRUE | TRUE | FALSE
4932 | MRT-YD02-P2LB-122063 | 2018-08-29 | MRT-DS-REC-TT-180722 | FI | 1 | TRUE | TRUE | FALSE
4933 | MRT-YD02-P3LB-122063 | 2018-08-29 | MRT-DS-REC-TT-180722 | FI | 1 | TRUE | TRUE | FALSE
4934 | MRT-YL00-P2MAJ-603207 | 2018-08-29 | MRT-DS-REC-TT-180724 | FC | 4 | TRUE | TRUE | FALSE
4935 | MRT-YL00-P3MAJ-604207 | 2018-08-29 | MRT-DS-REC-TT-180724 | FC | 4 | TRUE | TRUE | FALSE
4936 | MRT-CQ02-P2GM-128515 | 2018-08-29 | MRT-DS-REC-TT-180725 | FI | 0 | TRUE | FALSE | FALSE
4937 | MRT-CQ02-P3GM-128515 | 2018-08-29 | MRT-DS-REC-TT-180725 | FI | 0 | TRUE | FALSE | FALSE
4938 | MRT-XJ00-P3LCM-144000 | 2018-08-29 | MRT-DS-REC-TT-180726 | FI | 0 | TRUE | FALSE | FALSE
4939 | MRT-XJ00-P3LCA-144000 | 2018-08-29 | MRT-DS-REC-TT-180726 | FI | 0 | TRUE | FALSE | FALSE
4940 | MRT-YD00-P3CJA-240059 | 2018-08-29 | MRT-DS-REC-TT-180717 | FI | 0 | TRUE | FALSE | FALSE
4941 | MRT-YD00-P3CJA-240058 | 2018-08-29 | MRT-DS-REC-TT-180717 | FI | 0 | TRUE | FALSE | FALSE
4942 | MRT-YD00-P3CJA-240057 | 2018-08-29 | MRT-DS-REC-TT-180717 | FI | 0 | TRUE | FALSE | FALSE
4943 | MRT-YD00-P2CJA-240059 | 2018-08-29 | MRT-DS-REC-TT-180717 | FI | 0 | TRUE | FALSE | FALSE
4944 | MRT-YD00-P2CJA-240058 | 2018-08-29 | MRT-DS-REC-TT-180717 | FI | 0 | TRUE | FALSE | FALSE
4945 | MRT-YD00-P2CJA-240057 | 2018-08-29 | MRT-DS-REC-TT-180717 | FI | 0 | TRUE | FALSE | FALSE
7617 | MRT-YL13-P2CJJ-240061 | 2018-08-29 | MRT-DS-REC-TT-180592-FC | FC | 0 | TRUE | TRUE | FALSE
7618 | MRT-YL13-P3CJJ-240061 | 2018-08-29 | MRT-DS-REC-TT-180592-FC | FC | 0 | TRUE | TRUE | FALSE
4946 | MRT-YD00-P2LCB-127501 | 2018-08-30 | MRT-DS-REC-TT-180638-FC | FC | 2 | TRUE | TRUE | FALSE
4947 | MRT-YD00-P3LCB-127501 | 2018-08-30 | MRT-DS-REC-TT-180638-FC | FC | 2 | TRUE | TRUE | FALSE
4948 | MRT-UE00-P2LB-122008 | 2018-08-30 | MRT-DS-REC-TT-180727 | FC | 3 | TRUE | TRUE | FALSE
4949 | MRT-YD00-P2MKJ-220001 | 2018-08-30 | MRT-DS-REC-TT-180728 | FC | 1 | TRUE | TRUE | FALSE
4950 | MRT-YD00-P3MKW-220002 | 2018-08-30 | MRT-DS-REC-TT-180728 | FC | 1 | TRUE | TRUE | FALSE
4951 | MRT-YD00-P3MKW-220003 | 2018-08-30 | MRT-DS-REC-TT-180728 | FC | 1 | TRUE | TRUE | FALSE
4952 | MRT-YD00-P3MKW-220004 | 2018-08-30 | MRT-DS-REC-TT-180728 | FC | 1 | TRUE | TRUE | FALSE
4953 | MRT-YD00-P3MKG-220001 | 2018-08-30 | MRT-DS-REC-TT-180728 | FC | 1 | TRUE | TRUE | FALSE
4954 | MRT-YD00-P3MKG-220003 | 2018-08-30 | MRT-DS-REC-TT-180728 | FC | 1 | TRUE | TRUE | FALSE
4955 | MRT-YD00-P3MKG-220004 | 2018-08-30 | MRT-DS-REC-TT-180728 | FC | 1 | TRUE | TRUE | FALSE
4956 | MRT-YD00-P3MKG-220005 | 2018-08-30 | MRT-DS-REC-TT-180728 | FC | 1 | TRUE | TRUE | FALSE
4957 | MRT-YD00-P3MKG-220006 | 2018-08-30 | MRT-DS-REC-TT-180728 | FC | 1 | TRUE | TRUE | FALSE
4958 | MRT-YT01-P3MKA-240002 | 2018-08-30 | MRT-DS-REC-TT-180729 | FC | 1 | TRUE | TRUE | FALSE
4959 | MRT-CA06-P0UGA-186600 | 2018-08-30 | MRT-HK-REC-TT-180223 | FA | 3 | TRUE | TRUE | FALSE
4960 | MRT-CA01-P0UGA-186602 | 2018-08-30 | MRT-HK-REC-TT-180223 | FA | 3 | TRUE | TRUE | FALSE
4961 | MRT-CA06-P0UYX-187311 | 2018-08-30 | MRT-HK-REC-TT-180223 | FA | 1 | TRUE | TRUE | FALSE
4962 | MRT-CA01-P0UYX-187312 | 2018-08-30 | MRT-HK-REC-TT-180223 | FA | 1 | TRUE | TRUE | FALSE
4966 | MRT-CA00-P3CYP-160002 | 2018-08-30 | MRT-HK-REC-TT-180224 | FA | 1 | TRUE | TRUE | FALSE
4967 | MRT-YD00-P3CYP-160008 | 2018-08-30 | MRT-HK-REC-TT-180224 | FA | 0 | TRUE | FALSE | FALSE
4968 | MRT-YT01-P3CYP-160001 | 2018-08-30 | MRT-HK-REC-TT-180224 | FA | 0 | TRUE | FALSE | FALSE
4969 | MRT-XJ00-P3LBG-143000 | 2018-08-30 | MRT-DS-REC-TT-180730 | FI | 0 | TRUE | FALSE | FALSE
4970 | MRT-XJ00-P3LBG-144000 | 2018-08-30 | MRT-DS-REC-TT-180730 | FI | 0 | TRUE | FALSE | FALSE
4971 | MRT-YS00-P2LB-122092 | 2018-08-31 | MRT-DS-REC-TT-180732 | FA | 1 | TRUE | TRUE | FALSE
4972 | MRT-YS00-P3LB-122092 | 2018-08-31 | MRT-DS-REC-TT-180732 | FA | 1 | TRUE | TRUE | FALSE
4973 | MRT-XG07-P0ZEN-120050 | 2018-08-31 | MRT-DS-REC-TT-180733 | FC | 4 | TRUE | TRUE | FALSE
4974 | MRT-XJ00-P3PGB-144000 | 2018-08-31 | MRT-DS-REC-TT-180735 | FI | 0 | TRUE | FALSE | FALSE
4975 | MRT-XJ00-P2LB-122028 | 2018-09-03 | MRT-DS-REC-TT-180608-FC | FC | 1 | TRUE | TRUE | FALSE
4976 | MRT-XJ00-P3LB-122028 | 2018-09-03 | MRT-DS-REC-TT-180608-FC | FC | 1 | TRUE | TRUE | FALSE
4977 | MRT-CC02-P2UMA-170607 | 2018-09-03 | MRT-DS-REC-TT-180701-FC | FC | 4 | TRUE | TRUE | FALSE
4978 | MRT-CC02-P2UMA-170608 | 2018-09-03 | MRT-DS-REC-TT-180701-FC | FC | 4 | TRUE | TRUE | FALSE
4979 | MRT-CC02-P2UMA-170609 | 2018-09-03 | MRT-DS-REC-TT-180701-FC | FC | 4 | TRUE | TRUE | FALSE
4980 | MRT-VK02-P2UMA-170610 | 2018-09-03 | MRT-DS-REC-TT-180701-FC | FC | 3 | TRUE | TRUE | FALSE
4981 | MRT-CC02-P3UMA-170607 | 2018-09-03 | MRT-DS-REC-TT-180701-FC | FC | 4 | TRUE | TRUE | FALSE
4982 | MRT-CC02-P3UMA-170608 | 2018-09-03 | MRT-DS-REC-TT-180701-FC | FC | 4 | TRUE | TRUE | FALSE
4983 | MRT-CC02-P3UMA-170609 | 2018-09-03 | MRT-DS-REC-TT-180701-FC | FC | 4 | TRUE | TRUE | FALSE
4984 | MRT-VK02-P3UMA-170610 | 2018-09-03 | MRT-DS-REC-TT-180701-FC | FC | 3 | TRUE | TRUE | FALSE
4985 | MRT-CC02-P2UMA-170707 | 2018-09-03 | MRT-DS-REC-TT-180702-FC | FC | 4 | TRUE | TRUE | FALSE
4986 | MRT-CC02-P2UMA-170708 | 2018-09-03 | MRT-DS-REC-TT-180702-FC | FC | 4 | TRUE | TRUE | FALSE
4987 | MRT-CC02-P2UMA-170709 | 2018-09-03 | MRT-DS-REC-TT-180702-FC | FC | 4 | TRUE | TRUE | FALSE
4988 | MRT-CC02-P3UMA-170707 | 2018-09-03 | MRT-DS-REC-TT-180702-FC | FC | 4 | TRUE | TRUE | FALSE
4989 | MRT-CC02-P3UMA-170708 | 2018-09-03 | MRT-DS-REC-TT-180702-FC | FC | 4 | TRUE | TRUE | FALSE
4990 | MRT-CC02-P3UMA-170709 | 2018-09-03 | MRT-DS-REC-TT-180702-FC | FC | 4 | TRUE | TRUE | FALSE
4991 | MRT-VK02-P3UMA-170710 | 2018-09-03 | MRT-DS-REC-TT-180702-FC | FC | 3 | TRUE | TRUE | FALSE
4992 | MRT-CC07-P2UHA-170101 | 2018-09-03 | MRT-DS-REC-TT-180734 | FC | 2 | TRUE | TRUE | FALSE
4993 | MRT-CC07-P3UHA-170101 | 2018-09-03 | MRT-DS-REC-TT-180734 | FC | 2 | TRUE | TRUE | FALSE
4994 | MRT-CC02-P2UHA-170103 | 2018-09-03 | MRT-DS-REC-TT-180716-FC | FC | 6 | TRUE | TRUE | FALSE
4995 | MRT-CC02-P2UHA-170104 | 2018-09-03 | MRT-DS-REC-TT-180716-FC | FC | 5 | TRUE | TRUE | FALSE
4996 | MRT-VK02-P2UHA-170106 | 2018-09-03 | MRT-DS-REC-TT-180716-FC | FC | 6 | TRUE | TRUE | FALSE
4997 | MRT-CC02-P3UHA-170103 | 2018-09-03 | MRT-DS-REC-TT-180716-FC | FC | 6 | TRUE | TRUE | FALSE
4998 | MRT-CC02-P3UHA-170104 | 2018-09-03 | MRT-DS-REC-TT-180716-FC | FC | 5 | TRUE | TRUE | FALSE
4999 | MRT-VK02-P3UHA-170106 | 2018-09-03 | MRT-DS-REC-TT-180716-FC | FC | 6 | TRUE | TRUE | FALSE
5000 | MRT-YD00-P2LB-122056 | 2018-09-03 | MRT-DS-REC-TT-180706-FC | FC | 2 | TRUE | TRUE | FALSE
5001 | MRT-YD00-P3LB-122056 | 2018-09-03 | MRT-DS-REC-TT-180706-FC | FC | 2 | TRUE | TRUE | FALSE
5002 | MRT-YT01-P2LAC-126005 | 2018-09-03 | MRT-DS-REC-TT-180712-FC | FC | 4 | TRUE | TRUE | FALSE
5003 | MRT-YT01-P3LAC-126005 | 2018-09-03 | MRT-DS-REC-TT-180712-FC | FC | 4 | TRUE | TRUE | FALSE
5004 | MRT-YT01-P2LAC-126055 | 2018-09-03 | MRT-DS-REC-TT-180712-FC | FC | 2 | TRUE | TRUE | FALSE
5005 | MRT-YT01-P3LAC-126055 | 2018-09-03 | MRT-DS-REC-TT-180712-FC | FC | 2 | TRUE | TRUE | FALSE
5006 | MRT-YD00-P2ZEN-113400 | 2018-09-03 | MRT-DS-REC-TT-180736 | FC | 2 | TRUE | TRUE | FALSE
5007 | MRT-YT01-P2ZEN-113401 | 2018-09-03 | MRT-DS-REC-TT-180736 | FC | 2 | TRUE | TRUE | FALSE
5008 | MRT-YD00-P3ZEN-113400 | 2018-09-03 | MRT-DS-REC-TT-180736 | FC | 2 | TRUE | TRUE | FALSE
5009 | MRT-YT01-P3ZEN-113401 | 2018-09-03 | MRT-DS-REC-TT-180736 | FC | 2 | TRUE | TRUE | FALSE
5010 | MRT-YD00-P2ZEN-113500 | 2018-09-03 | MRT-DS-REC-TT-180737 | FC | 2 | TRUE | TRUE | FALSE
5011 | MRT-YD00-P3ZEN-113500 | 2018-09-03 | MRT-DS-REC-TT-180737 | FC | 2 | TRUE | TRUE | FALSE
5012 | MRT-YT01-P2ZEN-113501 | 2018-09-03 | MRT-DS-REC-TT-180737 | FC | 2 | TRUE | TRUE | FALSE
5013 | MRT-YT01-P3ZEN-113501 | 2018-09-03 | MRT-DS-REC-TT-180737 | FC | 2 | TRUE | TRUE | FALSE
5014 | MRT-XG02-P0GHD-120001 | 2018-09-03 | MRT-DS-REC-TT-180440-FC | FC | 4 | TRUE | TRUE | FALSE
5015 | MRT-CA05-P0UMA-180061 | 2018-09-03 | MRT-DS-REC-TT-180415-FC | FC | 3 | TRUE | TRUE | FALSE
5016 | MRT-CA05-P0UMA-180062 | 2018-09-03 | MRT-DS-REC-TT-180415-FC | FC | 3 | TRUE | TRUE | FALSE
5017 | MRT-YL00-P2GM-128512 | 2018-09-04 | MRT-DS-REC-TT-180740 | FI | 1 | TRUE | TRUE | FALSE
5018 | MRT-YR05-P2GM-128511 | 2018-09-04 | MRT-DS-REC-TT-180740 | FI | 1 | TRUE | TRUE | FALSE
5019 | MRT-YL00-P3GM-128512 | 2018-09-04 | MRT-DS-REC-TT-180740 | FI | 1 | TRUE | TRUE | FALSE
5020 | MRT-YR05-P3GM-128511 | 2018-09-04 | MRT-DS-REC-TT-180740 | FI | 1 | TRUE | TRUE | FALSE
5021 | MRT-XH01-P3UMA-144000 | 2018-09-04 | MRT-DS-REC-TT-180739 | FA | 0 | TRUE | FALSE | FALSE
5022 | MRT-DP00-P0ZEN-070001 | 2018-09-04 | MRT-DS-REC-TT-180731 | FC | 3 | TRUE | TRUE | FALSE
5023 | MRT-CN00-P3ZEN-110102 | 2018-09-04 | MRT-DS-REC-TT-180742 | FA | 1 | TRUE | TRUE | FALSE
5024 | MRT-YE00-P2MKA-230001 | 2018-09-04 | MRT-DS-REC-TT-180741 | FC | 1 | TRUE | TRUE | FALSE
5025 | MRT-YK00-P2BAT-240001 | 2018-09-04 | MRT-DS-REC-TT-180741 | FC | 1 | TRUE | TRUE | FALSE
5026 | MRT-UC02-P2BAT-240001 | 2018-09-04 | MRT-DS-REC-TT-180741 | FC | 1 | TRUE | TRUE | FALSE
5027 | MRT-YE00-P3MKA-230001 | 2018-09-04 | MRT-DS-REC-TT-180741 | FC | 1 | TRUE | TRUE | FALSE
5030 | MRT-YL00-P2MAG-601010 | 2018-09-04 | MRT-DS-REC-TT-180738 | FA | 1 | TRUE | TRUE | FALSE
5031 | MRT-YL00-P3MAG-602010 | 2018-09-04 | MRT-DS-REC-TT-180738 | FA | 1 | TRUE | TRUE | FALSE
5028 | MRT-YK00-P2SCA-127521 | 2018-09-05 | MRT-DS-REC-TT-180709-FC | FC | 2 | TRUE | TRUE | FALSE
5029 | MRT-YK00-P3SCA-127521 | 2018-09-05 | MRT-DS-REC-TT-180709-FC | FC | 2 | TRUE | TRUE | FALSE
5032 | MRT-XM00-P3BBT-150448 | 2018-09-05 | MRT-HK-REC-TT-180225 | FA | 0 | TRUE | FALSE | FALSE
5033 | MRT-XM00-P2BBT-150431 | 2018-09-05 | MRT-HK-REC-TT-180225 | FA | 0 | TRUE | FALSE | FALSE
5034 | MRT-XJ00-P3MKA-220001 | 2018-09-06 | MRT-DS-REC-TT-180743 | FC | 2 | TRUE | TRUE | FALSE
5035 | MRT-UC07-P0ZEN-100001 | 2018-09-06 | MRT-DS-REC-TT-180626-FC | FC | 4 | TRUE | TRUE | FALSE
5036 | MRT-UC08-P0ZEN-100002 | 2018-09-06 | MRT-DS-REC-TT-180626-FC | FC | 3 | TRUE | TRUE | FALSE
5037 | MRT-YT01-P2MAJ-603100 | 2018-09-06 | MRT-DS-REC-TT-180713-FC | FC | 4 | TRUE | TRUE | FALSE
5038 | MRT-XG02-P2MAJ-603101 | 2018-09-06 | MRT-DS-REC-TT-180713-FC | FC | 4 | TRUE | TRUE | FALSE
5039 | MRT-YK08-P2MAJ-603102 | 2018-09-06 | MRT-DS-REC-TT-180713-FC | FC | 3 | TRUE | TRUE | FALSE
5040 | MRT-XN00-P2MAJ-603106 | 2018-09-06 | MRT-DS-REC-TT-180713-FC | FC | 4 | TRUE | TRUE | FALSE
5041 | MRT-YT01-P3MAJ-604100 | 2018-09-06 | MRT-DS-REC-TT-180713-FC | FC | 4 | TRUE | TRUE | FALSE
5042 | MRT-XG02-P3MAJ-604101 | 2018-09-06 | MRT-DS-REC-TT-180713-FC | FC | 4 | TRUE | TRUE | FALSE
5043 | MRT-YK08-P3MAJ-604102 | 2018-09-06 | MRT-DS-REC-TT-180713-FC | FC | 3 | TRUE | TRUE | FALSE
5044 | MRT-XN00-P3MAJ-604106 | 2018-09-06 | MRT-DS-REC-TT-180713-FC | FC | 4 | TRUE | TRUE | FALSE
5045 | MRT-YL00-P2ZEN-165101 | 2018-09-06 | MRT-DS-REC-TT-180721-FC | FC | 3 | TRUE | TRUE | FALSE
5046 | MRT-YL00-P3ZEN-165101 | 2018-09-06 | MRT-DS-REC-TT-180721-FC | FC | 3 | TRUE | TRUE | FALSE
5047 | MRT-YF00-P2CBA-161203 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5048 | MRT-YF00-P2CGA-161303 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5049 | MRT-YF00-P3CBA-161203 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5050 | MRT-YF00-P3CGA-161303 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5051 | MRT-YF00-P2CBA-161204 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5052 | MRT-YF00-P2CGA-161304 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5053 | MRT-YF00-P3CBA-161204 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5054 | MRT-YF00-P3CGA-161304 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5055 | MRT-YF00-P2CBA-161205 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5056 | MRT-YF00-P2CGA-161305 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5057 | MRT-YF00-P3CBA-161205 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5058 | MRT-YF00-P3CGA-161305 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5059 | MRT-YF00-P2CBA-161206 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5060 | MRT-YF00-P2CGA-161306 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5061 | MRT-YF00-P3CBA-161206 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5062 | MRT-YF00-P3CGA-161306 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5063 | MRT-YF00-P2CBA-161207 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5064 | MRT-YF00-P2CGA-161307 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5065 | MRT-YF00-P3CBA-161207 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5066 | MRT-YF00-P3CGA-161307 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5067 | MRT-YF00-P2CBA-161208 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5068 | MRT-YF00-P2CGA-161308 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5069 | MRT-YF00-P3CBA-161208 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5070 | MRT-YF00-P3CGA-161308 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5071 | MRT-YF00-P0CBA-161221 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5072 | MRT-YF00-P0CGA-161321 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5073 | MRT-YF00-P2CBA-161209 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5074 | MRT-YF00-P2CGA-161309 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5075 | MRT-YF00-P3CBA-161209 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5076 | MRT-YF00-P3CGA-161309 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5077 | MRT-YF00-P0CBA-161222 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5078 | MRT-YF00-P0CGA-161322 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5079 | MRT-YF00-P2CBA-161211 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5080 | MRT-YF00-P2CBA-161212 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5081 | MRT-YF00-P2CBA-161210 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5082 | MRT-YF00-P2CGA-161311 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5083 | MRT-YF00-P2CGA-161312 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5084 | MRT-YF00-P2CGA-161310 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5085 | MRT-YF00-P3CBA-161211 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5086 | MRT-YF00-P3CBA-161212 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5087 | MRT-YF00-P3CBA-161210 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5088 | MRT-YF00-P3CGA-161311 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5089 | MRT-YF00-P3CGA-161312 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5090 | MRT-YF00-P3CGA-161310 | 2018-09-06 | MRT-DS-REC-TT-180582-FC | FC | 2 | TRUE | TRUE | FALSE
5091 | MRT-XJ00-P0GMA-140001 | 2018-09-06 | MRT-DS-REC-TT-180744 | FI | 0 | TRUE | FALSE | FALSE
5092 | MRT-CC02-P2UAG-170307 | 2018-09-07 | MRT-DS-REC-TT-180745 | FC | 1 | TRUE | TRUE | FALSE
5093 | MRT-CC02-P3UAG-170307 | 2018-09-07 | MRT-DS-REC-TT-180745 | FC | 1 | TRUE | TRUE | FALSE
5094 | MRT-CC02-P2UAG-170308 | 2018-09-07 | MRT-DS-REC-TT-180746 | FA | 1 | TRUE | TRUE | FALSE
5095 | MRT-CC02-P3UAG-170308 | 2018-09-07 | MRT-DS-REC-TT-180746 | FA | 1 | TRUE | TRUE | FALSE
5096 | MRT-QM03-P0ZEN-155008 | 2018-09-07 | MRT-HK-REC-TT-180226 | FA | 0 | TRUE | FALSE | FALSE
5097 | MRT-QM03-P0ZEN-155007 | 2018-09-07 | MRT-HK-REC-TT-180226 | FA | 0 | TRUE | FALSE | FALSE
5098 | MRT-XJ00-P0LBG-141000 | 2018-09-07 | MRT-DS-REC-TT-180747 | FI | 0 | TRUE | FALSE | FALSE
5099 | MRT-YT02-P2LAC-126011 | 2018-09-07 | MRT-DS-REC-TT-180748 | FC | 3 | TRUE | TRUE | FALSE
5100 | MRT-YT02-P3LAC-126011 | 2018-09-07 | MRT-DS-REC-TT-180748 | FC | 3 | TRUE | TRUE | FALSE
5101 | MRT-YT02-P2LAC-126061 | 2018-09-07 | MRT-DS-REC-TT-180748 | FC | 3 | TRUE | TRUE | FALSE
5102 | MRT-YT02-P3LAC-126061 | 2018-09-07 | MRT-DS-REC-TT-180748 | FC | 3 | TRUE | TRUE | FALSE
5103 | MRT-YV02-P3ZEN-163116 | 2018-09-10 | MRT-DS-REC-TT-180625-FC | FC | 0 | TRUE | TRUE | FALSE
5104 | MRT-YL15-P3ZEN-163117 | 2018-09-10 | MRT-DS-REC-TT-180625-FC | FC | 0 | TRUE | TRUE | FALSE
5105 | MRT-YD02-P2LB-122063 | 2018-09-10 | MRT-DS-REC-TT-180722-FC | FC | 1 | TRUE | TRUE | FALSE
5106 | MRT-YD02-P3LB-122063 | 2018-09-10 | MRT-DS-REC-TT-180722-FC | FC | 1 | TRUE | TRUE | FALSE
5107 | MRT-YU01-P2MKC-230010 | 2018-09-10 | MRT-DS-REC-TT-180723-FC | FC | 1 | TRUE | TRUE | FALSE
5108 | MRT-YU01-P3MKC-230010 | 2018-09-10 | MRT-DS-REC-TT-180723-FC | FC | 1 | TRUE | TRUE | FALSE
5109 | MRT-CC02-P0UAA-176070 | 2018-09-10 | MRT-HK-REC-TT-180227 | FA | 1 | TRUE | TRUE | FALSE
5110 | MRT-CC02-P0UAA-176075 | 2018-09-10 | MRT-HK-REC-TT-180227 | FA | 1 | TRUE | TRUE | FALSE
5111 | MRT-CC03-P0UAA-176085 | 2018-09-10 | MRT-HK-REC-TT-180227 | FA | 1 | TRUE | TRUE | FALSE
5112 | MRT-CC02-P0UAA-176071 | 2018-09-10 | MRT-HK-REC-TT-180227 | FA | 1 | TRUE | TRUE | FALSE
5113 | MRT-CC02-P0UAA-176072 | 2018-09-10 | MRT-HK-REC-TT-180227 | FA | 1 | TRUE | TRUE | FALSE
5114 | MRT-CC02-P0UAA-176073 | 2018-09-10 | MRT-HK-REC-TT-180227 | FA | 1 | TRUE | TRUE | FALSE
5115 | MRT-CC02-P0UAA-176074 | 2018-09-10 | MRT-HK-REC-TT-180227 | FA | 1 | TRUE | TRUE | FALSE
5116 | MRT-CC02-P0UAA-176076 | 2018-09-10 | MRT-HK-REC-TT-180227 | FA | 1 | TRUE | TRUE | FALSE
5117 | MRT-CC02-P0UAA-176077 | 2018-09-10 | MRT-HK-REC-TT-180227 | FA | 1 | TRUE | TRUE | FALSE
5118 | MRT-CC03-P0UAA-176080 | 2018-09-10 | MRT-HK-REC-TT-180227 | FA | 1 | TRUE | TRUE | FALSE
5119 | MRT-CC04-P0ULY-176206 | 2018-09-10 | MRT-HK-REC-TT-180228 | FA | 0 | TRUE | FALSE | FALSE
5120 | MRT-CC04-P0ULY-176205 | 2018-09-10 | MRT-HK-REC-TT-180228 | FA | 0 | TRUE | FALSE | FALSE
5121 | MRT-CC04-P0ULY-176204 | 2018-09-10 | MRT-HK-REC-TT-180228 | FA | 0 | TRUE | FALSE | FALSE
5122 | MRT-CC04-P0ULY-176203 | 2018-09-10 | MRT-HK-REC-TT-180228 | FA | 0 | TRUE | FALSE | FALSE
5123 | MRT-CC04-P0ULY-176202 | 2018-09-10 | MRT-HK-REC-TT-180228 | FA | 0 | TRUE | FALSE | FALSE
5124 | MRT-CC04-P0ULY-176201 | 2018-09-10 | MRT-HK-REC-TT-180228 | FA | 0 | TRUE | FALSE | FALSE
5125 | MRT-CC04-P0ULY-176200 | 2018-09-10 | MRT-HK-REC-TT-180228 | FA | 0 | TRUE | FALSE | FALSE
5126 | MRT-XG02-P2QC-130001 | 2018-09-10 | MRT-DS-REC-TT-180749 | FC | 3 | TRUE | TRUE | FALSE
5127 | MRT-XG02-P3QC-130001 | 2018-09-10 | MRT-DS-REC-TT-180749 | FC | 3 | TRUE | TRUE | FALSE
5128 | MRT-YD00-P2QC-130005 | 2018-09-10 | MRT-DS-REC-TT-180750 | FC | 3 | TRUE | TRUE | FALSE
5129 | MRT-YD00-P3QC-130005 | 2018-09-10 | MRT-DS-REC-TT-180750 | FC | 3 | TRUE | TRUE | FALSE
5130 | MRT-YF02-P2QC-130006 | 2018-09-10 | MRT-DS-REC-TT-180751 | FC | 3 | TRUE | TRUE | FALSE
5131 | MRT-YF02-P3QC-130006 | 2018-09-10 | MRT-DS-REC-TT-180751 | FC | 3 | TRUE | TRUE | FALSE
5132 | MRT-XB02-P2QC-130009 | 2018-09-10 | MRT-DS-REC-TT-180752 | FC | 2 | TRUE | TRUE | FALSE
5133 | MRT-XB02-P3QC-130009 | 2018-09-10 | MRT-DS-REC-TT-180752 | FC | 2 | TRUE | TRUE | FALSE
5134 | MRT-YL22-P2QC-130018 | 2018-09-10 | MRT-DS-REC-TT-180753 | FI | 1 | TRUE | TRUE | FALSE
5135 | MRT-YL22-P3QC-130018 | 2018-09-10 | MRT-DS-REC-TT-180753 | FI | 1 | TRUE | TRUE | FALSE
5136 | MRT-YE00-P2QC-130021 | 2018-09-10 | MRT-DS-REC-TT-180754 | FC | 3 | TRUE | TRUE | FALSE
5137 | MRT-YE00-P3QC-130021 | 2018-09-10 | MRT-DS-REC-TT-180754 | FC | 3 | TRUE | TRUE | FALSE
5138 | MRT-YD05-P2QC-130035 | 2018-09-10 | MRT-DS-REC-TT-180755 | FI | 1 | TRUE | TRUE | FALSE
5139 | MRT-YD05-P3QC-130035 | 2018-09-10 | MRT-DS-REC-TT-180755 | FI | 1 | TRUE | TRUE | FALSE
5140 | MRT-YS01-P2QC-130020 | 2018-09-10 | MRT-DS-REC-TT-180756 | FI | 1 | TRUE | TRUE | FALSE
5141 | MRT-YS01-P3QC-130020 | 2018-09-10 | MRT-DS-REC-TT-180756 | FI | 1 | TRUE | TRUE | FALSE
5142 | MRT-YT01-P2QU-130031 | 2018-09-10 | MRT-DS-REC-TT-180757 | FI | 3 | TRUE | TRUE | FALSE
5143 | MRT-YF00-P2QU-130033 | 2018-09-10 | MRT-DS-REC-TT-180757 | FI | 3 | TRUE | TRUE | FALSE
5144 | MRT-YT01-P3QU-130031 | 2018-09-10 | MRT-DS-REC-TT-180757 | FI | 3 | TRUE | TRUE | FALSE
5145 | MRT-YF00-P3QU-130033 | 2018-09-10 | MRT-DS-REC-TT-180757 | FI | 2 | TRUE | TRUE | FALSE
5146 | MRT-XA00-P2QU-130025 | 2018-09-10 | MRT-DS-REC-TT-180758 | FC | 4 | TRUE | TRUE | FALSE
5147 | MRT-XA00-P3QU-130025 | 2018-09-10 | MRT-DS-REC-TT-180758 | FC | 4 | TRUE | TRUE | FALSE
5148 | MRT-YD00-P2LB-122053 | 2018-09-11 | MRT-DS-REC-TT-180707-FC | FC | 2 | TRUE | TRUE | FALSE
5149 | MRT-YD00-P3LB-122053 | 2018-09-11 | MRT-DS-REC-TT-180707-FC | FC | 2 | TRUE | TRUE | FALSE
5150 | MRT-YD00-P2MKJ-220001 | 2018-09-11 | MRT-DS-REC-TT-180728-FC | FC | 1 | TRUE | TRUE | FALSE
5151 | MRT-YD00-P3MKW-220002 | 2018-09-11 | MRT-DS-REC-TT-180728-FC | FC | 1 | TRUE | TRUE | FALSE
5152 | MRT-YD00-P3MKW-220003 | 2018-09-11 | MRT-DS-REC-TT-180728-FC | FC | 1 | TRUE | TRUE | FALSE
5153 | MRT-YD00-P3MKW-220004 | 2018-09-11 | MRT-DS-REC-TT-180728-FC | FC | 1 | TRUE | TRUE | FALSE
5154 | MRT-YD00-P3MKG-220001 | 2018-09-11 | MRT-DS-REC-TT-180728-FC | FC | 1 | TRUE | TRUE | FALSE
5155 | MRT-YD00-P3MKG-220003 | 2018-09-11 | MRT-DS-REC-TT-180728-FC | FC | 1 | TRUE | TRUE | FALSE
5156 | MRT-YD00-P3MKG-220004 | 2018-09-11 | MRT-DS-REC-TT-180728-FC | FC | 1 | TRUE | TRUE | FALSE
5157 | MRT-YD00-P3MKG-220005 | 2018-09-11 | MRT-DS-REC-TT-180728-FC | FC | 1 | TRUE | TRUE | FALSE
5158 | MRT-YD00-P3MKG-220006 | 2018-09-11 | MRT-DS-REC-TT-180728-FC | FC | 1 | TRUE | TRUE | FALSE
5159 | MRT-XG02-P0GKC-120001 | 2018-09-11 | MRT-DS-REC-TT-180719-FC | FC | 4 | TRUE | TRUE | FALSE
5160 | MRT-XW01-P2SCA-127503 | 2018-09-11 | MRT-DS-REC-TT-180474-FC | FC | 2 | TRUE | TRUE | FALSE
5161 | MRT-XW01-P3SCA-127503 | 2018-09-11 | MRT-DS-REC-TT-180474-FC | FC | 2 | TRUE | TRUE | FALSE
5162 | MRT-UBE-P2BBT-150418 | 2018-09-11 | MRT-HK-REC-TT-180229 | FA | 1 | TRUE | TRUE | FALSE
5163 | MRT-UBE-P3BBT-150435 | 2018-09-11 | MRT-HK-REC-TT-180229 | FA | 1 | TRUE | TRUE | FALSE
5164 | MRT-YT01-P2BBT-150421 | 2018-09-11 | MRT-HK-REC-TT-180229 | FA | 1 | TRUE | TRUE | FALSE
5165 | MRT-YT01-P3BBT-150438 | 2018-09-11 | MRT-HK-REC-TT-180229 | FA | 1 | TRUE | TRUE | FALSE
5166 | MRT-YD00-P3BAT-150401 | 2018-09-11 | MRT-HK-REC-TT-180229 | FA | 1 | TRUE | TRUE | FALSE
5167 | MRT-XA00-P2QC-130002 | 2018-09-12 | MRT-DS-REC-TT-180760 | FC | 3 | TRUE | TRUE | FALSE
5168 | MRT-XA00-P3QC-130002 | 2018-09-12 | MRT-DS-REC-TT-180760 | FC | 3 | TRUE | TRUE | FALSE
5169 | MRT-XH01-P2QC-130011 | 2018-09-12 | MRT-DS-REC-TT-180761 | FC | 2 | TRUE | TRUE | FALSE
5170 | MRT-XH01-P3QC-130011 | 2018-09-12 | MRT-DS-REC-TT-180761 | FC | 2 | TRUE | TRUE | FALSE
5171 | MRT-YK00-P2QC-130022 | 2018-09-12 | MRT-DS-REC-TT-180762 | FC | 3 | TRUE | TRUE | FALSE
5172 | MRT-YK00-P3QC-130022 | 2018-09-12 | MRT-DS-REC-TT-180762 | FC | 3 | TRUE | TRUE | FALSE
5173 | MRT-CC02-P2UAG-170308 | 2018-09-12 | MRT-DS-REC-TT-180746-FC | FC | 1 | TRUE | TRUE | FALSE
5174 | MRT-CC02-P3UAG-170308 | 2018-09-12 | MRT-DS-REC-TT-180746-FC | FC | 1 | TRUE | TRUE | FALSE
5175 | MRT-CC02-P0UMA-170602 | 2018-09-12 | MRT-DS-REC-TT-180476-FC | FC | 2 | TRUE | TRUE | FALSE
5176 | MRT-CC02-P2UMA-170507 | 2018-09-12 | MRT-DS-REC-TT-180720-FC | FC | 4 | TRUE | TRUE | FALSE
5177 | MRT-VK02-P2UMA-170510 | 2018-09-12 | MRT-DS-REC-TT-180720-FC | FC | 4 | TRUE | TRUE | FALSE
5178 | MRT-CC02-P3UMA-170507 | 2018-09-12 | MRT-DS-REC-TT-180720-FC | FC | 4 | TRUE | TRUE | FALSE
5179 | MRT-VK02-P3UMA-170510 | 2018-09-12 | MRT-DS-REC-TT-180720-FC | FC | 4 | TRUE | TRUE | FALSE
5180 | MRT-CC02-P0UMA-170502 | 2018-09-12 | MRT-DS-REC-TT-180720-FC | FC | 4 | TRUE | TRUE | FALSE
5181 | MRT-CC07-P2UHA-170101 | 2018-09-12 | MRT-DS-REC-TT-180734-FC | FC | 2 | TRUE | TRUE | FALSE
5182 | MRT-CC07-P3UHA-170101 | 2018-09-12 | MRT-DS-REC-TT-180734-FC | FC | 2 | TRUE | TRUE | FALSE
5183 | MRT-UE00-P2LB-122008 | 2018-09-12 | MRT-DS-REC-TT-180727-FC | FC | 3 | TRUE | TRUE | FALSE
5184 | MRT-YT01-P3MKA-240002 | 2018-09-12 | MRT-DS-REC-TT-180729-FC | FC | 1 | TRUE | TRUE | FALSE
5185 | MRT-XG02-P0ZEN-110002 | 2018-09-13 | MRT-DS-REC-TT-170070-FC | FC | 2 | TRUE | FALSE | FALSE
5186 | MRT-XS00-P0GHD-120001 | 2018-09-13 | MRT-DS-REC-TT-170089-FC | FC | 2 | TRUE | FALSE | FALSE
5187 | MRT-XS00-P0GKC-120001 | 2018-09-13 | MRT-DS-REC-TT-170089-FC | FC | 2 | TRUE | FALSE | FALSE
5188 | MRT-XS00-P2SCA-120015 | 2018-09-13 | MRT-DS-REC-TT-170090-FC | FC | 2 | TRUE | FALSE | FALSE
5189 | MRT-XS00-P3SCA-120015 | 2018-09-13 | MRT-DS-REC-TT-170090-FC | FC | 2 | TRUE | FALSE | FALSE
5190 | MRT-XS00-P2PA-110404 | 2018-09-13 | MRT-DS-REC-TT-170096-FC | FC | 2 | TRUE | FALSE | FALSE
5191 | MRT-XS00-P2PG-110405 | 2018-09-13 | MRT-DS-REC-TT-170096-FC | FC | 2 | TRUE | FALSE | FALSE
5192 | MRT-XS00-P3PA-110404 | 2018-09-13 | MRT-DS-REC-TT-170096-FC | FC | 2 | TRUE | FALSE | FALSE
5193 | MRT-XS00-P3PG-110405 | 2018-09-13 | MRT-DS-REC-TT-170096-FC | FC | 2 | TRUE | FALSE | FALSE
5194 | MRT-YK08-P0ZEN-020004 | 2018-09-13 | MRT-DS-REC-TT-170100-FC | FC | 2 | TRUE | FALSE | FALSE
5195 | MRT-XG05-P0ZEN-110001 | 2018-09-13 | MRT-DS-REC-TT-170104-FC | FC | 3 | TRUE | FALSE | FALSE
5196 | MRT-XW03-P2SCA-120017 | 2018-09-13 | MRT-DS-REC-TT-170111-FC | FC | 2 | TRUE | FALSE | FALSE
5197 | MRT-XW03-P3SCA-120017 | 2018-09-13 | MRT-DS-REC-TT-170111-FC | FC | 2 | TRUE | FALSE | FALSE
5198 | MRT-CV03-P0ZEN-140002 | 2018-09-13 | MRT-DS-REC-TT-170117-FC | FC | 2 | TRUE | FALSE | FALSE
5199 | MRT-DE00-P0ZEN-140001 | 2018-09-13 | MRT-DS-REC-TT-170117-FC | FC | 2 | TRUE | FALSE | FALSE
5200 | MRT-XS00-P0GHC-110044 | 2018-09-13 | MRT-DS-REC-TT-170123-FC | FC | 2 | TRUE | FALSE | FALSE
5201 | MRT-XS00-P2LA-110402 | 2018-09-13 | MRT-DS-REC-TT-170123-FC | FC | 3 | TRUE | FALSE | FALSE
5202 | MRT-XS00-P2LBA-110400 | 2018-09-13 | MRT-DS-REC-TT-170123-FC | FC | 3 | TRUE | FALSE | FALSE
5203 | MRT-XS00-P2LBG-110401 | 2018-09-13 | MRT-DS-REC-TT-170123-FC | FC | 3 | TRUE | FALSE | FALSE
5204 | MRT-XS00-P2LC-110403 | 2018-09-13 | MRT-DS-REC-TT-170123-FC | FC | 3 | TRUE | FALSE | FALSE
5205 | MRT-XS00-P2PA-110400 | 2018-09-13 | MRT-DS-REC-TT-170123-FC | FC | 2 | TRUE | FALSE | FALSE
5206 | MRT-XS00-P3LA-110402 | 2018-09-13 | MRT-DS-REC-TT-170123-FC | FC | 3 | TRUE | FALSE | FALSE
5207 | MRT-XS00-P3LBA-110400 | 2018-09-13 | MRT-DS-REC-TT-170123-FC | FC | 3 | TRUE | FALSE | FALSE
5208 | MRT-XS00-P3LBG-110401 | 2018-09-13 | MRT-DS-REC-TT-170123-FC | FC | 3 | TRUE | FALSE | FALSE
5209 | MRT-XS00-P3LC-110403 | 2018-09-13 | MRT-DS-REC-TT-170123-FC | FC | 3 | TRUE | FALSE | FALSE
5210 | MRT-XS00-P3PA-110400 | 2018-09-13 | MRT-DS-REC-TT-170123-FC | FC | 2 | TRUE | FALSE | FALSE
5211 | MRT-XW03-P0GHC-110051 | 2018-09-13 | MRT-DS-REC-TT-170127-FC | FC | 2 | TRUE | FALSE | FALSE
5212 | MRT-XW03-P2LA-110500 | 2018-09-13 | MRT-DS-REC-TT-170127-FC | FC | 2 | TRUE | FALSE | FALSE
5213 | MRT-XW03-P2LC-110501 | 2018-09-13 | MRT-DS-REC-TT-170127-FC | FC | 2 | TRUE | FALSE | FALSE
5214 | MRT-XW03-P2PAC-113500 | 2018-09-13 | MRT-DS-REC-TT-170127-FC | FC | 2 | TRUE | FALSE | FALSE
5215 | MRT-XW03-P2PGB-113110 | 2018-09-13 | MRT-DS-REC-TT-170127-FC | FC | 2 | TRUE | FALSE | FALSE
5216 | MRT-XW03-P3LA-110500 | 2018-09-13 | MRT-DS-REC-TT-170127-FC | FC | 2 | TRUE | FALSE | FALSE
5217 | MRT-XW03-P3LC-110501 | 2018-09-13 | MRT-DS-REC-TT-170127-FC | FC | 2 | TRUE | FALSE | FALSE
5218 | MRT-XW03-P3PAC-113500 | 2018-09-13 | MRT-DS-REC-TT-170127-FC | FC | 2 | TRUE | FALSE | FALSE
5219 | MRT-XW03-P3PGB-113110 | 2018-09-13 | MRT-DS-REC-TT-170127-FC | FC | 2 | TRUE | FALSE | FALSE
5220 | MRT-YD00-P3MKA-220001 | 2018-09-13 | MRT-DS-REC-TT-170136-FC | FC | 1 | TRUE | FALSE | FALSE
5221 | MRT-CA06-P0UCA-180101 | 2018-09-13 | MRT-DS-REC-TT-170157-FC | FC | 2 | TRUE | FALSE | FALSE
5222 | MRT-XG02-P2SCA-120004 | 2018-09-13 | MRT-DS-REC-TT-180007-FC | FC | 4 | TRUE | FALSE | FALSE
5223 | MRT-XG02-P2SCA-120005 | 2018-09-13 | MRT-DS-REC-TT-180007-FC | FC | 4 | TRUE | FALSE | FALSE
5224 | MRT-XG02-P2SCA-120006 | 2018-09-13 | MRT-DS-REC-TT-180007-FC | FC | 4 | TRUE | FALSE | FALSE
5225 | MRT-XG02-P3SCA-120004 | 2018-09-13 | MRT-DS-REC-TT-180007-FC | FC | 4 | TRUE | FALSE | FALSE
5226 | MRT-XG02-P3SCA-120005 | 2018-09-13 | MRT-DS-REC-TT-180007-FC | FC | 4 | TRUE | FALSE | FALSE
5227 | MRT-XG02-P3SCA-120006 | 2018-09-13 | MRT-DS-REC-TT-180007-FC | FC | 4 | TRUE | FALSE | FALSE
5228 | MRT-YB03-P2LB-122048 | 2018-09-13 | MRT-DS-REC-TT-180025-FC | FC | 1 | TRUE | FALSE | FALSE
5229 | MRT-XG02-P2MAV-120054 | 2018-09-13 | MRT-DS-REC-TT-180032-FC | FC | 3 | TRUE | FALSE | FALSE
5230 | MRT-XG02-P3MAV-120054 | 2018-09-13 | MRT-DS-REC-TT-180032-FC | FC | 3 | TRUE | FALSE | FALSE
5231 | MRT-XS00-P2MAV-120053 | 2018-09-13 | MRT-DS-REC-TT-180032-FC | FC | 3 | TRUE | FALSE | FALSE
5232 | MRT-XS00-P3MAV-120053 | 2018-09-13 | MRT-DS-REC-TT-180032-FC | FC | 3 | TRUE | FALSE | FALSE
5233 | MRT-CA03-P0UMA-180043 | 2018-09-13 | MRT-DS-REC-TT-180035-FC | FC | 2 | TRUE | FALSE | FALSE
5234 | MRT-CA03-P0UMA-180046 | 2018-09-13 | MRT-DS-REC-TT-180035-FC | FC | 2 | TRUE | FALSE | FALSE
5235 | MRT-XW03-P0MJ-110511 | 2018-09-13 | MRT-DS-REC-TT-180036-FC | FC | 3 | TRUE | FALSE | FALSE
5236 | MRT-QM01-P0ZEN-040003 | 2018-09-13 | MRT-DS-REC-TT-180037-FC | FC | 3 | TRUE | FALSE | FALSE
5237 | MRT-CC02-P2UAG-170307 | 2018-09-13 | MRT-DS-REC-TT-180745-FC | FC | 1 | TRUE | TRUE | FALSE
5238 | MRT-CC02-P3UAG-170307 | 2018-09-13 | MRT-DS-REC-TT-180745-FC | FC | 1 | TRUE | TRUE | FALSE
5239 | MRT-YL00-P2MAJ-603105 | 2018-09-13 | MRT-DS-REC-TT-180714-FC | FC | 5 | TRUE | TRUE | FALSE
5240 | MRT-YV02-P2MAJ-603108 | 2018-09-13 | MRT-DS-REC-TT-180714-FC | FC | 5 | TRUE | TRUE | FALSE
5241 | MRT-YL00-P3MAJ-604105 | 2018-09-13 | MRT-DS-REC-TT-180714-FC | FC | 5 | TRUE | TRUE | FALSE
5242 | MRT-YV02-P3MAJ-604108 | 2018-09-13 | MRT-DS-REC-TT-180714-FC | FC | 5 | TRUE | TRUE | FALSE
5243 | MRT-CV03-P0ZEN-163101 | 2018-09-13 | MRT-DS-REC-TT-180484-FC | FC | 1 | TRUE | TRUE | FALSE
5244 | MRT-CV03-P0ZEN-163108 | 2018-09-13 | MRT-DS-REC-TT-180484-FC | FC | 1 | TRUE | TRUE | FALSE
5245 | MRT-YR05-P2GM-128511 | 2018-09-13 | MRT-DS-REC-TT-180740-FC | FC | 1 | TRUE | TRUE | FALSE
5246 | MRT-YR05-P3GM-128511 | 2018-09-13 | MRT-DS-REC-TT-180740-FC | FC | 1 | TRUE | TRUE | FALSE
5247 | MRT-CV03-P2ZEN-165103 | 2018-09-13 | MRT-DS-REC-TT-180767 | FA | 2 | TRUE | TRUE | FALSE
5248 | MRT-CV03-P3ZEN-165103 | 2018-09-13 | MRT-DS-REC-TT-180767 | FA | 2 | TRUE | TRUE | FALSE
5249 | MRT-CV03-P2ZEN-165102 | 2018-09-13 | MRT-DS-REC-TT-180768 | FC | 2 | TRUE | TRUE | FALSE
5250 | MRT-CV03-P3ZEN-165102 | 2018-09-13 | MRT-DS-REC-TT-180768 | FC | 2 | TRUE | TRUE | FALSE
5251 | MRT-US02-P0ABA-150004 | 2018-09-13 | MRT-HK-REC-TT-180230 | FA | 0 | TRUE | FALSE | FALSE
5252 | MRT-YF01-P0BBA-150106 | 2018-09-13 | MRT-HK-REC-TT-180230 | FA | 1 | TRUE | TRUE | FALSE
5253 | MRT-YF01-P0BFA-150356 | 2018-09-13 | MRT-HK-REC-TT-180230 | FA | 1 | TRUE | TRUE | FALSE
5254 | MRT-YE16-P0UGD-150140 | 2018-09-13 | MRT-HK-REC-TT-180230 | FA | 0 | TRUE | FALSE | FALSE
5255 | MRT-DN02-P2LBG-830002 | 2018-09-13 | MRT-DS-REC-TT-180764 | FA | 0 | TRUE | FALSE | FALSE
5256 | MRT-YL00-P2MAG-601010 | 2018-09-14 | MRT-DS-REC-TT-180738-FC | FC | 1 | TRUE | TRUE | FALSE
5257 | MRT-YL00-P3MAG-602010 | 2018-09-14 | MRT-DS-REC-TT-180738-FC | FC | 1 | TRUE | TRUE | FALSE
5258 | MRT-YT02-P2LAC-126011 | 2018-09-14 | MRT-DS-REC-TT-180748-FC | FC | 3 | TRUE | TRUE | FALSE
5259 | MRT-YT02-P3LAC-126011 | 2018-09-14 | MRT-DS-REC-TT-180748-FC | FC | 3 | TRUE | TRUE | FALSE
5260 | MRT-YT02-P2LAC-126061 | 2018-09-14 | MRT-DS-REC-TT-180748-FC | FC | 3 | TRUE | TRUE | FALSE
5261 | MRT-YT02-P3LAC-126061 | 2018-09-14 | MRT-DS-REC-TT-180748-FC | FC | 3 | TRUE | TRUE | FALSE
5262 | MRT-XG07-P0ZEN-120050 | 2018-09-14 | MRT-DS-REC-TT-180733-FC | FC | 4 | TRUE | TRUE | FALSE
5263 | MRT-DN02-P2LBA-830001 | 2018-09-14 | MRT-DS-REC-TT-180763 | FA | 0 | TRUE | FALSE | FALSE
5264 | MRT-DN02-P2PC-830003 | 2018-09-14 | MRT-DS-REC-TT-180765 | FA | 0 | TRUE | FALSE | FALSE
5265 | MRT-YK08-P2MAJ-603200 | 2018-09-14 | MRT-DS-REC-TT-180658-FC | FC | 3 | TRUE | TRUE | FALSE
5266 | MRT-XG02-P2MAJ-603201 | 2018-09-14 | MRT-DS-REC-TT-180658-FC | FC | 4 | TRUE | TRUE | FALSE
5267 | MRT-YK08-P3MAJ-604200 | 2018-09-14 | MRT-DS-REC-TT-180658-FC | FC | 3 | TRUE | TRUE | FALSE
5268 | MRT-XG02-P3MAJ-604201 | 2018-09-14 | MRT-DS-REC-TT-180658-FC | FC | 4 | TRUE | TRUE | FALSE
5269 | MRT-YD00-P2LAC-126049 | 2018-09-14 | MRT-DS-REC-TT-180703-FC | FC | 1 | TRUE | TRUE | FALSE
5270 | MRT-YD00-P3LAC-126049 | 2018-09-14 | MRT-DS-REC-TT-180703-FC | FC | 1 | TRUE | TRUE | FALSE
5271 | MRT-YD00-P2LAC-126096 | 2018-09-14 | MRT-DS-REC-TT-180703-FC | FC | 1 | TRUE | TRUE | FALSE
5272 | MRT-YD00-P3LAC-126096 | 2018-09-14 | MRT-DS-REC-TT-180703-FC | FC | 1 | TRUE | TRUE | FALSE
5273 | MRT-YD00-P2LAC-126050 | 2018-09-14 | MRT-DS-REC-TT-180703-FC | FC | 1 | TRUE | TRUE | FALSE
5274 | MRT-YD00-P3LAC-126050 | 2018-09-14 | MRT-DS-REC-TT-180703-FC | FC | 1 | TRUE | TRUE | FALSE
5275 | MRT-YD00-P2LAC-126097 | 2018-09-14 | MRT-DS-REC-TT-180703-FC | FC | 1 | TRUE | TRUE | FALSE
5276 | MRT-YD00-P3LAC-126097 | 2018-09-14 | MRT-DS-REC-TT-180703-FC | FC | 1 | TRUE | TRUE | FALSE
5277 | MRT-CA05-P0UMA-180061 | 2018-09-14 | MRT-DS-REC-TT-180770 | FC | 4 | TRUE | TRUE | FALSE
5278 | MRT-CA05-P0UMA-180062 | 2018-09-14 | MRT-DS-REC-TT-180770 | FC | 4 | TRUE | TRUE | FALSE
5279 | MRT-UE00-P2LB-122008 | 2018-09-14 | MRT-DS-REC-TT-180773 | FC | 4 | TRUE | TRUE | FALSE
5280 | MRT-UE00-P3LB-122008 | 2018-09-14 | MRT-DS-REC-TT-180773 | FC | 2 | TRUE | TRUE | FALSE
5281 | MRT-XB02-P2LB-122021 | 2018-09-14 | MRT-DS-REC-TT-180774 | FC | 3 | TRUE | TRUE | FALSE
5282 | MRT-YF00-P3PAH-604521 | 2018-09-17 | MRT-DS-REC-TT-180771 | FC | 2 | TRUE | TRUE | FALSE
5283 | MRT-YV02-P3PAH-604522 | 2018-09-17 | MRT-DS-REC-TT-180771 | FC | 2 | TRUE | TRUE | FALSE
5284 | MRT-YB03-P3PAH-604523 | 2018-09-17 | MRT-DS-REC-TT-180771 | FC | 3 | TRUE | TRUE | FALSE
5285 | MRT-YK08-P3PAH-604524 | 2018-09-17 | MRT-DS-REC-TT-180771 | FC | 3 | TRUE | TRUE | FALSE
5286 | MRT-YF00-P2PAH-604121 | 2018-09-17 | MRT-DS-REC-TT-180772 | FC | 2 | TRUE | TRUE | FALSE
5287 | MRT-YV02-P2PAH-604122 | 2018-09-17 | MRT-DS-REC-TT-180772 | FC | 3 | TRUE | TRUE | FALSE
5288 | MRT-YB03-P2PAH-604123 | 2018-09-17 | MRT-DS-REC-TT-180772 | FC | 4 | TRUE | TRUE | FALSE
5289 | MRT-YK08-P2PAH-604124 | 2018-09-17 | MRT-DS-REC-TT-180772 | FC | 5 | TRUE | TRUE | FALSE
5290 | MRT-YK09-P2MKC-230003 | 2018-09-17 | MRT-DS-REC-TT-180776 | FA | 1 | TRUE | TRUE | FALSE
5291 | MRT-CC07-P0ULY-176101 | 2018-09-17 | MRT-HK-REC-TT-180231 | FA | 3 | TRUE | TRUE | FALSE
5292 | MRT-CC02-P0ULY-176105 | 2018-09-17 | MRT-HK-REC-TT-180231 | FA | 2 | TRUE | TRUE | FALSE
5293 | MRT-CC02-P0ULY-176120 | 2018-09-17 | MRT-HK-REC-TT-180231 | FA | 2 | TRUE | TRUE | FALSE
5294 | MRT-CC04-P0ULY-176128 | 2018-09-17 | MRT-HK-REC-TT-180231 | FA | 2 | TRUE | TRUE | FALSE
5295 | MRT-CC04-P0ULY-176132 | 2018-09-17 | MRT-HK-REC-TT-180231 | FA | 1 | TRUE | TRUE | FALSE
5296 | MRT-YD00-P2ZEN-113500 | 2018-09-18 | MRT-DS-REC-TT-180737-FC | FC | 2 | TRUE | TRUE | FALSE
5297 | MRT-YD00-P3ZEN-113500 | 2018-09-18 | MRT-DS-REC-TT-180737-FC | FC | 2 | TRUE | TRUE | FALSE
5298 | MRT-YT01-P2ZEN-113501 | 2018-09-18 | MRT-DS-REC-TT-180737-FC | FC | 2 | TRUE | TRUE | FALSE
5299 | MRT-YT01-P3ZEN-113501 | 2018-09-18 | MRT-DS-REC-TT-180737-FC | FC | 2 | TRUE | TRUE | FALSE
5300 | MRT-YD00-P2ZEN-113400 | 2018-09-18 | MRT-DS-REC-TT-180736-FC | FC | 2 | TRUE | TRUE | FALSE
5301 | MRT-YT01-P2ZEN-113401 | 2018-09-18 | MRT-DS-REC-TT-180736-FC | FC | 2 | TRUE | TRUE | FALSE
5302 | MRT-YD00-P3ZEN-113400 | 2018-09-18 | MRT-DS-REC-TT-180736-FC | FC | 2 | TRUE | TRUE | FALSE
5303 | MRT-YT01-P3ZEN-113401 | 2018-09-18 | MRT-DS-REC-TT-180736-FC | FC | 2 | TRUE | TRUE | FALSE
5304 | MRT-UE00-P2ZEN-100004 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 4 | TRUE | TRUE | FALSE
5305 | MRT-UE00-P2ZEN-100005 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 4 | TRUE | TRUE | FALSE
5306 | MRT-UE00-P2ZEN-100006 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 4 | TRUE | TRUE | FALSE
5307 | MRT-UE00-P2ZEN-100007 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 4 | TRUE | TRUE | FALSE
5308 | MRT-UE00-P2ZEN-100008 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 4 | TRUE | TRUE | FALSE
5309 | MRT-UE00-P2ZEN-100009 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 4 | TRUE | TRUE | FALSE
5310 | MRT-UE00-P3ZEN-100010 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 4 | TRUE | TRUE | FALSE
5311 | MRT-UE00-P3ZEN-100011 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 4 | TRUE | TRUE | FALSE
5312 | MRT-UE00-P3ZEN-100012 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 4 | TRUE | TRUE | FALSE
5313 | MRT-UE00-P3ZEN-100013 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 4 | TRUE | TRUE | FALSE
5314 | MRT-UE00-P3ZEN-100014 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 4 | TRUE | TRUE | FALSE
5315 | MRT-UE00-P3ZEN-100015 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 4 | TRUE | TRUE | FALSE
5316 | MRT-UE00-P2ZEN-100016 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 2 | TRUE | TRUE | FALSE
5317 | MRT-UE00-P3ZEN-100017 | 2018-09-18 | MRT-DS-REC-TT-180674-FC | FC | 2 | TRUE | TRUE | FALSE
5318 | MRT-XV00-P2MAA-220036 | 2018-09-18 | MRT-DS-REC-TT-180621-FC | FC | 3 | TRUE | TRUE | FALSE
5319 | MRT-XV00-P2MAV-220037 | 2018-09-18 | MRT-DS-REC-TT-180621-FC | FC | 3 | TRUE | TRUE | FALSE
5320 | MRT-XV00-P3MAA-220036 | 2018-09-18 | MRT-DS-REC-TT-180621-FC | FC | 3 | TRUE | TRUE | FALSE
5321 | MRT-XV00-P3MAV-220037 | 2018-09-18 | MRT-DS-REC-TT-180621-FC | FC | 3 | TRUE | TRUE | FALSE
5322 | MRT-XA00-P3MAA-220016 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5323 | MRT-XA00-P2MAA-220014 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5324 | MRT-XA00-P2MAA-220015 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5325 | MRT-XA00-P2MAA-220016 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5326 | MRT-XA00-P2MAA-220017 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5327 | MRT-XA00-P2MAA-220018 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5328 | MRT-XA00-P3MAA-220014 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5329 | MRT-XA00-P3MAA-220015 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5330 | MRT-XA00-P3MAA-220017 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5331 | MRT-XA00-P3MAA-220018 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5332 | MRT-XA00-P3MAA-220019 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5333 | MRT-XA00-P2MAA-220020 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5334 | MRT-XA00-P3MAA-220020 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5335 | MRT-XA00-P2MAA-220021 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5336 | MRT-XA00-P3MAA-220021 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5337 | MRT-XA00-P2MAA-220022 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5338 | MRT-XA00-P3MAA-220022 | 2018-09-18 | MRT-DS-REC-TT-180613-FC | FC | 3 | TRUE | TRUE | FALSE
5339 | MRT-XB02-P2QC-130009 | 2018-09-18 | MRT-DS-REC-TT-180752-FC | FC | 2 | TRUE | TRUE | FALSE
5340 | MRT-XB02-P3QC-130009 | 2018-09-18 | MRT-DS-REC-TT-180752-FC | FC | 2 | TRUE | TRUE | FALSE
5341 | MRT-CC03-P0UPC-176370 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5342 | MRT-CC03-P0UPC-176371 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5343 | MRT-CC03-P0UPC-176372 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5344 | MRT-CC03-P0UPC-176373 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5345 | MRT-CC03-P0UPC-176374 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5346 | MRT-CC03-P0UPC-176375 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5347 | MRT-CC03-P0UPC-176376 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5348 | MRT-CC03-P0UPC-176377 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5349 | MRT-CC03-P0UPC-176380 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5350 | MRT-CC03-P0UPC-176381 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5351 | MRT-CC03-P0UPC-176382 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5352 | MRT-CC03-P0UPC-176383 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5353 | MRT-CC03-P0UPC-176384 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5354 | MRT-CC03-P0UPC-176385 | 2018-09-18 | MRT-HK-REC-TT-180232 | FA | 0 | TRUE | TRUE | FALSE
5355 | MRT-CC02-P0UPC-175793 | 2018-09-18 | MRT-HK-REC-TT-180233 | FA | 0 | TRUE | FALSE | FALSE
5356 | MRT-YD00-P0MKG-125331 | 2018-09-18 | MRT-HK-REC-TT-180234 | FI | 0 | TRUE | FALSE | FALSE
5357 | MRT-CC02-P2UAG-170308 | 2018-09-18 | MRT-DS-REC-TT-180777 | FC | 2 | TRUE | TRUE | FALSE
5358 | MRT-CC02-P3UAG-170308 | 2018-09-18 | MRT-DS-REC-TT-180777 | FC | 2 | TRUE | TRUE | FALSE
5359 | MRT-YD00-P2QHE-606003 | 2018-09-19 | MRT-DS-REC-TT-180785 | FC | 3 | TRUE | TRUE | FALSE
5360 | MRT-YD00-P0QHE-606001 | 2018-09-19 | MRT-DS-REC-TT-180785 | FC | 4 | TRUE | TRUE | FALSE
5361 | MRT-YD00-P0ERB-606001 | 2018-09-19 | MRT-DS-REC-TT-180785 | FC | 3 | TRUE | TRUE | FALSE
5362 | MRT-YD00-P0ERB-606002 | 2018-09-19 | MRT-DS-REC-TT-180785 | FC | 3 | TRUE | TRUE | FALSE
5363 | MRT-YD00-P0PGB-606001 | 2018-09-19 | MRT-DS-REC-TT-180785 | FC | 4 | TRUE | TRUE | FALSE
5364 | MRT-YD00-P3QHE-606003 | 2018-09-19 | MRT-DS-REC-TT-180785 | FC | 3 | TRUE | TRUE | FALSE
5365 | MRT-YE00-P2QC-130021 | 2018-09-19 | MRT-DS-REC-TT-180754-FC | FC | 3 | TRUE | TRUE | FALSE
5366 | MRT-YE00-P3QC-130021 | 2018-09-19 | MRT-DS-REC-TT-180754-FC | FC | 3 | TRUE | TRUE | FALSE
5367 | MRT-YL00-P2MAJ-603207 | 2018-09-19 | MRT-DS-REC-TT-180724-FC | FC | 4 | TRUE | TRUE | FALSE
5368 | MRT-YL00-P3MAJ-604207 | 2018-09-19 | MRT-DS-REC-TT-180724-FC | FC | 4 | TRUE | TRUE | FALSE
5369 | MRT-YD00-P2QC-130005 | 2018-09-19 | MRT-DS-REC-TT-180750-FC | FC | 3 | TRUE | TRUE | FALSE
5370 | MRT-YD00-P3QC-130005 | 2018-09-19 | MRT-DS-REC-TT-180750-FC | FC | 3 | TRUE | TRUE | FALSE
5371 | MRT-YF02-P2QC-130006 | 2018-09-19 | MRT-DS-REC-TT-180751-FC | FC | 3 | TRUE | TRUE | FALSE
5372 | MRT-YF02-P3QC-130006 | 2018-09-19 | MRT-DS-REC-TT-180751-FC | FC | 3 | TRUE | TRUE | FALSE
5373 | MRT-YD02-P3LB-122064 | 2018-09-19 | MRT-DS-REC-TT-180786 | FI | 0 | TRUE | TRUE | FALSE
5374 | MRT-YT01-P2PGB-113104 | 2018-09-19 | MRT-DS-REC-TT-180787 | FC | 3 | TRUE | TRUE | FALSE
5375 | MRT-YD00-P2PGB-113105 | 2018-09-19 | MRT-DS-REC-TT-180787 | FC | 3 | TRUE | TRUE | FALSE
5376 | MRT-YT01-P3PGB-113104 | 2018-09-19 | MRT-DS-REC-TT-180787 | FC | 3 | TRUE | TRUE | FALSE
5377 | MRT-YD00-P3PGB-113105 | 2018-09-19 | MRT-DS-REC-TT-180787 | FC | 3 | TRUE | TRUE | FALSE
5378 | MRT-XG02-P2MAA-220005 | 2018-09-19 | MRT-DS-REC-TT-180788 | FA | 1 | TRUE | TRUE | FALSE
5379 | MRT-XG02-P3MAA-220005 | 2018-09-19 | MRT-DS-REC-TT-180788 | FA | 1 | TRUE | TRUE | FALSE
5380 | MRT-XG02-P2MAV-220006 | 2018-09-19 | MRT-DS-REC-TT-180788 | FA | 1 | TRUE | TRUE | FALSE
5381 | MRT-XG02-P3MAV-220006 | 2018-09-19 | MRT-DS-REC-TT-180788 | FA | 1 | TRUE | TRUE | FALSE
5382 | MRT-XG02-P2MAX-220007 | 2018-09-19 | MRT-DS-REC-TT-180788 | FA | 1 | TRUE | TRUE | FALSE
5383 | MRT-DN02-P2PG-830004 | 2018-09-19 | MRT-DS-REC-TT-180766 | FA | 0 | TRUE | FALSE | FALSE
5384 | MRT-DN02-P2LC-830005 | 2018-09-19 | MRT-DS-REC-TT-180769 | FA | 0 | TRUE | FALSE | FALSE
5385 | MRT-DN02-P2LA-830006 | 2018-09-19 | MRT-DS-REC-TT-180780 | FA | 0 | TRUE | FALSE | FALSE
5386 | MRT-YS01-P3QU-130034 | 2018-09-19 | MRT-DS-REC-TT-180789 | FI | 3 | TRUE | TRUE | FALSE
5387 | MRT-YK10-P2QC-130010 | 2018-09-19 | MRT-DS-REC-TT-180698-FC | FC | 2 | TRUE | TRUE | FALSE
5388 | MRT-YK10-P3QC-130010 | 2018-09-19 | MRT-DS-REC-TT-180698-FC | FC | 2 | TRUE | TRUE | FALSE
5389 | MRT-XG02-P2QC-130001 | 2018-09-19 | MRT-DS-REC-TT-180749-FC | FC | 3 | TRUE | TRUE | FALSE
5390 | MRT-XG02-P3QC-130001 | 2018-09-19 | MRT-DS-REC-TT-180749-FC | FC | 3 | TRUE | TRUE | FALSE
5391 | MRT-CA01-P0UXA-186662 | 2018-09-19 | MRT-HK-REC-TT-180235 | FA | 2 | TRUE | TRUE | FALSE
5392 | MRT-CA06-P0UXA-186660 | 2018-09-19 | MRT-HK-REC-TT-180235 | FA | 2 | TRUE | TRUE | FALSE
5393 | MRT-YK00-P2QC-130022 | 2018-09-19 | MRT-DS-REC-TT-180762-FC | FC | 3 | TRUE | TRUE | FALSE
5394 | MRT-YK00-P3QC-130022 | 2018-09-19 | MRT-DS-REC-TT-180762-FC | FC | 3 | TRUE | TRUE | FALSE
5395 | MRT-DF04-P3ZEN-144001 | 2018-09-19 | MRT-DS-REC-TT-180790 | FI | 1 | TRUE | TRUE | FALSE
5396 | MRT-DF04-P3ZEN-144002 | 2018-09-19 | MRT-DS-REC-TT-180790 | FI | 1 | TRUE | TRUE | FALSE
5397 | MRT-DF04-P3ZEN-144004 | 2018-09-19 | MRT-DS-REC-TT-180790 | FI | 1 | TRUE | TRUE | FALSE
5398 | MRT-YE16-P0UGA-150138 | 2018-09-19 | MRT-HK-REC-TT-180236 | FA | 0 | TRUE | FALSE | FALSE
5399 | MRT-YK09-P2MKC-230002 | 2018-09-19 | MRT-DS-REC-TT-180791 | FC | 2 | TRUE | TRUE | FALSE
5400 | MRT-YK09-P3MKC-230002 | 2018-09-19 | MRT-DS-REC-TT-180791 | FC | 2 | TRUE | TRUE | FALSE
6467 | MRT-XG02-P3MAX-220007 | 2018-09-19 | MRT-DS-REC-TT-180788 | FA | 1 | TRUE | TRUE | FALSE
5401 | MRT-CV03-P2ZEN-165103 | 2018-09-21 | MRT-DS-REC-TT-180767-FC | FC | 2 | TRUE | TRUE | FALSE
5402 | MRT-CV03-P3ZEN-165103 | 2018-09-21 | MRT-DS-REC-TT-180767-FC | FC | 2 | TRUE | TRUE | FALSE
5403 | MRT-CA05-P0UMA-180061 | 2018-09-21 | MRT-DS-REC-TT-180770-FC | FC | 4 | TRUE | TRUE | FALSE
5404 | MRT-CA05-P0UMA-180062 | 2018-09-21 | MRT-DS-REC-TT-180770-FC | FC | 4 | TRUE | TRUE | FALSE
5405 | MRT-YE16-P0UBN-150145 | 2018-09-21 | MRT-HK-REC-TT-180237 | FA | 0 | TRUE | TRUE | FALSE
5406 | MRT-XP00-P3BAC-150370 | 2018-09-21 | MRT-HK-REC-TT-180239 | FI | 0 | TRUE | TRUE | FALSE
5407 | MRT-CV05-P3BAC-150369 | 2018-09-21 | MRT-HK-REC-TT-180239 | FI | 0 | TRUE | TRUE | FALSE
5408 | MRT-US02-P2BFA-150670 | 2018-09-21 | MRT-HK-REC-TT-180240 | FA | 0 | TRUE | TRUE | FALSE
5409 | MRT-US02-P2BJA-150676 | 2018-09-21 | MRT-HK-REC-TT-180240 | FA | 0 | TRUE | TRUE | FALSE
5410 | MRT-US02-P2BJB-150678 | 2018-09-21 | MRT-HK-REC-TT-180240 | FA | 0 | TRUE | TRUE | FALSE
5411 | MRT-US02-P2BLF-150740 | 2018-09-21 | MRT-HK-REC-TT-180240 | FA | 0 | TRUE | TRUE | FALSE
5412 | MRT-US02-P2BMF-150684 | 2018-09-21 | MRT-HK-REC-TT-180240 | FA | 0 | TRUE | TRUE | FALSE
5413 | MRT-US02-P2BRA-150746 | 2018-09-21 | MRT-HK-REC-TT-180240 | FA | 0 | TRUE | TRUE | FALSE
5414 | MRT-US02-P2BUA-150752 | 2018-09-21 | MRT-HK-REC-TT-180240 | FA | 0 | TRUE | TRUE | FALSE
5415 | MRT-US02-P2BUA-150754 | 2018-09-21 | MRT-HK-REC-TT-180240 | FA | 0 | TRUE | TRUE | FALSE
5416 | MRT-YT01-P0BAU-150618 | 2018-09-21 | MRT-HK-REC-TT-180241 | FA | 0 | TRUE | TRUE | FALSE
5417 | MRT-CA00-P0UCA-180107 | 2018-09-21 | MRT-DS-REC-TT-180792 | FC | 4 | TRUE | TRUE | FALSE
5418 | MRT-CA00-P0UCA-180108 | 2018-09-21 | MRT-DS-REC-TT-180792 | FC | 4 | TRUE | TRUE | FALSE
5419 | MRT-CA00-P0UCA-180113 | 2018-09-21 | MRT-DS-REC-TT-180792 | FC | 4 | TRUE | TRUE | FALSE
5420 | MRT-CA01-P0UCA-180122 | 2018-09-21 | MRT-DS-REC-TT-180792 | FC | 4 | TRUE | TRUE | FALSE
5421 | MRT-CA01-P0UCA-180123 | 2018-09-21 | MRT-DS-REC-TT-180792 | FC | 4 | TRUE | TRUE | FALSE
5422 | MRT-CA01-P0UCA-180127 | 2018-09-21 | MRT-DS-REC-TT-180792 | FC | 4 | TRUE | TRUE | FALSE
5423 | MRT-CA02-P0UCA-180134 | 2018-09-21 | MRT-DS-REC-TT-180792 | FC | 4 | TRUE | TRUE | FALSE
5503 | MRT-CC07-P0UBX-176001 | 2018-09-21 | MRT-HK-REC-TT-180244 | FA | 3 | TRUE | TRUE | FALSE
5504 | MRT-CC02-P0UBX-176005 | 2018-09-21 | MRT-HK-REC-TT-180244 | FA | 4 | TRUE | TRUE | FALSE
5505 | MRT-CC07-P0UBX-176015 | 2018-09-21 | MRT-HK-REC-TT-180244 | FA | 2 | TRUE | TRUE | FALSE
5506 | MRT-CC02-P0UBX-176020 | 2018-09-21 | MRT-HK-REC-TT-180244 | FA | 2 | TRUE | TRUE | FALSE
5507 | MRT-CC02-P0UBX-176006 | 2018-09-21 | MRT-HK-REC-TT-180244 | FA | 4 | TRUE | TRUE | FALSE
5508 | MRT-CC02-P0UBX-176007 | 2018-09-21 | MRT-HK-REC-TT-180244 | FA | 4 | TRUE | TRUE | FALSE
5509 | MRT-CC02-P0UBX-176035 | 2018-09-21 | MRT-HK-REC-TT-180244 | FA | 2 | TRUE | TRUE | FALSE
5510 | MRT-CC02-P0UBX-176036 | 2018-09-21 | MRT-HK-REC-TT-180244 | FA | 1 | TRUE | TRUE | FALSE
5511 | MRT-CA06-P0USX-186801 | 2018-09-21 | MRT-HK-REC-TT-180245 | FA | 1 | TRUE | TRUE | FALSE
5512 | MRT-CA01-P0USX-186802 | 2018-09-21 | MRT-HK-REC-TT-180245 | FA | 1 | TRUE | TRUE | FALSE
5513 | MRT-YT01-P0GEN-135327 | 2018-09-21 | MRT-HK-REC-TT-180242 | FA | 0 | TRUE | TRUE | FALSE
5514 | MRT-XG02-P0MKG-125312 | 2018-09-21 | MRT-HK-REC-TT-180242 | FA | 0 | TRUE | TRUE | FALSE
5515 | MRT-XG08-P0GDG-135020 | 2018-09-21 | MRT-HK-REC-TT-180246 | FA | 0 | TRUE | FALSE | FALSE
5516 | MRT-YU02-P0BAY-150027 | 2018-09-21 | MRT-HK-REC-TT-180248 | FA | 1 | TRUE | TRUE | FALSE
5530 | MRT-US02-P0BLL-150780 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5531 | MRT-US02-P0BLL-150782 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5532 | MRT-US02-P0BLL-150784 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5533 | MRT-US02-P2BLK-150764 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5534 | MRT-US02-P2BMA-150720 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5535 | MRT-US02-P3BLK-150766 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5536 | MRT-US02-P3BMA-150722 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5537 | MRT-US02-P3BMA-150724 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5538 | MRT-US02-P4BLK-150768 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5539 | MRT-YU02-P0BLL-150779 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5540 | MRT-YU02-P0BLL-150781 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5541 | MRT-YU02-P0BLL-150783 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5542 | MRT-YU02-P2BLK-150763 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5543 | MRT-YU02-P2BMA-150719 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5544 | MRT-YU02-P3BLK-150765 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5545 | MRT-YU02-P3BMA-150721 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5546 | MRT-YU02-P3BMA-150723 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
5547 | MRT-YU02-P4BLK-150767 | 2018-09-21 | MRT-HK-REC-TT-180247 | FA | 0 | TRUE | FALSE | FALSE
6495 | MRT-QM03-P0ZEN-185010 | 2018-09-21 | MRT-HK-REC-TT-180238 | FA | 0 | TRUE | FALSE | FALSE
5517 | MRT-YF01-P0BBA-150106 | 2018-09-22 | MRT-HK-REC-TT-180249 | FA | 0 | TRUE | TRUE | FALSE
5518 | MRT-YF01-P0BFA-150356 | 2018-09-22 | MRT-HK-REC-TT-180249 | FA | 0 | TRUE | TRUE | FALSE
5519 | MRT-CA06-P0UGX-186951 | 2018-09-24 | MRT-HK-REC-TT-180251 | FA | 2 | TRUE | TRUE | FALSE
5520 | MRT-CA01-P0UGX-186952 | 2018-09-24 | MRT-HK-REC-TT-180251 | FA | 3 | TRUE | TRUE | FALSE
5548 | MRT-UBM-P2BBT-150429 | 2018-09-24 | MRT-HK-REC-TT-180252 | FA | 0 | TRUE | FALSE | FALSE
5549 | MRT-UBM-P3BBT-150446 | 2018-09-24 | MRT-HK-REC-TT-180252 | FA | 0 | TRUE | FALSE | FALSE
5550 | MRT-YS01-P2BBA-150465 | 2018-09-24 | MRT-HK-REC-TT-180252 | FA | 0 | TRUE | FALSE | FALSE
5551 | MRT-YS01-P3BBA-150467 | 2018-09-24 | MRT-HK-REC-TT-180252 | FA | 0 | TRUE | FALSE | FALSE
5552 | MRT-YU02-P0BMA-150039 | 2018-09-25 | MRT-HK-REC-TT-180253 | FA | 0 | TRUE | FALSE | FALSE
5553 | MRT-YD00-P0UGA-150126 | 2018-09-25 | MRT-HK-REC-TT-180253 | FA | 0 | TRUE | FALSE | FALSE
5554 | MRT-YD00-P0UQA-150284 | 2018-09-25 | MRT-HK-REC-TT-180253 | FA | 0 | TRUE | FALSE | FALSE
5555 | MRT-YU02-P0BMB-150040 | 2018-09-25 | MRT-HK-REC-TT-180253 | FA | 0 | TRUE | FALSE | FALSE
5556 | MRT-XA01-P0ABA-150517 | 2018-09-25 | MRT-HK-REC-TT-180253 | FA | 0 | TRUE | FALSE | FALSE
5557 | MRT-YM02-P2BUA-150751 | 2018-09-25 | MRT-HK-REC-TT-180254 | FA | 0 | TRUE | FALSE | FALSE
5558 | MRT-YM02-P2BUA-150753 | 2018-09-25 | MRT-HK-REC-TT-180254 | FA | 0 | TRUE | FALSE | FALSE
5559 | MRT-YU02-P2BMF-150683 | 2018-09-25 | MRT-HK-REC-TT-180254 | FA | 0 | TRUE | FALSE | FALSE
5560 | MRT-YU02-P2BRA-150745 | 2018-09-25 | MRT-HK-REC-TT-180254 | FA | 0 | TRUE | FALSE | FALSE
5561 | MRT-XW03-P0BAA-150011 | 2018-09-25 | MRT-HK-REC-TT-180254 | FA | 0 | TRUE | FALSE | FALSE
5562 | MRT-YU02-P2BFA-150669 | 2018-09-25 | MRT-HK-REC-TT-180255 | FA | 0 | TRUE | TRUE | FALSE
5563 | MRT-YU02-P2BLF-150739 | 2018-09-25 | MRT-HK-REC-TT-180255 | FA | 0 | TRUE | TRUE | FALSE
5564 | MRT-YU02-P2BJA-150675 | 2018-09-25 | MRT-HK-REC-TT-180255 | FA | 0 | TRUE | TRUE | FALSE
5565 | MRT-YU02-P2BJB-150677 | 2018-09-25 | MRT-HK-REC-TT-180255 | FA | 0 | TRUE | TRUE | FALSE
5566 | MRT-DP00-P0ZEN-070517 | 2018-09-25 | MRT-HK-REC-TT-180256 | FA | 0 | TRUE | FALSE | FALSE
5567 | MRT-XW03-P2BAA-150479 | 2018-09-25 | MRT-HK-REC-TT-180256 | FA | 0 | TRUE | FALSE | FALSE
5568 | MRT-XW03-P3BAA-150500 | 2018-09-25 | MRT-HK-REC-TT-180256 | FA | 0 | TRUE | FALSE | FALSE
5569 | MRT-YT01-P2BAA-150475 | 2018-09-25 | MRT-HK-REC-TT-180256 | FA | 0 | TRUE | FALSE | FALSE
5570 | MRT-YT01-P3BAA-150498 | 2018-09-25 | MRT-HK-REC-TT-180256 | FA | 0 | TRUE | FALSE | FALSE
5571 | MRT-YM02-P2BAA-150478 | 2018-09-25 | MRT-HK-REC-TT-180257 | FA | 0 | TRUE | FALSE | FALSE
5572 | MRT-YM02-P2BAA-150493 | 2018-09-25 | MRT-HK-REC-TT-180257 | FA | 0 | TRUE | FALSE | FALSE
5573 | MRT-YM02-P3BAA-150499 | 2018-09-25 | MRT-HK-REC-TT-180257 | FA | 0 | TRUE | FALSE | FALSE
5574 | MRT-YM02-P3BAA-150951 | 2018-09-25 | MRT-HK-REC-TT-180257 | FA | 0 | TRUE | FALSE | FALSE
5575 | MRT-YS01-P3BAA-150943 | 2018-09-25 | MRT-HK-REC-TT-180257 | FA | 0 | TRUE | FALSE | FALSE
5576 | MRT-DP00-P0ZEN-070450 | 2018-09-25 | MRT-HK-REC-TT-180258 | FA | 0 | TRUE | FALSE | FALSE
5577 | MRT-YT01-P0BBA-150451 | 2018-09-25 | MRT-HK-REC-TT-180259 | FA | 0 | TRUE | FALSE | FALSE
5578 | MRT-YD00-P3UXA-150127 | 2018-09-26 | MRT-HK-REC-TT-180260 | FA | 0 | TRUE | FALSE | FALSE
5579 | MRT-YD00-P0UGD-150128 | 2018-09-26 | MRT-HK-REC-TT-180260 | FA | 0 | TRUE | FALSE | FALSE
5580 | MRT-YD00-P3UTH-150133 | 2018-09-26 | MRT-HK-REC-TT-180260 | FA | 0 | TRUE | FALSE | FALSE
5581 | MRT-CA01-P0UGX-186722 | 2018-09-26 | MRT-HK-REC-TT-180263 | FA | 2 | TRUE | TRUE | FALSE
5582 | MRT-CA06-P0UYX-187311 | 2018-09-26 | MRT-HK-REC-TT-180263 | FA | 2 | TRUE | TRUE | FALSE
5583 | MRT-CA01-P0UYX-187312 | 2018-09-26 | MRT-HK-REC-TT-180263 | FA | 2 | TRUE | TRUE | FALSE
5646 | MRT-YT01-P0BAU-150621 | 2018-09-26 | MRT-HK-REC-TT-180262 | FA | 0 | TRUE | TRUE | FALSE
5647 | MRT-YT01-P0BAU-150624 | 2018-09-26 | MRT-HK-REC-TT-180262 | FA | 0 | TRUE | TRUE | FALSE
5648 | MRT-YT01-P0BAU-150627 | 2018-09-26 | MRT-HK-REC-TT-180262 | FA | 0 | TRUE | TRUE | FALSE
5584 | MRT-YT01-P2BBT-150420 | 2018-09-27 | MRT-HK-REC-TT-180264 | FA | 0 | TRUE | FALSE | FALSE
5585 | MRT-YT01-P3BBT-150437 | 2018-09-27 | MRT-HK-REC-TT-180264 | FA | 0 | TRUE | FALSE | FALSE
5586 | MRT-YU02-P2BUB-150048 | 2018-09-27 | MRT-HK-REC-TT-180265 | FA | 0 | TRUE | FALSE | FALSE
5587 | MRT-YU02-P2BRB-150050 | 2018-09-27 | MRT-HK-REC-TT-180265 | FA | 0 | TRUE | FALSE | FALSE
5588 | MRT-YD00-P2BBT-150427 | 2018-09-28 | MRT-HK-REC-TT-180266 | FA | 0 | FALSE | TRUE | FALSE
5589 | MRT-YD00-P3BBT-150444 | 2018-09-28 | MRT-HK-REC-TT-180266 | FA | 0 | FALSE | TRUE | FALSE
5590 | MRT-YD00-P2BBT-150428 | 2018-09-28 | MRT-HK-REC-TT-180267 | FA | 0 | TRUE | FALSE | FALSE
5591 | MRT-YD00-P3BBT-150445 | 2018-09-28 | MRT-HK-REC-TT-180267 | FA | 0 | TRUE | FALSE | FALSE
5424 | MRT-XG02-P2SCA-127502 | 2018-10-01 | MRT-DS-REC-TT-180711-FC | FC | 2 | TRUE | TRUE | FALSE
5425 | MRT-XG02-P3SCA-127502 | 2018-10-01 | MRT-DS-REC-TT-180711-FC | FC | 2 | TRUE | TRUE | FALSE
5426 | MRT-DN02-P2LBG-830002 | 2018-10-01 | MRT-DS-REC-TT-180764-FC | FC | 0 | TRUE | TRUE | FALSE
5427 | MRT-XB02-P2LB-122021 | 2018-10-01 | MRT-DS-REC-TT-180774-FC | FC | 3 | TRUE | TRUE | FALSE
5428 | MRT-YF00-P3PAH-604521 | 2018-10-01 | MRT-DS-REC-TT-180771-FC | FC | 2 | TRUE | TRUE | FALSE
5429 | MRT-YV02-P3PAH-604522 | 2018-10-01 | MRT-DS-REC-TT-180771-FC | FC | 2 | TRUE | TRUE | FALSE
5430 | MRT-YB03-P3PAH-604523 | 2018-10-01 | MRT-DS-REC-TT-180771-FC | FC | 3 | TRUE | TRUE | FALSE
5431 | MRT-YK08-P3PAH-604524 | 2018-10-01 | MRT-DS-REC-TT-180771-FC | FC | 3 | TRUE | TRUE | FALSE
5432 | MRT-XK00-P3MKA-220001 | 2018-10-01 | MRT-DS-REC-TT-180663-FC | FC | 1 | TRUE | TRUE | FALSE
5433 | MRT-DN02-P2LBA-830001 | 2018-10-01 | MRT-DS-REC-TT-180763-FC | FC | 0 | TRUE | TRUE | FALSE
5434 | MRT-DN02-P2PC-830003 | 2018-10-01 | MRT-DS-REC-TT-180765-FC | FC | 0 | TRUE | TRUE | FALSE
5435 | MRT-YD00-P2QHE-606003 | 2018-10-01 | MRT-DS-REC-TT-180785-FC | FC | 3 | TRUE | TRUE | FALSE
5436 | MRT-YD00-P0QHE-606001 | 2018-10-01 | MRT-DS-REC-TT-180785-FC | FC | 4 | TRUE | TRUE | FALSE
5437 | MRT-YD00-P0ERB-606001 | 2018-10-01 | MRT-DS-REC-TT-180785-FC | FC | 3 | TRUE | TRUE | FALSE
5438 | MRT-YD00-P0ERB-606002 | 2018-10-01 | MRT-DS-REC-TT-180785-FC | FC | 3 | TRUE | TRUE | FALSE
5439 | MRT-YD00-P0PGB-606001 | 2018-10-01 | MRT-DS-REC-TT-180785-FC | FC | 4 | TRUE | TRUE | FALSE
5440 | MRT-YD00-P3QHE-606003 | 2018-10-01 | MRT-DS-REC-TT-180785-FC | FC | 3 | TRUE | TRUE | FALSE
5441 | MRT-DN02-P2LC-830005 | 2018-10-01 | MRT-DS-REC-TT-180769-FC | FC | 0 | TRUE | TRUE | FALSE
5442 | MRT-YK09-P2MKC-230003 | 2018-10-01 | MRT-DS-REC-TT-180776-FC | FC | 1 | TRUE | TRUE | FALSE
5443 | MRT-YK09-P2MKC-230002 | 2018-10-01 | MRT-DS-REC-TT-180791-FC | FC | 2 | TRUE | TRUE | FALSE
5444 | MRT-YK09-P3MKC-230002 | 2018-10-01 | MRT-DS-REC-TT-180791-FC | FC | 2 | TRUE | TRUE | FALSE
5445 | MRT-XJ00-P2MKJ-220001 | 2018-10-01 | MRT-DS-REC-TT-180778 | FC | 3 | TRUE | TRUE | FALSE
5446 | MRT-XK00-P2MKJ-220001 | 2018-10-01 | MRT-DS-REC-TT-180779 | FC | 2 | TRUE | TRUE | FALSE
5447 | MRT-YS01-P2SCA-127511 | 2018-10-01 | MRT-DS-REC-TT-180781 | FC | 2 | TRUE | TRUE | FALSE
5448 | MRT-YS01-P3SCA-127511 | 2018-10-01 | MRT-DS-REC-TT-180781 | FC | 2 | TRUE | TRUE | FALSE
5449 | MRT-XG02-P2MAA-220005 | 2018-10-01 | MRT-DS-REC-TT-180788-FC | FC | 1 | TRUE | TRUE | FALSE
5450 | MRT-XG02-P3MAA-220005 | 2018-10-01 | MRT-DS-REC-TT-180788-FC | FC | 1 | TRUE | TRUE | FALSE
5451 | MRT-XG02-P3MAV-220006 | 2018-10-01 | MRT-DS-REC-TT-180788-FC | FC | 1 | TRUE | TRUE | FALSE
5452 | MRT-XG02-P2MAX-220007 | 2018-10-01 | MRT-DS-REC-TT-180788-FC | FC | 1 | TRUE | TRUE | FALSE
5592 | MRT-CC00-P0ZEN-145401 | 2018-10-01 | MRT-HK-REC-TT-180269 | FA | 2 | TRUE | TRUE | FALSE
6468 | MRT-XG02-P3MAX-220007 | 2018-10-01 | MRT-DS-REC-TT-180788-FC | FC | 1 | TRUE | TRUE | FALSE
5521 | MRT-DN02-P2QC-830008 | 2018-10-02 | MRT-DS-REC-TT-180793 | FA | 0 | TRUE | FALSE | FALSE
5522 | MRT-XG02-P3PBB-604512 | 2018-10-02 | MRT-DS-REC-TT-180794 | FC | 3 | TRUE | TRUE | FALSE
5523 | MRT-DN02-P2SCA-830007 | 2018-10-02 | MRT-DS-REC-TT-180795 | FA | 0 | TRUE | FALSE | FALSE
5524 | MRT-CC02-P2UAG-170308 | 2018-10-02 | MRT-DS-REC-TT-180777-FC | FC | 2 | TRUE | TRUE | FALSE
5525 | MRT-CC02-P3UAG-170308 | 2018-10-02 | MRT-DS-REC-TT-180777-FC | FC | 2 | TRUE | TRUE | FALSE
5526 | MRT-YF00-P2PAH-604121 | 2018-10-02 | MRT-DS-REC-TT-180772-FC | FC | 2 | TRUE | TRUE | FALSE
5527 | MRT-YV02-P2PAH-604122 | 2018-10-02 | MRT-DS-REC-TT-180772-FC | FC | 3 | TRUE | TRUE | FALSE
5528 | MRT-YB03-P2PAH-604123 | 2018-10-02 | MRT-DS-REC-TT-180772-FC | FC | 4 | TRUE | TRUE | FALSE
5529 | MRT-YK08-P2PAH-604124 | 2018-10-02 | MRT-DS-REC-TT-180772-FC | FC | 5 | TRUE | TRUE | FALSE
5593 | MRT-US02-P2ASQ-150841 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5594 | MRT-US02-P2BAY-150800 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5595 | MRT-YM02-P2ASQ-150839 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5596 | MRT-YM02-P2BAY-150798 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5597 | MRT-YS01-P2ASQ-150840 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5598 | MRT-YS01-P2BAY-150799 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5599 | MRT-US02-P2BAY-150792 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5600 | MRT-US02-P3BAY-150824 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5601 | MRT-YM02-P2BAY-150790 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5602 | MRT-YM02-P3BAY-150822 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5603 | MRT-YS01-P2BAY-150791 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5604 | MRT-YS01-P3BAY-150823 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5605 | MRT-US02-P3ASQ-150849 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5606 | MRT-US02-P3BAY-150816 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5607 | MRT-YM02-P3ASQ-150847 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5608 | MRT-YM02-P3BAY-150814 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5609 | MRT-YS01-P3ASQ-150848 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5610 | MRT-YS01-P3BAY-150815 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5611 | MRT-US02-P3BAY-150808 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5612 | MRT-US02-P3BAY-150832 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5613 | MRT-YM02-P3BAY-150806 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5614 | MRT-YM02-P3BAY-150830 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5615 | MRT-YS01-P3BAY-150807 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5616 | MRT-YS01-P3BAY-150831 | 2018-10-02 | MRT-HK-REC-TT-180270 | FA | 0 | TRUE | FALSE | FALSE
5617 | MRT-XG02-P2MAV-220006 | 2018-10-02 | MRT-DS-REC-TT-180797 | FA | 2 | TRUE | TRUE | FALSE
5618 | MRT-XW03-P0BBB-150531 | 2018-10-02 | MRT-HK-REC-TT-180271 | FA | 0 | TRUE | FALSE | FALSE
5619 | MRT-YD00-P0BBB-150530 | 2018-10-02 | MRT-HK-REC-TT-180271 | FA | 0 | TRUE | FALSE | FALSE
5620 | MRT-YT01-P0BBB-150529 | 2018-10-02 | MRT-HK-REC-TT-180271 | FA | 0 | TRUE | FALSE | FALSE
5621 | MRT-YE16-P0UGA-150138 | 2018-10-02 | MRT-HK-REC-TT-180272 | FA | 1 | TRUE | TRUE | FALSE
5622 | MRT-BV02-P2PAC-130001 | 2018-10-02 | MRT-HK-REC-TT-180273 | FA | 0 | TRUE | TRUE | FALSE
5623 | MRT-CV03-P0GEN-135382 | 2018-10-02 | MRT-HK-REC-TT-180268 | FA | 0 | TRUE | FALSE | FALSE
5624 | MRT-QM03-P0ZEN-145009 | 2018-10-02 | MRT-HK-REC-TT-180274 | FA | 0 | TRUE | FALSE | FALSE
5625 | MRT-XG02-P2PBB-604112 | 2018-10-02 | MRT-DS-REC-TT-180794 | FC | 3 | TRUE | TRUE | FALSE
5626 | MRT-CC02-P0UPC-175735 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5627 | MRT-CC02-P0UPC-175720 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 2 | TRUE | TRUE | FALSE
5628 | MRT-CC02-P0UPC-175725 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 2 | TRUE | TRUE | FALSE
5629 | MRT-CC02-P0UPC-175730 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 2 | TRUE | TRUE | FALSE
5630 | MRT-CC02-P0UPC-175740 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5631 | MRT-CC02-P0UPC-175745 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5632 | MRT-CC02-P0UPC-175723 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5633 | MRT-CC02-P0UPC-175726 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 2 | TRUE | TRUE | FALSE
5634 | MRT-CC02-P0UPC-175727 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5635 | MRT-CC02-P0UPC-175728 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5636 | MRT-CC02-P0UPC-175729 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5637 | MRT-CC02-P0UPC-175731 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5638 | MRT-CC02-P0UPC-175732 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5639 | MRT-CC02-P0UPC-175733 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5640 | MRT-CC02-P0UPC-175737 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5641 | MRT-CC02-P0UPC-175741 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5642 | MRT-CC02-P0UPC-175742 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5643 | MRT-CC02-P0UPC-175743 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5644 | MRT-CC02-P0UPC-175744 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
5645 | MRT-CC02-P0UPC-175746 | 2018-10-02 | MRT-HK-REC-TT-180250 | FA | 1 | TRUE | TRUE | FALSE
6020 | MRT-CA00-P0UST-186909 | 2018-10-02 | MRT-HK-REC-TT-180275 | FA | 2 | TRUE | TRUE | FALSE
5649 | MRT-YR05-P2SCA-127523 | 2018-10-04 | MRT-DS-REC-TT-180782 | FC | 2 | TRUE | TRUE | FALSE
5650 | MRT-YR05-P3SCA-127523 | 2018-10-04 | MRT-DS-REC-TT-180782 | FC | 2 | TRUE | TRUE | FALSE
5651 | MRT-YV02-P2SCA-127532 | 2018-10-04 | MRT-DS-REC-TT-180784 | FI | 0 | TRUE | FALSE | FALSE
5652 | MRT-YV02-P3SCA-127532 | 2018-10-04 | MRT-DS-REC-TT-180784 | FI | 0 | TRUE | FALSE | FALSE
5653 | MRT-YT01-P2PGB-113104 | 2018-10-04 | MRT-DS-REC-TT-180787-FC | FC | 3 | TRUE | TRUE | FALSE
5654 | MRT-YD00-P2PGB-113105 | 2018-10-04 | MRT-DS-REC-TT-180787-FC | FC | 3 | TRUE | TRUE | FALSE
5655 | MRT-YT01-P3PGB-113104 | 2018-10-04 | MRT-DS-REC-TT-180787-FC | FC | 3 | TRUE | TRUE | FALSE
5656 | MRT-YD00-P3PGB-113105 | 2018-10-04 | MRT-DS-REC-TT-180787-FC | FC | 3 | TRUE | TRUE | FALSE
5657 | MRT-UE00-P2LB-122008 | 2018-10-04 | MRT-DS-REC-TT-180773-FC | FC | 4 | TRUE | TRUE | FALSE
5658 | MRT-UE00-P3LB-122008 | 2018-10-04 | MRT-DS-REC-TT-180773-FC | FC | 2 | TRUE | TRUE | FALSE
5659 | MRT-XJ00-P2MKJ-220001 | 2018-10-04 | MRT-DS-REC-TT-180778-FC | FC | 3 | TRUE | TRUE | FALSE
5660 | MRT-XK00-P2MKJ-220001 | 2018-10-04 | MRT-DS-REC-TT-180779-FC | FC | 2 | TRUE | TRUE | FALSE
5661 | MRT-YD00-P2LB-122109 | 2018-10-04 | MRT-DS-REC-TT-180798 | FI | 1 | TRUE | TRUE | FALSE
5662 | MRT-YD00-P3LB-122109 | 2018-10-04 | MRT-DS-REC-TT-180798 | FI | 1 | TRUE | TRUE | FALSE
5663 | MRT-XJ00-P2PAB-140001 | 2018-10-04 | MRT-DS-REC-TT-180583-FC | FC | 2 | TRUE | TRUE | FALSE
5664 | MRT-XJ00-P3PAB-140001 | 2018-10-04 | MRT-DS-REC-TT-180583-FC | FC | 2 | TRUE | TRUE | FALSE
5665 | MRT-XJ00-P2PAB-142100 | 2018-10-04 | MRT-DS-REC-TT-180523-FC | FC | 1 | TRUE | TRUE | FALSE
5666 | MRT-XJ00-P3PAB-143100 | 2018-10-04 | MRT-DS-REC-TT-180523-FC | FC | 1 | TRUE | TRUE | FALSE
5667 | MRT-XJ00-P3PAB-144100 | 2018-10-04 | MRT-DS-REC-TT-180523-FC | FC | 1 | TRUE | TRUE | FALSE
5668 | MRT-XA01-P0ABA-150513 | 2018-10-04 | MRT-HK-REC-TT-180261 | FA | 1 | TRUE | TRUE | FALSE
5669 | MRT-XA01-P0ABA-150510 | 2018-10-04 | MRT-HK-REC-TT-180261 | FA | 1 | TRUE | TRUE | FALSE
5670 | MRT-CA01-P0UMX-187214 | 2018-10-04 | MRT-HK-REC-TT-180277 | FA | 1 | TRUE | TRUE | FALSE
5671 | MRT-CA02-P0UMX-187220 | 2018-10-04 | MRT-HK-REC-TT-180277 | FA | 1 | TRUE | TRUE | FALSE
5672 | MRT-CA03-P0UMX-187222 | 2018-10-04 | MRT-HK-REC-TT-180277 | FA | 1 | TRUE | TRUE | FALSE
5673 | MRT-CC02-P0UQQ-175840 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 0 | TRUE | TRUE | FALSE
5674 | MRT-CC02-P0UQQ-175841 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 0 | TRUE | TRUE | FALSE
5675 | MRT-CC02-P0UQQ-175842 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 0 | TRUE | TRUE | FALSE
5676 | MRT-CC03-P0UQQ-175843 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 0 | TRUE | TRUE | FALSE
5677 | MRT-CC03-P0UQQ-175844 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 0 | TRUE | TRUE | FALSE
5678 | MRT-CC02-P0UQQ-175820 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 3 | TRUE | TRUE | FALSE
5679 | MRT-CC02-P0UQQ-175825 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 3 | TRUE | TRUE | FALSE
5680 | MRT-CC02-P0UQQ-175830 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 3 | TRUE | TRUE | FALSE
5681 | MRT-CC03-P0UQQ-175835 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 2 | TRUE | TRUE | FALSE
5682 | MRT-CC02-P0UQQ-175826 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 3 | TRUE | TRUE | FALSE
5683 | MRT-CC02-P0UQQ-175827 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 3 | TRUE | TRUE | FALSE
5684 | MRT-CC02-P0UQQ-175828 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 3 | TRUE | TRUE | FALSE
5685 | MRT-CC02-P0UQQ-175829 | 2018-10-04 | MRT-HK-REC-TT-276 | FA | 3 | TRUE | TRUE | FALSE
5686 | MRT-CA03-P0USG-186877 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 1 | TRUE | TRUE | FALSE
5687 | MRT-CA00-P0USG-186867 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 0 | TRUE | TRUE | FALSE
5688 | MRT-CA06-P0USG-186854 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 1 | TRUE | TRUE | FALSE
5689 | MRT-CA00-P0USG-186858 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 2 | TRUE | TRUE | FALSE
5690 | MRT-CA00-P0USG-186862 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 2 | TRUE | TRUE | FALSE
5691 | MRT-CA00-P0USG-186864 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 2 | TRUE | TRUE | FALSE
5692 | MRT-CA00-P0USG-186866 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 0 | TRUE | TRUE | FALSE
5693 | MRT-CA01-P0USG-186868 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 1 | TRUE | TRUE | FALSE
5694 | MRT-CA02-P0USG-186874 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 1 | TRUE | TRUE | FALSE
5695 | MRT-CA03-P0USG-186876 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 1 | TRUE | TRUE | FALSE
5696 | MRT-CA03-P0USG-186880 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 1 | TRUE | TRUE | FALSE
5697 | MRT-CA03-P0USG-186882 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 1 | TRUE | TRUE | FALSE
5698 | MRT-CA03-P0USG-186884 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 1 | TRUE | TRUE | FALSE
5699 | MRT-CA03-P0USG-186886 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 0 | TRUE | TRUE | FALSE
5700 | MRT-CA03-P0USG-186888 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 0 | TRUE | TRUE | FALSE
5701 | MRT-CA03-P0USG-186890 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 0 | TRUE | TRUE | FALSE
5702 | MRT-CA01-P0USG-186894 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 0 | TRUE | TRUE | FALSE
5703 | MRT-CA00-P0USG-186857 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 2 | TRUE | TRUE | FALSE
5704 | MRT-CA00-P0USG-186857 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 2 | TRUE | TRUE | FALSE
5705 | MRT-CA00-P0USG-186863 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 2 | TRUE | TRUE | FALSE
5706 | MRT-CA01-P0USG-186869 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 1 | TRUE | TRUE | FALSE
5707 | MRT-CA03-P0USG-186885 | 2018-10-04 | MRT-HK-REC-TT-180278 | FA | 1 | TRUE | TRUE | FALSE
5708 | MRT-YS00-P2LB-122092 | 2018-10-04 | MRT-DS-REC-TT-180801 | FC | 2 | TRUE | TRUE | FALSE
5709 | MRT-YS00-P3LB-122092 | 2018-10-04 | MRT-DS-REC-TT-180801 | FC | 2 | TRUE | TRUE | FALSE
5710 | MRT-XW03-P0BFT-150010 | 2018-10-05 | MRT-HK-REC-TT-180279 | FA | 1 | TRUE | TRUE | FALSE
5711 | MRT-XN00-P2LB-122032 | 2018-10-05 | MRT-DS-REC-TT-180803 | FI | 3 | TRUE | TRUE | FALSE
5712 | MRT-XN00-P3LB-122032 | 2018-10-05 | MRT-DS-REC-TT-180803 | FI | 2 | TRUE | TRUE | FALSE
5713 | MRT-YK01-P2LB-122074 | 2018-10-05 | MRT-DS-REC-TT-180804 | FC | 1 | TRUE | TRUE | FALSE
5714 | MRT-YK01-P3LB-122074 | 2018-10-05 | MRT-DS-REC-TT-180804 | FC | 1 | TRUE | TRUE | FALSE
5715 | MRT-CV03-P2ZEN-165201 | 2018-10-05 | MRT-DS-REC-TT-180802 | FC | 4 | TRUE | TRUE | FALSE
5716 | MRT-CV03-P3ZEN-165201 | 2018-10-05 | MRT-DS-REC-TT-180802 | FC | 4 | TRUE | TRUE | FALSE
5717 | MRT-CV03-P2ZEN-165102 | 2018-10-05 | MRT-DS-REC-TT-180805 | FC | 3 | TRUE | TRUE | FALSE
5718 | MRT-CV03-P3ZEN-165102 | 2018-10-05 | MRT-DS-REC-TT-180805 | FC | 3 | TRUE | TRUE | FALSE
5719 | MRT-DN02-P2MAJ-830011 | 2018-10-05 | MRT-DS-REC-TT-180806 | FA | 0 | TRUE | FALSE | FALSE
5720 | MRT-DN02-P2LBF-830013 | 2018-10-05 | MRT-DS-REC-TT-180800 | FA | 0 | TRUE | FALSE | FALSE
5721 | MRT-DN02-P2QU-830009 | 2018-10-05 | MRT-DS-REC-TT-180799 | FA | 0 | TRUE | FALSE | FALSE
5722 | MRT-CQ02-P3MAG-602011 | 2018-10-05 | MRT-DS-REC-TT-180807 | FI | 0 | TRUE | FALSE | FALSE
5723 | MRT-CA06-P0UPB-187001 | 2018-10-08 | MRT-HK-REC-TT-180280 | FA | 2 | TRUE | TRUE | FALSE
5724 | MRT-CA01-P0UPB-187002 | 2018-10-08 | MRT-HK-REC-TT-180280 | FA | 3 | TRUE | TRUE | FALSE
5725 | MRT-XA00-P2QU-130025 | 2018-10-08 | MRT-DS-REC-TT-180758-FC | FC | 4 | TRUE | TRUE | FALSE
5726 | MRT-XA00-P3QU-130025 | 2018-10-08 | MRT-DS-REC-TT-180758-FC | FC | 4 | TRUE | TRUE | FALSE
5727 | MRT-XA00-P2QC-130002 | 2018-10-08 | MRT-DS-REC-TT-180760-FC | FC | 3 | TRUE | TRUE | FALSE
5728 | MRT-XA00-P3QC-130002 | 2018-10-08 | MRT-DS-REC-TT-180760-FC | FC | 3 | TRUE | TRUE | FALSE
5729 | MRT-YT01-P3CYP-160001 | 2018-10-08 | MRT-HK-REC-TT-180281 | FA | 1 | TRUE | TRUE | FALSE
5730 | MRT-CA03-P0UMA-180035 | 2018-10-08 | MRT-DS-REC-TT-180808 | FC | 3 | TRUE | TRUE | FALSE
5731 | MRT-CA03-P0UMA-180036 | 2018-10-08 | MRT-DS-REC-TT-180808 | FC | 3 | TRUE | TRUE | FALSE
5732 | MRT-CA03-P0UMA-180037 | 2018-10-08 | MRT-DS-REC-TT-180808 | FC | 3 | TRUE | TRUE | FALSE
5733 | MRT-QM03-P0ZEN-145012 | 2018-10-10 | MRT-HK-REC-TT-180282 | FA | 1 | TRUE | TRUE | FALSE
5734 | MRT-YS01-P2SCA-127511 | 2018-10-10 | MRT-DS-REC-TT-180781-FC | FC | 2 | TRUE | TRUE | FALSE
5735 | MRT-YS01-P3SCA-127511 | 2018-10-10 | MRT-DS-REC-TT-180781-FC | FC | 2 | TRUE | TRUE | FALSE
5736 | MRT-CC02-P0UMA-171003 | 2018-10-10 | MRT-DS-REC-TT-180809 | FA | 0 | TRUE | FALSE | FALSE
5737 | MRT-VK02-P0UMA-171006 | 2018-10-10 | MRT-DS-REC-TT-180809 | FA | 0 | TRUE | FALSE | FALSE
5738 | MRT-YS01-P2QC-130020 | 2018-10-10 | MRT-DS-REC-TT-180811 | FI | 2 | TRUE | TRUE | FALSE
5739 | MRT-YS01-P3QC-130020 | 2018-10-10 | MRT-DS-REC-TT-180811 | FI | 2 | TRUE | TRUE | FALSE
5740 | MRT-CA01-P0UMA-180044 | 2018-10-10 | MRT-DS-REC-TT-180810 | FC | 2 | TRUE | TRUE | FALSE
5741 | MRT-CA02-P0UMA-180045 | 2018-10-10 | MRT-DS-REC-TT-180810 | FC | 2 | TRUE | TRUE | FALSE
5742 | MRT-CA00-P0UMA-180047 | 2018-10-10 | MRT-DS-REC-TT-180810 | FC | 3 | TRUE | TRUE | FALSE
5743 | MRT-DN02-P2MAJ-830014 | 2018-10-10 | MRT-DS-REC-TT-180812 | FA | 0 | TRUE | FALSE | FALSE
5744 | MRT-YL00-P2GM-128512 | 2018-10-11 | MRT-DS-REC-TT-180813 | FC | 2 | TRUE | TRUE | FALSE
5745 | MRT-YL00-P3GM-128512 | 2018-10-11 | MRT-DS-REC-TT-180813 | FC | 2 | TRUE | TRUE | FALSE
5746 | MRT-YD00-P2PAB-113251 | 2018-10-11 | MRT-DS-REC-TT-180814 | FC | 4 | TRUE | TRUE | FALSE
5747 | MRT-XG02-P2PAB-113253 | 2018-10-11 | MRT-DS-REC-TT-180814 | FC | 4 | TRUE | TRUE | FALSE
5748 | MRT-YD00-P3PAB-113251 | 2018-10-11 | MRT-DS-REC-TT-180814 | FC | 4 | TRUE | TRUE | FALSE
5749 | MRT-XG02-P3PAB-113253 | 2018-10-11 | MRT-DS-REC-TT-180814 | FC | 4 | TRUE | TRUE | FALSE
5750 | MRT-CC07-P2UHA-170101 | 2018-10-11 | MRT-DS-REC-TT-180815 | FC | 3 | TRUE | TRUE | FALSE
5751 | MRT-CC02-P2UHA-170103 | 2018-10-11 | MRT-DS-REC-TT-180815 | FC | 7 | TRUE | TRUE | FALSE
5752 | MRT-CC07-P3UHA-170101 | 2018-10-11 | MRT-DS-REC-TT-180815 | FC | 3 | TRUE | TRUE | FALSE
5753 | MRT-CC02-P3UHA-170103 | 2018-10-11 | MRT-DS-REC-TT-180815 | FC | 7 | TRUE | TRUE | FALSE
5754 | MRT-XS01-P2LB-122111 | 2018-10-12 | MRT-DS-REC-TT-180817 | FI | 0 | TRUE | FALSE | FALSE
5755 | MRT-XR00-P2MAV-220041 | 2018-10-12 | MRT-DS-REC-TT-180816 | FI | 0 | TRUE | FALSE | FALSE
5756 | MRT-CA00-P0UCA-180107 | 2018-10-12 | MRT-DS-REC-TT-180792-FC | FC | 4 | TRUE | TRUE | FALSE
5757 | MRT-CA00-P0UCA-180108 | 2018-10-12 | MRT-DS-REC-TT-180792-FC | FC | 4 | TRUE | TRUE | FALSE
5758 | MRT-CA00-P0UCA-180113 | 2018-10-12 | MRT-DS-REC-TT-180792-FC | FC | 4 | TRUE | TRUE | FALSE
5759 | MRT-CA01-P0UCA-180122 | 2018-10-12 | MRT-DS-REC-TT-180792-FC | FC | 4 | TRUE | TRUE | FALSE
5760 | MRT-CA01-P0UCA-180123 | 2018-10-12 | MRT-DS-REC-TT-180792-FC | FC | 4 | TRUE | TRUE | FALSE
5761 | MRT-CA01-P0UCA-180127 | 2018-10-12 | MRT-DS-REC-TT-180792-FC | FC | 4 | TRUE | TRUE | FALSE
5762 | MRT-CA02-P0UCA-180134 | 2018-10-12 | MRT-DS-REC-TT-180792-FC | FC | 4 | TRUE | TRUE | FALSE
5763 | MRT-CA03-P0UMA-180035 | 2018-10-12 | MRT-DS-REC-TT-180808-FC | FC | 3 | TRUE | TRUE | FALSE
5764 | MRT-CA03-P0UMA-180036 | 2018-10-12 | MRT-DS-REC-TT-180808-FC | FC | 3 | TRUE | TRUE | FALSE
5765 | MRT-CA03-P0UMA-180037 | 2018-10-12 | MRT-DS-REC-TT-180808-FC | FC | 3 | TRUE | TRUE | FALSE
5766 | MRT-CV03-P0GEN-135381 | 2018-10-12 | MRT-HK-REC-TT-180283 | FA | 0 | TRUE | FALSE | FALSE
5767 | MRT-CA05-P0UST-145107 | 2018-10-15 | MRT-HK-REC-TT-180289 | FA | 0 | TRUE | FALSE | FALSE
5768 | MRT-CA05-P0UST-145106 | 2018-10-15 | MRT-HK-REC-TT-180289 | FA | 0 | TRUE | FALSE | FALSE
5769 | MRT-CA05-P0UST-145105 | 2018-10-15 | MRT-HK-REC-TT-180289 | FA | 0 | TRUE | FALSE | FALSE
5770 | MRT-CA05-P0UST-145104 | 2018-10-15 | MRT-HK-REC-TT-180289 | FA | 0 | TRUE | FALSE | FALSE
5771 | MRT-CA05-P0UYX-145103 | 2018-10-15 | MRT-HK-REC-TT-180289 | FA | 0 | TRUE | FALSE | FALSE
5772 | MRT-CA05-P0UYX-145102 | 2018-10-15 | MRT-HK-REC-TT-180289 | FA | 0 | TRUE | FALSE | FALSE
5773 | MRT-CA05-P0UYX-145101 | 2018-10-15 | MRT-HK-REC-TT-180289 | FA | 0 | TRUE | FALSE | FALSE
5774 | MRT-CA05-P0UYX-145100 | 2018-10-15 | MRT-HK-REC-TT-180289 | FA | 0 | TRUE | FALSE | FALSE
5775 | MRT-YT01-P0GEN-135355 | 2018-10-15 | MRT-HK-REC-TT-180284 | FA | 0 | TRUE | FALSE | FALSE
5776 | MRT-YT01-P0GEN-135353 | 2018-10-15 | MRT-HK-REC-TT-180284 | FA | 0 | TRUE | FALSE | FALSE
5777 | MRT-XW03-P3GC-135111 | 2018-10-15 | MRT-HK-REC-TT-180284 | FA | 1 | TRUE | TRUE | FALSE
5778 | MRT-BF01-P3CYP-160008 | 2018-10-15 | MRT-HK-REC-TT-180285 | FA | 0 | TRUE | FALSE | FALSE
5779 | MRT-VN03-P2LB-122015 | 2018-10-15 | MRT-DS-REC-TT-180818 | FC | 3 | TRUE | TRUE | FALSE
5780 | MRT-VN03-P3LB-122015 | 2018-10-15 | MRT-DS-REC-TT-180818 | FC | 3 | TRUE | TRUE | FALSE
5781 | MRT-CH04-P3BAT-150399 | 2018-10-15 | MRT-HK-REC-TT-180286 | FA | 0 | TRUE | FALSE | FALSE
5782 | MRT-YS01-P4BBA-150120 | 2018-10-15 | MRT-HK-REC-TT-180286 | FA | 0 | TRUE | FALSE | FALSE
5783 | MRT-XW03-P0GN-135211 | 2018-10-16 | MRT-HK-REC-TT-180287 | FA | 0 | TRUE | TRUE | FALSE
5784 | MRT-XG02-P3GC-135102 | 2018-10-16 | MRT-HK-REC-TT-180287 | FA | 3 | TRUE | TRUE | FALSE
5785 | MRT-XG02-P0GN-135202 | 2018-10-16 | MRT-HK-REC-TT-180287 | FA | 4 | TRUE | TRUE | FALSE
5786 | MRT-QM03-P0ZEN-155009 | 2018-10-16 | MRT-HK-REC-TT-180288 | FI | 0 | TRUE | FALSE | FALSE
5787 | MRT-DN02-P2PAH-830015 | 2018-10-16 | MRT-DS-REC-TT-180820 | FA | 0 | TRUE | FALSE | FALSE
5788 | MRT-YD00-P3MKW-220001 | 2018-10-16 | MRT-DS-REC-TT-180796 | FC | 2 | TRUE | TRUE | FALSE
5789 | MRT-YD00-P3MKW-220005 | 2018-10-16 | MRT-DS-REC-TT-180796 | FC | 2 | TRUE | TRUE | FALSE
5790 | MRT-YQ03-P2LB-122086 | 2018-10-16 | MRT-DS-REC-TT-180819 | FI | 1 | TRUE | TRUE | FALSE
5791 | MRT-YQ03-P3LB-122086 | 2018-10-16 | MRT-DS-REC-TT-180819 | FI | 1 | TRUE | TRUE | FALSE
5792 | MRT-CC02-P2UMA-170207 | 2018-10-17 | MRT-DS-REC-TT-180821 | FC | 4 | TRUE | TRUE | FALSE
5793 | MRT-CC02-P2UMA-170208 | 2018-10-17 | MRT-DS-REC-TT-180821 | FC | 4 | TRUE | TRUE | FALSE
5794 | MRT-CC02-P3UMA-170207 | 2018-10-17 | MRT-DS-REC-TT-180821 | FC | 4 | TRUE | TRUE | FALSE
5795 | MRT-CC02-P3UMA-170208 | 2018-10-17 | MRT-DS-REC-TT-180821 | FC | 4 | TRUE | TRUE | FALSE
5796 | MRT-YT01-P2LB-122095 | 2018-10-17 | MRT-DS-REC-TT-180823 | FC | 2 | TRUE | TRUE | FALSE
5797 | MRT-YT01-P3LB-122095 | 2018-10-17 | MRT-DS-REC-TT-180823 | FC | 2 | TRUE | TRUE | FALSE
5798 | MRT-YS00-P2LB-122092 | 2018-10-17 | MRT-DS-REC-TT-180801-FC | FC | 2 | TRUE | TRUE | FALSE
5799 | MRT-YS00-P3LB-122092 | 2018-10-17 | MRT-DS-REC-TT-180801-FC | FC | 2 | TRUE | TRUE | FALSE
5800 | MRT-CV03-P2ZEN-165201 | 2018-10-17 | MRT-DS-REC-TT-180802-FC | FC | 4 | TRUE | TRUE | FALSE
5801 | MRT-CV03-P3ZEN-165201 | 2018-10-17 | MRT-DS-REC-TT-180802-FC | FC | 4 | TRUE | TRUE | FALSE
5802 | MRT-CV03-P2ZEN-165102 | 2018-10-17 | MRT-DS-REC-TT-180805-FC | FC | 3 | TRUE | TRUE | FALSE
5803 | MRT-CV03-P3ZEN-165102 | 2018-10-17 | MRT-DS-REC-TT-180805-FC | FC | 3 | TRUE | TRUE | FALSE
5804 | MRT-DN02-P2PG-830004 | 2018-10-17 | MRT-DS-REC-TT-180766-FC | FC | 0 | TRUE | TRUE | FALSE
5805 | MRT-DN02-P2QC-830008 | 2018-10-17 | MRT-DS-REC-TT-180793-FC | FC | 0 | TRUE | TRUE | FALSE
5806 | MRT-XG02-P2MAV-220006 | 2018-10-17 | MRT-DS-REC-TT-180797-FC | FC | 2 | TRUE | TRUE | FALSE
5807 | MRT-XS01-P3CJJ-240060 | 2018-10-17 | MRT-DS-REC-TT-180822 | FI | 0 | TRUE | FALSE | FALSE
5808 | MRT-DP00-P0ZEN-070001 | 2018-10-17 | MRT-DS-REC-TT-180731-FC | FC | 3 | TRUE | TRUE | FALSE
5809 | MRT-CC04-P0ULY-176501 | 2018-10-17 | MRT-HK-REC-TT-180290 | FI | 0 | TRUE | FALSE | FALSE
5810 | MRT-CC04-P0ULY-176502 | 2018-10-17 | MRT-HK-REC-TT-180290 | FI | 0 | TRUE | FALSE | FALSE
5811 | MRT-CC04-P0ULY-176505 | 2018-10-17 | MRT-HK-REC-TT-180290 | FI | 0 | TRUE | FALSE | FALSE
5812 | MRT-CC04-P0ULY-176506 | 2018-10-17 | MRT-HK-REC-TT-180290 | FI | 0 | TRUE | FALSE | FALSE
5813 | MRT-CC04-P0ULY-176509 | 2018-10-17 | MRT-HK-REC-TT-180290 | FI | 0 | TRUE | FALSE | FALSE
5814 | MRT-CC04-P0ULY-176510 | 2018-10-17 | MRT-HK-REC-TT-180290 | FI | 0 | TRUE | FALSE | FALSE
5815 | MRT-CC04-P0ULY-176512 | 2018-10-17 | MRT-HK-REC-TT-180290 | FI | 0 | TRUE | FALSE | FALSE
5816 | MRT-CC04-P0ULY-176513 | 2018-10-17 | MRT-HK-REC-TT-180290 | FI | 0 | TRUE | FALSE | FALSE
5817 | MRT-YF00-P2CJJ-240064 | 2018-10-19 | MRT-DS-REC-TT-180824 | FI | 0 | TRUE | FALSE | FALSE
5818 | MRT-CC00-P0ZEN-145401 | 2018-10-19 | MRT-HK-REC-TT-180292 | FA | 3 | TRUE | TRUE | FALSE
5819 | MRT-XH01-P2LB-122112 | 2018-10-19 | MRT-DS-REC-TT-180825 | FI | 0 | TRUE | FALSE | FALSE
5820 | MRT-XH01-P3LB-122112 | 2018-10-19 | MRT-DS-REC-TT-180825 | FI | 0 | TRUE | FALSE | FALSE
5821 | MRT-QM03-P0ZEN-155010 | 2018-10-19 | MRT-HK-REC-TT-180291 | FA | 0 | TRUE | FALSE | FALSE
5822 | MRT-QM03-P0ZEN-155011 | 2018-10-19 | MRT-HK-REC-TT-180291 | FA | 0 | TRUE | FALSE | FALSE
5823 | MRT-CA01-P0UCA-180122 | 2018-10-19 | MRT-DS-REC-TT-180826 | FC | 5 | TRUE | TRUE | FALSE
5824 | MRT-CA01-P0UCA-180123 | 2018-10-19 | MRT-DS-REC-TT-180826 | FC | 5 | TRUE | TRUE | FALSE
5825 | MRT-CA01-P0UCA-180128 | 2018-10-19 | MRT-DS-REC-TT-180826 | FC | 4 | TRUE | TRUE | FALSE
5826 | MRT-DN02-P2H-830016 | 2018-10-19 | MRT-DS-REC-TT-180827 | FA | 0 | TRUE | FALSE | FALSE
5827 | MRT-QM01-P0GEN-135384 | 2018-10-19 | MRT-HK-REC-TT-180293 | FA | 0 | TRUE | FALSE | FALSE
5828 | MRT-CA00-P0UGX-186956 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 2 | TRUE | TRUE | FALSE
5829 | MRT-CA00-P0UGX-186960 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 2 | TRUE | TRUE | FALSE
5830 | MRT-CA01-P0UGX-186972 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 0 | TRUE | TRUE | FALSE
5831 | MRT-CA02-P0UGX-186975 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 0 | TRUE | TRUE | FALSE
5832 | MRT-CA06-P0UGX-186954 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5833 | MRT-CA00-P0UGX-186962 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 0 | TRUE | TRUE | FALSE
5834 | MRT-CA00-P0UGX-186964 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 0 | TRUE | TRUE | FALSE
5835 | MRT-CA00-P0UGX-186966 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 2 | TRUE | TRUE | FALSE
5836 | MRT-CA01-P0UGX-186968 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 0 | TRUE | TRUE | FALSE
5837 | MRT-CA01-P0UGX-186976 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5838 | MRT-CA01-P0UGX-186978 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5839 | MRT-CA02-P0UGX-186982 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5840 | MRT-CA02-P0UGX-186984 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5841 | MRT-CA01-P0UGX-186988 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5842 | MRT-CA00-P0UGX-186957 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 2 | TRUE | TRUE | FALSE
5843 | MRT-CA00-P0UGX-186961 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 2 | TRUE | TRUE | FALSE
5844 | MRT-CA00-P0UGX-186963 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 2 | TRUE | TRUE | FALSE
5845 | MRT-CA01-P0UGX-186973 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5846 | MRT-CA01-P0UGX-186986 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5847 | MRT-CA02-P0UGX-186974 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5848 | MRT-CA02-P0UGX-186983 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5849 | MRT-CA02-P0UGX-186985 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5850 | MRT-CA02-P0UGX-186991 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5851 | MRT-CA02-P0UGX-186992 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5852 | MRT-CA02-P0UGX-186993 | 2018-10-19 | MRT-HK-REC-TT-180294 | FA | 1 | TRUE | TRUE | FALSE
5853 | MRT-CA01-P0UXA-186712 | 2018-10-19 | MRT-HK-REC-TT-180297 | FA | 1 | TRUE | TRUE | FALSE
5854 | MRT-CA01-P0UXA-186714 | 2018-10-19 | MRT-HK-REC-TT-180297 | FA | 1 | TRUE | TRUE | FALSE
5855 | MRT-CA01-P0UXA-186716 | 2018-10-19 | MRT-HK-REC-TT-180297 | FA | 1 | TRUE | TRUE | FALSE
5856 | MRT-CA01-P0UXA-186708 | 2018-10-19 | MRT-HK-REC-TT-180297 | FA | 1 | TRUE | TRUE | FALSE
5857 | MRT-CA01-P0UXA-186710 | 2018-10-19 | MRT-HK-REC-TT-180297 | FA | 1 | TRUE | TRUE | FALSE
5858 | MRT-CA01-P0UXA-186713 | 2018-10-19 | MRT-HK-REC-TT-180297 | FA | 1 | TRUE | TRUE | FALSE
5859 | MRT-CA01-P0UXA-186718 | 2018-10-19 | MRT-HK-REC-TT-180297 | FA | 1 | TRUE | TRUE | FALSE
5860 | MRT-CA01-P0UXA-186719 | 2018-10-19 | MRT-HK-REC-TT-180297 | FA | 1 | TRUE | TRUE | FALSE
5861 | MRT-YD00-P2PAB-113251 | 2018-10-22 | MRT-DS-REC-TT-180814-FC | FC | 4 | TRUE | TRUE | FALSE
5862 | MRT-XG02-P2PAB-113253 | 2018-10-22 | MRT-DS-REC-TT-180814-FC | FC | 4 | TRUE | TRUE | FALSE
5863 | MRT-YD00-P3PAB-113251 | 2018-10-22 | MRT-DS-REC-TT-180814-FC | FC | 4 | TRUE | TRUE | FALSE
5864 | MRT-XG02-P3PAB-113253 | 2018-10-22 | MRT-DS-REC-TT-180814-FC | FC | 4 | TRUE | TRUE | FALSE
5865 | MRT-DN02-P2SCA-830007 | 2018-10-22 | MRT-DS-REC-TT-180795-FC | FC | 0 | TRUE | TRUE | FALSE
5866 | MRT-CA06-P0UQA-186506 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 1 | TRUE | TRUE | FALSE
5867 | MRT-CA00-P0UQA-186510 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 2 | TRUE | TRUE | FALSE
5868 | MRT-CA00-P0UQA-186526 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 0 | TRUE | TRUE | FALSE
5869 | MRT-CA03-P0UQA-186550 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 1 | TRUE | TRUE | FALSE
5870 | MRT-CA03-P0UQA-186552 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 1 | TRUE | TRUE | FALSE
5871 | MRT-CA03-P0UQA-186554 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 1 | TRUE | TRUE | FALSE
5872 | MRT-CA03-P0UQA-186556 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 1 | TRUE | TRUE | FALSE
5873 | MRT-CA03-P0UQA-186558 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 1 | TRUE | TRUE | FALSE
5874 | MRT-CA03-P0UQA-186560 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 0 | TRUE | TRUE | FALSE
5875 | MRT-CA03-P0UQA-186562 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 1 | TRUE | TRUE | FALSE
5876 | MRT-CA03-P0UQA-186564 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 1 | TRUE | TRUE | FALSE
5877 | MRT-CA03-P0UQA-186566 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 1 | TRUE | TRUE | FALSE
5878 | MRT-CA03-P0UQA-186568 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 1 | TRUE | TRUE | FALSE
5879 | MRT-CA03-P0UQA-186574 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 0 | TRUE | TRUE | FALSE
5880 | MRT-CA00-P0UQA-186511 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 2 | TRUE | TRUE | FALSE
5881 | MRT-CA00-P0UQA-186512 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 2 | TRUE | TRUE | FALSE
5882 | MRT-CA00-P0UQA-186515 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 2 | TRUE | TRUE | FALSE
5883 | MRT-CA00-P0UQA-186520 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 2 | TRUE | TRUE | FALSE
5884 | MRT-CA00-P0UQA-186522 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 2 | TRUE | TRUE | FALSE
5885 | MRT-CA03-P0UQA-186559 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 1 | TRUE | TRUE | FALSE
5886 | MRT-CA03-P0UQA-186577 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 0 | TRUE | TRUE | FALSE
5887 | MRT-CA03-P0UQA-186576 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 0 | TRUE | TRUE | FALSE
5888 | MRT-CA03-P0UQA-186575 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 0 | TRUE | TRUE | FALSE
5889 | MRT-CA00-P0UQA-186523 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 0 | TRUE | TRUE | FALSE
5890 | MRT-CC00-P0UQA-186513 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 0 | TRUE | TRUE | FALSE
5891 | MRT-CA03-P0UQA-186561 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 0 | TRUE | TRUE | FALSE
5892 | MRT-CA03-P0UQA-186569 | 2018-10-22 | MRT-HK-REC-TT-180295 | FA | 0 | TRUE | TRUE | FALSE
5893 | MRT-CA06-P0UPB-187004 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 1 | TRUE | TRUE | FALSE
5894 | MRT-CA00-P0UPB-187006 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 2 | TRUE | TRUE | FALSE
5895 | MRT-CA00-P0UPB-187008 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 0 | TRUE | TRUE | FALSE
5896 | MRT-CA00-P0UPB-187010 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 0 | TRUE | TRUE | FALSE
5897 | MRT-CA00-P0UPB-187012 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 2 | TRUE | TRUE | FALSE
5898 | MRT-CA00-P0UPB-187014 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 2 | TRUE | TRUE | FALSE
5899 | MRT-CA01-P0UPB-187016 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 1 | TRUE | TRUE | FALSE
5900 | MRT-CA02-P0UPB-187018 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 1 | TRUE | TRUE | FALSE
5901 | MRT-CA01-P0UPB-187020 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 1 | TRUE | TRUE | FALSE
5902 | MRT-CA01-P0UPB-187022 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 1 | TRUE | TRUE | FALSE
5903 | MRT-CA01-P0UPB-187024 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 1 | TRUE | TRUE | FALSE
5904 | MRT-CA02-P0UPB-187026 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 1 | TRUE | TRUE | FALSE
5905 | MRT-CA02-P0UPB-187028 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 1 | TRUE | TRUE | FALSE
5906 | MRT-CA02-P0UPB-187030 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 0 | TRUE | TRUE | FALSE
5907 | MRT-CA01-P0UPB-187032 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 0 | TRUE | TRUE | FALSE
5908 | MRT-CA01-P0UPB-187034 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 0 | TRUE | TRUE | FALSE
5909 | MRT-CA00-P0UPB-187007 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 2 | TRUE | TRUE | FALSE
5910 | MRT-CA00-P0UPB-187009 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 2 | TRUE | TRUE | FALSE
5911 | MRT-CA01-P0UPB-187036 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 1 | TRUE | TRUE | FALSE
5912 | MRT-CA01-P0UPB-187037 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 1 | TRUE | TRUE | FALSE
5913 | MRT-CA01-P0UPB-187023 | 2018-10-22 | MRT-HK-REC-TT-180296 | FA | 1 | TRUE | TRUE | FALSE
5914 | MRT-YK01-P2LB-122074 | 2018-10-22 | MRT-DS-REC-TT-180804-FC | FC | 1 | TRUE | TRUE | FALSE
6057 | MRT-YK01-P3LB-122074 | 2018-10-22 | MRT-DS-REC-TT-180804-FC | FC | 1 | TRUE | TRUE | FALSE
5915 | MRT-YL01-P2QC-130034 | 2018-10-23 | MRT-DS-REC-TT-180830 | FI | 2 | TRUE | TRUE | FALSE
5916 | MRT-YL01-P3QC-130034 | 2018-10-23 | MRT-DS-REC-TT-180830 | FI | 2 | TRUE | TRUE | FALSE
5917 | MRT-YF02-P2QC-130006 | 2018-10-23 | MRT-DS-REC-TT-180831 | FC | 4 | TRUE | TRUE | FALSE
5918 | MRT-YF02-P3QC-130006 | 2018-10-23 | MRT-DS-REC-TT-180831 | FC | 4 | TRUE | TRUE | FALSE
5919 | MRT-XS00-P2QU-130026 | 2018-10-23 | MRT-DS-REC-TT-180832 | FC | 3 | TRUE | TRUE | FALSE
5920 | MRT-XS00-P3QU-130026 | 2018-10-23 | MRT-DS-REC-TT-180832 | FC | 3 | TRUE | TRUE | FALSE
5921 | MRT-YD05-P2QC-130035 | 2018-10-23 | MRT-DS-REC-TT-180833 | FI | 2 | TRUE | TRUE | FALSE
5922 | MRT-YD05-P3QC-130035 | 2018-10-23 | MRT-DS-REC-TT-180833 | FI | 2 | TRUE | TRUE | FALSE
5923 | MRT-YK10-P2MKA-220003 | 2018-10-23 | MRT-DS-REC-TT-180829 | FI | 1 | TRUE | TRUE | FALSE
5924 | MRT-YK09-P2MKC-230002 | 2018-10-23 | MRT-DS-REC-TT-180828 | FC | 3 | TRUE | TRUE | FALSE
5925 | MRT-YK09-P3MKC-230002 | 2018-10-23 | MRT-DS-REC-TT-180828 | FC | 3 | TRUE | TRUE | FALSE
5926 | MRT-YS01-P2MKC-230014 | 2018-10-23 | MRT-DS-REC-TT-180834 | FC | 2 | TRUE | TRUE | FALSE
5927 | MRT-YS01-P3MKC-230014 | 2018-10-23 | MRT-DS-REC-TT-180834 | FC | 2 | TRUE | TRUE | FALSE
6558 | MRT-XA01-P0ABA-150508 | 2018-10-23 | MRT-HK-REC-TT-180299 | FA | 1 | TRUE | TRUE | FALSE
7925 | MRT-YE06-P0UAA-150216 | 2018-10-23 | MRT-HK-REC-TT-180299 | FA | 0 | TRUE | FALSE | FALSE
8071 | MRT-YS01-P0ABA-150561 | 2018-10-23 | MRT-HK-REC-TT-180299 | FA | 0 | TRUE | FALSE | FALSE
8072 | MRT-YS01-P0ABA-150562 | 2018-10-23 | MRT-HK-REC-TT-180299 | FA | 0 | TRUE | FALSE | FALSE
5928 | MRT-XH01-P2LB-122112 | 2018-10-24 | MRT-DS-REC-TT-180825-FC | FC | 0 | TRUE | TRUE | FALSE
5929 | MRT-XH01-P3LB-122112 | 2018-10-24 | MRT-DS-REC-TT-180825-FC | FC | 0 | TRUE | TRUE | FALSE
5930 | MRT-YR05-P2SCA-127523 | 2018-10-24 | MRT-DS-REC-TT-180782-FC | FC | 2 | TRUE | TRUE | FALSE
5931 | MRT-YR05-P3SCA-127523 | 2018-10-24 | MRT-DS-REC-TT-180782-FC | FC | 2 | TRUE | TRUE | FALSE
5932 | MRT-YL00-P2GM-128512 | 2018-10-24 | MRT-DS-REC-TT-180813-FC | FC | 2 | TRUE | TRUE | FALSE
5933 | MRT-YL00-P3GM-128512 | 2018-10-24 | MRT-DS-REC-TT-180813-FC | FC | 2 | TRUE | TRUE | FALSE
5934 | MRT-YT01-P2LB-122095 | 2018-10-24 | MRT-DS-REC-TT-180823-FC | FC | 2 | TRUE | TRUE | FALSE
5935 | MRT-YT01-P3LB-122095 | 2018-10-24 | MRT-DS-REC-TT-180823-FC | FC | 2 | TRUE | TRUE | FALSE
5936 | MRT-DN02-P2QU-830009 | 2018-10-24 | MRT-DS-REC-TT-180799-FC | FC | 0 | TRUE | TRUE | FALSE
5937 | MRT-DN02-P2MAJ-830011 | 2018-10-24 | MRT-DS-REC-TT-180806-FC | FC | 0 | TRUE | TRUE | FALSE
5938 | MRT-VN03-P2LB-122015 | 2018-10-24 | MRT-DS-REC-TT-180818-FC | FC | 3 | TRUE | TRUE | FALSE
5939 | MRT-VN03-P3LB-122015 | 2018-10-24 | MRT-DS-REC-TT-180818-FC | FC | 3 | TRUE | TRUE | FALSE
5940 | MRT-YK09-P3MKC-230003 | 2018-10-24 | MRT-DS-REC-TT-180835 | FA | 1 | TRUE | TRUE | FALSE
5941 | MRT-YK00-P2LB-122076 | 2018-10-24 | MRT-DS-REC-TT-180837 | FC | 1 | TRUE | TRUE | FALSE
5942 | MRT-YK00-P3LB-122076 | 2018-10-24 | MRT-DS-REC-TT-180837 | FC | 1 | TRUE | TRUE | FALSE
5943 | MRT-YD02-P2LB-122064 | 2018-10-24 | MRT-DS-REC-TT-180836 | FC | 2 | TRUE | TRUE | FALSE
5944 | MRT-YD02-P3LB-122064 | 2018-10-24 | MRT-DS-REC-TT-180836 | FC | 1 | TRUE | TRUE | FALSE
5945 | MRT-CQ02-P2GM-128515 | 2018-10-24 | MRT-DS-REC-TT-180839 | FI | 1 | TRUE | TRUE | FALSE
5946 | MRT-CQ02-P3GM-128515 | 2018-10-24 | MRT-DS-REC-TT-180839 | FI | 1 | TRUE | TRUE | FALSE
5947 | MRT-YD00-P2SM-128020 | 2018-10-24 | MRT-DS-REC-TT-180838 | FC | 2 | TRUE | TRUE | FALSE
5948 | MRT-YD00-P3SM-128020 | 2018-10-24 | MRT-DS-REC-TT-180838 | FC | 2 | TRUE | TRUE | FALSE
5949 | MRT-YK09-P2SM-128040 | 2018-10-24 | MRT-DS-REC-TT-180841 | FI | 1 | TRUE | TRUE | FALSE
5950 | MRT-YK09-P3SM-128040 | 2018-10-24 | MRT-DS-REC-TT-180841 | FI | 1 | TRUE | TRUE | FALSE
5951 | MRT-YB03-P2LB-122113 | 2018-10-24 | MRT-DS-REC-TT-180840 | FI | 0 | TRUE | FALSE | FALSE
5952 | MRT-XA00-P2QU-130025 | 2018-10-24 | MRT-DS-REC-TT-180842 | FC | 5 | TRUE | TRUE | FALSE
5953 | MRT-XA00-P3QU-130025 | 2018-10-24 | MRT-DS-REC-TT-180842 | FC | 5 | TRUE | TRUE | FALSE
5954 | MRT-XR00-P2MAA-220040 | 2018-10-25 | MRT-DS-REC-TT-180843 | FI | 0 | TRUE | FALSE | FALSE
5955 | MRT-YK08-P2LBG-111300 | 2018-10-25 | MRT-DS-REC-TT-180844 | FC | 2 | TRUE | TRUE | FALSE
5956 | MRT-YK08-P3LBG-111300 | 2018-10-25 | MRT-DS-REC-TT-180844 | FC | 2 | TRUE | TRUE | FALSE
5957 | MRT-UE00-P2LB-122008 | 2018-10-25 | MRT-DS-REC-TT-180846 | FC | 5 | TRUE | TRUE | FALSE
5958 | MRT-UE00-P3LB-122008 | 2018-10-25 | MRT-DS-REC-TT-180846 | FC | 3 | TRUE | TRUE | FALSE
5959 | MRT-CC02-P0UMA-171003 | 2018-10-26 | MRT-DS-REC-TT-180809-FC | FC | 0 | TRUE | TRUE | FALSE
5960 | MRT-VK02-P0UMA-171006 | 2018-10-26 | MRT-DS-REC-TT-180809-FC | FC | 0 | TRUE | TRUE | FALSE
5961 | MRT-DD08-P0ZEN-075001 | 2018-10-26 | MRT-HK-REC-TT-180300 | FA | 1 | TRUE | TRUE | FALSE
5962 | MRT-QM03-P2PAC-130001 | 2018-10-26 | MRT-HK-REC-TT-180301 | FA | 0 | TRUE | FALSE | FALSE
5963 | MRT-CA01-P0UGA-186628 | 2018-10-26 | MRT-HK-REC-TT-180302 | FA | 1 | TRUE | TRUE | FALSE
5964 | MRT-CA02-P0UGA-186634 | 2018-10-26 | MRT-HK-REC-TT-180302 | FA | 1 | TRUE | TRUE | FALSE
5965 | MRT-CA03-P0UGA-186636 | 2018-10-26 | MRT-HK-REC-TT-180302 | FA | 1 | TRUE | TRUE | FALSE
5966 | MRT-CA03-P0UGA-186638 | 2018-10-26 | MRT-HK-REC-TT-180302 | FA | 1 | TRUE | TRUE | FALSE
5967 | MRT-CA03-P0UGA-186640 | 2018-10-26 | MRT-HK-REC-TT-180302 | FA | 1 | TRUE | TRUE | FALSE
5968 | MRT-CA01-P0UGA-186631 | 2018-10-26 | MRT-HK-REC-TT-180302 | FA | 1 | TRUE | TRUE | FALSE
5969 | MRT-CA02-P0UGA-186633 | 2018-10-26 | MRT-HK-REC-TT-180302 | FA | 1 | TRUE | TRUE | FALSE
5970 | MRT-CA03-P0UGA-186639 | 2018-10-26 | MRT-HK-REC-TT-180302 | FA | 1 | TRUE | TRUE | FALSE
5971 | MRT-XB02-P2LB-122018 | 2018-10-26 | MRT-DS-REC-TT-180847 | FC | 4 | TRUE | TRUE | FALSE
5972 | MRT-XB02-P3LB-122018 | 2018-10-26 | MRT-DS-REC-TT-180847 | FC | 3 | TRUE | TRUE | FALSE
5973 | MRT-CT00-P0SMM-128001 | 2018-10-29 | MRT-DS-REC-TT-180848 | FI | 0 | TRUE | FALSE | FALSE
5974 | MRT-DM02-P0SMM-128001 | 2018-10-29 | MRT-DS-REC-TT-180848 | FI | 0 | TRUE | FALSE | FALSE
5975 | MRT-YD00-P2LB-122114 | 2018-10-29 | MRT-DS-REC-TT-180849 | FA | 0 | TRUE | FALSE | FALSE
5976 | MRT-YD00-P3LB-122114 | 2018-10-29 | MRT-DS-REC-TT-180849 | FA | 0 | TRUE | FALSE | FALSE
5977 | MRT-YV02-P2SCA-127532 | 2018-10-29 | MRT-DS-REC-TT-180784-FC | FC | 0 | TRUE | TRUE | FALSE
5978 | MRT-YV02-P3SCA-127532 | 2018-10-29 | MRT-DS-REC-TT-180784-FC | FC | 0 | TRUE | TRUE | FALSE
5979 | MRT-CA01-P0UMA-180044 | 2018-10-29 | MRT-DS-REC-TT-180810-FC | FC | 2 | TRUE | TRUE | FALSE
5980 | MRT-CA02-P0UMA-180045 | 2018-10-29 | MRT-DS-REC-TT-180810-FC | FC | 2 | TRUE | TRUE | FALSE
5981 | MRT-CA00-P0UMA-180047 | 2018-10-29 | MRT-DS-REC-TT-180810-FC | FC | 3 | TRUE | TRUE | FALSE
5982 | MRT-YD02-P2LB-122065 | 2018-10-29 | MRT-DS-REC-TT-180850 | FC | 2 | TRUE | TRUE | FALSE
5983 | MRT-YD02-P3LB-122065 | 2018-10-29 | MRT-DS-REC-TT-180850 | FC | 1 | TRUE | TRUE | FALSE
5984 | MRT-DN02-P2MAJ-830014 | 2018-10-29 | MRT-DS-REC-TT-180812-FC | FC | 0 | TRUE | TRUE | FALSE
5985 | MRT-CA05-P0UCA-180163 | 2018-10-30 | MRT-DS-REC-TT-180845 | FC | 5 | TRUE | TRUE | FALSE
5986 | MRT-CA05-P0UCA-180164 | 2018-10-30 | MRT-DS-REC-TT-180845 | FC | 5 | TRUE | TRUE | FALSE
5987 | MRT-YT01-P0GEN-135338 | 2018-10-30 | MRT-HK-REC-TT-180303 | FA | 0 | TRUE | FALSE | FALSE
5988 | MRT-YT01-P0GEN-135358 | 2018-10-30 | MRT-HK-REC-TT-180303 | FA | 0 | TRUE | FALSE | FALSE
5989 | MRT-YD00-P2PGB-113107 | 2018-10-31 | MRT-DS-REC-TT-180851 | FI | 0 | TRUE | FALSE | FALSE
5990 | MRT-CQ02-P2PGB-113116 | 2018-10-31 | MRT-DS-REC-TT-180851 | FI | 0 | TRUE | FALSE | FALSE
5991 | MRT-CQ02-P2PGB-113117 | 2018-10-31 | MRT-DS-REC-TT-180851 | FI | 0 | TRUE | FALSE | FALSE
5992 | MRT-CQ02-P2PGB-113118 | 2018-10-31 | MRT-DS-REC-TT-180851 | FI | 0 | TRUE | FALSE | FALSE
5993 | MRT-YD00-P3PGB-113107 | 2018-10-31 | MRT-DS-REC-TT-180851 | FI | 0 | TRUE | FALSE | FALSE
5994 | MRT-CQ02-P3PGB-113116 | 2018-10-31 | MRT-DS-REC-TT-180851 | FI | 0 | TRUE | FALSE | FALSE
5995 | MRT-CQ02-P3PGB-113117 | 2018-10-31 | MRT-DS-REC-TT-180851 | FI | 0 | TRUE | FALSE | FALSE
5996 | MRT-CQ02-P3PGB-113118 | 2018-10-31 | MRT-DS-REC-TT-180851 | FI | 0 | TRUE | FALSE | FALSE
5997 | MRT-YB03-P2LB-122113 | 2018-10-31 | MRT-DS-REC-TT-180840-FC | FC | 0 | TRUE | TRUE | FALSE
5998 | MRT-CA00-P0UST-186907 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 0 | TRUE | TRUE | FALSE
5999 | MRT-CA00-P0UST-186913 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 0 | TRUE | TRUE | FALSE
6000 | MRT-CA02-P0UST-186941 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 0 | TRUE | TRUE | FALSE
6001 | MRT-CA03-P0UST-186943 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 0 | TRUE | TRUE | FALSE
6002 | MRT-CA01-P0UST-186902 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 4 | TRUE | TRUE | FALSE
6003 | MRT-CA06-P0UST-186904 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6004 | MRT-CA00-P0UST-186906 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 2 | TRUE | TRUE | FALSE
6005 | MRT-CA00-P0UST-186908 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 0 | TRUE | TRUE | FALSE
6006 | MRT-CA00-P0UST-186910 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 0 | TRUE | TRUE | FALSE
6007 | MRT-CA00-P0UST-186912 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 2 | FALSE | TRUE | FALSE
6008 | MRT-CA00-P0UST-186914 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 2 | TRUE | TRUE | FALSE
6009 | MRT-CA00-P0UST-186916 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 0 | TRUE | TRUE | FALSE
6010 | MRT-CA01-P0UST-186918 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 0 | TRUE | TRUE | FALSE
6011 | MRT-CA02-P0UST-186924 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6012 | MRT-CA03-P0UST-186928 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6013 | MRT-CA03-P0UST-186930 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6014 | MRT-CA03-P0UST-186932 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6015 | MRT-CA03-P0UST-186934 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6016 | MRT-CA03-P0UST-186936 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6017 | MRT-CA03-P0UST-186938 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6018 | MRT-CA03-P0UST-186940 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 0 | TRUE | TRUE | FALSE
6019 | MRT-CA01-P0UST-186944 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6021 | MRT-CA00-P0UST-186911 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 2 | TRUE | TRUE | FALSE
6022 | MRT-CA00-P0UST-186917 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 2 | TRUE | TRUE | FALSE
6023 | MRT-CA02-P0UST-186922 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6024 | MRT-CA03-P0UST-186937 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6025 | MRT-CA03-P0UST-186947 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6026 | MRT-CA03-P0UST-186948 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6027 | MRT-CA03-P0UST-186949 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6028 | MRT-CA03-P0UST-186927 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6029 | MRT-CA03-P0UST-186933 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6030 | MRT-CA03-P0UST-186950 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6031 | MRT-CA03-P0UST-186951 | 2018-10-31 | MRT-HK-REC-TT-180275 | FA | 1 | TRUE | TRUE | FALSE
6032 | MRT-YF02-P2QC-130006 | 2018-10-31 | MRT-DS-REC-TT-180831-FC | FC | 4 | TRUE | TRUE | FALSE
6033 | MRT-YF02-P3QC-130006 | 2018-10-31 | MRT-DS-REC-TT-180831-FC | FC | 4 | TRUE | TRUE | FALSE
6034 | MRT-CC07-P0UBX-176001 | 2018-10-31 | MRT-HK-REC-TT-180306 | FA | 4 | TRUE | TRUE | FALSE
6035 | MRT-CC02-P0UBX-176005 | 2018-10-31 | MRT-HK-REC-TT-180306 | FA | 5 | TRUE | TRUE | FALSE
6036 | MRT-CC07-P0UBX-176015 | 2018-10-31 | MRT-HK-REC-TT-180306 | FA | 3 | TRUE | TRUE | FALSE
6037 | MRT-CC02-P0UBX-176020 | 2018-10-31 | MRT-HK-REC-TT-180306 | FA | 3 | TRUE | TRUE | FALSE
6038 | MRT-CC02-P0UBX-176030 | 2018-10-31 | MRT-HK-REC-TT-180306 | FA | 2 | TRUE | TRUE | FALSE
6039 | MRT-CC02-P0UBX-176007 | 2018-10-31 | MRT-HK-REC-TT-180306 | FA | 5 | TRUE | TRUE | FALSE
6040 | MRT-CC02-P0UBX-176035 | 2018-10-31 | MRT-HK-REC-TT-180306 | FA | 3 | TRUE | TRUE | FALSE
6041 | MRT-CC02-P0UBX-176036 | 2018-10-31 | MRT-HK-REC-TT-180306 | FA | 2 | TRUE | TRUE | FALSE
6042 | MRT-BT00-P0GEN-135702 | 2018-10-31 | MRT-HK-REC-TT-180304 | FA | 0 | TRUE | FALSE | FALSE
6374 | MRT-CA00-P0UGA-186627 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 0 | TRUE | TRUE | FALSE
6375 | MRT-CA00-P0UGA-186623 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 0 | TRUE | TRUE | FALSE
6376 | MRT-CA01-P0UGA-186658 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 0 | TRUE | TRUE | FALSE
6377 | MRT-CA01-P0UGA-186659 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 0 | TRUE | TRUE | FALSE
6378 | MRT-CA03-P0UGA-186630 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 0 | TRUE | TRUE | FALSE
6379 | MRT-CA03-P0UGA-186632 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 0 | TRUE | TRUE | FALSE
6380 | MRT-CA03-P0UGA-186657 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 0 | TRUE | TRUE | FALSE
6381 | MRT-CA06-P0UGA-186605 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 1 | TRUE | TRUE | FALSE
6382 | MRT-CA00-P0UGA-186622 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 0 | TRUE | TRUE | FALSE
6383 | MRT-CA00-P0UGA-186626 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 0 | TRUE | TRUE | FALSE
6384 | MRT-CA01-P0UGA-186628 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 2 | TRUE | TRUE | FALSE
6385 | MRT-CA03-P0UGA-186644 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 1 | TRUE | TRUE | FALSE
6386 | MRT-CA03-P0UGA-186646 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 1 | TRUE | TRUE | FALSE
6387 | MRT-CA03-P0UGA-186648 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 0 | TRUE | TRUE | FALSE
6388 | MRT-CA03-P0UGA-186650 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 0 | TRUE | TRUE | FALSE
6389 | MRT-CA03-P0UGA-186643 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 1 | TRUE | TRUE | FALSE
6390 | MRT-CA03-P0UGA-186645 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 1 | TRUE | TRUE | FALSE
6391 | MRT-CA06-P0UGA-186604 | 2018-10-31 | MRT-HK-REC-TT-180305 | FA | 1 | TRUE | TRUE | FALSE
6043 | MRT-CC07-P2UHA-170101 | 2018-11-01 | MRT-DS-REC-TT-180815-FC | FC | 3 | TRUE | TRUE | FALSE
6044 | MRT-CC02-P2UHA-170103 | 2018-11-01 | MRT-DS-REC-TT-180815-FC | FC | 7 | TRUE | TRUE | FALSE
6045 | MRT-CC07-P3UHA-170101 | 2018-11-01 | MRT-DS-REC-TT-180815-FC | FC | 3 | TRUE | TRUE | FALSE
6046 | MRT-CC02-P3UHA-170103 | 2018-11-01 | MRT-DS-REC-TT-180815-FC | FC | 7 | TRUE | TRUE | FALSE
6047 | MRT-YV02-P3PAH-604522 | 2018-11-01 | MRT-DS-REC-TT-180852 | FC | 3 | TRUE | TRUE | FALSE
6048 | MRT-YK08-P3PAH-604524 | 2018-11-01 | MRT-DS-REC-TT-180852 | FC | 4 | TRUE | TRUE | FALSE
6049 | MRT-DP00-P2LB-122106 | 2018-11-01 | MRT-DS-REC-TT-180853 | FC | 4 | TRUE | TRUE | FALSE
6050 | MRT-DP00-P3LB-122106 | 2018-11-01 | MRT-DS-REC-TT-180853 | FC | 4 | TRUE | TRUE | FALSE
6051 | MRT-UE00-P2LB-122007 | 2018-11-01 | MRT-DS-REC-TT-180854 | FC | 3 | TRUE | TRUE | FALSE
6052 | MRT-UE00-P3LB-122007 | 2018-11-01 | MRT-DS-REC-TT-180854 | FC | 2 | TRUE | TRUE | FALSE
6053 | MRT-XB02-P2LB-122016 | 2018-11-01 | MRT-DS-REC-TT-180855 | FC | 3 | TRUE | TRUE | FALSE
6054 | MRT-XB02-P3LB-122016 | 2018-11-01 | MRT-DS-REC-TT-180855 | FC | 2 | TRUE | TRUE | FALSE
6055 | MRT-YD00-P2LB-122052 | 2018-11-01 | MRT-DS-REC-TT-180856 | FC | 2 | TRUE | TRUE | FALSE
6056 | MRT-YD00-P3LB-122052 | 2018-11-01 | MRT-DS-REC-TT-180856 | FC | 2 | TRUE | TRUE | FALSE
6058 | MRT-YE07-P2UGD-150151 | 2018-11-05 | MRT-HK-REC-TT-180307 | FA | 0 | TRUE | FALSE | FALSE
6059 | MRT-YE07-P0USG-150152 | 2018-11-05 | MRT-HK-REC-TT-180307 | FA | 0 | TRUE | FALSE | FALSE
6060 | MRT-YE07-P3UBN-150158 | 2018-11-05 | MRT-HK-REC-TT-180307 | FA | 0 | TRUE | FALSE | FALSE
6061 | MRT-CT00-P2ZEN-113300 | 2018-11-05 | MRT-DS-REC-TT-180859 | FI | 0 | TRUE | FALSE | FALSE
6062 | MRT-CT00-P3ZEN-113300 | 2018-11-05 | MRT-DS-REC-TT-180859 | FI | 0 | TRUE | FALSE | FALSE
6063 | MRT-CT00-P2ZEN-113400 | 2018-11-05 | MRT-DS-REC-TT-180860 | FI | 0 | TRUE | FALSE | FALSE
6064 | MRT-CT00-P3ZEN-113400 | 2018-11-05 | MRT-DS-REC-TT-180860 | FI | 0 | TRUE | FALSE | FALSE
6065 | MRT-CT00-P2ZEN-113500 | 2018-11-05 | MRT-DS-REC-TT-180861 | FI | 0 | TRUE | FALSE | FALSE
6066 | MRT-CT00-P3ZEN-113500 | 2018-11-05 | MRT-DS-REC-TT-180861 | FI | 0 | TRUE | FALSE | FALSE
6067 | MRT-YK08-P2LB-122115 | 2018-11-05 | MRT-DS-REC-TT-180857 | FI | 0 | TRUE | FALSE | FALSE
6068 | MRT-YK08-P3LB-122115 | 2018-11-05 | MRT-DS-REC-TT-180857 | FI | 0 | TRUE | FALSE | FALSE
6069 | MRT-YE00-P2LB-122116 | 2018-11-05 | MRT-DS-REC-TT-180858 | FA | 0 | TRUE | FALSE | FALSE
6070 | MRT-YE00-P3LB-122116 | 2018-11-05 | MRT-DS-REC-TT-180858 | FA | 0 | TRUE | FALSE | FALSE
6071 | MRT-YD00-P0QJA-111601 | 2018-11-06 | MRT-DS-REC-TT-180862 | FI | 0 | TRUE | FALSE | FALSE
6072 | MRT-YM02-P2BBA-150459 | 2018-11-06 | MRT-HK-REC-TT-180308 | FA | 1 | TRUE | TRUE | FALSE
6073 | MRT-YM02-P0BBA-150463 | 2018-11-06 | MRT-HK-REC-TT-180308 | FA | 1 | TRUE | TRUE | FALSE
6074 | MRT-YM02-P3BBA-150461 | 2018-11-06 | MRT-HK-REC-TT-180308 | FA | 1 | TRUE | TRUE | FALSE
6075 | MRT-YD00-P0BBB-150530 | 2018-11-06 | MRT-HK-REC-TT-180309 | FA | 1 | TRUE | TRUE | FALSE
6076 | MRT-XG02-P2PA-110002 | 2018-11-06 | MRT-DS-REC-TT-180864 | FC | 6 | TRUE | TRUE | FALSE
6077 | MRT-XG02-P3PA-110002 | 2018-11-06 | MRT-DS-REC-TT-180864 | FC | 6 | TRUE | TRUE | FALSE
6078 | MRT-XR00-P3MAA-220040 | 2018-11-07 | MRT-DS-REC-TT-180865 | FI | 0 | TRUE | FALSE | FALSE
6079 | MRT-XB02-P2LB-122022 | 2018-11-07 | MRT-DS-REC-TT-180863 | FI | 1 | TRUE | TRUE | FALSE
6080 | MRT-YK00-P2LB-122076 | 2018-11-07 | MRT-DS-REC-TT-180837-FC | FC | 1 | TRUE | TRUE | FALSE
6081 | MRT-YK00-P3LB-122076 | 2018-11-07 | MRT-DS-REC-TT-180837-FC | FC | 1 | TRUE | TRUE | FALSE
6082 | MRT-YK09-P2MKC-230002 | 2018-11-07 | MRT-DS-REC-TT-180828-FC | FC | 3 | TRUE | TRUE | FALSE
6083 | MRT-YK09-P3MKC-230002 | 2018-11-07 | MRT-DS-REC-TT-180828-FC | FC | 3 | TRUE | TRUE | FALSE
6084 | MRT-CA01-P0UCA-180122 | 2018-11-07 | MRT-DS-REC-TT-180826-FC | FC | 5 | TRUE | TRUE | FALSE
6085 | MRT-CA01-P0UCA-180123 | 2018-11-07 | MRT-DS-REC-TT-180826-FC | FC | 5 | TRUE | TRUE | FALSE
6086 | MRT-CA01-P0UCA-180128 | 2018-11-07 | MRT-DS-REC-TT-180826-FC | FC | 4 | TRUE | TRUE | FALSE
6087 | MRT-CA05-P0UCA-180163 | 2018-11-07 | MRT-DS-REC-TT-180845-FC | FC | 5 | TRUE | TRUE | FALSE
6088 | MRT-CA05-P0UCA-180164 | 2018-11-07 | MRT-DS-REC-TT-180845-FC | FC | 5 | TRUE | TRUE | FALSE
6089 | MRT-XB02-P2LB-122018 | 2018-11-07 | MRT-DS-REC-TT-180847-FC | FC | 4 | TRUE | TRUE | FALSE
6090 | MRT-XB02-P3LB-122018 | 2018-11-07 | MRT-DS-REC-TT-180847-FC | FC | 3 | TRUE | TRUE | FALSE
6091 | MRT-YD00-P2LAC-126049 | 2018-11-07 | MRT-DS-REC-TT-180867 | FC | 2 | TRUE | TRUE | FALSE
6092 | MRT-YD00-P3LAC-126049 | 2018-11-07 | MRT-DS-REC-TT-180867 | FC | 2 | TRUE | TRUE | FALSE
6093 | MRT-YD00-P2LAC-126096 | 2018-11-07 | MRT-DS-REC-TT-180867 | FC | 2 | TRUE | TRUE | FALSE
6094 | MRT-YD00-P3LAC-126096 | 2018-11-07 | MRT-DS-REC-TT-180867 | FC | 2 | TRUE | TRUE | FALSE
6095 | MRT-YD00-P2LAC-126050 | 2018-11-07 | MRT-DS-REC-TT-180867 | FC | 2 | TRUE | TRUE | FALSE
6096 | MRT-YD00-P3LAC-126050 | 2018-11-07 | MRT-DS-REC-TT-180867 | FC | 2 | TRUE | TRUE | FALSE
6097 | MRT-YD00-P2LAC-126097 | 2018-11-07 | MRT-DS-REC-TT-180867 | FC | 2 | TRUE | TRUE | FALSE
6098 | MRT-YD00-P3LAC-126097 | 2018-11-07 | MRT-DS-REC-TT-180867 | FC | 2 | TRUE | TRUE | FALSE
6099 | MRT-XS00-P2QU-130026 | 2018-11-07 | MRT-DS-REC-TT-180832-FC | FC | 3 | TRUE | TRUE | FALSE
6100 | MRT-XS00-P3QU-130026 | 2018-11-07 | MRT-DS-REC-TT-180832-FC | FC | 3 | TRUE | TRUE | FALSE
6101 | MRT-YK08-P2LBG-111300 | 2018-11-07 | MRT-DS-REC-TT-180844-FC | FC | 2 | TRUE | TRUE | FALSE
6102 | MRT-YK08-P3LBG-111300 | 2018-11-07 | MRT-DS-REC-TT-180844-FC | FC | 2 | TRUE | TRUE | FALSE
6103 | MRT-UE00-P2LB-122008 | 2018-11-07 | MRT-DS-REC-TT-180846-FC | FC | 5 | TRUE | TRUE | FALSE
6104 | MRT-UE00-P3LB-122008 | 2018-11-07 | MRT-DS-REC-TT-180846-FC | FC | 3 | TRUE | TRUE | FALSE
6105 | MRT-DP00-P2LB-122106 | 2018-11-07 | MRT-DS-REC-TT-180853-FC | FC | 4 | TRUE | TRUE | FALSE
6106 | MRT-DP00-P3LB-122106 | 2018-11-07 | MRT-DS-REC-TT-180853-FC | FC | 4 | TRUE | TRUE | FALSE
6107 | MRT-UE00-P2LB-122007 | 2018-11-07 | MRT-DS-REC-TT-180854-FC | FC | 3 | TRUE | TRUE | FALSE
6108 | MRT-UE00-P3LB-122007 | 2018-11-07 | MRT-DS-REC-TT-180854-FC | FC | 2 | TRUE | TRUE | FALSE
6109 | MRT-YD00-P2LB-122052 | 2018-11-07 | MRT-DS-REC-TT-180856-FC | FC | 2 | TRUE | TRUE | FALSE
6110 | MRT-YD00-P3LB-122052 | 2018-11-07 | MRT-DS-REC-TT-180856-FC | FC | 2 | TRUE | TRUE | FALSE
6116 | MRT-XP00-P0BBB-150557 | 2018-11-08 | MRT-HK-REC-TT-180313 | FA | 0 | TRUE | TRUE | FALSE
6117 | MRT-XP00-P3BAA-150518 | 2018-11-08 | MRT-HK-REC-TT-180313 | FA | 0 | TRUE | TRUE | FALSE
6118 | MRT-XW03-P0BBB-150532 | 2018-11-08 | MRT-HK-REC-TT-180313 | FA | 0 | TRUE | TRUE | FALSE
6119 | MRT-XW03-P2BAA-150480 | 2018-11-08 | MRT-HK-REC-TT-180313 | FA | 0 | TRUE | TRUE | FALSE
6120 | MRT-YM02-P0BBA-150464 | 2018-11-08 | MRT-HK-REC-TT-180313 | FA | 0 | TRUE | TRUE | FALSE
6111 | MRT-YF00-P2SCA-127518 | 2018-11-09 | MRT-DS-REC-TT-180866 | FC | 2 | TRUE | TRUE | FALSE
6112 | MRT-YF00-P3SCA-127518 | 2018-11-09 | MRT-DS-REC-TT-180866 | FC | 2 | TRUE | TRUE | FALSE
6113 | MRT-XH01-P3UMA-144000 | 2018-11-09 | MRT-DS-REC-TT-180739-FC | FC | 0 | TRUE | TRUE | FALSE
6114 | MRT-XG02-P2PBB-604112 | 2018-11-09 | MRT-DS-REC-TT-180794-FC | FC | 3 | TRUE | TRUE | FALSE
6115 | MRT-XG02-P3PBB-604512 | 2018-11-09 | MRT-DS-REC-TT-180794-FC | FC | 3 | TRUE | TRUE | FALSE
6121 | MRT-UBE-P2BBT-150418 | 2018-11-09 | MRT-HK-REC-TT-180311 | FA | 2 | TRUE | TRUE | FALSE
6122 | MRT-UBE-P3BBT-150435 | 2018-11-09 | MRT-HK-REC-TT-180311 | FA | 2 | TRUE | TRUE | FALSE
6123 | MRT-YT01-P2BBT-150421 | 2018-11-09 | MRT-HK-REC-TT-180311 | FA | 2 | TRUE | TRUE | FALSE
6124 | MRT-YT01-P3BBT-150438 | 2018-11-09 | MRT-HK-REC-TT-180311 | FA | 2 | TRUE | TRUE | FALSE
6125 | MRT-YD00-P3BAT-150401 | 2018-11-09 | MRT-HK-REC-TT-180311 | FA | 2 | TRUE | TRUE | FALSE
6126 | MRT-YU02-P3BMG-150685 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6127 | MRT-US02-P3BMG-150686 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6128 | MRT-YU02-P3BMH-150687 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6129 | MRT-US02-P3BMH-150688 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6130 | MRT-YU02-P3BJA-150679 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6131 | MRT-US02-P3BJA-150680 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6132 | MRT-YU02-P3BJC-150681 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6133 | MRT-US02-P3BJC-150682 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6134 | MRT-YU02-P3BFC-150671 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6135 | MRT-US02-P3BFC-150672 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6136 | MRT-YU02-P4BFE-150673 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6137 | MRT-US02-P4BFE-150674 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6138 | MRT-YU02-P3BLF-150741 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6139 | MRT-US02-P3BLF-150742 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6140 | MRT-YU02-P3BLF-150743 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6141 | MRT-US02-P3BLF-150744 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6142 | MRT-YU02-P3BRB-150747 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6143 | MRT-US02-P3BRB-150748 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6144 | MRT-YU02-P3BRC-150749 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6145 | MRT-US02-P3BRC-150750 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6146 | MRT-YU02-P3BUB-150755 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6147 | MRT-US02-P3BUB-150756 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6148 | MRT-YU02-P3BUB-150757 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6149 | MRT-US02-P3BUB-150758 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6150 | MRT-YU02-P3BUC-150759 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6151 | MRT-US02-P3BUC-150760 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6152 | MRT-YU02-P3BUC-150761 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6153 | MRT-US02-P3BUC-150762 | 2018-11-09 | MRT-HK-REC-TT-180312 | FA | 0 | TRUE | TRUE | FALSE
6154 | MRT-BT00-P3CYP-160009 | 2018-11-09 | MRT-HK-REC-TT-180310 | FA | 0 | TRUE | FALSE | FALSE
6155 | MRT-YK08-P3CYP-160005 | 2018-11-09 | MRT-HK-REC-TT-180310 | FA | 0 | TRUE | FALSE | FALSE
6156 | MRT-DP00-P2LB-122117 | 2018-11-09 | MRT-DS-REC-TT-180869 | FI | 0 | TRUE | FALSE | FALSE
6157 | MRT-XA00-P2QU-130025 | 2018-11-09 | MRT-DS-REC-TT-180870 | FC | 6 | TRUE | TRUE | FALSE
6158 | MRT-YT02-P2CJJ-240120 | 2018-11-09 | MRT-DS-REC-TT-180759 | FI | 0 | TRUE | FALSE | FALSE
6159 | MRT-YT02-P3CJJ-240112 | 2018-11-09 | MRT-DS-REC-TT-180759 | FI | 0 | TRUE | FALSE | FALSE
6160 | MRT-DP00-P2LB-122117 | 2018-11-09 | MRT-DS-REC-TT-180869-FC | FC | 0 | TRUE | TRUE | FALSE
6161 | MRT-CQ02-P2PGB-113203 | 2018-11-12 | MRT-DS-REC-TT-180868 | FI | 0 | TRUE | FALSE | FALSE
6162 | MRT-YD00-P2PAB-113263 | 2018-11-12 | MRT-DS-REC-TT-180868 | FI | 0 | TRUE | FALSE | FALSE
6163 | MRT-CQ02-P2PAB-113267 | 2018-11-12 | MRT-DS-REC-TT-180868 | FI | 0 | TRUE | FALSE | FALSE
6164 | MRT-CQ02-P3PGB-113203 | 2018-11-12 | MRT-DS-REC-TT-180868 | FI | 0 | TRUE | FALSE | FALSE
6165 | MRT-YD00-P3PAB-113263 | 2018-11-12 | MRT-DS-REC-TT-180868 | FI | 0 | TRUE | FALSE | FALSE
6166 | MRT-CQ02-P3PAB-113267 | 2018-11-12 | MRT-DS-REC-TT-180868 | FI | 0 | TRUE | FALSE | FALSE
6167 | MRT-XG02-P2LB-122022 | 2018-11-12 | MRT-DS-REC-TT-180872 | FC | 6 | TRUE | TRUE | FALSE
6168 | MRT-XG02-P3LB-122022 | 2018-11-12 | MRT-DS-REC-TT-180872 | FC | 3 | TRUE | TRUE | FALSE
6169 | MRT-YK00-P2LB-122076 | 2018-11-12 | MRT-DS-REC-TT-180873 | FC | 2 | TRUE | TRUE | FALSE
6170 | MRT-YK00-P3LB-122076 | 2018-11-12 | MRT-DS-REC-TT-180873 | FC | 2 | TRUE | TRUE | FALSE
6171 | MRT-DD00-P0ABA-155102 | 2018-11-12 | MRT-HK-REC-TT-180314 | FI | 0 | TRUE | FALSE | FALSE
6172 | MRT-DD00-P0BAC-155101 | 2018-11-12 | MRT-HK-REC-TT-180315 | FI | 0 | TRUE | FALSE | FALSE
6173 | MRT-CC04-P0ABA-150926 | 2018-11-12 | MRT-HK-REC-TT-180316 | FA | 0 | TRUE | TRUE | FALSE
6174 | MRT-CC08-P0ABA-150927 | 2018-11-12 | MRT-HK-REC-TT-180316 | FA | 0 | TRUE | TRUE | FALSE
6175 | MRT-CH04-P0ABA-150930 | 2018-11-12 | MRT-HK-REC-TT-180316 | FA | 0 | TRUE | TRUE | FALSE
6176 | MRT-CH04-P0ABA-150931 | 2018-11-12 | MRT-HK-REC-TT-180316 | FA | 0 | TRUE | TRUE | FALSE
6177 | MRT-XA10-P0ABA-150928 | 2018-11-12 | MRT-HK-REC-TT-180316 | FA | 0 | TRUE | TRUE | FALSE
6178 | MRT-YB11-P0ABA-150921 | 2018-11-12 | MRT-HK-REC-TT-180316 | FA | 0 | TRUE | TRUE | FALSE
6179 | MRT-YD00-P0ABA-150923 | 2018-11-12 | MRT-HK-REC-TT-180316 | FA | 1 | TRUE | TRUE | FALSE
6180 | MRT-YD00-P0ABA-150924 | 2018-11-12 | MRT-HK-REC-TT-180316 | FA | 0 | TRUE | TRUE | FALSE
6181 | MRT-YD00-P0ABA-150933 | 2018-11-12 | MRT-HK-REC-TT-180316 | FA | 0 | TRUE | TRUE | FALSE
6182 | MRT-YS01-P0ABA-150922 | 2018-11-12 | MRT-HK-REC-TT-180316 | FA | 0 | TRUE | TRUE | FALSE
6183 | MRT-YT01-P0ABA-150925 | 2018-11-12 | MRT-HK-REC-TT-180316 | FA | 0 | TRUE | TRUE | FALSE
6184 | MRT-QM03-P0MKG-125386 | 2018-11-12 | MRT-HK-REC-TT-180317 | FI | 0 | TRUE | FALSE | FALSE
6185 | MRT-YD00-P2SM-128020 | 2018-11-12 | MRT-DS-REC-TT-180838-FC | FC | 2 | TRUE | TRUE | FALSE
6186 | MRT-YD00-P3SM-128020 | 2018-11-12 | MRT-DS-REC-TT-180838-FC | FC | 2 | TRUE | TRUE | FALSE
6187 | MRT-DN02-P2LBF-830013 | 2018-11-12 | MRT-DS-REC-TT-180800-FC | FC | 0 | TRUE | TRUE | FALSE
6188 | MRT-CQ02-P3MAG-602011 | 2018-11-12 | MRT-DS-REC-TT-180807-FC | FC | 0 | TRUE | TRUE | FALSE
6189 | MRT-XA00-P2QU-130025 | 2018-11-12 | MRT-DS-REC-TT-180842-FC | FC | 5 | TRUE | TRUE | FALSE
6190 | MRT-XA00-P3QU-130025 | 2018-11-12 | MRT-DS-REC-TT-180842-FC | FC | 5 | TRUE | TRUE | FALSE
6191 | MRT-YD00-P2PGB-113107 | 2018-11-12 | MRT-DS-REC-TT-180851-FC | FC | 0 | TRUE | TRUE | FALSE
6192 | MRT-CQ02-P2PGB-113116 | 2018-11-12 | MRT-DS-REC-TT-180851-FC | FC | 0 | TRUE | TRUE | FALSE
6193 | MRT-CQ02-P2PGB-113117 | 2018-11-12 | MRT-DS-REC-TT-180851-FC | FC | 0 | TRUE | TRUE | FALSE
6194 | MRT-CQ02-P2PGB-113118 | 2018-11-12 | MRT-DS-REC-TT-180851-FC | FC | 0 | TRUE | TRUE | FALSE
6195 | MRT-YD00-P3PGB-113107 | 2018-11-12 | MRT-DS-REC-TT-180851-FC | FC | 0 | TRUE | TRUE | FALSE
6196 | MRT-CQ02-P3PGB-113116 | 2018-11-12 | MRT-DS-REC-TT-180851-FC | FC | 0 | TRUE | TRUE | FALSE
6197 | MRT-CQ02-P3PGB-113117 | 2018-11-12 | MRT-DS-REC-TT-180851-FC | FC | 0 | TRUE | TRUE | FALSE
6198 | MRT-CQ02-P3PGB-113118 | 2018-11-12 | MRT-DS-REC-TT-180851-FC | FC | 0 | TRUE | TRUE | FALSE
6902 | MRT-CA00-P3AY-160012 | 2018-11-12 | MRT-HK-REC-TT-180318 | FA | 0 | TRUE | FALSE | FALSE
6903 | MRT-CA00-P3AYA-160014 | 2018-11-12 | MRT-HK-REC-TT-180318 | FA | 0 | TRUE | FALSE | FALSE
6904 | MRT-CC07-P3AY-160001 | 2018-11-12 | MRT-HK-REC-TT-180318 | FA | 0 | TRUE | FALSE | FALSE
6905 | MRT-CT00-P3AYA-160047 | 2018-11-12 | MRT-HK-REC-TT-180318 | FA | 0 | TRUE | FALSE | FALSE
6906 | MRT-US02-P3AY-160046 | 2018-11-12 | MRT-HK-REC-TT-180318 | FA | 0 | TRUE | FALSE | FALSE
6907 | MRT-YQ07-P3AY-160002 | 2018-11-12 | MRT-HK-REC-TT-180318 | FA | 0 | TRUE | FALSE | FALSE
6908 | MRT-YQ07-P3AYA-160052 | 2018-11-12 | MRT-HK-REC-TT-180318 | FA | 0 | TRUE | FALSE | FALSE
6909 | MRT-YQ07-P3AYA-160038 | 2018-11-12 | MRT-HK-REC-TT-180318 | FA | 0 | TRUE | FALSE | FALSE
6910 | MRT-YT01-P3AY-160008 | 2018-11-12 | MRT-HK-REC-TT-180318 | FA | 0 | TRUE | FALSE | FALSE
6199 | MRT-YS01-P2MKC-230014 | 2018-11-13 | MRT-DS-REC-TT-180834-FC | FC | 2 | TRUE | TRUE | FALSE
6200 | MRT-YS01-P3MKC-230014 | 2018-11-13 | MRT-DS-REC-TT-180834-FC | FC | 2 | TRUE | TRUE | FALSE
6201 | MRT-YK09-P3MKC-230003 | 2018-11-13 | MRT-DS-REC-TT-180835-FC | FC | 1 | TRUE | TRUE | FALSE
6202 | MRT-BU09-P3AY-040001 | 2018-11-13 | MRT-HK-REC-TT-180319 | FA | 0 | TRUE | FALSE | FALSE
6203 | MRT-DD04-P3AY-020001 | 2018-11-13 | MRT-HK-REC-TT-180319 | FA | 0 | TRUE | FALSE | FALSE
6204 | MRT-GA04-P3AY-010001 | 2018-11-13 | MRT-HK-REC-TT-180319 | FA | 0 | TRUE | FALSE | FALSE
6205 | MRT-YU02-P2BFA-150669 | 2018-11-13 | MRT-HK-REC-TT-180320 | FA | 1 | TRUE | TRUE | FALSE
6206 | MRT-YU02-P2BLF-150739 | 2018-11-13 | MRT-HK-REC-TT-180320 | FA | 1 | TRUE | TRUE | FALSE
6207 | MRT-YU02-P2BJA-150675 | 2018-11-13 | MRT-HK-REC-TT-180320 | FA | 1 | TRUE | TRUE | FALSE
6208 | MRT-YU02-P2BJB-150677 | 2018-11-13 | MRT-HK-REC-TT-180320 | FA | 1 | TRUE | TRUE | FALSE
6209 | MRT-YD02-P2LB-122064 | 2018-11-13 | MRT-DS-REC-TT-180836-FC | FC | 2 | TRUE | TRUE | FALSE
6210 | MRT-YD02-P3LB-122064 | 2018-11-13 | MRT-DS-REC-TT-180836-FC | FC | 1 | TRUE | TRUE | FALSE
6211 | MRT-DD00-P0ABA-155106 | 2018-11-13 | MRT-HK-REC-TT-180321 | FI | 0 | TRUE | FALSE | FALSE
6212 | MRT-DD00-P0ABA-155105 | 2018-11-13 | MRT-HK-REC-TT-180321 | FI | 0 | TRUE | FALSE | FALSE
6213 | MRT-DD00-P3BAT-155104 | 2018-11-13 | MRT-HK-REC-TT-180321 | FI | 0 | TRUE | FALSE | FALSE
6214 | MRT-DD00-P2BAT-155103 | 2018-11-13 | MRT-HK-REC-TT-180321 | FI | 0 | TRUE | FALSE | FALSE
6215 | MRT-YS01-P2MKC-230012 | 2018-11-13 | MRT-DS-REC-TT-180871 | FC | 2 | TRUE | TRUE | FALSE
6216 | MRT-YS01-P2MKC-230013 | 2018-11-13 | MRT-DS-REC-TT-180871 | FC | 1 | TRUE | TRUE | FALSE
6217 | MRT-YS01-P3MKC-230012 | 2018-11-13 | MRT-DS-REC-TT-180871 | FC | 2 | TRUE | TRUE | FALSE
6218 | MRT-YS01-P3MKC-230013 | 2018-11-13 | MRT-DS-REC-TT-180871 | FC | 1 | TRUE | TRUE | FALSE
6219 | MRT-YD16-P0UAA-150208 | 2018-11-13 | MRT-HK-REC-TT-180322 | FA | 0 | TRUE | FALSE | FALSE
6220 | MRT-YE06-P0BAU-150209 | 2018-11-13 | MRT-HK-REC-TT-180322 | FA | 0 | TRUE | FALSE | FALSE
6221 | MRT-YS01-P0ABA-150564 | 2018-11-13 | MRT-HK-REC-TT-180323 | FA | 0 | TRUE | FALSE | FALSE
6222 | MRT-YD00-P0UAB-150210 | 2018-11-13 | MRT-HK-REC-TT-180323 | FA | 0 | TRUE | FALSE | FALSE
6223 | MRT-YT01-P3MKA-240003 | 2018-11-14 | MRT-DS-REC-TT-180875 | FI | 2 | TRUE | TRUE | FALSE
6224 | MRT-YV02-P3MKW-230001 | 2018-11-14 | MRT-DS-REC-TT-180878 | FC | 1 | TRUE | TRUE | FALSE
6225 | MRT-YV02-P3MKW-230002 | 2018-11-14 | MRT-DS-REC-TT-180878 | FC | 1 | TRUE | TRUE | FALSE
6226 | MRT-UE00-P2LB-122010 | 2018-11-14 | MRT-DS-REC-TT-180876 | FC | 3 | TRUE | TRUE | FALSE
6227 | MRT-UE00-P3LB-122010 | 2018-11-14 | MRT-DS-REC-TT-180876 | FC | 3 | TRUE | TRUE | FALSE
6228 | MRT-XJ00-P2LB-122028 | 2018-11-14 | MRT-DS-REC-TT-180877 | FC | 2 | TRUE | TRUE | FALSE
6229 | MRT-XJ00-P3LB-122028 | 2018-11-14 | MRT-DS-REC-TT-180877 | FC | 2 | TRUE | TRUE | FALSE
6230 | MRT-CC02-P2UAG-170307 | 2018-11-14 | MRT-DS-REC-TT-180879 | FC | 2 | TRUE | TRUE | FALSE
6231 | MRT-CC02-P2UAG-170308 | 2018-11-14 | MRT-DS-REC-TT-180879 | FC | 3 | TRUE | TRUE | FALSE
6232 | MRT-VK02-P2UAG-170310 | 2018-11-14 | MRT-DS-REC-TT-180879 | FC | 1 | TRUE | TRUE | FALSE
6233 | MRT-CQ02-P2GM-128515 | 2018-11-14 | MRT-DS-REC-TT-180839-FC | FC | 1 | TRUE | TRUE | FALSE
6234 | MRT-CQ02-P3GM-128515 | 2018-11-14 | MRT-DS-REC-TT-180839-FC | FC | 1 | TRUE | TRUE | FALSE
6235 | MRT-YD00-P3MKW-220001 | 2018-11-14 | MRT-DS-REC-TT-180796-FC | FC | 2 | TRUE | TRUE | FALSE
6236 | MRT-YD00-P3MKW-220005 | 2018-11-14 | MRT-DS-REC-TT-180796-FC | FC | 2 | TRUE | TRUE | FALSE
6237 | MRT-QM03-P0MKG-125386 | 2018-11-14 | MRT-HK-REC-TT-180324 | FA | 0 | TRUE | FALSE | FALSE
6238 | MRT-CA01-P0UGX-186968 | 2018-11-15 | MRT-HK-REC-TT-180325 | FA | 1 | TRUE | TRUE | FALSE
6239 | MRT-CA01-P0UGX-186972 | 2018-11-15 | MRT-HK-REC-TT-180325 | FA | 1 | TRUE | TRUE | FALSE
6240 | MRT-QM00-P0H-040003 | 2018-11-15 | MRT-DS-REC-TT-180624-FC | FC | 1 | TRUE | TRUE | FALSE
6241 | MRT-QM00-P0H-040004 | 2018-11-15 | MRT-DS-REC-TT-180624-FC | FC | 1 | TRUE | TRUE | FALSE
6242 | MRT-QM00-P0H-040005 | 2018-11-15 | MRT-DS-REC-TT-180624-FC | FC | 1 | TRUE | TRUE | FALSE
6243 | MRT-CA01-P0UST-186945 | 2018-11-15 | MRT-HK-REC-TT-180326 | FA | 0 | TRUE | TRUE | FALSE
6244 | MRT-CC05-P0ZEN-175049 | 2018-11-15 | MRT-HK-REC-TT-180326 | FA | 2 | TRUE | TRUE | FALSE
6245 | MRT-CA03-P0UST-186936 | 2018-11-15 | MRT-HK-REC-TT-180326 | FA | 2 | TRUE | TRUE | FALSE
6246 | MRT-CA03-P0UST-186938 | 2018-11-15 | MRT-HK-REC-TT-180326 | FA | 2 | TRUE | TRUE | FALSE
6247 | MRT-CA01-P0UST-186944 | 2018-11-15 | MRT-HK-REC-TT-180326 | FA | 1 | TRUE | TRUE | FALSE
6248 | MRT-CA01-P0UMX-187214 | 2018-11-15 | MRT-HK-REC-TT-180326 | FA | 2 | TRUE | TRUE | FALSE
6249 | MRT-CA02-P0UMX-187220 | 2018-11-15 | MRT-HK-REC-TT-180326 | FA | 2 | TRUE | TRUE | FALSE
6250 | MRT-CA03-P0UMX-187222 | 2018-11-15 | MRT-HK-REC-TT-180326 | FA | 2 | TRUE | TRUE | FALSE
6251 | MRT-CA03-P0UST-186937 | 2018-11-15 | MRT-HK-REC-TT-180326 | FA | 2 | TRUE | TRUE | FALSE
6252 | MRT-YS01-P3BAT-150412 | 2018-11-15 | MRT-HK-REC-TT-1803327 | FA | 0 | TRUE | FALSE | FALSE
6253 | MRT-YS01-P2BAT-150389 | 2018-11-15 | MRT-HK-REC-TT-1803327 | FA | 0 | TRUE | FALSE | FALSE
6254 | MRT-YD00-P3BAT-150411 | 2018-11-15 | MRT-HK-REC-TT-1803327 | FA | 0 | TRUE | FALSE | FALSE
6255 | MRT-YD00-P2BAT-150388 | 2018-11-15 | MRT-HK-REC-TT-1803327 | FA | 0 | TRUE | FALSE | FALSE
6256 | MRT-FF00-P0SGA-135460 | 2018-11-15 | MRT-HK-REC-TT-180328 | FA | 0 | TRUE | FALSE | FALSE
6257 | MRT-XW01-P2LB-122043 | 2018-11-15 | MRT-DS-REC-TT-180880 | FC | 2 | TRUE | TRUE | FALSE
6258 | MRT-XW01-P3LB-122043 | 2018-11-15 | MRT-DS-REC-TT-180880 | FC | 2 | TRUE | TRUE | FALSE
6259 | MRT-YD00-P2LB-122049 | 2018-11-15 | MRT-DS-REC-TT-180881 | FC | 3 | TRUE | TRUE | FALSE
6260 | MRT-YD00-P3LB-122049 | 2018-11-15 | MRT-DS-REC-TT-180881 | FC | 3 | TRUE | TRUE | FALSE
6261 | MRT-CQ02-P2QC-130023 | 2018-11-15 | MRT-DS-REC-TT-180581-FC | FC | 0 | TRUE | TRUE | FALSE
6262 | MRT-CQ02-P3QC-130023 | 2018-11-15 | MRT-DS-REC-TT-180581-FC | FC | 0 | TRUE | TRUE | FALSE
6263 | MRT-CQ02-P2QU-130035 | 2018-11-15 | MRT-DS-REC-TT-180373-FC | FC | 0 | TRUE | TRUE | FALSE
6264 | MRT-CQ02-P3QU-130035 | 2018-11-15 | MRT-DS-REC-TT-180373-FC | FC | 0 | TRUE | TRUE | FALSE
6265 | MRT-XP00-P0BAY-150837 | 2018-11-15 | MRT-HK-REC-TT-180329 | FA | 0 | TRUE | FALSE | FALSE
6266 | MRT-CV05-P3BBT-150447 | 2018-11-15 | MRT-HK-REC-TT-180329 | FA | 0 | TRUE | FALSE | FALSE
6267 | MRT-CV05-P3BAY-150826 | 2018-11-15 | MRT-HK-REC-TT-180329 | FA | 0 | TRUE | FALSE | FALSE
6268 | MRT-CV05-P2BAY-150794 | 2018-11-15 | MRT-HK-REC-TT-180329 | FA | 0 | TRUE | FALSE | FALSE
6269 | MRT-YD00-P0UAT-150123 | 2018-11-15 | MRT-HK-REC-TT-180330 | FA | 0 | TRUE | FALSE | FALSE
6270 | MRT-YT01-P2LCB-127033 | 2018-11-16 | MRT-DS-REC-TT-180874 | FC | 3 | TRUE | TRUE | FALSE
6271 | MRT-YD00-P2LB-122056 | 2018-11-16 | MRT-DS-REC-TT-180882 | FC | 3 | TRUE | TRUE | FALSE
6272 | MRT-YD00-P3LB-122056 | 2018-11-16 | MRT-DS-REC-TT-180882 | FC | 3 | TRUE | TRUE | FALSE
6273 | MRT-YD00-P2LB-122108 | 2018-11-16 | MRT-DS-REC-TT-180883 | FC | 4 | TRUE | TRUE | FALSE
6274 | MRT-YD00-P3LB-122108 | 2018-11-16 | MRT-DS-REC-TT-180883 | FC | 4 | TRUE | TRUE | FALSE
6275 | MRT-YL16-P2LB-122078 | 2018-11-16 | MRT-DS-REC-TT-180884 | FC | 2 | TRUE | TRUE | FALSE
6276 | MRT-YL16-P3LB-122078 | 2018-11-16 | MRT-DS-REC-TT-180884 | FC | 2 | TRUE | TRUE | FALSE
6277 | MRT-YT02-P2LB-122104 | 2018-11-16 | MRT-DS-REC-TT-180885 | FI | 1 | TRUE | TRUE | FALSE
6278 | MRT-YT02-P3LB-122104 | 2018-11-16 | MRT-DS-REC-TT-180885 | FI | 1 | TRUE | TRUE | FALSE
6279 | MRT-XG01-P2LB-122021 | 2018-11-16 | MRT-DS-REC-TT-180886 | FC | 1 | TRUE | TRUE | FALSE
6280 | MRT-YU04-P2LB-111105 | 2018-11-16 | MRT-DS-REC-TT-180888 | FI | 0 | TRUE | FALSE | FALSE
6281 | MRT-YV02-P2LB-111106 | 2018-11-16 | MRT-DS-REC-TT-180888 | FI | 0 | TRUE | FALSE | FALSE
6282 | MRT-YU04-P3LB-111105 | 2018-11-16 | MRT-DS-REC-TT-180888 | FI | 0 | TRUE | FALSE | FALSE
6283 | MRT-YV02-P3LB-111106 | 2018-11-16 | MRT-DS-REC-TT-180888 | FI | 0 | TRUE | FALSE | FALSE
6284 | MRT-XB02-P2LB-122016 | 2018-11-16 | MRT-DS-REC-TT-180855-FC | FC | 3 | TRUE | TRUE | FALSE
6285 | MRT-XB02-P3LB-122016 | 2018-11-16 | MRT-DS-REC-TT-180855-FC | FC | 2 | TRUE | TRUE | FALSE
6286 | MRT-DN02-P2LA-830006 | 2018-11-16 | MRT-DS-REC-TT-180780-FC | FC | 0 | TRUE | TRUE | FALSE
6287 | MRT-YD00-P2LAC-126049 | 2018-11-19 | MRT-DS-REC-TT-180867-FC | FC | 2 | TRUE | TRUE | FALSE
6288 | MRT-YD00-P3LAC-126049 | 2018-11-19 | MRT-DS-REC-TT-180867-FC | FC | 2 | TRUE | TRUE | FALSE
6289 | MRT-YD00-P2LAC-126096 | 2018-11-19 | MRT-DS-REC-TT-180867-FC | FC | 2 | TRUE | TRUE | FALSE
6290 | MRT-YD00-P3LAC-126096 | 2018-11-19 | MRT-DS-REC-TT-180867-FC | FC | 2 | TRUE | TRUE | FALSE
6291 | MRT-YD00-P2LAC-126050 | 2018-11-19 | MRT-DS-REC-TT-180867-FC | FC | 2 | TRUE | TRUE | FALSE
6292 | MRT-YD00-P3LAC-126050 | 2018-11-19 | MRT-DS-REC-TT-180867-FC | FC | 2 | TRUE | TRUE | FALSE
6293 | MRT-YD00-P2LAC-126097 | 2018-11-19 | MRT-DS-REC-TT-180867-FC | FC | 2 | TRUE | TRUE | FALSE
6294 | MRT-YD00-P3LAC-126097 | 2018-11-19 | MRT-DS-REC-TT-180867-FC | FC | 2 | TRUE | TRUE | FALSE
6295 | MRT-YS01-P2MKC-230012 | 2018-11-19 | MRT-DS-REC-TT-180871-FC | FC | 2 | TRUE | TRUE | FALSE
6296 | MRT-YS01-P2MKC-230013 | 2018-11-19 | MRT-DS-REC-TT-180871-FC | FC | 1 | TRUE | TRUE | FALSE
6297 | MRT-YS01-P3MKC-230012 | 2018-11-19 | MRT-DS-REC-TT-180871-FC | FC | 2 | TRUE | TRUE | FALSE
6298 | MRT-YS01-P3MKC-230013 | 2018-11-19 | MRT-DS-REC-TT-180871-FC | FC | 1 | TRUE | TRUE | FALSE
6299 | MRT-YD00-P2PGB-113107 | 2018-11-19 | MRT-DS-REC-TT-180889 | FC | 1 | TRUE | TRUE | FALSE
6300 | MRT-YD00-P3PGB-113107 | 2018-11-19 | MRT-DS-REC-TT-180889 | FC | 1 | TRUE | TRUE | FALSE
6301 | MRT-CC02-P3UAG-170307 | 2018-11-19 | MRT-DS-REC-TT-180890 | FC | 2 | TRUE | TRUE | FALSE
6302 | MRT-CC02-P3UAG-170308 | 2018-11-19 | MRT-DS-REC-TT-180890 | FC | 3 | TRUE | TRUE | FALSE
6303 | MRT-VK02-P3UAG-170310 | 2018-11-19 | MRT-DS-REC-TT-180890 | FC | 1 | TRUE | TRUE | FALSE
6304 | MRT-XJ00-P2LBA-142000 | 2018-11-19 | MRT-DS-REC-TT-180887 | FC | 1 | TRUE | TRUE | FALSE
6305 | MRT-YL01-P2QC-130034 | 2018-11-19 | MRT-DS-REC-TT-180891 | FI | 3 | TRUE | TRUE | FALSE
6306 | MRT-YL01-P3QC-130034 | 2018-11-19 | MRT-DS-REC-TT-180891 | FI | 3 | TRUE | TRUE | FALSE
6307 | MRT-YS01-P0ABA-150563 | 2018-11-19 | MRT-HK-REC-TT-180331 | FA | 0 | TRUE | FALSE | FALSE
6308 | MRT-YD00-P0BBB-150553 | 2018-11-19 | MRT-HK-REC-TT-180332 | FA | 0 | TRUE | FALSE | FALSE
6309 | MRT-YD00-P0BBB-150550 | 2018-11-19 | MRT-HK-REC-TT-180332 | FA | 0 | TRUE | FALSE | FALSE
6310 | MRT-YD00-P0BBB-150547 | 2018-11-19 | MRT-HK-REC-TT-180332 | FA | 0 | TRUE | FALSE | FALSE
6311 | MRT-YD00-P0BBB-150544 | 2018-11-19 | MRT-HK-REC-TT-180332 | FA | 0 | TRUE | FALSE | FALSE
6312 | MRT-YD00-P3BBB-150541 | 2018-11-19 | MRT-HK-REC-TT-180332 | FA | 0 | TRUE | FALSE | FALSE
6313 | MRT-YD00-P2BBB-150538 | 2018-11-19 | MRT-HK-REC-TT-180332 | FA | 0 | TRUE | FALSE | FALSE
6314 | MRT-YQ01-P2LB-122085 | 2018-11-19 | MRT-DS-REC-TT-180892 | FC | 2 | TRUE | TRUE | FALSE
6315 | MRT-YQ01-P3LB-122085 | 2018-11-19 | MRT-DS-REC-TT-180892 | FC | 2 | TRUE | TRUE | FALSE
6316 | MRT-YT01-P2LB-122100 | 2018-11-19 | MRT-DS-REC-TT-180893 | FI | 1 | TRUE | TRUE | FALSE
6317 | MRT-YT01-P3LB-122100 | 2018-11-19 | MRT-DS-REC-TT-180893 | FI | 1 | TRUE | TRUE | FALSE
6318 | MRT-YD02-P2LB-122065 | 2018-11-20 | MRT-DS-REC-TT-180850-FC | FC | 2 | TRUE | TRUE | FALSE
6319 | MRT-YD02-P3LB-122065 | 2018-11-20 | MRT-DS-REC-TT-180850-FC | FC | 1 | TRUE | TRUE | FALSE
6320 | MRT-YV02-P3PAH-604522 | 2018-11-20 | MRT-DS-REC-TT-180852-FC | FC | 3 | TRUE | TRUE | FALSE
6321 | MRT-YT01-P0MKG-125375 | 2018-11-20 | MRT-HK-REC-TT-180333 | FA | 0 | TRUE | FALSE | FALSE
6322 | MRT-CH03-P0MKG-125348 | 2018-11-20 | MRT-HK-REC-TT-180333 | FA | 0 | TRUE | FALSE | FALSE
6323 | MRT-DN04-P0MKG-125348 | 2018-11-20 | MRT-HK-REC-TT-180333 | FA | 0 | TRUE | FALSE | FALSE
6324 | MRT-YK10-P0MKG-125321 | 2018-11-20 | MRT-HK-REC-TT-180333 | FA | 0 | TRUE | FALSE | FALSE
6325 | MRT-YM02-P3BAA-150939 | 2018-11-20 | MRT-HK-REC-TT-180334 | FA | 0 | TRUE | FALSE | FALSE
6326 | MRT-YT01-P0GEN-135360 | 2018-11-20 | MRT-HK-REC-TT-180335 | FA | 0 | TRUE | FALSE | FALSE
6327 | MRT-YT01-P0GEN-135358 | 2018-11-20 | MRT-HK-REC-TT-180335 | FA | 0 | TRUE | FALSE | FALSE
6328 | MRT-YQ03-P2LB-122086 | 2018-11-20 | MRT-DS-REC-TT-180895 | FI | 2 | TRUE | TRUE | FALSE
6329 | MRT-YQ03-P3LB-122086 | 2018-11-20 | MRT-DS-REC-TT-180895 | FI | 2 | TRUE | TRUE | FALSE
6330 | MRT-XJ00-P2LB-122027 | 2018-11-20 | MRT-DS-REC-TT-180896 | FC | 1 | TRUE | TRUE | FALSE
6331 | MRT-XJ00-P3LB-122027 | 2018-11-20 | MRT-DS-REC-TT-180896 | FC | 1 | TRUE | TRUE | FALSE
6332 | MRT-US02-P0BFD-150700 | 2018-11-21 | MRT-HK-REC-TT-180336 | FA | 0 | TRUE | FALSE | FALSE
6333 | MRT-US02-P0BJJ-150702 | 2018-11-21 | MRT-HK-REC-TT-180336 | FA | 0 | TRUE | FALSE | FALSE
6334 | MRT-YU02-P0BFD-150699 | 2018-11-21 | MRT-HK-REC-TT-180336 | FA | 0 | TRUE | FALSE | FALSE
6335 | MRT-YU02-P0BJJ-150701 | 2018-11-21 | MRT-HK-REC-TT-180336 | FA | 0 | TRUE | FALSE | FALSE
6336 | MRT-XW03-P0BFA-150286 | 2018-11-21 | MRT-HK-REC-TT-180337 | FA | 0 | TRUE | FALSE | FALSE
6337 | MRT-XW03-P0BFA-150287 | 2018-11-21 | MRT-HK-REC-TT-180337 | FA | 0 | TRUE | FALSE | FALSE
6338 | MRT-XW03-P0BFA-150288 | 2018-11-21 | MRT-HK-REC-TT-180337 | FA | 0 | TRUE | FALSE | FALSE
6339 | MRT-XW03-P0BFA-150290 | 2018-11-21 | MRT-HK-REC-TT-180337 | FA | 0 | TRUE | FALSE | FALSE
6340 | MRT-XW03-P0BFA-150291 | 2018-11-21 | MRT-HK-REC-TT-180337 | FA | 0 | TRUE | FALSE | FALSE
6341 | MRT-XW03-P0BFA-150292 | 2018-11-21 | MRT-HK-REC-TT-180337 | FA | 0 | TRUE | FALSE | FALSE
6342 | MRT-XW03-P0BFA-150293 | 2018-11-21 | MRT-HK-REC-TT-180337 | FA | 0 | TRUE | FALSE | FALSE
6343 | MRT-XW03-P0BFA-150294 | 2018-11-21 | MRT-HK-REC-TT-180337 | FA | 0 | TRUE | FALSE | FALSE
6344 | MRT-XW03-P0BFA-150295 | 2018-11-21 | MRT-HK-REC-TT-180337 | FA | 0 | TRUE | FALSE | FALSE
6345 | MRT-YT01-P0GEN-135328 | 2018-11-21 | MRT-HK-REC-TT-180338 | FA | 0 | TRUE | FALSE | FALSE
6346 | MRT-YL15-P0GEN-135393 | 2018-11-21 | MRT-HK-REC-TT-180338 | FA | 0 | TRUE | FALSE | FALSE
6347 | MRT-XW03-P0GEN-135301 | 2018-11-21 | MRT-HK-REC-TT-180338 | FA | 2 | TRUE | TRUE | FALSE
6348 | MRT-XG02-P0GEN-135302 | 2018-11-21 | MRT-HK-REC-TT-180338 | FA | 3 | TRUE | TRUE | FALSE
6349 | MRT-YK09-P2MKC-230002 | 2018-11-21 | MRT-DS-REC-TT-180897 | FC | 4 | TRUE | TRUE | FALSE
6350 | MRT-YK09-P3MKC-230002 | 2018-11-21 | MRT-DS-REC-TT-180897 | FC | 4 | TRUE | TRUE | FALSE
6351 | MRT-XH01-P3UMA-143000 | 2018-11-21 | MRT-DS-REC-TT-180898 | FC | 1 | TRUE | TRUE | FALSE
6352 | MRT-DN05-P2QU-130001 | 2018-11-22 | MRT-DS-REC-TT-180900 | FA | 0 | TRUE | FALSE | FALSE
6353 | MRT-DN05-P3QU-130001 | 2018-11-22 | MRT-DS-REC-TT-180900 | FA | 0 | TRUE | FALSE | FALSE
6354 | MRT-CQ02-P2QU-130036 | 2018-11-22 | MRT-DS-REC-TT-180901 | FI | 0 | TRUE | FALSE | FALSE
6355 | MRT-CQ02-P3QU-130036 | 2018-11-22 | MRT-DS-REC-TT-180901 | FI | 0 | TRUE | FALSE | FALSE
6356 | MRT-YE00-P2MKA-230001 | 2018-11-22 | MRT-DS-REC-TT-180741-FC | FC | 1 | TRUE | TRUE | FALSE
6357 | MRT-YK00-P2BAT-240001 | 2018-11-22 | MRT-DS-REC-TT-180741-FC | FC | 1 | TRUE | TRUE | FALSE
6358 | MRT-UC02-P2BAT-240001 | 2018-11-22 | MRT-DS-REC-TT-180741-FC | FC | 1 | TRUE | TRUE | FALSE
6359 | MRT-YE00-P3MKA-230001 | 2018-11-22 | MRT-DS-REC-TT-180741-FC | FC | 1 | TRUE | TRUE | FALSE
6360 | MRT-YE00-P2LB-122116 | 2018-11-22 | MRT-DS-REC-TT-180858-FC | FC | 0 | TRUE | TRUE | FALSE
6361 | MRT-YE00-P3LB-122116 | 2018-11-22 | MRT-DS-REC-TT-180858-FC | FC | 0 | TRUE | TRUE | FALSE
6362 | MRT-YD00-P3MKG-220005 | 2018-11-22 | MRT-DS-REC-TT-180902 | FC | 2 | TRUE | TRUE | FALSE
6363 | MRT-CT00-P0SMM-128001 | 2018-11-22 | MRT-DS-REC-TT-180848-FC | FC | 0 | TRUE | FALSE | FALSE
6364 | MRT-DM02-P0SMM-128001 | 2018-11-22 | MRT-DS-REC-TT-180848-FC | FC | 0 | TRUE | FALSE | FALSE
6365 | MRT-YD00-P2LB-122120 | 2018-11-22 | MRT-DS-REC-TT-180903 | FI | 0 | TRUE | FALSE | FALSE
6366 | MRT-QE00-P0MKG-125363 | 2018-11-22 | MRT-HK-REC-TT-180339 | FI | 0 | TRUE | FALSE | FALSE
6367 | MRT-YD00-P0MKG-125331 | 2018-11-22 | MRT-HK-REC-TT-180339 | FI | 0 | TRUE | FALSE | FALSE
6368 | MRT-XW01-P2LB-122043 | 2018-11-22 | MRT-DS-REC-TT-180880-FC | FC | 2 | TRUE | TRUE | FALSE
6369 | MRT-XW01-P3LB-122043 | 2018-11-22 | MRT-DS-REC-TT-180880-FC | FC | 2 | TRUE | TRUE | FALSE
6370 | MRT-YD00-P3CWA-165003 | 2018-11-22 | MRT-HK-REC-TT-180340 | FA | 2 | TRUE | TRUE | FALSE
6371 | MRT-YD05-P2QC-130035 | 2018-11-22 | MRT-DS-REC-TT-180904 | FI | 3 | TRUE | TRUE | FALSE
6372 | MRT-YD05-P3QC-130035 | 2018-11-22 | MRT-DS-REC-TT-180904 | FI | 3 | TRUE | TRUE | FALSE
6373 | MRT-DN02-P2H-830016 | 2018-11-23 | MRT-DS-REC-TT-180905 | FA | 1 | TRUE | TRUE | FALSE
6392 | MRT-CQ02-P2QU-130036 | 2018-11-26 | MRT-DS-REC-TT-180901-FC | FC | 0 | TRUE | TRUE | FALSE
6393 | MRT-CQ02-P3QU-130036 | 2018-11-26 | MRT-DS-REC-TT-180901-FC | FC | 0 | TRUE | TRUE | FALSE
6394 | MRT-YD00-P2LB-122120 | 2018-11-26 | MRT-DS-REC-TT-180903-FC | FC | 0 | TRUE | TRUE | FALSE
6395 | MRT-XG02-P2LAC-126003 | 2018-11-26 | MRT-DS-REC-TT-180906 | FC | 3 | TRUE | TRUE | FALSE
6396 | MRT-XG02-P3LAC-126003 | 2018-11-26 | MRT-DS-REC-TT-180906 | FC | 3 | TRUE | TRUE | FALSE
6397 | MRT-XG02-P2LAC-126053 | 2018-11-26 | MRT-DS-REC-TT-180906 | FC | 3 | TRUE | TRUE | FALSE
6398 | MRT-XG02-P3LAC-126053 | 2018-11-26 | MRT-DS-REC-TT-180906 | FC | 3 | TRUE | TRUE | FALSE
6399 | MRT-CH01-P2LAC-126037 | 2018-11-26 | MRT-DS-REC-TT-180907 | FI | 0 | TRUE | FALSE | FALSE
6400 | MRT-CH01-P3LAC-126037 | 2018-11-26 | MRT-DS-REC-TT-180907 | FI | 0 | TRUE | FALSE | FALSE
6401 | MRT-CH01-P2LAC-126085 | 2018-11-26 | MRT-DS-REC-TT-180907 | FI | 0 | TRUE | FALSE | FALSE
6402 | MRT-CH01-P3LAC-126085 | 2018-11-26 | MRT-DS-REC-TT-180907 | FI | 0 | TRUE | FALSE | FALSE
6403 | MRT-CC04-P0ULY-176103 | 2018-11-26 | MRT-HK-REC-TT-180341 | FA | 0 | TRUE | FALSE | FALSE
6404 | MRT-CC04-P0ULY-176102 | 2018-11-26 | MRT-HK-REC-TT-180341 | FA | 0 | TRUE | FALSE | FALSE
6405 | MRT-CC04-P0ULY-176104 | 2018-11-26 | MRT-HK-REC-TT-180341 | FA | 0 | TRUE | FALSE | FALSE
6406 | MRT-CC04-P0ULY-176133 | 2018-11-26 | MRT-HK-REC-TT-180341 | FA | 0 | TRUE | FALSE | FALSE
6407 | MRT-CC04-P0ULY-176110 | 2018-11-26 | MRT-HK-REC-TT-180341 | FA | 0 | TRUE | FALSE | FALSE
6408 | MRT-CC04-P0ULY-176116 | 2018-11-26 | MRT-HK-REC-TT-180341 | FA | 0 | TRUE | FALSE | FALSE
6409 | MRT-CC04-P0ULY-176117 | 2018-11-26 | MRT-HK-REC-TT-180341 | FA | 0 | TRUE | FALSE | FALSE
6410 | MRT-CC04-P0ULY-176118 | 2018-11-26 | MRT-HK-REC-TT-180341 | FA | 0 | TRUE | FALSE | FALSE
6411 | MRT-CC04-P0ULY-176119 | 2018-11-26 | MRT-HK-REC-TT-180341 | FA | 0 | TRUE | FALSE | FALSE
6412 | MRT-CC04-P0ULY-176134 | 2018-11-26 | MRT-HK-REC-TT-180341 | FA | 0 | TRUE | FALSE | FALSE
6413 | MRT-CC07-P0ULY-176113 | 2018-11-26 | MRT-HK-REC-TT-180341 | FA | 0 | TRUE | FALSE | FALSE
6414 | MRT-CC04-P0ULY-176111 | 2018-11-26 | MRT-HK-REC-TT-180341 | FA | 0 | TRUE | FALSE | FALSE
6415 | MRT-CA00-P0UGA-186610 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6416 | MRT-CA00-P0UGA-186615 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6417 | MRT-CA01-P0UGA-186654 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 0 | TRUE | TRUE | FALSE
6418 | MRT-CA00-P0UGX-186960 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 3 | TRUE | TRUE | FALSE
6419 | MRT-CA01-P0UGX-186976 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6420 | MRT-CA01-P0UGX-186978 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6421 | MRT-CA01-P0UGX-186988 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6422 | MRT-CA01-P0UPB-187032 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 1 | TRUE | TRUE | FALSE
6423 | MRT-CA00-P0UGA-186611 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6424 | MRT-CA00-P0UGA-186612 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6425 | MRT-CA00-P0UGA-186613 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6426 | MRT-CA00-P0UGA-186614 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6427 | MRT-CA00-P0UGA-186616 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6428 | MRT-CA00-P0UGA-186617 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6429 | MRT-CA00-P0UGX-186961 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 3 | TRUE | TRUE | FALSE
6430 | MRT-CA00-P0UGX-186963 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 3 | TRUE | TRUE | FALSE
6431 | MRT-CA03-P0UGA-186635 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 1 | TRUE | TRUE | FALSE
6432 | MRT-CA01-P0UGX-186973 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6433 | MRT-CA01-P0UGX-186986 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6434 | MRT-CA02-P0UGX-186974 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6435 | MRT-CA02-P0UGX-186983 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6436 | MRT-CA02-P0UGX-186992 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6437 | MRT-CA02-P0UGX-186993 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 2 | TRUE | TRUE | FALSE
6438 | MRT-CA02-P0UGX-186975 | 2018-11-26 | MRT-HK-REC-TT-180344 | FA | 2 | TRUE | TRUE | FALSE
6439 | MRT-CA01-P0UGA-186655 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 0 | TRUE | TRUE | FALSE
6440 | MRT-CA01-P0UPB-187033 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 0 | TRUE | TRUE | FALSE
6441 | MRT-CA00-P0UGX-186956 | 2018-11-26 | MRT-HK-REC-TT-180342 | FA | 3 | TRUE | TRUE | FALSE
6442 | MRT-CA01-P0UGG-187286 | 2018-11-26 | MRT-HK-REC-TT-180343 | FA | 1 | TRUE | TRUE | FALSE
6443 | MRT-CA06-P0UGG-187278 | 2018-11-26 | MRT-HK-REC-TT-180343 | FA | 1 | TRUE | TRUE | FALSE
6444 | MRT-CA01-P0USG-186894 | 2018-11-26 | MRT-HK-REC-TT-180344 | FA | 1 | TRUE | TRUE | FALSE
6445 | MRT-YF02-P0MKG-125318 | 2018-11-26 | MRT-HK-REC-TT-180345 | FA | 0 | TRUE | FALSE | FALSE
6446 | MRT-YT01-P0MKG-125376 | 2018-11-26 | MRT-HK-REC-TT-180346 | FA | 0 | TRUE | FALSE | FALSE
6447 | MRT-YK01-P0MKG-125330 | 2018-11-26 | MRT-HK-REC-TT-180346 | FA | 0 | TRUE | FALSE | FALSE
6448 | MRT-CQ02-P2LB-122118 | 2018-11-27 | MRT-DS-REC-TT-180908 | FI | 0 | TRUE | FALSE | FALSE
6449 | MRT-DN05-P2LB-122119 | 2018-11-27 | MRT-DS-REC-TT-180908 | FA | 0 | TRUE | FALSE | FALSE
6450 | MRT-YS01-P2MKC-230012 | 2018-11-27 | MRT-DS-REC-TT-180909 | FC | 3 | TRUE | TRUE | FALSE
6451 | MRT-YS01-P2MKC-230013 | 2018-11-27 | MRT-DS-REC-TT-180909 | FC | 2 | TRUE | TRUE | FALSE
6452 | MRT-YS01-P3MKC-230012 | 2018-11-27 | MRT-DS-REC-TT-180909 | FC | 3 | TRUE | TRUE | FALSE
6453 | MRT-YS01-P3MKC-230013 | 2018-11-27 | MRT-DS-REC-TT-180909 | FC | 2 | TRUE | TRUE | FALSE
6454 | MRT-YS01-P2MKC-230014 | 2018-11-27 | MRT-DS-REC-TT-180910 | FC | 3 | TRUE | TRUE | FALSE
6455 | MRT-YS01-P2MKC-230015 | 2018-11-27 | MRT-DS-REC-TT-180910 | FC | 2 | TRUE | TRUE | FALSE
6456 | MRT-YS01-P3MKC-230014 | 2018-11-27 | MRT-DS-REC-TT-180910 | FC | 3 | TRUE | TRUE | FALSE
6457 | MRT-YS01-P3MKC-230015 | 2018-11-27 | MRT-DS-REC-TT-180910 | FC | 2 | TRUE | TRUE | FALSE
6458 | MRT-UC02-P2LB-122121 | 2018-11-27 | MRT-DS-REC-TT-180912 | FI | 0 | TRUE | FALSE | FALSE
6459 | MRT-XA01-P0ABA-150513 | 2018-11-27 | MRT-HK-REC-TT-180347 | FA | 2 | TRUE | TRUE | FALSE
6460 | MRT-XA01-P0ABA-150510 | 2018-11-27 | MRT-HK-REC-TT-180347 | FA | 2 | TRUE | TRUE | FALSE
6461 | MRT-XA01-P0ABA-150517 | 2018-11-27 | MRT-HK-REC-TT-180347 | FA | 1 | TRUE | TRUE | FALSE
6462 | MRT-CH01-P2LAC-126037 | 2018-11-28 | MRT-DS-REC-TT-180907-FC | FC | 0 | TRUE | TRUE | FALSE
6463 | MRT-CH01-P3LAC-126037 | 2018-11-28 | MRT-DS-REC-TT-180907-FC | FC | 0 | TRUE | TRUE | FALSE
6464 | MRT-CH01-P2LAC-126085 | 2018-11-28 | MRT-DS-REC-TT-180907-FC | FC | 0 | TRUE | TRUE | FALSE
6465 | MRT-CH01-P3LAC-126085 | 2018-11-28 | MRT-DS-REC-TT-180907-FC | FC | 0 | TRUE | TRUE | FALSE
6466 | MRT-UC02-P2LB-122121 | 2018-11-28 | MRT-DS-REC-TT-180912-FC | FC | 0 | TRUE | TRUE | FALSE
6469 | MRT-YF00-P2SCA-127518 | 2018-11-29 | MRT-DS-REC-TT-180913 | FC | 2 | TRUE | TRUE | FALSE
6470 | MRT-YF00-P3SCA-127518 | 2018-11-29 | MRT-DS-REC-TT-180913 | FC | 2 | TRUE | TRUE | FALSE
6471 | MRT-CQ02-P2LAC-126038 | 2018-11-29 | MRT-DS-REC-TT-180911 | FI | 0 | TRUE | FALSE | FALSE
6472 | MRT-CQ02-P3LAC-126038 | 2018-11-29 | MRT-DS-REC-TT-180911 | FI | 0 | TRUE | FALSE | FALSE
6473 | MRT-CQ02-P2LAC-126086 | 2018-11-29 | MRT-DS-REC-TT-180911 | FI | 0 | TRUE | FALSE | FALSE
6474 | MRT-CQ02-P3LAC-126086 | 2018-11-29 | MRT-DS-REC-TT-180911 | FI | 0 | TRUE | FALSE | FALSE
6475 | MRT-CT00-P2ZEN-113500 | 2018-11-29 | MRT-DS-REC-TT-180861-FC | FC | 0 | TRUE | TRUE | FALSE
6476 | MRT-CT00-P3ZEN-113500 | 2018-11-29 | MRT-DS-REC-TT-180861-FC | FC | 0 | TRUE | TRUE | FALSE
6477 | MRT-YD00-P0QJA-111601 | 2018-11-29 | MRT-DS-REC-TT-180862-FC | FC | 0 | TRUE | TRUE | FALSE
6478 | MRT-XG02-P2PA-110002 | 2018-11-29 | MRT-DS-REC-TT-180864-FC | FC | 6 | TRUE | TRUE | FALSE
6479 | MRT-XG02-P3PA-110002 | 2018-11-29 | MRT-DS-REC-TT-180864-FC | FC | 6 | TRUE | TRUE | FALSE
6480 | MRT-QM03-P0ZEN-155013 | 2018-11-29 | MRT-HK-REC-TT-180348 | FA | 0 | TRUE | FALSE | FALSE
6481 | MRT-YS01-P0BBA-150469 | 2018-11-29 | MRT-HK-REC-TT-180349 | FA | 0 | TRUE | FALSE | FALSE
6482 | MRT-YD00-P0ABA-150934 | 2018-11-29 | MRT-HK-REC-TT-180350 | FA | 0 | TRUE | FALSE | FALSE
6483 | MRT-QM03-P0ZEN-145017 | 2018-11-29 | MRT-HK-REC-TT-180351 | FA | 0 | TRUE | FALSE | FALSE
6489 | MRT-YT02-P2LB-122094 | 2018-11-29 | MRT-DS-REC-TT-180916 | FC | 2 | TRUE | TRUE | FALSE
6490 | MRT-YT02-P3LB-122094 | 2018-11-29 | MRT-DS-REC-TT-180916 | FC | 2 | TRUE | TRUE | FALSE
6491 | MRT-YE00-P2LB-122116 | 2018-11-29 | MRT-DS-REC-TT-180915 | FC | 1 | TRUE | TRUE | FALSE
6492 | MRT-YE00-P3LB-122116 | 2018-11-29 | MRT-DS-REC-TT-180915 | FC | 1 | TRUE | TRUE | FALSE
6493 | MRT-YE07-P0UGA-150149 | 2018-11-29 | MRT-HK-REC-TT-180352 | FA | 0 | TRUE | FALSE | FALSE
6484 | MRT-XJ00-P2LBG-142000 | 2018-11-30 | MRT-DS-REC-TT-180914 | FC | 1 | TRUE | TRUE | FALSE
6485 | MRT-XJ00-P2LAB-142000 | 2018-11-30 | MRT-DS-REC-TT-180914 | FC | 1 | TRUE | TRUE | FALSE
6486 | MRT-XJ00-P2LCA-142000 | 2018-11-30 | MRT-DS-REC-TT-180914 | FC | 1 | TRUE | TRUE | FALSE
6487 | MRT-XJ00-P2PGB-142000 | 2018-11-30 | MRT-DS-REC-TT-180914 | FC | 1 | TRUE | TRUE | FALSE
6488 | MRT-XJ00-P2LCM-142000 | 2018-11-30 | MRT-DS-REC-TT-180914 | FC | 1 | TRUE | TRUE | FALSE
6893 | MRT-YF01-P0BFB-150114 | 2018-12-01 | MRT-HK-REC-TT-180356 | FA | 0 | TRUE | FALSE | FALSE
6894 | MRT-YF01-P0BFB-150115 | 2018-12-01 | MRT-HK-REC-TT-180356 | FA | 0 | TRUE | FALSE | FALSE
6895 | MRT-YM02-P2BAA-150481 | 2018-12-01 | MRT-HK-REC-TT-180356 | FA | 0 | TRUE | FALSE | FALSE
6896 | MRT-YM02-P2BAA-150483 | 2018-12-01 | MRT-HK-REC-TT-180356 | FA | 0 | TRUE | FALSE | FALSE
6897 | MRT-YS01-P0BBA-150113 | 2018-12-01 | MRT-HK-REC-TT-180356 | FA | 0 | TRUE | FALSE | FALSE
6898 | MRT-YS01-P0BFB-150111 | 2018-12-01 | MRT-HK-REC-TT-180356 | FA | 0 | TRUE | FALSE | FALSE
6899 | MRT-YS01-P0BFB-150304 | 2018-12-01 | MRT-HK-REC-TT-180356 | FA | 0 | TRUE | FALSE | FALSE
6900 | MRT-YS01-P0BFB-150306 | 2018-12-01 | MRT-HK-REC-TT-180356 | FA | 0 | TRUE | FALSE | FALSE
7926 | MRT-CA01-P0UAB-187330 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7927 | MRT-CA01-P0UAB-187331 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7928 | MRT-CA01-P0UAB-187332 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7929 | MRT-CA02-P0UAB-187333 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7930 | MRT-CA02-P0UAB-187334 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7931 | MRT-CA01-P0UAB-187335 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7932 | MRT-CA01-P0UAB-187336 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7933 | MRT-CA00-P0UAB-187321 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7934 | MRT-CA00-P0UAB-187323 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7935 | MRT-CA01-P0UAB-187341 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7936 | MRT-CA01-P0UAB-187343 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7937 | MRT-CA01-P0UAB-187344 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7938 | MRT-CA01-P0UAB-187345 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7939 | MRT-CA01-P0UAB-187346 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7940 | MRT-CA02-P0UAB-187328 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7941 | MRT-CA02-P0UAB-187342 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
7943 | MRT-CA06-P0UYX-187315 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
8022 | MRT-CA01-P0UAB-187327 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 0 | TRUE | FALSE | FALSE
10611 | MRT-CA00-P0UAB-187319 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 1 | TRUE | TRUE | FALSE
10612 | MRT-CA00-P0UAB-187337 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 1 | TRUE | TRUE | FALSE
10613 | MRT-CA00-P0UAB-187339 | 2018-12-01 | MRT-HK-REC-TT-180360 | FA | 1 | TRUE | TRUE | FALSE
6496 | MRT-DN04-P0MKG-125348 | 2018-12-03 | MRT-HK-REC-TT-180353 | FA | 1 | TRUE | TRUE | FALSE
6497 | MRT-YF02-P0MKG-125318 | 2018-12-03 | MRT-HK-REC-TT-180353 | FA | 0 | TRUE | TRUE | FALSE
6498 | MRT-YL08-P0MKG-125362 | 2018-12-03 | MRT-HK-REC-TT-180353 | FA | 0 | TRUE | TRUE | FALSE
6499 | MRT-CT00-P3AYA-160005 | 2018-12-03 | MRT-HK-REC-TT-180354 | FA | 0 | TRUE | FALSE | FALSE
6500 | MRT-DD07-P3AYA-160027 | 2018-12-03 | MRT-HK-REC-TT-180354 | FA | 0 | TRUE | FALSE | FALSE
6501 | MRT-DD07-P3AYA-160030 | 2018-12-03 | MRT-HK-REC-TT-180354 | FA | 0 | TRUE | FALSE | FALSE
6502 | MRT-DS00-P3AYA-160024 | 2018-12-03 | MRT-HK-REC-TT-180354 | FA | 0 | TRUE | FALSE | FALSE
6503 | MRT-DS00-P3AYA-160026 | 2018-12-03 | MRT-HK-REC-TT-180354 | FA | 0 | TRUE | FALSE | FALSE
6504 | MRT-DS00-P3AYA-160029 | 2018-12-03 | MRT-HK-REC-TT-180354 | FA | 0 | TRUE | FALSE | FALSE
6505 | MRT-YK08-P3AYA-160019 | 2018-12-03 | MRT-HK-REC-TT-180354 | FA | 0 | TRUE | FALSE | FALSE
6506 | MRT-YE07-P0BJQ-150154 | 2018-12-03 | MRT-HK-REC-TT-180357 | FA | 0 | TRUE | FALSE | FALSE
6507 | MRT-YD00-P0BTL-150633 | 2018-12-03 | MRT-HK-REC-TT-180358 | FA | 0 | TRUE | FALSE | FALSE
6508 | MRT-YT01-P0BTL-150632 | 2018-12-03 | MRT-HK-REC-TT-180358 | FA | 0 | TRUE | FALSE | FALSE
6509 | MRT-CA06-P0USX-186804 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6510 | MRT-CA00-P0USX-186806 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 1 | TRUE | FALSE | FALSE
6511 | MRT-CA00-P0USX-186808 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 1 | TRUE | FALSE | FALSE
6512 | MRT-CA00-P0USX-186812 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6513 | MRT-CA00-P0USX-186816 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6514 | MRT-CA01-P0USX-186818 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6515 | MRT-CA01-P0USX-186820 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6516 | MRT-CA01-P0USX-186822 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6517 | MRT-CA02-P0USX-186824 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6518 | MRT-CA03-P0USX-186826 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6519 | MRT-CA03-P0USX-186828 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6520 | MRT-CA03-P0USX-186830 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6521 | MRT-CA03-P0USX-186832 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6522 | MRT-CA03-P0USX-186834 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6523 | MRT-CA03-P0USX-186836 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6524 | MRT-CA03-P0USX-186840 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6525 | MRT-CA01-P0USX-186842 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6526 | MRT-CA00-P0USX-186807 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 1 | TRUE | FALSE | FALSE
6527 | MRT-CA01-P0USX-186843 | 2018-12-03 | MRT-HK-REC-TT-180359 | FA | 0 | TRUE | FALSE | FALSE
6528 | MRT-CA01-P0UGA-186659 | 2018-12-03 | MRT-HK-REC-TT-180361 | FA | 1 | TRUE | TRUE | FALSE
6529 | MRT-CA01-P0UGA-186658 | 2018-12-03 | MRT-HK-REC-TT-180361 | FA | 1 | TRUE | TRUE | FALSE
6530 | MRT-YE07-P0GQA-150155 | 2018-12-04 | MRT-HK-REC-TT-180355 | FA | 0 | TRUE | FALSE | FALSE
6531 | MRT-CN00-P2ZEN-110102 | 2018-12-04 | MRT-DS-REC-TT-180917 | FA | 0 | TRUE | FALSE | FALSE
6532 | MRT-CN00-P3ZEN-110102 | 2018-12-04 | MRT-DS-REC-TT-180917 | FA | 2 | TRUE | TRUE | FALSE
6533 | MRT-CT00-P2ZEN-113400 | 2018-12-04 | MRT-DS-REC-TT-180860-FC | FC | 0 | TRUE | TRUE | FALSE
6534 | MRT-CT00-P3ZEN-113400 | 2018-12-04 | MRT-DS-REC-TT-180860-FC | FC | 0 | TRUE | TRUE | FALSE
6535 | MRT-CT00-P2ZEN-113300 | 2018-12-04 | MRT-DS-REC-TT-180859-FC | FC | 0 | TRUE | TRUE | FALSE
6536 | MRT-CT00-P3ZEN-113300 | 2018-12-04 | MRT-DS-REC-TT-180859-FC | FC | 0 | TRUE | TRUE | FALSE
6537 | MRT-YK00-P2LB-122076 | 2018-12-04 | MRT-DS-REC-TT-180873-FC | FC | 2 | TRUE | TRUE | FALSE
6538 | MRT-YK00-P3LB-122076 | 2018-12-04 | MRT-DS-REC-TT-180873-FC | FC | 2 | TRUE | TRUE | FALSE
6539 | MRT-YD00-P2LB-122108 | 2018-12-04 | MRT-DS-REC-TT-180883-FC | FC | 4 | TRUE | TRUE | FALSE
6540 | MRT-DN02-P2H-830016 | 2018-12-04 | MRT-DS-REC-TT-180905-FC | FC | 1 | TRUE | TRUE | FALSE
6541 | MRT-CC02-P3UAG-170307 | 2018-12-04 | MRT-DS-REC-TT-180890-FC | FC | 2 | TRUE | TRUE | FALSE
6542 | MRT-CC02-P3UAG-170308 | 2018-12-04 | MRT-DS-REC-TT-180890-FC | FC | 3 | TRUE | TRUE | FALSE
6543 | MRT-VK02-P3UAG-170310 | 2018-12-04 | MRT-DS-REC-TT-180890-FC | FC | 1 | TRUE | TRUE | FALSE
6544 | MRT-BT00-P0BAU-150620 | 2018-12-04 | MRT-HK-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
6545 | MRT-BT00-P0BAU-150623 | 2018-12-04 | MRT-HK-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
6546 | MRT-BT00-P2BAY-150795 | 2018-12-04 | MRT-HK-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
6547 | MRT-BT00-P3BAY-150827 | 2018-12-04 | MRT-HK-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
6548 | MRT-CH04-P2BAY-150796 | 2018-12-04 | MRT-HK-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
6549 | MRT-CH04-P3BAY-150828 | 2018-12-04 | MRT-HK-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
6550 | MRT-CV05-P0BBB-150534 | 2018-12-04 | MRT-HK-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
6551 | MRT-CV05-P3BAA-150948 | 2018-12-04 | MRT-HK-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
6552 | MRT-CV05-P3BAT-150414 | 2018-12-04 | MRT-HK-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
6553 | MRT-YT01-P2BAY-150789 | 2018-12-04 | MRT-HK-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
6554 | MRT-YT01-P3BAY-150821 | 2018-12-04 | MRT-HK-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
6563 | MRT-YD00-P3LB-122108 | 2018-12-04 | MRT-DS-REC-TT-180883-FC | FC | 4 | TRUE | TRUE | FALSE
7396 | MRT-DP00-P0EZN-070558 | 2018-12-04 | MRT-HK-REC-TT-180362 | FA | 0 | TRUE | FALSE | FALSE
6555 | MRT-CC02-P2UAG-170307 | 2018-12-05 | MRT-DS-REC-TT-180879-FC | FC | 2 | TRUE | TRUE | FALSE
6556 | MRT-CC02-P2UAG-170308 | 2018-12-05 | MRT-DS-REC-TT-180879-FC | FC | 3 | TRUE | TRUE | FALSE
6557 | MRT-VK02-P2UAG-170310 | 2018-12-05 | MRT-DS-REC-TT-180879-FC | FC | 1 | TRUE | TRUE | FALSE
6559 | MRT-CQ02-P2SM-128060 | 2018-12-06 | MRT-DS-REC-TT-180918 | FI | 0 | TRUE | FALSE | FALSE
6560 | MRT-CQ02-P3SM-128060 | 2018-12-06 | MRT-DS-REC-TT-180918 | FI | 0 | TRUE | FALSE | FALSE
6561 | MRT-XH01-P2LB-122112 | 2018-12-06 | MRT-DS-REC-TT-180919 | FC | 1 | TRUE | TRUE | FALSE
6562 | MRT-XH01-P3LB-122112 | 2018-12-06 | MRT-DS-REC-TT-180919 | FC | 1 | TRUE | TRUE | FALSE
6564 | MRT-YK09-P2MKC-230002 | 2018-12-07 | MRT-DS-REC-TT-180897-FC | FC | 4 | TRUE | TRUE | FALSE
6565 | MRT-YK09-P3MKC-230002 | 2018-12-07 | MRT-DS-REC-TT-180897-FC | FC | 4 | TRUE | TRUE | FALSE
6566 | MRT-YE07-P2UXA-150150 | 2018-12-07 | MRT-HK-REC-TT-180363 | FA | 0 | TRUE | FALSE | FALSE
6567 | MRT-YF02-P2CJJ-240112 | 2018-12-07 | MRT-DS-REC-TT-180920 | FI | 0 | TRUE | FALSE | FALSE
6568 | MRT-DM02-P2MAA-220165 | 2018-12-07 | MRT-DS-REC-TT-180920 | FI | 0 | TRUE | FALSE | FALSE
6569 | MRT-DM02-P2MAA-220166 | 2018-12-07 | MRT-DS-REC-TT-180920 | FI | 0 | TRUE | FALSE | FALSE
6570 | MRT-DM02-P2MAA-220134 | 2018-12-07 | MRT-DS-REC-TT-180921 | FI | 0 | TRUE | FALSE | FALSE
6571 | MRT-DM02-P3MAA-220133 | 2018-12-07 | MRT-DS-REC-TT-180921 | FI | 0 | TRUE | FALSE | FALSE
6572 | MRT-XK00-P2GM-128507 | 2018-12-10 | MRT-DS-REC-TT-180922 | FC | 3 | TRUE | TRUE | FALSE
6573 | MRT-XK00-P3GM-128507 | 2018-12-10 | MRT-DS-REC-TT-180922 | FC | 3 | TRUE | TRUE | FALSE
6574 | MRT-XA00-P2QU-130025 | 2018-12-10 | MRT-DS-REC-TT-180870-FC | FC | 6 | TRUE | TRUE | FALSE
6575 | MRT-CQ02-P2PGB-113203 | 2018-12-10 | MRT-DS-REC-TT-180868-FC | FC | 0 | TRUE | TRUE | FALSE
6576 | MRT-YD00-P2PAB-113263 | 2018-12-10 | MRT-DS-REC-TT-180868-FC | FC | 0 | TRUE | TRUE | FALSE
6577 | MRT-CQ02-P2PAB-113267 | 2018-12-10 | MRT-DS-REC-TT-180868-FC | FC | 0 | TRUE | TRUE | FALSE
6578 | MRT-CQ02-P3PGB-113203 | 2018-12-10 | MRT-DS-REC-TT-180868-FC | FC | 0 | TRUE | TRUE | FALSE
6579 | MRT-YD00-P3PAB-113263 | 2018-12-10 | MRT-DS-REC-TT-180868-FC | FC | 0 | TRUE | TRUE | FALSE
6580 | MRT-CQ02-P3PAB-113267 | 2018-12-10 | MRT-DS-REC-TT-180868-FC | FC | 0 | TRUE | TRUE | FALSE
6581 | MRT-XJ00-P2LB-122028 | 2018-12-10 | MRT-DS-REC-TT-180877-FC | FC | 2 | TRUE | TRUE | FALSE
6582 | MRT-XJ00-P3LB-122028 | 2018-12-10 | MRT-DS-REC-TT-180877-FC | FC | 2 | TRUE | TRUE | FALSE
6583 | MRT-XJ00-P2LBA-142000 | 2018-12-10 | MRT-DS-REC-TT-180887-FC | FC | 1 | TRUE | TRUE | FALSE
6584 | MRT-XG02-P2LAC-126003 | 2018-12-10 | MRT-DS-REC-TT-180906-FC | FC | 3 | TRUE | TRUE | FALSE
6585 | MRT-XG02-P3LAC-126003 | 2018-12-10 | MRT-DS-REC-TT-180906-FC | FC | 3 | TRUE | TRUE | FALSE
6586 | MRT-XG02-P2LAC-126053 | 2018-12-10 | MRT-DS-REC-TT-180906-FC | FC | 3 | TRUE | TRUE | FALSE
6587 | MRT-XG02-P3LAC-126053 | 2018-12-10 | MRT-DS-REC-TT-180906-FC | FC | 3 | TRUE | TRUE | FALSE
6588 | MRT-YQ01-P2LB-122085 | 2018-12-10 | MRT-DS-REC-TT-180892-FC | FC | 2 | TRUE | TRUE | FALSE
6589 | MRT-YQ01-P3LB-122085 | 2018-12-10 | MRT-DS-REC-TT-180892-FC | FC | 2 | TRUE | TRUE | FALSE
6590 | MRT-YD00-P2LB-122056 | 2018-12-10 | MRT-DS-REC-TT-180882-FC | FC | 3 | TRUE | TRUE | FALSE
6591 | MRT-YD00-P3LB-122056 | 2018-12-10 | MRT-DS-REC-TT-180882-FC | FC | 3 | TRUE | TRUE | FALSE
6592 | MRT-YL16-P2LB-122078 | 2018-12-10 | MRT-DS-REC-TT-180884-FC | FC | 2 | TRUE | TRUE | FALSE
6593 | MRT-YL16-P3LB-122078 | 2018-12-10 | MRT-DS-REC-TT-180884-FC | FC | 2 | TRUE | TRUE | FALSE
6594 | MRT-YT01-P2LCB-127033 | 2018-12-10 | MRT-DS-REC-TT-180874-FC | FC | 3 | TRUE | TRUE | FALSE
6595 | MRT-YD00-P2LCB-127031 | 2018-12-10 | MRT-DS-REC-TT-180923 | FC | 2 | TRUE | TRUE | FALSE
6596 | MRT-YM01-P2LCB-127039 | 2018-12-10 | MRT-DS-REC-TT-180923 | FC | 1 | TRUE | TRUE | FALSE
6597 | MRT-YL22-P2LCB-127042 | 2018-12-10 | MRT-DS-REC-TT-180923 | FC | 1 | TRUE | TRUE | FALSE
6598 | MRT-XG02-P2LCB-127032 | 2018-12-10 | MRT-DS-REC-TT-180923 | FC | 3 | TRUE | TRUE | FALSE
6599 | MRT-YK09-P2LCB-127034 | 2018-12-10 | MRT-DS-REC-TT-180923 | FC | 1 | TRUE | TRUE | FALSE
6600 | MRT-YD00-P3LCB-127031 | 2018-12-10 | MRT-DS-REC-TT-180923 | FC | 2 | TRUE | TRUE | FALSE
6601 | MRT-YM01-P3LCB-127039 | 2018-12-10 | MRT-DS-REC-TT-180923 | FC | 1 | TRUE | TRUE | FALSE
6602 | MRT-YL22-P3LCB-127042 | 2018-12-10 | MRT-DS-REC-TT-180923 | FC | 1 | TRUE | TRUE | FALSE
6603 | MRT-XG02-P3LCB-127032 | 2018-12-10 | MRT-DS-REC-TT-180923 | FC | 3 | TRUE | TRUE | FALSE
6604 | MRT-YK09-P3LCB-127034 | 2018-12-10 | MRT-DS-REC-TT-180923 | FC | 1 | TRUE | TRUE | FALSE
6605 | MRT-CA01-P0UGX-186764 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6606 | MRT-CA01-P0UGX-186766 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6607 | MRT-CA01-P0UGX-186763 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6608 | MRT-CA01-P0UGX-186765 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6609 | MRT-CA01-P0UGX-186767 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6610 | MRT-CA01-P0UGX-186768 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6611 | MRT-CA06-P0UGX-186725 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6612 | MRT-CA02-P0UGX-186770 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6613 | MRT-CA02-P0UGX-186771 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6614 | MRT-CA02-P0UGX-186772 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6615 | MRT-CA02-P0UGX-186773 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6616 | MRT-CA02-P0UGX-186778 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6617 | MRT-CA02-P0UGX-186779 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6618 | MRT-CA02-P0UGX-186774 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6619 | MRT-CA02-P0UGX-186775 | 2018-12-10 | MRT-HK-REC-TT-180364 | FA | 0 | TRUE | FALSE | FALSE
6620 | MRT-DN05-P2QC-130001 | 2018-12-10 | MRT-DS-REC-TT-180924 | FA | 0 | TRUE | FALSE | FALSE
6621 | MRT-DN05-P3QC-130001 | 2018-12-10 | MRT-DS-REC-TT-180924 | FA | 0 | TRUE | FALSE | FALSE
6622 | MRT-CQ02-P2QC-130036 | 2018-12-10 | MRT-DS-REC-TT-180925 | FI | 0 | TRUE | FALSE | FALSE
6623 | MRT-CQ02-P3QC-130036 | 2018-12-10 | MRT-DS-REC-TT-180925 | FI | 0 | TRUE | FALSE | FALSE
6624 | MRT-DD00-P0BAT-155108 | 2018-12-11 | MRT-HK-REC-TT-180365 | FI | 0 | TRUE | FALSE | FALSE
6625 | MRT-YT01-P3BBT-150524 | 2018-12-11 | MRT-HK-REC-TT-180366 | FA | 0 | TRUE | FALSE | FALSE
6626 | MRT-YT01-P2BBT-150519 | 2018-12-11 | MRT-HK-REC-TT-180366 | FA | 0 | TRUE | FALSE | FALSE
6665 | MRT-XG02-P2LB-122022 | 2018-12-13 | MRT-DS-REC-TT-180872-FC | FC | 6 | TRUE | TRUE | FALSE
6666 | MRT-XG02-P3LB-122022 | 2018-12-13 | MRT-DS-REC-TT-180872-FC | FC | 3 | TRUE | TRUE | FALSE
6667 | MRT-UE00-P2LB-122010 | 2018-12-13 | MRT-DS-REC-TT-180876-FC | FC | 3 | TRUE | TRUE | FALSE
6668 | MRT-UE00-P3LB-122010 | 2018-12-13 | MRT-DS-REC-TT-180876-FC | FC | 3 | TRUE | TRUE | FALSE
6669 | MRT-YV02-P3MKW-230001 | 2018-12-13 | MRT-DS-REC-TT-180878-FC | FC | 1 | TRUE | TRUE | FALSE
6670 | MRT-YV02-P3MKW-230002 | 2018-12-13 | MRT-DS-REC-TT-180878-FC | FC | 1 | TRUE | TRUE | FALSE
6671 | MRT-YD00-P2LB-122049 | 2018-12-13 | MRT-DS-REC-TT-180881-FC | FC | 3 | TRUE | TRUE | FALSE
6672 | MRT-YD00-P3LB-122049 | 2018-12-13 | MRT-DS-REC-TT-180881-FC | FC | 3 | TRUE | TRUE | FALSE
6673 | MRT-XG01-P2LB-122021 | 2018-12-13 | MRT-DS-REC-TT-180886-FC | FC | 1 | TRUE | TRUE | FALSE
6674 | MRT-XJ00-P2LB-122027 | 2018-12-13 | MRT-DS-REC-TT-180896-FC | FC | 1 | TRUE | TRUE | FALSE
6675 | MRT-XJ00-P3LB-122027 | 2018-12-13 | MRT-DS-REC-TT-180896-FC | FC | 1 | TRUE | TRUE | FALSE
6676 | MRT-XH01-P3UMA-143000 | 2018-12-13 | MRT-DS-REC-TT-180898-FC | FC | 1 | TRUE | TRUE | FALSE
6677 | MRT-DN05-P2QU-130001 | 2018-12-13 | MRT-DS-REC-TT-180900-FC | FC | 0 | TRUE | TRUE | FALSE
6678 | MRT-DN05-P3QU-130001 | 2018-12-13 | MRT-DS-REC-TT-180900-FC | FC | 0 | TRUE | TRUE | FALSE
6679 | MRT-YS01-P2MKC-230012 | 2018-12-13 | MRT-DS-REC-TT-180909-FC | FC | 2 | TRUE | TRUE | FALSE
6680 | MRT-YS01-P2MKC-230013 | 2018-12-13 | MRT-DS-REC-TT-180909-FC | FC | 2 | TRUE | TRUE | FALSE
6681 | MRT-YS01-P3MKC-230012 | 2018-12-13 | MRT-DS-REC-TT-180909-FC | FC | 2 | TRUE | TRUE | FALSE
6682 | MRT-YS01-P3MKC-230013 | 2018-12-13 | MRT-DS-REC-TT-180909-FC | FC | 2 | TRUE | TRUE | FALSE
6683 | MRT-YS01-P2MKC-230014 | 2018-12-13 | MRT-DS-REC-TT-180910-FC | FC | 3 | TRUE | TRUE | FALSE
6684 | MRT-YS01-P2MKC-230015 | 2018-12-13 | MRT-DS-REC-TT-180910-FC | FC | 2 | TRUE | TRUE | FALSE
6685 | MRT-YS01-P3MKC-230014 | 2018-12-13 | MRT-DS-REC-TT-180910-FC | FC | 3 | TRUE | TRUE | FALSE
6686 | MRT-YS01-P3MKC-230015 | 2018-12-13 | MRT-DS-REC-TT-180910-FC | FC | 2 | TRUE | TRUE | FALSE
6687 | MRT-YE00-P2LB-122116 | 2018-12-13 | MRT-DS-REC-TT-180915-FC | FC | 1 | TRUE | TRUE | FALSE
6688 | MRT-YE00-P3LB-122116 | 2018-12-13 | MRT-DS-REC-TT-180915-FC | FC | 1 | TRUE | TRUE | FALSE
7072 | MRT-DD00-P0BAT-155109 | 2018-12-13 | MRT-HK-REC-TT-180367 | FI | 0 | TRUE | FALSE | FALSE
6627 | MRT-CA00-P0UCA-180105 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 4 | TRUE | TRUE | FALSE
6628 | MRT-CA00-P0UCA-180106 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 4 | TRUE | TRUE | FALSE
6629 | MRT-CA00-P0UCA-180107 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 5 | TRUE | TRUE | FALSE
6630 | MRT-CA00-P0UCA-180108 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 5 | TRUE | TRUE | FALSE
6631 | MRT-CA00-P0UCA-180112 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 4 | TRUE | TRUE | FALSE
6632 | MRT-CA00-P0UCA-180113 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 5 | TRUE | TRUE | FALSE
6633 | MRT-CA00-P0UCA-180115 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 4 | TRUE | TRUE | FALSE
6634 | MRT-CA00-P0UCA-180117 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 4 | TRUE | TRUE | FALSE
6635 | MRT-CA00-P0UCA-180119 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 2 | TRUE | TRUE | FALSE
6636 | MRT-CA01-P0UCA-180122 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 6 | TRUE | TRUE | FALSE
6637 | MRT-CA01-P0UCA-180127 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 5 | TRUE | TRUE | FALSE
6638 | MRT-CA01-P0UCA-180128 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 5 | TRUE | TRUE | FALSE
6639 | MRT-CA03-P0UCA-180132 | 2018-12-14 | MRT-DS-REC-TT-180926 | FC | 4 | TRUE | TRUE | FALSE
6640 | MRT-YL16-P3AYA-160006 | 2018-12-14 | MRT-HK-REC-TT-180368 | FA | 0 | TRUE | FALSE | FALSE
6641 | MRT-CC02-P0UPC-176368 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6642 | MRT-CC02-P0UPC-176369 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6643 | MRT-CC03-P0UPC-176364 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6644 | MRT-CC03-P0UPC-176365 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6645 | MRT-CC03-P0UPC-176378 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6646 | MRT-CC03-P0UPC-176379 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6647 | MRT-CC03-P0UPC-176394 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6648 | MRT-CC03-P0UPC-176396 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6649 | MRT-CC03-P0UPC-176398 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6650 | MRT-CC03-P0UPC-176399 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6651 | MRT-CC03-P0UPC-176400 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6652 | MRT-CC03-P0UPC-176401 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6653 | MRT-CC03-P0UPC-176388 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6654 | MRT-CC03-P0UPC-176390 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6655 | MRT-CC03-P0UPC-176392 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6656 | MRT-CC03-P0UPC-176355 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6657 | MRT-CC03-P0UPC-176356 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6658 | MRT-CC03-P0UPC-176357 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6659 | MRT-CC03-P0UPC-176358 | 2018-12-14 | MRT-HK-REC-TT-180369 | FA | 0 | TRUE | FALSE | FALSE
6660 | MRT-CC02-P0ZEN-175005 | 2018-12-14 | MRT-HK-REC-TT-180370 | FA | 0 | TRUE | TRUE | FALSE
6661 | MRT-CC03-P0UPC-176370 | 2018-12-14 | MRT-HK-REC-TT-180370 | FA | 1 | TRUE | TRUE | FALSE
6662 | MRT-CC03-P0UPC-176371 | 2018-12-14 | MRT-HK-REC-TT-180370 | FA | 1 | TRUE | TRUE | FALSE
6663 | MRT-CC03-P0UPC-176374 | 2018-12-14 | MRT-HK-REC-TT-180370 | FA | 1 | TRUE | TRUE | FALSE
6664 | MRT-CC03-P0UPC-176375 | 2018-12-14 | MRT-HK-REC-TT-180370 | FA | 1 | TRUE | TRUE | FALSE
6689 | MRT-CA00-P0UGA-186626 | 2018-12-17 | MRT-HK-REC-TT-180371 | FA | 1 | TRUE | TRUE | FALSE
6690 | MRT-CA01-P0UGA-186654 | 2018-12-17 | MRT-HK-REC-TT-180371 | FA | 1 | TRUE | TRUE | FALSE
6691 | MRT-CA00-P0UGA-186611 | 2018-12-17 | MRT-HK-REC-TT-180371 | FA | 3 | TRUE | TRUE | FALSE
6692 | MRT-CA00-P0UGA-186613 | 2018-12-17 | MRT-HK-REC-TT-180371 | FA | 3 | TRUE | TRUE | FALSE
6693 | MRT-CA00-P0UGA-186616 | 2018-12-17 | MRT-HK-REC-TT-180371 | FA | 3 | TRUE | TRUE | FALSE
6694 | MRT-CA00-P0UGA-186617 | 2018-12-17 | MRT-HK-REC-TT-180371 | FA | 3 | TRUE | TRUE | FALSE
6695 | MRT-CA01-P0UGG-187262 | 2018-12-17 | MRT-HK-REC-TT-180371 | FA | 1 | TRUE | TRUE | FALSE
6696 | MRT-CA01-P0UGA-186659 | 2018-12-17 | MRT-HK-REC-TT-180371 | FA | 2 | TRUE | TRUE | FALSE
6697 | MRT-CA01-P0UGA-186658 | 2018-12-17 | MRT-HK-REC-TT-180371 | FA | 2 | TRUE | TRUE | FALSE
6698 | MRT-CA01-P0UGA-186655 | 2018-12-17 | MRT-HK-REC-TT-180371 | FA | 1 | TRUE | TRUE | FALSE
6699 | MRT-YT01-P0EKF-125610 | 2018-12-17 | MRT-HK-REC-TT-180372 | FA | 0 | TRUE | FALSE | FALSE
6700 | MRT-CC05-P0EKF-125613 | 2018-12-17 | MRT-HK-REC-TT-180372 | FA | 0 | TRUE | FALSE | FALSE
6701 | MRT-QM03-P0ZEN-155019 | 2018-12-17 | MRT-HK-REC-TT-180373 | FA | 0 | TRUE | FALSE | FALSE
6702 | MRT-CC02-P0UMA-171103 | 2018-12-18 | MRT-DS-REC-TT-180927 | FA | 0 | TRUE | FALSE | FALSE
6703 | MRT-VK02-P0UMA-171106 | 2018-12-18 | MRT-DS-REC-TT-180927 | FA | 0 | TRUE | FALSE | FALSE
6704 | MRT-YK10-P2MKA-230002 | 2018-12-18 | MRT-DS-REC-TT-180928 | FC | 1 | TRUE | TRUE | FALSE
6705 | MRT-YD00-P2MKA-220005 | 2018-12-18 | MRT-DS-REC-TT-180929 | FC | 1 | TRUE | TRUE | FALSE
6706 | MRT-QM03-P0ZEN-155012 | 2018-12-18 | MRT-HK-REC-TT-18374 | FA | 0 | TRUE | FALSE | FALSE
6707 | MRT-QM03-P0ZEN-155016 | 2018-12-18 | MRT-HK-REC-TT-180974 | FA | 0 | TRUE | FALSE | FALSE
6708 | MRT-QM03-P0ZEN-155014 | 2018-12-18 | MRT-HK-REC-TT-180974 | FA | 0 | TRUE | FALSE | FALSE
6709 | MRT-QM03-P0ZEN-155017 | 2018-12-18 | MRT-HK-REC-TT-180974 | FA | 0 | TRUE | FALSE | FALSE
6710 | MRT-QM03-P0ZEN-155015 | 2018-12-18 | MRT-HK-REC-TT-180974 | FA | 0 | TRUE | FALSE | FALSE
6711 | MRT-QM03-P0ZEN-155018 | 2018-12-18 | MRT-HK-REC-TT-180974 | FA | 0 | TRUE | FALSE | FALSE
6712 | MRT-XW03-P0PUR-150994 | 2018-12-18 | MRT-HK-REC-TT-180375 | FA | 0 | TRUE | FALSE | FALSE
6713 | MRT-XW03-P0PUR-150995 | 2018-12-18 | MRT-HK-REC-TT-180375 | FA | 0 | TRUE | FALSE | FALSE
6714 | MRT-YK09-P0PUR-150965 | 2018-12-18 | MRT-HK-REC-TT-180375 | FA | 0 | TRUE | FALSE | FALSE
6715 | MRT-YK09-P0PUR-150966 | 2018-12-18 | MRT-HK-REC-TT-180375 | FA | 0 | TRUE | FALSE | FALSE
6716 | MRT-YK09-P0PUR-150967 | 2018-12-18 | MRT-HK-REC-TT-180375 | FA | 0 | TRUE | FALSE | FALSE
6717 | MRT-YK09-P0PUR-150968 | 2018-12-18 | MRT-HK-REC-TT-180375 | FA | 0 | TRUE | FALSE | FALSE
6718 | MRT-US02-P0PUR-150996 | 2018-12-18 | MRT-HK-REC-TT-180375 | FA | 0 | TRUE | FALSE | FALSE
6719 | MRT-QM03-P0ZEN-155020 | 2018-12-18 | MRT-HK-REC-TT-180377 | FA | 0 | TRUE | FALSE | FALSE
6720 | MRT-CC02-P2UMA-170207 | 2018-12-19 | MRT-DS-REC-TT-180821-FC | FC | 4 | TRUE | TRUE | FALSE
6721 | MRT-CC02-P2UMA-170208 | 2018-12-19 | MRT-DS-REC-TT-180821-FC | FC | 4 | TRUE | TRUE | FALSE
6722 | MRT-YD00-P3MKG-220005 | 2018-12-19 | MRT-DS-REC-TT-180902-FC | FC | 2 | TRUE | TRUE | FALSE
6723 | MRT-XH01-P2LB-122112 | 2018-12-19 | MRT-DS-REC-TT-180919-FC | FC | 1 | TRUE | TRUE | FALSE
6724 | MRT-XH01-P3LB-122112 | 2018-12-19 | MRT-DS-REC-TT-180919-FC | FC | 1 | TRUE | TRUE | FALSE
6725 | MRT-DM02-P2MAA-220134 | 2018-12-19 | MRT-DS-REC-TT-180921-FC | FC | 0 | TRUE | TRUE | FALSE
6726 | MRT-DM02-P3MAA-220133 | 2018-12-19 | MRT-DS-REC-TT-180921-FC | FC | 0 | TRUE | TRUE | FALSE
6727 | MRT-CQ02-P2QC-130036 | 2018-12-19 | MRT-DS-REC-TT-180925-FC | FC | 0 | TRUE | TRUE | FALSE
6728 | MRT-CQ02-P3QC-130036 | 2018-12-19 | MRT-DS-REC-TT-180925-FC | FC | 0 | TRUE | TRUE | FALSE
6729 | MRT-CQ02-P2LAC-126038 | 2018-12-19 | MRT-DS-REC-TT-180911-FC | FC | 0 | TRUE | TRUE | FALSE
6730 | MRT-CQ02-P3LAC-126038 | 2018-12-19 | MRT-DS-REC-TT-180911-FC | FC | 0 | TRUE | TRUE | FALSE
6731 | MRT-CQ02-P2LAC-126086 | 2018-12-19 | MRT-DS-REC-TT-180911-FC | FC | 0 | TRUE | TRUE | FALSE
6732 | MRT-CQ02-P3LAC-126086 | 2018-12-19 | MRT-DS-REC-TT-180911-FC | FC | 0 | TRUE | TRUE | FALSE
6733 | MRT-YK08-P3PAH-604524 | 2018-12-19 | MRT-DS-REC-TT-180930 | FC | 5 | TRUE | TRUE | FALSE
6734 | MRT-DN02-P2H-830012 | 2018-12-19 | MRT-DS-REC-TT-180933 | FA | 0 | TRUE | FALSE | FALSE
6735 | MRT-XL00-P0ZEN-140002 | 2018-12-19 | MRT-DS-REC-TT-180932 | FC | 4 | TRUE | TRUE | FALSE
6736 | MRT-XN00-P0ZEN-140001 | 2018-12-19 | MRT-DS-REC-TT-180932 | FC | 4 | TRUE | TRUE | FALSE
6737 | MRT-CC02-P2UHA-170103 | 2018-12-19 | MRT-DS-REC-TT-180931 | FC | 8 | TRUE | TRUE | FALSE
6738 | MRT-CC02-P2UHA-170104 | 2018-12-19 | MRT-DS-REC-TT-180931 | FC | 6 | TRUE | TRUE | FALSE
6739 | MRT-VK02-P2UHA-170106 | 2018-12-19 | MRT-DS-REC-TT-180931 | FC | 7 | TRUE | TRUE | FALSE
6740 | MRT-CC02-P3UHA-170103 | 2018-12-19 | MRT-DS-REC-TT-180931 | FC | 8 | TRUE | TRUE | FALSE
6741 | MRT-CC02-P3UHA-170104 | 2018-12-19 | MRT-DS-REC-TT-180931 | FC | 6 | TRUE | TRUE | FALSE
6742 | MRT-VK02-P3UHA-170106 | 2018-12-19 | MRT-DS-REC-TT-180931 | FC | 7 | TRUE | TRUE | FALSE
6780 | MRT-CC02-P3UMA-170207 | 2018-12-19 | MRT-DS-REC-TT-180821-FC | FC | 4 | TRUE | TRUE | FALSE
6781 | MRT-CC02-P3UMA-170208 | 2018-12-19 | MRT-DS-REC-TT-180821-FC | FC | 4 | TRUE | TRUE | FALSE
10622 | MRT-YL08-P0MKG-125362 | 2018-12-19 | MRT-HK-REC-TT-180378 | FA | 1 | TRUE | FALSE | FALSE
6743 | MRT-YS01-P3BAA-150944 | 2018-12-20 | MRT-HK-REC-TT-180379 | FA | 0 | TRUE | FALSE | FALSE
6744 | MRT-YD00-P2LB-122114 | 2018-12-20 | MRT-DS-REC-TT-180935 | FA | 1 | TRUE | TRUE | FALSE
6745 | MRT-YD00-P3LB-122114 | 2018-12-20 | MRT-DS-REC-TT-180935 | FA | 1 | TRUE | TRUE | FALSE
6746 | MRT-CC05-P0ZEN-140001 | 2018-12-20 | MRT-DS-REC-TT-180934 | FA | 0 | TRUE | TRUE | FALSE
6747 | MRT-DE00-P0ZEN-140002 | 2018-12-20 | MRT-DS-REC-TT-180934 | FA | 0 | TRUE | TRUE | FALSE
6748 | MRT-CC07-P0ZEN-140001 | 2018-12-20 | MRT-DS-REC-TT-180934 | FA | 0 | TRUE | TRUE | FALSE
6749 | MRT-CN00-P2ZEN-110102 | 2018-12-21 | MRT-DS-REC-TT-180917-FC | FC | 0 | TRUE | TRUE | FALSE
6750 | MRT-CN00-P3ZEN-110102 | 2018-12-21 | MRT-DS-REC-TT-180917-FC | FC | 2 | TRUE | TRUE | FALSE
6751 | MRT-CA00-P0UCA-180105 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 4 | TRUE | TRUE | FALSE
6752 | MRT-CA00-P0UCA-180106 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 4 | TRUE | TRUE | FALSE
6753 | MRT-CA00-P0UCA-180107 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 5 | TRUE | TRUE | FALSE
6754 | MRT-CA00-P0UCA-180108 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 5 | TRUE | TRUE | FALSE
6755 | MRT-CA00-P0UCA-180112 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 4 | TRUE | TRUE | FALSE
6756 | MRT-CA00-P0UCA-180113 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 5 | TRUE | TRUE | FALSE
6757 | MRT-CA00-P0UCA-180115 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 4 | TRUE | TRUE | FALSE
6758 | MRT-CA00-P0UCA-180117 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 4 | TRUE | TRUE | FALSE
6759 | MRT-CA00-P0UCA-180119 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 2 | TRUE | TRUE | FALSE
6760 | MRT-CA01-P0UCA-180122 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 6 | TRUE | TRUE | FALSE
6761 | MRT-CA01-P0UCA-180127 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 5 | TRUE | TRUE | FALSE
6762 | MRT-CA01-P0UCA-180128 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 5 | TRUE | TRUE | FALSE
6763 | MRT-CA03-P0UCA-180132 | 2018-12-21 | MRT-DS-REC-TT-180926-FC | FC | 4 | TRUE | TRUE | FALSE
6764 | MRT-YK08-P3PAH-604524 | 2018-12-21 | MRT-DS-REC-TT-180930-FC | FC | 5 | TRUE | TRUE | FALSE
6765 | MRT-YF00-P3LB-122066 | 2018-12-21 | MRT-DS-REC-TT-180936 | FA | 0 | TRUE | FALSE | FALSE
6766 | MRT-DC04-P2LB-1111301 | 2018-12-21 | MRT-DS-REC-TT-180940 | FI | 0 | TRUE | FALSE | FALSE
6767 | MRT-DC04-P3LB-1111301 | 2018-12-21 | MRT-DS-REC-TT-180940 | FI | 0 | TRUE | FALSE | FALSE
6768 | MRT-XJ00-P2LAB-145000 | 2018-12-21 | MRT-DS-REC-TT-180938 | FI | 0 | TRUE | FALSE | FALSE
6769 | MRT-DE00-P0ZEN-140001 | 2018-12-21 | MRT-DS-REC-TT-180939 | FC | 3 | TRUE | TRUE | FALSE
6770 | MRT-CQ02-P2PAH-604105 | 2018-12-21 | MRT-DS-REC-TT-180937 | FI | 0 | TRUE | FALSE | FALSE
6771 | MRT-CQ02-P2PBB-604114 | 2018-12-21 | MRT-DS-REC-TT-180937 | FI | 0 | TRUE | FALSE | FALSE
6772 | MRT-CQ02-P2PAH-604505 | 2018-12-21 | MRT-DS-REC-TT-180937 | FI | 0 | TRUE | FALSE | FALSE
6773 | MRT-CQ02-P2PBB-604514 | 2018-12-21 | MRT-DS-REC-TT-180937 | FI | 0 | TRUE | FALSE | FALSE
6774 | MRT-VK02-P0UMA-171106 | 2018-12-24 | MRT-DS-REC-TT-180927-FC | FC | 0 | TRUE | TRUE | FALSE
6775 | MRT-CQ02-P2SM-128060 | 2018-12-24 | MRT-DS-REC-TT-180918-FC | FC | 0 | TRUE | TRUE | FALSE
6776 | MRT-CQ02-P3SM-128060 | 2018-12-24 | MRT-DS-REC-TT-180918-FC | FC | 0 | TRUE | TRUE | FALSE
6777 | MRT-YS01-P0BFB-150305 | 2018-12-24 | MRT-HK-REC-TT-180380 | FA | 0 | TRUE | TRUE | FALSE
6778 | MRT-YS01-P0BFB-150665 | 2018-12-24 | MRT-HK-REC-TT-180380 | FA | 0 | TRUE | TRUE | FALSE
6779 | MRT-CA05-P0UMA-180062 | 2018-12-24 | MRT-DS-REC-TT-180941 | FC | 5 | TRUE | TRUE | FALSE
8074 | MRT-DD00-P0BAT-155111 | 2018-12-28 | MRT-HK-REC-TT-180381 | FI | 0 | TRUE | FALSE | FALSE
6782 | MRT-YT01-P2GM-128502 | 2019-01-02 | MRT-DS-REC-TT-180943 | FC | 2 | TRUE | TRUE | FALSE
6783 | MRT-XB00-P2GM-128506 | 2019-01-02 | MRT-DS-REC-TT-180943 | FC | 1 | TRUE | TRUE | FALSE
6784 | MRT-XW01-P2GM-128507 | 2019-01-02 | MRT-DS-REC-TT-180943 | FC | 2 | TRUE | TRUE | FALSE
6785 | MRT-YD00-P2GM-128501 | 2019-01-02 | MRT-DS-REC-TT-180943 | FC | 2 | TRUE | TRUE | FALSE
6786 | MRT-YR05-P2GM-128511 | 2019-01-02 | MRT-DS-REC-TT-180943 | FC | 2 | TRUE | TRUE | FALSE
6787 | MRT-YT01-P3GM-128502 | 2019-01-02 | MRT-DS-REC-TT-180943 | FC | 2 | TRUE | TRUE | FALSE
6788 | MRT-XB00-P3GM-128506 | 2019-01-02 | MRT-DS-REC-TT-180943 | FC | 1 | TRUE | TRUE | FALSE
6789 | MRT-XW01-P3GM-128507 | 2019-01-02 | MRT-DS-REC-TT-180943 | FC | 2 | TRUE | TRUE | FALSE
6790 | MRT-YD00-P3GM-128501 | 2019-01-02 | MRT-DS-REC-TT-180943 | FC | 2 | TRUE | TRUE | FALSE
6791 | MRT-YR05-P3GM-128511 | 2019-01-02 | MRT-DS-REC-TT-180943 | FC | 2 | TRUE | TRUE | FALSE
6792 | MRT-DN05-P2QC-130001 | 2019-01-02 | MRT-DS-REC-TT-180924-FC | FC | 0 | TRUE | TRUE | FALSE
6793 | MRT-DN05-P3QC-130001 | 2019-01-02 | MRT-DS-REC-TT-180924-FC | FC | 0 | TRUE | TRUE | FALSE
6794 | MRT-CC05-P0ZEN-140001 | 2019-01-02 | MRT-DS-REC-TT-180934-FC | FC | 0 | TRUE | TRUE | FALSE
6795 | MRT-DE00-P0ZEN-140002 | 2019-01-02 | MRT-DS-REC-TT-180934-FC | FC | 0 | TRUE | TRUE | FALSE
6796 | MRT-CC07-P0ZEN-140001 | 2019-01-02 | MRT-DS-REC-TT-180934-FC | FC | 0 | TRUE | TRUE | FALSE
6797 | MRT-XK00-P2GM-128507 | 2019-01-02 | MRT-DS-REC-TT-180922-FC | FC | 3 | TRUE | TRUE | FALSE
6798 | MRT-XK00-P3GM-128507 | 2019-01-02 | MRT-DS-REC-TT-180922-FC | FC | 3 | TRUE | TRUE | FALSE
6799 | MRT-YD00-P2LCB-127031 | 2019-01-02 | MRT-DS-REC-TT-180923-FC | FC | 2 | TRUE | TRUE | FALSE
6800 | MRT-YM01-P2LCB-127039 | 2019-01-02 | MRT-DS-REC-TT-180923-FC | FC | 1 | TRUE | TRUE | FALSE
6801 | MRT-YL22-P2LCB-127042 | 2019-01-02 | MRT-DS-REC-TT-180923-FC | FC | 1 | TRUE | TRUE | FALSE
6802 | MRT-XG02-P2LCB-127032 | 2019-01-02 | MRT-DS-REC-TT-180923-FC | FC | 3 | TRUE | TRUE | FALSE
6803 | MRT-YK09-P2LCB-127034 | 2019-01-02 | MRT-DS-REC-TT-180923-FC | FC | 1 | TRUE | TRUE | FALSE
6804 | MRT-YD00-P3LCB-127031 | 2019-01-02 | MRT-DS-REC-TT-180923-FC | FC | 2 | TRUE | TRUE | FALSE
6805 | MRT-YM01-P3LCB-127039 | 2019-01-02 | MRT-DS-REC-TT-180923-FC | FC | 1 | TRUE | TRUE | FALSE
6806 | MRT-YL22-P3LCB-127042 | 2019-01-02 | MRT-DS-REC-TT-180923-FC | FC | 1 | TRUE | TRUE | FALSE
6807 | MRT-XG02-P3LCB-127032 | 2019-01-02 | MRT-DS-REC-TT-180923-FC | FC | 3 | TRUE | TRUE | FALSE
6808 | MRT-YK09-P3LCB-127034 | 2019-01-02 | MRT-DS-REC-TT-180923-FC | FC | 1 | TRUE | TRUE | FALSE
6809 | MRT-XJ00-P2LBG-142000 | 2019-01-02 | MRT-DS-REC-TT-180914-FC | FC | 1 | TRUE | TRUE | FALSE
6810 | MRT-XJ00-P2LAB-142000 | 2019-01-02 | MRT-DS-REC-TT-180914-FC | FC | 1 | TRUE | TRUE | FALSE
6811 | MRT-XJ00-P2LCA-142000 | 2019-01-02 | MRT-DS-REC-TT-180914-FC | FC | 1 | TRUE | TRUE | FALSE
6812 | MRT-XJ00-P2PGB-142000 | 2019-01-02 | MRT-DS-REC-TT-180914-FC | FC | 1 | TRUE | TRUE | FALSE
6813 | MRT-XJ00-P2LCM-142000 | 2019-01-02 | MRT-DS-REC-TT-180914-FC | FC | 1 | TRUE | TRUE | FALSE
6814 | MRT-CA05-P0UYX-145101 | 2019-01-02 | MRT-HK-REC-TT-180382 | FA | 1 | TRUE | TRUE | FALSE
6815 | MRT-CA05-P0UYX-145102 | 2019-01-02 | MRT-HK-REC-TT-180382 | FA | 1 | TRUE | TRUE | FALSE
6816 | MRT-CC02-P0UPC-175725 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 3 | TRUE | TRUE | FALSE
6817 | MRT-CC07-P0ULX-176215 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6818 | MRT-CA00-P0UVH-187060 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6819 | MRT-CA01-P0UVH-187082 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6820 | MRT-CC03-P0UPC-176352 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 1 | TRUE | TRUE | FALSE
6821 | MRT-CA03-P0UST-186950 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 2 | TRUE | TRUE | FALSE
6822 | MRT-CC02-P0ULX-176217 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6823 | MRT-CC02-P0ULX-176218 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6824 | MRT-CC02-P0ULX-176219 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6825 | MRT-CC02-P0ULX-176220 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6826 | MRT-CC02-P0ULX-176221 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6827 | MRT-CC02-P0ULX-176222 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6828 | MRT-CC02-P0ULX-176223 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6829 | MRT-CC02-P0ULX-176224 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6830 | MRT-CC02-P0ULX-176225 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6831 | MRT-CA00-P0UVH-187061 | 2019-01-02 | MRT-HK-REC-TT-180383 | FA | 0 | TRUE | TRUE | FALSE
6832 | MRT-CA06-P0UGX-186724 | 2019-01-02 | MRT-HK-REC-TT-180384 | FA | 0 | TRUE | TRUE | FALSE
6833 | MRT-CA01-P0UGX-186742 | 2019-01-02 | MRT-HK-REC-TT-180384 | FA | 1 | TRUE | TRUE | FALSE
6834 | MRT-CA03-P0UGX-186748 | 2019-01-02 | MRT-HK-REC-TT-180384 | FA | 1 | TRUE | TRUE | FALSE
6835 | MRT-CA03-P0UGX-186750 | 2019-01-02 | MRT-HK-REC-TT-180384 | FA | 1 | TRUE | TRUE | FALSE
6836 | MRT-CA03-P0UGX-186752 | 2019-01-02 | MRT-HK-REC-TT-180384 | FA | 1 | TRUE | TRUE | FALSE
6837 | MRT-CA03-P0UGX-186754 | 2019-01-02 | MRT-HK-REC-TT-180384 | FA | 1 | TRUE | TRUE | FALSE
6838 | MRT-CA03-P0UGX-186756 | 2019-01-02 | MRT-HK-REC-TT-180384 | FA | 1 | TRUE | TRUE | FALSE
6839 | MRT-CA01-P0UGX-186741 | 2019-01-02 | MRT-HK-REC-TT-180384 | FA | 1 | TRUE | TRUE | FALSE
6840 | MRT-CA03-P0UST-186936 | 2019-01-02 | MRT-HK-REC-TT-180385 | FA | 3 | TRUE | TRUE | FALSE
6841 | MRT-CA03-P0UST-186938 | 2019-01-02 | MRT-HK-REC-TT-180385 | FA | 3 | TRUE | TRUE | FALSE
6842 | MRT-CA03-P0UST-186937 | 2019-01-02 | MRT-HK-REC-TT-180385 | FA | 3 | TRUE | TRUE | FALSE
6843 | MRT-XG02-P3GC-135102 | 2019-01-02 | MRT-HK-REC-TT-180386 | FA | 4 | TRUE | TRUE | FALSE
6844 | MRT-DD02-P0SGA-135604 | 2019-01-02 | MRT-HK-REC-TT-180386 | FA | 0 | TRUE | TRUE | FALSE
6845 | MRT-DD02-P0SGA-135605 | 2019-01-02 | MRT-HK-REC-TT-180386 | FA | 0 | TRUE | TRUE | FALSE
6846 | MRT-DS00-P0SGA-135483 | 2019-01-02 | MRT-HK-REC-TT-180386 | FA | 0 | TRUE | TRUE | FALSE
6847 | MRT-FF01-P3SGA-135431 | 2019-01-02 | MRT-HK-REC-TT-180386 | FA | 0 | TRUE | TRUE | FALSE
6848 | MRT-YT01-P3GC-135126 | 2019-01-02 | MRT-HK-REC-TT-180387 | FA | 0 | TRUE | FALSE | FALSE
6849 | MRT-YT01-P3GC-135127 | 2019-01-02 | MRT-HK-REC-TT-180387 | FA | 0 | TRUE | FALSE | FALSE
6850 | MRT-YT01-P3GC-135125 | 2019-01-02 | MRT-HK-REC-TT-180387 | FA | 0 | TRUE | FALSE | FALSE
6851 | MRT-DM02-P2MAA-220165 | 2019-01-02 | MRT-DS-REC-TT-180920-FC | FC | 0 | TRUE | TRUE | FALSE
6852 | MRT-DM02-P2MAA-220166 | 2019-01-02 | MRT-DS-REC-TT-180920-FC | FC | 0 | TRUE | TRUE | FALSE
7619 | MRT-YF02-P2CJJ-240112 | 2019-01-02 | MRT-DS-REC-TT-180920-FC | FC | 0 | TRUE | TRUE | FALSE
6853 | MRT-CC02-P2UMA-170209 | 2019-01-03 | MRT-DS-REC-TT-190001 | FC | 3 | TRUE | TRUE | FALSE
6854 | MRT-VK02-P2UMA-170210 | 2019-01-03 | MRT-DS-REC-TT-190001 | FC | 3 | TRUE | TRUE | FALSE
6855 | MRT-CC02-P3UMA-170209 | 2019-01-03 | MRT-DS-REC-TT-190001 | FC | 3 | TRUE | TRUE | FALSE
6856 | MRT-VK02-P3UMA-170210 | 2019-01-03 | MRT-DS-REC-TT-190001 | FC | 3 | TRUE | TRUE | FALSE
6857 | MRT-YK10-P2MKA-230002 | 2019-01-03 | MRT-DS-REC-TT-180928-FC | FC | 1 | TRUE | TRUE | FALSE
6858 | MRT-YD00-P2MKA-220005 | 2019-01-03 | MRT-DS-REC-TT-180929-FC | FC | 1 | TRUE | TRUE | FALSE
6859 | MRT-CC07-P0UPC-175701 | 2019-01-03 | MRT-HK-REC-TT-190388 | FA | 3 | TRUE | TRUE | FALSE
6860 | MRT-CC02-P0UPC-175705 | 2019-01-03 | MRT-HK-REC-TT-190388 | FA | 5 | TRUE | TRUE | FALSE
6861 | MRT-VL00-P2MAA-220079 | 2019-01-04 | MRT-DS-REC-TT-190003 | FI | 0 | TRUE | TRUE | FALSE
6862 | MRT-VL00-P2MAA-220001 | 2019-01-04 | MRT-DS-REC-TT-190003 | FI | 1 | TRUE | TRUE | FALSE
6863 | MRT-VL00-P2MAA-220009 | 2019-01-04 | MRT-DS-REC-TT-190003 | FI | 1 | TRUE | TRUE | FALSE
6864 | MRT-VL00-P2MAA-220010 | 2019-01-04 | MRT-DS-REC-TT-190003 | FI | 1 | TRUE | TRUE | FALSE
6865 | MRT-XT00-P2MAA-220002 | 2019-01-04 | MRT-DS-REC-TT-190003 | FI | 1 | TRUE | TRUE | FALSE
8062 | MRT-DN04-P0EKF-125607 | 2019-01-04 | MRT-HK-REC-TT-190390 | FA | 0 | TRUE | FALSE | FALSE
8063 | MRT-DS05-P0EKF-125621 | 2019-01-04 | MRT-HK-REC-TT-190390 | FA | 0 | TRUE | FALSE | FALSE
8086 | MRT-QA00-P0GDG-135077 | 2019-01-04 | MRT-HK-REC-TT-180389 | FA | 0 | TRUE | FALSE | FALSE
8087 | MRT-QA00-P0GDG-135078 | 2019-01-04 | MRT-HK-REC-TT-180389 | FA | 0 | TRUE | FALSE | FALSE
6866 | MRT-VL00-P2MAA-220001 | 2019-01-07 | MRT-DS-REC-TT-190003-FC | FC | 1 | TRUE | TRUE | FALSE
6867 | MRT-VL00-P2MAA-220009 | 2019-01-07 | MRT-DS-REC-TT-190003-FC | FC | 1 | TRUE | TRUE | FALSE
6868 | MRT-VL00-P2MAA-220010 | 2019-01-07 | MRT-DS-REC-TT-190003-FC | FC | 1 | TRUE | TRUE | FALSE
6869 | MRT-XT00-P2MAA-220002 | 2019-01-07 | MRT-DS-REC-TT-190003-FC | FC | 1 | TRUE | TRUE | FALSE
6870 | MRT-VL00-P2MAA-220079 | 2019-01-07 | MRT-DS-REC-TT-190003-FC | FC | 0 | TRUE | TRUE | FALSE
6871 | MRT-CA00-P0UMA-180009 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 4 | TRUE | TRUE | FALSE
6872 | MRT-CA00-P0UMA-180010 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 4 | TRUE | TRUE | FALSE
6873 | MRT-CA00-P0UMA-180011 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 4 | TRUE | TRUE | FALSE
6874 | MRT-CA00-P0UMA-180013 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 4 | TRUE | TRUE | FALSE
6875 | MRT-CA00-P0UMA-180014 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 4 | TRUE | TRUE | FALSE
6876 | MRT-CA00-P0UMA-180015 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 4 | TRUE | TRUE | FALSE
6877 | MRT-CA00-P0UMA-180016 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 4 | TRUE | TRUE | FALSE
6878 | MRT-CA00-P0UMA-180017 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 4 | TRUE | TRUE | FALSE
6879 | MRT-CA00-P0UMA-180019 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 4 | TRUE | TRUE | FALSE
6880 | MRT-CA00-P0UMA-180021 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 4 | TRUE | TRUE | FALSE
6881 | MRT-CA00-P0UMA-180022 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 4 | TRUE | TRUE | FALSE
6882 | MRT-CA00-P0UMA-180023 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 2 | TRUE | TRUE | FALSE
6883 | MRT-CA00-P0UMA-180008 | 2019-01-07 | MRT-DS-REC-TT-190004 | FC | 4 | TRUE | TRUE | FALSE
6884 | MRT-CH04-P3BAA-150947 | 2019-01-07 | MRT-HK-REC-TT-190391 | FA | 0 | TRUE | FALSE | FALSE
6885 | MRT-CH04-P0BBB-150533 | 2019-01-07 | MRT-HK-REC-TT-190391 | FA | 0 | TRUE | FALSE | FALSE
6886 | MRT-XP00-P3BAC-150415 | 2019-01-07 | MRT-HK-REC-TT-190391 | FA | 0 | TRUE | FALSE | FALSE
6887 | MRT-YD00-P0BTA-150630 | 2019-01-07 | MRT-HK-REC-TT-190391 | FA | 0 | TRUE | FALSE | FALSE
6888 | MRT-YT01-P0BTA-150631 | 2019-01-07 | MRT-HK-REC-TT-190391 | FA | 0 | TRUE | FALSE | FALSE
6889 | MRT-VL00-P3MAA-220001 | 2019-01-07 | MRT-DS-REC-TT-190005 | FI | 1 | TRUE | TRUE | FALSE
6890 | MRT-VL00-P3MAA-220009 | 2019-01-07 | MRT-DS-REC-TT-190005 | FI | 1 | TRUE | TRUE | FALSE
6891 | MRT-XT00-P3MAA-220002 | 2019-01-07 | MRT-DS-REC-TT-190005 | FI | 1 | TRUE | TRUE | FALSE
6892 | MRT-VL00-P3MAA-220010 | 2019-01-07 | MRT-DS-REC-TT-190005 | FI | 1 | TRUE | TRUE | FALSE
8089 | MRT-YT01-P0GN-135229 | 2019-01-07 | MRT-HK-REC-TT-180392 | FA | 0 | TRUE | FALSE | FALSE
8090 | MRT-YT01-P0GN-135230 | 2019-01-07 | MRT-HK-REC-TT-180392 | FA | 0 | TRUE | FALSE | FALSE
8091 | MRT-YT01-P0GN-135231 | 2019-01-07 | MRT-HK-REC-TT-180392 | FA | 0 | TRUE | FALSE | FALSE
6901 | MRT-CC02-P0UMA-171103 | 2019-01-08 | MRT-DS-REC-TT-190006 | FA | 1 | TRUE | TRUE | FALSE
6911 | MRT-YD00-P0UCB-150302 | 2019-01-08 | MRT-HK-REC-TT-190394 | FA | 0 | TRUE | FALSE | FALSE
6912 | MRT-UBL-P0BBB-150454 | 2019-01-08 | MRT-HK-REC-TT-190393 | FA | 0 | TRUE | FALSE | FALSE
6913 | MRT-UBL-P0BBB-150548 | 2019-01-08 | MRT-HK-REC-TT-190393 | FA | 0 | TRUE | FALSE | FALSE
6914 | MRT-UBL-P0BBB-150551 | 2019-01-08 | MRT-HK-REC-TT-190393 | FA | 0 | TRUE | FALSE | FALSE
6915 | MRT-UBL-P0BBB-150554 | 2019-01-08 | MRT-HK-REC-TT-190393 | FA | 0 | TRUE | FALSE | FALSE
6916 | MRT-UBL-P2BBB-150539 | 2019-01-08 | MRT-HK-REC-TT-190393 | FA | 0 | TRUE | FALSE | FALSE
6917 | MRT-UBL-P3BBB-150542 | 2019-01-08 | MRT-HK-REC-TT-190393 | FA | 0 | TRUE | FALSE | FALSE
6918 | MRT-YM02-P3BAA-150941 | 2019-01-08 | MRT-HK-REC-TT-190393 | FA | 0 | TRUE | FALSE | FALSE
6919 | MRT-YD00-P0BFT-150590 | 2019-01-08 | MRT-HK-REC-TT-190393 | FA | 0 | TRUE | FALSE | FALSE
6920 | MRT-YT01-P0BFT-150588 | 2019-01-08 | MRT-HK-REC-TT-190393 | FA | 0 | TRUE | FALSE | FALSE
6921 | MRT-YT01-P0BFT-150596 | 2019-01-08 | MRT-HK-REC-TT-190393 | FA | 0 | TRUE | FALSE | FALSE
6922 | MRT-YF01-P0BFB-150116 | 2019-01-08 | MRT-HK-REC-TT-190393 | FA | 0 | TRUE | FALSE | FALSE
8073 | MRT-DD02-P0ABA-155107 | 2019-01-08 | MRT-HK-REC-TT-190395 | FI | 0 | TRUE | FALSE | FALSE
6923 | MRT-YF00-P2SCA-127518 | 2019-01-09 | MRT-DS-REC-TT-190002 | FC | 2 | TRUE | TRUE | FALSE
6924 | MRT-YF00-P3SCA-127518 | 2019-01-09 | MRT-DS-REC-TT-190002 | FC | 2 | TRUE | TRUE | FALSE
6925 | MRT-YF02-P3CJJ-240104 | 2019-01-09 | MRT-DS-REC-TT-190007 | FI | 0 | TRUE | TRUE | FALSE
6926 | MRT-YD00-P2CJA-240057 | 2019-01-09 | MRT-DS-REC-TT-190007 | FI | 1 | TRUE | TRUE | FALSE
6927 | MRT-YD00-P2CJA-240058 | 2019-01-09 | MRT-DS-REC-TT-190007 | FI | 1 | TRUE | TRUE | FALSE
6928 | MRT-YD00-P2CJA-240059 | 2019-01-09 | MRT-DS-REC-TT-190007 | FI | 1 | TRUE | TRUE | FALSE
6929 | MRT-YD00-P3CJA-240057 | 2019-01-09 | MRT-DS-REC-TT-190007 | FI | 1 | TRUE | TRUE | FALSE
6930 | MRT-YD00-P3CJA-240058 | 2019-01-09 | MRT-DS-REC-TT-190007 | FI | 1 | TRUE | TRUE | FALSE
6931 | MRT-YD00-P3CJA-240059 | 2019-01-09 | MRT-DS-REC-TT-190007 | FI | 1 | TRUE | TRUE | FALSE
6932 | MRT-QM03-P3CYP-160050 | 2019-01-09 | MRT-HK-REC-TT-190396 | FA | 0 | TRUE | FALSE | FALSE
6933 | MRT-CA05-P0UMA-180062 | 2019-01-09 | MRT-DS-REC-TT-180941-FC | FC | 5 | TRUE | TRUE | FALSE
6934 | MRT-CV05-P0BTA-150636 | 2019-01-09 | MRT-HK-REC-TT-190397 | FA | 0 | TRUE | FALSE | FALSE
6935 | MRT-CV05-P0BTL-150640 | 2019-01-09 | MRT-HK-REC-TT-190397 | FA | 0 | TRUE | FALSE | FALSE
6936 | MRT-YD00-P0QHB-125431 | 2019-01-09 | MRT-HK-REC-TT-190398 | FA | 0 | TRUE | FALSE | FALSE
6937 | MRT-XT00-P3MAA-220208 | 2019-01-10 | MRT-DS-REC-TT-190009 | FI | 0 | TRUE | FALSE | FALSE
6938 | MRT-XT00-P2MAA-220208 | 2019-01-10 | MRT-DS-REC-TT-190009 | FI | 0 | TRUE | FALSE | FALSE
6939 | MRT-CC02-P2UMA-170209 | 2019-01-10 | MRT-DS-REC-TT-190001-FC | FC | 3 | TRUE | TRUE | FALSE
6940 | MRT-VK02-P2UMA-170210 | 2019-01-10 | MRT-DS-REC-TT-190001-FC | FC | 3 | TRUE | TRUE | FALSE
6941 | MRT-CC02-P3UMA-170209 | 2019-01-10 | MRT-DS-REC-TT-190001-FC | FC | 3 | TRUE | TRUE | FALSE
6942 | MRT-VK02-P3UMA-170210 | 2019-01-10 | MRT-DS-REC-TT-190001-FC | FC | 3 | TRUE | TRUE | FALSE
6943 | MRT-YU04-P2LB-111105 | 2019-01-10 | MRT-DS-REC-TT-180888-FC | FC | 0 | TRUE | TRUE | FALSE
6944 | MRT-YV02-P2LB-111106 | 2019-01-10 | MRT-DS-REC-TT-180888-FC | FC | 0 | TRUE | TRUE | FALSE
6945 | MRT-YU04-P3LB-111105 | 2019-01-10 | MRT-DS-REC-TT-180888-FC | FC | 0 | TRUE | TRUE | FALSE
6946 | MRT-YV02-P3LB-111106 | 2019-01-10 | MRT-DS-REC-TT-180888-FC | FC | 0 | TRUE | TRUE | FALSE
6947 | MRT-YT01-P2GM-128502 | 2019-01-10 | MRT-DS-REC-TT-180943-FC | FC | 2 | TRUE | TRUE | FALSE
6948 | MRT-XB00-P2GM-128506 | 2019-01-10 | MRT-DS-REC-TT-180943-FC | FC | 1 | TRUE | TRUE | FALSE
6949 | MRT-XW01-P2GM-128507 | 2019-01-10 | MRT-DS-REC-TT-180943-FC | FC | 2 | TRUE | TRUE | FALSE
6950 | MRT-YD00-P2GM-128501 | 2019-01-10 | MRT-DS-REC-TT-180943-FC | FC | 2 | TRUE | TRUE | FALSE
6951 | MRT-YR05-P2GM-128511 | 2019-01-10 | MRT-DS-REC-TT-180943-FC | FC | 2 | TRUE | TRUE | FALSE
6952 | MRT-YT01-P3GM-128502 | 2019-01-10 | MRT-DS-REC-TT-180943-FC | FC | 2 | TRUE | TRUE | FALSE
6953 | MRT-XB00-P3GM-128506 | 2019-01-10 | MRT-DS-REC-TT-180943-FC | FC | 1 | TRUE | TRUE | FALSE
6954 | MRT-XW01-P3GM-128507 | 2019-01-10 | MRT-DS-REC-TT-180943-FC | FC | 2 | TRUE | TRUE | FALSE
6955 | MRT-YD00-P3GM-128501 | 2019-01-10 | MRT-DS-REC-TT-180943-FC | FC | 2 | TRUE | TRUE | FALSE
6956 | MRT-YR05-P3GM-128511 | 2019-01-10 | MRT-DS-REC-TT-180943-FC | FC | 2 | TRUE | TRUE | FALSE
6957 | MRT-FF00-P0SGA-135463 | 2019-01-11 | MRT-HK-REC-TT-190399 | FA | 0 | TRUE | FALSE | FALSE
6958 | MRT-YF00-P2SCA-127518 | 2019-01-11 | MRT-DS-REC-TT-190002-FC | FC | 2 | TRUE | TRUE | FALSE
6959 | MRT-YF00-P3SCA-127518 | 2019-01-11 | MRT-DS-REC-TT-190002-FC | FC | 2 | TRUE | TRUE | FALSE
6960 | MRT-XT00-P2MAA-220208 | 2019-01-11 | MRT-DS-REC-TT-190009-FC | FC | 0 | TRUE | TRUE | FALSE
6961 | MRT-XT00-P3MAA-220208 | 2019-01-11 | MRT-DS-REC-TT-190009-FC | FC | 0 | TRUE | TRUE | FALSE
6962 | MRT-XW03-P0BAA-150018 | 2019-01-11 | MRT-HK-REC-TT-190400 | FA | 1 | TRUE | TRUE | FALSE
6963 | MRT-XW03-P0BAA-150019 | 2019-01-11 | MRT-HK-REC-TT-190400 | FA | 1 | TRUE | TRUE | FALSE
6964 | MRT-XW03-P0BAA-150020 | 2019-01-11 | MRT-HK-REC-TT-190400 | FA | 1 | TRUE | TRUE | FALSE
6965 | MRT-QM01-P0ZEN-135006 | 2019-01-11 | MRT-HK-REC-TT-190402 | FA | 0 | TRUE | FALSE | FALSE
6966 | MRT-QM03-P0ZEN-135007 | 2019-01-11 | MRT-HK-REC-TT-190402 | FA | 0 | TRUE | FALSE | FALSE
6967 | MRT-XK00-P0GN-135298 | 2019-01-11 | MRT-HK-REC-TT-190402 | FA | 0 | TRUE | FALSE | FALSE
6968 | MRT-YR05-P0GEN-135375 | 2019-01-11 | MRT-HK-REC-TT-190403 | FA | 0 | TRUE | FALSE | FALSE
6969 | MRT-YR05-P0GEN-135374 | 2019-01-11 | MRT-HK-REC-TT-190403 | FA | 0 | TRUE | FALSE | FALSE
6970 | MRT-YT01-P0GEN-135335 | 2019-01-11 | MRT-HK-REC-TT-190403 | FA | 0 | TRUE | FALSE | FALSE
6971 | MRT-YT01-P0GEN-135332 | 2019-01-11 | MRT-HK-REC-TT-190403 | FA | 0 | TRUE | FALSE | FALSE
6972 | MRT-YT01-P0GEN-135333 | 2019-01-11 | MRT-HK-REC-TT-190403 | FA | 0 | TRUE | FALSE | FALSE
6973 | MRT-DD03-P0GEN-135386 | 2019-01-11 | MRT-HK-REC-TT-190404 | FA | 0 | TRUE | FALSE | FALSE
6974 | MRT-XA00-P0GEN-135324 | 2019-01-11 | MRT-HK-REC-TT-190404 | FA | 0 | TRUE | FALSE | FALSE
6975 | MRT-YT01-P0GEN-135356 | 2019-01-11 | MRT-HK-REC-TT-190404 | FA | 0 | TRUE | FALSE | FALSE
6976 | MRT-YT01-P0GEN-135361 | 2019-01-11 | MRT-HK-REC-TT-190404 | FA | 0 | TRUE | FALSE | FALSE
6977 | MRT-YE00-P2MKA-230002 | 2019-01-11 | MRT-DS-REC-TT-190010 | FC | 3 | TRUE | TRUE | FALSE
6978 | MRT-YE00-P3MKA-230002 | 2019-01-11 | MRT-DS-REC-TT-190010 | FC | 3 | TRUE | TRUE | FALSE
6979 | MRT-XG02-P0GN-135202 | 2019-01-14 | MRT-HK-REC-TT-190406 | FA | 5 | TRUE | TRUE | FALSE
6980 | MRT-VL00-P3MAA-220001 | 2019-01-14 | MRT-DS-REC-TT-190005-FC | FC | 1 | TRUE | TRUE | FALSE
6981 | MRT-VL00-P3MAA-220009 | 2019-01-14 | MRT-DS-REC-TT-190005-FC | FC | 1 | TRUE | TRUE | FALSE
6982 | MRT-XT00-P3MAA-220002 | 2019-01-14 | MRT-DS-REC-TT-190005-FC | FC | 1 | TRUE | TRUE | FALSE
6983 | MRT-VL00-P3MAA-220010 | 2019-01-14 | MRT-DS-REC-TT-190005-FC | FC | 1 | TRUE | TRUE | FALSE
6984 | MRT-DE00-P0ZEN-140001 | 2019-01-14 | MRT-DS-REC-TT-180939-FC | FC | 3 | TRUE | TRUE | FALSE
6985 | MRT-DC04-P2LB-1111301 | 2019-01-14 | MRT-DS-REC-TT-180940-FC | FC | 0 | TRUE | TRUE | FALSE
6986 | MRT-DC04-P3LB-1111301 | 2019-01-14 | MRT-DS-REC-TT-180940-FC | FC | 0 | TRUE | TRUE | FALSE
6987 | MRT-XG02-P0GHD-120001 | 2019-01-14 | MRT-DS-REC-TT-190012 | FC | 5 | TRUE | TRUE | FALSE
6988 | MRT-YD00-P2LAC-126049 | 2019-01-14 | MRT-DS-REC-TT-190008 | FC | 3 | TRUE | TRUE | FALSE
6989 | MRT-YD00-P3LAC-126049 | 2019-01-14 | MRT-DS-REC-TT-190008 | FC | 3 | TRUE | TRUE | FALSE
6990 | MRT-YD00-P2LAC-126050 | 2019-01-14 | MRT-DS-REC-TT-190008 | FC | 3 | TRUE | TRUE | FALSE
6991 | MRT-YD00-P3LAC-126050 | 2019-01-14 | MRT-DS-REC-TT-190008 | FC | 3 | TRUE | TRUE | FALSE
6992 | MRT-XG02-P0MKG-125312 | 2019-01-14 | MRT-HK-REC-TT-190405 | FA | 2 | TRUE | TRUE | FALSE
6993 | MRT-YE16-P0USG-150141 | 2019-01-15 | MRT-HK-REC-TT-190407 | FA | 0 | TRUE | FALSE | FALSE
6994 | MRT-YE16-P0BJQ-150143 | 2019-01-15 | MRT-HK-REC-TT-190407 | FA | 0 | TRUE | FALSE | FALSE
6995 | MRT-YE16-P0GQA-150144 | 2019-01-15 | MRT-HK-REC-TT-190407 | FA | 0 | TRUE | FALSE | FALSE
6996 | MRT-YE16-P3UTH-150146 | 2019-01-15 | MRT-HK-REC-TT-190407 | FA | 0 | TRUE | FALSE | FALSE
6997 | MRT-YT01-P3AYA-160009 | 2019-01-15 | MRT-HK-REC-TT-190407 | FA | 0 | TRUE | FALSE | FALSE
6998 | MRT-CA06-P0UXA-186664 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
6999 | MRT-CA00-P0UXA-186670 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 1 | TRUE | TRUE | FALSE
7000 | MRT-CA00-P0UXA-186682 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7001 | MRT-CA00-P0UXA-186684 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 1 | TRUE | TRUE | FALSE
7002 | MRT-CA00-P0UXA-186686 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7003 | MRT-CA01-P0UXA-186688 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7004 | MRT-CA01-P0UXA-186690 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7005 | MRT-CA01-P0UXA-186692 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7006 | MRT-CA02-P0UXA-186694 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7007 | MRT-CA03-P0UXA-186696 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7008 | MRT-CA03-P0UXA-186698 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7009 | MRT-CA03-P0UXA-186700 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7010 | MRT-CA03-P0UXA-186689 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7011 | MRT-CA03-P0UXA-186687 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7012 | MRT-CA00-P0UXA-186671 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 1 | TRUE | TRUE | FALSE
7013 | MRT-CA00-P0UXA-186672 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 1 | TRUE | TRUE | FALSE
7014 | MRT-CA00-P0UXA-186673 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 1 | TRUE | TRUE | FALSE
7015 | MRT-CA00-P0UXA-186674 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 1 | TRUE | TRUE | FALSE
7016 | MRT-CA01-P0UXA-186683 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7017 | MRT-CA01-P0UXA-186685 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7018 | MRT-CA03-P0UXA-186693 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7019 | MRT-CA03-P0UXA-186701 | 2019-01-15 | MRT-HK-REC-TT-190408 | FA | 0 | TRUE | TRUE | FALSE
7020 | MRT-CA00-P0UYX-187156 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 2 | TRUE | TRUE | FALSE
7021 | MRT-CA00-P0UYX-187158 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 2 | TRUE | TRUE | FALSE
7022 | MRT-CA00-P0UYX-187160 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 0 | TRUE | TRUE | FALSE
7023 | MRT-CA01-P0UYX-187164 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 2 | TRUE | TRUE | FALSE
7024 | MRT-CA01-P0UYX-187170 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 2 | TRUE | TRUE | FALSE
7025 | MRT-CA01-P0UYX-187172 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 2 | TRUE | TRUE | FALSE
7026 | MRT-CA01-P0UYX-187173 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 0 | TRUE | TRUE | FALSE
7027 | MRT-CA00-P0UYX-187159 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 2 | TRUE | TRUE | FALSE
7028 | MRT-CA00-P0UYX-187184 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 2 | TRUE | TRUE | FALSE
7029 | MRT-CA00-P0UYX-187157 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 2 | TRUE | TRUE | FALSE
7030 | MRT-CA01-P0UYX-187186 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 2 | TRUE | TRUE | FALSE
7031 | MRT-CA01-P0UYX-187187 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 2 | TRUE | TRUE | FALSE
7032 | MRT-CA00-P0UYX-187161 | 2019-01-15 | MRT-HK-REC-TT-190409 | FA | 0 | TRUE | TRUE | FALSE
7033 | MRT-YD00-P2BBT-150425 | 2019-01-15 | MRT-HK-REC-TT-190410 | FA | 0 | TRUE | FALSE | FALSE
7034 | MRT-YD00-P3BBT-150442 | 2019-01-15 | MRT-HK-REC-TT-190410 | FA | 0 | TRUE | FALSE | FALSE
7035 | MRT-YV02-P2BBT-150426 | 2019-01-15 | MRT-HK-REC-TT-190410 | FA | 0 | TRUE | FALSE | FALSE
7036 | MRT-YV02-P3BBT-150443 | 2019-01-15 | MRT-HK-REC-TT-190410 | FA | 0 | TRUE | FALSE | FALSE
7942 | MRT-CA02-P0UVH-187080 | 2019-01-15 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7037 | MRT-CM02-P2MKA-220001 | 2019-01-16 | MRT-DS-REC-TT-190013 | FI | 0 | TRUE | FALSE | FALSE
7038 | MRT-CM02-P3MKA-220001 | 2019-01-16 | MRT-DS-REC-TT-190013 | FI | 0 | TRUE | FALSE | FALSE
7039 | MRT-YK09-P2MKC-230003 | 2019-01-16 | MRT-DS-REC-TT-190011 | FC | 2 | TRUE | TRUE | FALSE
7040 | MRT-YK09-P3MKC-230003 | 2019-01-16 | MRT-DS-REC-TT-190011 | FC | 2 | TRUE | TRUE | FALSE
7041 | MRT-YT10-P2MKC-230016 | 2019-01-16 | MRT-DS-REC-TT-190014 | FA | 0 | TRUE | FALSE | FALSE
7042 | MRT-YT10-P3MKC-230016 | 2019-01-16 | MRT-DS-REC-TT-190014 | FA | 0 | TRUE | FALSE | FALSE
7043 | MRT-YD00-P0UZT-150655 | 2019-01-16 | MRT-HK-REC-TT-190411 | FA | 0 | TRUE | FALSE | FALSE
7044 | MRT-CA06-P0UVH-187054 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7045 | MRT-CA00-P0UVH-187056 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7046 | MRT-CA00-P0UVH-187058 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7047 | MRT-CA00-P0UVH-187060 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7048 | MRT-CA00-P0UVH-187062 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7049 | MRT-CA01-P0UVH-187066 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7050 | MRT-CA02-P0UVH-187068 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7051 | MRT-CA01-P0UVH-187070 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7052 | MRT-CA01-P0UVH-187082 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7053 | MRT-CA06-P0UMX-187204 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7054 | MRT-CA01-P0UMX-187214 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 3 | TRUE | TRUE | FALSE
7055 | MRT-CA02-P0UMX-187220 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 3 | TRUE | TRUE | FALSE
7056 | MRT-CA03-P0UMX-187222 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 3 | TRUE | TRUE | FALSE
7057 | MRT-CA00-P0UAB-187318 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 2 | TRUE | TRUE | FALSE
7058 | MRT-CA00-P0UAB-187320 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 2 | TRUE | TRUE | FALSE
7059 | MRT-CA00-P0UVH-187059 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7060 | MRT-CA00-P0UVH-187086 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7061 | MRT-CA01-P0UVH-187088 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7062 | MRT-CA02-P0UAB-187340 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7063 | MRT-CA00-P0UVH-187061 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 1 | TRUE | TRUE | FALSE
7064 | MRT-CA01-P0UMX-187215 | 2019-01-16 | MRT-HK-REC-TT-190412 | FA | 0 | TRUE | TRUE | FALSE
7065 | MRT-DD01-P0ZEN-175014 | 2019-01-16 | MRT-HK-REC-TT-190413 | FA | 0 | TRUE | FALSE | FALSE
7066 | MRT-DD01-P0ZEN-175015 | 2019-01-16 | MRT-HK-REC-TT-190415 | FA | 0 | TRUE | FALSE | FALSE
7067 | MRT-CA00-P3AY-160012 | 2019-01-17 | MRT-HK-REC-TT-190416 | FA | 1 | TRUE | TRUE | FALSE
7068 | MRT-BT00-P2PAC-130001 | 2019-01-17 | MRT-HK-REC-TT-190417 | FA | 0 | TRUE | FALSE | FALSE
7069 | MRT-YT01-P0GEN-135326 | 2019-01-17 | MRT-HK-REC-TT-190417 | FA | 0 | TRUE | FALSE | FALSE
7070 | MRT-CA05-P0UVH-145108 | 2019-01-18 | MRT-HK-REC-TT-190418 | FA | 0 | TRUE | FALSE | FALSE
7071 | MRT-CA05-P0UVH-145109 | 2019-01-18 | MRT-HK-REC-TT-190418 | FA | 0 | TRUE | FALSE | FALSE
7073 | MRT-DN02-P2PAH-830015 | 2019-01-18 | MRT-DS-REC-TT-180820-FC | FC | 0 | TRUE | TRUE | FALSE
7074 | MRT-YD00-P0MKG-125331 | 2019-01-18 | MRT-HK-REC-TT-190419 | FI | 0 | TRUE | TRUE | FALSE
7075 | MRT-CA02-P0UVH-187076 | 2019-01-18 | MRT-HK-REC-TT-190420 | FA | 1 | TRUE | TRUE | FALSE
7076 | MRT-XH01-P0GN-135239 | 2019-01-18 | MRT-HK-REC-TT-190421 | FA | 0 | TRUE | FALSE | FALSE
7077 | MRT-YV02-P3MKW-230002 | 2019-01-18 | MRT-DS-REC-TT-190015 | FC | 2 | TRUE | TRUE | FALSE
7078 | MRT-YK01-P0MKG-125330 | 2019-01-21 | MRT-HK-REC-TT-190422 | FA | 1 | TRUE | TRUE | FALSE
7079 | MRT-YE00-P0UBN-150169 | 2019-01-21 | MRT-HK-REC-TT-190425 | FA | 0 | TRUE | FALSE | FALSE
7080 | MRT-YT01-P2LB-122096 | 2019-01-21 | MRT-DS-REC-TT-190016 | FC | 2 | TRUE | TRUE | FALSE
7081 | MRT-YT01-P3LB-122096 | 2019-01-21 | MRT-DS-REC-TT-190016 | FC | 2 | TRUE | TRUE | FALSE
7082 | MRT-YE00-P2UXA-150163 | 2019-01-21 | MRT-HK-REC-TT-190426 | FA | 0 | TRUE | FALSE | FALSE
7083 | MRT-YE00-P0GQA-150168 | 2019-01-21 | MRT-HK-REC-TT-190426 | FA | 0 | TRUE | FALSE | FALSE
7084 | MRT-CC02-P2UHA-170103 | 2019-01-21 | MRT-DS-REC-TT-180931-FC | FC | 8 | TRUE | TRUE | FALSE
7085 | MRT-CC02-P2UHA-170104 | 2019-01-21 | MRT-DS-REC-TT-180931-FC | FC | 6 | TRUE | TRUE | FALSE
7086 | MRT-VK02-P2UHA-170106 | 2019-01-21 | MRT-DS-REC-TT-180931-FC | FC | 7 | TRUE | TRUE | FALSE
7087 | MRT-CC02-P3UHA-170103 | 2019-01-21 | MRT-DS-REC-TT-180931-FC | FC | 8 | TRUE | TRUE | FALSE
7088 | MRT-CC02-P3UHA-170104 | 2019-01-21 | MRT-DS-REC-TT-180931-FC | FC | 6 | TRUE | TRUE | FALSE
7089 | MRT-VK02-P3UHA-170106 | 2019-01-21 | MRT-DS-REC-TT-180931-FC | FC | 7 | TRUE | TRUE | FALSE
7090 | MRT-XL00-P0ZEN-140002 | 2019-01-21 | MRT-DS-REC-TT-180932-FC | FC | 4 | TRUE | TRUE | FALSE
7091 | MRT-XN00-P0ZEN-140001 | 2019-01-21 | MRT-DS-REC-TT-180932-FC | FC | 4 | TRUE | TRUE | FALSE
7092 | MRT-YT01-P0EKF-125610 | 2019-01-21 | MRT-HK-REC-TT-190427 | FA | 1 | TRUE | TRUE | FALSE
7093 | MRT-CC05-P0EKF-125613 | 2019-01-21 | MRT-HK-REC-TT-190427 | FA | 1 | TRUE | TRUE | FALSE
7094 | MRT-YF00-P0CBA-161202 | 2019-01-21 | MRT-DS-REC-TT-180376-FC | FC | 1 | TRUE | TRUE | FALSE
8088 | MRT-XH01-P3GC-135137 | 2019-01-21 | MRT-HK-REC-TT-180430 | FA | 0 | TRUE | FALSE | FALSE
7095 | MRT-XK00-P0GDG-135029 | 2019-01-22 | MRT-HK-REC-TT-190428 | FI | 0 | TRUE | FALSE | FALSE
7096 | MRT-XK00-P0GDG-135030 | 2019-01-22 | MRT-HK-REC-TT-190428 | FI | 0 | TRUE | FALSE | FALSE
7097 | MRT-XK00-P0GDT-135031 | 2019-01-22 | MRT-HK-REC-TT-190428 | FI | 0 | TRUE | FALSE | FALSE
7098 | MRT-XK00-P0GDT-135034 | 2019-01-22 | MRT-HK-REC-TT-190428 | FI | 0 | TRUE | FALSE | FALSE
7099 | MRT-DS05-P0EKF-125625 | 2019-01-22 | MRT-HK-REC-TT-190429 | FA | 0 | TRUE | FALSE | FALSE
7100 | MRT-YE07-P0UCB-150148 | 2019-01-22 | MRT-HK-REC-TT-190432 | FA | 0 | TRUE | FALSE | FALSE
7101 | MRT-YR05-P0GEN-135395 | 2019-01-22 | MRT-HK-REC-TT-190431 | FA | 0 | TRUE | FALSE | FALSE
7102 | MRT-YT01-P3GC-135127 | 2019-01-23 | MRT-HK-REC-TT-190433 | FA | 0 | TRUE | TRUE | FALSE
7103 | MRT-YR05-P0GEN-135373 | 2019-01-23 | MRT-HK-REC-TT-190434 | FA | 0 | TRUE | FALSE | FALSE
7104 | MRT-YF00-P2LB-122066 | 2019-01-23 | MRT-DS-REC-TT-190017 | FC | 3 | TRUE | TRUE | FALSE
7105 | MRT-CA00-P0UMA-180009 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 4 | TRUE | TRUE | FALSE
7106 | MRT-CA00-P0UMA-180010 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 4 | TRUE | TRUE | FALSE
7107 | MRT-CA00-P0UMA-180011 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 4 | TRUE | TRUE | FALSE
7108 | MRT-CA00-P0UMA-180013 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 4 | TRUE | TRUE | FALSE
7109 | MRT-CA00-P0UMA-180014 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 4 | TRUE | TRUE | FALSE
7110 | MRT-CA00-P0UMA-180015 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 4 | TRUE | TRUE | FALSE
7111 | MRT-CA00-P0UMA-180016 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 4 | TRUE | TRUE | FALSE
7112 | MRT-CA00-P0UMA-180017 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 4 | TRUE | TRUE | FALSE
7113 | MRT-CA00-P0UMA-180019 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 4 | TRUE | TRUE | FALSE
7114 | MRT-CA00-P0UMA-180021 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 4 | TRUE | TRUE | FALSE
7115 | MRT-CA00-P0UMA-180022 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 4 | TRUE | TRUE | FALSE
7116 | MRT-CA00-P0UMA-180023 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 2 | TRUE | TRUE | FALSE
7117 | MRT-CA00-P0UMA-180008 | 2019-01-23 | MRT-DS-REC-TT-190004-FC | FC | 4 | TRUE | TRUE | FALSE
7118 | MRT-CC02-P0UMA-171103 | 2019-01-23 | MRT-DS-REC-TT-190006-FC | FC | 1 | TRUE | TRUE | FALSE
7119 | MRT-YE00-P2MKA-230002 | 2019-01-23 | MRT-DS-REC-TT-190010-FC | FC | 3 | TRUE | TRUE | FALSE
7120 | MRT-YE00-P3MKA-230002 | 2019-01-23 | MRT-DS-REC-TT-190010-FC | FC | 3 | TRUE | TRUE | FALSE
7121 | MRT-XJ00-P2LAB-145000 | 2019-01-24 | MRT-DS-REC-TT-180938-FC | FC | 0 | TRUE | TRUE | FALSE
7122 | MRT-QM03-P0ZEN-155024 | 2019-01-24 | MRT-HK-REC-TT-190435 | FA | 0 | TRUE | FALSE | FALSE
7123 | MRT-CQ02-P2PAH-604105 | 2019-01-24 | MRT-DS-REC-TT-180937-FC | FC | 0 | TRUE | TRUE | FALSE
7124 | MRT-CQ02-P2PBB-604114 | 2019-01-24 | MRT-DS-REC-TT-180937-FC | FC | 0 | TRUE | TRUE | FALSE
7125 | MRT-CQ02-P2PAH-604505 | 2019-01-24 | MRT-DS-REC-TT-180937-FC | FC | 0 | TRUE | TRUE | FALSE
7126 | MRT-CQ02-P2PBB-604514 | 2019-01-24 | MRT-DS-REC-TT-180937-FC | FC | 0 | TRUE | TRUE | FALSE
7127 | MRT-XS01-P2LB-122111 | 2019-01-24 | MRT-DS-REC-TT-190018 | FI | 1 | TRUE | TRUE | FALSE
7128 | MRT-YT01-P3MKA-240003 | 2019-01-24 | MRT-DS-REC-TT-190020 | FI | 3 | TRUE | TRUE | FALSE
7129 | MRT-CQ02-P3MKW-260001 | 2019-01-24 | MRT-DS-REC-TT-190020 | FI | 0 | TRUE | FALSE | FALSE
7130 | MRT-CQ02-P3MKG-260001 | 2019-01-24 | MRT-DS-REC-TT-190020 | FI | 0 | TRUE | FALSE | FALSE
7131 | MRT-XG02-P2SCA-120004 | 2019-01-24 | MRT-DS-REC-TT-190019 | FC | 5 | TRUE | TRUE | FALSE
7132 | MRT-XG02-P2SCA-120005 | 2019-01-24 | MRT-DS-REC-TT-190019 | FC | 5 | TRUE | TRUE | FALSE
7133 | MRT-XG02-P2SCA-120006 | 2019-01-24 | MRT-DS-REC-TT-190019 | FC | 5 | TRUE | TRUE | FALSE
7134 | MRT-XG02-P3SCA-120004 | 2019-01-24 | MRT-DS-REC-TT-190019 | FC | 5 | TRUE | TRUE | FALSE
7135 | MRT-XG02-P3SCA-120005 | 2019-01-24 | MRT-DS-REC-TT-190019 | FC | 5 | TRUE | TRUE | FALSE
7136 | MRT-XG02-P3SCA-120006 | 2019-01-24 | MRT-DS-REC-TT-190019 | FC | 5 | TRUE | TRUE | FALSE
7137 | MRT-XA00-P0GAA-135004 | 2019-01-24 | MRT-HK-REC-TT-190436 | FA | 4 | TRUE | TRUE | FALSE
7138 | MRT-XK00-P0GDB-135037 | 2019-01-24 | MRT-HK-REC-TT-190436 | FI | 0 | TRUE | FALSE | FALSE
7139 | MRT-XK00-P0GAA-135046 | 2019-01-24 | MRT-HK-REC-TT-190436 | FI | 0 | TRUE | FALSE | FALSE
7140 | MRT-XK00-P0GDN-135041 | 2019-01-24 | MRT-HK-REC-TT-190436 | FI | 0 | TRUE | FALSE | FALSE
7141 | MRT-XK00-P0ZEN-135047 | 2019-01-24 | MRT-HK-REC-TT-190436 | FI | 0 | TRUE | FALSE | FALSE
7142 | MRT-DS05-P0EKF-125623 | 2019-01-24 | MRT-HK-REC-TT-190437 | FA | 0 | TRUE | FALSE | FALSE
7143 | MRT-DS05-P0EKF-125624 | 2019-01-24 | MRT-HK-REC-TT-190437 | FA | 0 | TRUE | FALSE | FALSE
7144 | MRT-YT01-P0GEN-135362 | 2019-01-24 | MRT-HK-REC-TT-190438 | FA | 0 | TRUE | FALSE | FALSE
7145 | MRT-YD00-P2LB-122114 | 2019-01-24 | MRT-DS-REC-TT-180935-FC | FC | 1 | TRUE | TRUE | FALSE
7146 | MRT-YD00-P3LB-122114 | 2019-01-24 | MRT-DS-REC-TT-180935-FC | FC | 1 | TRUE | TRUE | FALSE
7147 | MRT-QE00-P0MKG-125363 | 2019-01-25 | MRT-HK-REC-TT-190439 | FA | 0 | TRUE | TRUE | FALSE
7148 | MRT-CA03-P0AB-187401 | 2019-01-25 | MRT-HK-REC-TT-190440 | FA | 0 | TRUE | FALSE | FALSE
7149 | MRT-YT02-P2LB-122094 | 2019-01-25 | MRT-DS-REC-TT-190021 | FC | 3 | TRUE | TRUE | FALSE
7150 | MRT-YT02-P3LB-122094 | 2019-01-25 | MRT-DS-REC-TT-190021 | FC | 3 | TRUE | TRUE | FALSE
7151 | MRT-CC02-P2UHA-170007 | 2019-01-28 | MRT-DS-REC-TT-190022 | FC | 3 | TRUE | TRUE | FALSE
7152 | MRT-CC02-P2UHA-170009 | 2019-01-28 | MRT-DS-REC-TT-190022 | FC | 3 | TRUE | TRUE | FALSE
7153 | MRT-VK02-P2UHA-170010 | 2019-01-28 | MRT-DS-REC-TT-190022 | FC | 3 | TRUE | TRUE | FALSE
7154 | MRT-CC02-P3UHA-170007 | 2019-01-28 | MRT-DS-REC-TT-190022 | FC | 3 | TRUE | TRUE | FALSE
7155 | MRT-CC02-P3UHA-170009 | 2019-01-28 | MRT-DS-REC-TT-190022 | FC | 3 | TRUE | TRUE | FALSE
7156 | MRT-VK02-P3UHA-170010 | 2019-01-28 | MRT-DS-REC-TT-190022 | FC | 3 | TRUE | TRUE | FALSE
7157 | MRT-DP00-P3GC-135142 | 2019-01-29 | MRT-HK-REC-TT-190441 | FA | 0 | TRUE | FALSE | FALSE
7158 | MRT-DN03-P3GC-135191 | 2019-01-29 | MRT-HK-REC-TT-190441 | FA | 0 | TRUE | FALSE | FALSE
7159 | MRT-DN03-P3GC-135180 | 2019-01-29 | MRT-HK-REC-TT-190441 | FA | 0 | TRUE | FALSE | FALSE
7160 | MRT-DN03-P3GC-135192 | 2019-01-29 | MRT-HK-REC-TT-190441 | FA | 0 | TRUE | FALSE | FALSE
7161 | MRT-QM03-P3GC-135178 | 2019-01-29 | MRT-HK-REC-TT-190441 | FA | 0 | TRUE | FALSE | FALSE
7162 | MRT-DS00-P3GC-135181 | 2019-01-29 | MRT-HK-REC-TT-190441 | FA | 0 | TRUE | FALSE | FALSE
7163 | MRT-QM03-P0GN-135274 | 2019-01-29 | MRT-HK-REC-TT-190441 | FA | 0 | TRUE | FALSE | FALSE
7164 | MRT-DS00-P0GN-135277 | 2019-01-29 | MRT-HK-REC-TT-190441 | FA | 0 | TRUE | FALSE | FALSE
7165 | MRT-DP00-P0GN-135244 | 2019-01-29 | MRT-HK-REC-TT-190441 | FA | 0 | TRUE | FALSE | FALSE
7166 | MRT-DN03-P0GN-135290 | 2019-01-29 | MRT-HK-REC-TT-190441 | FA | 0 | TRUE | FALSE | FALSE
7167 | MRT-DN03-P0GN-135289 | 2019-01-29 | MRT-HK-REC-TT-190441 | FA | 0 | TRUE | FALSE | FALSE
7168 | MRT-DN03-P0GN-135276 | 2019-01-29 | MRT-HK-REC-TT-190441 | FA | 0 | TRUE | FALSE | FALSE
7169 | MRT-CA01-P0UGX-186971 | 2019-01-29 | MRT-HK-REC-TT-190442 | FA | 0 | TRUE | TRUE | FALSE
7170 | MRT-CA02-P0UGX-186989 | 2019-01-29 | MRT-HK-REC-TT-190442 | FA | 0 | TRUE | TRUE | FALSE
7171 | MRT-CA00-P0UGX-186956 | 2019-01-29 | MRT-HK-REC-TT-190442 | FA | 4 | TRUE | TRUE | FALSE
7172 | MRT-CA00-P0UGX-186960 | 2019-01-29 | MRT-HK-REC-TT-190442 | FA | 4 | TRUE | TRUE | FALSE
7173 | MRT-CA01-P0UGX-186968 | 2019-01-29 | MRT-HK-REC-TT-190442 | FA | 2 | TRUE | TRUE | FALSE
7174 | MRT-CA02-P0UGX-186984 | 2019-01-29 | MRT-HK-REC-TT-190442 | FA | 2 | TRUE | TRUE | FALSE
7175 | MRT-CA00-P0UGX-186961 | 2019-01-29 | MRT-HK-REC-TT-190442 | FA | 4 | TRUE | TRUE | FALSE
7176 | MRT-CA00-P0UGX-186963 | 2019-01-29 | MRT-HK-REC-TT-190442 | FA | 4 | TRUE | TRUE | FALSE
7177 | MRT-CA01-P0UGX-186973 | 2019-01-29 | MRT-HK-REC-TT-190442 | FA | 3 | TRUE | TRUE | FALSE
7178 | MRT-CA02-P0UGX-186975 | 2019-01-29 | MRT-HK-REC-TT-190442 | FA | 3 | TRUE | TRUE | FALSE
7179 | MRT-CA01-P0UGX-186972 | 2019-01-29 | MRT-HK-REC-TT-190442 | FA | 2 | TRUE | TRUE | FALSE
7180 | MRT-YL16-P2ZEN-165026 | 2019-01-29 | MRT-HK-REC-TT-190443 | FA | 0 | TRUE | FALSE | FALSE
7181 | MRT-YR05-P0GEN-135371 | 2019-01-29 | MRT-HK-REC-TT-190444 | FA | 0 | TRUE | FALSE | FALSE
7182 | MRT-XG02-P0GDK-135019 | 2019-01-29 | MRT-HK-REC-TT-190445 | FA | 0 | TRUE | FALSE | FALSE
7183 | MRT-DS00-P3AY-160049 | 2019-01-30 | MRT-HK-REC-TT-190446 | FA | 0 | TRUE | FALSE | FALSE
7184 | MRT-DS00-P3AYA-160028 | 2019-01-30 | MRT-HK-REC-TT-190446 | FA | 0 | TRUE | FALSE | FALSE
7185 | MRT-DS00-P3AY-160041 | 2019-01-30 | MRT-HK-REC-TT-190446 | FA | 0 | TRUE | FALSE | FALSE
7186 | MRT-CH04-P0BAU-150622 | 2019-01-30 | MRT-HK-REC-TT-190447 | FA | 0 | TRUE | FALSE | FALSE
7187 | MRT-YT01-P0GEN-135329 | 2019-01-30 | MRT-HK-REC-TT-190450 | FA | 0 | TRUE | FALSE | FALSE
7188 | MRT-YK10-P2MAA-128001 | 2019-01-30 | MRT-HK-REC-TT-190451 | FI | 0 | TRUE | FALSE | FALSE
7189 | MRT-YD00-P2PGB-113107 | 2019-01-30 | MRT-DS-REC-TT-180889-FC | FC | 1 | TRUE | TRUE | FALSE
7190 | MRT-YD00-P3PGB-113107 | 2019-01-30 | MRT-DS-REC-TT-180889-FC | FC | 1 | TRUE | TRUE | FALSE
7191 | MRT-CC02-P0UMA-171003 | 2019-01-31 | MRT-DS-REC-TT-190023 | FC | 1 | TRUE | TRUE | FALSE
7192 | MRT-VK02-P0UMA-171006 | 2019-01-31 | MRT-DS-REC-TT-190023 | FC | 1 | TRUE | TRUE | FALSE
7193 | MRT-YK09-P2MKC-230003 | 2019-01-31 | MRT-DS-REC-TT-190011-FC | FC | 2 | TRUE | TRUE | FALSE
7194 | MRT-YK09-P3MKC-230003 | 2019-01-31 | MRT-DS-REC-TT-190011-FC | FC | 2 | TRUE | TRUE | FALSE
7195 | MRT-CC02-P2UHA-170007 | 2019-01-31 | MRT-DS-REC-TT-190022-FC | FC | 3 | TRUE | TRUE | FALSE
7196 | MRT-CC02-P2UHA-170009 | 2019-01-31 | MRT-DS-REC-TT-190022-FC | FC | 3 | TRUE | TRUE | FALSE
7197 | MRT-VK02-P2UHA-170010 | 2019-01-31 | MRT-DS-REC-TT-190022-FC | FC | 3 | TRUE | TRUE | FALSE
7198 | MRT-CC02-P3UHA-170007 | 2019-01-31 | MRT-DS-REC-TT-190022-FC | FC | 3 | TRUE | TRUE | FALSE
7199 | MRT-CC02-P3UHA-170009 | 2019-01-31 | MRT-DS-REC-TT-190022-FC | FC | 3 | TRUE | TRUE | FALSE
7200 | MRT-VK02-P3UHA-170010 | 2019-01-31 | MRT-DS-REC-TT-190022-FC | FC | 3 | TRUE | TRUE | FALSE
7201 | MRT-XB02-P2LB-122018 | 2019-01-31 | MRT-DS-REC-TT-190024 | FC | 5 | TRUE | TRUE | FALSE
7202 | MRT-XB02-P3LB-122018 | 2019-01-31 | MRT-DS-REC-TT-190024 | FC | 4 | TRUE | TRUE | FALSE
7203 | MRT-XB02-P2LB-122016 | 2019-01-31 | MRT-DS-REC-TT-190025 | FC | 4 | TRUE | TRUE | FALSE
7204 | MRT-XB02-P3LB-122016 | 2019-01-31 | MRT-DS-REC-TT-190025 | FC | 3 | TRUE | TRUE | FALSE
7205 | MRT-VN03-P2LB-122015 | 2019-01-31 | MRT-DS-REC-TT-190026 | FC | 4 | TRUE | TRUE | FALSE
7206 | MRT-VN03-P3LB-122015 | 2019-01-31 | MRT-DS-REC-TT-190026 | FC | 4 | TRUE | TRUE | FALSE
10621 | MRT-QE06-P0GEN-135315 | 2019-01-31 | MRT-HK-REC-TT-190452 | FI | 0 | TRUE | FALSE | FALSE
7207 | MRT-DM01-P0ZEN-140001 | 2019-02-01 | MRT-DS-REC-TT-190027 | FI | 0 | TRUE | FALSE | FALSE
7208 | MRT-XJ00-P2PAB-140001 | 2019-02-01 | MRT-DS-REC-TT-190029 | FC | 3 | TRUE | TRUE | FALSE
7209 | MRT-XJ00-P3PAB-140001 | 2019-02-01 | MRT-DS-REC-TT-190029 | FC | 3 | TRUE | TRUE | FALSE
7210 | MRT-XJ00-P2PAB-145000 | 2019-02-01 | MRT-DS-REC-TT-190030 | FI | 0 | TRUE | FALSE | FALSE
7211 | MRT-XJ00-P3PAB-146000 | 2019-02-01 | MRT-DS-REC-TT-190030 | FI | 0 | TRUE | FALSE | FALSE
7212 | MRT-XJ00-P2PAB-142200 | 2019-02-01 | MRT-DS-REC-TT-190030 | FI | 0 | TRUE | FALSE | FALSE
7213 | MRT-XJ00-P3PAB-143200 | 2019-02-01 | MRT-DS-REC-TT-190030 | FI | 0 | TRUE | FALSE | FALSE
7214 | MRT-XJ00-P3PAB-144200 | 2019-02-01 | MRT-DS-REC-TT-190030 | FI | 0 | TRUE | FALSE | FALSE
7215 | MRT-XG02-P2MAA-220005 | 2019-02-01 | MRT-DS-REC-TT-190028 | FC | 2 | TRUE | TRUE | FALSE
7216 | MRT-XG02-P3MAA-220005 | 2019-02-01 | MRT-DS-REC-TT-190028 | FC | 2 | TRUE | TRUE | FALSE
7217 | MRT-YD00-P2MAA-220030 | 2019-02-01 | MRT-DS-REC-TT-190028 | FI | 1 | TRUE | TRUE | FALSE
7218 | MRT-YD00-P2MAA-220031 | 2019-02-01 | MRT-DS-REC-TT-190028 | FI | 1 | TRUE | TRUE | FALSE
7219 | MRT-YD00-P3MAA-220030 | 2019-02-01 | MRT-DS-REC-TT-190028 | FI | 1 | TRUE | TRUE | FALSE
7220 | MRT-YD00-P3MAA-220031 | 2019-02-01 | MRT-DS-REC-TT-190028 | FI | 1 | TRUE | TRUE | FALSE
7221 | MRT-VL00-P2MAA-220001 | 2019-02-01 | MRT-DS-REC-TT-190033 | FC | 2 | TRUE | TRUE | FALSE
7222 | MRT-VL00-P3MAA-220001 | 2019-02-01 | MRT-DS-REC-TT-190033 | FC | 2 | TRUE | TRUE | FALSE
7223 | MRT-XT00-P2MAA-220002 | 2019-02-01 | MRT-DS-REC-TT-190033 | FC | 2 | TRUE | TRUE | FALSE
7224 | MRT-XT00-P3MAA-220002 | 2019-02-01 | MRT-DS-REC-TT-190033 | FC | 2 | TRUE | TRUE | FALSE
7225 | MRT-XH01-P0UZT-140000 | 2019-02-01 | MRT-DS-REC-TT-190031 | FC | 2 | TRUE | TRUE | FALSE
8571 | MRT-CC04-P0ULY-176503 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8572 | MRT-CC04-P0ULY-176504 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8573 | MRT-CC04-P0ULY-176507 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8574 | MRT-CC04-P0ULY-176508 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8575 | MRT-CC04-P0ULY-176511 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8576 | MRT-CC04-P0ULY-176514 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8577 | MRT-CC04-P0ULY-176515 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8578 | MRT-CC04-P0ULY-176516 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8579 | MRT-CC04-P0ULY-176517 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8580 | MRT-CC04-P0ULY-176518 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8581 | MRT-CC04-P0ULY-176519 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8582 | MRT-CC04-P0ULY-176520 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8583 | MRT-CC04-P0ULY-176521 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8584 | MRT-CC04-P0ULY-176522 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8585 | MRT-CC04-P0ULY-176523 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8586 | MRT-CC04-P0ULY-176524 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8587 | MRT-CC04-P0ULY-176525 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8588 | MRT-CC04-P0ULY-176526 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8589 | MRT-CC04-P0ULY-176527 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8590 | MRT-CC04-P0ULY-176528 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8591 | MRT-CC04-P0ULY-176529 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8592 | MRT-CC04-P0ULY-176530 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8593 | MRT-CC04-P0ULY-176531 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8594 | MRT-CC04-P0ULY-176532 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8595 | MRT-CC04-P0ULY-176533 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8596 | MRT-CC04-P0ULY-176534 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8597 | MRT-CC04-P0ULY-176535 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8598 | MRT-CC04-P0ULY-176536 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8599 | MRT-CC04-P0ULY-176537 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8600 | MRT-CC04-P0ULY-176538 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8601 | MRT-CC04-P0ULY-176539 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8602 | MRT-CC04-P0ULY-176540 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8603 | MRT-CC04-P0ULY-176541 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8604 | MRT-CC04-P0ULY-176542 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8605 | MRT-CC04-P0ULY-176551 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8606 | MRT-CC04-P0ULY-176552 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8607 | MRT-CC04-P0ULY-176553 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8608 | MRT-CC04-P0ULY-176554 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8609 | MRT-CC04-P0ULY-176555 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8610 | MRT-CC04-P0ULY-176556 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8611 | MRT-CC04-P0ULY-176557 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8612 | MRT-CC04-P0ULY-176558 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8613 | MRT-CC04-P0ULY-176559 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8614 | MRT-CC04-P0ULY-176560 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8615 | MRT-CC04-P0ULY-176561 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8616 | MRT-CC04-P0ULY-176562 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8617 | MRT-CC04-P0ULY-176563 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8618 | MRT-CC04-P0ULY-176564 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8619 | MRT-CC04-P0ULY-176565 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8620 | MRT-CC04-P0ULY-176566 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8621 | MRT-CC04-P0ULY-176567 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8622 | MRT-CC04-P0ULY-176568 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8623 | MRT-CC04-P0ULY-176569 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8624 | MRT-CC04-P0ULY-176570 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8625 | MRT-CC04-P0ULY-176571 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8626 | MRT-CC04-P0ULY-176572 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8627 | MRT-CC04-P0ULY-176573 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8628 | MRT-CC04-P0ULY-176574 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8629 | MRT-CC04-P0ULY-176575 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8630 | MRT-CC04-P0ULY-176576 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8631 | MRT-CC04-P0ULY-176577 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8632 | MRT-CC04-P0ULY-176578 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8633 | MRT-CC04-P0ULY-176579 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8634 | MRT-CC04-P0ULY-176580 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8635 | MRT-CC04-P0ULY-176581 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8636 | MRT-CC04-P0ULY-176582 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8637 | MRT-CC04-P0ULY-176583 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8638 | MRT-CC04-P0ULY-176584 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8639 | MRT-CC04-P0ULY-176585 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8640 | MRT-CC04-P0ULY-176586 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8641 | MRT-CC04-P0ULY-176587 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8642 | MRT-CC04-P0ULY-176588 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8643 | MRT-CC04-P0ULY-176589 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8644 | MRT-CC04-P0ULY-176590 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8645 | MRT-CC04-P0ULY-176591 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8646 | MRT-CC04-P0ULY-176592 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8647 | MRT-CC04-P0ULY-176593 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8648 | MRT-CC04-P0ULY-176594 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8649 | MRT-CC04-P0ULY-176595 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8650 | MRT-CC04-P0ULY-176596 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8651 | MRT-CC04-P0ULY-176597 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8652 | MRT-CC04-P0ULY-176598 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8653 | MRT-CC04-P0ULY-176599 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8654 | MRT-CC04-P0ULY-176600 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8655 | MRT-CC04-P0ULY-176601 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8656 | MRT-CC04-P0ULY-176602 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8657 | MRT-CC04-P0ULY-176603 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8658 | MRT-CC04-P0ULY-176604 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8659 | MRT-CC04-P0ULY-176605 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8660 | MRT-CC04-P0ULY-176606 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8661 | MRT-CC04-P0ULY-176607 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8662 | MRT-CC04-P0ULY-176608 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8663 | MRT-CC04-P0ULY-176609 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8664 | MRT-CC04-P0ULY-176610 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8665 | MRT-CC04-P0ULY-176611 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8666 | MRT-CC04-P0ULY-176612 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8667 | MRT-CC04-P0ULY-176613 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8668 | MRT-CC04-P0ULY-176614 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8669 | MRT-CC04-P0ULY-176615 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8670 | MRT-CC04-P0ULY-176616 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8671 | MRT-CC04-P0ULY-176617 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
8672 | MRT-CC04-P0ULY-176618 | 2019-02-09 | MRT-HK-REC-TT-190466 | FA | 0 | TRUE | TRUE | FALSE
7226 | MRT-DM01-P0ZEN-140001 | 2019-02-11 | MRT-DS-REC-TT-190027-FC | FC | 0 | TRUE | TRUE | FALSE
7227 | MRT-CC02-P0UMA-171003 | 2019-02-11 | MRT-DS-REC-TT-190023-FC | FC | 1 | TRUE | TRUE | FALSE
7228 | MRT-VK02-P0UMA-171006 | 2019-02-11 | MRT-DS-REC-TT-190023-FC | FC | 1 | TRUE | TRUE | FALSE
7229 | MRT-XB02-P2LB-122018 | 2019-02-11 | MRT-DS-REC-TT-190024-FC | FC | 5 | TRUE | TRUE | FALSE
7230 | MRT-XB02-P3LB-122018 | 2019-02-11 | MRT-DS-REC-TT-190024-FC | FC | 4 | TRUE | TRUE | FALSE
7231 | MRT-XB02-P2LB-122016 | 2019-02-11 | MRT-DS-REC-TT-190025-FC | FC | 4 | TRUE | TRUE | FALSE
7232 | MRT-XB02-P3LB-122016 | 2019-02-11 | MRT-DS-REC-TT-190025-FC | FC | 3 | TRUE | TRUE | FALSE
7233 | MRT-DN02-P2H-830012 | 2019-02-11 | MRT-DS-REC-TT-180933-FC | FC | 0 | TRUE | TRUE | FALSE
7234 | MRT-YT10-P2MKC-230016 | 2019-02-11 | MRT-DS-REC-TT-190014-FC | FC | 0 | TRUE | TRUE | FALSE
7235 | MRT-YT10-P3MKC-230016 | 2019-02-11 | MRT-DS-REC-TT-190014-FC | FC | 0 | TRUE | TRUE | FALSE
7236 | MRT-CM02-P2MKA-220001 | 2019-02-11 | MRT-DS-REC-TT-190013-FC | FC | 0 | TRUE | TRUE | FALSE
7237 | MRT-CM02-P3MKA-220001 | 2019-02-11 | MRT-DS-REC-TT-190013-FC | FC | 0 | TRUE | TRUE | FALSE
7238 | MRT-YT01-P2LB-122096 | 2019-02-11 | MRT-DS-REC-TT-190016-FC | FC | 2 | TRUE | TRUE | FALSE
7239 | MRT-YT01-P3LB-122096 | 2019-02-11 | MRT-DS-REC-TT-190016-FC | FC | 2 | TRUE | TRUE | FALSE
7240 | MRT-YT02-P2LB-122094 | 2019-02-11 | MRT-DS-REC-TT-190021-FC | FC | 3 | TRUE | TRUE | FALSE
7241 | MRT-YT02-P3LB-122094 | 2019-02-11 | MRT-DS-REC-TT-190021-FC | FC | 3 | TRUE | TRUE | FALSE
7242 | MRT-YF00-P2LB-122066 | 2019-02-11 | MRT-DS-REC-TT-190017-FC | FC | 3 | TRUE | TRUE | FALSE
7243 | MRT-XK00-P0GDQ-135038 | 2019-02-12 | MRT-HK-REC-TT-190453 | FA | 0 | TRUE | FALSE | FALSE
7244 | MRT-XK00-P0GDB-135045 | 2019-02-12 | MRT-HK-REC-TT-190453 | FA | 0 | TRUE | FALSE | FALSE
7245 | MRT-XK00-P0GDT-135032 | 2019-02-12 | MRT-HK-REC-TT-190453 | FA | 0 | TRUE | FALSE | FALSE
7246 | MRT-YT01-P0GEN-135328 | 2019-02-12 | MRT-HK-REC-TT-190454 | FA | 1 | TRUE | TRUE | FALSE
7247 | MRT-YT01-P0GEN-135354 | 2019-02-12 | MRT-HK-REC-TT-190454 | FA | 0 | TRUE | TRUE | FALSE
7248 | MRT-DD03-P0GEN-135387 | 2019-02-12 | MRT-HK-REC-TT-190456 | FA | 0 | TRUE | TRUE | FALSE
7249 | MRT-DN04-P0QHB-125423 | 2019-02-12 | MRT-HK-REC-TT-190456 | FA | 0 | TRUE | TRUE | FALSE
7250 | MRT-YT01-P0GEN-135397 | 2019-02-12 | MRT-HK-REC-TT-190455 | FA | 0 | TRUE | TRUE | FALSE
7251 | MRT-YT01-P0GEN-135351 | 2019-02-12 | MRT-HK-REC-TT-190455 | FA | 0 | TRUE | TRUE | FALSE
7252 | MRT-YT01-P0GEN-135352 | 2019-02-12 | MRT-HK-REC-TT-190455 | FA | 0 | TRUE | TRUE | FALSE
7253 | MRT-YD08-P0GEN-135364 | 2019-02-12 | MRT-HK-REC-TT-190455 | FA | 0 | TRUE | TRUE | FALSE
7254 | MRT-CV03-P0GEN-135381 | 2019-02-12 | MRT-HK-REC-TT-190457 | FA | 1 | TRUE | TRUE | FALSE
7255 | MRT-YE00-P2UGA-150162 | 2019-02-12 | MRT-HK-REC-TT-190458 | FA | 0 | TRUE | TRUE | FALSE
7256 | MRT-YE00-P0BJQ-150167 | 2019-02-12 | MRT-HK-REC-TT-190458 | FA | 0 | TRUE | TRUE | FALSE
7257 | MRT-XA01-P0ABA-150511 | 2019-02-12 | MRT-HK-REC-TT-190458 | FA | 2 | TRUE | TRUE | FALSE
7258 | MRT-BT00-P0SGA-135485 | 2019-02-12 | MRT-HK-REC-TT-190459 | FA | 0 | TRUE | TRUE | FALSE
7259 | MRT-YL15-P0GEN-135393 | 2019-02-12 | MRT-HK-REC-TT-190460 | FA | 1 | TRUE | TRUE | FALSE
7260 | MRT-CH04-P3BBT-150439 | 2019-02-12 | MRT-HK-REC-TT-190461 | FA | 0 | TRUE | TRUE | FALSE
7261 | MRT-CV05-P0BBA-150474 | 2019-02-12 | MRT-HK-REC-TT-190461 | FA | 0 | TRUE | TRUE | FALSE
7262 | MRT-US02-P2BBA-150466 | 2019-02-12 | MRT-HK-REC-TT-190461 | FA | 0 | TRUE | TRUE | FALSE
7263 | MRT-US02-P3BBA-150468 | 2019-02-12 | MRT-HK-REC-TT-190461 | FA | 0 | TRUE | TRUE | FALSE
7264 | MRT-US02-P4BBA-150121 | 2019-02-12 | MRT-HK-REC-TT-190461 | FA | 0 | TRUE | TRUE | FALSE
7265 | MRT-US02-P0BBA-150470 | 2019-02-12 | MRT-HK-REC-TT-190461 | FA | 0 | TRUE | TRUE | FALSE
7266 | MRT-XP00-P0BBA-150457 | 2019-02-12 | MRT-HK-REC-TT-190461 | FA | 0 | TRUE | TRUE | FALSE
7267 | MRT-XP00-P0BTA-150637 | 2019-02-12 | MRT-HK-REC-TT-190461 | FA | 0 | TRUE | TRUE | FALSE
7268 | MRT-XW03-P3BAA-150938 | 2019-02-12 | MRT-HK-REC-TT-190461 | FA | 0 | TRUE | TRUE | FALSE
7269 | MRT-QM03-P0ZEN-155025 | 2019-02-12 | MRT-HK-REC-TT-190462 | FA | 0 | TRUE | TRUE | FALSE
7270 | MRT-CA00-P3AY-160012 | 2019-02-12 | MRT-HK-REC-TT-190463 | FA | 1 | TRUE | TRUE | FALSE
7271 | MRT-CA00-P3AYA-160014 | 2019-02-12 | MRT-HK-REC-TT-190463 | FA | 1 | TRUE | TRUE | FALSE
7272 | MRT-YQ07-P3AY-160002 | 2019-02-12 | MRT-HK-REC-TT-190463 | FA | 1 | TRUE | TRUE | FALSE
7273 | MRT-YQ07-P3AYA-160052 | 2019-02-12 | MRT-HK-REC-TT-190463 | FA | 1 | TRUE | TRUE | FALSE
7274 | MRT-YQ07-P3AYA-160038 | 2019-02-12 | MRT-HK-REC-TT-190463 | FA | 1 | TRUE | TRUE | FALSE
7275 | MRT-QM03-P0ZEN-185011 | 2019-02-12 | MRT-HK-REC-TT-190464 | FI | 0 | TRUE | TRUE | FALSE
7276 | MRT-XA01-P0BRU-150975 | 2019-02-12 | MRT-HK-REC-TT-190465 | FA | 0 | TRUE | TRUE | FALSE
7277 | MRT-XA01-P0BRU-150976 | 2019-02-12 | MRT-HK-REC-TT-190465 | FA | 0 | TRUE | TRUE | FALSE
7278 | MRT-XA01-P0BRU-150977 | 2019-02-12 | MRT-HK-REC-TT-190465 | FA | 0 | TRUE | TRUE | FALSE
7279 | MRT-DN05-P2MAA-220205 | 2019-02-12 | MRT-DS-REC-TT-190032 | FA | 0 | TRUE | TRUE | FALSE
7280 | MRT-YV02-P2MAV-230078 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | TRUE | FALSE
7281 | MRT-YV02-P3MAV-230078 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | TRUE | FALSE
7282 | MRT-YV02-P3MAK-230077 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | TRUE | FALSE
7283 | MRT-XR00-P3MAA-220082 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | TRUE | FALSE
7284 | MRT-YD05-P2CJJ-240069 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | TRUE | FALSE
7285 | MRT-YD05-P3CJJ-240069 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | TRUE | FALSE
7286 | MRT-YK00-P2CJJ-240119 | 2019-02-12 | MRT-DS-REC-TT-190032 | FA | 0 | TRUE | FALSE | FALSE
7287 | MRT-YK00-P3CJJ-240111 | 2019-02-12 | MRT-DS-REC-TT-190032 | FA | 0 | TRUE | FALSE | FALSE
7288 | MRT-YL01-P2CJJ-240070 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | FALSE | FALSE
7289 | MRT-YL01-P3CJJ-240070 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | FALSE | FALSE
7290 | MRT-YL01-P2CJJ-240073 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | FALSE | FALSE
7291 | MRT-YL01-P3CJJ-240073 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | FALSE | FALSE
7292 | MRT-YL00-P3CJJ-240052 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | FALSE | FALSE
7293 | MRT-YV02-P2MAK-230077 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | FALSE | FALSE
7294 | MRT-YL08-P2CJJ-240068 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | FALSE | FALSE
7295 | MRT-YL08-P3CJJ-240068 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | FALSE | FALSE
7296 | MRT-YL15-P2MAD-240171 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | FALSE | FALSE
7297 | MRT-YV02-P2MAD-240170 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | FALSE | FALSE
7298 | MRT-YV02-P2CJJ-240121 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | FALSE | FALSE
7299 | MRT-YV02-P3CJJ-240113 | 2019-02-12 | MRT-DS-REC-TT-190032 | FI | 0 | TRUE | FALSE | FALSE
7300 | MRT-DD00-P0BAT-155110 | 2019-02-13 | MRT-HK-REC-TT-190448 | FI | 0 | TRUE | FALSE | FALSE
7301 | MRT-DD00-P0BAT-155114 | 2019-02-13 | MRT-HK-REC-TT-190448 | FI | 0 | TRUE | FALSE | FALSE
7302 | MRT-DD00-P0BAT-155115 | 2019-02-13 | MRT-HK-REC-TT-190448 | FI | 0 | TRUE | FALSE | FALSE
7303 | MRT-YU02-P0BMY-150033 | 2019-02-13 | MRT-HK-REC-TT-190467 | FA | 0 | TRUE | FALSE | FALSE
7304 | MRT-YV02-P3MKW-230002 | 2019-02-13 | MRT-DS-REC-TT-190015-FC | FC | 2 | TRUE | TRUE | FALSE
7305 | MRT-YE07-P2UMA-150156 | 2019-02-13 | MRT-HK-REC-TT-190468 | FA | 0 | TRUE | FALSE | FALSE
7306 | MRT-DD03-P0GEN-135388 | 2019-02-13 | MRT-HK-REC-TT-190469 | FA | 0 | TRUE | FALSE | FALSE
7307 | MRT-YT01-P0GEN-135357 | 2019-02-13 | MRT-HK-REC-TT-190469 | FA | 0 | TRUE | FALSE | FALSE
7308 | MRT-CC04-P2ULY-176501 | 2019-02-14 | MRT-HK-REC-TT-190470 | FA | 0 | TRUE | FALSE | FALSE
7309 | MRT-CC04-P3ULY-176502 | 2019-02-14 | MRT-HK-REC-TT-190470 | FA | 0 | TRUE | FALSE | FALSE
7310 | MRT-QM03-P0ZEN-155026 | 2019-02-14 | MRT-HK-REC-TT-190471 | FA | 0 | TRUE | FALSE | FALSE
7311 | MRT-FF00-P0SGA-135460 | 2019-02-14 | MRT-HK-REC-TT-190472 | FA | 1 | TRUE | TRUE | FALSE
7312 | MRT-YE00-P2UGD-150164 | 2019-02-14 | MRT-HK-REC-TT-190473 | FA | 0 | TRUE | FALSE | FALSE
7313 | MRT-YE00-P0USG-150165 | 2019-02-14 | MRT-HK-REC-TT-190473 | FA | 0 | TRUE | FALSE | FALSE
7314 | MRT-YD00-P2LAC-126049 | 2019-02-15 | MRT-DS-REC-TT-190008-FC | FC | 3 | TRUE | TRUE | FALSE
7315 | MRT-YD00-P3LAC-126049 | 2019-02-15 | MRT-DS-REC-TT-190008-FC | FC | 3 | TRUE | TRUE | FALSE
7316 | MRT-YD00-P2LAC-126050 | 2019-02-15 | MRT-DS-REC-TT-190008-FC | FC | 3 | TRUE | TRUE | FALSE
7317 | MRT-YD00-P3LAC-126050 | 2019-02-15 | MRT-DS-REC-TT-190008-FC | FC | 3 | TRUE | TRUE | FALSE
7318 | MRT-XJ00-P2PAB-145100 | 2019-02-15 | MRT-DS-REC-TT-190034 | FI | 0 | TRUE | FALSE | FALSE
7319 | MRT-XJ00-P3PAB-146100 | 2019-02-15 | MRT-DS-REC-TT-190034 | FI | 0 | TRUE | FALSE | FALSE
7320 | MRT-XJ00-P3PAB-147100 | 2019-02-15 | MRT-DS-REC-TT-190034 | FI | 0 | TRUE | FALSE | FALSE
7321 | MRT-XG02-P2LA-110006 | 2019-02-15 | MRT-DS-REC-TT-190035 | FC | 6 | TRUE | TRUE | FALSE
7322 | MRT-XG02-P2LC-110007 | 2019-02-15 | MRT-DS-REC-TT-190035 | FC | 6 | TRUE | TRUE | FALSE
7323 | MRT-XG02-P0GHC-110002 | 2019-02-15 | MRT-DS-REC-TT-190035 | FC | 6 | TRUE | TRUE | FALSE
7324 | MRT-XG02-P3LA-110006 | 2019-02-15 | MRT-DS-REC-TT-190035 | FC | 6 | TRUE | TRUE | FALSE
7325 | MRT-XG02-P3LC-110007 | 2019-02-15 | MRT-DS-REC-TT-190035 | FC | 6 | TRUE | TRUE | FALSE
7326 | MRT-XJ00-P2PAB-142100 | 2019-02-15 | MRT-DS-REC-TT-190036 | FC | 2 | TRUE | TRUE | FALSE
7327 | MRT-XJ00-P3PAB-143100 | 2019-02-15 | MRT-DS-REC-TT-190036 | FC | 2 | TRUE | TRUE | FALSE
7328 | MRT-XJ00-P3PAB-144100 | 2019-02-15 | MRT-DS-REC-TT-190036 | FC | 2 | TRUE | TRUE | FALSE
8300 | MRT-QM01-P0ZEN-135006 | 2019-02-16 | MRT-HK-REC-TT-190474 | FA | 1 | TRUE | TRUE | FALSE
7329 | MRT-XR00-P3MAA-220040 | 2019-02-18 | MRT-DS-REC-TT-190037 | FI | 1 | TRUE | TRUE | FALSE
7330 | MRT-XN00-P2MAA-220038 | 2019-02-18 | MRT-DS-REC-TT-190037 | FI | 0 | TRUE | FALSE | FALSE
7331 | MRT-XN00-P2MAV-220039 | 2019-02-18 | MRT-DS-REC-TT-190037 | FI | 0 | TRUE | FALSE | FALSE
7332 | MRT-XN00-P3MAA-220038 | 2019-02-18 | MRT-DS-REC-TT-190037 | FI | 0 | TRUE | FALSE | FALSE
7333 | MRT-XN00-P3MAV-220039 | 2019-02-18 | MRT-DS-REC-TT-190037 | FI | 0 | TRUE | FALSE | FALSE
7334 | MRT-YF02-P2MAD-240168 | 2019-02-18 | MRT-DS-REC-TT-190037 | FI | 0 | TRUE | FALSE | FALSE
7335 | MRT-YL00-P2CJJ-240052 | 2019-02-18 | MRT-DS-REC-TT-190037 | FI | 0 | TRUE | FALSE | FALSE
7336 | MRT-YD00-P2LB-122052 | 2019-02-19 | MRT-DS-REC-TT-190038 | FC | 3 | TRUE | TRUE | FALSE
7337 | MRT-YD00-P3LB-122052 | 2019-02-19 | MRT-DS-REC-TT-190038 | FC | 3 | TRUE | TRUE | FALSE
7338 | MRT-XJ00-P2LBA-145000 | 2019-02-20 | MRT-DS-REC-TT-190039 | FI | 0 | TRUE | FALSE | FALSE
7339 | MRT-BT00-P0GEN-135706 | 2019-02-20 | MRT-HK-REC-TT-190475 | FA | 0 | TRUE | FALSE | FALSE
7340 | MRT-XK00-P0GDN-135040 | 2019-02-20 | MRT-HK-REC-TT-190475 | FI | 0 | TRUE | FALSE | FALSE
7341 | MRT-YD00-P2LB-122120 | 2019-02-20 | MRT-DS-REC-TT-190040 | FC | 1 | TRUE | TRUE | FALSE
7342 | MRT-UE00-P2LB-122008 | 2019-02-20 | MRT-DS-REC-TT-190041 | FC | 6 | TRUE | TRUE | FALSE
7343 | MRT-UE00-P3LB-122008 | 2019-02-20 | MRT-DS-REC-TT-190041 | FC | 4 | TRUE | TRUE | FALSE
7344 | MRT-XG01-P2MAA-220045 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 1 | TRUE | TRUE | FALSE
7345 | MRT-XG01-P3MAA-220045 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 1 | TRUE | TRUE | FALSE
7346 | MRT-DM02-P2CJJ-240114 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 0 | TRUE | FALSE | FALSE
7347 | MRT-DM02-P2CJJ-240123 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 0 | TRUE | FALSE | FALSE
7348 | MRT-DM02-P2LBA-220130 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 0 | TRUE | FALSE | FALSE
7349 | MRT-DM02-P2LBS-220087 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 0 | TRUE | FALSE | FALSE
7350 | MRT-DM02-P2LBS-220090 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 0 | TRUE | FALSE | FALSE
7351 | MRT-DM02-P2MAA-220131 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 0 | TRUE | FALSE | FALSE
7352 | MRT-DM02-P2MAA-220152 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 0 | TRUE | FALSE | FALSE
7353 | MRT-DM02-P2MAA-220155 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 0 | TRUE | FALSE | FALSE
7354 | MRT-XR00-P2MAA-220086 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 0 | TRUE | FALSE | FALSE
7355 | MRT-YL15-P2CJJ-240072 | 2019-02-20 | MRT-DS-REC-TT-190042 | FA | 0 | TRUE | FALSE | FALSE
7356 | MRT-YL15-P3CJJ-240072 | 2019-02-20 | MRT-DS-REC-TT-190042 | FA | 0 | TRUE | FALSE | FALSE
7357 | MRT-YL15-P3CJJ-240114 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 0 | TRUE | FALSE | FALSE
7358 | MRT-YL15-P3MAD-240181 | 2019-02-20 | MRT-DS-REC-TT-190042 | FI | 0 | TRUE | TRUE | FALSE
7359 | MRT-XJ00-P3LAB-146000 | 2019-02-21 | MRT-DS-REC-TT-190049 | FI | 0 | TRUE | FALSE | FALSE
7360 | MRT-DM01-P0ZEN-140002 | 2019-02-21 | MRT-DS-REC-TT-190050 | FI | 0 | TRUE | FALSE | FALSE
7361 | MRT-DL03-P0ZEN-140001 | 2019-02-21 | MRT-DS-REC-TT-190050 | FI | 0 | TRUE | FALSE | FALSE
7362 | MRT-YK10-P0QHA-125444 | 2019-02-21 | MRT-HK-REC-TT-190476 | FA | 0 | TRUE | FALSE | FALSE
7363 | MRT-XM00-P2BBT-150431 | 2019-02-21 | MRT-HK-REC-TT-190477 | FA | 1 | TRUE | TRUE | FALSE
7364 | MRT-XM00-P3BBT-150448 | 2019-02-21 | MRT-HK-REC-TT-190477 | FA | 1 | TRUE | TRUE | FALSE
7365 | MRT-YD00-P2BBB-150540 | 2019-02-21 | MRT-HK-REC-TT-190478 | FA | 0 | TRUE | FALSE | FALSE
7366 | MRT-YD00-P3BBB-150543 | 2019-02-21 | MRT-HK-REC-TT-190478 | FA | 0 | TRUE | FALSE | FALSE
7367 | MRT-YD00-P0BBB-150546 | 2019-02-21 | MRT-HK-REC-TT-190478 | FA | 0 | TRUE | FALSE | FALSE
7368 | MRT-YD00-P0BBB-150552 | 2019-02-21 | MRT-HK-REC-TT-190478 | FA | 0 | TRUE | FALSE | FALSE
7369 | MRT-YD00-P0BBB-150555 | 2019-02-21 | MRT-HK-REC-TT-190478 | FA | 0 | TRUE | FALSE | FALSE
7370 | MRT-XJ00-P3LBG-143000 | 2019-02-21 | MRT-DS-REC-TT-190045 | FC | 1 | TRUE | TRUE | FALSE
7371 | MRT-XK00-P0GDT-135033 | 2019-02-21 | MRT-HK-REC-TT-190479 | FI | 0 | TRUE | FALSE | FALSE
7372 | MRT-XK00-P0GDN-135036 | 2019-02-21 | MRT-HK-REC-TT-190479 | FI | 0 | TRUE | FALSE | FALSE
7373 | MRT-XK00-P0GDK-135039 | 2019-02-21 | MRT-HK-REC-TT-190479 | FI | 0 | TRUE | FALSE | FALSE
7374 | MRT-VL00-P2MAA-220001 | 2019-02-22 | MRT-DS-REC-TT-190033-FC | FC | 2 | TRUE | TRUE | FALSE
7375 | MRT-VL00-P3MAA-220001 | 2019-02-22 | MRT-DS-REC-TT-190033-FC | FC | 2 | TRUE | TRUE | FALSE
7376 | MRT-XT00-P2MAA-220002 | 2019-02-22 | MRT-DS-REC-TT-190033-FC | FC | 2 | TRUE | TRUE | FALSE
7377 | MRT-XT00-P3MAA-220002 | 2019-02-22 | MRT-DS-REC-TT-190033-FC | FC | 2 | TRUE | TRUE | FALSE
7378 | MRT-XJ00-P3LBA-146000 | 2019-02-22 | MRT-DS-REC-TT-190051 | FI | 0 | TRUE | FALSE | FALSE
7379 | MRT-XJ00-P3LBG-146000 | 2019-02-22 | MRT-DS-REC-TT-190051 | FI | 0 | TRUE | FALSE | FALSE
7380 | MRT-XJ00-P2LCM-145000 | 2019-02-22 | MRT-DS-REC-TT-190051 | FI | 0 | TRUE | FALSE | FALSE
7381 | MRT-XJ00-P3LCM-146000 | 2019-02-22 | MRT-DS-REC-TT-190051 | FI | 0 | TRUE | FALSE | FALSE
7382 | MRT-CQ02-P2LB-122118 | 2019-02-22 | MRT-DS-REC-TT-180908-FC | FC | 0 | TRUE | TRUE | FALSE
7383 | MRT-DN05-P2LB-122119 | 2019-02-22 | MRT-DS-REC-TT-180908-FC | FC | 0 | TRUE | TRUE | FALSE
7384 | MRT-XJ00-P2LBG-145000 | 2019-02-22 | MRT-DS-REC-TT-190052 | FI | 0 | TRUE | FALSE | FALSE
7385 | MRT-XJ00-P0LBG-140000 | 2019-02-22 | MRT-DS-REC-TT-190052 | FI | 0 | TRUE | FALSE | FALSE
7386 | MRT-XS01-P2CJJ-240060 | 2019-02-22 | MRT-DS-REC-TT-190053 | FI | 1 | TRUE | TRUE | FALSE
7387 | MRT-XJ00-P3LAB-143000 | 2019-02-25 | MRT-DS-REC-TT-190048 | FC | 1 | TRUE | TRUE | FALSE
7388 | MRT-BF05-P0ZEN-179003 | 2019-02-25 | MRT-HK-REC-TT-190480 | FI | 0 | TRUE | FALSE | FALSE
7389 | MRT-BF05-P0ZEN-179002 | 2019-02-25 | MRT-HK-REC-TT-190480 | FI | 0 | TRUE | FALSE | FALSE
7390 | MRT-BF05-P0ZEN-179001 | 2019-02-25 | MRT-HK-REC-TT-190480 | FI | 0 | TRUE | FALSE | FALSE
7391 | MRT-CV03-P0GEN-135381 | 2019-02-25 | MRT-HK-REC-TT-190481 | FA | 1 | TRUE | TRUE | FALSE
7392 | MRT-YK10-P0QHN-125448 | 2019-02-25 | MRT-HK-REC-TT-190482 | FA | 0 | TRUE | FALSE | FALSE
7393 | MRT-DT01-P0QHB-125429 | 2019-02-25 | MRT-HK-REC-TT-190482 | FA | 0 | TRUE | FALSE | FALSE
7394 | MRT-YF00-P3LB-122066 | 2019-02-25 | MRT-DS-REC-TT-180936-FC | FC | 0 | TRUE | TRUE | FALSE
7395 | MRT-XJ00-P3LAB-147000 | 2019-02-26 | MRT-DS-REC-TT-190054 | FI | 0 | TRUE | FALSE | FALSE
7397 | MRT-YB10-P0BBB-150535 | 2019-02-26 | MRT-HK-REC-TT-190483 | FA | 0 | TRUE | FALSE | FALSE
7398 | MRT-XJ00-P3PGB-143000 | 2019-02-26 | MRT-DS-REC-TT-190047 | FC | 1 | TRUE | TRUE | FALSE
7399 | MRT-YD00-P2BBB-150538 | 2019-02-26 | MRT-HK-REC-TT-190484 | FA | 1 | TRUE | TRUE | FALSE
7400 | MRT-YD00-P3BBB-150541 | 2019-02-26 | MRT-HK-REC-TT-190484 | FA | 1 | TRUE | TRUE | FALSE
7401 | MRT-YD00-P0BBB-150544 | 2019-02-26 | MRT-HK-REC-TT-190484 | FA | 1 | TRUE | TRUE | FALSE
7402 | MRT-YF01-P0BFB-150235 | 2019-02-26 | MRT-HK-REC-TT-190484 | FA | 0 | TRUE | FALSE | FALSE
7403 | MRT-YS01-P0BFB-150112 | 2019-02-26 | MRT-HK-REC-TT-190484 | FA | 0 | TRUE | FALSE | FALSE
7404 | MRT-YM02-P2BAA-150482 | 2019-02-26 | MRT-HK-REC-TT-190484 | FA | 0 | TRUE | FALSE | FALSE
7405 | MRT-BF01-P3CYP-160008 | 2019-02-26 | MRT-HK-REC-TT-190485 | FA | 1 | TRUE | TRUE | FALSE
7406 | MRT-XS00-P0GEN-135300 | 2019-02-27 | MRT-HK-REC-TT-190486 | FA | 2 | TRUE | TRUE | FALSE
7407 | MRT-YK10-P0QHB-125446 | 2019-02-27 | MRT-HK-REC-TT-190487 | FA | 0 | TRUE | FALSE | FALSE
7408 | MRT-YK10-P0QHE-125454 | 2019-02-27 | MRT-HK-REC-TT-190487 | FA | 0 | TRUE | FALSE | FALSE
7409 | MRT-YK10-P0QHN-125451 | 2019-02-27 | MRT-HK-REC-TT-190487 | FA | 0 | TRUE | FALSE | FALSE
7410 | MRT-CC02-P2UHA-170009 | 2019-02-27 | MRT-DS-REC-TT-190055 | FC | 4 | TRUE | TRUE | FALSE
7411 | MRT-CC02-P3UHA-170009 | 2019-02-27 | MRT-DS-REC-TT-190055 | FC | 4 | TRUE | TRUE | FALSE
7412 | MRT-XP00-P3BAC-150415 | 2019-02-28 | MRT-HK-REC-TT-190488 | FA | 1 | TRUE | TRUE | FALSE
7413 | MRT-XP00-P0BTA-150637 | 2019-02-28 | MRT-HK-REC-TT-190488 | FA | 0 | TRUE | TRUE | FALSE
7414 | MRT-CH04-P0BBA-150453 | 2019-02-28 | MRT-HK-REC-TT-190488 | FA | 0 | TRUE | TRUE | FALSE
7415 | MRT-YM02-P2BAA-150492 | 2019-02-28 | MRT-HK-REC-TT-190488 | FA | 0 | TRUE | TRUE | FALSE
7416 | MRT-YM02-P3BAA-150950 | 2019-02-28 | MRT-HK-REC-TT-190488 | FA | 0 | TRUE | TRUE | FALSE
7417 | MRT-YD00-P0BBB-150549 | 2019-02-28 | MRT-HK-REC-TT-190488 | FA | 0 | TRUE | TRUE | FALSE
7418 | MRT-XP00-P2BAC-150392 | 2019-02-28 | MRT-HK-REC-TT-190488 | FA | 0 | TRUE | TRUE | FALSE
7419 | MRT-XP00-P0BTL-150125 | 2019-02-28 | MRT-HK-REC-TT-190488 | FA | 0 | TRUE | TRUE | FALSE
7420 | MRT-CH04-P0BTL-150638 | 2019-02-28 | MRT-HK-REC-TT-190488 | FA | 0 | TRUE | TRUE | FALSE
7421 | MRT-BT00-P0BTL-150639 | 2019-02-28 | MRT-HK-REC-TT-190488 | FA | 0 | TRUE | TRUE | FALSE
7422 | MRT-BT00-P0BTA-150635 | 2019-02-28 | MRT-HK-REC-TT-190488 | FA | 0 | TRUE | TRUE | FALSE
7423 | MRT-HM05-P00SA-135504 | 2019-02-28 | MRT-HK-REC-TT-190489 | FA | 3 | TRUE | FALSE | FALSE
7424 | MRT-XJ00-P2PGB-145000 | 2019-02-28 | MRT-DS-REC-TT-190057 | FI | 0 | TRUE | FALSE | FALSE
7425 | MRT-CC02-P3UMA-170207 | 2019-02-28 | MRT-DS-REC-TT-190058 | FC | 5 | TRUE | TRUE | FALSE
7426 | MRT-XG02-P2SCA-120004 | 2019-02-28 | MRT-DS-REC-TT-190019-FC | FC | 5 | TRUE | TRUE | FALSE
7427 | MRT-XG02-P2SCA-120005 | 2019-02-28 | MRT-DS-REC-TT-190019-FC | FC | 5 | TRUE | TRUE | FALSE
7428 | MRT-XG02-P2SCA-120006 | 2019-02-28 | MRT-DS-REC-TT-190019-FC | FC | 5 | TRUE | TRUE | FALSE
7429 | MRT-XG02-P3SCA-120004 | 2019-02-28 | MRT-DS-REC-TT-190019-FC | FC | 5 | TRUE | TRUE | FALSE
7430 | MRT-XG02-P3SCA-120005 | 2019-02-28 | MRT-DS-REC-TT-190019-FC | FC | 5 | TRUE | TRUE | FALSE
7431 | MRT-XG02-P3SCA-120006 | 2019-02-28 | MRT-DS-REC-TT-190019-FC | FC | 5 | TRUE | TRUE | FALSE
7432 | MRT-CV03-P0ZEN-140002 | 2019-02-28 | MRT-DS-REC-TT-190060 | FC | 3 | TRUE | TRUE | FALSE
7433 | MRT-XJ00-P3LCA-143000 | 2019-02-28 | MRT-DS-REC-TT-190046 | FC | 1 | TRUE | TRUE | FALSE
8092 | MRT-DP00-P0SA-135738 | 2019-03-01 | MRT-HK-REC-TT-180492 | FA | 0 | TRUE | FALSE | FALSE
8093 | MRT-DP00-P0SA-135739 | 2019-03-01 | MRT-HK-REC-TT-180492 | FA | 0 | TRUE | FALSE | FALSE
7434 | MRT-UC07-P0ZEN-100001 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7435 | MRT-UC08-P0ZEN-100002 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 4 | TRUE | TRUE | FALSE
7436 | MRT-UC08-P0ZEN-100003 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 4 | TRUE | TRUE | FALSE
7437 | MRT-UE00-P2ZEN-100004 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7438 | MRT-UE00-P2ZEN-100005 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7439 | MRT-UE00-P2ZEN-100006 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7440 | MRT-UE00-P2ZEN-100007 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7441 | MRT-UE00-P2ZEN-100008 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7442 | MRT-UE00-P2ZEN-100009 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7443 | MRT-UE00-P3ZEN-100010 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7444 | MRT-UE00-P3ZEN-100011 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7445 | MRT-UE00-P3ZEN-100012 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7446 | MRT-UE00-P3ZEN-100013 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7447 | MRT-UE00-P3ZEN-100014 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7448 | MRT-UE00-P3ZEN-100015 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 5 | TRUE | TRUE | FALSE
7449 | MRT-UE00-P2ZEN-100016 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 3 | TRUE | TRUE | FALSE
7450 | MRT-UE00-P3ZEN-100017 | 2019-03-04 | MRT-DS-REC-TT-190059 | FC | 3 | TRUE | TRUE | FALSE
7451 | MRT-XJ00-P3LCA-146000 | 2019-03-04 | MRT-DS-REC-TT-190061 | FI | 0 | TRUE | FALSE | FALSE
7452 | MRT-XJ00-P3PGB-146000 | 2019-03-04 | MRT-DS-REC-TT-190061 | FI | 0 | TRUE | FALSE | FALSE
7453 | MRT-YD00-P2ASU-150008 | 2019-03-04 | MRT-HK-REC-TT-190490 | FA | 0 | TRUE | FALSE | FALSE
7454 | MRT-YD00-P2ASU-150007 | 2019-03-04 | MRT-HK-REC-TT-190490 | FA | 0 | TRUE | FALSE | FALSE
7455 | MRT-YD00-P2ASU-150006 | 2019-03-04 | MRT-HK-REC-TT-190490 | FA | 0 | TRUE | FALSE | FALSE
7456 | MRT-YD00-P2ASU-150005 | 2019-03-04 | MRT-HK-REC-TT-190490 | FA | 0 | TRUE | FALSE | FALSE
7457 | MRT-YD00-P2ASU-150004 | 2019-03-04 | MRT-HK-REC-TT-190490 | FA | 0 | TRUE | FALSE | FALSE
7458 | MRT-YD00-P2ASU-150003 | 2019-03-04 | MRT-HK-REC-TT-190490 | FA | 0 | TRUE | FALSE | FALSE
7459 | MRT-YD00-P2ASU-150002 | 2019-03-04 | MRT-HK-REC-TT-190490 | FA | 0 | TRUE | FALSE | FALSE
7460 | MRT-YD00-P2ASU-150001 | 2019-03-04 | MRT-HK-REC-TT-190490 | FA | 0 | TRUE | FALSE | FALSE
7461 | MRT-XW03-P0GEN-135301 | 2019-03-04 | MRT-HK-REC-TT-190491 | FA | 3 | TRUE | TRUE | FALSE
7462 | MRT-CC03-P0UPC-176387 | 2019-03-04 | MRT-HK-REC-TT-190493 | FA | 0 | TRUE | FALSE | FALSE
7463 | MRT-CC03-P0UPC-176386 | 2019-03-04 | MRT-HK-REC-TT-190493 | FA | 0 | TRUE | FALSE | FALSE
7464 | MRT-CC01-P0UAA-176095 | 2019-03-04 | MRT-HK-REC-TT-190493 | FA | 0 | TRUE | FALSE | FALSE
7465 | MRT-CA01-P0UXA-186688 | 2019-03-04 | MRT-HK-REC-TT-190493 | FA | 1 | TRUE | TRUE | FALSE
7466 | MRT-CA01-P0UXA-186690 | 2019-03-04 | MRT-HK-REC-TT-190493 | FA | 1 | TRUE | TRUE | FALSE
7467 | MRT-CC03-P0UPC-176361 | 2019-03-04 | MRT-HK-REC-TT-190493 | FA | 1 | TRUE | TRUE | FALSE
7468 | MRT-CC03-P0UPC-176383 | 2019-03-04 | MRT-HK-REC-TT-190493 | FA | 1 | TRUE | TRUE | FALSE
7469 | MRT-CA01-P0UXA-186683 | 2019-03-04 | MRT-HK-REC-TT-190493 | FA | 1 | TRUE | TRUE | FALSE
7470 | MRT-DM02-P3MAX-220145 | 2019-03-04 | MRT-DS-REC-TT-190062 | FI | 0 | TRUE | FALSE | FALSE
7471 | MRT-DM02-P3MAV-220097 | 2019-03-04 | MRT-DS-REC-TT-190062 | FI | 0 | TRUE | FALSE | FALSE
7472 | MRT-DM02-P3LBA-220129 | 2019-03-04 | MRT-DS-REC-TT-190062 | FI | 0 | TRUE | FALSE | FALSE
7473 | MRT-YR00-P2CJJ-240055 | 2019-03-04 | MRT-DS-REC-TT-190062 | FI | 1 | TRUE | TRUE | FALSE
7474 | MRT-UF00-P3MAA-220023 | 2019-03-04 | MRT-DS-REC-TT-190062 | FI | 1 | TRUE | TRUE | FALSE
7475 | MRT-YR00-P3CJJ-240055 | 2019-03-04 | MRT-DS-REC-TT-190062 | FI | 1 | TRUE | TRUE | FALSE
7476 | MRT-CQ02-P2MAA-220201 | 2019-03-04 | MRT-DS-REC-TT-190062 | FI | 0 | TRUE | FALSE | FALSE
7477 | MRT-DM02-P3MAA-220174 | 2019-03-04 | MRT-DS-REC-TT-190062 | FI | 0 | TRUE | FALSE | FALSE
7478 | MRT-UE00-P2LB-122010 | 2019-03-05 | MRT-DS-REC-TT-190063 | FC | 4 | TRUE | TRUE | FALSE
7479 | MRT-UE00-P3LB-122010 | 2019-03-05 | MRT-DS-REC-TT-190063 | FC | 4 | TRUE | TRUE | FALSE
7480 | MRT-CC02-P3UMA-170707 | 2019-03-05 | MRT-DS-REC-TT-190064 | FC | 5 | TRUE | TRUE | FALSE
7481 | MRT-CC02-P3UMA-170708 | 2019-03-05 | MRT-DS-REC-TT-190064 | FC | 5 | TRUE | TRUE | FALSE
7482 | MRT-CC02-P3UMA-170709 | 2019-03-05 | MRT-DS-REC-TT-190064 | FC | 5 | TRUE | TRUE | FALSE
7483 | MRT-VK02-P3UMA-170710 | 2019-03-05 | MRT-DS-REC-TT-190064 | FC | 4 | TRUE | TRUE | FALSE
7484 | MRT-YK10-P2MAA-185127 | 2019-03-05 | MRT-HK-REC-TT-190494 | FI | 0 | TRUE | FALSE | FALSE
7485 | MRT-DP00-P0ZEN-070528 | 2019-03-05 | MRT-HK-REC-TT-190495 | FA | 0 | TRUE | FALSE | FALSE
7486 | MRT-CH04-P0UZT-150656 | 2019-03-05 | MRT-HK-REC-TT-190495 | FA | 0 | TRUE | FALSE | FALSE
7487 | MRT-XJ00-P2LCA-145000 | 2019-03-05 | MRT-DS-REC-TT-190065 | FI | 0 | TRUE | FALSE | FALSE
7488 | MRT-YU02-P2BBA-150458 | 2019-03-06 | MRT-HK-REC-TT-190497 | FA | 1 | TRUE | TRUE | FALSE
7489 | MRT-YU02-P0BBA-150462 | 2019-03-06 | MRT-HK-REC-TT-190497 | FA | 1 | TRUE | TRUE | FALSE
7490 | MRT-YU02-P3BBA-150460 | 2019-03-06 | MRT-HK-REC-TT-190497 | FA | 1 | TRUE | TRUE | FALSE
7491 | MRT-CA03-P0UMA-180026 | 2019-03-06 | MRT-DS-REC-TT-190066 | FC | 5 | TRUE | TRUE | FALSE
7492 | MRT-CA01-P0UMA-180027 | 2019-03-06 | MRT-DS-REC-TT-190066 | FC | 5 | TRUE | TRUE | FALSE
7493 | MRT-CA03-P0UMA-180028 | 2019-03-06 | MRT-DS-REC-TT-190066 | FC | 5 | TRUE | TRUE | FALSE
7494 | MRT-CA03-P0UMA-180029 | 2019-03-06 | MRT-DS-REC-TT-190066 | FC | 5 | TRUE | TRUE | FALSE
7495 | MRT-CA03-P0UMA-180033 | 2019-03-06 | MRT-DS-REC-TT-190066 | FC | 5 | TRUE | TRUE | FALSE
7496 | MRT-CA03-P0UMA-180034 | 2019-03-06 | MRT-DS-REC-TT-190066 | FC | 5 | TRUE | TRUE | FALSE
7497 | MRT-CA03-P0UMA-180030 | 2019-03-06 | MRT-DS-REC-TT-190066 | FC | 5 | TRUE | TRUE | FALSE
7498 | MRT-BT00-P0BFB-150664 | 2019-03-06 | MRT-HK-REC-TT-190496 | FA | 0 | TRUE | FALSE | FALSE
7499 | MRT-CH04-P0BFB-150661 | 2019-03-06 | MRT-HK-REC-TT-190496 | FA | 0 | TRUE | FALSE | FALSE
7500 | MRT-XA01-P0ABA-150515 | 2019-03-06 | MRT-HK-REC-TT-190496 | FA | 0 | TRUE | FALSE | FALSE
7501 | MRT-CC07-P0UYX-175151 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7502 | MRT-CC02-P0UYX-175161 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7503 | MRT-CC07-P0UYX-175251 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7504 | MRT-CC02-P0UYX-175271 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7505 | MRT-CC07-P0UYX-175311 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7506 | MRT-CC02-P0UYX-175331 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7507 | MRT-CC07-P0UZT-175915 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7508 | MRT-CC02-P0UZT-175920 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7509 | MRT-CC02-P0UZT-175925 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7510 | MRT-CC02-P0UZT-175930 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7511 | MRT-CC02-P0UYX-175332 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7512 | MRT-CC02-P0UYX-175333 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7513 | MRT-CC02-P0UYX-175334 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7514 | MRT-CC02-P0UYX-175335 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7515 | MRT-CC02-P0UYX-175272 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7516 | MRT-CC02-P0UYX-175273 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7517 | MRT-CC02-P0UYX-175274 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7518 | MRT-CC02-P0UYX-175275 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7519 | MRT-CC02-P0UYX-175276 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7520 | MRT-CC02-P0UYX-175336 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7521 | MRT-CC02-P0UYX-175162 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7522 | MRT-CC02-P0UYX-175163 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7523 | MRT-CC02-P0UYX-175164 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7524 | MRT-CC02-P0UYX-175165 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7525 | MRT-CC02-P0UYX-175166 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7526 | MRT-CC02-P0UYX-175167 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7527 | MRT-CC02-P0UYX-175168 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7528 | MRT-CC02-P0UYX-175169 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7529 | MRT-CC02-P0UYX-175170 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7530 | MRT-CC02-P0UYX-175171 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7531 | MRT-CC02-P0UYX-175172 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7532 | MRT-CC02-P0UYX-175173 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7533 | MRT-CC02-P0UYX-175180 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7534 | MRT-CC02-P0UYX-175174 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7535 | MRT-CC02-P0UYX-175175 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7536 | MRT-CC02-P0UYX-175176 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7537 | MRT-CC02-P0UYX-175177 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7538 | MRT-CC02-P0UYX-175178 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7539 | MRT-CC02-P0UYX-175179 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7540 | MRT-CC02-P0UZT-175924 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7541 | MRT-CC02-P0UZT-175923 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7542 | MRT-CC02-P0UZT-175922 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7543 | MRT-CC02-P0UZT-175921 | 2019-03-06 | MRT-HK-REC-TT-190498 | FA | 0 | TRUE | TRUE | FALSE
7544 | MRT-QM03-P0ZEN-185012 | 2019-03-06 | MRT-HK-REC-TT-190499 | FI | 0 | TRUE | FALSE | FALSE
7545 | MRT-YT01-P3AYA-160010 | 2019-03-06 | MRT-HK-REC-TT-190501 | FA | 0 | TRUE | FALSE | FALSE
7546 | MRT-CC02-P2UHA-170009 | 2019-03-06 | MRT-DS-REC-TT-190055-FC | FC | 4 | TRUE | TRUE | FALSE
7547 | MRT-CC02-P3UHA-170009 | 2019-03-06 | MRT-DS-REC-TT-190055-FC | FC | 4 | TRUE | TRUE | FALSE
7548 | MRT-CQ02-P3MKW-260001 | 2019-03-06 | MRT-DS-REC-TT-190020-FC | FC | 0 | TRUE | TRUE | FALSE
7549 | MRT-CQ02-P3MKG-260001 | 2019-03-06 | MRT-DS-REC-TT-190020-FC | FC | 0 | TRUE | TRUE | FALSE
7550 | MRT-YR02-P2MKC-230001 | 2019-03-07 | MRT-DS-REC-TT-190068 | FI | 0 | TRUE | FALSE | FALSE
7551 | MRT-YR02-P3MKC-230001 | 2019-03-07 | MRT-DS-REC-TT-190068 | FI | 0 | TRUE | FALSE | FALSE
7552 | MRT-VN03-P2LB-122015 | 2019-03-07 | MRT-DS-REC-TT-190026-FC | FC | 4 | TRUE | TRUE | FALSE
7553 | MRT-VN03-P3LB-122015 | 2019-03-07 | MRT-DS-REC-TT-190026-FC | FC | 4 | TRUE | TRUE | FALSE
7554 | MRT-XH01-P0UZT-140000 | 2019-03-07 | MRT-DS-REC-TT-190031-FC | FC | 2 | TRUE | TRUE | FALSE
7555 | MRT-UE00-P2LB-122008 | 2019-03-07 | MRT-DS-REC-TT-190041-FC | FC | 6 | TRUE | TRUE | FALSE
7556 | MRT-UE00-P3LB-122008 | 2019-03-07 | MRT-DS-REC-TT-190041-FC | FC | 4 | TRUE | TRUE | FALSE
7557 | MRT-YR05-P0GDY-135065 | 2019-03-07 | MRT-DS-REC-TT-190500 | FI | 0 | TRUE | FALSE | FALSE
7558 | MRT-CA00-P0UCA-180107 | 2019-03-08 | MRT-DS-REC-TT-190071 | FC | 6 | TRUE | TRUE | FALSE
7559 | MRT-CA00-P0UCA-180108 | 2019-03-08 | MRT-DS-REC-TT-190071 | FC | 6 | TRUE | TRUE | FALSE
7560 | MRT-DP00-P2LB-122122 | 2019-03-08 | MRT-DS-REC-TT-190070 | FA | 0 | TRUE | FALSE | FALSE
7561 | MRT-DP00-P3LB-122122 | 2019-03-08 | MRT-DS-REC-TT-190070 | FA | 0 | TRUE | FALSE | FALSE
7562 | MRT-YB03-P2LB-122048 | 2019-03-08 | MRT-DS-REC-TT-190069 | FC | 2 | TRUE | TRUE | FALSE
7563 | MRT-YB03-P3LB-122048 | 2019-03-08 | MRT-DS-REC-TT-190069 | FC | 2 | TRUE | TRUE | FALSE
7564 | MRT-XJ00-P3LBA-143000 | 2019-03-08 | MRT-DS-REC-TT-190043 | FC | 1 | TRUE | TRUE | FALSE
7565 | MRT-XJ00-P0GHC-141000 | 2019-03-08 | MRT-DS-REC-TT-190072 | FI | 0 | TRUE | FALSE | FALSE
7566 | MRT-XH01-P2LB-122112 | 2019-03-08 | MRT-DS-REC-TT-190073 | FC | 2 | TRUE | TRUE | FALSE
7567 | MRT-XH01-P3LB-122112 | 2019-03-08 | MRT-DS-REC-TT-190073 | FC | 2 | TRUE | TRUE | FALSE
7568 | MRT-XJ00-P2PAB-142100 | 2019-03-11 | MRT-DS-REC-TT-190036-FC | FC | 2 | TRUE | TRUE | FALSE
7569 | MRT-XJ00-P3PAB-143100 | 2019-03-11 | MRT-DS-REC-TT-190036-FC | FC | 2 | TRUE | TRUE | FALSE
7570 | MRT-XJ00-P3PAB-144100 | 2019-03-11 | MRT-DS-REC-TT-190036-FC | FC | 2 | TRUE | TRUE | FALSE
7571 | MRT-YD00-P2LB-122052 | 2019-03-11 | MRT-DS-REC-TT-190038-FC | FC | 3 | TRUE | TRUE | FALSE
7572 | MRT-XN00-P2MAA-220038 | 2019-03-11 | MRT-DS-REC-TT-190037-FC | FC | 0 | TRUE | TRUE | FALSE
7573 | MRT-XN00-P2MAV-220039 | 2019-03-11 | MRT-DS-REC-TT-190037-FC | FC | 0 | TRUE | TRUE | FALSE
7574 | MRT-XN00-P3MAA-220038 | 2019-03-11 | MRT-DS-REC-TT-190037-FC | FC | 0 | TRUE | TRUE | FALSE
7575 | MRT-XN00-P3MAV-220039 | 2019-03-11 | MRT-DS-REC-TT-190037-FC | FC | 0 | TRUE | TRUE | FALSE
7576 | MRT-YD00-P3LB-122052 | 2019-03-11 | MRT-DS-REC-TT-190038-FC | FC | 3 | TRUE | TRUE | FALSE
7577 | MRT-YT01-P3MKA-240003 | 2019-03-11 | MRT-DS-REC-TT-190074 | FI | 4 | TRUE | TRUE | FALSE
7578 | MRT-YE00-P2UMA-150171 | 2019-03-11 | MRT-HK-REC-TT-190502 | FA | 0 | TRUE | FALSE | FALSE
7579 | MRT-YE00-P3UMA-150172 | 2019-03-11 | MRT-HK-REC-TT-190502 | FA | 0 | TRUE | FALSE | FALSE
7580 | MRT-YB01-P2BAA-150487 | 2019-03-11 | MRT-HK-REC-TT-190503 | FA | 0 | TRUE | FALSE | FALSE
7581 | MRT-XP00-P3BBT-150449 | 2019-03-11 | MRT-HK-REC-TT-190503 | FA | 0 | TRUE | FALSE | FALSE
7582 | MRT-XP00-P2BBT-150432 | 2019-03-11 | MRT-HK-REC-TT-190503 | FA | 0 | TRUE | FALSE | FALSE
7583 | MRT-UE00-P2LB-122007 | 2019-03-12 | MRT-DS-REC-TT-190075 | FC | 4 | TRUE | TRUE | FALSE
7584 | MRT-UE00-P3LB-122007 | 2019-03-12 | MRT-DS-REC-TT-190075 | FC | 3 | TRUE | TRUE | FALSE
7585 | MRT-YL15-P0GEN-135393 | 2019-03-12 | MRT-HK-REC-TT-190504 | FA | 1 | TRUE | TRUE | FALSE
7586 | MRT-YT01-P0EKF-125610 | 2019-03-12 | MRT-HK-REC-TT-190505 | FA | 2 | TRUE | TRUE | FALSE
7587 | MRT-CC05-P0EKF-125613 | 2019-03-12 | MRT-HK-REC-TT-190505 | FA | 2 | TRUE | TRUE | FALSE
7588 | MRT-YT01-P0GEN-135363 | 2019-03-12 | MRT-HK-REC-TT-190506 | FA | 0 | TRUE | FALSE | FALSE
7589 | MRT-DT01-P0QHB-125427 | 2019-03-12 | MRT-HK-REC-TT-190507 | FA | 0 | TRUE | FALSE | FALSE
7590 | MRT-FF00-P0SGA-135462 | 2019-03-12 | MRT-HK-REC-TT-190508 | FA | 0 | TRUE | FALSE | FALSE
7591 | MRT-YR05-P0GDY-135067 | 2019-03-12 | MRT-HK-REC-TT-190509 | FA | 0 | TRUE | FALSE | FALSE
7592 | MRT-YD05-P0GDY-135060 | 2019-03-12 | MRT-HK-REC-TT-190509 | FA | 0 | TRUE | FALSE | FALSE
7593 | MRT-YL01-P0GDY-135064 | 2019-03-12 | MRT-HK-REC-TT-190510 | FA | 0 | TRUE | FALSE | FALSE
8061 | MRT-YD02-P2ZEN-165019 | 2019-03-12 | MRT-HK-REC-TT-190512 | FA | 0 | TRUE | FALSE | FALSE
7594 | MRT-XJ00-P2LB-122027 | 2019-03-13 | MRT-DS-REC-TT-190076 | FC | 2 | TRUE | TRUE | FALSE
7595 | MRT-XJ00-P3LB-122027 | 2019-03-13 | MRT-DS-REC-TT-190076 | FC | 2 | TRUE | TRUE | FALSE
7596 | MRT-XJ00-P3LCM-143000 | 2019-03-13 | MRT-DS-REC-TT-190044 | FC | 1 | TRUE | TRUE | FALSE
7597 | MRT-YD00-P0BFT-150590 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7598 | MRT-YD00-P0BFT-150589 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7599 | MRT-YD00-P0BFT-150592 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7600 | MRT-YD00-P0BFT-150593 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7601 | MRT-YD00-P0BFT-150597 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7602 | MRT-YD00-P0BFT-150598 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7603 | MRT-YD00-P0BFT-150600 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7604 | MRT-YD00-P0BFT-150601 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7605 | MRT-YD00-P0BFT-150605 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7606 | MRT-YD00-P0BFT-150606 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7607 | MRT-YD00-P0BFT-150608 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7608 | MRT-YD00-P0BFT-150609 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7609 | MRT-YV02-P0BFT-150594 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7610 | MRT-YV02-P0BFT-150602 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7611 | MRT-YV02-P0BFT-150610 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7612 | MRT-YT01-P0ANA-150641 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7613 | MRT-XA01-P0ABA-150516 | 2019-03-13 | MRT-HK-REC-TT-190511 | FA | 0 | TRUE | FALSE | FALSE
7614 | MRT-XR00-P2MAA-220040 | 2019-03-14 | MRT-DS-REC-TT-180843-FC | FC | 0 | TRUE | TRUE | FALSE
7615 | MRT-XR00-P3MAA-220040 | 2019-03-14 | MRT-DS-REC-TT-190037-FC | FC | 1 | TRUE | TRUE | FALSE
7616 | MRT-XR00-P2MAV-220041 | 2019-03-14 | MRT-DS-REC-TT-180816-FC | FC | 0 | TRUE | TRUE | FALSE
7620 | MRT-YT02-P2CJJ-240120 | 2019-03-14 | MRT-DS-REC-TT-180759-FC | FC | 0 | TRUE | TRUE | FALSE
7621 | MRT-YT02-P3CJJ-240112 | 2019-03-14 | MRT-DS-REC-TT-180759-FC | FC | 0 | TRUE | TRUE | FALSE
7622 | MRT-XK00-P3MAA-220207 | 2019-03-14 | MRT-DS-REC-TT-190077 | FI | 0 | TRUE | FALSE | FALSE
7623 | MRT-XR00-P3MAV-220041 | 2019-03-14 | MRT-DS-REC-TT-190077 | FI | 0 | TRUE | FALSE | FALSE
7624 | MRT-XS01-P3CJJ-240060 | 2019-03-14 | MRT-DS-REC-TT-190077 | FI | 1 | TRUE | TRUE | FALSE
7625 | MRT-XG02-P3MAV-220006 | 2019-03-14 | MRT-DS-REC-TT-190078 | FC | 2 | TRUE | TRUE | FALSE
7626 | MRT-XV00-P3MAV-220037 | 2019-03-14 | MRT-DS-REC-TT-190078 | FC | 4 | TRUE | TRUE | FALSE
7627 | MRT-YE00-P0UST-150166 | 2019-03-14 | MRT-HK-REC-TT-190513 | FA | 0 | TRUE | FALSE | FALSE
7628 | MRT-YE00-P0UTH-150170 | 2019-03-14 | MRT-HK-REC-TT-190513 | FA | 0 | TRUE | FALSE | FALSE
7629 | MRT-XJ00-P2LB-122028 | 2019-03-14 | MRT-DS-REC-TT-190079 | FC | 3 | TRUE | TRUE | FALSE
7630 | MRT-XJ00-P3LB-122028 | 2019-03-14 | MRT-DS-REC-TT-190079 | FC | 3 | TRUE | TRUE | FALSE
7631 | MRT-DD00-P0BAT-155116 | 2019-03-15 | MRT-HK-REC-TT-190514 | FI | 0 | TRUE | FALSE | FALSE
7632 | MRT-XJ00-P3LCM-147000 | 2019-03-15 | MRT-DS-REC-TT-190080 | FI | 0 | TRUE | FALSE | FALSE
7633 | MRT-XJ00-P0GKB-141000 | 2019-03-15 | MRT-DS-REC-TT-190080 | FI | 0 | TRUE | FALSE | FALSE
7634 | MRT-YD00-P2CJA-240057 | 2019-03-18 | MRT-DS-REC-TT-190007-FC | FC | 1 | TRUE | TRUE | FALSE
7635 | MRT-YD00-P2CJA-240058 | 2019-03-18 | MRT-DS-REC-TT-190007-FC | FC | 1 | TRUE | TRUE | FALSE
7636 | MRT-YD00-P2CJA-240059 | 2019-03-18 | MRT-DS-REC-TT-190007-FC | FC | 1 | TRUE | TRUE | FALSE
7637 | MRT-YD00-P3CJA-240057 | 2019-03-18 | MRT-DS-REC-TT-190007-FC | FC | 1 | TRUE | TRUE | FALSE
7638 | MRT-YD00-P3CJA-240058 | 2019-03-18 | MRT-DS-REC-TT-190007-FC | FC | 1 | TRUE | TRUE | FALSE
7639 | MRT-YD00-P3CJA-240059 | 2019-03-18 | MRT-DS-REC-TT-190007-FC | FC | 1 | TRUE | TRUE | FALSE
7640 | MRT-YT01-P2SM-128030 | 2019-03-18 | MRT-DS-REC-TT-180402-FC | FC | 0 | TRUE | TRUE | FALSE
7641 | MRT-YT01-P3SM-128030 | 2019-03-18 | MRT-DS-REC-TT-180402-FC | FC | 0 | TRUE | TRUE | FALSE
7642 | MRT-YK09-P2SM-128040 | 2019-03-18 | MRT-DS-REC-TT-180841-FC | FC | 1 | TRUE | TRUE | FALSE
7643 | MRT-YK09-P3SM-128040 | 2019-03-18 | MRT-DS-REC-TT-180841-FC | FC | 1 | TRUE | TRUE | FALSE
7644 | MRT-YS18-P2SM-128050 | 2019-03-18 | MRT-DS-REC-TT-180420-FC | FC | 0 | TRUE | TRUE | FALSE
7645 | MRT-YS18-P3SM-128050 | 2019-03-18 | MRT-DS-REC-TT-180420-FC | FC | 0 | TRUE | TRUE | FALSE
7646 | MRT-CC02-P3UMA-170707 | 2019-03-18 | MRT-DS-REC-TT-190064-FC | FC | 5 | TRUE | TRUE | FALSE
7647 | MRT-CC02-P3UMA-170708 | 2019-03-18 | MRT-DS-REC-TT-190064-FC | FC | 5 | TRUE | TRUE | FALSE
7648 | MRT-CC02-P3UMA-170709 | 2019-03-18 | MRT-DS-REC-TT-190064-FC | FC | 5 | TRUE | TRUE | FALSE
7649 | MRT-VK02-P3UMA-170710 | 2019-03-18 | MRT-DS-REC-TT-190064-FC | FC | 4 | TRUE | TRUE | FALSE
7650 | MRT-CC02-P2UAG-170307 | 2019-03-18 | MRT-DS-REC-TT-190081 | FC | 3 | TRUE | TRUE | FALSE
7651 | MRT-CC02-P2UAG-170308 | 2019-03-18 | MRT-DS-REC-TT-190081 | FC | 4 | TRUE | TRUE | FALSE
7652 | MRT-VK02-P2UAG-170310 | 2019-03-18 | MRT-DS-REC-TT-190081 | FC | 2 | TRUE | TRUE | FALSE
7653 | MRT-YM02-P2BAA-150488 | 2019-03-18 | MRT-HK-REC-TT-190515 | FA | 0 | TRUE | FALSE | FALSE
7654 | MRT-XG02-P0SGA-135413 | 2019-03-18 | MRT-HK-REC-TT-190516 | FA | 0 | TRUE | FALSE | FALSE
7655 | MRT-XG02-P0SGF-135421 | 2019-03-19 | MRT-HK-REC-TT-190517 | FA | 0 | TRUE | FALSE | FALSE
7656 | MRT-FF01-P0SGA-135437 | 2019-03-19 | MRT-HK-REC-TT-190517 | FA | 0 | TRUE | FALSE | FALSE
7657 | MRT-BT00-P3PAC-130001 | 2019-03-19 | MRT-HK-REC-TT-190519 | FA | 0 | TRUE | FALSE | FALSE
7658 | MRT-XW01-P0GEN-135704 | 2019-03-19 | MRT-HK-REC-TT-190520 | FA | 0 | TRUE | FALSE | FALSE
7659 | MRT-XG02-P2SGE-135406 | 2019-03-19 | MRT-HK-REC-TT-190520 | FA | 0 | TRUE | FALSE | FALSE
7660 | MRT-XP00-P0BFA-150321 | 2019-03-19 | MRT-HK-REC-TT-190521 | FA | 0 | TRUE | FALSE | FALSE
7661 | MRT-CV05-P0BAU-150894 | 2019-03-19 | MRT-HK-REC-TT-190521 | FA | 0 | TRUE | FALSE | FALSE
7662 | MRT-CV05-P0BFA-150897 | 2019-03-19 | MRT-HK-REC-TT-190521 | FA | 0 | TRUE | FALSE | FALSE
7663 | MRT-CV05-P0BFA-150895 | 2019-03-19 | MRT-HK-REC-TT-190521 | FA | 0 | TRUE | FALSE | FALSE
7664 | MRT-QM03-P0ZEN-155029 | 2019-03-21 | MRT-HK-REC-TT-190523 | FI | 0 | TRUE | FALSE | FALSE
7665 | MRT-QM03-P0ZEN-155030 | 2019-03-21 | MRT-HK-REC-TT-190523 | FI | 0 | TRUE | FALSE | FALSE
7666 | MRT-YB01-P0BBA-150898 | 2019-03-21 | MRT-HK-REC-TT-190524 | FI | 0 | TRUE | FALSE | FALSE
7667 | MRT-XK00-P2LBA-142000 | 2019-03-21 | MRT-DS-REC-TT-190082 | FI | 0 | TRUE | FALSE | FALSE
7668 | MRT-CA03-P0UMA-180026 | 2019-03-21 | MRT-DS-REC-TT-190066-FC | FC | 5 | TRUE | TRUE | FALSE
7669 | MRT-CA01-P0UMA-180027 | 2019-03-21 | MRT-DS-REC-TT-190066-FC | FC | 5 | TRUE | TRUE | FALSE
7670 | MRT-CA03-P0UMA-180028 | 2019-03-21 | MRT-DS-REC-TT-190066-FC | FC | 5 | TRUE | TRUE | FALSE
7671 | MRT-CA03-P0UMA-180029 | 2019-03-21 | MRT-DS-REC-TT-190066-FC | FC | 5 | TRUE | TRUE | FALSE
7672 | MRT-CA03-P0UMA-180033 | 2019-03-21 | MRT-DS-REC-TT-190066-FC | FC | 5 | TRUE | TRUE | FALSE
7673 | MRT-CA03-P0UMA-180034 | 2019-03-21 | MRT-DS-REC-TT-190066-FC | FC | 5 | TRUE | TRUE | FALSE
7674 | MRT-CA03-P0UMA-180030 | 2019-03-21 | MRT-DS-REC-TT-190066-FC | FC | 5 | TRUE | TRUE | FALSE
7675 | MRT-XJ00-P2SCB-145000 | 2019-03-21 | MRT-DS-REC-TT-190088 | FI | 0 | TRUE | FALSE | FALSE
7676 | MRT-DM02-P2MAA-220199 | 2019-03-21 | MRT-DS-REC-TT-190090 | FI | 0 | TRUE | FALSE | FALSE
7677 | MRT-DM02-P3MAA-220199 | 2019-03-21 | MRT-DS-REC-TT-190090 | FI | 0 | TRUE | FALSE | FALSE
7678 | MRT-YR01-P2ZEN-110103 | 2019-03-21 | MRT-DS-REC-TT-190089 | FA | 0 | TRUE | FALSE | FALSE
7679 | MRT-YR01-P3ZEN-110103 | 2019-03-21 | MRT-DS-REC-TT-190089 | FA | 0 | TRUE | FALSE | FALSE
7680 | MRT-YE00-P2MKA-230001 | 2019-03-22 | MRT-DS-REC-TT-180942 | FC | 2 | TRUE | TRUE | FALSE
7681 | MRT-UC02-P2BAT-240001 | 2019-03-22 | MRT-DS-REC-TT-180942 | FC | 2 | TRUE | TRUE | FALSE
7682 | MRT-YE00-P3MKA-230001 | 2019-03-22 | MRT-DS-REC-TT-180942 | FC | 2 | TRUE | TRUE | FALSE
7683 | MRT-YK08-P3MKA-220002 | 2019-03-22 | MRT-DS-REC-TT-180264-FC | FC | 0 | TRUE | TRUE | FALSE
7684 | MRT-YK08-P2MKA-220002 | 2019-03-22 | MRT-DS-REC-TT-180264-FC | FC | 0 | TRUE | TRUE | FALSE
7685 | MRT-YK10-P2MKA-220003 | 2019-03-22 | MRT-DS-REC-TT-180829-FC | FC | 1 | TRUE | TRUE | FALSE
7686 | MRT-CA00-P0UCA-180107 | 2019-03-22 | MRT-DS-REC-TT-190071-FC | FC | 6 | TRUE | TRUE | FALSE
7687 | MRT-CA00-P0UCA-180108 | 2019-03-22 | MRT-DS-REC-TT-190071-FC | FC | 6 | TRUE | TRUE | FALSE
7688 | MRT-XK00-P2PAB-142000 | 2019-03-22 | MRT-DS-REC-TT-190086 | FI | 0 | TRUE | FALSE | FALSE
7689 | MRT-XK00-P3PAB-143000 | 2019-03-22 | MRT-DS-REC-TT-190086 | FI | 0 | TRUE | FALSE | FALSE
7690 | MRT-XK00-P4PAB-144000 | 2019-03-22 | MRT-DS-REC-TT-190086 | FI | 0 | TRUE | FALSE | FALSE
7691 | MRT-YE00-P2MKA-230001 | 2019-03-25 | MRT-DS-REC-TT-180942-FC | FC | 2 | TRUE | TRUE | FALSE
7692 | MRT-UC02-P2BAT-240001 | 2019-03-25 | MRT-DS-REC-TT-180942-FC | FC | 2 | TRUE | TRUE | FALSE
7693 | MRT-YE00-P3MKA-230001 | 2019-03-25 | MRT-DS-REC-TT-180942-FC | FC | 2 | TRUE | TRUE | FALSE
7694 | MRT-YR02-P2MKC-230001 | 2019-03-25 | MRT-DS-REC-TT-190068-FC | FC | 0 | TRUE | TRUE | FALSE
7695 | MRT-YR02-P3MKC-230001 | 2019-03-25 | MRT-DS-REC-TT-190068-FC | FC | 0 | TRUE | TRUE | FALSE
7696 | MRT-XJ00-P3LBG-147000 | 2019-03-25 | MRT-DS-REC-TT-190091 | FI | 0 | TRUE | FALSE | FALSE
7697 | MRT-XJ00-P0GHD-141000 | 2019-03-25 | MRT-DS-REC-TT-190091 | FI | 0 | TRUE | FALSE | FALSE
7698 | MRT-XJ00-P0QJA-141000 | 2019-03-25 | MRT-DS-REC-TT-190091 | FI | 0 | TRUE | FALSE | FALSE
7699 | MRT-XJ00-P2QU-145000 | 2019-03-25 | MRT-DS-REC-TT-190091 | FI | 0 | TRUE | FALSE | FALSE
7700 | MRT-XJ00-P3QU-146000 | 2019-03-25 | MRT-DS-REC-TT-190091 | FI | 0 | TRUE | FALSE | FALSE
7701 | MRT-XJ00-P3QU-147000 | 2019-03-25 | MRT-DS-REC-TT-190091 | FI | 0 | TRUE | FALSE | FALSE
7702 | MRT-XJ00-P2MAA-145000 | 2019-03-25 | MRT-DS-REC-TT-190091 | FI | 0 | TRUE | FALSE | FALSE
7703 | MRT-XJ00-P2PAB-145100 | 2019-03-25 | MRT-DS-REC-TT-190034-FC | FC | 0 | TRUE | TRUE | FALSE
7704 | MRT-XJ00-P3PAB-146100 | 2019-03-25 | MRT-DS-REC-TT-190034-FC | FC | 0 | TRUE | TRUE | FALSE
7705 | MRT-XJ00-P3PAB-147100 | 2019-03-25 | MRT-DS-REC-TT-190034-FC | FC | 0 | TRUE | TRUE | FALSE
7706 | MRT-XJ00-P2LBA-145000 | 2019-03-25 | MRT-DS-REC-TT-190039-FC | FC | 0 | TRUE | TRUE | FALSE
7707 | MRT-XJ00-P3LBG-143000 | 2019-03-25 | MRT-DS-REC-TT-190045-FC | FC | 1 | TRUE | TRUE | FALSE
7708 | MRT-XJ00-P3PGB-143000 | 2019-03-25 | MRT-DS-REC-TT-190047-FC | FC | 1 | TRUE | TRUE | FALSE
7709 | MRT-XJ00-P3LAB-143000 | 2019-03-25 | MRT-DS-REC-TT-190048-FC | FC | 1 | TRUE | TRUE | FALSE
7710 | MRT-XJ00-P3LAB-146000 | 2019-03-25 | MRT-DS-REC-TT-190049-FC | FC | 0 | TRUE | TRUE | FALSE
7711 | MRT-XJ00-P2LBG-145000 | 2019-03-25 | MRT-DS-REC-TT-190052-FC | FC | 0 | TRUE | TRUE | FALSE
7712 | MRT-XJ00-P0LBG-140000 | 2019-03-25 | MRT-DS-REC-TT-190052-FC | FC | 0 | TRUE | TRUE | FALSE
7713 | MRT-XG02-P3SGK-135426 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7714 | MRT-XG02-P2SGC-135418 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7715 | MRT-YL19-P0PBB-135245 | 2019-03-25 | MRT-HK-REC-TT-190526 | FI | 0 | TRUE | FALSE | FALSE
7716 | MRT-YS01-P0PBB-135260 | 2019-03-25 | MRT-HK-REC-TT-190526 | FI | 0 | TRUE | FALSE | FALSE
7717 | MRT-YL19-P2PAC-130001 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7718 | MRT-CC05-P2PAC-130011 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7719 | MRT-CC05-P2PAC-130013 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7720 | MRT-CC05-P2PAC-130012 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7721 | MRT-CC05-P2PAC-130010 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7722 | MRT-CC05-P2PAC-130009 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7723 | MRT-CC05-P0PAC-130001 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7724 | MRT-CC05-P2PAC-130008 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7725 | MRT-CC05-P2PAC-130014 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7726 | MRT-CC05-P2PAC-130007 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7727 | MRT-CC05-P2PAC-130006 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7728 | MRT-CC05-P2PAC-130005 | 2019-03-25 | MRT-HK-REC-TT-190526 | FA | 0 | TRUE | FALSE | FALSE
7729 | MRT-XA00-P0PBB-135228 | 2019-03-25 | MRT-HK-REC-TT-190527 | FA | 1 | TRUE | TRUE | FALSE
7730 | MRT-XA00-P2PBB-135230 | 2019-03-25 | MRT-HK-REC-TT-190527 | FA | 1 | TRUE | TRUE | FALSE
7731 | MRT-XA00-P3PBB-135231 | 2019-03-25 | MRT-HK-REC-TT-190527 | FA | 1 | TRUE | TRUE | FALSE
7732 | MRT-DD00-P0BAT-155126 | 2019-03-25 | MRT-HK-REC-TT-190528 | FI | 0 | TRUE | FALSE | FALSE
7733 | MRT-DS00-P3GC-135604 | 2019-03-25 | MRT-HK-REC-TT-190529 | FI | 0 | TRUE | FALSE | FALSE
7734 | MRT-DS00-P3GC-135844 | 2019-03-25 | MRT-HK-REC-TT-190529 | FI | 0 | TRUE | FALSE | FALSE
7735 | MRT-DS00-P3GC-135843 | 2019-03-25 | MRT-HK-REC-TT-190529 | FI | 0 | TRUE | FALSE | FALSE
7736 | MRT-DS00-P3GC-135842 | 2019-03-25 | MRT-HK-REC-TT-190529 | FI | 0 | TRUE | FALSE | FALSE
7737 | MRT-DS00-P3GC-135600 | 2019-03-25 | MRT-HK-REC-TT-190529 | FI | 0 | TRUE | FALSE | FALSE
7738 | MRT-QM03-P0ZEN-155031 | 2019-03-25 | MRT-HK-REC-TT-190530 | FI | 0 | TRUE | FALSE | FALSE
7739 | MRT-DD00-P0BAT-155117 | 2019-03-26 | MRT-HK-REC-TT-190531 | FI | 0 | TRUE | FALSE | FALSE
7740 | MRT-DD00-P0BAT-155118 | 2019-03-26 | MRT-HK-REC-TT-190531 | FI | 0 | TRUE | FALSE | FALSE
7741 | MRT-DD00-P0BAT-155119 | 2019-03-26 | MRT-HK-REC-TT-190531 | FI | 0 | TRUE | FALSE | FALSE
7742 | MRT-DD00-P0BAT-155120 | 2019-03-26 | MRT-HK-REC-TT-190531 | FI | 0 | TRUE | FALSE | FALSE
7743 | MRT-DD00-P0BAT-155121 | 2019-03-26 | MRT-HK-REC-TT-190531 | FI | 0 | TRUE | FALSE | FALSE
7744 | MRT-DD00-P0BAT-155122 | 2019-03-26 | MRT-HK-REC-TT-190531 | FI | 0 | TRUE | FALSE | FALSE
7745 | MRT-DD00-P0BAT-155123 | 2019-03-26 | MRT-HK-REC-TT-190531 | FI | 0 | TRUE | FALSE | FALSE
7746 | MRT-DD00-P0BAT-155124 | 2019-03-26 | MRT-HK-REC-TT-190531 | FI | 0 | TRUE | FALSE | FALSE
7747 | MRT-DD00-P0BAT-155125 | 2019-03-26 | MRT-HK-REC-TT-190531 | FI | 0 | TRUE | FALSE | FALSE
7749 | MRT-XJ00-P3LBA-146000 | 2019-03-26 | MRT-DS-REC-TT-190051-FC | FC | 0 | TRUE | TRUE | FALSE
7750 | MRT-XJ00-P3LBG-146000 | 2019-03-26 | MRT-DS-REC-TT-190051-FC | FC | 0 | TRUE | TRUE | FALSE
7751 | MRT-XJ00-P2LCM-145000 | 2019-03-26 | MRT-DS-REC-TT-190051-FC | FC | 0 | TRUE | TRUE | FALSE
7752 | MRT-XJ00-P3LCM-146000 | 2019-03-26 | MRT-DS-REC-TT-190051-FC | FC | 0 | TRUE | TRUE | FALSE
7753 | MRT-UE00-P2LB-122010 | 2019-03-26 | MRT-DS-REC-TT-190063-FC | FC | 4 | TRUE | TRUE | FALSE
7754 | MRT-UE00-P3LB-122010 | 2019-03-26 | MRT-DS-REC-TT-190063-FC | FC | 4 | TRUE | TRUE | FALSE
7755 | MRT-YB03-P2LB-122048 | 2019-03-26 | MRT-DS-REC-TT-190069-FC | FC | 2 | TRUE | TRUE | FALSE
7756 | MRT-YB03-P3LB-122048 | 2019-03-26 | MRT-DS-REC-TT-190069-FC | FC | 2 | TRUE | TRUE | FALSE
7757 | MRT-XH01-P2LB-122112 | 2019-03-26 | MRT-DS-REC-TT-190073-FC | FC | 2 | TRUE | TRUE | FALSE
7758 | MRT-XH01-P3LB-122112 | 2019-03-26 | MRT-DS-REC-TT-190073-FC | FC | 2 | TRUE | TRUE | FALSE
7759 | MRT-UE00-P2LB-122007 | 2019-03-26 | MRT-DS-REC-TT-190075-FC | FC | 4 | TRUE | TRUE | FALSE
7760 | MRT-UE00-P3LB-122007 | 2019-03-26 | MRT-DS-REC-TT-190075-FC | FC | 3 | TRUE | TRUE | FALSE
7761 | MRT-XJ00-P2LB-122027 | 2019-03-26 | MRT-DS-REC-TT-190076-FC | FC | 2 | TRUE | TRUE | FALSE
7762 | MRT-XJ00-P3LB-122027 | 2019-03-26 | MRT-DS-REC-TT-190076-FC | FC | 2 | TRUE | TRUE | FALSE
7763 | MRT-XG02-P2LBA-110003 | 2019-03-26 | MRT-DS-REC-TT-190092 | FC | 6 | TRUE | TRUE | FALSE
7764 | MRT-XG02-P3LBA-110003 | 2019-03-26 | MRT-DS-REC-TT-190092 | FC | 6 | TRUE | TRUE | FALSE
7765 | MRT-XH01-P2LB-122025 | 2019-03-27 | MRT-DS-REC-TT-190093 | FC | 1 | TRUE | TRUE | FALSE
7766 | MRT-XH01-P3LB-122025 | 2019-03-27 | MRT-DS-REC-TT-190093 | FC | 1 | TRUE | TRUE | FALSE
7767 | MRT-XA01-P0ABA-150513 | 2019-03-27 | MRT-HK-REC-TT-190535 | FA | 3 | TRUE | TRUE | FALSE
7768 | MRT-XA01-P0ABA-150510 | 2019-03-27 | MRT-HK-REC-TT-190535 | FA | 3 | TRUE | TRUE | FALSE
7769 | MRT-CC05-P2MJA-120001 | 2019-03-27 | MRT-HK-REC-TT-190532 | FA | 0 | TRUE | FALSE | FALSE
7770 | MRT-CC05-P2MJA-120002 | 2019-03-27 | MRT-HK-REC-TT-190532 | FA | 0 | TRUE | FALSE | FALSE
7771 | MRT-CC05-P2MJA-120003 | 2019-03-27 | MRT-HK-REC-TT-190532 | FA | 0 | TRUE | FALSE | FALSE
7772 | MRT-CC05-P2MJA-120004 | 2019-03-27 | MRT-HK-REC-TT-190532 | FA | 0 | TRUE | FALSE | FALSE
7773 | MRT-YT10-P2PYA-125506 | 2019-03-27 | MRT-HK-REC-TT-190533 | FA | 0 | TRUE | FALSE | FALSE
7774 | MRT-YT01-P0MJA-150981 | 2019-03-27 | MRT-HK-REC-TT-190533 | FA | 0 | TRUE | FALSE | FALSE
7775 | MRT-YK08-P0GHE-145040 | 2019-03-27 | MRT-HK-REC-TT-190534 | FA | 0 | TRUE | FALSE | FALSE
7776 | MRT-XW03-P0GHE-145052 | 2019-03-27 | MRT-HK-REC-TT-190534 | FA | 0 | TRUE | FALSE | FALSE
7748 | MRT-XJ00-P3LBA-143000 | 2019-03-28 | MRT-DS-REC-TT-190043-FC | FC | 1 | TRUE | TRUE | FALSE
7777 | MRT-XJ00-P2PAB-140001 | 2019-03-28 | MRT-DS-REC-TT-190029-FC | FC | 3 | TRUE | TRUE | FALSE
7778 | MRT-XJ00-P3PAB-140001 | 2019-03-28 | MRT-DS-REC-TT-190029-FC | FC | 3 | TRUE | TRUE | FALSE
7779 | MRT-YD00-P2LB-122120 | 2019-03-28 | MRT-DS-REC-TT-190040-FC | FC | 1 | TRUE | TRUE | FALSE
7780 | MRT-UC07-P0ZEN-100001 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7781 | MRT-UC08-P0ZEN-100002 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 4 | TRUE | TRUE | FALSE
7782 | MRT-UC08-P0ZEN-100003 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 4 | TRUE | TRUE | FALSE
7783 | MRT-UE00-P2ZEN-100004 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7784 | MRT-UE00-P2ZEN-100005 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7785 | MRT-UE00-P2ZEN-100006 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7786 | MRT-UE00-P2ZEN-100007 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7787 | MRT-UE00-P2ZEN-100008 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7788 | MRT-UE00-P2ZEN-100009 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7789 | MRT-UE00-P3ZEN-100010 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7790 | MRT-UE00-P3ZEN-100011 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7791 | MRT-UE00-P3ZEN-100012 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7792 | MRT-UE00-P3ZEN-100013 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7793 | MRT-UE00-P3ZEN-100014 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7794 | MRT-UE00-P3ZEN-100015 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 5 | TRUE | TRUE | FALSE
7795 | MRT-UE00-P2ZEN-100016 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 3 | TRUE | TRUE | FALSE
7796 | MRT-UE00-P3ZEN-100017 | 2019-03-28 | MRT-DS-REC-TT-190059-FC | FC | 3 | TRUE | TRUE | FALSE
7797 | MRT-CV03-P0ZEN-140002 | 2019-03-28 | MRT-DS-REC-TT-190060-FC | FC | 3 | TRUE | TRUE | FALSE
7798 | MRT-DP00-P2LB-122122 | 2019-03-28 | MRT-DS-REC-TT-190070-FC | FC | 0 | TRUE | TRUE | FALSE
7799 | MRT-DP00-P3LB-122122 | 2019-03-28 | MRT-DS-REC-TT-190070-FC | FC | 0 | TRUE | TRUE | FALSE
7800 | MRT-XJ00-P0GHC-141000 | 2019-03-28 | MRT-DS-REC-TT-190072-FC | FC | 0 | TRUE | TRUE | FALSE
7801 | MRT-XJ00-P2LB-122028 | 2019-03-28 | MRT-DS-REC-TT-190079-FC | FC | 3 | TRUE | TRUE | FALSE
7802 | MRT-XJ00-P3LB-122028 | 2019-03-28 | MRT-DS-REC-TT-190079-FC | FC | 3 | TRUE | TRUE | FALSE
7803 | MRT-CC02-P2UAG-170307 | 2019-03-28 | MRT-DS-REC-TT-190081-FC | FC | 3 | TRUE | TRUE | FALSE
7804 | MRT-CC02-P2UAG-170308 | 2019-03-28 | MRT-DS-REC-TT-190081-FC | FC | 4 | TRUE | TRUE | FALSE
7805 | MRT-VK02-P2UAG-170310 | 2019-03-28 | MRT-DS-REC-TT-190081-FC | FC | 2 | TRUE | TRUE | FALSE
7806 | MRT-XJ00-P3LCM-143000 | 2019-03-28 | MRT-DS-REC-TT-190044-FC | FC | 1 | TRUE | TRUE | FALSE
7810 | MRT-XJ00-P2LCA-145000 | 2019-03-28 | MRT-DS-REC-TT-190065-FC | FC | 0 | TRUE | TRUE | FALSE
7811 | MRT-XJ00-P3LCA-146000 | 2019-03-28 | MRT-DS-REC-TT-190061-FC | FC | 0 | TRUE | TRUE | FALSE
7812 | MRT-XJ00-P3PGB-146000 | 2019-03-28 | MRT-DS-REC-TT-190061-FC | FC | 0 | TRUE | TRUE | FALSE
7813 | MRT-XJ00-P3LBA-147000 | 2019-03-29 | MRT-DS-REC-TT-190094 | FI | 0 | TRUE | FALSE | FALSE
7814 | MRT-XJ00-P2QC-145000 | 2019-03-29 | MRT-DS-REC-TT-190094 | FI | 0 | TRUE | FALSE | FALSE
7815 | MRT-XJ00-P3QC-146000 | 2019-03-29 | MRT-DS-REC-TT-190094 | FI | 0 | TRUE | FALSE | FALSE
7816 | MRT-XJ00-P3QC-147000 | 2019-03-29 | MRT-DS-REC-TT-190094 | FI | 0 | TRUE | FALSE | FALSE
7817 | MRT-XJ00-P0MKG-141000 | 2019-03-29 | MRT-DS-REC-TT-190094 | FI | 0 | TRUE | FALSE | FALSE
7818 | MRT-XJ00-P0EGD-141000 | 2019-03-29 | MRT-DS-REC-TT-190094 | FI | 0 | TRUE | FALSE | FALSE
7819 | MRT-XJ00-P0EKG-141000 | 2019-03-29 | MRT-DS-REC-TT-190094 | FI | 0 | TRUE | FALSE | FALSE
7820 | MRT-XJ00-P2QFB-145000 | 2019-03-29 | MRT-DS-REC-TT-190094 | FI | 0 | TRUE | FALSE | FALSE
7821 | MRT-XJ00-P3QFB-146000 | 2019-03-29 | MRT-DS-REC-TT-190094 | FI | 0 | TRUE | FALSE | FALSE
7822 | MRT-XJ00-P3QFB-147000 | 2019-03-29 | MRT-DS-REC-TT-190094 | FI | 0 | TRUE | FALSE | FALSE
7823 | MRT-XJ00-P3SCB-147000 | 2019-03-29 | MRT-DS-REC-TT-190094 | FI | 0 | TRUE | FALSE | FALSE
7824 | MRT-CC02-P2UHA-170103 | 2019-03-29 | MRT-DS-REC-TT-190095 | FC | 9 | TRUE | TRUE | FALSE
7825 | MRT-VK02-P2UHA-170106 | 2019-03-29 | MRT-DS-REC-TT-190095 | FC | 8 | TRUE | TRUE | FALSE
7826 | MRT-CC02-P3UHA-170103 | 2019-03-29 | MRT-DS-REC-TT-190095 | FC | 9 | TRUE | TRUE | FALSE
7827 | MRT-VK02-P3UHA-170106 | 2019-03-29 | MRT-DS-REC-TT-190095 | FC | 8 | TRUE | TRUE | FALSE
7828 | MRT-XJ00-P2PAB-145000 | 2019-04-01 | MRT-DS-REC-TT-190030-FC | FC | 0 | TRUE | TRUE | FALSE
7829 | MRT-XJ00-P3PAB-146000 | 2019-04-01 | MRT-DS-REC-TT-190030-FC | FC | 0 | TRUE | TRUE | FALSE
7830 | MRT-XJ00-P2PAB-142200 | 2019-04-01 | MRT-DS-REC-TT-190030-FC | FC | 0 | TRUE | TRUE | FALSE
7831 | MRT-XJ00-P3PAB-143200 | 2019-04-01 | MRT-DS-REC-TT-190030-FC | FC | 0 | TRUE | TRUE | FALSE
7832 | MRT-XJ00-P3PAB-144200 | 2019-04-01 | MRT-DS-REC-TT-190030-FC | FC | 0 | TRUE | TRUE | FALSE
7833 | MRT-DN05-P2MAA-220205 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7834 | MRT-YV02-P2MAV-230078 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7835 | MRT-YV02-P3MAV-230078 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7836 | MRT-YV02-P3MAK-230077 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7837 | MRT-XR00-P3MAA-220082 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7838 | MRT-YD05-P2CJJ-240069 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7839 | MRT-YD05-P3CJJ-240069 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7840 | MRT-YK00-P2CJJ-240119 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7841 | MRT-YK00-P3CJJ-240111 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7842 | MRT-YL01-P2CJJ-240070 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7843 | MRT-YL01-P3CJJ-240070 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7844 | MRT-YL01-P2CJJ-240073 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7845 | MRT-YL01-P3CJJ-240073 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7846 | MRT-YL00-P3CJJ-240052 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7847 | MRT-YV02-P2MAK-230077 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7848 | MRT-YL08-P2CJJ-240068 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7849 | MRT-YL08-P3CJJ-240068 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7850 | MRT-YL15-P2MAD-240171 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7851 | MRT-YV02-P2MAD-240170 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7852 | MRT-YV02-P2CJJ-240121 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7853 | MRT-YV02-P3CJJ-240113 | 2019-04-01 | MRT-DS-REC-TT-190032-FC | FC | 0 | TRUE | TRUE | FALSE
7854 | MRT-XG01-P2MAA-220045 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 1 | TRUE | TRUE | FALSE
7855 | MRT-XG01-P3MAA-220045 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 1 | TRUE | TRUE | FALSE
7856 | MRT-DM02-P2CJJ-240114 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7857 | MRT-DM02-P2CJJ-240123 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7858 | MRT-DM02-P2LBA-220130 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7859 | MRT-DM02-P2LBS-220087 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7860 | MRT-DM02-P2LBS-220090 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7861 | MRT-DM02-P2MAA-220131 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7862 | MRT-DM02-P2MAA-220152 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7863 | MRT-DM02-P2MAA-220155 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7864 | MRT-XR00-P2MAA-220086 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7865 | MRT-YL15-P2CJJ-240072 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7866 | MRT-YL15-P3CJJ-240072 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7867 | MRT-YL15-P3CJJ-240114 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7868 | MRT-YL15-P3MAD-240181 | 2019-04-01 | MRT-DS-REC-TT-190042-FC | FC | 0 | TRUE | TRUE | FALSE
7869 | MRT-CC02-P3UMA-170207 | 2019-04-01 | MRT-DS-REC-TT-190058-FC | FC | 5 | TRUE | TRUE | FALSE
7870 | MRT-XG02-P0GHD-120001 | 2019-04-01 | MRT-DS-REC-TT-190012-FC | FC | 5 | TRUE | TRUE | FALSE
7871 | MRT-XJ00-P3PGB-147000 | 2019-04-01 | MRT-DS-REC-TT-190096 | FI | 0 | TRUE | FALSE | FALSE
7872 | MRT-XJ00-P2SCA-145000 | 2019-04-01 | MRT-DS-REC-TT-190096 | FI | 0 | TRUE | FALSE | FALSE
7873 | MRT-XJ00-P3SCA-146000 | 2019-04-01 | MRT-DS-REC-TT-190096 | FI | 0 | TRUE | FALSE | FALSE
7874 | MRT-XJ00-P3SCA-147000 | 2019-04-01 | MRT-DS-REC-TT-190096 | FI | 0 | TRUE | FALSE | FALSE
7875 | MRT-XJ00-P3SCB-146000 | 2019-04-01 | MRT-DS-REC-TT-190096 | FI | 0 | TRUE | FALSE | FALSE
7876 | MRT-XJ00-P3MAA-146000 | 2019-04-01 | MRT-DS-REC-TT-190096 | FI | 0 | TRUE | FALSE | FALSE
7877 | MRT-XJ00-P3MAA-147000 | 2019-04-01 | MRT-DS-REC-TT-190096 | FI | 0 | TRUE | FALSE | FALSE
7878 | MRT-YE00-P0UAT-150173 | 2019-04-01 | MRT-HK-REC-TT-190536 | FA | 0 | TRUE | FALSE | FALSE
7879 | MRT-YE00-P0UZA-150174 | 2019-04-01 | MRT-HK-REC-TT-190536 | FA | 0 | TRUE | FALSE | FALSE
7880 | MRT-YE07-P0UST-150153 | 2019-04-01 | MRT-HK-REC-TT-190537 | FA | 0 | TRUE | FALSE | FALSE
7881 | MRT-XJ00-P0GMA-141000 | 2019-04-02 | MRT-DS-REC-TT-190097 | FI | 0 | TRUE | FALSE | FALSE
7882 | MRT-YB01-P3BAA-150945 | 2019-04-02 | MRT-HK-REC-TT-190538 | FA | 0 | TRUE | FALSE | FALSE
7883 | MRT-YM02-P3BAA-150940 | 2019-04-02 | MRT-HK-REC-TT-190538 | FA | 0 | TRUE | FALSE | FALSE
7884 | MRT-YM02-P3BAA-150946 | 2019-04-02 | MRT-HK-REC-TT-190538 | FA | 0 | TRUE | FALSE | FALSE
7885 | MRT-YT01-P0BFT-150604 | 2019-04-02 | MRT-HK-REC-TT-190538 | FA | 0 | TRUE | FALSE | FALSE
7886 | MRT-CC02-P0UMA-171103 | 2019-04-02 | MRT-DS-REC-TT-190098 | FC | 2 | TRUE | TRUE | FALSE
7887 | MRT-CC02-P2UMA-170207 | 2019-04-02 | MRT-DS-REC-TT-190100 | FC | 5 | TRUE | TRUE | FALSE
7888 | MRT-CC02-P2UMA-170209 | 2019-04-02 | MRT-DS-REC-TT-190100 | FC | 4 | TRUE | TRUE | FALSE
7889 | MRT-VK02-P2UMA-170210 | 2019-04-02 | MRT-DS-REC-TT-190100 | FC | 4 | TRUE | TRUE | FALSE
7890 | MRT-CC02-P3UMA-170207 | 2019-04-02 | MRT-DS-REC-TT-190100 | FC | 6 | TRUE | TRUE | FALSE
7891 | MRT-CC02-P3UMA-170209 | 2019-04-02 | MRT-DS-REC-TT-190100 | FC | 4 | TRUE | TRUE | FALSE
7892 | MRT-VK02-P3UMA-170210 | 2019-04-02 | MRT-DS-REC-TT-190100 | FC | 4 | TRUE | TRUE | FALSE
7893 | MRT-YD00-P0BBB-150536 | 2019-04-03 | MRT-HK-REC-TT-190539 | FA | 0 | TRUE | FALSE | FALSE
7894 | MRT-YT01-P0UZT-150654 | 2019-04-03 | MRT-HK-REC-TT-190539 | FA | 0 | TRUE | FALSE | FALSE
7895 | MRT-YD00-P0UZT-150655 | 2019-04-03 | MRT-HK-REC-TT-190539 | FA | 1 | TRUE | TRUE | FALSE
7896 | MRT-BT00-P0BFB-150664 | 2019-04-03 | MRT-HK-REC-TT-190539 | FA | 1 | TRUE | TRUE | FALSE
7897 | MRT-XB02-P2LB-122018 | 2019-04-03 | MRT-DS-REC-TT-190101 | FC | 6 | TRUE | TRUE | FALSE
7898 | MRT-XB02-P3LB-122018 | 2019-04-03 | MRT-DS-REC-TT-190101 | FC | 5 | TRUE | TRUE | FALSE
7807 | MRT-XJ00-P3LCA-143000 | 2019-04-04 | MRT-DS-REC-TT-190046-FC | FC | 1 | TRUE | TRUE | FALSE
7808 | MRT-XJ00-P3LAB-147000 | 2019-04-04 | MRT-DS-REC-TT-190054-FC | FC | 0 | TRUE | TRUE | FALSE
7809 | MRT-XJ00-P2PGB-145000 | 2019-04-04 | MRT-DS-REC-TT-190057-FC | FC | 0 | TRUE | TRUE | FALSE
7899 | MRT-YR01-P0GDG-135085 | 2019-04-04 | MRT-HK-REC-TT-190540 | FA | 0 | TRUE | FALSE | FALSE
7900 | MRT-XJ00-P2LB-122028 | 2019-04-04 | MRT-DS-REC-TT-190104 | FC | 4 | TRUE | TRUE | FALSE
7901 | MRT-XJ00-P3LB-122028 | 2019-04-04 | MRT-DS-REC-TT-190104 | FC | 4 | TRUE | TRUE | FALSE
7902 | MRT-YV02-P3MAD-240180 | 2019-04-04 | MRT-DS-REC-TT-190102 | FI | 0 | TRUE | FALSE | FALSE
7903 | MRT-XJ00-P3MKA-220001 | 2019-04-04 | MRT-DS-REC-TT-190103 | FC | 3 | TRUE | TRUE | FALSE
7904 | MRT-YF02-P2MAD-240168 | 2019-04-05 | MRT-DS-REC-TT-190037-FC | FC | 0 | TRUE | TRUE | FALSE
7905 | MRT-YL00-P2CJJ-240052 | 2019-04-05 | MRT-DS-REC-TT-190037-FC | FC | 0 | TRUE | TRUE | FALSE
7906 | MRT-CQ02-P2MAA-220201 | 2019-04-05 | MRT-DS-REC-TT-190062-FC | FC | 0 | TRUE | TRUE | FALSE
7907 | MRT-DM02-P3MAA-220174 | 2019-04-05 | MRT-DS-REC-TT-190062-FC | FC | 0 | TRUE | TRUE | FALSE
7908 | MRT-DM02-P3LBA-220129 | 2019-04-05 | MRT-DS-REC-TT-190062-FC | FC | 0 | TRUE | TRUE | FALSE
7909 | MRT-DM02-P3MAV-220097 | 2019-04-05 | MRT-DS-REC-TT-190062-FC | FC | 0 | TRUE | TRUE | FALSE
7910 | MRT-DM02-P3MAX-220145 | 2019-04-05 | MRT-DS-REC-TT-190062-FC | FC | 0 | TRUE | TRUE | FALSE
7911 | MRT-XR00-P3MAV-220041 | 2019-04-05 | MRT-DS-REC-TT-190077-FC | FC | 0 | TRUE | TRUE | FALSE
7912 | MRT-XK00-P3MAA-220207 | 2019-04-05 | MRT-DS-REC-TT-190077-FC | FC | 0 | TRUE | TRUE | FALSE
7913 | MRT-XG02-P3MAV-220006 | 2019-04-05 | MRT-DS-REC-TT-190078-FC | FC | 2 | TRUE | TRUE | FALSE
7914 | MRT-XV00-P3MAV-220037 | 2019-04-05 | MRT-DS-REC-TT-190078-FC | FC | 4 | TRUE | TRUE | FALSE
7915 | MRT-XK00-P2LBA-142000 | 2019-04-05 | MRT-DS-REC-TT-190082-FC | FC | 0 | TRUE | TRUE | FALSE
7916 | MRT-XK00-P2PAB-142000 | 2019-04-05 | MRT-DS-REC-TT-190086-FC | FC | 0 | TRUE | TRUE | FALSE
7917 | MRT-XK00-P3PAB-143000 | 2019-04-05 | MRT-DS-REC-TT-190086-FC | FC | 0 | TRUE | TRUE | FALSE
7918 | MRT-XK00-P4PAB-144000 | 2019-04-05 | MRT-DS-REC-TT-190086-FC | FC | 0 | TRUE | TRUE | FALSE
7919 | MRT-XH01-P2LB-122025 | 2019-04-05 | MRT-DS-REC-TT-190093-FC | FC | 1 | TRUE | TRUE | FALSE
7920 | MRT-XH01-P3LB-122025 | 2019-04-05 | MRT-DS-REC-TT-190093-FC | FC | 1 | TRUE | TRUE | FALSE
7921 | MRT-CC02-P2UHA-170103 | 2019-04-05 | MRT-DS-REC-TT-190095-FC | FC | 9 | TRUE | TRUE | FALSE
7922 | MRT-VK02-P2UHA-170106 | 2019-04-05 | MRT-DS-REC-TT-190095-FC | FC | 8 | TRUE | TRUE | FALSE
7923 | MRT-CC02-P3UHA-170103 | 2019-04-05 | MRT-DS-REC-TT-190095-FC | FC | 9 | TRUE | TRUE | FALSE
7924 | MRT-VK02-P3UHA-170106 | 2019-04-05 | MRT-DS-REC-TT-190095-FC | FC | 8 | TRUE | TRUE | FALSE
7946 | MRT-XW03-P0GHE-145022 | 2019-04-05 | MRT-HK-REC-TT-190541 | FA | 0 | TRUE | FALSE | FALSE
7947 | MRT-YK09-P0GHE-145010 | 2019-04-05 | MRT-HK-REC-TT-190541 | FA | 0 | TRUE | FALSE | FALSE
7948 | MRT-DS05-P0EKF-125645 | 2019-04-05 | MRT-HK-REC-TT-190541 | FA | 0 | TRUE | FALSE | FALSE
7949 | MRT-YS02-P0GEN-135399 | 2019-04-05 | MRT-HK-REC-TT-190541 | FA | 0 | TRUE | FALSE | FALSE
7950 | MRT-DT01-P0QHB-125428 | 2019-04-05 | MRT-HK-REC-TT-190541 | FA | 0 | TRUE | FALSE | FALSE
7951 | MRT-DD00-P0BAT-155127 | 2019-04-05 | MRT-HK-REC-TT-190542 | FA | 0 | TRUE | FALSE | FALSE
8172 | MRT-CC02-P0ULX-176228 | 2019-04-05 | MRT-HK-REC-TT-190544 | FA | 0 | TRUE | FALSE | FALSE
8173 | MRT-CC02-P0ULX-176227 | 2019-04-05 | MRT-HK-REC-TT-190544 | FA | 0 | TRUE | FALSE | FALSE
8174 | MRT-CC02-P0ULX-176226 | 2019-04-05 | MRT-HK-REC-TT-190544 | FA | 0 | TRUE | FALSE | FALSE
8175 | MRT-CC07-P0UZT-175965 | 2019-04-05 | MRT-HK-REC-TT-190544 | FA | 0 | TRUE | FALSE | FALSE
8176 | MRT-CC02-P0ULX-176217 | 2019-04-05 | MRT-HK-REC-TT-190544 | FA | 1 | TRUE | FALSE | FALSE
7952 | MRT-XJ00-P3LCA-147000 | 2019-04-08 | MRT-DS-REC-TT-190106 | FI | 0 | TRUE | FALSE | FALSE
7953 | MRT-XJ00-P2MAV-145000 | 2019-04-08 | MRT-DS-REC-TT-190106 | FI | 0 | TRUE | FALSE | FALSE
7954 | MRT-XJ00-P3MAV-146000 | 2019-04-08 | MRT-DS-REC-TT-190106 | FI | 0 | TRUE | FALSE | FALSE
7955 | MRT-XJ00-P3MAV-147000 | 2019-04-08 | MRT-DS-REC-TT-190106 | FI | 0 | TRUE | FALSE | FALSE
7956 | MRT-XB02-P0UMA-180004 | 2019-04-08 | MRT-DS-REC-TT-190105 | FC | 7 | TRUE | TRUE | FALSE
7957 | MRT-CA01-P0UMA-180005 | 2019-04-08 | MRT-DS-REC-TT-190105 | FC | 6 | TRUE | TRUE | FALSE
7958 | MRT-CA01-P0UMA-180006 | 2019-04-08 | MRT-DS-REC-TT-190105 | FC | 5 | TRUE | TRUE | FALSE
7959 | MRT-CA01-P0UMA-180007 | 2019-04-08 | MRT-DS-REC-TT-190105 | FC | 5 | TRUE | TRUE | FALSE
7960 | MRT-VN03-P2LB-122015 | 2019-04-08 | MRT-DS-REC-TT-190107 | FC | 5 | TRUE | TRUE | FALSE
7961 | MRT-VN03-P3LB-122015 | 2019-04-08 | MRT-DS-REC-TT-190107 | FC | 5 | TRUE | TRUE | FALSE
7962 | MRT-CA00-P0UGX-186738 | 2019-04-08 | MRT-HK-REC-TT-190543 | FA | 0 | TRUE | FALSE | FALSE
7963 | MRT-CA00-P0UGX-186739 | 2019-04-08 | MRT-HK-REC-TT-190543 | FA | 0 | TRUE | FALSE | FALSE
7964 | MRT-CA00-P0UGX-186734 | 2019-04-08 | MRT-HK-REC-TT-190543 | FA | 2 | TRUE | TRUE | FALSE
7965 | MRT-CA00-P0UGX-186732 | 2019-04-08 | MRT-HK-REC-TT-190543 | FA | 2 | TRUE | TRUE | FALSE
7966 | MRT-CA00-P0UGX-186730 | 2019-04-08 | MRT-HK-REC-TT-190543 | FA | 2 | TRUE | TRUE | FALSE
7967 | MRT-CC01-P0UAA-176095 | 2019-04-08 | MRT-HK-REC-TT-190543 | FA | 1 | TRUE | TRUE | FALSE
7968 | MRT-CA03-P0UGX-186760 | 2019-04-08 | MRT-HK-REC-TT-190543 | FA | 0 | TRUE | FALSE | FALSE
7969 | MRT-CA03-P0UGX-186762 | 2019-04-08 | MRT-HK-REC-TT-190543 | FA | 0 | TRUE | FALSE | FALSE
7970 | MRT-CA01-P0UGX-186973 | 2019-04-08 | MRT-HK-REC-TT-190543 | FA | 4 | TRUE | TRUE | FALSE
7971 | MRT-CA02-P0UGX-186985 | 2019-04-08 | MRT-HK-REC-TT-190543 | FA | 2 | TRUE | TRUE | FALSE
7972 | MRT-CA02-P0UGX-186975 | 2019-04-08 | MRT-HK-REC-TT-190543 | FA | 4 | TRUE | TRUE | FALSE
7973 | MRT-CA00-P0UYX-187162 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 2 | TRUE | TRUE | FALSE
7974 | MRT-CA00-P0UGA-186624 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 2 | TRUE | TRUE | FALSE
7975 | MRT-CA00-P0UXA-186684 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 2 | TRUE | TRUE | FALSE
7976 | MRT-CA00-P0USX-186814 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 1 | TRUE | TRUE | FALSE
7977 | MRT-CA00-P0USG-186864 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 3 | TRUE | TRUE | FALSE
7978 | MRT-CA00-P0UGX-186966 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 3 | TRUE | TRUE | FALSE
7979 | MRT-CA00-P0UPB-187014 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 3 | TRUE | TRUE | FALSE
7980 | MRT-CA00-P0UVH-187062 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 2 | TRUE | TRUE | FALSE
7981 | MRT-CA00-P0UQA-186512 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 3 | TRUE | TRUE | FALSE
7982 | MRT-CA00-P0UGA-186625 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 2 | TRUE | TRUE | FALSE
7983 | MRT-CA00-P0UST-186917 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 3 | TRUE | TRUE | FALSE
7984 | MRT-CA00-P0UAB-187322 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 2 | TRUE | TRUE | FALSE
7985 | MRT-CA00-P0UGX-186736 | 2019-04-08 | MRT-HK-REC-TT-190545 | FA | 2 | TRUE | TRUE | FALSE
7986 | MRT-CM02-P2MJA-125528 | 2019-04-08 | MRT-HK-REC-TT-190547 | FA | 0 | TRUE | FALSE | FALSE
7987 | MRT-CC02-P2UEJ-170907 | 2019-04-08 | MRT-DS-REC-TT-190108 | FC | 2 | TRUE | TRUE | FALSE
7988 | MRT-VK02-P2UEJ-170910 | 2019-04-08 | MRT-DS-REC-TT-190108 | FC | 2 | TRUE | TRUE | FALSE
7989 | MRT-CC02-P3UEJ-170907 | 2019-04-08 | MRT-DS-REC-TT-190108 | FC | 2 | TRUE | TRUE | FALSE
7990 | MRT-VK02-P3UEJ-170910 | 2019-04-08 | MRT-DS-REC-TT-190108 | FC | 2 | TRUE | TRUE | FALSE
8023 | MRT-VE01-P2MAA-220044 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | TRUE | TRUE | FALSE
8024 | MRT-VE01-P3MAA-220044 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | TRUE | TRUE | FALSE
8025 | MRT-YD00-P3MAA-220026 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | TRUE | TRUE | FALSE
8026 | MRT-YD00-P3MAA-220027 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | TRUE | TRUE | FALSE
8027 | MRT-YD00-P2MAA-220026 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | TRUE | TRUE | FALSE
8028 | MRT-YD00-P2MAA-220027 | 2019-04-08 | MRT-DS-REC-TT-190067 | FI | 1 | TRUE | TRUE | FALSE
8096 | MRT-CA00-P0UGX-186726 | 2019-04-08 | MRT-HK-REC-TT-190543 | FA | 2 | TRUE | TRUE | FALSE
7991 | MRT-YT01-P3GC-135152 | 2019-04-09 | MRT-HK-REC-TT-190548 | FA | 0 | TRUE | FALSE | FALSE
7992 | MRT-YT01-P3GC-135153 | 2019-04-09 | MRT-HK-REC-TT-190548 | FA | 0 | TRUE | FALSE | FALSE
7993 | MRT-YT01-P3GC-135164 | 2019-04-09 | MRT-HK-REC-TT-190548 | FA | 0 | TRUE | FALSE | FALSE
7994 | MRT-YT01-P3GC-135154 | 2019-04-09 | MRT-HK-REC-TT-190548 | FA | 0 | TRUE | FALSE | FALSE
7995 | MRT-YT01-P3GC-135157 | 2019-04-09 | MRT-HK-REC-TT-190548 | FA | 0 | TRUE | FALSE | FALSE
7996 | MRT-YT01-P3GC-135166 | 2019-04-09 | MRT-HK-REC-TT-190548 | FA | 0 | TRUE | FALSE | FALSE
7997 | MRT-YT01-P3GC-135162 | 2019-04-09 | MRT-HK-REC-TT-190548 | FA | 0 | TRUE | FALSE | FALSE
7998 | MRT-YT01-P3GC-135158 | 2019-04-09 | MRT-HK-REC-TT-190548 | FA | 0 | TRUE | FALSE | FALSE
7999 | MRT-YT01-P3GC-135155 | 2019-04-09 | MRT-HK-REC-TT-190548 | FA | 0 | TRUE | FALSE | FALSE
8000 | MRT-XJ00-P3LCM-147000 | 2019-04-09 | MRT-DS-REC-TT-190080-FC | FC | 0 | TRUE | FALSE | FALSE
8001 | MRT-XJ00-P0GKB-141000 | 2019-04-09 | MRT-DS-REC-TT-190080-FC | FC | 0 | TRUE | FALSE | FALSE
8002 | MRT-CA01-P0UGX-186968 | 2019-04-09 | MRT-HK-REC-TT-190550 | FA | 3 | TRUE | TRUE | FALSE
8003 | MRT-CA01-P0UGX-186972 | 2019-04-09 | MRT-HK-REC-TT-190550 | FA | 3 | TRUE | TRUE | FALSE
8004 | MRT-CA02-P0UGX-186989 | 2019-04-09 | MRT-HK-REC-TT-190550 | FA | 1 | TRUE | TRUE | FALSE
8005 | MRT-CA01-P0UGX-186971 | 2019-04-09 | MRT-HK-REC-TT-190550 | FA | 1 | TRUE | TRUE | FALSE
8006 | MRT-CA03-P0USX-186832 | 2019-04-09 | MRT-HK-REC-TT-190551 | FA | 1 | TRUE | TRUE | FALSE
8007 | MRT-CA01-P0UGA-186659 | 2019-04-09 | MRT-HK-REC-TT-190551 | FA | 3 | TRUE | TRUE | FALSE
8008 | MRT-CA01-P0UGA-186658 | 2019-04-09 | MRT-HK-REC-TT-190551 | FA | 3 | TRUE | TRUE | FALSE
8010 | MRT-CC02-P2UMA-170707 | 2019-04-10 | MRT-DS-REC-TT-190109 | FC | 5 | TRUE | TRUE | FALSE
8011 | MRT-CC02-P2UMA-170708 | 2019-04-10 | MRT-DS-REC-TT-190109 | FC | 5 | TRUE | TRUE | FALSE
8012 | MRT-CC02-P2UMA-170709 | 2019-04-10 | MRT-DS-REC-TT-190109 | FC | 5 | TRUE | TRUE | FALSE
8013 | MRT-CC02-P3UMA-170707 | 2019-04-10 | MRT-DS-REC-TT-190109 | FC | 6 | TRUE | TRUE | FALSE
8014 | MRT-CC02-P3UMA-170708 | 2019-04-10 | MRT-DS-REC-TT-190109 | FC | 6 | TRUE | TRUE | FALSE
8015 | MRT-CC02-P3UMA-170709 | 2019-04-10 | MRT-DS-REC-TT-190109 | FC | 6 | TRUE | TRUE | FALSE
8016 | MRT-CC02-P2UMA-170607 | 2019-04-10 | MRT-DS-REC-TT-190099 | FC | 5 | TRUE | TRUE | FALSE
8017 | MRT-CC02-P2UMA-170608 | 2019-04-10 | MRT-DS-REC-TT-190099 | FC | 5 | TRUE | TRUE | FALSE
8018 | MRT-CC02-P3UMA-170607 | 2019-04-10 | MRT-DS-REC-TT-190099 | FC | 5 | TRUE | TRUE | FALSE
8019 | MRT-CC02-P3UMA-170608 | 2019-04-10 | MRT-DS-REC-TT-190099 | FC | 5 | TRUE | TRUE | FALSE
8029 | MRT-CC02-P0UMA-171103 | 2019-04-11 | MRT-DS-REC-TT-190098-FC | FC | 2 | TRUE | TRUE | FALSE
8030 | MRT-CC02-P2UMA-170207 | 2019-04-11 | MRT-DS-REC-TT-190100-FC | FC | 5 | TRUE | TRUE | FALSE
8031 | MRT-CC02-P2UMA-170209 | 2019-04-11 | MRT-DS-REC-TT-190100-FC | FC | 4 | TRUE | TRUE | FALSE
8032 | MRT-VK02-P2UMA-170210 | 2019-04-11 | MRT-DS-REC-TT-190100-FC | FC | 4 | TRUE | TRUE | FALSE
8033 | MRT-CC02-P3UMA-170207 | 2019-04-11 | MRT-DS-REC-TT-190100-FC | FC | 6 | TRUE | TRUE | FALSE
8034 | MRT-CC02-P3UMA-170209 | 2019-04-11 | MRT-DS-REC-TT-190100-FC | FC | 4 | TRUE | TRUE | FALSE
8035 | MRT-VK02-P3UMA-170210 | 2019-04-11 | MRT-DS-REC-TT-190100-FC | FC | 4 | TRUE | TRUE | FALSE
8036 | MRT-XB02-P2LB-122018 | 2019-04-11 | MRT-DS-REC-TT-190101-FC | FC | 6 | TRUE | TRUE | FALSE
8037 | MRT-XB02-P3LB-122018 | 2019-04-11 | MRT-DS-REC-TT-190101-FC | FC | 5 | TRUE | TRUE | FALSE
8038 | MRT-XB02-P0UMA-180004 | 2019-04-11 | MRT-DS-REC-TT-190105-FC | FC | 7 | TRUE | TRUE | FALSE
8039 | MRT-CA01-P0UMA-180005 | 2019-04-11 | MRT-DS-REC-TT-190105-FC | FC | 6 | TRUE | TRUE | FALSE
8040 | MRT-CA01-P0UMA-180006 | 2019-04-11 | MRT-DS-REC-TT-190105-FC | FC | 5 | TRUE | TRUE | FALSE
8041 | MRT-CA01-P0UMA-180007 | 2019-04-11 | MRT-DS-REC-TT-190105-FC | FC | 5 | TRUE | TRUE | FALSE
8042 | MRT-YT01-P3GC-135134 | 2019-04-11 | MRT-HK-REC-TT-190549 | FA | 0 | TRUE | FALSE | FALSE
8043 | MRT-XB00-P3GC-135136 | 2019-04-11 | MRT-HK-REC-TT-190549 | FA | 0 | TRUE | FALSE | FALSE
8044 | MRT-YT01-P3GC-135132 | 2019-04-11 | MRT-HK-REC-TT-190549 | FI | 0 | TRUE | FALSE | FALSE
8045 | MRT-YT01-P3GC-135130 | 2019-04-11 | MRT-HK-REC-TT-190549 | FI | 0 | TRUE | FALSE | FALSE
8046 | MRT-YT01-P3GC-135185 | 2019-04-11 | MRT-HK-REC-TT-190549 | FA | 0 | TRUE | FALSE | FALSE
8047 | MRT-YT01-P3GC-135129 | 2019-04-11 | MRT-HK-REC-TT-190549 | FA | 0 | TRUE | FALSE | FALSE
8048 | MRT-XW03-P3GC-135112 | 2019-04-11 | MRT-HK-REC-TT-190549 | FA | 0 | TRUE | FALSE | FALSE
8049 | MRT-XS02-P3GC-135116 | 2019-04-11 | MRT-HK-REC-TT-190549 | FA | 0 | TRUE | FALSE | FALSE
8050 | MRT-YT01-P3GC-135128 | 2019-04-11 | MRT-HK-REC-TT-190549 | FA | 0 | TRUE | FALSE | FALSE
8051 | MRT-YT01-P3GC-135131 | 2019-04-11 | MRT-HK-REC-TT-190549 | FA | 0 | TRUE | FALSE | FALSE
8052 | MRT-CA01-P0UGA-186654 | 2019-04-11 | MRT-HK-REC-TT-190552 | FA | 2 | TRUE | TRUE | FALSE
8053 | MRT-CA01-P0UGA-186659 | 2019-04-11 | MRT-HK-REC-TT-190552 | FA | 4 | TRUE | TRUE | FALSE
8054 | MRT-CA01-P0UGA-186658 | 2019-04-11 | MRT-HK-REC-TT-190552 | FA | 4 | TRUE | TRUE | FALSE
8055 | MRT-CA01-P0UGA-186655 | 2019-04-11 | MRT-HK-REC-TT-190552 | FA | 2 | TRUE | TRUE | FALSE
8056 | MRT-CA01-P0UGX-186766 | 2019-04-11 | MRT-HK-REC-TT-190552 | FA | 1 | TRUE | TRUE | FALSE
8057 | MRT-CA02-P0UGX-186778 | 2019-04-11 | MRT-HK-REC-TT-190552 | FA | 1 | TRUE | TRUE | FALSE
8058 | MRT-CA02-P0UGX-186779 | 2019-04-11 | MRT-HK-REC-TT-190552 | FA | 1 | TRUE | TRUE | FALSE
8059 | MRT-DD00-P0BAT-155128 | 2019-04-11 | MRT-HK-REC-TT-190553 | FI | 0 | TRUE | FALSE | FALSE
8060 | MRT-DD00-P0ABA-155129 | 2019-04-11 | MRT-HK-REC-TT-190553 | FI | 0 | TRUE | FALSE | FALSE
8009 | MRT-DL03-P0ZEN-140001 | 2019-04-12 | MRT-DS-REC-TT-190050-FC | FC | 0 | TRUE | TRUE | FALSE
8064 | MRT-DS05-P0EKF-125623 | 2019-04-12 | MRT-HK-REC-TT-190554 | FA | 1 | TRUE | TRUE | FALSE
8065 | MRT-DS05-P0EKF-125624 | 2019-04-12 | MRT-HK-REC-TT-190554 | FA | 1 | TRUE | TRUE | FALSE
8066 | MRT-DN04-P0EKF-125607 | 2019-04-12 | MRT-HK-REC-TT-190554 | FA | 1 | TRUE | TRUE | FALSE
8067 | MRT-BN00-P0EKF-125634 | 2019-04-12 | MRT-HK-REC-TT-190554 | FA | 0 | TRUE | FALSE | FALSE
8068 | MRT-YK10-P0EGB-125458 | 2019-04-12 | MRT-HK-REC-TT-190555 | FA | 0 | TRUE | FALSE | FALSE
8069 | MRT-YK08-P3CYP-160005 | 2019-04-12 | MRT-HK-REC-TT-190556 | FA | 1 | TRUE | TRUE | FALSE
8075 | MRT-QM03-P0ZEN-155032 | 2019-04-15 | MRT-HK-REC-TT-190557 | FI | 0 | TRUE | FALSE | FALSE
8076 | MRT-YK01-P0GEN-135377 | 2019-04-15 | MRT-HK-REC-TT-190558 | FA | 0 | TRUE | FALSE | FALSE
8077 | MRT-XG02-P0LAA-125438 | 2019-04-15 | MRT-HK-REC-TT-190559 | FA | 0 | TRUE | FALSE | FALSE
8078 | MRT-XG02-P0QHA-125435 | 2019-04-15 | MRT-HK-REC-TT-190559 | FA | 0 | TRUE | FALSE | FALSE
8079 | MRT-XG02-P0QHG-125436 | 2019-04-15 | MRT-HK-REC-TT-190559 | FA | 0 | TRUE | FALSE | FALSE
8080 | MRT-XG02-P0QHN-125437 | 2019-04-15 | MRT-HK-REC-TT-190559 | FA | 0 | TRUE | FALSE | FALSE
8081 | MRT-YT01-P0GEN-135330 | 2019-04-15 | MRT-HK-REC-TT-190560 | FA | 0 | TRUE | FALSE | FALSE
8082 | MRT-YT01-P0GEN-135331 | 2019-04-15 | MRT-HK-REC-TT-190560 | FA | 0 | TRUE | FALSE | FALSE
8083 | MRT-YK10-P0LAA-125456 | 2019-04-15 | MRT-HK-REC-TT-190561 | FA | 0 | TRUE | FALSE | FALSE
8084 | MRT-YK10-P0QHA-125445 | 2019-04-15 | MRT-HK-REC-TT-190561 | FA | 0 | TRUE | FALSE | FALSE
8085 | MRT-YE00-P3MKA-230001 | 2019-04-15 | MRT-DS-REC-TT-190112 | FC | 3 | TRUE | TRUE | FALSE
8094 | MRT-DP00-P2LB-122123 | 2019-04-15 | MRT-DS-REC-TT-190113 | FI | 0 | TRUE | FALSE | FALSE
8095 | MRT-DP00-P3LB-122123 | 2019-04-15 | MRT-DS-REC-TT-190113 | FI | 0 | TRUE | FALSE | FALSE
8097 | MRT-YT01-P0QJA-110001 | 2019-04-16 | MRT-DS-REC-TT-190114 | FA | 0 | TRUE | FALSE | FALSE
8098 | MRT-UE00-P2LB-122008 | 2019-04-16 | MRT-DS-REC-TT-190115 | FC | 7 | TRUE | TRUE | FALSE
8099 | MRT-UE00-P3LB-122008 | 2019-04-16 | MRT-DS-REC-TT-190115 | FC | 5 | TRUE | TRUE | FALSE
8100 | MRT-XK00-P2MAA-220207 | 2019-04-18 | MRT-DS-REC-TT-190117 | FI | 0 | TRUE | FALSE | FALSE
8101 | MRT-CA01-P0UMA-180044 | 2019-04-18 | MRT-DS-REC-TT-190116 | FC | 3 | TRUE | TRUE | FALSE
8102 | MRT-CA02-P0UMA-180045 | 2019-04-18 | MRT-DS-REC-TT-190116 | FC | 3 | TRUE | TRUE | FALSE
8103 | MRT-CA00-P0UMA-180047 | 2019-04-18 | MRT-DS-REC-TT-190116 | FC | 4 | TRUE | TRUE | FALSE
8104 | MRT-XB00-P2GM-128506 | 2019-04-19 | MRT-DS-REC-TT-190118 | FC | 2 | TRUE | TRUE | FALSE
8105 | MRT-XB00-P3GM-128506 | 2019-04-19 | MRT-DS-REC-TT-190118 | FC | 2 | TRUE | TRUE | FALSE
8106 | MRT-XJ00-P3LBA-144000 | 2019-04-19 | MRT-DS-REC-TT-190111 | FC | 1 | TRUE | TRUE | FALSE
8107 | MRT-XJ00-P3LBG-144000 | 2019-04-19 | MRT-DS-REC-TT-190111 | FC | 1 | TRUE | TRUE | FALSE
8108 | MRT-XJ00-P3LCM-144000 | 2019-04-19 | MRT-DS-REC-TT-190111 | FC | 1 | TRUE | TRUE | FALSE
8109 | MRT-XJ00-P3LAB-144000 | 2019-04-19 | MRT-DS-REC-TT-190111 | FC | 1 | TRUE | TRUE | FALSE
8110 | MRT-XJ00-P3LCA-144000 | 2019-04-19 | MRT-DS-REC-TT-190111 | FC | 1 | TRUE | TRUE | FALSE
8111 | MRT-XJ00-P3PGB-144000 | 2019-04-19 | MRT-DS-REC-TT-190111 | FC | 1 | TRUE | TRUE | FALSE
8112 | MRT-YL01-P2MKA-125508 | 2019-04-22 | MRT-HK-REC-TT-190562 | FA | 0 | TRUE | FALSE | FALSE
8113 | MRT-FF01-P0SGA-135429 | 2019-04-22 | MRT-HK-REC-TT-190563 | FA | 0 | TRUE | FALSE | FALSE
8114 | MRT-CC02-P2UEJ-170907 | 2019-04-23 | MRT-DS-REC-TT-190108-FC | FC | 2 | TRUE | TRUE | FALSE
8115 | MRT-VK02-P2UEJ-170910 | 2019-04-23 | MRT-DS-REC-TT-190108-FC | FC | 2 | TRUE | TRUE | FALSE
8116 | MRT-CC02-P3UEJ-170907 | 2019-04-23 | MRT-DS-REC-TT-190108-FC | FC | 2 | TRUE | TRUE | FALSE
8117 | MRT-VK02-P3UEJ-170910 | 2019-04-23 | MRT-DS-REC-TT-190108-FC | FC | 2 | TRUE | TRUE | FALSE
8118 | MRT-CC02-P2UMA-170707 | 2019-04-23 | MRT-DS-REC-TT-190109-FC | FC | 5 | TRUE | TRUE | FALSE
8119 | MRT-CC02-P2UMA-170708 | 2019-04-23 | MRT-DS-REC-TT-190109-FC | FC | 5 | TRUE | TRUE | FALSE
8120 | MRT-CC02-P2UMA-170709 | 2019-04-23 | MRT-DS-REC-TT-190109-FC | FC | 6 | TRUE | TRUE | FALSE
8121 | MRT-CC02-P3UMA-170707 | 2019-04-23 | MRT-DS-REC-TT-190109-FC | FC | 6 | TRUE | TRUE | FALSE
8122 | MRT-CC02-P3UMA-170708 | 2019-04-23 | MRT-DS-REC-TT-190109-FC | FC | 6 | TRUE | TRUE | FALSE
8123 | MRT-CC02-P3UMA-170709 | 2019-04-23 | MRT-DS-REC-TT-190109-FC | FC | 6 | TRUE | TRUE | FALSE
8124 | MRT-BN00-P0EKF-125632 | 2019-04-23 | MRT-HK-REC-TT-190564 | FA | 0 | TRUE | FALSE | FALSE
8125 | MRT-YR01-P0GEN-135323 | 2019-04-23 | MRT-HK-REC-TT-190564 | FA | 0 | TRUE | FALSE | FALSE
8126 | MRT-YT01-P0GN-135256 | 2019-04-23 | MRT-HK-REC-TT-190565 | FA | 0 | TRUE | FALSE | FALSE
8127 | MRT-YT01-P0GN-135259 | 2019-04-23 | MRT-HK-REC-TT-190565 | FA | 0 | TRUE | FALSE | FALSE
8128 | MRT-YT01-P0GN-135261 | 2019-04-23 | MRT-HK-REC-TT-190565 | FA | 0 | TRUE | FALSE | FALSE
8129 | MRT-YT01-P3GC-135198 | 2019-04-23 | MRT-HK-REC-TT-190565 | FA | 0 | TRUE | FALSE | FALSE
8130 | MRT-YT01-P3GC-135196 | 2019-04-23 | MRT-HK-REC-TT-190565 | FA | 0 | TRUE | FALSE | FALSE
8131 | MRT-YR05-P0GDY-135067 | 2019-04-23 | MRT-HK-REC-TT-190566 | FA | 1 | TRUE | TRUE | FALSE
8132 | MRT-YL01-P0GDY-135064 | 2019-04-23 | MRT-HK-REC-TT-190566 | FA | 1 | TRUE | TRUE | FALSE
8133 | MRT-XK00-P3LBA-143000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8134 | MRT-XK00-P4LBA-144000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8135 | MRT-XK00-P2LAB-142000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8136 | MRT-XK00-P3LAB-143000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8137 | MRT-XK00-P4LAB-144000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8138 | MRT-XK00-P2LBG-142000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8139 | MRT-XK00-P3LBG-143000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8140 | MRT-XK00-P4LBG-144000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8141 | MRT-XK00-P2LCA-142000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8142 | MRT-XK00-P3LCA-143000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8143 | MRT-XK00-P4LCA-144000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8144 | MRT-XK00-P2LCM-142000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8145 | MRT-XK00-P3LCM-143000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8146 | MRT-XK00-P4LCM-144000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8147 | MRT-XK00-P2ACW-142000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8148 | MRT-XK00-P3ACW-143000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8149 | MRT-XK00-P4ACW-144000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8150 | MRT-XK00-P2MAM-142000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8151 | MRT-XK00-P3MAM-142000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8152 | MRT-XK00-P4MAM-142000 | 2019-04-23 | MRT-DS-REC-TT-190110 | FI | 0 | TRUE | FALSE | FALSE
8153 | MRT-YT01-P0GN-135255 | 2019-04-23 | MRT-HK-REC-TT-190567 | FA | 0 | TRUE | FALSE | FALSE
8154 | MRT-YT01-P0GN-135258 | 2019-04-23 | MRT-HK-REC-TT-190567 | FA | 0 | TRUE | FALSE | FALSE
8155 | MRT-CA00-P3CYP-160002 | 2019-04-23 | MRT-HK-REC-TT-190568 | FA | 2 | TRUE | TRUE | FALSE
8156 | MRT-YT01-P0EKF-125610 | 2019-04-23 | MRT-HK-REC-TT-190569 | FA | 3 | TRUE | TRUE | FALSE
8157 | MRT-CC05-P0EKF-125613 | 2019-04-23 | MRT-HK-REC-TT-190569 | FA | 3 | TRUE | TRUE | FALSE
8158 | MRT-CC02-P2UHA-170103 | 2019-04-23 | MRT-DS-REC-TT-190119 | FC | 10 | TRUE | TRUE | FALSE
8159 | MRT-CC02-P3UHA-170103 | 2019-04-23 | MRT-DS-REC-TT-190119 | FC | 10 | TRUE | TRUE | FALSE
8168 | MRT-CC02-P2UMA-170607 | 2019-04-23 | MRT-DS-REC-TT-190099-FC | FC | 5 | TRUE | TRUE | FALSE
8169 | MRT-CC02-P2UMA-170608 | 2019-04-23 | MRT-DS-REC-TT-190099-FC | FC | 5 | TRUE | TRUE | FALSE
8170 | MRT-CC02-P3UMA-170607 | 2019-04-23 | MRT-DS-REC-TT-190099-FC | FC | 5 | TRUE | TRUE | FALSE
8171 | MRT-CC02-P3UMA-170608 | 2019-04-23 | MRT-DS-REC-TT-190099-FC | FC | 5 | TRUE | TRUE | FALSE
8160 | MRT-QM03-P0ZEN-155026 | 2019-04-24 | MRT-HK-REC-TT-190570 | FA | 0 | TRUE | TRUE | FALSE
8161 | MRT-XA01-P0ABA-150510 | 2019-04-24 | MRT-HK-REC-TT-190571 | FA | 4 | TRUE | TRUE | FALSE
8162 | MRT-CA05-P0UYX-145100 | 2019-04-24 | MRT-HK-REC-TT-190572 | FA | 1 | TRUE | TRUE | FALSE
8163 | MRT-CA05-P0UYX-145102 | 2019-04-24 | MRT-HK-REC-TT-190572 | FA | 2 | TRUE | TRUE | FALSE
8164 | MRT-CA05-P0UYX-145103 | 2019-04-24 | MRT-HK-REC-TT-190572 | FA | 1 | TRUE | TRUE | FALSE
8165 | MRT-QM03-P0ZEN-145007 | 2019-04-24 | MRT-HK-REC-TT-190573 | FA | 1 | TRUE | TRUE | FALSE
8166 | MRT-CC02-P2UHA-170103 | 2019-04-25 | MRT-DS-REC-TT-190119-FC | FC | 10 | TRUE | TRUE | FALSE
8167 | MRT-CC02-P3UHA-170103 | 2019-04-25 | MRT-DS-REC-TT-190119-FC | FC | 10 | TRUE | TRUE | FALSE
8177 | MRT-XB00-P2GM-128506 | 2019-04-26 | MRT-DS-REC-TT-190118-FC | FC | 2 | TRUE | TRUE | FALSE
8178 | MRT-XB00-P3GM-128506 | 2019-04-26 | MRT-DS-REC-TT-190118-FC | FC | 2 | TRUE | TRUE | FALSE
8179 | MRT-CQ03-P0MKC-230001 | 2019-04-26 | MRT-DS-REC-TT-190120 | FI | 0 | TRUE | FALSE | FALSE
8180 | MRT-XJ00-P2SCB-145000 | 2019-04-29 | MRT-DS-REC-TT-190088-FC | FC | 0 | TRUE | TRUE | FALSE
8181 | MRT-XJ00-P3LBG-147000 | 2019-04-29 | MRT-DS-REC-TT-190091-FC | FC | 0 | TRUE | TRUE | FALSE
8182 | MRT-XJ00-P0GHD-141000 | 2019-04-29 | MRT-DS-REC-TT-190091-FC | FC | 0 | TRUE | TRUE | FALSE
8183 | MRT-XJ00-P0QJA-141000 | 2019-04-29 | MRT-DS-REC-TT-190091-FC | FC | 0 | TRUE | TRUE | FALSE
8184 | MRT-XJ00-P2QU-145000 | 2019-04-29 | MRT-DS-REC-TT-190091-FC | FC | 0 | TRUE | TRUE | FALSE
8185 | MRT-XJ00-P3QU-146000 | 2019-04-29 | MRT-DS-REC-TT-190091-FC | FC | 0 | TRUE | TRUE | FALSE
8186 | MRT-XJ00-P3QU-147000 | 2019-04-29 | MRT-DS-REC-TT-190091-FC | FC | 0 | TRUE | TRUE | FALSE
8187 | MRT-XJ00-P2MAA-145000 | 2019-04-29 | MRT-DS-REC-TT-190091-FC | FC | 0 | TRUE | TRUE | FALSE
8188 | MRT-XG02-P2LBA-110003 | 2019-04-29 | MRT-DS-REC-TT-190092-FC | FC | 6 | TRUE | TRUE | FALSE
8189 | MRT-XG02-P3LBA-110003 | 2019-04-29 | MRT-DS-REC-TT-190092-FC | FC | 6 | TRUE | TRUE | FALSE
8190 | MRT-XJ00-P3LBA-147000 | 2019-04-29 | MRT-DS-REC-TT-190094-FC | FC | 0 | TRUE | TRUE | FALSE
8191 | MRT-XJ00-P2QC-145000 | 2019-04-29 | MRT-DS-REC-TT-190094-FC | FC | 0 | TRUE | TRUE | FALSE
8192 | MRT-XJ00-P3QC-146000 | 2019-04-29 | MRT-DS-REC-TT-190094-FC | FC | 0 | TRUE | TRUE | FALSE
8193 | MRT-XJ00-P3QC-147000 | 2019-04-29 | MRT-DS-REC-TT-190094-FC | FC | 0 | TRUE | TRUE | FALSE
8194 | MRT-XJ00-P0MKG-141000 | 2019-04-29 | MRT-DS-REC-TT-190094-FC | FC | 0 | TRUE | TRUE | FALSE
8195 | MRT-XJ00-P0EGD-141000 | 2019-04-29 | MRT-DS-REC-TT-190094-FC | FC | 0 | TRUE | TRUE | FALSE
8196 | MRT-XJ00-P0EKG-141000 | 2019-04-29 | MRT-DS-REC-TT-190094-FC | FC | 0 | TRUE | TRUE | FALSE
8197 | MRT-XJ00-P2QFB-145000 | 2019-04-29 | MRT-DS-REC-TT-190094-FC | FC | 0 | TRUE | TRUE | FALSE
8198 | MRT-XJ00-P3QFB-146000 | 2019-04-29 | MRT-DS-REC-TT-190094-FC | FC | 0 | TRUE | TRUE | FALSE
8199 | MRT-XJ00-P3QFB-147000 | 2019-04-29 | MRT-DS-REC-TT-190094-FC | FC | 0 | TRUE | TRUE | FALSE
8200 | MRT-XJ00-P3SCB-147000 | 2019-04-29 | MRT-DS-REC-TT-190094-FC | FC | 0 | TRUE | TRUE | FALSE
8201 | MRT-XJ00-P0GMA-141000 | 2019-04-29 | MRT-DS-REC-TT-190097-FC | FC | 0 | TRUE | TRUE | FALSE
8202 | MRT-YV02-P3MAD-240180 | 2019-04-29 | MRT-DS-REC-TT-190102-FC | FC | 0 | TRUE | TRUE | FALSE
8203 | MRT-VN03-P2LB-122015 | 2019-04-29 | MRT-DS-REC-TT-190107-FC | FC | 5 | TRUE | TRUE | FALSE
8204 | MRT-VN03-P3LB-122015 | 2019-04-29 | MRT-DS-REC-TT-190107-FC | FC | 5 | TRUE | TRUE | FALSE
8205 | MRT-XJ00-P3MKA-220001 | 2019-04-29 | MRT-DS-REC-TT-190103-FC | FC | 3 | TRUE | TRUE | FALSE
8206 | MRT-XJ00-P2LB-122028 | 2019-04-29 | MRT-DS-REC-TT-190104-FC | FC | 4 | TRUE | TRUE | FALSE
8207 | MRT-XJ00-P3LB-122028 | 2019-04-29 | MRT-DS-REC-TT-190104-FC | FC | 4 | TRUE | TRUE | FALSE
8208 | MRT-XJ00-P3PGB-147000 | 2019-04-29 | MRT-DS-REC-TT-190096-FC | FC | 0 | TRUE | TRUE | FALSE
8209 | MRT-XJ00-P2SCA-145000 | 2019-04-29 | MRT-DS-REC-TT-190096-FC | FC | 0 | TRUE | TRUE | FALSE
8210 | MRT-XJ00-P3SCA-147000 | 2019-04-29 | MRT-DS-REC-TT-190096-FC | FC | 0 | TRUE | TRUE | FALSE
8211 | MRT-XJ00-P3SCB-146000 | 2019-04-29 | MRT-DS-REC-TT-190096-FC | FC | 0 | TRUE | TRUE | FALSE
8212 | MRT-XJ00-P3MAA-146000 | 2019-04-29 | MRT-DS-REC-TT-190096-FC | FC | 0 | TRUE | TRUE | FALSE
8213 | MRT-XJ00-P3MAA-147000 | 2019-04-29 | MRT-DS-REC-TT-190096-FC | FC | 0 | TRUE | TRUE | FALSE
8214 | MRT-FF00-P0SGA-135461 | 2019-04-29 | MRT-HK-REC-TT-190574 | FA | 0 | TRUE | FALSE | FALSE
8230 | MRT-XJ00-P3SCA-146000 | 2019-04-29 | MRT-DS-REC-TT-190096-FC | FC | 0 | TRUE | TRUE | FALSE
8215 | MRT-CA03-P0UMA-180036 | 2019-04-30 | MRT-DS-REC-TT-190121 | FC | 4 | TRUE | TRUE | FALSE
8216 | MRT-CA03-P0UMA-180037 | 2019-04-30 | MRT-DS-REC-TT-190121 | FC | 4 | TRUE | TRUE | FALSE
8217 | MRT-CA03-P0UMA-180039 | 2019-04-30 | MRT-DS-REC-TT-190121 | FC | 4 | TRUE | TRUE | FALSE
8218 | MRT-CA03-P0UMA-180040 | 2019-04-30 | MRT-DS-REC-TT-190121 | FC | 4 | TRUE | TRUE | FALSE
8219 | MRT-YE00-P3MKA-230001 | 2019-04-30 | MRT-DS-REC-TT-190112-FC | FC | 3 | TRUE | TRUE | FALSE
8220 | MRT-CA01-P0UMA-180044 | 2019-04-30 | MRT-DS-REC-TT-190116-FC | FC | 3 | TRUE | TRUE | FALSE
8221 | MRT-CA02-P0UMA-180045 | 2019-04-30 | MRT-DS-REC-TT-190116-FC | FC | 3 | TRUE | TRUE | FALSE
8222 | MRT-CA00-P0UMA-180047 | 2019-04-30 | MRT-DS-REC-TT-190116-FC | FC | 4 | TRUE | TRUE | FALSE
8223 | MRT-DD09-P0ZEN-128217 | 2019-04-30 | MRT-HK-REC-TT-190575 | FA | 0 | TRUE | FALSE | FALSE
8224 | MRT-DD09-P0ZEN-128216 | 2019-04-30 | MRT-HK-REC-TT-190575 | FA | 0 | TRUE | FALSE | FALSE
8225 | MRT-XG02-P2SGE-135407 | 2019-05-02 | MRT-HK-REC-TT-190576 | FA | 0 | TRUE | FALSE | FALSE
8226 | MRT-FF01-P2SGA-135430 | 2019-05-02 | MRT-HK-REC-TT-190576 | FA | 0 | TRUE | FALSE | FALSE
8227 | MRT-XG02-P2SGC-135415 | 2019-05-02 | MRT-HK-REC-TT-190576 | FA | 0 | TRUE | FALSE | FALSE
8228 | MRT-UE00-P2LB-122008 | 2019-05-03 | MRT-DS-REC-TT-190115-FC | FC | 7 | TRUE | TRUE | FALSE
8229 | MRT-UE00-P3LB-122008 | 2019-05-03 | MRT-DS-REC-TT-190115-FC | FC | 5 | TRUE | TRUE | FALSE
8231 | MRT-YT01-P0QJA-110001 | 2019-05-07 | MRT-DS-REC-TT-190114-FC | FC | 0 | TRUE | TRUE | FALSE
8232 | MRT-QM03-P3CYP-160050 | 2019-05-07 | MRT-HK-REC-TT-190579 | FA | 1 | TRUE | TRUE | FALSE
8233 | MRT-XV00-P3GC-135115 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 0 | TRUE | FALSE | FALSE
8234 | MRT-US02-P3GC-135140 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 0 | TRUE | FALSE | FALSE
8235 | MRT-YT01-P0GN-135295 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 0 | TRUE | FALSE | FALSE
8236 | MRT-YT01-P0GN-135296 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 0 | TRUE | FALSE | FALSE
8237 | MRT-UT00-P0GN-135282 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 0 | TRUE | FALSE | FALSE
8238 | MRT-XB00-P0GN-135238 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 0 | TRUE | FALSE | FALSE
8239 | MRT-YT01-P0GN-135288 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 0 | TRUE | FALSE | FALSE
8240 | MRT-YT01-P0GN-135235 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 0 | TRUE | FALSE | FALSE
8241 | MRT-YT01-P0GN-135285 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 0 | TRUE | FALSE | FALSE
8242 | MRT-YT01-P0GN-135234 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 0 | TRUE | FALSE | FALSE
8243 | MRT-YT01-P0GN-135233 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 0 | TRUE | FALSE | FALSE
8244 | MRT-XA00-P3GC-135105 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 3 | TRUE | TRUE | FALSE
8245 | MRT-XA00-P0GN-135205 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 2 | TRUE | TRUE | FALSE
8246 | MRT-XH01-P0GN-135239 | 2019-05-07 | MRT-HK-REC-TT-190577 | FA | 1 | TRUE | TRUE | FALSE
8247 | MRT-XG02-P2SGC-135419 | 2019-05-07 | MRT-HK-REC-TT-190578 | FA | 0 | TRUE | FALSE | FALSE
8248 | MRT-DN04-P0BRU-150267 | 2019-05-07 | MRT-HK-REC-TT-190580 | FA | 0 | TRUE | FALSE | FALSE
8249 | MRT-DS00-P3GC-135841 | 2019-05-07 | MRT-HK-REC-TT-190581 | FI | 0 | TRUE | FALSE | FALSE
8250 | MRT-DS00-P3GC-135842 | 2019-05-07 | MRT-HK-REC-TT-190581 | FI | 0 | TRUE | FALSE | FALSE
8251 | MRT-DS00-P3GC-135846 | 2019-05-07 | MRT-HK-REC-TT-190581 | FI | 0 | TRUE | FALSE | FALSE
8252 | MRT-DS00-P3GC-135848 | 2019-05-07 | MRT-HK-REC-TT-190581 | FI | 0 | TRUE | FALSE | FALSE
8253 | MRT-DS00-P0GN-135868 | 2019-05-07 | MRT-HK-REC-TT-190581 | FI | 0 | TRUE | FALSE | FALSE
8254 | MRT-DP00-P0GN-135244 | 2019-05-07 | MRT-HK-REC-TT-190581 | FI | 1 | TRUE | TRUE | FALSE
8255 | MRT-DP00-P3GC-135142 | 2019-05-07 | MRT-HK-REC-TT-190581 | FI | 1 | TRUE | TRUE | FALSE
8256 | MRT-CQ03-P0MKC-230002 | 2019-05-07 | MRT-DS-REC-TT-190122 | FI | 0 | TRUE | FALSE | FALSE
8257 | MRT-CQ03-P0MKC-230014 | 2019-05-07 | MRT-DS-REC-TT-190122 | FI | 0 | TRUE | FALSE | FALSE
8258 | MRT-CQ03-P0MKC-230015 | 2019-05-07 | MRT-DS-REC-TT-190122 | FI | 0 | TRUE | FALSE | FALSE
8259 | MRT-CQ03-P0MKC-230017 | 2019-05-07 | MRT-DS-REC-TT-190122 | FI | 0 | TRUE | FALSE | FALSE
8260 | MRT-CA03-P0UMA-180036 | 2019-05-07 | MRT-DS-REC-TT-190121-FC | FC | 4 | TRUE | TRUE | FALSE
8261 | MRT-CA03-P0UMA-180037 | 2019-05-07 | MRT-DS-REC-TT-190121-FC | FC | 4 | TRUE | TRUE | FALSE
8262 | MRT-CA03-P0UMA-180039 | 2019-05-07 | MRT-DS-REC-TT-190121-FC | FC | 4 | TRUE | TRUE | FALSE
8263 | MRT-CA03-P0UMA-180040 | 2019-05-07 | MRT-DS-REC-TT-190121-FC | FC | 4 | TRUE | TRUE | FALSE
8264 | MRT-DP00-P2LB-122123 | 2019-05-08 | MRT-DS-REC-TT-190113-FC | FC | 0 | TRUE | TRUE | FALSE
8265 | MRT-DP00-P3LB-122123 | 2019-05-08 | MRT-DS-REC-TT-190113-FC | FC | 0 | TRUE | TRUE | FALSE
8266 | MRT-XK00-P3LBA-143000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8267 | MRT-XK00-P4LBA-144000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8268 | MRT-XK00-P2LAB-142000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8269 | MRT-XK00-P3LAB-143000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8270 | MRT-XK00-P4LAB-144000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8271 | MRT-XK00-P2LBG-142000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8272 | MRT-XK00-P3LBG-143000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8273 | MRT-XK00-P4LBG-144000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8274 | MRT-XK00-P2LCA-142000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8275 | MRT-XK00-P3LCA-143000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8276 | MRT-XK00-P4LCA-144000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8277 | MRT-XK00-P2LCM-142000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8278 | MRT-XK00-P3LCM-143000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8279 | MRT-XK00-P4LCM-144000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8280 | MRT-XK00-P2ACW-142000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8281 | MRT-XK00-P3ACW-143000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8282 | MRT-XK00-P4ACW-144000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8283 | MRT-XK00-P2MAM-142000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8284 | MRT-XK00-P3MAM-142000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8285 | MRT-XK00-P4MAM-142000 | 2019-05-08 | MRT-DS-REC-TT-190110-FC | FC | 0 | TRUE | TRUE | FALSE
8286 | MRT-QM03-P0ZEN-145007 | 2019-05-09 | MRT-HK-REC-TT-190852 | FA | 2 | TRUE | TRUE | FALSE
8287 | MRT-CQ03-P0MKC-230001 | 2019-05-09 | MRT-DS-REC-TT-190120-FC | FC | 0 | TRUE | TRUE | FALSE
8288 | MRT-YD05-P0GDY-135060 | 2019-05-09 | MRT-HK-REC-TT-190584 | FA | 1 | TRUE | TRUE | FALSE
8289 | MRT-YK08-P3CYP-160005 | 2019-05-09 | MRT-HK-REC-TT-190587 | FA | 2 | TRUE | TRUE | FALSE
8296 | MRT-DD01-P0ZEN-175017 | 2019-05-09 | MRT-HK-REC-TT-190588 | FA | 0 | TRUE | FALSE | FALSE
8297 | MRT-QA00-P0SGA-135482 | 2019-05-09 | MRT-HK-REC-TT-190585 | FA | 0 | TRUE | FALSE | FALSE
8298 | MRT-FF01-P0SGA-135413 | 2019-05-09 | MRT-HK-REC-TT-190586 | FA | 0 | TRUE | FALSE | FALSE
8290 | MRT-DM01-P0ZEN-140002 | 2019-05-10 | MRT-DS-REC-TT-190123 | FI | 1 | TRUE | TRUE | FALSE
8291 | MRT-YT01-P3MKA-240003 | 2019-05-10 | MRT-DS-REC-TT-190124 | FI | 5 | TRUE | TRUE | FALSE
8292 | MRT-CQ03-P0MKC-230002 | 2019-05-10 | MRT-DS-REC-TT-190122-FC | FC | 0 | TRUE | TRUE | FALSE
8293 | MRT-CQ03-P0MKC-230014 | 2019-05-10 | MRT-DS-REC-TT-190122-FC | FC | 0 | TRUE | TRUE | FALSE
8294 | MRT-CQ03-P0MKC-230015 | 2019-05-10 | MRT-DS-REC-TT-190122-FC | FC | 0 | TRUE | TRUE | FALSE
8295 | MRT-CQ03-P0MKC-230017 | 2019-05-10 | MRT-DS-REC-TT-190122-FC | FC | 0 | TRUE | TRUE | FALSE
10609 | MRT-DT01-P0QHB-125429 | 2019-05-10 | MRT-HK-REC-TT-190589 | FA | 1 | TRUE | TRUE | FALSE
8299 | MRT-DT01-P0QHB-125427 | 2019-05-14 | MRT-HK-REC-TT-190590 | FA | 1 | TRUE | TRUE | FALSE
8742 | MRT-YU02-P0BJN-150709 | 2019-05-14 | MRT-HK-REC-TT-190594 | FA | 0 | TRUE | FALSE | FALSE
8743 | MRT-YU02-P0BJM-150711 | 2019-05-14 | MRT-HK-REC-TT-190594 | FA | 0 | TRUE | FALSE | FALSE
8744 | MRT-YU02-P0BJK-150703 | 2019-05-14 | MRT-HK-REC-TT-190594 | FA | 0 | TRUE | FALSE | FALSE
8745 | MRT-US02-P0BJN-150710 | 2019-05-14 | MRT-HK-REC-TT-190594 | FA | 0 | TRUE | FALSE | FALSE
8746 | MRT-US02-P0BJM-150712 | 2019-05-14 | MRT-HK-REC-TT-190594 | FA | 0 | TRUE | FALSE | FALSE
8747 | MRT-US02-P0BJK-150704 | 2019-05-14 | MRT-HK-REC-TT-190594 | FA | 0 | TRUE | FALSE | FALSE
8301 | MRT-DD01-P0ZEN-175018 | 2019-05-15 | MRT-HK-REC-TT-190591 | FA | 0 | TRUE | FALSE | FALSE
8302 | MRT-YK10-P2MAA-185140 | 2019-05-15 | MRT-HK-REC-TT-190592 | FI | 0 | TRUE | FALSE | FALSE
8303 | MRT-FF01-P0SGA-135435 | 2019-05-15 | MRT-HK-REC-TT-190593 | FA | 0 | TRUE | FALSE | FALSE
8304 | MRT-CQ03-P0MKC-230012 | 2019-05-15 | MRT-DS-REC-TT-190126 | FI | 0 | TRUE | FALSE | FALSE
8305 | MRT-CQ03-P0MKC-230013 | 2019-05-15 | MRT-DS-REC-TT-190126 | FI | 0 | TRUE | FALSE | FALSE
8306 | MRT-YD00-P2CJA-240057 | 2019-05-15 | MRT-DS-REC-TT-190127 | FC | 2 | TRUE | TRUE | FALSE
8307 | MRT-YD00-P2CJA-240058 | 2019-05-15 | MRT-DS-REC-TT-190127 | FC | 2 | TRUE | TRUE | FALSE
8308 | MRT-YD00-P2CJA-240059 | 2019-05-15 | MRT-DS-REC-TT-190127 | FC | 2 | TRUE | TRUE | FALSE
8309 | MRT-YF00-P2CJJ-240064 | 2019-05-15 | MRT-DS-REC-TT-190125 | FI | 1 | TRUE | TRUE | FALSE
10627 | MRT-YL01-P2MKA-125508 | 2019-05-15 | MRT-HK-REC-TT-190595 | FA | 0 | TRUE | FALSE | FALSE
8310 | MRT-YR05-P0GEN-135372 | 2019-05-16 | MRT-HK-REC-TT-190596 | FA | 1 | TRUE | TRUE | FALSE
8311 | MRT-YR05-P0GEN-135374 | 2019-05-16 | MRT-HK-REC-TT-190596 | FA | 1 | TRUE | TRUE | FALSE
8312 | MRT-YR05-P0GEN-135375 | 2019-05-16 | MRT-HK-REC-TT-190596 | FA | 1 | TRUE | TRUE | FALSE
8313 | MRT-YR05-P0GEN-135373 | 2019-05-16 | MRT-HK-REC-TT-190596 | FA | 1 | TRUE | TRUE | FALSE
8314 | MRT-YR05-P0GEN-135371 | 2019-05-16 | MRT-HK-REC-TT-190596 | FA | 1 | TRUE | TRUE | FALSE
8315 | MRT-DD03-P0GEN-135386 | 2019-05-16 | MRT-HK-REC-TT-190597 | FA | 1 | TRUE | TRUE | FALSE
8316 | MRT-DS00-P3GC-135181 | 2019-05-16 | MRT-HK-REC-TT-190597 | FA | 1 | TRUE | TRUE | FALSE
8317 | MRT-QM07-P0GEN-135710 | 2019-05-16 | MRT-HK-REC-TT-190597 | FA | 0 | TRUE | FALSE | FALSE
8318 | MRT-BT00-P0GEN-135702 | 2019-05-16 | MRT-HK-REC-TT-190598 | FA | 1 | TRUE | TRUE | FALSE
8319 | MRT-XR00-P0SA-135744 | 2019-05-16 | MRT-HK-REC-TT-190599 | FA | 0 | TRUE | FALSE | FALSE
8320 | MRT-XR00-P0SA-135743 | 2019-05-16 | MRT-HK-REC-TT-190599 | FA | 0 | TRUE | FALSE | FALSE
8321 | MRT-XR00-P0SA-135745 | 2019-05-16 | MRT-HK-REC-TT-190599 | FA | 0 | TRUE | FALSE | FALSE
8322 | MRT-XR00-P0SA-135746 | 2019-05-16 | MRT-HK-REC-TT-190599 | FA | 0 | TRUE | FALSE | FALSE
8323 | MRT-XR00-P0SA-135747 | 2019-05-16 | MRT-HK-REC-TT-190599 | FA | 0 | TRUE | FALSE | FALSE
8324 | MRT-XR00-P0SA-135748 | 2019-05-16 | MRT-HK-REC-TT-190599 | FA | 0 | TRUE | FALSE | FALSE
8325 | MRT-XR00-P0SA-135749 | 2019-05-16 | MRT-HK-REC-TT-190599 | FA | 0 | TRUE | FALSE | FALSE
8326 | MRT-XR00-P0SA-135751 | 2019-05-16 | MRT-HK-REC-TT-190599 | FA | 0 | TRUE | FALSE | FALSE
8327 | MRT-XR00-P0SA-135752 | 2019-05-16 | MRT-HK-REC-TT-190599 | FA | 0 | TRUE | FALSE | FALSE
8328 | MRT-XR00-P0SA-135758 | 2019-05-16 | MRT-HK-REC-TT-190599 | FA | 0 | TRUE | FALSE | FALSE
8329 | MRT-HM01-P0SAC-135533 | 2019-05-16 | MRT-HK-REC-TT-190600 | FA | 0 | TRUE | FALSE | FALSE
8330 | MRT-DP00-P0SA-135741 | 2019-05-16 | MRT-HK-REC-TT-190600 | FA | 0 | TRUE | FALSE | FALSE
8331 | MRT-XG01-P2MAA-220045 | 2019-05-16 | MRT-DS-REC-TT-190128 | FC | 2 | TRUE | TRUE | FALSE
8332 | MRT-XN00-P3MAV-220039 | 2019-05-16 | MRT-DS-REC-TT-190128 | FC | 1 | TRUE | TRUE | FALSE
8333 | MRT-XJ00-P2MAA-142000 | 2019-05-17 | MRT-DS-REC-TT-190129 | FI | 0 | TRUE | FALSE | FALSE
8334 | MRT-XJ00-P3MAA-143000 | 2019-05-17 | MRT-DS-REC-TT-190129 | FI | 0 | TRUE | FALSE | FALSE
8335 | MRT-XJ00-P3MAA-144000 | 2019-05-17 | MRT-DS-REC-TT-190129 | FI | 0 | TRUE | FALSE | FALSE
8336 | MRT-DM02-P3MAA-220174 | 2019-05-21 | MRT-DS-REC-TT-190131 | FC | 1 | TRUE | TRUE | FALSE
8337 | MRT-DM02-P2LBS-220087 | 2019-05-21 | MRT-DS-REC-TT-190131 | FC | 1 | TRUE | TRUE | FALSE
8338 | MRT-DM02-P3MAA-220175 | 2019-05-21 | MRT-DS-REC-TT-190130 | FI | 0 | TRUE | FALSE | FALSE
8339 | MRT-CC02-P2UMA-170207 | 2019-05-21 | MRT-DS-REC-TT-190132 | FC | 6 | TRUE | TRUE | FALSE
8340 | MRT-CC02-P3UMA-170208 | 2019-05-21 | MRT-DS-REC-TT-190132 | FC | 5 | TRUE | TRUE | FALSE
8341 | MRT-XJ00-P0LAA-140000 | 2019-05-21 | MRT-DS-REC-TT-190133 | FI | 0 | TRUE | FALSE | FALSE
8342 | MRT-XJ00-P3LBA-144000 | 2019-05-21 | MRT-DS-REC-TT-190111-FC | FC | 1 | TRUE | TRUE | FALSE
8343 | MRT-XJ00-P3LBG-144000 | 2019-05-21 | MRT-DS-REC-TT-190111-FC | FC | 1 | TRUE | TRUE | FALSE
8344 | MRT-XJ00-P3LCM-144000 | 2019-05-21 | MRT-DS-REC-TT-190111-FC | FC | 1 | TRUE | TRUE | FALSE
8345 | MRT-XJ00-P3LAB-144000 | 2019-05-21 | MRT-DS-REC-TT-190111-FC | FC | 1 | TRUE | TRUE | FALSE
8346 | MRT-XJ00-P3LCA-144000 | 2019-05-21 | MRT-DS-REC-TT-190111-FC | FC | 1 | TRUE | TRUE | FALSE
8347 | MRT-XJ00-P3PGB-144000 | 2019-05-21 | MRT-DS-REC-TT-190111-FC | FC | 1 | TRUE | TRUE | FALSE
8348 | MRT-QM03-P0ZEN-145007 | 2019-05-21 | MRT-HK-REC-TT-190601 | FA | 3 | TRUE | TRUE | FALSE
8349 | MRT-DD09-P0ZEN-128202 | 2019-05-21 | MRT-HK-REC-TT-190601 | FA | 0 | TRUE | TRUE | FALSE
8350 | MRT-YB10-P0BBA-150891 | 2019-05-21 | MRT-HK-REC-TT-190602 | FA | 0 | TRUE | FALSE | FALSE
8351 | MRT-US02-P0BJC-150692 | 2019-05-21 | MRT-HK-REC-TT-190604 | FA | 0 | TRUE | FALSE | FALSE
8352 | MRT-YU02-P0BJC-150691 | 2019-05-21 | MRT-HK-REC-TT-190604 | FA | 0 | TRUE | FALSE | FALSE
8353 | MRT-DS00-P0ZEN-150276 | 2019-05-21 | MRT-HK-REC-TT-190605 | FA | 0 | TRUE | FALSE | FALSE
8354 | MRT-QM03-P0ZEN-150274 | 2019-05-21 | MRT-HK-REC-TT-190605 | FA | 0 | TRUE | FALSE | FALSE
8355 | MRT-YD00-P0ANA-150643 | 2019-05-21 | MRT-HK-REC-TT-190606 | FA | 0 | TRUE | FALSE | FALSE
8356 | MRT-YT01-P0ANA-150647 | 2019-05-21 | MRT-HK-REC-TT-190606 | FA | 0 | TRUE | FALSE | FALSE
8357 | MRT-YD00-P0ANA-150648 | 2019-05-21 | MRT-HK-REC-TT-190606 | FA | 0 | TRUE | FALSE | FALSE
8358 | MRT-YD00-P0ANA-150649 | 2019-05-21 | MRT-HK-REC-TT-190606 | FA | 0 | TRUE | FALSE | FALSE
8359 | MRT-YD00-P0ANA-150650 | 2019-05-21 | MRT-HK-REC-TT-190606 | FA | 0 | TRUE | FALSE | FALSE
8360 | MRT-XG02-P0SGA-135414 | 2019-05-21 | MRT-HK-REC-TT-190607 | FA | 0 | TRUE | FALSE | FALSE
8361 | MRT-BAB-P3BAT-150395 | 2019-05-21 | MRT-HK-REC-TT-190608 | FA | 2 | TRUE | TRUE | FALSE
8362 | MRT-BAB-P2BAT-150372 | 2019-05-21 | MRT-HK-REC-TT-190608 | FA | 2 | TRUE | TRUE | FALSE
8363 | MRT-CC07-P0UZA-175101 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8364 | MRT-CC09-P0UZA-175111 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8365 | MRT-CC02-P0UYX-175211 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8366 | MRT-CC02-P0UYX-175231 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8367 | MRT-CC09-P0UZA-175112 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8368 | MRT-CC09-P0UZA-175113 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8369 | MRT-CC09-P0UZA-175114 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8370 | MRT-CC09-P0UZA-175115 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8371 | MRT-CC09-P0UZA-175116 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8372 | MRT-CC09-P0UZA-175117 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8373 | MRT-CC09-P0UZA-175118 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8374 | MRT-CC09-P0UZA-175119 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8375 | MRT-CC09-P0UZA-175120 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8376 | MRT-CC09-P0UZA-175121 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8377 | MRT-CC09-P0UZA-175122 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8378 | MRT-CC09-P0UZA-175123 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8379 | MRT-CC09-P0UZA-175124 | 2019-05-21 | MRT-HK-REC-TT-190609 | FA | 0 | TRUE | FALSE | FALSE
8380 | MRT-CC04-P0ULY-176145 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8381 | MRT-CC04-P0ULY-176150 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8382 | MRT-CC04-P0ULY-176155 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8383 | MRT-CC04-P0ULY-176160 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8384 | MRT-CC04-P0ULY-176153 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8385 | MRT-CC04-P0ULY-176154 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8386 | MRT-CC04-P0ULY-176156 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8387 | MRT-CC04-P0ULY-176157 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8388 | MRT-CC04-P0ULY-176161 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8389 | MRT-CC04-P0ULY-176162 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8390 | MRT-CC04-P0ULY-176163 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8391 | MRT-CC04-P0ULY-176164 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8392 | MRT-CC04-P0ULY-176165 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8393 | MRT-CC04-P0ULY-176166 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8394 | MRT-CC04-P0ULY-176167 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8395 | MRT-CC04-P0ULY-176168 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8396 | MRT-CC04-P0ULY-176169 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8397 | MRT-CC04-P0ULY-176170 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8398 | MRT-CC04-P0ULY-176171 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8399 | MRT-CC04-P0ULY-176172 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8400 | MRT-CC04-P0ULY-176180 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8401 | MRT-CC04-P0ULY-176181 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8402 | MRT-CC04-P0ULY-176182 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8403 | MRT-CC04-P0ULY-176183 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8404 | MRT-CC04-P0ULY-176184 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8405 | MRT-CC04-P0ULY-176185 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8406 | MRT-CC04-P0ULY-176186 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8407 | MRT-CC04-P0ULY-176187 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8408 | MRT-CC04-P0ULY-176173 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8409 | MRT-CC04-P0ULY-176174 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8410 | MRT-CC04-P0ULY-176175 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8411 | MRT-CC04-P0ULY-176177 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8412 | MRT-CC04-P0ULY-176178 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8413 | MRT-CC04-P0ULY-176179 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8414 | MRT-CC04-P0ULY-176197 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8415 | MRT-CC04-P0ULY-176198 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8416 | MRT-CC04-P0ULY-176199 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 2 | TRUE | TRUE | FALSE
8417 | MRT-CC04-P0ULY-176201 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 1 | TRUE | TRUE | FALSE
8418 | MRT-CC04-P0ULY-176203 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 1 | TRUE | TRUE | FALSE
8419 | MRT-CC04-P0ULY-176206 | 2019-05-21 | MRT-HK-REC-TT-190610 | FA | 1 | TRUE | TRUE | FALSE
8420 | MRT-CC07-P0ULX-176215 | 2019-05-21 | MRT-HK-REC-TT-190611 | FA | 1 | TRUE | TRUE | FALSE
8421 | MRT-CC02-P0ULX-176218 | 2019-05-21 | MRT-HK-REC-TT-190611 | FA | 1 | TRUE | TRUE | FALSE
8422 | MRT-CC02-P0ULX-176219 | 2019-05-21 | MRT-HK-REC-TT-190611 | FA | 1 | TRUE | TRUE | FALSE
8423 | MRT-CC02-P0ULX-176220 | 2019-05-21 | MRT-HK-REC-TT-190611 | FA | 1 | TRUE | TRUE | FALSE
8424 | MRT-CC02-P0ULX-176221 | 2019-05-21 | MRT-HK-REC-TT-190611 | FA | 1 | TRUE | TRUE | FALSE
8425 | MRT-CC02-P0ULX-176222 | 2019-05-21 | MRT-HK-REC-TT-190611 | FA | 1 | TRUE | TRUE | FALSE
8426 | MRT-CC02-P0ULX-176223 | 2019-05-21 | MRT-HK-REC-TT-190611 | FA | 1 | TRUE | TRUE | FALSE
8427 | MRT-CC02-P0ULX-176224 | 2019-05-21 | MRT-HK-REC-TT-190611 | FA | 1 | TRUE | TRUE | FALSE
8428 | MRT-CC02-P0ULX-176225 | 2019-05-21 | MRT-HK-REC-TT-190611 | FA | 1 | TRUE | TRUE | FALSE
8429 | MRT-QM03-P0ZEN-145007 | 2019-05-22 | MRT-HK-REC-TT-190612 | FA | 4 | TRUE | TRUE | FALSE
8430 | MRT-VN03-P2LB-122015 | 2019-05-23 | MRT-DS-REC-TT-190134 | FC | 6 | TRUE | TRUE | FALSE
8431 | MRT-VN03-P3LB-122015 | 2019-05-23 | MRT-DS-REC-TT-190134 | FC | 6 | TRUE | TRUE | FALSE
8432 | MRT-DS00-P0GN-135865 | 2019-05-24 | MRT-HK-REC-TT-190613 | FI | 0 | TRUE | FALSE | FALSE
8433 | MRT-DN03-P0GN-135276 | 2019-05-24 | MRT-HK-REC-TT-190613 | FA | 1 | TRUE | TRUE | FALSE
8434 | MRT-DN03-P3GC-135180 | 2019-05-24 | MRT-HK-REC-TT-190613 | FA | 1 | TRUE | TRUE | FALSE
8435 | MRT-XN00-P2QU-130029 | 2019-05-24 | MRT-DS-REC-TT-180152-FC | FC | 0 | TRUE | TRUE | FALSE
8436 | MRT-XN00-P3QU-130029 | 2019-05-24 | MRT-DS-REC-TT-180152-FC | FC | 0 | TRUE | TRUE | FALSE
8437 | MRT-YL00-P3QU-130028 | 2019-05-24 | MRT-DS-REC-TT-180153-FC | FC | 0 | TRUE | TRUE | FALSE
8438 | MRT-YK09-P2GHC-129003 | 2019-05-24 | MRT-DS-REC-TT-180190-FC | FC | 0 | TRUE | TRUE | FALSE
8439 | MRT-YK09-P3GHC-129003 | 2019-05-24 | MRT-DS-REC-TT-180190-FC | FC | 0 | TRUE | TRUE | FALSE
8440 | MRT-YK08-P0SMM-128001 | 2019-05-24 | MRT-DS-REC-TT-180232-FC | FC | 0 | TRUE | TRUE | FALSE
8441 | MRT-YK08-P2MAJ-603205 | 2019-05-24 | MRT-DS-REC-TT-180269-FC | FC | 1 | TRUE | TRUE | FALSE
8442 | MRT-YK08-P3MAJ-604205 | 2019-05-24 | MRT-DS-REC-TT-180269-FC | FC | 1 | TRUE | TRUE | FALSE
8443 | MRT-YT01-P2GHC-129004 | 2019-05-24 | MRT-DS-REC-TT-180277-FC | FC | 0 | TRUE | TRUE | FALSE
8444 | MRT-YT01-P3GHC-129004 | 2019-05-24 | MRT-DS-REC-TT-180277-FC | FC | 0 | TRUE | TRUE | FALSE
8445 | MRT-YT01-P3QU-130030 | 2019-05-24 | MRT-DS-REC-TT-180293-FC | FC | 0 | TRUE | TRUE | FALSE
8446 | MRT-YL00-P2GHC-129011 | 2019-05-24 | MRT-DS-REC-TT-180382-FC | FC | 0 | TRUE | TRUE | FALSE
8447 | MRT-YL00-P3GHC-129011 | 2019-05-24 | MRT-DS-REC-TT-180382-FC | FC | 0 | TRUE | TRUE | FALSE
8448 | MRT-YS18-P0SMM-128010 | 2019-05-24 | MRT-DS-REC-TT-180401-FC | FC | 1 | TRUE | TRUE | FALSE
8449 | MRT-YD00-P2LAC-126016 | 2019-05-24 | MRT-DS-REC-TT-180422-FC | FC | 0 | TRUE | TRUE | FALSE
8450 | MRT-YD00-P3LAC-126016 | 2019-05-24 | MRT-DS-REC-TT-180422-FC | FC | 0 | TRUE | TRUE | FALSE
8451 | MRT-YD00-P2LAC-126064 | 2019-05-24 | MRT-DS-REC-TT-180422-FC | FC | 0 | TRUE | TRUE | FALSE
8452 | MRT-YD00-P3LAC-126064 | 2019-05-24 | MRT-DS-REC-TT-180422-FC | FC | 0 | TRUE | TRUE | FALSE
8453 | MRT-YT01-P2QU-130030 | 2019-05-24 | MRT-DS-REC-TT-180423-FC | FC | 1 | TRUE | TRUE | FALSE
8454 | MRT-YL00-P2QU-130028 | 2019-05-24 | MRT-DS-REC-TT-180424-FC | FC | 1 | TRUE | TRUE | FALSE
8455 | MRT-XF00-P2GM-128510 | 2019-05-24 | MRT-DS-REC-TT-180442-FC | FC | 0 | TRUE | TRUE | FALSE
8456 | MRT-XF00-P3GM-128510 | 2019-05-24 | MRT-DS-REC-TT-180442-FC | FC | 0 | TRUE | TRUE | FALSE
8457 | MRT-YT01-P2MAJ-603206 | 2019-05-24 | MRT-DS-REC-TT-180448-FC | FC | 1 | TRUE | TRUE | FALSE
8458 | MRT-YT01-P3MAJ-604206 | 2019-05-24 | MRT-DS-REC-TT-180448-FC | FC | 1 | TRUE | TRUE | FALSE
8459 | MRT-YL08-P2LB-122083 | 2019-05-24 | MRT-DS-REC-TT-180487-FC | FC | 0 | TRUE | TRUE | FALSE
8460 | MRT-YL22-P2GHC-129014 | 2019-05-24 | MRT-DS-REC-TT-180502-FC | FC | 0 | TRUE | TRUE | FALSE
8461 | MRT-YL22-P3GHC-129014 | 2019-05-24 | MRT-DS-REC-TT-180502-FC | FC | 0 | TRUE | TRUE | FALSE
8462 | MRT-YT01-P2QC-130033 | 2019-05-24 | MRT-DS-REC-TT-180509-FC | FC | 1 | TRUE | TRUE | FALSE
8463 | MRT-YT01-P3QC-130033 | 2019-05-24 | MRT-DS-REC-TT-180509-FC | FC | 1 | TRUE | TRUE | FALSE
8464 | MRT-YT01-P2QC-130014 | 2019-05-24 | MRT-DS-REC-TT-180511-FC | FC | 1 | TRUE | TRUE | FALSE
8465 | MRT-YT01-P3QC-130014 | 2019-05-24 | MRT-DS-REC-TT-180511-FC | FC | 1 | TRUE | TRUE | FALSE
8466 | MRT-XN00-P2QC-130008 | 2019-05-24 | MRT-DS-REC-TT-180519-FC | FC | 1 | TRUE | TRUE | FALSE
8467 | MRT-XN00-P3QC-130008 | 2019-05-24 | MRT-DS-REC-TT-180519-FC | FC | 1 | TRUE | TRUE | FALSE
8468 | MRT-YF00-P2QC-130019 | 2019-05-24 | MRT-DS-REC-TT-180520-FC | FC | 1 | TRUE | TRUE | FALSE
8469 | MRT-YF00-P3QC-130019 | 2019-05-24 | MRT-DS-REC-TT-180520-FC | FC | 1 | TRUE | TRUE | FALSE
8470 | MRT-XK00-P2LAC-126013 | 2019-05-24 | MRT-DS-REC-TT-180556-FC | FC | 0 | TRUE | TRUE | FALSE
8471 | MRT-XK00-P3LAC-126013 | 2019-05-24 | MRT-DS-REC-TT-180556-FC | FC | 0 | TRUE | TRUE | FALSE
8472 | MRT-XK00-P2LAC-126063 | 2019-05-24 | MRT-DS-REC-TT-180556-FC | FC | 0 | TRUE | TRUE | FALSE
8473 | MRT-XK00-P3LAC-126063 | 2019-05-24 | MRT-DS-REC-TT-180556-FC | FC | 0 | TRUE | TRUE | FALSE
8474 | MRT-YT01-P2QC-130013 | 2019-05-24 | MRT-DS-REC-TT-180563-FC | FC | 1 | TRUE | TRUE | FALSE
8475 | MRT-YT01-P3QC-130013 | 2019-05-24 | MRT-DS-REC-TT-180563-FC | FC | 1 | TRUE | TRUE | FALSE
8476 | MRT-YR01-P2LB-122082 | 2019-05-24 | MRT-DS-REC-TT-180595-FC | FC | 0 | TRUE | TRUE | FALSE
8477 | MRT-YL00-P2QC-130007 | 2019-05-24 | MRT-DS-REC-TT-180694-FC | FC | 2 | TRUE | TRUE | FALSE
8478 | MRT-YL00-P3QC-130007 | 2019-05-24 | MRT-DS-REC-TT-180694-FC | FC | 2 | TRUE | TRUE | FALSE
8479 | MRT-YT01-P2QC-130016 | 2019-05-24 | MRT-DS-REC-TT-180695-FC | FC | 2 | TRUE | TRUE | FALSE
8480 | MRT-YT01-P3QC-130016 | 2019-05-24 | MRT-DS-REC-TT-180695-FC | FC | 2 | TRUE | TRUE | FALSE
8481 | MRT-YT01-P2QC-130012 | 2019-05-24 | MRT-DS-REC-TT-180697-FC | FC | 1 | TRUE | TRUE | FALSE
8482 | MRT-YT01-P3QC-130012 | 2019-05-24 | MRT-DS-REC-TT-180697-FC | FC | 1 | TRUE | TRUE | FALSE
8483 | MRT-YL00-P2LB-122075 | 2019-05-24 | MRT-DS-REC-TT-180704-FC | FC | 1 | TRUE | TRUE | FALSE
8484 | MRT-YS01-P2QU-130034 | 2019-05-24 | MRT-DS-REC-TT-180715-FC | FC | 3 | TRUE | TRUE | FALSE
8485 | MRT-YL22-P2QC-130018 | 2019-05-24 | MRT-DS-REC-TT-180753-FC | FC | 1 | TRUE | TRUE | FALSE
8486 | MRT-YL22-P3QC-130018 | 2019-05-24 | MRT-DS-REC-TT-180753-FC | FC | 1 | TRUE | TRUE | FALSE
8487 | MRT-YT01-P2QU-130031 | 2019-05-24 | MRT-DS-REC-TT-180757-FC | FC | 3 | TRUE | TRUE | FALSE
8488 | MRT-YF00-P2QU-130033 | 2019-05-24 | MRT-DS-REC-TT-180757-FC | FC | 3 | TRUE | TRUE | FALSE
8489 | MRT-YT01-P3QU-130031 | 2019-05-24 | MRT-DS-REC-TT-180757-FC | FC | 3 | TRUE | TRUE | FALSE
8490 | MRT-YF00-P3QU-130033 | 2019-05-24 | MRT-DS-REC-TT-180757-FC | FC | 2 | TRUE | TRUE | FALSE
8491 | MRT-YS01-P3QU-130034 | 2019-05-24 | MRT-DS-REC-TT-180789-FC | FC | 3 | TRUE | TRUE | FALSE
8492 | MRT-YD00-P2LB-122109 | 2019-05-24 | MRT-DS-REC-TT-180798-FC | FC | 1 | TRUE | TRUE | FALSE
8493 | MRT-YD00-P3LB-122109 | 2019-05-24 | MRT-DS-REC-TT-180798-FC | FC | 1 | TRUE | TRUE | FALSE
8494 | MRT-XN00-P2LB-122032 | 2019-05-24 | MRT-DS-REC-TT-180803-FC | FC | 3 | TRUE | TRUE | FALSE
8495 | MRT-XN00-P3LB-122032 | 2019-05-24 | MRT-DS-REC-TT-180803-FC | FC | 2 | TRUE | TRUE | FALSE
8496 | MRT-YS01-P2QC-130020 | 2019-05-24 | MRT-DS-REC-TT-180811-FC | FC | 2 | TRUE | TRUE | FALSE
8497 | MRT-YS01-P3QC-130020 | 2019-05-24 | MRT-DS-REC-TT-180811-FC | FC | 2 | TRUE | TRUE | FALSE
8498 | MRT-YK08-P2LB-122115 | 2019-05-24 | MRT-DS-REC-TT-180857-FC | FC | 0 | TRUE | TRUE | FALSE
8499 | MRT-YK08-P3LB-122115 | 2019-05-24 | MRT-DS-REC-TT-180857-FC | FC | 0 | TRUE | TRUE | FALSE
8500 | MRT-YL01-P2QC-130034 | 2019-05-24 | MRT-DS-REC-TT-180891-FC | FC | 3 | TRUE | TRUE | FALSE
8501 | MRT-YL01-P3QC-130034 | 2019-05-24 | MRT-DS-REC-TT-180891-FC | FC | 3 | TRUE | TRUE | FALSE
8502 | MRT-YT01-P2LB-122100 | 2019-05-24 | MRT-DS-REC-TT-180893-FC | FC | 1 | TRUE | TRUE | FALSE
8503 | MRT-YT01-P3LB-122100 | 2019-05-24 | MRT-DS-REC-TT-180893-FC | FC | 1 | TRUE | TRUE | FALSE
8504 | MRT-YQ03-P2LB-122086 | 2019-05-24 | MRT-DS-REC-TT-180895-FC | FC | 2 | TRUE | TRUE | FALSE
8505 | MRT-YQ03-P3LB-122086 | 2019-05-24 | MRT-DS-REC-TT-180895-FC | FC | 2 | TRUE | TRUE | FALSE
8506 | MRT-YD05-P2QC-130035 | 2019-05-24 | MRT-DS-REC-TT-180904-FC | FC | 3 | TRUE | TRUE | FALSE
8507 | MRT-YD05-P3QC-130035 | 2019-05-24 | MRT-DS-REC-TT-180904-FC | FC | 3 | TRUE | TRUE | FALSE
8508 | MRT-XH01-P2QC-130011 | 2019-05-24 | MRT-DS-REC-TT-180761-FC | FC | 2 | TRUE | TRUE | FALSE
8509 | MRT-XH01-P3QC-130011 | 2019-05-24 | MRT-DS-REC-TT-180761-FC | FC | 2 | TRUE | TRUE | FALSE
8510 | MRT-YF02-P3CJJ-240104 | 2019-05-24 | MRT-DS-REC-TT-190007-FC | FC | 0 | TRUE | TRUE | FALSE
8511 | MRT-XG02-P2LA-110006 | 2019-05-24 | MRT-DS-REC-TT-190035-FC | FC | 6 | TRUE | TRUE | FALSE
8512 | MRT-XG02-P2LC-110007 | 2019-05-24 | MRT-DS-REC-TT-190035-FC | FC | 6 | TRUE | TRUE | FALSE
8513 | MRT-XG02-P0GHC-110002 | 2019-05-24 | MRT-DS-REC-TT-190035-FC | FC | 6 | TRUE | TRUE | FALSE
8514 | MRT-XG02-P3LA-110006 | 2019-05-24 | MRT-DS-REC-TT-190035-FC | FC | 6 | TRUE | TRUE | FALSE
8515 | MRT-XG02-P3LC-110007 | 2019-05-24 | MRT-DS-REC-TT-190035-FC | FC | 6 | TRUE | TRUE | FALSE
8516 | MRT-YK00-P2LB-122076 | 2019-05-24 | MRT-DS-REC-TT-190135 | FC | 3 | TRUE | TRUE | FALSE
8517 | MRT-YK00-P3LB-122076 | 2019-05-24 | MRT-DS-REC-TT-190135 | FC | 3 | TRUE | TRUE | FALSE
8518 | MRT-DP00-P0SA-135740 | 2019-05-27 | MRT-HK-REC-TT-190614 | FA | 0 | TRUE | FALSE | FALSE
8519 | MRT-XR00-P0SA-135755 | 2019-05-27 | MRT-HK-REC-TT-190614 | FA | 0 | TRUE | FALSE | FALSE
8520 | MRT-XR00-P0SA-135759 | 2019-05-27 | MRT-HK-REC-TT-190614 | FA | 0 | TRUE | FALSE | FALSE
8521 | MRT-YE07-P3UMA-150157 | 2019-05-27 | MRT-HK-REC-TT-190615 | FA | 0 | TRUE | FALSE | FALSE
8522 | MRT-XW03-P0ABA-150324 | 2019-05-27 | MRT-HK-REC-TT-190616 | FI | 0 | TRUE | FALSE | FALSE
8523 | MRT-XA01-P0ABA-150507 | 2019-05-27 | MRT-HK-REC-TT-190617 | FA | 1 | TRUE | TRUE | FALSE
8524 | MRT-XA01-P0ABA-150567 | 2019-05-27 | MRT-HK-REC-TT-190617 | FA | 0 | TRUE | FALSE | FALSE
8525 | MRT-XJ00-P0QCH-140000 | 2019-05-28 | MRT-DS-REC-TT-190136 | FI | 0 | TRUE | FALSE | FALSE
8526 | MRT-YT01-P3GC-135188 | 2019-05-28 | MRT-HK-REC-TT-190618 | FA | 0 | TRUE | FALSE | FALSE
8527 | MRT-FF00-P0SGA-135459 | 2019-05-28 | MRT-HK-REC-TT-190618 | FA | 1 | TRUE | FALSE | FALSE
8528 | MRT-DS00-P0GN-135866 | 2019-05-28 | MRT-HK-REC-TT-190618 | FA | 0 | TRUE | FALSE | FALSE
8529 | MRT-YT01-P3GC-135156 | 2019-05-28 | MRT-HK-REC-TT-190619 | FA | 0 | TRUE | FALSE | FALSE
8530 | MRT-YU02-P0BJA-150031 | 2019-05-28 | MRT-HK-REC-TT-190620 | FA | 0 | TRUE | FALSE | FALSE
8531 | MRT-YU02-P0BJC-150032 | 2019-05-28 | MRT-HK-REC-TT-190620 | FA | 0 | TRUE | FALSE | FALSE
8532 | MRT-YE07-P3UTH-150159 | 2019-05-28 | MRT-HK-REC-TT-190620 | FA | 0 | TRUE | FALSE | FALSE
8533 | MRT-XJ00-P3LCA-147000 | 2019-05-28 | MRT-DS-REC-TT-190106-FC | FC | 0 | TRUE | TRUE | FALSE
8534 | MRT-XJ00-P2MAV-145000 | 2019-05-28 | MRT-DS-REC-TT-190106-FC | FC | 0 | TRUE | TRUE | FALSE
8535 | MRT-XJ00-P3MAV-146000 | 2019-05-28 | MRT-DS-REC-TT-190106-FC | FC | 0 | TRUE | TRUE | FALSE
8536 | MRT-XJ00-P3MAV-147000 | 2019-05-28 | MRT-DS-REC-TT-190106-FC | FC | 0 | TRUE | TRUE | FALSE
8537 | MRT-CC02-P2UMA-170207 | 2019-05-28 | MRT-DS-REC-TT-190132-FC | FC | 6 | TRUE | TRUE | FALSE
8538 | MRT-CC02-P3UMA-170208 | 2019-05-28 | MRT-DS-REC-TT-190132-FC | FC | 5 | TRUE | TRUE | FALSE
8539 | MRT-YU02-P0BJN-150713 | 2019-05-29 | MRT-HK-REC-TT-190621 | FA | 0 | TRUE | FALSE | FALSE
8540 | MRT-US02-P0BJN-150714 | 2019-05-29 | MRT-HK-REC-TT-190621 | FA | 0 | TRUE | FALSE | FALSE
8541 | MRT-HM01-P0SAC-135562 | 2019-05-29 | MRT-HK-REC-TT-190622 | FA | 1 | TRUE | TRUE | FALSE
8542 | MRT-DP00-P2LB-122123 | 2019-05-29 | MRT-DS-REC-TT-190137 | FC | 1 | TRUE | TRUE | FALSE
8543 | MRT-DP00-P3LB-122123 | 2019-05-29 | MRT-DS-REC-TT-190137 | FC | 1 | TRUE | TRUE | FALSE
8544 | MRT-QA00-P3MAA-220210 | 2019-05-29 | MRT-DS-REC-TT-190138 | FI | 0 | TRUE | FALSE | FALSE
8545 | MRT-QA00-P2MAA-220210 | 2019-05-29 | MRT-DS-REC-TT-190138 | FI | 0 | TRUE | FALSE | FALSE
8546 | MRT-DM01-P0ZEN-140002 | 2019-05-30 | MRT-DS-REC-TT-190123-FC | FC | 1 | TRUE | TRUE | FALSE
8547 | MRT-YD00-P2CJA-240057 | 2019-05-30 | MRT-DS-REC-TT-190127-FC | FC | 2 | TRUE | TRUE | FALSE
8548 | MRT-YD00-P2CJA-240058 | 2019-05-30 | MRT-DS-REC-TT-190127-FC | FC | 2 | TRUE | TRUE | FALSE
8549 | MRT-YD00-P2CJA-240059 | 2019-05-30 | MRT-DS-REC-TT-190127-FC | FC | 2 | TRUE | TRUE | FALSE
8550 | MRT-XG01-P2MAA-220045 | 2019-05-30 | MRT-DS-REC-TT-190128-FC | FC | 2 | TRUE | TRUE | FALSE
8551 | MRT-XN00-P3MAV-220039 | 2019-05-30 | MRT-DS-REC-TT-190128-FC | FC | 1 | TRUE | TRUE | FALSE
8552 | MRT-XJ00-P2MAA-142000 | 2019-05-30 | MRT-DS-REC-TT-190129-FC | FC | 0 | TRUE | TRUE | FALSE
8553 | MRT-XJ00-P3MAA-143000 | 2019-05-30 | MRT-DS-REC-TT-190129-FC | FC | 0 | TRUE | TRUE | FALSE
8554 | MRT-XJ00-P3MAA-144000 | 2019-05-30 | MRT-DS-REC-TT-190129-FC | FC | 0 | TRUE | TRUE | FALSE
8555 | MRT-CQ03-P0MKC-230012 | 2019-05-31 | MRT-DS-REC-TT-190126-FC | FC | 0 | TRUE | TRUE | FALSE
8556 | MRT-CQ03-P0MKC-230013 | 2019-05-31 | MRT-DS-REC-TT-190126-FC | FC | 0 | TRUE | TRUE | FALSE
8557 | MRT-DM02-P3MAA-220174 | 2019-05-31 | MRT-DS-REC-TT-190131-FC | FC | I | TRUE | TRUE | FALSE
8558 | MRT-DM02-P2LBS-220087 | 2019-05-31 | MRT-DS-REC-TT-190131-FC | FC | I | TRUE | TRUE | FALSE
8559 | MRT-XJ00-P0LAA-140000 | 2019-05-31 | MRT-DS-REC-TT-190133-FC | FC | 0 | TRUE | TRUE | FALSE
8560 | MRT-YF00-P3CJJ-240064 | 2019-05-31 | MRT-DS-REC-TT-190140 | FI | 0 | TRUE | FALSE | FALSE
8561 | MRT-XA00-P2MAA-220014 | 2019-05-31 | MRT-DS-REC-TT-190139 | FC | 4 | TRUE | TRUE | FALSE
8562 | MRT-XA00-P2MAA-220015 | 2019-05-31 | MRT-DS-REC-TT-190139 | FC | 4 | TRUE | TRUE | FALSE
8563 | MRT-XA00-P2MAA-220016 | 2019-05-31 | MRT-DS-REC-TT-190139 | FC | 4 | TRUE | TRUE | FALSE
8564 | MRT-XA00-P2MAA-220017 | 2019-05-31 | MRT-DS-REC-TT-190139 | FC | 4 | TRUE | TRUE | FALSE
8565 | MRT-XA00-P2MAA-220018 | 2019-05-31 | MRT-DS-REC-TT-190139 | FC | 4 | TRUE | TRUE | FALSE
8566 | MRT-XA00-P2MAA-220020 | 2019-05-31 | MRT-DS-REC-TT-190139 | FC | 4 | TRUE | TRUE | FALSE
8567 | MRT-XA00-P2MAA-220021 | 2019-05-31 | MRT-DS-REC-TT-190139 | FC | 4 | TRUE | TRUE | FALSE
8568 | MRT-XA00-P2MAA-220022 | 2019-05-31 | MRT-DS-REC-TT-190139 | FC | 4 | TRUE | TRUE | FALSE
8569 | MRT-DN05-P2MAA-220205 | 2019-05-31 | MRT-DS-REC-TT-190139 | FC | 1 | TRUE | TRUE | FALSE
8570 | MRT-YV02-P2CJJ-240121 | 2019-05-31 | MRT-DS-REC-TT-190139 | FC | 1 | TRUE | TRUE | FALSE
8673 | MRT-DN02-P2MAV-830017 | 2019-06-04 | MRT-DS-REC-TT-190141 | FA | 0 | TRUE | FALSE | FALSE
8674 | MRT-CC02-P2UHA-170104 | 2019-06-11 | MRT-DS-REC-TT-190142 | FC | 7 | TRUE | TRUE | FALSE
8675 | MRT-CC02-P3UHA-170104 | 2019-06-11 | MRT-DS-REC-TT-190142 | FC | 7 | TRUE | TRUE | FALSE
8676 | MRT-DN02-P2ZEN-830025 | 2019-06-12 | MRT-DS-REC-TT-190143 | FA | 0 | TRUE | FALSE | FALSE
8677 | MRT-YL16-P2BFA-150063 | 2019-06-14 | MRT-HK-REC-TT-190629 | FI | 0 | TRUE | FALSE | FALSE
8678 | MRT-YL16-P3BFC-150064 | 2019-06-14 | MRT-HK-REC-TT-190629 | FI | 0 | TRUE | FALSE | FALSE
8679 | MRT-YL16-P3BFE-150065 | 2019-06-14 | MRT-HK-REC-TT-190629 | FI | 0 | TRUE | FALSE | FALSE
8680 | MRT-YL16-P0BMA-150067 | 2019-06-14 | MRT-HK-REC-TT-190629 | FI | 0 | TRUE | FALSE | FALSE
8681 | MRT-YL16-P0BMC-150068 | 2019-06-14 | MRT-HK-REC-TT-190629 | FI | 0 | TRUE | FALSE | FALSE
8682 | MRT-YL16-P2BJA-150069 | 2019-06-14 | MRT-HK-REC-TT-190629 | FI | 0 | TRUE | FALSE | FALSE
8683 | MRT-YL16-P3BJA-150070 | 2019-06-14 | MRT-HK-REC-TT-190629 | FI | 0 | TRUE | FALSE | FALSE
8684 | MRT-YL16-P3BJC-150071 | 2019-06-14 | MRT-HK-REC-TT-190629 | FI | 0 | TRUE | FALSE | FALSE
8685 | MRT-YL16-P0BJJ-150098 | 2019-06-14 | MRT-HK-REC-TT-190630 | FI | 0 | TRUE | FALSE | FALSE
8686 | MRT-YL16-P3BJL-150099 | 2019-06-14 | MRT-HK-REC-TT-190630 | FI | 0 | TRUE | FALSE | FALSE
8687 | MRT-YL16-P0BJL-150101 | 2019-06-14 | MRT-HK-REC-TT-190630 | FI | 0 | TRUE | FALSE | FALSE
8688 | MRT-YL16-P0BJN-150102 | 2019-06-14 | MRT-HK-REC-TT-190630 | FI | 0 | TRUE | FALSE | FALSE
8689 | MRT-HM01-P0SAL-135540 | 2019-06-14 | MRT-HK-REC-TT-190625 | FA | 0 | TRUE | FALSE | FALSE
8690 | MRT-HM01-P0SAK-135537 | 2019-06-14 | MRT-HK-REC-TT-190625 | FA | 0 | TRUE | FALSE | FALSE
8691 | MRT-HM01-P0SAG-135535 | 2019-06-14 | MRT-HK-REC-TT-190625 | FA | 0 | TRUE | FALSE | FALSE
8692 | MRT-HM01-P0SAF-135538 | 2019-06-14 | MRT-HK-REC-TT-190625 | FA | 0 | TRUE | FALSE | FALSE
8693 | MRT-HM01-P0SA-135545 | 2019-06-14 | MRT-HK-REC-TT-190625 | FA | 0 | TRUE | FALSE | FALSE
8694 | MRT-HM01-P0SA-135543 | 2019-06-14 | MRT-HK-REC-TT-190625 | FA | 0 | TRUE | FALSE | FALSE
8695 | MRT-HM01-P0SA-135542 | 2019-06-14 | MRT-HK-REC-TT-190625 | FA | 0 | TRUE | FALSE | FALSE
8696 | MRT-XG02-P3SGE-135406 | 2019-06-14 | MRT-HK-REC-TT-190627 | FA | 0 | TRUE | FALSE | FALSE
8697 | MRT-YK00-P2LB-122076 | 2019-06-17 | MRT-DS-REC-TT-190135-FC | FC | 3 | TRUE | TRUE | FALSE
8698 | MRT-YK00-P3LB-122076 | 2019-06-17 | MRT-DS-REC-TT-190135-FC | FC | 3 | TRUE | TRUE | FALSE
8699 | MRT-CC02-P2UHA-170104 | 2019-06-17 | MRT-DS-REC-TT-190142-FC | FC | 7 | TRUE | TRUE | FALSE
8700 | MRT-CC02-P3UHA-170104 | 2019-06-17 | MRT-DS-REC-TT-190142-FC | FC | 7 | TRUE | TRUE | FALSE
8701 | MRT-XA00-P0GAA-135004 | 2019-06-17 | MRT-HK-REC-TT-190626 | FA | 4 | TRUE | TRUE | FALSE
8702 | MRT-YE16-P2UMA-150329 | 2019-06-17 | MRT-HK-REC-TT-190631 | FA | 0 | TRUE | FALSE | FALSE
8703 | MRT-DS00-P3GC-135843 | 2019-06-17 | MRT-HK-REC-TT-190632 | FA | 1 | TRUE | TRUE | FALSE
8704 | MRT-QM03-P0GHE-145071 | 2019-06-17 | MRT-HK-REC-TT-190623 | FA | 0 | TRUE | FALSE | FALSE
8705 | MRT-QM03-P0GHE-145062 | 2019-06-17 | MRT-HK-REC-TT-190623 | FA | 0 | TRUE | FALSE | FALSE
8706 | MRT-QM03-P0GHE-145072 | 2019-06-17 | MRT-HK-REC-TT-190623 | FA | 0 | TRUE | FALSE | FALSE
8707 | MRT-QM01-P0GHE-145069 | 2019-06-17 | MRT-HK-REC-TT-190624 | FA | 0 | TRUE | FALSE | FALSE
8708 | MRT-QM01-P0GHE-145070 | 2019-06-17 | MRT-HK-REC-TT-190624 | FA | 0 | TRUE | FALSE | FALSE
8709 | MRT-QM03-P0GHE-145063 | 2019-06-17 | MRT-HK-REC-TT-190624 | FA | 0 | TRUE | FALSE | FALSE
8710 | MRT-QM03-P0GHE-145064 | 2019-06-17 | MRT-HK-REC-TT-190624 | FA | 0 | TRUE | FALSE | FALSE
8711 | MRT-QM03-P0GHE-145065 | 2019-06-17 | MRT-HK-REC-TT-190624 | FA | 0 | TRUE | FALSE | FALSE
8712 | MRT-QM03-P0GHE-145066 | 2019-06-17 | MRT-HK-REC-TT-190624 | FA | 0 | TRUE | FALSE | FALSE
8713 | MRT-QM03-P0GHE-145067 | 2019-06-17 | MRT-HK-REC-TT-190624 | FA | 0 | TRUE | FALSE | FALSE
8714 | MRT-QM03-P0GHE-145068 | 2019-06-17 | MRT-HK-REC-TT-190624 | FA | 0 | TRUE | FALSE | FALSE
8715 | MRT-QM03-P0GHE-145073 | 2019-06-17 | MRT-HK-REC-TT-190624 | FA | 0 | TRUE | FALSE | FALSE
8716 | MRT-QM03-P0GHE-145074 | 2019-06-17 | MRT-HK-REC-TT-190624 | FA | 0 | TRUE | FALSE | FALSE
8717 | MRT-DN03-P0GN-135290 | 2019-06-17 | MRT-HK-REC-TT-190628 | FA | 1 | TRUE | TRUE | FALSE
8718 | MRT-DS00-P0GN-135277 | 2019-06-17 | MRT-HK-REC-TT-190628 | FA | 1 | TRUE | TRUE | FALSE
8719 | MRT-DN03-P3GC-135192 | 2019-06-17 | MRT-HK-REC-TT-190628 | FA | 1 | TRUE | TRUE | FALSE
8720 | MRT-DS00-P0GN-135868 | 2019-06-17 | MRT-HK-REC-TT-190628 | FI | 1 | TRUE | TRUE | FALSE
8721 | MRT-DS00-P3GC-135848 | 2019-06-17 | MRT-HK-REC-TT-190628 | FI | 1 | TRUE | TRUE | FALSE
8722 | MRT-DD03-P0GEN-135385 | 2019-06-17 | MRT-HK-REC-TT-190628 | FA | 0 | TRUE | FALSE | FALSE
8723 | MRT-XG02-P0GEN-135302 | 2019-06-18 | MRT-HK-REC-TT-190635 | FA | 4 | TRUE | TRUE | FALSE
8724 | MRT-XG02-P0SGE-135410 | 2019-06-18 | MRT-HK-REC-TT-190634 | FA | 0 | TRUE | FALSE | FALSE
8725 | MRT-XJ00-P2LB-122027 | 2019-06-19 | MRT-DS-REC-TT-190144 | FC | 3 | TRUE | TRUE | FALSE
8726 | MRT-XJ00-P3LB-122027 | 2019-06-19 | MRT-DS-REC-TT-190144 | FC | 3 | TRUE | TRUE | FALSE
8727 | MRT-XJ00-P2LB-122028 | 2019-06-19 | MRT-DS-REC-TT-190145 | FC | 5 | TRUE | TRUE | FALSE
8728 | MRT-XJ00-P3LB-122028 | 2019-06-19 | MRT-DS-REC-TT-190145 | FC | 5 | TRUE | TRUE | FALSE
8729 | MRT-YL16-P3BJN-150100 | 2019-06-19 | MRT-HK-REC-TT-190636 | FA | 0 | TRUE | FALSE | FALSE
8730 | MRT-YL16-P0SRA-150103 | 2019-06-19 | MRT-HK-REC-TT-190636 | FA | 0 | TRUE | FALSE | FALSE
8731 | MRT-XH01-P2LB-122112 | 2019-06-19 | MRT-DS-REC-TT-190146 | FC | 3 | TRUE | TRUE | FALSE
8732 | MRT-XH01-P3LB-122112 | 2019-06-19 | MRT-DS-REC-TT-190146 | FC | 3 | TRUE | TRUE | FALSE
8733 | MRT-XK00-P2PGB-142000 | 2019-06-19 | MRT-DS-REC-TT-190147 | FI | 0 | TRUE | FALSE | FALSE
8734 | MRT-XK00-P3PGB-143000 | 2019-06-19 | MRT-DS-REC-TT-190147 | FI | 0 | TRUE | FALSE | FALSE
8735 | MRT-XK00-P4PGB-144000 | 2019-06-19 | MRT-DS-REC-TT-190147 | FI | 0 | TRUE | FALSE | FALSE
8736 | MRT-YU01-P0ABA-150024 | 2019-06-19 | MRT-HK-REC-TT-190637 | FA | 3 | TRUE | TRUE | FALSE
8737 | MRT-XA01-P0ABA-150515 | 2019-06-20 | MRT-HK-REC-TT-190639 | FA | 1 | TRUE | TRUE | FALSE
8738 | MRT-XB02-P2LB-122018 | 2019-06-20 | MRT-DS-REC-TT-190148 | FC | 7 | TRUE | TRUE | FALSE
8739 | MRT-XB02-P3LB-122018 | 2019-06-20 | MRT-DS-REC-TT-190148 | FC | 6 | TRUE | TRUE | FALSE
8740 | MRT-YT01-P2LB-122096 | 2019-06-20 | MRT-DS-REC-TT-190149 | FC | 3 | TRUE | TRUE | FALSE
8741 | MRT-YT01-P3LB-122096 | 2019-06-20 | MRT-DS-REC-TT-190149 | FC | 3 | TRUE | TRUE | FALSE
8748 | MRT-YU02-P0BJM-150711 | 2019-06-20 | MRT-HK-REC-TT-190640 | FA | 1 | TRUE | TRUE | FALSE
8749 | MRT-US02-P0BJM-150712 | 2019-06-20 | MRT-HK-REC-TT-190640 | FA | 1 | TRUE | TRUE | FALSE
8750 | MRT-US02-P0BJJ-150702 | 2019-06-20 | MRT-HK-REC-TT-190640 | FA | 1 | TRUE | TRUE | FALSE
8751 | MRT-YU02-P0BJJ-150701 | 2019-06-20 | MRT-HK-REC-TT-190640 | FA | 1 | TRUE | TRUE | FALSE
8752 | MRT-YU02-P0BMA-150715 | 2019-06-20 | MRT-HK-REC-TT-190638 | FA | 0 | TRUE | FALSE | FALSE
8753 | MRT-US02-P0BMA-150716 | 2019-06-20 | MRT-HK-REC-TT-190638 | FA | 0 | TRUE | FALSE | FALSE
8754 | MRT-XJ00-P0QCH-140000 | 2019-06-21 | MRT-DS-REC-TT-190136-FC | FC | 0 | TRUE | TRUE | FALSE
8755 | MRT-YU02-P0SRA-150057 | 2019-06-21 | MRT-HK-REC-TT-190641 | FA | 0 | TRUE | FALSE | FALSE
8756 | MRT-YL16-P0BCA-150060 | 2019-06-21 | MRT-HK-REC-TT-190641 | FI | 0 | TRUE | FALSE | FALSE
8757 | MRT-YL16-P2BBA-150061 | 2019-06-21 | MRT-HK-REC-TT-190641 | FI | 0 | TRUE | FALSE | FALSE
8758 | MRT-YL16-P3BBC-150062 | 2019-06-21 | MRT-HK-REC-TT-190641 | FI | 0 | TRUE | FALSE | FALSE
8759 | MRT-US02-P0BLL-150788 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8760 | MRT-YU02-P0BLL-150787 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8761 | MRT-US02-P0BLL-150786 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8762 | MRT-YU02-P0BLL-150785 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8763 | MRT-US02-P0BLK-150326 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8764 | MRT-YU02-P0BLK-150325 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8765 | MRT-US02-P0BLK-150778 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8766 | MRT-YU02-P0BLK-150777 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8767 | MRT-US02-P0BLK-150776 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8768 | MRT-YU02-P0BLK-150775 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8769 | MRT-US02-P0BLK-150323 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8770 | MRT-YU02-P0BLK-150322 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8771 | MRT-YD00-P0ANA-150651 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8772 | MRT-YD00-P0ANA-150652 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8773 | MRT-YD00-P0ANA-150653 | 2019-06-21 | MRT-HK-REC-TT-190642 | FA | 0 | TRUE | FALSE | FALSE
8774 | MRT-CC02-P0UYX-175337 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 0 | TRUE | TRUE | FALSE
8775 | MRT-CC02-P0UYX-175161 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8776 | MRT-CC02-P0UYX-175211 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8777 | MRT-CC02-P0UYX-175231 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8778 | MRT-CC02-P0UYX-175331 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8779 | MRT-CC02-P0UZT-175920 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8780 | MRT-CC02-P0UZT-175925 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8781 | MRT-CC02-P0UZT-175930 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8782 | MRT-CC02-P0ULX-176217 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 2 | TRUE | TRUE | FALSE
8783 | MRT-CC02-P0UYX-175332 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8784 | MRT-CC02-P0UYX-175333 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8785 | MRT-CC02-P0UYX-175334 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8786 | MRT-CC02-P0UYX-175335 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8787 | MRT-CC02-P0UYX-175336 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8788 | MRT-CC02-P0UYX-175172 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8789 | MRT-CC02-P0UYX-175173 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8790 | MRT-CC02-P0UYX-175180 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8791 | MRT-CC02-P0UZT-175924 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8792 | MRT-CC02-P0UZT-175923 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8793 | MRT-CC02-P0UZT-175922 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8794 | MRT-CC02-P0UZT-175921 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8795 | MRT-CC02-P0ULX-176227 | 2019-06-21 | MRT-HK-REC-TT-190643 | FA | 1 | TRUE | TRUE | FALSE
8796 | MRT-FF00-P0SGA-135460 | 2019-06-24 | MRT-HK-REC-TT-190644 | FA | 2 | TRUE | TRUE | FALSE
8797 | MRT-QM03-P0GHE-145061 | 2019-06-24 | MRT-HK-REC-TT-190645 | FA | 0 | TRUE | FALSE | FALSE
8798 | MRT-DP00-P2LB-122106 | 2019-06-25 | MRT-DS-REC-TT-190151 | FC | 5 | TRUE | TRUE | FALSE
8799 | MRT-DP00-P3LB-122106 | 2019-06-25 | MRT-DS-REC-TT-190151 | FC | 5 | TRUE | TRUE | FALSE
8800 | MRT-CC02-P2UMA-170609 | 2019-06-25 | MRT-DS-REC-TT-190150 | FC | 5 | TRUE | TRUE | FALSE
8801 | MRT-XK00-P2MAA-220207 | 2019-06-26 | MRT-DS-REC-TT-190117-FC | FC | 0 | TRUE | TRUE | FALSE
8802 | MRT-DM02-P3MAA-220175 | 2019-06-26 | MRT-DS-REC-TT-190130-FC | FC | 0 | TRUE | TRUE | FALSE
8803 | MRT-QA00-P2MAA-220210 | 2019-06-26 | MRT-DS-REC-TT-190138-FC | FC | 0 | TRUE | TRUE | FALSE
8804 | MRT-QA00-P3MAA-220210 | 2019-06-26 | MRT-DS-REC-TT-190138-FC | FC | 0 | TRUE | TRUE | FALSE
8805 | MRT-FF03-P0SGF-135423 | 2019-06-26 | MRT-HK-REC-TT-190646 | FA | 0 | TRUE | FALSE | FALSE
8806 | MRT-YT01-P0BFB-150660 | 2019-06-26 | MRT-HK-REC-TT-190647 | FA | 0 | TRUE | FALSE | FALSE
8807 | MRT-DP00-P0EZN-070587 | 2019-06-26 | MRT-HK-REC-TT-190647 | FA | 0 | TRUE | FALSE | FALSE
8808 | MRT-CH04-P3BBT-150525 | 2019-06-26 | MRT-HK-REC-TT-190647 | FA | 0 | TRUE | FALSE | FALSE
8809 | MRT-CV05-P0BFT-150583 | 2019-06-26 | MRT-HK-REC-TT-190647 | FA | 0 | TRUE | FALSE | FALSE
8810 | MRT-YT01-P0BRU-150974 | 2019-06-26 | MRT-HK-REC-TT-190648 | FA | 0 | TRUE | FALSE | FALSE
8811 | MRT-CA03-P2UMA-185201 | 2019-06-26 | MRT-HK-REC-TT-190649 | FI | 0 | TRUE | FALSE | FALSE
8812 | MRT-XB02-P2LB-122018 | 2019-06-27 | MRT-DS-REC-TT-190148-FC | FC | 7 | TRUE | TRUE | FALSE
8813 | MRT-XB02-P3LB-122018 | 2019-06-27 | MRT-DS-REC-TT-190148-FC | FC | 6 | TRUE | TRUE | FALSE
8814 | MRT-US02-P0BHA-150690 | 2019-06-27 | MRT-HK-REC-TT-190650 | FA | 0 | TRUE | FALSE | FALSE
8815 | MRT-YU02-P0BHA-150689 | 2019-06-27 | MRT-HK-REC-TT-190650 | FA | 0 | TRUE | FALSE | FALSE
8816 | MRT-CH04-P0BFT-150585 | 2019-06-27 | MRT-HK-REC-TT-190650 | FA | 0 | TRUE | FALSE | FALSE
8817 | MRT-CC02-P0UGA-176250 | 2019-06-27 | MRT-HK-REC-TT-190651 | FA | 2 | TRUE | TRUE | FALSE
8818 | MRT-CC02-P0UGA-176255 | 2019-06-27 | MRT-HK-REC-TT-190651 | FA | 1 | TRUE | TRUE | FALSE
8819 | MRT-CC02-P0UGA-176290 | 2019-06-27 | MRT-HK-REC-TT-190651 | FA | 2 | TRUE | TRUE | FALSE
8820 | MRT-CC02-P0UGA-176295 | 2019-06-27 | MRT-HK-REC-TT-190651 | FA | 1 | TRUE | TRUE | FALSE
8821 | MRT-CV03-P2ZEN-165103 | 2019-06-28 | MRT-DS-REC-TT-190152 | FC | 3 | TRUE | TRUE | FALSE
8822 | MRT-CV03-P3ZEN-165103 | 2019-06-28 | MRT-DS-REC-TT-190152 | FC | 3 | TRUE | TRUE | FALSE
8823 | MRT-XK00-P0LBG-141000 | 2019-07-01 | MRT-DS-REC-TT-190154 | FI | 0 | TRUE | FALSE | FALSE
8824 | MRT-XK00-P0GMA-140001 | 2019-07-01 | MRT-DS-REC-TT-190154 | FI | 0 | TRUE | FALSE | FALSE
8825 | MRT-XK00-P0GHD-140001 | 2019-07-01 | MRT-DS-REC-TT-190154 | FI | 0 | TRUE | FALSE | FALSE
8826 | MRT-XK00-P0GHC-140001 | 2019-07-01 | MRT-DS-REC-TT-190154 | FI | 0 | TRUE | FALSE | FALSE
8827 | MRT-XH01-P2LB-122025 | 2019-07-01 | MRT-DS-REC-TT-190155 | FC | 2 | TRUE | TRUE | FALSE
8828 | MRT-XH01-P3LB-122025 | 2019-07-01 | MRT-DS-REC-TT-190155 | FC | 2 | TRUE | TRUE | FALSE
8829 | MRT-YL16-P2BRB-150078 | 2019-07-01 | MRT-HK-REC-TT-190652 | FI | 0 | TRUE | FALSE | FALSE
8830 | MRT-YE16-P0UST-150142 | 2019-07-01 | MRT-HK-REC-TT-190652 | FA | 0 | TRUE | FALSE | FALSE
8831 | MRT-XJ00-P2LBA-142000 | 2019-07-01 | MRT-DS-REC-TT-190153 | FC | 2 | TRUE | TRUE | FALSE
8832 | MRT-XJ00-P2LBG-142000 | 2019-07-01 | MRT-DS-REC-TT-190153 | FC | 2 | TRUE | TRUE | FALSE
8833 | MRT-XJ00-P2LAB-142000 | 2019-07-01 | MRT-DS-REC-TT-190153 | FC | 2 | TRUE | TRUE | FALSE
8834 | MRT-XJ00-P2LCA-142000 | 2019-07-01 | MRT-DS-REC-TT-190153 | FC | 2 | TRUE | TRUE | FALSE
8835 | MRT-XJ00-P2LCM-142000 | 2019-07-01 | MRT-DS-REC-TT-190153 | FC | 2 | TRUE | TRUE | FALSE
8836 | MRT-US02-P0BJN-150710 | 2019-07-02 | MRT-HK-REC-TT-190653 | FA | 1 | TRUE | TRUE | FALSE
8837 | MRT-YU02-P0BJN-150709 | 2019-07-02 | MRT-HK-REC-TT-190653 | FA | 1 | TRUE | TRUE | FALSE
8838 | MRT-XA01-P0ABA-150514 | 2019-07-02 | MRT-HK-REC-TT-190654 | FA | 1 | TRUE | TRUE | FALSE
8839 | MRT-XG02-P2SGK-135427 | 2019-07-02 | MRT-HK-REC-TT-190655 | FA | 0 | TRUE | FALSE | FALSE
8840 | MRT-FF03-P0SGE-135410 | 2019-07-02 | MRT-HK-REC-TT-190655 | FA | 0 | TRUE | FALSE | FALSE
8841 | MRT-FF01-P0SGA-135432 | 2019-07-02 | MRT-HK-REC-TT-190656 | FA | 0 | TRUE | FALSE | FALSE
8842 | MRT-YR01-P2ZEN-110103 | 2019-07-02 | MRT-DS-REC-TT-190156 | FC | 1 | TRUE | TRUE | FALSE
8843 | MRT-YR01-P3ZEN-110103 | 2019-07-02 | MRT-DS-REC-TT-190156 | FC | 1 | TRUE | TRUE | FALSE
8844 | MRT-YD00-P0UST-150130 | 2019-07-04 | MRT-HK-REC-TT-190657 | FA | 0 | TRUE | FALSE | FALSE
8845 | MRT-DD00-P0BAT-155133 | 2019-07-05 | MRT-HK-REC-TT-190658 | FI | 0 | TRUE | FALSE | FALSE
8846 | MRT-DD00-P0ABA-155132 | 2019-07-05 | MRT-HK-REC-TT-190658 | FI | 0 | TRUE | FALSE | FALSE
8847 | MRT-DD00-P0ABA-155131 | 2019-07-05 | MRT-HK-REC-TT-190658 | FI | 0 | TRUE | FALSE | FALSE
8848 | MRT-DD00-P0ABA-155130 | 2019-07-05 | MRT-HK-REC-TT-190658 | FI | 0 | TRUE | FALSE | FALSE
8849 | MRT-YU02-P0BMA-150729 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8850 | MRT-YU02-P0BMC-150717 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8851 | MRT-US02-P0BMC-150718 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8852 | MRT-YU02-P0BMA-150725 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8853 | MRT-US02-P0BMA-150726 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8854 | MRT-YU02-P0BMA-150727 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8855 | MRT-US02-P0BMA-150730 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8856 | MRT-YU02-P0BMA-150731 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8857 | MRT-US02-P0BMA-150732 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8858 | MRT-YU02-P0BMA-150733 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8859 | MRT-US02-P0BMA-150734 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8860 | MRT-YU02-P0BMA-150735 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8861 | MRT-US02-P0BMA-150728 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8862 | MRT-US02-P0BMA-150736 | 2019-07-08 | MRT-HK-REC-TT-190659 | FA | 0 | TRUE | FALSE | FALSE
8863 | MRT-YF01-P0BFB-150236 | 2019-07-08 | MRT-HK-REC-TT-190660 | FA | 0 | TRUE | FALSE | FALSE
8864 | MRT-HM01-P00SA-135563 | 2019-07-08 | MRT-HK-REC-TT-190661 | FA | 1 | TRUE | TRUE | FALSE
8865 | MRT-HM01-P00SA-135566 | 2019-07-08 | MRT-HK-REC-TT-190661 | FA | 1 | TRUE | TRUE | FALSE
8866 | MRT-HM01-P00SA-135568 | 2019-07-08 | MRT-HK-REC-TT-190661 | FA | 1 | TRUE | TRUE | FALSE
8867 | MRT-HM01-P00SA-135571 | 2019-07-08 | MRT-HK-REC-TT-190661 | FA | 1 | TRUE | TRUE | FALSE
8868 | MRT-HM01-P0SAK-135565 | 2019-07-08 | MRT-HK-REC-TT-190661 | FA | 1 | TRUE | TRUE | FALSE
8869 | MRT-FF03-P2SGE-135406 | 2019-07-08 | MRT-HK-REC-TT-1906662 | FA | 0 | TRUE | FALSE | FALSE
8870 | MRT-FF03-P2SGC-135418 | 2019-07-08 | MRT-HK-REC-TT-1906662 | FA | 0 | TRUE | FALSE | FALSE
8871 | MRT-DD00-P0BAT-155141 | 2019-07-09 | MRT-HK-REC-TT-190664 | FI | 0 | TRUE | FALSE | FALSE
8872 | MRT-DD00-P0BAT-155140 | 2019-07-09 | MRT-HK-REC-TT-190664 | FI | 0 | TRUE | FALSE | FALSE
8873 | MRT-DD00-P0BAT-155139 | 2019-07-09 | MRT-HK-REC-TT-190664 | FI | 0 | TRUE | FALSE | FALSE
8874 | MRT-DD00-P0BAT-155138 | 2019-07-09 | MRT-HK-REC-TT-190664 | FI | 0 | TRUE | FALSE | FALSE
8875 | MRT-DD00-P0BAT-155137 | 2019-07-09 | MRT-HK-REC-TT-190664 | FI | 0 | TRUE | FALSE | FALSE
8876 | MRT-DD00-P0BAT-155136 | 2019-07-09 | MRT-HK-REC-TT-190664 | FI | 0 | TRUE | FALSE | FALSE
8877 | MRT-DD00-P0BAT-155135 | 2019-07-09 | MRT-HK-REC-TT-190664 | FI | 0 | TRUE | FALSE | FALSE
8878 | MRT-DD00-P0BAT-155134 | 2019-07-09 | MRT-HK-REC-TT-190664 | FI | 0 | TRUE | FALSE | FALSE
8879 | MRT-XA00-P2MAA-220014 | 2019-07-09 | MRT-DS-REC-TT-190139-FC | FC | 4 | TRUE | TRUE | FALSE
8880 | MRT-XA00-P2MAA-220015 | 2019-07-09 | MRT-DS-REC-TT-190139-FC | FC | 4 | TRUE | TRUE | FALSE
8881 | MRT-XA00-P2MAA-220016 | 2019-07-09 | MRT-DS-REC-TT-190139-FC | FC | 4 | TRUE | TRUE | FALSE
8882 | MRT-XA00-P2MAA-220017 | 2019-07-09 | MRT-DS-REC-TT-190139-FC | FC | 4 | TRUE | TRUE | FALSE
8883 | MRT-XA00-P2MAA-220018 | 2019-07-09 | MRT-DS-REC-TT-190139-FC | FC | 4 | TRUE | TRUE | FALSE
8884 | MRT-XA00-P2MAA-220020 | 2019-07-09 | MRT-DS-REC-TT-190139-FC | FC | 4 | TRUE | TRUE | FALSE
8885 | MRT-XA00-P2MAA-220021 | 2019-07-09 | MRT-DS-REC-TT-190139-FC | FC | 4 | TRUE | TRUE | FALSE
8886 | MRT-XA00-P2MAA-220022 | 2019-07-09 | MRT-DS-REC-TT-190139-FC | FC | 4 | TRUE | TRUE | FALSE
8887 | MRT-DN05-P2MAA-220205 | 2019-07-09 | MRT-DS-REC-TT-190139-FC | FC | 1 | TRUE | TRUE | FALSE
8888 | MRT-YV02-P2CJJ-240121 | 2019-07-09 | MRT-DS-REC-TT-190139-FC | FC | 1 | TRUE | TRUE | FALSE
8889 | MRT-QM03-P0ZEN-155033 | 2019-07-10 | MRT-HK-REC-TT-190665 | FI | 0 | TRUE | FALSE | FALSE
8890 | MRT-YL08-P3GC-135174 | 2019-07-10 | MRT-HK-REC-TT-190666 | FI | 0 | TRUE | FALSE | FALSE
8891 | MRT-YD08-P3GC-135177 | 2019-07-10 | MRT-HK-REC-TT-190666 | FI | 0 | TRUE | FALSE | FALSE
8892 | MRT-YT01-P0GN-135254 | 2019-07-10 | MRT-HK-REC-TT-190666 | FI | 0 | TRUE | FALSE | FALSE
8893 | MRT-YL08-P0GN-135270 | 2019-07-10 | MRT-HK-REC-TT-190666 | FI | 0 | TRUE | FALSE | FALSE
8894 | MRT-FF03-P3SGK-135426 | 2019-07-10 | MRT-HK-REC-TT-190667 | FA | 0 | TRUE | FALSE | FALSE
8895 | MRT-XG02-P0SGF-135423 | 2019-07-10 | MRT-HK-REC-TT-190667 | FA | 0 | TRUE | FALSE | FALSE
8896 | MRT-XG02-P0SGA-135413 | 2019-07-10 | MRT-HK-REC-TT-190667 | FA | 1 | TRUE | TRUE | FALSE
8897 | MRT-QA00-P0GDG-135077 | 2019-07-11 | MRT-HK-REC-TT-190668 | FA | 1 | TRUE | TRUE | FALSE
8898 | MRT-QA00-P0GDG-135078 | 2019-07-11 | MRT-HK-REC-TT-190669 | FA | 1 | TRUE | TRUE | FALSE
8899 | MRT-QM03-P0ZEN-135007 | 2019-07-11 | MRT-HK-REC-TT-190670 | FA | 1 | TRUE | TRUE | FALSE
8900 | MRT-QM01-P0ZEN-135006 | 2019-07-11 | MRT-HK-REC-TT-190671 | FA | 1 | TRUE | TRUE | FALSE
8901 | MRT-DN03-P0GN-135289 | 2019-07-11 | MRT-HK-REC-TT-190672 | FA | 1 | TRUE | TRUE | FALSE
8902 | MRT-DN03-P3GC-135191 | 2019-07-11 | MRT-HK-REC-TT-190672 | FA | 1 | TRUE | TRUE | FALSE
8903 | MRT-XJ00-P0GHD-140001 | 2019-07-11 | MRT-DS-REC-TT-190158 | FC | 1 | TRUE | TRUE | FALSE
8904 | MRT-XJ00-P0GKB-140001 | 2019-07-11 | MRT-DS-REC-TT-190158 | FC | 1 | TRUE | TRUE | FALSE
8905 | MRT-XJ00-P0GMA-140001 | 2019-07-11 | MRT-DS-REC-TT-190158 | FC | 1 | TRUE | TRUE | FALSE
8906 | MRT-CQ02-P2MAA-220202 | 2019-07-11 | MRT-DS-REC-TT-190157 | FI | 0 | TRUE | FALSE | FALSE
8907 | MRT-CQ02-P3MAA-220201 | 2019-07-11 | MRT-DS-REC-TT-190157 | FI | 0 | TRUE | FALSE | FALSE
8908 | MRT-DN05-P3MAA-220205 | 2019-07-11 | MRT-DS-REC-TT-190157 | FA | 0 | TRUE | FALSE | FALSE
8911 | MRT-DD08-P0ZEN-085001 | 2019-07-11 | MRT-HK-REC-TT-190673 | FA | 0 | TRUE | FALSE | FALSE
8912 | MRT-DS00-P0ZEN-150275 | 2019-07-11 | MRT-HK-REC-TT-190674 | FA | 0 | TRUE | FALSE | FALSE
8913 | MRT-CZ00-P0PUR-150998 | 2019-07-11 | MRT-HK-REC-TT-190674 | FI | 0 | TRUE | FALSE | FALSE
8914 | MRT-YD08-P0GN-135273 | 2019-07-11 | MRT-HK-REC-TT-190675 | FI | 0 | TRUE | FALSE | FALSE
8915 | MRT-CC07-P0GN-135246 | 2019-07-11 | MRT-HK-REC-TT-190676 | FA | 0 | TRUE | FALSE | FALSE
8916 | MRT-CC07-P3GC-135144 | 2019-07-11 | MRT-HK-REC-TT-190676 | FA | 0 | TRUE | FALSE | FALSE
8917 | MRT-US02-P0BJL-150708 | 2019-07-11 | MRT-HK-REC-TT-190677 | FA | 0 | TRUE | FALSE | FALSE
8918 | MRT-YU02-P0BJL-150707 | 2019-07-11 | MRT-HK-REC-TT-190677 | FA | 0 | TRUE | FALSE | FALSE
8919 | MRT-US02-P0BFB-150706 | 2019-07-11 | MRT-HK-REC-TT-190678 | FA | 0 | TRUE | FALSE | FALSE
8920 | MRT-YU02-P0BFB-150705 | 2019-07-11 | MRT-HK-REC-TT-190678 | FA | 0 | TRUE | FALSE | FALSE
8909 | MRT-CC02-P2UHA-170103 | 2019-07-15 | MRT-DS-REC-TT-190159 | FC | 11 | TRUE | TRUE | FALSE
8910 | MRT-CC02-P3UHA-170103 | 2019-07-15 | MRT-DS-REC-TT-190159 | FC | 11 | TRUE | TRUE | FALSE
8921 | MRT-YL00-P3GC-135171 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 0 | TRUE | FALSE | FALSE
8922 | MRT-YT01-P3GC-135199 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 0 | TRUE | FALSE | FALSE
8923 | MRT-YT01-P3GC-135159 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 0 | TRUE | FALSE | FALSE
8924 | MRT-YT01-P3GC-135161 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 0 | TRUE | FALSE | FALSE
8925 | MRT-VL00-P3GC-135176 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 0 | TRUE | FALSE | FALSE
8926 | MRT-YF00-P3GC-135169 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 0 | TRUE | FALSE | FALSE
8927 | MRT-YL00-P0GN-135267 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 0 | TRUE | FALSE | FALSE
8928 | MRT-YT01-P0GN-135297 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 0 | TRUE | FALSE | FALSE
8929 | MRT-YT01-P0GN-135260 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 0 | TRUE | FALSE | FALSE
8930 | MRT-YT01-P0GN-135262 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 0 | TRUE | FALSE | FALSE
8931 | MRT-YT01-P3GC-135155 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 1 | TRUE | TRUE | FALSE
8932 | MRT-YT01-P3GC-135162 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 1 | TRUE | TRUE | FALSE
8933 | MRT-YT01-P3GC-135157 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 1 | TRUE | TRUE | FALSE
8934 | MRT-YT01-P3GC-135164 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 0 | TRUE | FALSE | FALSE
8935 | MRT-YT01-P0GN-135256 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 1 | TRUE | TRUE | FALSE
8936 | MRT-YT01-P0GN-135261 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 1 | TRUE | TRUE | FALSE
8937 | MRT-YT01-P3GC-135198 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 0 | TRUE | FALSE | FALSE
8938 | MRT-YT01-P0GN-135255 | 2019-07-15 | MRT-HK-REC-TT-190680 | FA | 1 | TRUE | TRUE | FALSE
8939 | MRT-DD00-P0BAT-155145 | 2019-07-15 | MRT-HK-REC-TT-190679 | FI | 0 | TRUE | FALSE | FALSE
8940 | MRT-DD00-P0BAT-155144 | 2019-07-15 | MRT-HK-REC-TT-190679 | FI | 0 | TRUE | FALSE | FALSE
8941 | MRT-DD00-P0BAT-155143 | 2019-07-15 | MRT-HK-REC-TT-190679 | FI | 0 | TRUE | FALSE | FALSE
8942 | MRT-DD00-P0BAT-155142 | 2019-07-15 | MRT-HK-REC-TT-190679 | FI | 0 | TRUE | FALSE | FALSE
8943 | MRT-HM01-P00SA-135572 | 2019-07-15 | MRT-HK-REC-TT-190681 | FA | 2 | TRUE | TRUE | FALSE
8944 | MRT-HM01-P00SA-135573 | 2019-07-15 | MRT-HK-REC-TT-190681 | FA | 1 | TRUE | TRUE | FALSE
8945 | MRT-HM01-P0SAK-135564 | 2019-07-15 | MRT-HK-REC-TT-190681 | FA | 1 | TRUE | TRUE | FALSE
8946 | MRT-HM01-P00SA-135575 | 2019-07-15 | MRT-HK-REC-TT-190681 | FA | 1 | TRUE | TRUE | FALSE
8947 | MRT-HM01-P0SAL-135569 | 2019-07-15 | MRT-HK-REC-TT-190681 | FA | 1 | TRUE | TRUE | FALSE
8948 | MRT-HM01-P00SA-135574 | 2019-07-15 | MRT-HK-REC-TT-190681 | FA | 1 | TRUE | TRUE | FALSE
8949 | MRT-YT01-P3GC-135197 | 2019-07-16 | MRT-HK-REC-TT-190682 | FA | 0 | TRUE | FALSE | FALSE
8950 | MRT-YT01-P0GN-135232 | 2019-07-16 | MRT-HK-REC-TT-190682 | FA | 0 | TRUE | FALSE | FALSE
8951 | MRT-YT01-P0GN-135225 | 2019-07-16 | MRT-HK-REC-TT-190682 | FA | 0 | TRUE | FALSE | FALSE
8952 | MRT-YT01-P0GN-135223 | 2019-07-16 | MRT-HK-REC-TT-190682 | FA | 1 | TRUE | TRUE | FALSE
8953 | MRT-XG02-P3GC-135102 | 2019-07-16 | MRT-HK-REC-TT-190682 | FA | 5 | TRUE | TRUE | FALSE
8954 | MRT-XB00-P3GC-135136 | 2019-07-16 | MRT-HK-REC-TT-190682 | FA | 1 | TRUE | TRUE | FALSE
8955 | MRT-BT00-P0GEN-135715 | 2019-07-16 | MRT-HK-REC-TT-190683 | FA | 0 | TRUE | FALSE | FALSE
8956 | MRT-BT00-P0GEN-135714 | 2019-07-16 | MRT-HK-REC-TT-190683 | FA | 0 | TRUE | FALSE | FALSE
8957 | MRT-BT00-P0GEN-135713 | 2019-07-16 | MRT-HK-REC-TT-190683 | FA | 0 | TRUE | FALSE | FALSE
8958 | MRT-CH04-P0GEN-135718 | 2019-07-16 | MRT-HK-REC-TT-190683 | FA | 0 | TRUE | FALSE | FALSE
8959 | MRT-BT00-P0GEN-135716 | 2019-07-16 | MRT-HK-REC-TT-190683 | FA | 0 | TRUE | FALSE | FALSE
8960 | MRT-YF00-P0GEN-135367 | 2019-07-16 | MRT-HK-REC-TT-190683 | FA | 0 | TRUE | FALSE | FALSE
8961 | MRT-QM01-P0GEN-135384 | 2019-07-16 | MRT-HK-REC-TT-190683 | FA | 2 | TRUE | TRUE | FALSE
8962 | MRT-XA00-P0GEN-135324 | 2019-07-16 | MRT-HK-REC-TT-190683 | FA | 1 | TRUE | TRUE | FALSE
8963 | MRT-XG02-P0QHN-125437 | 2019-07-16 | MRT-HK-REC-TT-190685 | FA | 1 | TRUE | TRUE | FALSE
8964 | MRT-XG02-P0QHG-125436 | 2019-07-16 | MRT-HK-REC-TT-190686 | FA | 1 | TRUE | TRUE | FALSE
8965 | MRT-XG02-P0LAA-125438 | 2019-07-16 | MRT-HK-REC-TT-190687 | FA | 1 | TRUE | TRUE | FALSE
8966 | MRT-XG02-P0QHA-125435 | 2019-07-16 | MRT-HK-REC-TT-190688 | FA | 1 | TRUE | TRUE | FALSE
8967 | MRT-DS05-P0EKF-125625 | 2019-07-16 | MRT-HK-REC-TT-190689 | FA | 1 | TRUE | TRUE | FALSE
8968 | MRT-BN00-P0EKF-125634 | 2019-07-16 | MRT-HK-REC-TT-190690 | FA | 1 | TRUE | TRUE | FALSE
8969 | MRT-DS05-P0EKF-125624 | 2019-07-16 | MRT-HK-REC-TT-190691 | FA | 2 | TRUE | TRUE | FALSE
8970 | MRT-DT01-P0QHB-125428 | 2019-07-16 | MRT-HK-REC-TT-190692 | FA | 2 | TRUE | TRUE | FALSE
8971 | MRT-DS00-P0ZEN-150273 | 2019-07-16 | MRT-HK-REC-TT-190693 | FA | 0 | TRUE | FALSE | FALSE
8972 | MRT-CV05-P0ZEN-150277 | 2019-07-16 | MRT-HK-REC-TT-190693 | FI | 0 | TRUE | FALSE | FALSE
8973 | MRT-US02-P0BJK-150704 | 2019-07-16 | MRT-HK-REC-TT-190694 | FA | 1 | TRUE | TRUE | FALSE
8974 | MRT-YU02-P0BJK-150703 | 2019-07-16 | MRT-HK-REC-TT-190694 | FA | 1 | TRUE | TRUE | FALSE
8975 | MRT-CC07-P0UMA-171201 | 2019-07-16 | MRT-DS-REC-TT-190160 | FA | 0 | TRUE | FALSE | FALSE
8976 | MRT-CC02-P0UMA-171203 | 2019-07-16 | MRT-DS-REC-TT-190160 | FA | 0 | TRUE | FALSE | FALSE
8977 | MRT-XJ00-P0GHC-140001 | 2019-07-17 | MRT-DS-REC-TT-190161 | FC | 1 | TRUE | TRUE | FALSE
8978 | MRT-XJ00-P2PGB-142000 | 2019-07-17 | MRT-DS-REC-TT-190161 | FC | 2 | TRUE | TRUE | FALSE
8979 | MRT-XJ00-P0LBG-141000 | 2019-07-17 | MRT-DS-REC-TT-190161 | FC | 1 | TRUE | TRUE | FALSE
8980 | MRT-DN04-P0EKF-125607 | 2019-07-17 | MRT-HK-REC-TT-190695 | FA | 2 | TRUE | TRUE | FALSE
8981 | MRT-DN04-P0SGA-135478 | 2019-07-17 | MRT-HK-REC-TT-190696 | FA | 0 | TRUE | TRUE | FALSE
8982 | MRT-BT00-P0SGA-135485 | 2019-07-17 | MRT-HK-REC-TT-190696 | FA | 1 | TRUE | TRUE | FALSE
8983 | MRT-XB02-P2LB-122018 | 2019-07-18 | MRT-DS-REC-TT-190162 | FC | 8 | TRUE | TRUE | FALSE
8984 | MRT-XB02-P3LB-122018 | 2019-07-18 | MRT-DS-REC-TT-190162 | FC | 7 | TRUE | TRUE | FALSE
8985 | MRT-XH01-P2LB-122112 | 2019-07-18 | MRT-DS-REC-TT-190146-FC | FC | 3 | TRUE | TRUE | FALSE
8986 | MRT-XH01-P3LB-122112 | 2019-07-18 | MRT-DS-REC-TT-190146-FC | FC | 3 | TRUE | TRUE | FALSE
8987 | MRT-YE16-P2UMA-150136 | 2019-07-19 | MRT-HK-REC-TT-190697 | FA | 0 | TRUE | FALSE | FALSE
8988 | MRT-CN00-P3MKW-210001 | 2019-07-19 | MRT-DS-REC-TT-190163 | FA | 0 | TRUE | FALSE | FALSE
8989 | MRT-CN00-P3MKG-210001 | 2019-07-19 | MRT-DS-REC-TT-190163 | FA | 0 | TRUE | FALSE | FALSE
8990 | MRT-XH01-P2LB-122112 | 2019-07-19 | MRT-DS-REC-TT-190164 | FC | 4 | TRUE | TRUE | FALSE
8991 | MRT-XH01-P3LB-122112 | 2019-07-19 | MRT-DS-REC-TT-190164 | FC | 4 | TRUE | TRUE | FALSE
8992 | MRT-XJ00-P2LB-122027 | 2019-07-19 | MRT-DS-REC-TT-190165 | FC | 4 | TRUE | TRUE | FALSE
8993 | MRT-XJ00-P3LB-122027 | 2019-07-19 | MRT-DS-REC-TT-190165 | FC | 4 | TRUE | TRUE | FALSE
8994 | MRT-DN04-P0QHB-125423 | 2019-07-22 | MRT-HK-REC-TT-190699 | FA | 1 | TRUE | TRUE | FALSE
8995 | MRT-FF03-P3SGK-135425 | 2019-07-22 | MRT-HK-REC-TT-190698 | FA | 0 | TRUE | FALSE | FALSE
8996 | MRT-FF03-P2SGK-135427 | 2019-07-22 | MRT-HK-REC-TT-190698 | FA | 0 | TRUE | FALSE | FALSE
8997 | MRT-FF03-P2SGE-135407 | 2019-07-22 | MRT-HK-REC-TT-190698 | FA | 0 | TRUE | FALSE | FALSE
8998 | MRT-XG02-P3SGE-135407 | 2019-07-22 | MRT-HK-REC-TT-190702 | FA | 0 | TRUE | FALSE | FALSE
8999 | MRT-FF03-P3SGE-135407 | 2019-07-22 | MRT-HK-REC-TT-190702 | FA | 0 | TRUE | FALSE | FALSE
9000 | MRT-XW01-P3GC-135109 | 2019-07-22 | MRT-HK-REC-TT-190703 | FA | 0 | TRUE | FALSE | FALSE
9001 | MRT-XW01-P0GN-135209 | 2019-07-22 | MRT-HK-REC-TT-190703 | FA | 0 | TRUE | FALSE | FALSE
9002 | MRT-YT01-P0GN-135257 | 2019-07-22 | MRT-HK-REC-TT-190704 | FA | 0 | TRUE | FALSE | FALSE
9003 | MRT-XG02-P3SGK-135425 | 2019-07-22 | MRT-HK-REC-TT-190705 | FA | 0 | TRUE | FALSE | FALSE
9004 | MRT-FF03-P3SGK-135428 | 2019-07-22 | MRT-HK-REC-TT-190705 | FA | 0 | TRUE | FALSE | FALSE
9005 | MRT-FF03-P3SGK-135424 | 2019-07-22 | MRT-HK-REC-TT-190705 | FA | 0 | TRUE | FALSE | FALSE
9006 | MRT-CC05-P0SMU-125018 | 2019-07-22 | MRT-HK-REC-TT-190701 | FA | 0 | TRUE | FALSE | FALSE
9007 | MRT-QM03-P0ZEN-185013 | 2019-07-22 | MRT-HK-REC-TT-190707 | FA | 0 | TRUE | FALSE | FALSE
9008 | MRT-QM03-P0ZEN-185015 | 2019-07-22 | MRT-HK-REC-TT-190707 | FA | 0 | TRUE | FALSE | FALSE
9009 | MRT-QM03-P0ZEN-185016 | 2019-07-22 | MRT-HK-REC-TT-190707 | FA | 0 | TRUE | FALSE | FALSE
9010 | MRT-QM03-P0ZEN-185017 | 2019-07-22 | MRT-HK-REC-TT-190707 | FA | 0 | TRUE | FALSE | FALSE
9011 | MRT-QM03-P0ZEN-185018 | 2019-07-22 | MRT-HK-REC-TT-190707 | FA | 0 | TRUE | FALSE | FALSE
9012 | MRT-QM03-P0ZEN-185019 | 2019-07-22 | MRT-HK-REC-TT-190707 | FA | 0 | TRUE | FALSE | FALSE
9013 | MRT-QM03-P0ZEN-155034 | 2019-07-22 | MRT-HK-REC-TT-190708 | FA | 0 | TRUE | FALSE | FALSE
9014 | MRT-XG02-P0SGE-135411 | 2019-07-23 | MRT-HK-REC-TT-190709 | FA | 0 | TRUE | FALSE | FALSE
9015 | MRT-FF03-P2SGC-135419 | 2019-07-23 | MRT-HK-REC-TT-190709 | FA | 0 | TRUE | FALSE | FALSE
9016 | MRT-FF03-P2SGC-135415 | 2019-07-23 | MRT-HK-REC-TT-190709 | FA | 0 | TRUE | FALSE | FALSE
9017 | MRT-FF03-P0SGE-135411 | 2019-07-23 | MRT-HK-REC-TT-190709 | FA | 0 | TRUE | FALSE | FALSE
9018 | MRT-FF00-P0SGA-135654 | 2019-07-23 | MRT-HK-REC-TT-190709 | FA | 0 | TRUE | FALSE | FALSE
9019 | MRT-DD00-P0BAT-155153 | 2019-07-24 | MRT-HK-REC-TT-190710 | FI | 0 | TRUE | FALSE | FALSE
9020 | MRT-DD00-P0BAT-155152 | 2019-07-24 | MRT-HK-REC-TT-190710 | FI | 0 | TRUE | FALSE | FALSE
9021 | MRT-DD00-P0BAT-155151 | 2019-07-24 | MRT-HK-REC-TT-190710 | FI | 0 | TRUE | FALSE | FALSE
9022 | MRT-DD00-P0BAT-155150 | 2019-07-24 | MRT-HK-REC-TT-190710 | FI | 0 | TRUE | FALSE | FALSE
9023 | MRT-DD00-P0BAT-155149 | 2019-07-24 | MRT-HK-REC-TT-190710 | FI | 0 | TRUE | FALSE | FALSE
9024 | MRT-DD00-P0BAT-155148 | 2019-07-24 | MRT-HK-REC-TT-190710 | FI | 0 | TRUE | FALSE | FALSE
9025 | MRT-DD00-P0BAT-155147 | 2019-07-24 | MRT-HK-REC-TT-190710 | FI | 0 | TRUE | FALSE | FALSE
9026 | MRT-DD00-P0BAT-155146 | 2019-07-24 | MRT-HK-REC-TT-190710 | FI | 0 | TRUE | FALSE | FALSE
9027 | MRT-HM01-P0SAK-135536 | 2019-07-24 | MRT-HK-REC-TT-190711 | FA | 0 | TRUE | FALSE | FALSE
9028 | MRT-HM01-P0SAH-135534 | 2019-07-24 | MRT-HK-REC-TT-190711 | FA | 0 | TRUE | FALSE | FALSE
9029 | MRT-HM01-P0SAF-135541 | 2019-07-24 | MRT-HK-REC-TT-190711 | FA | 0 | TRUE | FALSE | FALSE
9030 | MRT-HM01-P0SAE-135544 | 2019-07-24 | MRT-HK-REC-TT-190711 | FA | 0 | TRUE | FALSE | FALSE
9031 | MRT-HM01-P0SA-135539 | 2019-07-24 | MRT-HK-REC-TT-190711 | FA | 0 | TRUE | FALSE | FALSE
9032 | MRT-YK08-P0GHE-145040 | 2019-07-24 | MRT-HK-REC-TT-190712 | FA | 1 | TRUE | TRUE | FALSE
9033 | MRT-YK09-P0GHE-145010 | 2019-07-24 | MRT-HK-REC-TT-190712 | FA | 1 | TRUE | TRUE | FALSE
9034 | MRT-QA00-P0ZEN-150271 | 2019-07-24 | MRT-HK-REC-TT-190713 | FA | 0 | TRUE | FALSE | FALSE
9035 | MRT-DS00-P0ZEN-150272 | 2019-07-24 | MRT-HK-REC-TT-190713 | FA | 0 | TRUE | FALSE | FALSE
9036 | MRT-XG02-P0SGE-135409 | 2019-07-24 | MRT-HK-REC-TT-190714 | FA | 0 | TRUE | FALSE | FALSE
9037 | MRT-XG02-P3SGK-135424 | 2019-07-24 | MRT-HK-REC-TT-190715 | FA | 0 | TRUE | FALSE | FALSE
9038 | MRT-XG02-P0SGE-135408 | 2019-07-24 | MRT-HK-REC-TT-190715 | FA | 0 | TRUE | FALSE | FALSE
9039 | MRT-DM02-P3MAA-220193 | 2019-07-24 | MRT-DS-REC-TT-190166 | FI | 0 | TRUE | FALSE | FALSE
9040 | MRT-CQ02-P3MAA-220202 | 2019-07-24 | MRT-DS-REC-TT-190166 | FI | 0 | TRUE | FALSE | FALSE
9041 | MRT-DM02-P2MAA-220199 | 2019-07-24 | MRT-DS-REC-TT-190166 | FI | 0 | TRUE | TRUE | FALSE
9042 | MRT-DM02-P3MAA-220199 | 2019-07-24 | MRT-DS-REC-TT-190166 | FI | 0 | TRUE | TRUE | FALSE
9043 | MRT-CQ02-P2MAA-220201 | 2019-07-24 | MRT-DS-REC-TT-190167 | FC | 1 | TRUE | TRUE | FALSE
9044 | MRT-CC02-P0UYX-175392 | 2019-07-25 | MRT-HK-REC-TT-190716 | FA | 0 | TRUE | FALSE | FALSE
9045 | MRT-CC03-P0UYX-175412 | 2019-07-25 | MRT-HK-REC-TT-190716 | FA | 0 | TRUE | FALSE | FALSE
9046 | MRT-CC02-P0UYX-175391 | 2019-07-25 | MRT-HK-REC-TT-190716 | FA | 0 | TRUE | FALSE | FALSE
9047 | MRT-CC03-P0UYX-175411 | 2019-07-25 | MRT-HK-REC-TT-190716 | FA | 0 | TRUE | FALSE | FALSE
9048 | MRT-CA01-P0UPB-187016 | 2019-07-25 | MRT-HK-REC-TT-190716 | FA | 3 | TRUE | TRUE | FALSE
9049 | MRT-CC02-P0UAA-176070 | 2019-07-25 | MRT-HK-REC-TT-190717 | FA | 2 | TRUE | TRUE | FALSE
9050 | MRT-CC02-P0UAA-176071 | 2019-07-25 | MRT-HK-REC-TT-190717 | FA | 2 | TRUE | TRUE | FALSE
9051 | MRT-CC02-P0UAA-176073 | 2019-07-25 | MRT-HK-REC-TT-190717 | FA | 2 | TRUE | TRUE | FALSE
9052 | MRT-CC02-P0UAA-176074 | 2019-07-25 | MRT-HK-REC-TT-190717 | FA | 2 | TRUE | TRUE | FALSE
9053 | MRT-CC02-P0UAA-176076 | 2019-07-25 | MRT-HK-REC-TT-190717 | FA | 2 | TRUE | TRUE | FALSE
9054 | MRT-CC03-P0UAA-176080 | 2019-07-25 | MRT-HK-REC-TT-190717 | FA | 2 | TRUE | TRUE | FALSE
9055 | MRT-CC02-P0UPC-175720 | 2019-07-25 | MRT-HK-REC-TT-190718 | FA | 3 | TRUE | TRUE | FALSE
9056 | MRT-CC02-P0UPC-175740 | 2019-07-25 | MRT-HK-REC-TT-190718 | FA | 2 | TRUE | TRUE | FALSE
9057 | MRT-CC02-P0UPC-175745 | 2019-07-25 | MRT-HK-REC-TT-190718 | FA | 2 | TRUE | TRUE | FALSE
9058 | MRT-CC02-P0UPC-175726 | 2019-07-25 | MRT-HK-REC-TT-190718 | FA | 3 | TRUE | TRUE | FALSE
9059 | MRT-CC02-P0UPC-175727 | 2019-07-25 | MRT-HK-REC-TT-190718 | FA | 2 | TRUE | TRUE | FALSE
9060 | MRT-CC02-P0UPC-175728 | 2019-07-25 | MRT-HK-REC-TT-190718 | FA | 2 | TRUE | TRUE | FALSE
9061 | MRT-CC02-P0UPC-175729 | 2019-07-25 | MRT-HK-REC-TT-190718 | FA | 2 | TRUE | TRUE | FALSE
9062 | MRT-CC02-P0UPC-175737 | 2019-07-25 | MRT-HK-REC-TT-190718 | FA | 2 | TRUE | TRUE | FALSE
9063 | MRT-CC02-P0UPC-175744 | 2019-07-25 | MRT-HK-REC-TT-190718 | FA | 2 | TRUE | TRUE | FALSE
9064 | MRT-YL16-P0BHA-150066 | 2019-07-25 | MRT-HK-REC-TT-190720 | FI | 0 | TRUE | FALSE | FALSE
9065 | MRT-HM02-P3SAC-150079 | 2019-07-25 | MRT-HK-REC-TT-190720 | FI | 0 | TRUE | FALSE | FALSE
9066 | MRT-CA00-P0UCA-180108 | 2019-07-25 | MRT-DS-REC-TT-190168 | FC | 7 | TRUE | TRUE | FALSE
9067 | MRT-CA00-P0UCA-180113 | 2019-07-25 | MRT-DS-REC-TT-190168 | FC | 6 | TRUE | TRUE | FALSE
9068 | MRT-CA03-P0UCA-180132 | 2019-07-25 | MRT-DS-REC-TT-190168 | FC | 5 | TRUE | TRUE | FALSE
9069 | MRT-CA01-P0UCA-180133 | 2019-07-25 | MRT-DS-REC-TT-190168 | FC | 4 | TRUE | TRUE | FALSE
9070 | MRT-CH04-P0BTA-150634 | 2019-07-25 | MRT-HK-REC-TT-190721 | FA | 0 | TRUE | FALSE | FALSE
9071 | MRT-XJ00-P2PGB-145000 | 2019-07-25 | MRT-DS-REC-TT-190169 | FC | 1 | TRUE | TRUE | FALSE
9072 | MRT-YT01-P3GC-135154 | 2019-07-26 | MRT-HK-REC-TT-190722 | FA | 0 | TRUE | TRUE | FALSE
9073 | MRT-YT01-P3GC-135153 | 2019-07-26 | MRT-HK-REC-TT-190722 | FA | 0 | TRUE | TRUE | FALSE
9074 | MRT-YT01-P3GC-135152 | 2019-07-26 | MRT-HK-REC-TT-190722 | FA | 0 | TRUE | TRUE | FALSE
9075 | MRT-YT01-P0GN-135259 | 2019-07-26 | MRT-HK-REC-TT-190722 | FA | 0 | TRUE | TRUE | FALSE
9076 | MRT-YT01-P0GN-135258 | 2019-07-26 | MRT-HK-REC-TT-190722 | FA | 0 | TRUE | TRUE | FALSE
9077 | MRT-XJ00-P2PAB-145000 | 2019-07-26 | MRT-DS-REC-TT-190171 | FC | 1 | TRUE | TRUE | FALSE
9078 | MRT-XJ00-P3PAB-146000 | 2019-07-26 | MRT-DS-REC-TT-190171 | FC | 1 | TRUE | TRUE | FALSE
9079 | MRT-XJ00-P2PAB-145100 | 2019-07-26 | MRT-DS-REC-TT-190171 | FC | 1 | TRUE | TRUE | FALSE
9080 | MRT-XJ00-P3PAB-146100 | 2019-07-26 | MRT-DS-REC-TT-190171 | FC | 1 | TRUE | TRUE | FALSE
9081 | MRT-XJ00-P3PAB-147100 | 2019-07-26 | MRT-DS-REC-TT-190171 | FC | 1 | TRUE | TRUE | FALSE
9082 | MRT-XJ00-P2LBA-142000 | 2019-07-26 | MRT-DS-REC-TT-190170 | FC | 2 | TRUE | TRUE | FALSE
9083 | MRT-XJ00-P2LBG-142000 | 2019-07-26 | MRT-DS-REC-TT-190170 | FC | 2 | TRUE | TRUE | FALSE
9084 | MRT-XJ00-P2LAB-142000 | 2019-07-26 | MRT-DS-REC-TT-190170 | FC | 2 | TRUE | TRUE | FALSE
9085 | MRT-XJ00-P2LCA-142000 | 2019-07-26 | MRT-DS-REC-TT-190170 | FC | 2 | TRUE | TRUE | FALSE
9086 | MRT-XJ00-P2PGB-142000 | 2019-07-26 | MRT-DS-REC-TT-190170 | FC | 2 | TRUE | TRUE | FALSE
9087 | MRT-XJ00-P2LCM-142000 | 2019-07-26 | MRT-DS-REC-TT-190170 | FC | 2 | TRUE | TRUE | FALSE
9088 | MRT-XJ00-P2PAB-140001 | 2019-07-26 | MRT-DS-REC-TT-190172 | FC | 4 | TRUE | TRUE | FALSE
9089 | MRT-XJ00-P3PAB-140001 | 2019-07-26 | MRT-DS-REC-TT-190172 | FC | 4 | TRUE | TRUE | FALSE
9090 | MRT-XJ00-P2PAB-142100 | 2019-07-26 | MRT-DS-REC-TT-190172 | FC | 3 | TRUE | TRUE | FALSE
9091 | MRT-XJ00-P3PAB-143100 | 2019-07-26 | MRT-DS-REC-TT-190172 | FC | 3 | TRUE | TRUE | FALSE
9092 | MRT-XJ00-P3PAB-144100 | 2019-07-26 | MRT-DS-REC-TT-190172 | FC | 3 | TRUE | TRUE | FALSE
9093 | MRT-XJ00-P2PAB-142200 | 2019-07-26 | MRT-DS-REC-TT-190172 | FC | 1 | TRUE | TRUE | FALSE
9094 | MRT-XJ00-P3PAB-143200 | 2019-07-26 | MRT-DS-REC-TT-190172 | FC | 1 | TRUE | TRUE | FALSE
9095 | MRT-XJ00-P3PAB-144200 | 2019-07-26 | MRT-DS-REC-TT-190172 | FC | 1 | TRUE | TRUE | FALSE
9096 | MRT-CA05-P0UMA-180062 | 2019-07-26 | MRT-DS-REC-TT-190173 | FC | 6 | TRUE | TRUE | FALSE
9099 | MRT-DP00-P2LB-122123 | 2019-07-26 | MRT-DS-REC-TT-190137-FC | FC | 1 | TRUE | TRUE | FALSE
9100 | MRT-DP00-P3LB-122123 | 2019-07-26 | MRT-DS-REC-TT-190137-FC | FC | 1 | TRUE | TRUE | FALSE
9103 | MRT-CV03-P2ZEN-165103 | 2019-07-26 | MRT-DS-REC-TT-190152-FC | FC | 3 | TRUE | TRUE | FALSE
9104 | MRT-CV03-P3ZEN-165103 | 2019-07-26 | MRT-DS-REC-TT-190152-FC | FC | 3 | TRUE | TRUE | FALSE
9105 | MRT-XH01-P2LB-122025 | 2019-07-26 | MRT-DS-REC-TT-190155-FC | FC | 2 | TRUE | TRUE | FALSE
9106 | MRT-XH01-P3LB-122025 | 2019-07-26 | MRT-DS-REC-TT-190155-FC | FC | 2 | TRUE | TRUE | FALSE
9109 | MRT-CQ02-P2MAA-220202 | 2019-07-26 | MRT-DS-REC-TT-190157-FC | FC | 0 | TRUE | TRUE | FALSE
9110 | MRT-CQ02-P3MAA-220201 | 2019-07-26 | MRT-DS-REC-TT-190157-FC | FC | 0 | TRUE | TRUE | FALSE
9111 | MRT-DN05-P3MAA-220205 | 2019-07-26 | MRT-DS-REC-TT-190157-FC | FC | 0 | TRUE | TRUE | FALSE
9142 | MRT-CH04-P0ABA-150566 | 2019-07-26 | MRT-HK-REC-TT-190723 | FA | 0 | TRUE | FALSE | FALSE
9126 | MRT-QM03-P0ZEN-045007 | 2019-07-29 | MRT-HK-REC-TT-190724 | FA | 1 | TRUE | TRUE | FALSE
9115 | MRT-XB02-P2LB-122018 | 2019-07-31 | MRT-DS-REC-TT-190162-FC | FC | 8 | TRUE | TRUE | FALSE
9116 | MRT-XB02-P3LB-122018 | 2019-07-31 | MRT-DS-REC-TT-190162-FC | FC | 7 | TRUE | TRUE | FALSE
9117 | MRT-XH01-P2LB-122112 | 2019-07-31 | MRT-DS-REC-TT-190164-FC | FC | 4 | TRUE | TRUE | FALSE
9118 | MRT-XH01-P3LB-122112 | 2019-07-31 | MRT-DS-REC-TT-190164-FC | FC | 4 | TRUE | TRUE | FALSE
9119 | MRT-CA00-P0UCA-180108 | 2019-07-31 | MRT-DS-REC-TT-190168-FC | FC | 7 | TRUE | TRUE | FALSE
9120 | MRT-CA00-P0UCA-180113 | 2019-07-31 | MRT-DS-REC-TT-190168-FC | FC | 6 | TRUE | TRUE | FALSE
9121 | MRT-CA03-P0UCA-180132 | 2019-07-31 | MRT-DS-REC-TT-190168-FC | FC | 5 | TRUE | TRUE | FALSE
9122 | MRT-CA01-P0UCA-180133 | 2019-07-31 | MRT-DS-REC-TT-190168-FC | FC | 4 | TRUE | TRUE | FALSE
9123 | MRT-CC07-P0UMA-171201 | 2019-07-31 | MRT-DS-REC-TT-190160-FC | FC | 0 | TRUE | TRUE | FALSE
9097 | MRT-VN03-P2LB-122015 | 2019-08-05 | MRT-DS-REC-TT-190134-FC | FC | 6 | TRUE | TRUE | FALSE
9098 | MRT-VN03-P3LB-122015 | 2019-08-05 | MRT-DS-REC-TT-190134-FC | FC | 6 | TRUE | TRUE | FALSE
9101 | MRT-XJ00-P2LB-122028 | 2019-08-05 | MRT-DS-REC-TT-190145-FC | FC | 5 | TRUE | TRUE | FALSE
9102 | MRT-XJ00-P3LB-122028 | 2019-08-05 | MRT-DS-REC-TT-190145-FC | FC | 5 | TRUE | TRUE | FALSE
9107 | MRT-YR01-P2ZEN-110103 | 2019-08-05 | MRT-DS-REC-TT-190156-FC | FC | 1 | TRUE | TRUE | FALSE
9108 | MRT-YR01-P3ZEN-110103 | 2019-08-05 | MRT-DS-REC-TT-190156-FC | FC | 1 | TRUE | TRUE | FALSE
9112 | MRT-XJ00-P0GHD-140001 | 2019-08-05 | MRT-DS-REC-TT-190158-FC | FC | 1 | TRUE | TRUE | FALSE
9113 | MRT-XJ00-P0GKB-140001 | 2019-08-05 | MRT-DS-REC-TT-190158-FC | FC | 1 | TRUE | TRUE | FALSE
9114 | MRT-XJ00-P0GMA-140001 | 2019-08-05 | MRT-DS-REC-TT-190158-FC | FC | 1 | TRUE | TRUE | FALSE
9124 | MRT-XJ00-P2LB-122027 | 2019-08-05 | MRT-DS-REC-TT-190165-FC | FC | 4 | TRUE | TRUE | FALSE
9125 | MRT-XJ00-P3LB-122027 | 2019-08-05 | MRT-DS-REC-TT-190165-FC | FC | 4 | TRUE | TRUE | FALSE
9127 | MRT-DD01-P0ZEN-175022 | 2019-08-05 | MRT-HK-REC-TT-190725 | FA | 0 | TRUE | FALSE | FALSE
9128 | MRT-QM03-P0GHE-145076 | 2019-08-05 | MRT-HK-REC-TT-190726 | FA | 0 | TRUE | FALSE | FALSE
9129 | MRT-QM03-P0GHE-145060 | 2019-08-05 | MRT-HK-REC-TT-190726 | FA | 0 | TRUE | FALSE | FALSE
9130 | MRT-YT01-P0GN-135293 | 2019-08-05 | MRT-HK-REC-TT-190727 | FA | 0 | TRUE | FALSE | FALSE
9131 | MRT-YT01-P0GN-135224 | 2019-08-05 | MRT-HK-REC-TT-190727 | FA | 0 | TRUE | FALSE | FALSE
9132 | MRT-YT01-P0GEN-135391 | 2019-08-05 | MRT-HK-REC-TT-190727 | FA | 0 | TRUE | FALSE | FALSE
9133 | MRT-XG02-P0SGE-135412 | 2019-08-05 | MRT-HK-REC-TT-190728 | FA | 0 | TRUE | FALSE | FALSE
9134 | MRT-XV00-P0GN-135215 | 2019-08-05 | MRT-HK-REC-TT-190728 | FA | 0 | TRUE | FALSE | FALSE
9135 | MRT-YM03-P0GEN-135882 | 2019-08-05 | MRT-HK-REC-TT-190729 | FA | 0 | TRUE | FALSE | FALSE
9136 | MRT-YT01-P3GC-135156 | 2019-08-05 | MRT-HK-REC-TT-190729 | FA | 0 | TRUE | FALSE | FALSE
9137 | MRT-XR00-P0SA-135754 | 2019-08-05 | MRT-HK-REC-TT-190730 | FA | 0 | TRUE | FALSE | FALSE
9138 | MRT-XR00-P0SA-135753 | 2019-08-05 | MRT-HK-REC-TT-190730 | FA | 0 | TRUE | FALSE | FALSE
9139 | MRT-XR00-P0SA-135742 | 2019-08-05 | MRT-HK-REC-TT-190730 | FA | 0 | TRUE | FALSE | FALSE
9140 | MRT-CC02-P0UMA-171203 | 2019-08-06 | MRT-DS-REC-TT-190174 | FA | 1 | TRUE | TRUE | FALSE
9141 | MRT-YD00-P0UAB-150210 | 2019-08-07 | MRT-HK-REC-TT-190731 | FA | 1 | TRUE | TRUE | FALSE
9143 | MRT-DD09-P0ZEN-128202 | 2019-08-07 | MRT-HK-REC-TT-190732 | FA | 1 | TRUE | TRUE | FALSE
9144 | MRT-CC02-P2UMA-170207 | 2019-08-08 | MRT-DS-REC-TT-190175 | FC | 7 | TRUE | TRUE | FALSE
9145 | MRT-CC02-P3UMA-170207 | 2019-08-08 | MRT-DS-REC-TT-190175 | FC | 7 | TRUE | TRUE | FALSE
9146 | MRT-QM03-P0ZEN-155035 | 2019-08-08 | MRT-HK-REC-TT-190733 | FA | 0 | TRUE | FALSE | FALSE
9147 | MRT-DN04-P0BRU-150267 | 2019-08-08 | MRT-HK-REC-TT-190733 | FA | 0 | TRUE | FALSE | FALSE
9148 | MRT-CC02-P2UMA-170609 | 2019-08-09 | MRT-DS-REC-TT-190150-FC | FC | 5 | TRUE | TRUE | FALSE
9149 | MRT-DP00-P2LB-122106 | 2019-08-09 | MRT-DS-REC-TT-190151-FC | FC | 5 | TRUE | TRUE | FALSE
9150 | MRT-DP00-P3LB-122106 | 2019-08-09 | MRT-DS-REC-TT-190151-FC | FC | 5 | TRUE | TRUE | FALSE
9151 | MRT-CC02-P2UHA-170103 | 2019-08-09 | MRT-DS-REC-TT-190159-FC | FC | 11 | TRUE | TRUE | FALSE
9152 | MRT-CC02-P3UHA-170103 | 2019-08-09 | MRT-DS-REC-TT-190159-FC | FC | 11 | TRUE | TRUE | FALSE
9153 | MRT-YL00-P2GM-128512 | 2019-08-09 | MRT-DS-REC-TT-190176-FC | FC | 3 | TRUE | TRUE | FALSE
9154 | MRT-YL00-P3GM-128512 | 2019-08-09 | MRT-DS-REC-TT-190176-FC | FC | 3 | TRUE | TRUE | FALSE
9155 | MRT-XJ00-P2LAB-145000 | 2019-08-12 | MRT-DS-REC-TT-190177-FC | FC | 1 | TRUE | TRUE | FALSE
9156 | MRT-XJ00-P3LAB-146000 | 2019-08-12 | MRT-DS-REC-TT-190177-FC | FC | 1 | TRUE | TRUE | FALSE
9157 | MRT-XJ00-P3LAB-147000 | 2019-08-12 | MRT-DS-REC-TT-190177-FC | FC | 1 | TRUE | TRUE | FALSE
9158 | MRT-XJ00-P2LBA-145000 | 2019-08-14 | MRT-DS-REC-TT-190178-FC | FC | 1 | TRUE | TRUE | FALSE
9159 | MRT-XJ00-P2LBG-145000 | 2019-08-14 | MRT-DS-REC-TT-190178-FC | FC | 1 | TRUE | TRUE | FALSE
9160 | MRT-XJ00-P2LCM-145000 | 2019-08-14 | MRT-DS-REC-TT-190178-FC | FC | 1 | TRUE | TRUE | FALSE
9161 | MRT-CA05-P0UMA-180062 | 2019-08-19 | MRT-DS-REC-TT-190173-FC | FC | 6 | TRUE | TRUE | FALSE
9163 | MRT-US02-P0SAC-150696 | 2019-08-19 | MRT-HK-REC-TT-190736 | FA | 0 | TRUE | FALSE | FALSE
9164 | MRT-US02-P0SRA-150698 | 2019-08-19 | MRT-HK-REC-TT-190736 | FA | 0 | TRUE | FALSE | FALSE
9165 | MRT-YU02-P0SAC-150695 | 2019-08-19 | MRT-HK-REC-TT-190736 | FA | 0 | TRUE | FALSE | FALSE
9166 | MRT-YU02-P0SRA-150697 | 2019-08-19 | MRT-HK-REC-TT-190736 | FA | 0 | TRUE | FALSE | FALSE
9167 | MRT-XW03-P0ABA-150324 | 2019-08-19 | MRT-HK-REC-TT-190737 | FA | 1 | TRUE | TRUE | FALSE
9168 | MRT-YL16-P0BUB-150076 | 2019-08-19 | MRT-HK-REC-TT-190738 | FA | 0 | TRUE | FALSE | FALSE
9169 | MRT-YE16-P2UMA-150330 | 2019-08-19 | MRT-HK-REC-TT-190738 | FA | 0 | TRUE | FALSE | FALSE
9170 | MRT-DD00-P0BAT-155154 | 2019-08-19 | MRT-HK-REC-TT-190739 | FI | 0 | TRUE | FALSE | FALSE
9171 | MRT-DD00-P0BAT-155155 | 2019-08-19 | MRT-HK-REC-TT-190739 | FI | 0 | TRUE | FALSE | FALSE
9172 | MRT-DD00-P0BAT-155156 | 2019-08-19 | MRT-HK-REC-TT-190739 | FI | 0 | TRUE | FALSE | FALSE
9173 | MRT-DD00-P0BAT-155157 | 2019-08-19 | MRT-HK-REC-TT-190739 | FI | 0 | TRUE | FALSE | FALSE
9174 | MRT-DS00-P0ZEN-175020 | 2019-08-19 | MRT-HK-REC-TT-190735 | FI | 3 | TRUE | TRUE | FALSE
9175 | MRT-YT01-P0GN-135227 | 2019-08-19 | MRT-HK-REC-TT-190741 | FA | 0 | TRUE | FALSE | FALSE
9176 | MRT-YT01-P3GC-135195 | 2019-08-19 | MRT-HK-REC-TT-190742 | FA | 0 | TRUE | FALSE | FALSE
9177 | MRT-DS00-P0GN-135871 | 2019-08-19 | MRT-HK-REC-TT-190742 | FA | 0 | TRUE | FALSE | FALSE
9178 | MRT-UC02-P2LB-122121 | 2019-08-20 | MRT-DS-REC-TT-190180-FC | FC | 1 | TRUE | TRUE | FALSE
9179 | MRT-YD00-P2CJA-240057 | 2019-08-21 | MRT-DS-REC-TT-190179-FC | FC | 3 | TRUE | TRUE | FALSE
9180 | MRT-YD00-P2CJA-240058 | 2019-08-21 | MRT-DS-REC-TT-190179-FC | FC | 3 | TRUE | TRUE | FALSE
9181 | MRT-YD00-P2CJA-240059 | 2019-08-21 | MRT-DS-REC-TT-190179-FC | FC | 3 | TRUE | TRUE | FALSE
9182 | MRT-YD00-P3CJA-240057 | 2019-08-21 | MRT-DS-REC-TT-190179-FC | FC | 2 | TRUE | TRUE | FALSE
9183 | MRT-YD00-P3CJA-240058 | 2019-08-21 | MRT-DS-REC-TT-190179-FC | FC | 2 | TRUE | TRUE | FALSE
9184 | MRT-YD00-P3CJA-240059 | 2019-08-21 | MRT-DS-REC-TT-190179-FC | FC | 2 | TRUE | TRUE | FALSE
9185 | MRT-DD04-P0GEN-135389 | 2019-08-21 | MRT-HK-REC-TT-190743 | FI | 0 | TRUE | FALSE | FALSE
9186 | MRT-CV05-P0GEN-135318 | 2019-08-21 | MRT-HK-REC-TT-190743 | FI | 0 | TRUE | FALSE | FALSE
9187 | MRT-US02-P0GN-135242 | 2019-08-21 | MRT-HK-REC-TT-190744 | FI | 0 | TRUE | FALSE | FALSE
9188 | MRT-DP00-P0GDY-135066 | 2019-08-21 | MRT-HK-REC-TT-190745 | FI | 0 | TRUE | FALSE | FALSE
9189 | MRT-XJ00-P2PAB-145100 | 2019-08-21 | MRT-DS-REC-TT-190181-FC | FC | 2 | TRUE | TRUE | FALSE
9190 | MRT-XJ00-P3PAB-146100 | 2019-08-21 | MRT-DS-REC-TT-190181-FC | FC | 2 | TRUE | TRUE | FALSE
9191 | MRT-XJ00-P3PAB-147100 | 2019-08-21 | MRT-DS-REC-TT-190181-FC | FC | 2 | TRUE | TRUE | FALSE
9192 | MRT-XJ00-P3LBA-146000 | 2019-08-21 | MRT-DS-REC-TT-190181-FC | FC | 1 | TRUE | TRUE | FALSE
9193 | MRT-XJ00-P3LBA-147000 | 2019-08-21 | MRT-DS-REC-TT-190181-FC | FC | 1 | TRUE | TRUE | FALSE
9194 | MRT-YD00-P3ZEN-113300 | 2019-08-22 | MRT-DS-REC-TT-190182 | FC | 3 | TRUE | TRUE | FALSE
9195 | MRT-YT01-P3ZEN-113301 | 2019-08-22 | MRT-DS-REC-TT-190182 | FC | 3 | TRUE | TRUE | FALSE
9196 | MRT-XJ00-P0GHC-141000 | 2019-08-22 | MRT-DS-REC-TT-190184-FC | FC | 1 | TRUE | TRUE | FALSE
9197 | MRT-XJ00-P2QU-145000 | 2019-08-22 | MRT-DS-REC-TT-190184-FC | FC | 1 | TRUE | TRUE | FALSE
9198 | MRT-XJ00-P0EGD-141000 | 2019-08-22 | MRT-DS-REC-TT-190184-FC | FC | 1 | TRUE | TRUE | FALSE
9199 | MRT-XJ00-P0EKG-141000 | 2019-08-22 | MRT-DS-REC-TT-190184-FC | FC | 1 | TRUE | TRUE | FALSE
9200 | MRT-XJ00-P0LAA-140000 | 2019-08-22 | MRT-DS-REC-TT-190184-FC | FC | 1 | TRUE | TRUE | FALSE
9201 | MRT-YT01-P3MKA-240003 | 2019-08-22 | MRT-DS-REC-TT-190183 | FI | 6 | TRUE | TRUE | FALSE
9202 | MRT-CQ02-P2LB-122118 | 2019-08-23 | MRT-DS-REC-TT-190185-FC | FC | 1 | TRUE | TRUE | FALSE
9203 | MRT-XJ00-P3LBG-146000 | 2019-08-26 | MRT-DS-REC-TT-190186-FC | FC | 1 | TRUE | TRUE | FALSE
9204 | MRT-XJ00-P3LBG-147000 | 2019-08-26 | MRT-DS-REC-TT-190186-FC | FC | 1 | TRUE | TRUE | FALSE
9205 | MRT-XJ00-P3QU-146000 | 2019-08-26 | MRT-DS-REC-TT-190186-FC | FC | 1 | TRUE | TRUE | FALSE
9206 | MRT-CC05-P0SMU-125016 | 2019-08-26 | MRT-HK-REC-TT-190747 | FA | 0 | TRUE | FALSE | FALSE
9207 | MRT-CC05-P0SMU-125017 | 2019-08-26 | MRT-HK-REC-TT-190747 | FA | 0 | TRUE | FALSE | FALSE
9208 | MRT-CC05-P0SMU-125013 | 2019-08-26 | MRT-HK-REC-TT-190747 | FA | 0 | TRUE | FALSE | FALSE
9209 | MRT-CC05-P0SMU-125014 | 2019-08-26 | MRT-HK-REC-TT-190747 | FA | 0 | TRUE | FALSE | FALSE
9210 | MRT-CC05-P0SMU-125015 | 2019-08-26 | MRT-HK-REC-TT-190747 | FA | 0 | TRUE | FALSE | FALSE
9211 | MRT-YT01-P0GN-135294 | 2019-08-26 | MRT-HK-REC-TT-190748 | FA | 0 | TRUE | FALSE | FALSE
9212 | MRT-DM02-P0MKG-125365 | 2019-08-26 | MRT-HK-REC-TT-190749 | FI | 0 | TRUE | FALSE | FALSE
9213 | MRT-CQ02-P0MKG-125378 | 2019-08-26 | MRT-HK-REC-TT-190749 | FI | 0 | TRUE | FALSE | FALSE
9214 | MRT-CM00-P0MKG-125379 | 2019-08-26 | MRT-HK-REC-TT-190749 | FA | 0 | TRUE | FALSE | FALSE
9215 | MRT-YT01-P0GN-135237 | 2019-08-26 | MRT-HK-REC-TT-190750 | FI | 0 | TRUE | TRUE | FALSE
9216 | MRT-YT01-P3GC-135134 | 2019-08-26 | MRT-HK-REC-TT-190750 | FI | 0 | TRUE | TRUE | FALSE
9217 | MRT-XS02-P3GC-135116 | 2019-08-26 | MRT-HK-REC-TT-190750 | FA | 1 | TRUE | TRUE | FALSE
9218 | MRT-BT00-P0GEN-135711 | 2019-08-26 | MRT-HK-REC-TT-190751 | FA | 0 | TRUE | FALSE | FALSE
9219 | MRT-YT01-P3GC-135166 | 2019-08-26 | MRT-HK-REC-TT-190752 | FA | 1 | TRUE | TRUE | FALSE
9220 | MRT-XG02-P2PA-110002 | 2019-08-26 | MRT-DS-REC-TT-190187 | FC | 7 | TRUE | TRUE | FALSE
9221 | MRT-XG02-P0PA-110002 | 2019-08-26 | MRT-DS-REC-TT-190187 | FC | 6 | TRUE | TRUE | FALSE
9222 | MRT-XG02-P3PA-110002 | 2019-08-26 | MRT-DS-REC-TT-190187 | FC | 7 | TRUE | TRUE | FALSE
9223 | MRT-DC01-P0ZEN-165036 | 2019-08-26 | MRT-HK-REC-TT-190753 | FA | 0 | TRUE | FALSE | FALSE
9162 | MRT-CC02-P0UMA-171203 | 2019-08-27 | MRT-DS-REC-TT-190174-FC | FC | 1 | TRUE | TRUE | FALSE
9224 | MRT-YT01-P2LB-122096 | 2019-08-27 | MRT-DS-REC-TT-190149-FC | FC | 3 | TRUE | TRUE | FALSE
9225 | MRT-YT01-P3LB-122096 | 2019-08-27 | MRT-DS-REC-TT-190149-FC | FC | 3 | TRUE | TRUE | FALSE
9226 | MRT-CC02-P2UMA-170207 | 2019-08-27 | MRT-DS-REC-TT-190175-FC | FC | 7 | TRUE | TRUE | FALSE
9227 | MRT-CC02-P3UMA-170207 | 2019-08-27 | MRT-DS-REC-TT-190175-FC | FC | 7 | TRUE | TRUE | FALSE
9228 | MRT-CQ02-P2MAA-220201 | 2019-08-27 | MRT-DS-REC-TT-190167-FC | FC | 1 | TRUE | TRUE | FALSE
9229 | MRT-XJ00-P2LBA-142000 | 2019-08-27 | MRT-DS-REC-TT-190170-FC | FC | 2 | TRUE | TRUE | FALSE
9230 | MRT-XJ00-P2LBG-142000 | 2019-08-27 | MRT-DS-REC-TT-190170-FC | FC | 2 | TRUE | TRUE | FALSE
9231 | MRT-XJ00-P2LAB-142000 | 2019-08-27 | MRT-DS-REC-TT-190170-FC | FC | 2 | TRUE | TRUE | FALSE
9232 | MRT-XJ00-P2LCA-142000 | 2019-08-27 | MRT-DS-REC-TT-190170-FC | FC | 2 | TRUE | TRUE | FALSE
9233 | MRT-XJ00-P2PGB-142000 | 2019-08-27 | MRT-DS-REC-TT-190170-FC | FC | 2 | TRUE | TRUE | FALSE
9234 | MRT-XJ00-P2LCM-142000 | 2019-08-27 | MRT-DS-REC-TT-190170-FC | FC | 2 | TRUE | TRUE | FALSE
9235 | MRT-XG02-P0GKC-120001 | 2019-08-27 | MRT-DS-REC-TT-190188 | FC | 5 | TRUE | TRUE | FALSE
9236 | MRT-XG02-P0GHD-120001 | 2019-08-27 | MRT-DS-REC-TT-190188 | FC | 6 | TRUE | TRUE | FALSE
9237 | MRT-XK00-P2GM-128507 | 2019-08-27 | MRT-DS-REC-TT-190188 | FC | 4 | TRUE | TRUE | FALSE
9238 | MRT-XK00-P3GM-128507 | 2019-08-27 | MRT-DS-REC-TT-190188 | FC | 4 | TRUE | TRUE | FALSE
9241 | MRT-YK00-P0GDY-135072 | 2019-08-29 | MRT-HK-REC-TT-190754 | FI | 0 | TRUE | FALSE | FALSE
9239 | MRT-XJ00-P0GHC-140001 | 2019-08-30 | MRT-DS-REC-TT-190161-FC | FC | 1 | TRUE | TRUE | FALSE
9240 | MRT-XJ00-P0LBG-141000 | 2019-08-30 | MRT-DS-REC-TT-190161-FC | FC | 1 | TRUE | TRUE | FALSE
9242 | MRT-BT00-P0SGA-135485 | 2019-08-30 | MRT-HK-REC-TT-190755 | FA | 2 | TRUE | TRUE | FALSE
9243 | MRT-DN04-P0SGA-135478 | 2019-08-30 | MRT-HK-REC-TT-190755 | FA | 1 | TRUE | TRUE | FALSE
9244 | MRT-XJ00-P0QJA-141000 | 2019-08-30 | MRT-DS-REC-TT-190189-FC | FC | 1 | TRUE | TRUE | FALSE
9245 | MRT-XJ00-P0LBG-140000 | 2019-08-30 | MRT-DS-REC-TT-190189-FC | FC | 1 | TRUE | TRUE | FALSE
9246 | MRT-XJ00-P2QC-145000 | 2019-08-30 | MRT-DS-REC-TT-190189-FC | FC | 1 | TRUE | TRUE | FALSE
9247 | MRT-XJ00-P3QC-146000 | 2019-08-30 | MRT-DS-REC-TT-190189-FC | FC | 1 | TRUE | TRUE | FALSE
9248 | MRT-XJ00-P0MKG-141000 | 2019-08-30 | MRT-DS-REC-TT-190189-FC | FC | 1 | TRUE | TRUE | FALSE
9249 | MRT-XK00-P0GHC-140001 | 2019-09-02 | MRT-DS-REC-TT-190154-FC | FC | 0 | TRUE | TRUE | FALSE
9250 | MRT-XK00-P0GHD-140001 | 2019-09-02 | MRT-DS-REC-TT-190154-FC | FC | 0 | TRUE | TRUE | FALSE
9251 | MRT-XK00-P0GMA-140001 | 2019-09-02 | MRT-DS-REC-TT-190154-FC | FC | 0 | TRUE | TRUE | FALSE
9252 | MRT-XK00-P0LBG-141000 | 2019-09-02 | MRT-DS-REC-TT-190154-FC | FC | 0 | TRUE | TRUE | FALSE
9253 | MRT-XK00-P2PGB-142000 | 2019-09-02 | MRT-DS-REC-TT-190147-FC | FC | 0 | TRUE | TRUE | FALSE
9254 | MRT-XK00-P3PGB-143000 | 2019-09-02 | MRT-DS-REC-TT-190147-FC | FC | 0 | TRUE | TRUE | FALSE
9255 | MRT-XK00-P4PGB-144000 | 2019-09-02 | MRT-DS-REC-TT-190147-FC | FC | 0 | TRUE | TRUE | FALSE
9256 | MRT-CN00-P3MKW-210001 | 2019-09-02 | MRT-DS-REC-TT-190163-FC | FC | 0 | TRUE | TRUE | FALSE
9257 | MRT-CN00-P3MKG-210001 | 2019-09-02 | MRT-DS-REC-TT-190163-FC | FC | 0 | TRUE | TRUE | FALSE
9258 | MRT-XJ00-P3LCM-146000 | 2019-09-03 | MRT-DS-REC-TT-190190-FC | FC | 1 | TRUE | TRUE | FALSE
9259 | MRT-XJ00-P3LCM-147000 | 2019-09-03 | MRT-DS-REC-TT-190190-FC | FC | 1 | TRUE | TRUE | FALSE
9260 | MRT-XJ00-P2LCA-145000 | 2019-09-03 | MRT-DS-REC-TT-190190-FC | FC | 1 | TRUE | TRUE | FALSE
9261 | MRT-XG02-P2LBA-110003 | 2019-09-03 | MRT-DS-REC-TT-190191 | FC | 7 | TRUE | TRUE | FALSE
9262 | MRT-XG02-P2LBG-110004 | 2019-09-03 | MRT-DS-REC-TT-190191 | FC | 6 | TRUE | TRUE | FALSE
9263 | MRT-XG02-P0LBG-110004 | 2019-09-03 | MRT-DS-REC-TT-190191 | FC | 6 | TRUE | TRUE | FALSE
9264 | MRT-XG02-P2LCM-110005 | 2019-09-03 | MRT-DS-REC-TT-190191 | FC | 7 | TRUE | TRUE | FALSE
9265 | MRT-XG02-P2LA-110006 | 2019-09-03 | MRT-DS-REC-TT-190191 | FC | 7 | TRUE | TRUE | FALSE
9266 | MRT-XG02-P2LC-110007 | 2019-09-03 | MRT-DS-REC-TT-190191 | FC | 7 | TRUE | TRUE | FALSE
9267 | MRT-XG02-P0GHC-110002 | 2019-09-03 | MRT-DS-REC-TT-190191 | FC | 7 | TRUE | TRUE | FALSE
9268 | MRT-XG02-P3LBA-110003 | 2019-09-03 | MRT-DS-REC-TT-190191 | FC | 7 | TRUE | TRUE | FALSE
9269 | MRT-XG02-P3LBG-110004 | 2019-09-03 | MRT-DS-REC-TT-190191 | FC | 6 | TRUE | TRUE | FALSE
9270 | MRT-XG02-P3LCM-110005 | 2019-09-03 | MRT-DS-REC-TT-190191 | FC | 7 | TRUE | TRUE | FALSE
9271 | MRT-XG02-P3LA-110006 | 2019-09-03 | MRT-DS-REC-TT-190191 | FC | 7 | TRUE | TRUE | FALSE
9272 | MRT-XG02-P3LC-110007 | 2019-09-03 | MRT-DS-REC-TT-190191 | FC | 7 | TRUE | TRUE | FALSE
9273 | MRT-CA03-P0UCA-180132 | 2019-09-04 | MRT-DS-REC-TT-190192 | FC | 6 | TRUE | TRUE | FALSE
9274 | MRT-DN02-P0BAT-150910 | 2019-09-05 | MRT-HK-REC-TT-190756 | FA | 0 | TRUE | FALSE | FALSE
9275 | MRT-DD09-P0ZEN-128216 | 2019-09-05 | MRT-HK-REC-TT-190757 | FA | 1 | TRUE | TRUE | FALSE
9276 | MRT-CA06-P0UQA-186572 | 2019-09-05 | MRT-HK-REC-TT-190758 | FA | 0 | TRUE | FALSE | FALSE
9277 | MRT-CA03-P0UQA-186570 | 2019-09-05 | MRT-HK-REC-TT-190758 | FA | 0 | TRUE | FALSE | FALSE
9278 | MRT-CA03-P0UQA-186571 | 2019-09-05 | MRT-HK-REC-TT-190758 | FA | 0 | TRUE | FALSE | FALSE
9279 | MRT-XJ00-P0GKB-141000 | 2019-09-05 | MRT-DS-REC-TT-190193-FC | FC | 1 | TRUE | TRUE | FALSE
9280 | MRT-XJ00-P3QC-147000 | 2019-09-05 | MRT-DS-REC-TT-190193-FC | FC | 1 | TRUE | TRUE | FALSE
9281 | MRT-XJ00-P2MAA-145000 | 2019-09-05 | MRT-DS-REC-TT-190193-FC | FC | 1 | TRUE | TRUE | FALSE
9282 | MRT-XJ00-P3MAA-146000 | 2019-09-05 | MRT-DS-REC-TT-190193-FC | FC | 1 | TRUE | TRUE | FALSE
9283 | MRT-XJ00-P3MAA-147000 | 2019-09-05 | MRT-DS-REC-TT-190193-FC | FC | 1 | TRUE | TRUE | FALSE
9284 | MRT-QM03-P0ZEN-155037 | 2019-09-06 | MRT-HK-REC-TT-190759 | FA | 0 | TRUE | FALSE | FALSE
9285 | MRT-CH04-P0ABA-150566 | 2019-09-06 | MRT-HK-REC-TT-190759 | FA | 0 | TRUE | FALSE | FALSE
9286 | MRT-QM03-P0ZEN-155035 | 2019-09-06 | MRT-HK-REC-TT-190759 | FA | 1 | TRUE | TRUE | FALSE
9287 | MRT-DN02-P0BBT-150911 | 2019-09-06 | MRT-HK-REC-TT-190760 | FA | 0 | TRUE | FALSE | FALSE
9288 | MRT-DN02-P0BAC-150615 | 2019-09-06 | MRT-HK-REC-TT-190760 | FA | 0 | TRUE | FALSE | FALSE
9289 | MRT-XJ00-P0GMA-141000 | 2019-09-09 | MRT-DS-REC-TT-190194-FC | FC | 1 | TRUE | TRUE | FALSE
9290 | MRT-XJ00-P2MAV-145000 | 2019-09-09 | MRT-DS-REC-TT-190194-FC | FC | 1 | TRUE | TRUE | FALSE
9291 | MRT-CQ02-P3MAA-220202 | 2019-09-09 | MRT-DS-REC-TT-190166-FC | FC | 0 | TRUE | TRUE | FALSE
9292 | MRT-DM02-P3MAA-220193 | 2019-09-09 | MRT-DS-REC-TT-190166-FC | FC | 0 | TRUE | TRUE | FALSE
9293 | MRT-DN02-P0ABA-150905 | 2019-09-09 | MRT-HK-REC-TT-190761 | FA | 0 | TRUE | FALSE | FALSE
9294 | MRT-DN02-P0ABA-150904 | 2019-09-09 | MRT-HK-REC-TT-190761 | FA | 0 | TRUE | FALSE | FALSE
9295 | MRT-DN02-P0ABA-150903 | 2019-09-09 | MRT-HK-REC-TT-190761 | FA | 0 | TRUE | FALSE | FALSE
9296 | MRT-DN02-P0ABA-150902 | 2019-09-09 | MRT-HK-REC-TT-190761 | FA | 0 | TRUE | FALSE | FALSE
9297 | MRT-DN02-P0ABA-150901 | 2019-09-09 | MRT-HK-REC-TT-190761 | FA | 0 | TRUE | FALSE | FALSE
9298 | MRT-DN02-P0ABA-150900 | 2019-09-09 | MRT-HK-REC-TT-190761 | FA | 0 | TRUE | FALSE | FALSE
9299 | MRT-DN02-P0ABA-150899 | 2019-09-09 | MRT-HK-REC-TT-190761 | FA | 0 | TRUE | FALSE | FALSE
9300 | MRT-DN02-P0ABA-150898 | 2019-09-09 | MRT-HK-REC-TT-190761 | FA | 0 | TRUE | FALSE | FALSE
9301 | MRT-YR01-P0GEN-135323 | 2019-09-09 | MRT-HK-REC-TT-190762 | FA | 1 | TRUE | TRUE | FALSE
9302 | MRT-DS00-P0GN-135864 | 2019-09-09 | MRT-HK-REC-TT-190762 | FI | 0 | TRUE | FALSE | FALSE
9303 | MRT-YT01-P0GN-135226 | 2019-09-09 | MRT-HK-REC-TT-190762 | FA | 0 | TRUE | FALSE | FALSE
9304 | MRT-DS00-P0GN-135867 | 2019-09-09 | MRT-HK-REC-TT-190762 | FI | 0 | TRUE | FALSE | FALSE
9305 | MRT-DS00-P0GN-135861 | 2019-09-09 | MRT-HK-REC-TT-190762 | FI | 0 | TRUE | FALSE | FALSE
9306 | MRT-DS00-P0GN-135863 | 2019-09-09 | MRT-HK-REC-TT-190762 | FI | 0 | TRUE | FALSE | FALSE
9307 | MRT-YT01-P3GC-135186 | 2019-09-09 | MRT-HK-REC-TT-190762 | FA | 0 | TRUE | FALSE | FALSE
9308 | MRT-YT01-P3GC-135135 | 2019-09-09 | MRT-HK-REC-TT-190762 | FA | 0 | TRUE | FALSE | FALSE
9309 | MRT-DS00-P3GC-135847 | 2019-09-09 | MRT-HK-REC-TT-190762 | FI | 0 | TRUE | FALSE | FALSE
9310 | MRT-DD04-P0GEN-135390 | 2019-09-09 | MRT-HK-REC-TT-190762 | FA | 0 | TRUE | FALSE | FALSE
9311 | MRT-YT01-P0GEN-135359 | 2019-09-09 | MRT-HK-REC-TT-190762 | FA | 0 | TRUE | FALSE | FALSE
9312 | MRT-BT00-P0GEN-135886 | 2019-09-09 | MRT-HK-REC-TT-190762 | FA | 0 | TRUE | FALSE | FALSE
9313 | MRT-YV02-P0GEN-135379 | 2019-09-09 | MRT-HK-REC-TT-190762 | FA | 0 | TRUE | FALSE | FALSE
9314 | MRT-FF03-P0SGE-135412 | 2019-09-09 | MRT-HK-REC-TT-190763 | FA | 0 | TRUE | FALSE | FALSE
9315 | MRT-FF01-P0SGJ-135452 | 2019-09-09 | MRT-HK-REC-TT-190763 | FA | 0 | TRUE | FALSE | FALSE
9316 | MRT-FF01-P0SGA-135434 | 2019-09-09 | MRT-HK-REC-TT-190764 | FA | 0 | TRUE | FALSE | FALSE
9317 | MRT-XG02-P3SGC-135418 | 2019-09-09 | MRT-HK-REC-TT-190764 | FA | 0 | TRUE | FALSE | FALSE
9318 | MRT-XG02-P3SGC-135415 | 2019-09-09 | MRT-HK-REC-TT-190764 | FA | 0 | TRUE | FALSE | FALSE
9319 | MRT-XG02-P2SGC-135417 | 2019-09-09 | MRT-HK-REC-TT-190764 | FA | 0 | TRUE | FALSE | FALSE
9320 | MRT-FF03-P3SGC-135419 | 2019-09-09 | MRT-HK-REC-TT-190765 | FA | 0 | TRUE | FALSE | FALSE
9321 | MRT-FF03-P3SGC-135418 | 2019-09-09 | MRT-HK-REC-TT-190765 | FA | 0 | TRUE | FALSE | FALSE
9322 | MRT-FF03-P0SGF-135421 | 2019-09-09 | MRT-HK-REC-TT-190765 | FA | 0 | TRUE | FALSE | FALSE
9323 | MRT-FF03-P0SGE-135409 | 2019-09-09 | MRT-HK-REC-TT-190765 | FA | 0 | TRUE | FALSE | FALSE
9324 | MRT-FF01-P0SGJ-135443 | 2019-09-09 | MRT-HK-REC-TT-190765 | FA | 0 | TRUE | FALSE | FALSE
9325 | MRT-FF01-P0SGA-135436 | 2019-09-09 | MRT-HK-REC-TT-190765 | FA | 0 | TRUE | FALSE | FALSE
9326 | MRT-XG02-P0SGF-135422 | 2019-09-09 | MRT-HK-REC-TT-190768 | FA | 0 | TRUE | FALSE | FALSE
9327 | MRT-FF03-P2SGC-135417 | 2019-09-09 | MRT-HK-REC-TT-190768 | FA | 0 | TRUE | FALSE | FALSE
9328 | MRT-YK10-P0LAA-125456 | 2019-09-09 | MRT-HK-REC-TT-190767 | FA | 1 | TRUE | FALSE | FALSE
9329 | MRT-FF01-P0SGA-135433 | 2019-09-09 | MRT-HK-REC-TT-190769 | FA | 0 | TRUE | FALSE | FALSE
9330 | MRT-FF03-P0SGE-135408 | 2019-09-09 | MRT-HK-REC-TT-190769 | FA | 0 | TRUE | FALSE | FALSE
9331 | MRT-FF03-P0SGF-135422 | 2019-09-09 | MRT-HK-REC-TT-190769 | FA | 0 | TRUE | FALSE | FALSE
9332 | MRT-DS00-P3GC-135844 | 2019-09-09 | MRT-HK-REC-TT-190770 | FI | 0 | TRUE | FALSE | FALSE
9333 | MRT-DS00-P0GN-135862 | 2019-09-09 | MRT-HK-REC-TT-190770 | FI | 0 | TRUE | FALSE | FALSE
9334 | MRT-DN03-P0GN-135290 | 2019-09-09 | MRT-HK-REC-TT-190770 | FA | 2 | TRUE | TRUE | FALSE
9335 | MRT-XG02-P3SGC-135417 | 2019-09-09 | MRT-HK-REC-TT-190771 | FA | 0 | TRUE | FALSE | FALSE
9336 | MRT-FF03-P3SGC-135415 | 2019-09-09 | MRT-HK-REC-TT-190771 | FA | 0 | TRUE | FALSE | FALSE
9337 | MRT-FF01-P0SGJ-135457 | 2019-09-09 | MRT-HK-REC-TT-190771 | FA | 0 | TRUE | FALSE | FALSE
9338 | MRT-QM00-P0SA-135775 | 2019-09-09 | MRT-HK-REC-TT-190772 | FA | 0 | TRUE | FALSE | FALSE
9339 | MRT-DM01-P0SA-135735 | 2019-09-09 | MRT-HK-REC-TT-190772 | FA | 0 | TRUE | FALSE | FALSE
9340 | MRT-DM01-P0SA-135734 | 2019-09-09 | MRT-HK-REC-TT-190772 | FA | 0 | TRUE | FALSE | FALSE
9341 | MRT-YK10-P0QHA-125445 | 2019-09-09 | MRT-HK-REC-TT-190766 | FA | 1 | TRUE | TRUE | FALSE
9342 | MRT-YD08-P0QHY-125498 | 2019-09-09 | MRT-HK-REC-TT-190773 | FA | 0 | TRUE | FALSE | FALSE
9343 | MRT-YD08-P0QHY-125493 | 2019-09-09 | MRT-HK-REC-TT-190773 | FA | 0 | TRUE | FALSE | FALSE
9344 | MRT-YD08-P0QHY-125492 | 2019-09-09 | MRT-HK-REC-TT-190773 | FA | 0 | TRUE | FALSE | FALSE
9345 | MRT-CQ02-P0GDG-135083 | 2019-09-09 | MRT-HK-REC-TT-190774 | FI | 0 | TRUE | FALSE | FALSE
10625 | MRT-YU01-P3GC-135150 | 2019-09-09 | MRT-HK-REC-TT-190781 | FA | 0 | TRUE | FALSE | FALSE
9346 | MRT-BN00-P0EKF-125632 | 2019-09-10 | MRT-HK-REC-TT-190775 | FA | 1 | TRUE | TRUE | FALSE
9347 | MRT-YT01-P3GC-135163 | 2019-09-10 | MRT-HK-REC-TT-190776 | FA | 0 | TRUE | FALSE | FALSE
9348 | MRT-YT01-P3GC-135165 | 2019-09-10 | MRT-HK-REC-TT-190776 | FA | 0 | TRUE | FALSE | FALSE
9349 | MRT-FF01-P0SGA-135488 | 2019-09-10 | MRT-HK-REC-TT-190778 | FA | 0 | TRUE | FALSE | FALSE
9350 | MRT-DN03-P3GC-135191 | 2019-09-10 | MRT-HK-REC-TT-190779 | FA | 1 | TRUE | TRUE | FALSE
9351 | MRT-DS00-P3GC-135851 | 2019-09-10 | MRT-HK-REC-TT-190780 | FA | 0 | TRUE | FALSE | FALSE
9352 | MRT-FF01-P0SGA-135489 | 2019-09-10 | MRT-HK-REC-TT-190781 | FA | 0 | TRUE | FALSE | FALSE
9353 | MRT-US02-P0BFB-150706 | 2019-09-10 | MRT-HK-REC-TT-190783 | FA | 1 | TRUE | TRUE | FALSE
9354 | MRT-YU02-P0BFB-150705 | 2019-09-10 | MRT-HK-REC-TT-190783 | FA | 1 | TRUE | TRUE | FALSE
9355 | MRT-XJ00-P3LCA-146000 | 2019-09-10 | MRT-DS-REC-TT-190195-FC | FC | 1 | TRUE | TRUE | FALSE
9356 | MRT-XJ00-P3LCA-147000 | 2019-09-10 | MRT-DS-REC-TT-190195-FC | FC | 1 | TRUE | TRUE | FALSE
9357 | MRT-XJ00-P3PGB-146000 | 2019-09-10 | MRT-DS-REC-TT-190195-FC | FC | 1 | TRUE | TRUE | FALSE
9358 | MRT-XJ00-P3PGB-147000 | 2019-09-10 | MRT-DS-REC-TT-190195-FC | FC | 1 | TRUE | TRUE | FALSE
9359 | MRT-XJ00-P3MAV-146000 | 2019-09-10 | MRT-DS-REC-TT-190195-FC | FC | 1 | TRUE | TRUE | FALSE
9360 | MRT-XJ00-P3MAV-147000 | 2019-09-10 | MRT-DS-REC-TT-190195-FC | FC | 1 | TRUE | TRUE | FALSE
9361 | MRT-QM00-P0SA-135770 | 2019-09-10 | MRT-HK-REC-TT-190782 | FA | 0 | TRUE | FALSE | FALSE
9362 | MRT-QM00-P0SA-135769 | 2019-09-10 | MRT-HK-REC-TT-190782 | FA | 0 | TRUE | FALSE | FALSE
9363 | MRT-CA03-P0UCA-180132 | 2019-09-11 | MRT-DS-REC-TT-190192-FC | FC | 6 | TRUE | TRUE | FALSE
9364 | MRT-CN00-P0PBB-135268 | 2019-09-11 | MRT-HK-REC-TT-190784 | FA | 0 | TRUE | FALSE | FALSE
9365 | MRT-CT00-P2PAC-130001 | 2019-09-11 | MRT-HK-REC-TT-190784 | FA | 0 | TRUE | FALSE | FALSE
9366 | MRT-YL00-P0GN-135267 | 2019-09-11 | MRT-HK-REC-TT-190785 | FA | 1 | TRUE | TRUE | FALSE
9367 | MRT-DN02-P0MJA-150916 | 2019-09-11 | MRT-HK-REC-TT-190786 | FA | 0 | TRUE | FALSE | FALSE
9368 | MRT-XJ00-P2PGB-145000 | 2019-09-11 | MRT-DS-REC-TT-190169-FC | FC | 1 | TRUE | TRUE | FALSE
9369 | MRT-XJ00-P2PAB-145000 | 2019-09-11 | MRT-DS-REC-TT-190171-FC | FC | 1 | TRUE | TRUE | FALSE
9370 | MRT-XJ00-P3PAB-146000 | 2019-09-11 | MRT-DS-REC-TT-190171-FC | FC | 1 | TRUE | TRUE | FALSE
9371 | MRT-XJ00-P2PAB-145100 | 2019-09-11 | MRT-DS-REC-TT-190171-FC | FC | 1 | TRUE | TRUE | FALSE
9372 | MRT-XJ00-P3PAB-146100 | 2019-09-11 | MRT-DS-REC-TT-190171-FC | FC | 1 | TRUE | TRUE | FALSE
9373 | MRT-XJ00-P3PAB-147100 | 2019-09-11 | MRT-DS-REC-TT-190171-FC | FC | 1 | TRUE | TRUE | FALSE
9374 | MRT-XJ00-P2PAB-140001 | 2019-09-11 | MRT-DS-REC-TT-190172-FC | FC | 4 | TRUE | TRUE | FALSE
9375 | MRT-XJ00-P3PAB-140001 | 2019-09-11 | MRT-DS-REC-TT-190172-FC | FC | 4 | TRUE | TRUE | FALSE
9376 | MRT-XJ00-P2PAB-142100 | 2019-09-11 | MRT-DS-REC-TT-190172-FC | FC | 3 | TRUE | TRUE | FALSE
9377 | MRT-XJ00-P3PAB-143100 | 2019-09-11 | MRT-DS-REC-TT-190172-FC | FC | 3 | TRUE | TRUE | FALSE
9378 | MRT-XJ00-P3PAB-144100 | 2019-09-11 | MRT-DS-REC-TT-190172-FC | FC | 3 | TRUE | TRUE | FALSE
9379 | MRT-XJ00-P2PAB-142200 | 2019-09-11 | MRT-DS-REC-TT-190172-FC | FC | 1 | TRUE | TRUE | FALSE
9380 | MRT-XJ00-P3PAB-143200 | 2019-09-11 | MRT-DS-REC-TT-190172-FC | FC | 1 | TRUE | TRUE | FALSE
9381 | MRT-XJ00-P3PAB-144200 | 2019-09-11 | MRT-DS-REC-TT-190172-FC | FC | 1 | TRUE | TRUE | FALSE
9382 | MRT-HM01-P0SAH-135561 | 2019-09-11 | MRT-HK-REC-TT-190787 | FA | 1 | TRUE | TRUE | FALSE
9383 | MRT-XG02-P0GKC-120001 | 2019-09-16 | MRT-DS-REC-TT-190188-FC | FC | 5 | TRUE | TRUE | FALSE
9384 | MRT-XG02-P0GHD-120001 | 2019-09-16 | MRT-DS-REC-TT-190188-FC | FC | 6 | TRUE | TRUE | FALSE
9385 | MRT-XK00-P2GM-128507 | 2019-09-16 | MRT-DS-REC-TT-190188-FC | FC | 4 | TRUE | TRUE | FALSE
9386 | MRT-XK00-P3GM-128507 | 2019-09-16 | MRT-DS-REC-TT-190188-FC | FC | 4 | TRUE | TRUE | FALSE
9387 | MRT-XJ00-P0GHD-141000 | 2019-09-16 | MRT-DS-REC-TT-190196-FC | FC | 1 | TRUE | TRUE | FALSE
9388 | MRT-XJ00-P3QU-147000 | 2019-09-16 | MRT-DS-REC-TT-190196-FC | FC | 1 | TRUE | TRUE | FALSE
9389 | MRT-XJ00-P2SCA-145000 | 2019-09-16 | MRT-DS-REC-TT-190196-FC | FC | 1 | TRUE | TRUE | FALSE
9390 | MRT-XJ00-P3SCA-146000 | 2019-09-16 | MRT-DS-REC-TT-190196-FC | FC | 1 | TRUE | TRUE | FALSE
9391 | MRT-XJ00-P3SCA-147000 | 2019-09-16 | MRT-DS-REC-TT-190196-FC | FC | 1 | TRUE | TRUE | FALSE
9392 | MRT-XJ00-P2QFB-145000 | 2019-09-16 | MRT-DS-REC-TT-190196-FC | FC | 1 | TRUE | TRUE | FALSE
9393 | MRT-XJ00-P3QFB-146000 | 2019-09-16 | MRT-DS-REC-TT-190196-FC | FC | 1 | TRUE | TRUE | FALSE
9394 | MRT-XJ00-P3QFB-147000 | 2019-09-16 | MRT-DS-REC-TT-190196-FC | FC | 1 | TRUE | TRUE | FALSE
9395 | MRT-XJ00-P2SCB-145000 | 2019-09-16 | MRT-DS-REC-TT-190196-FC | FC | 1 | TRUE | TRUE | FALSE
9396 | MRT-XJ00-P3SCB-146000 | 2019-09-16 | MRT-DS-REC-TT-190196-FC | FC | 1 | TRUE | TRUE | FALSE
9397 | MRT-XJ00-P3SCB-147000 | 2019-09-16 | MRT-DS-REC-TT-190196-FC | FC | 1 | TRUE | TRUE | FALSE
9398 | MRT-QM01-P0GHE-145070 | 2019-09-16 | MRT-HK-REC-TT-190788 | FA | 1 | TRUE | TRUE | FALSE
9399 | MRT-QM03-P0GHE-145063 | 2019-09-16 | MRT-HK-REC-TT-190788 | FA | 1 | TRUE | TRUE | FALSE
9400 | MRT-XM01-P0PBB-135265 | 2019-09-16 | MRT-HK-REC-TT-190789 | FA | 0 | TRUE | FALSE | FALSE
9401 | MRT-XA01-P0ABA-150614 | 2019-09-16 | MRT-HK-REC-TT-190790 | FA | 0 | TRUE | FALSE | FALSE
9402 | MRT-DN02-P0ABA-150907 | 2019-09-16 | MRT-HK-REC-TT-190790 | FA | 0 | TRUE | FALSE | FALSE
9403 | MRT-HM02-P0SAL-135594 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9404 | MRT-HM02-P0SAH-135588 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9405 | MRT-HM02-P0SAC-135587 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9406 | MRT-HM02-P0SAG-135527 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9407 | MRT-HM02-P0SAK-135590 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9408 | MRT-HM02-P0SAK-135591 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9409 | MRT-HM02-P0SAF-135592 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9410 | MRT-HM02-P0SA-135593 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9411 | MRT-HM02-P0SAF-135595 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9412 | MRT-HM02-P0SA-135596 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9413 | MRT-HM02-P0SA-135597 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9414 | MRT-HM02-P0SAE-135598 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9415 | MRT-HM02-P0SA-135599 | 2019-09-16 | MRT-HK-REC-TT-190791 | FA | 0 | TRUE | TRUE | FALSE
9416 | MRT-DS00-P3GC-135845 | 2019-09-16 | MRT-HK-REC-TT-190792 | FI | 0 | TRUE | FALSE | FALSE
9417 | MRT-XS02-P0GN-135216 | 2019-09-16 | MRT-HK-REC-TT-190792 | FA | 0 | TRUE | FALSE | FALSE
9418 | MRT-XS00-P3GC-135100 | 2019-09-16 | MRT-HK-REC-TT-190792 | FA | 3 | TRUE | TRUE | FALSE
9419 | MRT-XS00-P0GN-135200 | 2019-09-16 | MRT-HK-REC-TT-190792 | FA | 3 | TRUE | TRUE | FALSE
9420 | MRT-DD03-P0GEN-135387 | 2019-09-16 | MRT-HK-REC-TT-190792 | FA | 1 | TRUE | TRUE | FALSE
9421 | MRT-YD08-P0GN-135273 | 2019-09-16 | MRT-HK-REC-TT-190793 | FA | 1 | TRUE | TRUE | FALSE
9422 | MRT-XL00-P0ZEN-150278 | 2019-09-16 | MRT-HK-REC-TT-190795 | FA | 0 | TRUE | FALSE | FALSE
9423 | MRT-YT01-P0PUR-150997 | 2019-09-16 | MRT-HK-REC-TT-190795 | FA | 0 | TRUE | FALSE | FALSE
9424 | MRT-YL00-P0ZEN-150993 | 2019-09-16 | MRT-HK-REC-TT-190795 | FA | 0 | TRUE | FALSE | FALSE
9425 | MRT-YK09-P0PUR-150965 | 2019-09-16 | MRT-HK-REC-TT-190795 | FA | 1 | TRUE | TRUE | FALSE
9426 | MRT-YK09-P0PUR-150967 | 2019-09-16 | MRT-HK-REC-TT-190795 | FA | 1 | TRUE | TRUE | FALSE
9427 | MRT-US02-P0PUR-150996 | 2019-09-16 | MRT-HK-REC-TT-190795 | FA | 1 | TRUE | TRUE | FALSE
9428 | MRT-DS00-P0ZEN-150272 | 2019-09-16 | MRT-HK-REC-TT-190795 | FA | 0 | TRUE | FALSE | FALSE
9429 | MRT-YL15-P0GEN-135369 | 2019-09-16 | MRT-HK-REC-TT-190796 | FA | 0 | TRUE | FALSE | FALSE
9430 | MRT-DN03-P0GEN-135884 | 2019-09-16 | MRT-HK-REC-TT-190796 | FA | 0 | TRUE | FALSE | FALSE
9431 | MRT-BT00-P0GEN-135887 | 2019-09-16 | MRT-HK-REC-TT-190797 | FA | 0 | TRUE | FALSE | FALSE
9432 | MRT-DS00-P0ZEN-175022 | 2019-09-17 | MRT-HK-REC-TT-190777 | FA | 0 | TRUE | FALSE | FALSE
9433 | MRT-XG02-P2LBA-110003 | 2019-09-19 | MRT-DS-REC-TT-190191-FC | FC | 7 | TRUE | TRUE | FALSE
9434 | MRT-XG02-P2LBG-110004 | 2019-09-19 | MRT-DS-REC-TT-190191-FC | FC | 6 | TRUE | TRUE | FALSE
9435 | MRT-XG02-P0LBG-110004 | 2019-09-19 | MRT-DS-REC-TT-190191-FC | FC | 6 | TRUE | TRUE | FALSE
9436 | MRT-XG02-P2LCM-110005 | 2019-09-19 | MRT-DS-REC-TT-190191-FC | FC | 7 | TRUE | TRUE | FALSE
9437 | MRT-XG02-P2LA-110006 | 2019-09-19 | MRT-DS-REC-TT-190191-FC | FC | 7 | TRUE | TRUE | FALSE
9438 | MRT-XG02-P2LC-110007 | 2019-09-19 | MRT-DS-REC-TT-190191-FC | FC | 7 | TRUE | TRUE | FALSE
9439 | MRT-XG02-P0GHC-110002 | 2019-09-19 | MRT-DS-REC-TT-190191-FC | FC | 7 | TRUE | TRUE | FALSE
9440 | MRT-XG02-P3LBA-110003 | 2019-09-19 | MRT-DS-REC-TT-190191-FC | FC | 7 | TRUE | TRUE | FALSE
9441 | MRT-XG02-P3LBG-110004 | 2019-09-19 | MRT-DS-REC-TT-190191-FC | FC | 6 | TRUE | TRUE | FALSE
9442 | MRT-XG02-P3LCM-110005 | 2019-09-19 | MRT-DS-REC-TT-190191-FC | FC | 7 | TRUE | TRUE | FALSE
9443 | MRT-XG02-P3LA-110006 | 2019-09-19 | MRT-DS-REC-TT-190191-FC | FC | 7 | TRUE | TRUE | FALSE
9444 | MRT-XG02-P3LC-110007 | 2019-09-19 | MRT-DS-REC-TT-190191-FC | FC | 7 | TRUE | TRUE | FALSE
9445 | MRT-DD09-P0ZEN-128202 | 2019-09-19 | MRT-HK-REC-TT-190798 | FA | 2 | TRUE | TRUE | FALSE
9446 | MRT-YD00-P3ZEN-113300 | 2019-09-19 | MRT-DS-REC-TT-190182-FC | FC | 3 | TRUE | TRUE | FALSE
9447 | MRT-YT01-P3ZEN-113301 | 2019-09-19 | MRT-DS-REC-TT-190182-FC | FC | 3 | TRUE | TRUE | FALSE
9448 | MRT-XG02-P2PA-110002 | 2019-09-19 | MRT-DS-REC-TT-190187-FC | FC | 7 | TRUE | TRUE | FALSE
9449 | MRT-XG02-P0PA-110002 | 2019-09-19 | MRT-DS-REC-TT-190187-FC | FC | 6 | TRUE | TRUE | FALSE
9450 | MRT-XG02-P3PA-110002 | 2019-09-19 | MRT-DS-REC-TT-190187-FC | FC | 7 | TRUE | TRUE | FALSE
9451 | MRT-DN02-P0BTA-150917 | 2019-09-23 | MRT-HK-REC-TT-190799 | FA | 0 | TRUE | FALSE | FALSE
9452 | MRT-DN02-P0BFA-150914 | 2019-09-23 | MRT-HK-REC-TT-190799 | FA | 0 | TRUE | FALSE | FALSE
9453 | MRT-DN02-P0BBA-150913 | 2019-09-23 | MRT-HK-REC-TT-190799 | FA | 0 | TRUE | FALSE | FALSE
9454 | MRT-DN02-P0BFT-150912 | 2019-09-23 | MRT-HK-REC-TT-190799 | FA | 0 | TRUE | FALSE | FALSE
9455 | MRT-DN04-P0GEN-135890 | 2019-09-25 | MRT-HK-REC-TT-190800 | FA | 0 | TRUE | FALSE | FALSE
9456 | MRT-QM03-P2PAC-130001 | 2019-09-25 | MRT-HK-REC-TT-190800 | FA | 1 | TRUE | TRUE | FALSE
9457 | MRT-HM01-P0SAC-135533 | 2019-09-25 | MRT-HK-REC-TT-190801 | FA | 0 | TRUE | FALSE | FALSE
9458 | MRT-DP00-P0SA-135741 | 2019-09-25 | MRT-HK-REC-TT-190801 | FA | 0 | TRUE | FALSE | FALSE
9459 | MRT-HM01-P0SA-135542 | 2019-09-25 | MRT-HK-REC-TT-190801 | FA | 0 | TRUE | FALSE | FALSE
9460 | MRT-HM01-P0SA-135543 | 2019-09-25 | MRT-HK-REC-TT-190801 | FA | 0 | TRUE | FALSE | FALSE
9461 | MRT-HM01-P0SA-135545 | 2019-09-25 | MRT-HK-REC-TT-190801 | FA | 0 | TRUE | FALSE | FALSE
9462 | MRT-HM01-P0SAF-135538 | 2019-09-25 | MRT-HK-REC-TT-190801 | FA | 0 | TRUE | FALSE | FALSE
9463 | MRT-HM01-P0SAG-135535 | 2019-09-25 | MRT-HK-REC-TT-190801 | FA | 0 | TRUE | FALSE | FALSE
9464 | MRT-HM01-P0SAK-135537 | 2019-09-25 | MRT-HK-REC-TT-190801 | FA | 0 | TRUE | FALSE | FALSE
9465 | MRT-HM01-P0SAL-135540 | 2019-09-25 | MRT-HK-REC-TT-190801 | FA | 0 | TRUE | FALSE | FALSE
9466 | MRT-QM03-P0GHE-145061 | 2019-09-26 | MRT-HK-REC-TT-190803 | FA | 1 | TRUE | TRUE | FALSE
9467 | MRT-XA01-P0ABA-150613 | 2019-09-26 | MRT-HK-REC-TT-190802 | FI | 0 | TRUE | FALSE | FALSE
9468 | MRT-US02-P0BMA-150716 | 2019-09-26 | MRT-HK-REC-TT-190802 | FA | 1 | TRUE | TRUE | FALSE
9469 | MRT-YU02-P0BMA-150715 | 2019-09-26 | MRT-HK-REC-TT-190802 | FA | 1 | TRUE | TRUE | FALSE
9470 | MRT-CA03-P0UCA-180132 | 2019-09-26 | MRT-DS-REC-TT-190197 | FC | 7 | TRUE | TRUE | FALSE
9471 | MRT-HM02-P0SAC-135548 | 2019-09-26 | MRT-HK-REC-TT-190804 | FA | 0 | TRUE | FALSE | FALSE
9472 | MRT-YT01-P0GN-135254 | 2019-09-27 | MRT-HK-REC-TT-190805 | FA | 0 | TRUE | FALSE | FALSE
9473 | MRT-XJ00-P2PAB-140001 | 2019-09-27 | MRT-DS-REC-TT-190198-FC | FC | 4A | TRUE | TRUE | FALSE
9474 | MRT-XJ00-P2PAB-142100 | 2019-09-27 | MRT-DS-REC-TT-190198-FC | FC | 3A | TRUE | TRUE | FALSE
9475 | MRT-BT00-P0GEN-135712 | 2019-09-30 | MRT-HK-REC-TT-190807 | FA | 0 | TRUE | FALSE | FALSE
9476 | MRT-DD04-P0SMU-125051 | 2019-09-30 | MRT-HK-REC-TT-190807 | FA | 0 | TRUE | FALSE | FALSE
9477 | MRT-DD04-P0SMU-125037 | 2019-09-30 | MRT-HK-REC-TT-190807 | FI | 0 | TRUE | FALSE | FALSE
9478 | MRT-CC05-P0SMU-125049 | 2019-09-30 | MRT-HK-REC-TT-190807 | FA | 0 | TRUE | FALSE | FALSE
9479 | MRT-DS00-P0GN-135870 | 2019-09-30 | MRT-HK-REC-TT-190807 | FI | 0 | TRUE | FALSE | FALSE
9480 | MRT-DS00-P3GC-135850 | 2019-09-30 | MRT-HK-REC-TT-190807 | FI | 0 | TRUE | FALSE | FALSE
9481 | MRT-DS00-P3GC-135841 | 2019-09-30 | MRT-HK-REC-TT-190807 | FI | 1 | TRUE | FALSE | FALSE
9482 | MRT-QE02-P0PBB-135249 | 2019-09-30 | MRT-HK-REC-TT-190806 | FI | 0 | TRUE | FALSE | FALSE
9483 | MRT-US02-P0BFD-150700 | 2019-09-30 | MRT-HK-REC-TT-190808 | FA | 1 | TRUE | TRUE | FALSE
9484 | MRT-YU02-P0BFD-150699 | 2019-09-30 | MRT-HK-REC-TT-190808 | FA | 1 | TRUE | TRUE | FALSE
9485 | MRT-YR05-P0GDY-135065 | 2019-09-30 | MRT-HK-REC-TT-190809 | FI | 1 | TRUE | TRUE | FALSE
9486 | MRT-XK00-P0GDY-135062 | 2019-09-30 | MRT-HK-REC-TT-190809 | FI | 0 | TRUE | TRUE | FALSE
9487 | MRT-YL01-P0QHY-125417 | 2019-09-30 | MRT-HK-REC-TT-190810 | FI | 0 | TRUE | FALSE | FALSE
9488 | MRT-YF00-P0QHY-125474 | 2019-09-30 | MRT-HK-REC-TT-190810 | FI | 0 | TRUE | FALSE | FALSE
9489 | MRT-YD08-P0QHY-125489 | 2019-09-30 | MRT-HK-REC-TT-190810 | FA | 0 | TRUE | FALSE | FALSE
9490 | MRT-BT00-P0GEN-135888 | 2019-09-30 | MRT-HK-REC-TT-190810 | FA | 0 | TRUE | FALSE | FALSE
9491 | MRT-YF00-P0GN-135265 | 2019-09-30 | MRT-HK-REC-TT-190810 | FI | 0 | TRUE | FALSE | FALSE
9492 | MRT-XH01-P2LB-122025 | 2019-09-30 | MRT-DS-REC-TT-190200-FC | FC | 3 | TRUE | TRUE | FALSE
9493 | MRT-XH01-P3LB-122025 | 2019-09-30 | MRT-DS-REC-TT-190200-FC | FC | 3 | TRUE | TRUE | FALSE
9494 | MRT-XJ00-P2LB-122027 | 2019-09-30 | MRT-DS-REC-TT-190202-FC | FC | 5 | TRUE | TRUE | FALSE
9495 | MRT-XJ00-P3LB-122027 | 2019-09-30 | MRT-DS-REC-TT-190202-FC | FC | 5 | TRUE | TRUE | FALSE
9496 | MRT-XJ00-P2LB-122028 | 2019-09-30 | MRT-DS-REC-TT-190203-FC | FC | 6 | TRUE | TRUE | FALSE
9497 | MRT-XJ00-P3LB-122028 | 2019-09-30 | MRT-DS-REC-TT-190203-FC | FC | 6 | TRUE | TRUE | FALSE
9498 | MRT-VN03-P2LB-122015 | 2019-09-30 | MRT-DS-REC-TT-190199-FC | FC | 7 | TRUE | TRUE | FALSE
9499 | MRT-VN03-P3LB-122015 | 2019-09-30 | MRT-DS-REC-TT-190199-FC | FC | 7 | TRUE | TRUE | FALSE
9500 | MRT-CA06-P0UVH-187054 | 2019-10-01 | MRT-HK-REC-TT-190811 | FA | 2 | TRUE | TRUE | FALSE
9501 | MRT-CA01-P0UVH-187066 | 2019-10-01 | MRT-HK-REC-TT-190811 | FA | 2 | TRUE | TRUE | FALSE
9502 | MRT-CA02-P0UVH-187068 | 2019-10-01 | MRT-HK-REC-TT-190811 | FA | 2 | TRUE | TRUE | FALSE
9503 | MRT-CC05-P0SMU-125012 | 2019-10-01 | MRT-HK-REC-TT-190812 | FI | 0 | TRUE | FALSE | FALSE
9504 | MRT-YT01-P0SMU-125027 | 2019-10-01 | MRT-HK-REC-TT-190812 | FI | 0 | TRUE | FALSE | FALSE
9505 | MRT-YT01-P0SMU-125023 | 2019-10-01 | MRT-HK-REC-TT-190812 | FI | 0 | TRUE | FALSE | FALSE
9506 | MRT-YL16-P0SMU-125029 | 2019-10-01 | MRT-HK-REC-TT-190812 | FI | 0 | TRUE | FALSE | FALSE
9507 | MRT-YL15-P0SMU-125028 | 2019-10-01 | MRT-HK-REC-TT-190812 | FI | 0 | TRUE | FALSE | FALSE
9508 | MRT-YT01-P0SMU-125022 | 2019-10-01 | MRT-HK-REC-TT-190812 | FI | 0 | TRUE | FALSE | FALSE
9509 | MRT-CC05-P0SMU-125019 | 2019-10-01 | MRT-HK-REC-TT-190812 | FI | 0 | TRUE | FALSE | FALSE
9510 | MRT-CC05-P0SMU-125050 | 2019-10-01 | MRT-HK-REC-TT-190812 | FI | 0 | TRUE | FALSE | FALSE
9511 | MRT-CC05-P0SMU-125020 | 2019-10-01 | MRT-HK-REC-TT-190812 | FI | 0 | TRUE | FALSE | FALSE
9512 | MRT-CC05-P0SMU-125021 | 2019-10-01 | MRT-HK-REC-TT-190812 | FI | 0 | TRUE | FALSE | FALSE
9513 | MRT-YF00-P3GC-135189 | 2019-10-02 | MRT-HK-REC-TT-190813 | FA | 0 | TRUE | FALSE | FALSE
9514 | MRT-YF00-P0GN-135283 | 2019-10-02 | MRT-HK-REC-TT-190813 | FA | 0 | TRUE | FALSE | FALSE
9515 | MRT-YT01-P0GN-135222 | 2019-10-02 | MRT-HK-REC-TT-190814 | FI | 0 | TRUE | FALSE | FALSE
9516 | MRT-YT01-P3GC-135123 | 2019-10-02 | MRT-HK-REC-TT-190814 | FI | 0 | TRUE | FALSE | FALSE
9517 | MRT-YT01-P3GC-135122 | 2019-10-02 | MRT-HK-REC-TT-190814 | FI | 0 | TRUE | FALSE | FALSE
9518 | MRT-YT01-P3GC-135124 | 2019-10-02 | MRT-HK-REC-TT-190814 | FI | 0 | TRUE | FALSE | FALSE
9519 | MRT-DS00-P0GN-135277 | 2019-10-02 | MRT-HK-REC-TT-190814 | FI | 2 | TRUE | TRUE | FALSE
9520 | MRT-DS00-P3GC-135842 | 2019-10-02 | MRT-HK-REC-TT-190814 | FI | 1 | TRUE | TRUE | FALSE
9521 | MRT-DD03-P0GEN-135385 | 2019-10-02 | MRT-HK-REC-TT-190814 | FI | 1 | TRUE | TRUE | FALSE
9522 | MRT-FF00-P0SGA-135654 | 2019-10-02 | MRT-HK-REC-TT-190814 | FI | 1 | TRUE | FALSE | FALSE
9523 | MRT-DD09-P0ZEN-128202 | 2019-10-07 | MRT-HK-REC-TT-190816 | FI | 3 | TRUE | TRUE | FALSE
9524 | MRT-DN03-P0GEN-135881 | 2019-10-07 | MRT-HK-REC-TT-190817 | FI | 0 | TRUE | FALSE | FALSE
9525 | MRT-DD00-P3BBT-150616 | 2019-10-07 | MRT-HK-REC-TT-190818 | FI | 0 | TRUE | FALSE | FALSE
9526 | MRT-QM03-P0ZEN-155038 | 2019-10-07 | MRT-HK-REC-TT-190818 | FA | 0 | TRUE | FALSE | FALSE
9527 | MRT-QM03-P0ZEN-155039 | 2019-10-07 | MRT-HK-REC-TT-190818 | FA | 0 | TRUE | FALSE | FALSE
9528 | MRT-DD08-P0ZEN-075001 | 2019-10-07 | MRT-HK-REC-TT-190819 | FA | 2 | TRUE | TRUE | FALSE
9529 | MRT-CA01-P0UGX-186764 | 2019-10-07 | MRT-HK-REC-TT-190820 | FA | 1 | TRUE | TRUE | FALSE
9530 | MRT-CA01-P0UGX-186763 | 2019-10-07 | MRT-HK-REC-TT-190820 | FA | 1 | TRUE | TRUE | FALSE
9531 | MRT-CA01-P0UGX-186765 | 2019-10-07 | MRT-HK-REC-TT-190820 | FA | 1 | TRUE | TRUE | FALSE
9532 | MRT-CA01-P0UGX-186767 | 2019-10-07 | MRT-HK-REC-TT-190820 | FA | 1 | TRUE | TRUE | FALSE
9533 | MRT-CA01-P0UGX-186768 | 2019-10-07 | MRT-HK-REC-TT-190820 | FA | 1 | TRUE | TRUE | FALSE
9534 | MRT-CA02-P0UGX-186772 | 2019-10-07 | MRT-HK-REC-TT-190820 | FA | 1 | TRUE | TRUE | FALSE
9535 | MRT-CA02-P0UGX-186773 | 2019-10-07 | MRT-HK-REC-TT-190820 | FA | 1 | TRUE | TRUE | FALSE
9536 | MRT-DC01-P0ZEN-165037 | 2019-10-07 | MRT-HK-REC-TT-190821 | FA | 0 | TRUE | FALSE | FALSE
9537 | MRT-DN04-P0QHB-125439 | 2019-10-07 | MRT-HK-REC-TT-190822 | FI | 0 | TRUE | FALSE | FALSE
9563 | MRT-QM03-P0ZEN-155035 | 2019-10-07 | MRT-HK-REC-TT-190825 | FA | 1 | TRUE | TRUE | FALSE
9538 | MRT-DP00-P0SA-135738 | 2019-10-08 | MRT-HK-REC-TT-190823 | FA | 1 | TRUE | TRUE | FALSE
9539 | MRT-DP00-P0SA-135739 | 2019-10-08 | MRT-HK-REC-TT-190823 | FA | 1 | TRUE | TRUE | FALSE
9540 | MRT-DN04-P0GEN-135890 | 2019-10-08 | MRT-HK-REC-TT-190827 | FA | 1 | TRUE | TRUE | FALSE
9541 | MRT-YR01-P0GDG-135085 | 2019-10-08 | MRT-HK-REC-TT-190828 | FA | 1 | TRUE | TRUE | FALSE
9542 | MRT-XJ00-P3LBA-143000 | 2019-10-08 | MRT-DS-REC-TT-190206-FC | FC | 2 | TRUE | TRUE | FALSE
9543 | MRT-XJ00-P3LBG-143000 | 2019-10-08 | MRT-DS-REC-TT-190206-FC | FC | 2 | TRUE | TRUE | FALSE
9544 | MRT-XJ00-P3LAB-143000 | 2019-10-08 | MRT-DS-REC-TT-190206-FC | FC | 2 | TRUE | TRUE | FALSE
9545 | MRT-XJ00-P3LCA-143000 | 2019-10-08 | MRT-DS-REC-TT-190206-FC | FC | 2 | TRUE | TRUE | FALSE
9546 | MRT-XJ00-P3PGB-143000 | 2019-10-08 | MRT-DS-REC-TT-190206-FC | FC | 2 | TRUE | TRUE | FALSE
9547 | MRT-XJ00-P3LCM-143000 | 2019-10-08 | MRT-DS-REC-TT-190206-FC | FC | 2 | TRUE | TRUE | FALSE
9548 | MRT-XJ00-P3LBA-144000 | 2019-10-08 | MRT-DS-REC-TT-190207-FC | FC | 2 | TRUE | TRUE | FALSE
9549 | MRT-XJ00-P3LBG-144000 | 2019-10-08 | MRT-DS-REC-TT-190207-FC | FC | 2 | TRUE | TRUE | FALSE
9550 | MRT-XJ00-P3LCM-144000 | 2019-10-08 | MRT-DS-REC-TT-190207-FC | FC | 2 | TRUE | TRUE | FALSE
9551 | MRT-XJ00-P3LAB-144000 | 2019-10-08 | MRT-DS-REC-TT-190207-FC | FC | 2 | TRUE | TRUE | FALSE
9552 | MRT-XJ00-P3LCA-144000 | 2019-10-08 | MRT-DS-REC-TT-190207-FC | FC | 2 | TRUE | TRUE | FALSE
9553 | MRT-XJ00-P3PGB-144000 | 2019-10-08 | MRT-DS-REC-TT-190207-FC | FC | 2 | TRUE | TRUE | FALSE
9554 | MRT-XK00-P2LBA-142000 | 2019-10-10 | MRT-DS-REC-TT-190201-FC | FC | 1 | TRUE | TRUE | FALSE
9555 | MRT-XK00-P2PAB-142000 | 2019-10-10 | MRT-DS-REC-TT-190201-FC | FC | 1 | TRUE | TRUE | FALSE
9556 | MRT-XK00-P2PGB-142000 | 2019-10-10 | MRT-DS-REC-TT-190201-FC | FC | 1 | TRUE | TRUE | FALSE
9557 | MRT-XK00-P2LAB-142000 | 2019-10-10 | MRT-DS-REC-TT-190201-FC | FC | 1 | TRUE | TRUE | FALSE
9558 | MRT-XK00-P2LBG-142000 | 2019-10-10 | MRT-DS-REC-TT-190201-FC | FC | 1 | TRUE | TRUE | FALSE
9559 | MRT-XK00-P2LCA-142000 | 2019-10-10 | MRT-DS-REC-TT-190201-FC | FC | 1 | TRUE | TRUE | FALSE
9560 | MRT-XK00-P2LCM-142000 | 2019-10-10 | MRT-DS-REC-TT-190201-FC | FC | 1 | TRUE | TRUE | FALSE
9561 | MRT-XK00-P2ACW-142000 | 2019-10-10 | MRT-DS-REC-TT-190201-FC | FC | 1 | TRUE | TRUE | FALSE
9562 | MRT-XK00-P2MAM-142000 | 2019-10-10 | MRT-DS-REC-TT-190201-FC | FC | 1 | TRUE | TRUE | FALSE
9564 | MRT-QM03-P0ZEN-175001 | 2019-10-10 | MRT-HK-REC-TT-190824 | FI | 0 | TRUE | FALSE | FALSE
9565 | MRT-YR01-P0PBB-135251 | 2019-10-11 | MRT-HK-REC-TT-190830 | FI | 0 | TRUE | FALSE | FALSE
9566 | MRT-CC05-P0SMU-125012 | 2019-10-11 | MRT-HK-REC-TT-190830 | FI | 0 | TRUE | FALSE | FALSE
9567 | MRT-BN00-P0EKF-125633 | 2019-10-11 | MRT-HK-REC-TT-190831 | FI | 0 | TRUE | FALSE | FALSE
9568 | MRT-DM01-P0QHB-125418 | 2019-10-11 | MRT-HK-REC-TT-190831 | FI | 0 | TRUE | FALSE | FALSE
9569 | MRT-YD08-P0QHY-125479 | 2019-10-11 | MRT-HK-REC-TT-190831 | FI | 0 | TRUE | FALSE | FALSE
9570 | MRT-YF00-P0MKG-125314 | 2019-10-11 | MRT-HK-REC-TT-190832 | FI | 0 | TRUE | FALSE | FALSE
9571 | MRT-XG02-P2MAA-220005 | 2019-10-11 | MRT-DS-REC-TT-190208 | FC | 3 | TRUE | TRUE | FALSE
9572 | MRT-XG02-P3MAA-220005 | 2019-10-11 | MRT-DS-REC-TT-190208 | FC | 3 | TRUE | TRUE | FALSE
9573 | MRT-BT00-P2PAC-130001 | 2019-10-11 | MRT-HK-REC-TT-190833 | FA | 1 | TRUE | TRUE | FALSE
9574 | MRT-XW01-P3GC-135109 | 2019-10-14 | MRT-HK-REC-TT-190834 | FA | 0 | TRUE | FALSE | FALSE
9575 | MRT-XJ00-P2LBA-142000 | 2019-10-14 | MRT-DS-REC-TT-190209-FC | FC | 2A | TRUE | TRUE | FALSE
9576 | MRT-XJ00-P2LCA-142000 | 2019-10-14 | MRT-DS-REC-TT-190209-FC | FC | 2A | TRUE | TRUE | FALSE
9577 | MRT-XJ00-P2PGB-142000 | 2019-10-14 | MRT-DS-REC-TT-190209-FC | FC | 2A | TRUE | TRUE | FALSE
10610 | MRT-CT00-P3AYA-160005 | 2019-10-14 | MRT-HK-REC-TT-190835 | FA | 1 | TRUE | TRUE | FALSE
9578 | MRT-BF01-P3AYA-160036 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9579 | MRT-YK08-P3AYA-160020 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9580 | MRT-YV02-P3AYA-160017 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9581 | MRT-YT01-P3AYA-160010 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9582 | MRT-YL16-P3AYA-160007 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9583 | MRT-CT00-P3AY-160005 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 1 | TRUE | TRUE | FALSE
9584 | MRT-YV02-P3AYA-160016 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9585 | MRT-YQ07-P3AYA-160038 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 1 | TRUE | TRUE | FALSE
9586 | MRT-YL16-P3AYA-160039 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9587 | MRT-CT00-P3AYA-160047 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 1 | TRUE | TRUE | FALSE
9588 | MRT-CA00-P3AYA-160013 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9589 | MRT-BF01-P3AYA-160033 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9590 | MRT-YV02-P3AY-160040 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9591 | MRT-YD00-P3AY-160011 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9592 | MRT-YV02-P3AY-160015 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | TRUE | FALSE
9593 | MRT-YT01-P3AY-160008 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 1 | TRUE | TRUE | FALSE
9594 | MRT-YL16-P3AYA-160006 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9595 | MRT-DD07-P3AY-160025 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | FALSE | FALSE
9596 | MRT-BF01-P3AY-160031 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 0 | TRUE | TRUE | FALSE
9597 | MRT-YK08-P3AYA-160019 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 1 | TRUE | TRUE | FALSE
9598 | MRT-CA00-P3AY-160012 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 1 | TRUE | TRUE | FALSE
9599 | MRT-CA00-P3AYA-160014 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 1 | TRUE | TRUE | FALSE
9600 | MRT-CC07-P3AY-160001 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 1 | TRUE | TRUE | FALSE
9601 | MRT-YQ07-P3AY-160002 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 1 | TRUE | TRUE | FALSE
9602 | MRT-YT01-P3AYA-160009 | 2019-10-15 | MRT-HK-REC-TT-190835 | FA | 1 | TRUE | TRUE | FALSE
9603 | MRT-US02-P0BJK-150704 | 2019-10-15 | MRT-HK-REC-TT-190836 | FA | 2 | TRUE | TRUE | FALSE
9604 | MRT-YU02-P0BJK-150703 | 2019-10-15 | MRT-HK-REC-TT-190836 | FA | 2 | TRUE | TRUE | FALSE
9605 | MRT-US02-P0SAC-150696 | 2019-10-16 | MRT-HK-REC-TT-190837 | FA | 1 | TRUE | TRUE | FALSE
9606 | MRT-US02-P0SRA-150698 | 2019-10-16 | MRT-HK-REC-TT-190837 | FA | 1 | TRUE | TRUE | FALSE
9607 | MRT-YU02-P0SAC-150695 | 2019-10-16 | MRT-HK-REC-TT-190837 | FA | 1 | TRUE | TRUE | FALSE
9608 | MRT-YU02-P0SRA-150697 | 2019-10-16 | MRT-HK-REC-TT-190837 | FA | 1 | TRUE | TRUE | FALSE
9609 | MRT-DD07-P3AYA-160027 | 2019-10-16 | MRT-HK-REC-TT-190838 | FA | 1 | TRUE | TRUE | FALSE
9610 | MRT-DD07-P3AYA-160030 | 2019-10-16 | MRT-HK-REC-TT-190838 | FA | 1 | TRUE | TRUE | FALSE
9611 | MRT-DS00-P3AYA-160024 | 2019-10-16 | MRT-HK-REC-TT-190838 | FA | 1 | TRUE | TRUE | FALSE
9612 | MRT-DS00-P3AYA-160026 | 2019-10-16 | MRT-HK-REC-TT-190838 | FA | 1 | TRUE | TRUE | FALSE
9613 | MRT-DS00-P3AYA-160029 | 2019-10-16 | MRT-HK-REC-TT-190838 | FA | 1 | TRUE | TRUE | FALSE
9614 | MRT-CA00-P0UMA-180009 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9615 | MRT-CA00-P0UMA-180010 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9616 | MRT-CA00-P0UMA-180011 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9617 | MRT-CA00-P0UMA-180013 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9618 | MRT-CA00-P0UMA-180014 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9619 | MRT-CA00-P0UMA-180015 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9620 | MRT-CA00-P0UMA-180016 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9621 | MRT-CA00-P0UMA-180017 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9622 | MRT-CA00-P0UMA-180019 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9623 | MRT-CA00-P0UMA-180021 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9624 | MRT-CA00-P0UMA-180023 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 3 | TRUE | TRUE | FALSE
9625 | MRT-CA03-P0UMA-180036 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9626 | MRT-CA03-P0UMA-180037 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9627 | MRT-CA03-P0UMA-180039 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9628 | MRT-CA01-P0UMA-180044 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 4 | TRUE | TRUE | FALSE
9629 | MRT-CA02-P0UMA-180045 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 4 | TRUE | TRUE | FALSE
9630 | MRT-CA00-P0UMA-180047 | 2019-10-16 | MRT-DS-REC-TT-190210 | FC | 5 | TRUE | TRUE | FALSE
9631 | MRT-XG02-P3MKW-210001 | 2019-10-17 | MRT-DS-REC-TT-190204 | FC | 2 | TRUE | TRUE | FALSE
9632 | MRT-XG02-P3MKG-210001 | 2019-10-17 | MRT-DS-REC-TT-190205 | FC | 2 | TRUE | TRUE | FALSE
9633 | MRT-DS00-P0GN-135869 | 2019-10-17 | MRT-HK-REC-TT-190840 | FI | 0 | TRUE | FALSE | FALSE
9634 | MRT-YR01-P3GC-135182 | 2019-10-17 | MRT-HK-REC-TT-190839 | FA | 0 | TRUE | FALSE | FALSE
9635 | MRT-DS00-P3GC-135183 | 2019-10-17 | MRT-HK-REC-TT-190839 | FA | 0 | TRUE | FALSE | FALSE
9636 | MRT-YR01-P0GN-135278 | 2019-10-17 | MRT-HK-REC-TT-190839 | FA | 0 | TRUE | FALSE | FALSE
9637 | MRT-DS00-P0GN-135279 | 2019-10-17 | MRT-HK-REC-TT-190839 | FA | 0 | TRUE | FALSE | FALSE
9638 | MRT-YT01-P0GN-135228 | 2019-10-17 | MRT-HK-REC-TT-190841 | FI | 0 | TRUE | FALSE | FALSE
9639 | MRT-YT01-P3GC-135134 | 2019-10-17 | MRT-HK-REC-TT-190841 | FA | 0 | TRUE | FALSE | FALSE
9640 | MRT-YT01-P0GN-135294 | 2019-10-17 | MRT-HK-REC-TT-190841 | FI | 1 | TRUE | FALSE | FALSE
9641 | MRT-YL01-P3GC-135167 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9642 | MRT-YR08-P3GC-135170 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9643 | MRT-YL11-P3GC-135175 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9644 | MRT-YR05-P0GN-135249 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9645 | MRT-YS01-P0GN-135250 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9646 | MRT-YL01-P0GN-135263 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9647 | MRT-YR08-P0GN-135266 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9648 | MRT-YL11-P0GN-135271 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9649 | MRT-YT01-P3GC-135155 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 2 | TRUE | TRUE | FALSE
9650 | MRT-YT01-P3GC-135157 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 1 | TRUE | TRUE | FALSE
9651 | MRT-YT01-P3GC-135164 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9652 | MRT-YT01-P0GN-135256 | 2019-10-17 | MRT-HK-REC-TT-190842 | FA | 1 | TRUE | TRUE | FALSE
9653 | MRT-YT01-P0GN-135259 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9654 | MRT-YT01-P3GC-135198 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9655 | MRT-YT01-P0GN-135255 | 2019-10-17 | MRT-HK-REC-TT-190842 | FA | 1 | TRUE | TRUE | FALSE
9656 | MRT-YT01-P0GN-135258 | 2019-10-17 | MRT-HK-REC-TT-190842 | FA | 0 | TRUE | TRUE | FALSE
9657 | MRT-YT01-P0GN-135262 | 2019-10-17 | MRT-HK-REC-TT-190842 | FA | 0 | TRUE | TRUE | FALSE
9658 | MRT-YT01-P0GN-135297 | 2019-10-17 | MRT-HK-REC-TT-190842 | FA | 0 | TRUE | TRUE | FALSE
9659 | MRT-YT01-P3GC-135161 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9660 | MRT-YT01-P3GC-135159 | 2019-10-17 | MRT-HK-REC-TT-190842 | FA | 0 | TRUE | TRUE | FALSE
9661 | MRT-YT01-P3GC-135199 | 2019-10-17 | MRT-HK-REC-TT-190842 | FI | 0 | TRUE | TRUE | FALSE
9662 | MRT-YD04-P0UZT-150147 | 2019-10-18 | MRT-HK-REC-TT-190844 | FI | 0 | TRUE | FALSE | FALSE
9663 | MRT-DN03-P0GEN-135881 | 2019-10-18 | MRT-HK-REC-TT-190843 | FI | 1 | TRUE | FALSE | FALSE
9664 | MRT-US02-P0BJC-150692 | 2019-10-18 | MRT-HK-REC-TT-190845 | FA | 1 | TRUE | TRUE | FALSE
9665 | MRT-YU02-P0BJC-150691 | 2019-10-18 | MRT-HK-REC-TT-190845 | FA | 1 | TRUE | TRUE | FALSE
9666 | MRT-QE02-P0PBB-135249 | 2019-10-18 | MRT-HK-REC-TT-190846 | FI | 1 | TRUE | TRUE | FALSE
9667 | MRT-QM03-P0ZEN-175001 | 2019-10-18 | MRT-HK-REC-TT-190847 | FI | 1 | TRUE | TRUE | FALSE
9668 | MRT-XM00-P2MAA-220012 | 2019-10-18 | MRT-DS-REC-TT-190211-FC | FC | 1 | TRUE | TRUE | FALSE
9669 | MRT-XM00-P3MAA-220012 | 2019-10-18 | MRT-DS-REC-TT-190211-FC | FC | 1 | TRUE | TRUE | FALSE
9670 | MRT-DN02-P2SM-120001 | 2019-10-18 | MRT-DS-REC-TT-190212 | FA | 0 | TRUE | FALSE | FALSE
9671 | MRT-XG02-P2LB-122022 | 2019-10-21 | MRT-DS-REC-TT-190213 | FC | 7 | TRUE | TRUE | FALSE
9672 | MRT-XG02-P3LB-122022 | 2019-10-21 | MRT-DS-REC-TT-190213 | FC | 4 | TRUE | TRUE | FALSE
9673 | MRT-CC04-P0UGG-185236 | 2019-10-21 | MRT-HK-REC-TT-190851 | FI | 0 | TRUE | FALSE | FALSE
9674 | MRT-CC04-P0UGG-185231 | 2019-10-21 | MRT-HK-REC-TT-190851 | FI | 0 | TRUE | FALSE | FALSE
9675 | MRT-CC04-P0MKG-185226 | 2019-10-21 | MRT-HK-REC-TT-190851 | FI | 0 | TRUE | FALSE | FALSE
9676 | MRT-XV00-P0GN-135213 | 2019-10-21 | MRT-HK-REC-TT-190853 | FI | 0 | TRUE | FALSE | FALSE
9677 | MRT-YF02-P0GN-135268 | 2019-10-21 | MRT-HK-REC-TT-190853 | FI | 0 | TRUE | FALSE | FALSE
9678 | MRT-YF02-P3GC-135172 | 2019-10-21 | MRT-HK-REC-TT-190853 | FI | 0 | TRUE | FALSE | FALSE
9679 | MRT-YL00-P3GC-135113 | 2019-10-21 | MRT-HK-REC-TT-190853 | FI | 0 | TRUE | FALSE | FALSE
9680 | MRT-YR05-P3GC-135147 | 2019-10-21 | MRT-HK-REC-TT-190853 | FI | 0 | TRUE | FALSE | FALSE
9681 | MRT-YS01-P3GC-135148 | 2019-10-21 | MRT-HK-REC-TT-190853 | FI | 0 | TRUE | FALSE | FALSE
9682 | MRT-DS00-P0GN-135871 | 2019-10-21 | MRT-HK-REC-TT-190853 | FI | 0 | TRUE | FALSE | FALSE
9683 | MRT-YK10-P0QHN-125447 | 2019-10-21 | MRT-HK-REC-TT-190854 | FI | 0 | TRUE | FALSE | FALSE
9684 | MRT-DN05-P0QHY-125419 | 2019-10-21 | MRT-HK-REC-TT-190854 | FA | 0 | TRUE | FALSE | FALSE
9685 | MRT-YK10-P0EGB-125458 | 2019-10-21 | MRT-HK-REC-TT-190854 | FA | 1 | TRUE | TRUE | FALSE
9686 | MRT-YD08-P0QHY-125485 | 2019-10-21 | MRT-HK-REC-TT-190855 | FI | 0 | TRUE | FALSE | FALSE
9687 | MRT-PL03-P0QHA-125433 | 2019-10-21 | MRT-HK-REC-TT-190855 | FI | 0 | TRUE | FALSE | FALSE
9688 | MRT-XK00-P0GDG-135063 | 2019-10-21 | MRT-HK-REC-TT-190855 | FI | 0 | TRUE | FALSE | FALSE
9689 | MRT-YD08-P0QHY-125499 | 2019-10-21 | MRT-HK-REC-TT-190856 | FI | 0 | TRUE | FALSE | FALSE
9690 | MRT-YF02-P3CRA-1601118 | 2019-10-21 | MRT-HK-REC-TT-190856 | FI | 0 | TRUE | FALSE | FALSE
9700 | MRT-XP00-P0BFT-150584 | 2019-10-21 | MRT-HK-REC-TT-190858 | FA | 0 | TRUE | FALSE | FALSE
9782 | MRT-YF00-P3GC-135189 | 2019-10-21 | MRT-HK-REC-TT-190853 | FI | 0 | TRUE | FALSE | FALSE
10397 | MRT-YD08-P0QHY-125496 | 2019-10-21 | MRT-HK-REC-TT-190856 | FI | 0 | TRUE | FALSE | FALSE
9691 | MRT-XJ00-P2LCA-142000 | 2019-10-23 | MRT-DS-REC-TT-190215-FC | FC | 2B | TRUE | TRUE | FALSE
9692 | MRT-XJ00-P3LCA-143000 | 2019-10-23 | MRT-DS-REC-TT-190215-FC | FC | 2A | TRUE | TRUE | FALSE
9693 | MRT-XJ00-P3LCA-144000 | 2019-10-23 | MRT-DS-REC-TT-190215-FC | FC | 2A | TRUE | TRUE | FALSE
9694 | MRT-XJ00-P2LBA-142000 | 2019-10-23 | MRT-DS-REC-TT-190214-FC | FC | 2B | TRUE | TRUE | FALSE
9695 | MRT-XJ00-P3LBA-143000 | 2019-10-23 | MRT-DS-REC-TT-190214-FC | FC | 2A | TRUE | TRUE | FALSE
9696 | MRT-XJ00-P3LBA-144000 | 2019-10-23 | MRT-DS-REC-TT-190214-FC | FC | 2A | TRUE | TRUE | FALSE
9697 | MRT-QM03-P3CYP-160050 | 2019-10-23 | MRT-HK-REC-TT-190857 | FA | 2 | TRUE | TRUE | FALSE
9698 | MRT-YB10-P0BBA-150891 | 2019-10-23 | MRT-HK-REC-TT-190860 | FA | 1 | TRUE | TRUE | FALSE
10603 | MRT-XP00-P0BFT-150584 | 2019-10-23 | MRT-HK-REC-TT-190860 | FA | 1 | TRUE | TRUE | FALSE
9699 | MRT-QM03-P0ZEN-045007 | 2019-10-24 | MRT-HK-REC-TT-190861 | FA | 2 | TRUE | TRUE | FALSE
9701 | MRT-QM04-P0SA-135772 | 2019-10-25 | MRT-HK-REC-TT-190862 | FI | 0 | TRUE | FALSE | FALSE
9702 | MRT-QM04-P0SA-135771 | 2019-10-25 | MRT-HK-REC-TT-190862 | FI | 0 | TRUE | FALSE | FALSE
9703 | MRT-YT02-P0SA-135767 | 2019-10-25 | MRT-HK-REC-TT-190863 | FI | 0 | TRUE | FALSE | FALSE
9704 | MRT-YL00-P0SA-135766 | 2019-10-25 | MRT-HK-REC-TT-190863 | FI | 0 | TRUE | FALSE | FALSE
9705 | MRT-QM00-P0SA-135778 | 2019-10-25 | MRT-HK-REC-TT-190864 | FI | 0 | TRUE | FALSE | FALSE
9706 | MRT-QM00-P0SA-135777 | 2019-10-25 | MRT-HK-REC-TT-190864 | FI | 0 | TRUE | FALSE | FALSE
9707 | MRT-CT00-P2PAC-130001 | 2019-10-25 | MRT-HK-REC-TT-190865 | FI | 0 | TRUE | TRUE | FALSE
9708 | MRT-YD08-P0QHY-125491 | 2019-10-25 | MRT-HK-REC-TT-190866 | FI | 0 | TRUE | FALSE | FALSE
9709 | MRT-CQ02-P0SMU-125038 | 2019-10-25 | MRT-HK-REC-TT-190867 | FI | 0 | TRUE | FALSE | FALSE
9710 | MRT-DD03-P0SMU-125040 | 2019-10-25 | MRT-HK-REC-TT-190867 | FI | 0 | TRUE | FALSE | FALSE
9711 | MRT-DD00-P0SMU-125036 | 2019-10-25 | MRT-HK-REC-TT-190867 | FI | 0 | TRUE | FALSE | FALSE
9712 | MRT-DD00-P0SMU-125035 | 2019-10-25 | MRT-HK-REC-TT-190867 | FI | 0 | TRUE | FALSE | FALSE
9713 | MRT-DD03-P0SMU-125034 | 2019-10-25 | MRT-HK-REC-TT-190867 | FI | 0 | TRUE | FALSE | FALSE
9714 | MRT-CC05-P0SMU-125018 | 2019-10-25 | MRT-HK-REC-TT-190867 | FI | 1 | TRUE | TRUE | FALSE
9715 | MRT-CC05-P0SMU-125016 | 2019-10-25 | MRT-HK-REC-TT-190867 | FI | 1 | TRUE | TRUE | FALSE
9716 | MRT-CC05-P0SMU-125017 | 2019-10-25 | MRT-HK-REC-TT-190867 | FI | 1 | TRUE | TRUE | FALSE
9717 | MRT-CC05-P0SMU-125013 | 2019-10-25 | MRT-HK-REC-TT-190867 | FI | 1 | TRUE | TRUE | FALSE
9718 | MRT-CC05-P0SMU-125014 | 2019-10-25 | MRT-HK-REC-TT-190867 | FI | 1 | TRUE | TRUE | FALSE
9719 | MRT-CC05-P0SMU-125015 | 2019-10-25 | MRT-HK-REC-TT-190867 | FI | 1 | TRUE | TRUE | FALSE
9720 | MRT-XH01-P2ULY-142000 | 2019-10-25 | MRT-DS-REC-TT-190216 | FC | 3 | TRUE | TRUE | FALSE
9721 | MRT-XH01-P3ULY-143000 | 2019-10-25 | MRT-DS-REC-TT-190216 | FC | 3 | TRUE | TRUE | FALSE
9722 | MRT-XH01-P3ULY-144000 | 2019-10-25 | MRT-DS-REC-TT-190216 | FC | 3 | TRUE | TRUE | FALSE
9723 | MRT-CA03-P0UCA-180132 | 2019-10-28 | MRT-DS-REC-TT-190197-FC | FC | 7 | TRUE | TRUE | FALSE
9724 | MRT-CA01-P0UXA-186692 | 2019-10-28 | MRT-HK-REC-TT-190868 | FA | 1 | TRUE | TRUE | FALSE
9725 | MRT-YE16-P2UMA-150617 | 2019-10-28 | MRT-HK-REC-TT-190870 | FI | 0 | TRUE | FALSE | FALSE
9726 | MRT-CC02-P0UYX-175577 | 2019-10-28 | MRT-HK-REC-TT-190871 | FA | 0 | TRUE | FALSE | FALSE
9727 | MRT-CC02-P0UYX-175576 | 2019-10-28 | MRT-HK-REC-TT-190871 | FA | 0 | TRUE | FALSE | FALSE
9728 | MRT-CC02-P0UYX-175575 | 2019-10-28 | MRT-HK-REC-TT-190871 | FA | 0 | TRUE | FALSE | FALSE
9729 | MRT-CC02-P0UYX-175574 | 2019-10-28 | MRT-HK-REC-TT-190871 | FA | 0 | TRUE | FALSE | FALSE
9730 | MRT-CC02-P0UYX-175573 | 2019-10-28 | MRT-HK-REC-TT-190871 | FA | 0 | TRUE | FALSE | FALSE
9731 | MRT-CC02-P0UYX-175572 | 2019-10-28 | MRT-HK-REC-TT-190871 | FA | 0 | TRUE | FALSE | FALSE
9732 | MRT-CC02-P0UYX-175571 | 2019-10-28 | MRT-HK-REC-TT-190871 | FA | 0 | TRUE | FALSE | FALSE
9733 | MRT-CC02-P0UYX-175591 | 2019-10-28 | MRT-HK-REC-TT-190871 | FA | 0 | TRUE | FALSE | FALSE
9734 | MRT-DN05-P0GDG-135082 | 2019-10-28 | MRT-HK-REC-TT-190872 | FA | 0 | TRUE | FALSE | FALSE
9735 | MRT-DM01-P0GDG-135080 | 2019-10-28 | MRT-HK-REC-TT-190872 | FI | 0 | TRUE | FALSE | FALSE
9736 | MRT-DM01-P0GHE-145084 | 2019-10-28 | MRT-HK-REC-TT-190873 | FA | 0 | TRUE | FALSE | FALSE
9737 | MRT-CT00-P3GC-135184 | 2019-10-28 | MRT-HK-REC-TT-190874 | FI | 0 | TRUE | FALSE | FALSE
9738 | MRT-DS00-P3GC-135849 | 2019-10-28 | MRT-HK-REC-TT-190874 | FI | 0 | TRUE | FALSE | FALSE
9739 | MRT-CQ02-P0GEN-135317 | 2019-10-28 | MRT-HK-REC-TT-190874 | FI | 0 | TRUE | FALSE | FALSE
9740 | MRT-CV05-P0GEN-135891 | 2019-10-28 | MRT-HK-REC-TT-190874 | FI | 0 | TRUE | FALSE | FALSE
9741 | MRT-YR05-P0GEN-135376 | 2019-10-28 | MRT-HK-REC-TT-190875 | FA | 0 | TRUE | FALSE | FALSE
9742 | MRT-YB03-P0GN-135269 | 2019-10-28 | MRT-HK-REC-TT-190875 | FI | 0 | TRUE | FALSE | FALSE
9743 | MRT-YB03-P3GC-135173 | 2019-10-28 | MRT-HK-REC-TT-190875 | FI | 0 | TRUE | FALSE | FALSE
9744 | MRT-YL30-P0GDY-135017 | 2019-10-28 | MRT-HK-REC-TT-190875 | FI | 0 | TRUE | FALSE | FALSE
9745 | MRT-YL00-P0GDG-135061 | 2019-10-28 | MRT-HK-REC-TT-190875 | FI | 0 | TRUE | FALSE | FALSE
9746 | MRT-YF02-P3GC-135172 | 2019-10-28 | MRT-HK-REC-TT-190875 | FA | 0 | TRUE | FALSE | FALSE
9747 | MRT-YF02-P0GN-135268 | 2019-10-28 | MRT-HK-REC-TT-190875 | FA | 0 | TRUE | FALSE | FALSE
9748 | MRT-YS01-P0GDG-135068 | 2019-10-28 | MRT-HK-REC-TT-190876 | FI | 0 | TRUE | FALSE | FALSE
9749 | MRT-FF02-P0AYE-135648 | 2019-10-28 | MRT-HK-REC-TT-190877 | FI | 0 | TRUE | FALSE | FALSE
9750 | MRT-YD00-P3MAA-220030 | 2019-10-28 | MRT-DS-REC-TT-190217-FC | FC | 2 | TRUE | TRUE | FALSE
9751 | MRT-YD00-P3MAA-220031 | 2019-10-28 | MRT-DS-REC-TT-190217-FC | FC | 2 | TRUE | TRUE | FALSE
9752 | MRT-YD02-P2LB-122064 | 2019-10-29 | MRT-DS-REC-TT-190218-FC | FC | 3 | TRUE | TRUE | FALSE
9753 | MRT-YD02-P3LB-122064 | 2019-10-29 | MRT-DS-REC-TT-190218-FC | FC | 2 | TRUE | TRUE | FALSE
9754 | MRT-DD03-P0GEN-135702 | 2019-10-29 | MRT-HK-REC-TT-190878 | FA | 0 | TRUE | FALSE | FALSE
9755 | MRT-DN03-P0GEN-135881 | 2019-10-29 | MRT-HK-REC-TT-190878 | FA | 2 | TRUE | TRUE | FALSE
9756 | MRT-DS00-P0GN-135869 | 2019-10-29 | MRT-HK-REC-TT-190879 | FA | 1 | TRUE | TRUE | FALSE
9757 | MRT-QM03-P3CYP-160050 | 2019-10-29 | MRT-HK-REC-TT-190880 | FA | 3 | TRUE | TRUE | FALSE
9758 | MRT-FF03-P0UAT-128218 | 2019-10-29 | MRT-HK-REC-TT-190881 | FI | 0 | TRUE | FALSE | FALSE
9759 | MRT-YT01-P0BBB-150529 | 2019-10-30 | MRT-HK-REC-TT-190882 | FA | 0 | TRUE | FALSE | FALSE
9760 | MRT-YL16-P2ZEN-165026 | 2019-10-30 | MRT-HK-REC-TT-190883 | FA | 1 | TRUE | TRUE | FALSE
9761 | MRT-FF00-P0SGA-135654 | 2019-10-30 | MRT-HK-REC-TT-190884 | FA | 1 | TRUE | TRUE | FALSE
9762 | MRT-BF01-P3AY-160031 | 2019-10-31 | MRT-HK-REC-TT-190885 | FA | 0 | TRUE | FALSE | FALSE
9763 | MRT-CP00-P0ZEN-128204 | 2019-10-31 | MRT-HK-REC-TT-190886 | FA | 1 | TRUE | TRUE | FALSE
9764 | MRT-YK01-P2MAA-185130 | 2019-10-31 | MRT-HK-REC-TT-190887 | FI | 0 | TRUE | FALSE | FALSE
9765 | MRT-XG02-P3MKW-210001 | 2019-10-31 | MRT-DS-REC-TT-190204-FC | FC | 2 | TRUE | TRUE | FALSE
9766 | MRT-XG02-P2MAA-220005 | 2019-10-31 | MRT-DS-REC-TT-190208-FC | FC | 3 | TRUE | TRUE | FALSE
9767 | MRT-XG02-P3MAA-220005 | 2019-10-31 | MRT-DS-REC-TT-190208-FC | FC | 3 | TRUE | TRUE | FALSE
9768 | MRT-XG02-P3MKG-210001 | 2019-11-01 | MRT-DS-REC-TT-190205-FC | FC | 2 | TRUE | TRUE | FALSE
9769 | MRT-QM03-P0ZEN-155041 | 2019-11-01 | MRT-HK-REC-TT-190888 | FA | 0 | TRUE | FALSE | FALSE
9770 | MRT-QM03-P0ZEN-155040 | 2019-11-01 | MRT-HK-REC-TT-190888 | FA | 0 | TRUE | FALSE | FALSE
9771 | MRT-CA01-P0UGA-186654 | 2019-11-01 | MRT-HK-REC-TT-190889 | FA | 3 | TRUE | TRUE | FALSE
9772 | MRT-CA01-P0UGA-186659 | 2019-11-01 | MRT-HK-REC-TT-190889 | FA | 5 | TRUE | TRUE | FALSE
9773 | MRT-CA01-P0UGA-186658 | 2019-11-01 | MRT-HK-REC-TT-190889 | FA | 5 | TRUE | TRUE | FALSE
9774 | MRT-CA01-P0UGA-186655 | 2019-11-01 | MRT-HK-REC-TT-190889 | FA | 3 | TRUE | TRUE | FALSE
9775 | MRT-CC02-P0UPC-175786 | 2019-11-01 | MRT-HK-REC-TT-190890 | FA | 2 | TRUE | TRUE | FALSE
9776 | MRT-CC02-P0UPC-175787 | 2019-11-01 | MRT-HK-REC-TT-190890 | FA | 2 | TRUE | TRUE | FALSE
9777 | MRT-CC03-P0UPC-175788 | 2019-11-01 | MRT-HK-REC-TT-190890 | FA | 1 | TRUE | TRUE | FALSE
9778 | MRT-CC03-P0UPC-175789 | 2019-11-01 | MRT-HK-REC-TT-190890 | FA | 1 | TRUE | TRUE | FALSE
9779 | MRT-CC02-P0UPC-175793 | 2019-11-01 | MRT-HK-REC-TT-190890 | FA | 1 | TRUE | TRUE | FALSE
9780 | MRT-XH01-P2LB-122025 | 2019-11-04 | MRT-DS-REC-TT-190219-FC | FC | 4 | TRUE | TRUE | FALSE
9781 | MRT-XH01-P3LB-122025 | 2019-11-04 | MRT-DS-REC-TT-190219-FC | FC | 4 | TRUE | TRUE | FALSE
9783 | MRT-CC02-P2UAG-170307 | 2019-11-05 | MRT-DS-REC-TT-190220 | FC | 4 | TRUE | TRUE | FALSE
9784 | MRT-CC02-P2UAG-170308 | 2019-11-05 | MRT-DS-REC-TT-190220 | FC | 5 | TRUE | TRUE | FALSE
9785 | MRT-CC02-P3UAG-170307 | 2019-11-05 | MRT-DS-REC-TT-190220 | FC | 3 | TRUE | TRUE | FALSE
9786 | MRT-CC02-P3UAG-170308 | 2019-11-05 | MRT-DS-REC-TT-190220 | FC | 4 | TRUE | TRUE | FALSE
9787 | MRT-XA01-P0ABA-150517 | 2019-11-05 | MRT-HK-REC-TT-190891 | FA | 2 | TRUE | TRUE | FALSE
9788 | MRT-XJ00-P2LCA-145000 | 2019-11-06 | MRT-DS-REC-TT-190221-FC | FC | 2 | TRUE | TRUE | FALSE
9789 | MRT-XJ00-P3MKA-220001 | 2019-11-06 | MRT-DS-REC-TT-190222 | FC | 4 | TRUE | TRUE | FALSE
9790 | MRT-BT00-P0BAU-150629 | 2019-11-06 | MRT-HK-REC-TT-190892 | FA | 0 | TRUE | FALSE | FALSE
9791 | MRT-DD09-P0ZEN-128235 | 2019-11-06 | MRT-HK-REC-TT-190893 | FA | 0 | TRUE | FALSE | FALSE
9792 | MRT-YL00-P0SA-135768 | 2019-11-06 | MRT-HK-REC-TT-190894 | FI | 0 | TRUE | FALSE | FALSE
9793 | MRT-QM03-P0GHE-145071 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 1 | TRUE | TRUE | FALSE
9794 | MRT-QM03-P0GHE-145062 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 1 | TRUE | TRUE | FALSE
9795 | MRT-QM03-P0GHE-145072 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 1 | TRUE | TRUE | FALSE
9796 | MRT-QM03-P0GHE-145064 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 1 | TRUE | TRUE | FALSE
9797 | MRT-QM03-P0GHE-145065 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 1 | TRUE | TRUE | FALSE
9798 | MRT-QM03-P0GHE-145066 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 1 | TRUE | TRUE | FALSE
9799 | MRT-QM03-P0GHE-145067 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 1 | TRUE | TRUE | FALSE
9800 | MRT-QM03-P0GHE-145068 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 1 | TRUE | TRUE | FALSE
9801 | MRT-QM03-P0GHE-145073 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 1 | TRUE | TRUE | FALSE
9802 | MRT-QM03-P0GHE-145074 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 1 | TRUE | TRUE | FALSE
9803 | MRT-QM03-P0GHE-145061 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 2 | TRUE | TRUE | FALSE
9804 | MRT-QM03-P0GHE-145060 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 3 | TRUE | TRUE | FALSE
9805 | MRT-QM03-P0GHE-145076 | 2019-11-07 | MRT-HK-REC-TT-190895 | FA | 1 | TRUE | TRUE | FALSE
9806 | MRT-CT00-P2PAC-130002 | 2019-11-07 | MRT-HK-REC-TT-190896 | FI | 0 | TRUE | FALSE | FALSE
9807 | MRT-BT00-P0BAU-150626 | 2019-11-07 | MRT-HK-REC-TT-190897 | FA | 0 | TRUE | FALSE | FALSE
9808 | MRT-DS00-P3GC-135841 | 2019-11-07 | MRT-HK-REC-TT-190898 | FI | 2 | TRUE | TRUE | FALSE
9809 | MRT-FF01-P0SGJ-135448 | 2019-11-08 | MRT-HK-REC-TT-190899 | FI | 0 | TRUE | FALSE | FALSE
9810 | MRT-FF01-P0SGJ-135450 | 2019-11-08 | MRT-HK-REC-TT-190899 | FI | 0 | TRUE | FALSE | FALSE
9811 | MRT-FF01-P0SGJ-135441 | 2019-11-08 | MRT-HK-REC-TT-190899 | FI | 0 | TRUE | FALSE | FALSE
9812 | MRT-FF01-P0SGJ-135440 | 2019-11-08 | MRT-HK-REC-TT-190899 | FI | 0 | TRUE | FALSE | FALSE
9813 | MRT-FF02-P3AYE-135625 | 2019-11-08 | MRT-HK-REC-TT-190900 | FI | 0 | TRUE | FALSE | FALSE
9814 | MRT-FF02-P2AYE-135637 | 2019-11-08 | MRT-HK-REC-TT-190900 | FI | 0 | TRUE | FALSE | FALSE
9815 | MRT-FF02-P2AYE-135635 | 2019-11-08 | MRT-HK-REC-TT-190900 | FI | 0 | TRUE | FALSE | FALSE
9816 | MRT-FF02-P2AYE-135634 | 2019-11-08 | MRT-HK-REC-TT-190900 | FI | 0 | TRUE | FALSE | FALSE
9817 | MRT-FF02-P0AYE-135622 | 2019-11-08 | MRT-HK-REC-TT-190900 | FI | 0 | TRUE | FALSE | FALSE
9818 | MRT-FF02-P0AYE-135621 | 2019-11-08 | MRT-HK-REC-TT-190900 | FI | 0 | TRUE | FALSE | FALSE
9819 | MRT-FF02-P2AYE-135632 | 2019-11-08 | MRT-HK-REC-TT-190900 | FI | 0 | TRUE | FALSE | FALSE
9820 | MRT-FF00-P0SGA-135652 | 2019-11-08 | MRT-HK-REC-TT-190900 | FA | 0 | TRUE | FALSE | FALSE
9821 | MRT-FF02-P2AYE-135633 | 2019-11-08 | MRT-HK-REC-TT-190900 | FI | 0 | TRUE | FALSE | FALSE
9822 | MRT-YD00-P0SMM-128001 | 2019-11-08 | MRT-DS-REC-TT-190223 | FC | 4 | TRUE | TRUE | FALSE
9823 | MRT-YK09-P0SMM-128007 | 2019-11-08 | MRT-DS-REC-TT-190223 | FC | 3 | TRUE | TRUE | FALSE
9824 | MRT-FF02-P3AYE-135628 | 2019-11-11 | MRT-HK-REC-TT-190902 | FI | 0 | TRUE | FALSE | FALSE
9825 | MRT-FF02-P3AYE-135627 | 2019-11-11 | MRT-HK-REC-TT-190902 | FI | 0 | TRUE | FALSE | FALSE
9826 | MRT-FF02-P2AYE-135638 | 2019-11-11 | MRT-HK-REC-TT-190902 | FI | 0 | TRUE | FALSE | FALSE
9827 | MRT-FF02-P2AYE-135623 | 2019-11-11 | MRT-HK-REC-TT-190902 | FI | 0 | TRUE | FALSE | FALSE
9828 | MRT-FF02-P0AYE-135644 | 2019-11-11 | MRT-HK-REC-TT-190902 | FI | 0 | TRUE | FALSE | FALSE
9829 | MRT-FF02-P0AYE-135620 | 2019-11-11 | MRT-HK-REC-TT-190902 | FI | 0 | TRUE | FALSE | FALSE
9830 | MRT-FF02-P0AYE-135614 | 2019-11-11 | MRT-HK-REC-TT-190902 | FI | 0 | TRUE | FALSE | FALSE
9831 | MRT-FF02-P0AYE-135613 | 2019-11-11 | MRT-HK-REC-TT-190902 | FI | 0 | TRUE | FALSE | FALSE
9832 | MRT-YL19-P0ABA-150003 | 2019-11-11 | MRT-HK-REC-TT-190904 | FA | 1 | TRUE | TRUE | FALSE
9833 | MRT-FF01-P0SGJ-135458 | 2019-11-11 | MRT-HK-REC-TT-190903 | FI | 0 | TRUE | FALSE | FALSE
9834 | MRT-FF01-P0SGJ-135455 | 2019-11-11 | MRT-HK-REC-TT-190903 | FI | 0 | TRUE | FALSE | FALSE
9835 | MRT-FF00-P0SGA-135654 | 2019-11-11 | MRT-HK-REC-TT-190903 | FI | 2 | TRUE | TRUE | FALSE
9836 | MRT-YE16-P2UMA-150136 | 2019-11-11 | MRT-HK-REC-TT-190905 | FA | 1 | TRUE | TRUE | FALSE
9837 | MRT-DN02-P0BAA-150908 | 2019-11-11 | MRT-HK-REC-TT-190906 | FA | 0 | TRUE | FALSE | FALSE
9838 | MRT-XJ00-P2LB-142000 | 2019-11-11 | MRT-DS-REC-TT-190224-FC | FI | 0 | TRUE | FALSE | FALSE
9839 | MRT-XJ00-P3LB-143000 | 2019-11-11 | MRT-DS-REC-TT-190224-FC | FI | 0 | TRUE | FALSE | FALSE
9840 | MRT-XJ00-P3LB-144000 | 2019-11-11 | MRT-DS-REC-TT-190224-FC | FI | 0 | TRUE | FALSE | FALSE
9841 | MRT-FF03-P3SGE-135406 | 2019-11-12 | MRT-HK-REC-TT-190907 | FI | 0 | TRUE | FALSE | FALSE
9842 | MRT-FF03-P3SGC-135417 | 2019-11-12 | MRT-HK-REC-TT-190907 | FI | 0 | TRUE | FALSE | FALSE
9843 | MRT-FF00-P0SGA-135653 | 2019-11-12 | MRT-HK-REC-TT-190907 | FA | 0 | TRUE | FALSE | FALSE
9844 | MRT-DN05-P0SGA-135472 | 2019-11-12 | MRT-HK-REC-TT-190907 | FA | 0 | TRUE | FALSE | FALSE
9845 | MRT-DN05-P0AYE-135473 | 2019-11-12 | MRT-HK-REC-TT-190907 | FA | 0 | TRUE | FALSE | FALSE
9846 | MRT-DD02-P0SGA-135482 | 2019-11-12 | MRT-HK-REC-TT-190907 | FI | 0 | TRUE | FALSE | FALSE
9847 | MRT-XG02-P3SGK-135428 | 2019-11-12 | MRT-HK-REC-TT-190907 | FA | 0 | TRUE | FALSE | FALSE
9848 | MRT-XG02-P3SGC-135419 | 2019-11-12 | MRT-HK-REC-TT-190907 | FA | 0 | TRUE | FALSE | FALSE
9849 | MRT-XG02-P3SGC-135416 | 2019-11-12 | MRT-HK-REC-TT-190907 | FA | 0 | TRUE | FALSE | FALSE
9850 | MRT-FF01-P3SGA-135430 | 2019-11-12 | MRT-HK-REC-TT-190907 | FA | 0 | TRUE | FALSE | FALSE
9851 | MRT-FF02-P3AYE-135626 | 2019-11-12 | MRT-HK-REC-TT-190908 | FI | 0 | TRUE | FALSE | FALSE
9852 | MRT-FF02-P0AYE-135617 | 2019-11-12 | MRT-HK-REC-TT-190908 | FI | 0 | TRUE | FALSE | FALSE
9853 | MRT-FF02-P0AYE-135616 | 2019-11-12 | MRT-HK-REC-TT-190908 | FI | 0 | TRUE | FALSE | FALSE
9854 | MRT-FF00-P0SGA-135464 | 2019-11-12 | MRT-HK-REC-TT-190909 | FA | 0 | TRUE | FALSE | FALSE
9855 | MRT-BT00-P0SGA-135485 | 2019-11-12 | MRT-HK-REC-TT-190910 | FA | 3 | TRUE | TRUE | FALSE
9856 | MRT-DN04-P0SGA-135478 | 2019-11-12 | MRT-HK-REC-TT-190910 | FA | 2 | TRUE | TRUE | FALSE
9857 | MRT-DD03-P0GEN-135702 | 2019-11-12 | MRT-HK-REC-TT-190911 | FA | 1 | TRUE | TRUE | FALSE
9858 | MRT-CC04-P0ULY-185254 | 2019-11-13 | MRT-HK-REC-TT-190912 | FA | 0 | TRUE | FALSE | FALSE
9859 | MRT-CC04-P0ULY-185253 | 2019-11-13 | MRT-HK-REC-TT-190912 | FA | 0 | TRUE | FALSE | FALSE
9860 | MRT-CC04-P0ULY-185252 | 2019-11-13 | MRT-HK-REC-TT-190912 | FA | 0 | TRUE | FALSE | FALSE
9861 | MRT-CC04-P0ULY-185251 | 2019-11-13 | MRT-HK-REC-TT-190912 | FA | 0 | TRUE | FALSE | FALSE
9862 | MRT-CC04-P0UXA-185276 | 2019-11-13 | MRT-HK-REC-TT-190912 | FA | 0 | TRUE | FALSE | FALSE
9863 | MRT-CC04-P0UGG-185246 | 2019-11-13 | MRT-HK-REC-TT-190912 | FA | 0 | TRUE | FALSE | FALSE
9864 | MRT-CC04-P0SGE-185221 | 2019-11-13 | MRT-HK-REC-TT-190912 | FA | 0 | TRUE | FALSE | FALSE
9865 | MRT-CC04-P0SGE-185223 | 2019-11-13 | MRT-HK-REC-TT-190912 | FA | 0 | TRUE | FALSE | FALSE
9866 | MRT-CA03-P0UGA-186649 | 2019-11-13 | MRT-HK-REC-TT-190913 | FA | 0 | TRUE | FALSE | FALSE
9867 | MRT-CA03-P0UGA-186648 | 2019-11-13 | MRT-HK-REC-TT-190913 | FA | 1 | TRUE | TRUE | FALSE
9868 | MRT-DM01-P0GHE-145084 | 2019-11-13 | MRT-HK-REC-TT-190914 | FA | 1 | TRUE | TRUE | FALSE
9869 | MRT-BT00-P0GEN-135892 | 2019-11-13 | MRT-HK-REC-TT-190915 | FA | 0 | TRUE | FALSE | FALSE
9870 | MRT-US02-P0BJL-150708 | 2019-11-13 | MRT-HK-REC-TT-190917 | FA | 1 | TRUE | TRUE | FALSE
9871 | MRT-YU02-P0BJL-150707 | 2019-11-13 | MRT-HK-REC-TT-190917 | FA | 1 | TRUE | TRUE | FALSE
9872 | MRT-QM03-P0ZEN-185027 | 2019-11-13 | MRT-HK-REC-TT-190916 | FI | 1 | TRUE | TRUE | FALSE
9873 | MRT-QM03-P0ZEN-185026 | 2019-11-13 | MRT-HK-REC-TT-190916 | FI | 1 | TRUE | TRUE | FALSE
9874 | MRT-CA00-P0UMA-180009 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9875 | MRT-CA00-P0UMA-180010 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9876 | MRT-CA00-P0UMA-180011 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9877 | MRT-CA00-P0UMA-180013 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9878 | MRT-CA00-P0UMA-180014 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9879 | MRT-CA00-P0UMA-180015 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9880 | MRT-CA00-P0UMA-180016 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9881 | MRT-CA00-P0UMA-180017 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9882 | MRT-CA00-P0UMA-180019 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9883 | MRT-CA00-P0UMA-180021 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9884 | MRT-CA00-P0UMA-180023 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 3 | TRUE | TRUE | FALSE
9885 | MRT-CA03-P0UMA-180036 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9886 | MRT-CA03-P0UMA-180037 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9887 | MRT-CA03-P0UMA-180039 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9888 | MRT-CA01-P0UMA-180044 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 4 | TRUE | TRUE | FALSE
9889 | MRT-CA02-P0UMA-180045 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 4 | TRUE | TRUE | FALSE
9890 | MRT-CA00-P0UMA-180047 | 2019-11-14 | MRT-DS-REC-TT-190210-FC | FC | 5 | TRUE | TRUE | FALSE
9891 | MRT-YE16-P2UMA-150329 | 2019-11-14 | MRT-HK-REC-TT-190918 | FA | 1 | TRUE | TRUE | FALSE
9892 | MRT-XJ00-P2PAB-142100 | 2019-11-14 | MRT-DS-REC-TT-190226-FC | FC | 3B | TRUE | TRUE | FALSE
9893 | MRT-DD04-P0GEN-135389 | 2019-11-14 | MRT-HK-REC-TT-190919 | FI | 1 | TRUE | TRUE | FALSE
9894 | MRT-FF02-P0AYE-135643 | 2019-11-14 | MRT-HK-REC-TT-190920 | FA | 0 | TRUE | FALSE | FALSE
9895 | MRT-FF02-P0AYE-135640 | 2019-11-14 | MRT-HK-REC-TT-190920 | FA | 0 | TRUE | FALSE | FALSE
9896 | MRT-BF05-P0ZEN-175023 | 2019-11-14 | MRT-HK-REC-TT-190924 | FA | 1 | TRUE | TRUE | FALSE
9897 | MRT-XB02-P0UMA-180004 | 2019-11-14 | MRT-HK-REC-TT-190924 | FC | 8 | TRUE | TRUE | FALSE
9898 | MRT-CA01-P0UMA-180005 | 2019-11-14 | MRT-HK-REC-TT-190924 | FC | 7 | TRUE | TRUE | FALSE
9899 | MRT-CA01-P0UMA-180006 | 2019-11-14 | MRT-HK-REC-TT-190924 | FC | 6 | TRUE | TRUE | FALSE
9900 | MRT-CA01-P0UMA-180007 | 2019-11-14 | MRT-HK-REC-TT-190924 | FC | 6 | TRUE | TRUE | FALSE
9901 | MRT-FF02-P0AYE-135619 | 2019-11-14 | MRT-HK-REC-TT-190922 | FI | 0 | TRUE | TRUE | FALSE
9902 | MRT-FF02-P0AYE-135639 | 2019-11-14 | MRT-HK-REC-TT-190922 | FI | 0 | TRUE | FALSE | FALSE
9903 | MRT-FF02-P0AYE-135641 | 2019-11-14 | MRT-HK-REC-TT-190922 | FI | 0 | TRUE | FALSE | FALSE
9904 | MRT-FF02-P3AYE-135629 | 2019-11-14 | MRT-HK-REC-TT-190922 | FI | 0 | TRUE | FALSE | FALSE
9905 | MRT-FF02-P3AYE-135630 | 2019-11-14 | MRT-HK-REC-TT-190922 | FI | 0 | TRUE | FALSE | FALSE
9906 | MRT-YM01-P0GDG-135048 | 2019-11-14 | MRT-HK-REC-TT-190922 | FI | 0 | TRUE | FALSE | FALSE
9907 | MRT-YL15-P0GDG-135055 | 2019-11-14 | MRT-HK-REC-TT-190922 | FI | 0 | TRUE | FALSE | FALSE
9908 | MRT-FF01-P0SGA-135488 | 2019-11-14 | MRT-HK-REC-TT-190922 | FA | 1 | TRUE | TRUE | FALSE
9909 | MRT-FF01-P0SGJ-135444 | 2019-11-15 | MRT-HK-REC-TT-190923 | FA | 0 | TRUE | FALSE | FALSE
9910 | MRT-FF01-P0SGJ-135456 | 2019-11-15 | MRT-HK-REC-TT-190923 | FA | 0 | TRUE | FALSE | FALSE
9911 | MRT-FF01-P0SGJ-135447 | 2019-11-15 | MRT-HK-REC-TT-190923 | FA | 0 | TRUE | FALSE | FALSE
9912 | MRT-FF01-P0SGJ-135442 | 2019-11-15 | MRT-HK-REC-TT-190923 | FA | 0 | TRUE | FALSE | FALSE
9913 | MRT-FF01-P0SGJ-135438 | 2019-11-15 | MRT-HK-REC-TT-190923 | FA | 0 | TRUE | FALSE | FALSE
9914 | MRT-FF03-P0SGF-135423 | 2019-11-15 | MRT-HK-REC-TT-190923 | FI | 0 | TRUE | FALSE | FALSE
9915 | MRT-FF03-P3SGC-135416 | 2019-11-15 | MRT-HK-REC-TT-190921 | FI | 0 | TRUE | FALSE | FALSE
9916 | MRT-FF01-P0SGJ-135454 | 2019-11-15 | MRT-HK-REC-TT-190921 | FA | 0 | TRUE | FALSE | FALSE
9917 | MRT-FF01-P0SGJ-135453 | 2019-11-15 | MRT-HK-REC-TT-190921 | FA | 0 | TRUE | FALSE | FALSE
9918 | MRT-FF01-P0SGJ-135451 | 2019-11-15 | MRT-HK-REC-TT-190921 | FA | 0 | TRUE | FALSE | FALSE
9919 | MRT-FF01-P0SGJ-135449 | 2019-11-15 | MRT-HK-REC-TT-190921 | FA | 0 | TRUE | FALSE | FALSE
9920 | MRT-FF01-P0SGJ-135445 | 2019-11-15 | MRT-HK-REC-TT-190921 | FA | 0 | TRUE | FALSE | FALSE
9921 | MRT-FF01-P0SGJ-135439 | 2019-11-15 | MRT-HK-REC-TT-190921 | FA | 0 | TRUE | FALSE | FALSE
9922 | MRT-YL16-P0SAK-135565 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9923 | MRT-HM03-P0SA-135800 | 2019-11-15 | MRT-HK-REC-TT-190926 | FA | 0 | TRUE | FALSE | FALSE
9924 | MRT-HM03-P0SAE-135799 | 2019-11-15 | MRT-HK-REC-TT-190926 | FA | 0 | TRUE | FALSE | FALSE
9925 | MRT-HM03-P0SA-135798 | 2019-11-15 | MRT-HK-REC-TT-190926 | FA | 0 | TRUE | FALSE | FALSE
9926 | MRT-HM03-P0SA-135797 | 2019-11-15 | MRT-HK-REC-TT-190926 | FA | 0 | TRUE | FALSE | FALSE
9927 | MRT-HM03-P0SAL-135795 | 2019-11-15 | MRT-HK-REC-TT-190926 | FA | 0 | TRUE | FALSE | FALSE
9928 | MRT-HM03-P0SA-135794 | 2019-11-15 | MRT-HK-REC-TT-190926 | FA | 0 | TRUE | FALSE | FALSE
9929 | MRT-HM03-P0SAF-135793 | 2019-11-15 | MRT-HK-REC-TT-190926 | FA | 0 | TRUE | FALSE | FALSE
9930 | MRT-HM03-P0SAK-135792 | 2019-11-15 | MRT-HK-REC-TT-190926 | FA | 0 | TRUE | FALSE | FALSE
9931 | MRT-HM03-P0SAK-135791 | 2019-11-15 | MRT-HK-REC-TT-190926 | FA | 0 | TRUE | FALSE | FALSE
9932 | MRT-HM03-P0SAG-135790 | 2019-11-15 | MRT-HK-REC-TT-190926 | FA | 0 | TRUE | FALSE | FALSE
9933 | MRT-HM03-P0SAC-135786 | 2019-11-15 | MRT-HK-REC-TT-190926 | FA | 0 | TRUE | FALSE | FALSE
9934 | MRT-YL16-P0SAC-135561 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9935 | MRT-YL16-P0SAH-135562 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9936 | MRT-YL16-P0SAG-135563 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9937 | MRT-YL16-P0SAK-135564 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9938 | MRT-YL16-P0SAF-135566 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9939 | MRT-YL16-P0SA-135567 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9940 | MRT-YL16-P0SAL-135568 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9941 | MRT-YL16-P0SAF-135569 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9942 | MRT-YL16-P0SA-135570 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9943 | MRT-YL16-P0SA-135571 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9944 | MRT-YL16-P0SAE-135572 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9945 | MRT-YL16-P0SA-135573 | 2019-11-15 | MRT-HK-REC-TT-190926 | FI | 0 | TRUE | FALSE | FALSE
9946 | MRT-DS00-P0GN-135869 | 2019-11-15 | MRT-HK-REC-TT-190927 | FA | 2 | TRUE | TRUE | FALSE
9947 | MRT-XB02-P0SGA-135603 | 2019-11-15 | MRT-HK-REC-TT-190928 | FA | 0 | TRUE | FALSE | FALSE
9948 | MRT-QM04-P0SA-135771 | 2019-11-18 | MRT-HK-REC-TT-190933 | FA | 1 | TRUE | TRUE | FALSE
9949 | MRT-QM04-P0SA-135772 | 2019-11-18 | MRT-HK-REC-TT-190934 | FA | 1 | TRUE | TRUE | FALSE
9950 | MRT-CQ02-P0SGA-135469 | 2019-11-18 | MRT-HK-REC-TT-190929 | FA | 0 | TRUE | FALSE | FALSE
9951 | MRT-CQ02-P0AYE-135470 | 2019-11-18 | MRT-HK-REC-TT-190929 | FA | 0 | TRUE | FALSE | FALSE
9952 | MRT-FF02-P3AYE-135631 | 2019-11-18 | MRT-HK-REC-TT-190930 | FA | 0 | TRUE | FALSE | FALSE
9953 | MRT-FF02-P3AYE-135624 | 2019-11-18 | MRT-HK-REC-TT-190930 | FA | 0 | TRUE | FALSE | FALSE
9954 | MRT-FF02-P0AYE-135618 | 2019-11-18 | MRT-HK-REC-TT-190930 | FA | 0 | TRUE | FALSE | FALSE
9955 | MRT-FF02-P0AYE-135615 | 2019-11-18 | MRT-HK-REC-TT-190930 | FA | 0 | TRUE | FALSE | FALSE
9956 | MRT-DM01-P0SGA-135474 | 2019-11-18 | MRT-HK-REC-TT-190931 | FI | 0 | TRUE | FALSE | FALSE
9957 | MRT-XK00-P2PAB-142000 | 2019-11-18 | MRT-DS-REC-TT-190227-FC | FC | 2 | TRUE | TRUE | FALSE
9958 | MRT-XJ00-P0LBG-141000 | 2019-11-19 | MRT-DS-REC-TT-190228-FC | FC | 1A | TRUE | TRUE | FALSE
9959 | MRT-YT01-P3GC-135163 | 2019-11-19 | MRT-HK-REC-TT-190935 | FA | 1 | TRUE | TRUE | FALSE
9960 | MRT-YT01-P3GC-135165 | 2019-11-19 | MRT-HK-REC-TT-190935 | FA | 1 | TRUE | TRUE | FALSE
9961 | MRT-XA00-P2PBB-135232 | 2019-11-19 | MRT-HK-REC-TT-190937 | FI | 0 | TRUE | FALSE | FALSE
9962 | MRT-XA00-P3PBB-135233 | 2019-11-19 | MRT-HK-REC-TT-190937 | FI | 0 | TRUE | FALSE | FALSE
9963 | MRT-XA00-P2PBB-135234 | 2019-11-19 | MRT-HK-REC-TT-190937 | FI | 0 | TRUE | FALSE | FALSE
9964 | MRT-XA00-P3PBB-135235 | 2019-11-19 | MRT-HK-REC-TT-190937 | FI | 0 | TRUE | FALSE | FALSE
9965 | MRT-CT00-P0QHA-125412 | 2019-11-19 | MRT-HK-REC-TT-190936 | FI | 0 | TRUE | FALSE | FALSE
9966 | MRT-YL19-P0SA-135765 | 2019-11-19 | MRT-HK-REC-TT-190938 | FA | 0 | TRUE | FALSE | FALSE
9967 | MRT-QM00-P0SA-135777 | 2019-11-19 | MRT-HK-REC-TT-190939 | FI | 1 | TRUE | TRUE | FALSE
9968 | MRT-XK00-P3PAB-143000 | 2019-11-20 | MRT-DS-REC-TT-190225-FC | FC | 1 | TRUE | TRUE | FALSE
9969 | MRT-XK00-P3LBA-143000 | 2019-11-20 | MRT-DS-REC-TT-190225-FC | FC | 1 | TRUE | TRUE | FALSE
9970 | MRT-XK00-P3PGB-143000 | 2019-11-20 | MRT-DS-REC-TT-190225-FC | FC | 1 | TRUE | TRUE | FALSE
9971 | MRT-XK00-P3LAB-143000 | 2019-11-20 | MRT-DS-REC-TT-190225-FC | FC | 1 | TRUE | TRUE | FALSE
9972 | MRT-XK00-P3LBG-143000 | 2019-11-20 | MRT-DS-REC-TT-190225-FC | FC | 1 | TRUE | TRUE | FALSE
9973 | MRT-XK00-P3LCA-143000 | 2019-11-20 | MRT-DS-REC-TT-190225-FC | FC | 1 | TRUE | TRUE | FALSE
9974 | MRT-XK00-P3LCM-143000 | 2019-11-20 | MRT-DS-REC-TT-190225-FC | FC | 1 | TRUE | TRUE | FALSE
9975 | MRT-XK00-P3ACW-143000 | 2019-11-20 | MRT-DS-REC-TT-190225-FC | FC | 1 | TRUE | TRUE | FALSE
9976 | MRT-XK00-P3MAM-142000 | 2019-11-20 | MRT-DS-REC-TT-190225-FC | FC | 1 | TRUE | TRUE | FALSE
9977 | MRT-QM00-P0SA-135778 | 2019-11-20 | MRT-HK-REC-TT-190941 | FI | 1 | TRUE | TRUE | FALSE
9978 | MRT-XG02-P2SCA-120004 | 2019-11-20 | MRT-DS-REC-TT-190230 | FC | 6 | TRUE | TRUE | FALSE
9979 | MRT-XG02-P2SCA-120005 | 2019-11-20 | MRT-DS-REC-TT-190230 | FC | 6 | TRUE | TRUE | FALSE
9980 | MRT-XG02-P2SCA-120006 | 2019-11-20 | MRT-DS-REC-TT-190230 | FC | 6 | TRUE | TRUE | FALSE
9981 | MRT-XG02-P3SCA-120005 | 2019-11-20 | MRT-DS-REC-TT-190230 | FC | 6 | TRUE | TRUE | FALSE
9982 | MRT-XG02-P3SCA-120006 | 2019-11-20 | MRT-DS-REC-TT-190230 | FC | 6 | TRUE | TRUE | FALSE
9983 | MRT-QM03-P0GHE-145068 | 2019-11-21 | MRT-HK-REC-TT-190942 | FA | 2 | TRUE | TRUE | FALSE
9984 | MRT-FF01-P0SGJ-135446 | 2019-11-21 | MRT-HK-REC-TT-190943 | FA | 0 | TRUE | FALSE | FALSE
9985 | MRT-DT03-P0SGA-135479 | 2019-11-21 | MRT-HK-REC-TT-190943 | FA | 0 | TRUE | FALSE | FALSE
9986 | MRT-FF02-P0AYE-135612 | 2019-11-21 | MRT-HK-REC-TT-190945 | FA | 0 | TRUE | FALSE | FALSE
9987 | MRT-FF02-P0AYE-135611 | 2019-11-21 | MRT-HK-REC-TT-190945 | FA | 0 | TRUE | FALSE | FALSE
9988 | MRT-FF02-P0AYE-135642 | 2019-11-21 | MRT-HK-REC-TT-190945 | FI | 0 | TRUE | FALSE | FALSE
9989 | MRT-HM02-P0SAE-135598 | 2019-11-21 | MRT-HK-REC-TT-190944 | FI | 1 | TRUE | TRUE | FALSE
9990 | MRT-HM02-P0SA-135596 | 2019-11-21 | MRT-HK-REC-TT-190944 | FI | 1 | TRUE | TRUE | FALSE
9991 | MRT-HM02-P0SAK-135591 | 2019-11-21 | MRT-HK-REC-TT-190944 | FI | 1 | TRUE | TRUE | FALSE
9992 | MRT-HM02-P0SAG-135527 | 2019-11-21 | MRT-HK-REC-TT-190944 | FI | 1 | TRUE | TRUE | FALSE
9993 | MRT-HM02-P0SAC-135587 | 2019-11-21 | MRT-HK-REC-TT-190944 | FI | 1 | TRUE | TRUE | FALSE
9994 | MRT-HM02-P0SAH-135588 | 2019-11-21 | MRT-HK-REC-TT-190944 | FI | 1 | TRUE | TRUE | FALSE
9995 | MRT-XK00-P0GDY-135062 | 2019-11-21 | MRT-HK-REC-TT-190946 | FI | 1 | TRUE | TRUE | FALSE
9996 | MRT-XB02-P0UMA-180004 | 2019-11-21 | MRT-HK-REC-TT-190947 | FC | 9 | TRUE | TRUE | FALSE
9997 | MRT-CA01-P0UMA-180005 | 2019-11-21 | MRT-HK-REC-TT-190947 | FC | 8 | TRUE | TRUE | FALSE
9998 | MRT-CA01-P0UMA-180007 | 2019-11-21 | MRT-HK-REC-TT-190947 | FC | 7 | TRUE | TRUE | FALSE
9999 | MRT-DN02-P2SM-120001 | 2019-11-22 | MRT-DS-REC-TT-190231 | FA | 1 | TRUE | TRUE | FALSE
10000 | MRT-CC02-P2UAG-170307 | 2019-11-25 | MRT-DS-REC-TT-190220-FC | FC | 4 | TRUE | TRUE | FALSE
10001 | MRT-CC02-P2UAG-170308 | 2019-11-25 | MRT-DS-REC-TT-190220-FC | FC | 5 | TRUE | TRUE | FALSE
10002 | MRT-CC02-P3UAG-170307 | 2019-11-25 | MRT-DS-REC-TT-190220-FC | FC | 3 | TRUE | TRUE | FALSE
10003 | MRT-CC02-P3UAG-170308 | 2019-11-25 | MRT-DS-REC-TT-190220-FC | FC | 4 | TRUE | TRUE | FALSE
10004 | MRT-XG02-P2LB-122022 | 2019-11-25 | MRT-DS-REC-TT-190213-FC | FC | 7 | TRUE | TRUE | FALSE
10005 | MRT-XG02-P3LB-122022 | 2019-11-25 | MRT-DS-REC-TT-190213-FC | FC | 4 | TRUE | TRUE | FALSE
10006 | MRT-XH01-P2ULY-142000 | 2019-11-25 | MRT-DS-REC-TT-190216-FC | FC | 3 | TRUE | TRUE | FALSE
10007 | MRT-XH01-P3ULY-143000 | 2019-11-25 | MRT-DS-REC-TT-190216-FC | FC | 3 | TRUE | TRUE | FALSE
10008 | MRT-XH01-P3ULY-144000 | 2019-11-25 | MRT-DS-REC-TT-190216-FC | FC | 3 | TRUE | TRUE | FALSE
10009 | MRT-YE06-P0BAU-150160 | 2019-11-25 | MRT-HK-REC-TT-190948 | FA | 2 | TRUE | TRUE | FALSE
10010 | MRT-DS00-P3GC-135842 | 2019-11-25 | MRT-HK-REC-TT-190950 | FI | 2 | TRUE | TRUE | FALSE
10011 | MRT-FF02-P0AYE-135647 | 2019-11-25 | MRT-HK-REC-TT-190951 | FA | 0 | TRUE | FALSE | FALSE
10012 | MRT-QM01-P0SMU-125052 | 2019-11-25 | MRT-HK-REC-TT-190952 | FA | 0 | TRUE | FALSE | FALSE
10013 | MRT-QM01-P0SMU-125051 | 2019-11-25 | MRT-HK-REC-TT-190952 | FA | 0 | TRUE | FALSE | FALSE
10014 | MRT-XG02-P2LB-122022 | 2019-11-26 | MRT-DS-REC-TT-190233 | FC | 8 | TRUE | TRUE | FALSE
10015 | MRT-XG02-P3LB-122022 | 2019-11-26 | MRT-DS-REC-TT-190233 | FC | 5 | TRUE | TRUE | FALSE
10016 | MRT-XG02-P2LB-122022 | 2019-11-27 | MRT-DS-REC-TT-190233-FC | FC | 8 | TRUE | TRUE | FALSE
10017 | MRT-XG02-P3LB-122022 | 2019-11-27 | MRT-DS-REC-TT-190233-FC | FC | 5 | TRUE | TRUE | FALSE
10018 | MRT-QM03-P0ZEN-155040 | 2019-11-27 | MRT-HK-REC-TT-190953 | FA | 1 | TRUE | TRUE | FALSE
10019 | MRT-QM03-P0ZEN-155041 | 2019-11-27 | MRT-HK-REC-TT-190953 | FA | 1 | TRUE | TRUE | FALSE
10020 | MRT-QM00-P0SA-135777 | 2019-11-28 | MRT-HK-REC-TT-190955 | FA | 2 | TRUE | TRUE | FALSE
10021 | MRT-DN04-P0QHB-125439 | 2019-11-28 | MRT-HK-REC-TT-190956 | FA | 1 | TRUE | TRUE | FALSE
10022 | MRT-DM02-P3CJJ-240106 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10023 | MRT-DM02-P2MAV-220105 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10024 | MRT-DM02-P3CJJ-240115 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10025 | MRT-DM02-P3MAV-220170 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10026 | MRT-DM02-P2MAV-240136 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10027 | MRT-DM02-P3MAV-220093 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10028 | MRT-DM02-P2MAA-230180 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10029 | MRT-DM02-P3MAA-230191 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10030 | MRT-DM02-P2MAW-220158 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10031 | MRT-DM02-P3MAW-220167 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10032 | MRT-DM02-P3MAA-220164 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10033 | MRT-DM02-P2MAW-220108 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10034 | MRT-DM02-P3MAW-220100 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10035 | MRT-DM02-P3MAD-240182 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10036 | MRT-DM02-P3MAA-220189 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10037 | MRT-YF02-P3MAD-240178 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10038 | MRT-YT02-P3MAD-240177 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10039 | MRT-YD00-P3MAA-220214 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10040 | MRT-CQ02-P2CJJ-240116 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10041 | MRT-CQ02-P2MAA-220153 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10042 | MRT-CQ02-P2MAV-220106 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10043 | MRT-CQ02-P2CJJ-240125 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10044 | MRT-CQ02-P3CJJ-240117 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10045 | MRT-CQ02-P3MAX-220147 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10046 | MRT-CQ02-P3MAV-220172 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10047 | MRT-CQ02-P2MAV-240138 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10048 | MRT-CQ02-P3MAV-240137 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10049 | MRT-CQ02-P2MAA-230181 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10050 | MRT-CQ02-P2LBS-220088 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10051 | MRT-CQ02-P3LBA-220084 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10052 | MRT-CQ02-P2MAW-220109 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10053 | MRT-CQ02-P3MAW-220101 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10054 | MRT-CQ02-P3MAA-220131 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10055 | MRT-CQ02-P3MAD-240184 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10056 | MRT-DB00-P3MAA-210188 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10057 | MRT-CY05-P2CJJ-240117 | 2019-11-28 | MRT-DS-REC-TT-190234-FC | FI | 0 | TRUE | FALSE | FALSE
10058 | MRT-DN05-P2CJJ-240115 | 2019-11-28 | MRT-DS-REC-TT-190235 | FA | 0 | TRUE | FALSE | FALSE
10059 | MRT-DN05-P3CJJ-240107 | 2019-11-28 | MRT-DS-REC-TT-190235 | FA | 0 | TRUE | FALSE | FALSE
10060 | MRT-DN05-P2CJJ-240124 | 2019-11-28 | MRT-DS-REC-TT-190235 | FA | 0 | TRUE | FALSE | FALSE
10061 | MRT-DN05-P3CJJ-240116 | 2019-11-28 | MRT-DS-REC-TT-190235 | FA | 0 | TRUE | FALSE | FALSE
10062 | MRT-DN05-P3MAX-220146 | 2019-11-28 | MRT-DS-REC-TT-190235 | FA | 0 | TRUE | FALSE | FALSE
10063 | MRT-DN05-P3MAV-220171 | 2019-11-28 | MRT-DS-REC-TT-190235 | FA | 0 | TRUE | FALSE | FALSE
10064 | MRT-DN05-P2MAV-240137 | 2019-11-28 | MRT-DS-REC-TT-190235 | FA | 0 | TRUE | FALSE | FALSE
10065 | MRT-DN05-P3MAV-240136 | 2019-11-28 | MRT-DS-REC-TT-190235 | FA | 0 | TRUE | FALSE | FALSE
10066 | MRT-DN05-P3MAV-220094 | 2019-11-28 | MRT-DS-REC-TT-190235 | FA | 0 | TRUE | FALSE | FALSE
10067 | MRT-DN05-P3MAD-240183 | 2019-11-28 | MRT-DS-REC-TT-190235 | FA | 0 | TRUE | FALSE | FALSE
10068 | MRT-DN05-P3MAM-220140 | 2019-11-28 | MRT-DS-REC-TT-190235 | FA | 0 | TRUE | FALSE | FALSE
10069 | MRT-DD00-P0BAT-155174 | 2019-11-28 | MRT-HK-REC-TT-190954 | FI | 0 | TRUE | FALSE | FALSE
10070 | MRT-DD00-P0BAT-155173 | 2019-11-28 | MRT-HK-REC-TT-190954 | FI | 0 | TRUE | FALSE | FALSE
10071 | MRT-DD00-P0BAT-155172 | 2019-11-28 | MRT-HK-REC-TT-190954 | FI | 0 | TRUE | FALSE | FALSE
10072 | MRT-DD00-P0BAT-155171 | 2019-11-28 | MRT-HK-REC-TT-190954 | FI | 0 | TRUE | FALSE | FALSE
10073 | MRT-DD00-P0BAT-155170 | 2019-11-28 | MRT-HK-REC-TT-190954 | FI | 0 | TRUE | FALSE | FALSE
10074 | MRT-FF01-P0SGA-135654 | 2019-11-28 | MRT-HK-REC-TT-190957 | FI | 0 | TRUE | FALSE | FALSE
10075 | MRT-FF01-P0SGA-135653 | 2019-11-28 | MRT-HK-REC-TT-190957 | FI | 0 | TRUE | FALSE | FALSE
10076 | MRT-FF02-P0AYE-135645 | 2019-11-28 | MRT-HK-REC-TT-190957 | FI | 0 | TRUE | FALSE | FALSE
10077 | MRT-CY05-P0SGA-135471 | 2019-11-28 | MRT-HK-REC-TT-190958 | FI | 0 | TRUE | FALSE | FALSE
10078 | MRT-DN03-P0GEN-135719 | 2019-11-28 | MRT-HK-REC-TT-190959 | FA | 0 | TRUE | FALSE | FALSE
10079 | MRT-CC04-P0UGG-186261 | 2019-11-29 | MRT-HK-REC-TT-190960 | FA | 0 | TRUE | FALSE | FALSE
10080 | MRT-CC04-P0UXA-185271 | 2019-11-29 | MRT-HK-REC-TT-190960 | FA | 0 | TRUE | FALSE | FALSE
10081 | MRT-CC04-P0UGA-185241 | 2019-11-29 | MRT-HK-REC-TT-190960 | FA | 0 | TRUE | FALSE | FALSE
10082 | MRT-DM01-P0QHB-125418 | 2019-12-02 | MRT-HK-REC-TT-190961 | FA | 1 | TRUE | TRUE | FALSE
10083 | MRT-FF01-P0SGJ-135440 | 2019-12-02 | MRT-HK-REC-TT-190961 | FA | 1 | TRUE | TRUE | FALSE
10084 | MRT-DD00-P0BAT-155175 | 2019-12-02 | MRT-HK-REC-TT-190964 | FA | 0 | TRUE | FALSE | FALSE
10085 | MRT-DD00-P0BAT-155169 | 2019-12-02 | MRT-HK-REC-TT-190963 | FA | 1 | TRUE | TRUE | FALSE
10086 | MRT-DD00-P0BAT-155168 | 2019-12-02 | MRT-HK-REC-TT-190963 | FA | 1 | TRUE | TRUE | FALSE
10087 | MRT-DD00-P0BAT-155167 | 2019-12-02 | MRT-HK-REC-TT-190963 | FA | 1 | TRUE | TRUE | FALSE
10088 | MRT-DD00-P0BAT-155166 | 2019-12-02 | MRT-HK-REC-TT-190963 | FA | 1 | TRUE | TRUE | FALSE
10089 | MRT-DD00-P0BAT-155165 | 2019-12-02 | MRT-HK-REC-TT-190963 | FA | 1 | TRUE | TRUE | FALSE
10090 | MRT-DD00-P0BAT-155164 | 2019-12-02 | MRT-HK-REC-TT-190963 | FA | 1 | TRUE | TRUE | FALSE
10091 | MRT-DD00-P0BAT-155160 | 2019-12-02 | MRT-HK-REC-TT-190963 | FA | 1 | TRUE | TRUE | FALSE
10092 | MRT-XG02-P2LB-122022 | 2019-12-03 | MRT-DS-REC-TT-190237 | FC | 9 | TRUE | TRUE | FALSE
10093 | MRT-XG02-P3LB-122022 | 2019-12-03 | MRT-DS-REC-TT-190237 | FC | 6 | TRUE | TRUE | FALSE
10094 | MRT-XG02-P2SCA-120004 | 2019-12-04 | MRT-DS-REC-TT-190230-FC | FC | 6 | TRUE | TRUE | FALSE
10095 | MRT-XG02-P2SCA-120005 | 2019-12-04 | MRT-DS-REC-TT-190230-FC | FC | 6 | TRUE | TRUE | FALSE
10096 | MRT-XG02-P2SCA-120006 | 2019-12-04 | MRT-DS-REC-TT-190230-FC | FC | 6 | TRUE | TRUE | FALSE
10097 | MRT-XG02-P3SCA-120005 | 2019-12-04 | MRT-DS-REC-TT-190230-FC | FC | 6 | TRUE | TRUE | FALSE
10098 | MRT-XG02-P3SCA-120006 | 2019-12-04 | MRT-DS-REC-TT-190230-FC | FC | 6 | TRUE | TRUE | FALSE
10099 | MRT-CA01-P0USG-186894 | 2019-12-04 | MRT-HK-REC-TT-190966 | FA | 2 | TRUE | TRUE | FALSE
10100 | MRT-YD08-P0QHY-125473 | 2019-12-04 | MRT-HK-REC-TT-190962 | FI | 0 | TRUE | FALSE | FALSE
10101 | MRT-FF02-P0AYE-135646 | 2019-12-04 | MRT-HK-REC-TT-190962 | FI | 0 | TRUE | FALSE | FALSE
10102 | MRT-FF01-P0SGA-135652 | 2019-12-04 | MRT-HK-REC-TT-190962 | FI | 0 | TRUE | FALSE | FALSE
10103 | MRT-HM03-P0SAH-135787 | 2019-12-04 | MRT-HK-REC-TT-190967 | FA | 0 | TRUE | FALSE | FALSE
10104 | MRT-XK00-P2LBG-141000 | 2019-12-05 | MRT-DS-REC-TT-190236-FC | FI | 0 | TRUE | FALSE | FALSE
10105 | MRT-XK00-P2LCA-141000 | 2019-12-05 | MRT-DS-REC-TT-190236-FC | FI | 0 | TRUE | FALSE | FALSE
10106 | MRT-XK00-P3LCE-141000 | 2019-12-05 | MRT-DS-REC-TT-190236-FC | FI | 0 | TRUE | FALSE | FALSE
10107 | MRT-XK00-P4LCE-142000 | 2019-12-05 | MRT-DS-REC-TT-190236-FC | FI | 0 | TRUE | FALSE | FALSE
10108 | MRT-XK00-P3LAB-141100 | 2019-12-05 | MRT-DS-REC-TT-190236-FC | FI | 0 | TRUE | FALSE | FALSE
10109 | MRT-XK00-P0EGD-141000 | 2019-12-05 | MRT-DS-REC-TT-190236-FC | FI | 0 | TRUE | FALSE | FALSE
10110 | MRT-XK00-P2LBA-141000 | 2019-12-05 | MRT-DS-REC-TT-190236-FC | FI | 0 | TRUE | FALSE | FALSE
10111 | MRT-XK00-P3LBA-141000 | 2019-12-05 | MRT-DS-REC-TT-190236-FC | FI | 0 | TRUE | FALSE | FALSE
10112 | MRT-XK00-P4LBA-141100 | 2019-12-05 | MRT-DS-REC-TT-190236-FC | FI | 0 | TRUE | FALSE | FALSE
10113 | MRT-XK00-P2LBA-141100 | 2019-12-05 | MRT-DS-REC-TT-190236-FC | FI | 0 | TRUE | FALSE | FALSE
10114 | MRT-XK00-P3LBA-141100 | 2019-12-05 | MRT-DS-REC-TT-190236-FC | FI | 0 | TRUE | FALSE | FALSE
10115 | MRT-XK00-P4LBA-141200 | 2019-12-05 | MRT-DS-REC-TT-190236-FC | FI | 0 | TRUE | FALSE | FALSE
10116 | MRT-HM03-P0SAH-135788 | 2019-12-05 | MRT-HK-REC-TT-190968 | FA | 0 | TRUE | FALSE | FALSE
10117 | MRT-HM03-P0SAH-135789 | 2019-12-05 | MRT-HK-REC-TT-190968 | FA | 0 | TRUE | FALSE | FALSE
10118 | MRT-HM03-P0SAF-135796 | 2019-12-05 | MRT-HK-REC-TT-190968 | FA | 0 | TRUE | FALSE | FALSE
10119 | MRT-YF02-P0GEN-135398 | 2019-12-05 | MRT-HK-REC-TT-190969 | FA | 0 | TRUE | FALSE | FALSE
10120 | MRT-YL16-P0BBY-150083 | 2019-12-06 | MRT-HK-REC-TT-190970 | FA | 0 | TRUE | FALSE | FALSE
10121 | MRT-DD00-P0BAT-155176 | 2019-12-09 | MRT-HK-REC-TT-190965 | FA | 0 | TRUE | FALSE | FALSE
10122 | MRT-DN04-P0BRU-150267 | 2019-12-09 | MRT-HK-REC-TT-190965 | FA | 1 | TRUE | TRUE | FALSE
10123 | MRT-BT00-P0GEN-135889 | 2019-12-09 | MRT-HK-REC-TT-190972 | FA | 0 | TRUE | FALSE | FALSE
10124 | MRT-DD00-P0SGA-135476 | 2019-12-09 | MRT-HK-REC-TT-190973 | FA | 0 | TRUE | FALSE | FALSE
10125 | MRT-BB00-P0QHB-125426 | 2019-12-09 | MRT-HK-REC-TT-190973 | FA | 0 | TRUE | FALSE | FALSE
10126 | MRT-CT00-P0GN-135280 | 2019-12-09 | MRT-HK-REC-TT-190974 | FI | 0 | TRUE | FALSE | FALSE
10127 | MRT-YT01-P0GEN-135334 | 2019-12-09 | MRT-HK-REC-TT-190974 | FA | 0 | TRUE | FALSE | FALSE
10128 | MRT-XK00-P2LBA-142000 | 2019-12-10 | MRT-DS-REC-TT-190239-FC | FC | 2 | TRUE | TRUE | FALSE
10129 | MRT-XK00-P2PAB-142000 | 2019-12-10 | MRT-DS-REC-TT-190239-FC | FC | 3 | TRUE | TRUE | FALSE
10130 | MRT-XK00-P2PGB-142000 | 2019-12-10 | MRT-DS-REC-TT-190239-FC | FC | 2 | TRUE | TRUE | FALSE
10131 | MRT-XK00-P2LAB-142000 | 2019-12-10 | MRT-DS-REC-TT-190239-FC | FC | 2 | TRUE | TRUE | FALSE
10132 | MRT-XK00-P2LBG-142000 | 2019-12-10 | MRT-DS-REC-TT-190239-FC | FC | 2 | TRUE | TRUE | FALSE
10133 | MRT-XK00-P2LCA-142000 | 2019-12-10 | MRT-DS-REC-TT-190239-FC | FC | 2 | TRUE | TRUE | FALSE
10134 | MRT-XK00-P2LCM-142000 | 2019-12-10 | MRT-DS-REC-TT-190239-FC | FC | 2 | TRUE | TRUE | FALSE
10135 | MRT-XK00-P2ACW-142000 | 2019-12-10 | MRT-DS-REC-TT-190239-FC | FC | 2 | TRUE | TRUE | FALSE
10136 | MRT-XK00-P2MAM-142000 | 2019-12-10 | MRT-DS-REC-TT-190239-FC | FC | 2 | TRUE | TRUE | FALSE
10137 | MRT-FF01-P0SGA-135413 | 2019-12-11 | MRT-HK-REC-TT-190975 | FA | 1 | TRUE | TRUE | FALSE
10138 | MRT-QA00-P0SA-135737 | 2019-12-11 | MRT-HK-REC-TT-190976 | FA | 0 | TRUE | FALSE | FALSE
10139 | MRT-QM00-P0SA-135778 | 2019-12-11 | MRT-HK-REC-TT-190976 | FA | 2 | TRUE | TRUE | FALSE
10140 | MRT-YK09-P0SMM-128007 | 2019-12-11 | MRT-DS-REC-TT-190232 | FC | 4 | TRUE | TRUE | FALSE
10141 | MRT-XJ00-P0GHC-141000 | 2019-12-12 | MRT-DS-REC-TT-190238-FC | FC | 1A | TRUE | TRUE | FALSE
10142 | MRT-XJ00-P0GHD-141000 | 2019-12-12 | MRT-DS-REC-TT-190238-FC | FC | 1A | TRUE | TRUE | FALSE
10143 | MRT-XJ00-P0GKB-141000 | 2019-12-12 | MRT-DS-REC-TT-190238-FC | FC | 1A | TRUE | TRUE | FALSE
10144 | MRT-XJ00-P0QJA-141000 | 2019-12-12 | MRT-DS-REC-TT-190238-FC | FC | 1A | TRUE | TRUE | FALSE
10145 | MRT-XJ00-P0GMA-141000 | 2019-12-12 | MRT-DS-REC-TT-190238-FC | FC | 1A | TRUE | TRUE | FALSE
10146 | MRT-XJ00-P0LBG-140000 | 2019-12-12 | MRT-DS-REC-TT-190238-FC | FC | 1A | TRUE | TRUE | FALSE
10147 | MRT-XJ00-P0MKG-141000 | 2019-12-12 | MRT-DS-REC-TT-190238-FC | FC | 1A | TRUE | TRUE | FALSE
10148 | MRT-XJ00-P0EGD-141000 | 2019-12-12 | MRT-DS-REC-TT-190238-FC | FC | 1A | TRUE | TRUE | FALSE
10149 | MRT-XJ00-P0EKG-141000 | 2019-12-12 | MRT-DS-REC-TT-190238-FC | FC | 1A | TRUE | TRUE | FALSE
10150 | MRT-XJ00-P2QFB-145000 | 2019-12-12 | MRT-DS-REC-TT-190238-FC | FC | 1A | TRUE | TRUE | FALSE
10151 | MRT-XJ00-P2SCB-145000 | 2019-12-12 | MRT-DS-REC-TT-190238-FC | FC | 1A | TRUE | TRUE | FALSE
10152 | MRT-XJ00-P0LAA-140000 | 2019-12-12 | MRT-DS-REC-TT-190238-FC | FC | 1A | TRUE | TRUE | FALSE
10153 | MRT-YM01-P2LCB-127039 | 2019-12-12 | MRT-DS-REC-TT-190243 | FC | 2 | TRUE | TRUE | FALSE
10154 | MRT-YM01-P3LCB-127039 | 2019-12-12 | MRT-DS-REC-TT-190243 | FC | 2 | TRUE | TRUE | FALSE
10155 | MRT-XG02-P2LCB-127032 | 2019-12-12 | MRT-DS-REC-TT-190244 | FC | 4 | TRUE | TRUE | FALSE
10156 | MRT-XG02-P3LCB-127032 | 2019-12-12 | MRT-DS-REC-TT-190244 | FC | 4 | TRUE | TRUE | FALSE
10157 | MRT-YF02-P3CJJ-240104 | 2019-12-12 | MRT-DS-REC-TT-190241-FC | FC | 1 | TRUE | TRUE | FALSE
10158 | MRT-YT02-P3CJJ-240112 | 2019-12-12 | MRT-DS-REC-TT-190241-FC | FC | 1 | TRUE | TRUE | FALSE
10159 | MRT-YL01-P2CJJ-240070 | 2019-12-12 | MRT-DS-REC-TT-190241-FC | FC | 1 | TRUE | TRUE | FALSE
10160 | MRT-YL15-P3CJJ-240114 | 2019-12-12 | MRT-DS-REC-TT-190241-FC | FC | 1 | TRUE | TRUE | FALSE
10161 | MRT-CA02-P0UAB-187340 | 2019-12-13 | MRT-HK-REC-TT-190977 | FA | 2 | TRUE | TRUE | FALSE
10162 | MRT-XS00-P0GEN-135300 | 2019-12-13 | MRT-HK-REC-TT-190978 | FA | 3 | TRUE | TRUE | FALSE
10163 | MRT-XG02-P0GEN-135302 | 2019-12-13 | MRT-HK-REC-TT-190978 | FA | 5 | TRUE | TRUE | FALSE
10164 | MRT-QM01-P0SMU-125052 | 2019-12-13 | MRT-HK-REC-TT-190979 | FA | 1 | TRUE | TRUE | FALSE
10165 | MRT-XK00-P0GHC-140001 | 2019-12-13 | MRT-DS-REC-TT-190240-FC | FC | 1 | TRUE | TRUE | FALSE
10166 | MRT-XK00-P0GHD-140001 | 2019-12-13 | MRT-DS-REC-TT-190240-FC | FC | 1 | TRUE | TRUE | FALSE
10167 | MRT-XK00-P0GMA-140001 | 2019-12-13 | MRT-DS-REC-TT-190240-FC | FC | 1 | TRUE | TRUE | FALSE
10168 | MRT-XK00-P0LBG-141000 | 2019-12-13 | MRT-DS-REC-TT-190240-FC | FC | 1 | TRUE | TRUE | FALSE
10169 | MRT-DM01-P0GDG-135080 | 2019-12-16 | MRT-HK-REC-TT-190980 | FA | 0 | TRUE | FALSE | FALSE
10170 | MRT-XJ00-P3MKA-220001 | 2019-12-16 | MRT-DS-REC-TT-190222-FC | FC | 4 | TRUE | TRUE | FALSE
10171 | MRT-XR00-P0SA-135757 | 2019-12-16 | MRT-HK-REC-TT-190981 | FA | 0 | TRUE | FALSE | FALSE
10172 | MRT-DD00-P0BAT-155179 | 2019-12-16 | MRT-HK-REC-TT-190982 | FA | 0 | TRUE | FALSE | FALSE
10173 | MRT-QM03-P0ZEN-155040 | 2019-12-16 | MRT-HK-REC-TT-190982 | FA | 2 | TRUE | TRUE | FALSE
10174 | MRT-FF03-P0SGF-135423 | 2019-12-17 | MRT-HK-REC-TT-190984 | FA | 1 | TRUE | TRUE | FALSE
10175 | MRT-FF01-P0SGJ-135446 | 2019-12-17 | MRT-HK-REC-TT-190983 | FA | 1 | TRUE | TRUE | FALSE
10176 | MRT-QM00-P0SA-135777 | 2019-12-20 | MRT-HK-REC-TT-190985 | FA | 3 | TRUE | TRUE | FALSE
10177 | MRT-CA06-P0UYX-187151 | 2019-12-20 | MRT-HK-REC-TT-190986 | FA | 2 | TRUE | TRUE | FALSE
10178 | MRT-CA01-P0UYX-187152 | 2019-12-20 | MRT-HK-REC-TT-190986 | FA | 2 | TRUE | TRUE | FALSE
10179 | MRT-CA06-P0UYX-187154 | 2019-12-20 | MRT-HK-REC-TT-190986 | FA | 2 | TRUE | TRUE | FALSE
10180 | MRT-CA01-P0UYX-187164 | 2019-12-20 | MRT-HK-REC-TT-190986 | FA | 3 | TRUE | TRUE | FALSE
10181 | MRT-CA02-P0UYX-187166 | 2019-12-20 | MRT-HK-REC-TT-190986 | FA | 2 | TRUE | TRUE | FALSE
10182 | MRT-CA02-P0UYX-187174 | 2019-12-20 | MRT-HK-REC-TT-190986 | FA | 3 | TRUE | TRUE | FALSE
10183 | MRT-CA00-P0UYX-187184 | 2019-12-20 | MRT-HK-REC-TT-190986 | FA | 3 | TRUE | TRUE | FALSE
10184 | MRT-CA01-P0UYX-187186 | 2019-12-20 | MRT-HK-REC-TT-190986 | FA | 3 | TRUE | TRUE | FALSE
10185 | MRT-CA01-P0UYX-187187 | 2019-12-20 | MRT-HK-REC-TT-190986 | FA | 3 | TRUE | TRUE | FALSE
10186 | MRT-CM02-P2MJA-125525 | 2019-12-20 | MRT-HK-REC-TT-190987 | FA | 0 | TRUE | FALSE | FALSE
10187 | MRT-CM02-P2MJA-125528 | 2019-12-20 | MRT-HK-REC-TT-190987 | FA | 1 | TRUE | TRUE | FALSE
10188 | MRT-YL01-P2MKA-125510 | 2019-12-20 | MRT-HK-REC-TT-190988 | FI | 0 | TRUE | FALSE | FALSE
10189 | MRT-CM02-P2MJA-125542 | 2019-12-20 | MRT-HK-REC-TT-190988 | FI | 0 | TRUE | FALSE | FALSE
10190 | MRT-DS00-P3GC-135849 | 2019-12-23 | MRT-HK-REC-TT-190989 | FA | 1 | TRUE | TRUE | FALSE
10191 | MRT-DM01-P0SGA-135474 | 2019-12-23 | MRT-HK-REC-TT-190989 | FI | 1 | TRUE | TRUE | FALSE
10192 | MRT-YD00-P0SMM-128001 | 2019-12-23 | MRT-DS-REC-TT-190223-FC | FC | 4 | TRUE | TRUE | FALSE
10614 | MRT-CQ02-P0GEN-135317 | 2019-12-23 | MRT-HK-REC-TT-190991 | FA | 1 | TRUE | TRUE | FALSE
10196 | MRT-CA01-P0UXA-186690 | 2019-12-26 | MRT-HK-REC-TT-190994 | FA | 2 | TRUE | TRUE | FALSE
10197 | MRT-CA01-P0UMX-187214 | 2019-12-26 | MRT-HK-REC-TT-190994 | FA | 4 | TRUE | TRUE | FALSE
10198 | MRT-CA02-P0UMX-187220 | 2019-12-26 | MRT-HK-REC-TT-190994 | FA | 4 | TRUE | TRUE | FALSE
10199 | MRT-CA01-P0UXA-186683 | 2019-12-26 | MRT-HK-REC-TT-190994 | FA | 2 | TRUE | TRUE | FALSE
10200 | MRT-CA01-P0UMX-187215 | 2019-12-26 | MRT-HK-REC-TT-190994 | FA | 1 | TRUE | TRUE | FALSE
10193 | MRT-YK09-P0SMM-128007 | 2020-01-02 | MRT-DS-REC-TT-190232-FC | FC | 4 | TRUE | TRUE | FALSE
10194 | MRT-XG02-P2LB-122022 | 2020-01-02 | MRT-DS-REC-TT-190237-FC | FC | 9 | TRUE | TRUE | FALSE
10195 | MRT-XG02-P3LB-122022 | 2020-01-02 | MRT-DS-REC-TT-190237-FC | FC | 6 | TRUE | TRUE | FALSE
10201 | MRT-YE04-P0BAU-150175 | 2020-01-02 | MRT-HK-REC-TT-190995 | FA | 1 | TRUE | TRUE | FALSE
10202 | MRT-YS01-P0PBB-135288 | 2020-01-02 | MRT-HK-REC-TT-190996 | FI | 0 | TRUE | FALSE | FALSE
10203 | MRT-BF05-P0ZEN-175024 | 2020-01-02 | MRT-HK-REC-TT-190997 | FI | 0 | TRUE | FALSE | FALSE
10204 | MRT-XB02-P0UMA-180004 | 2020-01-02 | MRT-HK-REC-TT-190997 | FC | 10 | TRUE | TRUE | FALSE
10205 | MRT-CA01-P0UMA-180005 | 2020-01-02 | MRT-HK-REC-TT-190997 | FC | 9 | TRUE | TRUE | FALSE
10206 | MRT-CA01-P0UMA-180007 | 2020-01-02 | MRT-HK-REC-TT-190997 | FC | 8 | TRUE | TRUE | FALSE
10264 | MRT-DN04-P0QHB-125439 | 2020-01-04 | MRT-HK-REC-TT-201003 | FA | 2 | TRUE | TRUE | FALSE
10265 | MRT-CA01-P0UGX-186968 | 2020-01-04 | MRT-HK-REC-TT-200999 | FA | 4 | TRUE | TRUE | FALSE
10266 | MRT-CA01-P0UGX-186971 | 2020-01-04 | MRT-HK-REC-TT-200999 | FA | 2 | TRUE | TRUE | FALSE
10267 | MRT-HM02-P0SAG-135550 | 2020-01-04 | MRT-HK-REC-TT-200998 | FI | 0 | TRUE | FALSE | FALSE
10268 | MRT-HM02-P0SAK-135551 | 2020-01-04 | MRT-HK-REC-TT-200998 | FI | 0 | TRUE | FALSE | FALSE
10269 | MRT-HM02-P0SAK-135552 | 2020-01-04 | MRT-HK-REC-TT-200998 | FI | 0 | TRUE | FALSE | FALSE
10270 | MRT-HM02-P0SAF-135553 | 2020-01-04 | MRT-HK-REC-TT-200998 | FI | 0 | TRUE | FALSE | FALSE
10271 | MRT-HM02-P0SA-135554 | 2020-01-04 | MRT-HK-REC-TT-200998 | FI | 0 | TRUE | FALSE | FALSE
10272 | MRT-HM02-P0SAL-135555 | 2020-01-04 | MRT-HK-REC-TT-200998 | FI | 0 | TRUE | FALSE | FALSE
10273 | MRT-HM02-P0SAF-135556 | 2020-01-04 | MRT-HK-REC-TT-200998 | FI | 0 | TRUE | FALSE | FALSE
10274 | MRT-HM02-P0SA-135557 | 2020-01-04 | MRT-HK-REC-TT-200998 | FI | 0 | TRUE | FALSE | FALSE
10275 | MRT-HM02-P0SA-135558 | 2020-01-04 | MRT-HK-REC-TT-200998 | FI | 0 | TRUE | FALSE | FALSE
10276 | MRT-HM02-P0SAE-135559 | 2020-01-04 | MRT-HK-REC-TT-200998 | FI | 0 | TRUE | FALSE | FALSE
10277 | MRT-HM02-P0SA-135560 | 2020-01-04 | MRT-HK-REC-TT-200998 | FI | 0 | TRUE | FALSE | FALSE
10278 | MRT-XW03-P0BAU-150017 | 2020-01-04 | MRT-HK-REC-TT-200997 | FA | 0 | TRUE | FALSE | FALSE
10281 | MRT-QM03-P2PAC-130003 | 2020-01-04 | MRT-HK-REC-TT-201001 | FA | 0 | TRUE | FALSE | FALSE
10282 | MRT-BF01-P2MJD-125515 | 2020-01-04 | MRT-HK-REC-TT-201002 | FA | 0 | TRUE | FALSE | FALSE
10283 | MRT-DT01-P0GDG-135079 | 2020-01-04 | MRT-HK-REC-TT-201002 | FA | 0 | TRUE | FALSE | FALSE
10207 | MRT-XJ00-P0GMA-140001 | 2020-01-06 | MRT-DS-REC-TT-200001-FC | FC | 1A | TRUE | TRUE | FALSE
10208 | MRT-UE00-P2ZEN-100004 | 2020-01-06 | MRT-DS-REC-TT-200002 | FC | 6 | TRUE | TRUE | FALSE
10209 | MRT-UE00-P2ZEN-100005 | 2020-01-06 | MRT-DS-REC-TT-200002 | FC | 6 | TRUE | TRUE | FALSE
10210 | MRT-UE00-P2ZEN-100006 | 2020-01-06 | MRT-DS-REC-TT-200002 | FC | 6 | TRUE | TRUE | FALSE
10211 | MRT-UE00-P2ZEN-100007 | 2020-01-06 | MRT-DS-REC-TT-200002 | FC | 6 | TRUE | TRUE | FALSE
10212 | MRT-UE00-P3ZEN-100010 | 2020-01-06 | MRT-DS-REC-TT-200002 | FC | 6 | TRUE | TRUE | FALSE
10213 | MRT-UE00-P3ZEN-100011 | 2020-01-06 | MRT-DS-REC-TT-200002 | FC | 6 | TRUE | TRUE | FALSE
10214 | MRT-UE00-P3ZEN-100012 | 2020-01-06 | MRT-DS-REC-TT-200002 | FC | 6 | TRUE | TRUE | FALSE
10215 | MRT-UE00-P3ZEN-100013 | 2020-01-06 | MRT-DS-REC-TT-200002 | FC | 6 | TRUE | TRUE | FALSE
10216 | MRT-UE00-P2ZEN-100016 | 2020-01-06 | MRT-DS-REC-TT-200002 | FC | 4 | TRUE | TRUE | FALSE
10217 | MRT-UE00-P3ZEN-100017 | 2020-01-06 | MRT-DS-REC-TT-200002 | FC | 4 | TRUE | TRUE | FALSE
10263 | MRT-CC02-P0UPC-175737 | 2020-01-06 | MRT-HK-REC-TT-201004 | FA | 3 | TRUE | TRUE | FALSE
10218 | MRT-CC02-P0UPC-175740 | 2020-01-07 | MRT-HK-REC-TT-201004 | FA | 3 | TRUE | TRUE | FALSE
10219 | MRT-CC02-P0UPC-175745 | 2020-01-07 | MRT-HK-REC-TT-201004 | FA | 3 | TRUE | TRUE | FALSE
10220 | MRT-CC02-P0UPC-175726 | 2020-01-07 | MRT-HK-REC-TT-201004 | FA | 4 | TRUE | TRUE | FALSE
10221 | MRT-CC02-P0UPC-175727 | 2020-01-07 | MRT-HK-REC-TT-201004 | FA | 3 | TRUE | TRUE | FALSE
10222 | MRT-CC02-P0UPC-175728 | 2020-01-07 | MRT-HK-REC-TT-201004 | FA | 3 | TRUE | TRUE | FALSE
10223 | MRT-CC02-P0UPC-175729 | 2020-01-07 | MRT-HK-REC-TT-201004 | FA | 3 | TRUE | TRUE | FALSE
10224 | MRT-CC02-P0UPC-175744 | 2020-01-07 | MRT-HK-REC-TT-201004 | FA | 3 | TRUE | TRUE | FALSE
10225 | MRT-XW03-P0SMU-125002 | 2020-01-07 | MRT-HK-REC-TT-201005 | FA | 2 | TRUE | TRUE | FALSE
10226 | MRT-DD04-P0GEN-135389 | 2020-01-07 | MRT-HK-REC-TT-201006 | FA | 2 | TRUE | TRUE | FALSE
10227 | MRT-FF03-P0UAT-128218 | 2020-01-07 | MRT-HK-REC-TT-201007 | FA | 1 | TRUE | TRUE | FALSE
10228 | MRT-HM02-P0SAH-135549 | 2020-01-08 | MRT-HK-REC-TT-201008 | FA | 0 | TRUE | FALSE | FALSE
10229 | MRT-XG02-P2LCB-127032 | 2020-01-09 | MRT-DS-REC-TT-190244-FC | FC | 4 | TRUE | TRUE | FALSE
10230 | MRT-XG02-P3LCB-127032 | 2020-01-09 | MRT-DS-REC-TT-190244-FC | FC | 4 | TRUE | TRUE | FALSE
10231 | MRT-YD00-P0ERB-606001 | 2020-01-09 | MRT-DS-REC-TT-200003 | FC | 4 | TRUE | TRUE | FALSE
10232 | MRT-YD00-P0ERB-606002 | 2020-01-09 | MRT-DS-REC-TT-200003 | FC | 4 | TRUE | TRUE | FALSE
10233 | MRT-XW03-P0SMU-125025 | 2020-01-09 | MRT-HK-REC-TT-201009 | FA | 0 | TRUE | FALSE | FALSE
10234 | MRT-CY03-P0SA-135529 | 2020-01-09 | MRT-HK-REC-TT-201010 | FA | 0 | TRUE | FALSE | FALSE
10235 | MRT-YT01-P3GC-135164 | 2020-01-09 | MRT-HK-REC-TT-201011 | FA | 0 | TRUE | TRUE | FALSE
10236 | MRT-YT01-P3GC-135161 | 2020-01-09 | MRT-HK-REC-TT-201011 | FA | 1 | TRUE | TRUE | FALSE
10237 | MRT-YS18-P0SMM-128010 | 2020-01-10 | MRT-DS-REC-TT-190242-FC | FC | 2 | TRUE | TRUE | FALSE
10238 | MRT-YK10-P2MAA-185130 | 2020-01-10 | MRT-HK-REC-TT-201012 | FA | 1 | TRUE | TRUE | FALSE
10239 | MRT-YK10-P2MAA-185128 | 2020-01-10 | MRT-HK-REC-TT-201012 | FA | 1 | TRUE | TRUE | FALSE
10240 | MRT-YK10-P2MAA-185125 | 2020-01-10 | MRT-HK-REC-TT-201012 | FA | 1 | TRUE | TRUE | FALSE
10241 | MRT-CT00-P2PAC-130004 | 2020-01-10 | MRT-HK-REC-TT-201013 | FA | 0 | TRUE | FALSE | FALSE
10242 | MRT-CC02-P0ULX-176229 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 0 | TRUE | TRUE | FALSE
10243 | MRT-CC02-P0ULX-176211 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 0 | TRUE | TRUE | FALSE
10244 | MRT-CC02-P0ULX-176210 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 0 | TRUE | TRUE | FALSE
10245 | MRT-CC02-P0ULX-176217 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 3 | TRUE | TRUE | FALSE
10246 | MRT-CC02-P0ULX-176218 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 2 | TRUE | TRUE | FALSE
10247 | MRT-CC02-P0ULX-176220 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 2 | TRUE | TRUE | FALSE
10248 | MRT-CC02-P0ULX-176221 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 2 | TRUE | TRUE | FALSE
10249 | MRT-CC02-P0ULX-176222 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 2 | TRUE | TRUE | FALSE
10250 | MRT-CC02-P0ULX-176223 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 2 | TRUE | TRUE | FALSE
10251 | MRT-CC02-P0ULX-176224 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 2 | TRUE | TRUE | FALSE
10252 | MRT-CC02-P0ULX-176225 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 3 | TRUE | TRUE | FALSE
10253 | MRT-CC02-P0ULX-176226 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 1 | TRUE | TRUE | FALSE
10254 | MRT-CC02-P0ULX-176227 | 2020-01-10 | MRT-HK-REC-TT-201014 | FA | 2 | TRUE | TRUE | FALSE
10255 | MRT-CC02-P0UZT-175927 | 2020-01-10 | MRT-HK-REC-TT-201015 | FA | 0 | TRUE | TRUE | FALSE
10256 | MRT-CC02-P0UZT-175926 | 2020-01-10 | MRT-HK-REC-TT-201015 | FA | 0 | TRUE | TRUE | FALSE
10257 | MRT-CC02-P0UZT-175920 | 2020-01-10 | MRT-HK-REC-TT-201015 | FA | 2 | TRUE | TRUE | FALSE
10258 | MRT-CC02-P0UZT-175925 | 2020-01-10 | MRT-HK-REC-TT-201015 | FA | 2 | TRUE | TRUE | FALSE
10259 | MRT-CC02-P0UZT-175930 | 2020-01-10 | MRT-HK-REC-TT-201015 | FA | 2 | TRUE | TRUE | FALSE
10260 | MRT-CC02-P0UZT-175922 | 2020-01-10 | MRT-HK-REC-TT-201015 | FA | 2 | TRUE | TRUE | FALSE
10261 | MRT-CC02-P0UZT-175921 | 2020-01-10 | MRT-HK-REC-TT-201015 | FA | 2 | TRUE | TRUE | FALSE
10262 | MRT-YL16-P0BFY-150081 | 2020-01-10 | MRT-HK-REC-TT-201016 | FA | 0 | TRUE | FALSE | FALSE
10279 | MRT-YL16-P2BLF-150237 | 2020-01-13 | MRT-HK-REC-TT-201017 | FA | 0 | TRUE | FALSE | FALSE
10280 | MRT-YL16-P0BBY-150080 | 2020-01-13 | MRT-HK-REC-TT-201017 | FA | 0 | TRUE | FALSE | FALSE
10574 | MRT-YL35-P3PAC-130001 | 2020-01-14 | MRT-HK-REC-TT-201018 | FI | 0 | TRUE | FALSE | FALSE
10575 | MRT-YL35-P2PAC-130001 | 2020-01-14 | MRT-HK-REC-TT-201018 | FI | 0 | TRUE | FALSE | FALSE
10576 | MRT-CC05-P2PAC-130004 | 2020-01-14 | MRT-HK-REC-TT-201018 | FI | 0 | TRUE | FALSE | FALSE
10577 | MRT-YL00-P3PAC-130001 | 2020-01-14 | MRT-HK-REC-TT-201018 | FI | 0 | TRUE | FALSE | FALSE
10578 | MRT-YL00-P2PAC-130001 | 2020-01-14 | MRT-HK-REC-TT-201018 | FI | 0 | TRUE | FALSE | FALSE
10579 | MRT-YT02-P3PAC-130001 | 2020-01-14 | MRT-HK-REC-TT-201018 | FI | 0 | TRUE | FALSE | FALSE
10580 | MRT-YT02-P2PAC-130001 | 2020-01-14 | MRT-HK-REC-TT-201018 | FI | 0 | TRUE | FALSE | FALSE
10581 | MRT-YM01-P2PAC-130001 | 2020-01-14 | MRT-HK-REC-TT-201018 | FI | 0 | TRUE | TRUE | FALSE
10284 | MRT-XJ00-P2LB-142000 | 2020-01-16 | MRT-DS-REC-TT-200004-FC | FC | 1 | TRUE | TRUE | FALSE
10285 | MRT-XJ00-P3LB-143000 | 2020-01-16 | MRT-DS-REC-TT-200004-FC | FC | 1 | TRUE | TRUE | FALSE
10286 | MRT-XJ00-P3LB-144000 | 2020-01-16 | MRT-DS-REC-TT-200004-FC | FC | 1 | TRUE | TRUE | FALSE
10287 | MRT-YL01-P0PBB-135258 | 2020-01-17 | MRT-HK-REC-TT-201019 | FA | 0 | TRUE | FALSE | FALSE
10288 | MRT-YL01-P0PBB-135287 | 2020-01-17 | MRT-HK-REC-TT-201019 | FI | 0 | TRUE | FALSE | FALSE
10289 | MRT-CQ02-P0PBB-135264 | 2020-01-17 | MRT-HK-REC-TT-201020 | FI | 0 | TRUE | FALSE | FALSE
10290 | MRT-CQ02-P0PBB-135277 | 2020-01-17 | MRT-HK-REC-TT-201020 | FI | 0 | TRUE | FALSE | FALSE
10291 | MRT-CQ02-P0PBB-135276 | 2020-01-17 | MRT-HK-REC-TT-201020 | FI | 0 | TRUE | FALSE | FALSE
10292 | MRT-CQ02-P0PBB-135278 | 2020-01-17 | MRT-HK-REC-TT-201020 | FI | 0 | TRUE | FALSE | FALSE
10293 | MRT-CC05-P0SMU-125049 | 2020-01-17 | MRT-HK-REC-TT-201021 | FI | 1 | TRUE | TRUE | FALSE
10294 | MRT-CA02-P0UYX-187166 | 2020-01-17 | MRT-HK-REC-TT-201022 | FA | 3 | TRUE | TRUE | FALSE
10295 | MRT-DN04-P0BRU-150267 | 2020-01-17 | MRT-HK-REC-TT-201023 | FA | 2 | TRUE | TRUE | FALSE
10296 | MRT-DD00-P0BAT-155176 | 2020-01-17 | MRT-HK-REC-TT-201023 | FA | 1 | TRUE | TRUE | FALSE
10790 | MRT-CA01-P0UMA-180005 | 2020-01-17 | MRT-HK-REC-TT-201025 | FC | 10 | TRUE | TRUE | FALSE
10297 | MRT-CC04-P0MKG-185226 | 2020-01-20 | MRT-HK-REC-TT-201024 | FA | 0 | TRUE | FALSE | FALSE
10298 | MRT-XK00-P2LB0-140001 | 2020-01-20 | MRT-DS-REC-TT-200005-FC | FI | 0 | TRUE | FALSE | FALSE
10299 | MRT-FF03-P0UAT-128218 | 2020-01-21 | MRT-HK-REC-TT-201026 | FA | 2 | TRUE | TRUE | FALSE
10300 | MRT-XK00-P4LB0-140001 | 2020-01-21 | MRT-DS-REC-TT-200006-FC | FI | 0 | TRUE | FALSE | FALSE
10301 | MRT-XK00-P3LB0-140001 | 2020-01-21 | MRT-DS-REC-TT-200006-FC | FI | 0 | TRUE | FALSE | FALSE
10474 | MRT-CT00-P3GC-135184 | 2020-01-21 | MRT-HK-REC-TT-201028 | FI | 1 | TRUE | TRUE | FALSE
10302 | MRT-CC02-P0ULX-176217 | 2020-01-22 | MRT-HK-REC-TT-201027 | FA | 4 | TRUE | TRUE | FALSE
10303 | MRT-CC02-P0ULX-176221 | 2020-01-22 | MRT-HK-REC-TT-201027 | FA | 3 | TRUE | TRUE | FALSE
10304 | MRT-CC02-P0ULX-176211 | 2020-01-22 | MRT-HK-REC-TT-201027 | FA | 1 | TRUE | TRUE | FALSE
10305 | MRT-CC02-P0ULX-176229 | 2020-01-22 | MRT-HK-REC-TT-201027 | FA | 1 | TRUE | TRUE | FALSE
10306 | MRT-XH01-P2LB-122025 | 2020-01-22 | MRT-DS-REC-TT-200007-FC | FC | 5 | TRUE | TRUE | FALSE
10307 | MRT-XH01-P3LB-122025 | 2020-01-22 | MRT-DS-REC-TT-200007-FC | FC | 5 | TRUE | TRUE | FALSE
10308 | MRT-QM03-P0ZEN-155040 | 2020-01-22 | MRT-HK-REC-TT-201029 | FA | 3 | TRUE | TRUE | FALSE
10309 | MRT-DN03-P0GEN-135719 | 2020-01-22 | MRT-HK-REC-TT-201029 | FA | 1 | TRUE | TRUE | FALSE
10310 | MRT-DD00-P0BAT-155179 | 2020-01-22 | MRT-HK-REC-TT-201029 | FA | 1 | TRUE | TRUE | FALSE
10311 | MRT-YF00-P2ZEN-161601 | 2020-01-22 | MRT-DS-REC-TT-200008 | FC | 2 | TRUE | TRUE | FALSE
10312 | MRT-YF00-P3ZEN-161601 | 2020-01-22 | MRT-DS-REC-TT-200008 | FC | 2 | TRUE | TRUE | FALSE
10313 | MRT-CC07-P3AY-160001 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 2 | TRUE | TRUE | FALSE
10314 | MRT-YQ07-P3AY-160002 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 2 | TRUE | TRUE | FALSE
10315 | MRT-YT01-P3AYA-160009 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 2 | TRUE | TRUE | FALSE
10316 | MRT-BF01-P3AY-160031 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 1 | TRUE | TRUE | FALSE
10317 | MRT-DD07-P3AY-160025 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 1 | TRUE | TRUE | FALSE
10318 | MRT-YL16-P3AYA-160006 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 1 | TRUE | TRUE | FALSE
10319 | MRT-YT01-P3AY-160008 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 2 | TRUE | TRUE | FALSE
10320 | MRT-BF01-P3AYA-160033 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 1 | TRUE | TRUE | FALSE
10321 | MRT-YL16-P3AYA-160039 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 1 | TRUE | TRUE | FALSE
10322 | MRT-YQ07-P3AYA-160038 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 1 | TRUE | TRUE | FALSE
10323 | MRT-YL16-P3AYA-160007 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 1 | TRUE | TRUE | FALSE
10324 | MRT-YT01-P3AYA-160010 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 1 | TRUE | TRUE | FALSE
10325 | MRT-BF01-P3AYA-160036 | 2020-01-23 | MRT-HK-REC-TT-201030 | FA | 1 | TRUE | TRUE | FALSE
10326 | MRT-CA00-P0USG-186864 | 2020-01-23 | MRT-HK-REC-TT-201031 | FC | 4 | TRUE | TRUE | FALSE
10327 | MRT-CA00-P0UST-186917 | 2020-01-23 | MRT-HK-REC-TT-201031 | FC | 4 | TRUE | TRUE | FALSE
10328 | MRT-CA01-P0UGX-186972 | 2020-01-23 | MRT-HK-REC-TT-201031 | FC | 4 | TRUE | TRUE | FALSE
10329 | MRT-BT00-P0GEN-135892 | 2020-01-23 | MRT-HK-REC-TT-201032 | FC | 1 | TRUE | TRUE | FALSE
10330 | MRT-XJ00-P2LBA-142000 | 2020-01-23 | MRT-DS-REC-TT-200009-FC | FC | 2C | TRUE | TRUE | FALSE
10331 | MRT-XJ00-P2LBG-142000 | 2020-01-23 | MRT-DS-REC-TT-200009-FC | FC | 2A | TRUE | TRUE | FALSE
10332 | MRT-XJ00-P2LAB-142000 | 2020-01-23 | MRT-DS-REC-TT-200009-FC | FC | 2A | TRUE | TRUE | FALSE
10333 | MRT-XJ00-P2LCA-142000 | 2020-01-23 | MRT-DS-REC-TT-200009-FC | FC | 2C | TRUE | TRUE | FALSE
10334 | MRT-XJ00-P2PGB-142000 | 2020-01-23 | MRT-DS-REC-TT-200009-FC | FC | 2B | TRUE | TRUE | FALSE
10335 | MRT-XJ00-P2LCM-142000 | 2020-01-23 | MRT-DS-REC-TT-200009-FC | FC | 2A | TRUE | TRUE | FALSE
10336 | MRT-CT00-P3AYA-160048 | 2020-01-29 | MRT-HK-REC-TT-201033 | FA | 0 | TRUE | FALSE | FALSE
10337 | MRT-CT00-P3AYA-160047 | 2020-01-29 | MRT-HK-REC-TT-201033 | FA | 2 | TRUE | TRUE | FALSE
10338 | MRT-XA00-P0GEN-135305 | 2020-01-29 | MRT-HK-REC-TT-201034 | FA | 2 | TRUE | TRUE | FALSE
10339 | MRT-DD03-P0SMU-125040 | 2020-01-29 | MRT-HK-REC-TT-201036 | FA | 1 | TRUE | TRUE | FALSE
10340 | MRT-YT01-P3GC-135146 | 2020-01-29 | MRT-HK-REC-TT-201035 | FA | 0 | TRUE | FALSE | FALSE
10341 | MRT-YT01-P0GN-135248 | 2020-01-29 | MRT-HK-REC-TT-201035 | FA | 0 | TRUE | FALSE | FALSE
10342 | MRT-CT00-P3AY-160006 | 2020-01-29 | MRT-HK-REC-TT-201037 | FA | 1 | TRUE | TRUE | FALSE
10343 | MRT-CT00-P3AY-160005 | 2020-01-29 | MRT-HK-REC-TT-201037 | FA | 1 | TRUE | TRUE | FALSE
10344 | MRT-DT03-P0SGA-135479 | 2020-01-30 | MRT-HK-REC-TT-201040 | FA | 1 | TRUE | TRUE | FALSE
10345 | MRT-XJ00-P2LB-122028 | 2020-01-30 | MRT-DS-REC-TT-200010-FC | FC | 7 | TRUE | TRUE | FALSE
10346 | MRT-XJ00-P3LB-122028 | 2020-01-30 | MRT-DS-REC-TT-200010-FC | FC | 7 | TRUE | TRUE | FALSE
10347 | MRT-YL01-P3CRA-160102 | 2020-01-31 | MRT-HK-REC-TT-201041 | FI | 0 | TRUE | FALSE | FALSE
10348 | MRT-YL01-P0ZEN-165016 | 2020-01-31 | MRT-HK-REC-TT-201041 | FI | 0 | TRUE | FALSE | FALSE
10349 | MRT-YL01-P3CRA-160103 | 2020-01-31 | MRT-HK-REC-TT-201041 | FI | 0 | TRUE | FALSE | FALSE
10350 | MRT-YL16-P0BCA-150091 | 2020-01-31 | MRT-HK-REC-TT-201042 | FI | 0 | TRUE | FALSE | FALSE
10351 | MRT-DD02-P0SGA-135482 | 2020-01-31 | MRT-HK-REC-TT-201043 | FI | 1 | TRUE | TRUE | FALSE
10352 | MRT-DD00-P0BAT-155170 | 2020-01-31 | MRT-HK-REC-TT-201039 | FA | 1 | TRUE | TRUE | FALSE
10353 | MRT-DD00-P0BAT-155171 | 2020-01-31 | MRT-HK-REC-TT-201039 | FA | 1 | TRUE | TRUE | FALSE
10354 | MRT-DD00-P0BAT-155172 | 2020-01-31 | MRT-HK-REC-TT-201039 | FA | 1 | TRUE | TRUE | FALSE
10355 | MRT-DD00-P0BAT-155173 | 2020-01-31 | MRT-HK-REC-TT-201039 | FA | 1 | TRUE | TRUE | FALSE
10356 | MRT-DD00-P0BAT-155174 | 2020-01-31 | MRT-HK-REC-TT-201039 | FA | 1 | TRUE | TRUE | FALSE
10357 | MRT-XJ00-P0GHC-141000 | 2020-02-03 | MRT-DS-REC-TT-200011-FC | FC | 1B | TRUE | TRUE | FALSE
10358 | MRT-DN02-P0BAT-150910 | 2020-02-04 | MRT-HK-REC-TT-201044 | FA | 0 | TRUE | TRUE | FALSE
10359 | MRT-DD04-P0GEN-135390 | 2020-02-04 | MRT-HK-REC-TT-201044 | FA | 0 | TRUE | TRUE | FALSE
10360 | MRT-QM00-P0SA-135775 | 2020-02-04 | MRT-HK-REC-TT-201044 | FA | 0 | TRUE | TRUE | FALSE
10361 | MRT-CN00-P0PBB-135268 | 2020-02-04 | MRT-HK-REC-TT-201044 | FA | 0 | TRUE | TRUE | FALSE
10362 | MRT-DS00-P0GN-135279 | 2020-02-04 | MRT-HK-REC-TT-201044 | FA | 0 | TRUE | TRUE | FALSE
10363 | MRT-DS00-P3GC-135183 | 2020-02-04 | MRT-HK-REC-TT-201044 | FA | 0 | TRUE | TRUE | FALSE
10364 | MRT-DN05-P0QHY-125419 | 2020-02-04 | MRT-HK-REC-TT-201044 | FA | 0 | TRUE | TRUE | FALSE
10365 | MRT-FF02-P0AYE-135613 | 2020-02-04 | MRT-HK-REC-TT-201046 | FI | 1 | TRUE | TRUE | FALSE
10366 | MRT-FF02-P0AYE-135614 | 2020-02-04 | MRT-HK-REC-TT-201046 | FI | 1 | TRUE | TRUE | FALSE
10367 | MRT-FF02-P0AYE-135620 | 2020-02-04 | MRT-HK-REC-TT-201046 | FI | 1 | TRUE | TRUE | FALSE
10368 | MRT-FF02-P0AYE-135644 | 2020-02-04 | MRT-HK-REC-TT-201046 | FI | 1 | TRUE | TRUE | FALSE
10369 | MRT-FF02-P2AYE-135623 | 2020-02-04 | MRT-HK-REC-TT-201046 | FI | 1 | TRUE | TRUE | FALSE
10370 | MRT-FF02-P2AYE-135638 | 2020-02-04 | MRT-HK-REC-TT-201046 | FI | 1 | TRUE | TRUE | FALSE
10371 | MRT-FF02-P3AYE-135627 | 2020-02-04 | MRT-HK-REC-TT-201046 | FI | 1 | TRUE | TRUE | FALSE
10372 | MRT-FF02-P3AYE-135628 | 2020-02-04 | MRT-HK-REC-TT-201046 | FI | 1 | TRUE | TRUE | FALSE
10373 | MRT-QM04-P2PAC-130001 | 2020-02-05 | MRT-HK-REC-TT-201047 | FI | 0 | TRUE | FALSE | FALSE
10374 | MRT-YL16-P0BAC-150084 | 2020-02-05 | MRT-HK-REC-TT-201048 | FI | 0 | TRUE | FALSE | FALSE
10375 | MRT-XJ00-P2MAA-145000 | 2020-02-05 | MRT-DS-REC-TT-200012-FC | FC | 1A | TRUE | TRUE | FALSE
10376 | MRT-FF01-P0SGA-135488 | 2020-02-06 | MRT-HK-REC-TT-201051 | FA | 2 | TRUE | TRUE | FALSE
10377 | MRT-FF00-P0SGA-135464 | 2020-02-06 | MRT-HK-REC-TT-201051 | FA | 1 | TRUE | TRUE | FALSE
10378 | MRT-FF02-P0AYE-135640 | 2020-02-06 | MRT-HK-REC-TT-201051 | FI | 1 | TRUE | TRUE | FALSE
10379 | MRT-FF02-P0AYE-135643 | 2020-02-06 | MRT-HK-REC-TT-201051 | FI | 1 | TRUE | TRUE | FALSE
10380 | MRT-FF02-P3AYE-135630 | 2020-02-06 | MRT-HK-REC-TT-201051 | FI | 1 | TRUE | TRUE | FALSE
10381 | MRT-FF02-P3AYE-135629 | 2020-02-06 | MRT-HK-REC-TT-201051 | FI | 1 | TRUE | TRUE | FALSE
10382 | MRT-FF02-P0AYE-135641 | 2020-02-06 | MRT-HK-REC-TT-201051 | FI | 1 | TRUE | TRUE | FALSE
10383 | MRT-FF02-P0AYE-135639 | 2020-02-06 | MRT-HK-REC-TT-201051 | FI | 1 | TRUE | TRUE | FALSE
10384 | MRT-FF02-P0AYE-135619 | 2020-02-06 | MRT-HK-REC-TT-201051 | FI | 1 | TRUE | TRUE | FALSE
10385 | MRT-FF02-P0AYE-135615 | 2020-02-06 | MRT-HK-REC-TT-201051 | FI | 1 | TRUE | TRUE | FALSE
10386 | MRT-FF02-P0AYE-135618 | 2020-02-06 | MRT-HK-REC-TT-201051 | FI | 1 | TRUE | TRUE | FALSE
10387 | MRT-FF02-P3AYE-135624 | 2020-02-06 | MRT-HK-REC-TT-201051 | FI | 1 | TRUE | TRUE | FALSE
10388 | MRT-FF02-P3AYE-135631 | 2020-02-06 | MRT-HK-REC-TT-201051 | FI | 1 | TRUE | TRUE | FALSE
10389 | MRT-GT00-P2ZEN-167001 | 2020-02-06 | MRT-DS-REC-TT-200013 | FA | 0 | TRUE | FALSE | FALSE
10390 | MRT-XG02-P2LB-122022 | 2020-02-10 | MRT-DS-REC-TT-200014 | FC | 10 | TRUE | TRUE | FALSE
10391 | MRT-XG02-P3LB-122022 | 2020-02-10 | MRT-DS-REC-TT-200014 | FC | 7 | TRUE | TRUE | FALSE
10392 | MRT-XJ00-P0GHD-141000 | 2020-02-10 | MRT-DS-REC-TT-200015-FC | FC | 1B | TRUE | TRUE | FALSE
10393 | MRT-XJ00-P0GKB-141000 | 2020-02-10 | MRT-DS-REC-TT-200015-FC | FC | 1B | TRUE | TRUE | FALSE
10394 | MRT-XJ00-P0GMA-141000 | 2020-02-10 | MRT-DS-REC-TT-200015-FC | FC | 1B | TRUE | TRUE | FALSE
10395 | MRT-XJ00-P2QFB-145000 | 2020-02-10 | MRT-DS-REC-TT-200015-FC | FC | 1B | TRUE | TRUE | FALSE
10396 | MRT-XJ00-P2SCB-145000 | 2020-02-10 | MRT-DS-REC-TT-200015-FC | FC | 1B | TRUE | TRUE | FALSE
10398 | MRT-YD08-P0QHY-125496 | 2020-02-10 | MRT-HK-REC-TT-201053 | FA | 1 | TRUE | TRUE | FALSE
10399 | MRT-YD08-P0QHY-125499 | 2020-02-10 | MRT-HK-REC-TT-201053 | FA | 3 | TRUE | TRUE | FALSE
10400 | MRT-YR01-P0LB-830502 | 2020-02-10 | MRT-HK-REC-TT-201055 | FA | 0 | TRUE | FALSE | FALSE
10401 | MRT-YR01-P0LB-830501 | 2020-02-10 | MRT-HK-REC-TT-201055 | FA | 0 | TRUE | FALSE | FALSE
10402 | MRT-YD08-P0QHY-125491 | 2020-02-11 | MRT-HK-REC-TT-201056 | FA | 1 | TRUE | TRUE | FALSE
10403 | MRT-DN05-P0AYE-135473 | 2020-02-11 | MRT-HK-REC-TT-201057 | FA | 1 | TRUE | TRUE | FALSE
10404 | MRT-FF02-P0AYE-135647 | 2020-02-11 | MRT-HK-REC-TT-201057 | FA | 1 | TRUE | TRUE | FALSE
10405 | MRT-FF01-P0SGA-135652 | 2020-02-11 | MRT-HK-REC-TT-201057 | FI | 1 | TRUE | TRUE | FALSE
10406 | MRT-YF02-P2CRA-160117 | 2020-02-12 | MRT-HK-REC-TT-201058 | FA | 0 | TRUE | FALSE | FALSE
10407 | MRT-CC02-P2UMA-170507 | 2020-02-17 | MRT-DS-REC-TT-200016 | FC | 5 | TRUE | TRUE | FALSE
10408 | MRT-VK02-P2UMA-170510 | 2020-02-17 | MRT-DS-REC-TT-200016 | FC | 5 | TRUE | TRUE | FALSE
10409 | MRT-CC02-P3UMA-170507 | 2020-02-17 | MRT-DS-REC-TT-200016 | FC | 5 | TRUE | TRUE | FALSE
10410 | MRT-VK02-P3UMA-170510 | 2020-02-17 | MRT-DS-REC-TT-200016 | FC | 5 | TRUE | TRUE | FALSE
10411 | MRT-DN02-P0ABA-150904 | 2020-02-17 | MRT-HK-REC-TT-201061 | FA | 1 | TRUE | TRUE | FALSE
10412 | MRT-YD00-PWCRA-160113 | 2020-02-17 | MRT-HK-REC-TT-201060 | FA | 0 | TRUE | FALSE | FALSE
10413 | MRT-YD00-PWCRA-160112 | 2020-02-17 | MRT-HK-REC-TT-201060 | FA | 0 | TRUE | FALSE | FALSE
10414 | MRT-YD00-PWCRA-160111 | 2020-02-17 | MRT-HK-REC-TT-201060 | FA | 0 | TRUE | FALSE | FALSE
10415 | MRT-XK00-P0GDY-135062 | 2020-02-18 | MRT-HK-REC-TT-201063 | FA | 2 | TRUE | TRUE | FALSE
10416 | MRT-DN05-P0SGA-135472 | 2020-02-18 | MRT-HK-REC-TT-201064 | FA | 1 | TRUE | TRUE | FALSE
10417 | MRT-CA00-P0USG-186864 | 2020-02-18 | MRT-HK-REC-TT-201065 | FA | 5 | TRUE | TRUE | FALSE
10418 | MRT-CA02-P0UYX-187166 | 2020-02-18 | MRT-HK-REC-TT-201065 | FA | 4 | TRUE | TRUE | FALSE
10419 | MRT-CA00-P0UST-186917 | 2020-02-18 | MRT-HK-REC-TT-201065 | FA | 5 | TRUE | TRUE | FALSE
10420 | MRT-CA01-P0UGX-186972 | 2020-02-18 | MRT-HK-REC-TT-201065 | FA | 5 | TRUE | TRUE | FALSE
10421 | MRT-XJ00-P2MAA-142000 | 2020-02-19 | MRT-DS-REC-TT-200017-FC | FC | 1 | TRUE | TRUE | FALSE
10422 | MRT-XJ00-P3MAA-143000 | 2020-02-19 | MRT-DS-REC-TT-200017-FC | FC | 1 | TRUE | TRUE | FALSE
10423 | MRT-XJ00-P3MAA-144000 | 2020-02-19 | MRT-DS-REC-TT-200017-FC | FC | 1 | TRUE | TRUE | FALSE
10424 | MRT-XJ00-P2LBA-145000 | 2020-02-19 | MRT-DS-REC-TT-200018-FC | FC | 1A | TRUE | TRUE | FALSE
10425 | MRT-YL01-P2CRA-160101 | 2020-02-20 | MRT-HK-REC-TT-201067 | FI | 0 | TRUE | FALSE | FALSE
10426 | MRT-YD00-P2MAA-220214 | 2020-02-25 | MRT-DS-REC-TT-200019-FC | FI | 0 | TRUE | FALSE | FALSE
10427 | MRT-YD00-P0ERB-606001 | 2020-02-25 | MRT-DS-REC-TT-200003-FC | FC | 4 | TRUE | TRUE | FALSE
10428 | MRT-YD00-P0ERB-606002 | 2020-02-25 | MRT-DS-REC-TT-200003-FC | FC | 4 | TRUE | TRUE | FALSE
10429 | MRT-XJ00-P2LBG-145000 | 2020-02-25 | MRT-DS-REC-TT-200020-FC | FC | 1A | TRUE | TRUE | FALSE
10430 | MRT-XJ00-P2LCM-145000 | 2020-02-25 | MRT-DS-REC-TT-200020-FC | FC | 1A | TRUE | TRUE | FALSE
10431 | MRT-XJ00-P2LAB-145000 | 2020-02-25 | MRT-DS-REC-TT-200020-FC | FC | 1A | TRUE | TRUE | FALSE
10432 | MRT-XJ00-P2LCA-145000 | 2020-02-25 | MRT-DS-REC-TT-200020-FC | FC | 2A | TRUE | TRUE | FALSE
10433 | MRT-XJ00-P2PGB-145000 | 2020-02-25 | MRT-DS-REC-TT-200020-FC | FC | 1A | TRUE | TRUE | FALSE
10434 | MRT-XJ00-P2QC-145000 | 2020-02-25 | MRT-DS-REC-TT-200020-FC | FC | 1A | TRUE | TRUE | FALSE
10435 | MRT-XJ00-P2MAV-145000 | 2020-02-25 | MRT-DS-REC-TT-200020-FC | FC | 1A | TRUE | TRUE | FALSE
10436 | MRT-XJ00-P2SCA-145000 | 2020-02-25 | MRT-DS-REC-TT-200020-FC | FC | 1A | TRUE | TRUE | FALSE
10437 | MRT-YD08-P0QHY-125473 | 2020-02-27 | MRT-HK-REC-TT-201066 | FA | 1 | TRUE | TRUE | FALSE
10438 | MRT-DP00-P0SA-135741 | 2020-02-27 | MRT-HK-REC-TT-201069 | FA | 1 | TRUE | TRUE | FALSE
10439 | MRT-DT01-P0GDG-135079 | 2020-02-27 | MRT-HK-REC-TT-201068 | FA | 1 | TRUE | TRUE | FALSE
10440 | MRT-XJ00-P2PAB-142200 | 2020-02-27 | MRT-DS-REC-TT-200021-FC | FC | 1A | TRUE | TRUE | FALSE
10441 | MRT-YT01-P3GC-135164 | 2020-02-28 | MRT-HK-REC-TT-201070 | FA | 1 | TRUE | TRUE | FALSE
10442 | MRT-YV02-P2CJJ-240121 | 2020-02-28 | MRT-DS-REC-TT-200022-FC | FC | 2 | TRUE | TRUE | FALSE
10443 | MRT-YV02-P3CJJ-240113 | 2020-02-28 | MRT-DS-REC-TT-200022-FC | FC | 1 | TRUE | TRUE | FALSE
10444 | MRT-YK08-P2LBG-111300 | 2020-02-28 | MRT-DS-REC-TT-200023-FC | FC | 3 | TRUE | TRUE | FALSE
10445 | MRT-YK08-P3LBG-111300 | 2020-02-28 | MRT-DS-REC-TT-200023-FC | FC | 3 | TRUE | TRUE | FALSE
10446 | MRT-YU01-P0SMU-125026 | 2020-03-02 | MRT-HK-REC-TT-201071 | FA | 0 | TRUE | FALSE | FALSE
10447 | MRT-XW03-P0BAY-150023 | 2020-03-02 | MRT-HK-REC-TT-201072 | FI | 0 | TRUE | FALSE | FALSE
10448 | MRT-XJ00-P0QCH-140000 | 2020-03-02 | MRT-DS-REC-TT-200024-FC | FC | 1 | TRUE | TRUE | FALSE
10449 | MRT-XJ00-P0GHC-141000 | 2020-03-03 | MRT-DS-REC-TT-200027-FC | FC | 1C | TRUE | TRUE | FALSE
10450 | MRT-XJ00-P0GHD-141000 | 2020-03-03 | MRT-DS-REC-TT-200027-FC | FC | 1C | TRUE | TRUE | FALSE
10451 | MRT-XJ00-P0GKB-141000 | 2020-03-03 | MRT-DS-REC-TT-200027-FC | FC | 1C | TRUE | TRUE | FALSE
10452 | MRT-XJ00-P0QJA-141000 | 2020-03-03 | MRT-DS-REC-TT-200027-FC | FC | 1B | TRUE | TRUE | FALSE
10453 | MRT-XJ00-P0GMA-141000 | 2020-03-03 | MRT-DS-REC-TT-200027-FC | FC | 1C | TRUE | TRUE | FALSE
10454 | MRT-XJ00-P0EGD-141000 | 2020-03-03 | MRT-DS-REC-TT-200027-FC | FC | 1B | TRUE | TRUE | FALSE
10455 | MRT-XJ00-P0EKG-141000 | 2020-03-03 | MRT-DS-REC-TT-200027-FC | FC | 1B | TRUE | TRUE | FALSE
10456 | MRT-XJ00-P0LAA-140000 | 2020-03-03 | MRT-DS-REC-TT-200027-FC | FC | 1B | TRUE | TRUE | FALSE
10457 | MRT-XK00-P2LBA-142000 | 2020-03-04 | MRT-DS-REC-TT-200025-FC | FC | 3 | TRUE | TRUE | FALSE
10458 | MRT-XK00-P2LAB-142000 | 2020-03-04 | MRT-DS-REC-TT-200025-FC | FC | 3 | TRUE | TRUE | FALSE
10459 | MRT-XK00-P2ACW-142000 | 2020-03-04 | MRT-DS-REC-TT-200025-FC | FC | 3 | TRUE | TRUE | FALSE
10460 | MRT-XK00-P0QCH-140001 | 2020-03-04 | MRT-DS-REC-TT-200025-FC | FI | 0 | TRUE | TRUE | FALSE
10461 | MRT-QM03-P0GHE-145065 | 2020-03-05 | MRT-HK-REC-TT-201075 | FA | 2 | TRUE | TRUE | FALSE
10462 | MRT-BT00-P0GEN-135892 | 2020-03-06 | MRT-HK-REC-TT-201077 | FA | 2 | TRUE | TRUE | FALSE
10463 | MRT-YE03-P2ZEN-163104 | 2020-03-09 | MRT-DS-REC-TT-200026 | FC | 2 | TRUE | TRUE | FALSE
10464 | MRT-MA02-P2ZEN-163105 | 2020-03-09 | MRT-DS-REC-TT-200026 | FC | 2 | TRUE | TRUE | FALSE
10465 | MRT-YD06-P2ZEN-163106 | 2020-03-09 | MRT-DS-REC-TT-200026 | FC | 2 | TRUE | TRUE | FALSE
10466 | MRT-CV03-P0ZEN-163107 | 2020-03-09 | MRT-DS-REC-TT-200026 | FC | 2 | TRUE | TRUE | FALSE
10467 | MRT-CV03-P0ZEN-163108 | 2020-03-09 | MRT-DS-REC-TT-200026 | FC | 2 | TRUE | TRUE | FALSE
10468 | MRT-YD07-P2ZEN-163109 | 2020-03-09 | MRT-DS-REC-TT-200026 | FC | 2 | TRUE | TRUE | FALSE
10469 | MRT-YR05-P2ZEN-163110 | 2020-03-09 | MRT-DS-REC-TT-200026 | FC | 2 | TRUE | TRUE | FALSE
10470 | MRT-YR05-P2ZEN-163111 | 2020-03-09 | MRT-DS-REC-TT-200026 | FC | 2 | TRUE | TRUE | FALSE
10471 | MRT-YR05-P2ZEN-163112 | 2020-03-09 | MRT-DS-REC-TT-200026 | FC | 2 | TRUE | TRUE | FALSE
10472 | MRT-YR05-P2ZEN-163113 | 2020-03-09 | MRT-DS-REC-TT-200026 | FC | 2 | TRUE | TRUE | FALSE
10473 | MRT-YR05-P2ZEN-163114 | 2020-03-09 | MRT-DS-REC-TT-200026 | FC | 2 | TRUE | TRUE | FALSE
10475 | MRT-GT00-P2ZEN-167001 | 2020-03-11 | MRT-DS-REC-TT-200013-FC | FC | 0 | TRUE | TRUE | FALSE
10476 | MRT-FF01-P0SGA-135429 | 2020-03-13 | MRT-HK-REC-TT-201078 | FA | 1 | TRUE | TRUE | FALSE
10477 | MRT-DS00-P3GC-135842 | 2020-03-13 | MRT-HK-REC-TT-201079 | FA | 3 | TRUE | TRUE | FALSE
10478 | MRT-CV05-P0GEN-135891 | 2020-03-13 | MRT-HK-REC-TT-201079 | FA | 1 | TRUE | TRUE | FALSE
10479 | MRT-XJ00-P3LBA-146000 | 2020-03-13 | MRT-DS-REC-TT-200028-FC | FC | 1A | TRUE | TRUE | FALSE
10480 | MRT-XJ00-P3LBG-146000 | 2020-03-13 | MRT-DS-REC-TT-200028-FC | FC | 1A | TRUE | TRUE | FALSE
10481 | MRT-XJ00-P3LCM-146000 | 2020-03-13 | MRT-DS-REC-TT-200028-FC | FC | 1A | TRUE | TRUE | FALSE
10482 | MRT-XJ00-P3LAB-146000 | 2020-03-13 | MRT-DS-REC-TT-200028-FC | FC | 1A | TRUE | TRUE | FALSE
10483 | MRT-XJ00-P3LCA-146000 | 2020-03-13 | MRT-DS-REC-TT-200028-FC | FC | 1A | TRUE | TRUE | FALSE
10484 | MRT-XJ00-P3QU-146000 | 2020-03-13 | MRT-DS-REC-TT-200028-FC | FC | 1A | TRUE | TRUE | FALSE
10485 | MRT-XJ00-P3QC-146000 | 2020-03-13 | MRT-DS-REC-TT-200028-FC | FC | 1A | TRUE | TRUE | FALSE
10486 | MRT-XJ00-P3MAV-146000 | 2020-03-13 | MRT-DS-REC-TT-200028-FC | FC | 1A | TRUE | TRUE | FALSE
10487 | MRT-XJ00-P3SCA-146000 | 2020-03-13 | MRT-DS-REC-TT-200028-FC | FC | 1A | TRUE | TRUE | FALSE
10488 | MRT-XJ00-P3QFB-146000 | 2020-03-13 | MRT-DS-REC-TT-200028-FC | FC | 1A | TRUE | TRUE | FALSE
10489 | MRT-XJ00-P3SCB-146000 | 2020-03-13 | MRT-DS-REC-TT-200028-FC | FC | 1A | TRUE | TRUE | FALSE
10490 | MRT-XJ00-P3MAA-146000 | 2020-03-13 | MRT-DS-REC-TT-200028-FC | FC | 1A | TRUE | TRUE | FALSE
10491 | MRT-YF02-P3CRA-160118 | 2020-03-16 | MRT-HK-REC-TT-201080 | FI | 0 | TRUE | FALSE | FALSE
10492 | MRT-DN02-P2ZEN-830025 | 2020-03-19 | MRT-DS-REC-TT-200030 | FA | 0 | TRUE | TRUE | FALSE
10493 | MRT-CA00-P0USX-186806 | 2020-03-19 | MRT-HK-REC-TT-201082 | FA | 2 | TRUE | TRUE | FALSE
10494 | MRT-CA00-P0USX-186808 | 2020-03-19 | MRT-HK-REC-TT-201082 | FA | 2 | TRUE | TRUE | FALSE
10495 | MRT-CA01-P0USX-186818 | 2020-03-19 | MRT-HK-REC-TT-201082 | FA | 1 | TRUE | TRUE | FALSE
10496 | MRT-CA03-P0USX-186828 | 2020-03-19 | MRT-HK-REC-TT-201082 | FA | 1 | TRUE | TRUE | FALSE
10497 | MRT-CA01-P0USX-186842 | 2020-03-19 | MRT-HK-REC-TT-201082 | FA | 1 | TRUE | TRUE | FALSE
10498 | MRT-CA00-P0USX-186807 | 2020-03-19 | MRT-HK-REC-TT-201082 | FA | 2 | TRUE | TRUE | FALSE
10499 | MRT-DP00-P2LB-122106 | 2020-03-19 | MRT-DS-REC-TT-200031 | FC | 6 | TRUE | TRUE | FALSE
10500 | MRT-YT01-P0GN-135248 | 2020-03-19 | MRT-HK-REC-TT-201083 | FA | 1 | TRUE | TRUE | FALSE
10501 | MRT-YT01-P3GC-135146 | 2020-03-19 | MRT-HK-REC-TT-201083 | FA | 1 | TRUE | TRUE | FALSE
10502 | MRT-XR00-P0SA-135757 | 2020-03-20 | MRT-HK-REC-TT-201084 | FA | 1 | TRUE | TRUE | FALSE
10503 | MRT-YT01-P0GEN-135717 | 2020-03-20 | MRT-HK-REC-TT-201085 | FA | 0 | TRUE | FALSE | FALSE
10504 | MRT-DD03-P0GEN-135385 | 2020-03-20 | MRT-HK-REC-TT-201086 | FA | 2 | TRUE | TRUE | FALSE
10505 | MRT-CH04-P0BTL-150638 | 2020-03-20 | MRT-HK-REC-TT-201087 | FA | 1 | TRUE | TRUE | FALSE
10506 | MRT-DN04-P0BRU-150267 | 2020-03-20 | MRT-HK-REC-TT-201087 | FA | 3 | TRUE | TRUE | FALSE
10507 | MRT-XJ00-P3LBA-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10508 | MRT-XJ00-P3LBG-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10509 | MRT-XJ00-P3LCM-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10510 | MRT-XJ00-P3LAB-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10511 | MRT-XJ00-P3LCA-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10512 | MRT-XJ00-P3QC-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10513 | MRT-XJ00-P3MAV-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10514 | MRT-XJ00-P3SCA-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10515 | MRT-XJ00-P3QFB-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10516 | MRT-XJ00-P3QFB-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10517 | MRT-XJ00-P3SCB-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10518 | MRT-XJ00-P3MAA-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10519 | MRT-XJ00-P3LBA-143000 | 2020-03-25 | MRT-DS-REC-TT-200029-FC | FC | 2B | TRUE | TRUE | FALSE
10520 | MRT-XJ00-P3LBG-143000 | 2020-03-25 | MRT-DS-REC-TT-200029-FC | FC | 2A | TRUE | TRUE | FALSE
10521 | MRT-XJ00-P3LAB-143000 | 2020-03-25 | MRT-DS-REC-TT-200029-FC | FC | 2A | TRUE | TRUE | FALSE
10522 | MRT-XJ00-P3LCA-143000 | 2020-03-25 | MRT-DS-REC-TT-200029-FC | FC | 2B | TRUE | TRUE | FALSE
10523 | MRT-XJ00-P3PGB-143000 | 2020-03-25 | MRT-DS-REC-TT-200029-FC | FC | 2A | TRUE | TRUE | FALSE
10524 | MRT-XJ00-P3LCM-143000 | 2020-03-25 | MRT-DS-REC-TT-200029-FC | FC | 2A | TRUE | TRUE | FALSE
10525 | MRT-XJ00-P3QU-147000 | 2020-03-25 | MRT-DS-REC-TT-200032-FC | FC | 1A | TRUE | TRUE | FALSE
10526 | MRT-CA00-P0USG-186856 | 2020-03-25 | MRT-HK-REC-TT-201089 | FA | 3 | TRUE | TRUE | FALSE
10527 | MRT-CA00-P0USG-186862 | 2020-03-25 | MRT-HK-REC-TT-201089 | FA | 3 | TRUE | TRUE | FALSE
10528 | MRT-CA00-P0USG-186866 | 2020-03-25 | MRT-HK-REC-TT-201089 | FA | 1 | TRUE | TRUE | FALSE
10529 | MRT-CA00-P0USG-186867 | 2020-03-25 | MRT-HK-REC-TT-201089 | FA | 1 | TRUE | TRUE | FALSE
10530 | MRT-DD04-P0GEN-135390 | 2020-03-25 | MRT-HK-REC-TT-201090 | FA | 1 | TRUE | TRUE | FALSE
10531 | MRT-XG02-P2LB-122022 | 2020-03-30 | MRT-DS-REC-TT-200014-FC | FC | 10 | TRUE | TRUE | FALSE
10532 | MRT-XG02-P3LB-122022 | 2020-03-30 | MRT-DS-REC-TT-200014-FC | FC | 7 | TRUE | TRUE | FALSE
10533 | MRT-CC02-P2UMA-170507 | 2020-03-30 | MRT-DS-REC-TT-200016-FC | FC | 5 | TRUE | TRUE | FALSE
10534 | MRT-VK02-P2UMA-170510 | 2020-03-30 | MRT-DS-REC-TT-200016-FC | FC | 5 | TRUE | TRUE | FALSE
10535 | MRT-CC02-P3UMA-170507 | 2020-03-30 | MRT-DS-REC-TT-200016-FC | FC | 5 | TRUE | TRUE | FALSE
10536 | MRT-VK02-P3UMA-170510 | 2020-03-30 | MRT-DS-REC-TT-200016-FC | FC | 5 | TRUE | TRUE | FALSE
10537 | MRT-DN05-P2CJJ-240115 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | TRUE | TRUE | FALSE
10538 | MRT-DN05-P3CJJ-240107 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | TRUE | TRUE | FALSE
10539 | MRT-DN05-P2CJJ-240124 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | TRUE | TRUE | FALSE
10540 | MRT-DN05-P3CJJ-240116 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | TRUE | TRUE | FALSE
10541 | MRT-DN05-P3MAX-220146 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | TRUE | TRUE | FALSE
10542 | MRT-DN05-P3MAV-220171 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | TRUE | TRUE | FALSE
10543 | MRT-DN05-P2MAV-240137 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | TRUE | TRUE | FALSE
10544 | MRT-DN05-P3MAV-240136 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | TRUE | TRUE | FALSE
10545 | MRT-DN05-P3MAV-220094 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | TRUE | TRUE | FALSE
10546 | MRT-DN05-P3MAD-240183 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | TRUE | TRUE | FALSE
10547 | MRT-DN05-P3MAM-220140 | 2020-04-02 | MRT-DS-REC-TT-200034 | FC | 1 | TRUE | TRUE | FALSE
10548 | MRT-YL15-P0SMU-125028 | 2020-04-07 | MRT-HK-REC-TT-201093 | FA | 1 | TRUE | TRUE | FALSE
10549 | MRT-YL16-P0SMU-125029 | 2020-04-07 | MRT-HK-REC-TT-201093 | FA | 1 | TRUE | TRUE | FALSE
10550 | MRT-YV02-P2MAX-220095 | 2020-04-08 | MRT-DS-REC-TT-200033-FC | FI | 0 | TRUE | FALSE | FALSE
10551 | MRT-XJ00-P2LB-142000 | 2020-04-09 | MRT-DS-REC-TT-200035-FC | FC | 1A | TRUE | TRUE | FALSE
10552 | MRT-XJ00-P3LB-143000 | 2020-04-09 | MRT-DS-REC-TT-200035-FC | FC | 1A | TRUE | TRUE | FALSE
10553 | MRT-XJ00-P3LB-144000 | 2020-04-09 | MRT-DS-REC-TT-200035-FC | FC | 1A | TRUE | TRUE | FALSE
10554 | MRT-YL00-P0SA-135768 | 2020-04-16 | MRT-HK-REC-TT-201094 | FI | 1 | TRUE | TRUE | FALSE
10555 | MRT-YR01-P0LB-830501 | 2020-04-16 | MRT-HK-REC-TT-201097 | FA | 1 | TRUE | TRUE | FALSE
10556 | MRT-YR08-P3GC-135170 | 2020-04-16 | MRT-HK-REC-TT-201102 | FI | 1 | TRUE | TRUE | FALSE
10557 | MRT-YR08-P0GN-135266 | 2020-04-16 | MRT-HK-REC-TT-201103 | FI | 1 | TRUE | TRUE | FALSE
10558 | MRT-DN02-P0ABA-150904 | 2020-04-16 | MRT-HK-REC-TT-201106 | FA | 2 | TRUE | TRUE | FALSE
10559 | MRT-UC08-P0LB-830514 | 2020-04-16 | MRT-HK-REC-TT-201098 | FA | 0 | TRUE | FALSE | FALSE
10560 | MRT-XV00-P0LB-830511 | 2020-04-16 | MRT-HK-REC-TT-201099 | FA | 0 | TRUE | FALSE | FALSE
10561 | MRT-DN03-P0GEN-135883 | 2020-04-16 | MRT-HK-REC-TT-201101 | FA | 0 | TRUE | FALSE | FALSE
10562 | MRT-FF01-P0SGA-135653 | 2020-04-16 | MRT-HK-REC-TT-201104 | FI | 1 | TRUE | TRUE | FALSE
10563 | MRT-FF01-P0SGA-135654 | 2020-04-16 | MRT-HK-REC-TT-201105 | FI | 1 | TRUE | TRUE | FALSE
10564 | MRT-DN02-P0MAV-830519 | 2020-04-16 | MRT-HK-REC-TT-201095 | FA | 0 | TRUE | FALSE | FALSE
10565 | MRT-DD00-P0SMU-125036 | 2020-04-17 | MRT-HK-REC-TT-201108 | FA | 1 | TRUE | TRUE | FALSE
10566 | MRT-CQ02-P0SMU-125038 | 2020-04-17 | MRT-HK-REC-TT-201107 | FA | 1 | TRUE | TRUE | FALSE
10567 | MRT-DN03-P0GEN-135719 | 2020-04-17 | MRT-HK-REC-TT-201109 | FA | 1 | TRUE | TRUE | FALSE
10568 | MRT-DD04-P0GEN-135894 | 2020-04-17 | MRT-HK-REC-TT-201110 | FA | 0 | TRUE | FALSE | FALSE
10569 | MRT-QM01-P0GEN-135893 | 2020-04-17 | MRT-HK-REC-TT-201111 | FI | 0 | TRUE | FALSE | FALSE
10570 | MRT-QM01-P0SMU-125051 | 2020-04-17 | MRT-HK-REC-TT-201112 | FA | 1 | TRUE | TRUE | FALSE
10571 | MRT-CA00-P0USG-186864 | 2020-04-20 | MRT-HK-REC-TT-201113 | FA | 6 | TRUE | TRUE | FALSE
10572 | MRT-CA00-P0UST-186917 | 2020-04-20 | MRT-HK-REC-TT-201114 | FA | 6 | TRUE | TRUE | FALSE
10573 | MRT-CA01-P0UGX-186972 | 2020-04-20 | MRT-HK-REC-TT-201115 | FA | 6 | TRUE | TRUE | FALSE
10582 | MRT-QM03-P0ZEN-155046 | 2020-04-22 | MRT-HK-REC-TT-201116 | FA | 0 | TRUE | FALSE | FALSE
10583 | MRT-BN00-P0EKF-125633 | 2020-04-22 | MRT-HK-REC-TT-201118 | FA | 1 | TRUE | TRUE | FALSE
10584 | MRT-YT01-P0SMU-125022 | 2020-04-22 | MRT-HK-REC-TT-201120 | FI | 1 | TRUE | TRUE | FALSE
10585 | MRT-YD02-P3ZEN-165020 | 2020-04-23 | MRT-HK-REC-TT-201119 | FI | 0 | TRUE | TRUE | FALSE
10586 | MRT-YT02-P3PAC-130001 | 2020-04-25 | MRT-HK-REC-TT-201142 | FI | 1 | TRUE | TRUE | FALSE
10587 | MRT-YT02-P2PAC-130001 | 2020-04-25 | MRT-HK-REC-TT-201141 | FI | 1 | TRUE | TRUE | FALSE
10588 | MRT-YL35-P3PAC-130001 | 2020-04-25 | MRT-HK-REC-TT-201140 | FI | 1 | TRUE | TRUE | FALSE
10591 | MRT-YL35-P2PAC-130001 | 2020-04-25 | MRT-HK-REC-TT-201139 | FI | 1 | TRUE | TRUE | FALSE
10592 | MRT-YL00-P3PAC-130001 | 2020-04-25 | MRT-HK-REC-TT-201138 | FI | 1 | TRUE | TRUE | FALSE
10593 | MRT-YL00-P2PAC-130001 | 2020-04-25 | MRT-HK-REC-TT-201137 | FI | 1 | TRUE | TRUE | FALSE
10594 | MRT-CC05-P2PAC-130004 | 2020-04-25 | MRT-HK-REC-TT-201136 | FI | 1 | TRUE | TRUE | FALSE
10595 | MRT-YV02-P0GEN-135378 | 2020-04-25 | MRT-HK-REC-TT-201131 | FA | 0 | TRUE | TRUE | FALSE
10596 | MRT-DN05-P0AYE-135486 | 2020-04-25 | MRT-HK-REC-TT-201132 | FA | 0 | TRUE | TRUE | FALSE
10597 | MRT-DN03-P0GEN-135720 | 2020-04-25 | MRT-HK-REC-TT-201134 | FA | 0 | TRUE | TRUE | FALSE
10598 | MRT-YL01-P0GEN-135348 | 2020-04-25 | MRT-HK-REC-TT-201135 | FA | 0 | TRUE | TRUE | FALSE
10589 | MRT-DN02-P0ZEN-860026 | 2020-04-27 | MRT-DS-REC-TT-200037 | FI | 0 | TRUE | TRUE | FALSE
10590 | MRT-DN02-P0ZEN-860027 | 2020-04-27 | MRT-DS-REC-TT-200038 | FA | 0 | TRUE | TRUE | FALSE
10600 | MRT-YL16-P0ZEN-165028 | 2020-04-28 | MRT-HK-REC-TT-201143 | FI | 0 | TRUE | TRUE | FALSE
10599 | MRT-DN02-P2ZEN-830019 | 2020-04-29 | MRT-DS-REC-TT-200039 | FA | 0 | TRUE | TRUE | FALSE
10601 | MRT-YV02-P3MAX-220144 | 2020-04-29 | MRT-DS-REC-TT-200040-FC | FI | 0 | TRUE | TRUE | FALSE
10602 | MRT-XW03-P0ASR-150197 | 2020-05-02 | MRT-HK-REC-TT-201144 | FA | 0 | TRUE | TRUE | FALSE
10604 | MRT-YF02-P2CJJ-240112 | 2020-05-08 | MRT-DS-REC-TT-200041-FC | FC | 1 | TRUE | TRUE | FALSE
10605 | MRT-YF02-P3CJJ-240104 | 2020-05-08 | MRT-DS-REC-TT-200041-FC | FC | 2 | TRUE | TRUE | FALSE
10606 | MRT-XK00-P3MAA-220207 | 2020-05-08 | MRT-DS-REC-TT-200041-FC | FC | 1 | TRUE | TRUE | FALSE
10607 | MRT-DM02-P2MAA-220199 | 2020-05-08 | MRT-DS-REC-TT-200041-FC | FC | 1 | TRUE | TRUE | FALSE
10608 | MRT-DM02-P3MAA-220199 | 2020-05-08 | MRT-DS-REC-TT-200041-FC | FC | 1 | TRUE | TRUE | FALSE
10615 | MRT-DM01-P0SA-135736 | 2020-05-14 | MRT-HK-REC-TT-201160 | FA | 0 | TRUE | TRUE | FALSE
10616 | MRT-DN02-P2ZEN-830021 | 2020-05-18 | MRT-DS-REC-TT-200042 | FA | 0 | TRUE | FALSE | FALSE
10617 | MRT-DN02-P2ZEN-830018 | 2020-05-18 | MRT-DS-REC-TT-200043 | FA | 0 | TRUE | FALSE | FALSE
10618 | MRT-DN02-P2ZEN-830020 | 2020-05-18 | MRT-DS-REC-TT-200044 | FA | 0 | TRUE | FALSE | FALSE
10619 | MRT-DN02-P2ZEN-830022 | 2020-05-18 | MRT-DS-REC-TT-200045 | FA | 0 | TRUE | FALSE | FALSE
10620 | MRT-DN02-P2ZEN-830024 | 2020-05-18 | MRT-DS-REC-TT-200046 | FA | 0 | TRUE | FALSE | FALSE
10623 | MRT-DN02-P2MAV-830017 | 2020-05-18 | MRT-DS-REC-TT-200048 | FA | 1 | TRUE | TRUE | FALSE
10624 | MRT-DN02-P2ZEN-830023 | 2020-05-18 | MRT-DS-REC-TT-200047 | FA | 0 | TRUE | FALSE | FALSE
10628 | MRT-YL16-P3MKA-150097 | 2020-05-20 | MRT-HK-REC-TT-201163 | FI | 0 | TRUE | TRUE | FALSE
10629 | MRT-DD00-P0SMU-125035 | 2020-05-28 | MRT-HK-REC-TT-201167 | FA | 1 | TRUE | TRUE | FALSE
10630 | MRT-XA00-P0GEN-135305 | 2020-05-28 | MRT-HK-REC-TT-201164 | FA | 3 | TRUE | TRUE | FALSE
10631 | MRT-DD04-P0GEN-135390 | 2020-05-28 | MRT-HK-REC-TT-201168 | FA | 2 | TRUE | TRUE | FALSE
10632 | MRT-DN04-P0GEN-135890 | 2020-05-29 | MRT-HK-REC-TT-201170 | FA | 1 | TRUE | TRUE | FALSE
10633 | MRT-CC02-P0UPC-175720 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 4 | TRUE | TRUE | FALSE
10634 | MRT-CC02-P0UPC-175725 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 4 | TRUE | TRUE | FALSE
10635 | MRT-CC02-P0UPC-175750 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10636 | MRT-CC02-P0UPC-175751 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10637 | MRT-CC02-P0UPC-175752 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10638 | MRT-CC02-P0UPC-175753 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10639 | MRT-CC02-P0UPC-175755 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10640 | MRT-CC02-P0UPC-175756 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10641 | MRT-CC02-P0UPC-175757 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10642 | MRT-CC02-P0UPC-175759 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10643 | MRT-CC02-P0UPC-175760 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10644 | MRT-CC02-P0UPC-175762 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10645 | MRT-CC02-P0UPC-175763 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10646 | MRT-CC02-P0UPC-175765 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10647 | MRT-CC02-P0UPC-175766 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10648 | MRT-CC02-P0UPC-175767 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10649 | MRT-CC02-P0UPC-175769 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10650 | MRT-CC02-P0UPC-175770 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10651 | MRT-CC02-P0UPC-175771 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10652 | MRT-CC02-P0UPC-175754 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10653 | MRT-CC02-P0UPC-175773 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10654 | MRT-CC02-P0UPC-175774 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 2 | TRUE | TRUE | FALSE
10655 | MRT-CC03-P0UPC-176385 | 2020-06-03 | MRT-HK-REC-TT-201172 | FA | 1 | TRUE | TRUE | FALSE
10656 | MRT-XT00-P2MAA-220002 | 2020-06-09 | MRT-DS-REC-TT-200049 | FC | 2 | TRUE | TRUE | FALSE
10657 | MRT-XT00-P3MAA-220002 | 2020-06-09 | MRT-DS-REC-TT-200049 | FC | 2 | TRUE | TRUE | FALSE
10658 | MRT-CA03-P0UQA-186578 | 2020-06-10 | MRT-HK-REC-TT-201175 | FA | 0 | TRUE | TRUE | FALSE
10659 | MRT-CC02-P0UPC-175735 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 2 | TRUE | TRUE | FALSE
10660 | MRT-CC02-P0UPC-175746 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 2 | TRUE | TRUE | FALSE
10661 | MRT-CC02-P0UPC-175743 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 2 | TRUE | TRUE | FALSE
10662 | MRT-CC02-P0UPC-175742 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 2 | TRUE | TRUE | FALSE
10663 | MRT-CC02-P0UPC-175741 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 2 | TRUE | TRUE | FALSE
10664 | MRT-CC02-P0UPC-175733 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 2 | TRUE | TRUE | FALSE
10665 | MRT-CC03-P0UPC-176350 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 1 | TRUE | TRUE | FALSE
10666 | MRT-CC03-P0UPC-176360 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 1 | TRUE | TRUE | FALSE
10667 | MRT-CC03-P0UPC-176351 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 1 | TRUE | TRUE | FALSE
10668 | MRT-CC02-P0ULX-176217 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 5 | TRUE | TRUE | FALSE
10669 | MRT-CC02-P0ULX-176218 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 3 | TRUE | TRUE | FALSE
10670 | MRT-CC02-P0ULX-176219 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 2 | TRUE | TRUE | FALSE
10671 | MRT-CC02-P0ULX-176220 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 3 | TRUE | TRUE | FALSE
10672 | MRT-CC02-P0ULX-176221 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 4 | TRUE | TRUE | FALSE
10673 | MRT-CC02-P0ULX-176222 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 3 | TRUE | TRUE | FALSE
10674 | MRT-CC02-P0ULX-176223 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 3 | TRUE | TRUE | FALSE
10675 | MRT-CC02-P0ULX-176224 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 3 | TRUE | TRUE | FALSE
10676 | MRT-CC02-P0ULX-176225 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 4 | TRUE | TRUE | FALSE
10677 | MRT-CC02-P0UZT-175930 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 3 | TRUE | TRUE | FALSE
10678 | MRT-CC02-P0UZT-175925 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 3 | TRUE | TRUE | FALSE
10679 | MRT-CC02-P0UZT-175924 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 2 | TRUE | TRUE | FALSE
10680 | MRT-CC02-P0UZT-175923 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 2 | TRUE | TRUE | FALSE
10681 | MRT-CC02-P0UZT-175922 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 3 | TRUE | TRUE | FALSE
10682 | MRT-CC02-P0UZT-175921 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 3 | TRUE | TRUE | FALSE
10683 | MRT-CC02-P0UZT-175920 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 3 | TRUE | TRUE | FALSE
10684 | MRT-CC02-P0ULX-176226 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 2 | TRUE | TRUE | FALSE
10685 | MRT-CC02-P0ULX-176227 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 3 | TRUE | TRUE | FALSE
10686 | MRT-CC02-P0ULX-176228 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 1 | TRUE | TRUE | FALSE
10687 | MRT-CC02-P0UZT-175927 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 1 | TRUE | TRUE | FALSE
10688 | MRT-CC02-P0UZT-175926 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 1 | TRUE | TRUE | FALSE
10689 | MRT-CC02-P0ULX-176210 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 1 | TRUE | TRUE | FALSE
10690 | MRT-CC02-P0ULX-176211 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 2 | TRUE | TRUE | FALSE
10691 | MRT-CC02-P0ULX-176229 | 2020-06-15 | MRT-HK-REC-TT-201179 | FA | 2 | TRUE | TRUE | FALSE
10692 | MRT-YL16-P2ZEN-165029 | 2020-06-16 | MRT-HK-REC-TT-201184 | FI | 0 | TRUE | TRUE | FALSE
10693 | MRT-DM01-P0SGA-135474 | 2020-06-20 | MRT-HK-REC-TT-201178 | FA | 2 | TRUE | TRUE | FALSE
10694 | MRT-DM02-P2MAA-220178 | 2020-06-22 | MRT-DS-REC-TT-200050 | FI | 0 | TRUE | TRUE | FALSE
10695 | MRT-DM02-P3MAA-220189 | 2020-06-22 | MRT-DS-REC-TT-200050 | FC | 1 | TRUE | TRUE | FALSE
10696 | MRT-DD04-P0SMU-125051 | 2020-06-23 | MRT-HK-REC-TT-201187 | FA | 1 | TRUE | TRUE | FALSE
10697 | MRT-QM03-P0ZEN-185011 | 2020-06-24 | MRT-HK-REC-TT-201190 | FA | 1 | TRUE | TRUE | FALSE
10698 | MRT-DN02-P2MAV-830017 | 2020-06-25 | MRT-DS-REC-TT-200051 | FA | 1 | FALSE | TRUE | FALSE
10699 | MRT-DN02-P2ZEN-830018 | 2020-06-25 | MRT-DS-REC-TT-200051 | FA | 0 | FALSE | TRUE | FALSE
10700 | MRT-DN02-P2ZEN-830019 | 2020-06-25 | MRT-DS-REC-TT-200051 | FA | 1 | TRUE | TRUE | FALSE
10701 | MRT-DN02-P2ZEN-830020 | 2020-06-25 | MRT-DS-REC-TT-200051 | FA | 0 | FALSE | TRUE | FALSE
10702 | MRT-DN02-P2ZEN-830021 | 2020-06-25 | MRT-DS-REC-TT-200051 | FA | 0 | FALSE | TRUE | FALSE
10703 | MRT-DN02-P2ZEN-830022 | 2020-06-25 | MRT-DS-REC-TT-200051 | FA | 0 | FALSE | TRUE | FALSE
10704 | MRT-DN02-P2ZEN-830023 | 2020-06-25 | MRT-DS-REC-TT-200051 | FA | 0 | FALSE | TRUE | FALSE
10705 | MRT-DN02-P2ZEN-830024 | 2020-06-25 | MRT-DS-REC-TT-200051 | FA | 0 | FALSE | TRUE | FALSE
10706 | MRT-XG01-P2MAA-220045 | 2020-06-25 | MRT-DS-REC-TT-200052 | FC | 3 | TRUE | TRUE | FALSE
10707 | MRT-XG01-P3MAA-220045 | 2020-06-26 | MRT-DS-REC-TT-200054-FC | FC | 2 | TRUE | TRUE | FALSE
10708 | MRT-DM02-P3MAA-220161 | 2020-06-29 | MRT-DS-REC-TT-200053 | FI | 0 | TRUE | TRUE | FALSE
10709 | MRT-DM02-P2MAA-220193 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10710 | MRT-DM02-P3LBA-220083 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10711 | MRT-DM02-P2MAK-220082 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10712 | MRT-DM02-P2MAX-220096 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10713 | MRT-DM02-P2MAV-220161 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10714 | MRT-DM02-P3MAV-240135 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10715 | MRT-DM02-P2MAV-220101 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10716 | MRT-DM02-P3MAA-220130 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10717 | MRT-DM02-P3MAA-240158 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10718 | MRT-DM02-P2MAD-240172 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10719 | MRT-DM02-P2MAM-220141 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10720 | MRT-DM02-P3MAM-220139 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10721 | MRT-CQ02-P2MAK-220084 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10722 | MRT-CQ02-P2MAX-220098 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10723 | MRT-CQ02-P2MAV-220163 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10724 | MRT-CQ02-P2MAV-220103 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10725 | MRT-CQ02-P2MAA-240145 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10726 | MRT-CQ02-P2MAA-220194 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10727 | MRT-CQ02-P3MAA-220194 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10728 | MRT-CQ02-P2MAW-220159 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10729 | MRT-CQ02-P2MAA-220156 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10730 | MRT-CQ02-P2MAA-220132 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10731 | MRT-CQ02-P2MAD-240174 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10732 | MRT-CQ02-P2MAM-220143 | 2020-06-29 | MRT-DS-REC-TT-200053-FC | FI | 0 | TRUE | TRUE | FALSE
10733 |  | 2020-06-29 | MRT-DS-REC-TT-200053 |  |  | FALSE | FALSE | FALSE
10734 | MRT-DN05-P2MAX-220097 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | TRUE | TRUE | FALSE
10735 | MRT-DN05-P2MAV-220162 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | TRUE | TRUE | FALSE
10736 | MRT-DN05-P2MAV-220102 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | TRUE | TRUE | FALSE
10737 | MRT-DN05-P2MAD-240173 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | TRUE | TRUE | FALSE
10738 | MRT-DN05-P2MAM-220142 | 2020-06-29 | MRT-DS-REC-TT-200055 | FA | 0 | TRUE | TRUE | FALSE
10740 | MRT-DD04-P0GEN-135390 | 2020-06-29 | MRT-HK-REC-TT-201198 | FA | 3 | TRUE | TRUE | FALSE
10741 | MRT-YD00-P3MKA-220004 | 2020-06-30 | MRT-DS-REC-TT-200056-FC | FI | 1 | TRUE | TRUE | FALSE
10744 | MRT-CA01-P0UXA-186709 | 2020-06-30 | MRT-HK-REC-TT-201199 | FA | 0 | TRUE | TRUE | FALSE
10742 | MRT-XG02-P2LBA-110003 | 2020-07-02 | MRT-DS-REC-TT-200057 | FC | 8 | TRUE | TRUE | FALSE
10743 | MRT-XG02-P3LBA-110003 | 2020-07-02 | MRT-DS-REC-TT-200057 | FC | 8 | TRUE | TRUE | FALSE
10745 | MRT-DL01-P0SA-135776 | 2020-07-02 | MRT-HK-REC-TT-201200 | FI | 0 | TRUE | TRUE | FALSE
10746 | MRT-QM04-P0SA-135773 | 2020-07-02 | MRT-HK-REC-TT-201200 | FI | 0 | TRUE | TRUE | FALSE
10747 | MRT-YL19-P0SA-135763 | 2020-07-02 | MRT-HK-REC-TT-201200 | FI | 0 | TRUE | TRUE | FALSE
10748 | MRT-YL19-P0SA-135764 | 2020-07-02 | MRT-HK-REC-TT-201200 | FI | 0 | TRUE | TRUE | FALSE
10749 | MRT-DN05-P0AYE-135486 | 2020-07-02 | MRT-HK-REC-TT-201201 | FA | 1 | TRUE | TRUE | FALSE
10750 | MRT-QM07-P0CRS-160006 | 2020-07-03 | MRT-HK-REC-TT-201202 | FI | 0 | TRUE | TRUE | FALSE
10751 | MRT-BF06-P0CRA-160110 | 2020-07-03 | MRT-HK-REC-TT-201202 | FI | 0 | TRUE | TRUE | FALSE
10752 | MRT-BF06-P0CRA-160109 | 2020-07-03 | MRT-HK-REC-TT-201202 | FI | 0 | TRUE | TRUE | FALSE
10753 | MRT-BF06-P0CRA-160108 | 2020-07-03 | MRT-HK-REC-TT-201202 | FA | 0 | TRUE | TRUE | FALSE
10754 | MRT-XR00-P0QHY-125414 | 2020-07-07 | MRT-HK-REC-TT-201204 | FA | 0 | TRUE | TRUE | FALSE
10967 | MRT-YR01-P0LB-830501 | 2020-07-07 | MRT-HK-REC-TT-201203 | FA | 2 | TRUE | TRUE | FALSE
10755 | MRT-QM03-P0ZEN-185012 | 2020-07-08 | MRT-HK-REC-TT-201205 | FI | 1 | TRUE | TRUE | FALSE
10756 | MRT-YL15-P2CJJ-240122 | 2020-07-09 | MRT-DS-REC-TT-200058 | FI | 0 | TRUE | TRUE | FALSE
10757 | MRT-YT02-P2MAD-240167 | 2020-07-09 | MRT-DS-REC-TT-200058 | FI | 0 | TRUE | TRUE | FALSE
4 | MRT-CC02-P0UYX-175336 | 2020-07-11 | MRT-HK-REC-TT-201207 | FA | 2 | TRUE | TRUE | FALSE
5 | MRT-CC02-P0UYX-175276 | 2020-07-11 | MRT-HK-REC-TT-201207 | FA | 1 | TRUE | TRUE | FALSE
10758 | MRT-YE00-P0GEN-135365 | 2020-07-11 | MRT-HK-REC-TT-201206 | FI | 0 | TRUE | TRUE | FALSE
10759 | MRT-XG08-P0GEN-135321 | 2020-07-11 | MRT-HK-REC-TT-201206 | FI | 0 | TRUE | TRUE | FALSE
1 | MRT-CC02-P3UEJ-170907 | 2020-07-13 | MRT-DS-REC-TT-200059-FC | FC | 3 | TRUE | TRUE | FALSE
2 | MRT-CC02-P2UEJ-170907 | 2020-07-13 | MRT-DS-REC-TT-200059 | FC | 3 | TRUE | TRUE | FALSE
3 | MRT-DN04-P0GEN-135890 | 2020-07-13 | MRT-HK-REC-TT-201208 | FA | 2 | TRUE | TRUE | FALSE
10760 | MRT-YF00-P0GEN-135366 | 2020-07-13 | MRT-HK-REC-TT-201209 | FI | 0 | TRUE | TRUE | FALSE
10761 | MRT-YV02-P0GEN-135707 | 2020-07-14 | MRT-HK-REC-TT-201211 | FI | 0 | TRUE | TRUE | FALSE
10765 | MRT-YV02-P2CJJ-240113 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | TRUE | TRUE | FALSE
10766 | MRT-YS01-P2CJJ-240051 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | TRUE | TRUE | FALSE
10767 | MRT-YL01-P2MAD-240169 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | TRUE | TRUE | FALSE
10768 | MRT-YL00-P2CJJ-240053 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | TRUE | TRUE | FALSE
10769 | MRT-YK00-P2CJJ-240065 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | TRUE | TRUE | FALSE
10770 | MRT-YK00-P2CJJ-240049 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | TRUE | TRUE | FALSE
10771 | MRT-YF02-P2MAX-220094 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | TRUE | TRUE | FALSE
10772 | MRT-YF00-P2CJJ-240213 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | TRUE | TRUE | FALSE
10773 | MRT-CQ02-P2MAA-220203 | 2020-07-14 | MRT-DS-REC-TT-200060-FC | FI | 0 | TRUE | TRUE | FALSE
10774 | MRT-DS00-P0GN-135871 | 2020-07-14 | MRT-HK-REC-TT-201213 | FA | 1 | TRUE | TRUE | FALSE
10775 | MRT-CA00-P0UST-186912 | 2020-07-15 | MRT-HK-REC-TT-201215 | FA | 3 | TRUE | TRUE | FALSE
10776 | MRT-CA00-P0UST-186917 | 2020-07-15 | MRT-HK-REC-TT-201215 | FA | 7 | TRUE | TRUE | FALSE
10762 | MRT-QM03-P0ZEN-155017 | 2020-07-16 | MRT-HK-REC-TT-201218 | FA | 1 | TRUE | TRUE | FALSE
10763 | MRT-QM01-P0SMU-125051 | 2020-07-16 | MRT-HK-REC-TT-201219 | FI | 2 | TRUE | TRUE | FALSE
10764 | MRT-CA00-P0UCA-180106 | 2020-07-17 | MRT-DS-REC-TT-200062-FC | FC | 5 | TRUE | TRUE | FALSE
10894 | MRT-CC07-P0UZA-175101 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 1 | TRUE | TRUE | FALSE
10895 | MRT-CC02-P0UYX-175391 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 1 | TRUE | TRUE | FALSE
10896 | MRT-CC07-P0UGA-176245 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 1 | TRUE | TRUE | FALSE
10897 | MRT-CC07-P0UGA-176285 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 1 | TRUE | TRUE | FALSE
10898 | MRT-CA02-P0UGA-176305 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 1 | TRUE | TRUE | FALSE
10899 | MRT-CA06-P0UGX-186724 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 1 | TRUE | TRUE | FALSE
10900 | MRT-CA01-P0UGX-186742 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10901 | MRT-CA02-P0USG-186874 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10902 | MRT-CA06-P0UPB-187004 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10903 | MRT-CA02-P0UPB-187018 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10904 | MRT-CA02-P0UPB-187026 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10905 | MRT-CA02-P0UPB-187028 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10906 | MRT-CA02-P0UVH-187076 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10907 | MRT-CC02-P0ULY-176106 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10908 | MRT-CC02-P0ULY-176107 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10909 | MRT-CA00-P0UVH-187057 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 1 | TRUE | TRUE | FALSE
10910 | MRT-CA00-P0UXA-186671 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10911 | MRT-CA00-P0UXA-186672 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10912 | MRT-CA00-P0UXA-186673 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10913 | MRT-CA02-P0UGA-176300 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 1 | TRUE | TRUE | FALSE
10914 | MRT-CA02-P0UGA-176260 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 1 | TRUE | TRUE | FALSE
10915 | MRT-CA02-P0UGA-176265 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 1 | TRUE | TRUE | FALSE
10916 | MRT-CA01-P0UGX-186741 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10917 | MRT-CA01-P0UPB-187036 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10918 | MRT-CA01-P0UXA-186708 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10919 | MRT-CA01-P0UXA-186710 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10920 | MRT-CA01-P0UST-186945 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 1 | TRUE | TRUE | FALSE
10921 | MRT-CA01-P0UGX-186764 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10922 | MRT-CA01-P0UGX-186766 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10923 | MRT-CA01-P0UGX-186763 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10924 | MRT-CA01-P0UGX-186765 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10925 | MRT-CA01-P0UGX-186767 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10926 | MRT-CA01-P0UGX-186768 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 2 | TRUE | TRUE | FALSE
10927 | MRT-CC02-P0UYX-175392 | 2020-07-20 | MRT-HK-REC-TT-201220 | FA | 1 | TRUE | TRUE | FALSE
10783 | MRT-XS00-P0GEN-135300 | 2020-07-21 | MRT-HK-REC-TT-201221 | FA | 4 | TRUE | TRUE | FALSE
10784 | MRT-FF01-P0SGJ-135440 | 2020-07-21 | MRT-HK-REC-TT-201222 | FA | 2 | TRUE | TRUE | FALSE
10785 | MRT-YL16-P0GEN-135705 | 2020-07-21 | MRT-HK-REC-TT-201223 | FI | 0 | TRUE | TRUE | FALSE
10786 | MRT-YT01-P0QHY-125517 | 2020-07-21 | MRT-HK-REC-TT-201224 | FA | 0 | TRUE | TRUE | FALSE
10787 | MRT-YT01-P0QHY-125518 | 2020-07-21 | MRT-HK-REC-TT-201224 | FA | 0 | TRUE | TRUE | FALSE
10777 | MRT-XJ00-P3LBA-144000 | 2020-07-24 | MRT-DS-REC-TT-200061-FC | FC | 2B | TRUE | TRUE | FALSE
10778 | MRT-XJ00-P3LBG-144000 | 2020-07-24 | MRT-DS-REC-TT-200061-FC | FC | 2A | TRUE | TRUE | FALSE
10779 | MRT-XJ00-P3LCM-144000 | 2020-07-24 | MRT-DS-REC-TT-200061-FC | FC | 2A | TRUE | TRUE | FALSE
10780 | MRT-XJ00-P3LAB-144000 | 2020-07-24 | MRT-DS-REC-TT-200061-FC | FC | 2A | TRUE | TRUE | FALSE
10781 | MRT-XJ00-P3LCA-144000 | 2020-07-24 | MRT-DS-REC-TT-200061-FC | FC | 2B | TRUE | TRUE | FALSE
10782 | MRT-XJ00-P3PGB-144000 | 2020-07-24 | MRT-DS-REC-TT-200061-FC | FC | 2A | TRUE | TRUE | FALSE
10788 | MRT-DD04-P0GEN-135894 | 2020-07-24 | MRT-HK-REC-TT-201225 | FI | 1 | TRUE | TRUE | FALSE
10789 |  | 2020-07-24 | MRT-HK-REC-TT-201225 |  |  | FALSE | FALSE | FALSE
10804 | MRT-YL16-P2MKY-150085 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10805 | MRT-YL16-P3MKY-150086 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10806 | MRT-YL16-P3MKY-150087 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10807 | MRT-YL16-P2MKX-150088 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10808 | MRT-YL16-P3MKX-150089 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10809 | MRT-YL16-P4MKX-150090 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10810 | MRT-YL16-P0BFA-150092 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10811 | MRT-YL16-P0BAC-150094 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10812 | MRT-YL16-P2MKA-150095 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10813 | MRT-YL16-P3MKA-150096 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10814 | MRT-YL16-P0BJQ-150104 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10815 | MRT-YL16-P0BFA-150241 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10816 | MRT-YL16-P0BFA-150242 | 2020-07-28 | MRT-HK-REC-TT-201234 | FI | 0 | TRUE | TRUE | FALSE
10817 | MRT-GT00-P2ZEN-167001 | 2020-07-29 | MRT-DS-REC-TT-200063 | FC | 1 | TRUE | TRUE | FALSE
10818 | MRT-YL16-P0BMY-150082 | 2020-07-29 | MRT-HK-REC-TT-201235 | FI | 0 | TRUE | TRUE | FALSE
10819 | MRT-YL16-P0BMA-150093 | 2020-07-29 | MRT-HK-REC-TT-201235 | FI | 0 | TRUE | TRUE | FALSE
10820 | MRT-DL01-P0SA-135776 | 2020-08-03 | MRT-HK-REC-TT-201238 | FI | 1 | TRUE | TRUE | FALSE
10821 | MRT-QM04-P0SA-135773 | 2020-08-03 | MRT-HK-REC-TT-201238 | FI | 1 | TRUE | TRUE | FALSE
10825 | MRT-YR05-P0CRA-160107 | 2020-08-03 | MRT-HK-REC-TT-201237 | FA | 0 | TRUE | TRUE | FALSE
10822 | MRT-YE16-P0UXA-150139 | 2020-08-04 | MRT-HK-REC-TT-201239 | FI | 0 | TRUE | TRUE | FALSE
10823 | MRT-YB03-P3GC-135173 | 2020-08-04 | MRT-HK-REC-TT-201240 | FC | 1 | TRUE | TRUE | FALSE
10824 | MRT-YB03-P0GN-135269 | 2020-08-04 | MRT-HK-REC-TT-201240 | FC | 1 | TRUE | TRUE | FALSE
10826 | MRT-YL19-P0SA-135763 | 2020-08-08 | MRT-HK-REC-TT-201242 | FI | 0 | TRUE | TRUE | FALSE
10827 | MRT-YL19-P0SA-135764 | 2020-08-08 | MRT-HK-REC-TT-201242 | FI | 0 | TRUE | TRUE | FALSE
10828 | MRT-YE07-P2UMA-150156 | 2020-08-12 | MRT-HK-REC-TT-201246 | FA | 1 | TRUE | TRUE | FALSE
10829 | MRT-YE07-P3UMA-150157 | 2020-08-12 | MRT-HK-REC-TT-201246 | FA | 1 | TRUE | TRUE | FALSE
10830 | MRT-CA06-P0UPB-187350 | 2020-08-12 | MRT-HK-REC-TT-201245 | FA | 0 | TRUE | TRUE | FALSE
10831 | MRT-CA02-P0UGX-186995 | 2020-08-12 | MRT-HK-REC-TT-201245 | FA | 0 | TRUE | TRUE | FALSE
10832 | MRT-YT01-P0QHY-125519 | 2020-08-13 | MRT-HK-REC-TT-201247 | FA | 0 | TRUE | TRUE | FALSE
10833 | MRT-YT01-P0QHY-125516 | 2020-08-13 | MRT-HK-REC-TT-201247 | FA | 0 | TRUE | TRUE | FALSE
10834 | MRT-YL19-P0SA-135764 | 2020-08-18 | MRT-HK-REC-TT-201248 | FI | 0 | FALSE | TRUE | FALSE
10835 | MRT-HM02-P0SAH-135549 | 2020-08-18 | MRT-HK-REC-TT-201249 | FI | 0 | FALSE | TRUE | FALSE
10836 | MRT-DM01-P0SA-135736 | 2020-08-18 | MRT-HK-REC-TT-201250 | FA | 1 | TRUE | TRUE | FALSE
10837 | MRT-DN02-P0ZEN-860026 | 2020-08-21 | MRT-DS-REC-TT-200064 | FI | 1 | TRUE | TRUE | FALSE
10838 | MRT-XV00-P0ZEN-020003 | 2020-08-24 | MRT-DS-REC-TT-200067-FC | FC | 2 | TRUE | TRUE | FALSE
10855 | MRT-BF06-P0CRA-160109 | 2020-08-24 | MRT-HK-REC-TT-201254 | FI | 1 | TRUE | TRUE | FALSE
10839 | MRT-YL00-P3CJJ-240053 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10840 | MRT-YS01-P3CJJ-240051 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10841 | MRT-CQ02-P3MAX-220143 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10842 | MRT-YF02-P3MAA-240156 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10843 | MRT-YV02-P3CJJ-240105 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10844 | MRT-YK00-P3CJJ-240049 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10845 | MRT-YL01-P3MAD-240179 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10846 | MRT-CQ02-P3MAV-220095 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10847 | MRT-YD05-P3MAA-240157 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10848 | MRT-YK00-P3CJJ-240065 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10849 | MRT-CQ02-P3CJJ-240108 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10850 | MRT-CQ02-P3MAW-220168 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10851 | MRT-CQ02-P3MAM-220141 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10852 | MRT-CQ02-P3MAA-220162 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10853 | MRT-CQ02-P3MAA-220203 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10854 | MRT-CQ02-P3MAA-240159 | 2020-08-25 | MRT-DS-REC-TT-200066-FC | FI | 0 | TRUE | FALSE | FALSE
10857 | MRT-DD00-P0SMU-125036 | 2020-08-25 | MRT-HK-REC-TT-201251 | FA | 2 | TRUE | TRUE | FALSE
10858 | MRT-DM02-P3LBC-220086 | 2020-08-26 | MRT-DS-REC-TT-200068-FC | FI | 0 | TRUE | TRUE | FALSE
10859 | MRT-CY05-P3CJJ-240109 | 2020-08-26 | MRT-DS-REC-TT-200068-FC | FI | 0 | TRUE | TRUE | FALSE
10860 | MRT-CQ02-P3MAA-220165 | 2020-08-26 | MRT-DS-REC-TT-200068-FC | FI | 0 | TRUE | TRUE | FALSE
10861 | MRT-CQ02-P2MAA-220201 | 2020-08-26 | MRT-DS-REC-TT-200068 | FC | 2 | TRUE | TRUE | FALSE
10862 | MRT-YT01-P3MKA-240003 | 2020-08-31 | MRT-DS-REC-TT-200069-FC | FC | 7 | TRUE | TRUE | FALSE
10863 | MRT-YM01-P2LCB-127039 | 2020-08-31 | MRT-DS-REC-TT-200070-FC | FC | 3 | TRUE | TRUE | FALSE
10864 | MRT-YM01-P3LCB-127039 | 2020-08-31 | MRT-DS-REC-TT-200070-FC | FC | 3 | TRUE | TRUE | FALSE
10865 | MRT-YF00-P3CJJ-240064 | 2020-09-01 | MRT-DS-REC-TT-200071-FC | FI | 1 | TRUE | TRUE | FALSE
10866 | MRT-XG02-P0GEN-135302 | 2020-09-01 | MRT-HK-REC-TT-201264 | FA | 6 | TRUE | TRUE | FALSE
10867 | MRT-BF06-P0CRA-160110 | 2020-09-01 | MRT-HK-REC-TT-201262 | FI | 0 | FALSE | TRUE | FALSE
10868 | MRT-YK08-P3AY-160018 | 2020-09-01 | MRT-HK-REC-TT-201263 | FI | 0 | TRUE | TRUE | FALSE
10869 | MRT-YF02-P3CRA-160118 | 2020-09-01 | MRT-HK-REC-TT-201265 | FI | 1 | FALSE | TRUE | FALSE
10886 | MRT-QM03-P0ZEN-155014 | 2020-09-02 | MRT-HK-REC-TT-201267 | FA | 1 | TRUE | TRUE | FALSE
10887 | MRT-QM03-P0ZEN-155015 | 2020-09-02 | MRT-HK-REC-TT-201267 | FA | 1 | TRUE | TRUE | FALSE
10948 | MRT-QM03-P0BAT-155045 | 2020-09-03 | MRT-HK-REC-TT-201268 | FA | 0 | TRUE | FALSE | FALSE
10949 | MRT-QM03-P0BAT-155053 | 2020-09-03 | MRT-HK-REC-TT-201268 | FA | 0 | TRUE | FALSE | FALSE
10950 | MRT-QM03-P0BAT-155052 | 2020-09-03 | MRT-HK-REC-TT-201268 | FA | 0 | TRUE | FALSE | FALSE
10951 | MRT-QM03-P0ZEN-155019 | 2020-09-03 | MRT-HK-REC-TT-201268 | FA | 1 | TRUE | FALSE | FALSE
10870 | MRT-GT00-P3ZEN-167001 | 2020-09-04 | MRT-DS-REC-TT-200072 | FA | 0 | TRUE | FALSE | FALSE
10888 | MRT-QM03-P0ZEN-185013 | 2020-09-04 | MRT-HK-REC-TT-201275 | FA | 1 | TRUE | TRUE | FALSE
10889 | MRT-QM03-P0ZEN-185015 | 2020-09-04 | MRT-HK-REC-TT-201275 | FA | 1 | TRUE | TRUE | FALSE
10890 | MRT-QM03-P0ZEN-185016 | 2020-09-04 | MRT-HK-REC-TT-201275 | FA | 1 | TRUE | TRUE | FALSE
10891 | MRT-QM03-P0ZEN-185017 | 2020-09-04 | MRT-HK-REC-TT-201275 | FA | 1 | TRUE | TRUE | FALSE
10892 | MRT-QM03-P0ZEN-185018 | 2020-09-04 | MRT-HK-REC-TT-201275 | FA | 1 | TRUE | TRUE | FALSE
10893 | MRT-QM03-P0ZEN-185019 | 2020-09-04 | MRT-HK-REC-TT-201275 | FA | 1 | TRUE | TRUE | FALSE
10871 | MRT-UE00-P2ZEN-100004 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 7 | TRUE | TRUE | FALSE
10872 | MRT-UE00-P2ZEN-100005 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 7 | TRUE | TRUE | FALSE
10873 | MRT-UE00-P2ZEN-100006 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 7 | TRUE | TRUE | FALSE
10874 | MRT-UE00-P2ZEN-100007 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 7 | TRUE | TRUE | FALSE
10875 | MRT-UE00-P2ZEN-100008 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 6 | TRUE | TRUE | FALSE
10876 | MRT-UE00-P2ZEN-100009 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 6 | TRUE | TRUE | FALSE
10877 | MRT-UE00-P3ZEN-100010 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 7 | TRUE | TRUE | FALSE
10878 | MRT-UE00-P3ZEN-100011 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 7 | TRUE | TRUE | FALSE
10879 | MRT-UE00-P3ZEN-100012 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 7 | TRUE | TRUE | FALSE
10880 | MRT-UE00-P3ZEN-100013 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 7 | TRUE | TRUE | FALSE
10881 | MRT-UE00-P3ZEN-100014 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 6 | TRUE | TRUE | FALSE
10882 | MRT-UE00-P3ZEN-100015 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 6 | TRUE | TRUE | FALSE
10883 | MRT-UE00-P2ZEN-100016 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 5 | TRUE | TRUE | FALSE
10884 | MRT-UE00-P3ZEN-100017 | 2020-09-07 | MRT-DS-REC-TT-200073 | FC | 5 | TRUE | TRUE | FALSE
10885 | MRT-QM04-P0SA-135773 | 2020-09-10 | MRT-HK-REC-TT-201278 | FI | 2 | TRUE | TRUE | FALSE
10928 | MRT-YD04-P0UZT-150147 | 2020-09-17 | MRT-HK-REC-TT-201281 | FA | 1 | TRUE | TRUE | FALSE
10929 | MRT-CT00-P2PAC-130004 | 2020-09-19 | MRT-HK-REC-TT-201284 | FA | 1 | TRUE | TRUE | FALSE
10930 | MRT-QM03-P2PAC-130003 | 2020-09-19 | MRT-HK-REC-TT-201284 | FA | 1 | TRUE | TRUE | FALSE
10931 | MRT-YF02-P3CRA-160118 | 2020-09-21 | MRT-HK-REC-TT-201285 | FA | 2 | TRUE | TRUE | FALSE
10932 | MRT-YF02-P2CRA-160117 | 2020-09-21 | MRT-HK-REC-TT-201285 | FA | 1 | TRUE | TRUE | FALSE
10933 | MRT-UC07-P0ZEN-100001 | 2020-09-25 | MRT-DS-REC-TT-200074 | FC | 6 | TRUE | TRUE | FALSE
10934 | MRT-UC08-P0ZEN-100002 | 2020-09-25 | MRT-DS-REC-TT-200074 | FC | 5 | TRUE | TRUE | FALSE
10935 | MRT-UC08-P0ZEN-100003 | 2020-09-25 | MRT-DS-REC-TT-200074 | FC | 5 | TRUE | TRUE | FALSE
10936 | MRT-YT01-P0SMU-125022 | 2020-10-01 | MRT-HK-REC-TT-201288 | FA | 1 | FALSE | TRUE | FALSE
10937 | MRT-DM01-P0SGA-135474 | 2020-10-01 | MRT-HK-REC-TT-201289 | FI | 3 | TRUE | TRUE | FALSE
10943 | MRT-QM04-P0SA-135773 | 2020-10-02 | MRT-HK-REC-TT-201290 | FI | 3 | TRUE | TRUE | FALSE
10944 | MRT-YK09-P0GHE-145010 | 2020-10-03 | MRT-HK-REC-TT-201294 | FA | 2 | TRUE | TRUE | FALSE
10945 | MRT-QM01-P0GEN-135893 | 2020-10-03 | MRT-HK-REC-TT-201295 | FI | 1 | TRUE | TRUE | FALSE
10946 | MRT-CV05-P0GEN-135318 | 2020-10-03 | MRT-HK-REC-TT-201296 | FI | 1 | TRUE | TRUE | FALSE
10952 | MRT-QM03-P0BAT-155053 | 2020-10-03 | MRT-HK-REC-TT-201297 | FA | 1 | TRUE | TRUE | FALSE
10953 | MRT-QM03-P0ZEN-155019 | 2020-10-03 | MRT-HK-REC-TT-201297 | FA | 2 | TRUE | TRUE | FALSE
10954 | MRT-CH04-P0BAU-150622 | 2020-10-03 | MRT-HK-REC-TT-201297 | FA | 1 | TRUE | TRUE | FALSE
10955 | MRT-QM03-P0ZEN-155025 | 2020-10-03 | MRT-HK-REC-TT-201297 | FA | 1 | TRUE | TRUE | FALSE
10956 | MRT-QM03-P0ZEN-185015 | 2020-10-08 | MRT-HK-REC-TT-201299 | FA | 2 | TRUE | FALSE | FALSE
10957 | MRT-QM03-P0ZEN-185017 | 2020-10-08 | MRT-HK-REC-TT-201299 | FA | 2 | TRUE | FALSE | FALSE
10958 | MRT-QM03-P0ZEN-185019 | 2020-10-08 | MRT-HK-REC-TT-201299 | FA | 2 | TRUE | FALSE | FALSE
10938 | MRT-XG02-P2PA-110008 | 2020-10-12 | MRT-DS-REC-TT-200065 | FC | 6 | TRUE | TRUE | FALSE
10939 | MRT-XG02-P2PG-110009 | 2020-10-12 | MRT-DS-REC-TT-200065 | FC | 6 | TRUE | TRUE | FALSE
10940 | MRT-XG02-P0QJA-110010 | 2020-10-12 | MRT-DS-REC-TT-200065 | FC | 5 | TRUE | TRUE | FALSE
10941 | MRT-XG02-P3PA-110008 | 2020-10-12 | MRT-DS-REC-TT-200065 | FC | 6 | TRUE | TRUE | FALSE
10942 | MRT-XG02-P3PG-110009 | 2020-10-12 | MRT-DS-REC-TT-200065 | FC | 6 | TRUE | TRUE | FALSE
10962 | MRT-YD02-P3ZEN-165020 | 2020-10-12 | MRT-HK-REC-TT-201301 | FI | 1 | TRUE | TRUE | FALSE
10947 | MRT-XK00-P2LCM-142000 | 2020-10-13 | MRT-DS-REC-TT-200077-FC | FC | 3 | TRUE | FALSE | FALSE
10963 | MRT-YR01-P0LB-830505 | 2020-10-13 | MRT-HK-REC-TT-201302 | FA | 0 | TRUE | FALSE | FALSE
10964 | MRT-DN02-P0ZEN-860026 | 2020-10-14 | MRT-DS-REC-TT-200075 | FA | 2 | TRUE | TRUE | FALSE
10965 | MRT-GT00-P3ZEN-167001 | 2020-10-14 | MRT-DS-REC-TT-200078 | FC | 1 | TRUE | FALSE | FALSE
10966 | MRT-XV00-P2MAV-220037 | 2020-10-16 | MRT-DS-REC-TT-200079 | FC | 4 | TRUE | FALSE | FALSE
10959 | MRT-YR05-P2ZEN-163110 | 2020-10-19 | MRT-DS-REC-TT-200076 | FC | 3 | TRUE | TRUE | FALSE
10961 | MRT-YR05-P2ZEN-163113 | 2020-10-19 | MRT-DS-REC-TT-200076 | FC | 3 | TRUE | TRUE | FALSE
10968 | MRT-YR01-P0LB-830501 | 2020-10-19 | MRT-HK-REC-TT-201312 | FA | 3 | TRUE | TRUE | FALSE
10969 | MRT-YE16-P2UMA-150329 | 2020-10-21 | MRT-HK-REC-TT-201313 | FC | 2 | TRUE | FALSE | FALSE
10970 | MRT-HM03-P0SAF-135796 | 2020-10-23 | MRT-HK-REC-TT-201316 | FA | 1 | TRUE | FALSE | FALSE
10971 | MRT-VN03-P2LB-122015 | 2020-10-28 | MRT-DS-REC-TT-200080-FC | FC | 8 | TRUE | TRUE | FALSE
10972 | MRT-VN03-P3LB-122015 | 2020-10-28 | MRT-DS-REC-TT-200080-FC | FC | 8 | TRUE | TRUE | FALSE
10973 | MRT-YK00-P3CJJ-240111 | 2020-11-03 | MRT-DS-REC-TT-200081-FC | FC | 1 | TRUE | FALSE | FALSE
10974 | MRT-DA01-P0ZEN-020001 | 2020-11-04 | MRT-DS-REC-TT-200082-FC | FC | 2 | TRUE | FALSE | FALSE
10975 | MRT-YT01-P0SMU-125022 | 2020-11-05 | MRT-HK-REC-TT-201321 | FA | 2 | TRUE | TRUE | FALSE
10976 | MRT-CV05-P0GEN-135318 | 2020-11-10 | MRT-HK-REC-TT-201323 | FI | 2 | TRUE | TRUE | FALSE
10977 | MRT-XS00-P0GEN-135300 | 2020-11-13 | MRT-HK-REC-TT-201326 | FA | 5 | TRUE | TRUE | FALSE
11067 | MRT-HM05-P0SAH-135531 | 2020-11-13 | MRT-HK-REC-TT-201328 | FI | 0 | TRUE | TRUE | FALSE
11068 | MRT-HM05-P0SAC-135530 | 2020-11-13 | MRT-HK-REC-TT-201328 | FI | 0 | TRUE | TRUE | FALSE
10978 | MRT-XJ00-P2PGB-145000 | 2020-11-19 | MRT-DS-REC-TT-200083-FC | FC | 1B | TRUE | FALSE | FALSE
10979 | MRT-XJ00-P3PGB-146000 | 2020-11-19 | MRT-DS-REC-TT-200083-FC | FC | 1A | TRUE | FALSE | FALSE
10980 | MRT-XJ00-P3PGB-147000 | 2020-11-19 | MRT-DS-REC-TT-200083-FC | FC | 1A | TRUE | FALSE | FALSE
11069 | MRT-XK00-P0GDQ-135038 | 2020-11-19 | MRT-HK-REC-TT-201331 | FI | 1 | TRUE | TRUE | FALSE
11070 | MRT-XG02-P0GDK-135019 | 2020-11-19 | MRT-HK-REC-TT-201332 | FA | 1 | TRUE | TRUE | FALSE
11071 | MRT-XA00-P0GAA-135004 | 2020-11-19 | MRT-HK-REC-TT-201333 | FA | 5 | TRUE | TRUE | FALSE
11072 | MRT-QM03-P0ZEN-185022 | 2020-11-27 | MRT-HK-REC-TT-201335 | FA | 0 | TRUE | TRUE | FALSE
11073 | MRT-QM03-P0ZEN-185021 | 2020-11-27 | MRT-HK-REC-TT-201335 | FA | 0 | TRUE | TRUE | FALSE
11074 | MRT-QM03-P0ZEN-185020 | 2020-11-27 | MRT-HK-REC-TT-201335 | FA | 0 | TRUE | TRUE | FALSE
10981 | MRT-DN02-P2ZEN-830020 | 2020-11-30 | MRT-DS-REC-TT-200085 | FA | 1 | TRUE | TRUE | FALSE
10982 | MRT-DN02-P2ZEN-830024 | 2020-11-30 | MRT-DS-REC-TT-200085 | FA | 1 | TRUE | TRUE | FALSE
11075 | MRT-YT01-P0QHY-125516 | 2020-12-01 | MRT-HK-REC-TT-201340 | FA | 1 | TRUE | TRUE | FALSE
11076 | MRT-YT01-P0QHY-125519 | 2020-12-01 | MRT-HK-REC-TT-201340 | FA | 1 | TRUE | TRUE | FALSE
10983 | MRT-CQ02-P3MAV-220098 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FI | 0 | TRUE | FALSE | FALSE
10984 | MRT-UF00-P2MAA-220023 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FC | 1 | TRUE | FALSE | FALSE
10985 | MRT-YD00-P2MAA-220031 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FC | 2 | TRUE | FALSE | FALSE
10986 | MRT-CQ02-P3MAA-220201 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FC | 1 | TRUE | FALSE | FALSE
10987 | MRT-YL01-P3CJJ-240070 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FC | 1 | TRUE | FALSE | FALSE
10988 | MRT-YL08-P2CJJ-240068 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FC | 1 | TRUE | FALSE | FALSE
10989 | MRT-YL08-P3CJJ-240068 | 2020-12-03 | MRT-DS-REC-TT-200084-FC | FC | 1 | TRUE | FALSE | FALSE
10990 | MRT-DN02-P0ZEN-860027 | 2020-12-03 | MRT-DS-REC-TT-200086 | FA | 1 | TRUE | TRUE | FALSE
11077 | MRT-XR00-P0QHY-125414 | 2020-12-03 | MRT-HK-REC-TT-201343 | FI | 1 | TRUE | TRUE | FALSE
11078 | MRT-FF00-P0SGA-135654 | 2020-12-03 | MRT-HK-REC-TT-201344 | FI | 3 | TRUE | TRUE | FALSE
10991 | MRT-CQ02-P2MAA-220201 | 2020-12-07 | MRT-DS-REC-TT-200087 | FC | 3 | TRUE | FALSE | FALSE
10992 | MRT-XJ00-P2LCM-145000 | 2020-12-07 | MRT-DS-REC-TT-200088 | FC | 1B | TRUE | FALSE | FALSE
10993 | MRT-XJ00-P2LCA-145000 | 2020-12-07 | MRT-DS-REC-TT-200088 | FC | 2B | TRUE | FALSE | FALSE
10994 | MRT-XJ00-P0MKG-141000 | 2020-12-07 | MRT-DS-REC-TT-200088 | FC | 1B | TRUE | FALSE | FALSE
10995 | MRT-XJ00-P2MAA-145000 | 2020-12-07 | MRT-DS-REC-TT-200088 | FC | 1B | TRUE | FALSE | FALSE
11079 | MRT-QM03-P0ZEN-185022 | 2020-12-07 | MRT-HK-REC-TT-201346 | FA | 1 | TRUE | TRUE | FALSE
10996 | MRT-DN02-P2ZEN-830020 | 2020-12-11 | MRT-DS-REC-TT-200089 | FA | 2 | TRUE | TRUE | FALSE
11080 | MRT-YL15-P0SMU-125028 | 2020-12-12 | MRT-HK-REC-TT-201349 | FI | 1 | TRUE | TRUE | FALSE
11081 | MRT-HM03-P0SAF-135796 | 2020-12-12 | MRT-HK-REC-TT-201348 | FI | 2 | TRUE | TRUE | FALSE
10997 | MRT-DN02-P0ZEN-860026 | 2021-01-15 | MRT-DS-REC-TT-210001 | FA | 3 | TRUE | TRUE | FALSE
11366 | MRT-YD02-P3ZEN-165020 | 2021-01-20 | MRT-HK-REC-TT-211364 | FA | 2 | TRUE | TRUE | FALSE
10998 | MRT-DN02-P2LBA-830001 | 2021-02-05 | MRT-DS-REC-TT-210002 | FC | 1 | TRUE | TRUE | FALSE
10999 | MRT-DN02-P2LC-830005 | 2021-02-05 | MRT-DS-REC-TT-210002 | FC | 1 | TRUE | TRUE | FALSE
11000 | MRT-DN05-P2QU-130001 | 2021-02-09 | MRT-DS-REC-TT-210003 | FC | 1 | TRUE | TRUE | FALSE
11001 | MRT-DN05-P3QU-130001 | 2021-02-09 | MRT-DS-REC-TT-210003 | FC | 1 | TRUE | TRUE | FALSE
11002 | MRT-DN02-P2LA-830006 | 2021-02-15 | MRT-DS-REC-TT-210004 | FC | 1 | TRUE | TRUE | FALSE
11003 | MRT-DN02-P2MAJ-830011 | 2021-02-15 | MRT-DS-REC-TT-210004 | FC | 1 | TRUE | TRUE | FALSE
11004 | MRT-DN02-P2MAJ-830014 | 2021-02-15 | MRT-DS-REC-TT-210004 | FC | 1 | TRUE | TRUE | FALSE
11005 | MRT-XK00-P2PAB-142000 | 2021-02-17 | MRT-DS-REC-TT-210006 | FC | 4 | TRUE | FALSE | FALSE
11006 | MRT-DN02-P2PG-830004 | 2021-02-17 | MRT-DS-REC-TT-210005 | FC | 1 | TRUE | TRUE | FALSE
11007 | MRT-DN02-P2SCA-830007 | 2021-02-17 | MRT-DS-REC-TT-210005 | FC | 1 | TRUE | TRUE | FALSE
11008 | MRT-DN02-P2QC-830008 | 2021-02-17 | MRT-DS-REC-TT-210005 | FC | 1 | TRUE | TRUE | FALSE
11009 | MRT-DN02-P2QU-830009 | 2021-02-17 | MRT-DS-REC-TT-210005 | FC | 1 | TRUE | TRUE | FALSE
11010 | MRT-DN02-P2H-830012 | 2021-02-17 | MRT-DS-REC-TT-210005 | FC | 1 | TRUE | TRUE | FALSE
11048 | MRT-YR01-P2ZEN-110103 | 2021-02-18 | MRT-DS-REC-TT-210007 | FC | 1 | TRUE | TRUE | FALSE
11049 | MRT-YR01-P3ZEN-110103 | 2021-02-18 | MRT-DS-REC-TT-210007 | FC | 1 | TRUE | TRUE | FALSE
11011 | MRT-DN02-P2LBG-830002 | 2021-02-19 | MRT-DS-REC-TT-210008 | FC | 1 | TRUE | TRUE | FALSE
11012 | MRT-DN02-P2PAH-830015 | 2021-02-19 | MRT-DS-REC-TT-210008 | FC | 1 | TRUE | TRUE | FALSE
11013 | MRT-DN02-P2H-830016 | 2021-02-19 | MRT-DS-REC-TT-210008 | FC | 2 | TRUE | TRUE | FALSE
11014 | MRT-DN02-P0GHD-830028 | 2021-02-25 | MRT-DS-REC-TT-210009 | FA | 0 | TRUE | FALSE | FALSE
11015 | MRT-DN02-P0GHC-830010 | 2021-02-25 | MRT-DS-REC-TT-210009 | FA | 0 | TRUE | FALSE | FALSE
11016 | MRT-DN02-P0ZEN-860026 | 2021-02-25 | MRT-DS-REC-TT-210009 | FA | 4 | TRUE | TRUE | FALSE
11017 | MRT-DN02-P2PC-830003 | 2021-03-02 | MRT-DS-REC-TT-210011 | FC | 1 | TRUE | TRUE | FALSE
11018 | MRT-YK08-P2PAH-604104 | 2021-03-08 | MRT-DS-REC-TT-210012 | FC | 3 | TRUE | TRUE | FALSE
11019 | MRT-YK08-P3PAH-604504 | 2021-03-08 | MRT-DS-REC-TT-210012 | FC | 3 | TRUE | TRUE | FALSE
11020 | MRT-CN00-P3MKW-210001 | 2021-03-15 | MRT-DS-REC-TT-210014 | FC | 1 | TRUE | TRUE | FALSE
11021 | MRT-CN00-P3MKG-210001 | 2021-03-15 | MRT-DS-REC-TT-210014 | FC | 1 | TRUE | TRUE | FALSE
11022 | MRT-DN02-P2ZEN-830020 | 2021-03-16 | MRT-DS-REC-TT-210015 | FC | 4 | TRUE | TRUE | FALSE
11023 | MRT-DN02-P2ZEN-830022 | 2021-03-16 | MRT-DS-REC-TT-210015 | FC | 2 | TRUE | TRUE | FALSE
11024 | MRT-DN02-P2ZEN-830024 | 2021-03-16 | MRT-DS-REC-TT-210015 | FC | 3 | TRUE | TRUE | FALSE
11025 | MRT-DN02-P0GHC-830010 | 2021-03-16 | MRT-DS-REC-TT-210015 | FC | 1 | TRUE | TRUE | FALSE
11026 | MRT-DN02-P0GHD-830028 | 2021-03-16 | MRT-DS-REC-TT-210015 | FC | 1 | TRUE | TRUE | FALSE
11027 | MRT-DN02-P2H-830026 | 2021-03-18 | MRT-DS-REC-TT-210016 | FA | 0 | TRUE | FALSE | FALSE
11028 | MRT-DN02-P0ZEN-860026 | 2021-03-18 | MRT-DS-REC-TT-210016 | FA | 5 | TRUE | TRUE | FALSE
11029 | MRT-DN02-P0ZEN-860027 | 2021-03-19 | MRT-DS-REC-TT-210017 | FA | 2 | TRUE | TRUE | FALSE
11030 | MRT-XJ00-P0GHC-141000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1D | TRUE | TRUE | FALSE
11031 | MRT-XJ00-P0GHD-141000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1D | TRUE | TRUE | FALSE
11032 | MRT-XJ00-P0GKB-141000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1D | TRUE | TRUE | FALSE
11033 | MRT-XJ00-P0GMA-141000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1D | TRUE | TRUE | FALSE
11034 | MRT-XJ00-P2PAB-142200 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1B | TRUE | TRUE | FALSE
11035 | MRT-XJ00-P2QU-145000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1A | TRUE | TRUE | FALSE
11036 | MRT-XJ00-P3QU-146000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1B | TRUE | TRUE | FALSE
11037 | MRT-XJ00-P3QU-147000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1B | TRUE | TRUE | FALSE
11038 | MRT-XJ00-P2QC-145000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1B | TRUE | TRUE | FALSE
11039 | MRT-XJ00-P3QC-146000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1B | TRUE | TRUE | FALSE
11040 | MRT-XJ00-P3QC-147000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1B | TRUE | TRUE | FALSE
11041 | MRT-XJ00-P2QFB-145000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1C | TRUE | TRUE | FALSE
11042 | MRT-XJ00-P3QFB-146000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1B | TRUE | TRUE | FALSE
11043 | MRT-XJ00-P3QFB-147000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1B | TRUE | TRUE | FALSE
11044 | MRT-XJ00-P2SCB-145000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1C | TRUE | TRUE | FALSE
11045 | MRT-XJ00-P3SCB-146000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1B | TRUE | TRUE | FALSE
11046 | MRT-XJ00-P3SCB-147000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1B | TRUE | TRUE | FALSE
11047 | MRT-XJ00-P0QCH-140000 | 2021-03-23 | MRT-DS-REC-TT-210018 | FC | 1A | TRUE | TRUE | FALSE
11050 | MRT-DN02-P0ZEN-860026 | 2021-03-26 | MRT-DS-REC-TT-210019 | FC | 6 | TRUE | TRUE | FALSE
11051 | MRT-DN02-P0ZEN-860027 | 2021-03-26 | MRT-DS-REC-TT-210019 | FC | 3 | TRUE | TRUE | FALSE
11052 | MRT-DN02-P2H-830026 | 2021-03-26 | MRT-DS-REC-TT-210019 | FA | 1 | TRUE | TRUE | FALSE
11053 | MRT-DN02-P2LBF-830013 | 2021-03-26 | MRT-DS-REC-TT-210020 | FC | 1 | TRUE | FALSE | FALSE
11054 | MRT-DN02-P2ZEN-830019 | 2021-03-26 | MRT-DS-REC-TT-210021 | FC | 2 | TRUE | FALSE | FALSE
11055 | MRT-DN02-P2ZEN-830023 | 2021-03-26 | MRT-DS-REC-TT-210021 | FC | 1 | TRUE | FALSE | FALSE
11373 | MRT-YD00-P2CWA-165002 | 2021-03-30 | MRT-HK-REC-TT-2114135 | FI | 0 | TRUE | FALSE | FALSE
11056 | MRT-DN02-P2ZEN-830018 | 2021-03-31 | MRT-DS-REC-TT-210022 | FA | 1 | TRUE | TRUE | FALSE
11057 | MRT-DN02-P2ZEN-830021 | 2021-03-31 | MRT-DS-REC-TT-210022 | FA | 1 | TRUE | TRUE | FALSE
11058 | MRT-DN02-P2H-830026 | 2021-03-31 | MRT-DS-REC-TT-210022 | FC | 2 | TRUE | TRUE | FALSE
11059 | MRT-DN02-P2ZEN-830018 | 2021-04-08 | MRT-DS-REC-TT-210025 | FC | 2 | TRUE | FALSE | FALSE
11060 | MRT-DN02-P2ZEN-830021 | 2021-04-08 | MRT-DS-REC-TT-210025 | FC | 2 | TRUE | FALSE | FALSE
11061 | MRT-YR01-P2ZEN-110103 | 2021-04-08 | MRT-DS-REC-TT-210026 | FC | 1 | TRUE | TRUE | FALSE
11062 | MRT-YR01-P3ZEN-110103 | 2021-04-08 | MRT-DS-REC-TT-210026 | FC | 1 | TRUE | TRUE | FALSE
11340 | MRT-YQ08-P0UGA-150223 | 2021-04-09 | MRT-HK-REC-TT-211452 | FA | 0 | TRUE | FALSE | FALSE
11341 | MRT-YQ08-P0BJQ-150228 | 2021-04-09 | MRT-HK-REC-TT-211452 | FA | 0 | TRUE | FALSE | FALSE
11342 | MRT-YQ08-P0UTH-150230 | 2021-04-09 | MRT-HK-REC-TT-211452 | FA | 0 | TRUE | FALSE | FALSE
11063 | MRT-XJ00-P3PAB-140001 | 2021-04-20 | MRT-DS-REC-TT-210029 | FC | 4A | TRUE | FALSE | FALSE
11064 | MRT-BT00-P0CRN-164001 | 2021-04-26 | MRT-DS-REC-TT-210031 | FA | 0 | TRUE | FALSE | FALSE
11065 | MRT-YR01-P2ZEN-110103 | 2021-04-28 | MRT-DS-REC-TT-210030 | FC | 2 | TRUE | TRUE | FALSE
11066 | MRT-YR01-P3ZEN-110103 | 2021-04-28 | MRT-DS-REC-TT-210030 | FC | 2 | TRUE | TRUE | FALSE
11082 | MRT-YL01-P0GAF-110010 | 2021-04-29 | MRT-HK-REC-TT-211476 | FA | 0 | TRUE | TRUE | FALSE
11083 | MRT-DN02-P2MAV-830017 | 2021-05-12 | MRT-DS-REC-TT-210036 | FA | 2 | TRUE | TRUE | FALSE
11084 | MRT-YV02-P2SCA-127532 | 2021-05-13 | MRT-DS-REC-TT-210037 | FC | 1 | TRUE | TRUE | FALSE
11085 | MRT-YV02-P3SCA-127532 | 2021-05-13 | MRT-DS-REC-TT-210037 | FC | 1 | TRUE | TRUE | FALSE
11086 | MRT-DN02-P0ZEN-860026 | 2021-05-24 | MRT-DS-REC-TT-210035 | FC | 7 | TRUE | TRUE | FALSE
11087 | MRT-GT00-P2ZEN-167001 | 2021-05-24 | MRT-DS-REC-TT-210038 | FC | 1 | TRUE | TRUE | FALSE
11091 | MRT-YR01-P0LB-830501 | 2021-05-24 | MRT-HK-REC-TT-211488 | FA | 6 | TRUE | TRUE | FALSE
11092 | MRT-YR01-P0LB-830502 | 2021-05-24 | MRT-HK-REC-TT-211488 | FA | 3 | TRUE | TRUE | FALSE
11090 | MRT-BT00-P0CRN-164001 | 2021-05-31 | MRT-DS-REC-TT-210039 | FA | 1 | TRUE | TRUE | FALSE
11093 | MRT-XJ00-P2MAV-145000 | 2021-06-02 | MRT-DS-REC-TT-210040 | FC | 1B | TRUE | TRUE | FALSE
11099 | MRT-CC07-P0UPC-175701 | 2021-06-16 | MRT-HK-REC-TT-211507 | FA | 4 | TRUE | TRUE | FALSE
11094 | MRT-CC02-P2UEJ-170907 | 2021-06-17 | MRT-DS-REC-TT-210041 | FC | 4 | TRUE | TRUE | FALSE
11095 | MRT-CC02-P3UEJ-170907 | 2021-06-17 | MRT-DS-REC-TT-210041 | FC | 4 | TRUE | TRUE | FALSE
11096 | MRT-XJ00-P2MAV-145000 | 2021-06-17 | MRT-DS-REC-TT-210042 | FC | 1C | TRUE | FALSE | FALSE
11097 | MRT-XJ00-P3MAV-146000 | 2021-06-17 | MRT-DS-REC-TT-210042 | FC | 1B | TRUE | FALSE | FALSE
11098 | MRT-XJ00-P3MAV-147000 | 2021-06-17 | MRT-DS-REC-TT-210042 | FC | 1B | TRUE | FALSE | FALSE
11100 | MRT-CC02-P0UZT-175920 | 2021-06-17 | MRT-HK-REC-TT-211509 | FA | 4 | TRUE | TRUE | FALSE
11101 | MRT-CC02-P0UZT-175930 | 2021-06-17 | MRT-HK-REC-TT-211509 | FA | 4 | TRUE | TRUE | FALSE
11102 | MRT-CC02-P0UZT-175921 | 2021-06-17 | MRT-HK-REC-TT-211509 | FA | 4 | TRUE | TRUE | FALSE
11103 | MRT-CA00-P0UYX-187158 | 2021-06-17 | MRT-HK-REC-TT-211510 | FA | 3 | TRUE | TRUE | FALSE
11104 | MRT-CA00-P0UYX-187159 | 2021-06-17 | MRT-HK-REC-TT-211510 | FA | 3 | TRUE | TRUE | FALSE
11105 | MRT-CA00-P0UYX-187184 | 2021-06-17 | MRT-HK-REC-TT-211510 | FA | 4 | TRUE | TRUE | FALSE
11106 | MRT-CA02-P0UGA-176305 | 2021-06-19 | MRT-HK-REC-TT-211513 | FA | 1 | TRUE | TRUE | FALSE
11107 | MRT-CA02-P0UGA-176300 | 2021-06-19 | MRT-HK-REC-TT-211513 | FA | 2 | TRUE | TRUE | FALSE
11108 | MRT-CC02-P0ULX-176211 | 2021-06-21 | MRT-HK-REC-TT-211515 | FA | 3 | TRUE | TRUE | FALSE
11109 | MRT-XJ00-P0GHD-141000 | 2021-07-01 | MRT-DS-REC-TT-210044 | FC | 1E | TRUE | TRUE | FALSE
11110 | MRT-XJ00-P0GKB-141000 | 2021-07-01 | MRT-DS-REC-TT-210044 | FC | 1E | TRUE | TRUE | FALSE
11111 | MRT-XJ00-P2SCB-145000 | 2021-07-01 | MRT-DS-REC-TT-210044 | FC | 1D | TRUE | TRUE | FALSE
11112 | MRT-YU02-P0ABA-150026 | 2021-07-02 | MRT-HK-REC-TT-211522 | FA | 3 | TRUE | TRUE | FALSE
11368 | MRT-XA01-P0ABA-150507 | 2021-07-03 | MRT-HK-REC-TT-211523 | FA | 2 | TRUE | TRUE | FALSE
11115 | MRT-YR01-P0LB-830501 | 2021-07-10 | MRT-HK-REC-TT-211526 | FA | 7 | TRUE | TRUE | FALSE
11113 | MRT-YV02-P2MAJ-603202 | 2021-07-12 | MRT-DS-REC-TT-210045 | FC | 3 | TRUE | TRUE | FALSE
11114 | MRT-YV02-P3MAJ-604202 | 2021-07-12 | MRT-DS-REC-TT-210045 | FC | 3 | TRUE | TRUE | FALSE
11116 | MRT-XW03-P0BBY-150021 | 2021-07-13 | MRT-HK-REC-TT-211530 | FI | 0 | TRUE | FALSE | FALSE
11117 | MRT-YR01-P0LB-830501 | 2021-07-13 | MRT-HK-REC-TT-211533 | FA | 8 | TRUE | TRUE | FALSE
11118 | MRT-YV02-P0GAF-110016 | 2021-07-13 | MRT-HK-REC-TT-211534 | FA | 0 | TRUE | FALSE | FALSE
11119 | MRT-BT00-P0CRN-164001 | 2021-07-16 | MRT-DS-REC-TT-210046 | FC | 2 | TRUE | FALSE | FALSE
11120 | MRT-CC02-POUGA-176250 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11121 | MRT-CC02-P0UPC-175705 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11122 | MRT-CC02-P0UAA-176070 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11123 | MRT-CC02-P0UAA-176075 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11124 | MRT-CC03-P0UAA-176085 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11125 | MRT-CC02-P0ULY-176105 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11126 | MRT-CC02-P0UGA-176235 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11127 | MRT-CC02-P0UGA-176255 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11128 | MRT-CC02-P0UGA-176275 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11129 | MRT-CC02-P0UGA-176290 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11130 | MRT-CC02-P0UGA-176295 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11131 | MRT-CA03-P0UXA-186704 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11132 | MRT-CA01-P0UXA-186692 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11133 | MRT-CA01-P0UXA-186712 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11134 | MRT-CA01-P0UXA-186714 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11135 | MRT-CA01-P0UXA-186716 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11136 | MRT-CA01-P0USG-186852 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11137 | MRT-CA01-P0USG-186868 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11138 | MRT-CA01-P0UGX-186952 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11139 | MRT-CA00-P0UGX-186956 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11140 | MRT-CA01-P0UGX-186968 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11141 | MRT-CA01-P0UGX-186976 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11142 | MRT-CA01-P0UGX-186978 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11143 | MRT-CA02-P0UGX-186982 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11144 | MRT-CA02-P0UGX-186984 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11145 | MRT-CA01-P0UMX-187202 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11146 | MRT-CA01-P0UMX-187214 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11147 | MRT-CA02-P0UMX-187220 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11148 | MRT-CC02-P0UPC-175752 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11149 | MRT-CC02-P0UPC-175753 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11150 | MRT-CC02-P0UPC-175755 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11151 | MRT-CC02-P0UPC-175756 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11152 | MRT-CC02-P0UPC-175757 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11153 | MRT-CC02-P0UPC-175758 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11154 | MRT-CC02-P0UPC-175759 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11155 | MRT-CC02-P0UPC-175761 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11156 | MRT-CC02-P0UPC-175762 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11157 | MRT-CC02-P0UPC-175763 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11158 | MRT-CC02-P0UPC-175764 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11159 | MRT-CC02-P0UPC-175765 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11160 | MRT-CC02-P0UPC-175766 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11161 | MRT-CC02-P0UPC-175767 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11162 | MRT-CC02-P0UPC-175768 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11163 | MRT-CC02-P0UPC-175769 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11164 | MRT-CC02-P0UPC-175770 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11165 | MRT-CC02-P0UPC-175771 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11166 | MRT-CC02-P0UPC-175754 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11167 | MRT-CC02-P0UPC-175772 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11168 | MRT-CC02-P0UPC-175773 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11169 | MRT-CC02-P0UPC-175774 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11170 | MRT-CC02-P0UPC-175775 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11171 | MRT-CA00-P0UGX-186957 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11172 | MRT-CC02-P0ULY-176108 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11173 | MRT-CC02-P0UZT-175991 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11174 | MRT-CC07-P0UZT-175990 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11175 | MRT-CC02-P0UZT-175992 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11176 | MRT-CA01-P0UXA-186662 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11177 | MRT-CA01-P0UGX-186973 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11178 | MRT-CA01-P0UGX-186986 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11179 | MRT-CA02-P0UGX-186974 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11180 | MRT-CA02-P0UGX-186983 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11181 | MRT-CA02-P0UGX-186985 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11182 | MRT-CA02-P0UGX-186991 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11183 | MRT-CA02-P0UGX-186992 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11184 | MRT-CA02-P0UGX-186993 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11185 | MRT-CA01-P0USG-186869 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11186 | MRT-CC02-P0UAA-176071 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11187 | MRT-CC02-P0UAA-176072 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11188 | MRT-CC02-P0UAA-176073 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11189 | MRT-CC02-P0UAA-176074 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11190 | MRT-CC02-P0UAA-176076 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11191 | MRT-CC02-P0UAA-176077 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11192 | MRT-CC03-P0UAA-176080 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11193 | MRT-CA01-P0UXA-186713 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11194 | MRT-CA01-P0UXA-186718 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11195 | MRT-CA01-P0UXA-186719 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11196 | MRT-CA06-P0UXA-186706 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11197 | MRT-CA02-P0UGX-186975 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11198 | MRT-CA01-P0UGX-186972 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11199 | MRT-CA01-P0UXA-186683 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11200 | MRT-CA01-P0UXA-186685 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11201 | MRT-CA01-P0UMX-187215 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11202 | MRT-CA01-P0UGX-186971 | 2021-07-22 | MRT-HK-REC-TT-211539 | AB | 0 | TRUE | TRUE | FALSE
11203 | MRT-CC05-P0ZEN-175021 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11204 | MRT-CC05-P0ZEN-175022 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11205 | MRT-CC05-P0ZEN-175023 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11206 | MRT-CC05-P0ZEN-175024 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11207 | MRT-CC05-P0ZEN-175025 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11208 | MRT-CC05-P0ZEN-175026 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11209 | MRT-CC05-P0ZEN-175027 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11210 | MRT-CC05-P0ZEN-175028 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11211 | MRT-CC05-P0ZEN-175029 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11212 | MRT-CC05-P0ZEN-175030 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11213 | MRT-CC05-P0ZEN-175031 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11214 | MRT-CC05-P0ZEN-175032 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11215 | MRT-CC05-P0ZEN-175033 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11216 | MRT-CC05-P0ZEN-175034 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11217 | MRT-CC05-P0ZEN-175035 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11218 | MRT-CC05-P0ZEN-175036 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11219 | MRT-CC05-P0ZEN-175037 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11220 | MRT-CC05-P0ZEN-175041 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11221 | MRT-CC05-P0ZEN-175042 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11222 | MRT-CC05-P0ZEN-175043 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11223 | MRT-CC05-P0ZEN-175044 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11224 | MRT-CC05-P0ZEN-175045 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11225 | MRT-CC05-P0ZEN-175046 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11226 | MRT-CC05-P0ZEN-175047 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11227 | MRT-CC05-P0ZEN-175048 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11228 | MRT-CC05-P0ZEN-175049 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11229 | MRT-CC05-P0ZEN-175051 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11230 | MRT-CC05-P0ZEN-175052 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11231 | MRT-CC05-P0ZEN-175053 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11232 | MRT-CC05-P0ZEN-175054 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11233 | MRT-CC05-P0ZEN-175061 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11234 | MRT-CC05-P0ZEN-175062 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11235 | MRT-CC05-P0ZEN-175063 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11236 | MRT-CC05-P0ZEN-175064 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11237 | MRT-CC05-P0ZEN-175065 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11238 | MRT-CC05-P0ZEN-175066 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11239 | MRT-CC05-P0ZEN-175067 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11240 | MRT-CC05-P0ZEN-175068 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11241 | MRT-CC05-P0ZEN-175069 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11242 | MRT-CC05-P0ZEN-175070 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11243 | MRT-CC05-P0ZEN-175071 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11244 | MRT-CC05-P0ZEN-175072 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11245 | MRT-CC02-P0UQQ-175805 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11246 | MRT-CC02-P0UZT-175905 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11247 | MRT-CC02-P0UBX-176005 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11248 | MRT-CA01-P0UGX-186722 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11249 | MRT-CA01-P0USX-186802 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11250 | MRT-CA00-P0UST-186906 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11251 | MRT-CA00-P0UST-186908 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11252 | MRT-CA00-P0UST-186910 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11253 | MRT-CA00-P0UST-186912 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11254 | MRT-CA00-P0UST-186914 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11255 | MRT-CA00-P0UST-186916 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11256 | MRT-CA01-P0UST-186918 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11257 | MRT-CA02-P0UST-186924 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11258 | MRT-CA03-P0UST-186928 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11259 | MRT-CA03-P0UST-186930 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11260 | MRT-CA03-P0UST-186932 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11261 | MRT-CA03-P0UST-186934 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11262 | MRT-CA03-P0UST-186936 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11263 | MRT-CA03-P0UST-186938 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11264 | MRT-CA03-P0UST-186940 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11265 | MRT-CA01-P0UST-186944 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | TRUE | FALSE
11266 | MRT-CA01-P0UYX-187152 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11267 | MRT-CA01-P0UYX-187312 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11268 | MRT-CA01-P0UAB-187330 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11269 | MRT-CA01-P0UAB-187331 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11270 | MRT-CA01-P0UAB-187332 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11271 | MRT-CA02-P0UAB-187333 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11272 | MRT-CA02-P0UAB-187334 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11273 | MRT-CA01-P0UAB-187335 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11274 | MRT-CA01-P0UAB-187336 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11275 | MRT-CA01-P0UGA-186603 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11276 | MRT-CA00-P0UST-186909 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11277 | MRT-CA00-P0UST-186911 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11278 | MRT-CA00-P0UST-186917 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11279 | MRT-CC02-P0UBX-176006 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11280 | MRT-CC02-P0UBX-176007 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11281 | MRT-CA02-P0UST-186922 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11282 | MRT-CA03-P0UST-186937 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11283 | MRT-CA03-P0UST-186947 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11284 | MRT-CA03-P0UST-186948 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11285 | MRT-CA03-P0UST-186949 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11286 | MRT-CA03-P0UST-186927 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11287 | MRT-CC03-P0UPC-176350 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11288 | MRT-CC03-P0UPC-176351 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11289 | MRT-CC03-P0UPC-176352 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11290 | MRT-CC03-P0UPC-176360 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11291 | MRT-CC03-P0UPC-176361 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11292 | MRT-CC03-P0UPC-176362 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11293 | MRT-CC03-P0UPC-176363 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11294 | MRT-CA03-P0UST-186933 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11295 | MRT-CA03-P0UST-186950 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11296 | MRT-CC03-P0UPC-176370 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11297 | MRT-CC03-P0UPC-176371 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11298 | MRT-CC03-P0UPC-176372 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11299 | MRT-CC03-P0UPC-176373 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11300 | MRT-CC03-P0UPC-176374 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11301 | MRT-CC03-P0UPC-176375 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11302 | MRT-CC03-P0UPC-176376 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11303 | MRT-CC03-P0UPC-176377 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11304 | MRT-CC03-P0UPC-176380 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11305 | MRT-CC03-P0UPC-176381 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11306 | MRT-CC03-P0UPC-176382 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11307 | MRT-CC03-P0UPC-176383 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11308 | MRT-CC03-P0UPC-176384 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11309 | MRT-CC03-P0UPC-176385 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11310 | MRT-CA03-P0UST-186943 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11311 | MRT-CA02-P0UST-186941 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11312 | MRT-CA00-P0UST-186913 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11313 | MRT-CA00-P0UST-186907 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11314 | MRT-CA01-P0UST-186945 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11315 | MRT-CC02-P0UPC-176368 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11316 | MRT-CC02-P0UPC-176369 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11317 | MRT-CC03-P0UPC-176364 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11318 | MRT-CC03-P0UPC-176365 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11319 | MRT-CC03-P0UPC-176378 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11320 | MRT-CC03-P0UPC-176379 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11321 | MRT-CC03-P0UPC-176394 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11322 | MRT-CC03-P0UPC-176396 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11323 | MRT-CC03-P0UPC-176398 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11324 | MRT-CC03-P0UPC-176399 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11325 | MRT-CC03-P0UPC-176400 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11326 | MRT-CC03-P0UPC-176401 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11327 | MRT-CC03-P0UPC-176388 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11328 | MRT-CC03-P0UPC-176390 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11329 | MRT-CC03-P0UPC-176392 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11330 | MRT-CC03-P0UPC-176355 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11331 | MRT-CC03-P0UPC-176356 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11332 | MRT-CC03-P0UPC-176357 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11333 | MRT-CC03-P0UPC-176358 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11334 | MRT-CA01-P0UAB-187327 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11335 | MRT-CA02-P0UAB-187328 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11336 | MRT-CC03-P0UPC-176386 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11337 | MRT-CC03-P0UPC-176387 | 2021-07-22 | MRT-HK-REC-TT-211540 | AB | 0 | TRUE | FALSE | FALSE
11442 | MRT-YL16-P0BMY-150082 | 2021-08-02 | MRT-HK-REC-TT-211547 | FI | 1 | TRUE | TRUE | FALSE
11443 | MRT-YL16-P3MKY-150087 | 2021-08-02 | MRT-HK-REC-TT-211547 | FI | 1 | TRUE | TRUE | FALSE
11444 | MRT-YL16-P3MKA-150097 | 2021-08-02 | MRT-HK-REC-TT-211547 | FI | 1 | TRUE | TRUE | FALSE
11447 | MRT-YL35-P3PAC-130001 | 2021-08-02 | MRT-HK-REC-TT-211549 | FI | 2 | TRUE | TRUE | FALSE
11338 | MRT-DN02-P2LBA-830001 | 2021-08-09 | MRT-DS-REC-TT-210047 | FC | 2 | TRUE | TRUE | FALSE
11339 | MRT-DN02-P0ZEN-860026 | 2021-08-09 | MRT-DS-REC-TT-210047 | FC | 8 | TRUE | TRUE | FALSE
11372 | MRT-XW03-P0BFY-150022 | 2021-08-18 | MRT-HK-REC-TT-211556 | FA | 0 | TRUE | FALSE | FALSE
11343 | MRT-XN00-P2MAA-220038 | 2021-08-24 | MRT-DS-REC-TT-210048 | FC | 1 | TRUE | FALSE | FALSE
11344 | MRT-DM02-P2MAA-220131 | 2021-08-24 | MRT-DS-REC-TT-210048 | FC | 1 | TRUE | FALSE | FALSE
11345 | MRT-XA00-P0GAA-135004 | 2021-08-30 | MRT-HK-REC-TT-211568 | FA | 5 | TRUE | TRUE | FALSE
11346 | MRT-YL16-P2BBA-150061 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 1 | TRUE | TRUE | FALSE
11347 | MRT-YL16-P2BFA-150063 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 1 | TRUE | TRUE | FALSE
11348 | MRT-YL16-P0BMA-150067 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 1 | TRUE | TRUE | FALSE
11349 | MRT-YL16-P2BJA-150069 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 1 | TRUE | TRUE | FALSE
11350 | MRT-YL16-P2MKA-150095 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 1 | TRUE | TRUE | FALSE
11351 | MRT-YL16-P0BJJ-150098 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 1 | TRUE | TRUE | FALSE
11352 | MRT-YL16-P3BJL-150099 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 1 | TRUE | TRUE | FALSE
11353 | MRT-YL16-P3BJN-150100 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 1 | TRUE | TRUE | FALSE
11354 | MRT-YL16-P0BJL-150101 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 1 | TRUE | TRUE | FALSE
11355 | MRT-YL16-P0BJN-150102 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 1 | TRUE | TRUE | FALSE
11356 | MRT-YL16-P0SRA-150103 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 1 | TRUE | TRUE | FALSE
11357 | MRT-YL16-P0BJQ-150104 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 0 | TRUE | TRUE | FALSE
11358 | MRT-YL16-P2BLF-150237 | 2021-08-30 | MRT-HK-REC-TT-211566 | FI | 1 | TRUE | TRUE | FALSE
11362 | MRT-CA06-P0UQA-186506 | 2021-08-30 | MRT-HK-REC-TT-211570 | FA | 2 | TRUE | FALSE | FALSE
11363 | MRT-CA03-P0UQA-186575 | 2021-08-30 | MRT-HK-REC-TT-211570 | FA | 1 | TRUE | FALSE | FALSE
11359 | MRT-YL01-P2ZEN-161051 | 2021-09-03 | MRT-DS-REC-TT-210049 | FC | 4 | TRUE | FALSE | FALSE
11360 | MRT-CN00-P3MKW-210001 | 2021-09-03 | MRT-DS-REC-TT-210050 | FC | 2 | TRUE | TRUE | FALSE
11361 | MRT-CN00-P3MKG-210001 | 2021-09-03 | MRT-DS-REC-TT-210050 | FC | 2 | TRUE | TRUE | FALSE
11364 | MRT-DN02-P2MAV-830017 | 2021-09-13 | MRT-DS-REC-TT-210051 | FA | 3 | TRUE | TRUE | FALSE
11365 | MRT-DN02-P0ZEN-860026 | 2021-09-13 | MRT-DS-REC-TT-210051 | FC | 9 | TRUE | TRUE | FALSE
11441 | MRT-YL16-P3BJC-150071 | 2021-09-13 | MRT-HK-REC-TT-211572 | FI | 1 | TRUE | FALSE | FALSE
11369 | MRT-XA01-P0ABA-150507 | 2021-09-30 | MRT-HK-REC-TT-211586 | FA | 3 | TRUE | TRUE | FALSE
11367 | MRT-YD00-P2MKA-220005 | 2021-10-05 | MRT-DS-REC-TT-210052 | FC | 2 | TRUE | TRUE | FALSE
11370 | MRT-YD00-P0UAA-150204 | 2021-10-05 | MRT-HK-REC-TT-211588 | FA | 3 | TRUE | TRUE | FALSE
11371 | MRT-YD00-P0QHB-125431 | 2021-10-05 | MRT-HK-REC-TT-211591 | FA | 1 | TRUE | FALSE | FALSE
11374 | MRT-XJ00-P2LB-142000 | 2021-10-12 | MRT-DS-REC-TT-210053 | FC | 1B | TRUE | FALSE | FALSE
11375 | MRT-FF01-P0SGA-135429 | 2021-10-16 | MRT-HK-REC-TT-211600 | FA | 3 | TRUE | FALSE | FALSE
11448 | MRT-YD02-P3ZEN-165020 | 2021-10-16 | MRT-HK-REC-TT-211601 | FA | 3 | TRUE | TRUE | FALSE
11376 | MRT-YL16-P0BCA-150060 | 2021-10-18 | MRT-HK-REC-TT-211602 | FI | 1 | TRUE | FALSE | FALSE
11377 | MRT-YL16-P3BBC-150062 | 2021-10-18 | MRT-HK-REC-TT-211602 | FI | 1 | TRUE | FALSE | FALSE
11378 | MRT-YL16-P3BFC-150064 | 2021-10-18 | MRT-HK-REC-TT-211602 | FI | 1 | TRUE | FALSE | FALSE
11379 | MRT-YL16-P3BFE-150065 | 2021-10-18 | MRT-HK-REC-TT-211602 | FI | 1 | TRUE | FALSE | FALSE
11380 | MRT-YL16-P0BHA-150066 | 2021-10-18 | MRT-HK-REC-TT-211602 | FI | 1 | TRUE | FALSE | FALSE
11381 | MRT-YL16-P0BMC-150068 | 2021-10-18 | MRT-HK-REC-TT-211602 | FI | 1 | TRUE | FALSE | FALSE
11382 | MRT-YL16-P2BRB-150078 | 2021-10-18 | MRT-HK-REC-TT-211602 | FI | 1 | TRUE | FALSE | FALSE
11383 | MRT-YL16-P0BUB-150076 | 2021-10-18 | MRT-HK-REC-TT-211602 | FI | 1 | TRUE | FALSE | FALSE
11384 | MRT-DD00-P0BAT-155154 | 2021-10-21 | MRT-HK-REC-TT-211605 | FI | 1 | TRUE | TRUE | FALSE
11385 | MRT-XJ00-P0GHC-140001 | 2021-10-22 | MRT-DS-REC-TT-210055 | FC | 2 | TRUE | FALSE | FALSE
11386 | MRT-XJ00-P0GHD-140001 | 2021-10-22 | MRT-DS-REC-TT-210055 | FC | 2 | TRUE | FALSE | FALSE
11387 | MRT-DN02-P0ZEN-860026 | 2021-11-02 | MRT-DS-REC-TT-210056 | FC | 10 | TRUE | FALSE | FALSE
11388 | MRT-YE00-P3UMA-150172 | 2021-11-09 | MRT-HK-REC-TT-211619 | FA | 2 | TRUE | FALSE | FALSE
11392 | MRT-YS01-P0ZEN-165004 | 2021-11-12 | MRT-HK-REC-TT-211622 | FA | 0 | TRUE | TRUE | FALSE
11389 | MRT-DS00-P0GN-135279 | 2021-11-13 | MRT-HK-REC-TT-211623 | FA | 1 | TRUE | FALSE | FALSE
11390 | MRT-DS00-P3GC-135183 | 2021-11-13 | MRT-HK-REC-TT-211623 | FA | 1 | TRUE | FALSE | FALSE
11391 | MRT-YF01-P0BFB-150115 | 2021-11-16 | MRT-HK-REC-TT-211627 | FA | A | TRUE | TRUE | FALSE
11393 | MRT-YQ08-P2UMA-150232 | 2021-11-16 | MRT-HK-REC-TT-211628 | FA | 0 | TRUE | FALSE | FALSE
11394 | MRT-XJ00-P2LCA-145000 | 2021-11-17 | MRT-DS-REC-TT-210057 | FC | 2C | TRUE | FALSE | FALSE
11395 | MRT-XJ00-P3LCA-146000 | 2021-11-17 | MRT-DS-REC-TT-210057 | FC | 1B | TRUE | FALSE | FALSE
11396 | MRT-XJ00-P3LCA-147000 | 2021-11-17 | MRT-DS-REC-TT-210057 | FC | 1B | TRUE | FALSE | FALSE
11397 | MRT-XJ00-P0GHC-140001 | 2021-11-22 | MRT-DS-REC-TT-210058 | FC | 3 | TRUE | FALSE | FALSE
11398 | MRT-XJ00-P0GHD-140001 | 2021-11-22 | MRT-DS-REC-TT-210058 | FC | 3 | TRUE | FALSE | FALSE
11399 | MRT-XJ00-P2SCB-145000 | 2021-11-23 | MRT-DS-REC-TT-210059 | FC | 1E | TRUE | FALSE | FALSE
11400 | MRT-YL01-P0PBB-135258 | 2021-12-04 | MRT-HK-REC-TT-211640 | FI | 1 | TRUE | TRUE | FALSE
11401 | MRT-YL01-P0PBB-135287 | 2021-12-04 | MRT-HK-REC-TT-211640 | FI | 1 | TRUE | TRUE | FALSE
11402 | MRT-XW03-P0ASR-150196 | 2021-12-08 | MRT-HK-REC-TT-211643 | FA | 1 | TRUE | FALSE | FALSE
11403 | MRT-HM02-P3SAC-150079 | 2021-12-08 | MRT-HK-REC-TT-211644 | FI | 1 | TRUE | TRUE | FALSE
11404 | MRT-YE16-P2UMA-150136 | 2021-12-08 | MRT-HK-REC-TT-211644 | FI | 2 | TRUE | TRUE | FALSE
11405 | MRT-YL16-P2BLF-150237 | 2021-12-08 | MRT-HK-REC-TT-211644 | FI | 2 | TRUE | TRUE | FALSE
11406 | MRT-DN02-P2MAV-830017 | 2021-12-13 | MRT-DS-REC-TT-210060 | FA | 4 | TRUE | TRUE | FALSE
11407 | MRT-DN02-P0ZEN-860026 | 2021-12-13 | MRT-DS-REC-TT-210060 | FC | 11 | TRUE | TRUE | FALSE
11408 | MRT-DN02-P2MKA-830029 | 2021-12-13 | MRT-DS-REC-TT-210060 | FA | 0 | TRUE | FALSE | FALSE
11409 | MRT-XG02-P0GDK-135019 | 2021-12-14 | MRT-HK-REC-TT-211647 | FA | 2 | TRUE | FALSE | FALSE
11410 | MRT-YD00-P0UAA-150207 | 2021-12-23 | MRT-HK-REC-TT-211651 | FA | 1 | TRUE | TRUE | FALSE
11411 | MRT-YS01-P4BBA-150120 | 2021-12-23 | MRT-HK-REC-TT-211654 | FA | 1 | TRUE | TRUE | FALSE
11412 | MRT-CV05-P0BFA-150897 | 2021-12-23 | MRT-HK-REC-TT-211656 | FI | 0 | TRUE | TRUE | FALSE
11413 | MRT-YL16-P3MKY-150086 | 2021-12-23 | MRT-HK-REC-TT-211659 | FI | 1 | TRUE | FALSE | FALSE
11414 | MRT-YL16-P3MKX-150089 | 2021-12-23 | MRT-HK-REC-TT-211659 | FI | 1 | TRUE | FALSE | FALSE
11415 | MRT-YL16-P4MKX-150090 | 2021-12-23 | MRT-HK-REC-TT-211659 | FI | 1 | TRUE | FALSE | FALSE
11416 | MRT-YL16-P0BFA-150092 | 2021-12-23 | MRT-HK-REC-TT-211659 | FI | 1 | TRUE | FALSE | FALSE
11417 | MRT-YF01-P0BFB-150115 | 2021-12-23 | MRT-HK-REC-TT-211659 | FI | 1 | TRUE | FALSE | FALSE
11418 | MRT-CA00-P0USX-186808 | 2021-12-27 | MRT-HK-REC-TT-211662 | AB | 3 | TRUE | FALSE | FALSE
11419 | MRT-CC02-P0UPC-175781 | 2021-12-27 | MRT-HK-REC-TT-211662 | AB | 3 | TRUE | FALSE | FALSE
11420 | MRT-CA01-P0UGX-186764 | 2021-12-27 | MRT-HK-REC-TT-211662 | AB | 3 | TRUE | FALSE | FALSE
11421 | MRT-CA01-P0UGX-186766 | 2021-12-27 | MRT-HK-REC-TT-211662 | AB | 3 | TRUE | FALSE | FALSE
11422 | MRT-CA01-P0UGX-186763 | 2021-12-27 | MRT-HK-REC-TT-211662 | AB | 3 | TRUE | FALSE | FALSE
11423 | MRT-CA01-P0UGX-186765 | 2021-12-27 | MRT-HK-REC-TT-211662 | AB | 3 | TRUE | FALSE | FALSE
11424 | MRT-CA01-P0UGX-186767 | 2021-12-27 | MRT-HK-REC-TT-211662 | AB | 3 | TRUE | FALSE | FALSE
11425 | MRT-YL16-P3MKA-150096 | 2021-12-28 | MRT-HK-REC-TT-211665 | FI | 1 | TRUE | TRUE | FALSE
11426 | MRT-YL16-P0BFA-150242 | 2021-12-28 | MRT-HK-REC-TT-211665 | FI | 1 | TRUE | TRUE | FALSE
11427 | MRT-CA01-P0UPB-187034 | 2021-12-29 | MRT-HK-REC-TT-211663 | FA | 1 | TRUE | TRUE | FALSE
11428 | MRT-CA02-P0UVH-187076 | 2021-12-29 | MRT-HK-REC-TT-211663 | FA | 2 | TRUE | TRUE | FALSE
11429 | MRT-CA02-P0UGA-176260 | 2021-12-29 | MRT-HK-REC-TT-211663 | FA | 2 | TRUE | TRUE | FALSE
11430 | MRT-CA02-P0UGA-176265 | 2021-12-29 | MRT-HK-REC-TT-211663 | FA | 1 | TRUE | TRUE | FALSE
11431 | MRT-QM01-P0GHE-145070 | 2022-01-03 | MRT-HK-REC-TT-221670 | FA | 2 | TRUE | FALSE | FALSE
11432 | MRT-QM01-P0GHE-145070 | 2022-01-06 | MRT-HK-REC-TT-221677 | FA | 3 | TRUE | TRUE | FALSE
11433 | MRT-DN02-P2MAV-830017 | 2022-01-13 | MRT-DS-REC-TT-220001 | FA | 5 | TRUE | TRUE | FALSE
11434 | MRT-QM01-P0GHE-145070 | 2022-01-15 | MRT-HK-REC-TT-221683 | FA | 4 | TRUE | TRUE | FALSE
11435 | MRT-CC04-P0MKG-185226 | 2022-01-20 | MRT-HK-REC-TT-221687 | AB | 1 | TRUE | TRUE | FALSE
11436 | MRT-DN02-P2MAV-830017 | 2022-01-24 | MRT-DS-REC-TT-220002 | FC | 6 | TRUE | TRUE | FALSE
11437 | MRT-YE07-P2UMA-150156 | 2022-01-25 | MRT-HK-REC-TT-221696 | FA | 1 | TRUE | TRUE | FALSE
11438 | MRT-YE07-P3UMA-150157 | 2022-01-25 | MRT-HK-REC-TT-221696 | FA | 1 | TRUE | TRUE | FALSE
11439 | MRT-XR00-P0QHY-125414 | 2022-01-27 | MRT-HK-REC-TT-221695 | FA | 2 | TRUE | TRUE | FALSE
11440 | MRT-DN02-P2ZEN-830025 | 2022-02-10 | MRT-DS-REC-TT-220003 | FA | 1 | TRUE | TRUE | FALSE
11445 | MRT-XJ00-P0GHC-140001 | 2022-02-21 | MRT-DS-REC-TT-220004 | FC | 4 | TRUE | TRUE | FALSE
11446 | MRT-XJ00-P0GHD-140001 | 2022-02-21 | MRT-DS-REC-TT-220004 | FC | 4 | TRUE | TRUE | FALSE
11449 | MRT-YL16-P0BBY-150080 | 2022-03-29 | MRT-HK-REC-TT-221747 | FI | 1 | TRUE | FALSE | FALSE
11450 | MRT-FF02-P0AYE-135640 | 2022-04-04 | MRT-HK-REC-TT-221753 | FI | 2 | TRUE | FALSE | FALSE
11451 | MRT-FF02-P2AYE-135637 | 2022-04-06 | MRT-HK-REC-TT-221756 | AB | 1 | TRUE | FALSE | FALSE
11452 | MRT-FF02-P2AYE-135638 | 2022-04-06 | MRT-HK-REC-TT-221756 | AB | 2 | TRUE | FALSE | FALSE
11453 | MRT-YS01-P0PBB-135256 | 2022-04-07 | MRT-HK-REC-TT-221758 | FI | 0 | TRUE | FALSE | FALSE
11454 | MRT-YS01-P0PBB-135257 | 2022-04-07 | MRT-HK-REC-TT-221758 | FI | 0 | TRUE | FALSE | FALSE
11455 | MRT-YU01-P0PBB-135261 | 2022-04-07 | MRT-HK-REC-TT-221758 | FA | 0 | TRUE | FALSE | FALSE
11456 | MRT-XJ00-P0QCH-140000 | 2022-04-14 | MRT-DS-REC-TT-220005 | FC | 1B | TRUE | FALSE | FALSE
11457 | MRT-YD02-P3ZEN-165020 | 2022-04-26 | MRT-HK-REC-TT-221775 | FA | 4 | TRUE | FALSE | FALSE
11458 | MRT-XJ00-P2LB-142000 | 2022-05-23 | MRT-DS-REC-TT-220006 | FC | 1C | TRUE | FALSE | FALSE
11459 | MRT-YL16-P3BJC-150071 | 2022-06-16 | MRT-HK-REC-TT-221813 | FI | 2 | TRUE | TRUE | FALSE
11460 | MRT-CC02-P2UHA-170103 | 2022-06-28 | MRT-DS-REC-TT-220007 | FC | 12 | TRUE | FALSE | FALSE
11461 | MRT-CC02-P3UHA-170103 | 2022-06-28 | MRT-DS-REC-TT-220007 | FC | 12 | TRUE | FALSE | FALSE
11463 | MRT-YK09-P0PUR-150965 | 2022-07-06 | MRT-HK-REC-TT-221831 | FA | 1 | TRUE | TRUE | FALSE
11464 | MRT-YK09-P0PUR-150967 | 2022-07-06 | MRT-HK-REC-TT-221831 | FA | 1 | TRUE | TRUE | FALSE
11465 | MRT-US02-P0PUR-150996 | 2022-07-06 | MRT-HK-REC-TT-221831 | FA | 1 | TRUE | TRUE | FALSE
11466 | MRT-YL16-P3MKY-150087 | 2022-07-06 | MRT-HK-REC-TT-221833 | FI | 1 | TRUE | FALSE | FALSE
11462 | MRT-DN02-P2MKA-830029 | 2022-07-07 | MRT-DS-REC-TT-220009 | FA | 1 | TRUE | TRUE | FALSE
11467 | MRT-XG02-P2SGC-135418 | 2022-07-12 | MRT-HK-REC-TT-221837 | AB | 2 | TRUE | FALSE | FALSE
11468 | MRT-FF03-P2SGC-135418 | 2022-07-12 | MRT-HK-REC-TT-221837 | AB | 3 | TRUE | FALSE | FALSE
11469 | MRT-XG02-P2SGC-135417 | 2022-07-12 | MRT-HK-REC-TT-221837 | AB | 1 | TRUE | FALSE | FALSE
11470 | MRT-FF03-P2SGC-135417 | 2022-07-12 | MRT-HK-REC-TT-221837 | AB | 2 | TRUE | FALSE | FALSE
11471 | MRT-CV05-P0ZEN-150277 | 2022-07-13 | MRT-HK-REC-TT-221839 | FI | 1 | TRUE | TRUE | FALSE
11472 | MRT-FF02-P2AYE-135633 | 2022-07-15 | MRT-HK-REC-TT-221843 | AB | 1 | TRUE | FALSE | FALSE
11473 | MRT-FF02-P2AYE-135635 | 2022-07-15 | MRT-HK-REC-TT-221843 | AB | 2 | TRUE | FALSE | FALSE
11474 | MRT-FF02-P2AYE-135637 | 2022-07-15 | MRT-HK-REC-TT-221843 | AB | 2 | TRUE | FALSE | FALSE
11475 | MRT-FF02-P2AYE-135623 | 2022-07-15 | MRT-HK-REC-TT-221843 | AB | 2 | TRUE | FALSE | FALSE
11476 | MRT-FF02-P2AYE-135638 | 2022-07-15 | MRT-HK-REC-TT-221843 | AB | 2 | TRUE | FALSE | FALSE
11477 | MRT-YL19-P0PBB-135245 | 2022-07-15 | MRT-HK-REC-TT-221845 | AB | 1 | TRUE | FALSE | FALSE
11478 | MRT-CC05-P0SMU-125016 | 2022-07-15 | MRT-HK-REC-TT-221845 | AB | 1 | TRUE | FALSE | FALSE
11479 | MRT-CC05-P0SMU-125016 | 2022-07-15 | MRT-HK-REC-TT-221845 | AB | 1 | TRUE | FALSE | FALSE
11480 | MRT-CC05-P0SMU-125016 | 2022-07-15 | MRT-HK-REC-TT-221845 | AB | 1 | TRUE | FALSE | FALSE
11481 | MRT-CC05-P0SMU-125013 | 2022-07-15 | MRT-HK-REC-TT-221845 | AB | 2 | TRUE | FALSE | FALSE
11482 | MRT-CC05-P0SMU-125015 | 2022-07-15 | MRT-HK-REC-TT-221845 | AB | 2 | TRUE | FALSE | FALSE
11483 | MRT-CC05-P0SMU-125020 | 2022-07-15 | MRT-HK-REC-TT-221845 | AB | 1 | TRUE | FALSE | FALSE
11484 | MRT-CC05-P0SMU-125050 | 2022-07-15 | MRT-HK-REC-TT-221845 | AB | 1 | TRUE | FALSE | FALSE
11485 | MRT-CC05-P0SMU-125019 | 2022-07-15 | MRT-HK-REC-TT-221845 | AB | 1 | TRUE | FALSE | FALSE
11486 | MRT-YT01-P0SMU-125023 | 2022-07-15 | MRT-HK-REC-TT-221845 | AB | 1 | TRUE | FALSE | FALSE
11487 | MRT-CC05-P0SMU-125012 | 2022-07-15 | MRT-HK-REC-TT-221845 | AB | 1 | TRUE | FALSE | FALSE
11488 | MRT-XG02-P2SGK-135427 | 2022-07-16 | MRT-HK-REC-TT-221846 | AB | 1 | TRUE | FALSE | FALSE
11489 | MRT-FF03-P2SGK-135427 | 2022-07-16 | MRT-HK-REC-TT-221846 | AB | 1 | TRUE | FALSE | FALSE
11490 | MRT-YD00-P2ZEN-113300 | 2022-07-19 | MRT-DS-REC-TT-220010 | FC | 3 | TRUE | TRUE | FALSE
11491 | MRT-YT01-P2ZEN-113301 | 2022-07-19 | MRT-DS-REC-TT-220010 | FC | 3 | TRUE | TRUE | FALSE
11492 | MRT-XR00-P0QHY-125414 | 2022-07-20 | MRT-HK-REC-TT-221857 | FA | 3 | TRUE | FALSE | FALSE
11493 | MRT-YQ08-P2UMA-150232 | 2022-08-08 | MRT-HK-REC-TT-221879 | FA | 1 | TRUE | TRUE | FALSE
11494 | MRT-DS00-P3AY-160049 | 2022-08-08 | MRT-HK-REC-TT-221879 | FA | 1 | TRUE | TRUE | FALSE
11495 | MRT-DS00-P3AYA-160028 | 2022-08-08 | MRT-HK-REC-TT-221879 | FA | 1 | TRUE | TRUE | FALSE
11496 | MRT-DS00-P3AY-160041 | 2022-08-08 | MRT-HK-REC-TT-221879 | FA | 1 | TRUE | TRUE | FALSE
11497 | MRT-XA00-P3PBB-135220 | 2022-08-18 | MRT-HK-REC-TT-221895 | FA | 1 | TRUE | FALSE | FALSE
11498 | MRT-XA00-P3PBB-135221 | 2022-08-18 | MRT-HK-REC-TT-221895 | FA | 1 | TRUE | FALSE | FALSE
11499 | MRT-XA00-P2PBB-135232 | 2022-08-18 | MRT-HK-REC-TT-221895 | FA | 1 | TRUE | FALSE | FALSE
11500 | MRT-XA00-P2PBB-135234 | 2022-08-18 | MRT-HK-REC-TT-221895 | FA | 1 | TRUE | FALSE | FALSE
11501 | MRT-XG02-P0GKC-120001 | 2022-08-19 | MRT-DS-REC-TT-220011 | FC | 6 | TRUE | TRUE | FALSE
11502 | MRT-YK09-P2MKC-230006 | 2022-08-26 | MRT-DS-REC-TT-220012 | FC | 2 | TRUE | TRUE | FALSE
11503 | MRT-YK09-P3MKC-230006 | 2022-08-26 | MRT-DS-REC-TT-220012 | FC | 2 | TRUE | TRUE | FALSE
11504 | MRT-DN02-P2MKA-830029 | 2022-08-30 | MRT-DS-REC-TT-220013 | FC | 2 | TRUE | TRUE | FALSE
11505 | MRT-YF01-P0BFB-150114 | 2022-08-30 | MRT-HK-REC-TT-221905 | FA | 1 | TRUE | TRUE | FALSE
11506 | MRT-YF01-P0BFB-150115 | 2022-08-30 | MRT-HK-REC-TT-221905 | FA | 2 | TRUE | TRUE | FALSE
11507 | MRT-YS01-P0BBA-150113 | 2022-08-30 | MRT-HK-REC-TT-221905 | FA | 1 | TRUE | TRUE | FALSE
11508 | MRT-YS01-P0BFB-150111 | 2022-08-30 | MRT-HK-REC-TT-221905 | FA | 1 | TRUE | TRUE | FALSE
11509 | MRT-YF01-P0BFB-150116 | 2022-08-30 | MRT-HK-REC-TT-221905 | FA | 1 | TRUE | TRUE | FALSE
11510 | MRT-YS01-P0BFB-150112 | 2022-08-30 | MRT-HK-REC-TT-221905 | FA | 1 | TRUE | TRUE | FALSE
11516 | MRT-YU02-P2BMF-150683 | 2022-08-30 | MRT-HK-REC-TT-221902 | FA | 1 | TRUE | FALSE | FALSE
11517 | MRT-YU02-P2BRA-150745 | 2022-08-30 | MRT-HK-REC-TT-221902 | FA | 1 | TRUE | FALSE | FALSE
11518 | MRT-YU02-P2BFA-150669 | 2022-08-30 | MRT-HK-REC-TT-221902 | FA | 2 | TRUE | FALSE | FALSE
11519 | MRT-YU02-P2BLF-150739 | 2022-08-30 | MRT-HK-REC-TT-221902 | FA | 2 | TRUE | FALSE | FALSE
11520 | MRT-YU02-P2BJA-150675 | 2022-08-30 | MRT-HK-REC-TT-221902 | FA | 2 | TRUE | FALSE | FALSE
11515 | MRT-DN02-P2LBF-830013 | 2022-08-31 | MRT-DS-REC-TT-220014 | FC | 2 | TRUE | TRUE | FALSE
11521 | MRT-YT10-P2MKC-230016 | 2022-09-15 | MRT-DS-REC-TT-220015 | FC | 1 | TRUE | FALSE | FALSE
11522 | MRT-XG02-P2PAC-130001 | 2022-09-16 | MRT-HK-REC-TT-221928 | FA | 1 | TRUE | FALSE | FALSE
11523 | MRT-XG02-P3PAC-130001 | 2022-09-16 | MRT-HK-REC-TT-221928 | FA | 1 | TRUE | FALSE | FALSE
11524 | MRT-YL16-P2BBA-150061 | 2022-09-19 | MRT-HK-REC-TT-221932 | AB | 2 | TRUE | FALSE | FALSE
11525 | MRT-YL16-P2BFA-150063 | 2022-09-19 | MRT-HK-REC-TT-221932 | AB | 2 | TRUE | FALSE | FALSE
11526 | MRT-YL16-P2BJA-150069 | 2022-09-19 | MRT-HK-REC-TT-221932 | AB | 2 | TRUE | FALSE | FALSE
11527 | MRT-YE16-P2UMA-150329 | 2022-09-19 | MRT-HK-REC-TT-221932 | AB | 3 | TRUE | FALSE | FALSE
11528 | MRT-YE00-P2UMA-150171 | 2022-09-19 | MRT-HK-REC-TT-221932 | AB | 1 | TRUE | FALSE | FALSE
11529 | MRT-YE16-P2UMA-150136 | 2022-09-19 | MRT-HK-REC-TT-221932 | AB | 3 | TRUE | FALSE | FALSE
11530 | MRT-XJ00-P3PGB-146000 | 2022-09-26 | MRT-DS-REC-TT-220016 | FC | 1B | TRUE | FALSE | FALSE
11531 | MRT-XJ00-P3PGB-147000 | 2022-09-26 | MRT-DS-REC-TT-220016 | FC | 1B | TRUE | FALSE | FALSE
11532 | MRT-XS00-P0GEN-135300 | 2022-09-26 | MRT-HK-REC-TT-221938 | FA | 6 | TRUE | TRUE | FALSE
11544 | MRT-HM03-P0SAF-135796 | 2022-09-28 | MRT-HK-REC-TT-221941 | FA | 1 | TRUE | TRUE | FALSE
11533 | MRT-YK01-P0GEN-135377 | 2022-09-30 | MRT-HK-REC-TT-221943 | FA | 1 | TRUE | FALSE | FALSE
11534 | MRT-YM03-P0GEN-135882 | 2022-09-30 | MRT-HK-REC-TT-221943 | FA | 1 | TRUE | FALSE | FALSE
11535 | MRT-YE00-P0GEN-135365 | 2022-09-30 | MRT-HK-REC-TT-221943 | FA | 1 | TRUE | FALSE | FALSE
11536 | MRT-YL16-P2BJA-150069 | 2022-10-03 | MRT-HK-REC-TT-221945 | FA | 2 | TRUE | FALSE | FALSE
11537 | MRT-YL16-P2MKY-150085 | 2022-10-03 | MRT-HK-REC-TT-221945 | FA | 2 | TRUE | FALSE | FALSE
11538 | MRT-YL16-P2MKX-150088 | 2022-10-03 | MRT-HK-REC-TT-221945 | FA | 2 | TRUE | FALSE | FALSE
11539 | MRT-YL16-P2MKA-150095 | 2022-10-03 | MRT-HK-REC-TT-221945 | FA | 2 | TRUE | FALSE | FALSE
11540 | MRT-YU02-P0BLL-150779 | 2022-10-03 | MRT-HK-REC-TT-221945 | FA | 1 | TRUE | FALSE | FALSE
11541 | MRT-YU02-P2BLK-150763 | 2022-10-03 | MRT-HK-REC-TT-221945 | FA | 1 | TRUE | FALSE | FALSE
11542 | MRT-YU02-P2BMA-150719 | 2022-10-03 | MRT-HK-REC-TT-221945 | FA | 1 | TRUE | FALSE | FALSE
11543 | MRT-YU02-P2BJB-150677 | 2022-10-03 | MRT-HK-REC-TT-221945 | FA | 2 | TRUE | FALSE | FALSE
11545 | MRT-XG02-P2SGE-135406 | 2022-10-10 | MRT-HK-REC-TT-221954 | FA | 1 | TRUE | FALSE | FALSE
11546 | MRT-XG02-P2SGC-135415 | 2022-10-10 | MRT-HK-REC-TT-221954 | FA | 2 | TRUE | FALSE | FALSE
11547 | MRT-FF01-P2SGA-135430 | 2022-10-10 | MRT-HK-REC-TT-221954 | FA | 1 | TRUE | FALSE | FALSE
11548 | MRT-XG02-P2SGE-135407 | 2022-10-10 | MRT-HK-REC-TT-221954 | FA | 1 | TRUE | FALSE | FALSE
11549 | MRT-FF03-P2SGE-135406 | 2022-10-10 | MRT-HK-REC-TT-221954 | FA | 2 | TRUE | FALSE | FALSE
11550 | MRT-FF03-P2SGE-135407 | 2022-10-10 | MRT-HK-REC-TT-221954 | FA | 3 | TRUE | FALSE | FALSE
11551 | MRT-FF03-P2SGC-135415 | 2022-10-10 | MRT-HK-REC-TT-221954 | FA | 3 | TRUE | FALSE | FALSE
11552 | MRT-DN02-P0MAV-830519 | 2022-10-24 | MRT-HK-REC-TT-221964 | FA | 3 | TRUE | FALSE | FALSE
11553 | MRT-DN02-P2ZEN-830022 | 2022-10-27 | MRT-DS-REC-TT-220017 | FC | 3 | TRUE | TRUE | FALSE
11554 | MRT-DN02-P2H-830026 | 2022-11-01 | MRT-DS-REC-TT-220018 | FC | 3 | TRUE | TRUE | FALSE
11555 | MRT-DN02-P2LBF-830013 | 2022-11-07 | MRT-DS-REC-TT-220019 | FC | 3 | TRUE | FALSE | FALSE
11556 | MRT-XJ00-P3LCA-146000 | 2022-11-09 | MRT-DS-REC-TT-220020 | FC | 1C | TRUE | FALSE | FALSE
11557 | MRT-XJ00-P3LCA-147000 | 2022-11-09 | MRT-DS-REC-TT-220020 | FC | 1C | TRUE | FALSE | FALSE
11558 | MRT-DN02-P0MAV-830519 | 2022-11-11 | MRT-HK-REC-TT-221972 | FA | 4 | TRUE | FALSE | FALSE
11559 | MRT-YU02-P0SAC-150695 | 2022-11-15 | MRT-HK-REC-TT-221976 | FA | 2 | TRUE | TRUE | FALSE
11560 | MRT-YU02-P0SAC-150695 | 2022-11-22 | MRT-HK-REC-TT-221981 | FA | 3 | TRUE | TRUE | FALSE
11561 | MRT-XJ00-P2PGB-145000 | 2022-11-23 | MRT-DS-REC-TT-220021 | FC | 1C | TRUE | TRUE | FALSE
11562 | MRT-XJ00-P3PGB-146000 | 2022-11-23 | MRT-DS-REC-TT-220021 | FC | 1C | TRUE | TRUE | FALSE
11563 | MRT-XJ00-P3PGB-147000 | 2022-11-23 | MRT-DS-REC-TT-220021 | FC | 1C | TRUE | TRUE | FALSE
11564 | MRT-XJ00-P3LCA-146000 | 2022-11-24 | MRT-DS-REC-TT-220022 | FC | 1D | TRUE | FALSE | FALSE
11565 | MRT-XJ00-P3LCA-147000 | 2022-11-24 | MRT-DS-REC-TT-220022 | FC | 1D | TRUE | FALSE | FALSE
11566 | MRT-XJ00-P3LBG-143000 | 2022-11-24 | MRT-DS-REC-TT-220023 | FC | 2B | TRUE | FALSE | FALSE
11567 | MRT-XJ00-P2PGB-142000 | 2022-11-24 | MRT-DS-REC-TT-220023 | FC | 2C | TRUE | FALSE | FALSE
11568 | MRT-XJ00-P3PGB-143000 | 2022-11-24 | MRT-DS-REC-TT-220023 | FC | 2C | TRUE | FALSE | FALSE
11569 | MRT-XJ00-P3LBG-144000 | 2022-11-24 | MRT-DS-REC-TT-220023 | FC | 2B | TRUE | FALSE | FALSE
11570 | MRT-XJ00-P3PGB-144000 | 2022-11-24 | MRT-DS-REC-TT-220023 | FC | 2B | TRUE | FALSE | FALSE
11571 | MRT-XJ00-P3PAB-143100 | 2022-11-25 | MRT-DS-REC-TT-220024 | FC | 3A | TRUE | FALSE | FALSE
11572 | MRT-XJ00-P3PAB-144100 | 2022-11-25 | MRT-DS-REC-TT-220024 | FC | 3A | TRUE | FALSE | FALSE
11573 | MRT-DN02-P2ZEN-830025 | 2022-12-02 | DT MRT-DS-REC-TT-220025 | FA | 2 | TRUE | FALSE | FALSE
11574 | MRT-DN05-P2LB-122119 | 2022-12-12 | MRT-DS-REC-TT-220026 | FC | 0 | TRUE | TRUE | FALSE
11575 | MRT-XG02-P2LBA-110003 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11576 | MRT-XG02-P2LBG-110004 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11577 | MRT-XG02-P0LBG-110004 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11578 | MRT-XG02-P2LCM-110005 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11579 | MRT-XG02-P2LA-110006 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11580 | MRT-XG02-P2LC-110007 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11581 | MRT-XG02-P2PA-110002 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11582 | MRT-XG02-P0PA-110002 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11583 | MRT-XG02-P2PA-110008 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11584 | MRT-XG02-P0GHC-110002 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11585 | MRT-XG02-P2PG-110009 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11586 | MRT-XG02-P0QJA-110010 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11587 | MRT-XG02-P3LBA-110003 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11588 | MRT-XG02-P3LBG-110004 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11589 | MRT-XG02-P3LCM-110005 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11590 | MRT-XG02-P3LA-110006 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11591 | MRT-XG02-P3LC-110007 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11592 | MRT-XG02-P3PA-110002 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11593 | MRT-XG02-P3PA-110008 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11594 | MRT-XG02-P3PG-110009 | 2022-12-14 | MRT-DS-REC-TT-220027 | AB | Z0 | TRUE | FALSE | FALSE
11595 | MRT-YD00-P2PGB-113101 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11596 | MRT-YT01-P2PGB-113102 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11597 | MRT-YK10-P2PGB-113103 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11598 | MRT-YT01-P2PGB-113104 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11599 | MRT-YD00-P2PGB-113105 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11600 | MRT-YK08-P2LBG-111300 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11601 | MRT-YT01-P2LBG-111301 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11602 | MRT-YT01-P2LB-111102 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11603 | MRT-YK08-P2LB-111101 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11604 | MRT-YK09-P2LB-111103 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11605 | MRT-YD00-P2ZEN-113300 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11606 | MRT-YT01-P2ZEN-113301 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11607 | MRT-YD00-P2ZEN-113400 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11608 | MRT-YT01-P2ZEN-113401 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11609 | MRT-YK08-P2ZEN-111200 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11610 | MRT-YT01-P2ZEN-111201 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11611 | MRT-YT01-P2PGB-113200 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11612 | MRT-YD00-P2PGB-113201 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11613 | MRT-YD00-P0QJA-111101 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11614 | MRT-YD00-P3PGB-113101 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11615 | MRT-YT01-P3PGB-113102 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11616 | MRT-YK10-P3PGB-113103 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11617 | MRT-YT01-P3PGB-113104 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11618 | MRT-YD00-P3PGB-113105 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11619 | MRT-YK08-P3LBG-111300 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11620 | MRT-YT01-P3LBG-111301 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11621 | MRT-YT01-P3LB-111102 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11622 | MRT-YK08-P3LB-111101 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11623 | MRT-YK09-P3LB-111103 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11624 | MRT-YD00-P3ZEN-113300 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11625 | MRT-YT01-P3ZEN-113301 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11626 | MRT-YD00-P3ZEN-113400 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11627 | MRT-YT01-P3ZEN-113401 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11628 | MRT-YK08-P3ZEN-111200 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11629 | MRT-YT01-P3ZEN-111201 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11630 | MRT-YT01-P3PGB-113200 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11631 | MRT-YD00-P3PGB-113201 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11632 | MRT-YD00-P2PAB-113251 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11633 | MRT-YT01-P2PAB-113252 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11634 | MRT-XG02-P2PAB-113253 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11635 | MRT-YD00-P3PAB-113251 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11636 | MRT-YT01-P3PAB-113252 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11637 | MRT-XG02-P3PAB-113253 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11638 | MRT-YD00-P2ZEN-113500 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11639 | MRT-YD00-P3ZEN-113500 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11640 | MRT-YT01-P2ZEN-113501 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11641 | MRT-YT01-P3ZEN-113501 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11642 | MRT-YU04-P2LB-111105 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11643 | MRT-YV02-P2LB-111106 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11644 | MRT-YU04-P3LB-111105 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11645 | MRT-YV02-P3LB-111106 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11646 | MRT-YD00-P2PGB-113107 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11647 | MRT-YD00-P2PAB-113263 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11648 | MRT-YD00-P3PGB-113107 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11649 | MRT-YD00-P3PAB-113263 | 2022-12-14 | MRT-DS-REC-TT-220028 | AB | Z0 | TRUE | TRUE | FALSE
11650 | MRT-XG02-P2SCA-120004 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | TRUE | TRUE | FALSE
11651 | MRT-XG02-P2SCA-120005 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | TRUE | TRUE | FALSE
11652 | MRT-XG02-P2SCA-120006 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | TRUE | TRUE | FALSE
11653 | MRT-XG02-P3SCA-120004 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | TRUE | TRUE | FALSE
11654 | MRT-XG02-P3SCA-120005 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | TRUE | TRUE | FALSE
11655 | MRT-XG02-P3SCA-120006 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | TRUE | TRUE | FALSE
11656 | MRT-XG02-P0GKC-120001 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | TRUE | TRUE | FALSE
11657 | MRT-XG02-P0GHD-120001 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | TRUE | TRUE | FALSE
11658 | MRT-XG02-P2MAV-120054 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | TRUE | TRUE | FALSE
11659 | MRT-XG02-P3MAV-120054 | 2022-12-14 | MRT-DS-REC-TT-220029 | AB | Z0 | TRUE | TRUE | FALSE
11660 | MRT-YL16-P2LB-122078 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11661 | MRT-YS00-P2LB-122092 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11662 | MRT-VN03-P2LB-122015 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11663 | MRT-UE00-P2LB-122008 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11664 | MRT-UE00-P2LB-122010 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11665 | MRT-XB02-P2LB-122018 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11666 | MRT-YD02-P2LB-122064 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11667 | MRT-YT01-P2LB-122093 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11668 | MRT-XB02-P2LB-122016 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11669 | MRT-YD02-P2LB-122063 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11670 | MRT-YF00-P2LB-122066 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11671 | MRT-VN02-P2LB-122090 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11672 | MRT-YQ03-P2LB-122086 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11673 | MRT-YT01-P2LB-122096 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11674 | MRT-YT01-P2LB-122100 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11675 | MRT-YD00-P2LB-122055 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11676 | MRT-YT01-P2LB-122097 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11677 | MRT-UE00-P2LB-122007 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11678 | MRT-YD02-P2LB-122065 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11679 | MRT-YK00-P2LB-122072 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11680 | MRT-YL00-P2LB-122075 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11681 | MRT-YM03-P2LB-122069 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11682 | MRT-XJ00-P2LB-122027 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11683 | MRT-XG01-P2LB-122021 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11684 | MRT-XL00-P2LB-122030 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11685 | MRT-YT02-P2LB-122094 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11686 | MRT-YK01-P2LB-122074 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11687 | MRT-XN00-P2LB-122032 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11688 | MRT-VN02-P2LB-122089 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11689 | MRT-XG02-P2LB-122022 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11690 | MRT-XH01-P2LB-122026 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11691 | MRT-YD00-P2LB-122056 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11692 | MRT-YB03-P2LB-122048 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11693 | MRT-XJ00-P2LB-122028 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11694 | MRT-YD00-P2LB-122050 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11695 | MRT-YT01-P2LB-122051 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11696 | MRT-YD00-P2LB-122053 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11697 | MRT-YD00-P2LB-122052 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11698 | MRT-YD00-P2LB-122049 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11699 | MRT-XW01-P2LB-122043 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11700 | MRT-YT01-P2LB-122095 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11701 | MRT-XH01-P2LB-122025 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11702 | MRT-YQ01-P2LB-122085 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11703 | MRT-DP00-P2LB-122106 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11704 | MRT-DP00-P3LB-122106 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11705 | MRT-YD00-P2LB-122107 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11706 | MRT-YD00-P2LB-122108 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11707 | MRT-XB02-P3LB-122018 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11708 | MRT-UE00-P3LB-122010 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11709 | MRT-YB03-P3LB-122048 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11710 | MRT-XB02-P3LB-122016 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11711 | MRT-VN03-P3LB-122015 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11712 | MRT-YF00-P3LB-122066 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11713 | MRT-YD00-P3LB-122107 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11714 | MRT-YD00-P3LB-122108 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11715 | MRT-YT01-P3LB-122100 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11716 | MRT-YD00-P3LB-122049 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11717 | MRT-XJ00-P3LB-122028 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11718 | MRT-XG02-P3LB-122022 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11719 | MRT-XL00-P3LB-122030 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11720 | MRT-XN00-P3LB-122032 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11721 | MRT-UE00-P3LB-122008 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11722 | MRT-UE00-P3LB-122007 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11723 | MRT-YQ03-P3LB-122086 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11724 | MRT-XG01-P3LB-122021 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11725 | MRT-XH01-P3LB-122025 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11726 | MRT-XH01-P3LB-122026 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11727 | MRT-XJ00-P3LB-122027 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11728 | MRT-XW01-P3LB-122043 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11729 | MRT-YD00-P3LB-122050 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11730 | MRT-YT01-P3LB-122051 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11731 | MRT-YD00-P3LB-122052 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11732 | MRT-YD00-P3LB-122053 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11733 | MRT-YD00-P3LB-122055 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11734 | MRT-YD00-P3LB-122056 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11735 | MRT-YD02-P3LB-122063 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11736 | MRT-YD02-P3LB-122064 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11737 | MRT-YD02-P3LB-122065 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11738 | MRT-YM03-P3LB-122069 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11739 | MRT-YK00-P3LB-122072 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11740 | MRT-YK01-P3LB-122074 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11741 | MRT-YL16-P3LB-122078 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11742 | MRT-YQ01-P3LB-122085 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11743 | MRT-VN02-P3LB-122089 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11744 | MRT-VN02-P3LB-122090 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11745 | MRT-YS00-P3LB-122092 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11746 | MRT-YT01-P3LB-122093 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11747 | MRT-YT02-P3LB-122094 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11748 | MRT-YT01-P3LB-122095 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11749 | MRT-YT01-P3LB-122096 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11750 | MRT-YT01-P3LB-122097 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11751 | MRT-YK00-P2LB-122076 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11752 | MRT-YK00-P3LB-122076 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11753 | MRT-YD00-P2LB-122109 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11754 | MRT-YD00-P3LB-122109 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11755 | MRT-XH01-P2LB-122112 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11756 | MRT-XH01-P3LB-122112 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11757 | MRT-YB03-P2LB-122113 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11758 | MRT-YD00-P2LB-122114 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11759 | MRT-YD00-P3LB-122114 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11760 | MRT-YE00-P2LB-122116 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11761 | MRT-YE00-P3LB-122116 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11762 | MRT-YD00-P2LB-122120 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11763 | MRT-DP00-P2LB-122122 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11764 | MRT-DP00-P3LB-122122 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11765 | MRT-DP00-P2LB-122123 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11766 | MRT-DP00-P3LB-122123 | 2022-12-14 | MRT-DS-REC-TT-220030 | AB | Z0 | TRUE | TRUE | FALSE
11767 | MRT-YT01-P2LCB-127036 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11768 | MRT-YT01-P2LCB-127033 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11769 | MRT-YD00-P2LCB-127031 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11770 | MRT-YL00-P2LCB-127040 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11771 | MRT-YT01-P2LCB-127035 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11772 | MRT-YM01-P2LCB-127039 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11773 | MRT-XG02-P2LCB-127032 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11774 | MRT-YK09-P2LCB-127034 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11775 | MRT-YT01-P2LCB-127037 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11776 | MRT-YT01-P3LCB-127036 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11777 | MRT-YT01-P3LCB-127033 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11778 | MRT-YD00-P3LCB-127031 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11779 | MRT-YL00-P3LCB-127040 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11780 | MRT-YT01-P3LCB-127035 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11781 | MRT-YM01-P3LCB-127039 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11782 | MRT-XG02-P3LCB-127032 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11783 | MRT-YK09-P3LCB-127034 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11784 | MRT-YT01-P3LCB-127037 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11785 | MRT-YS18-P0SMM-128010 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11786 | MRT-YD00-P0SMM-128001 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11787 | MRT-YK09-P0SMM-128007 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11788 | MRT-YT01-P2GHC-129002 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11789 | MRT-YD00-P2GHC-129001 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11790 | MRT-YL00-P2GHC-129011 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11791 | MRT-YT01-P2GHC-129004 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11792 | MRT-YM01-P2GHC-129008 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11793 | MRT-YK09-P2GHC-129003 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11794 | MRT-YM01-P3GHC-129008 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11795 | MRT-YT01-P3GHC-129002 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11796 | MRT-YD00-P3GHC-129001 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11797 | MRT-YL00-P3GHC-129011 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11798 | MRT-YT01-P3GHC-129004 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11799 | MRT-YK09-P3GHC-129003 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11800 | MRT-XK00-P2GM-128505 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11801 | MRT-YT01-P2GM-128502 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11802 | MRT-XB00-P2GM-128506 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11803 | MRT-YL00-P2GM-128512 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11804 | MRT-XK00-P2GM-128504 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11805 | MRT-XW01-P2GM-128507 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11806 | MRT-YD00-P2GM-128501 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11807 | MRT-YD00-P2GM-128503 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11808 | MRT-YR05-P2GM-128511 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11809 | MRT-XK00-P3GM-128505 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11810 | MRT-YT01-P3GM-128502 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11811 | MRT-XB00-P3GM-128506 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11812 | MRT-YL00-P3GM-128512 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11813 | MRT-XK00-P3GM-128504 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11814 | MRT-XW01-P3GM-128507 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11815 | MRT-YD00-P3GM-128501 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11816 | MRT-YD00-P3GM-128503 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11817 | MRT-YR05-P3GM-128511 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11818 | MRT-XK00-P2GM-128507 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11819 | MRT-XK00-P3GM-128507 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11820 | MRT-YD00-P2SM-128020 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11821 | MRT-YD00-P3SM-128020 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11822 | MRT-YT01-P2SM-128030 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11823 | MRT-YT01-P3SM-128030 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11824 | MRT-YK09-P2SM-128040 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11825 | MRT-YK09-P3SM-128040 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11826 | MRT-YS18-P2SM-128050 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11827 | MRT-YS18-P3SM-128050 | 2022-12-14 | MRT-DS-REC-TT-220031 | AB | Z0 | TRUE | TRUE | FALSE
11828 | MRT-XG02-P2QC-130001 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11829 | MRT-XA00-P2QC-130002 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11830 | MRT-YD00-P2QC-130005 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11831 | MRT-YF02-P2QC-130006 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11832 | MRT-YL00-P2QC-130007 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11833 | MRT-XN00-P2QC-130008 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11834 | MRT-YK10-P2QC-130010 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11835 | MRT-XH01-P2QC-130011 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11836 | MRT-YT01-P2QC-130012 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11837 | MRT-YT01-P2QC-130013 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11838 | MRT-YT01-P2QC-130014 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11839 | MRT-YT01-P2QC-130033 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11840 | MRT-YT01-P2QC-130016 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11841 | MRT-YV02-P2QC-130017 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11842 | MRT-YL01-P2QC-130034 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11843 | MRT-YF00-P2QC-130019 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11844 | MRT-YS01-P2QC-130020 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11845 | MRT-YE00-P2QC-130021 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11846 | MRT-YK00-P2QC-130022 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11847 | MRT-YD05-P2QC-130035 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11848 | MRT-XG02-P3QC-130001 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11849 | MRT-XA00-P3QC-130002 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11850 | MRT-YD00-P3QC-130005 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11851 | MRT-YF02-P3QC-130006 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11852 | MRT-YL00-P3QC-130007 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11853 | MRT-XN00-P3QC-130008 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11854 | MRT-YK10-P3QC-130010 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11855 | MRT-XH01-P3QC-130011 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11856 | MRT-YT01-P3QC-130012 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11857 | MRT-YT01-P3QC-130013 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11858 | MRT-YT01-P3QC-130014 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11859 | MRT-YT01-P3QC-130033 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11860 | MRT-YT01-P3QC-130016 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11861 | MRT-YV02-P3QC-130017 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11862 | MRT-YL01-P3QC-130034 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11863 | MRT-YF00-P3QC-130019 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11864 | MRT-YS01-P3QC-130020 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11865 | MRT-YE00-P3QC-130021 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11866 | MRT-YK00-P3QC-130022 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11867 | MRT-YD05-P3QC-130035 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11868 | MRT-XG02-P2QU-130024 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11869 | MRT-XA00-P2QU-130025 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11870 | MRT-YF02-P2QU-130027 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11871 | MRT-YL00-P2QU-130028 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11872 | MRT-XN00-P2QU-130029 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11873 | MRT-YT01-P2QU-130030 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11874 | MRT-YT01-P2QU-130031 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11875 | MRT-YV02-P2QU-130032 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11876 | MRT-YF00-P2QU-130033 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11877 | MRT-YS01-P2QU-130034 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11878 | MRT-XG02-P3QU-130024 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11879 | MRT-XA00-P3QU-130025 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11880 | MRT-YF02-P3QU-130027 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11881 | MRT-YL00-P3QU-130028 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11882 | MRT-XN00-P3QU-130029 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11883 | MRT-YT01-P3QU-130030 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11884 | MRT-YT01-P3QU-130031 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11885 | MRT-YV02-P3QU-130032 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11886 | MRT-YF00-P3QU-130033 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11887 | MRT-YS01-P3QU-130034 | 2022-12-14 | MRT-DS-REC-TT-220032 | AB | Z0 | TRUE | TRUE | FALSE
11888 | MRT-UE00-P2ZEN-100004 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | TRUE | TRUE | FALSE
11889 | MRT-UE00-P2ZEN-100005 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | TRUE | TRUE | FALSE
11890 | MRT-UE00-P2ZEN-100006 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | TRUE | TRUE | FALSE
11891 | MRT-UE00-P2ZEN-100007 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | TRUE | TRUE | FALSE
11892 | MRT-UE00-P2ZEN-100008 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | TRUE | TRUE | FALSE
11893 | MRT-UE00-P2ZEN-100009 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | TRUE | TRUE | FALSE
11894 | MRT-UE00-P2ZEN-100016 | 2022-12-14 | MRT-DS-REC-TT-220033 | AB | Z0 | TRUE | TRUE | FALSE
11895 | MRT-XB02-P0UMA-180004 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11896 | MRT-CA01-P0UMA-180005 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11897 | MRT-CA01-P0UMA-180006 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11898 | MRT-CA01-P0UMA-180007 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11899 | MRT-CA00-P0UMA-180009 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11900 | MRT-CA00-P0UMA-180010 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11901 | MRT-CA00-P0UMA-180011 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11902 | MRT-CA00-P0UMA-180013 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11903 | MRT-CA00-P0UMA-180014 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11904 | MRT-CA00-P0UMA-180015 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11905 | MRT-CA00-P0UMA-180016 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11906 | MRT-CA00-P0UMA-180017 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11907 | MRT-CA00-P0UMA-180019 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11908 | MRT-CA00-P0UMA-180021 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11909 | MRT-CA00-P0UMA-180022 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11910 | MRT-CA00-P0UMA-180023 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11911 | MRT-CA00-P0UMA-180024 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11912 | MRT-CA03-P0UMA-180025 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11913 | MRT-CA03-P0UMA-180026 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11914 | MRT-CA01-P0UMA-180027 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11915 | MRT-CA03-P0UMA-180028 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11916 | MRT-CA03-P0UMA-180029 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11917 | MRT-CA03-P0UMA-180031 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11918 | MRT-CA03-P0UMA-180032 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11919 | MRT-CA03-P0UMA-180033 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11920 | MRT-CA03-P0UMA-180034 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11921 | MRT-CA03-P0UMA-180035 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11922 | MRT-CA03-P0UMA-180036 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11923 | MRT-CA03-P0UMA-180037 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11924 | MRT-CA03-P0UMA-180039 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11925 | MRT-CA03-P0UMA-180040 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11926 | MRT-CA03-P0UMA-180042 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11927 | MRT-CA03-P0UMA-180043 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11928 | MRT-CA01-P0UMA-180044 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11929 | MRT-CA02-P0UMA-180045 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11930 | MRT-CA03-P0UMA-180046 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11931 | MRT-CA00-P0UMA-180047 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11932 | MRT-CA05-P0UMA-180061 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11933 | MRT-CA05-P0UMA-180062 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11934 | MRT-XB02-P0UCA-180102 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11935 | MRT-CA01-P0UCA-180103 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11936 | MRT-CA02-P0UCA-180104 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11937 | MRT-CA00-P0UCA-180105 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11938 | MRT-CA00-P0UCA-180106 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11939 | MRT-CA00-P0UCA-180107 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11940 | MRT-CA00-P0UCA-180108 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11941 | MRT-CA00-P0UCA-180112 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11942 | MRT-CA00-P0UCA-180113 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11943 | MRT-CA00-P0UCA-180114 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11944 | MRT-CA00-P0UCA-180115 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11945 | MRT-CA00-P0UCA-180116 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11946 | MRT-CA00-P0UCA-180117 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11947 | MRT-CA00-P0UCA-180119 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11948 | MRT-CA00-P0UCA-180120 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11949 | MRT-CA01-P0UCA-180122 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11950 | MRT-CA01-P0UCA-180123 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11951 | MRT-CA01-P0UCA-180127 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11952 | MRT-CA01-P0UCA-180128 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11953 | MRT-CA01-P0UCA-180129 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11954 | MRT-CA03-P0UCA-180132 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11955 | MRT-CA01-P0UCA-180133 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11956 | MRT-CA02-P0UCA-180134 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11957 | MRT-CA02-P0UCA-180135 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11958 | MRT-CA02-P0UCA-180136 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11959 | MRT-CA05-P0UCA-180161 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11960 | MRT-CA05-P0UCA-180162 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11961 | MRT-CA05-P0UCA-180163 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11962 | MRT-CA05-P0UCA-180164 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11963 | MRT-CA03-P0UMA-180030 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11964 | MRT-CA00-P0UMA-180008 | 2022-12-14 | MRT-DS-REC-TT-220034 | AB | Z0 | TRUE | TRUE | FALSE
11965 | MRT-CC02-P2UHA-170003 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11966 | MRT-CC02-P2UHA-170004 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11967 | MRT-CC02-P2UHA-170007 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11968 | MRT-CC02-P2UHA-170008 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11969 | MRT-CC02-P2UHA-170009 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11970 | MRT-VK02-P2UHA-170010 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11971 | MRT-CC02-P2UHA-170103 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11972 | MRT-CC02-P2UHA-170104 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11973 | MRT-VK02-P2UHA-170106 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11974 | MRT-CC02-P2UMA-170203 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11975 | MRT-CC02-P2UMA-170204 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11976 | MRT-CC02-P2UMA-170207 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11977 | MRT-CC02-P2UMA-170208 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11978 | MRT-CC02-P2UMA-170209 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11979 | MRT-VK02-P2UMA-170210 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11980 | MRT-CC02-P2UAG-170303 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11981 | MRT-CC02-P2UAG-170307 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11982 | MRT-CC02-P2UAG-170308 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11983 | MRT-VK02-P2UAG-170310 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11984 | MRT-CC02-P2UMA-170503 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11985 | MRT-CC02-P2UMA-170507 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11986 | MRT-VK02-P2UMA-170510 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11987 | MRT-CC02-P2UMA-170603 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11988 | MRT-CC02-P2UMA-170607 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11989 | MRT-CC02-P2UMA-170608 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11990 | MRT-CC02-P2UMA-170609 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11991 | MRT-VK02-P2UMA-170610 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11992 | MRT-CC02-P2UMA-170703 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11993 | MRT-CC02-P2UMA-170707 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11994 | MRT-CC02-P2UMA-170708 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11995 | MRT-CC02-P2UMA-170709 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11996 | MRT-VK02-P2UMA-170710 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11997 | MRT-CC02-P2UMA-170803 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11998 | MRT-VK02-P2UMA-170806 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
11999 | MRT-CC02-P2UEJ-170907 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
12000 | MRT-VK02-P2UEJ-170910 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
12001 | MRT-CC02-P0UHA-170002 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
12002 | MRT-CC02-P0UMA-170502 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
12003 | MRT-CC02-P0UMA-170602 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
12004 | MRT-CC02-P0UMA-170702 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
12005 | MRT-CC02-P0UMA-171003 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
12006 | MRT-VK02-P0UMA-171006 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
12007 | MRT-CC02-P0UMA-171103 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
12008 | MRT-VK02-P0UMA-171106 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
12009 | MRT-CC02-P0UMA-171203 | 2022-12-14 | MRT-DS-REC-TT-220035 | AB | Z0 | TRUE | TRUE | FALSE
12010 | MRT-XW01-P2SCA-127503 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12011 | MRT-XW01-P2SCA-127504 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12012 | MRT-YF00-P2SCA-127518 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12013 | MRT-YS01-P2SCA-127511 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12014 | MRT-XB00-P2SCA-127509 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12015 | MRT-YD00-P2LCB-127501 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12016 | MRT-YL00-P2SCA-127520 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12017 | MRT-YD05-P2SCA-127515 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12018 | MRT-YR05-P2SCA-127523 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12019 | MRT-YU02-P2SCA-127510 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12020 | MRT-XG02-P2SCA-127502 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12021 | MRT-XW01-P3SCA-127503 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12022 | MRT-XW01-P3SCA-127504 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12023 | MRT-YF00-P3SCA-127518 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12024 | MRT-YS01-P3SCA-127511 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12025 | MRT-XB00-P3SCA-127509 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12026 | MRT-YD00-P3LCB-127501 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12027 | MRT-YL00-P3SCA-127520 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12028 | MRT-YD05-P3SCA-127515 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12029 | MRT-YR05-P3SCA-127523 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12030 | MRT-YU02-P3SCA-127510 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12031 | MRT-XG02-P3SCA-127502 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12032 | MRT-YD16-P2SCA-127531 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12033 | MRT-YD16-P3SCA-127531 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12034 | MRT-YK00-P2SCA-127521 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12035 | MRT-YK00-P3SCA-127521 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12036 | MRT-YV02-P2SCA-127532 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12037 | MRT-YV02-P3SCA-127532 | 2022-12-15 | MRT-DS-REC-TT-220036 | AB | Z0 | TRUE | TRUE | FALSE
12038 | MRT-YT01-P2LAC-126005 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12039 | MRT-YT01-P2LAC-126004 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12040 | MRT-YD00-P2LAC-126001 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12041 | MRT-YT02-P2LAC-126011 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12042 | MRT-XG02-P2LAC-126003 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12043 | MRT-YK01-P2LAC-126006 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12044 | MRT-YT01-P3LAC-126005 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12045 | MRT-YT01-P3LAC-126004 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12046 | MRT-YD00-P3LAC-126001 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12047 | MRT-YT02-P3LAC-126011 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12048 | MRT-XG02-P3LAC-126003 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12049 | MRT-YK01-P3LAC-126006 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12050 | MRT-YT01-P2LAC-126055 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12051 | MRT-YT01-P2LAC-126054 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12052 | MRT-YD00-P2LAC-126051 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12053 | MRT-YT02-P2LAC-126061 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12054 | MRT-XG02-P2LAC-126053 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12055 | MRT-YK01-P2LAC-126056 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12056 | MRT-YT01-P3LAC-126055 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12057 | MRT-YT01-P3LAC-126054 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12058 | MRT-YD00-P3LAC-126051 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12059 | MRT-YT02-P3LAC-126061 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12060 | MRT-XG02-P3LAC-126053 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12061 | MRT-YK01-P3LAC-126056 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12062 | MRT-XB00-P2LAC-126022 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12063 | MRT-XB00-P3LAC-126022 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12064 | MRT-XB00-P2LAC-126070 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12065 | MRT-XB00-P3LAC-126070 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12066 | MRT-XK00-P2LAC-126014 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12067 | MRT-XK00-P3LAC-126014 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12068 | MRT-YD00-P2LAC-126017 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12069 | MRT-YD00-P2LAC-126065 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12070 | MRT-YD00-P3LAC-126065 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12071 | MRT-YD00-P2LAC-126049 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12072 | MRT-YD00-P3LAC-126049 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12073 | MRT-YD00-P2LAC-126096 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12074 | MRT-YD00-P3LAC-126096 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12075 | MRT-YD00-P2LAC-126050 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12076 | MRT-YD00-P3LAC-126050 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12077 | MRT-YD00-P2LAC-126097 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12078 | MRT-YD00-P3LAC-126097 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12079 | MRT-YD00-P2LAC-126016 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12080 | MRT-YD00-P3LAC-126016 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12081 | MRT-YD00-P2LAC-126064 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12082 | MRT-YD00-P3LAC-126064 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12083 | MRT-XK00-P2LAC-126013 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12084 | MRT-XK00-P3LAC-126013 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12085 | MRT-XK00-P2LAC-126063 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12086 | MRT-XK00-P3LAC-126063 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12087 | MRT-YD00-P3LAC-126017 | 2022-12-15 | MRT-DS-REC-TT-220037 | AB | Z0 | TRUE | TRUE | FALSE
12089 | MRT-XL00-P0ZEN-140001 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12090 | MRT-XL00-P0ZEN-140002 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12091 | MRT-XN00-P0ZEN-140001 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12092 | MRT-XK00-P0ZEN-140001 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12093 | MRT-XJ00-P2LBG-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12094 | MRT-XJ00-P2LAB-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12095 | MRT-XJ00-P2LCA-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12096 | MRT-XJ00-P2PAB-140001 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12097 | MRT-XJ00-P2PAB-142100 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12098 | MRT-XJ00-P2PGB-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12099 | MRT-XH01-P0UZT-140001 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12100 | MRT-XH01-P0UZT-140000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12101 | MRT-XH01-P2UMA-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12102 | MRT-XH01-P3UMA-143000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12103 | MRT-XH01-P3UMA-144000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12104 | MRT-XH01-P2ULY-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12105 | MRT-XH01-P3ULY-143000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12106 | MRT-XH01-P3ULY-144000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12107 | MRT-XJ00-P2LCM-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12108 | MRT-XJ00-P2PAB-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12109 | MRT-XJ00-P2PAB-145100 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12110 | MRT-XJ00-P2LBG-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12111 | MRT-XJ00-P2LCM-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12112 | MRT-XJ00-P2LAB-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12113 | MRT-XJ00-P2LCA-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12114 | MRT-XJ00-P2PGB-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12115 | MRT-XJ00-P2PAB-142200 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12116 | MRT-XJ00-P2QU-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12117 | MRT-XJ00-P2QC-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12118 | MRT-XJ00-P2MAV-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12119 | MRT-XJ00-P2SCA-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12120 | MRT-XJ00-P2QFB-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12121 | MRT-XJ00-P2SCB-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12122 | MRT-XK00-P2LBA-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12123 | MRT-XK00-P2PAB-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12124 | MRT-XJ00-P2MAA-145000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12125 | MRT-XK00-P2PGB-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12126 | MRT-XK00-P2LAB-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12127 | MRT-XK00-P2LBG-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12128 | MRT-XK00-P2LCA-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12129 | MRT-XK00-P2LCM-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12130 | MRT-XK00-P2ACW-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12131 | MRT-XK00-P2MAM-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12132 | MRT-XJ00-P2MAA-142000 | 2022-12-15 | MRT-DS-REC-TT-220038 | AB | Z0 | TRUE | TRUE | FALSE
12133 | MRT-YK08-P2MAG-601001 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12134 | MRT-YK08-P2MAG-601002 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12135 | MRT-XL00-P2MAG-601003 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12136 | MRT-XL00-P2MAG-601004 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12137 | MRT-VL00-P2MAG-601005 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12138 | MRT-VL00-P2MAG-601006 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12139 | MRT-YT01-P2MAG-601007 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12140 | MRT-YT01-P2MAG-601009 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12141 | MRT-YL00-P2MAG-601010 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12142 | MRT-YK08-P3MAG-602001 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12143 | MRT-YK08-P3MAG-602002 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12144 | MRT-XL00-P3MAG-602003 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12145 | MRT-XL00-P3MAG-602004 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12146 | MRT-VL00-P3MAG-602005 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12147 | MRT-VL00-P3MAG-602006 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12148 | MRT-YT01-P3MAG-602007 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12149 | MRT-YT01-P3MAG-602009 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12150 | MRT-YL00-P3MAG-602010 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12151 | MRT-YT01-P2MAJ-603100 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12152 | MRT-XG02-P2MAJ-603101 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12153 | MRT-YK08-P2MAJ-603102 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12154 | MRT-YT01-P2MAJ-603103 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12155 | MRT-YT01-P2MAJ-603104 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12156 | MRT-YL00-P2MAJ-603105 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12157 | MRT-XN00-P2MAJ-603106 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12158 | MRT-YV02-P2MAJ-603108 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12159 | MRT-YK08-P2MAJ-603200 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12160 | MRT-XG02-P2MAJ-603201 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12161 | MRT-YV02-P2MAJ-603202 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12162 | MRT-YK08-P2MAJ-603203 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12163 | MRT-YT01-P2MAJ-603204 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12164 | MRT-YK08-P2MAJ-603205 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12165 | MRT-YT01-P2MAJ-603206 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12166 | MRT-YL00-P2MAJ-603207 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12167 | MRT-YT01-P3MAJ-604100 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12168 | MRT-XG02-P3MAJ-604101 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12169 | MRT-YK08-P3MAJ-604102 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12170 | MRT-YT01-P3MAJ-604103 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12171 | MRT-YT01-P3MAJ-604104 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12172 | MRT-YL00-P3MAJ-604105 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12173 | MRT-XN00-P3MAJ-604106 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12174 | MRT-YV02-P3MAJ-604108 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12175 | MRT-YK08-P3MAJ-604200 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12176 | MRT-XG02-P3MAJ-604201 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12177 | MRT-YV02-P3MAJ-604202 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12178 | MRT-YK08-P3MAJ-604203 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12179 | MRT-YT01-P3MAJ-604204 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12180 | MRT-YK08-P3MAJ-604205 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12181 | MRT-YT01-P3MAJ-604206 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12182 | MRT-YL00-P3MAJ-604207 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12183 | MRT-YT01-P2PAH-604101 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12184 | MRT-XG02-P2PAH-604102 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12185 | MRT-YK08-P2PAH-604103 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12186 | MRT-YK08-P2PAH-604104 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12187 | MRT-YT01-P2PBB-604111 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12188 | MRT-XG02-P2PBB-604112 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12189 | MRT-YK08-P2PBB-604113 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12190 | MRT-YF00-P2PAH-604121 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12191 | MRT-YV02-P2PAH-604122 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12192 | MRT-YB03-P2PAH-604123 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12193 | MRT-YK08-P2PAH-604124 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12194 | MRT-YT01-P3PAH-604501 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12195 | MRT-XG02-P3PAH-604502 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12196 | MRT-YK08-P3PAH-604503 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12197 | MRT-YK08-P3PAH-604504 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12198 | MRT-YT01-P3PBB-604511 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12199 | MRT-XG02-P3PBB-604512 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12200 | MRT-YK08-P3PBB-604513 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12201 | MRT-YF00-P3PAH-604521 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12202 | MRT-YV02-P3PAH-604522 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12203 | MRT-YB03-P3PAH-604523 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12204 | MRT-YK08-P3PAH-604524 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12205 | MRT-YD00-P0PGB-606000 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12206 | MRT-YD00-P2QHE-606003 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12207 | MRT-YD00-P0QHE-606001 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12208 | MRT-YD00-P0ERB-606001 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12209 | MRT-YD00-P0ERB-606002 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12210 | MRT-YK08-P2LAA-605100 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12211 | MRT-YT01-P2LAA-605101 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12212 | MRT-YK08-P2LAA-605102 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12213 | MRT-YK08-P3LAA-605500 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12214 | MRT-YT01-P3LAA-605501 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12215 | MRT-YK08-P3LAA-605502 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12216 | MRT-YD00-P0PGB-606001 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12217 | MRT-YD00-P3QHE-606003 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12218 | MRT-YK08-P2MAJ-603308 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12219 | MRT-YK08-P3MAJ-604308 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12220 | MRT-YT01-P2MAJ-603110 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12221 | MRT-YT01-P3MAJ-604110 | 2022-12-15 | MRT-DS-REC-TT-220039 | AB | Z0 | TRUE | TRUE | FALSE
12222 | MRT-XB00-P2MKA-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12223 | MRT-YD00-P2MKA-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12224 | MRT-YD00-P2MKA-220003 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12225 | MRT-YD00-P2MKA-220004 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12226 | MRT-YD00-P2MKA-220005 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12227 | MRT-YK10-P2MKA-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12228 | MRT-YK10-P2MKA-220002 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12229 | MRT-YK08-P2MKJ-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12230 | MRT-YK10-P2MKB-230001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12231 | MRT-YT01-P2MKA-240001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12232 | MRT-YE00-P2MKA-230001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12233 | MRT-YE00-P2MKA-230002 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12234 | MRT-YK00-P2BAT-240001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12235 | MRT-UC02-P2BAT-240001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12236 | MRT-XB00-P3MKA-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12237 | MRT-YD00-P3MKA-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12238 | MRT-YD00-P3MKA-220003 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12239 | MRT-YD00-P3MKA-220004 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12240 | MRT-YD00-P3MKA-220005 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12241 | MRT-YK10-P3MKA-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12242 | MRT-YK10-P3MKA-220002 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12243 | MRT-YK08-P3MKA-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12244 | MRT-YK10-P3MKB-230001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12245 | MRT-YE00-P3MKA-230001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12246 | MRT-YE00-P3MKA-230002 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12247 | MRT-YT01-P3MKA-240001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12248 | MRT-YD00-P2MKJ-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12249 | MRT-XG02-P2MKJ-210001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12250 | MRT-XJ00-P2MKJ-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12251 | MRT-XH01-P2MKJ-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12252 | MRT-XK00-P2MKJ-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12253 | MRT-YD00-P3MKW-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12254 | MRT-XG02-P3MKW-210001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12255 | MRT-YD00-P3MKW-220002 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12256 | MRT-YD00-P3MKW-220003 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12257 | MRT-YV02-P3MKW-230001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12258 | MRT-YD00-P3MKW-220004 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12259 | MRT-XG02-P3MKG-210001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12260 | MRT-YD00-P3MKG-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12261 | MRT-YD00-P3MKG-220003 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12262 | MRT-YD00-P3MKG-220004 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12263 | MRT-YV02-P3MKW-230002 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12264 | MRT-YD00-P3MKG-220005 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12265 | MRT-XJ00-P3MKA-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12266 | MRT-XH01-P3MKA-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12267 | MRT-XK00-P3MKA-220001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12268 | MRT-YT01-P3MKA-240002 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12269 | MRT-XW03-P3MKA-210001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12270 | MRT-XL00-P3MKA-210001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12271 | MRT-XN00-P3MKA-210001 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12272 | MRT-YD00-P3MKG-220006 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12273 | MRT-YT01-P3MKA-240003 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12274 | MRT-YD00-P3MKW-220005 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12275 | MRT-YK10-P2MKA-220003 | 2022-12-15 | MRT-DS-REC-TT-220040 | AB | Z0 | TRUE | TRUE | FALSE
12276 | MRT-DN02-P2ZEN-830025 | 2022-12-19 | MRT-DS-REC-TT-220041 | FC | 3 | TRUE | FALSE | FALSE
12277 | MRT-XM00-P2MAA-220012 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12278 | MRT-XG02-P2MAA-220005 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12279 | MRT-XG01-P2MAA-220045 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12280 | MRT-YF02-P2CJJ-240112 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12281 | MRT-YT02-P2CJJ-240120 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12282 | MRT-YR00-P2CJJ-240055 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12283 | MRT-YF00-P2CJJ-240064 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12284 | MRT-XG02-P2MAV-220006 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12285 | MRT-XA00-P2MAA-220014 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12286 | MRT-XA00-P2MAA-220015 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12287 | MRT-XA00-P2MAA-220016 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12288 | MRT-XA00-P2MAA-220017 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12289 | MRT-XA00-P2MAA-220018 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12290 | MRT-XT00-P2MAA-220002 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12291 | MRT-XG02-P2MAX-220007 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12292 | MRT-XA00-P2MAA-220020 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12293 | MRT-XA00-P2MAA-220021 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12294 | MRT-XA00-P2MAA-220022 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12295 | MRT-XV00-P2MAA-220036 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12296 | MRT-XV00-P2MAV-220037 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12297 | MRT-YD00-P2CJA-240057 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12298 | MRT-YD00-P2CJA-240058 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12299 | MRT-YD00-P2CJA-240059 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12300 | MRT-XR00-P2MAV-220041 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12301 | MRT-XR00-P2MAA-220040 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12302 | MRT-YV02-P2MAV-230078 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12303 | MRT-YD05-P2CJJ-240069 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12304 | MRT-YK00-P2CJJ-240119 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12305 | MRT-YL01-P2CJJ-240070 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12306 | MRT-YL01-P2CJJ-240073 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12307 | MRT-YV02-P2MAK-230077 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12308 | MRT-YL08-P2CJJ-240068 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12309 | MRT-YL15-P2MAD-240171 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12310 | MRT-YV02-P2MAD-240170 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12311 | MRT-YV02-P2CJJ-240121 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12312 | MRT-XN00-P2MAA-220038 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12313 | MRT-XN00-P2MAV-220039 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12314 | MRT-YF02-P2MAD-240168 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12315 | MRT-YL00-P2CJJ-240052 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12316 | MRT-YD00-P2MAA-220214 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12317 | MRT-YV02-P2MAX-220095 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12318 | MRT-YL15-P2CJJ-240122 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12319 | MRT-YT02-P2MAD-240167 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12320 | MRT-YF00-P2CJJ-240213 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12321 | MRT-YF02-P2MAX-220094 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12322 | MRT-YK00-P2CJJ-240049 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12323 | MRT-YL01-P2MAD-240169 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12324 | MRT-YV02-P2CJJ-240113 | 2022-12-20 | MRT-DS-REC-TT-220042 | AB | Z0 | TRUE | TRUE | FALSE
12325 | MRT-XM00-P3MAA-220012 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12326 | MRT-XG02-P3MAA-220005 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12327 | MRT-XG01-P3MAA-220045 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12328 | MRT-YF02-P3CJJ-240104 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12329 | MRT-YT02-P3CJJ-240112 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12330 | MRT-YR00-P3CJJ-240055 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12331 | MRT-YF00-P3CJJ-240064 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12332 | MRT-XA00-P3MAA-220016 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12333 | MRT-XA00-P3MAA-220014 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12334 | MRT-XA00-P3MAA-220015 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12335 | MRT-XA00-P3MAA-220017 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12336 | MRT-XA00-P3MAA-220018 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12337 | MRT-XA00-P3MAA-220019 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12338 | MRT-XT00-P3MAA-220002 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12339 | MRT-XG02-P3MAV-220006 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12340 | MRT-XG02-P3MAX-220007 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12341 | MRT-XA00-P3MAA-220020 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12342 | MRT-XA00-P3MAA-220021 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12343 | MRT-XA00-P3MAA-220022 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12344 | MRT-XV00-P3MAA-220036 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12345 | MRT-XV00-P3MAV-220037 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12346 | MRT-YD00-P3CJA-240057 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12347 | MRT-YD00-P3CJA-240058 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12348 | MRT-YD00-P3CJA-240059 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12349 | MRT-XR00-P3MAA-220040 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12350 | MRT-YV02-P3MAV-230078 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12351 | MRT-YV02-P3MAK-230077 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12352 | MRT-YD05-P3CJJ-240069 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12353 | MRT-YK00-P3CJJ-240111 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12354 | MRT-YL01-P3CJJ-240070 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12355 | MRT-YL01-P3CJJ-240073 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12356 | MRT-YL00-P3CJJ-240052 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12357 | MRT-YL08-P3CJJ-240068 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12358 | MRT-YV02-P3CJJ-240113 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12359 | MRT-XN00-P3MAA-220038 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12360 | MRT-XN00-P3MAV-220039 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12361 | MRT-YL15-P3CJJ-240114 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12362 | MRT-YL15-P3MAD-240181 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12363 | MRT-XR00-P3MAV-220041 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12364 | MRT-YV02-P3MAD-240180 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12365 | MRT-YF02-P3MAD-240178 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12366 | MRT-YT02-P3MAD-240177 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12367 | MRT-YD00-P3MAA-220214 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12368 | MRT-YV02-P3MAX-220144 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12369 | MRT-YD05-P3MAA-240157 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12370 | MRT-YL01-P3MAD-240179 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12371 | MRT-YK00-P3CJJ-240049 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12372 | MRT-YV02-P3CJJ-240105 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12373 | MRT-YF02-P3MAA-240156 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12374 | MRT-CQ02-P3MAX-220143 | 2022-12-20 | MRT-DS-REC-TT-220043 | AB | Z0 | TRUE | TRUE | FALSE
12376 | MRT-XJ00-P2LBA-145000 | 2022-12-21 | MRT-DS-REC-TT-220044 | FC | 1B | TRUE | FALSE | FALSE
12377 | MRT-XJ00-P3LBA-146000 | 2022-12-21 | MRT-DS-REC-TT-220044 | FC | 1B | TRUE | FALSE | FALSE
12378 | MRT-XJ00-P3LBA-147000 | 2022-12-21 | MRT-DS-REC-TT-220044 | FC | 1B | TRUE | FALSE | FALSE
12379 | MRT-CQ02-P2MAA-220201 | 2022-12-22 | MRT-DS-REC-TT-220045 | FC | 3 | TRUE | TRUE | FALSE
12380 | MRT-YK09-P2MKC-230001 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12381 | MRT-YK09-P2MKC-230002 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12382 | MRT-YK09-P2MKC-230003 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12383 | MRT-YK09-P2MKC-230006 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12384 | MRT-YK09-P3MKC-230002 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12385 | MRT-YK09-P3MKC-230003 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12386 | MRT-YU01-P2MKC-230010 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12387 | MRT-YF00-P2MKC-230011 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12388 | MRT-YS01-P2MKC-230012 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12389 | MRT-YS01-P2MKC-230013 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12390 | MRT-YS01-P2MKC-230014 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12391 | MRT-YS01-P2MKC-230015 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12392 | MRT-YU01-P3MKC-230010 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12393 | MRT-YS01-P3MKC-230014 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12394 | MRT-YS01-P3MKC-230015 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12395 | MRT-YS01-P3MKC-230017 | 2022-12-22 | MRT-DS-REC-TT-220046 | AB | Z0 | TRUE | FALSE | FALSE
12400 | MRT-DN02-P0ZEN-830030 | 2022-12-27 | MRT-DS-REC-TT-220047 | FA | A | TRUE | FALSE | FALSE
12401 | MRT-CV03-P0ZEN-163101 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12402 | MRT-CV03-P0ZEN-163102 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12403 | MRT-CV03-P0ZEN-163103 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12404 | MRT-YE03-P2ZEN-163104 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12405 | MRT-MA02-P2ZEN-163105 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12406 | MRT-YD06-P2ZEN-163106 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12407 | MRT-CV03-P0ZEN-163107 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12408 | MRT-CV03-P0ZEN-163108 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12409 | MRT-YD07-P2ZEN-163109 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12410 | MRT-YR05-P2ZEN-163110 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12411 | MRT-YR05-P2ZEN-163111 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12412 | MRT-YR05-P2ZEN-163112 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12413 | MRT-YR05-P2ZEN-163113 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12414 | MRT-YR05-P2ZEN-163114 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12415 | MRT-YR05-P2ZEN-163116 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12416 | MRT-YE03-P3ZEN-163104 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12417 | MRT-MA02-P3ZEN-163105 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12418 | MRT-YD06-P3ZEN-163106 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12419 | MRT-CV03-P3ZEN-163118 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12420 | MRT-YD07-P3ZEN-163109 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12421 | MRT-YV02-P3ZEN-163116 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12422 | MRT-YR05-P3ZEN-163110 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12423 | MRT-YR05-P3ZEN-163111 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12424 | MRT-YR05-P3ZEN-163113 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12425 | MRT-YR05-P3ZEN-163114 | 2022-12-27 | MRT-DS-REC-TT-220048 | AB | Z0 | TRUE | FALSE | FALSE
12426 | MRT-CV03-P2ZEN-165102 | 2022-12-27 | MRT-DS-REC-TT-220049 | AB | Z0 | TRUE | FALSE | FALSE
12427 | MRT-CV03-P2ZEN-165103 | 2022-12-27 | MRT-DS-REC-TT-220049 | AB | Z0 | TRUE | FALSE | FALSE
12428 | MRT-CV03-P2ZEN-165104 | 2022-12-27 | MRT-DS-REC-TT-220049 | AB | Z0 | TRUE | FALSE | FALSE
12429 | MRT-YL00-P2ZEN-165101 | 2022-12-27 | MRT-DS-REC-TT-220049 | AB | Z0 | TRUE | FALSE | FALSE
12430 | MRT-YF00-P2CBA-161203 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | TRUE | FALSE | FALSE
12431 | MRT-YF00-P2CBA-161204 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | TRUE | FALSE | FALSE
12432 | MRT-YF00-P0CBA-161221 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | TRUE | FALSE | FALSE
12433 | MRT-YF00-P0CGA-161321 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | TRUE | FALSE | FALSE
12434 | MRT-YL01-P2ZEN-161051 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | TRUE | FALSE | FALSE
12435 | MRT-MA02-P2ZEN-161015 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | TRUE | FALSE | FALSE
12436 | MRT-YF00-P0CBA-161201 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | TRUE | FALSE | FALSE
12437 | MRT-YF00-P0CBA-161202 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | TRUE | FALSE | FALSE
12438 | MRT-YF00-P0CGA-161301 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | TRUE | FALSE | FALSE
12439 | MRT-YF00-P0CGA-161302 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | TRUE | FALSE | FALSE
12440 | MRT-MA01-P2ZEN-161011 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | TRUE | FALSE | FALSE
12441 | MRT-GT00-P2ZEN-167001 | 2022-12-27 | MRT-DS-REC-TT-220050 | AB | Z0 | TRUE | FALSE | FALSE
12442 | MRT-YF00-P2CGA-161303 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12443 | MRT-YF00-P2CGA-161304 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12444 | MRT-YF00-P2CBA-161205 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12445 | MRT-YF00-P2CGA-161305 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12446 | MRT-YF00-P2CBA-161206 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12447 | MRT-YF00-P2CGA-161306 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12448 | MRT-YF00-P2CBA-161207 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12449 | MRT-YF00-P2CGA-161307 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12450 | MRT-YF00-P2CBA-161208 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12451 | MRT-YF00-P2CGA-161308 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12452 | MRT-YF00-P2CBA-161209 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12453 | MRT-YF00-P2CGA-161309 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12454 | MRT-YF00-P0CBA-161222 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12455 | MRT-YF00-P0CGA-161322 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12456 | MRT-YF00-P2CBA-161211 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12457 | MRT-YF00-P2CBA-161212 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12458 | MRT-YF00-P2CBA-161210 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12459 | MRT-YF00-P2CGA-161311 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12460 | MRT-YF00-P2CGA-161312 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12461 | MRT-YF00-P2CGA-161310 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12462 | MRT-YF00-P0CJD-161401 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12463 | MRT-YF00-P2CJD-161402 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12464 | MRT-YF00-P2CJD-161403 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12465 | MRT-YF00-P2ZEN-161601 | 2023-01-02 | MRT-DS-REC-TT-220051 | AB | Z0 | TRUE | FALSE | FALSE
12466 | MRT-CV03-P2ZEN-165201 | 2023-01-02 | MRT-DS-REC-TT-220052 | AB | Z0 | TRUE | FALSE | FALSE
12467 | MRT-XK00-P2LBG-141000 | 2023-01-02 | MRT-DS-REC-TT-220053 | AB | Z0 | TRUE | FALSE | FALSE
12468 | MRT-XK00-P2LCA-141000 | 2023-01-02 | MRT-DS-REC-TT-220053 | AB | Z0 | TRUE | FALSE | FALSE
12469 | MRT-XK00-P2LBA-141000 | 2023-01-02 | MRT-DS-REC-TT-220053 | AB | Z0 | TRUE | FALSE | FALSE
12470 | MRT-XK00-P2LBA-141100 | 2023-01-02 | MRT-DS-REC-TT-220053 | AB | Z0 | TRUE | FALSE | FALSE
12471 | MRT-XJ00-P2LBA-142000 | 2023-02-02 | MRT-DS-REC-TT-220054 | AB | Z0 | TRUE | FALSE | FALSE
12472 | MRT-XJ00-P2LBA-145000 | 2023-02-02 | MRT-DS-REC-TT-220054 | AB | Z0 | TRUE | FALSE | FALSE
12473 | MRT-DN02-P0ZEN-830031 | 2023-02-06 | MRT-DS-REC-TT-230001 | FI | 0 | TRUE | FALSE | FALSE
12474 | MRT-DN02-P0ZEN-830031 | 2023-02-13 | MRT-DS-REC-TT-230002 | FI | 1 | TRUE | TRUE | FALSE
12475 | MRT-DN02-P0ZEN-860027 | 2023-02-15 | MRT-DS-REC-TT-230003 | FC | 4 | TRUE | TRUE | FALSE
12476 | MRT-CC02-P3UHA-170003 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12477 | MRT-CC02-P3UHA-170004 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12478 | MRT-CC02-P3UHA-170007 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12479 | MRT-CC02-P3UHA-170008 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12480 | MRT-CC02-P3UHA-170009 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12481 | MRT-VK02-P3UHA-170010 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12482 | MRT-CC02-P3UHA-170103 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12483 | MRT-CC02-P3UHA-170104 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12484 | MRT-VK02-P3UHA-170106 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12485 | MRT-CC02-P3UMA-170203 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12486 | MRT-CC02-P3UMA-170204 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12487 | MRT-CC02-P3UMA-170207 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12488 | MRT-CC02-P3UMA-170208 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12489 | MRT-CC02-P3UMA-170209 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12490 | MRT-VK02-P3UMA-170210 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12491 | MRT-CC02-P3UAG-170303 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12492 | MRT-CC02-P3UAG-170307 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12493 | MRT-CC02-P3UAG-170308 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12494 | MRT-VK02-P3UAG-170310 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12495 | MRT-CC02-P3UMA-170503 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12496 | MRT-CC02-P3UMA-170507 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12497 | MRT-VK02-P3UMA-170510 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12498 | MRT-CC02-P3UMA-170603 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12499 | MRT-CC02-P3UMA-170607 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12500 | MRT-CC02-P3UMA-170608 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12501 | MRT-CC02-P3UMA-170609 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12502 | MRT-VK02-P3UMA-170610 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12503 | MRT-CC02-P3UMA-170703 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12504 | MRT-CC02-P3UMA-170707 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12505 | MRT-CC02-P3UMA-170708 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12506 | MRT-CC02-P3UMA-170709 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12507 | MRT-VK02-P3UMA-170710 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12508 | MRT-CC02-P3UMA-170803 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12509 | MRT-VK02-P3UMA-170806 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12510 | MRT-CC02-P3UEJ-170907 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12511 | MRT-VK02-P3UEJ-170910 | 2023-02-20 | MRT-DS-REC-TT-230004 | AB | Z0 | TRUE | FALSE | FALSE
12569 | MRT-XG02-P2SGE-135406 | 2023-02-22 | MRT-HK-REC-TT-232117 | AB | Z0 | TRUE | FALSE | FALSE
12570 | MRT-XG02-P2SGC-135415 | 2023-02-22 | MRT-HK-REC-TT-232117 | AB | Z0 | TRUE | FALSE | FALSE
12571 | MRT-FF01-P2SGA-135430 | 2023-02-22 | MRT-HK-REC-TT-232117 | AB | Z0 | TRUE | FALSE | FALSE
12572 | MRT-XG02-P2SGE-135407 | 2023-02-22 | MRT-HK-REC-TT-232117 | AB | Z0 | TRUE | FALSE | FALSE
12573 | MRT-FF03-P2SGE-135406 | 2023-02-22 | MRT-HK-REC-TT-232117 | AB | Z0 | TRUE | FALSE | FALSE
12574 | MRT-FF03-P2SGE-135407 | 2023-02-22 | MRT-HK-REC-TT-232117 | AB | Z0 | TRUE | FALSE | FALSE
12575 | MRT-FF03-P2SGC-135415 | 2023-02-22 | MRT-HK-REC-TT-232117 | AB | Z0 | TRUE | FALSE | FALSE
12576 | MRT-FF01-P0SGA-135403 | 2023-02-22 | MRT-HK-REC-TT-232118 | AB | Z0 | TRUE | FALSE | FALSE
12577 | MRT-FF01-P0SGA-135437 | 2023-02-22 | MRT-HK-REC-TT-232118 | AB | Z0 | TRUE | FALSE | FALSE
12578 | MRT-FF03-P0SGF-135423 | 2023-02-22 | MRT-HK-REC-TT-232118 | AB | Z0 | TRUE | FALSE | FALSE
12579 | MRT-XG02-P0SGF-135423 | 2023-02-22 | MRT-HK-REC-TT-232118 | AB | Z0 | TRUE | FALSE | FALSE
12580 | MRT-FF01-P0SGA-135433 | 2023-02-22 | MRT-HK-REC-TT-232118 | AB | Z0 | TRUE | FALSE | FALSE
12581 | MRT-FF02-P2AYE-135634 | 2023-02-24 | MRT-HK-REC-TT-232124 | AB | Z0 | TRUE | FALSE | FALSE
12582 | MRT-XA00-P2PBB-135232 | 2023-02-28 | MRT-HK-REC-TT-232128 | AB | Z0 | TRUE | FALSE | FALSE
12583 | MRT-XA00-P2PBB-135234 | 2023-02-28 | MRT-HK-REC-TT-232128 | AB | Z0 | TRUE | FALSE | FALSE
12584 | MRT-XG02-P2PAC-130001 | 2023-02-28 | MRT-HK-REC-TT-232130 | AB | Z0 | TRUE | FALSE | FALSE
12585 | MRT-XG02-P3PAC-130001 | 2023-02-28 | MRT-HK-REC-TT-232130 | AB | Z0 | TRUE | FALSE | FALSE
12512 | MRT-UC07-P0ZEN-100001 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | TRUE | FALSE | FALSE
12513 | MRT-UC08-P0ZEN-100002 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | TRUE | FALSE | FALSE
12514 | MRT-UC08-P0ZEN-100003 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | TRUE | FALSE | FALSE
12515 | MRT-UE00-P3ZEN-100010 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | TRUE | FALSE | FALSE
12516 | MRT-UE00-P3ZEN-100011 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | TRUE | FALSE | FALSE
12517 | MRT-UE00-P3ZEN-100012 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | TRUE | FALSE | FALSE
12518 | MRT-UE00-P3ZEN-100013 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | TRUE | FALSE | FALSE
12519 | MRT-UE00-P3ZEN-100014 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | TRUE | FALSE | FALSE
12520 | MRT-UE00-P3ZEN-100015 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | TRUE | FALSE | FALSE
12521 | MRT-UE00-P3ZEN-100017 | 2023-03-02 | MRT-DS-REC-TT-230005 | AB | Z0 | TRUE | FALSE | FALSE
12522 | MRT-DN02-P2H-830026 | 2023-03-08 | MRT-DS-REC-TT-230006 | FC | 4 | TRUE | FALSE | FALSE
12523 | MRT-XG02-P0SGA-135413 | 2023-03-08 | MRT-HK-REC-TT-222015 | AB | Z0 | TRUE | FALSE | FALSE
12524 | MRT-FF01-P0SGA-135413 | 2023-03-08 | MRT-HK-REC-TT-222015 | AB | Z0 | TRUE | FALSE | FALSE
12525 | MRT-XG02-P0SGE-135412 | 2023-03-08 | MRT-HK-REC-TT-222015 | AB | Z0 | TRUE | FALSE | FALSE
12526 | MRT-FF03-P0SGE-135412 | 2023-03-08 | MRT-HK-REC-TT-222015 | AB | Z0 | TRUE | FALSE | FALSE
12527 | MRT-FF01-P0SGJ-135443 | 2023-03-08 | MRT-HK-REC-TT-222019 | AB | Z0 | TRUE | FALSE | FALSE
12528 | MRT-FF01-P0SGJ-135457 | 2023-03-08 | MRT-HK-REC-TT-222019 | AB | Z0 | TRUE | FALSE | FALSE
12529 | MRT-FF01-P0SGJ-135455 | 2023-03-08 | MRT-HK-REC-TT-222019 | AB | Z0 | TRUE | FALSE | FALSE
12530 | MRT-FF01-P0SGJ-135438 | 2023-03-08 | MRT-HK-REC-TT-222019 | AB | Z0 | TRUE | FALSE | FALSE
12531 | MRT-FF01-P0SGJ-135447 | 2023-03-08 | MRT-HK-REC-TT-222019 | AB | Z0 | TRUE | FALSE | FALSE
12532 | MRT-FF01-P0SGJ-135444 | 2023-03-08 | MRT-HK-REC-TT-222019 | AB | Z0 | TRUE | FALSE | FALSE
12533 | MRT-FF01-P0SGJ-135449 | 2023-03-08 | MRT-HK-REC-TT-222019 | AB | Z0 | TRUE | FALSE | FALSE
12534 | MRT-FF01-P0SGJ-135451 | 2023-03-08 | MRT-HK-REC-TT-222019 | AB | Z0 | TRUE | FALSE | FALSE
12535 | MRT-FF01-P0SGJ-135453 | 2023-03-08 | MRT-HK-REC-TT-222019 | AB | Z0 | TRUE | FALSE | FALSE
12536 | MRT-FF01-P0SGJ-135454 | 2023-03-08 | MRT-HK-REC-TT-222019 | AB | Z0 | TRUE | FALSE | FALSE
12537 | MRT-FF01-P0SGJ-135446 | 2023-03-08 | MRT-HK-REC-TT-222019 | AB | Z0 | TRUE | FALSE | FALSE
12538 | MRT-FF01-P0SGJ-135452 | 2023-03-08 | MRT-HK-REC-TT-222024 | AB | Z0 | TRUE | FALSE | FALSE
12539 | MRT-FF01-P0SGJ-135440 | 2023-03-08 | MRT-HK-REC-TT-222024 | AB | Z0 | TRUE | FALSE | FALSE
12540 | MRT-FF01-P0SGJ-135441 | 2023-03-08 | MRT-HK-REC-TT-222024 | AB | Z0 | TRUE | FALSE | FALSE
12541 | MRT-FF01-P0SGJ-135456 | 2023-03-08 | MRT-HK-REC-TT-222024 | AB | Z0 | TRUE | FALSE | FALSE
12542 | MRT-FF01-P0SGJ-135439 | 2023-03-08 | MRT-HK-REC-TT-222024 | AB | Z0 | TRUE | FALSE | FALSE
12543 | MRT-YL16-P2BBA-150061 | 2023-03-08 | MRT-HK-REC-TT-232033 | AB | Z0 | TRUE | FALSE | FALSE
12544 | MRT-YL16-P2BFA-150063 | 2023-03-08 | MRT-HK-REC-TT-232033 | AB | Z0 | TRUE | FALSE | FALSE
12545 | MRT-YL16-P2BJA-150069 | 2023-03-08 | MRT-HK-REC-TT-232033 | AB | Z0 | TRUE | FALSE | FALSE
12546 | MRT-YL16-P2MKY-150085 | 2023-03-08 | MRT-HK-REC-TT-232033 | AB | Z0 | TRUE | FALSE | FALSE
12547 | MRT-YL16-P2MKX-150088 | 2023-03-08 | MRT-HK-REC-TT-232033 | AB | Z0 | TRUE | FALSE | FALSE
12548 | MRT-YL16-P2MKA-150095 | 2023-03-08 | MRT-HK-REC-TT-232033 | AB | Z0 | TRUE | FALSE | FALSE
12549 | MRT-YD00-P0UAB-150210 | 2023-03-08 | MRT-HK-REC-TT-232033 | AB | Z0 | TRUE | FALSE | FALSE
12550 | MRT-YU02-P2BMF-150683 | 2023-03-09 | MRT-HK-REC-TT-232076 | AB | Z0 | TRUE | FALSE | FALSE
12551 | MRT-YU02-P2BRA-150745 | 2023-03-09 | MRT-HK-REC-TT-232076 | AB | Z0 | TRUE | FALSE | FALSE
12552 | MRT-YU02-P2BFA-150669 | 2023-03-09 | MRT-HK-REC-TT-232076 | AB | Z0 | TRUE | FALSE | FALSE
12553 | MRT-YU02-P2BLF-150739 | 2023-03-09 | MRT-HK-REC-TT-232076 | AB | Z0 | TRUE | FALSE | FALSE
12554 | MRT-YU02-P2BJA-150675 | 2023-03-09 | MRT-HK-REC-TT-232076 | AB | Z0 | TRUE | FALSE | FALSE
12555 | MRT-YU02-P2BFA-150035 | 2023-03-09 | MRT-HK-REC-TT-232091 | AB | Z0 | TRUE | FALSE | FALSE
12556 | MRT-YU02-P2BJA-150041 | 2023-03-09 | MRT-HK-REC-TT-232091 | AB | Z0 | TRUE | FALSE | FALSE
12557 | MRT-YU02-P0BLL-150779 | 2023-03-09 | MRT-HK-REC-TT-232091 | AB | Z0 | TRUE | FALSE | FALSE
12558 | MRT-YU02-P2BLK-150763 | 2023-03-09 | MRT-HK-REC-TT-232091 | AB | Z0 | TRUE | FALSE | FALSE
12559 | MRT-YU02-P2BMA-150719 | 2023-03-09 | MRT-HK-REC-TT-232091 | AB | Z0 | TRUE | FALSE | FALSE
12560 | MRT-YM02-P2BUA-150751 | 2023-03-09 | MRT-HK-REC-TT-232091 | AB | Z0 | TRUE | FALSE | FALSE
12561 | MRT-YM02-P2BUA-150753 | 2023-03-09 | MRT-HK-REC-TT-232091 | AB | Z0 | TRUE | FALSE | FALSE
12562 | MRT-YU02-P2BJB-150677 | 2023-03-09 | MRT-HK-REC-TT-232091 | AB | Z0 | TRUE | FALSE | FALSE
12563 | MRT-YD00-P2ASU-150002 | 2023-03-14 | MRT-HK-REC-TT-232090 | AB | Z0 | TRUE | FALSE | FALSE
12564 | MRT-YD00-P2ASU-150003 | 2023-03-14 | MRT-HK-REC-TT-232090 | AB | Z0 | TRUE | FALSE | FALSE
12565 | MRT-YD00-P2ASU-150004 | 2023-03-14 | MRT-HK-REC-TT-232090 | AB | Z0 | TRUE | FALSE | FALSE
12566 | MRT-YE16-P2UMA-150617 | 2023-03-14 | MRT-HK-REC-TT-232090 | AB | Z0 | TRUE | FALSE | FALSE
12654 | MRT-XJ00-P3LBA-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12655 | MRT-XJ00-P3LBA-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12656 | MRT-XJ00-P3LCM-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12657 | MRT-XJ00-P3LCM-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12658 | MRT-XJ00-P3MAA-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12659 | MRT-XJ00-P3MAA-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12660 | MRT-XJ00-P0LBG-140000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12661 | MRT-XJ00-P3LBG-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12662 | MRT-XJ00-P3LBG-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12663 | MRT-XJ00-P3LCA-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12664 | MRT-XJ00-P3LCA-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12665 | MRT-XJ00-P3LAB-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12666 | MRT-XJ00-P3LAB-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12667 | MRT-XJ00-P0GHC-141000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12668 | MRT-XJ00-P3PAB-140001 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12669 | MRT-XJ00-P3PAB-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12670 | MRT-XJ00-P3PAB-143200 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12671 | MRT-XJ00-P3PAB-144200 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12672 | MRT-XJ00-P3PAB-143100 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12673 | MRT-XJ00-P3PAB-146100 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12674 | MRT-XJ00-P3PAB-144100 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12675 | MRT-XJ00-P3PAB-147100 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12676 | MRT-XJ00-P3PGB-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12677 | MRT-XJ00-P3PGB-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12678 | MRT-XJ00-P3QC-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12679 | MRT-XJ00-P3QC-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12680 | MRT-XJ00-P3QU-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12681 | MRT-XJ00-P3QU-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12682 | MRT-XJ00-P0GKB-141000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12683 | MRT-XJ00-P0GHD-141000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12684 | MRT-XJ00-P3SCA-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12685 | MRT-XJ00-P3SCA-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12686 | MRT-XJ00-P3QFB-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12687 | MRT-XJ00-P3QFB-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12688 | MRT-XJ00-P3SCB-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12689 | MRT-XJ00-P3SCB-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12690 | MRT-XJ00-P3MAV-146000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12691 | MRT-XJ00-P3MAV-147000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12692 | MRT-XJ00-P0QJA-141000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12693 | MRT-XJ00-P0EKG-141000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12694 | MRT-XJ00-P0EGD-141000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12695 | MRT-XJ00-P0MKG-141000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12696 | MRT-XJ00-P0GMA-141000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12697 | MRT-XJ00-P0QCH-140000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12698 | MRT-XJ00-P0LAA-140000 | 2023-03-15 | MRT-DS-REC-TT-230007 | AB | Z0 | TRUE | FALSE | FALSE
12567 | MRT-DN02-P2ZEN-830025 | 2023-03-28 | MRT-DS-REC-TT-230008 | FC | 4 | TRUE | FALSE | FALSE
12568 | MRT-YR00-P0ZEN-163001 | 2023-04-11 | MRT-DS-REC-TT-230009 | FA | A | TRUE | FALSE | FALSE
12586 | MRT-YR05-P0ZEN-163115 | 2023-05-09 | MRT-DS-REC-TT-230010 | AB | Z0 | TRUE | FALSE | FALSE
12587 | MRT-YR05-P3ZEN-163112 | 2023-05-09 | MRT-DS-REC-TT-230010 | AB | Z0 | TRUE | FALSE | FALSE
12588 | MRT-XJ00-P3LBA-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12589 | MRT-XJ00-P3LBG-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12590 | MRT-XJ00-P3LAB-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12591 | MRT-XJ00-P3LCA-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12592 | MRT-XJ00-P0GHC-140001 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12593 | MRT-XJ00-P3PGB-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12594 | MRT-XJ00-P0GHD-140001 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12595 | MRT-XJ00-P0GKB-140001 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12596 | MRT-XJ00-P0GMA-140001 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12597 | MRT-XJ00-P3LBA-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12598 | MRT-XJ00-P3LBG-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12599 | MRT-XJ00-P3LCM-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12600 | MRT-XJ00-P3LCM-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12601 | MRT-XJ00-P3LAB-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12602 | MRT-XJ00-P3LCA-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12603 | MRT-XJ00-P3PGB-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12604 | MRT-XJ00-P0LBG-141000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12605 | MRT-XK00-P3PAB-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12606 | MRT-XK00-P4PAB-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12607 | MRT-XK00-P3LBA-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12608 | MRT-XK00-P4LBA-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12609 | MRT-XK00-P3PGB-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12610 | MRT-XK00-P4PGB-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12611 | MRT-XK00-P3LAB-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12612 | MRT-XK00-P4LAB-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12613 | MRT-XK00-P3LBG-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12614 | MRT-XK00-P4LBG-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12615 | MRT-XK00-P3LCA-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12616 | MRT-XK00-P4LCA-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12617 | MRT-XK00-P3LCM-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12618 | MRT-XK00-P4LCM-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12619 | MRT-XK00-P3ACW-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12620 | MRT-XK00-P4ACW-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12621 | MRT-XK00-P3MAM-142000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12622 | MRT-XK00-P4MAM-142000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12623 | MRT-XJ00-P3MAA-143000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12624 | MRT-XJ00-P3MAA-144000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12625 | MRT-XK00-P0GHC-140001 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12626 | MRT-XK00-P0GHD-140001 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12627 | MRT-XK00-P0GMA-140001 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12628 | MRT-XK00-P0LBG-141000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12629 | MRT-XK00-P3LCE-141000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12630 | MRT-XK00-P4LCE-142000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12631 | MRT-XK00-P3LAB-141100 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12632 | MRT-XK00-P0EGD-141000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12633 | MRT-XK00-P3LBA-141000 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12634 | MRT-XK00-P4LBA-141100 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12635 | MRT-XK00-P3LBA-141100 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12636 | MRT-XK00-P4LBA-141200 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12637 | MRT-XK00-P0QCH-140001 | 2023-05-31 | MRT-DS-REC-TT-230011 | AB | Z0 | TRUE | TRUE | FALSE
12645 | MRT-XG02-P3MKG-210001 | 2023-07-19 | MRT-DS-REC-TT-230012 | AB | Z0 | TRUE | FALSE | FALSE
12646 | MRT-DN02-P2MAV-830017 | 2023-08-31 | MRT-DS-REC-TT-230013 | FC | 7 | TRUE | TRUE | FALSE
12647 | MRT-DN02-P0ZEN-830031 | 2023-10-05 | MRT-DS-REC-TT-230014 | FI | 2 | TRUE | TRUE | FALSE
12648 | MRT-DN05-P3MAX-220146 | 2023-10-19 | MRT-DS-REC-TT-230015 | FC | 2 | TRUE | TRUE | FALSE
12649 | MRT-DN05-P3MAV-220171 | 2023-10-19 | MRT-DS-REC-TT-230015 | FC | 1 | TRUE | TRUE | FALSE
12650 | MRT-DN05-P3MAV-220094 | 2023-10-19 | MRT-DS-REC-TT-230015 | FC | 2 | TRUE | TRUE | FALSE
12651 | MRT-YK00-P0ZEN-165023 | 2023-11-07 | MRT-DS-REC-TT-230016 | AB | Z0 | TRUE | TRUE | FALSE
12652 | MRT-YK00-P3LB-122072 | 2023-12-11 | MRT-DS-REC-TT-230017 | AB | Z1 | TRUE | TRUE | FALSE
12653 | MRT-VN02-P3LB-122090 | 2023-12-11 | MRT-DS-REC-TT-230017 | AB | Z1 | TRUE | TRUE | FALSE
12699 | MRT-YK09-P3MKC-230001 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | TRUE | TRUE | FALSE
12700 | MRT-YK09-P3MKC-230006 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | TRUE | TRUE | FALSE
12701 | MRT-YF00-P3MKC-230011 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | TRUE | TRUE | FALSE
12702 | MRT-YS01-P3MKC-230012 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | TRUE | TRUE | FALSE
12703 | MRT-YS01-P3MKC-230013 | 2024-01-08 | MRT-DS-REC-TT-240001 | AB | Z0 | TRUE | TRUE | FALSE
12704 | MRT-CV03-P3ZEN-165102 | 2024-01-08 | MRT-DS-REC-TT-240002 | AB | Z0 | TRUE | TRUE | FALSE
12705 | MRT-CV03-P3ZEN-165103 | 2024-01-08 | MRT-DS-REC-TT-240002 | AB | Z0 | TRUE | TRUE | FALSE
12706 | MRT-CV03-P3ZEN-165104 | 2024-01-08 | MRT-DS-REC-TT-240002 | AB | Z0 | TRUE | TRUE | FALSE
12707 | MRT-YL00-P3ZEN-165101 | 2024-01-08 | MRT-DS-REC-TT-240002 | AB | Z0 | TRUE | TRUE | FALSE
12708 | MRT-DN02-P2GM-830032 | 2024-02-21 | MRT-DS-REC-TT-240003 | FA | 0 | TRUE | FALSE | FALSE
12709 | MRT-YK00-P3LB-122072 | 2024-02-23 | MRT-DS-REC-TT-240004 | AB | Z2 | TRUE | TRUE | FALSE
12710 | MRT-VN02-P3LB-122090 | 2024-02-23 | MRT-DS-REC-TT-240004 | AB | Z2 | TRUE | TRUE | FALSE
12711 | MRT-DN02-P2GM-830032 | 2024-02-29 | MRT-DS-REC-TT-240005 | FC | 1 | TRUE | TRUE | FALSE
12712 | MRT-DP00-P3LB-122106 | 2024-03-05 | MRT-DS-REC-TT-240006 | AB | Z1 | TRUE | TRUE | FALSE
12713 | MRT-YM03-P3LB-122069 | 2024-03-05 | MRT-DS-REC-TT-240006 | AB | Z1 | TRUE | TRUE | FALSE
12714 | MRT-VN02-P3LB-122089 | 2024-03-05 | MRT-DS-REC-TT-240006 | AB | Z1 | TRUE | TRUE | FALSE
12715 | MRT-YT02-P3LB-122094 | 2024-03-05 | MRT-DS-REC-TT-240006 | AB | Z1 | TRUE | TRUE | FALSE
12716 | MRT-YT01-P3LB-122096 | 2024-03-05 | MRT-DS-REC-TT-240006 | AB | Z1 | TRUE | TRUE | FALSE
12717 | MRT-YK00-P3LB-122076 | 2024-03-05 | MRT-DS-REC-TT-240006 | AB | Z1 | TRUE | TRUE | FALSE
12718 | MRT-XJ00-P3LB-122027 | 2024-03-12 | MRT-DS-REC-TT-240007 | AB | Z1 | TRUE | TRUE | FALSE
12719 | MRT-YK08-P3LAA-605500 | 2024-04-08 | MRT-DS-REC-TT-240008 | AB | Z1 | TRUE | TRUE | FALSE
12720 | MRT-YK08-P3LAA-605502 | 2024-04-08 | MRT-DS-REC-TT-240008 | AB | Z1 | TRUE | TRUE | FALSE
12721 | MRT-YD00-P3LAC-126001 | 2024-04-09 | MRT-DS-REC-TT-240009 | AB | Z1 | TRUE | TRUE | FALSE
12722 | MRT-YD00-P3LAC-126051 | 2024-04-09 | MRT-DS-REC-TT-240009 | AB | Z1 | TRUE | TRUE | FALSE
12723 | MRT-YD00-P3LAC-126017 | 2024-04-09 | MRT-DS-REC-TT-240009 | AB | Z1 | TRUE | TRUE | FALSE
12724 | MRT-DN02-P2ZEN-830025 | 2024-04-30 | MRT-DS-REC-TT-240010 | FC | 5 | TRUE | TRUE | FALSE
12725 | MRT-XJ00-P2LBA-142000 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | TRUE | TRUE | FALSE
12726 | MRT-XJ00-P3LBA-143000 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | TRUE | TRUE | FALSE
12727 | MRT-XJ00-P3LBA-144000 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | TRUE | TRUE | FALSE
12728 | MRT-XJ00-P2LBA-145000 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | TRUE | TRUE | FALSE
12729 | MRT-XJ00-P3LBA-146000 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | TRUE | TRUE | FALSE
12730 | MRT-XJ00-P3LBA-147000 | 2024-05-14 | MRT-DS-REC-TT-240011 | AB | Z1 | TRUE | TRUE | FALSE
12732 | MRT-XG02-P3QC-130001 | 2024-05-20 | MRT-DS-REC-TT-240012 | AB | Z1 | TRUE | TRUE | FALSE
12733 | MRT-DN02-P2LA-830006 | 2024-06-05 | MRT-DS-REC-TT-240013 | FC | 2 | TRUE | TRUE | FALSE
12734 | MRT-XG02-P2LBG-110004 | 2024-06-11 | MRT-DS-REC-TT-240014 | AB | Z1 | TRUE | TRUE | FALSE
12735 | MRT-XG02-P3LBG-110004 | 2024-06-11 | MRT-DS-REC-TT-240014 | AB | Z1 | TRUE | TRUE | FALSE
12736 | MRT-VN02-P3LB-122089 | 2024-10-17 | MRT-DS-REC-TT-240015 | AB | Z2 | TRUE | TRUE | FALSE
12737 | MRT-YK00-P3LB-122076 | 2024-10-17 | MRT-DS-REC-TT-240015 | AB | Z2 | TRUE | TRUE | FALSE
12738 | MRT-XJ00-P3LBA-146000 | 2024-10-18 | MRT-DS-REC-TT-240016 | AB | Z1 | TRUE | TRUE | FALSE
12739 | MRT-XJ00-P3LBA-147000 | 2024-10-18 | MRT-DS-REC-TT-240016 | AB | Z1 | TRUE | TRUE | FALSE
12740 | MRT-XJ00-P3LBG-146000 | 2024-10-18 | MRT-DS-REC-TT-240016 | AB | Z1 | TRUE | TRUE | FALSE
12741 | MRT-XJ00-P3LBG-147000 | 2024-10-18 | MRT-DS-REC-TT-240016 | AB | Z1 | TRUE | TRUE | FALSE
12742 | MRT-YF00-P3CBA-161203 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12743 | MRT-YF00-P3CGA-161303 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12744 | MRT-YF00-P3CBA-161204 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12745 | MRT-YF00-P3CGA-161304 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12746 | MRT-YF00-P3CBA-161205 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12747 | MRT-YF00-P3CGA-161305 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12748 | MRT-YF00-P3CBA-161206 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12749 | MRT-YF00-P3CGA-161306 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12750 | MRT-YF00-P3CBA-161207 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12751 | MRT-YF00-P3CGA-161307 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12752 | MRT-YF00-P3CBA-161208 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12753 | MRT-YF00-P3CGA-161308 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12754 | MRT-YF00-P3CBA-161209 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12755 | MRT-YF00-P3CGA-161309 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12756 | MRT-YF00-P3CBA-161211 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12757 | MRT-YF00-P3CBA-161212 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12758 | MRT-YF00-P3CBA-161210 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12759 | MRT-YF00-P3CGA-161311 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12760 | MRT-YF00-P3CGA-161312 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12761 | MRT-YF00-P3CGA-161310 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12762 | MRT-YF00-P3CJD-161402 | 2024-10-21 | MRT-DS-REC-TT-240017 | AB | Z0 | TRUE | TRUE | FALSE
12763 |  | 2024-10-21 | MRT-DS-REC-TT-240017 |  |  | FALSE | FALSE | FALSE
12764 |  | 2024-10-21 | MRT-DS-REC-TT-240017 |  |  | FALSE | FALSE | FALSE
12765 |  | 2024-10-21 | MRT-DS-REC-TT-240017 |  |  | FALSE | FALSE | FALSE
12779 | MRT-YL00-P3GHC-129011 | 2024-10-21 | MRT-DS-REC-TT-240018 | AB | Z1 | TRUE | TRUE | FALSE
12780 | MRT-YL00-P3GM-128512 | 2024-10-21 | MRT-DS-REC-TT-240018 | AB | Z1 | TRUE | TRUE | FALSE
12781 | MRT-YR05-P3GM-128511 | 2024-10-21 | MRT-DS-REC-TT-240018 | AB | Z1 | TRUE | TRUE | FALSE
12766 | MRT-YK08-P3LBG-111300 | 2024-10-23 | MRT-DS-REC-TT-240019 | AB | Z1 | TRUE | TRUE | FALSE
12767 | MRT-YT01-P3ZEN-111201 | 2024-10-23 | MRT-DS-REC-TT-240019 | AB | Z0 | TRUE | TRUE | FALSE
12768 | MRT-XG02-P3PAB-113253 | 2024-10-23 | MRT-DS-REC-TT-240019 | AB | Z1 | TRUE | TRUE | FALSE
12769 | MRT-YT01-P3ZEN-113501 | 2024-10-23 | MRT-DS-REC-TT-240019 | AB | Z1 | TRUE | TRUE | FALSE
12770 | MRT-YK10-P3QC-130010 | 2024-10-24 | MRT-DS-REC-TT-240020 | AB | Z0 | TRUE | TRUE | FALSE
12771 | MRT-YF00-P3CJD-161403 | 2024-10-24 | MRT-DS-REC-TT-240021 | AB | Z0 | TRUE | TRUE | FALSE
12772 | MRT-YF00-P3ZEN-161601 | 2024-10-24 | MRT-DS-REC-TT-240021 | AB | Z0 | TRUE | TRUE | FALSE
12773 | MRT-GT00-P3ZEN-167001 | 2024-10-24 | MRT-DS-REC-TT-240021 | AB | Z0 | TRUE | TRUE | FALSE
12774 | MRT-MA02-P3ZEN-161015 | 2024-10-25 | MRT-DS-REC-TT-240022 | AB | Z0 | TRUE | TRUE | FALSE
12775 | MRT-MA01-P3ZEN-161011 | 2024-10-25 | MRT-DS-REC-TT-240022 | AB | Z0 | TRUE | TRUE | FALSE
12776 | MRT-YT01-P3ZEN-111201 | 2024-10-31 | MRT-DS-REC-TT-240023 | AB | Z0 | TRUE | TRUE | FALSE
12777 | MRT-YT01-P3MKA-240003 | 2024-11-05 | MRT-DS-REC-TT-240024 | AB | Z0 | TRUE | TRUE | FALSE
12778 | MRT-YT01-P3ZEN-111201 | 2024-11-11 | MRT-DS-REC-TT-240025 | AB | Z2 | TRUE | TRUE | FALSE
12782 | MRT-CV03-P3ZEN-165201 | 2024-11-12 | MRT-DS-REC-TT-240026 | AB | Z0 | TRUE | TRUE | FALSE
12783 | MRT-YL01-P3ZEN-161051 | 2024-11-14 | MRT-DS-REC-TT-240027 | AB | Z0 | TRUE | TRUE | FALSE
12784 | MRT-DP00-P3LB-122106 | 2024-11-14 | MRT-DS-REC-TT-240028 | AB | Z1 | TRUE | TRUE | FALSE
12785 | MRT-YT01-P3LB-122100 | 2024-11-14 | MRT-DS-REC-TT-240028 | AB | Z0 | TRUE | TRUE | FALSE
12786 | MRT-YL16-P3LB-122078 | 2024-11-14 | MRT-DS-REC-TT-240028 | AB | Z0 | TRUE | TRUE | FALSE
12787 | MRT-YE00-P3LB-122116 | 2024-11-14 | MRT-DS-REC-TT-240028 | AB | Z0 | TRUE | TRUE | FALSE
12788 | MRT-XB00-P3GM-128506 | 2024-11-15 | MRT-DS-REC-TT-240029 | AB | Z0 | TRUE | TRUE | FALSE
12789 | MRT-YL00-P3SCA-127520 | 2024-11-18 | MRT-DS-REC-TT-240030 | AB | Z1 | TRUE | TRUE | FALSE
12790 | MRT-YD00-P3LAC-126001 | 2024-11-18 | MRT-DS-REC-TT-240031 | AB | Z1 | TRUE | TRUE | FALSE
12791 | MRT-YD00-P3LAC-126065 | 2024-11-18 | MRT-DS-REC-TT-240031 | AB | Z1 | TRUE | TRUE | FALSE
12792 | MRT-XH01-P3UMA-143000 | 2024-11-18 | MRT-DS-REC-TT-240032 | AB | Z1 | TRUE | TRUE | FALSE
12793 | MRT-XJ00-P3LCA-146000 | 2024-11-18 | MRT-DS-REC-TT-240032 | AB | Z0 | TRUE | TRUE | FALSE
12794 | MRT-YT01-P3PAH-604501 | 2024-11-18 | MRT-DS-REC-TT-240033 | AB | Z1 | TRUE | TRUE | FALSE
12795 | MRT-XK00-P3LBA-143000 | 2024-11-18 | MRT-DS-REC-TT-240034 | AB | Z1 | TRUE | TRUE | FALSE
12796 | MRT-XK00-P4LBA-144000 | 2024-11-18 | MRT-DS-REC-TT-240034 | AB | Z1 | TRUE | TRUE | FALSE
12797 | MRT-XK00-P3LAB-143000 | 2024-11-18 | MRT-DS-REC-TT-240034 | AB | Z1 | TRUE | TRUE | FALSE
12798 | MRT-XK00-P4LAB-144000 | 2024-11-18 | MRT-DS-REC-TT-240034 | AB | Z1 | TRUE | TRUE | FALSE
12799 | MRT-YE03-P3ZEN-163104 | 2024-11-18 | MRT-DS-REC-TT-240035 | AB | Z1 | TRUE | TRUE | FALSE
12800 | MRT-XG02-P2SCA-120004 | 2024-11-19 | MRT-DS-REC-TT-240036 | AB | Z1 | TRUE | TRUE | FALSE
12801 | MRT-XG02-P2SCA-120006 | 2024-11-19 | MRT-DS-REC-TT-240036 | AB | Z1 | TRUE | TRUE | FALSE
12803 | MRT-YL00-P3MAJ-604207 | 2024-11-20 | MRT-DS-REC-TT-240037 | AB | Z1 | TRUE | TRUE | FALSE
12804 | MRT-YT01-P3MAJ-604103 | 2024-11-20 | MRT-DS-REC-TT-240038 | AB | Z1 | TRUE | TRUE | FALSE
12805 | MRT-YT01-P3MAJ-604204 | 2024-11-20 | MRT-DS-REC-TT-240038 | AB | Z1 | TRUE | TRUE | FALSE
12806 | MRT-YK08-P3MAJ-604205 | 2024-11-20 | MRT-DS-REC-TT-240038 | AB | Z1 | TRUE | TRUE | FALSE
12807 | MRT-YT01-P3MAJ-604206 | 2024-11-20 | MRT-DS-REC-TT-240038 | AB | Z1 | TRUE | TRUE | FALSE
12808 | MRT-YT01-P3PAH-604501 | 2024-11-25 | MRT-DS-REC-TT-240039 | AB | Z2 | TRUE | TRUE | FALSE
12809 | MRT-YD00-P3LAC-126065 | 2024-11-25 | MRT-DS-REC-TT-240040 | AB | Z1 | TRUE | TRUE | FALSE
12810 | MRT-CV03-P3ZEN-165102 | 2024-11-26 | MRT-DS-REC-TT-240041 | AB | Z1 | TRUE | TRUE | FALSE
12811 | MRT-CV03-P3ZEN-165103 | 2024-11-26 | MRT-DS-REC-TT-240041 | AB | Z1 | TRUE | TRUE | FALSE
12812 | MRT-YL00-P3ZEN-165101 | 2024-11-26 | MRT-DS-REC-TT-240041 | AB | Z1 | TRUE | TRUE | FALSE
12813 | MRT-YT01-P3MAJ-604206 | 2024-12-02 | MRT-DS-REC-TT-240042 | AB | Z2 | TRUE | TRUE | FALSE
12814 | MRT-YK00-P3LB-122076 | 2024-12-09 | MRT-DS-REC-TT-240043 | AB | Z3 | TRUE | TRUE | FALSE
12815 | MRT-XG02-P2SCA-120006 | 2025-01-09 | MRT-DS-REC-TT-250001 | AB | Z2 | TRUE | TRUE | FALSE
12816 | MRT-GT00-P3ZEN-167001 | 2025-01-10 | MRT-DS-REC-TT-250002 | AB | Z0 | TRUE | TRUE | FALSE
12817 | MRT-XJ00-P3LCA-146000 | 2025-01-13 | MRT-DS-REC-TT-250003 | AB | Z0 | TRUE | TRUE | FALSE
12818 | MRT-XJ00-P3LCA-146000 | 2025-01-17 | MRT-DS-REC-TT-250004 | AB | Z0 | TRUE | TRUE | FALSE
12819 | MRT-YK10-P3QC-130010 | 2025-01-21 | MRT-DS-REC-TT-250005 | AB | Z2 | TRUE | TRUE | FALSE
12820 | MRT-YT01-P3QC-130016 | 2025-01-21 | MRT-DS-REC-TT-250005 | AB | Z1 | TRUE | TRUE | FALSE
12821 | MRT-YL01-P3QC-130034 | 2025-01-21 | MRT-DS-REC-TT-250005 | AB | Z1 | TRUE | TRUE | FALSE
12822 | MRT-XG02-P2SCA-120006 | 2025-02-07 | MRT-DS-REC-TT-250006 | AB | Z3 | TRUE | TRUE | FALSE
12823 | MRT-GT00-P3ZEN-167001 | 2025-02-17 | MRT-DS-REC-TT-250007 | AB | Z1 | TRUE | TRUE | FALSE