## Sheet1
| Discipline | Serial | Document No | Title | Pur | First Plan | Final Plan | SA | ESOD | HAZOP | PKG Code
EL(15) | Electrical | 152004 | T16182-YD04-P0ZEN-152004 | 380KV CABLE ROUTE PLAN | IFR | 2017-03-03 | 2017-06-21 |  | O
I&C(16) | Instrumentation & Control | 161117 | T16182-YL01-P0CRN-161117 | 3RD PARTY DATA - LINK INTERFACE SIGNAL DATABASE | IFR | 2017-07-15 | 2017-11-12 |  | O
EM(02) | Engineering Management | 020007 | T16182-DP00-P0ZEN-020007 | ABBREVIATION LIST | IFI | 2017-05-01
GN-I&C(29) | Instrumentation & Control | 290005 | T16182-YE00-P0CJN-290005 | AC/DC POWER CABLE/RACEWAY LAYOUT | IFR | 2017-06-30 | 2017-09-30 |  |  |  | PKG-040-STG
PT(12) | Mechanical | 123012 | T16182-YT01-P0MAJ-123012 | ACC - CLEANING WATER PUMP DATASHEET | IFI | 2017-07-07 |  |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123007 | T16182-XW01-P0MAG-123007 | ACC - CONDENSATE COLLECTING TANK OUTLINE DRAWING | IFI | 2017-06-07 | 2017-11-04 |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123010 | T16182-XS00-P0MAG-123010 | ACC - CONDENSATE DRAIN PUMP SPECIFICATION | IFI | 2017-07-07 |  |  |  |  | PKG-013-ACC
PT(12) | Instrumentation & Control | 123029 | T16182-YM02-P0MAG-123029 | ACC - CONTROL LOGIC & LOOP DIAGRAM | IFI | 2017-06-17 |  |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123013 | T16182-XR00-P0MAG-123013 | ACC - ELECTRICAL LIFTING HOIST DATASHEET | IFI | 2017-07-07 |  |  |  |  | PKG-013-ACC
PT(12) | Electrical | 123023 | T16182-XB00-P0MAG-123023 | ACC - ELECTRICAL LOAD LIST | IFI | 2017-03-19 |  |  |  |  | PKG-013-ACC
PT(12) | Civil | 123022 | T16182-VN02-P0MAG-123022 | ACC - EMBEDDED MATERIAL SPECIFICATION | IFI | 2017-03-09 |  |  |  |  | PKG-013-ACC
PT(12) | General | 123005 | T16182-XS00-P0MAG-123005 | ACC - EQUIPMENT LIST | IFI | 2017-03-09 |  |  |  |  | PKG-013-ACC
PT(12) | Electrical | 123009 | T16182-XK00-P0MAG-123009 | ACC - FAN MOTOR DATA SHEET | IFI | 2017-04-28 |  |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123006 | T16182-VN02-P0MAG-123006 | ACC - FAN SPECIFICATION | IFI | 2017-07-07 |  |  |  |  | PKG-013-ACC
PT(12) | Civil | 123021 | T16182-XL00-P0MAG-123021 | ACC - FOUNDATION DRAWINGS / CIVIL LOADING DATA | IFI | 2017-03-09 | 2017-08-06 |  |  |  | PKG-013-ACC
PT(12) | Instrumentation & Control | 123027 | T16182-XK00-P0MAG-123027 | ACC - FUNCTIONAL DESCRIPTION | IFR | 2017-04-08 | 2019-11-01 | O |  |  | PKG-013-ACC
PT(12) | Electrical | 123008 | T16182-XK00-P0MAG-123008 | ACC - GEARBOX DATASHEET | IFI | 2017-07-07 |  |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123001 | T16182-YD00-P0MAG-123001 | ACC - GENERAL ARRANGEMENT DRAWING | IFR | 2017-03-09 | 2017-06-07 | O |  |  | PKG-013-ACC
PT(12) | Mechanical | 123049 | T16182-XA00-P0MAG-123049 | ACC - HOGGING EJECTOR DRAWING | IFI | 2018-03-30 |  |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123048 | T16182-XA00-P0MAG-123048 | ACC - HOLDING EJECTOR DRAWING | IFI | 2018-03-30 |  |  |  |  | PKG-013-ACC
PT(12) | Electrical | 123037 | T16182-YK00-P0MAG-123037 | ACC - I&C JB OUTLINE AND LAYOUT DRAWING | IFI | 2017-07-17 |  |  |  |  | PKG-013-ACC
PT(12) | Instrumentation & Control | 123030 | T16182-YR04-P0MAG-123030 | ACC - I&C WIRING DIAGRAMS | IFI | 2017-07-27 |  |  |  |  | PKG-013-ACC
PT(12) | Instrumentation & Control | 123034 | T16182-YL01-P0MAG-123034 | ACC - INSTRUMENT CALIBRATION SHEET | IFI | 2017-12-16 |  |  |  |  | PKG-013-ACC
PT(12) | Instrumentation & Control | 123032 | T16182-YF00-P0MAG-123032 | ACC - INSTRUMENT DATASHEET | IFI | 2017-06-17 |  |  |  |  | PKG-013-ACC
PT(12) | Instrumentation & Control | 123033 | T16182-YV02-P0MAG-123033 | ACC - INSTRUMENT DRAWING | IFI | 2017-10-05 |  |  |  |  | PKG-013-ACC
PT(12) | Instrumentation & Control | 123031 | T16182-YL00-P0MAG-123031 | ACC - INSTRUMENT LIST | IFI | 2017-05-08 |  |  |  |  | PKG-013-ACC
PT(12) | Instrumentation & Control | 123035 | T16182-YT02-P0MAG-123035 | ACC - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-07-17 |  |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123019 | T16182-XJ00-P0MAG-123019 | ACC - LINE LIST | IFI | 2017-07-22 |  |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123014 | T16182-YT01-P0MAG-123014 | ACC - MANUAL VALVE LIST | IFI | 2017-06-07 | 2017-11-04 |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123015 | T16182-XH02-P0MAG-123015 | ACC - MANUAL VALVE OUTLINE DRAWING | IFI | 2017-08-16 | 2018-01-13 |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123025 | T16182-YM01-P0MAG-123025 | ACC - MOTOR THERMAL LIMIT CURVE | IFI | 2017-07-17 |  |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123002 | T16182-XG02-P0MAG-123002 | ACC - P&I DIAGRAM | IFR | 2017-03-19 | 2017-06-17 | O |  | O | PKG-013-ACC
PT(12) | Mechanical | 123004 | T16182-XS00-P0MAG-123004 | ACC - PERFORMANCE CURVE | IFR | 2017-05-18 | 2017-08-16 |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123016 | T16182-XH01-P0MAG-123016 | ACC - PIPING ARRANGEMENT DRAWING | IFI | 2017-07-22 | 2017-12-19 |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123017 | T16182-YK08-P0MAG-123017 | ACC - PIPING ISOMETRIC DRAWING | IFI | 2017-10-05 | 2018-03-04 |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123011 | T16182-DH02-P0MAG-123011 | ACC - SJAE DATASHEET | IFI | 2017-07-07 |  |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123026 | T16182-YU02-P0MAG-123026 | ACC - SPEED - TORQUE & CURRENT CURVE | IFI | 2017-07-17 |  |  |  |  | PKG-013-ACC
PT(12) | Civil | 123020 | T16182-DE00-P0MAG-123020 | ACC - STEEL STRUCTURE SPECIFICATION | IFI | 2017-04-28 |  |  |  |  | PKG-013-ACC
PT(12) | General | 123038 | T16182-YT01-P0MAG-123038 | ACC - TERMINAL POINT LIST | IFI | 2017-04-28 |  |  |  |  | PKG-013-ACC
PT(12) | General | 123039 | T16182-YD00-P0MAG-123039 | ACC - UTILITY CONSUMPTION LIST | IFI | 2017-04-18 |  |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123050 | T16182-VN01-P0MAG-123050 | ACC - WINDWALL DRAWING | IFI | 2018-05-29 | 2018-06-29 |  |  |  | PKG-013-ACC
PT(12) | Mechanical | 123053 | T16182-DS00-P0MAG-123053 | ACC – CLEANING PROCEDURE | IFI | 2018-11-13 |  |  |  |  | PKG-013-ACC
PT(12) | Electrical | 123051 | T16182-YD00-P0MAG-123051 | ACC CABLE TRAY LAYOUT DRAWING | IFI | 2018-10-25 | 2018-11-12 |  |  |  | PKG-013-ACC
PT(12) |  | 123045 | T16182-VN01-P0MAG-123045 | ACC ERECTION DRAWING | Internal
PT(12) |  | 123047 | T16182-VN01-P0MAG-123047 | ACC ERECTION MANUAL | Internal
PT(12) |  | 123046 | T16182-VN01-P0MAG-123046 | ACC REFERENCE DRAWING | Internal
PT(12) | Mechanical | 123052 | T16182-YQ01-P0ZEN-123052 | ACC_LIGHTING & SMALL POWER LAYOUT DRAWING | IFI | 2018-10-18 |  |  |  |  | PKG-013-ACC
PT(12) | Instrumentation & Control | 123036 | T16182-YT01-P0MAG-123036 | ACC-MOTORISED VALVE SPECIFICATION | IFI | 2017-06-07 | 2017-09-05 |  |  |  | PKG-013-ACC
|  | 860004 | T16182-DN05-P0ZEN-860004 | ACTIVE POWER RESPONSE AND VOLTAGE CONTROL RESPONSE TEST
S&A(18) | Structural & Architectural | 182957 | T16182-CA02-P0UYC-182957 | ADMINISTRATION & SOCIAL BUILDING - BEAM & GIRDER REBAR DETAIL | IFR | 2017-06-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182900 | T16182-CA06-P0UYC-182900 | ADMINISTRATION & SOCIAL BUILDING - CALCULATION SHEET | IFR | 2017-06-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182908 | T16182-CA00-P0UYC-182908 | ADMINISTRATION & SOCIAL BUILDING - CEILING PLAN | IFR | 2018-04-15 | 2018-06-15
S&A(18) | Structural & Architectural | 182985 | T16182-CA05-P0UYC-182985 | ADMINISTRATION & SOCIAL BUILDING - ENLARGED PLUMBING PLAN | IFR | 2017-06-20 | 2017-09-20
S&A(18) | Structural & Architectural | 182907 | T16182-CA00-P0UYC-182907 | ADMINISTRATION & SOCIAL BUILDING - ENLARGED REST ROOM PLAN & ELEVATION | IFR | 2018-04-15 | 2018-06-15
S&A(18) | Structural & Architectural | 182951 | T16182-CA01-P0UYC-182951 | ADMINISTRATION & SOCIAL BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-06-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182956 | T16182-CA01-P0UYC-182956 | ADMINISTRATION & SOCIAL BUILDING - FOUNDATION & COLUMN REBAR DETAIL | IFR | 2017-06-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182952 | T16182-CA01-P0UYC-182952 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR FRAMING PLAN | IFR | 2017-06-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182901 | T16182-CA00-P0UYC-182901 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR PLAN | IFR | 2017-05-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182983 | T16182-CA05-P0UYC-182983 | ADMINISTRATION & SOCIAL BUILDING - GROUND FLOOR PLUMBING PLAN | IFR | 2017-06-20 | 2017-09-20
S&A(18) | Structural & Architectural | 182905 | T16182-CA00-P0UYC-182905 | ADMINISTRATION & SOCIAL BUILDING - INTERIOR FINISH & DOOR / WINDOW SCHEDULE | IFR | 2017-05-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182954 | T16182-CA01-P0UYC-182954 | ADMINISTRATION & SOCIAL BUILDING - LINE FRAMING ELEVATION | IFR | 2017-06-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182904 | T16182-CA00-P0UYC-182904 | ADMINISTRATION & SOCIAL BUILDING - MAIN SECTION | IFR | 2017-05-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182981 | T16182-CA05-P0UYC-182981 | ADMINISTRATION & SOCIAL BUILDING - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-06-20 | 2017-09-20
S&A(18) | Structural & Architectural | 182982 | T16182-CA05-P0UYC-182982 | ADMINISTRATION & SOCIAL BUILDING - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-06-20 | 2017-09-20
S&A(18) | Structural & Architectural | 182953 | T16182-CA01-P0UYC-182953 | ADMINISTRATION & SOCIAL BUILDING - ROOF FRAMING PLAN | IFR | 2017-06-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182902 | T16182-CA00-P0UYC-182902 | ADMINISTRATION & SOCIAL BUILDING - ROOF PLAN | IFR | 2017-05-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182984 | T16182-CA05-P0UYC-182984 | ADMINISTRATION & SOCIAL BUILDING - ROOF PLUMBING PLAN | IFR | 2017-06-20 | 2017-09-20
S&A(18) | Structural & Architectural | 182955 | T16182-CA01-P0UYC-182955 | ADMINISTRATION & SOCIAL BUILDING - ROW FRAMING ELEVATION | IFR | 2017-06-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182903 | T16182-CA00-P0UYC-182903 | ADMINISTRATION & SOCIAL BUILDING - SIDE ELEVATION | IFR | 2017-05-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182958 | T16182-CA02-P0UYC-182958 | ADMINISTRATION & SOCIAL BUILDING - SLAB & MISC REBAR DETAIL | IFR | 2017-06-20 | 2017-08-20
S&A(18) | Structural & Architectural | 182906 | T16182-CA00-P0UYC-182906 | ADMINISTRATION & SOCIAL BUILDING - WALL SECTION | IFR | 2018-04-15 | 2018-06-15
|  | 860011 | T16182-DN05-P0ZEN-860011 | AGC
PT(12) | Mechanical | 127556 | T16182-XW01-P0SCA-127556 | AIR COMPRESSOR - AIR CHILLER - DATA SHEET | IFR | 2018-12-17 | 2019-02-28 |  |  |  | PKG-021-AC
PT(12) | Mechanical | 127555 | T16182-YD00-P0LCB-127555 | AIR COMPRESSOR - AIR CHILLER - GENERAL ARRANGEMENT DRAWING | IFR | 2018-12-17 | 2019-02-28 |  |  |  | PKG-021-AC
PT(12) | Mechanical | 127557 | T16182-XG02-P0SCA-127557 | AIR COMPRESSOR - AIR CHILLER - P&I DIAGRAM | IFR | 2018-12-17 | 2019-02-28 |  |  |  | PKG-021-AC
PT(12) | Mechanical | 127503 | T16182-XW01-P0SCA-127503 | AIR COMPRESSOR - AIR COMPRESSOR SPECIFICATION | IFR | 2017-04-26 | 2017-07-25 |  | O |  | PKG-021-AC
PT(12) | Mechanical | 127504 | T16182-XW01-P0SCA-127504 | AIR COMPRESSOR - AIR DRYER SPECIFICATION | IFI | 2017-04-26 |  |  | O |  | PKG-021-AC
PT(12) | Mechanical | 127506 | T16182-XW01-P0SCA-127506 | AIR COMPRESSOR - AIR FILTER SPECIFICATION | IFI | 2017-04-26 |  |  | O |  | PKG-021-AC
PT(12) | Mechanical | 127505 | T16182-XW01-P0SCA-127505 | AIR COMPRESSOR - AIR RECEIVER SPECIFICATION | IFI | 2017-04-26 |  |  | O |  | PKG-021-AC
PT(12) | Instrumentation & Control | 127514 | T16182-YF02-P0SCA-127514 | AIR COMPRESSOR - CONTROL DESCRIPTION (PHILOSOPHY) | IFI | 2017-05-26 |  |  | O | O | PKG-021-AC
PT(12) | Instrumentation & Control | 127518 | T16182-YF00-P0SCA-127518 | AIR COMPRESSOR - CONTROL LOGIC & LOOP DIAGRAM | IFI | 2017-05-26 |  |  | O |  | PKG-021-AC
PT(12) | Instrumentation & Control | 127517 | T16182-YL01-P0SCA-127517 | AIR COMPRESSOR - DATALINK INTERFACE IO LIST | IFI | 2017-05-26 |  |  | O |  | PKG-021-AC
PT(12) | Instrumentation & Control | 127546 | T16182-YD16-P0SCA-127546 | AIR COMPRESSOR - EMBEDDED CONDUIT LAYOUT FOR CONTROL CABLES (FROM MCP TO EQUIPMENT) | IFI | 2017-07-11 |  |  | O |  | PKG-021-AC
PT(12) | Civil | 127509 | T16182-XB00-P0SCA-127509 | AIR COMPRESSOR - FOUNDATION DRAWINGS | IFI | 2017-04-26 | 2017-07-07 |  | O |  | PKG-021-AC
PT(12) | Mechanical | 127501 | T16182-YD00-P0LCB-127501 | AIR COMPRESSOR - GENERAL ARRANGEMENT DRAWING | IFR | 2017-04-26 | 2017-06-25 | O | O |  | PKG-021-AC
PT(12) | Instrumentation & Control | 127520 | T16182-YL00-P0SCA-127520 | AIR COMPRESSOR - INSTRUMENT LIST | IFI | 2017-06-16 |  |  | O |  | PKG-021-AC
PT(12) | Instrumentation & Control | 127521 | T16182-CV03-P0SCA-127521 | AIR COMPRESSOR - INSTRUMENT SPECIFICATION | IFI | 2017-06-16 |  |  | O |  | PKG-021-AC
PT(12) | Instrumentation & Control | 127522 | T16182-YK00-P0SCA-127522 | AIR COMPRESSOR - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-06-16 | 2018-07-05 |  | O |  | PKG-021-AC
PT(12) | Mechanical | 127524 | T16182-XF00-P0SCA-127524 | AIR COMPRESSOR - NAME PLATE DRAWING | IFI | 2017-07-28 |  |  | O |  | PKG-021-AC
PT(12) | Mechanical | 127502 | T16182-XG02-P0SCA-127502 | AIR COMPRESSOR - P&I DIAGRAM | IFR | 2017-04-26 | 2017-06-15 | O | O | O | PKG-021-AC
PT(12) | Instrumentation & Control | 127516 | T16182-YL01-P0SCA-127516 | AIR COMPRESSOR - PLC HARDWIRED IO LIST | IFI | 2017-05-26 |  |  | O |  | PKG-021-AC
PT(12) | Instrumentation & Control | 127515 | T16182-YD05-P0SCA-127515 | AIR COMPRESSOR - PLC HMI GRAPHICS | IFI | 2017-06-25 |  |  | O |  | PKG-021-AC
PT(12) | Instrumentation & Control | 127523 | T16182-YR05-P0SCA-127523 | AIR COMPRESSOR - PLC PANEL DRAWING | IFI | 2017-06-02 |  |  | O |  | PKG-021-AC
PT(12) | Electrical | 127511 | T16182-YV02-P0SCA-127511 | AIR COMPRESSOR - SCHEMATIC & WIRING DIAGRAM | IFI | 2017-05-26 |  |  | O |  | PKG-021-AC
PT(12) | Electrical | 127510 | T16182-YU02-P0SCA-127510 | AIR COMPRESSOR - SINGLE LINE DIAGRAM | IFI | 2017-06-02 |  |  | O |  | PKG-021-AC
PT(12) | Mechanical | 127525 | T16182-XN00-P0SCA-127525 | AIR COMPRESSOR - VALVE LIST | IFI | 2017-06-13 |  |  | O |  | PKG-021-AC
PT(12) | Mechanical | 127526 | T16182-YT01-P0SCA-127526 | AIR COMPRESSOR - VALVE SPECIFICATION | IFI | 2017-06-13 |  |  | O |  | PKG-021-AC
PT(12) | Instrumentation & Control | 127548 | T16182-YV02-P0SCA-127548 | AIR COMPRESSOR – I&C CABLE INTERCONNECTION WIRING DIAGRAM | IFI | 2019-02-15 |  |  |  |  | PKG-021-AC
S&A(18) | Structural & Architectural | 182800 | T16182-CA06-P0UTF-182800 | AIR COMPRESSOR SHELTER - CALCULATION SHEET | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 182852 | T16182-CA01-P0UTF-182852 | AIR COMPRESSOR SHELTER - COLUMN ARRANGEMENT PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 182851 | T16182-CA01-P0UTF-182851 | AIR COMPRESSOR SHELTER - FOUNDATION ARRANGEMENT PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 182853 | T16182-CA01-P0UTF-182853 | AIR COMPRESSOR SHELTER - GROUND FLOOR FRAMING PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 182801 | T16182-CA00-P0UTF-182801 | AIR COMPRESSOR SHELTER - GROUND FLOOR PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 182855 | T16182-CA01-P0UTF-182855 | AIR COMPRESSOR SHELTER - LINE FRAMING ELEVATION | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 182804 | T16182-CA00-P0UTF-182804 | AIR COMPRESSOR SHELTER - MAIN SECTION | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 182857 | T16182-CA02-P0UTF-182857 | AIR COMPRESSOR SHELTER - REBAR DETAIL | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 182854 | T16182-CA01-P0UTF-182854 | AIR COMPRESSOR SHELTER - ROOF FRAMING PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 182802 | T16182-CA00-P0UTF-182802 | AIR COMPRESSOR SHELTER - ROOF PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 182856 | T16182-CA01-P0UTF-182856 | AIR COMPRESSOR SHELTER - ROW FRAMING ELEVATION | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 182803 | T16182-CA00-P0UTF-182803 | AIR COMPRESSOR SHELTER - SIDE ELEVATION | IFR | 2017-04-15 | 2017-06-15 |  | O
CV(17) | Civil | 171309 | T16182-VK02-P0ULC-171309 | AIR COOLED CONDENSER DRAIN WATER PUMP PIT DETAIL | IFR | 2017-06-15 | 2017-08-15
CV(17) | Civil | 171302 | T16182-XB02-P0ULC-171302 | AIR COOLED CONDENSER FOUNDATION LAYOUT | IFR | 2017-03-15 | 2017-05-31
CV(17) | Civil | 171303 | T16182-XB02-P0ULC-171303 | AIR COOLED CONDENSER FOUNDATION PLAN AND SECTION | IFR | 2017-03-15 | 2017-05-31
CV(17) | Civil | 171308 | T16182-VK02-P0ULC-171308 | AIR COOLED CONDENSER FOUNDATION R.C DETAIL | IFR | 2017-03-15 | 2017-05-31
MCH(13) | Mechanical | 134002 | T16182-XG07-P0SAL-134002 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135202 | T16182-XG07-P0SAQ-135202 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR AUX. LEB | IFR | 2018-01-18 | 2018-02-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133502 | T16182-XG07-P0SAC-133502 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-03-17 | 2017-05-01 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 135002 | T16182-XG07-P0SAM-135002 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | IFR | 2017-08-29 | 2017-10-28 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133702 | T16182-XG07-P0SAJ-133702 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-08-04 | 2017-10-03 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 134702 | T16182-XG07-P0SAF-134702 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FIRE BRIGADE | IFR | 2017-10-29 | 2017-12-28 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134902 | T16182-XG07-P0SAG-134902 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-06-14 | 2017-08-13 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 133802 | T16182-XG07-P0SAI-133802 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR GTG #1/2 LEB | IFR | 2017-03-26 | 2017-05-15 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 133902 | T16182-XG07-P0SAI-133902 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR GTG #3/4/5 LEB | IFR | 2017-04-30 | 2017-06-29 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134302 | T16182-XG07-P0SAE-134302 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR MAIN GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135402 | T16182-XG07-P0SAE-135402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR PIC GATE HOUSE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135302 | T16182-XG07-P0SAE-135302 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134602 | T16182-XG07-P0SAE-134602 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134502 | T16182-XG07-P0SAD-134502 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SECURITY BUILDING | IFR | 2018-07-17 | 2018-10-16 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135102 | T16182-XG07-P0SAV-135102 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | IFR | 2017-04-30 | 2017-06-30 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 134102 | T16182-XG07-P0SAR-134102 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ST #1 LEB | IFR | 2017-06-22 | 2017-08-21 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134202 | T16182-XG07-P0SAR-134202 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR ST #2 LEB | IFR | 2017-07-22 | 2017-09-20 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133402 | T16182-XG07-P0SAH-133402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR STEAM TURBINE BUILDING | IFR | 2017-06-14 | 2017-08-13 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134402 | T16182-XG07-P0SAN-134402 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR SUPPORT BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133602 | T16182-XG07-P0SAK-133602 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-04-15 | 2017-06-14 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 134802 | T16182-XG07-P0SAB-134802 | AIR FLOW DIAGRAM OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2017-09-14 | 2017-11-13 |  |  |  | PKG-041-HVAC
TG-MCH(22) | Mechanical | 220047 | T16182-VE01-P6MAA-220047 | ALLOWABLE LOADINGS AND DISPLACEMENTS | IFI | 2017-03-17 |  |  |  |  | PKG-040-STG
MCH(13) | Mechanical | 130502 | T16182-YD00-P0STG-130502 | ARRANGEMENT DRAWING FOR CHEMICAL LABORATORY EQUIPMENT | IFR | 2017-08-04 | 2017-11-16 |  |  |  | PKG-029-CLAB
CV(17) | Civil | 173802 | T16182-XB02-P0GHC-173802 | ATM FLASH TANK & DRAIN PUMP PIT DETAIL | IFR | 2017-11-30 | 2018-02-02
S&A(18) | Structural & Architectural | 186800 | T16182-CA06-P0UBA-186800 | AUX. LEB - CALCULATION | IFR | 2017-11-20 | 2017-12-20
S&A(18) | Structural & Architectural | 186855 | T16182-CA02-P0UBA-186855 | AUX. LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-11-20 | 2017-12-20
S&A(18) | Structural & Architectural | 186851 | T16182-CA01-P0UBA-186851 | AUX. LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-11-20 | 2017-12-20
S&A(18) | Structural & Architectural | 186854 | T16182-CA02-P0UBA-186854 | AUX. LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | IFR | 2017-11-20 | 2017-12-20
S&A(18) | Structural & Architectural | 186852 | T16182-CA01-P0UBA-186852 | AUX. LEB - GROUND FLOOR FRAMING PLAN & ROOF FRAMING PLAN | IFR | 2017-11-20 | 2017-12-20
S&A(18) | Structural & Architectural | 186801 | T16182-CA00-P0UBA-186801 | AUX. LEB - GROUND FLOOR PLAN & ROOF PLAN | IFR | 2017-11-20 | 2017-12-20
S&A(18) | Structural & Architectural | 186853 | T16182-CA01-P0UBA-186853 | AUX. LEB - LINE & ROW FRAMING ELEVATION | IFR | 2017-11-20 | 2017-12-20
S&A(18) | Structural & Architectural | 186803 | T16182-CA00-P0UBA-186803 | AUX. LEB - MAIN SECTION | IFR | 2017-11-20 | 2017-12-20
S&A(18) | Structural & Architectural | 186802 | T16182-CA00-P0UBA-186802 | AUX. LEB - SIDE WALL ELEVATION | IFR | 2017-11-20 | 2017-12-20
MCH(13) | Instrumentation & Control | 139043 | T16182-YT10-P0CYE-139043 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136743 | T16182-YT10-P0CYE-136743 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | IFI | 2018-01-20 |  |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137643 | T16182-YT10-P0CYE-137643 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139443 | T16182-YT10-P0CYE-139443 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136843 | T16182-YT10-P0CYE-136843 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | IFI | 2018-01-20 |  |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136943 | T16182-YT10-P0CYE-136943 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139143 | T16182-YT10-P0CYE-139143 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | IFI | 2018-11-17 |  |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138643 | T16182-YT10-P0CYE-138643 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST BUILDING | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138743 | T16182-YT10-P0CYE-138743 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST#1 LEB | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138843 | T16182-YT10-P0CYE-138843 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR ST#2 LEB | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137943 | T16182-YT10-P0CYE-137943 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139543 | T16182-YT10-P0CYE-139543 | BATTERY CALCULATION OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFI | 2018-01-20 |  |  |  |  | PKG-030-FF
GN-SYS(26) | Mechanical | 260002 | T16182-YD00-P0MKW-260002 | BEARING OIL DRAIN ENLARGEMENT OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG
|  | 860017 | T16182-DN05-P0ZEN-860017 | BLACK START-UP TEST
I&C(16) | Instrumentation & Control | 165531 | T16182-YB03-P0ZEN-165531 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM - GENERAL INFORMATION | IFI | 2017-09-15 | 2017-12-14 |  | O
I&C(16) | Instrumentation & Control | 165539 | T16182-YB03-P0ZEN-165539 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR CLOSED COOLING WATER SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O
I&C(16) | Instrumentation & Control | 165545 | T16182-YB03-P0ZEN-165545 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR COMPRESSED AIR SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O
I&C(16) | Instrumentation & Control | 165537 | T16182-YB03-P0ZEN-165537 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR CONDENSATE SYSTEM | IFI | 2017-09-15 | 2017-12-14
I&C(16) | Instrumentation & Control | 165540 | T16182-YB03-P0ZEN-165540 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O
I&C(16) | Instrumentation & Control | 165547 | T16182-YB03-P0ZEN-165547 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR ELECTRICAL SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O
I&C(16) | Instrumentation & Control | 165538 | T16182-YB03-P0ZEN-165538 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR FEEDWATER SYSTEM | IFI | 2017-09-15 | 2017-12-14
I&C(16) | Instrumentation & Control | 165546 | T16182-YB03-P0ZEN-165546 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR FUEL GAS SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O
I&C(16) | Instrumentation & Control | 165542 | T16182-YB03-P0ZEN-165542 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | IFI | 2017-09-15 | 2017-12-14
I&C(16) | Instrumentation & Control | 165541 | T16182-YB03-P0ZEN-165541 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | IFI | 2017-09-15 | 2017-12-14
I&C(16) | Instrumentation & Control | 165532 | T16182-YB03-P0ZEN-165532 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR HP STEAM SYSTEM | IFI | 2017-09-15 | 2017-12-14
I&C(16) | Instrumentation & Control | 165548 | T16182-YB03-P0ZEN-165548 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | IFI | 2017-12-15 | 2018-03-15 |  | O
I&C(16) | Instrumentation & Control | 165533 | T16182-YB03-P0ZEN-165533 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR IP STEAM SYSTEM | IFI | 2017-09-15 | 2017-12-14
I&C(16) | Instrumentation & Control | 165534 | T16182-YB03-P0ZEN-165534 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR LP STEAM SYSTEM | IFI | 2017-09-15 | 2017-12-14
I&C(16) | Instrumentation & Control | 165544 | T16182-YB03-P0ZEN-165544 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR POTABLE WATER DISTRIBUTION SYSTEM | IFI | 2017-09-15 | 2017-12-14
I&C(16) | Instrumentation & Control | 165543 | T16182-YB03-P0ZEN-165543 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O
I&C(16) | Instrumentation & Control | 165535 | T16182-YB03-P0ZEN-165535 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR PROCESS STEAM SYSTEM | IFI | 2017-09-15 | 2017-12-14 |  | O
I&C(16) | Instrumentation & Control | 165536 | T16182-YB03-P0ZEN-165536 | BOP - I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR STEAM DRAIN SYSTEM | IFI | 2017-09-15 | 2017-12-14
I&C(16) | Instrumentation & Control | 165551 | T16182-YL16-P0ZEN-165551 | BOP - I&C CABLE SCHEDULE - GENERAL INFORMATION | IFI | 2017-10-15 | 2018-01-13 |  | O
I&C(16) | Instrumentation & Control | 165559 | T16182-YL16-P0ZEN-165559 | BOP - I&C CABLE SCHEDULE FOR CLOSED COOLING WATER SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O
I&C(16) | Instrumentation & Control | 165565 | T16182-YL16-P0ZEN-165565 | BOP - I&C CABLE SCHEDULE FOR COMPRESSED AIR SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O
I&C(16) | Instrumentation & Control | 165557 | T16182-YL16-P0ZEN-165557 | BOP - I&C CABLE SCHEDULE FOR CONDENSATE SYSTEM | IFI | 2017-10-15 | 2018-01-13
I&C(16) | Instrumentation & Control | 165560 | T16182-YL16-P0ZEN-165560 | BOP - I&C CABLE SCHEDULE FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O
I&C(16) | Instrumentation & Control | 165567 | T16182-YL16-P0ZEN-165567 | BOP - I&C CABLE SCHEDULE FOR ELECTRICAL SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O
I&C(16) | Instrumentation & Control | 165558 | T16182-YL16-P0ZEN-165558 | BOP - I&C CABLE SCHEDULE FOR FEEDWATER SYSTEM | IFI | 2017-10-15 | 2018-01-13
I&C(16) | Instrumentation & Control | 165566 | T16182-YL16-P0ZEN-165566 | BOP - I&C CABLE SCHEDULE FOR FUEL GAS SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O
I&C(16) | Instrumentation & Control | 165562 | T16182-YL16-P0ZEN-165562 | BOP - I&C CABLE SCHEDULE FOR GT PERFORMANCE HEATER SYSTEM | IFI | 2017-10-15 | 2018-01-13
I&C(16) | Instrumentation & Control | 165561 | T16182-YL16-P0ZEN-165561 | BOP - I&C CABLE SCHEDULE FOR GT ROTOR COOLING AIR SYSTEM | IFI | 2017-10-15 | 2018-01-13
I&C(16) | Instrumentation & Control | 165552 | T16182-YL16-P0ZEN-165552 | BOP - I&C CABLE SCHEDULE FOR HP STEAM SYSTEM | IFI | 2017-10-15 | 2018-01-13
I&C(16) | Instrumentation & Control | 165568 | T16182-YL16-P0ZEN-165568 | BOP - I&C CABLE SCHEDULE FOR INTERFACE WITH OTHER CONTROL SYSTEM | IFI | 2017-12-15 | 2018-03-15 |  | O
I&C(16) | Instrumentation & Control | 165553 | T16182-YL16-P0ZEN-165553 | BOP - I&C CABLE SCHEDULE FOR IP STEAM SYSTEM | IFI | 2017-10-15 | 2018-01-13
I&C(16) | Instrumentation & Control | 165554 | T16182-YL16-P0ZEN-165554 | BOP - I&C CABLE SCHEDULE FOR LP STEAM SYSTEM | IFI | 2017-10-15 | 2018-01-13
I&C(16) | Instrumentation & Control | 165564 | T16182-YL16-P0ZEN-165564 | BOP - I&C CABLE SCHEDULE FOR POTABLE WATER DISTRIBUTION SYSTEM | IFI | 2017-10-15 | 2018-01-13
I&C(16) | Instrumentation & Control | 165563 | T16182-YL16-P0ZEN-165563 | BOP - I&C CABLE SCHEDULE FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O
I&C(16) | Instrumentation & Control | 165555 | T16182-YL16-P0ZEN-165555 | BOP - I&C CABLE SCHEDULE FOR PROCESS STEAM SYSTEM | IFI | 2017-10-15 | 2018-01-13 |  | O
I&C(16) | Instrumentation & Control | 165556 | T16182-YL16-P0ZEN-165556 | BOP - I&C CABLE SCHEDULE FOR STEAM DRAIN SYSTEM | IFI | 2017-10-15 | 2018-01-13
I&C(16) | Instrumentation & Control | 165311 | T16182-YK00-P0ZEN-165311 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - GENERAL NOTE | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165313 | T16182-YK00-P0ZEN-165313 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - MATERIAL LISTS | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165312 | T16182-YK00-P0ZEN-165312 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS - SYMBOL & LEGEND | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165317 | T16182-YK00-P0ZEN-165317 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR DIFF. PRESSURE TRANSMITTER | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165314 | T16182-YK00-P0ZEN-165314 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR FLOW TRANSMITTER | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165315 | T16182-YK00-P0ZEN-165315 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR LEVEL TRANSMITTER | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165322 | T16182-YK00-P0ZEN-165322 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PNEUMATIC CONTROL VALVES | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165318 | T16182-YK00-P0ZEN-165318 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PRESSURE GAUGE | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165316 | T16182-YK00-P0ZEN-165316 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR PRESSURE TRANSMITTER | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165323 | T16182-YK00-P0ZEN-165323 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR STANCHION & RACK | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165320 | T16182-YK00-P0ZEN-165320 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEMPERATURE GAUGE | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165319 | T16182-YK00-P0ZEN-165319 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEMPERATURE TRANSMITTER (RTD/TC) | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165321 | T16182-YK00-P0ZEN-165321 | BOP - INSTRUMENT INSTALLATION DETAIL DRAWINGS FOR TEST WELL | IFI | 2017-02-01 | 2017-07-01 |  | O
I&C(16) | Instrumentation & Control | 165508 | T16182-YD02-P0ZEN-165508 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-08-01 | 2018-10-30 |  | O
I&C(16) | Instrumentation & Control | 165517 | T16182-YD02-P0ZEN-165517 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR AIR COMPRESSOR SHELTER | IFI | 2018-02-04 | 2018-05-05 |  | O
PT(12) | Mechanical | 123054 | T16182-YD00-P0MAG-123054 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR AIR COOLED CONDENSER | IFI | 2019-01-14 |  |  |  |  | PKG-013-ACC
I&C(16) | Instrumentation & Control | 165501 | T16182-YD02-P0ZEN-165501 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-14 | 2017-12-13 |  | O
I&C(16) | Instrumentation & Control | 165524 | T16182-YD02-P0ZEN-165524 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CHEMICAL DOSING SHELTER FOR HRSG | IFI | 2018-02-19 | 2018-05-20 |  | O
I&C(16) | Instrumentation & Control | 165523 | T16182-YD02-P0ZEN-165523 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | IFI | 2018-06-04 | 2018-09-02 |  | O
I&C(16) | Instrumentation & Control | 165522 | T16182-YD02-P0ZEN-165522 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR CPP & CPP REGENERATION BUILDING | IFI | 2018-04-02 | 2018-07-01 |  | O
I&C(16) | Instrumentation & Control | 165518 | T16182-YD02-P0ZEN-165518 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2018-01-29 | 2018-04-29 |  | O
I&C(16) | Instrumentation & Control | 165507 | T16182-YD02-P0ZEN-165507 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FGS ELECTRICAL BUILDING | IFI | 2018-02-04 | 2018-05-05 |  | O
I&C(16) | Instrumentation & Control | 165514 | T16182-YD02-P0ZEN-165514 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FIRE BRIGADE | IFI | 2018-09-13 | 2018-12-12 |  | O
I&C(16) | Instrumentation & Control | 165519 | T16182-YD02-P0ZEN-165519 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR FIRE WATER PUMP HOUSE & FIN FAN COOLER (CPP) | IFI | 2017-09-07 | 2017-12-06 |  | O
I&C(16) | Instrumentation & Control | 165502 | T16182-YD02-P0ZEN-165502 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR GTG #1,2 LEB | IFI | 2017-10-17 | 2018-01-15 |  | O
I&C(16) | Instrumentation & Control | 165503 | T16182-YD02-P0ZEN-165503 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR GTG #3,4,5 LEB | IFI | 2018-01-22 | 2018-04-22 |  | O
I&C(16) | Instrumentation & Control | 165516 | T16182-YD02-P0ZEN-165516 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR H2, CO2, N2 STORAGE SHELTER | IFI | 2017-09-24 | 2017-12-23 |  | O
I&C(16) | Instrumentation & Control | 165510 | T16182-YD02-P0ZEN-165510 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR MAIN GATE HOUSE AREA | IFI | 2018-05-21 | 2018-08-19 |  | O
I&C(16) | Instrumentation & Control | 165509 | T16182-YD02-P0ZEN-165509 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR SECURITY BUILDING | IFI | 2019-01-06 | 2019-04-06 |  | O
I&C(16) | Instrumentation & Control | 165504 | T16182-YD02-P0ZEN-165504 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST #1 LEB | IFI | 2018-05-09 | 2018-08-07 |  | O
I&C(16) | Instrumentation & Control | 165505 | T16182-YD02-P0ZEN-165505 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST #2 LEB | IFI | 2018-06-07 | 2018-09-05 |  | O
I&C(16) | Instrumentation & Control | 165506 | T16182-YD02-P0ZEN-165506 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR ST BUILDING | IFI | 2018-05-09 | 2018-08-07 |  | O
I&C(16) | Instrumentation & Control | 165521 | T16182-YD02-P0ZEN-165521 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WATER TREATMENT BUILDING | IFI | 2017-09-28 | 2017-12-27 |  | O
I&C(16) | Instrumentation & Control | 165515 | T16182-YD02-P0ZEN-165515 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WORKSHOP & STORAGE BUILDING | IFI | 2018-04-18 | 2018-07-17 |  | O
I&C(16) | Instrumentation & Control | 165520 | T16182-YD02-P0ZEN-165520 | BOP EXPOSED CONDUIT LAYOUT AND INSTRUMENT LOCATION DRAWING FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-12-26 | 2018-03-26 |  | O
I&C(16) | Instrumentation & Control | 165573 | T16182-YD02-P0ZEN-165573 | BOP EXPOSED CONDUIT LAYOUT FOR CONDENSATE STORAGE TANK AREA | IFI | 2017-10-19 | 2018-01-17
I&C(16) | Instrumentation & Control | 165572 | T16182-YD02-P0ZEN-165572 | BOP EXPOSED CONDUIT LAYOUT FOR DEMI WATER STORAGE TANK AREA | IFI | 2017-08-28 | 2017-11-26
I&C(16) | Instrumentation & Control | 165575 | T16182-YD02-P0ZEN-165575 | BOP EXPOSED CONDUIT LAYOUT FOR FIN FAN COOLER(CCW) & CCW PUMP AREA | IFI | 2018-01-25 | 2018-04-25
I&C(16) | Instrumentation & Control | 165525 | T16182-YD02-P0ZEN-165525 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #1 | IFI | 2017-11-05 | 2018-02-03
I&C(16) | Instrumentation & Control | 165526 | T16182-YD02-P0ZEN-165526 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #2 | IFI | 2017-12-05 | 2018-03-05
I&C(16) | Instrumentation & Control | 165527 | T16182-YD02-P0ZEN-165527 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #3 | IFI | 2018-01-02 | 2018-04-02
I&C(16) | Instrumentation & Control | 165528 | T16182-YD02-P0ZEN-165528 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #4 | IFI | 2018-02-16 | 2018-05-17
I&C(16) | Instrumentation & Control | 165529 | T16182-YD02-P0ZEN-165529 | BOP EXPOSED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #5 | IFI | 2018-04-10 | 2018-07-09
I&C(16) | Instrumentation & Control | 165577 | T16182-YD02-P0ZEN-165577 | BOP EXPOSED CONDUIT LAYOUT FOR PIPE RACK AREA | IFI | 2018-05-09 | 2018-08-07
I&C(16) | Instrumentation & Control | 165571 | T16182-YD02-P0ZEN-165571 | BOP EXPOSED CONDUIT LAYOUT FOR POTABLE STORAGE WATER TANK & FIRE WATER TANK AREA | IFI | 2017-08-20 | 2017-11-18
I&C(16) | Instrumentation & Control | 165576 | T16182-YD02-P0ZEN-165576 | BOP EXPOSED CONDUIT LAYOUT FOR STG TRANSFORMER AREA #1,#2 | IFI | 2018-05-09 | 2018-08-07
GN-MCH(25) | Mechanical | 250007 | T16182-YK10-P0MKA-250007 | BRUSH HOLDER RIGGING ASSEMBLY | IFI | 2017-08-17 |  |  |  |  | PKG-040-STG
CV(17) | Civil | 172202 | T16182-XB02-P0UBN-172202 | BSDG FOUNDATION PLAN & SECTION | IFR | 2017-09-04 | 2017-11-03 |  | O
CV(17) | Civil | 172203 | T16182-VK02-P0UBN-172203 | BSDG FOUNDATION R.C DETAIL | IFR | 2017-09-04 | 2017-11-03 |  | O
PS(11) | Mechanical | 110053 | T16182-XW03-P0MJ-110053 | BSEDG - CALCULATION | IFR | 2017-02-28 | 2017-05-29 |  | O |  | PKG-007-BSDG
PS(11) | Instrumentation & Control | 110511 | T16182-YF00-P0MJ-110511 | BSEDG - CONTROL LOGIC DIAGRAM | IFR | 2017-05-15 | 2017-08-17 |  |  |  | PKG-007-BSDG
PS(11) | Electrical | 110561 | T16182-YM02-P0MJ-110561 | BSEDG - CONTROL PANEL OUTLINE DRAWING | IFI | 2018-06-12 |  |  |  |  | PKG-007-BSDG
PS(11) | Mechanical | 110508 | T16182-YT01-P0MJ-110508 | BSEDG - DATA SHEET | IFR | 2017-04-30 | 2017-07-31 |  | O |  | PKG-007-BSDG
PS(11) | Electrical | 110512 | T16182-YE00-P0MJ-110512 | BSEDG - EMBEDDED CONDUIT LAYOUT | IFI | 2017-06-30 | 2017-10-11 |  | O |  | PKG-007-BSDG
PS(11) | Mechanical | 110504 | T16182-YD00-P0MJ-110504 | BSEDG - GENERAL ARRANGEMENT DRAWING | IFR | 2017-04-30 | 2017-07-31 | O | O |  | PKG-007-BSDG
PS(11) | Mechanical | 110506 | T16182-YK08-P0MJ-110506 | BSEDG - OUTLINE DRAWING | IFR | 2017-04-30 | 2017-07-31 |  | O |  | PKG-007-BSDG
PS(11) | Mechanical | 110505 | T16182-XG02-P0MJ-110505 | BSEDG - P&I DIAGRAM | IFR | 2017-04-30 | 2017-07-31 | O | O |  | PKG-007-BSDG
PS(11) | Mechanical | 110509 | T16182-XG01-P0MJ-110509 | BSEDG - PIPING ISOMETRIC DRAWING | IFI | 2017-04-30 | 2017-06-30 |  | O |  | PKG-007-BSDG
PS(11) | Electrical | 110568 | T16182-YT10-P0MJ-110568 | BSEDG - PROTECTION RELAY SETTING REPORT | IFI | 2018-06-12 |  |  |  |  | PKG-007-BSDG
PS(11) | Electrical | 110564 | T16182-XG11-P0MJ-110564 | BSEDG - SCHEMATIC DIAGRAM | IFI | 2018-06-12 |  |  |  |  | PKG-007-BSDG
PS(11) | Electrical | 110507 | T16182-YU02-P0MJ-110507 | BSEDG - SINGLE LINE DIAGRAM | IFI | 2017-04-30 |  |  | O |  | PKG-007-BSDG
PS(11) | Mechanical | 110510 | T16182-XS00-P0MJ-110510 | BSEDG - SYSTEM DESCRIPTION | IFR | 2017-05-15 | 2017-08-17 | O | O |  | PKG-007-BSDG
PS(11) | Electrical | 110578 | T16182-YM02-P0MJ-110578 | BSEDG – MV SWGR DRAWING | IFI | 2018-06-21 |  |  |  |  | PKG-007-BSDG
S&A(18) | Structural & Architectural | 050001 | T16182-BV02-P0ZEN-050001 | BUILDING RISK ASSESSMENT | IFI | 2017-05-25 |  | O
MCH(13) | Instrumentation & Control | 136618 | T16182-YT01-P0CYE-136618 | CABLE AND BULK MATERIAL - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
PT(12) | Instrumentation & Control | 124048 | T16182-YS02-P0EKG-124048 | CABLE CONNECTION DIAGRAM | Internal
MCH(13) | Electrical | 130215 | T16182-YE00-P0LD-130215 | CABLE TRAY LAYOUT DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2017-09-01 | 2018-11-14 |  |  |  | PKG-026-CPP
MCH(13) | Electrical | 130015 | T16182-YE00-P0GCF-130015 | CABLE TRAY LAYOUT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-05-05 | 2018-03-30 |  | O |  | PKG-025-WT
EL(15) | Electrical | 152014 | T16182-YD04-P0ZEN-152014 | CABLE TRAY LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-06-08 | 2018-08-07
EL(15) | Electrical | 152016 | T16182-YD04-P0ZEN-152016 | CABLE TRAY LAYOUT FOR AUX LEB | IFI | 2018-01-26 | 2018-04-26
EL(15) | Electrical | 152005 | T16182-YD04-P0ZEN-152005 | CABLE TRAY LAYOUT FOR CENTRAL CONTROL BUILDING | IFI | 2017-07-18 | 2017-09-16 |  | O
EL(15) | Electrical | 152019 | T16182-YD04-P0ZEN-152019 | CABLE TRAY LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2018-01-26 | 2018-04-26
EL(15) | Electrical | 152012 | T16182-YD04-P0ZEN-152012 | CABLE TRAY LAYOUT FOR FGS ELECTRICAL BUILDING | IFI | 2017-12-06 | 2018-02-04 |  | O
EL(15) | Electrical | 152006 | T16182-YD04-P0ZEN-152006 | CABLE TRAY LAYOUT FOR GTG #1,2 LEB | IFI | 2017-08-24 | 2017-10-23 |  | O
EL(15) | Electrical | 152007 | T16182-YD04-P0ZEN-152007 | CABLE TRAY LAYOUT FOR GTG #3,4,5 LEB | IFI | 2017-11-23 | 2018-01-22
EL(15) | Electrical | 152017 | T16182-YD04-P0ZEN-152017 | CABLE TRAY LAYOUT FOR GTG PCC #1,2,3,4,5 | IFI | 2018-01-26 | 2018-04-26
EL(15) | Electrical | 152015 | T16182-YD04-P0ZEN-152015 | CABLE TRAY LAYOUT FOR PIPE RACK | IFI | 2017-09-07 | 2017-11-06
EL(15) | Electrical | 152020 | T16182-YD04-P0ZEN-152020 | CABLE TRAY LAYOUT FOR SECURITY BUILDING | IFI | 2019-02-28 | 2019-05-28
EL(15) | Electrical | 152008 | T16182-YD04-P0ZEN-152008 | CABLE TRAY LAYOUT FOR ST #1 LEB | IFI | 2017-11-03 | 2018-01-02
EL(15) | Electrical | 152009 | T16182-YD04-P0ZEN-152009 | CABLE TRAY LAYOUT FOR ST #2 LEB | IFI | 2017-12-06 | 2018-02-04
EL(15) | Electrical | 152010 | T16182-YD04-P0ZEN-152010 | CABLE TRAY LAYOUT FOR ST BUILDING | IFI | 2018-04-19 | 2018-06-18
EL(15) | Electrical | 152018 | T16182-YD04-P0ZEN-152018 | CABLE TRAY LAYOUT FOR TANK SLEEPER AREA | IFI | 2018-01-08 | 2018-04-08
EL(15) | Electrical | 152011 | T16182-YD04-P0ZEN-152011 | CABLE TRAY LAYOUT FOR WATER TREATMENT BUILDING | IFI | 2017-07-20 | 2017-09-18
EL(15) | Electrical | 152013 | T16182-YD04-P0ZEN-152013 | CABLE TRAY LAYOUT FOR WORKSHOP & STORAGE BUILDING | IFI | 2018-02-22 | 2018-04-23
CV(17) | Civil | 171301 | T16182-VE04-P0ULC-171301 | CALCULATION OF AIR COOLED CONDENSER FOUNDATION | IFR | 2017-03-15 | 2017-05-31
CV(17) | Civil | 173801 | T16182-VE04-P0GHC-173801 | CALCULATION OF ATM FLASH TANK & DRAIN PUMP PIT | IFR | 2017-11-30 | 2018-02-02
CV(17) | Civil | 172201 | T16182-VE04-P0UBN-172201 | CALCULATION OF BSDG FOUNDATION | IFR | 2017-09-04 | 2017-11-03 |  | O
CV(17) | Civil | 171201 | T16182-VE04-P0ULX-171201 | CALCULATION OF CCW FIN FAN COOLER FOUNDATION | IFR | 2017-05-24 | 2017-08-06
CV(17) | Civil | 173601 | T16182-VE04-P0GKC-173601 | CALCULATION OF CHILLED WATER STORAGE TANK FOUNDATION | IFR | 2017-11-24 | 2018-02-02
CV(17) | Civil | 172501 | T16182-VE04-P0ULC-172501 | CALCULATION OF CONDENSATE WATER TANK FOUNDATION | IFR | 2017-03-31 | 2017-05-31
CV(17) | Civil | 171221 | T16182-VE04-P0ULX-171221 | CALCULATION OF CPP FIN FAN COOLER FOUNDATION | IFR | 2017-07-31 | 2017-10-31 |  | O
CV(17) | Civil | 172541 | T16182-VE04-P0UGD-172541 | CALCULATION OF DEMINERALIZED WATER TANK FOUNDATION | IFR | 2017-03-31 | 2017-05-31 |  | O
CV(17) | Civil | 172601 | T16182-VE04-P0UAZ-172601 | CALCULATION OF EHV CABLE TRENCH & DIRECT BURIED CABLE | IFR | 2017-04-11 | 2017-07-02 |  | O
CV(17) | Civil | 172701 | T16182-VE04-P0UZT-172701 | CALCULATION OF ELECTRICAL DUCT BANK MANHOLE | IFR | 2017-07-01 | 2017-09-15
CV(17) | Civil | 172011 | T16182-VE04-P8UTH-172011 | CALCULATION OF FD FAN AND MISC. FOUNDATION | IFR | 2017-04-01 | 2017-07-01 |  | O
CV(17) | Civil | 172581 | T16182-VE04-P0ULX-172581 | CALCULATION OF GENERAL SERVICE PUMP FOUNDATION | IFR | 2017-08-16 | 2017-10-20
CV(17) | Civil | 171601 | T16182-VE04-P0ULX-171601 | CALCULATION OF GT PERFORMANCE HEATER FOUNDATION | IFR | 2017-08-18 | 2017-11-18 |  | O
CV(17) | Civil | 172151 | T16182-VE04-P0UAG-172151 | CALCULATION OF GTG STEP UP & UNIT AUX. TRANSFORMER FOUNDATION | IFR | 2017-04-25 | 2017-07-24 |  | O
CV(17) | Civil | 171802 | T16182-VE04-P0UHA-171802 | CALCULATION OF HRSG FOUNDATION | IFR | 2017-04-27 | 2017-07-26
CV(17) | Civil | 171801 | T16182-VE04-P0UHA-171801 | CALCULATION OF HRSG FOUNDATION PILING | IFR | 2017-01-25 | 2017-04-25
CV(17) | Civil | 171819 | T16182-VE04-P0UHA-171819 | CALCULATION OF HRSG MISC. FOUNDATION | IFR | 2017-06-16 | 2017-09-14
CV(17) | Civil | 172401 | T16182-VE04-P0BAA-172401 | CALCULATION OF IPB FOUNDATION | IFR | 2017-04-23 | 2017-07-22
CV(17) | Civil | 173001 | T16182-VE04-P0UZT-173001 | CALCULATION OF LIGHTING POLE FOUNDATION | IFR | 2018-04-13 | 2018-07-13
CV(17) | Civil | 171401 | T16182-VE04-P0UNX-171401 | CALCULATION OF PIPE SLEEPER FOUNDATION | IFR | 2017-05-05 | 2017-07-04
CV(17) | Civil | 172521 | T16182-VE04-P0UGF-172521 | CALCULATION OF POTABLE & FIRE FIGHTING WATER TANK FOUNDATION | IFR | 2017-03-31 | 2017-05-31 |  | O
CV(17) | Civil | 172561 | T16182-VE04-P0UGG-172561 | CALCULATION OF POTABLE WATER TANK FOUNDATION | IFR | 2017-03-31 | 2017-05-31 |  | O
CV(17) | Civil | 172001 | T16182-VE04-P8UTH-172001 | CALCULATION OF RESERVE BOILER FOUNDATION | IFR | 2017-02-28 | 2017-05-29
CV(17) | Civil | 172901 | T16182-VE04-P0UZA-172901 | CALCULATION OF ROAD AND PAVING | IFR | 2017-07-01 | 2018-08-29
CV(17) | Civil | 171102 | T16182-VE04-P0MPA-171102 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION DYNAMIC ANALYSIS | IFR | 2017-03-28 | 2017-06-11
CV(17) | Civil | 171101 | T16182-VE04-P0MPA-171101 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION PILE DESIGN | IFR | 2017-02-28 | 2017-05-14
CV(17) | Civil | 171103 | T16182-VE04-P0MPA-171103 | CALCULATION OF STEAM TURBINE GENERATOR FOUNDATION R.C DESIGN | IFR | 2017-06-28 | 2017-09-11
CV(17) | Civil | 172101 | T16182-VE04-P0UAG-172101 | CALCULATION OF STG STEP - UP AND EXCITATION TRANSFORMER FOUNDATION | IFR | 2017-04-25 | 2017-07-24
CV(17) | Civil | 173301 | T16182-VE04-P0GUB-173301 | CALCULATION OF STORMWATER DRAINAGE | IFR | 2017-07-01 | 2018-08-29
CV(17) | Civil | 172801 | T16182-VE04-P0GUC-172801 | CALCULATION OF STORMWATER POND | IFR | 2017-06-30 | 2017-08-29
CV(17) | Civil | 173401 | T16182-VE04-P0GQB-173401 | CALCULATION OF WASTE WATER DRAINAGE OVERALL LAYOUT | IFR | 2017-12-31 | 2018-03-31 |  | O
CV(17) | Civil | 171701 | T16182-VE04-P0UEM-171701 | CALCULATION OF WASTE WATER TREATMENT PLANT | IFR | 2017-03-15 | 2017-05-16 |  | O
MCH(13) | Mechanical | 130304 | T16182-XW03-P0QC-130304 | CALCULATION SHEET FOR CHEMICAL DOSING SYSTEM | IFI | 2017-10-05 |  |  |  |  | PKG-027-CDS
MCH(13) | Mechanical | 130205 | T16182-XW03-P0LD-130205 | CALCULATION SHEET FOR CONDENSATE POLISHING PLANT | IFR | 2017-06-03 | 2017-09-15 |  |  |  | PKG-026-CPP
MCH(13) | Mechanical | 130104 | T16182-XW03-P0GNR-130104 | CALCULATION SHEET FOR WASTE WATER TREATMENT PLANT | IFR | 2017-03-06 | 2017-06-04 |  | O |  | PKG-025-WT
MCH(13) | Mechanical | 130005 | T16182-XW03-P0GCF-130005 | CALCULATION SHEET FOR WATER TREATMENT PLANT | IFR | 2017-02-04 | 2017-05-05 |  | O |  | PKG-025-WT
TK(40) | Electrical | 411001 | T16182-CV03-P0PUR-411001 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR CONDENSATE STORAGE TANK | IFR | 2017-03-10 | 2017-05-10 |  | O
TK(40) | Electrical | 411011 | T16182-CV03-P0PUR-411011 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR DEMINERALIZED WATER STORAGE TANK | IFR | 2017-03-10 | 2017-05-10 |  | O
TK(40) | Electrical | 411021 | T16182-CV03-P0PUR-411021 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | IFR | 2017-03-10 | 2017-05-10 |  | O
TK(40) | Electrical | 411031 | T16182-CV03-P0PUR-411031 | CATHODIC PROTECTION SYSTEM TECHNICAL SPECIFICATION FOR POTABLE WATER STORAGE TANK | IFR | 2017-03-10 | 2017-05-10 |  | O
MCH(13) | Instrumentation & Control | 139044 | T16182-XG02-P0CYE-139044 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136744 | T16182-XG02-P0CYE-136744 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2018-01-20 | 2018-04-20 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137644 | T16182-XG02-P0CYE-137644 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139444 | T16182-XG02-P0CYE-139444 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136844 | T16182-XG02-P0CYE-136844 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | IFR | 2018-01-20 | 2018-04-20 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136944 | T16182-XG02-P0CYE-136944 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139144 | T16182-XG02-P0CYE-139144 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | IFR | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138644 | T16182-XG02-P0CYE-138644 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST BUILDING | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138744 | T16182-XG02-P0CYE-138744 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST#1 LEB | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138844 | T16182-XG02-P0CYE-138844 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR ST#2 LEB | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137944 | T16182-XG02-P0CYE-137944 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139544 | T16182-XG02-P0CYE-139544 | CAUSE & EFFECT MATRIX OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
CV(17) | Civil | 171202 | T16182-XB02-P0ULX-171202 | CCW FIN FAN COOLER FOUNDATION LAYOUT | IFR | 2017-05-24 | 2017-08-06 |  | O
CV(17) | Civil | 171203 | T16182-XB02-P0ULX-171203 | CCW FIN FAN COOLER FOUNDATION PLAN AND SECTION | IFR | 2017-05-24 | 2017-08-06 |  | O
S&A(18) | Structural & Architectural | 180653 | T16182-CA01-P0UCB-180653 | CENTRAL CONTROL BUILDING - 1ST FLOOR FRAMING PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180660 | T16182-CA01-P0UCB-180660 | CENTRAL CONTROL BUILDING - 1ST FLOOR OPENING PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 180602 | T16182-CA00-P0UCB-180602 | CENTRAL CONTROL BUILDING - 1ST FLOOR PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180684 | T16182-CA05-P0UCB-180684 | CENTRAL CONTROL BUILDING - 1ST FLOOR PLUMBING PLAN | IFR | 2017-02-09 | 2017-04-09
S&A(18) | Structural & Architectural | 180654 | T16182-CA01-P0UCB-180654 | CENTRAL CONTROL BUILDING - 2ND FLOOR FRAMING PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180661 | T16182-CA01-P0UCB-180661 | CENTRAL CONTROL BUILDING - 2ND FLOOR OPENING PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 180603 | T16182-CA00-P0UCB-180603 | CENTRAL CONTROL BUILDING - 2ND FLOOR PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180685 | T16182-CA05-P0UCB-180685 | CENTRAL CONTROL BUILDING - 2ND FLOOR PLUMBING PLAN | IFR | 2017-02-09 | 2017-04-09
S&A(18) | Structural & Architectural | 180666 | T16182-CA02-P0UCB-180666 | CENTRAL CONTROL BUILDING - BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-01-31 | 2017-02-28 |  | O
S&A(18) | Structural & Architectural | 180600 | T16182-CA06-P0UCB-180600 | CENTRAL CONTROL BUILDING - CALCULATION | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180613 | T16182-CA00-P0UCB-180613 | CENTRAL CONTROL BUILDING - CEILING PLAN | IFR | 2017-05-31 | 2017-07-31 |  | O
S&A(18) | Structural & Architectural | 180665 | T16182-CA02-P0UCB-180665 | CENTRAL CONTROL BUILDING - COLUMN RE - BAR SCHEDULE | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180608 | T16182-CA00-P0UCB-180608 | CENTRAL CONTROL BUILDING - DOOR & WINDOW SCHEDULE | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 180687 | T16182-CA05-P0UCB-180687 | CENTRAL CONTROL BUILDING - ENLARGED TOILET & SHOWER PLUMBING PLAN | IFR | 2017-02-09 | 2017-04-09
S&A(18) | Structural & Architectural | 180611 | T16182-CA00-P0UCB-180611 | CENTRAL CONTROL BUILDING - ENLARGED TOILET PLAN & ELEVATION | IFR | 2017-03-31 | 2017-05-31 |  | O
S&A(18) | Structural & Architectural | 180651 | T16182-CA01-P0UCB-180651 | CENTRAL CONTROL BUILDING - FDN & COLUMN ARRANGEMENT PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180664 | T16182-CA02-P0UCB-180664 | CENTRAL CONTROL BUILDING - FOUNDATION RE - BAR DETAIL | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180652 | T16182-CA01-P0UCB-180652 | CENTRAL CONTROL BUILDING - GROUND FLOOR FRAMING PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180601 | T16182-CA00-P0UCB-180601 | CENTRAL CONTROL BUILDING - GROUND FLOOR PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180683 | T16182-CA05-P0UCB-180683 | CENTRAL CONTROL BUILDING - GROUND FLOOR PLUMBING PLAN | IFR | 2017-02-09 | 2017-04-09
S&A(18) | Structural & Architectural | 180607 | T16182-CA00-P0UCB-180607 | CENTRAL CONTROL BUILDING - INTERIOR FINISH SCHEDULE | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 180656 | T16182-CA01-P0UCB-180656 | CENTRAL CONTROL BUILDING - LINE FRAMING ELEVATION | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180606 | T16182-CA00-P0UCB-180606 | CENTRAL CONTROL BUILDING - MAIN SECTION | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180614 | T16182-CA00-P0UCB-180614 | CENTRAL CONTROL BUILDING - MISC. DETAIL | IFR | 2017-05-31 | 2017-07-31 |  | O
S&A(18) | Structural & Architectural | 180681 | T16182-CA05-P0UCB-180681 | CENTRAL CONTROL BUILDING - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-02-09 | 2017-04-09
S&A(18) | Structural & Architectural | 180682 | T16182-CA05-P0UCB-180682 | CENTRAL CONTROL BUILDING - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-02-09 | 2017-04-09
S&A(18) | Structural & Architectural | 180655 | T16182-CA01-P0UCB-180655 | CENTRAL CONTROL BUILDING - ROOF FRAMING PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180604 | T16182-CA00-P0UCB-180604 | CENTRAL CONTROL BUILDING - ROOF PLAN | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180686 | T16182-CA05-P0UCB-180686 | CENTRAL CONTROL BUILDING - ROOF PLUMBING PLAN | IFR | 2017-02-09 | 2017-04-09
S&A(18) | Structural & Architectural | 180657 | T16182-CA01-P0UCB-180657 | CENTRAL CONTROL BUILDING - ROW FRAMING ELEVATION | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180605 | T16182-CA00-P0UCB-180605 | CENTRAL CONTROL BUILDING - SIDE WALL ELEVATION | IFR | 2016-11-30 | 2017-01-24 |  | O
S&A(18) | Structural & Architectural | 180667 | T16182-CA02-P0UCB-180667 | CENTRAL CONTROL BUILDING - SLAB & MISC. RE - BAR SCHEDULE | IFR | 2017-01-31 | 2017-02-28 |  | O
S&A(18) | Structural & Architectural | 180609 | T16182-CA00-P0UCB-180609 | CENTRAL CONTROL BUILDING - STAIRCASE#1 ENLARGED PLAN | IFR | 2017-03-31 | 2017-05-31 |  | O
S&A(18) | Structural & Architectural | 180658 | T16182-CA01-P0UCB-180658 | CENTRAL CONTROL BUILDING - STAIRCASE#1 FRAMING PLAN & ELEVATION | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 180610 | T16182-CA00-P0UCB-180610 | CENTRAL CONTROL BUILDING - STAIRCASE#2 ENLARGED PLAN | IFR | 2017-03-31 | 2017-05-31 |  | O
S&A(18) | Structural & Architectural | 180659 | T16182-CA01-P0UCB-180659 | CENTRAL CONTROL BUILDING - STAIRCASE#2 FRAMING PLAN & ELEVATION | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 180668 | T16182-CA02-P0UCB-180668 | CENTRAL CONTROL BUILDING - STRUCTURAL MISC. DETAIL | IFR | 2017-01-31 | 2017-02-28 |  | O
S&A(18) | Structural & Architectural | 180612 | T16182-CA00-P0UCB-180612 | CENTRAL CONTROL BUILDING - WALL OPENING ELEVATION | IFR | 2017-05-31 | 2017-07-31 |  | O
PT(12) | Mechanical | 127036 | T16182-YT01-P0LCB-127036 | CEP - COUPLING SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-020-CEP
PT(12) | Mechanical | 127033 | T16182-YT01-P0LCB-127033 | CEP - DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-07-15 |  |  |  |  | PKG-020-CEP
PT(12) | Mechanical | 127038 | T16182-YD00-P0LCB-127038 | CEP - FOUNDATION DRAWINGS | IFI | 2017-07-15 | 2017-12-12 |  |  |  | PKG-020-CEP
PT(12) | Mechanical | 127031 | T16182-YD00-P0LCB-127031 | CEP - GENERAL ARRANGEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-020-CEP
PT(12) | Instrumentation & Control | 127040 | T16182-YL00-P0LCB-127040 | CEP - INSTRUMENT LIST AND DATA SHEET | IFI | 2017-07-15 |  |  |  |  | PKG-020-CEP
PT(12) | Instrumentation & Control | 127041 | T16182-YK00-P0LCB-127041 | CEP - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-09-30 |  |  |  |  | PKG-020-CEP
PT(12) | Mechanical | 127035 | T16182-YT01-P0LCB-127035 | CEP - MECHANICAL SEAL SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-020-CEP
PT(12) | Electrical | 127039 | T16182-YM01-P0LCB-127039 | CEP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-07-15 |  |  |  |  | PKG-020-CEP
PT(12) | Mechanical | 127042 | T16182-YL22-P0LCB-127042 | CEP - NAME PLATE DRAWING | IFI | 2017-09-30 |  |  |  |  | PKG-020-CEP
PT(12) | Mechanical | 127032 | T16182-XG02-P0LCB-127032 | CEP - P&I DIAGRAM | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-020-CEP
PT(12) | Mechanical | 127034 | T16182-YK09-P0LCB-127034 | CEP - PUMP SECTIONAL DRAWING | IFI | 2017-07-31 | 2017-12-28 |  |  |  | PKG-020-CEP
PT(12) | Mechanical | 127037 | T16182-YT01-P0LCB-127037 | CEP - SUCTION STRAINER SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-020-CEP
S&A(18) | Structural & Architectural | 185751 | T16182-CA01-P0GEN-185751 | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR FRAMING PLAN | IFR | 2017-09-15 | 2017-10-15
S&A(18) | Structural & Architectural | 185701 | T16182-CA00-P0GEN-185701 | CHEMICAL DOSING SHELTER FOR HRSG - GROUND FLOOR PLAN, ROOF PLAN | IFR | 2017-09-15 | 2017-10-15
S&A(18) | Structural & Architectural | 185800 | T16182-CA06-P0GEN-185800 | CHEMICAL DOSING SHELTER FOR STG & HRSG - CALCULATION | IFR | 2017-09-15 | 2017-10-15
S&A(18) | Structural & Architectural | 185802 | T16182-CA00-P0GEN-185802 | CHEMICAL DOSING SHELTER FOR STG & HRSG - ELEVATION | IFR | 2017-09-15 | 2017-10-15
S&A(18) | Structural & Architectural | 185853 | T16182-CA01-P0GEN-185853 | CHEMICAL DOSING SHELTER FOR STG & HRSG - FRAMING ELEVATION | IFR | 2017-09-15 | 2017-10-15
S&A(18) | Structural & Architectural | 185851 | T16182-CA01-P0GEN-185851 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR FRAMING PLAN | IFR | 2017-09-15 | 2017-10-15
S&A(18) | Structural & Architectural | 185852 | T16182-CA01-P0GEN-185852 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | IFR | 2017-09-15 | 2017-10-15
S&A(18) | Structural & Architectural | 185801 | T16182-CA00-P0GEN-185801 | CHEMICAL DOSING SHELTER FOR STG & HRSG - GROUND FLOOR PLAN, ROOF PLAN | IFR | 2017-09-15 | 2017-10-15
S&A(18) | Structural & Architectural | 185803 | T16182-CA00-P0GEN-185803 | CHEMICAL DOSING SHELTER FOR STG & HRSG - MAIN SECTION | IFR | 2017-09-15 | 2017-10-15
S&A(18) | Structural & Architectural | 185854 | T16182-CA02-P0GEN-185854 | CHEMICAL DOSING SHELTER FOR STG & HRSG - REBAR DETAIL | IFR | 2017-09-15 | 2017-10-15
PT(12) | Mechanical | 129050 | T16182-YT01-P0GHC-129050 | CHILLED WATER DISTRIBUTION PUMP - DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-10-11 |  |  |  |  | PKG-024-BOPP
PT(12) | Mechanical | 129051 | T16182-YD00-P0GHC-129051 | CHILLED WATER DISTRIBUTION PUMP - GENERAL ARRANGEMENT DRAWING | IFI | 2017-10-11 | 2017-12-11 |  |  |  | PKG-024-BOPP
PT(12) | Instrumentation & Control | 129063 | T16182-YL00-P0GHC-129063 | CHILLED WATER DISTRIBUTION PUMP - INSTRUMENT LIST AND DATA SHEET | IFI | 2017-10-18 |  |  |  |  | PKG-024-BOPP
PT(12) | Instrumentation & Control | 129064 | T16182-YK00-P0GHC-129064 | CHILLED WATER DISTRIBUTION PUMP - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-10-18 |  |  |  |  | PKG-024-BOPP
PT(12) | Mechanical | 129055 | T16182-YT01-P0GHC-129055 | CHILLED WATER DISTRIBUTION PUMP - MECHANICAL SEAL SPECIFICATION | IFI | 2017-10-18 |  |  |  |  | PKG-024-BOPP
PT(12) | Mechanical | 129060 | T16182-YM01-P0GHC-129060 | CHILLED WATER DISTRIBUTION PUMP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-10-11 |  |  |  |  | PKG-024-BOPP
PT(12) | Mechanical | 129056 | T16182-YL22-P0GHC-129056 | CHILLED WATER DISTRIBUTION PUMP - NAME PLATE DRAWING | IFI | 2017-10-11 |  |  |  |  | PKG-024-BOPP
PT(12) | Mechanical | 129053 | T16182-YK09-P0GHC-129053 | CHILLED WATER DISTRIBUTION PUMP - PUMP SECTIONAL DRAWING | IFI | 2017-10-11 | 2017-12-11 |  |  |  | PKG-024-BOPP
CV(17) | Civil | 173602 | T16182-XB02-P0GKC-173602 | CHILLED WATER STORAGE TANK FOUNDATION DETAIL | IFR | 2017-11-24 | 2018-02-02
TG-MCH(22) | Civil | 220002 | T16182-VL00-P7MPA-220002 | CIVIL - STG FOUNDATION - SHAPE - UNIT P7 | IFI | 2017-01-24 |  |  |  |  | PKG-040-STG
TG-MCH(22) | Civil | 220001 | T16182-VL00-P0MPA-220001 | CIVIL - STG FOUNDATION - SHAPE UNIT P6 | IFI | 2017-01-24 |  |  |  |  | PKG-040-STG
MCH(13) | Mechanical | 136614 | T16182-YT01-P0SGK-136614 | CLEAN AGENT SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
CV(17) | Civil | 172802 | T16182-XB02-P0GUC-172802 | CLEAN STORM WATER PONDS OVERALL LAYOUT | IFR | 2017-06-30 | 2017-08-29
CV(17) | Civil | 172803 | T16182-XB02-P0GUC-172803 | CLEAN STORM WATER PONDS PLAN AND SECTION | IFR | 2017-06-30 | 2017-08-29
GN-SYS(26) | Mechanical | 260016 | T16182-YD00-P0MKG-260016 | CO2 BOTTLE MANIFOLD OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG
EL(15) | Electrical | 154038 | T16182-YQ08-P0CY-154038 | COMMUNICATION LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-07-02 | 2018-08-31
EL(15) | Electrical | 154031 | T16182-YQ08-P0CY-154031 | COMMUNICATION LAYOUT DRAWING - CENTRAL CONTROL BUILDING | IFI | 2017-08-15 | 2017-10-14 |  | O
EL(15) | Electrical | 154052 | T16182-YQ08-P0CY-154052 | COMMUNICATION LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | IFI | 2018-03-23 | 2018-04-23
EL(15) | Electrical | 154037 | T16182-YQ08-P0CY-154037 | COMMUNICATION LAYOUT DRAWING - FGS ELECTRICAL BUILDING | IFI | 2018-01-05 | 2018-03-06 |  | O
EL(15) | Electrical | 154044 | T16182-YQ08-P0CY-154044 | COMMUNICATION LAYOUT DRAWING - FIRE BRIGADE & AUX. LEB | IFI | 2018-08-03 | 2018-07-13
EL(15) | Electrical | 154049 | T16182-YQ08-P0CY-154049 | COMMUNICATION LAYOUT DRAWING - FIRE WATER PUMP HOUSE | IFI | 2017-09-03 | 2017-11-02
EL(15) | Electrical | 154032 | T16182-YQ08-P0CY-154032 | COMMUNICATION LAYOUT DRAWING - GTG #1,2 LEB | IFI | 2017-09-03 | 2017-11-02 |  | O
EL(15) | Electrical | 154033 | T16182-YQ08-P0CY-154033 | COMMUNICATION LAYOUT DRAWING - GTG #3,4,5 LEB | IFI | 2017-12-23 | 2018-02-21
EL(15) | Electrical | 154039 | T16182-YQ08-P0CY-154039 | COMMUNICATION LAYOUT DRAWING - SECURITY BUILDING | IFI | 2018-12-01 | 2018-06-29
EL(15) | Electrical | 154034 | T16182-YQ08-P0CY-154034 | COMMUNICATION LAYOUT DRAWING - ST #1 LEB | IFI | 2017-12-03 | 2018-02-01
EL(15) | Electrical | 154035 | T16182-YQ08-P0CY-154035 | COMMUNICATION LAYOUT DRAWING - ST #2 LEB | IFI | 2018-01-05 | 2018-03-06
EL(15) | Electrical | 154036 | T16182-YQ08-P0CY-154036 | COMMUNICATION LAYOUT DRAWING - ST BUILDING | IFI | 2018-05-19 | 2018-07-18
EL(15) | Electrical | 154041 | T16182-YQ08-P0CY-154041 | COMMUNICATION LAYOUT DRAWING - SUPPORT BUILDING | IFI | 2018-04-21 | 2018-06-29
EL(15) | Electrical | 154051 | T16182-YQ08-P0CY-154051 | COMMUNICATION LAYOUT DRAWING - WATER TREATMENT BUILDING | IFI | 2017-08-29 | 2017-10-28 |  | O
EL(15) | Electrical | 154045 | T16182-YQ08-P0CY-154045 | COMMUNICATION LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | IFI | 2018-03-19 | 2018-05-18
EL(15) | Electrical | 154042 | T16182-YQ08-P0CY-154042 | COMMUNICATION LAYOUT DRAWING - X-RAY SEARCHING ROOM | IFI | 2018-04-21 | 2018-06-29
EL(15) | Electrical | 154040 | T16182-YQ08-P0CY-154040 | COMMUNICATION LAYOUT DRAWING – MAIN GATE & PLANT ACCESS GATE HOUSE | IFI | 2018-04-21 | 2018-06-29
EL(15) | Electrical | 154053 | T16182-YQ08-P0CY-154053 | COMMUNICATION LAYOUT DRAWING – PIPE RACK | IFI | 2018-07-30 | 2018-10-30
CV(17) | Civil | 172502 | T16182-XB02-P0ULC-172502 | CONDENSATE WATER TANK FOUNDATION PLAN & SECTION | IFR | 2017-03-31 | 2017-05-31
CV(17) | Civil | 172503 | T16182-VK02-P0ULC-172503 | CONDENSATE WATER TANK FOUNDATION REBAR DETAIL | IFR | 2017-03-31 | 2017-05-31
EL(15) | Electrical | 154011 | T16182-YU02-P0CYA-154011 | CONFIGURATION DIAGRAM - OFFICE TELEPHONE & LAN SYSTEM | IFR | 2017-04-07 | 2017-08-11
EL(15) | Electrical | 154013 | T16182-YU02-P0CYM-154013 | CONFIGURATION DIAGRAM - PUBLIC ADDRESS SYSTEM (SIREN SYSTEM) | IFR | 2017-04-07 | 2017-08-11
EL(15) | Electrical | 151131 | T16182-YD00-P0CHB-151131 | CONFIGURATION DIAGRM - FAULT MONITORING SYSTEM | IFI | 2017-05-15 |  |  |  |  | PKG-038-MP
EL(15) | Electrical | 150766 | T16182-YD00-P0BAA-150766 | CONNECTION DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | IFI | 2017-05-31 |  |  |  |  | PKG-033-IPB
EL(15) | Electrical | 150767 | T16182-YD00-P0BAA-150767 | CONNECTION DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | IFI | 2017-06-30 |  |  |  |  | PKG-033-IPB
EM(02) | Project Management | 020003 | T16182-VA08-P0ZEN-020003 | CONTRACTORS ADMIN PLAN | IFI | 2016-12-23
EL(15) | Electrical | 152052 | T16182-YB03-P0ZEN-152052 | CONTROL CABLE CONNECTION DIAGRAM | IFI | 2017-09-15
EL(15) | Electrical | 152860 | T16182-YL16-P0ZEN-152860 | CONTROL CABLE SCHEDULE | IFI | 2017-08-29 |  |  | O
MCH(13) | Instrumentation & Control | 130211 | T16182-YF02-P0LD-130211 | CONTROL CONFIGURATION DIAGRAM FOR CONDENSATE POLISHING PLANT | IFI | 2017-07-03 |  |  |  |  | PKG-026-CPP
MCH(13) | Instrumentation & Control | 130011 | T16182-YF02-P0GCF-130011 | CONTROL CONFIGURATION DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-03-06 |  |  | O |  | PKG-025-WT
I&C(16) | Instrumentation & Control | 163405 | T16182-YF00-P0SAY-163405 | CONTROL LOGIC & LOOP DIAGRAM FOR HVAC | IFI | 2017-08-30 |  |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 161201 | T16182-YF00-P0CBA-161201 | CONTROL LOGIC DIAGRAM - SYMBOL & LEGEND | IFR | 2017-04-30 | 2017-08-13 |  | O
I&C(16) | Instrumentation & Control | 161202 | T16182-YF00-P0CBA-161202 | CONTROL LOGIC DIAGRAM - TYPICAL FUNCTION | IFR | 2017-04-30 | 2017-08-13 |  | O
I&C(16) | Instrumentation & Control | 161210 | T16182-YF00-P0CBA-161210 | CONTROL LOGIC DIAGRAM FOR CLOSED COOLING WATER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O
I&C(16) | Instrumentation & Control | 161216 | T16182-YF00-P0CBA-161216 | CONTROL LOGIC DIAGRAM FOR COMPRESSED AIR SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O
I&C(16) | Instrumentation & Control | 161208 | T16182-YF00-P0CBA-161208 | CONTROL LOGIC DIAGRAM FOR CONDENSATE SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O
I&C(16) | Instrumentation & Control | 161211 | T16182-YF00-P0CBA-161211 | CONTROL LOGIC DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O
I&C(16) | Instrumentation & Control | 161220 | T16182-YF00-P0CBA-161220 | CONTROL LOGIC DIAGRAM FOR ELECTRICAL SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  | O
I&C(16) | Instrumentation & Control | 161209 | T16182-YF00-P0CBA-161209 | CONTROL LOGIC DIAGRAM FOR FEEDWATER SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O
I&C(16) | Instrumentation & Control | 161213 | T16182-YF00-P0CBA-161213 | CONTROL LOGIC DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  |  | O
I&C(16) | Instrumentation & Control | 161212 | T16182-YF00-P0CBA-161212 | CONTROL LOGIC DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  |  | O
I&C(16) | Instrumentation & Control | 161203 | T16182-YF00-P0CBA-161203 | CONTROL LOGIC DIAGRAM FOR HP STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O
I&C(16) | Instrumentation & Control | 161221 | T16182-YF00-P0CBA-161221 | CONTROL LOGIC DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  | O
I&C(16) | Instrumentation & Control | 161204 | T16182-YF00-P0CBA-161204 | CONTROL LOGIC DIAGRAM FOR IP STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O
I&C(16) | Instrumentation & Control | 161205 | T16182-YF00-P0CBA-161205 | CONTROL LOGIC DIAGRAM FOR LP STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O
I&C(16) | Instrumentation & Control | 161222 | T16182-YF00-P0CBA-161222 | CONTROL LOGIC DIAGRAM FOR MISCELLANEOUS SYSTEM | IFR | 2017-05-15 | 2017-08-28
I&C(16) | Instrumentation & Control | 161214 | T16182-YF00-P0CBA-161214 | CONTROL LOGIC DIAGRAM FOR POTABLE WATER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O
I&C(16) | Instrumentation & Control | 161206 | T16182-YF00-P0CBA-161206 | CONTROL LOGIC DIAGRAM FOR PROCESS STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  | O | O
I&C(16) | Instrumentation & Control | 161207 | T16182-YF00-P0CBA-161207 | CONTROL LOGIC DIAGRAM FOR STEAM DRAIN SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O
MCH(13) | Instrumentation & Control | 130309 | T16182-YF00-P0QC-130309 | CONTROL LOOP & LOGIC DIAGRAM FOR CHEMICAL DOSING SYSTEM | IFI | 2018-01-03 |  |  |  |  | PKG-027-CDS
MCH(13) | Instrumentation & Control | 130218 | T16182-YF00-P0LD-130218 | CONTROL LOOP & LOGIC DIAGRAM FOR CONDENSATE POLISHING PLANT | IFI | 2017-09-01 |  |  |  |  | PKG-026-CPP
MCH(13) | Instrumentation & Control | 130407 | T16182-YF00-P0QU-130407 | CONTROL LOOP & LOGIC DIAGRAM FOR SAMPLING SYSTEM | IFI | 2018-01-02 |  |  |  |  | PKG-028-SP
MCH(13) | Instrumentation & Control | 130018 | T16182-YF00-P0GCF-130018 | CONTROL LOOP & LOGIC DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-05-05 |  |  | O |  | PKG-025-WT
I&C(16) | Instrumentation & Control | 161301 | T16182-YF00-P0CGA-161301 | CONTROL LOOP DIAGRAM - SYMBOL & LEGEND | IFR | 2017-04-30 | 2017-08-13 |  | O | O
I&C(16) | Instrumentation & Control | 161302 | T16182-YF00-P0CGA-161302 | CONTROL LOOP DIAGRAM - TYPICAL FUNCTION | IFR | 2017-04-30 | 2017-08-13 |  | O | O
I&C(16) | Instrumentation & Control | 161310 | T16182-YF00-P0CGA-161310 | CONTROL LOOP DIAGRAM FOR CLOSED COOLING WATER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O
I&C(16) | Instrumentation & Control | 161316 | T16182-YF00-P0CGA-161316 | CONTROL LOOP DIAGRAM FOR COMPRESSED AIR SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O
I&C(16) | Instrumentation & Control | 161308 | T16182-YF00-P0CGA-161308 | CONTROL LOOP DIAGRAM FOR CONDENSATE SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O
I&C(16) | Instrumentation & Control | 161311 | T16182-YF00-P0CGA-161311 | CONTROL LOOP DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O
I&C(16) | Instrumentation & Control | 161320 | T16182-YF00-P0CGA-161320 | CONTROL LOOP DIAGRAM FOR ELECTRICAL SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  | O
I&C(16) | Instrumentation & Control | 161309 | T16182-YF00-P0CGA-161309 | CONTROL LOOP DIAGRAM FOR FEEDWATER SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O
I&C(16) | Instrumentation & Control | 161313 | T16182-YF00-P0CGA-161313 | CONTROL LOOP DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  |  | O
I&C(16) | Instrumentation & Control | 161312 | T16182-YF00-P0CGA-161312 | CONTROL LOOP DIAGRAM FOR GT ROTOR COOLING AIR SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  |  | O
I&C(16) | Instrumentation & Control | 161303 | T16182-YF00-P0CGA-161303 | CONTROL LOOP DIAGRAM FOR HP STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O
I&C(16) | Instrumentation & Control | 161321 | T16182-YF00-P0CGA-161321 | CONTROL LOOP DIAGRAM FOR INTERFACE WITH OTHER CONTROL SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  | O
I&C(16) | Instrumentation & Control | 161304 | T16182-YF00-P0CGA-161304 | CONTROL LOOP DIAGRAM FOR IP STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O
I&C(16) | Instrumentation & Control | 161305 | T16182-YF00-P0CGA-161305 | CONTROL LOOP DIAGRAM FOR LP STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O
I&C(16) | Instrumentation & Control | 161322 | T16182-YF00-P0CGA-161322 | CONTROL LOOP DIAGRAM FOR MISCELLANEOUS SYSTEM | IFR | 2017-05-15 | 2017-08-28
I&C(16) | Instrumentation & Control | 161314 | T16182-YF00-P0CGA-161314 | CONTROL LOOP DIAGRAM FOR POTABLE WATER SYSTEM | IFR | 2017-04-30 | 2017-08-13 |  | O | O
I&C(16) | Instrumentation & Control | 161306 | T16182-YF00-P0CGA-161306 | CONTROL LOOP DIAGRAM FOR PROCESS STEAM SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  | O | O
I&C(16) | Instrumentation & Control | 161307 | T16182-YF00-P0CGA-161307 | CONTROL LOOP DIAGRAM FOR STEAM DRAIN SYSTEM | IFR | 2017-05-15 | 2017-08-28 |  |  | O
MCH(13) | Instrumentation & Control | 130306 | T16182-YR05-P0QC-130306 | CONTROL PANEL ARRANGEMENT DRAWING FOR CHEMICAL DOSING SYSTEM | IFI | 2017-11-04 |  |  |  |  | PKG-027-CDS
MCH(13) | Instrumentation & Control | 130207 | T16182-YR05-P0LD-130207 | CONTROL PANEL ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2017-07-03 | 2018-11-22 |  |  |  | PKG-026-CPP
MCH(13) | Instrumentation & Control | 130007 | T16182-YR05-P0GCF-130007 | CONTROL PANEL ARRANGEMENT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-03-06 | 2017-07-07 |  | O |  | PKG-025-WT
I&C(16) | Instrumentation & Control | 163423 | T16182-YR05-P0SAY-163423 | CONTROL PANEL OUTLINE & DETAIL DRAWING FOR HVAC | IFI | 2017-07-15 |  |  | O |  | PKG-041-HVAC
TG-MCH(22) | Instrumentation & Control | 220073 | T16182-YR00-P6MAA-220073 | CONTROL SYSTEM ARCHITECTURE | IFI | 2018-06-29 |  |  |  |  | PKG-040-STG
I&C(16) | Instrumentation & Control | 163401 | T16182-YF02-P0SAY-163401 | CONTROL SYSTEM CONFIGURATION DIAGRAM FOR HVAC | IFR | 2017-03-10 | 2017-06-23 |  | O |  | PKG-041-HVAC
TG-MCH(22) | Instrumentation & Control | 220093 | T16182-XS01-P6MAA-220093 | CONTROL SYSTEM FUNCTIONS PHILOSOPHY | IFI | 2018-06-29 |  |  |  |  | PKG-040-STG
TG-MCH(22) | Instrumentation & Control | 220275 | T16182-YF02-P6CJJ-220275 | CONTROL SYSTEM HARDWARE SPECIFICATION – UNIT P6 | IFI | 2018-05-20 |  |  |  |  | PKG-040-STG
TG-MCH(22) | Instrumentation & Control | 220276 | T16182-YF02-P7CJJ-220276 | CONTROL SYSTEM HARDWARE SPECIFICATION – UNIT P7 | IFI | 2018-05-20 |  |  |  |  | PKG-040-STG
EM(02) | Engineering Management | 020030 | T16182-BV02-P0ZEN-020030 | CORROSION AND MATERIAL STUDY | IFI | 2018-09-20
S&A(18) | Structural & Architectural | 183910 | T16182-CA00-P0ULD-183910 | CPP & CPP REGEN BUILDING - ARCHITECTURAL MISC. DETAIL | IFR | 2018-04-30 | 2018-06-28
S&A(18) | Structural & Architectural | 183900 | T16182-CA06-P0ULD-183900 | CPP & CPP REGEN BUILDING - CALCULATION | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183956 | T16182-CA02-P0ULD-183956 | CPP & CPP REGEN BUILDING - COLUMN REBAR DETAIL | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183904 | T16182-CA00-P0ULD-183904 | CPP & CPP REGEN BUILDING - ELEVATION | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183960 | T16182-CA02-P0ULD-183960 | CPP & CPP REGEN BUILDING - EMBEDDED PLATE & SLEEVE PLAN | IFR | 2017-06-14 | 2017-08-14
S&A(18) | Structural & Architectural | 183963 | T16182-CA03-P0ULD-183963 | CPP & CPP REGEN BUILDING - ENLARGED ROOF FRAMING PLAN | IFR | 2017-06-14 | 2017-08-14
S&A(18) | Structural & Architectural | 183959 | T16182-CA02-P0ULD-183959 | CPP & CPP REGEN BUILDING - EQUIPMENT FOUNDTAION REBAR DETAIL | IFR | 2017-06-14 | 2017-08-14
S&A(18) | Structural & Architectural | 183951 | T16182-CA01-P0ULD-183951 | CPP & CPP REGEN BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183955 | T16182-CA02-P0ULD-183955 | CPP & CPP REGEN BUILDING - FOUNDATION REBAR DETAIL | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183954 | T16182-CA01-P0ULD-183954 | CPP & CPP REGEN BUILDING - FRAMING ELEVATION | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183957 | T16182-CA02-P0ULD-183957 | CPP & CPP REGEN BUILDING - GIRDER & BEAM REBAR SCHEDULE | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183964 | T16182-CA03-P0ULD-183964 | CPP & CPP REGEN BUILDING - GIRT LINE & ROW ELEVATION | IFR | 2017-06-14 | 2017-08-14
S&A(18) | Structural & Architectural | 183952 | T16182-CA01-P0ULD-183952 | CPP & CPP REGEN BUILDING - GROUND FLOOR FRAMING PLAN | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183902 | T16182-CA00-P0ULD-183902 | CPP & CPP REGEN BUILDING - GROUND FLOOR PLAN | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183906 | T16182-CA00-P0ULD-183906 | CPP & CPP REGEN BUILDING - INTERIOR FINISH, DOOR & WINDOW SCHEDULE | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183961 | T16182-CA02-P0ULD-183961 | CPP & CPP REGEN BUILDING - MISC. REBAR DETAIL | IFR | 2017-06-14 | 2017-08-14
S&A(18) | Structural & Architectural | 183962 | T16182-CA03-P0ULD-183962 | CPP & CPP REGEN BUILDING - ROOF COLUMN LOCATION PLAN | IFR | 2017-06-14 | 2017-08-14
S&A(18) | Structural & Architectural | 183953 | T16182-CA01-P0ULD-183953 | CPP & CPP REGEN BUILDING - ROOF FLOOR FRAMING PLAN | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183903 | T16182-CA00-P0ULD-183903 | CPP & CPP REGEN BUILDING - ROOF FLOOR PLAN | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183905 | T16182-CA00-P0ULD-183905 | CPP & CPP REGEN BUILDING - SECTION | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183958 | T16182-CA02-P0ULD-183958 | CPP & CPP REGEN BUILDING - SLAB REBAR DETAIL | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 183965 | T16182-CA03-P0ULD-183965 | CPP & CPP REGEN BUILDING - STEEL CONNECTION DETAIL | IFR | 2017-06-14 | 2017-08-14
S&A(18) | Structural & Architectural | 183909 | T16182-CA00-P0ULD-183909 | CPP & CPP REGEN BUILDING - WALL OPENING PLAN | IFR | 2018-04-30 | 2018-06-28
S&A(18) | Structural & Architectural | 183908 | T16182-CA00-P0ULD-183908 | CPP & CPP REGEN BUILDING - WALL SECTION DETAIL | IFR | 2018-04-30 | 2018-06-28
CV(17) | Civil | 171222 | T16182-XB02-P0ULX-171222 | CPP FIN FAN COOLER FOUNDATION LAYOUT | IFR | 2017-07-31 | 2017-10-31 |  | O
CV(17) | Civil | 171223 | T16182-XB02-P0ULX-171223 | CPP FIN FAN COOLER FOUNDATION PLAN AND SECTION | IFR | 2017-07-31 | 2017-10-31 |  | O
PT(12) | Mechanical | 128018 | T16182-YT01-P0SML-128018 | CRANE - DATA SHEETS FOR DEAERATOR SUPPORT STRUCTURE CRANE | IFI | 2017-09-29 | 2017-11-02 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128004 | T16182-YT01-P0SMM-128004 | CRANE - DATA SHEETS FOR STEAM TURBINE BUILDING CRANE | IFI | 2017-05-10 | 2017-09-15 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128005 | T16182-YT01-P0SMS-128005 | CRANE - DATA SHEETS FOR WORKSHOP CRANE | IFI | 2017-09-29 | 2017-11-08 |  |  |  | PKG-022-CR
PT(12) | Electrical | 128027 | T16182-YS18-P0SML-128027 | CRANE - ELECTRICAL DETAIL FOR DEAERATOR SUPPORT STRUCTURE CRANE | IFI | 2017-12-29 | 2018-01-19 |  |  |  | PKG-022-CR
PT(12) | Electrical | 128010 | T16182-YS18-P0SMM-128010 | CRANE - ELECTRICAL DETAIL FOR STEAM TURBINE BUILDING CRANE | IFI | 2017-07-29 | 2018-01-19 |  |  |  | PKG-022-CR
PT(12) | Electrical | 128011 | T16182-YS18-P0SMS-128011 | CRANE - ELECTRICAL DETAIL FOR WORKSHOP CRANE | IFI | 2017-12-29 | 2018-01-19 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128013 | T16182-YD00-P0SML-128013 | CRANE - GA DRAWING FOR DEAERATOR SUPPORT STRUCTURE CRANE | IFI | 2017-09-29 | 2017-11-28 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128001 | T16182-YD00-P0SMM-128001 | CRANE - GA DRAWING FOR STEAM TURBINE BUILDING CRANE | IFI | 2017-05-10 | 2017-11-28 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128002 | T16182-YD00-P0SMS-128002 | CRANE - GA DRAWING FOR WORKSHOP CRANE | IFI | 2017-09-29 | 2017-11-28 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128023 | T16182-YK09-P0SML-128023 | CRANE - MECHNICAL DETAIL FOR DEAERATOR SUPPORT STRUCTURE CRANE | IFI | 2017-12-29 | 2018-05-28 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128007 | T16182-YK09-P0SMM-128007 | CRANE - MECHNICAL DETAIL FOR STEAM TURBINE BUILDING CRANE | IFI | 2017-07-29 | 2018-01-19 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128008 | T16182-YK09-P0SMS-128008 | CRANE - MECHNICAL DETAIL FOR WORKSHOP CRANE | IFI | 2017-12-29 | 2018-01-19 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128103 | T16182-YD00-P0SML-128103 | CRANE - NAME PLATE DRAWING FOR DEAERATOR SUPPORT STRUCTURE CRANE | IFI | 2017-12-29 |  |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128101 | T16182-YD00-P0SMM-128101 | CRANE - NAME PLATE DRAWING FOR STEAM TURBINE BUILDING CRANE | IFI | 2017-12-29 |  |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128102 | T16182-YD00-P0SMS-128102 | CRANE - NAME PLATE DRAWING FOR WORKSHOP CRANE | IFI | 2017-12-29 |  |  |  |  | PKG-022-CR
EL(15) | Electrical | 150303 | T16182-YT10-P0ZEN-150303 | CT PT CALCULATION STUDY REPORT FOR HV EQUIPMENT | IFR | 2017-04-30 | 2017-10-15 |  | O
GN-MCH(25) | Mechanical | 250013 | T16182-UC02-P0MKA-250013 | CURRENT TRANSFORMER ASSEMBLY | IFI | 2017-04-14 |  |  |  |  | PKG-040-STG
I&C(16) | Instrumentation & Control | 167001 | T16182-YF00-P0ZEN-167001 | CYBER SECURITY PLAN | IFI | 2019-06-30
PS(11) | Mechanical | 110153 | T16182-YT01-P0MAN-110153 | DATA SHEET FOR BYPASS AND PRDS | IFI | 2017-06-30 |  |  |  |  | PKG-002-PRDS
PS(11) | Mechanical | 110403 | T16182-YT01-P0PGB-110403 | DATA SHEET FOR CLOSED COOLING WATER PUMP | IFR | 2017-04-30 | 2017-07-28 |  | O |  | PKG-005-CCWP
PS(11) | Electrical | 110407 | T16182-YT01-P0PGB-110407 | DATA SHEET FOR CLOSED COOLING WATER PUMP MOTOR | IFI | 2017-04-30 |  |  | O |  | PKG-005-CCWP
PS(11) | Mechanical | 110301 | T16182-YT01-P0LCP-110301 | DATA SHEET FOR CONDENSATE PLATE TYPE HEAT EXCHANGER | IFR | 2017-05-15 | 2017-09-14 |  |  |  | PKG-004-PHE
PS(11) | Mechanical | 110503 | T16182-YT01-P0QJA-110503 | DATA SHEET FOR NITROGEN GAS SYSTEM | IFR | 2017-06-15 | 2017-08-30 |  | O |  | PKG-006-N2
PS(11) | Mechanical | 110101 | T16182-YT01-P0LF-110101 | DATA SHEET FOR SAFETY RELIEF VALVE AND RUPTURE DISC FOR BOP SYSTEMS | IFI | 2017-05-31 |  |  |  |  | PKG-001-SRV
PS(11) | Mechanical | 110251 | T16182-YT01-P0LBG-110251 | DATA SHEET FOR SILENCER | IFI | 2017-07-31 |  |  |  |  | PKG-003-SILENCER
B.I&C(16) | Instrumentation & Control | 161115 | T16182-YL16-P0CRN-161115 | DCS - CABLE LIST | IFI | 2017-04-30 | 2017-09-29 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161123 | T16182-CV03-P0CWQ-161123 | DCS - FIELD INSTRUMENT MONITORING SYSTEM | IFR | 2017-03-15 | 2017-05-29 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161103 | T16182-CV03-P0CRN-161103 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR HARDWARE | IFR | 2017-02-01 | 2017-05-17 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161105 | T16182-CV03-P0CRN-161105 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR HMI GRAPHIC | IFR | 2017-02-15 | 2017-05-31 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161104 | T16182-CV03-P0CRN-161104 | DCS - FUNCTIONAL DESIGN SPECIFICATION FOR SOFTWARE | IFR | 2017-02-01 | 2017-05-17 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161119 | T16182-YD00-P0CUQ-161119 | DCS - GROUNDING DRAWING | IFR | 2017-02-01 | 2017-04-02 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161116 | T16182-YD05-P0CRN-161116 | DCS - HMI GRAPHIC DISPLAY DIAGRAM | IFR | 2017-06-30 | 2017-09-22 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161114 | T16182-YB03-P0CRN-161114 | DCS - INTERNAL CABLE CONNECTION DIAGRAM | IFI | 2017-05-15 | 2017-10-12 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161113 | T16182-YD00-P0CRN-161113 | DCS - IO & MODULE ALLOCATION | IFI | 2017-04-21 | 2017-09-29 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161102 | T16182-YF02-P0CRV-161102 | DCS - LAN CONFIGURATION DIAGRAM | IFR | 2017-02-01 | 2017-04-02 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161146 | T16182-YR05-P0CWQ-161146 | DCS - OUTLINE & DETAIL DRAWING FOR DCS CONSOLE & DESK | IFR | 2017-05-08 | 2017-07-21 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161148 | T16182-YR05-P0CWQ-161148 | DCS - OUTLINE & DETAIL DRAWING FOR DCS GROUNDING BOX | IFR | 2017-05-08 | 2017-07-21 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161147 | T16182-YR05-P0CWQ-161147 | DCS - OUTLINE & DETAIL DRAWING FOR DCS POWER DISTRIBUTION CABINET | IFR | 2017-03-15 | 2017-06-08 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161141 | T16182-YR05-P0CWQ-161141 | DCS - OUTLINE & DETAIL DRAWING FOR DCS SYSTEM CABINET | IFR | 2017-03-15 | 2017-06-08 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161142 | T16182-YR05-P0CWQ-161142 | DCS - OUTLINE & DETAIL DRAWING FOR LAN/SERVER CABINET | IFR | 2017-03-15 | 2017-06-08 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161143 | T16182-YR05-P0CWQ-161143 | DCS - OUTLINE & DETAIL DRAWING FOR MARSHALLING CABINET | IFR | 2017-03-15 | 2017-06-08 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161121 | T16182-CV03-P0CWQ-161121 | DCS - PERFORMANCE MONITORING SYSTEM | IFR | 2017-04-07 | 2017-06-23 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161122 | T16182-CV03-P0CWQ-161122 | DCS - PLANT INFORMATION HISTORIAN | IFR | 2017-04-15 | 2017-06-30 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161112 | T16182-YD00-P0CUQ-161112 | DCS - POWER DISTRIBUTION DRAWING | IFR | 2017-02-01 | 2017-04-02 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161133 | T16182-CV03-P0CWQ-161133 | DCS - TECHNICAL SPECIFICATION FOR EMERGENCY PUSH BUTTON | IFR | 2017-05-08 | 2017-06-16 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161149 | T16182-CV03-P0CRT-161149 | DCS - TECHNICAL SPECIFICATION FOR FIELDBUS MOV | IFR | 2017-04-28 | 2017-07-28 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161135 | T16182-CV03-P0CWQ-161135 | DCS - TECHNICAL SPECIFICATION FOR LARGE SCREEN DISPLAY | IFR | 2017-05-08 | 2017-06-16 |  | O |  | PKG-039-DCS
B.I&C(16) | Instrumentation & Control | 161132 | T16182-CV03-P0CWQ-161132 | DCS - TECHNICAL SPECIFICATION FOR TIME SYNCHRONIZATION | IFR | 2017-03-15 | 2017-06-28 |  | O |  | PKG-039-DCS
I&C(16) | Instrumentation & Control | 161101 | T16182-YL01-P0CBA-161101 | DCS I/O DATABASE | IFR | 2017-02-28 | 2017-07-28 |  | O
I&C(16) | Instrumentation & Control | 161111 | T16182-YR04-P0CUQ-161111 | DCS POWER DISTRIBUTION CONCEPT DIAGRAM | IFR | 2017-02-01 | 2017-04-02 |  | O
S&A(18) | Structural & Architectural | 182160 | T16182-CA03-P0ULA-182160 | DEAERATOR SUPPORT STRUCTURE - BASE PLATE DETAIL | IFR | 2017-02-10 | 2017-04-10
S&A(18) | Structural & Architectural | 182152 | T16182-CA03-P0ULA-182152 | DEAERATOR SUPPORT STRUCTURE - COLUMN LOCATION PLAN | IFR | 2016-12-15 | 2017-02-15
S&A(18) | Structural & Architectural | 182154 | T16182-CA03-P0ULA-182154 | DEAERATOR SUPPORT STRUCTURE - DEAERATOR FLOOR FRAMING PLAN | IFR | 2017-02-10 | 2017-04-10
S&A(18) | Structural & Architectural | 182157 | T16182-CA03-P0ULA-182157 | DEAERATOR SUPPORT STRUCTURE - FOUNDATION DETAIL | IFR | 2016-12-15 | 2017-02-15
S&A(18) | Structural & Architectural | 182155 | T16182-CA03-P0ULA-182155 | DEAERATOR SUPPORT STRUCTURE - FRAMING ELEVATION | IFR | 2017-02-10 | 2017-04-10
S&A(18) | Structural & Architectural | 182153 | T16182-CA03-P0ULA-182153 | DEAERATOR SUPPORT STRUCTURE - GROUND FLOOR FRAMING PLAN | IFR | 2017-02-10 | 2017-07-10
S&A(18) | Structural & Architectural | 182190 | T16182-CA06-P0ULA-182190 | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION CALCULATION | IFR | 2016-12-15 | 2017-02-15
S&A(18) | Structural & Architectural | 182151 | T16182-CA01-P0ULA-182151 | DEAERATOR SUPPORT STRUCTURE - PILE & FOUNDATION PLAN | IFR | 2016-12-15 | 2017-02-15
S&A(18) | Structural & Architectural | 182191 | T16182-CA06-P0ULA-182191 | DEAERATOR SUPPORT STRUCTURE - SUPERSTRUCTURE CALCULATION | IFR | 2017-02-10 | 2017-04-10
CV(17) | Civil | 172542 | T16182-XB02-P0UGD-172542 | DEMINERALIZED WATER TANK FOUNDATION PLAN & SECTION | IFR | 2017-03-31 | 2017-05-31 |  | O
CV(17) | Civil | 172543 | T16182-VK02-P0UGD-172543 | DEMINERALIZED WATER TANK FOUNDATION REBAR DETAIL | IFR | 2017-03-31 | 2017-05-31 |  | O
I&C(16) | Instrumentation & Control | 165900 | T16182-YR02-P0ZEN-165900 | DESCRIPTION OF SETTLEMENT SYSTEM | IFR | 2016-12-23 | 2017-08-01
S&A(18) | Structural & Architectural | 189000 | T16182-CA07-P0ZEN-189000 | DESIGN CRITERIA FOR CIVIL AND BUILDING STRUCTURES | IFR | 2016-10-27 | 2017-01-31
PS(11) | Mechanical | 110038 | T16182-XW01-P0PGB-110038 | DESIGN CRITERIA FOR CLOSED COOLING WATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  | O
PT(12) | Mechanical | 120016 | T16182-XS00-P0SCA-120016 | DESIGN CRITERIA FOR COMPRESSED AIR SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O
PS(11) | Mechanical | 110036 | T16182-XW01-P0LC-110036 | DESIGN CRITERIA FOR CONDENSATE SYSTEM | IFR | 2016-10-28 | 2017-04-28
PS(11) | Mechanical | 110039 | T16182-XW01-P0GHC-110039 | DESIGN CRITERIA FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  | O
EL(15) | Electrical | 150001 | T16182-YR02-P0ZEN-150001 | DESIGN CRITERIA FOR ELECTRICAL SYSTEM | IFR | 2016-12-01 | 2017-06-30 |  | O
PS(11) | Mechanical | 110037 | T16182-XW01-P0LA-110037 | DESIGN CRITERIA FOR FEEDWATER SYSTEM | IFR | 2016-10-28 | 2017-03-27
PT(12) | Mechanical | 120020 | T16182-XS00-P0EKG-120020 | DESIGN CRITERIA FOR FUEL GAS SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O |  | PKG-014-FGS
I&C(16) | Instrumentation & Control | 161001 | T16182-XW01-P0ZEN-161001 | DESIGN CRITERIA FOR GENERAL I&C SYSTEM | IFR | 2016-10-28 | 2017-04-30
MCH(13) | Mechanical | 133301 | T16182-XW01-P0SAA-133301 | DESIGN CRITERIA FOR HVAC SYSTEM | IFR | 2017-01-25 | 2017-04-15 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 165001 | T16182-XW01-P0ZEN-165001 | DESIGN CRITERIA FOR I&C CABLE | IFR | 2016-11-30 | 2017-03-15
PT(12) | Mechanical | 120012 | T16182-XS00-P0GKS-120012 | DESIGN CRITERIA FOR POTABLE WATER SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O
PS(11) | Mechanical | 110035 | T16182-XW01-P0LB-110035 | DESIGN CRITERIA FOR STEAM AND BYPASS SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  | O
PT(12) | Mechanical | 120023 | T16182-XS00-P0GM-120023 | DESIGN CRITERIA FOR WASTE WATER TRANSFER SYSTEM | IFR | 2017-05-30 | 2017-08-28
EL(15) | Electrical | 150776 | T16182-YD00-P0BAA-150776 | DETAIL DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | IFI | 2017-06-30 |  |  |  |  | PKG-033-IPB
EL(15) | Electrical | 150777 | T16182-YD00-P0BAA-150777 | DETAIL DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | IFI | 2017-07-28 |  |  |  |  | PKG-033-IPB
TG-MCH(22) | Mechanical | 220089 | T16182-XG01-P6MAA-220089 | DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM - UNIT P6 | IFI | 2018-02-04 |  |  |  |  | PKG-040-STG
TG-MCH(22) | Mechanical | 220090 | T16182-XG01-P7MAA-220090 | DETAIL DRAWINGS - PIPING, COMPONENTS AND BOM - UNIT P7 | IFI | 2018-03-20 |  |  |  |  | PKG-040-STG
EM(02) | Engineering Management | 020001 | 020001 | DOCUMENT IDENTIFICATION | IFI | 2017-01-30 |  |  | O
EL(15) | Electrical | 150836 | T16182-YU03-P0BB-150836 | DRAWINGS - HTS | IFI | 2017-06-16 |  |  |  |  | PKG-034-MVSWGR
GN-I&C(29) | Instrumentation & Control | 290004 | T16182-YR05-P0CJN-290004 | DRAWINGS OF EXCITATION TRANSFORMER FOR ST | IFR | 2017-03-10 | 2017-05-10 |  |  |  | PKG-040-STG
TG-MCH(22) | Mechanical | 220205 | T16182-CM01-P6MAA-220205 | DRAWINGS, PART LISTS OF TURBINE – UNIT P6 | IFI | 2018-05-15 |  |  |  |  | PKG-040-STG
TG-MCH(22) | Mechanical | 220206 | T16182-CM01-P7MAA-220206 | DRAWINGS, PART LISTS OF TURBINE – UNIT P7 | IFI | 2018-05-15 |  |  |  |  | PKG-040-STG
MCH(13) | Mechanical | 133404 | T16182-XH02-P0SAH-133404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSEM FOR STEAM TURBINE BUILDING | IFR | 2017-06-14 | 2017-08-13 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134004 | T16182-XH02-P0SAL-134004 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135204 | T16182-XH02-P0SAQ-135204 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR AUX. LEB | IFR | 2018-01-18 | 2018-02-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133504 | T16182-XH02-P0SAC-133504 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-03-17 | 2017-05-01 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 135004 | T16182-XH02-P0SAM-135004 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | IFR | 2017-08-29 | 2017-10-28 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133704 | T16182-XH02-P0SAJ-133704 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-08-04 | 2017-10-03 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 134704 | T16182-XH02-P0SAF-134704 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FIRE BRIGADE | IFR | 2017-10-29 | 2017-12-28 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134904 | T16182-XH02-P0SAG-134904 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-06-14 | 2017-08-13 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 133804 | T16182-XH02-P0SAI-133804 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR GTG #1/2 LEB | IFR | 2017-03-26 | 2017-05-15 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 133904 | T16182-XH02-P0SAI-133904 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR GTG #3/4/5 LEB | IFR | 2017-04-30 | 2017-06-29 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134304 | T16182-XH02-P0SAE-134304 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR MAIN GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135404 | T16182-XH02-P0SAE-135404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR PIC GATE HOUSE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135304 | T16182-XH02-P0SAE-135304 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134604 | T16182-XH02-P0SAE-134604 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134504 | T16182-XH02-P0SAD-134504 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SECURITY BUILDING | IFR | 2018-07-17 | 2018-10-16 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135104 | T16182-XH02-P0SAV-135104 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | IFR | 2017-04-30 | 2017-06-30 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 134104 | T16182-XH02-P0SAR-134104 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ST #1 LEB | IFR | 2017-06-22 | 2017-08-21 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134204 | T16182-XH02-P0SAR-134204 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR ST #2 LEB | IFR | 2017-07-22 | 2017-09-20 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134404 | T16182-XH02-P0SAN-134404 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR SUPPORT BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133604 | T16182-XH02-P0SAK-133604 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-04-15 | 2017-06-14 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 134804 | T16182-XH02-P0SAB-134804 | DUCT & REFRIGERANT PIPING PLAN OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2017-09-14 | 2017-11-13 |  |  |  | PKG-041-HVAC
EL(15) | Electrical | 152539 | T16182-YE03-P0BAU-152539 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - CHEMICAL DOSING SYSTEM | IFI | 2017-12-14 | 2018-03-14
EL(15) | Electrical | 152520 | T16182-YE03-P0BAU-152520 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COMPRESSOR SHELTER | IFI | 2017-07-01 | 2017-08-30
EL(15) | Electrical | 152532 | T16182-YE03-P0BAU-152532 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COOLED CONDENSER-1 | IFI | 2017-05-25 | 2017-07-24
EL(15) | Electrical | 152533 | T16182-YE03-P0BAU-152533 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AIR COOLED CONDENSER-2 | IFI | 2017-07-25 | 2017-09-23
EL(15) | Electrical | 152527 | T16182-YE03-P0BAU-152527 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - AUX. LEB | IFI | 2017-12-14 | 2018-03-14
EL(15) | Electrical | 152536 | T16182-YE03-P0BAU-152536 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - BLACK START DIESEL GENERATOR AREA | IFI | 2017-09-14 | 2017-12-13
EL(15) | Electrical | 152535 | T16182-YE03-P0BAU-152535 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FGS AREA | IFI | 2017-08-15 | 2017-10-14
EL(15) | Electrical | 152511 | T16182-YE03-P0BAU-152511 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FGS ELECTRICAL BUILDING | IFI | 2017-06-06 | 2017-08-05 |  | O
EL(15) | Electrical | 152534 | T16182-YE03-P0BAU-152534 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIN FAN COOLER & CCW PUMP AREA | IFI | 2017-07-25 | 2017-09-23
EL(15) | Electrical | 152517 | T16182-YE03-P0BAU-152517 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIRE BRIGADE | IFI | 2017-09-13 | 2017-11-15
EL(15) | Electrical | 152522 | T16182-YE03-P0BAU-152522 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - FIRE WATER PUMP HOUSE | IFI | 2017-06-29 | 2017-08-28
EL(15) | Electrical | 152514 | T16182-YE03-P0BAU-152514 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GATE HOUSE | IFI | 2018-02-06 | 2018-04-27
EL(15) | Electrical | 152529 | T16182-YE03-P0BAU-152529 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GTG & TR #1,2 AREA | IFI | 2017-08-01 | 2017-09-30
EL(15) | Electrical | 152530 | T16182-YE03-P0BAU-152530 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - GTG & TR #3,4,5 AREA | IFI | 2017-09-01 | 2017-10-31
EL(15) | Electrical | 152537 | T16182-YE03-P0BAU-152537 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - H2, CO2 STORAGE SHELTER | IFI | 2017-11-14 | 2018-02-12
EL(15) | Electrical | 152519 | T16182-YE03-P0BAU-152519 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - N2 STORAGE SHELTER | IFI | 2017-07-09 | 2017-09-07
EL(15) | Electrical | 152540 | T16182-YE03-P0BAU-152540 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - PRELIMINARY INSPECTION CHECK POINT (PIC) | IFI | 2018-06-14 | 2018-09-14
EL(15) | Electrical | 152516 | T16182-YE03-P0BAU-152516 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - SEARCH FACILITY AND VISITORS CENTRE | IFI | 2018-02-06 | 2018-04-27
EL(15) | Electrical | 152508 | T16182-YE03-P6BAU-152508 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - ST #1 LEB | IFI | 2017-04-26 | 2017-06-30
EL(15) | Electrical | 152509 | T16182-YE03-P7BAU-152509 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - ST #2 LEB | IFI | 2017-04-26 | 2017-06-30
EL(15) | Electrical | 152531 | T16182-YE03-P0BAU-152531 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - STG TR AREA | IFI | 2018-01-20 | 2018-03-21
EL(15) | Electrical | 152515 | T16182-YE03-P0BAU-152515 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - SUPPORT BUILDING | IFI | 2018-02-06 | 2018-02-02
EL(15) | Electrical | 152523 | T16182-YE03-P0BAU-152523 | EARTHING & LIGHTNING PROTECTION LAYOUT DRAWING - WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-05-31 | 2017-07-30
EL(15) | Electrical | 152538 | T16182-YE03-P0BAU-152538 | EARTHING LAYOUT DRAWING - 380kV EHV CABLE INSULATION JOINT AREA | IFI | 2017-11-14 | 2018-02-12
EL(15) | Electrical | 152512 | T16182-YE03-P0BAU-152512 | EARTHING LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | IFI | 2017-09-16 | 2017-11-15
EL(15) | Electrical | 152505 | T16182-YE03-P0BAU-152505 | EARTHING LAYOUT DRAWING - CENTRAL CONTROL BUILDING | IFR | 2017-01-26 | 2017-04-08 |  | O
EL(15) | Electrical | 152525 | T16182-YE03-P0BAU-152525 | EARTHING LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | IFI | 2017-08-15 | 2017-09-29
EL(15) | Electrical | 152521 | T16182-YE03-P0BAU-152521 | EARTHING LAYOUT DRAWING - DEAERATOR SUPPORT STRUCTURE | IFI | 2017-05-23 | 2017-07-22
EL(15) | Electrical | 152506 | T16182-YE03-P0BAU-152506 | EARTHING LAYOUT DRAWING - GTG #1,2 LEB | IFR | 2017-02-04 | 2017-04-30 |  | O
EL(15) | Electrical | 152507 | T16182-YE03-P0BAU-152507 | EARTHING LAYOUT DRAWING - GTG #3,4,5 LEB | IFI | 2017-03-15 | 2017-06-30
EL(15) | Electrical | 152504 | T16182-YE03-P0BAU-152504 | EARTHING LAYOUT DRAWING - MAIN GRID | IFR | 2017-01-26 | 2017-04-08 |  | O
EL(15) | Electrical | 152526 | T16182-YE03-P0BAU-152526 | EARTHING LAYOUT DRAWING - PIPE RACK FOR HRSG | IFI | 2017-11-02 | 2018-02-02
EL(15) | Electrical | 152513 | T16182-YE03-P0BAU-152513 | EARTHING LAYOUT DRAWING - SECURITY BUILDING | IFI | 2018-07-01 | 2018-08-30
EL(15) | Electrical | 152510 | T16182-YE03-P0BAU-152510 | EARTHING LAYOUT DRAWING - ST BUILDING | IFI | 2017-05-16 | 2017-07-15
EL(15) | Electrical | 152528 | T16182-YE03-P0BAU-152528 | EARTHING LAYOUT DRAWING - TANK AREA | IFI | 2017-06-30 | 2017-08-29
EL(15) | Electrical | 152524 | T16182-YE03-P0BAU-152524 | EARTHING LAYOUT DRAWING - WATER TREATMENT BUILDING | IFI | 2017-02-25 | 2017-06-30 |  | O
EL(15) | Electrical | 152518 | T16182-YE03-P0BAU-152518 | EARTHING LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | IFI | 2017-11-11 | 2018-01-10
CV(17) | Civil | 172613 | T16182-VK02-P0UAZ-172613 | EHV CABLE TRENCH & DIRECT BURIED CABLE DETAIL | IFR | 2017-04-11 | 2017-07-02 |  | O
CV(17) | Civil | 172603 | T16182-XB02-P0UAZ-172603 | EHV CABLE TRENCH & DIRECT BURIED CABLE LAYOUT | IFR | 2017-04-11 | 2017-07-02 |  | O
CV(17) | Civil | 172602 | T16182-XB02-P0UAZ-172602 | EHV CABLE TRENCH & DIRECT BURIED CABLE OVERALL LAYOUT | IFR | 2017-04-11 | 2017-07-02 |  | O
CV(17) | Civil | 172608 | T16182-XB02-P0UAZ-172608 | EHV CABLE TRENCH & DIRECT BURIED CABLE PLAN & SECTION | IFR | 2017-04-11 | 2017-07-02 |  | O
EL(15) | Electrical | 150404 | T16182-YF00-P0BA-150404 | ELECTRICAL CONTROL LOGIC DIAGRAM - GSUT / OVERALL PROTECTION FOR STG UNIT | IFR | 2017-04-14 | 2017-08-25
EL(15) | Electrical | 150401 | T16182-YF00-P0BA-150401 | ELECTRICAL CONTROL LOGIC DIAGRAM - GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | IFR | 2017-04-14 | 2017-08-25 |  | O
EL(15) | Electrical | 150403 | T16182-YF00-P0BB-150403 | ELECTRICAL CONTROL LOGIC DIAGRAM - LV SWITCHGEAR | IFR | 2017-04-14 | 2017-08-11 |  | O |  | PKG-035-LVSWGR
EL(15) | Electrical | 150402 | T16182-YF00-P0BB-150402 | ELECTRICAL CONTROL LOGIC DIAGRAM - MV SWITCHGEAR | IFR | 2017-04-14 | 2017-08-25 |  | O |  | PKG-034-MVSWGR
GN-I&C(29) | Instrumentation & Control | 290001 | T16182-YS00-P0CJN-290001 | ELECTRICAL DIAGRAM STATIC EXCITATION SYSTEM FOR ST | IFR | 2017-04-10 | 2017-09-30 |  |  |  | PKG-040-STG
MCH(13) | Mechanical | 130602 | T16182-YS01-P0GK-130602 | ELECTRICAL DRAWING FOR POTABLE WATER CHILLER | IFI | 2017-12-08
CV(17) | Civil | 172703 | T16182-XB02-P0UZT-172703 | ELECTRICAL DUCT BANK LAYOUT | IFR | 2017-07-01 | 2017-09-15
EL(15) | Electrical | 152766 | T16182-YE00-P0ZEN-152766 | ELECTRICAL DUCT BANK LAYOUT ADMINISTRATION & SOCIAL BUILDING AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152759 | T16182-YE00-P0ZEN-152759 | ELECTRICAL DUCT BANK LAYOUT AIR COMPRESSOR & ACC AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152764 | T16182-YE00-P0ZEN-152764 | ELECTRICAL DUCT BANK LAYOUT CPP REGEN BUILDING AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152750 | T16182-YE00-P0ZEN-152750 | ELECTRICAL DUCT BANK LAYOUT DRAWING CENTRAL CONTROL BUILDING AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152769 | T16182-YE00-P0ZEN-152769 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 1 | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152770 | T16182-YE00-P0ZEN-152770 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 2 | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152771 | T16182-YE00-P0ZEN-152771 | ELECTRICAL DUCT BANK LAYOUT EHV CABLE AREA - 3 | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152765 | T16182-YE00-P0ZEN-152765 | ELECTRICAL DUCT BANK LAYOUT FGS & RESERVE BOILER AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152751 | T16182-YE00-P0ZEN-152751 | ELECTRICAL DUCT BANK LAYOUT GTG #1 AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152752 | T16182-YE00-P0ZEN-152752 | ELECTRICAL DUCT BANK LAYOUT GTG #2 AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152753 | T16182-YE00-P0ZEN-152753 | ELECTRICAL DUCT BANK LAYOUT GTG #3,#4 AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152754 | T16182-YE00-P0ZEN-152754 | ELECTRICAL DUCT BANK LAYOUT GTG #5 AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152755 | T16182-YE00-P0ZEN-152755 | ELECTRICAL DUCT BANK LAYOUT HRSG #1 AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152756 | T16182-YE00-P0ZEN-152756 | ELECTRICAL DUCT BANK LAYOUT HRSG #2 AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152757 | T16182-YE00-P0ZEN-152757 | ELECTRICAL DUCT BANK LAYOUT HRSG #3,#4 AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152758 | T16182-YE00-P0ZEN-152758 | ELECTRICAL DUCT BANK LAYOUT HRSG #5 AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152768 | T16182-YE00-P0ZEN-152768 | ELECTRICAL DUCT BANK LAYOUT MAIN GATE HOUSE AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152767 | T16182-YE00-P0ZEN-152767 | ELECTRICAL DUCT BANK LAYOUT SECURITY BUILDING AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152760 | T16182-YE00-P0ZEN-152760 | ELECTRICAL DUCT BANK LAYOUT ST #1 LEB | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152761 | T16182-YE00-P0ZEN-152761 | ELECTRICAL DUCT BANK LAYOUT ST #2 LEB | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152762 | T16182-YE00-P0ZEN-152762 | ELECTRICAL DUCT BANK LAYOUT TANK AREA | IFI | 2017-01-26 | 2017-09-25
EL(15) | Electrical | 152763 | T16182-YE00-P0ZEN-152763 | ELECTRICAL DUCT BANK LAYOUT WATER TREATMENT BUILDING AREA | IFI | 2017-01-26 | 2017-09-25
CV(17) | Civil | 172716 | T16182-XB02-P0UZT-172716 | ELECTRICAL DUCT BANK MANHOLE PLAN, SECTION & R.C DETAILS | IFR | 2017-07-01 | 2017-09-15
CV(17) | Civil | 172713 | T16182-VK02-P0UZT-172713 | ELECTRICAL DUCT BANK MANHOLE SCHEDULE | IFR | 2017-07-01 | 2017-09-15
CV(17) | Civil | 172702 | T16182-XB02-P0UZT-172702 | ELECTRICAL DUCT BANK OVERALL LAYOUT | IFR | 2017-07-01 | 2017-09-15
CV(17) | Civil | 172704 | T16182-VK02-P0UZT-172704 | ELECTRICAL DUCT BANK TYPICAL SECTION & R.C DETAILS | IFR | 2017-07-01 | 2017-09-15
EL(15) | Electrical | 150101 | T16182-YL06-P0ZEN-150101 | ELECTRICAL LOAD LIST | IFR | 2017-01-31 | 2017-07-18 |  | O
EL(15) | Electrical | 150501 | T16182-YD00-P0UCA-150501 | ELECTRICAL ROOM LAYOUT DRAWING - CENTRAL CONTROL BUILDING | IFR | 2017-01-31 | 2017-06-13 |  | O
EL(15) | Electrical | 150502 | T16182-YD00-P0UBA-150502 | ELECTRICAL ROOM LAYOUT DRAWING - GTG #1,2 LEB | IFR | 2017-01-31 | 2017-06-13 |  | O
EL(15) | Electrical | 150503 | T16182-YD00-P0UBA-150503 | ELECTRICAL ROOM LAYOUT DRAWING - GTG #3,4,5 LEB | IFR | 2017-01-31 | 2017-06-13
EL(15) | Electrical | 150504 | T16182-YD00-P0UBA-150504 | ELECTRICAL ROOM LAYOUT DRAWING - STG #1 LEB | IFR | 2017-04-30 | 2017-09-10
EL(15) | Electrical | 150505 | T16182-YD00-P0UBA-150505 | ELECTRICAL ROOM LAYOUT DRAWING - STG #2 LEB | IFR | 2017-04-30 | 2017-09-10
EL(15) | Electrical | 150506 | T16182-YD00-P0UBA-150506 | ELECTRICAL ROOM LAYOUT DRAWING - WATER TREATMENT PLANT BUILDING | IFR | 2017-02-28 | 2017-07-11 |  | O
EL(15) | Electrical | 150508 | T16182-YD00-P0UBA-150508 | ELECTRICAL ROOM LAYOUT DRAWING –AUX. LEB | IFR | 2017-05-31 | 2017-10-11
EL(15) | Electrical | 152709 | T16182-YE00-P0ZEN-152709 | EMBEDDED CONDUIT LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2017-09-01 | 2017-10-31
EL(15) | Electrical | 152718 | T16182-YE00-P0ZEN-152718 | EMBEDDED CONDUIT LAYOUT FOR AIR COMPRESSOR SHELTER | IFI | 2017-07-01 | 2017-08-30
EL(15) | Electrical | 152725 | T16182-YE00-P0ZEN-152725 | EMBEDDED CONDUIT LAYOUT FOR CHEMICAL DOSING SHELTER FOR HRSG | IFI | 2017-10-25 | 2017-12-08
EL(15) | Electrical | 152724 | T16182-YE00-P0ZEN-152724 | EMBEDDED CONDUIT LAYOUT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | IFI | 2017-10-18 | 2017-12-08
EL(15) | Electrical | 152733 | T16182-YE00-P0ZEN-152733 | EMBEDDED CONDUIT LAYOUT FOR CONDENSATE STORAGE TANK AREA | IFI | 2017-07-14 | 2017-09-12
EL(15) | Electrical | 152719 | T16182-YE00-P0ZEN-152719 | EMBEDDED CONDUIT LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2017-05-23 | 2017-07-22
EL(15) | Electrical | 152732 | T16182-YE00-P0ZEN-152732 | EMBEDDED CONDUIT LAYOUT FOR DEMI WATER STORAGE TANK AREA | IFI | 2017-06-09 | 2017-08-08
EL(15) | Electrical | 152708 | T16182-YE00-P0ZEN-152708 | EMBEDDED CONDUIT LAYOUT FOR FGS ELECTRICAL BUILDING | IFI | 2017-05-22 | 2017-07-21 |  | O
EL(15) | Electrical | 152735 | T16182-YE00-P0ZEN-152735 | EMBEDDED CONDUIT LAYOUT FOR FIN FAN COOLER(CCW) & CCW PUMP AREA | IFI | 2017-07-07 | 2017-09-05
EL(15) | Electrical | 152715 | T16182-YE00-P0ZEN-152715 | EMBEDDED CONDUIT LAYOUT FOR FIRE BRIGADE | IFI | 2017-08-29 | 2017-12-08
EL(15) | Electrical | 152720 | T16182-YE00-P0ZEN-152720 | EMBEDDED CONDUIT LAYOUT FOR FIRE WATER PUMP HOUSE & FIN FAN COOLER(CPP) | IFI | 2017-06-29 | 2017-08-28
EL(15) | Electrical | 152726 | T16182-YE00-P0ZEN-152726 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #1 | IFI | 2017-05-23 | 2017-07-22
EL(15) | Electrical | 152727 | T16182-YE00-P0ZEN-152727 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #2 | IFI | 2017-08-21 | 2017-10-20
EL(15) | Electrical | 152728 | T16182-YE00-P0ZEN-152728 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #3 | IFI | 2017-08-21 | 2017-10-20
EL(15) | Electrical | 152729 | T16182-YE00-P0ZEN-152729 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #4 | IFI | 2017-05-23 | 2017-07-22
EL(15) | Electrical | 152730 | T16182-YE00-P0ZEN-152730 | EMBEDDED CONDUIT LAYOUT FOR GTG TRANSFORMER AREA #5 | IFI | 2017-08-21 | 2017-10-20
EL(15) | Electrical | 152717 | T16182-YE00-P0ZEN-152717 | EMBEDDED CONDUIT LAYOUT FOR H2, CO2, N2 STORAGE SHELTER | IFI | 2017-06-24 | 2017-08-23
EL(15) | Electrical | 152711 | T16182-YE00-P0ZEN-152711 | EMBEDDED CONDUIT LAYOUT FOR MAIN GATE HOUSE AREA | IFI | 2018-01-22 | 2018-05-15
EL(15) | Electrical | 152731 | T16182-YE00-P0ZEN-152731 | EMBEDDED CONDUIT LAYOUT FOR POTABLE STORAGE WATER TANK & FIRE WATER TANK AREA | IFI | 2017-06-09 | 2017-08-08
EL(15) | Electrical | 152710 | T16182-YE00-P0ZEN-152710 | EMBEDDED CONDUIT LAYOUT FOR SECURITY BUILDING | IFI | 2018-06-16 | 2018-07-10
EL(15) | Electrical | 152705 | T16182-YE00-P0ZEN-152705 | EMBEDDED CONDUIT LAYOUT FOR ST #1 LEB | IFI | 2017-04-28 | 2017-06-30
EL(15) | Electrical | 152706 | T16182-YE00-P0ZEN-152706 | EMBEDDED CONDUIT LAYOUT FOR ST #2 LEB | IFI | 2017-04-28 | 2017-06-30
EL(15) | Electrical | 152707 | T16182-YE00-P0ZEN-152707 | EMBEDDED CONDUIT LAYOUT FOR ST BUILDING | IFI | 2017-05-17 | 2017-07-16
EL(15) | Electrical | 152736 | T16182-YE00-P0ZEN-152736 | EMBEDDED CONDUIT LAYOUT FOR STG TRANSFORMER AREA #1,#2 | IFI | 2017-06-16 | 2017-08-15
EL(15) | Electrical | 152722 | T16182-YE00-P0ZEN-152722 | EMBEDDED CONDUIT LAYOUT FOR WATER TREATMENT BUILDING | IFI | 2017-02-28 | 2017-06-30 |  | O
EL(15) | Electrical | 152716 | T16182-YE00-P0ZEN-152716 | EMBEDDED CONDUIT LAYOUT FOR WORKSHOP & STORAGE BUILDING | IFI | 2017-10-27 | 2017-12-26
EL(15) | Electrical | 152721 | T16182-YE00-P0ZEN-152721 | EMBEDDED CONDUIT LAYOUT FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-05-31 | 2017-07-30
EM(02) | Engineering Management | 020002 | T16182-DA01-P0ZEN-020002 | EQUIPMENT AND SYSTEM IDENTIFICATION | IFI | 2017-01-30 |  |  | O
PS(11) | Mechanical | 110501 | T16182-YK08-P0QJA-110501 | EQUIPMENT ASSEMBLY AND DETAIL DRAWING FOR NITROGEN GAS SYSTEM | IFI | 2017-06-15 | 2017-08-14 |  | O |  | PKG-006-N2
MCH(13) | Mechanical | 130212 | T16182-YK09-P0LD-130212 | EQUIPMENT ASSEMBLY DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2017-08-02 | 2017-10-01 |  |  |  | PKG-026-CPP
MCH(13) | Mechanical | 130107 | T16182-XN00-P0GNR-130107 | EQUIPMENT ASSEMBLY DRAWING FOR WASTE WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-06-30 |  | O |  | PKG-025-WT
MCH(13) | Mechanical | 130012 | T16182-YK09-P0GCF-130012 | EQUIPMENT ASSEMBLY DRAWING FOR WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-06-30 |  | O |  | PKG-025-WT
MCH(13) | Mechanical | 130503 | T16182-XL00-P0STG-130503 | EQUIPMENT LIST FOR CHEMICAL LABORATORY | IFR | 2017-08-04 | 2017-11-30 |  |  |  | PKG-029-CLAB
MCH(13) | Mechanical | 134003 | T16182-XW03-P0SAL-134003 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ADMIN & SOCIAL BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135203 | T16182-XW03-P0SAQ-135203 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR AUX. LEB | IFR | 2018-01-18 | 2018-02-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133503 | T16182-XW03-P0SAC-133503 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-03-17 | 2017-05-01 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 135003 | T16182-XW03-P0SAM-135003 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR CPP & CPP REGEN BUILDING | IFR | 2017-08-29 | 2017-10-28 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133703 | T16182-XW03-P0SAJ-133703 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-08-04 | 2017-10-03 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 134703 | T16182-XW03-P0SAF-134703 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FIRE BRIGADE | IFR | 2017-10-29 | 2017-12-28 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134903 | T16182-XW03-P0SAG-134903 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-06-14 | 2017-08-13 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 133803 | T16182-XW03-P0SAI-133803 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR GTG #1/2 LEB | IFR | 2017-03-26 | 2017-05-15 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 133903 | T16182-XW03-P0SAI-133903 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR GTG #3/4/5 LEB | IFR | 2017-04-30 | 2017-06-29 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134303 | T16182-XW03-P0SAE-134303 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR MAIN GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135403 | T16182-XW03-P0SAE-135403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR PIC GATE HOUSE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135303 | T16182-XW03-P0SAE-135303 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR PLANT ACCESS GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134603 | T16182-XW03-P0SAE-134603 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SEARCH FACILITY & VISITORS CENTRE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134503 | T16182-XW03-P0SAD-134503 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SECURITY BUILDING | IFR | 2018-07-17 | 2018-10-16 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135103 | T16182-XW03-P0SAV-135103 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | IFR | 2017-04-30 | 2017-06-30 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 134103 | T16182-XW03-P0SAR-134103 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ST#1 LEB | IFR | 2017-06-22 | 2017-08-21 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134203 | T16182-XW03-P0SAR-134203 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR ST#2 LEB | IFR | 2017-07-22 | 2017-09-20 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133403 | T16182-XW03-P0SAH-133403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR STEAM TURBINE BUILDING | IFR | 2017-06-14 | 2017-08-13 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134403 | T16182-XW03-P0SAN-134403 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR SUPPORT BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133603 | T16182-XW03-P0SAK-133603 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR WATER TREATMENT BUILDING | IFR | 2017-04-15 | 2017-06-14 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 134803 | T16182-XW03-P0SAB-134803 | EQUIPMENT SCHEDULE OF HVAC SYSEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2017-09-14 | 2017-11-13 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 130501 | T16182-XW01-P0STG-130501 | EQUIPMENT SPECIFICATION FOR CHEMICAL LABORATORY | IFI | 2017-08-04 |  |  |  |  | PKG-029-CLAB
GN-I&C(29) | Instrumentation & Control | 290002 | T16182-YR05-P0CJN-290002 | EXCITER PANEL OUTLINE DRAWING FOR ST | IFR | 2017-03-10 | 2017-05-10 |  |  |  | PKG-040-STG
PP(14) | Mechanical | 140109 | T16182-XJ00-P0PGB-140109 | FABRICATION ISOMETRIC DRAWING FOR CLOSED COOLING WATER SYSTEM | IFI | 2017-09-08 | 2017-11-03 |  | O
PP(14) | Mechanical | 140106 | T16182-XJ00-P0LCA-140106 | FABRICATION ISOMETRIC DRAWING FOR CONDENSATE SYSTEM | IFI | 2017-09-08 | 2017-11-03
PP(14) | Mechanical | 140113 | T16182-XJ00-P0GHC-140113 | FABRICATION ISOMETRIC DRAWING FOR DEMI WATER SYSTEM | IFI | 2017-09-08 | 2017-11-03 |  | O
PP(14) | Mechanical | 140108 | T16182-XJ00-P0LAB-140108 | FABRICATION ISOMETRIC DRAWING FOR FEED WATER SYSTEM | IFI | 2017-09-08 | 2017-11-03 |  | O
PP(14) | Mechanical | 140118 | T16182-XJ00-P0EKG-140118 | FABRICATION ISOMETRIC DRAWING FOR FUEL GAS SYSTEM | IFI | 2017-09-08 | 2017-10-13 |  | O
PP(14) | Mechanical | 140117 | T16182-XJ00-P0EKC-140117 | FABRICATION ISOMETRIC DRAWING FOR GT PERFORMANCE HEATER SYSTEM | IFI | 2017-10-20 | 2017-11-24
PP(14) | Mechanical | 140116 | T16182-XJ00-P0MBH-140116 | FABRICATION ISOMETRIC DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM | IFI | 2017-10-20 | 2017-11-24
PP(14) | Mechanical | 140101 | T16182-XJ00-P0LBA-140101 | FABRICATION ISOMETRIC DRAWING FOR HP STEAM SYSTEM | IFI | 2017-10-06 | 2017-12-08
PP(14) | Mechanical | 140102 | T16182-XJ00-P0LBC-140102 | FABRICATION ISOMETRIC DRAWING FOR IP STEAM SYSTEM | IFI | 2017-10-06 | 2017-12-14
PP(14) | Mechanical | 140103 | T16182-XJ00-P0LBG-140103 | FABRICATION ISOMETRIC DRAWING FOR LP STEAM SYSTEM | IFI | 2017-10-06 | 2017-12-20 |  | O
PP(14) | Mechanical | 140112 | T16182-XJ00-P0GKB-140112 | FABRICATION ISOMETRIC DRAWING FOR POTABLE WATER SYSTEM | IFI | 2017-09-08 | 2017-11-03 |  | O
PP(14) | Mechanical | 140104 | T16182-XJ00-P0LBG-140104 | FABRICATION ISOMETRIC DRAWING FOR PROCESS STEAM SYSTEM | IFI | 2017-09-08 | 2017-10-13 |  | O
PP(14) | Mechanical | 140110 | T16182-XJ00-P0SCA-140110 | FABRICATION ISOMETRIC DRAWING FOR SERVICE AIR SYSTEM | IFI | 2018-11-23 | 2018-12-14
PP(14) | Mechanical | 140105 | T16182-XJ00-P0LCM-140105 | FABRICATION ISOMETRIC DRAWING FOR STEAM DRAIN SYSTEM | IFI | 2017-12-01 | 2018-02-23
PP(14) | Mechanical | 140119 | T16182-XJ00-P0ZEN-140119 | FABRICATION ISOMETRIC DRAWING FOR TG MISCELLANEOUS SYSTEM | IFI | 2018-03-09 | 2018-04-13
PP(14) | Mechanical | 140114 | T16182-XJ00-P0PDA-140114 | FABRICATION ISOMETRIC DRAWING FOR TREATED EFFLUENT COLLECTION AND TRANSFER SYSTEM | IFI | 2017-10-06 | 2017-11-10 |  | O
PP(14) | Mechanical | 140121 | T16182-XJ00-P0GM-140121 | FABRICATION ISOMETRIC DRAWING FOR WASTE WATER SYSTEM | IFI | 2018-02-16 | 2018-03-16
PP(14) | Mechanical | 140100 | T16182-XJ00-P0ZEN-140100 | FABRICATION STANDARD DRAWING | IFI | 2017-10-20
CV(17) | Civil | 173202 | T16182-XB02-P0UZJ-173202 | FENCE AND GATE OVERALL LAYOUT | IFR | 2018-07-01 | 2018-09-29
CV(17) | Civil | 173208 | T16182-VK02-P0UZJ-173208 | FENCE AND GATE PLAN AND DETAIL | IFR | 2018-07-01 | 2018-09-29
PT(12) | Mechanical | 127006 | T16182-YT01-P0LCB-127006 | FGP COP - COUPLING SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-019-COP
PT(12) | Mechanical | 127003 | T16182-YT01-P0LCB-127003 | FGP COP - DATA SHEET & CHARACTERISTIC CURVE | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-019-COP
PT(12) | Instrumentation & Control | 127011 | T16182-YK09-P0LCB-127011 | FGP COP - EMERGENCY PUSH BUTTON DRAWING | IFI | 2017-07-15 |  |  |  |  | PKG-019-COP
PT(12) | Mechanical | 127009 | T16182-YD00-P0LCB-127009 | FGP COP - FOUNDATION DRAWINGS | IFI | 2017-07-15 | 2017-12-12 |  |  |  | PKG-019-COP
PT(12) | Mechanical | 127001 | T16182-YD00-P0LCB-127001 | FGP COP - GENERAL ARRANGEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-019-COP
PT(12) | Instrumentation & Control | 127013 | T16182-YL00-P0LCB-127013 | FGP COP - INSTRUMENT LIST AND DATA SHEET | IFI | 2017-07-15 |  |  |  |  | PKG-019-COP
PT(12) | Instrumentation & Control | 127015 | T16182-YK00-P0LCB-127015 | FGP COP - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-09-30 |  |  |  |  | PKG-019-COP
PT(12) | Mechanical | 127005 | T16182-YT01-P0LCB-127005 | FGP COP - MECHANICAL SEAL SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-019-COP
PT(12) | Electrical | 127010 | T16182-YM01-P0LCB-127010 | FGP COP - MOTOR DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-07-15 |  |  |  |  | PKG-019-COP
PT(12) | Mechanical | 127018 | T16182-YL22-P0LCB-127018 | FGP COP - NAME PLATE DRAWING | IFI | 2017-09-30 |  |  |  |  | PKG-019-COP
PT(12) | Mechanical | 127002 | T16182-XG02-P0LCB-127002 | FGP COP - P&I DIAGRAM | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-019-COP
PT(12) | Mechanical | 127004 | T16182-YK09-P0LCB-127004 | FGP COP - PUMP SECTIONAL DRAWING | IFI | 2017-07-31 | 2017-12-28 |  |  |  | PKG-019-COP
PT(12) | Mechanical | 127007 | T16182-YT01-P0LCB-127007 | FGP COP - SUCTION STRAINER SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-019-COP
PT(12) | Instrumentation & Control | 127016 | T16182-YT01-P0LCB-127016 | FGP COP - VMS SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-019-COP
PT(12) | Instrumentation & Control | 126352 | T16182-YS02-P0LAC-126352 | FGP FEEDWATER PUMP - CABLE INTERCONNECTION WIRING DIAGRAM | IFI | 2018-02-15 |  |  |  |  | PKG-017-FFWP
PT(12) | Electrical | 126055 | T16182-YT01-P0LAC-126055 | FGP FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | IFI | 2017-08-08 | 2017-11-05 |  |  |  | PKG-017-FFWP
PT(12) | Mechanical | 126054 | T16182-YT01-P0LAC-126054 | FGP FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | IFR | 2017-08-08 | 2017-11-05 | O |  |  | PKG-017-FFWP
PT(12) | Electrical | 126069 | T16182-YD00-P0LAC-126069 | FGP FEEDWATER PUMP - EMERGENCY PUSH BUTTON DRAWING | IFI | 2017-07-29 |  |  |  |  | PKG-017-FFWP
PT(12) | Mechanical | 126077 | T16182-YK08-P0LAC-126077 | FGP FEEDWATER PUMP - FLEXIBLE COUPLING DATA SHEET & DRAWING | IFI | 2017-09-28 |  |  |  |  | PKG-017-FFWP
PT(12) | Mechanical | 126051 | T16182-YD00-P0LAC-126051 | FGP FEEDWATER PUMP - GENERAL ARRANGEMENT DRAWING | IFR | 2017-08-08 | 2017-11-05 | O |  |  | PKG-017-FFWP
PT(12) | Instrumentation & Control | 126351 | T16182-YB11-P0LAC-126351 | FGP FEEDWATER PUMP - I&C JUNCTION BOX DRAWING | IFI | 2018-02-15 |  |  |  |  | PKG-017-FFWP
PT(12) | Mechanical | 126062 | T16182-DM01-P0LAC-126062 | FGP FEEDWATER PUMP - INSTALLATION MANUAL | IFI | 2017-09-25 | 2018-07-26 |  |  |  | PKG-017-FFWP
PT(12) | Instrumentation & Control | 126061 | T16182-YT02-P0LAC-126061 | FGP FEEDWATER PUMP - LIST AND DATA SHEET FOR INSTRUMENT | IFI | 2017-08-08 |  |  |  |  | PKG-017-FFWP
PT(12) | Mechanical | 126057 | T16182-YD00-P0LAC-126057 | FGP FEEDWATER PUMP - NAME PLATE DRAWING | IFI | 2017-08-08 |  |  |  |  | PKG-017-FFWP
PT(12) | Mechanical | 126066 | T16182-YT01-P0LAC-126066 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR LUBE OIL UNIT | IFI | 2017-09-16 |  |  |  |  | PKG-017-FFWP
PT(12) | Mechanical | 126060 | T16182-YD00-P0LAC-126060 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR MECHANICA SEAL | IFI | 2017-08-08 | 2017-11-08 |  |  |  | PKG-017-FFWP
PT(12) | Mechanical | 126059 | T16182-YT01-P0LAC-126059 | FGP FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR SUCTION STRAINER | IFI | 2017-08-08 | 2018-07-16 |  |  |  | PKG-017-FFWP
PT(12) | Mechanical | 126053 | T16182-XG02-P0LAC-126053 | FGP FEEDWATER PUMP - P&I DIAGRAM | IFR | 2017-08-08 | 2017-11-05 | O |  |  | PKG-017-FFWP
PT(12) | Mechanical | 126056 | T16182-YK01-P0LAC-126056 | FGP FEEDWATER PUMP - SECTIONAL DRAWING FOR PUMP | IFI | 2017-08-08 | 2018-07-16 |  |  |  | PKG-017-FFWP
PT(12) | Mechanical | 124180 | T16182-YB03-P0EKG-124180 | FGS - 120V TR PANEL FOR GAS CHROMATOGRAPH | IFI | 2018-08-16 |  |  |  |  | PKG-014-FGS
PT(12) | Mechanical | 124006 | T16182-YK10-P0EKG-124006 | FGS - 2ND GAS PRESSURE REDUCING STATION ASSEMBLY DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124027 | T16182-YT01-P0EKG-124027 | FGS - 2ND GAS PRESSURE REDUCING STATION DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124032 | T16182-YT01-P0EKG-124032 | FGS - BOOSTER COMPRESSOR DATA SHEET | IFI | 2017-05-28 |  |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124024 | T16182-YT01-P0EKG-124024 | FGS - BOOSTER COMPRESSOR OUTLINE DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124033 | T16182-YT01-P0EKG-124033 | FGS - BUFFER TANK DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124023 | T16182-XN00-P0EKG-124023 | FGS - BUFFER TANK OUTLINE DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS
PT(12) | Electrical | 124015 | T16182-XB02-P0EKG-124015 | FGS - CABLE BLOCK DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS
PT(12) | Electrical | 124012 | T16182-YD00-P0EKG-124012 | FGS - CABLE ROUTE LAYOUT FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-05-28 | 2018-01-29 |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124007 | T16182-YK10-P0EKG-124007 | FGS - COLD VENT STACK ASSEMBLY DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124028 | T16182-YT01-P0EKG-124028 | FGS - COLD VENT STACK DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124008 | T16182-YK10-P0EKG-124008 | FGS - CONDENSATE COLLECTING TANK & CONDENSATE PUMP ASSEMBLY DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124029 | T16182-YT01-P0EKG-124029 | FGS - CONDENSATE COLLECTING TANK & CONDENSATE PUMP DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS
PT(12) | Instrumentation & Control | 124014 | T16182-YE00-P0EKG-124014 | FGS - CONTROL LOOP, LOGIC DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-05-28 |  |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124011 | T16182-YD00-P0EKG-124011 | FGS - ESD VALVE ASSEMBLY DRAWING | IFI | 2017-05-28 | 2017-07-30 |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124031 | T16182-YT01-P0EKG-124031 | FGS - ESD VALVE DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS
PT(12) | Civil | 124013 | T16182-YK10-P0EKG-124013 | FGS - FOUDATION & LOADS FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124001 | T16182-XG01-P0EKG-124001 | FGS - FUEL GAS SYSTEM GENERAL LAYOUT DRAWING | IFR | 2017-02-28 | 2017-05-31 | O | O |  | PKG-014-FGS
PT(12) | Instrumentation & Control | 124075 | T16182-UB01-P0EKG-124075 | FGS - FUNCTIONAL DESCRIPTION | IFI | 2017-11-01 | 2018-03-09 |  |  |  | PKG-014-FGS
PT(12) | Instrumentation & Control | 124030 | T16182-YT01-P0EKG-124030 | FGS - GAS CHROMATOGRAPH DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS
PT(12) | Instrumentation & Control | 124010 | T16182-YK10-P0EKG-124010 | FGS - GAS CHROMATOGRAPH OUTLINE DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124003 | T16182-XG07-P0EKG-124003 | FGS - GAS FILTER & SEPARATOR ASSEMBLY DRAWING | IFI | 2017-02-28 | 2017-07-30 |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124004 | T16182-YD00-P0EKG-124004 | FGS - GAS HEATER ASSEMBLY DRAWING | IFI | 2017-05-10 | 2017-07-30 |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124025 | T16182-YD00-P0EKG-124025 | FGS - GAS HEATER DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124005 | T16182-YK10-P0EKG-124005 | FGS - MAIN GAS PRESSURE REDUCING STATION ASSEMBLY DRAWING | IFI | 2017-04-10 | 2017-07-30 |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124026 | T16182-YD00-P0EKG-124026 | FGS - MAIN GAS PRESSURE REDUCING STATION DATA SHEET | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS
PT(12) | Instrumentation & Control | 124018 | T16182-YD00-P0EKG-124018 | FGS - MEASUREMENT LIST FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-05-28 |  |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124002 | T16182-XH01-P0EKG-124002 | FGS - P&I DIAGRAM | IFR | 2017-02-28 | 2017-05-31 | O | O | O | PKG-014-FGS
PT(12) | Electrical | 124009 | T16182-YD00-P0EKG-124009 | FGS - PANEL LAYOUT FOR LOCAL ELECTRICAL ROOM FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS
PT(12) | Electrical | 124017 | T16182-YB03-P0EKG-124017 | FGS - SINGLE LINE DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-05-28 |  |  | O |  | PKG-014-FGS
PT(12) | Electrical | 124016 | T16182-YF00-P0EKG-124016 | FGS - TERMINAL BOX DRAWING FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-05-28 |  |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124022 | T16182-YV02-P0EKG-124022 | FGS - VALVE DATA SHEET | IFI | 2017-06-30 |  |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124021 | T16182-XS00-P0EKG-124021 | FGS - VALVE LIST | IFI | 2017-04-10 |  |  | O |  | PKG-014-FGS
PT(12) | Electrical | 124020 | T16182-BX03-P0EKG-124020 | FGS - WIRING DIAGRAM FOR FUEL GAS SUPPLY SYSTEM | IFI | 2017-05-28 |  |  | O |  | PKG-014-FGS
PT(12) | Mechanical | 124079 | T16182-YT01-P0EKG-124079 | FGS – DUPLEX STRAINER INSTRUMENT DATA & DRAWING | IFI | 2019-11-20
PT(12) | Mechanical | 124077 | T16182-XJ00-P0EKG-124077 | FGS – ISO DRAWING | Internal
PT(12) | Mechanical | 124078 | T16182-YL30-P0EKG-124078 | FGS – SALES GAS CONTROL VALVE STATION DOCUMENT & DRAWING | IFI | 2019-11-15
CV(17) | Civil | 171501 | T16182-VE04-P0UEG-171501 | FGS AREA FOUNDATION CALCULATION | IFR | 2017-04-29 | 2017-06-30 |  | O
CV(17) | Civil | 171502 | T16182-XB02-P0UEG-171502 | FGS AREA LAYOUT | IFR | 2017-04-29 | 2017-06-30 |  | O
CV(17) | Civil | 171504 | T16182-XB02-P0UEG-171504 | FGS AREA PLAN AND SECTION | IFR | 2017-04-29 | 2017-06-30 |  | O
S&A(18) | Structural & Architectural | 186100 | T16182-CA06-P0UBA-186100 | FGS ELECTRICAL BUILDING - CALCULATION | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 186156 | T16182-CA02-P0UBA-186156 | FGS ELECTRICAL BUILDING - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 186151 | T16182-CA01-P0UBA-186151 | FGS ELECTRICAL BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 186155 | T16182-CA02-P0UBA-186155 | FGS ELECTRICAL BUILDING - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 186152 | T16182-CA01-P0UBA-186152 | FGS ELECTRICAL BUILDING - GROUND FLOOR & ROOF FRAMING PLAN | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 186101 | T16182-CA00-P0UBA-186101 | FGS ELECTRICAL BUILDING - GROUND FLOOR, ROOF PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 186154 | T16182-CA01-P0UBA-186154 | FGS ELECTRICAL BUILDING - LINE & ROW FRAMING ELEVATION | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 186104 | T16182-CA00-P0UBA-186104 | FGS ELECTRICAL BUILDING - MAIN SECTION | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 186103 | T16182-CA00-P0UBA-186103 | FGS ELECTRICAL BUILDING - SIDE WALL ELEVATION | IFR | 2017-03-10 | 2017-05-10 |  | O
PT(12) | Mechanical | 124040 | T16182-YT01-P0EKG-124040 | FGS_DATASHEET AND OUTLINE DRAWING FOR GTG INLET STRAINERS | IFR | 2019-09-25 | 2019-10-25
GN-MCH(25) | Mechanical | 250015 | T16182-UC02-P0MKA-250015 | FIELD CLEARANCE DIAGRAM | IFI | 2017-08-17 |  |  |  |  | PKG-040-STG
I&C(16) | Instrumentation & Control | 163101 | T16182-YL00-P0ZEN-163101 | FIELD INSTRUMENT LIST FOR BOP | IFR | 2017-02-01 | 2017-09-15 |  | O
PT(12) | Mechanical | 126508 | T16182-XK00-P0PCA-126508 | FIN FAN COOLER - BELT PULLEY DATA SHEET | IFI | 2017-08-03 |  |  | O |  | PKG-018-FFC
PT(12) | Instrumentation & Control | 126519 | T16182-DE00-P0PCA-126519 | FIN FAN COOLER - CONTROL DESCRIPTION (PHILOSOPHY) | IFI | 2017-07-04 |  |  | O |  | PKG-018-FFC
PT(12) | Electrical | 126527 | T16182-YL01-P0PCA-126527 | FIN FAN COOLER - DRIVE LIST (MOVS, MOTORS, CONTROL VALVES, SOLENOID VALVES, ETC..) | IFI | 2017-06-04 |  |  | O |  | PKG-018-FFC
PT(12) | Mechanical | 126506 | T16182-XV00-P0PCA-126506 | FIN FAN COOLER - EQUIPMENT LIST | IFI | 2017-05-05 |  |  | O |  | PKG-018-FFC
PT(12) | Mechanical | 126509 | T16182-XS00-P0PCA-126509 | FIN FAN COOLER - FAN MOTOR DATA SHEET | IFI | 2017-08-03 |  |  | O |  | PKG-018-FFC
PT(12) | Mechanical | 126512 | T16182-YK08-P0PCA-126512 | FIN FAN COOLER - FAN OUTLINE DRAWING (WITH MOTOR) | IFI | 2017-08-03 | 2017-12-20 |  | O |  | PKG-018-FFC
PT(12) | Civil | 126538 | T16182-XK00-P0PCA-126538 | FIN FAN COOLER - FOUNDATION DRAWINGS / CIVIL LOADING DATA WITH EMBEDDED MATERIAL DRAWING (INCLUDE AUXILIARY EQUIPMENT) | IFI | 2017-06-20 | 2017-08-24 |  | O |  | PKG-018-FFC
PT(12) | Mechanical | 126503 | T16182-YD00-P0PCA-126503 | FIN FAN COOLER - GENERAL ARRANGEMENT & PLOT PLAN DRAWING | IFR | 2017-05-05 | 2017-08-03 | O | O |  | PKG-018-FFC
PT(12) | Instrumentation & Control | 126524 | T16182-YL01-P0PCA-126524 | FIN FAN COOLER - INSTRUMENT CATALOG | IFI | 2017-06-04 |  |  | O |  | PKG-018-FFC
PT(12) | Instrumentation & Control | 126526 | T16182-YL01-P0PCA-126526 | FIN FAN COOLER - INSTRUMENT DATA SHEET | IFI | 2017-07-04 |  |  | O |  | PKG-018-FFC
PT(12) | Instrumentation & Control | 126525 | T16182-YK00-P0PCA-126525 | FIN FAN COOLER - INSTRUMENT INSTALLATION DETAIL DRAWING | IFI | 2017-06-20 |  |  | O |  | PKG-018-FFC
PT(12) | Instrumentation & Control | 126523 | T16182-YL00-P0PCA-126523 | FIN FAN COOLER - INSTRUMENT LIST | IFI | 2017-06-04 |  |  | O |  | PKG-018-FFC
PT(12) | Instrumentation & Control | 126522 | T16182-YF00-P0PCA-126522 | FIN FAN COOLER - LOGIC / FUNCTIONAL LOOP DIAGRAMS | IFI | 2017-07-04 |  |  | O |  | PKG-018-FFC
PT(12) | Mechanical | 126502 | T16182-XG02-P0PCA-126502 | FIN FAN COOLER - P&I DIAGRAM | IFR | 2017-06-04 | 2017-09-02 | O | O |  | PKG-018-FFC
PT(12) | Mechanical | 126504 | T16182-XS00-P0PCA-126504 | FIN FAN COOLER - PERFORMANCE CURVE | IFR | 2017-06-04 | 2017-09-02 |  | O |  | PKG-018-FFC
PT(12) | Mechanical | 126517 | T16182-XH01-P0PCA-126517 | FIN FAN COOLER - PIPE LINE LIST | IFI | 2017-08-03 |  |  | O |  | PKG-018-FFC
PT(12) | Mechanical | 126516 | T16182-YK08-P0PCA-126516 | FIN FAN COOLER - PIPE MATERIAL SPECIFICATION | IFI | 2017-08-03 |  |  | O |  | PKG-018-FFC
PT(12) | Mechanical | 126514 | T16182-YK08-P0PCA-126514 | FIN FAN COOLER - PIPING ARRANGEMENT DRAWING | IFI | 2017-08-03 | 2017-12-20 |  | O |  | PKG-018-FFC
PT(12) | Mechanical | 126515 | T16182-YK08-P0PCA-126515 | FIN FAN COOLER - PIPING ISOMETRIC DRAWRING | IFI | 2017-10-04 | 2018-01-15 |  | O |  | PKG-018-FFC
PT(12) | Electrical | 126529 | T16182-YT02-P0PCA-126529 | FIN FAN COOLER - RACEWAY DRAWING | IFI | 2017-08-03 | 2018-11-27 |  | O |  | PKG-018-FFC
PT(12) | Civil | 126539 | T16182-XK00-P0PCA-126539 | FIN FAN COOLER - STEEL STRUCTURE CALCULATION | IFI | 2017-05-21 |  |  | O |  | PKG-018-FFC
PT(12) | Mechanical | 126501 | T16182-XS00-P0PCA-126501 | FIN FAN COOLER - SYSTEM DESCRIPTION | IFR | 2017-06-04 | 2017-09-02 | O | O |  | PKG-018-FFC
PT(12) | Mechanical | 126505 | T16182-YL25-P0PCA-126505 | FIN FAN COOLER - TERMINAL POINT LIST & DRAWING | IFI | 2017-05-05 |  |  | O |  | PKG-018-FFC
PT(12) | Mechanical | 126507 | T16182-XN00-P0PCA-126507 | FIN FAN COOLER - VALVE LIST | IFI | 2017-08-03 |  |  | O |  | PKG-018-FFC
PT(12) | Mechanical | 126513 | T16182-YK08-P0PCA-126513 | FIN FAN COOLER - VALVE OUTLINE DRAWING | IFI | 2017-08-03 |  |  | O |  | PKG-018-FFC
PT(12) | Electrical | 126533 | T16182-YB03-P0PCA-126533 | FIN FAN COOLER - WIRING DIAGRAMS FOR JUNCTION BOXES | IFI | 2017-07-04 |  |  | O |  | PKG-018-FFC
PT(12) | Electrical | 126540 | T16182-YK09-P0PCA-126540 | FIN FAN COOLER – DETAIL DRAWING FOR CLEANING COMPRESSOR | IFI | 2018-11-01 |  |  |  |  | PKG-018-FFC
MCH(13) | Instrumentation & Control | 139041 | T16182-YD00-P0CYE-139041 | FIRE ALARM SYSTEM LAYOUT FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-07-17 | 2018-10-15 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137741 | T16182-YD00-P0CYE-137741 | FIRE ALARM SYSTEM LAYOUT FOR AIR COMPRESSOR SHELTER | IFI | 2018-01-01 | 2018-04-01 | O | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138541 | T16182-YD00-P0CYE-138541 | FIRE ALARM SYSTEM LAYOUT FOR AUX. LEB | IFI | 2017-11-30 | 2018-01-10 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138241 | T16182-YD00-P0CYE-138241 | FIRE ALARM SYSTEM LAYOUT FOR BSDG DIESEL OIL DAY TANK | IFI | 2017-07-21 | 2017-10-19 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136741 | T16182-YD00-P0CYE-136741 | FIRE ALARM SYSTEM LAYOUT FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 | O | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139841 | T16182-YD00-P0CYE-139841 | FIRE ALARM SYSTEM LAYOUT FOR CHEMICAL DOSING SHELTER FOR HRSG | IFI | 2018-03-17 | 2018-06-15 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139741 | T16182-YD00-P0CYE-139741 | FIRE ALARM SYSTEM LAYOUT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | IFI | 2018-03-17 | 2018-06-15 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139641 | T16182-YD00-P0CYE-139641 | FIRE ALARM SYSTEM LAYOUT FOR CPP BUILDING | IFI | 2018-04-16 | 2018-07-15 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138941 | T16182-YD00-P0CYE-138941 | FIRE ALARM SYSTEM LAYOUT FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2017-07-03 | 2017-10-30 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137641 | T16182-YD00-P0CYE-137641 | FIRE ALARM SYSTEM LAYOUT FOR FGS ELECTRICAL BUILDING | IFI | 2017-11-12 | 2018-02-10 | O | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139441 | T16182-YD00-P0CYE-139441 | FIRE ALARM SYSTEM LAYOUT FOR FIRE BRIGADE BUILDING | IFI | 2018-05-03 | 2018-08-01 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137341 | T16182-YD00-P0CYE-137341 | FIRE ALARM SYSTEM LAYOUT FOR FIRE WATER PUMP HOUSE | IFI | 2017-05-17 | 2017-08-15 | O | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138341 | T16182-YD00-P0CYE-138341 | FIRE ALARM SYSTEM LAYOUT FOR GPRS AREA | IFI | 2017-07-19 | 2017-10-17 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136841 | T16182-YD00-P0CYE-136841 | FIRE ALARM SYSTEM LAYOUT FOR GTG #1,2 LEB | IFI | 2017-07-22 | 2017-10-20 | O | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136941 | T16182-YD00-P0CYE-136941 | FIRE ALARM SYSTEM LAYOUT FOR GTG #3,4,5 LEB | IFI | 2017-12-01 | 2018-03-01 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137041 | T16182-YD00-P0CYE-137041 | FIRE ALARM SYSTEM LAYOUT FOR GTG GSU TRANSFORMER | IFI | 2017-05-03 | 2017-08-01 | O | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138143 | T16182-YD00-P0CYE-138143 | FIRE ALARM SYSTEM LAYOUT FOR GTG LUBE OIL UNIT | IFI | 2019-01-10 | 2019-02-08 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137141 | T16182-YD00-P0CYE-137141 | FIRE ALARM SYSTEM LAYOUT FOR GTG UNIT AUX. TRANSFORMER | IFI | 2017-05-03 | 2017-08-01 | O | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138441 | T16182-YD00-P0CYE-138441 | FIRE ALARM SYSTEM LAYOUT FOR H2, CO2 GAS STORAGE SHELTER | IFI | 2017-09-04 | 2017-11-03 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138141 | T16182-YD00-P0CYE-138141 | FIRE ALARM SYSTEM LAYOUT FOR HRSG | IFI | 2017-11-12 | 2018-02-10 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139241 | T16182-YD00-P0CYE-139241 | FIRE ALARM SYSTEM LAYOUT FOR MAIN GATE HOUSE | IFI | 2018-05-03 | 2018-08-01 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139541 | T16182-YD00-P0CYE-139541 | FIRE ALARM SYSTEM LAYOUT FOR MAINTENANCE AND WORKSHOP & STORAGE BUILDING | IFI | 2018-07-01 | 2018-09-29 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138041 | T16182-YD00-P0CYE-138041 | FIRE ALARM SYSTEM LAYOUT FOR N2 GAS STORAGE SHELTER | IFI | 2017-07-03 | 2017-10-30 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137441 | T16182-YD00-P0CYE-137441 | FIRE ALARM SYSTEM LAYOUT FOR RESERVE BOILER | IFI | 2017-10-18 | 2018-01-16 | O | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139141 | T16182-YD00-P0CYE-139141 | FIRE ALARM SYSTEM LAYOUT FOR SECURITY BUILDING | IFI | 2018-11-17 | 2019-02-15 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138641 | T16182-YD00-P0CYE-138641 | FIRE ALARM SYSTEM LAYOUT FOR ST BUILDING | IFI | 2017-12-10 | 2018-03-10 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138741 | T16182-YD00-P0CYE-138741 | FIRE ALARM SYSTEM LAYOUT FOR ST#1 LEB | IFI | 2017-12-15 | 2018-03-15 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138841 | T16182-YD00-P0CYE-138841 | FIRE ALARM SYSTEM LAYOUT FOR ST#2 LEB | IFI | 2018-01-20 | 2018-04-20 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139941 | T16182-YD00-P0CYE-139941 | FIRE ALARM SYSTEM LAYOUT FOR STG EXCITATION TRANSFORMER | IFI | 2017-09-03 | 2017-12-01 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137241 | T16182-YD00-P0CYE-137241 | FIRE ALARM SYSTEM LAYOUT FOR STG GSU TRANSFORMER | IFI | 2017-09-03 | 2017-12-01 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136641 | T16182-YD00-P0CYE-136641 | FIRE ALARM SYSTEM LAYOUT FOR SUPPORT BUILDING | IFI | 2018-06-15 | 2018-09-13 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137941 | T16182-YD00-P0CYE-137941 | FIRE ALARM SYSTEM LAYOUT FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 | O | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139341 | T16182-YD00-P0CYE-139341 | FIRE ALARM SYSTEM LAYOUT FOR X-RAY SEARCHING ROOM | IFI | 2018-10-17 | 2019-01-15 | O |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137841 | T16182-YD00-P0CYE-137841 | FIRE ALARM SYSTEM LAYOUT FORSHELTER FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-11-22 | 2018-02-20 | O | O |  | PKG-030-FF
S&A(18) | Structural & Architectural | 183200 | T16182-CA06-P0UYP-183200 | FIRE BRIGADE - CALCULATION | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 183257 | T16182-CA02-P0UYP-183257 | FIRE BRIGADE - COLUMN, GIRDER, BEAM SHEDULE | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 183203 | T16182-CA00-P0UYP-183203 | FIRE BRIGADE - ELEVATION | IFR | 2017-06-15 | 2017-09-15
S&A(18) | Structural & Architectural | 183205 | T16182-CA00-P0UYP-183205 | FIRE BRIGADE - ENLARGED PLAN, CEILING PLAN | IFR | 2018-03-15 | 2018-05-15
S&A(18) | Structural & Architectural | 183285 | T16182-CA05-P0UYP-183285 | FIRE BRIGADE - ENLARGED PLUMBING PLAN | IFR | 2017-09-15 | 2017-11-15
S&A(18) | Structural & Architectural | 183251 | T16182-CA01-P0UYP-183251 | FIRE BRIGADE - FOUNDATION, COLUMN ARRAGEMENT PLAN | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 183256 | T16182-CA02-P0UYP-183256 | FIRE BRIGADE - FOUNDATION, SLAB REBAR SCHEDULE | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 183254 | T16182-CA01-P0UYP-183254 | FIRE BRIGADE - FRAMING ELEVATION | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 183252 | T16182-CA01-P0UYP-183252 | FIRE BRIGADE - GROUND FLOOR FRAMING PLAN | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 183201 | T16182-CA00-P0UYP-183201 | FIRE BRIGADE - GROUND FLOOR PLAN, INTERIOR FINISH SCHEDULE | IFR | 2017-06-15 | 2017-09-15
S&A(18) | Structural & Architectural | 183283 | T16182-CA05-P0UYP-183283 | FIRE BRIGADE - GROUND FLOOR PLUMBING PLAN | IFR | 2017-09-15 | 2017-11-15
S&A(18) | Structural & Architectural | 183204 | T16182-CA00-P0UYP-183204 | FIRE BRIGADE - MAIN SECTION | IFR | 2017-06-15 | 2017-09-15
S&A(18) | Structural & Architectural | 183255 | T16182-CA01-P0UYP-183255 | FIRE BRIGADE - MISC. STRUCTURAL DETAIL | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 183281 | T16182-CA05-P0UYP-183281 | FIRE BRIGADE - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-09-15 | 2017-11-15
S&A(18) | Structural & Architectural | 183282 | T16182-CA05-P0UYP-183282 | FIRE BRIGADE - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-09-15 | 2017-11-15
S&A(18) | Structural & Architectural | 183253 | T16182-CA01-P0UYP-183253 | FIRE BRIGADE - ROOF FRAMING PLAN | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 183202 | T16182-CA00-P0UYP-183202 | FIRE BRIGADE - ROOF PLAN | IFR | 2017-06-15 | 2017-09-15
S&A(18) | Structural & Architectural | 183284 | T16182-CA05-P0UYP-183284 | FIRE BRIGADE - ROOF PLUMBING PLAN | IFR | 2017-09-15 | 2017-11-15
MCH(13) | Instrumentation & Control | 136606 | T16182-YU03-P0CYE-136606 | FIRE DETECTION AND ALARM SYSTEM - BLOCK DIAGRAM | IFR | 2017-05-03 | 2017-08-01 | O | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136617 | T16182-YT01-P0CYE-136617 | FIRE DETECTION AND ALARM SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136607 | T16182-YU02-P0CYE-136607 | FIRE DETECTION AND ALARM SYSTEM - NETWORK SINGLE LINE DIAGRAM | IFR | 2017-05-03 | 2017-08-01 | O | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136624 | T16182-YD00-P0CYE-136624 | FIRE DETECTION AND ALARM SYSTEM LAYOUT FOR YARD AREA | IFI | 2019-01-04 | 2019-02-08 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 136615 | T16182-YT01-P0SGZ-136615 | FIRE EXTINGUISHER SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136609 | T16182-YT01-P0SGA-136609 | FIRE FIGHTING PUMP SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136601 | T16182-XS00-P0SG-136601 | FIRE FIGHTING SYSTEM CONCEPTUAL DESIGN | IFR | 2017-05-01 | 2017-07-30 |  | O |  | PKG-030-FF
MCH(13) | Commissioning | 136620 | T16182-DN05-P0SG-136620 | FIRE FIGHTING, DETECTION AND ALARM SYSTEM_TEST & COMMISSIONING PROCEDURE FOR ESOD | IFR | 2017-07-25 | 2017-10-23 | O |  |  | PKG-030-FF
MCH(13) | Commissioning | 136623 | T16182-DN05-P0SG-136623 | FIRE FIGHTING, DETECTION AND ALARM SYSTEM_TEST & COMMISSIONING PROCEDURE FOR NON ESOD | IFR | 2018-07-25 | 2018-10-23 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 136602 | T16182-XS00-P0SG-136602 | FIRE RISK EVALUATION | IFR | 2017-05-01 | 2017-07-30 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136605 | T16182-YT10-P0SGA-136605 | FIRE SERVICE RING MAIN SYSTEM - HYDRAULIC CALCULATION | IFR | 2017-05-25 | 2017-08-23 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136603 | T16182-XG02-P0SGA-136603 | FIRE SERVICE RING MAIN SYSTEM - P&ID | IFR | 2017-05-01 | 2017-07-01 | O | O |  | PKG-030-FF
MCH(13) | Mechanical | 136604 | T16182-XH01-P0SGA-136604 | FIRE SERVICE RING MAIN SYSTEM - PIPE LAYOUT AND DETAIL DRAWING | IFR | 2017-05-01 | 2017-07-01 |  |  |  | PKG-030-FF
EM(02) | Engineering Management | 020040 | T16182-BV02-P0ZEN-020040 | FIRE STUDY | IFI | 2018-09-18 |  |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137331 | T16182-YD00-P0SGZ-137331 | FIRE WATER PUMP ARRANGEMENT FOR FIRE WATER PUMP HOUSE | IFR | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF
S&A(18) | Structural & Architectural | 182700 | T16182-CA06-P0USG-182700 | FIRE WATER PUMP HOUSE - CALCULATION | IFR | 2017-04-01 | 2017-06-02 |  | O
S&A(18) | Structural & Architectural | 182755 | T16182-CA02-P0USG-182755 | FIRE WATER PUMP HOUSE - COLUMN, GIRDER, BEAM SHEDULE | IFR | 2017-04-01 | 2017-06-02 |  | O
S&A(18) | Structural & Architectural | 182703 | T16182-CA00-P0USG-182703 | FIRE WATER PUMP HOUSE - ELEVATION | IFR | 2017-04-01 | 2017-06-02 |  | O
S&A(18) | Structural & Architectural | 182754 | T16182-CA02-P0USG-182754 | FIRE WATER PUMP HOUSE - FOUNDATION REBAR SCHEDULE, SLAB REBAR DETAIL | IFR | 2017-04-01 | 2017-06-02 |  | O
S&A(18) | Structural & Architectural | 182751 | T16182-CA01-P0USG-182751 | FIRE WATER PUMP HOUSE - FOUNDATION, COLUMN ARRAGEMENT PLAN | IFR | 2017-04-01 | 2017-06-02 |  | O
S&A(18) | Structural & Architectural | 182753 | T16182-CA01-P0USG-182753 | FIRE WATER PUMP HOUSE - FRAMING ELEVATION | IFR | 2017-04-01 | 2017-06-02 |  | O
S&A(18) | Structural & Architectural | 182752 | T16182-CA01-P0USG-182752 | FIRE WATER PUMP HOUSE - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | IFR | 2017-04-01 | 2017-06-02 |  | O
S&A(18) | Structural & Architectural | 182701 | T16182-CA00-P0USG-182701 | FIRE WATER PUMP HOUSE - GROUND FLOOR PLAN, INTERIOR FINISH SCHEDULE | IFR | 2017-04-01 | 2017-06-02 |  | O
S&A(18) | Structural & Architectural | 182704 | T16182-CA00-P0USG-182704 | FIRE WATER PUMP HOUSE - MAIN SECTION | IFR | 2017-04-01 | 2017-06-02 |  | O
S&A(18) | Structural & Architectural | 182702 | T16182-CA00-P0USG-182702 | FIRE WATER PUMP HOUSE - ROOF PLAN | IFR | 2017-04-01 | 2017-06-02 |  | O
CV(17) | Civil | 173107 | T16182-VK02-P0UGF-173107 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS | IFR | 2017-04-30 | 2017-07-30 |  | O
CV(17) | Civil | 173102 | T16182-XB02-P0UGF-173102 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS LAYOUT | IFR | 2017-04-30 | 2017-07-30 |  | O
CV(17) | Civil | 173101 | T16182-XB02-P0UGF-173101 | FIREFIGHTING & POTABLE WATER PIPE CIVIL WORKS OVERALL LAYOUT | IFR | 2017-04-30 | 2017-07-30 |  | O
GN-SYS(26) | Mechanical | 260012 | T16182-YD00-P0MKW-260012 | FLOAT TRAP OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG
MCH(13) | Mechanical | 139023 | T16182-YT10-P0SGK-139023 | Flow calculation of Clean Agent system for Administration & Social Building | IFR | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138522 | T16182-YT10-P0SGK-138522 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR AUX. LEB | IFR | 2017-11-30 | 2018-01-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 136723 | T16182-YT10-P0SGK-136723 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139622 | T16182-YT10-P0SGK-139622 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR CPP BUILDING | IFR | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138628 | T16182-YT10-P0SGK-138628 | Flow calculation of Clean Agent system for Excitation Panel Room for ST Building | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137623 | T16182-YT10-P0SGK-137623 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-11-12 | 2018-02-10 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136823 | T16182-YT10-P0SGK-136823 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | IFR | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136923 | T16182-YT10-P0SGK-136923 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | IFR | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139123 | T16182-YT10-P0SGK-139123 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | IFR | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138722 | T16182-YT10-P0SGK-138722 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR ST#1 LEB | IFR | 2017-12-15 | 2018-03-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138822 | T16182-YT10-P0SGK-138822 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR ST#2 LEB | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137922 | T16182-YT10-P0SGK-137922 | FLOW CALCULATION OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 130220 | T16182-XB02-P0LD-130220 | FOUNDATION AND LOADING DATA FOR CONDENSATE POLISHING PLANT | IFI | 2018-10-05 | 2018-12-05 |  |  |  | PKG-026-CPP
MCH(13) | Mechanical | 130042 | T16182-XB02-P0GCF-130042 | FOUNDATION AND LOADING DATA FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-06-30 |  | O |  | PKG-025-WT
CV(17) | Civil | 171060 | T16182-VK02-P0UMX-171060 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM BAR BENDING SCHEDULE | IFR | 2017-07-15 | 2017-10-13
CV(17) | Civil | 171058 | T16182-XB02-P0UMX-171058 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM PLAN, SECTIONS AND DETAILS FORMWORK DRAWING | IFR | 2017-07-15 | 2017-10-13
CV(17) | Civil | 171059 | T16182-VK02-P0UMX-171059 | FOUNDATION FOR CONTROL OIL SKID, AIR BACKUP COMPRESSOR, FILTER HOUSE, GENERATOR AIR FILTER, LUBE OIL PACKAGE, ELECTRICAL PACKAGE & GTE RS INLET END EXT. PLATFORM PLAN, SECTIONS AND DETAILS REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13
CV(17) | Civil | 171054 | T16182-XB02-P0UMX-171054 | FOUNDATION FOR EXHAUST TRANSITION DUCT & COMPRESSOR BLEED PIPE SUPPORT PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13
CV(17) | Civil | 171063 | T16182-XB02-P0UMX-171063 | FOUNDATION FOR PULSE AIR COMPRESSIOR SKID PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13
CV(17) | Civil | 171061 | T16182-XB02-P0UMX-171061 | FOUNDATION FOR ROTOR AIR COOLER(KETTLE BOILER) & ROTOR COOLING AIR PIPE SUPPORTS PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13
CV(17) | Civil | 171056 | T16182-XB02-P0UMX-171056 | FOUNDATION FOR SEE/ SFC PACKAGE FOUNDATION INTERFACE-SEE ONLY PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13
CV(17) | Civil | 171057 | T16182-XB02-P0UMX-171057 | FOUNDATION FOR SEE/ SFC PACKAGE SEE WITH SFC NORMAL START PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13
CV(17) | Civil | 171053 | T16182-XB02-P0UMX-171053 | FOUNDATION FOR SFC & SEE TRANSFORMER PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13
CV(17) | Civil | 171062 | T16182-XB02-P0UMX-171062 | FOUNDATION FOR SFC CROSSOVER SWITCH & FIRE PROTECTION SKID PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13
CV(17) | Civil | 171055 | T16182-XB02-P0UMX-171055 | FOUNDATION FOR WOBBE METER CABINET, GT ENCLOSURE RIGHT SIDE EXHAUST END EXTERIOR PLATFORM & AIR COMPRESSOR SKID(DAIS) PLAN, SECTIONS AND DETAILS FORMWORK & REINFORCEMENT DRAWING | IFR | 2017-07-15 | 2017-10-13
GN-SYS(26) | Mechanical | 260032 | T16182-CY03-P0MKG-260032 | GAS CONTROL SYSTEM - SYSTEM DESCRIPTION | IFR | 2017-04-30 | 2017-07-31 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260022 | T16182-YV02-P0MKG-260022 | GAS CONTROL SYSTEM - WIRING DIAGRAMS | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260034 | T16182-XG02-P0MKG-260034 | GAS CONTROL SYSTEM P&ID | IFR | 2017-03-21 | 2017-06-30 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260014 | T16182-YD00-P0MKG-260014 | GAS CONTROL VALVE STATION OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG
|  | 810006 | T16182-DN05-P8MB-810006 | GAS TURBINE FUEL CHANGE-OVER TEST
EL(15) | Electrical | 150761 | T16182-YD00-P0BAA-150761 | GENERAL ARRANGEMENT DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | IFR | 2017-05-12 | 2017-09-17 |  | O |  | PKG-033-IPB
EL(15) | Electrical | 150762 | T16182-YD00-P0BAA-150762 | GENERAL ARRANGEMENT DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | IFR | 2017-06-16 | 2017-10-13 |  |  |  | PKG-033-IPB
MCH(13) | Mechanical | 130302 | T16182-YD00-P0QC-130302 | GENERAL ARRANGEMENT DRAWING FOR CHEMICAL DOSING SYSTEM | IFR | 2017-10-05 | 2018-01-17 |  |  |  | PKG-027-CDS
PS(11) | Mechanical | 110401 | T16182-YD00-P0PGB-110401 | GENERAL ARRANGEMENT DRAWING FOR CLOSED COOLING WATER PUMP | IFR | 2017-04-30 | 2017-07-28 |  | O |  | PKG-005-CCWP
MCH(13) | Mechanical | 130202 | T16182-YD00-P0LD-130202 | GENERAL ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | IFR | 2017-06-03 | 2017-09-15 | O |  |  | PKG-026-CPP
PS(11) | Mechanical | 110502 | T16182-YD00-P0QJA-110502 | GENERAL ARRANGEMENT DRAWING FOR NITROGEN GAS SYSTEM | IFR | 2017-06-15 | 2017-07-31 |  | O |  | PKG-006-N2
MCH(13) | Mechanical | 130601 | T16182-YD00-P0GK-130601 | GENERAL ARRANGEMENT DRAWING FOR POTABLE WATER CHILLER | IFR | 2017-12-08 | 2018-01-26
MCH(13) | Mechanical | 130402 | T16182-YD00-P0QU-130402 | GENERAL ARRANGEMENT DRAWING FOR SAMPLING SYSTEM | IFR | 2017-10-04 | 2018-01-16 |  |  |  | PKG-028-SP
MCH(13) | Mechanical | 130002 | T16182-YD00-P0GCF-130002 | GENERAL ARRANGEMENT DRAWING FOR WATER TREATMENT PLANT | IFR | 2017-02-04 | 2017-05-19 | O | O |  | PKG-025-WT
CV(17) | Civil | 172583 | T16182-XB02-P0ULX-172583 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (1) | IFR | 2017-08-16 | 2017-10-20
CV(17) | Civil | 172584 | T16182-XB02-P0ULX-172584 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (2) | IFR | 2017-08-16 | 2017-10-20
CV(17) | Civil | 172585 | T16182-XB02-P0ULX-172585 | GENERAL SERVICE PUMP FOUNDATIONS DETAILS (3) | IFR | 2017-08-16 | 2017-10-20
CV(17) | Civil | 172582 | T16182-XB02-P0ULX-172582 | GENERAL SERVICE PUMP FOUNDATIONS LAYOUT | IFR | 2017-08-16 | 2017-10-20
GN-SYS(26) | Mechanical | 260020 | T16182-YT01-P0MKA-260020 | GENERATOR AUX SYSTEM INSTRUMENT DATA SHEET | IFI | 2017-08-08 |  |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260019 | T16182-YT01-P0MKA-260019 | GENERATOR AUX SYSTEM MOTOR & PUMP DATA SHEET | IFR | 2017-04-30 | 2017-07-30 |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250009 | T16182-YT01-P0MKA-250009 | GENERATOR DATA SHEET | IFI | 2017-03-30 |  | O |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250010 | T16182-UC02-P0MKA-250010 | GENERATOR ELECTRICAL CONNECTION OUTLINE WITH PACKAGE WIRING AND TERMINAL | IFI | 2017-04-14 |  |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250011 | T16182-UC02-P6MKA-250011 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (UNIT#P6) | IFI | 2016-12-08 | 2017-08-31 |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250012 | T16182-UC02-P7MKA-250012 | GENERATOR ELECTRICAL FOUNDATION CONDUITS LAYOUT (UNIT#P7) | IFI | 2016-12-08 | 2017-08-31 |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250004 | T16182-YD00-P0MKA-250004 | GENERATOR PIPING CONNECTION | IFI | 2017-03-30 |  |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250005 | T16182-YD00-P0MKA-250005 | GENERATOR STATOR HANDLING AND SHIPPING DIMENSION | IFI | 2017-08-17 |  |  |  |  | PKG-040-STG
CV(17) | Civil | 171010 | T16182-XB02-P0UMX-171010 | GT FDN ANCHOR BOLT DETAILS FORMWORK DWG, PART 5/6 | IFR | 2017-06-15 | 2017-09-13 |  | O
CV(17) | Civil | 171024 | T16182-VK02-P0UMX-171024 | GT FDN BENDING SCHEDULES - GENERATOR DECK | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171014 | T16182-VK02-P0UMX-171014 | GT FDN BOTTOM & TOP (3rd + 4th LAYER) LATERAL & LONGITUDINAL REINFORCEMENT, PART 3/9 | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171012 | T16182-VK02-P0UMX-171012 | GT FDN BOTTOM LONGITUDINAL & LATERAL REINFORCEMENT REINFORCEMENT DRAWING BASEMAT, PART 1/9 | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171015 | T16182-VK02-P0UMX-171015 | GT FDN CONNECTION AND SIDE FACE REINFORCEMENT PLAN AT +0.152M & 1.099M LEVEL REINFORCEMENT DRAWING BASEMAT, PART 4/9 | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171005 | T16182-XB02-P0UMX-171005 | GT FDN GENERAL NOTES FORMWORK DWG | IFR | 2017-06-15 | 2017-09-13 |  | O
CV(17) | Civil | 171019 | T16182-VK02-P0UMX-171019 | GT FDN REINFORCEMENT DETAILS SECTION 4-4 AND 5-5 REINFORCEMENT DRAWING BASEMAT, PART 8/9 | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171020 | T16182-VK02-P0UMX-171020 | GT FDN REINFORCEMENT PLAN & SECTIONS FOR COMPRESSION SUPPORT, TURNING GEAR PEDESTAL AND MOUNTING PAD PEDESTAL REINFORCEMENT DRAWING BASEMAT, PART 9/9 | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171021 | T16182-VK02-P0UMX-171021 | GT FDN REINFORCEMENT PLAN AT +1.099M LEVEL AND SPACER & SIDE FACE REBARS GENERATOR DECK REINFORCEMENT, PART 1/2 | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171018 | T16182-VK02-P0UMX-171018 | GT FDN REINFORCEMENT SECTION 2-2 AND 3-3 REINFORCEMENT DRAWING BASEMAT, PART 7/9 | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171017 | T16182-VK02-P0UMX-171017 | GT FDN SECTION 1-1 AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 6/9 | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171022 | T16182-VK02-P0UMX-171022 | GT FDN SECTIONS & DETAILS GENERATOR DECK REINFORCEMENT, PART 2/2 | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171016 | T16182-VK02-P0UMX-171016 | GT FDN SPACER REBARS AND DETAILS REINFORCEMENT DRAWING BASEMAT, PART 5/9 | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171013 | T16182-VK02-P0UMX-171013 | GT FDN TOP LOGITUDINAL & LATERAL REINFORCEMENT DWG BASEMAT, PART 2/9 | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171007 | T16182-XB02-P0UMX-171007 | GT FDN TOP PLAN VIEW ANCHOR BOLT ARRANGEMENT AND DETAILS FORMWORK DRAWING, PART 2/6 | IFR | 2017-06-15 | 2017-09-13 |  | O
CV(17) | Civil | 171008 | T16182-XB02-P0UMX-171008 | GT FDN TOP PLAN VIEW EXPANSION BOLT ARRGMNT AND DETAIL FORMWORK DWG, 3/6 | IFR | 2017-06-15 | 2017-09-13 |  | O
CV(17) | Civil | 171006 | T16182-XB02-P0UMX-171006 | GT FDN TOP PLAN VIEW INSERT PLATE ARRANGEMENT AND DETAILS FORMWORK DWG, PART 1/6 | IFR | 2017-06-15 | 2017-09-13 |  | O
CV(17) | Civil | 171011 | T16182-XB02-P0UMX-171011 | GT FDN TOP PLAN VIEW SCHEDULE OF EMBEDDED PARTS FORMWORK DRAWING, PART 6/6 | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 171009 | T16182-XB02-P0UMX-171009 | GT FDN VIEWS & SECTIONS FORMWORK DWG, PART 4/6 | IFR | 2017-06-15 | 2017-09-13 |  | O
|  | 860001 | T16182-DN05-P0ZEN-860001 | GT LOAD REJECTION TEST
CV(17) | Civil | 171602 | T16182-XB02-P0ULX-171602 | GT PERFORMANCE HEATER FOUNDATION LAYOUT | IFR | 2017-08-18 | 2017-11-18 |  | O
CV(17) | Civil | 171603 | T16182-XB02-P0ULX-171603 | GT PERFORMANCE HEATER FOUNDATION PLAN AND SECTION | IFR | 2017-08-18 | 2017-11-18 |  | O
CV(17) | Civil | 171604 | T16182-VK02-P0ULX-171604 | GT PERFORMANCE HEATER FOUNDATION R.C DETAIL | IFR | 2017-08-18 | 2017-11-18 |  | O
PT(12) | Electrical | 121021 | T16182-YD02-P0MBA-121021 | GTG - ABOVE - GRADE FIELD CONDUIT PLAN | IFI | 2018-02-08 |  |  |  |  | PKG-011-GTG
PT(12) | Mechanical | 121044 | T16182-VN01-P0MBA-121044 | GTG - ACCESS PLATFORM LAYOUT | IFI | 2017-03-15 |  |  |  |  | PKG-011-GTG
PT(12) | Civil | 121007 | T16182-XB00-P0MBA-121007 | GTG - AUXILIARY EQUIPMENT FOUNDATION INTERFACE DRAWINGS | IFI | 2017-04-14 |  |  |  |  | PKG-011-GTG
PT(12) | Instrumentation & Control | 121031 | T16182-YR05-P0MBA-121031 | GTG - CABINET / PANEL TERMINAL BLOCK DETAILS | IFI | 2017-04-08 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121022 | T16182-YL01-P0MBA-121022 | GTG - CABLE AND CONDUIT LIST | IFI | 2018-02-08 |  |  |  |  | PKG-011-GTG
PT(12) | Instrumentation & Control | 121026 | T16182-XS01-P0MBA-121026 | GTG - CONTROL PHILOSOPHY | IFI | 2018-08-15 |  |  |  |  | PKG-011-GTG
PT(12) | Instrumentation & Control | 121027 | T16182-XS01-P0MBA-121027 | GTG - CONTROL SYSTEM DESCRIPTION | IFI | 2018-08-15 |  |  |  |  | PKG-011-GTG
PT(12) | Instrumentation & Control | 121028 | T16182-YL01-P0MBA-121028 | GTG - CONTROL SYSTEM INPUT/OUTPUT DATABASE (I/O DATABASE) | IFI | 2017-04-14 |  |  |  |  | PKG-011-GTG
PT(12) | Instrumentation & Control | 121033 | T16182-XS01-P0MBA-121033 | GTG - CONTROL SYSTEM OVERVIEW | IFI | 2017-02-13 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121019 | T16182-YB03-P0MBA-121019 | GTG - CUSTOMER ELECTRICAL CONNECTIONS | IFI | 2017-05-09 |  |  |  |  | PKG-011-GTG
PT(12) | Mechanical | 121008 | T16182-XJ00-P0MBA-121008 | GTG - CUSTOMER PIPING CONNECTIONS PHYSICAL AND PROCESS DATA | IFI | 2017-04-14 |  |  |  |  | PKG-011-GTG
PT(12) | Instrumentation & Control | 121030 | T16182-YT01-P0MBA-121030 | GTG - DATA SHEETS FOR I&C EQUIPMENT | IFI | 2017-04-08 |  |  |  |  | PKG-011-GTG
PT(12) | Instrumentation & Control | 121024 | T16182-YL25-P0MBA-121024 | GTG - DCS SIGNAL INTERFACE INFORMATION | IFI | 2017-02-28 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121015 | T16182-XW01-P0MBA-121015 | GTG - DESIGN REQUIREMENTS FOR VT & SURGE, BAB36 | IFI | 2017-03-15 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121016 | T16182-YL06-P0MBA-121016 | GTG - ELECTRICAL LOAD LIST | IFI | 2017-04-14 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121020 | T16182-YS00-P0MBA-121020 | GTG - ELECTRICAL SCHEMATICS | IFI | 2018-02-08 |  |  |  |  | PKG-011-GTG
PT(12) | Mechanical | 121001 | T16182-YD00-P0MBA-121001 | GTG - EQUIPMENT ARRANGEMENT | IFR | 2017-03-15 | 2017-05-29 | O |  |  | PKG-011-GTG
PT(12) | Civil | 121034 | T16182-XS01-P0MBA-121034 | GTG - FOUNDATION DESIGN BASIS DOCUMENT | IFI | 2017-03-28 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121013 | T16182-YT01-P0MBA-121013 | GTG - GENERATOR CAPABILITY CURVES AND DATA | IFI | 2017-02-28 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121014 | T16182-YL25-P0MBA-121014 | GTG - GENERATOR ISOPHASE BUS INTERFACE | IFI | 2017-03-15 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121006 | T16182-XW01-P0MBA-121006 | GTG - GENERATOR, EXCITATION SYSTEM, AND POWER SYSTEM STABILIZER MODEL | IFI | 2017-04-04 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121012 | T16182-YU02-P0MBA-121012 | GTG - GENERATOR/MEDIUM VOLTAGE SINGLE LINE DIAGRAM | IFI | 2017-02-28 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121005 | T16182-XW01-P0MBA-121005 | GTG - GOVERNOR AND TURBINE MODEL | IFI | 2017-04-04 |  |  |  |  | PKG-011-GTG
PT(12) | Mechanical | 121002 | T16182-YL25-P0MBA-121002 | GTG - GT EXHAUST MECHANICAL INTERFACE REQUIREMENTS | IFI | 2017-03-15 |  |  |  |  | PKG-011-GTG
PT(12) | Instrumentation & Control | 121032 | T16182-YD05-P0MBA-121032 | GTG - HMI GRAPHIC | IFI | 2018-08-15 |  |  |  |  | PKG-011-GTG
PT(12) | Mechanical | 121009 | T16182-YK08-P0MBA-121009 | GTG - INLET FILTER AND DUCT SUPPLIER DRAWINGS | IFI | 2017-06-13 | 2017-10-13 |  |  |  | PKG-011-GTG
PT(12) | Instrumentation & Control | 121025 | T16182-YL01-P0MBA-121025 | GTG - INSTRUMENT, VALVE AND CONTROL SETTINGS LIST | IFI | 2017-12-10 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121018 | T16182-YU02-P0MBA-121018 | GTG - MCC & 125VDC SINGLE LINE DIAGRAM | IFI | 2017-05-09 |  |  |  |  | PKG-011-GTG
PT(12) | Mechanical | 121003 | T16182-XG02-P0MBA-121003 | GTG - P&I DIAGRAM | IFR | 2017-04-04 | 2017-06-18 | O |  | O | PKG-011-GTG
PT(12) | Mechanical | 110013 | T16182-XG02-P1MBH-110013 | GTG - P&I DIAGRAM FOR GT ROTOR COOLING AIR COOLER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  |  | O | PKG-011-GTG
PT(12) | Civil | 121035 | T16182-XS01-P0MBA-121035 | GTG - POWER BLOCK FOUNDATION GENERAL NOTES | IFI | 2017-03-28 |  |  |  |  | PKG-011-GTG
PT(12) | Instrumentation & Control | 121029 | T16182-YS00-P0MBA-121029 | GTG - POWER SUPPLY DISTRIBUTION DRAWING | IFI | 2017-03-11 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121037 | T16182-XW01-P0MBA-121037 | GTG - PSS STUDY REPORT_DRAFT | IFR | 2019-01-16 | 2019-04-30 |  |  |  | PKG-011-GTG
PT(12) | Mechanical | 121004 | T16182-XW01-P0MBA-121004 | GTG - ROTOR COOLING AIR SYSTEM REQUIREMENTS | IFI | 2017-03-30 |  |  |  |  | PKG-011-GTG
PT(12) | General | 121011 | T16182-XS00-P0MBA-121011 | GTG - SYSTEM DESCRIPTION | IFR | 2017-02-13 | 2017-04-29 | O |  | O | PKG-011-GTG
PT(12) | Electrical | 121017 | T16182-YU05-P0MBA-121017 | GTG - THREE - LINE SCHEMATICS | IFI | 2017-04-14 |  |  |  |  | PKG-011-GTG
PT(12) | Mechanical | 121100 | T16182-XG02-P0GM-121100 | GTG – DRAIN INTERFACE FLOW DIAGRAM | IFI | 2018-12-03 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121036 | T16182-YQ03-P0CY-121036 | GTG – ELECTRICAL PACKAGE COMMUNICATION LAYOUT DRAWING | IFI | 2018-12-03 |  |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121971 | T16182-YT01-P0MBA-121971 | GTG – SFC / SEE CIRCUIT DIAGRAM | IFI | 2018-09-10 |  |  |  |  | PKG-011-GTG
S&A(18) | Structural & Architectural | 181208 | T16182-CA00-P0UBA-181208 | GTG #1,2 LEB - ARCHITECTURAL MISC. DETAIL | IFR | 2017-02-15 | 2017-04-30 |  | O
S&A(18) | Structural & Architectural | 181201 | T16182-CA00-P0UBA-181201 | GTG #1,2 LEB - BASEMENT FLOOR PLAN | IFR | 2016-12-15 | 2017-02-08 |  | O
S&A(18) | Structural & Architectural | 181259 | T16182-CA02-P0UBA-181259 | GTG #1,2 LEB - BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-02-15 | 2017-04-30 |  | O
S&A(18) | Structural & Architectural | 181200 | T16182-CA06-P0UBA-181200 | GTG #1,2 LEB - CALCULATION | IFR | 2016-12-15 | 2017-02-08 |  | O
S&A(18) | Structural & Architectural | 181258 | T16182-CA02-P0UBA-181258 | GTG #1,2 LEB - COLUMN RE - BAR SCHEDULE | IFR | 2016-12-15 | 2017-02-08 |  | O
S&A(18) | Structural & Architectural | 181251 | T16182-CA01-P0UBA-181251 | GTG #1,2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2016-12-15 | 2017-02-08 |  | O
S&A(18) | Structural & Architectural | 181257 | T16182-CA02-P0UBA-181257 | GTG #1,2 LEB - FOUNDATION RE - BAR DETAIL | IFR | 2016-12-15 | 2017-02-08 |  | O
S&A(18) | Structural & Architectural | 181252 | T16182-CA01-P0UBA-181252 | GTG #1,2 LEB - GROUND FLOOR FRAMING PLAN | IFR | 2016-12-15 | 2017-02-08 |  | O
S&A(18) | Structural & Architectural | 181256 | T16182-CA01-P0UBA-181256 | GTG #1,2 LEB - GROUND FLOOR OPENING PLAN | IFR | 2017-02-15 | 2017-04-30 |  | O
S&A(18) | Structural & Architectural | 181202 | T16182-CA00-P0UBA-181202 | GTG #1,2 LEB - GROUND FLOOR PLAN | IFR | 2016-12-15 | 2017-02-08 |  | O
S&A(18) | Structural & Architectural | 181284 | T16182-CA05-P0UBA-181284 | GTG #1,2 LEB - GROUND FLOOR PLUMBING PLAN | IFR | 2017-01-28 | 2017-03-30 |  | O
S&A(18) | Structural & Architectural | 181206 | T16182-CA00-P0UBA-181206 | GTG #1,2 LEB - INTERIOR FINISH SCHEDULE (INCL. DOOR & WINDOW) | IFR | 2017-02-15 | 2017-04-30 |  | O
S&A(18) | Structural & Architectural | 181254 | T16182-CA01-P0UBA-181254 | GTG #1,2 LEB - LINE & ROW FRAMING ELEVATION | IFR | 2016-12-15 | 2017-02-08 |  | O
S&A(18) | Structural & Architectural | 181205 | T16182-CA00-P0UBA-181205 | GTG #1,2 LEB - MAIN SECTION | IFR | 2016-12-15 | 2017-02-08 |  | O
S&A(18) | Structural & Architectural | 181281 | T16182-CA05-P0UBA-181281 | GTG #1,2 LEB - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-01-28 | 2017-03-30 |  | O
S&A(18) | Structural & Architectural | 181282 | T16182-CA05-P0UBA-181282 | GTG #1,2 LEB - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-01-28 | 2017-03-30 |  | O
S&A(18) | Structural & Architectural | 181253 | T16182-CA01-P0UBA-181253 | GTG #1,2 LEB - ROOF FRAMING PLAN | IFR | 2016-12-15 | 2017-02-08 |  | O
S&A(18) | Structural & Architectural | 181203 | T16182-CA00-P0UBA-181203 | GTG #1,2 LEB - ROOF PLAN | IFR | 2016-12-15 | 2017-02-08 |  | O
S&A(18) | Structural & Architectural | 181204 | T16182-CA00-P0UBA-181204 | GTG #1,2 LEB - SIDE WALL ELEVATION | IFR | 2016-12-15 | 2017-02-08 |  | O
S&A(18) | Structural & Architectural | 181260 | T16182-CA02-P0UBA-181260 | GTG #1,2 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | IFR | 2017-02-15 | 2017-04-30 |  | O
S&A(18) | Structural & Architectural | 181255 | T16182-CA01-P0UBA-181255 | GTG #1,2 LEB - STAIR FRAMING PLAN & ELEVATION | IFR | 2017-02-15 | 2017-04-30 |  | O
S&A(18) | Structural & Architectural | 181207 | T16182-CA00-P0UBA-181207 | GTG #1,2 LEB - STAIR PLAN & SECTION | IFR | 2017-02-15 | 2017-04-30 |  | O
S&A(18) | Structural & Architectural | 181301 | T16182-CA00-P0UBA-181301 | GTG #3,4,5 LEB - BASEMENT FLOOR PLAN | IFR | 2017-01-15 | 2017-03-15
S&A(18) | Structural & Architectural | 181359 | T16182-CA02-P0UBA-181359 | GTG #3,4,5 LEB - BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-04-28 | 2017-05-29
S&A(18) | Structural & Architectural | 181300 | T16182-CA06-P0UBA-181300 | GTG #3,4,5 LEB - CALCULATION | IFR | 2017-01-15 | 2017-03-15
S&A(18) | Structural & Architectural | 181358 | T16182-CA02-P0UBA-181358 | GTG #3,4,5 LEB - COLUMN RE - BAR SCHEDULE | IFR | 2017-01-15 | 2017-03-15
S&A(18) | Structural & Architectural | 181351 | T16182-CA01-P0UBA-181351 | GTG #3,4,5 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-01-15 | 2017-03-15
S&A(18) | Structural & Architectural | 181357 | T16182-CA02-P0UBA-181357 | GTG #3,4,5 LEB - FOUNDATION RE - BAR DETAIL | IFR | 2017-01-15 | 2017-03-15
S&A(18) | Structural & Architectural | 181352 | T16182-CA01-P0UBA-181352 | GTG #3,4,5 LEB - GROUND FLOOR FRAMING PLAN | IFR | 2017-01-15 | 2017-03-15
S&A(18) | Structural & Architectural | 181356 | T16182-CA01-P0UBA-181356 | GTG #3,4,5 LEB - GROUND FLOOR OPENING PLAN | IFR | 2017-04-28 | 2017-05-29
S&A(18) | Structural & Architectural | 181302 | T16182-CA00-P0UBA-181302 | GTG #3,4,5 LEB - GROUND FLOOR PLAN | IFR | 2017-01-15 | 2017-03-15
S&A(18) | Structural & Architectural | 181306 | T16182-CA00-P0UBA-181306 | GTG #3,4,5 LEB - INTERIOR FINISH SCHEDULE (INCL. DOOR & WINDOW) | IFR | 2017-09-21 | 2017-11-21
S&A(18) | Structural & Architectural | 181354 | T16182-CA01-P0UBA-181354 | GTG #3,4,5 LEB - LINE & ROW FRAMING ELEVATION | IFR | 2017-01-15 | 2017-03-15
S&A(18) | Structural & Architectural | 181305 | T16182-CA00-P0UBA-181305 | GTG #3,4,5 LEB - MAIN SECTION | IFR | 2017-01-15 | 2017-03-15
S&A(18) | Structural & Architectural | 181353 | T16182-CA01-P0UBA-181353 | GTG #3,4,5 LEB - ROOF FRAMING PLAN | IFR | 2017-01-15 | 2017-03-15
S&A(18) | Structural & Architectural | 181303 | T16182-CA00-P0UBA-181303 | GTG #3,4,5 LEB - ROOF PLAN | IFR | 2017-01-15 | 2017-03-15
S&A(18) | Structural & Architectural | 181304 | T16182-CA00-P0UBA-181304 | GTG #3,4,5 LEB - SIDE WALL ELEVATION | IFR | 2017-01-15 | 2017-03-15
S&A(18) | Structural & Architectural | 181360 | T16182-CA02-P0UBA-181360 | GTG #3,4,5 LEB - SLAB & MISC. DETAIL RE - BAR DETAIL | IFR | 2017-04-28 | 2017-05-29
S&A(18) | Structural & Architectural | 181355 | T16182-CA01-P0UBA-181355 | GTG #3,4,5 LEB - STAIR FRAMING PLAN & ELEVATION | IFR | 2017-04-28 | 2017-05-29
S&A(18) | Structural & Architectural | 181307 | T16182-CA00-P0UBA-181307 | GTG #3,4,5 LEB - STAIR PLAN & SECTION | IFR | 2017-09-21 | 2017-11-21
CV(17) | Civil | 171051 | T16182-VE04-P0UMX-171051 | GTG AUXILIARY FOUNDATION - DESIGN REPORT | IFR | 2017-07-15 | 2017-10-13
CV(17) | Civil | 171052 | T16182-XB02-P0UMX-171052 | GTG AUXILIARY FOUNDATION - GENERAL ARRANGEMENT | IFR | 2017-07-15 | 2017-10-13
PT(12) |  | 121099 | T16182-CQ02-P0MBA-121099 | GTG ERECTION DRAWING PACKAGE | Internal
CV(17) | Civil | 171004 | T16182-VE04-P0UMX-171004 | GTG FOUNDATION - DESIGN REPORT | IFR | 2017-06-15 | 2017-09-13 |  | O
CV(17) | Civil | 171002 | T16182-XB02-P0UMX-171002 | GTG FOUNDATION - PILE ARRANGEMENT DRAWING | IFR | 2017-03-28 | 2017-05-12 |  | O
CV(17) | Civil | 171001 | T16182-VE04-P0UMX-171001 | GTG FOUNDATION - PILE CALCULATION SHEET | IFR | 2017-03-28 | 2017-05-12 |  | O
CV(17) | Civil | 171023 | T16182-VK02-P0UMX-171023 | GTG FOUNDATION BAR BENDING SCHEDULE | IFR | 2017-06-15 | 2017-09-13
CV(17) | Civil | 172162 | T16182-XB02-P0UAG-172162 | GTG STEP UP & UNIT AUX. TRANSFORMER FOUNDATION PLAN & SECTION | IFR | 2017-04-25 | 2017-07-24 |  | O
CV(17) | Civil | 172168 | T16182-XB02-P0UAG-172168 | GTG STEP UP & UNIT AUX. TRANSFORMER GRATING & GRATING SUPPORT ARRANGEMENT PLAN & SECTION | IFR | 2017-04-25 | 2017-07-24 |  | O
CV(17) | Civil | 172170 | T16182-VK02-P0UAG-172170 | GTG STEP UP & UNIT AUX. TRANSFORMER RE-BAR DETAIL | IFR | 2017-04-25 | 2017-07-24 |  | O
PT(12) | Instrumentation & Control | 121555 | T16182-YT01-P0MBA-121555 | GTG_CONDUIT LAYOUT DRAWING | IFI | 2017-09-22 | 2017-12-22 |  |  |  | PKG-011-GTG
PT(12) | Electrical | 121023 | T16182-YT01-P0MBA-121023 | GTG_ELECTRICAL PROTECTION AND OPERATION SETTINGS | IFI | 2018-02-08 |  |  |  |  | PKG-011-GTG
PT(12) | Mechanical | 121824 | T16182-YT01-P0MBA-121824 | GTG_FIRE PROTECTION SYSTEM DRAWING | IFI | 2018-04-30 |  |  |  |  | PKG-011-GTG
PT(12) | Mechanical | 121073 | T16182-CQ02-P0MBA-121073 | GTG_GAS TURBINE AND AUXILIARIES COMMISSIOINING MANUAL | IFI | 2018-08-30 |  |  |  |  | PKG-011-GTG
PT(12) | Mechanical | 121051 | T16182-CQ02-P0MBA-121051 | GTG_GAS TURBINE AND AUXILIARIES INSTALLATION MANUAL | IFI | 2018-08-30 |  |  |  |  | PKG-011-GTG
PT(12) | Mechanical | 121677 | T16182-YT01-P0MBA-121677 | GTG_GAS TURBINE GENERATOR COMMISSIOINING MANUAL | IFI | 2018-08-30 |  |  |  |  | PKG-011-GTG
PT(12) | General | 121077 | T16182-CQ02-P0MBA-121077 | GTG_GENERATOR REMOVAL PROCEDURE | IFI | 2019-06-25
PT(12) | Instrumentation & Control | 121678 | T16182-YS00-P0MBA-121678 | GTG_I&C SCHEMATICS | IFI | 2018-08-30 |  |  |  |  | PKG-011-GTG
PT(12) | General | 121076 | T16182-CQ02-P0MBA-121076 | GTG_INSTALLATION MANUAL | IFI | 2018-02-28 |  |  |  |  | PKG-011-GTG
PT(12) | General | 121010 | T16182-DM02-P0MBA-121010 | GTG_STG-PAC INSTRUCTION BOOK VOLUME I (GAS TURBINE AND AUXILIARIES | IFI | 2018-10-06 |  | O |  |  | PKG-011-GTG
PT(12) | General | 121038 | T16182-DM02-P0MBA-121038 | GTG_STG-PAC INSTRUCTION BOOK VOLUME II (GENERATOR AND AUXILIARIES) | IFI | 2019-02-18 |  |  |  |  | PKG-011-GTG
S&A(18) | Structural & Architectural | 181384 | T16182-CA05-P0UBA-181384 | GTG#3,4,5LEB - GROUND FLOOR PLUMBING PLAN | IFR | 2017-02-28 | 2017-04-30
S&A(18) | Structural & Architectural | 181381 | T16182-CA05-P0UBA-181381 | GTG#3,4,5LEB - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-02-28 | 2017-04-30
S&A(18) | Structural & Architectural | 181382 | T16182-CA05-P0UBA-181382 | GTG#3,4,5LEB - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-02-28 | 2017-04-30
GN-SYS(26) | Mechanical | 260015 | T16182-YD00-P0MKG-260015 | H2 BOTTLE MANIFOLD OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260017 | T16182-YD00-P0MKG-260017 | H2 CONTROL CABINET OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260018 | T16182-YD00-P0MKG-260018 | H2 GAS DRYER OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260031 | T16182-CY03-P0MKW-260031 | H2 SEAL OIL SYSTEM - SYSTEM DESCRIPTION | IFR | 2017-04-30 | 2017-07-31 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260021 | T16182-YV02-P0MKW-260021 | H2 SEAL OIL SYSTEM - WIRING DIAGRAMS | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260033 | T16182-XG02-P0MKW-260033 | H2 SEAL OIL SYTSEM P&ID | IFR | 2017-04-30 | 2017-06-30 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260011 | T16182-YD00-P0MKW-260011 | H2 SEAL OIL UNIT OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG
S&A(18) | Structural & Architectural | 184900 | T16182-CA06-P0UTG-184900 | H2, CO2 STORAGE SHELTER - CALCULATION | IFR | 2017-07-31 | 2017-09-30
S&A(18) | Structural & Architectural | 184902 | T16182-CA00-P0UTG-184902 | H2, CO2 STORAGE SHELTER - ELEVATION | IFR | 2017-07-31 | 2017-09-30
S&A(18) | Structural & Architectural | 184951 | T16182-CA01-P0UTG-184951 | H2, CO2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | IFR | 2017-07-31 | 2017-09-30
S&A(18) | Structural & Architectural | 184953 | T16182-CA01-P0UTG-184953 | H2, CO2 STORAGE SHELTER - FRAMING ELEVATION | IFR | 2017-07-31 | 2017-09-30
S&A(18) | Structural & Architectural | 184952 | T16182-CA01-P0UTG-184952 | H2, CO2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | IFR | 2017-07-31 | 2017-09-30
S&A(18) | Structural & Architectural | 184901 | T16182-CA00-P0UTG-184901 | H2, CO2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | IFR | 2017-07-31 | 2017-09-30
S&A(18) | Structural & Architectural | 184903 | T16182-CA00-P0UTG-184903 | H2, CO2 STORAGE SHELTER - MAIN SECTION | IFR | 2017-07-31 | 2017-09-30
S&A(18) | Structural & Architectural | 184954 | T16182-CA02-P0UTG-184954 | H2, CO2 STORAGE SHELTER - REBAR DETAIL | IFR | 2017-07-31 | 2017-09-30
GN-MCH(25) | Mechanical | 250006 | T16182-YD00-P0MKA-250006 | HANDLING DIMENSION FOR GENERATOR ROTOR | IFI | 2017-08-17 |  |  |  |  | PKG-040-STG
EL(15) | Electrical | 150304 | T16182-YT10-P0ZEN-150304 | HARMONIC STUDY REPORT | IFR | 2017-07-30 | 2017-10-15 |  | O
PS(11) | General | 110703 | T16182-CN00-P0ZEN-110703 | HAZARD AND OPERABILITY STUDY | IFR | 2017-06-01 | 2017-08-01 |  | O
PS(11) | General | 110705 | T16182-CN00-P0ZEN-110705 | HAZARDOUS AREA CLASSIFICATION REPORT | IFR | 2017-06-01 | 2017-08-01 |  | O
PS(11) | General | 110706 | T16182-CN00-P0ZEN-110706 | HAZOP AND SIL STUDY PROCEDURE | IFI | 2017-03-06 |  |  | O | O
PS(11) | Mechanical | 110001 | T16182-XG05-P0ZEN-110001 | HEAT BALANCE DIAGRAMS | IFR | 2016-12-14 | 2017-04-25 | O | O
TG-MCH(22) | Instrumentation & Control | 220277 | T16182-YV02-P6CJJ-220277 | HMI DESIGN – UNIT P6 | IFI | 2017-11-30 |  |  |  |  | PKG-040-STG
TG-MCH(22) | Instrumentation & Control | 220278 | T16182-YV02-P7CJJ-220278 | HMI DESIGN – UNIT P7 | IFI | 2018-05-20 |  |  |  |  | PKG-040-STG
I&C(16) | Instrumentation & Control | 163424 | T16182-YD05-P0SAY-163424 | HMI GRAPHIC DISPLAY DIAGRAM FOR HVAC | IFI | 2017-09-15 |  |  | O |  | PKG-041-HVAC
PT(12) | Mechanical | 128020 | T16182-YT01-P0SMU-128020 | HOIST - DATA SHEETS FOR AIR COMPRSSOR HOUSE HOIST | IFI | 2017-11-29 | 2018-02-09 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128033 | T16182-YT01-P0SMC-128033 | HOIST - DATA SHEETS FOR CENTRAL CONTROL BUILDING HOIST | IFI | 2018-03-31 | 2018-02-09 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128022 | T16182-YT01-P0SMU-128022 | HOIST - DATA SHEETS FOR CHAIN BLOCK | IFI | 2018-01-29 |  |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128036 | T16182-YT01-P0SMM-128036 | HOIST - DATA SHEETS FOR CPP HOIST | IFI | 2018-03-31 | 2018-02-09 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128021 | T16182-YT01-P0SMG-128021 | HOIST - DATA SHEETS FOR DM WATER TREATMENT HOIST | IFI | 2017-12-29 | 2018-02-09 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128019 | T16182-YT01-P0SMQ-128019 | HOIST - DATA SHEETS FOR FF PUMP HOUSE HOIST | IFI | 2017-10-29 | 2018-02-09 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128034 | T16182-YT01-P0SMS-128034 | HOIST - DATA SHEETS FOR WAREHOUSE HOIST | IFI | 2018-03-31 | 2018-02-09 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128035 | T16182-YT01-P0SMG-128035 | HOIST - DATA SHEETS FOR WASTE WATER TREATMENT HOIST | IFI | 2018-03-31 | 2018-02-09 |  |  |  | PKG-022-CR
PT(12) | Electrical | 128046 | T16182-YS18-P0SMU-128046 | HOIST - ELECTRICAL DETAIL FOR AIR COMPRSSOR HOUSE HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Electrical | 128043 | T16182-YS18-P0SMC-128043 | HOIST - ELECTRICAL DETAIL FOR CENTRAL CONTROL BUILDING HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Electrical | 128049 | T16182-YS18-P0SMM-128049 | HOIST - ELECTRICAL DETAIL FOR CPP HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Electrical | 128047 | T16182-YS18-P0SMG-128047 | HOIST - ELECTRICAL DETAIL FOR DM WATER TREATMENT HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Electrical | 128045 | T16182-YS18-P0SMQ-128045 | HOIST - ELECTRICAL DETAIL FOR FF PUMP HOUSE HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Electrical | 128044 | T16182-YS18-P0SMS-128044 | HOIST - ELECTRICAL DETAIL FOR WAREHOUSE HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Electrical | 128048 | T16182-YS18-P0SMG-128048 | HOIST - ELECTRICAL DETAIL FOR WASTE WATER TREATMENT HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128015 | T16182-YD00-P0SMU-128015 | HOIST - GA DRAWING FOR AIR COMPRSSOR HOUSE HOIST | IFI | 2017-11-29 | 2018-03-28 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128028 | T16182-YD00-P0SMC-128028 | HOIST - GA DRAWING FOR CENTRAL CONTROL BUILDING HOIST | IFI | 2018-03-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128017 | T16182-YD00-P0SMU-128017 | HOIST - GA DRAWING FOR CHAIN BLOCK | IFI | 2018-01-29 |  |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128031 | T16182-YD00-P0SMM-128031 | HOIST - GA DRAWING FOR CPP HOIST | IFI | 2018-03-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128016 | T16182-YD00-P0SMG-128016 | HOIST - GA DRAWING FOR DM WATER TREATMENT HOIST | IFI | 2017-12-29 | 2018-03-28 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128014 | T16182-YD00-P0SMQ-128014 | HOIST - GA DRAWING FOR FF PUMP HOUSE HOIST | IFI | 2017-10-29 | 2018-03-28 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128070 | T16182-YD00-P0SMU-128070 | HOIST - GA DRAWING FOR ST GSUT | IFI | 2020-01-10
PT(12) | Mechanical | 128029 | T16182-YD00-P0SMS-128029 | HOIST - GA DRAWING FOR WAREHOUSE HOIST | IFI | 2018-03-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128030 | T16182-YD00-P0SMG-128030 | HOIST - GA DRAWING FOR WASTE WATER TREATMENT HOIST | IFI | 2018-03-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128025 | T16182-YK09-P0SMU-128025 | HOIST - MECHANICAL DETAIL FOR AIR COMPRSSOR HOUSE HOIST | IFI | 2018-02-28 | 2018-05-28 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128038 | T16182-YK09-P0SMC-128038 | HOIST - MECHANICAL DETAIL FOR CENTRAL CONTROL BUILDING HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128041 | T16182-YK09-P0SMM-128041 | HOIST - MECHANICAL DETAIL FOR CPP HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128026 | T16182-YK09-P0SMG-128026 | HOIST - MECHANICAL DETAIL FOR DM WATER TREATMENT HOIST | IFI | 2018-03-29 | 2018-05-28 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128024 | T16182-YK09-P0SMQ-128024 | HOIST - MECHANICAL DETAIL FOR FF PUMP HOUSE HOIST | IFI | 2018-01-29 | 2018-05-28 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128039 | T16182-YK09-P0SMS-128039 | HOIST - MECHANICAL DETAIL FOR WAREHOUSE HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128040 | T16182-YK09-P0SMG-128040 | HOIST - MECHANICAL DETAIL FOR WASTE WATER TREATMENT HOIST | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR
MCH(13) | Instrumentation & Control | 130216 | T16182-YK00-P0LD-130216 | HOOK - UP DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2017-09-01 |  |  |  |  | PKG-026-CPP
MCH(13) | Instrumentation & Control | 130016 | T16182-YK00-P0GCF-130016 | HOOK - UP DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-05-05 |  |  | O |  | PKG-025-WT
PT(12) | Electrical | 122092 | T16182-YS00-P0LB-122092 | HRSG - AIRCRAFT WARNING LIGHT DATASHEET & LAYOUT DIAGRAM | IFI | 2017-06-30 | 2018-03-15 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122077 | T16182-YK10-P0LB-122077 | HRSG - ALARM AND TRIP SETTING LIST FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Civil | 122019 | T16182-XB02-P0LB-122019 | HRSG - ANCHOR BOLT & TEMPLATE DETAIL FOR STACK | IFI | 2017-02-28 | 2017-08-31 |  |  |  | PKG-012-HRSG
PT(12) | Structural & Architectural | 122015 | T16182-VN03-P0LB-122015 | HRSG - ARRANGEMENT FOR PLATFORM STRUCTURE | IFI | 2017-05-31 | 2017-10-28 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122008 | T16182-UE00-P0LB-122008 | HRSG - ARRANGEMENT OF CASING & FIELD ERECTION | IFR | 2017-04-30 | 2017-07-29 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122009 | T16182-UE00-P0LB-122009 | HRSG - ARRANGEMENT OF INLET DUCT | IFR | 2017-04-30 | 2017-07-29 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122010 | T16182-UE00-P0LB-122010 | HRSG - ARRANGEMENT OF MAIN STACK& FIELD ERECTION | IFR | 2017-04-30 | 2017-07-29 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122103 | T16182-YT01-P0LB-122103 | HRSG - ARRANGEMENT OF PARTITION PLATE & GAS BAFFLE | IFI | 2017-04-30 | 2017-09-27 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122062 | T16182-UE00-P0LB-122062 | HRSG - ARRANGEMENT OF STACK SILENCER | IFI | 2017-06-30 | 2017-11-27 |  |  |  | PKG-012-HRSG
PT(12) | Civil | 122018 | T16182-XB02-P0LB-122018 | HRSG - BASE PLATE AND ANCHOR BOLTS DETAIL FOR STEEL STRUCTURE | IFI | 2017-02-28 | 2017-08-31 |  |  |  | PKG-012-HRSG
PT(12) | General | 122037 | T16182-XS00-P0LB-122037 | HRSG - BLOWDOWN SYSTEM SUMMARY | IFR | 2017-01-31 | 2017-05-01 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122058 | T16182-YD00-P0LB-122058 | HRSG - BMS PANEL LAYOUT FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122038 | T16182-XV00-P0LB-122038 | HRSG - BMS PANEL PART LIST FOR DUCT BURNER SYSTEM | IFI | 2017-10-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122044 | T16182-YD00-P0LB-122044 | HRSG - BMS SHELTER LAYOUT FOR DUCT BURNER SYSTEM | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122108 | T16182-YT01-P0LB-122108 | HRSG - BMS SPECIFICATION FOR DUCT BURNER SYSTEM | IFR | 2017-08-15 | 2017-11-13 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122070 | T16182-YF00-P0LB-122070 | HRSG - BMS SYSTEM CONFIGURATION FOR DUCT BURNER SYSTEM | IFI | 2017-07-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122047 | T16182-YB03-P0LB-122047 | HRSG - CABLE CONNECTION DIAGRAM | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122078 | T16182-YL16-P0LB-122078 | HRSG - CABLE SCHEDULE | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122064 | T16182-YD02-P0LB-122064 | HRSG - CABLE TRAY & RACEWAY LAYOUT DIAGRAM | IFI | 2017-06-30 | 2018-03-21 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122093 | T16182-YT01-P0LB-122093 | HRSG - CEMS DATASHEET & DRAWINGS | IFR | 2017-06-30 | 2017-09-28 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122005 | T16182-DF04-P0LB-122005 | HRSG - CFD REPORT FOR DUCT BURNER SYSTEM | IFI | 2017-07-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122004 | T16182-DF04-P0LB-122004 | HRSG - CFD REPORT FOR INLET DUCT | IFI | 2017-04-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122082 | T16182-YR01-P0LB-122082 | HRSG - CHEMICAL CLEANING PROCEDURE | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Civil | 122016 | T16182-XB02-P0LB-122016 | HRSG - COLUMN LOCATION FOR STEEL STRUCTURE AND STACK | IFI | 2017-02-28 | 2017-08-31 |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122080 | T16182-YL01-P0LB-122080 | HRSG - COMMUNICATION BLOCK DIAGRAM | IFI | 2017-06-30 | 2018-03-21 |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122081 | T16182-US02-P0LB-122081 | HRSG - COMMUNICATION LAYOUT DRAWING | IFI | 2017-06-30 | 2018-03-21 |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122063 | T16182-YD02-P0LB-122063 | HRSG - CONDUIT LAYOUT DRAWING | IFI | 2017-08-31 | 2018-03-21 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122066 | T16182-YF00-P0LB-122066 | HRSG - CONTROL LOGIC DIAGRAM | IFI | 2017-07-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122067 | T16182-YE03-P0LB-122067 | HRSG - CONTROL LOOP DIAGRAM | IFI | 2017-07-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122042 | T16182-YT01-P0LB-122042 | HRSG - COOLING AIR FAN & MOTOR DATASHEET FOR DUCT BURNER SYSTEM | IFI | 2017-08-31 | 2019-08-27 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122014 | T16182-UE00-P0LB-122014 | HRSG - COOLING AIR SKID ARRANGEMENT FOR DUCT BURNER SYSTEM | IFR | 2017-08-15 | 2017-11-13 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122090 | T16182-VN02-P0LB-122090 | HRSG - CV DATASHEET & DRAWINGS | IFI | 2017-05-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122086 | T16182-YQ03-P0LB-122086 | HRSG - DATA & BOM OF INSULATION FOR BLOWDOWN TANK | IFI | 2017-05-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122087 | T16182-YQ03-P0LB-122087 | HRSG - DATA & BOM OF INSULATION FOR INTERNAL PIPING | IFI | 2017-07-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122091 | T16182-YS00-P0LB-122091 | HRSG - DESH. DATASHEET & DRAWINGS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122012 | T16182-UE00-P0LB-122012 | HRSG - DETAIL ARRANGEMENT FOR DUCT BURNER SYSTEM | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122096 | T16182-YT01-P0LB-122096 | HRSG - DRUM LEVEL GAUGE DATASHEET & DRAWINGS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122100 | T16182-YT01-P0LB-122100 | HRSG - ELECTRICAL SINGLE LINE DIAGRAMS | IFI | 2017-04-30 |  |  |  |  | PKG-012-HRSG
PT(12) | General | 122039 | T16182-XV00-P0LB-122039 | HRSG - EQUIPMENT LIST | IFI | 2017-01-31 | 2017-06-30 | O |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122055 | T16182-YD00-P0LB-122055 | HRSG - EQUIPMENT OUTLINE DRAWING FOR BLOWDOWN TANK | IFI | 2017-05-31 | 2017-10-28 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122061 | T16182-XW01-P0LB-122061 | HRSG - FLAME SCANNER & IGNITION BURNER SPECIFICATION FOR DUCT BURNER SYSTEM | IFI | 2017-09-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122097 | T16182-YT01-P0LB-122097 | HRSG - FLOW ELEMENT DATASHEET & DRAWINGS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Civil | 122017 | T16182-XB02-P0LB-122017 | HRSG - FOUNDATION LOAD TABLE FOR STEEL STRUCTURE AND STACK | IFI | 2017-02-28 | 2017-06-29 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122020 | T16182-XB02-P0LB-122020 | HRSG - FOUNDATION LOADING & LOCATION DRAWING FOR BLOWDOWN TANK | IFI | 2017-04-30 | 2017-10-30 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122013 | T16182-UE00-P0LB-122013 | HRSG - FUEL GAS SKID ARRANGEMENT FOR DUCT BURNER SYSTEM | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122007 | T16182-UE00-P0LB-122007 | HRSG - GENERAL ARRANGEMENT | IFR | 2017-01-31 | 2017-05-01 | O |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122011 | T16182-UE00-P0LB-122011 | HRSG - GENERAL ARRANGEMENT FOR DUCT BURNER SYSTEM | IFR | 2017-07-15 | 2017-10-13 |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122065 | T16182-YD02-P0LB-122065 | HRSG - GROUNDING AND LIGHTNING PLAN DIAGRAMS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | General | 122040 | T16182-CN00-P0LB-122040 | HRSG - HAZARDOUS AREA CLASSIFICATION SPECIFICATION & DRAWING FOR DUCT BURNER SYSTEM | IFR | 2017-08-15 | 2017-11-13 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122057 | T16182-YD00-P0LB-122057 | HRSG - HEADER AND SUPPORT DRAWING FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 | 2018-01-12 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122059 | T16182-YD05-P0LB-122059 | HRSG - HMI SCREEN LAYOUT FOR DUCT BURNER SYSTEM | IFI | 2017-10-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122102 | T16182-YT01-P0LB-122102 | HRSG - I/O LIST FOR BMS AND CEMS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122101 | T16182-YT01-P0LB-122101 | HRSG - ILLUMINATION CALCULATION | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122001 | T16182-CQ02-P0LB-122001 | HRSG - INSTALLATION AND INSTRUCTION MANUAL | IFI | 2019-09-05 |  |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122072 | T16182-YK00-P0LB-122072 | HRSG - INSTRUMENT INSTALLATION DETAIL DRAWINGS | IFI | 2017-05-31 | 2019-01-17 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122075 | T16182-YL00-P0LB-122075 | HRSG - INSTRUMENT LIST | IFI | 2017-03-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122076 | T16182-YL00-P0LB-122076 | HRSG - INSTRUMENT LIST FOR DUCT BURNER SYSTEM | IFI | 2017-09-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122069 | T16182-YM03-P0LB-122069 | HRSG - INSTRUMENT LOCATION | IFI | 2017-07-15 | 2018-11-06 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122105 | T16182-YT01-P0LB-122105 | HRSG - INSTRUMENT SPECIFICATION & DATASHEET FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122107 | T16182-YQ01-P0LB-122107 | HRSG - INTERCONNECTION WIRING DIAGRAM FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122060 | T16182-YT01-P0LB-122060 | HRSG - JUNCTION BOX DATASHEET FOR DUCT BURNER SYSTEM | IFI | 2017-09-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122027 | T16182-XJ00-P0LB-122027 | HRSG - LARGE BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | IFI | 2017-06-30 | 2017-11-27 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122021 | T16182-XG01-P0LB-122021 | HRSG - LARGE BORE PIPING ARRANGEMENT | IFI | 2017-08-31 | 2018-01-28 |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122079 | T16182-YL00-P0LB-122079 | HRSG - LIGHTING PLAN DIAGRAMS | IFI | 2017-06-30 | 2018-03-21 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122030 | T16182-XL00-P0LB-122030 | HRSG - LINE LIST | IFI | 2017-03-31 | 2017-08-28 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122031 | T16182-XL00-P0LB-122031 | HRSG - LINE LIST FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 | 2018-01-12 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122071 | T16182-YK00-P0LB-122071 | HRSG - LINK ASSEMBLY DRAWING | IFI | 2017-04-30 | 2017-10-30 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122094 | T16182-YT02-P0LB-122094 | HRSG - LOCAL INSTRUMENT DATASHEET & DRAWINGS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122068 | T16182-YF00-P0LB-122068 | HRSG - LOGIC DIAGRAM FOR DUCT BURNER SYSTEM | IFI | 2017-09-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122074 | T16182-YK01-P0LB-122074 | HRSG - MANUAL VALVE ASSEMBLY DRAWING FOR EXTERNAL PIPING | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122032 | T16182-XN00-P0LB-122032 | HRSG - MANUAL VALVE LIST | IFI | 2017-03-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122033 | T16182-XN00-P0LB-122033 | HRSG - MOV & CV LIST | IFI | 2017-03-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122089 | T16182-VN02-P0LB-122089 | HRSG - MOV DATASHEET & DRAWINGS | IFI | 2017-05-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122022 | T16182-XG02-P0LB-122022 | HRSG - P&I DIAGRAM | IFR | 2017-01-31 | 2017-05-01 | O |  | O | PKG-012-HRSG
PT(12) | Mechanical | 122023 | T16182-XG02-P0LB-122023 | HRSG - P&I DIAGRAM FOR HRSG DUCT BURNER SYSTEM | IFR | 2017-07-15 | 2017-10-13 |  |  | O | PKG-012-HRSG
PT(12) | Electrical | 122084 | T16182-YR05-P0LB-122084 | HRSG - PANEL ELECTRIC SCHEME FOR DUCT BURNER SYSTEM | IFI | 2017-09-15 |  |  |  |  | PKG-012-HRSG
PT(12) | General | 122088 | T16182-YQ03-P0LB-122088 | HRSG - PERFORMANCE AND OPERATIONAL DATA | IFI | 2017-02-28 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122024 | T16182-XH01-P0LB-122024 | HRSG - PIPE SUPPORT DRAWING FOR EXTERNAL PIPING | IFI | 2017-08-31 | 2018-01-28 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122026 | T16182-XH01-P0LB-122026 | HRSG - PIPE SUPPORT DRAWINGS | IFI | 2017-07-31 | 2017-12-28 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122104 | T16182-YT02-P0LB-122104 | HRSG - PIPING MATERIAL CLASSIFICATION | IFI | 2017-04-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122056 | T16182-YD00-P0LB-122056 | HRSG - POWER DISTRIBUTION PANEL DRAWINGS | IFI | 2017-07-31 |  |  |  |  | PKG-012-HRSG
PT(12) | General | 122083 | T16182-YL08-P0LB-122083 | HRSG - PRESERVATION AND STORAGE PROCEDURE | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122048 | T16182-YB03-P0LB-122048 | HRSG - PRESSURE PART ARRANGEMENT | IFI | 2017-02-28 | 2017-07-28 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122098 | T16182-YT01-P0LB-122098 | HRSG - REMOTE DRUM LEVEL INDICATOR DATASHEET & DRAWINGS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122106 | T16182-YT01-P0LB-122106 | HRSG - SHUT OFF AND CONTROL VALVE DATASHEET FOR DUCT BURNER SYSTEM | IFI | 2017-08-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122028 | T16182-XJ00-P0LB-122028 | HRSG - SMALL BORE ERECTION ISOMETRIC DRAWING FOR EXTERNAL PIPING | IFI | 2017-07-31 | 2017-12-28 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122050 | T16182-YD00-P0LB-122050 | HRSG - SPEC. & DRAWING FOR BLOWDOWN PUMP | IFI | 2017-06-30 | 2017-10-30 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122054 | T16182-YD00-P0LB-122054 | HRSG - SPEC. & DRAWING FOR DEAERATOR & STORAGE TANK | IFI | 2017-06-30 | 2017-11-27 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122006 | T16182-YD00-P0LB-122006 | HRSG - SPEC. & DRAWING FOR HOIST | IFI | 2018-01-01 | 2018-02-02 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122051 | T16182-YT01-P0LB-122051 | HRSG - SPEC. & DRAWING FOR SAFETY & RELIEF VALVE | IFI | 2017-06-30 | 2017-10-16 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122052 | T16182-YD00-P0LB-122052 | HRSG - SPEC. & DRAWING FOR STACK DAMPER | IFI | 2017-06-30 | 2017-11-27 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122049 | T16182-YD00-P0LB-122049 | HRSG - SPEC. & DRAWING FOR STEAM DRUM | IFI | 2017-06-30 | 2017-11-27 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122053 | T16182-YD00-P0LB-122053 | HRSG - SPEC. & DRAWING FOR VENT SILENCER | IFI | 2017-06-30 | 2017-10-16 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122073 | T16182-YK00-P0LB-122073 | HRSG - SPECIALTY DRAWING FOR EXTERNAL PIPING | IFI | 2017-08-31 |  |  |  |  | PKG-012-HRSG
PT(12) | Structural & Architectural | 122110 | T16182-XW03-P0LB-122110 | HRSG - STRENGTH CALCULATION REPORT FOR STEEL STRUCTURE | IFI | 2018-03-21 | 2018-07-25 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122003 | T16182-DF04-P0LB-122003 | HRSG - STRESS ANALYSIS ISOMETRIC DRAWING FOR CRITICAL PIPING | IFI | 2017-03-18 |  |  |  |  | PKG-012-HRSG
PT(12) | General | 122035 | T16182-XS00-P0LB-122035 | HRSG - SYSTEM DESCRIPTION | IFR | 2017-02-28 | 2017-05-29 | O |  | O | PKG-012-HRSG
PT(12) | General | 122036 | T16182-XS00-P0LB-122036 | HRSG - SYSTEM DESCRIPTION FOR HRSG DUCT BURNER SYSTEM | IFR | 2017-07-15 | 2017-10-13 |  |  | O | PKG-012-HRSG
PT(12) | Electrical | 122041 | T16182-XW01-P0LB-122041 | HRSG - TECHNICAL SPECIFICATION FOR AC & DC DISTRIBUTION BOARD | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122046 | T16182-XW01-P0LB-122046 | HRSG - TECHNICAL SPECIFICATION FOR COMMUNICATION SYSTEM | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122045 | T16182-XW01-P0LB-122045 | HRSG - TECHNICAL SPECIFICATION FOR EARTHING & LIGHTNING PROTECTION SYSTEM | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122099 | T16182-YT01-P0LB-122099 | HRSG - TECHNICAL SPECIFICATION FOR LIGHTING & SMALL POWER SYSTEM | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 122095 | T16182-YT01-P0LB-122095 | HRSG - TRANSMITTER DATASHEET & DRAWINGS | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122025 | T16182-XH01-P0LB-122025 | HRSG - TYPICAL SUPPORT DRAWING FOR SMALL BORE PIPING | IFI | 2017-08-31 | 2018-01-28 |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122109 | T16182-YD00-P0LB-122109 | HRSG - UNDERGROUND EARTHING CABLE LAYOUT DRAWING | IFI | 2017-04-15 | 2018-03-21 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122034 | T16182-XN00-P0LB-122034 | HRSG - VALVE LIST FOR DUCT BURNER SYSTEM | IFI | 2017-09-15 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122029 | T16182-XJ00-P0LB-122029 | HRSG - VENT & DRAIN LINE (MODULE /FIELD WELD) | IFI | 2017-04-30 | 2017-09-27 |  |  |  | PKG-012-HRSG
PT(12) | Electrical | 122085 | T16182-YQ01-P0LB-122085 | HRSG - WIRING & SCHEMATIC DIAGRAM | IFI | 2017-06-30 |  |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122112 | T16182-XG02-P0GM-122112 | HRSG – DRAIN FLOW DIAGRAM | IFI | 2018-10-19 | 2018-11-15 |  |  |  | PKG-012-HRSG
PT(12) | Mechanical | 122111 | T16182-UE00-P0LB-122111 | HRSG – PERPENDICULAR BAFFLE AND TIE PLATE ASSY DRAWINGS | IFR | 2018-10-19 | 2018-11-15 |  |  |  | PKG-012-HRSG
PT(12) | Instrumentation & Control | 126302 | T16182-YS02-P0LAC-126302 | HRSG FEEDWATER PUMP - CABLE INTERCONNECTION WIRING DIAGRAM | IFI | 2017-12-15 |  |  |  |  | PKG-016-HFWP
PT(12) | Electrical | 126005 | T16182-YT01-P0LAC-126005 | HRSG FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR MOTOR | IFI | 2017-05-16 | 2017-12-06 |  |  |  | PKG-016-HFWP
PT(12) | Mechanical | 126004 | T16182-YT01-P0LAC-126004 | HRSG FEEDWATER PUMP - DATA SHEET AND CHARACTERISTIC CURVE FOR PUMP | IFR | 2017-04-14 | 2017-07-27 | O |  |  | PKG-016-HFWP
PT(12) | Electrical | 126019 | T16182-YD00-P0LAC-126019 | HRSG FEEDWATER PUMP - EMERGENCY PUSH BUTTON DRAWING | IFI | 2017-07-28 |  |  |  |  | PKG-016-HFWP
PT(12) | Mechanical | 126027 | T16182-YK08-P0LAC-126027 | HRSG FEEDWATER PUMP - FLEXIBLE COUPLING DATA SHEET & DRAWING | IFI | 2017-09-28 |  |  |  |  | PKG-016-HFWP
PT(12) | Mechanical | 126001 | T16182-YD00-P0LAC-126001 | HRSG FEEDWATER PUMP - GENERAL ARRANGEMENT DRAWING | IFR | 2017-04-14 | 2017-07-27 | O |  |  | PKG-016-HFWP
PT(12) | Instrumentation & Control | 126301 | T16182-YB11-P0LAC-126301 | HRSG FEEDWATER PUMP - I&C JUNCTION BOX DRAWING | IFI | 2017-12-15 |  |  |  |  | PKG-016-HFWP
PT(12) | Mechanical | 126012 | T16182-DM01-P0LAC-126012 | HRSG FEEDWATER PUMP - INSTALLATION MANUAL | IFI | 2017-12-27 | 2018-07-17 |  |  |  | PKG-016-HFWP
PT(12) | Instrumentation & Control | 126011 | T16182-YT02-P0LAC-126011 | HRSG FEEDWATER PUMP - LIST AND DATA SHEET FOR INSTRUMENT | IFI | 2017-08-30 |  |  |  |  | PKG-016-HFWP
PT(12) | Mechanical | 126007 | T16182-YD00-P0LAC-126007 | HRSG FEEDWATER PUMP - NAME PLATE DRAWING | IFI | 2017-06-28 |  |  |  |  | PKG-016-HFWP
PT(12) | Mechanical | 126016 | T16182-YT01-P0LAC-126016 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR LUBE OIL UNIT | IFI | 2017-06-28 |  |  |  |  | PKG-016-HFWP
PT(12) | Mechanical | 126010 | T16182-YD00-P0LAC-126010 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR MECHANICA SEAL | IFI | 2017-06-28 | 2017-11-08 |  |  |  | PKG-016-HFWP
PT(12) | Mechanical | 126009 | T16182-YT01-P0LAC-126009 | HRSG FEEDWATER PUMP - OUTLINE DRAWING AND DATA SHEET FOR SUCTION STRAINER | IFI | 2017-06-28 | 2017-12-28 |  |  |  | PKG-016-HFWP
PT(12) | Mechanical | 126003 | T16182-XG02-P0LAC-126003 | HRSG FEEDWATER PUMP - P&I DIAGRAM | IFR | 2017-04-14 | 2017-07-27 | O |  |  | PKG-016-HFWP
PT(12) | Mechanical | 126006 | T16182-YK01-P0LAC-126006 | HRSG FEEDWATER PUMP - SECTIONAL DRAWING FOR PUMP | IFI | 2017-05-16 |  |  |  |  | PKG-016-HFWP
CV(17) | Civil | 171803 | T16182-XB02-P0UHA-171803 | HRSG FOUNDATION ARRANGEMENT | IFR | 2017-01-25 | 2017-04-25
CV(17) | Civil | 171805 | T16182-XB02-P0UHA-171805 | HRSG FOUNDATION LAYOUT | IFR | 2017-04-27 | 2017-07-26
CV(17) | Civil | 171804 | T16182-XB02-P0UHA-171804 | HRSG FOUNDATION PILE ARRANGEMENT PLAN | IFR | 2017-01-25 | 2017-04-25
CV(17) | Civil | 171806 | T16182-XB02-P0UHA-171806 | HRSG FOUNDATION PLAN SECTION & DETAIL | IFR | 2017-04-27 | 2017-07-26
CV(17) | Civil | 171807 | T16182-XB02-P0UHA-171807 | HRSG FOUNDATION REBAR DETAIL | IFR | 2017-04-27 | 2017-07-26
CV(17) | Civil | 171816 | T16182-XB02-P0UHA-171816 | HRSG MISC. FOUNDATION DETAILS | IFR | 2017-06-16 | 2017-09-14
CV(17) | Civil | 171815 | T16182-XB02-P0UHA-171815 | HRSG MISC. FOUNDATION PLAN | IFR | 2017-06-16 | 2017-09-14
PS(11) | Mechanical | 110061 | T16182-XW03-P0LA-110061 | HRSG/FGP FEEDWATER PUMP NPSH TRANSIENT ANALYSIS | IFI | 2017-07-20
I&C(16) | Instrumentation & Control | 163408 | T16182-YD02-P0SAC-163408 | HVAC I&C CABLE RACEWAY DRAWING FOR CCB | IFI | 2017-11-15 | 2018-06-28 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163422 | T16182-YD02-P0SAC-163422 | HVAC I&C CABLE RACEWAY DRAWING FOR CPP BUILDING | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163419 | T16182-YD02-P0SAC-163419 | HVAC I&C CABLE RACEWAY DRAWING FOR FGS ELECTRICAL BUILDING | IFI | 2017-12-15 | 2018-02-13 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163417 | T16182-YD02-P0SAC-163417 | HVAC I&C CABLE RACEWAY DRAWING FOR FIRE BRIGADE & AUX LEB | IFI | 2018-02-15 | 2018-04-16 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163420 | T16182-YD02-P0SAC-163420 | HVAC I&C CABLE RACEWAY DRAWING FOR FIRE WATER PUMP HOUSE | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163413 | T16182-YD02-P0SAC-163413 | HVAC I&C CABLE RACEWAY DRAWING FOR GTG ELECTRICAL BUILDING FOR #1,2 | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163414 | T16182-YD02-P0SAC-163414 | HVAC I&C CABLE RACEWAY DRAWING FOR GTG ELECTRICAL BUILDING FOR #3, 4, 5 | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163415 | T16182-YD02-P0SAC-163415 | HVAC I&C CABLE RACEWAY DRAWING FOR MAIN ADMINISTRATION BUILDING /W SOCIAL FACILITIES BUILDING | IFI | 2018-06-15 | 2018-08-14 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163426 | T16182-YD02-P0SAC-163426 | HVAC I&C CABLE RACEWAY DRAWING FOR MAIN GATE HOUSE AREA | IFI | 2018-09-30 | 2018-11-30 |  |  |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163418 | T16182-YD02-P0SAC-163418 | HVAC I&C CABLE RACEWAY DRAWING FOR MAINTENANCE AND WORKSHOP BUILDING /W WAREHOUSE | IFI | 2018-02-15 | 2018-04-16 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163416 | T16182-YD02-P0SAC-163416 | HVAC I&C CABLE RACEWAY DRAWING FOR SECURITY BUILDING | IFI | 2018-06-15 | 2018-08-14 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163409 | T16182-YD02-P0SAC-163409 | HVAC I&C CABLE RACEWAY DRAWING FOR STEAM TURBINE BUILDING | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163411 | T16182-YD02-P0SAC-163411 | HVAC I&C CABLE RACEWAY DRAWING FOR STG ELECTRICAL BUILDING FOR #1 | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163412 | T16182-YD02-P0SAC-163412 | HVAC I&C CABLE RACEWAY DRAWING FOR STG ELECTRICAL BUILDING FOR #2 | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163421 | T16182-YD02-P0SAC-163421 | HVAC I&C CABLE RACEWAY DRAWING FOR WATER TREATMENT BUILDING /W MAIN LABORATORY | IFI | 2017-11-15 | 2018-05-29 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 138623 | T16182-YT10-P0SGE-138623 | HYDRAULIC CALCULATION OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | IFR | 2018-03-03 | 2018-06-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 136722 | T16182-YT10-P0SGE-136722 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139623 | T16182-YT10-P0SGE-139623 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR CPP BUILDING | IFR | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137322 | T16182-YT10-P0SGE-137322 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136822 | T16182-YT10-P0SGE-136822 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | IFR | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136922 | T16182-YT10-P0SGE-136922 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | IFR | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138622 | T16182-YT10-P0SGE-138622 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137923 | T16182-YT10-P0SGE-137923 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | IFI | 2017-09-11 | 2017-12-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139522 | T16182-YT10-P0SGE-139522 | HYDRAULIC CALCULATION OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2018-07-01 | 2017-11-23 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138221 | T16182-YT10-P0SGC-138221 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | IFR | 2017-07-21 | 2017-10-19 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138121 | T16182-YT10-P0SGC-138121 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | IFR | 2017-11-12 | 2018-02-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137421 | T16182-YT10-P0SGC-137421 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | IFR | 2017-10-18 | 2018-01-16 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138922 | T16182-YT10-P0SGC-138922 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | IFR | 2018-11-19 | 2018-12-20 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138321 | T16182-YT10-P0SGC-138321 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | IFR | 2017-07-19 | 2017-10-17 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138626 | T16182-YT10-P0SGC-138626 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138624 | T16182-YT10-P0SGC-138624 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137021 | T16182-YT10-P0SGC-137021 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138122 | T16182-YT10-P0SGC-138122 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | IFR | 2019-01-10 | 2019-02-08 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137121 | T16182-YT10-P0SGC-137121 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139921 | T16182-YT10-P0SGC-139921 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | IFR | 2017-09-03 | 2017-12-02 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137221 | T16182-YT10-P0SGC-137221 | HYDRAULIC CALCULATION OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | IFR | 2017-09-03 | 2017-12-02 |  |  |  | PKG-030-FF
I&C(16) | Instrumentation & Control | 163402 | T16182-YL01-P0SAY-163402 | I/O LIST FOR HVAC | IFI | 2017-06-15 |  |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163407 | T16182-YB03-P0SAY-163407 | I&C CABLE INTERCONNECTION WIRING DIAGRAM FOR HVAC | IFI | 2017-11-01 | 2018-01-30 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 165011 | T16182-YL02-P0ZEN-165011 | I&C CABLE PRINCIPLE DIAGRAM | IFR | 2016-11-30 | 2017-03-15
I&C(16) | Instrumentation & Control | 163406 | T16182-YL16-P0SAY-163406 | I&C CABLE SCHEDULE FOR HVAC | IFI | 2017-11-01 | 2018-01-30 |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 161401 | T16182-YD00-P0CWQ-161401 | I&C EQUIPMENT LAYOUT DRAWING FOR CENTRAL CONTROL ROOM | IFR | 2017-01-15 | 2017-04-30 |  | O
I&C(16) | Instrumentation & Control | 161402 | T16182-YD00-P0CWQ-161402 | I&C EQUIPMENT LAYOUT DRAWING FOR CENTRAL ELECTRONIC ROOM | IFR | 2017-01-15 | 2017-04-30 |  | O
I&C(16) | Instrumentation & Control | 161403 | T16182-YD00-P0CWQ-161403 | I&C EQUIPMENT LAYOUT DRAWING FOR COMPUTER ROOM | IFR | 2017-01-15 | 2017-04-30 |  | O
I&C(16) | Instrumentation & Control | 161409 | T16182-YD00-P0CWQ-161409 | I&C EQUIPMENT LAYOUT DRAWING FOR FGS ELECTRICAL BUILDING LOCAL ELECTRONIC ROOM | IFR | 2017-03-10 | 2017-06-23 |  | O
I&C(16) | Instrumentation & Control | 161405 | T16182-YD00-P0CWQ-161405 | I&C EQUIPMENT LAYOUT DRAWING FOR GTG #1,2 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | IFR | 2017-01-15 | 2017-04-30 |  | O
I&C(16) | Instrumentation & Control | 161406 | T16182-YD00-P0CWQ-161406 | I&C EQUIPMENT LAYOUT DRAWING FOR GTG #3,4,5 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | IFR | 2017-01-15 | 2017-04-30 |  | O
I&C(16) | Instrumentation & Control | 161404 | T16182-YD00-P0CWQ-161404 | I&C EQUIPMENT LAYOUT DRAWING FOR IT & COMMUNICATION ROOM | IFR | 2017-01-15 | 2017-04-30 |  | O
I&C(16) | Instrumentation & Control | 161407 | T16182-YD00-P0CWQ-161407 | I&C EQUIPMENT LAYOUT DRAWING FOR ST #1 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | IFR | 2017-04-01 | 2017-07-15
I&C(16) | Instrumentation & Control | 161408 | T16182-YD00-P0CWQ-161408 | I&C EQUIPMENT LAYOUT DRAWING FOR ST #2 LEB LOCAL ELECTRICAL & ELECTRONIC ROOM | IFR | 2017-05-01 | 2017-08-14
I&C(16) | Instrumentation & Control | 161118 | T16182-YR04-P0CUQ-161118 | I&C GROUNDING CONCEPT DIAGRAM | IFR | 2017-02-15 | 2017-04-16 |  | O
EL(15) | Electrical | 152210 | T16182-YT10-P0ZEN-152210 | ILLUMINATION CALCULATION - ADMINISTRATION | IFI | 2018-07-02
EL(15) | Electrical | 152219 | T16182-YT10-P0ZEN-152219 | ILLUMINATION CALCULATION - AIR COMPRESSOR SHELTER | IFI | 2018-01-05
EL(15) | Electrical | 152203 | T16182-YT10-P0ZEN-152203 | ILLUMINATION CALCULATION - CENTRAL CONTROL BUILDING | IFI | 2017-08-15 |  |  | O
EL(15) | Electrical | 152226 | T16182-YT10-P0ZEN-152226 | ILLUMINATION CALCULATION - CHEMICAL DOSING SHELTER FOR HRSG | IFI | 2018-05-11
EL(15) | Electrical | 152225 | T16182-YT10-P0ZEN-152225 | ILLUMINATION CALCULATION - CHEMICAL DOSING SHELTER FOR STG & HRSG | IFI | 2018-04-17
EL(15) | Electrical | 152224 | T16182-YT10-P0ZEN-152224 | ILLUMINATION CALCULATION - CPP & CPP REGENERATION BUILDING | IFI | 2018-03-23
EL(15) | Electrical | 152220 | T16182-YT10-P0ZEN-152220 | ILLUMINATION CALCULATION - DEAERATOR SUPPORT STRUCTURE | IFI | 2017-12-15
EL(15) | Electrical | 152209 | T16182-YT10-P0ZEN-152209 | ILLUMINATION CALCULATION - FGS ELECTRICAL BUILDING | IFI | 2018-01-05 |  |  | O
EL(15) | Electrical | 152216 | T16182-YT10-P0ZEN-152216 | ILLUMINATION CALCULATION - FIRE BRIGADE & AUX. LEB | IFI | 2018-08-03
EL(15) | Electrical | 152221 | T16182-YT10-P0ZEN-152221 | ILLUMINATION CALCULATION - FIRE WATER PUMP HOUSE | IFI | 2017-09-03
EL(15) | Electrical | 152204 | T16182-YT10-P0ZEN-152204 | ILLUMINATION CALCULATION - GTG #1,2 LEB | IFI | 2017-09-03 |  |  | O
EL(15) | Electrical | 152205 | T16182-YT10-P0ZEN-152205 | ILLUMINATION CALCULATION - GTG #3,4,5 LEB | IFI | 2017-12-23
EL(15) | Electrical | 152218 | T16182-YT10-P0ZEN-152218 | ILLUMINATION CALCULATION - H2, CO2, N2 STORAGE SHELTER | IFI | 2017-08-25
EL(15) | Electrical | 152212 | T16182-YT10-P0ZEN-152212 | ILLUMINATION CALCULATION - MAIN GATE HOUSE | IFI | 2018-04-21
EL(15) | Electrical | 152215 | T16182-YT10-P0ZEN-152215 | ILLUMINATION CALCULATION - MAIN GATE HOUSE SUNSHADE | IFI | 2018-04-21
EL(15) | Electrical | 152211 | T16182-YT10-P0ZEN-152211 | ILLUMINATION CALCULATION - SECURITY BUILDING | IFI | 2018-12-01
EL(15) | Electrical | 152206 | T16182-YT10-P0ZEN-152206 | ILLUMINATION CALCULATION - ST #1 LEB | IFI | 2017-12-03
EL(15) | Electrical | 152207 | T16182-YT10-P0ZEN-152207 | ILLUMINATION CALCULATION - ST #2 LEB | IFI | 2018-01-05
EL(15) | Electrical | 152208 | T16182-YT10-P0ZEN-152208 | ILLUMINATION CALCULATION - ST BUILDING | IFI | 2018-05-19
EL(15) | Electrical | 152213 | T16182-YT10-P0ZEN-152213 | ILLUMINATION CALCULATION - SUPPORT BUILDING | IFI | 2018-04-21
EL(15) | Electrical | 152223 | T16182-YT10-P0ZEN-152223 | ILLUMINATION CALCULATION - WATER TREATMENT BUILDING | IFI | 2017-08-29 |  |  | O
EL(15) | Electrical | 152217 | T16182-YT10-P0ZEN-152217 | ILLUMINATION CALCULATION - WORKSHOP & STORAGE BUILDING | IFI | 2018-03-19
EL(15) | Electrical | 152222 | T16182-YT10-P0ZEN-152222 | ILLUMINATION CALCULATION - WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-10-30
EL(15) | Electrical | 152214 | T16182-YT10-P0ZEN-152214 | ILLUMINATION CALCULATION - X-RAY SEARCHING ROOM | IFI | 2018-04-21
EL(15) | Electrical | 152229 | T16182-YT10-P0ZEN-152229 | ILLUMINATION CALCULATION - YARD | IFI | 2018-03-14
EL(15) | Electrical | 152234 | T16182-YT10-P0ZEN-152234 | ILLUMINATION CALCULATION – FUEL GAS SYSTEM AREA | IFI | 2018-04-06
EL(15) | Electrical | 152231 | T16182-YT10-P0ZEN-152231 | ILLUMINATION CALCULATION – GTG #1, 2 TRANSFORMER AREA | IFI | 2018-01-22
EL(15) | Electrical | 152232 | T16182-YT10-P0ZEN-152232 | ILLUMINATION CALCULATION – GTG #3, 4, 5 TRANSFORMER AREA | IFI | 2018-03-02
EL(15) | Electrical | 152233 | T16182-YT10-P0ZEN-152233 | ILLUMINATION CALCULATION – STG #1, 2 TRANSFORMER AREA | IFI | 2018-03-02
EL(15) | Electrical | 152230 | T16182-YT10-P0ZEN-152230 | ILLUMINATION CALCULATION – TANK AREA | IFI | 2018-01-22
PT(12) | Mechanical | 124039 | T16182-CH01-P0EKG-124039 | INSTALLATION & ERECTION MANUAL | Internal
EL(15) | Electrical | 152823 | T16182-DE00-P0ZEN-152823 | INSTALLATION DRAWING - 380KV EHV CABLE AND ACCESSOIRES | IFI | 2017-09-15 | 2017-12-14
I&C(16) | Instrumentation & Control | 163404 | T16182-YK00-P0SAY-163404 | INSTRUMENT INSTALLATION DETAIL DRAWING FOR HVAC | IFI | 2017-08-15 | 2017-11-13 |  | O |  | PKG-041-HVAC
MCH(13) | Instrumentation & Control | 130305 | T16182-YL00-P0QC-130305 | INSTRUMENT LIST FOR CHEMICAL DOSING SYSTEM | IFI | 2017-11-04 |  |  |  |  | PKG-027-CDS
MCH(13) | Instrumentation & Control | 130209 | T16182-YL00-P0LD-130209 | INSTRUMENT LIST FOR CONDENSATE POLISHING PLANT | IFI | 2017-07-03 |  |  |  |  | PKG-026-CPP
MCH(13) | Instrumentation & Control | 130404 | T16182-YL00-P0QU-130404 | INSTRUMENT LIST FOR SAMPLING SYSTEM | IFI | 2017-11-03 |  |  |  |  | PKG-028-SP
MCH(13) | Instrumentation & Control | 130106 | T16182-YL00-P0GNR-130106 | INSTRUMENT LIST FOR WASTE WATER TREATMENT PLANT | IFI | 2017-03-06 |  |  | O |  | PKG-025-WT
MCH(13) | Instrumentation & Control | 130009 | T16182-YL00-P0GCF-130009 | INSTRUMENT LIST FOR WATER TREATMENT PLANT | IFI | 2017-03-06 |  |  | O |  | PKG-025-WT
MCH(13) | Instrumentation & Control | 130221 | T16182-YM03-P0LD-130221 | INSTRUMENT LOCATION DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2019-03-15
TG-MCH(22) | Instrumentation & Control | 220293 | T16182-YT02-P6CJJ-220293 | INSTRUMENTATION DATA SHEETS - UNIT P6 | IFI | 2018-06-29 |  |  |  |  | PKG-040-STG
TG-MCH(22) | Instrumentation & Control | 220294 | T16182-YT02-P7CJJ-220294 | INSTRUMENTATION DATA SHEETS - UNIT P7 | IFI | 2018-03-20 |  |  |  |  | PKG-040-STG
TK(40) | Mechanical | 420051 | T16182-YK08-P0GKC-420051 | INSULATION DETAIL DRAWING FOR CHILLED WATER STORAGE TANK | IFI | 2018-01-05 | 2018-03-05
PT(12) |  | 124161 | T16182-DN04-P0EKG-124161 | INSULATION PROCEDURE FOR FGSS AREA AND HEATER SKIDS | Internal
EL(15) | Electrical | 150305 | T16182-YT10-P0ZEN-150305 | INSULATION STUDY REPORT | IFR | 2017-07-30 | 2017-10-15 |  | O
B.I&C(16) | Instrumentation & Control | 161150 | T16182-YR01-P0CRU-161150 | INTEGRATED SAT(SITE ACCEPTANCE TEST) PROCEDURE FOR DCS | IFR | 2018-07-09 | 2018-08-13 |  |  |  | PKG-039-DCS
CV(17) | Civil | 173209 | T16182-VK02-P0UZJ-173209 | INTERNAL FENCE AND GATE PLAN AND DETAIL | IFR | 2018-01-30 | 2018-06-30
CV(17) | Civil | 172402 | T16182-XB02-P0BAA-172402 | IPB FOUNDATION PLAN & SECTION | IFR | 2017-04-23 | 2017-07-22
CV(17) | Civil | 172403 | T16182-VK02-P0BAA-172403 | IPB FOUNDATION R.C DETAIL | IFR | 2017-04-23 | 2017-07-22
|  | 860006 | T16182-DN05-P0ZEN-860006 | ISLAND MODE TEST
PP(14) | Mechanical | 140221 | T16182-XJ00-P0QCA-140221 | ISOMETRIC DRAWING FOR CHEMICAL DOSING SYSTEM SMALL BORE | IFI | 2018-02-20 | 2018-03-21
PP(14) | Mechanical | 140209 | T16182-XJ00-P0PGB-140209 | ISOMETRIC DRAWING FOR CLOSED COOLING WATER SYSTEM SMALL BORE | IFI | 2018-01-10 | 2018-02-16 |  | O
PP(14) | Mechanical | 140206 | T16182-XJ00-P0LCA-140206 | ISOMETRIC DRAWING FOR CONDENSATE SYSTEM SMALL BORE | IFI | 2018-02-14 | 2018-03-13
PP(14) | Mechanical | 140213 | T16182-XJ00-P0GHC-140213 | ISOMETRIC DRAWING FOR DEMI WATER SYSTEM SMALL BORE | IFI | 2017-12-15 | 2018-02-28 |  | O
PP(14) | Mechanical | 140208 | T16182-XJ00-P0LAB-140208 | ISOMETRIC DRAWING FOR FEED WATER SYSTEM SMALL BORE | IFI | 2018-01-10 | 2018-02-16 |  | O
MCH(13) | Commissioning | 136622 | T16182-XJ00-P0SGA-136622 | ISOMETRIC DRAWING FOR FIRE SERVICE RING MAIN SYSTEM | IFI | 2018-07-25 | 2018-10-23 |  |  |  | PKG-030-FF
PP(14) | Mechanical | 140217 | T16182-XJ00-P0EKC-140217 | ISOMETRIC DRAWING FOR GT PERFORMANCE HEATER SYSTEM SMALL BORE | IFI | 2018-02-14 | 2018-03-13
PP(14) | Mechanical | 140216 | T16182-XJ00-P0MBH-140216 | ISOMETRIC DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM SMALL BORE | IFI | 2018-02-14 | 2018-03-13
PP(14) | Mechanical | 140201 | T16182-XJ00-P0LBA-140201 | ISOMETRIC DRAWING FOR HP STEAM SYSTEM SMALL BORE | IFI | 2018-02-09 | 2018-03-09
PP(14) | Mechanical | 140211 | T16182-XJ00-P0QFB-140211 | ISOMETRIC DRAWING FOR INSTRUMENT AIR SYSTEM SMALL BORE | IFI | 2017-12-20 | 2018-03-09 |  | O
PP(14) | Mechanical | 140202 | T16182-XJ00-P0LBC-140202 | ISOMETRIC DRAWING FOR IP STEAM SYSTEM SMALL BORE | IFI | 2018-02-09 | 2018-03-09
PP(14) | Mechanical | 140203 | T16182-XJ00-P0LBG-140203 | ISOMETRIC DRAWING FOR LP STEAM SYSTEM SMALL BORE | IFI | 2018-02-09 | 2018-03-09 |  | O
PP(14) | Mechanical | 140223 | T16182-XJ00-P0QJA-140223 | ISOMETRIC DRAWING FOR N2 GAS SYSTEM SMALL BORE | IFI | 2017-12-20 | 2018-03-09 |  | O
PP(14) | Mechanical | 140212 | T16182-XJ00-P0GKB-140212 | ISOMETRIC DRAWING FOR POTABLE WATER SYSTEM SMALL BORE | IFI | 2017-12-15 | 2018-02-28 |  | O
PP(14) | Mechanical | 140204 | T16182-XJ00-P0LBG-140204 | ISOMETRIC DRAWING FOR PROCESS STEAM SYSTEM SMALL BORE | IFI | 2017-12-15 | 2018-02-28 |  | O
PP(14) | Mechanical | 140219 | T16182-XJ00-P0QUB-140219 | ISOMETRIC DRAWING FOR SAMPLING SYSTEM SMALL BORE | IFI | 2018-02-20 | 2018-03-21
PP(14) | Mechanical | 140210 | T16182-XJ00-P0SCA-140210 | ISOMETRIC DRAWING FOR SERVICE AIR SYSTEM SMALL BORE | IFI | 2017-12-20 | 2018-03-09
PP(14) | Mechanical | 140205 | T16182-XJ00-P0LCM-140205 | ISOMETRIC DRAWING FOR STEAM DRAIN SYSTEM SMALL BORE | IFI | 2018-02-14 | 2018-03-13
PP(14) | Mechanical | 140120 | T16182-XJ00-P0ZEN-140120 | ISOMETRIC DRAWING FOR TG MISCELLANEOUS SMALL BORE SYSTEM | IFI | 2018-03-09 | 2018-04-13
PP(14) | Mechanical | 140215 | T16182-XJ00-P0GKB-140215 | ISOMETRIC DRAWING FOR UNDERGROUND PIPING SYSTEM | IFI | 2017-11-10 | 2017-12-04
PP(14) | Mechanical | 140224 | T16182-XJ00-P0GM-140224 | ISOMETRIC DRAWING FOR WASTE WATER SYSTEM SMALL BORE | IFI | 2018-02-16 | 2018-03-16
TG-MCH(22) | Mechanical | 220383 | T16182-XJ00-P6MAA-220383 | ISOMETRIC DRAWINGS OF PIPELINES - SMALL BORE PIPING P6 | IFI | 2018-10-26 |  |  |  |  | PKG-040-STG
TG-MCH(22) | Mechanical | 220384 | T16182-XJ00-P7MAA-220384 | ISOMETRIC DRAWINGS OF PIPELINES - SMALL BORE PIPING P7 | IFI | 2018-10-26 |  |  |  |  | PKG-040-STG
PT(12) | Mechanical | 128037 | T16182-YT01-P0SMU-128037 | JIB CRANE - DATA SHEETS FOR AIR COOLED CONDENSER JIB CRANE | IFI | 2018-03-31 | 2018-02-09 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128052 | T16182-YD00-P0SMG-128052 | JIB CRANE - DATA SHEETS FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | IFI | 2018-01-30 | 2018-03-30 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128032 | T16182-YD00-P0SMU-128032 | JIB CRANE - GA DRAWING FOR AIR COOLED CONDENSER JIB CRANE | IFI | 2018-03-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128051 | T16182-YD00-P0SMG-128051 | JIB CRANE - GA DRAWING FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | IFI | 2018-01-30 | 2018-03-30 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128042 | T16182-YK09-P0SMU-128042 | JIB CRANE - MECHANICAL DETAIL FOR AIR COOLED CONDENSER JIB CRANE | IFI | 2018-05-31 | 2018-02-23 |  |  |  | PKG-022-CR
PT(12) | Mechanical | 128053 | T16182-YD00-P0SMG-128053 | JIB CRANE - MECHANICAL DETAIL FOR ATM. FLESH TANK DRAIN PUMP JIB CRANE | IFI | 2018-01-30 | 2018-03-30 |  |  |  | PKG-022-CR
PT(12) | Electrical | 126530 | T16182-YD00-P0PCA-126530 | JUNCTION BOX OUTLINE AND LAYOUT DRAWING | IFI | 2017-07-04 |  |  | O |  | PKG-018-FFC
PP(14) | Mechanical | 140020 | T16182-XH01-P0ZEN-140020 | KEY PLAN DRAWING | IFI | 2017-09-29
EL(15) | Electrical | 150202 | T16182-YU02-P0ZEN-150202 | KEY SINGLE LINE DIAGRAM | IFR | 2016-12-01 | 2017-05-04 | O | O | O
EM(02) | Engineering Management | 020008 | T16182-YK08-P0ZEN-020008 | LABELING LAYOUT FOR WATER STORAGE TANKS | IFI | 2018-06-04 | 2018-09-07
CV(17) | Civil | 173501 | T16182-XB02-P0UZK-173501 | LANDSCAPE LAYOUT | IFR | 2019-03-01 | 2018-09-29
CV(17) | Civil | 173502 | T16182-VK02-P0UZK-173502 | LANDSCAPING CROSS SECTION & DETAIL | IFR | 2019-03-01 | 2018-09-29
TG-MCH(22) | Mechanical | 220015 | T16182-XM00-P0MAA-220015 | LAYDOWN PLAN - UNIT P6 & P7 | IFI | 2017-02-24 |  |  |  |  | PKG-040-STG
|  | 860008 | T16182-DN05-P0ZEN-860008 | LDC Integration
EL(15) | Electrical | 152308 | T16182-YQ01-P0ZEN-152308 | LIGHTING & SMALL POWER LAYOUT DRAWING - ADMINISTRATION | IFI | 2018-07-02 | 2018-03-27
EL(15) | Electrical | 152317 | T16182-YQ01-P0ZEN-152317 | LIGHTING & SMALL POWER LAYOUT DRAWING - AIR COMPRESSOR SHELTER | IFI | 2018-01-05 | 2018-03-06
EL(15) | Electrical | 152301 | T16182-YQ01-P0ZEN-152301 | LIGHTING & SMALL POWER LAYOUT DRAWING - CENTRAL CONTROL BUILDING | IFI | 2017-08-15 | 2017-10-14 |  | O
EL(15) | Electrical | 152324 | T16182-YQ01-P0ZEN-152324 | LIGHTING & SMALL POWER LAYOUT DRAWING - CHEMICAL DOSING SHELTER FOR HRSG | IFI | 2018-05-11 | 2018-07-10
EL(15) | Electrical | 152323 | T16182-YQ01-P0ZEN-152323 | LIGHTING & SMALL POWER LAYOUT DRAWING - CHEMICAL DOSING SHELTER FOR STG & HRSG | IFI | 2018-04-17 | 2018-06-16
EL(15) | Electrical | 152322 | T16182-YQ01-P0ZEN-152322 | LIGHTING & SMALL POWER LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | IFI | 2018-03-23 | 2018-05-22
EL(15) | Electrical | 152318 | T16182-YQ01-P0ZEN-152318 | LIGHTING & SMALL POWER LAYOUT DRAWING - DEAERATOR SUPPORT STRUCTURE | IFI | 2017-12-15 | 2018-02-13
EL(15) | Electrical | 152307 | T16182-YQ01-P0ZEN-152307 | LIGHTING & SMALL POWER LAYOUT DRAWING - FGS ELECTRICAL BUILDING | IFI | 2018-01-05 | 2018-03-06 |  | O
EL(15) | Electrical | 152314 | T16182-YQ01-P0ZEN-152314 | LIGHTING & SMALL POWER LAYOUT DRAWING - FIRE BRIGADE & AUX. LEB | IFI | 2018-08-03 | 2018-05-17
EL(15) | Electrical | 152319 | T16182-YQ01-P0ZEN-152319 | LIGHTING & SMALL POWER LAYOUT DRAWING - FIRE WATER PUMP HOUSE | IFI | 2017-09-03 | 2017-11-02
EL(15) | Electrical | 152302 | T16182-YQ01-P0ZEN-152302 | LIGHTING & SMALL POWER LAYOUT DRAWING - GTG #1,2 LEB | IFI | 2017-09-03 | 2017-11-02 |  | O
EL(15) | Electrical | 152303 | T16182-YQ01-P0ZEN-152303 | LIGHTING & SMALL POWER LAYOUT DRAWING - GTG #3,4,5 LEB | IFI | 2017-12-23 | 2018-02-21
EL(15) | Electrical | 152316 | T16182-YQ01-P0ZEN-152316 | LIGHTING & SMALL POWER LAYOUT DRAWING - H2, CO2, N2 STORAGE SHELTER | IFI | 2017-08-25 | 2018-04-25
EL(15) | Electrical | 152310 | T16182-YQ01-P0ZEN-152310 | LIGHTING & SMALL POWER LAYOUT DRAWING - MAIN GATE HOUSE | IFI | 2018-04-21 | 2018-10-24
EL(15) | Electrical | 152313 | T16182-YQ01-P0ZEN-152313 | LIGHTING & SMALL POWER LAYOUT DRAWING - MAIN GATE HOUSE SUNSHADE | IFI | 2018-04-21 | 2018-10-24
EL(15) | Electrical | 152309 | T16182-YQ01-P0ZEN-152309 | LIGHTING & SMALL POWER LAYOUT DRAWING - SECURITY BUILDING | IFI | 2018-12-01 | 2018-10-24
EL(15) | Electrical | 152304 | T16182-YQ01-P0ZEN-152304 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST #1 LEB | IFI | 2017-12-03 | 2018-02-01
EL(15) | Electrical | 152305 | T16182-YQ01-P0ZEN-152305 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST #2 LEB | IFI | 2018-01-05 | 2018-03-06
EL(15) | Electrical | 152306 | T16182-YQ01-P0ZEN-152306 | LIGHTING & SMALL POWER LAYOUT DRAWING - ST BUILDING | IFI | 2018-05-19 | 2018-07-18
EL(15) | Electrical | 152311 | T16182-YQ01-P0ZEN-152311 | LIGHTING & SMALL POWER LAYOUT DRAWING - SUPPORT BUILDING | IFI | 2018-04-21 | 2018-10-24
EL(15) | Electrical | 152321 | T16182-YQ01-P0ZEN-152321 | LIGHTING & SMALL POWER LAYOUT DRAWING - WATER TREATMENT BUILDING | IFI | 2017-08-29 | 2017-10-28 |  | O
EL(15) | Electrical | 152315 | T16182-YQ01-P0ZEN-152315 | LIGHTING & SMALL POWER LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | IFI | 2018-03-19 | 2018-05-18
EL(15) | Electrical | 152320 | T16182-YQ01-P0ZEN-152320 | LIGHTING & SMALL POWER LAYOUT DRAWING - WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-10-30 | 2017-12-29
EL(15) | Electrical | 152312 | T16182-YQ01-P0ZEN-152312 | LIGHTING & SMALL POWER LAYOUT DRAWING - X-RAY SEARCHING ROOM | IFI | 2018-04-21 | 2018-10-24
EL(15) | Electrical | 152327 | T16182-YQ01-P0ZEN-152327 | LIGHTING & SMALL POWER LAYOUT DRAWING - YARD | IFR | 2018-03-14 | 2018-07-12
EL(15) | Electrical | 152332 | T16182-YQ01-P0ZEN-152332 | LIGHTING & SMALL POWER LAYOUT DRAWING – FUEL GAS SYSTEM AREA | IFI | 2018-04-06 | 2018-07-06
EL(15) | Electrical | 152329 | T16182-YQ01-P0ZEN-152329 | LIGHTING & SMALL POWER LAYOUT DRAWING – GTG #1, 2 TRANSFORMER AREA | IFI | 2018-01-22 | 2018-03-22
EL(15) | Electrical | 152330 | T16182-YQ01-P0ZEN-152330 | LIGHTING & SMALL POWER LAYOUT DRAWING – GTG #3, 4, 5 TRANSFORMER AREA | IFI | 2018-03-02 | 2018-06-01
EL(15) | Electrical | 152331 | T16182-YQ01-P0ZEN-152331 | LIGHTING & SMALL POWER LAYOUT DRAWING – STG #1, 2 TRANSFORMER AREA | IFI | 2018-03-02 | 2018-06-01
EL(15) | Electrical | 152328 | T16182-YQ01-P0ZEN-152328 | LIGHTING & SMALL POWER LAYOUT DRAWING – TANK AREA | IFI | 2018-01-22 | 2018-03-22
EL(15) | Electrical | 152333 | T16182-YQ01-P0ZEN-152333 | LIGHTING & SMALL POWER LAYOUT DRAWING – WELDING SHED AND CONTAINER AT OPEN STORAGE AREA | IFI | 2020-01-10 | 2020-02-07
EL(15) | Electrical | 152408 | T16182-YB11-P0ZEN-152408 | LIGHTING PANEL BOARD SCHEDULE - ADMINISTRATION | IFI | 2018-07-02 | 2018-04-23
EL(15) | Electrical | 152401 | T16182-YB11-P0ZEN-152401 | LIGHTING PANEL BOARD SCHEDULE - CENTRAL CONTROL BUILDING | IFI | 2017-08-15 | 2018-04-23 |  | O
EL(15) | Electrical | 152422 | T16182-YB11-P0ZEN-152422 | LIGHTING PANEL BOARD SCHEDULE - CPP & CPP REGENERATION BUILDING | IFI | 2018-03-23 | 2018-06-30
EL(15) | Electrical | 152418 | T16182-YB11-P0ZEN-152418 | LIGHTING PANEL BOARD SCHEDULE - DEAERATOR SUPPORT STRUCTURE | IFI | 2017-12-15 | 2018-04-23
EL(15) | Electrical | 152407 | T16182-YB11-P0ZEN-152407 | LIGHTING PANEL BOARD SCHEDULE - FGS ELECTRICAL BUILDING | IFI | 2018-01-05 | 2018-04-23 |  | O
EL(15) | Electrical | 152414 | T16182-YB11-P0ZEN-152414 | LIGHTING PANEL BOARD SCHEDULE - FIRE BRIGADE & AUX. LEB | IFI | 2018-08-03 | 2018-04-23
EL(15) | Electrical | 152419 | T16182-YB11-P0ZEN-152419 | LIGHTING PANEL BOARD SCHEDULE - FIRE WATER PUMP HOUSE | IFI | 2017-09-03 | 2018-04-23
EL(15) | Electrical | 152402 | T16182-YB11-P0ZEN-152402 | LIGHTING PANEL BOARD SCHEDULE - GTG #1,2 LEB | IFI | 2017-09-03 | 2018-04-23 |  | O
EL(15) | Electrical | 152403 | T16182-YB11-P0ZEN-152403 | LIGHTING PANEL BOARD SCHEDULE - GTG #3,4,5 LEB | IFI | 2017-12-23 | 2018-04-23
EL(15) | Electrical | 152409 | T16182-YB11-P0ZEN-152409 | LIGHTING PANEL BOARD SCHEDULE - SECURITY BUILDING | IFI | 2018-12-01 | 2019-03-12
EL(15) | Electrical | 152404 | T16182-YB11-P0ZEN-152404 | LIGHTING PANEL BOARD SCHEDULE - ST #1 LEB | IFI | 2017-12-03 | 2018-04-23
EL(15) | Electrical | 152405 | T16182-YB11-P0ZEN-152405 | LIGHTING PANEL BOARD SCHEDULE - ST #2 LEB | IFI | 2018-01-05 | 2018-04-23
EL(15) | Electrical | 152406 | T16182-YB11-P0ZEN-152406 | LIGHTING PANEL BOARD SCHEDULE - ST BUILDING | IFI | 2018-05-19 | 2018-07-26
EL(15) | Electrical | 152411 | T16182-YB11-P0ZEN-152411 | LIGHTING PANEL BOARD SCHEDULE - SUPPORT BUILDING | IFI | 2018-04-21 | 2019-03-12
EL(15) | Electrical | 152421 | T16182-YB11-P0ZEN-152421 | LIGHTING PANEL BOARD SCHEDULE - WATER TREATMENT BUILDING | IFI | 2017-08-29 | 2018-04-23 |  | O
EL(15) | Electrical | 152415 | T16182-YB11-P0ZEN-152415 | LIGHTING PANEL BOARD SCHEDULE - WORKSHOP & STORAGE BUILDING | IFI | 2018-03-19 | 2018-06-30
EL(15) | Electrical | 152427 | T16182-YB11-P0ZEN-152427 | LIGHTING PANEL BOARD SCHEDULE - YARD | IFI | 2018-03-14 | 2018-06-30
EL(15) | Electrical | 152428 | T16182-YB11-P0ZEN-152428 | LIGHTING PANEL BOARD SCHEDULE – TANK AREA | IFI | 2018-01-22 | 2018-07-26
CV(17) | Civil | 173003 | T16182-XB02-P0UZT-173003 | LIGHTING POLE FOUNDATION LAYOUT | IFR | 2018-04-13 | 2018-07-13
CV(17) | Civil | 173002 | T16182-XB02-P0UZT-173002 | LIGHTING POLE FOUNDATION OVERALL LAYOUT | IFR | 2018-04-13 | 2018-07-13
CV(17) | Civil | 173008 | T16182-VK02-P0UZT-173008 | LIGHTING POLE FOUNDATION PLAN & DETAIL | IFR | 2018-04-13 | 2018-07-13
EL(15) | Electrical | 152608 | T16182-YE01-P0BAU-152608 | LIGHTNING PROTECTION LAYOUT DRAWING - ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-07-16 | 2018-03-26
EL(15) | Electrical | 152601 | T16182-YE01-P0BAU-152601 | LIGHTNING PROTECTION LAYOUT DRAWING - CENTRAL CONTROL BUILDING | IFI | 2017-11-30 | 2018-02-02 |  | O
EL(15) | Electrical | 152621 | T16182-YE01-P0BAU-152621 | LIGHTNING PROTECTION LAYOUT DRAWING - CPP & CPP REGENERATION BUILDING | IFI | 2017-09-28 | 2017-11-15
EL(15) | Electrical | 152602 | T16182-YE01-P0BAU-152602 | LIGHTNING PROTECTION LAYOUT DRAWING - GTG #1,2 LEB | IFI | 2017-06-29 | 2017-08-22 |  | O
EL(15) | Electrical | 152603 | T16182-YE01-P0BAU-152603 | LIGHTNING PROTECTION LAYOUT DRAWING - GTG #3,4,5 LEB | IFI | 2017-09-18 | 2017-11-15
EL(15) | Electrical | 152600 | T16182-YE01-P0BAU-152600 | LIGHTNING PROTECTION LAYOUT DRAWING - OVERALL AREA | IFI | 2017-12-15 | 2018-01-23
EL(15) | Electrical | 152609 | T16182-YE01-P0BAU-152609 | LIGHTNING PROTECTION LAYOUT DRAWING - SECURITY BUILDING | IFI | 2018-09-01 | 2018-07-24
EL(15) | Electrical | 152606 | T16182-YE01-P0BAU-152606 | LIGHTNING PROTECTION LAYOUT DRAWING - ST BUILDING | IFI | 2018-04-14 | 2018-07-14
EL(15) | Electrical | 152620 | T16182-YE01-P0BAU-152620 | LIGHTNING PROTECTION LAYOUT DRAWING - WATER TREATMENT BUILDING | IFI | 2017-07-29 | 2018-02-02 |  | O
EL(15) | Electrical | 152614 | T16182-YE01-P0BAU-152614 | LIGHTNING PROTECTION LAYOUT DRAWING - WORKSHOP & STORAGE BUILDING | IFI | 2018-05-15 | 2018-03-26
GN-SYS(26) | Mechanical | 260035 | T16182-XL00-P0MKA-260035 | LINE LIST FOR ST GENERATOR | IFR | 2017-04-30 | 2017-07-30 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260013 | T16182-YD00-P0MKW-260013 | LIQUID LEVEL DETECTOR OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG
MCH(13) | Mechanical | 134001 | T16182-XW03-P0SAL-134001 | LOAD CALCULATION OF HVAC SYSTEM FOR ADMIN & SOCIAL BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135201 | T16182-XW03-P0SAQ-135201 | LOAD CALCULATION OF HVAC SYSTEM FOR AUX. LEB | IFR | 2018-01-18 | 2018-02-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133501 | T16182-XW03-P0SAC-133501 | LOAD CALCULATION OF HVAC SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-03-17 | 2017-05-01 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 135001 | T16182-XW03-P0SAM-135001 | LOAD CALCULATION OF HVAC SYSTEM FOR CPP & CPP REGEN BUILDING | IFR | 2017-08-29 | 2017-10-28 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133701 | T16182-XW03-P0SAJ-133701 | LOAD CALCULATION OF HVAC SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-08-04 | 2017-10-03 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 134701 | T16182-XW03-P0SAF-134701 | LOAD CALCULATION OF HVAC SYSTEM FOR FIRE BRIGADE | IFR | 2017-10-29 | 2017-12-28 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134901 | T16182-XW03-P0SAG-134901 | LOAD CALCULATION OF HVAC SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-06-14 | 2017-08-13 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 133801 | T16182-XW03-P0SAI-133801 | LOAD CALCULATION OF HVAC SYSTEM FOR GTG #1/2 LEB | IFR | 2017-03-26 | 2017-05-15 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 133901 | T16182-XW03-P0SAI-133901 | LOAD CALCULATION OF HVAC SYSTEM FOR GTG #3/4/5 LEB | IFR | 2017-04-30 | 2017-06-29 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134301 | T16182-XW03-P0SAE-134301 | LOAD CALCULATION OF HVAC SYSTEM FOR MAIN GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135401 | T16182-XW03-P0SAE-135401 | LOAD CALCULATION OF HVAC SYSTEM FOR PIC GATE HOUSE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135301 | T16182-XW03-P0SAE-135301 | LOAD CALCULATION OF HVAC SYSTEM FOR PLANT ACCESS GATE HOUSE | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134601 | T16182-XW03-P0SAE-134601 | LOAD CALCULATION OF HVAC SYSTEM FOR SEARCH FACILITY & VISITORS CENTRE | IFR | 2018-04-20 | 2018-06-20 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134501 | T16182-XW03-P0SAD-134501 | LOAD CALCULATION OF HVAC SYSTEM FOR SECURITY BUILDING | IFR | 2018-07-17 | 2018-10-16 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 135101 | T16182-XW03-P0SAV-135101 | LOAD CALCULATION OF HVAC SYSTEM FOR SHELTER FOR WASTE WATER TREATMENT W/ OILY WATER SEPARATOR | IFR | 2017-04-30 | 2017-06-30 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 134101 | T16182-XW03-P0SAR-134101 | LOAD CALCULATION OF HVAC SYSTEM FOR ST #1 LEB | IFR | 2017-06-22 | 2017-08-21 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134201 | T16182-XW03-P0SAR-134201 | LOAD CALCULATION OF HVAC SYSTEM FOR ST #2 LEB | IFR | 2017-07-22 | 2017-09-20 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133401 | T16182-XW03-P0SAH-133401 | LOAD CALCULATION OF HVAC SYSTEM FOR STEAM TURBINE BUILDING | IFR | 2017-06-14 | 2017-08-13 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 134401 | T16182-XW03-P0SAN-134401 | LOAD CALCULATION OF HVAC SYSTEM FOR SUPPORT BUILDING | IFR | 2018-03-16 | 2018-05-14 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 133601 | T16182-XW03-P0SAK-133601 | LOAD CALCULATION OF HVAC SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-04-15 | 2017-06-14 |  | O |  | PKG-041-HVAC
MCH(13) | Mechanical | 134801 | T16182-XW03-P0SAB-134801 | LOAD CALCULATION OF HVAC SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2017-09-14 | 2017-11-13 |  |  |  | PKG-041-HVAC
EL(15) | Electrical | 150302 | T16182-YT10-P0ZEN-150302 | LOAD FLOW & LARGE MOTOR STARTING STUDY | IFR | 2017-04-30 | 2017-10-15 |  | O
|  | 860007 | T16182-DN05-P0ZEN-860007 | LOAD SWING TEST
TG-MCH(22) | Instrumentation & Control | 220097 | T16182-YF00-P6MAA-220097 | LOGIC DIAGRAMS FOR ST | IFI | 2018-06-29 |  |  |  |  | PKG-040-STG
GN-I&C(29) | Instrumentation & Control | 290007 | T16182-YF00-P0MKY-290007 | LOGIC DIAGRAMS OF GENERATOR CONTROL PANEL FOR STG | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG
EL(15) | Electrical | 152003 | T16182-YD16-P0ZEN-152003 | MAIN CABLE ROUTE PLAN | IFR | 2017-01-26 | 2017-05-16 |  | O
EL(15) | Electrical | 152503 | T16182-YT10-P0BAU-152503 | MAIN EARTHING GRID CALCULATION | IFR | 2017-01-26 | 2017-04-08 |  | O
S&A(18) | Structural & Architectural | 183300 | T16182-CA06-P0UYE-183300 | MAIN GATE HOUSE - CALCULATION | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183354 | T16182-CA02-P0UYE-183354 | MAIN GATE HOUSE - COLUMN, GIRDER & BEAM RE - BAR DETAIL | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183302 | T16182-CA00-P0UYE-183302 | MAIN GATE HOUSE - ELEVATIONS | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183351 | T16182-CA01-P0UYE-183351 | MAIN GATE HOUSE - FOUNDATION ARRANGEMENT, GROUND FLOOR FRAMING PLAN | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183355 | T16182-CA02-P0UYE-183355 | MAIN GATE HOUSE - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183353 | T16182-CA01-P0UYE-183353 | MAIN GATE HOUSE - FRAMING ELEVATION | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183301 | T16182-CA00-P0UYE-183301 | MAIN GATE HOUSE - GROUND FLOOR , ROOF PLAN, INTERIOR FINISH, DOOR & WINDOW SCHEDULES | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183352 | T16182-CA01-P0UYE-183352 | MAIN GATE HOUSE - ROOF FRAMING PLAN | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183303 | T16182-CA00-P0UYE-183303 | MAIN GATE HOUSE - SECTIONS & DETAILS | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183375 | T16182-CA03-P0UTX-183375 | MAIN GATE HOUSE SUNSHADE - BASE PLATE & CONNECTION DETAIL | IFR | 2018-04-25 | 2018-06-25
S&A(18) | Structural & Architectural | 183390 | T16182-CA06-P0UTX-183390 | MAIN GATE HOUSE SUNSHADE - CALCULATION | IFR | 2018-04-25 | 2018-06-25
S&A(18) | Structural & Architectural | 183377 | T16182-CA02-P0UTX-183377 | MAIN GATE HOUSE SUNSHADE - FOUNDATION RE - BAR DETAIL | IFR | 2018-04-25 | 2018-06-25
S&A(18) | Structural & Architectural | 183373 | T16182-CA03-P0UTX-183373 | MAIN GATE HOUSE SUNSHADE - FRAMING ELEVATION | IFR | 2018-04-25 | 2018-06-25
S&A(18) | Structural & Architectural | 183361 | T16182-CA00-P0UTX-183361 | MAIN GATE HOUSE SUNSHADE - GROUND FLOOR, ROOF PLAN & ELEVATION | IFR | 2018-04-25 | 2018-06-25
S&A(18) | Structural & Architectural | 183372 | T16182-CA03-P0UTX-183372 | MAIN GATE HOUSE SUNSHADE - ROOF FRAMING PLAN (BOTTOM CHORD) | IFR | 2018-04-25 | 2018-06-25
S&A(18) | Structural & Architectural | 183371 | T16182-CA03-P0UTX-183371 | MAIN GATE HOUSE SUNSHADE - ROOF FRAMING PLAN (TOP CHORD) | IFR | 2018-04-25 | 2018-06-25
PS(11) | Electrical | 110405 | T16182-YD00-P0PGB-110405 | MAIN TERMINAL BOX DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | IFI | 2017-04-30 |  |  | O |  | PKG-005-CCWP
EM(02) | Engineering Management | 020020 | T16182-BV02-P0ZEN-020020 | MAINTAINABILITY STUDY | IFI | 2018-09-20
PP(14) | Mechanical | 140301 | T16182-YK10-P0LF-140301 | MANUAL BUTTERFLY VALVE OUTLINE DRAWINGS | IFI | 2017-09-15
PP(14) | Mechanical | 140304 | T16182-YK10-P0LF-140304 | MANUAL FORGING VALVE OUTLINE DRAWINGS | IFI | 2017-09-15
PP(14) | Mechanical | 140303 | T16182-YK10-P0LF-140303 | MANUAL HIGH PRESSURE CASTING VALVE OUTLINE DRAWINGS | IFI | 2017-11-17
PP(14) | Mechanical | 140302 | T16182-YK10-P0LF-140302 | MANUAL LOW PRESSURE CASTING VALVE OUTLINE DRAWINGS | IFI | 2017-09-15
PP(14) | Mechanical | 140003 | T16182-XN00-P0ZEN-140003 | MANUAL VALVE LIST | IFI | 2017-05-16 |  |  | O
I&C(16) | Instrumentation & Control | 161011 | T16182-YR05-P0ZEN-161011 | MASTER CLOCK CONCEPT DIAGRAM | IFR | 2017-03-15 | 2017-07-28 |  | O
MCH(13) | Electrical | 130206 | T16182-YD00-P0LD-130206 | MCC ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2017-07-03 | 2018-11-19 |  |  |  | PKG-026-CPP
MCH(13) | Electrical | 130006 | T16182-YD00-P0GCF-130006 | MCC ARRANGEMENT DRAWING FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-03-06 | 2017-07-25 |  | O |  | PKG-025-WT
PT(12) | General | 125597 | T16182-YR01-P8ZEN-125597 | METHODS STATEMENTS OF STEAM FLUSHING FOR RESERVE BOILER | IFR | 2018-09-10 | 2018-10-30 |  |  |  | PKG-015-RB
|  | 860010 | T16182-DN05-P0ZEN-860010 | MINIMUM LOAD TEST
S&A(18) | Structural & Architectural | 184800 | T16182-CA06-P0QJA-184800 | N2 STORAGE SHELTER - CALCULATION | IFR | 2017-03-25 | 2017-05-25
S&A(18) | Structural & Architectural | 184802 | T16182-CA00-P0QJA-184802 | N2 STORAGE SHELTER - ELEVATION | IFR | 2017-03-25 | 2017-05-25
S&A(18) | Structural & Architectural | 184851 | T16182-CA01-P0QJA-184851 | N2 STORAGE SHELTER - FOUNDATION, COLUMN ARRAGEMENT PLAN | IFR | 2017-03-25 | 2017-05-25
S&A(18) | Structural & Architectural | 184853 | T16182-CA01-P0QJA-184853 | N2 STORAGE SHELTER - FRAMING ELEVATION | IFR | 2017-03-25 | 2017-05-25
S&A(18) | Structural & Architectural | 184852 | T16182-CA01-P0QJA-184852 | N2 STORAGE SHELTER - GROUND FLOOR FRAMING PLAN, ROOF FRAMING PLAN | IFR | 2017-03-25 | 2017-05-25
S&A(18) | Structural & Architectural | 184801 | T16182-CA00-P0QJA-184801 | N2 STORAGE SHELTER - GROUND FLOOR PLAN, ROOF PLAN | IFR | 2017-03-25 | 2017-05-25
S&A(18) | Structural & Architectural | 184803 | T16182-CA00-P0QJA-184803 | N2 STORAGE SHELTER - MAIN SECTION | IFR | 2017-03-25 | 2017-05-25
S&A(18) | Structural & Architectural | 184854 | T16182-CA02-P0QJA-184854 | N2 STORAGE SHELTER - REBAR DETAIL | IFR | 2017-03-25 | 2017-05-25
EM(02) | Engineering Management | 020006 | T16182-DP00-P0ZEN-020006 | NAME AND TAG PLATE | IFI | 2017-06-01
PS(11) | Mechanical | 110402 | T16182-YL22-P0PGB-110402 | NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP | IFI | 2017-04-30 |  |  | O |  | PKG-005-CCWP
PS(11) | Electrical | 110406 | T16182-YL22-P0PGB-110406 | NAMEPLATE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | IFI | 2017-04-30 |  |  | O |  | PKG-005-CCWP
S&A(18) | Structural & Architectural | 186600 | T16182-CA06-P0UGD-186600 | NAOCL DOSING SKID SHELTER - CALCULATION | IFR | 2017-09-15 | 2017-11-15
S&A(18) | Structural & Architectural | 186602 | T16182-CA00-P0UGD-186602 | NAOCL DOSING SKID SHELTER - ELEVATION & SECTION | IFR | 2017-09-15 | 2017-11-15
S&A(18) | Structural & Architectural | 186651 | T16182-CA01-P0UGD-186651 | NAOCL DOSING SKID SHELTER - FND, GROUND, ROOF FRAMING PLAN & FRAMING ELEVATION | IFR | 2017-09-15 | 2017-11-15
S&A(18) | Structural & Architectural | 186601 | T16182-CA00-P0UGD-186601 | NAOCL DOSING SKID SHELTER - GROUND & ROOF FLOOR PLAN | IFR | 2017-09-15 | 2017-11-15
S&A(18) | Structural & Architectural | 186652 | T16182-CA01-P0UGD-186652 | NAOCL DOSING SKID SHELTER - REBAR DETAIL | IFR | 2017-09-15 | 2017-11-15
|  | 860014 | T16182-DN05-P0ZEN-860014 | NET DEPENDABLE CAPACITY TEST
PS(11) | General | 110701 | T16182-CN00-P0ZEN-110701 | OPERATION PHILOSOPHY OF OVERALL PLANT | IFR | 2017-04-15 | 2017-07-03
MCH(13) | Mechanical | 136610 | T16182-YT01-P0SGA-136610 | OUTDOOR HYDRANT SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
EL(15) | Electrical | 152822 | T16182-YD00-P0ZEN-152822 | OUTLINE & SCHEMATIC DRAWING - 380KV EHV CABLE AND ACCESSOIRES | IFR | 2017-03-10 | 2017-05-26
EL(15) | Electrical | 150939 | T16182-YD00-P0BF-150939 | OUTLINE DRAWING - 13.8/0.48kV MOLD TRANSFORMER | IFI | 2017-04-30 |  | O |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150936 | T16182-YD00-P0BF-150936 | OUTLINE DRAWING - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | IFI | 2017-04-30 |  | O |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150937 | T16182-YD00-P0BF-150937 | OUTLINE DRAWING - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | IFI | 2017-06-30 |  | O |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150938 | T16182-YD00-P0BF-150938 | OUTLINE DRAWING - 480V COMMON ESSENTIAL SWITCHGEAR | IFI | 2017-04-30 |  | O |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150933 | T16182-YD00-P0BF-150933 | OUTLINE DRAWING - 480V COMMON SWITCHGEAR | IFI | 2017-04-30 |  | O |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150935 | T16182-YD00-P0BF-150935 | OUTLINE DRAWING - 480V FIRE BRIGADE SWITCHGEAR | IFI | 2017-06-30 |  | O |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150931 | T16182-YD00-P0BF-150931 | OUTLINE DRAWING - 480V GTG/HRSG SWITCHGEAR | IFI | 2017-04-30 |  | O |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150940 | T16182-YD00-P0BF-150940 | OUTLINE DRAWING - 480V NON SEGREGATED PHASE BUS DUCT | IFI | 2017-06-30 |  | O |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150932 | T16182-YD00-P0BF-150932 | OUTLINE DRAWING - 480V STG/ACC SWITCHGEAR | IFI | 2017-06-30 |  | O |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150934 | T16182-YD00-P0BF-150934 | OUTLINE DRAWING - 480V WT SWITCHGEAR | IFI | 2017-04-30 |  | O |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 151041 | T16182-YD00-P0BT-151041 | OUTLINE DRAWING - BLOCK #1 DC & AC UPS SYSTEM | IFI | 2017-07-07 |  |  |  |  | PKG-036-DCACUPS
EL(15) | Electrical | 151046 | T16182-YD00-P0BT-151046 | OUTLINE DRAWING - BLOCK #2 DC & AC UPS SYSTEM | IFI | 2017-07-07 |  |  |  |  | PKG-036-DCACUPS
EL(15) | Electrical | 151051 | T16182-YD00-P0BT-151051 | OUTLINE DRAWING - COMMON DC & AC UPS SYSTEM | IFI | 2017-07-07 |  |  |  |  | PKG-036-DCACUPS
EL(15) | Electrical | 150721 | T16182-YD00-P0BAC-150721 | OUTLINE DRAWING - GENERATOR CIRCUIT BREAKER | IFI | 2017-05-26 |  | O | O |  | PKG-032-GCB
EL(15) | Electrical | 150621 | T16182-YD00-P0BAT-150621 | OUTLINE DRAWING - GENERATOR STEP - UP TRANSFORMER (GTG) | IFI | 2017-04-14 |  | O | O |  | PKG-031-TR
EL(15) | Electrical | 150626 | T16182-YD00-P0BAT-150626 | OUTLINE DRAWING - GENERATOR STEP - UP TRANSFORMER (STG) | IFI | 2017-06-02 |  |  |  |  | PKG-031-TR
EL(15) | Electrical | 151171 | T16182-YD00-P0CFA-151171 | OUTLINE DRAWING - METERING PANEL | IFI | 2017-05-15 |  |  |  |  | PKG-038-MP
EL(15) | Electrical | 150821 | T16182-YD00-P0BB-150821 | OUTLINE DRAWING - MV SWITCHGEAR | IFI | 2017-04-30 |  | O |  |  | PKG-034-MVSWGR
EL(15) | Electrical | 151111 | T16182-YD00-P0CHB-151111 | OUTLINE DRAWING - PROTECTION RELAY PANEL & FMS FOR GTG UNIT | IFI | 2017-05-15 |  |  |  |  | PKG-037-PRP
EL(15) | Electrical | 151112 | T16182-YD00-P0CHB-151112 | OUTLINE DRAWING - PROTECTION RELAY PANEL & FMS FOR STG UNIT | IFI | 2017-05-15 |  |  |  |  | PKG-037-PRP
EL(15) | Electrical | 150671 | T16182-YD00-P0BBT-150671 | OUTLINE DRAWING - UNIT AUXILIARY TRANSFORMER | IFI | 2017-03-17 |  | O | O |  | PKG-031-TR
TK(40) | Mechanical | 420030 | T16182-YK08-P0LCM-420030 | OUTLINE DRAWING FOR ATMOSPHERIC FLASH TANK | IFR | 2017-04-14 | 2017-09-29
PS(11) | Mechanical | 110154 | T16182-YK08-P0MAN-110154 | OUTLINE DRAWING FOR BYPASS AND PRDS | IFI | 2017-06-30 | 2017-08-29 |  |  |  | PKG-002-PRDS
TK(40) | Mechanical | 420020 | T16182-YK08-P0PGB-420020 | OUTLINE DRAWING FOR CCW CHEMICAL ADDITIVE TANK | IFR | 2017-03-10 | 2017-09-15 |  | O
TK(40) | Mechanical | 420010 | T16182-YK08-P0PGB-420010 | OUTLINE DRAWING FOR CCW EXPANSION HEAD TANK | IFR | 2017-03-10 | 2017-09-15 |  | O
TK(40) | Mechanical | 420050 | T16182-YK08-P0GKC-420050 | OUTLINE DRAWING FOR CHILLED WATER STORAGE TANK | IFR | 2017-10-31 | 2017-12-15
PS(11) | Electrical | 110404 | T16182-YD00-P0PGB-110404 | OUTLINE DRAWING FOR CLOSED COOLING WATER PUMP MOTOR | IFI | 2017-04-30 |  |  | O |  | PKG-005-CCWP
PS(11) | Mechanical | 110302 | T16182-YD00-P0LCP-110302 | OUTLINE DRAWING FOR CONDENSATE PLATE TYPE HEAT EXCHANGER | IFR | 2017-05-15 | 2017-09-14 |  |  |  | PKG-004-PHE
TK(40) | Mechanical | 410001 | T16182-YK10-P0LCP-410001 | OUTLINE DRAWING FOR CONDENSATE STORAGE TANK | IFR | 2017-02-17 | 2017-04-28 |  | O
TK(40) | Mechanical | 410011 | T16182-YK10-P0GHC-410011 | OUTLINE DRAWING FOR DEMINERALIZED WATER STORAGE TANK | IFR | 2017-02-17 | 2017-04-28 |  | O
PS(11) | Mechanical | 110604 | T16182-YK10-P0LF-110604 | OUTLINE DRAWING FOR MOV (BUTTERFLY) | IFR | 2017-04-30 | 2017-09-14 |  | O |  | PKG-010-MOVB
PS(11) | Mechanical | 110602 | T16182-YK10-P0LF-110602 | OUTLINE DRAWING FOR MOV (G&G) | IFR | 2017-04-17 | 2017-09-14 |  | O |  | PKG-009-MOVG
TK(40) | Mechanical | 410021 | T16182-YK10-P0GKB-410021 | OUTLINE DRAWING FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | IFR | 2017-02-17 | 2017-04-28 |  | O
TK(40) | Mechanical | 410031 | T16182-YK10-P0GKB-410031 | OUTLINE DRAWING FOR POTABLE WATER STORAGE TANK | IFR | 2017-02-17 | 2017-04-28 |  | O
PS(11) | Mechanical | 110102 | T16182-YK08-P0LF-110102 | OUTLINE DRAWING FOR SAFETY RELIEF VALVE AND RUPTURE DISC FOR BOP SYSTEMS | IFI | 2017-05-31 | 2017-07-30 |  |  |  | PKG-001-SRV
PS(11) | Mechanical | 110252 | T16182-YK08-P0LBG-110252 | OUTLINE DRAWING FOR SILENCER | IFI | 2017-07-31 | 2017-09-29 |  |  |  | PKG-003-SILENCER
TK(40) | Mechanical | 420040 | T16182-YK08-P0LCM-420040 | OUTLINE DRAWING FOR VACUUM FLASH TANK | IFR | 2017-04-14 | 2017-09-29
GA(10) | General | 100003 | T16182-UC07-P0ZEN-100003 | OVERALL PLOT PLAN | IFR | 2016-10-30 | 2017-02-14 | O | O | O
GA(10) | General | 100002 | T16182-UC07-P0ZEN-100002 | OVERALL PLOT PLAN WITH ESF AREA | IFR | 2016-10-30 | 2017-02-14 |  | O
PS(11) | Mechanical | 110010 | T16182-XG02-P0PGB-110010 | P&I DIAGRAM FOR CLOSED COOLING WATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 | O | O | O
PT(12) | Mechanical | 120004 | T16182-XG02-P0SCA-120004 | P&I DIAGRAM FOR COMPRESSED AIR SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O | O
PS(11) | Mechanical | 110008 | T16182-XG02-P6LCA-110008 | P&I DIAGRAM FOR CONDENSATE SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  |  | O
PS(11) | Mechanical | 110011 | T16182-XG02-P0GHC-110011 | P&I DIAGRAM FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  | O | O
PS(11) | Mechanical | 110009 | T16182-XG02-P0LAA-110009 | P&I DIAGRAM FOR FEEDWATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 | O |  | O
PT(12) | Mechanical | 120007 | T16182-XG02-P0EK-120007 | P&I DIAGRAM FOR FUEL GAS SYSTEM | IFR | 2017-01-30 | 2017-04-30 | O | O | O | PKG-014-FGS
PS(11) | Mechanical | 110014 | T16182-XG02-P1EKC-110014 | P&I DIAGRAM FOR GT PERFORMANCE HEATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  |  | O
PS(11) | Mechanical | 110003 | T16182-XG02-P0LBA-110003 | P&I DIAGRAM FOR HP STEAM SYSTEM | IFR | 2016-10-28 | 2017-04-28 | O | O | O
PT(12) | Mechanical | 120005 | T16182-XG02-P0SCA-120005 | P&I DIAGRAM FOR INSTRUMENT AIR SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O | O
PS(11) | Mechanical | 110004 | T16182-XG02-P0LBC-110004 | P&I DIAGRAM FOR IP STEAM SYSTEM | IFR | 2016-10-28 | 2017-04-28 | O | O | O
PS(11) | Mechanical | 110005 | T16182-XG02-P0LBG-110005 | P&I DIAGRAM FOR LP STEAM SYSTEM | IFR | 2016-10-28 | 2017-04-28 | O | O | O
PS(11) | Mechanical | 110012 | T16182-XG02-P0QJA-110012 | P&I DIAGRAM FOR NITROGEN GAS SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  | O | O | PKG-006-N2
PT(12) | Mechanical | 120002 | T16182-XG02-P0GKC-120002 | P&I DIAGRAM FOR POTABLE WATER DISTRIBUTION SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O | O
PT(12) | Mechanical | 120001 | T16182-XG02-P0GKB-120001 | P&I DIAGRAM FOR POTABLE WATER STORAGE AND SUPPLY SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O | O
PS(11) | Mechanical | 110006 | T16182-XG02-P0LBS-110006 | P&I DIAGRAM FOR PROCESS STEAM SYSTEM | IFR | 2016-10-28 | 2017-04-28 | O | O | O
PT(12) | Mechanical | 120006 | T16182-XG02-P0SCA-120006 | P&I DIAGRAM FOR SERVICE AIR SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O | O
PS(11) | Mechanical | 110007 | T16182-XG02-P6LCM-110007 | P&I DIAGRAM FOR STEAM DRAIN SYSTEM | IFR | 2016-10-28 | 2017-04-28 |  | O | O
PS(11) | Mechanical | 110002 | T16182-XG02-P0ZEN-110002 | P&I DIAGRAM FOR SYMBOL AND LEGEND | IFR | 2016-10-28 | 2017-03-27 |  | O | O
PT(12) | Mechanical | 120008 | T16182-XG02-P0GM-120008 | P&I DIAGRAM FOR WASTE WATER TRANSFER SYSTEM | IFR | 2017-05-30 | 2017-08-28 |  |  | O
TG-MCH(22) | Mechanical | 220027 | T16182-XG02-P6MAA-220027 | P&I DIAGRAM HPH - UNIT P6 | IFR | 2017-03-17 | 2017-09-22 |  |  | O | PKG-040-STG
TG-MCH(22) | Mechanical | 220029 | T16182-XG02-P6MAA-220029 | P&I DIAGRAM LUBRICATION OIL - UNIT P6 | IFR | 2017-03-17 | 2017-09-22 |  |  | O | PKG-040-STG
TG-MCH(22) | Mechanical | 220030 | T16182-XG02-P7MAA-220030 | P&I DIAGRAM LUBRICATION OIL - UNIT P7 | IFR | 2018-02-21 | 2018-03-21 |  |  |  | PKG-040-STG
TG-MCH(22) | Mechanical | 220025 | T16182-XG02-P6MAA-220025 | P&I DIAGRAM STEAM TURBINE SYSTEM - UNIT P6 | IFR | 2017-03-17 | 2017-09-22 | O |  | O | PKG-040-STG
TG-MCH(22) | Mechanical | 220026 | T16182-XG02-P7MAA-220026 | P&I DIAGRAM STEAM TURBINE SYSTEM - UNIT P7 | IFR | 2018-02-21 | 2018-03-21 |  |  |  | PKG-040-STG
TG-MCH(22) | Mechanical | 220028 | T16182-XG02-P7MAA-220028 | P&I DIAGRAMS HPH - UNIT P7 | IFR | 2018-02-21 | 2018-03-21 |  |  |  | PKG-040-STG
MCH(13) | Mechanical | 139002 | T16182-XG02-P0SGK-139002 | P&ID of Clean Agent system for Administration & Social Building | IFR | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138502 | T16182-XG02-P0SGK-138502 | P&ID OF CLEAN AGENT SYSTEM FOR AUX. LEB | IFR | 2017-11-30 | 2018-01-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 136703 | T16182-XG02-P0SGK-136703 | P&ID OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139602 | T16182-XG02-P0SGK-139602 | P&ID OF CLEAN AGENT SYSTEM FOR CPP BUILDING | IFR | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138608 | T16182-XG02-P0SGK-138608 | P&ID of Clean agent system for Excitation Panel Room for ST Building | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137603 | T16182-XG02-P0SGK-137603 | P&ID OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-11-12 | 2018-02-10 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136803 | T16182-XG02-P0SGK-136803 | P&ID OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | IFR | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136903 | T16182-XG02-P0SGK-136903 | P&ID OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | IFR | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139103 | T16182-XG02-P0SGK-139103 | P&ID OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | IFR | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138702 | T16182-XG02-P0SGK-138702 | P&ID OF CLEAN AGENT SYSTEM FOR ST#1 LEB | IFR | 2017-12-15 | 2018-03-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138802 | T16182-XG02-P0SGK-138802 | P&ID OF CLEAN AGENT SYSTEM FOR ST#2 LEB | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137902 | T16182-XG02-P0SGK-137902 | P&ID OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 137303 | T16182-XG02-P0SGE-137303 | P&ID OF FIRE WATER PUMP FOR FIRE WATER PUMP HOUSE | IFR | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138603 | T16182-XG02-P0SGE-138603 | P&ID OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | IFR | 2018-03-03 | 2018-06-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 136702 | T16182-XG02-P0SGE-136702 | P&ID OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139603 | T16182-XG02-P0SGE-139603 | P&ID OF SPRINKLER SYSTEM FOR CPP BUILDING | IFR | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137302 | T16182-XG02-P0SGE-137302 | P&ID OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136802 | T16182-XG02-P0SGE-136802 | P&ID OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | IFR | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136902 | T16182-XG02-P0SGE-136902 | P&ID OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | IFR | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138602 | T16182-XG02-P0SGE-138602 | P&ID OF SPRINKLER SYSTEM FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137903 | T16182-XG02-P0SGE-137903 | P&ID OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139502 | T16182-XG02-P0SGE-139502 | P&ID OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2018-07-01 | 2018-09-29 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139001 | T16182-XG02-P0SGA-139001 | P&ID OF STAND PIPE SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | IFR | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137701 | T16182-XG02-P0SGA-137701 | P&ID OF STAND PIPE SYSTEM FOR AIR COMPRESSOR SHELTER | IFR | 2018-01-01 | 2018-04-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136701 | T16182-XG02-P0SGA-136701 | P&ID OF STAND PIPE SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139601 | T16182-XG02-P0SGA-139601 | P&ID OF STAND PIPE SYSTEM FOR CPP BUILDING | IFR | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138901 | T16182-XG02-P0SGA-138901 | P&ID OF STAND PIPE SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | IFR | 2017-09-04 | 2017-11-03 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139401 | T16182-XG02-P0SGA-139401 | P&ID OF STAND PIPE SYSTEM FOR FIRE BRIGADE BUILDING | IFR | 2018-05-03 | 2018-08-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137301 | T16182-XG02-P0SGA-137301 | P&ID OF STAND PIPE SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136801 | T16182-XG02-P0SGA-136801 | P&ID OF STAND PIPE SYSTEM FOR GTG #1,2 LEB | IFR | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136901 | T16182-XG02-P0SGA-136901 | P&ID OF STAND PIPE SYSTEM FOR GTG #3,4,5 LEB | IFR | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139101 | T16182-XG02-P0SGA-139101 | P&ID OF STAND PIPE SYSTEM FOR SECURITY BUILDING | IFR | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138601 | T16182-XG02-P0SGA-138601 | P&ID OF STAND PIPE SYSTEM FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137901 | T16182-XG02-P0SGA-137901 | P&ID OF STAND PIPE SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139501 | T16182-XG02-P0SGA-139501 | P&ID OF STAND PIPE SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2018-07-01 | 2018-09-29 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137801 | T16182-XG02-P0SGA-137801 | P&ID OF STAND PIPE SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFR | 2017-11-22 | 2018-02-20 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139301 | T16182-XG02-P0SGA-139301 | P&ID OF STAND PIPE SYSTEM FOR X-RAY SEARCHING ROOM | IFR | 2018-10-17 | 2019-01-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138401 | T16182-XG02-P0SGA-138401 | P&ID of Standpipe system for H2, CO2 Gas Storage Shelter | IFR | 2017-08-03 | 2017-10-30 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138001 | T16182-XG02-P0SGA-138001 | P&ID OF STANDPIPE SYSTEM FOR N2 GAS STORAGE SHELTER | IFR | 2017-09-04 | 2017-11-03 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138201 | T16182-XG02-P0SGC-138201 | P&ID OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | IFR | 2017-07-21 | 2017-10-19 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138101 | T16182-XG02-P0SGC-138101 | P&ID OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | IFR | 2017-11-12 | 2018-02-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137401 | T16182-XG02-P0SGC-137401 | P&ID OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | IFR | 2017-10-18 | 2018-01-16 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138902 | T16182-XG02-P0SGC-138902 | P&ID OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | IFR | 2018-11-19 | 2018-12-20 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138301 | T16182-XG02-P0SGC-138301 | P&ID OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | IFR | 2017-07-19 | 2017-10-17 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138606 | T16182-XG02-P0SGC-138606 | P&ID OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138604 | T16182-XG02-P0SGC-138604 | P&ID OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL UNIT FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137001 | T16182-XG02-P0SGC-137001 | P&ID OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138102 | T16182-XG02-P0SGC-138102 | P&ID OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | IFR | 2019-01-10 | 2019-02-08 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137101 | T16182-XG02-P0SGC-137101 | P&ID OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139901 | T16182-XG02-P0SGC-139901 | P&ID OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | IFR | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137201 | T16182-XG02-P0SGC-137201 | P&ID OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | IFR | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF
EM(02) | Project Management | 020005 | T16182-DP00-P0ZEN-020005 | PACKING SPECIFICATION | IFI | 2017-05-01
EM(02) | Project Management | 020004 | T16182-DP00-P0ZEN-020004 | PAINTING SPECIFICATION | IFR | 2017-04-30 | 2017-07-30
CV(17) | Civil | 173504 | T16182-VK02-P0UZK-173504 | PAVILION PLAN & DETAIL | IFR | 2019-06-01 | 2019-09-01
S&A(18) |  | 189002 | T16182-CA03-P0HBD-189002 | PEECC PLATFORM | Internal
|  | 860021 | T16182-DN05-P0ZEN-860021 | PERFORMANCE TEST PROCEDURE FOR AIR EMISSION
|  | 860020 | T16182-DN05-P0ZEN-860020 | PERFORMANCE TEST PROCEDURE FOR NOISE EMISSION
|  | 860012 | T16182-DN05-P0ZEN-860012 | PERFORMANCE TEST PROCEDURE FOR THERMAL PERFORMANCE
EL(15) | Electrical | 150221 | T16182-YU05-P0ZEN-150221 | PHASING DIAGRAM | IFR | 2017-03-31 | 2017-08-25 |  | O
CV(17) | Civil | 170103 | T16182-VE04-P0ZEN-170103 | PILE CAPACITY CALCULATION | IFR | 2016-10-24 | 2017-01-18
MCH(13) | Mechanical | 136616 | T16182-YT01-P0SGX-136616 | PIPE AND BULK MATERIAL - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138618 | T16182-XH01-P0SGK-138618 | Pipe Layout and detail of Clean agent system for Excitation Panel Room for ST Building | IFI | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139012 | T16182-XH01-P0SGK-139012 | Pipe Layout and detail of Clean Agent system for Administration & Social Building | IFI | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138512 | T16182-XH01-P0SGK-138512 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR AUX. LEB | IFI | 2017-11-30 | 2018-01-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 136713 | T16182-XH01-P0SGK-136713 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139612 | T16182-XH01-P0SGK-139612 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR CPP BUILDING | IFI | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137613 | T16182-XH01-P0SGK-137613 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR FGS ELECTRICAL BUILDING | IFI | 2017-11-12 | 2018-02-10 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136813 | T16182-XH01-P0SGK-136813 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR GTG #1,2 LEB | IFI | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136913 | T16182-XH01-P0SGK-136913 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR GTG #3,4,5 LEB | IFI | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139113 | T16182-XH01-P0SGK-139113 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR SECURITY BUILDING | IFI | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138712 | T16182-XH01-P0SGK-138712 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR ST#1 LEB | IFI | 2017-12-15 | 2018-03-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138812 | T16182-XH01-P0SGK-138812 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR ST#2 LEB | IFI | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137912 | T16182-XH01-P0SGK-137912 | PIPE LAYOUT AND DETAIL OF CLEAN AGENT SYSTEM FOR WATER TREATMENT BUILDING | IFI | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138613 | T16182-XH01-P0SGE-138613 | PIPE LAYOUT AND DETAIL OF PRE - ACTION SPRINKLER SYSTEM FOR ST BUILDING | IFI | 2018-03-03 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 136712 | T16182-XH01-P0SGE-136712 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139613 | T16182-XH01-P0SGE-139613 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR CPP BUILDING | IFI | 2018-04-16 | 2018-06-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137312 | T16182-XH01-P0SGE-137312 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR FIRE WATER PUMP HOUSE | IFI | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136812 | T16182-XH01-P0SGE-136812 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR GTG #1,2 LEB | IFI | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136912 | T16182-XH01-P0SGE-136912 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR GTG #3,4,5 LEB | IFI | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138612 | T16182-XH01-P0SGE-138612 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR ST BUILDING | IFI | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137913 | T16182-XH01-P0SGE-137913 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139512 | T16182-XH01-P0SGE-139512 | PIPE LAYOUT AND DETAIL OF SPRINKLER SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFI | 2018-07-01 | 2018-09-29 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139011 | T16182-XH01-P0SGA-139011 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137711 | T16182-XH01-P0SGA-137711 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR AIR COMPRESSOR SHELTER | IFI | 2018-01-01 | 2018-04-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136711 | T16182-XH01-P0SGA-136711 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139611 | T16182-XH01-P0SGA-139611 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR CPP BUILDING | IFI | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138911 | T16182-XH01-P0SGA-138911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2017-09-04 | 2017-11-03 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139411 | T16182-XH01-P0SGA-139411 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR FIRE BRIGADE BUILDING | IFI | 2018-05-03 | 2018-08-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137311 | T16182-XH01-P0SGA-137311 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR FIRE WATER PUMP HOUSE | IFI | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136811 | T16182-XH01-P0SGA-136811 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR GTG #1,2 LEB | IFI | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136911 | T16182-XH01-P0SGA-136911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR GTG #3,4,5 LEB | IFI | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139111 | T16182-XH01-P0SGA-139111 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR SECURITY BUILDING | IFI | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138611 | T16182-XH01-P0SGA-138611 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR ST BUILDING | IFI | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137911 | T16182-XH01-P0SGA-137911 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139511 | T16182-XH01-P0SGA-139511 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFI | 2018-07-01 | 2018-09-29 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137811 | T16182-XH01-P0SGA-137811 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-11-22 | 2018-02-20 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139311 | T16182-XH01-P0SGA-139311 | PIPE LAYOUT AND DETAIL OF STAND PIPE SYSTEM FOR X-RAY SEARCHING ROOM | IFI | 2018-10-17 | 2019-01-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138411 | T16182-XH01-P0SGA-138411 | Pipe layout and detail of Standpipe system for H2, CO2 Gas Storage Shelter | IFI | 2017-08-03 | 2017-10-30 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138011 | T16182-XH01-P0SGA-138011 | PIPE LAYOUT AND DETAIL OF STANDPIPE SYSTEM FOR N2 GAS STORAGE SHELTER | IFI | 2017-09-04 | 2017-11-03 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138211 | T16182-XH01-P0SGC-138211 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BSDG DIESEL OIL DAY TANK | IFI | 2017-07-21 | 2017-10-19 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138111 | T16182-XH01-P0SGC-138111 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BURNER FOR HRSG | IFI | 2017-11-12 | 2018-02-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137411 | T16182-XH01-P0SGC-137411 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR BURNER FOR RESERVE BOILER | IFI | 2017-10-18 | 2018-01-16 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138912 | T16182-XH01-P0SGC-138912 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2018-11-19 | 2018-12-20 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138311 | T16182-XH01-P0SGC-138311 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GAS COMPRESSOR IN GPRS AREA | IFI | 2017-07-19 | 2017-10-17 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138616 | T16182-XH01-P0SGC-138616 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GENERATOR HYDROGEN SEAL OIL UNITS FOR ST BUILDING | IFI | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138614 | T16182-XH01-P0SGC-138614 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GENERATOR LUBE OIL UNIT FOR ST BUILDING | IFI | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137011 | T16182-XH01-P0SGC-137011 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG GSU TRANSFORMER | IFI | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138112 | T16182-XH01-P0SGC-138112 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG LUBE OIL UNIT | IFI | 2019-01-10 | 2019-02-08 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137111 | T16182-XH01-P0SGC-137111 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR GTG UNIT AUX. TRANSFORMER | IFI | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139911 | T16182-XH01-P0SGC-139911 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR STG EXCITATION TRANSFORMER | IFI | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137211 | T16182-XH01-P0SGC-137211 | PIPE LAYOUT AND DETAIL OF WATER SPRAY SYSTEM FOR STG GSU TRANSFORMER | IFI | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF
S&A(18) | Structural & Architectural | 185178 | T16182-CA03-P0UMY-185178 | PIPE RACK - MISC DETAIL | IFR | 2017-05-02 | 2017-07-02
S&A(18) | Structural & Architectural | 185190 | T16182-CA06-P0UMY-185190 | PIPE RACK #1 - CALCULATION | IFR | 2017-06-01 | 2017-08-01 |  | O
S&A(18) | Structural & Architectural | 185152 | T16182-CA03-P0UMY-185152 | PIPE RACK #1 - COLUMN LOCATION PLAN & BASE PLATE DETAIL | IFR | 2017-06-01 | 2017-08-01 |  | O
S&A(18) | Structural & Architectural | 185154 | T16182-CA03-P0UMY-185154 | PIPE RACK #1 - ELEVATION | IFR | 2017-06-01 | 2017-08-01 |  | O
S&A(18) | Structural & Architectural | 185155 | T16182-CA03-P0UMY-185155 | PIPE RACK #1 - FOUNDATION & PEDETAL DETAIL | IFR | 2017-06-01 | 2017-08-01 |  | O
S&A(18) | Structural & Architectural | 185151 | T16182-CA03-P0UMY-185151 | PIPE RACK #1 - FOUNDATION PLAN | IFR | 2017-06-01 | 2017-08-01 |  | O
S&A(18) | Structural & Architectural | 185153 | T16182-CA03-P0UMY-185153 | PIPE RACK #1 - FRAMING PLAN | IFR | 2017-06-01 | 2017-08-01 |  | O
S&A(18) | Structural & Architectural | 185168 | T16182-CA03-P0UMY-185168 | PIPE RACK #2 - BASE PLATE DETAIL | IFR | 2017-05-02 | 2017-07-02
S&A(18) | Structural & Architectural | 185191 | T16182-CA06-P0UMY-185191 | PIPE RACK #2 - CALCULATION | IFR | 2017-05-02 | 2017-07-02
S&A(18) | Structural & Architectural | 185161 | T16182-CA03-P0UMY-185161 | PIPE RACK #2 - COLUMN LOCATION PLAN | IFR | 2017-05-02 | 2017-07-02
S&A(18) | Structural & Architectural | 185166 | T16182-CA03-P0UMY-185166 | PIPE RACK #2 - FOUNDATION DETAIL | IFR | 2017-05-02 | 2017-07-02
S&A(18) | Structural & Architectural | 185160 | T16182-CA03-P0UMY-185160 | PIPE RACK #2 - FOUNDATION PLAN | IFR | 2017-05-02 | 2017-07-02
S&A(18) | Structural & Architectural | 185162 | T16182-CA03-P0UMY-185162 | PIPE RACK #2 - FRAMING PLAN - 1 | IFR | 2017-05-02 | 2017-07-02
S&A(18) | Structural & Architectural | 185163 | T16182-CA03-P0UMY-185163 | PIPE RACK #2 - FRAMING PLAN - 2 | IFR | 2017-05-02 | 2017-07-02
S&A(18) | Structural & Architectural | 185164 | T16182-CA03-P0UMY-185164 | PIPE RACK #2 - LINE ELEVATION | IFR | 2017-05-02 | 2017-07-02
S&A(18) | Structural & Architectural | 185167 | T16182-CA03-P0UMY-185167 | PIPE RACK #2 - PEDETAL DETAIL | IFR | 2017-05-02 | 2017-07-02
S&A(18) | Structural & Architectural | 185165 | T16182-CA03-P0UMY-185165 | PIPE RACK #2 - ROW ELEVATION | IFR | 2017-05-02 | 2017-07-02
S&A(18) | Structural & Architectural | 185177 | T16182-CA03-P0UMY-185177 | PIPE RACK #3 - BASE PLATE DETAIL | IFR | 2017-08-25 | 2017-10-25
S&A(18) | Structural & Architectural | 185192 | T16182-CA06-P0UMY-185192 | PIPE RACK #3 - CALCULATION | IFR | 2017-08-25 | 2017-10-25
S&A(18) | Structural & Architectural | 185170 | T16182-CA03-P0UMY-185170 | PIPE RACK #3 - COLUMN LOCATION PLAN | IFR | 2017-08-25 | 2017-10-25
S&A(18) | Structural & Architectural | 185175 | T16182-CA03-P0UMY-185175 | PIPE RACK #3 - FOUNDATION DETAIL | IFR | 2017-08-25 | 2017-10-25
S&A(18) | Structural & Architectural | 185169 | T16182-CA03-P0UMY-185169 | PIPE RACK #3 - FOUNDATION PLAN | IFR | 2017-08-25 | 2017-10-25
S&A(18) | Structural & Architectural | 185171 | T16182-CA03-P0UMY-185171 | PIPE RACK #3 - FRAMING PLAN - 1 | IFR | 2017-08-25 | 2017-10-25
S&A(18) | Structural & Architectural | 185172 | T16182-CA03-P0UMY-185172 | PIPE RACK #3 - FRAMING PLAN - 2 | IFR | 2017-08-25 | 2017-10-25
S&A(18) | Structural & Architectural | 185173 | T16182-CA03-P0UMY-185173 | PIPE RACK #3 - LINE ELEVATION | IFR | 2017-08-25 | 2017-10-25
S&A(18) | Structural & Architectural | 185176 | T16182-CA03-P0UMY-185176 | PIPE RACK #3 - PEDETAL & TIE GIRDER DETAIL | IFR | 2017-08-25 | 2017-10-25
S&A(18) | Structural & Architectural | 185174 | T16182-CA03-P0UMY-185174 | PIPE RACK #3 - ROW SECTION | IFR | 2017-08-25 | 2017-10-25
CV(17) | Civil | 171403 | T16182-XB02-P0UNX-171403 | PIPE SLEEPER FOUNDATION LAYOUT | IFR | 2017-05-05 | 2017-07-04
CV(17) | Civil | 171402 | T16182-XB02-P0UNX-171402 | PIPE SLEEPER FOUNDATION OVERALL LAYOUT | IFR | 2017-05-05 | 2017-07-04 |  | O
CV(17) | Civil | 171410 | T16182-XB02-P0UNX-171410 | PIPE SLEEPER FOUNDATION PLAN AND SECTION | IFR | 2017-05-05 | 2017-07-04 |  | O
MCH(13) | Mechanical | 130303 | T16182-XG02-P0QC-130303 | PIPING & INSTRUMENT DIAGRAM FOR CHEMICAL DOSING SYSTEM | IFR | 2017-10-05 | 2018-01-17 |  |  |  | PKG-027-CDS
MCH(13) | Mechanical | 130204 | T16182-XG02-P0LD-130204 | PIPING & INSTRUMENT DIAGRAM FOR CONDENSATE POLISHING PLANT | IFR | 2017-06-03 | 2017-09-15 | O |  |  | PKG-026-CPP
MCH(13) | Mechanical | 130403 | T16182-XG02-P0QU-130403 | PIPING & INSTRUMENT DIAGRAM FOR SAMPLING SYSTEM | IFR | 2017-10-04 | 2018-01-16 |  |  |  | PKG-028-SP
MCH(13) | Mechanical | 130103 | T16182-XG02-P0GNR-130103 | PIPING & INSTRUMENT DIAGRAM FOR WASTE WATER TREATMENT PLANT | IFR | 2017-03-06 | 2017-06-18 | O | O |  | PKG-025-WT
MCH(13) | Mechanical | 130004 | T16182-XG02-P0GCF-130004 | PIPING & INSTRUMENT DIAGRAM FOR WATER TREATMENT PLANT | IFR | 2017-02-04 | 2017-05-19 | O | O |  | PKG-025-WT
PP(14) | Mechanical | 140063 | T16182-XH01-P0UTF-140063 | PIPING ARRANGEMENT DRAWING FOR AIR COMPRESSOR AREA | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140025 | T16182-XH01-P6UMA-140025 | PIPING ARRANGEMENT DRAWING FOR AIR COOLED CONDENSER #1 AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140026 | T16182-XH01-P7UMA-140026 | PIPING ARRANGEMENT DRAWING FOR AIR COOLED CONDENSER #2 & H2 CO2 N2 STORAGE SHELTER AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140054 | T16182-XH01-P0ULA-140054 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +0 | IFI | 2017-06-30
PP(14) | Mechanical | 140055 | T16182-XH01-P0ULA-140055 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +111,500 | IFI | 2017-06-30
PP(14) | Mechanical | 140056 | T16182-XH01-P0ULA-140056 | PIPING ARRANGEMENT DRAWING FOR BFP SHELTER AREA EL. +114,500 | IFI | 2017-06-30
PP(14) | Mechanical | 140068 | T16182-XH01-P0UCB-140068 | PIPING ARRANGEMENT DRAWING FOR CCB AREA | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140062 | T16182-XH01-P0ZEN-140062 | PIPING ARRANGEMENT DRAWING FOR CCW FIN FAN COOLER AREA | IFI | 2017-04-28 |  |  | O
MCH(13) | Mechanical | 130213 | T16182-XH01-P0LD-130213 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE POLISHING PLANT | IFI | 2017-09-15 | 2017-11-15 |  |  |  | PKG-026-CPP
PP(14) | Mechanical | 140083 | T16182-XH01-P0ZEN-140083 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK A & YARD AREA | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140070 | T16182-XH01-P0LCA-140070 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK A/B AREA | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140069 | T16182-XH01-P0LCA-140069 | PIPING ARRANGEMENT DRAWING FOR CONDENSATE TANK C AREA | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140071 | T16182-XH01-P0LDK-140071 | PIPING ARRANGEMENT DRAWING FOR CPP BLDG AREA 1 | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140072 | T16182-XH01-P0LDK-140072 | PIPING ARRANGEMENT DRAWING FOR CPP BLDG AREA 2 | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140057 | T16182-XH01-P0ULA-140057 | PIPING ARRANGEMENT DRAWING FOR DEAERATOR AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140065 | T16182-XH01-P0UGD-140065 | PIPING ARRANGEMENT DRAWING FOR DEMI & POTABLE WATER TANK AREA | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140081 | T16182-XH01-P0ZEN-140081 | PIPING ARRANGEMENT DRAWING FOR FGP TP AREA | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140078 | T16182-XH01-P0UYP-140078 | PIPING ARRANGEMENT DRAWING FOR FIRE BRIGATE AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140073 | T16182-XH01-P0EKG-140073 | PIPING ARRANGEMENT DRAWING FOR GPRS AREA | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140049 | T16182-XH01-P1MBA-140049 | PIPING ARRANGEMENT DRAWING FOR GT #1 AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140050 | T16182-XH01-P2MBA-140050 | PIPING ARRANGEMENT DRAWING FOR GT #2 AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140051 | T16182-XH01-P3MBA-140051 | PIPING ARRANGEMENT DRAWING FOR GT #3 AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140052 | T16182-XH01-P4MBA-140052 | PIPING ARRANGEMENT DRAWING FOR GT #4 AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140053 | T16182-XH01-P5MBA-140053 | PIPING ARRANGEMENT DRAWING FOR GT #5 AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140032 | T16182-XH01-P1UHA-140032 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +0 | IFI | 2017-06-30
PP(14) | Mechanical | 140034 | T16182-XH01-P1UHA-140034 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +106,000 | IFI | 2017-06-30
PP(14) | Mechanical | 140036 | T16182-XH01-P1UHA-140036 | PIPING ARRANGEMENT DRAWING FOR HRSG #1 AREA EL +108,000 & ABOVE | IFI | 2017-06-30
PP(14) | Mechanical | 140037 | T16182-XH01-P2UHA-140037 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +0 | IFI | 2017-06-30
PP(14) | Mechanical | 140038 | T16182-XH01-P2UHA-140038 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +106,000 | IFI | 2017-06-30
PP(14) | Mechanical | 140039 | T16182-XH01-P2UHA-140039 | PIPING ARRANGEMENT DRAWING FOR HRSG #2 AREA EL +108,000 & ABOVE | IFI | 2017-06-30
PP(14) | Mechanical | 140040 | T16182-XH01-P3UHA-140040 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +0 | IFI | 2017-06-30
PP(14) | Mechanical | 140041 | T16182-XH01-P3UHA-140041 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +106,000 | IFI | 2017-06-30
PP(14) | Mechanical | 140042 | T16182-XH01-P3UHA-140042 | PIPING ARRANGEMENT DRAWING FOR HRSG #3 AREA EL +108,000 & ABOVE | IFI | 2017-06-30
PP(14) | Mechanical | 140043 | T16182-XH01-P4UHA-140043 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +0 | IFI | 2017-06-30
PP(14) | Mechanical | 140044 | T16182-XH01-P4UHA-140044 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +106,000 | IFI | 2017-06-30
PP(14) | Mechanical | 140045 | T16182-XH01-P4UHA-140045 | PIPING ARRANGEMENT DRAWING FOR HRSG #4 AREA EL +108,000 & ABOVE | IFI | 2017-06-30
PP(14) | Mechanical | 140046 | T16182-XH01-P5UHA-140046 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +0 | IFI | 2017-06-30
PP(14) | Mechanical | 140047 | T16182-XH01-P5UHA-140047 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +106,000 | IFI | 2017-06-30
PP(14) | Mechanical | 140048 | T16182-XH01-P5UHA-140048 | PIPING ARRANGEMENT DRAWING FOR HRSG #5 AREA EL +108,000 & ABOVE | IFI | 2017-06-30
PP(14) | Mechanical | 140076 | T16182-XH01-P0UYC-140076 | PIPING ARRANGEMENT DRAWING FOR MAIN ADMIN BUILDING AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140074 | T16182-XH01-P0UYE-140074 | PIPING ARRANGEMENT DRAWING FOR MAIN GATE HOUSE AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140058 | T16182-XH01-P0ULY-140058 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 1 | IFI | 2017-06-30
PP(14) | Mechanical | 140059 | T16182-XH01-P0ULY-140059 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 2 | IFI | 2017-06-30
PP(14) | Mechanical | 140060 | T16182-XH01-P0ULY-140060 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 3 | IFI | 2017-06-30
PP(14) | Mechanical | 140061 | T16182-XH01-P0ULY-140061 | PIPING ARRANGEMENT DRAWING FOR MAIN PIPE RACK AREA 4 | IFI | 2017-06-30
PP(14) | Mechanical | 140077 | T16182-XH01-P0UST-140077 | PIPING ARRANGEMENT DRAWING FOR MAINTENANCE & WORKSHOP BUILDING AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140066 | T16182-XH01-P0UGA-140066 | PIPING ARRANGEMENT DRAWING FOR POTABLE & FIRE WATER TANK A/B AREA | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140067 | T16182-XH01-P0UGA-140067 | PIPING ARRANGEMENT DRAWING FOR POTABLE & FIRE WATER TANK C AREA | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140075 | T16182-XH01-P0UYF-140075 | PIPING ARRANGEMENT DRAWING FOR SECURITY BUILDING AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140021 | T16182-XH01-P6UMA-140021 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #1 GROUND FLOOR | IFI | 2017-06-30
PP(14) | Mechanical | 140022 | T16182-XH01-P6UMA-140022 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #1 OPERATING FLOOR | IFI | 2017-06-30
PP(14) | Mechanical | 140023 | T16182-XH01-P7UMA-140023 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #2 GROUND FLOOR | IFI | 2017-06-30
PP(14) | Mechanical | 140024 | T16182-XH01-P7UMA-140024 | PIPING ARRANGEMENT DRAWING FOR ST BLDG #2 OPERATING FLOOR | IFI | 2017-06-30
PP(14) | Mechanical | 140027 | T16182-XH01-P0ULY-140027 | PIPING ARRANGEMENT DRAWING FOR ST BLDG PIPE RACK AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140080 | T16182-XH01-P6UBA-140080 | PIPING ARRANGEMENT DRAWING FOR STG ELECTRICAL BUILDING #1 & SWAS CONTAINER AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140079 | T16182-XH01-P7UBA-140079 | PIPING ARRANGEMENT DRAWING FOR STG ELECTRICAL BUILDING #2 AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140031 | T16182-XH01-P0ZEN-140031 | PIPING ARRANGEMENT DRAWING FOR TO ESF AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140030 | T16182-XH01-P0ULY-140030 | PIPING ARRANGEMENT DRAWING FOR TO MAIN FCP GATE HOUSE AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140028 | T16182-XH01-P0ULY-140028 | PIPING ARRANGEMENT DRAWING FOR TO ST BLDG #1 MAIN PIPE RACK AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140029 | T16182-XH01-P0ULY-140029 | PIPING ARRANGEMENT DRAWING FOR TO ST BLDG #2 MAIN PIPE RACK AREA | IFI | 2017-06-30
PP(14) | Mechanical | 140064 | T16182-XH01-P0GRK-140064 | PIPING ARRANGEMENT DRAWING FOR WATER TREATMENT BLDG AREA | IFI | 2017-04-28 |  |  | O
MCH(13) | Mechanical | 130013 | T16182-XH01-P0GCF-130013 | PIPING ARRANGEMENT DRAWING FOR WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-07-28 |  | O |  | PKG-025-WT
PP(14) | Mechanical | 140082 | T16182-XH01-P0ZEN-140082 | PIPING ARRANGEMENT DRAWING FOR YARD AREA TO FGP TP | IFI | 2017-04-28 |  |  | O
PP(14) | Mechanical | 140002 | T16182-CV03-P0ZEN-140002 | PIPING INSULATION SPECIFICATION | IFI | 2017-01-25 |  |  | O
PP(14) | Mechanical | 140005 | T16182-XL00-P0ZEN-140005 | PIPING LINE LIST | IFI | 2017-06-16 |  |  | O
MCH(13) | Mechanical | 130055 | T16182-CV03-P0GCF-130055 | PIPING MATERIAL CLASSIFICATION FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-04-05 |  |  | O |  | PKG-025-WT
PP(14) | Mechanical | 140001 | T16182-CV03-P0ZEN-140001 | PIPING MATERIAL SPECIFICATION | IFI | 2017-01-25 |  |  | O
MCH(13) | Mechanical | 130219 | T16182-CV03-P0LD-130219 | PIPING MATERIAL SPECIFICATION FOR CONDENSATE POLISHING PLANT | IFI | 2017-12-08 |  |  |  |  | PKG-026-CPP
MCH(13) | Mechanical | 136621 | T16182-CV03-P0SG-136621 | PIPING MATERIAL SPECIFICATION FOR FIRE FIGHTING SYSTEM | IFI | 2017-06-23 |  |  |  |  | PKG-030-FF
PP(14) | Mechanical | 140004 | T16182-XL00-P0ZEN-140004 | PIPING SPECIALTY LIST | IFI | 2017-05-16 |  |  | O
PP(14) | Mechanical | 140408 | T16182-XH01-P0LF-140408 | PIPING SUPPORT DETAIL DRAWING FOR CLOSED COOLING WATER SYSTEM | IFI | 2017-11-17 | 2017-12-15
PP(14) | Mechanical | 140406 | T16182-XH01-P0LF-140406 | PIPING SUPPORT DETAIL DRAWING FOR CONDENSATE SYSTEM | IFI | 2017-11-17 | 2017-12-15
PP(14) | Mechanical | 140412 | T16182-XH01-P0LF-140412 | PIPING SUPPORT DETAIL DRAWING FOR DEMI. WATER SYSTEM | IFI | 2017-11-17 | 2017-12-15
PP(14) | Mechanical | 140407 | T16182-XH01-P0LF-140407 | PIPING SUPPORT DETAIL DRAWING FOR FEEDWATER SYSTEM | IFI | 2017-11-17 | 2017-12-15
PP(14) | Mechanical | 140417 | T16182-XH01-P0LF-140417 | PIPING SUPPORT DETAIL DRAWING FOR FUEL GAS SYSTEM | IFI | 2017-11-17 | 2017-12-15
PP(14) | Mechanical | 140416 | T16182-XH01-P0LF-140416 | PIPING SUPPORT DETAIL DRAWING FOR GT PERFORMANCE HEATER SYSTEM | IFI | 2017-12-21 | 2018-02-02
PP(14) | Mechanical | 140415 | T16182-XH01-P0LF-140415 | PIPING SUPPORT DETAIL DRAWING FOR GT ROTOR COOLING AIR COOLING SYSTEM | IFI | 2017-12-21 | 2018-02-02
PP(14) | Mechanical | 140401 | T16182-XH01-P0LF-140401 | PIPING SUPPORT DETAIL DRAWING FOR HP STEAM SYSTEM | IFI | 2018-01-12 | 2018-02-06
PP(14) | Mechanical | 140402 | T16182-XH01-P0LF-140402 | PIPING SUPPORT DETAIL DRAWING FOR IP STEAM SYSTEM | IFI | 2018-01-12 | 2018-02-06
PP(14) | Mechanical | 140403 | T16182-XH01-P0LF-140403 | PIPING SUPPORT DETAIL DRAWING FOR LP STEAM SYSTEM | IFI | 2018-01-12 | 2018-02-06
PP(14) | Mechanical | 140411 | T16182-XH01-P0LF-140411 | PIPING SUPPORT DETAIL DRAWING FOR POTABLE WATER SYSTEM | IFI | 2017-11-17 | 2017-12-15
PP(14) | Mechanical | 140404 | T16182-XH01-P0LF-140404 | PIPING SUPPORT DETAIL DRAWING FOR PROCESS STEAM SYSTEM | IFI | 2017-10-20 | 2017-11-10
PP(14) | Mechanical | 140410 | T16182-XH01-P0LF-140410 | PIPING SUPPORT DETAIL DRAWING FOR SERVICE AIR SYSTEM | IFI | 2018-11-30 | 2018-12-21
PP(14) | Mechanical | 140418 | T16182-XH01-P0LF-140418 | PIPING SUPPORT DETAIL DRAWING FOR STEAM BLOWING | IFI | 2018-09-14 | 2018-10-12
PP(14) | Mechanical | 140405 | T16182-XH01-P0LF-140405 | PIPING SUPPORT DETAIL DRAWING FOR STEAM DRAIN SYSTEM | IFI | 2018-01-12 | 2018-02-02
PP(14) | Mechanical | 140422 | T16182-XH01-P0LF-140422 | PIPING SUPPORT DETAIL DRAWING FOR TG MISCELLANEOUS SYSTEM | IFI | 2018-07-27 | 2018-08-20
PP(14) | Mechanical | 140419 | T16182-XH01-P0LF-140419 | PIPING SUPPORT DETAIL DRAWING FOR TREATED EFFLUENT COLLECTION AND TRANSFER SYSTEM | IFI | 2017-11-17 | 2017-12-15
PP(14) | Mechanical | 140421 | T16182-XH01-P0LF-140421 | PIPING SUPPORT DETAIL DRAWING FOR WASTE WATER SYSTEM | IFI | 2018-07-27 | 2018-08-20
PP(14) | Mechanical | 140420 | T16182-XH01-P0LF-140420 | PIPING SUPPORT TYPICAL DRAWING FOR SB PIPING ESOD AREA | IFI | 2018-02-16 | 2018-03-23
PP(14) | Mechanical | 140423 | T16182-XH01-P0LF-140423 | PIPING SUPPORT TYPICAL DRAWING FOR SB PIPING NON ESOD AREA | IFI | 2018-08-31 | 2018-09-24
PP(14) | Mechanical | 140006 | T16182-XL00-P0ZEN-140006 | PIPING TERMINAL POINT LIST BETWEEN FCHPP AND FGP | IFI | 2017-02-10 |  |  | O
I&C(16) | Instrumentation & Control | 161031 | T16182-YF02-P0ZEN-161031 | PLANT CONTROL SYSTEM CONFIGURATION DIAGRAM | IFR | 2016-12-30 | 2017-05-15 | O
|  | 810030 | T16182-DN05-P8ZEN-810030 | PLANT EMERGENCY FUEL CHANGE-OVER TEST
GA(10) | General | 100006 | T16182-UE00-P0MB-100006 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA (SECTION A - A) | IFR | 2016-10-30 | 2017-05-04 |  | O | O
GA(10) | General | 100007 | T16182-UE00-P0MB-100007 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA (SECTION B - B) | IFR | 2016-10-30 | 2017-05-04 |  | O | O
GA(10) | General | 100004 | T16182-UE00-P0MB-100004 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA UNIT 1&2 (PLAN VIEW) | IFR | 2016-10-30 | 2017-05-04 | O | O | O
GA(10) | General | 100005 | T16182-UE00-P0MB-100005 | PLANT GENERAL ARRANGEMENT FOR GTG & HRSG AREA UNIT 3&4&5 (PLAN VIEW) | IFR | 2016-10-30 | 2017-05-04 | O | O | O
GA(10) | General | 100008 | T16182-UE00-P0UMA-100008 | PLANT GENERAL ARRANGEMENT FOR STG AREA (PLAN VIEW) | IFR | 2016-10-30 | 2017-05-04 | O | O | O
GA(10) | General | 100009 | T16182-UE00-P0UMA-100009 | PLANT GENERAL ARRANGEMENT FOR STG AREA (SECTION A - A) | IFR | 2016-10-30 | 2017-05-04 |  | O | O
GA(10) | General | 100010 | T16182-UE00-P0UMA-100010 | PLANT GENERAL ARRANGEMENT FOR STG AREA (SECTION B - B) | IFR | 2016-10-30 | 2017-05-04 |  | O | O
PT(12) | Mechanical | 129002 | T16182-YT01-P0GHC-129002 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-04-28 |  |  | O |  | PKG-024-BOPP
PT(12) | Mechanical | 129001 | T16182-YD00-P0GHC-129001 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - GENERAL ARRANGEMENT DRAWING | IFI | 2017-04-28 | 2017-09-25 |  | O |  | PKG-024-BOPP
PT(12) | Instrumentation & Control | 129011 | T16182-YL00-P0GHC-129011 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - INSTRUMENT LIST AND DATA SHEET | IFI | 2017-05-19 |  |  | O |  | PKG-024-BOPP
PT(12) | Instrumentation & Control | 129013 | T16182-YK00-P0GHC-129013 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-06-30 |  |  | O |  | PKG-024-BOPP
PT(12) | Mechanical | 129004 | T16182-YT01-P0GHC-129004 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - MECHANICAL SEAL SPECIFICATION | IFI | 2017-05-31 |  |  | O |  | PKG-024-BOPP
PT(12) | Electrical | 129008 | T16182-YM01-P0GHC-129008 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - MOTOR DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-05-19 |  |  | O |  | PKG-024-BOPP
PT(12) | Mechanical | 129014 | T16182-YL22-P0GHC-129014 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - NAME PLATE DRAWING | IFI | 2017-06-30 |  |  | O |  | PKG-024-BOPP
PT(12) | Mechanical | 129003 | T16182-YK09-P0GHC-129003 | PLANT INTERNAL WATER DISTRIBUTION (3 PUMPS) - PUMP SECTIONAL DRAWING | IFI | 2017-04-30 | 2017-09-27 |  | O |  | PKG-024-BOPP
I&C(16) | Instrumentation & Control | 161041 | T16182-YF00-P0CJA-161041 | PLANT MASTER CONTROL DIAGRAM | IFR | 2017-05-30 | 2017-09-27 | O | O
I&C(16) | Instrumentation & Control | 161051 | T16182-YF01-P0BYA-161051 | PLANT PROTECTION & INTERLOCK DIAGRAM | IFR | 2017-05-15 | 2017-09-13 |  | O
I&C(16) | Instrumentation & Control | 161021 | T16182-YF00-P0CJD-161021 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM – SYMBOL & LEGEND | IFR | 2017-05-30 | 2017-09-27 |  | O
I&C(16) | Instrumentation & Control | 161025 | T16182-YF00-P0CJD-161025 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM FOR SHUTDOWN | IFR | 2017-05-30 | 2017-09-27 |  | O
I&C(16) | Instrumentation & Control | 161022 | T16182-YF00-P0CJD-161022 | PLANT START - UP & SHUTDOWN SEQUENCE DIAGRAM FOR START - UP | IFR | 2017-05-30 | 2017-09-27 |  | O
PS(11) | General | 110702 | T16182-CN00-P0ZEN-110702 | PLANT START-UP AND SHUT-DOWN PROCEDURE | IFR | 2017-04-15 | 2017-07-03
MCH(13) | Instrumentation & Control | 130035 | T16182-YL01-P0GCF-130035 | PLC IO LIST FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-04-05 |  |  | O |  | PKG-025-WT
MCH(13) | Mechanical | 139031 | T16182-YD00-P0SGZ-139031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ADMINISTRATION & SOCIAL BUILDING | IFI | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137731 | T16182-YD00-P0SGZ-137731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR AIR COMPRESSOR SHELTER | IFI | 2018-01-01 | 2018-04-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138531 | T16182-YD00-P0SGZ-138531 | PORTABLE EXTINGUISHER ARRANGEMENT FOR AUX. LEB | IFI | 2017-11-30 | 2018-01-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138231 | T16182-YD00-P0SGZ-138231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR BSDG DIESEL OIL DAY TANK | IFI | 2017-07-21 | 2017-09-19 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 136731 | T16182-YD00-P0SGZ-136731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CENTRAL CONTROL BUILDING | IFI | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139831 | T16182-YD00-P0SGZ-139831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CHEMICAL DOSING SHELTER FOR HRSG | IFI | 2018-03-17 | 2018-06-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139731 | T16182-YD00-P0SGZ-139731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | IFI | 2018-03-17 | 2018-06-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139631 | T16182-YD00-P0SGZ-139631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR CPP BUILDING | IFI | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138931 | T16182-YD00-P0SGZ-138931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR DEAERATOR SUPPORT STRUCTURE | IFI | 2017-09-04 | 2017-11-03 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137631 | T16182-YD00-P0SGZ-137631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FGS ELECTRICAL BUILDING | IFI | 2017-11-12 | 2018-02-10 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139431 | T16182-YD00-P0SGZ-139431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FIRE BRIGADE BUILDING | IFI | 2018-05-03 | 2018-08-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137332 | T16182-YD00-P0SGZ-137332 | PORTABLE EXTINGUISHER ARRANGEMENT FOR FIRE WATER PUMP HOUSE | IFI | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 138331 | T16182-YD00-P0SGZ-138331 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GPRS AREA | IFI | 2017-07-19 | 2017-09-17 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 136831 | T16182-YD00-P0SGZ-136831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG #1,2 LEB | IFI | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 136931 | T16182-YD00-P0SGZ-136931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG #3,4,5 LEB | IFI | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137031 | T16182-YD00-P0SGZ-137031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG GSU TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137131 | T16182-YD00-P0SGZ-137131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR GTG UNIT AUX. TRANSFORMER | IFI | 2017-05-03 | 2017-08-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138431 | T16182-YD00-P0SGZ-138431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR H2, CO2 GAS STORAGE SHELTER | IFI | 2017-09-04 | 2017-11-03 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138131 | T16182-YD00-P0SGZ-138131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR HRSG | IFR | 2017-11-12 | 2018-02-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139231 | T16182-YD00-P0SGZ-139231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR MAIN GATE HOUSE | IFI | 2018-05-03 | 2018-08-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138031 | T16182-YD00-P0SGZ-138031 | PORTABLE EXTINGUISHER ARRANGEMENT FOR N2 GAS STORAGE SHELTER | IFI | 2017-09-04 | 2017-11-03 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137431 | T16182-YD00-P0SGZ-137431 | PORTABLE EXTINGUISHER ARRANGEMENT FOR RESERVE BOILER | IFI | 2017-10-18 | 2018-01-16 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139131 | T16182-YD00-P0SGZ-139131 | PORTABLE EXTINGUISHER ARRANGEMENT FOR SECURITY BUILDING | IFI | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138631 | T16182-YD00-P0SGZ-138631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST BUILDING | IFI | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138731 | T16182-YD00-P0SGZ-138731 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST#1 LEB | IFI | 2017-12-15 | 2018-03-15 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 138831 | T16182-YD00-P0SGZ-138831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR ST#2 LEB | IFI | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 139931 | T16182-YD00-P0SGZ-139931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR STG EXCITATION TRANSFORMER | IFI | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137231 | T16182-YD00-P0SGZ-137231 | PORTABLE EXTINGUISHER ARRANGEMENT FOR STG GSU TRANSFORMER | IFI | 2017-09-03 | 2017-11-02 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 136631 | T16182-YD00-P0SGZ-136631 | PORTABLE EXTINGUISHER ARRANGEMENT FOR SUPPORT BUILDING | IFI | 2018-06-15 | 2018-09-13 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137931 | T16182-YD00-P0SGZ-137931 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139531 | T16182-YD00-P0SGZ-139531 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WORKSHOP & STORAGE BUILDING | IFI | 2018-07-01 | 2018-09-29 |  |  |  | PKG-030-FF
MCH(13) | Mechanical | 137831 | T16182-YD00-P0SGZ-137831 | PORTABLE EXTINGUISHER ARRANGEMENT FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFI | 2017-11-22 | 2018-02-20 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 139331 | T16182-YD00-P0SGZ-139331 | PORTABLE EXTINGUISHER ARRANGEMENT FOR X-RAY SEARCHING ROOM | IFI | 2018-10-17 | 2019-01-15 |  |  |  | PKG-030-FF
PT(12) | Mechanical | 128060 | T16182-YD00-P0SMS-128060 | PORTABLE GANTRY - GA DRAWING | IFI | 2020-01-10
CV(17) | Civil | 172522 | T16182-XB02-P0UGF-172522 | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION PLAN & SECTION | IFR | 2017-03-31 | 2017-05-31 |  | O
CV(17) | Civil | 172523 | T16182-VK02-P0UGF-172523 | POTABLE & FIRE FIGHTING WATER TANK FOUNDATION REBAR DETAIL | IFR | 2017-03-31 | 2017-05-31 |  | O
CV(17) | Civil | 173702 | T16182-XB02-P0GKC-173702 | POTABLE WATER CHILLER FOUNDATION DETAIL | IFR | 2017-11-24 | 2018-02-02
CV(17) | Civil | 172562 | T16182-XB02-P0UGG-172562 | POTABLE WATER TANK FOUNDATION PLAN & SECTION | IFR | 2017-03-31 | 2017-05-31 |  | O
CV(17) | Civil | 172563 | T16182-VK02-P0UGG-172563 | POTABLE WATER TANK FOUNDATION REBAR DETAIL | IFR | 2017-03-31 | 2017-05-31 |  | O
EL(15) | Electrical | 152850 | T16182-YL16-P0ZEN-152850 | POWER CABLE SCHEDULE | IFI | 2017-08-29 |  |  | O
CV(17) | Civil | 173902 | T16182-XB02-P0UZJ-173902 | POWER PLANT DIESEL GENERATOR FOUNDATION PLAN | IFR | 2019-05-10 | 2019-08-10
CV(17) | Civil | 173903 | T16182-VK02-P0UZJ-173903 | POWER PLANT DIESEL GENERATOR FOUNDATION REINF. DETAIL | IFR | 2019-05-10 | 2019-08-10
PS(11) | Mechanical | 110045 | T16182-XW03-P0LB-110045 | PRESSURE LOSS CALCULATIONS FOR MAIN STEAM SYSTEM | IFR | 2017-01-19 | 2017-06-11
EL(15) | Electrical | 150771 | T16182-YD00-P0BAA-150771 | PRESSURIZATION PANEL DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | IFI | 2017-06-30 |  |  |  |  | PKG-033-IPB
EL(15) | Electrical | 150772 | T16182-YD00-P0BAA-150772 | PRESSURIZATION PANEL DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | IFI | 2017-07-28 |  |  |  |  | PKG-033-IPB
|  | 860016 | T16182-DN05-P0ZEN-860016 | PRIMARY RESPONSE TEST
PS(11) | Mechanical | 110032 | T16182-XG07-P0PG-110032 | PROCESS FLOW DIAGRAM FOR CCW SYSTEM | IFR | 2016-10-28 | 2017-03-27
PT(12) | Mechanical | 120014 | T16182-XG07-P0SCA-120014 | PROCESS FLOW DIAGRAM FOR COMPRESSED AIR SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O
MCH(13) | Mechanical | 130203 | T16182-XG07-P0LD-130203 | PROCESS FLOW DIAGRAM FOR CONDENSATE POLISHING PLANT | IFR | 2017-06-03 | 2017-09-15 |  |  |  | PKG-026-CPP
PS(11) | Mechanical | 110033 | T16182-XG07-P0GHC-110033 | PROCESS FLOW DIAGRAM FOR DM WATER SYSTEM | IFR | 2016-10-28 | 2017-03-27
PT(12) | Mechanical | 120018 | T16182-XG07-P0EKG-120018 | PROCESS FLOW DIAGRAM FOR FUEL GAS SYSTEM | IFR | 2017-01-30 | 2017-04-30 | O | O |  | PKG-014-FGS
PS(11) | Mechanical | 110031 | T16182-XG07-P0LA-110031 | PROCESS FLOW DIAGRAM FOR STEAM/CONDENSATE/FW SYSTEM | IFR | 2016-10-28 | 2017-03-27
MCH(13) | Mechanical | 130102 | T16182-XG07-P0GNR-130102 | PROCESS FLOW DIAGRAM FOR WASTE WATER TREATMENT PLANT | IFR | 2017-03-06 | 2017-06-18 |  | O |  | PKG-025-WT
MCH(13) | Mechanical | 130003 | T16182-XG07-P0GCF-130003 | PROCESS FLOW DIAGRAM FOR WATER TREATMENT PLANT | IFR | 2017-02-04 | 2017-05-19 |  | O |  | PKG-025-WT
EL(15) | Electrical | 150211 | T16182-YU02-P0ZEN-150211 | PROTECTION AND METERING SINGLE LINE DIAGRAM FOR GTG UNIT | IFR | 2017-01-31 | 2017-06-27 |  | O
EL(15) | Electrical | 150212 | T16182-YU02-P0ZEN-150212 | PROTECTION AND METERING SINGLE LINE DIAGRAM FOR STG UNIT | IFR | 2017-01-31 | 2017-06-27
EL(15) | Electrical | 150314 | T16182-YT10-P0ZEN-150314 | PROTECTION RELAY COORDINATION STUDY - GSUT / OVERALL PROTECTION FOR STG UNIT | IFR | 2017-08-30 | 2018-02-14
EL(15) | Electrical | 150311 | T16182-YT10-P0ZEN-150311 | PROTECTION RELAY COORDINATION STUDY - GSUT / UAT / OVERALL PROTECTION FOR GTG UNIT | IFR | 2017-08-30 | 2018-02-14 |  | O
EL(15) | Electrical | 150313 | T16182-YT10-P0ZEN-150313 | PROTECTION RELAY COORDINATION STUDY - LV SWITCHGEAR | IFR | 2017-08-30 | 2018-02-14 |  | O |  | PKG-035-LVSWGR
EL(15) | Electrical | 150312 | T16182-YT10-P0ZEN-150312 | PROTECTION RELAY COORDINATION STUDY - MV SWITCHGEAR | IFR | 2017-08-30 | 2018-02-14 |  | O |  | PKG-034-MVSWGR
GN-I&C(29) | Instrumentation & Control | 290010 | T16182-YT10-P0MKY-290010 | PROTECTION RELAY SETTING DATA AND CALCULATION FOR STG | IFR | 2017-08-14 | 2017-09-30 |  |  |  | PKG-040-STG
GN-I&C(29) | Instrumentation & Control | 290003 | T16182-BV02-P0CJN-290003 | PSS STUDY REPORT FOR ST | IFR | 2018-01-26 | 2018-09-30 |  |  |  | PKG-040-STG
|  | 860018 | T16182-DN05-P0ZEN-860018 | PSS TEST
|  | 860028 | T16182-DN05-P0ZEN-860028 | PSS TEST OF STG
CV(17) | Civil | 173505 | T16182-VK02-P0UZK-173505 | PUMP ROOM PLAN AND DETAIL | IFR | 2019-06-01 | 2019-09-01
EL(15) | Electrical | 152791 | T16182-YE00-P0ZEN-152791 | RACEWAY DRAWING FOR HCIS – MAIN GATE HOUSE | IFI | 2018-06-30 | 2018-09-28
EL(15) | Electrical | 152792 | T16182-YE00-P0ZEN-152792 | RACEWAY DRAWING FOR HCIS – PLANT ACCESS GATE HOUSE | IFI | 2018-07-13 | 2018-10-12
EL(15) | Electrical | 152795 | T16182-YE00-P0ZEN-152795 | RACEWAY DRAWING FOR HCIS – PRELIMINARY INSPECTION CHECKPOINT | IFI | 2018-07-13 | 2018-10-12
EL(15) | Electrical | 152793 | T16182-YE00-P0ZEN-152793 | RACEWAY DRAWING FOR HCIS – SEARCH FACILITY & VISITOR CENTRE | IFI | 2018-06-30 | 2018-09-28
EL(15) | Electrical | 152794 | T16182-YE00-P0ZEN-152794 | RACEWAY DRAWING FOR HCIS – SUPPORT BUILDING | IFI | 2018-07-13 | 2018-10-12
|  | 860015 | T16182-DN05-P0ZEN-860015 | REACTIVE POWER TEST
|  | 860027 | T16182-DN05-P0ZEN-860027 | REACTIVE POWER TEST OF STG
EL(15) | Electrical | 155014 | T16182-YT10-P0ASR-155014 | RELAY SETTING CALCULATION FOR 13.8kV CABLE PROTECTION – COGEN TO ESF | IFR | 2018-12-21 | 2019-01-25
EL(15) | Electrical | 155012 | T16182-YT10-P0ASR-155012 | RELAY SETTING CALCULATION FOR GTG #3, 4, 5 CABLE PROTECTION | IFR | 2018-11-27
EL(15) | Electrical | 155011 | T16182-YT10-P0ASR-155011 | RELAY SETTING CALCULATION FOR GTG1 & GTG2 CABLE PROTECTION | IFR | 2018-07-25 | 2018-08-31
EL(15) | Electrical | 155013 | T16182-YT10-P0ASR-155013 | RELAY SETTING CALCULATION FOR STG #1, 2 CABLE PROTECTION | IFR | 2019-03-11 | 2019-04-04
EL(15) | Electrical | 155001 | T16182-YT01-P0ASS-155001 | RELAY SETTING CALCULATION OF 380kV SYNCHRONIZING SYSTEM | IFI | 2018-07-20
|  | 860013 | T16182-DN05-P0ZEN-860013 | RELIABILITY TEST
CV(17) | Civil | 170105 | T16182-BF05-P0ZEN-170105 | REPORT FOR PILE LOAD TEST OF BORED CAST - IN - PLACE PILE | IFI | 2016-10-24 |  |  | O
PT(12) | Mechanical | 125737 | T16182-DP00-P8ZEN-125737 | RESERVE BOILER _ VMS SPECIFICATION | IFI | 2017-10-13 |  |  |  |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125719 | T16182-YT02-P8ZEN-125719 | RESERVE BOILER - AIR OPERATED VALVE DOCUMENT & DRAWING | IFI | 2017-07-02 | 2017-12-07 |  | O |  | PKG-015-RB
PT(12) | Electrical | 125766 | T16182-DP00-P8ZEN-125766 | RESERVE BOILER - AIRCRAFT WARNING LIGHT DRAWING | IFI | 2017-07-02 | 2017-09-18 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125708 | T16182-YL00-P8ZEN-125708 | RESERVE BOILER - ALARM AND TRIP SETTING LIST | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB
PT(12) | Civil | 125153 | T16182-XT00-P8QHB-125153 | RESERVE BOILER - ANCHOR BOLT ARRANGEMENT DRAWING FOR STACK | IFI | 2017-03-10 | 2017-09-26 |  | O |  | PKG-015-RB
PT(12) | Civil | 125152 | T16182-XT00-P8QHB-125152 | RESERVE BOILER - ANCHOR BOLT ARRANGEMENT DRAWING FOR STEEL STRUCTURE | IFI | 2017-03-10 | 2017-09-26 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125172 | T16182-CC02-P8QHB-125172 | RESERVE BOILER - ARRANGEMENT DRAWING FOR STACK | IFI | 2017-05-12 | 2017-11-28 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125164 | T16182-CC02-P8QHB-125164 | RESERVE BOILER - ARRANGEMENT DRAWING FOR STEEL STRUCTURE | IFI | 2017-05-12 | 2017-11-28 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125704 | T16182-YL01-P8ZEN-125704 | RESERVE BOILER - BCS I/O LIST | IFI | 2017-06-02 | 2017-09-21 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125734 | T16182-DP00-P8ZEN-125734 | RESERVE BOILER - BCS SPECIFICATION | IFI | 2017-06-02 | 2017-10-23 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125604 | T16182-CV03-P8ZEN-125604 | RESERVE BOILER - BFP DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125611 | T16182-CV03-P8ZEN-125611 | RESERVE BOILER - BLOWDOWN TANK DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125703 | T16182-YL01-P8ZEN-125703 | RESERVE BOILER - BMS I/O LIST | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125711 | T16182-YF00-P8ZEN-125711 | RESERVE BOILER - BMS LOGIC DIAGRAM | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125702 | T16182-DP00-P8ZEN-125702 | RESERVE BOILER - BMS SPECIFICATION | IFR | 2017-06-02 | 2017-08-31 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125012 | T16182-XW03-P8ZEN-125012 | RESERVE BOILER - BOILER PREDICTED PERFORMANCE DATA & CURVE | IFR | 2017-05-12 | 2017-06-29 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125014 | T16182-XW03-P8ZEN-125014 | RESERVE BOILER - BOILER START - UP CURVE | IFR | 2017-03-03 | 2017-06-01 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125602 | T16182-CV03-P8ZEN-125602 | RESERVE BOILER - BURNER DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125727 | T16182-YT02-P8ZEN-125727 | RESERVE BOILER - CEMS DOCUMENT & DRAWING | IFR | 2017-06-02 | 2017-08-17 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125608 | T16182-CV03-P8ZEN-125608 | RESERVE BOILER - CHEMICAL DOSING SYSTEM DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB
PT(12) | Electrical | 125769 | T16182-YQ03-P8ZEN-125769 | RESERVE BOILER - COMMUNICATION SYSTEM DOCUMENT & DRAWING | IFI | 2017-07-28 | 2017-09-18 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125162 | T16182-CC05-P8QHB-125162 | RESERVE BOILER - CONNECTION DETAIL DRAWING FOR STEEL STRUCTURE | IFI | 2017-02-10 | 2017-08-29 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125709 | T16182-YF00-P8ZEN-125709 | RESERVE BOILER - CONTROL LOGIC DIAGRAM | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125710 | T16182-YF00-P8ZEN-125710 | RESERVE BOILER - CONTROL LOOP DIAGRAM | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125728 | T16182-YD00-P8ZEN-125728 | RESERVE BOILER - CONTROL ROOM & ELECTRICAL ROOM ARRANGEMENT DRAWING | IFI | 2017-07-02 | 2018-05-31 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125701 | T16182-YF02-P8ZEN-125701 | RESERVE BOILER - CONTROL SYSTEM CONFIGURATION | IFR | 2017-06-02 | 2017-09-02 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125514 | T16182-YL30-P8ZEN-125514 | RESERVE BOILER - CONTROL VALVE DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125401 | T16182-XA00-P8QHL-125401 | RESERVE BOILER - DAMPER DOCUMENT & DRAWING | IFI | 2017-03-24 | 2017-10-10 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125706 | T16182-YL01-P8ZEN-125706 | RESERVE BOILER - DATALINK I/O LIST | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125605 | T16182-CV03-P8ZEN-125605 | RESERVE BOILER - DEAERATOR WITH STORAGE TANK DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125161 | T16182-CC05-P8QHB-125161 | RESERVE BOILER - DESIGN CRITERIA FOR STEEL STRUCTURE | IFI | 2017-02-10 |  |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125202 | T16182-YK10-P8QHA-125202 | RESERVE BOILER - DESUPERHEATER DRAWING | IFI | 2017-04-28 | 2017-11-14 |  | O |  | PKG-015-RB
PT(12) | Electrical | 125767 | T16182-YE03-P8ZEN-125767 | RESERVE BOILER - EARTHING DOCUMENT & DRAWING | IFI | 2017-01-13 | 2017-07-11 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125207 | T16182-YK10-P8QHA-125207 | RESERVE BOILER - ECONOMIZER DRAWING | IFI | 2017-06-19 | 2018-01-20 |  | O |  | PKG-015-RB
PT(12) | Electrical | 125762 | T16182-YD02-P8ZEN-125762 | RESERVE BOILER - EMBEDDED CONDUIT LAYOUT DRAWING | IFI | 2017-02-10 | 2017-07-05 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125402 | T16182-XA00-P8QHL-125402 | RESERVE BOILER - EXPANSION JOINT DOCUMENT & DRAWING | IFI | 2017-03-24 | 2017-10-10 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125601 | T16182-CV03-P8ZEN-125601 | RESERVE BOILER - F.D FAN DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125723 | T16182-YT10-P8ZEN-125723 | RESERVE BOILER - FLOW ELEMENT CALIBRATION SHEET | IFI | 2017-12-22 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125717 | T16182-YT02-P8ZEN-125717 | RESERVE BOILER - FLOW ELEMENT SPECIFICATION | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB
PT(12) | Civil | 125619 | T16182-CC08-P8ZEN-125619 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR BLOW DOWN TANK | IFI | 2017-03-24 |  |  | O |  | PKG-015-RB
PT(12) | Civil | 125615 | T16182-CC08-P8ZEN-125615 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR BOILER FEED WATER PUMP | IFI | 2017-03-24 |  |  | O |  | PKG-015-RB
PT(12) | Civil | 125618 | T16182-CC08-P8ZEN-125618 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR CHEMICAL DOSING SYSTEM | IFI | 2017-03-24 |  |  | O |  | PKG-015-RB
PT(12) | Civil | 125620 | T16182-CC08-P8ZEN-125620 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR ELECTRICAL & CONTROL ROOM | IFI | 2017-05-12 |  |  | O |  | PKG-015-RB
PT(12) | Civil | 125614 | T16182-CC08-P8ZEN-125614 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR F.D FAN | IFI | 2017-03-24 |  |  | O |  | PKG-015-RB
PT(12) | Civil | 125616 | T16182-CC08-P8ZEN-125616 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR FUEL SKID | IFI | 2017-03-24 |  |  | O |  | PKG-015-RB
PT(12) | Civil | 125617 | T16182-CC08-P8ZEN-125617 | RESERVE BOILER - FOUNDATION DRAWING & LOADING DATA FOR SAMPLING SYSTEM | IFI | 2017-03-24 |  |  | O |  | PKG-015-RB
PT(12) | Civil | 125300 | T16182-CC08-P8QHA-125300 | RESERVE BOILER - FOUNDATION LOADING DATA FOR BOILER PROPER | IFI | 2017-01-13 |  |  | O |  | PKG-015-RB
PT(12) | Civil | 125151 | T16182-CC08-P8QHB-125151 | RESERVE BOILER - FOUNDATION LOADING DATA FOR STEEL STRUCTURE & STACK | IFI | 2017-01-13 |  |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125400 | T16182-XH02-P8QHL-125400 | RESERVE BOILER - GAS & AIR DUCT ARRANGEMENT DRAWING | IFI | 2017-04-28 | 2017-11-14 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125725 | T16182-YT02-P8ZEN-125725 | RESERVE BOILER - GAS LEAK DETECTION SYSTEM DOCUMENT & DRAWING | IFI | 2017-07-02 | 2017-09-27 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125101 | T16182-CC00-P8QHA-125101 | RESERVE BOILER - GENERAL ARRANGEMENT DRAWING | IFR | 2017-01-13 | 2017-04-13 | O | O |  | PKG-015-RB
PT(12) | Engineering Management | 125735 | T16182-YD00-P8ZEN-125735 | RESERVE BOILER - HAZARDOUS AREA CLASSFICATION | IFI | 2017-06-16 |  |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125571 | T16182-XG05-P8ZEN-125571 | RESERVE BOILER - HEAT & MASS BLANCE DIAGRAM | IFR | 2017-01-13 | 2017-04-13 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125732 | T16182-YB03-P8ZEN-125732 | RESERVE BOILER - I&C CABLE CONNECTION DIAGRAM | IFI | 2017-07-02 | 2019-04-09 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125731 | T16182-YL16-P8ZEN-125731 | RESERVE BOILER - I&C CABLE SCHEDULE | IFI | 2017-07-02 | 2018-04-23 |  | O |  | PKG-015-RB
PT(12) | Electrical | 125764 | T16182-YT10-P8ZEN-125764 | RESERVE BOILER - ILLUMINATION CALCULATION | IFI | 2017-07-28 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125720 | T16182-YK00-P8ZEN-125720 | RESERVE BOILER - INSTRUMENT INSTALLATION DETAIL DRAWING | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125707 | T16182-YL00-P8ZEN-125707 | RESERVE BOILER - INSTRUMENT LIST | IFI | 2017-06-02 | 2018-04-23 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125721 | T16182-YM03-P8ZEN-125721 | RESERVE BOILER - INSTRUMENT LOCATION DRAWING | IFI | 2017-07-02 | 2018-03-26 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125304 | T16182-UC02-P8QHA-125304 | RESERVE BOILER - INSULATION SPECIFICATION & DRAWING FOR BOILER PROPER | IFI | 2017-05-12 | 2017-11-28 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125403 | T16182-YK08-P8QHL-125403 | RESERVE BOILER - INSULATION SPECIFICATION & DRAWING FOR DUCT | IFI | 2017-03-24 | 2017-10-10 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125729 | T16182-XF00-P8ZEN-125729 | RESERVE BOILER - JUNCTION BOX DRAWING | IFI | 2017-07-02 | 2018-04-23 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125612 | T16182-CV03-P8ZEN-125612 | RESERVE BOILER - LEVEL GAUGE DOCUMENT & DRAWING | IFI | 2017-03-24 | 2018-03-12 |  | O |  | PKG-015-RB
PT(12) | Electrical | 125765 | T16182-YQ01-P8ZEN-125765 | RESERVE BOILER - LIGHTING LAYOUT DRAWING | IFI | 2017-07-28 | 2018-03-26 |  | O |  | PKG-015-RB
PT(12) | Electrical | 125768 | T16182-YE01-P8ZEN-125768 | RESERVE BOILER - LIGHTNING PROTECTION DOCUMENT & DRAWING | IFI | 2017-06-30 | 2018-03-26 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125503 | T16182-XN00-P8ZEN-125503 | RESERVE BOILER - LINE LIST | IFI | 2017-04-28 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125715 | T16182-YT02-P8ZEN-125715 | RESERVE BOILER - LOCAL GAUGE SPECIFICATION | IFI | 2017-07-02 | 2017-09-29 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125506 | T16182-DP00-P8ZEN-125506 | RESERVE BOILER - MANUAL VALVE DRAWING | IFI | 2017-06-09 | 2017-12-26 |  | O |  | PKG-015-RB
PT(12) | Electrical | 125756 | T16182-YU03-P8ZEN-125756 | RESERVE BOILER - MCC SCHEMATIC DIAGRAM | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB
PT(12) | Electrical | 125755 | T16182-YU02-P8ZEN-125755 | RESERVE BOILER - MCC SINGLE LINE DIAGRAM | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125724 | T16182-YF00-P8ZEN-125724 | RESERVE BOILER - MONITOR SCREEN DIAGRAM | IFI | 2017-06-16 |  |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125609 | T16182-CV03-P8ZEN-125609 | RESERVE BOILER - MONORAIL HOIST DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB
PT(12) | Electrical | 125749 | T16182-DP00-P8ZEN-125749 | RESERVE BOILER - MOTOR LIST | IFI | 2017-05-19 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125713 | T16182-YT02-P8ZEN-125713 | RESERVE BOILER - MOV DOCUMENT & DRAWING | IFI | 2017-07-02 | 2017-12-07 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125308 | T16182-YK10-P8QHA-125308 | RESERVE BOILER - NAME PLATE DRAWING OF BOILER PROPER | IFI | 2017-10-06 |  |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125310 | T16182-DP00-P8ZEN-125310 | RESERVE BOILER - NAME PLATE DRAWING OF VALVE | IFI | 2017-06-09 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125726 | T16182-YT02-P8ZEN-125726 | RESERVE BOILER - O2 ANALYZER DOCUMENT & DRAWING | IFI | 2017-07-02 | 2017-09-22 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125700 | T16182-XS01-P8ZEN-125700 | RESERVE BOILER - OPERATION PHILOSOPHY | IFR | 2017-06-02 | 2017-09-02 |  | O | O | PKG-015-RB
PT(12) | Mechanical | 125588 | T16182-XG02-P8ZEN-125588 | RESERVE BOILER - P&ID OF BLOWDOWN SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB
PT(12) | Mechanical | 125585 | T16182-XG02-P8ZEN-125585 | RESERVE BOILER - P&ID OF BOILER STEAM SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB
PT(12) | Mechanical | 125584 | T16182-XG02-P8ZEN-125584 | RESERVE BOILER - P&ID OF BOILER WATER SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB
PT(12) | Mechanical | 125587 | T16182-XG02-P8ZEN-125587 | RESERVE BOILER - P&ID OF BURNER & FUEL GAS SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB
PT(12) | Mechanical | 125590 | T16182-XG02-P8ZEN-125590 | RESERVE BOILER - P&ID OF CHEMICAL DOSING SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB
PT(12) | Mechanical | 125591 | T16182-XG02-P8ZEN-125591 | RESERVE BOILER - P&ID OF CLOSED COOLING WATER & SERVICE WATER SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB
PT(12) | Mechanical | 125586 | T16182-XG02-P8ZEN-125586 | RESERVE BOILER - P&ID OF COMBUSTION AIR & FLUE GAS SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB
PT(12) | Mechanical | 125582 | T16182-XG02-P8ZEN-125582 | RESERVE BOILER - P&ID OF DEAERATOR SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB
PT(12) | Mechanical | 125583 | T16182-XG02-P8ZEN-125583 | RESERVE BOILER - P&ID OF FEEDWATER PUMP SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB
PT(12) | Mechanical | 125592 | T16182-XG02-P8ZEN-125592 | RESERVE BOILER - P&ID OF INSTRUMENT AIR SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB
PT(12) | Mechanical | 125589 | T16182-XG02-P8ZEN-125589 | RESERVE BOILER - P&ID OF SAMPLING SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB
PT(12) | Mechanical | 125593 | T16182-XG02-P8ZEN-125593 | RESERVE BOILER - P&ID OF SERVICE AIR & SEALING AIR SYSTEM | IFR | 2017-01-13 | 2017-04-13 | O | O | O | PKG-015-RB
PT(12) | Mechanical | 125507 | T16182-YD00-P8ZEN-125507 | RESERVE BOILER - PIPING & PIPING SUPPORT PLAN DRAWING | IFI | 2017-08-25 | 2018-03-13 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125505 | T16182-XV00-P8ZEN-125505 | RESERVE BOILER - PIPING SPECIALITY DRAWING & LIST | IFI | 2017-06-09 | 2017-12-26 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125509 | T16182-XK00-P8ZEN-125509 | RESERVE BOILER - PIPING SUPPORT DETAIL DRAWING FOR SMALL BORE PIPING. | IFI | 2017-09-08 | 2018-03-27 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125502 | T16182-DE00-P8ZEN-125502 | RESERVE BOILER - PMS (PIPE MATERIAL SPECIFICATION) | IFI | 2017-04-28 |  |  | O |  | PKG-015-RB
PT(12) | Electrical | 125761 | T16182-YB03-P8ZEN-125761 | RESERVE BOILER - POWER CABLE CONNECTION DIAGRAM | IFI | 2017-07-02 | 2018-04-23 |  | O |  | PKG-015-RB
PT(12) | Electrical | 125760 | T16182-YL16-P8ZEN-125760 | RESERVE BOILER - POWER CABLE SCHEDULE | IFI | 2017-07-02 | 2018-04-23 |  | O |  | PKG-015-RB
PT(12) | Electrical | 125750 | T16182-YD00-P8ZEN-125750 | RESERVE BOILER - POWER DISTRIBUTION PANEL DRAWING | IFI | 2017-07-02 | 2018-04-23 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125201 | T16182-YD07-P8QHA-125201 | RESERVE BOILER - PRESSURE PART ARRANGEMENT OF BOILER DRAWING | IFI | 2017-03-24 | 2017-10-10 |  | O |  | PKG-015-RB
PT(12) | Electrical | 125752 | T16182-YE00-P8ZEN-125752 | RESERVE BOILER - RACEWAY DOCUMENT & DRAWING | IFI | 2017-06-16 |  |  | O |  | PKG-015-RB
PT(12) | Electrical | 125751 | T16182-YE00-P8ZEN-125751 | RESERVE BOILER - RACEWAY PLAN DRAWING | IFI | 2017-06-16 | 2018-03-26 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125303 | T16182-UC02-P8QHA-125303 | RESERVE BOILER - REFRACTORY LINING PROCEDURE FOR BOILER PROPER | IFI | 2017-05-12 | 2017-12-14 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125718 | T16182-YT02-P8ZEN-125718 | RESERVE BOILER - REMOTE DRUM LEVEL INDICATOR SPECIFICATION | IFI | 2017-07-02 | 2017-12-06 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125607 | T16182-CV03-P8ZEN-125607 | RESERVE BOILER - SAMPLING SYSTEM DOCUMENT & DRAWING | IFI | 2017-06-02 | 2017-12-19 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125606 | T16182-CV03-P8ZEN-125606 | RESERVE BOILER - SILENCER DOCUMENT & DRAWING | IFI | 2017-03-24 | 2017-10-10 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125610 | T16182-CV03-P8ZEN-125610 | RESERVE BOILER - SRV DOCUMENT & DRAWING | IFI | 2017-03-24 | 2017-10-10 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125001 | T16182-XV00-P8ZEN-125001 | RESERVE BOILER - SUPPLY/EQUIPMENT LIST | IFI | 2017-06-16 |  |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125002 | T16182-XS00-P8QHA-125002 | RESERVE BOILER - SYSTEM DESCRIPTION | IFR | 2017-05-19 | 2017-08-17 | O | O | O | PKG-015-RB
PT(12) | Electrical | 125757 | T16182-DP00-P8ZEN-125757 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR CABLE | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB
PT(12) | Electrical | 125758 | T16182-DP00-P8ZEN-125758 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR CABLING ACCESSORIES | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB
PT(12) | Electrical | 125759 | T16182-DP00-P8ZEN-125759 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR FIRE STOP MATERIALS | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB
PT(12) | Electrical | 125763 | T16182-DP00-P8ZEN-125763 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR LIGHTING SYSTEM | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB
PT(12) | Electrical | 125754 | T16182-DP00-P8ZEN-125754 | RESERVE BOILER - TECHNICAL SPECIFICATION FOR MCC | IFI | 2017-07-02 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125716 | T16182-YT02-P8ZEN-125716 | RESERVE BOILER - TEMP. ELEMENT SPECIFICATION | IFI | 2017-07-02 | 2017-09-29 |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125722 | T16182-YT10-P8ZEN-125722 | RESERVE BOILER - TRANSMITTER CALIBRATION SHEET | IFI | 2017-12-22 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125714 | T16182-YT02-P8ZEN-125714 | RESERVE BOILER - TRANSMITTER SPECIFICATION | IFI | 2017-07-02 | 2017-09-18 |  | O |  | PKG-015-RB
PT(12) | Mechanical | 125504 | T16182-XN00-P8ZEN-125504 | RESERVE BOILER - VALVE LIST | IFI | 2017-04-28 |  |  | O |  | PKG-015-RB
PT(12) | Instrumentation & Control | 125705 | T16182-YL01-P8ZEN-125705 | RESERVE BOILER - VMS I/O LIST | IFI | 2017-06-02 |  |  | O |  | PKG-015-RB
CV(17) | Civil | 172012 | T16182-XB02-P8UTH-172012 | RESERVE BOILER FD FAN FOUNDATION | IFR | 2017-04-01 | 2017-07-01 |  | O
CV(17) | Civil | 172003 | T16182-XB02-P8UTH-172003 | RESERVE BOILER FOUNDATION LAYOUT | IFR | 2017-02-28 | 2017-05-29 |  | O
CV(17) | Civil | 172005 | T16182-VK02-P8UTH-172005 | RESERVE BOILER FOUNDATION REBAR DETAIL | IFR | 2017-02-28 | 2017-05-29 |  | O
CV(17) | Civil | 172004 | T16182-XB02-P8UTH-172004 | RESERVE BOILER FOUNDATION SECTION & DETAIL | IFR | 2017-02-28 | 2017-05-29 |  | O
CV(17) | Civil | 172007 | T16182-XB02-P8UTH-172007 | RESERVE BOILER GRADE SLAB PLAN & SECTION | IFR | 2017-06-01 | 2017-09-01 |  | O
CV(17) | Civil | 172008 | T16182-VK02-P8UTH-172008 | RESERVE BOILER GRADE SLAB REBAR DETAIL | IFR | 2017-06-01 | 2017-09-01 |  | O
CV(17) | Civil | 172013 | T16182-XB02-P8UTH-172013 | RESERVE BOILER MISC. FOUNDATION | IFR | 2017-04-01 | 2017-07-01 |  | O
|  | 860019 | T16182-DN05-P0ZEN-860019 | RESERVE BOILER THERMAL PERFORMANCE TEST PROCEDURE
PT(12) | Mechanical | 125650 | T16182-CV03-P8SGK-125650 | RESERVE BOILER_ FM GAS SYSTEM CALCULATION & DOCUMENT | IFR | 2018-06-05 | 2018-08-01 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125570 | T16182-XJ00-P8ZEN-125570 | RESERVE BOILER_ FUEL SKID DETAIL DRAWING | IFI | 2018-01-12 | 2018-01-30 |  |  |  | PKG-015-RB
PT(12) |  | 125019 | T16182-CQ02-P8ZEN-125019 | RESERVE BOILER_ERECTION MANUAL | Internal
PT(12) | Mechanical | 125525 | T16182-XJ00-P8ZEN-125525 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BLOWDOWN SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125523 | T16182-XJ00-P8ZEN-125523 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BOILER STEAM SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125522 | T16182-XJ00-P8ZEN-125522 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BOILER WATER SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125524 | T16182-XJ00-P8ZEN-125524 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(BURNER SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125526 | T16182-XJ00-P8ZEN-125526 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125520 | T16182-XJ00-P8ZEN-125520 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(DEAERATOR SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125521 | T16182-XJ00-P8ZEN-125521 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(FEEDWATER PUMP SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125527 | T16182-XJ00-P8ZEN-125527 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR LARGE BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | IFI | 2017-09-22 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125546 | T16182-XJ00-P8ZEN-125546 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BLOWDOWN SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125543 | T16182-XJ00-P8ZEN-125543 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BOILER STEAM SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125542 | T16182-XJ00-P8ZEN-125542 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BOILER WATER SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125545 | T16182-XJ00-P8ZEN-125545 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(BURNER SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125547 | T16182-XJ00-P8ZEN-125547 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(CHEMICAL DOSING SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125548 | T16182-XJ00-P8ZEN-125548 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125544 | T16182-XJ00-P8ZEN-125544 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(COMBUSTION AIR & FLUE GAS SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125540 | T16182-XJ00-P8ZEN-125540 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(DEAERATOR SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125541 | T16182-XJ00-P8ZEN-125541 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(FEEDWATER PUMP SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125549 | T16182-XJ00-P8ZEN-125549 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(INSTRUMENT AIR SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125550 | T16182-XJ00-P8ZEN-125550 | RESERVE BOILER-PIPING ISOMETRIC DRAWING FOR SMALL BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | IFI | 2017-10-27 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125535 | T16182-XK00-P8ZEN-125535 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BLOWDOWN SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125533 | T16182-XK00-P8ZEN-125533 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BOILER STEAM SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125532 | T16182-XK00-P8ZEN-125532 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BOILER WATER SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125534 | T16182-XK00-P8ZEN-125534 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(BURNER SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125536 | T16182-XK00-P8ZEN-125536 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(CLOSED COOLING WATER & SERVICE WATER SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125530 | T16182-XK00-P8ZEN-125530 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(DEAERATOR SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125531 | T16182-XK00-P8ZEN-125531 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(FEEDWATER PUMP SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB
PT(12) | Mechanical | 125537 | T16182-XK00-P8ZEN-125537 | RESERVE BOILER-PIPING SUPPORT DETAIL DRAWING FOR LARGE BORE PIPING(SERVICE AIR & SEALING AIR SYSTEM) | IFI | 2017-09-08 | 2018-01-20 |  |  |  | PKG-015-RB
CV(17) | Civil | 172904 | T16182-XB02-P0UZA-172904 | ROAD AND PAVING - GRAVEL PAVEMENT PLAN & SECTION | IFR | 2017-12-20 | 2018-08-29
CV(17) | Civil | 172908 | T16182-VK02-P0UZA-172908 | ROAD AND PAVING DETAIL | IFR | 2017-07-01 | 2018-08-29
CV(17) | Civil | 172903 | T16182-XB02-P0UZA-172903 | ROAD AND PAVING LAYOUT | IFR | 2017-07-01 | 2018-08-29
CV(17) | Civil | 172902 | T16182-XB02-P0UZA-172902 | ROAD AND PAVING OVERALL LAYOUT | IFR | 2017-07-01 | 2018-08-29
CV(17) | Civil | 172912 | T16182-VK02-P0UZA-172912 | ROAD MARKING AND SIGN BOARD DETAIL | IFR | 2019-04-30 | 2019-07-30
CV(17) | Civil | 172911 | T16182-XB02-P0UZA-172911 | ROAD MARKING AND SIGN BOARD LAYOUT | IFR | 2019-04-30 | 2019-07-30
S&A(18) | Structural & Architectural | 180512 | T16182-CA03-P1BAT-180512 | ROOF FOR GTG #1 TR - COLUMN ARRAGEMENT, ROOF FRAMING PLAN, BASEPLATE DETAILS | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 180511 | T16182-CA00-P1BAT-180511 | ROOF FOR GTG #1 TR - PLAN, SECTION, ELEVATION | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 180513 | T16182-CA03-P1BAT-180513 | ROOF FOR GTG #1 TR - ROOF FRAMING ELEVATION, CONNECTION DETAILS | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 180500 | T16182-CA06-P0BAT-180500 | ROOF FOR GTG TR - CALCULATION | IFR | 2017-05-15 | 2017-07-15
S&A(18) | Structural & Architectural | 181800 | T16182-CA06-P0BAT-181800 | ROOF FOR STG TR - CALCULATION | IFR | 2017-09-08 | 2017-11-08
S&A(18) | Structural & Architectural | 181812 | T16182-CA03-P6BAT-181812 | ROOF FOR STG TR - COLUMN ARRAGEMENT, ROOF FRAMING PLAN, BASEPLATE DETAILS | IFR | 2017-09-08 | 2017-11-08
S&A(18) | Structural & Architectural | 181811 | T16182-CA00-P6BAT-181811 | ROOF FOR STG TR - PLAN, SECTION, ELEVATION | IFR | 2017-09-08 | 2017-11-08
S&A(18) | Structural & Architectural | 181813 | T16182-CA03-P6BAT-181813 | ROOF FOR STG TR - ROOF FRAMING ELEVATION, CONNECTION DETAILS | IFR | 2017-09-08 | 2017-11-08
GN-MCH(25) | Mechanical | 250022 | T16182-UC02-P0MKA-250022 | ROTOR ASSEMBLY DISASSEMBLY DIAGRAM | IFI | 2017-04-14 |  |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250021 | T16182-DM02-P0MKA-250021 | ROTOR ASSEMBLY DISASSEMBLY NOTE | IFI | 2017-04-14 |  |  |  |  | PKG-040-STG
PS(11) | General | 110704 | T16182-CN00-P0ZEN-110704 | SAFETY INTEGRITY LEVEL STUDY | IFR | 2017-06-01 | 2017-08-01 |  | O
|  | 755013 | T16182-DD09-P0ZEN-755013 | SAT Procedure for 13.8 kV MV Switch Gear
|  | 755003 | T16182-DD09-P0ZEN-755003 | SAT Procedure for 380kv EHV Cable and Accessories
|  | 755012 | T16182-DD09-P0ZEN-755012 | SAT Procedure for 480V Motor Control Center
|  | 755007 | T16182-DD09-P0ZEN-755007 | SAT Procedure for AC-UPS System
|  | 755008 | T16182-DD09-P0ZEN-755008 | SAT Procedure for DC Battery Charger System
|  | 755009 | T16182-DD09-P0ZEN-755009 | SAT Procedure for Generator Circuit Breaker (GCB)
|  | 755021 | T16182-DD09-P0ZEN-755021 | SAT Procedure for Ground, Step & touch Voltage
|  | 755002 | T16182-DD09-P0ZEN-755002 | SAT Procedure for GSUT
|  | 755001 | T16182-DD09-P0ZEN-755001 | SAT Procedure for Isolated Phase Busbar (IPB)
|  | 755015 | T16182-DD09-P0ZEN-755015 | SAT Procedure for Lighting Distribution Board (LDB)
|  | 755010 | T16182-DD09-P0ZEN-755010 | SAT Procedure for LV Cable
|  | 755014 | T16182-DD09-P0ZEN-755014 | SAT Procedure for LV Switchgear
|  | 755016 | T16182-DD09-P0ZEN-755016 | SAT Procedure for Mold / Dry Transformer
|  | 755017 | T16182-DD09-P0ZEN-755017 | SAT Procedure for MV & LV Motors
|  | 755011 | T16182-DD09-P0ZEN-755011 | SAT Procedure for MV Cable
|  | 755020 | T16182-DD09-P0ZEN-755020 | SAT Procedure for Neutral Grounding Transformer (NGTR) Neutral Grounding Resistor (NGR)
|  | 755004 | T16182-DD09-P0ZEN-755004 | SAT Procedure for Non Segregated Phase Busduct (NSPBD)
|  | 755006 | T16182-DD09-P0ZEN-755006 | SAT Procedure for Protection Relay Panel, GSUT HV Side Energy Metering Panel
|  | 755019 | T16182-DD09-P0ZEN-755019 | SAT Procedure for STG Excitation Transformer (Oil Type)
|  | 755005 | T16182-DD09-P0ZEN-755005 | SAT Procedure for Unit Auxillary Transformer (UAT)
MCH(13) | Electrical | 130308 | T16182-YU03-P0QC-130308 | SCHEMATIC & WIRING DIAGRAM FOR CHEMICAL DOSING SYSTEM | IFI | 2018-01-03 |  |  |  |  | PKG-027-CDS
MCH(13) | Electrical | 130217 | T16182-YU03-P0LD-130217 | SCHEMATIC & WIRING DIAGRAM FOR CONDENSATE POLISHING PLANT | IFI | 2017-09-01 |  |  |  |  | PKG-026-CPP
MCH(13) | Electrical | 130406 | T16182-YU03-P0QU-130406 | SCHEMATIC & WIRING DIAGRAM FOR SAMPLING SYSTEM | IFI | 2018-01-02 |  |  |  |  | PKG-028-SP
MCH(13) | Electrical | 130017 | T16182-YU03-P0GCF-130017 | SCHEMATIC AND WIRING DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-05-05 | 2017-08-31 |  | O |  | PKG-025-WT
EL(15) | Electrical | 151061 | T16182-YU03-P0BT-151061 | SCHEMATIC DIAGRAM - BLOCK #1 DC & AC UPS SYSTEM | IFI | 2017-07-31 |  |  |  |  | PKG-036-DCACUPS
EL(15) | Electrical | 151066 | T16182-YU03-P0BT-151066 | SCHEMATIC DIAGRAM - BLOCK #2 DC & AC UPS SYSTEM | IFI | 2017-07-31 |  |  |  |  | PKG-036-DCACUPS
EL(15) | Electrical | 151071 | T16182-YU03-P0BT-151071 | SCHEMATIC DIAGRAM - COMMON DC & AC UPS SYSTEM | IFI | 2017-07-31 |  |  |  |  | PKG-036-DCACUPS
EL(15) | Electrical | 150731 | T16182-YU03-P0BAC-150731 | SCHEMATIC DIAGRAM - GENERATOR CIRCUIT BREAKER | IFR | 2017-06-30 | 2017-10-18 |  |  |  | PKG-032-GCB
EL(15) | Electrical | 150631 | T16182-YU03-P0BAT-150631 | SCHEMATIC DIAGRAM - GENERATOR STEP - UP TRANSFORMER | IFR | 2017-04-28 | 2017-08-26 |  |  |  | PKG-031-TR
EL(15) | Electrical | 150636 | T16182-YU03-P0BAT-150636 | SCHEMATIC DIAGRAM - GENERATOR STEP - UP TRANSFORMER (STG) | IFR | 2017-05-12 | 2017-08-26 |  |  |  | PKG-031-TR
EL(15) | Electrical | 150681 | T16182-YU03-P0BBT-150681 | SCHEMATIC DIAGRAM - UNIT AUXILIARY TRANSFORMER | IFR | 2017-04-28 | 2017-08-26 |  |  |  | PKG-031-TR
GN-I&C(29) | Instrumentation & Control | 290011 | T16182-YS01-P0MKY-290011 | SCHEMATIC DIAGRAMS FOR EMERGENCY SEAL OIL DC MOTOR STARTER PANEL | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG
GN-I&C(29) | Instrumentation & Control | 290009 | T16182-YS01-P0MKY-290009 | SCHEMATIC DIAGRAMS FOR GENERATOR CONTROL PANEL | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG
GN-I&C(29) | Instrumentation & Control | 290008 | T16182-YS01-P0MKY-290008 | SCHEMATIC DIAGRAMS FOR GENERATOR PROTECTION RELAY FOR STG | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG
GN-I&C(29) | Instrumentation & Control | 290012 | T16182-YS01-P0MKY-290012 | SCHEMATIC DIAGRAMS FOR NGR AND NGTR PANEL FOR STG | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG
GN-I&C(29) | Instrumentation & Control | 290013 | T16182-YS01-P0MKY-290013 | SCHEMATIC DIAGRAMS FOR PT/SA PANEL FOR STG | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260001 | T16182-YD00-P0MKW-260001 | SEAL OIL DRAIN ENLARGEMENT OUTLINE | IFR | 2017-04-30 | 2017-08-31 |  |  |  | PKG-040-STG
S&A(18) | Structural & Architectural | 183600 | T16182-CA06-P0UYF-183600 | SEARCH FACILITY & VISITORS CENTRE - CALCULATION | IFR | 2018-04-01 | 2018-06-01
S&A(18) | Structural & Architectural | 183603 | T16182-CA00-P0UYF-183603 | SEARCH FACILITY & VISITORS CENTRE - ELEVATION | IFR | 2018-04-01 | 2018-06-01
S&A(18) | Structural & Architectural | 183651 | T16182-CA01-P0UYF-183651 | SEARCH FACILITY & VISITORS CENTRE - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2018-04-01 | 2018-06-01
S&A(18) | Structural & Architectural | 183653 | T16182-CA01-P0UYF-183653 | SEARCH FACILITY & VISITORS CENTRE - FRAMING ELEVATION | IFR | 2018-04-01 | 2018-06-01
S&A(18) | Structural & Architectural | 183652 | T16182-CA01-P0UYF-183652 | SEARCH FACILITY & VISITORS CENTRE - GROUND FLOOR & ROOF FRAMING PLAN | IFR | 2018-04-01 | 2018-06-01
S&A(18) | Structural & Architectural | 183601 | T16182-CA00-P0UYF-183601 | SEARCH FACILITY & VISITORS CENTRE - GROUND FLOOR PLAN | IFR | 2018-04-01 | 2018-06-01
S&A(18) | Structural & Architectural | 183604 | T16182-CA00-P0UYF-183604 | SEARCH FACILITY & VISITORS CENTRE - MAIN SECTION | IFR | 2018-04-01 | 2018-06-01
S&A(18) | Structural & Architectural | 183681 | T16182-CA05-P0UYF-183681 | SEARCH FACILITY & VISITORS CENTRE - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | IFR | 2018-04-15 | 2018-06-15
S&A(18) | Structural & Architectural | 183682 | T16182-CA05-P0UYF-183682 | SEARCH FACILITY & VISITORS CENTRE - PLUMBING PLAN | IFR | 2018-04-15 | 2018-06-15
S&A(18) | Structural & Architectural | 183654 | T16182-CA02-P0UYF-183654 | SEARCH FACILITY & VISITORS CENTRE - REBAR SCHEDULE & DETAIL | IFR | 2018-04-01 | 2018-06-01
S&A(18) | Structural & Architectural | 183602 | T16182-CA00-P0UYF-183602 | SEARCH FACILITY & VISITORS CENTRE - ROOF PLAN | IFR | 2018-04-01 | 2018-06-01
|  | 860029 | T16182-DN05-P0ZEN-860029 | SECONDARY RESPONSE TEST
S&A(18) | Structural & Architectural | 183100 | T16182-CA06-P0UYA-183100 | SECURITY BUILDING - CALCULATION | IFR | 2018-05-18 | 2018-07-18
S&A(18) | Structural & Architectural | 183151 | T16182-CA01-P0UYA-183151 | SECURITY BUILDING - FOUNDATION & COLUMN LOCATION PLAN | IFR | 2018-05-18 | 2018-07-18
S&A(18) | Structural & Architectural | 183154 | T16182-CA01-P0UYA-183154 | SECURITY BUILDING - FRAMING ELEVATION | IFR | 2018-05-18 | 2018-07-18
S&A(18) | Structural & Architectural | 183152 | T16182-CA01-P0UYA-183152 | SECURITY BUILDING - GROUND FLOOR FRAMING PLAN | IFR | 2018-05-18 | 2018-07-18
S&A(18) | Structural & Architectural | 183101 | T16182-CA00-P0UYA-183101 | SECURITY BUILDING - GROUND FLOOR PLAN | IFR | 2018-04-18 | 2018-07-18
S&A(18) | Structural & Architectural | 183105 | T16182-CA00-P0UYA-183105 | SECURITY BUILDING - INTERIOR FINISH SCHEDULE | IFR | 2018-10-01 | 2018-12-01
S&A(18) | Structural & Architectural | 183104 | T16182-CA00-P0UYA-183104 | SECURITY BUILDING - MAIN SECTION | IFR | 2018-04-18 | 2018-07-18
S&A(18) | Structural & Architectural | 183181 | T16182-CA05-P0UYA-183181 | SECURITY BUILDING - PLUMBING EQUIPMENT SCHEDULE | IFR | 2018-06-18 | 2018-09-18
S&A(18) | Structural & Architectural | 183183 | T16182-CA05-P0UYA-183183 | SECURITY BUILDING - PLUMBING PLAN | IFR | 2018-06-18 | 2018-09-18
S&A(18) | Structural & Architectural | 183182 | T16182-CA05-P0UYA-183182 | SECURITY BUILDING - PLUMBING SCHEMATIC DIAGRAM | IFR | 2018-06-18 | 2018-09-18
S&A(18) | Structural & Architectural | 183155 | T16182-CA02-P0UYA-183155 | SECURITY BUILDING - RE - BAR DETAIL | IFR | 2018-05-18 | 2018-07-18
S&A(18) | Structural & Architectural | 183153 | T16182-CA01-P0UYA-183153 | SECURITY BUILDING - ROOF FLOOR FRAMING PLAN | IFR | 2018-05-18 | 2018-07-18
S&A(18) | Structural & Architectural | 183102 | T16182-CA00-P0UYA-183102 | SECURITY BUILDING - ROOF PLAN | IFR | 2018-04-18 | 2018-07-18
S&A(18) | Structural & Architectural | 183103 | T16182-CA00-P0UYA-183103 | SECURITY BUILDING - SIDE WALL ELEVATION | IFR | 2018-04-18 | 2018-07-18
EL(15) | Electrical | 150301 | T16182-YT10-P0ZEN-150301 | SHORT CIRCUIT STUDY | IFR | 2017-04-30 | 2017-10-15 |  | O
TG-MCH(22) | Instrumentation & Control | 220095 | T16182-YL13-P6MAA-220095 | SIGNAL TRANSFER LIST BETWEEN TCS AND DCS (HW) | IFI | 2018-06-29 |  |  |  |  | PKG-040-STG
TG-MCH(22) | Instrumentation & Control | 220143 | T16182-YL13-P6MAA-220143 | SIGNAL TRANSFER LIST BETWEEN TCS AND DCS (SW) - UNIT 1+2 | IFI | 2017-11-30 |  |  |  |  | PKG-040-STG
EL(15) | Electrical | 150916 | T16182-YU02-P0BFA-150916 | SINGLE LINE DIAGRAM - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | IFI | 2017-04-30 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150917 | T16182-YU02-P0BFA-150917 | SINGLE LINE DIAGRAM - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | IFI | 2017-06-30 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150918 | T16182-YU02-P0BFA-150918 | SINGLE LINE DIAGRAM - 480V COMMON ESSENTIAL SWITCHGEAR | IFI | 2017-04-30 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150913 | T16182-YU02-P0BFA-150913 | SINGLE LINE DIAGRAM - 480V COMMON SWITCHGEAR | IFI | 2017-04-30 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150915 | T16182-YU02-P0BFA-150915 | SINGLE LINE DIAGRAM - 480V FIRE BRIGADE SWITCHGEAR | IFI | 2017-06-30 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150911 | T16182-YU02-P0BFA-150911 | SINGLE LINE DIAGRAM - 480V GTG/HRSG SWITCHGEAR | IFI | 2017-04-30 |  |  | O |  | PKG-035-LVSWGR
EL(15) | Electrical | 150912 | T16182-YU02-P0BFA-150912 | SINGLE LINE DIAGRAM - 480V STG/ACC SWITCHGEAR | IFI | 2017-06-30 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150914 | T16182-YU02-P0BFA-150914 | SINGLE LINE DIAGRAM - 480V WT SWITCHGEAR | IFI | 2017-04-30 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 151021 | T16182-YU02-P0BT-151021 | SINGLE LINE DIAGRAM - BLOCK #1 DC & AC UPS SYSTEM | IFI | 2017-06-16 |  |  | O |  | PKG-036-DCACUPS
EL(15) | Electrical | 151026 | T16182-YU02-P0BT-151026 | SINGLE LINE DIAGRAM - BLOCK #2 DC & AC UPS SYSTEM | IFI | 2017-06-16 |  |  | O |  | PKG-036-DCACUPS
EL(15) | Electrical | 151031 | T16182-YU02-P0BT-151031 | SINGLE LINE DIAGRAM - COMMON DC & UPS SYSTEM | IFI | 2017-06-16 |  |  | O |  | PKG-036-DCACUPS
EL(15) | Electrical | 150816 | T16182-YU02-P0BB-150816 | SINGLE LINE DIAGRAM – 13.8kV COMMON SWITCHGEAR | IFI | 2017-04-30 |  |  | O |  | PKG-034-MVSWGR
EL(15) | Electrical | 150811 | T16182-YU02-P0BB-150811 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #1 | IFI | 2017-04-30 |  |  | O |  | PKG-034-MVSWGR
EL(15) | Electrical | 150812 | T16182-YU02-P0BB-150812 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #2 | IFI | 2017-04-30 |  |  | O |  | PKG-034-MVSWGR
EL(15) | Electrical | 150813 | T16182-YU02-P0BB-150813 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #3 | IFI | 2017-04-30 |  |  | O |  | PKG-034-MVSWGR
EL(15) | Electrical | 150814 | T16182-YU02-P0BB-150814 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #4 | IFI | 2017-04-30 |  |  | O |  | PKG-034-MVSWGR
EL(15) | Electrical | 150815 | T16182-YU02-P0BB-150815 | SINGLE LINE DIAGRAM – 13.8kV GTG SWITCHGEAR #5 | IFI | 2017-04-30 |  |  | O |  | PKG-034-MVSWGR
MCH(13) | Electrical | 130210 | T16182-YU02-P0LD-130210 | SINGLE LINE DIAGRAM FOR CONDENSATE POLISHING PLANT | IFI | 2017-07-03 |  |  |  |  | PKG-026-CPP
MCH(13) | Electrical | 130010 | T16182-YU02-P0GCF-130010 | SINGLE LINE DIAGRAM FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-03-06 | 2017-07-25 |  | O |  | PKG-025-WT
MCH(13) | Instrumentation & Control | 139042 | T16182-YU02-P0CYE-139042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ADMINISTRATION & SOCIAL BUILDING | IFR | 2018-07-17 | 2018-10-15 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137742 | T16182-YU02-P0CYE-137742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR AIR COMPRESSOR SHELTER | IFR | 2018-01-01 | 2018-04-01 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138542 | T16182-YU02-P0CYE-138542 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR AUX. LEB | IFR | 2017-11-30 | 2018-01-10 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138242 | T16182-YU02-P0CYE-138242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR BSDG DIESEL OIL DAY TANK | IFR | 2017-07-21 | 2017-10-19 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136742 | T16182-YU02-P0CYE-136742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CENTRAL CONTROL BUILDING | IFR | 2017-09-02 | 2017-12-01 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139842 | T16182-YU02-P0CYE-139842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CHEMICAL DOSING SHELTER FOR HRSG | IFR | 2018-03-17 | 2018-06-15 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139742 | T16182-YU02-P0CYE-139742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CHEMICAL DOSING SHELTER FOR STG & HRSG | IFR | 2018-03-17 | 2018-06-15 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139642 | T16182-YU02-P0CYE-139642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR CPP BUILDING | IFR | 2018-04-16 | 2018-07-15 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138942 | T16182-YU02-P0CYE-138942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR DEAERATOR SUPPORT STRUCTURE | IFR | 2017-07-03 | 2017-10-30 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137642 | T16182-YU02-P0CYE-137642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FGS ELECTRICAL BUILDING | IFR | 2017-11-12 | 2018-02-10 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139442 | T16182-YU02-P0CYE-139442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FIRE BRIGADE BUILDING | IFR | 2018-05-03 | 2018-08-01 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137342 | T16182-YU02-P0CYE-137342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR FIRE WATER PUMP HOUSE | IFR | 2017-05-17 | 2017-08-15 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138342 | T16182-YU02-P0CYE-138342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GPRS AREA | IFR | 2017-07-19 | 2017-10-17 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136842 | T16182-YU02-P0CYE-136842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG #1,2 LEB | IFR | 2017-07-22 | 2017-10-20 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136942 | T16182-YU02-P0CYE-136942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG #3,4,5 LEB | IFR | 2017-12-01 | 2018-03-01 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137042 | T16182-YU02-P0CYE-137042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG GSU TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138144 | T16182-YU02-P0CYE-138144 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG LUBE OIL UNIT | IFR | 2019-01-10 | 2019-02-08 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137142 | T16182-YU02-P0CYE-137142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR GTG UNIT AUX. TRANSFORMER | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138442 | T16182-YU02-P0CYE-138442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR H2, CO2 GAS STORAGE SHELTER | IFR | 2017-09-04 | 2017-11-03 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138142 | T16182-YU02-P0CYE-138142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR HRSG | IFR | 2017-11-12 | 2018-02-10 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139242 | T16182-YU02-P0CYE-139242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR MAIN GATE HOUSE | IFR | 2018-05-03 | 2018-08-01 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138042 | T16182-YU02-P0CYE-138042 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR N2 GAS STORAGE SHELTER | IFR | 2017-07-03 | 2017-10-30 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137442 | T16182-YU02-P0CYE-137442 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR RESERVE BOILER | IFR | 2017-10-18 | 2018-01-16 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139142 | T16182-YU02-P0CYE-139142 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR SECURITY BUILDING | IFR | 2018-11-17 | 2019-02-15 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138642 | T16182-YU02-P0CYE-138642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST BUILDING | IFR | 2017-12-10 | 2018-03-10 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138742 | T16182-YU02-P0CYE-138742 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST#1 LEB | IFR | 2017-12-15 | 2018-03-15 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 138842 | T16182-YU02-P0CYE-138842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR ST#2 LEB | IFR | 2018-01-20 | 2018-04-20 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139942 | T16182-YU02-P0CYE-139942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR STG EXCITATION TRANSFORMER | IFR | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137242 | T16182-YU02-P0CYE-137242 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR STG GSU TRANSFORMER | IFR | 2017-09-03 | 2017-12-01 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 136642 | T16182-YU02-P0CYE-136642 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR SUPPORT BUILDING | IFR | 2018-06-15 | 2018-09-13 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137942 | T16182-YU02-P0CYE-137942 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WATER TREATMENT BUILDING | IFR | 2017-09-11 | 2017-12-10 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139542 | T16182-YU02-P0CYE-139542 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WORKSHOP & STORAGE BUILDING | IFR | 2018-07-01 | 2018-09-29 |  |  |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 137842 | T16182-YU02-P0CYE-137842 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR WWT & BULK CHEMICAL STORAGE TANK SHELTER | IFR | 2017-11-22 | 2018-02-20 |  | O |  | PKG-030-FF
MCH(13) | Instrumentation & Control | 139342 | T16182-YU02-P0CYE-139342 | SINGLE LINE DIAGRAM OF FIRE ALARM SYSTEM FOR X-RAY SEARCHING ROOM | IFR | 2018-10-17 | 2019-01-15 |  |  |  | PKG-030-FF
GN-I&C(29) | Instrumentation & Control | 290006 | T16182-YU02-P0MKY-290006 | SINGLE LINE DIAGRAMS INCLUDING GENERATOR CONTROL & PROTECTION | IFR | 2017-05-20 | 2017-09-30 |  |  |  | PKG-040-STG
|  | 755022 | T16182-DD09-P0ZEN-755022 | Site Acceptance Test Procedure for Generator & Exc. TR Protection Relay, Control Panel
|  | 755023 | T16182-DD09-P0ZEN-755023 | Site Acceptance Test Procedure for HCIS Security System
GA(10) | General | 100001 | T16182-UC07-P0ZEN-100001 | SITE PLAN | IFR | 2016-10-30 | 2017-02-14 |  | O | O
EL(15) | Electrical | 152810 | T16182-YT10-P0ZEN-152810 | SIZING CALCULATION - 380KV EHV CABLE AND ACCESSOIRES | IFR | 2017-02-28 | 2017-05-16 |  | O
PT(12) | Mechanical | 120017 | T16182-XW03-P0SCA-120017 | SIZING CALCULATION - COMPRESSED AIR SYSTEM | IFR | 2017-02-10 | 2017-05-31 |  | O
EL(15) | Electrical | 151001 | T16182-YT10-P0BT-151001 | SIZING CALCULATION - DC & AC UPS SYSTEM | IFR | 2017-02-28 | 2017-07-25 |  | O |  | PKG-036-DCACUPS
PT(12) | Mechanical | 120021 | T16182-XW03-P0EKG-120021 | SIZING CALCULATION - FUEL GAS SYSTEM | IFR | 2017-02-28 | 2017-05-31 |  | O |  | PKG-014-FGS
EL(15) | Electrical | 150701 | T16182-YT10-P0BAA-150701 | SIZING CALCULATION - GENERATOR CIRCUIT BREAKER / ISOLATED PHASE BUSDUCT | IFR | 2017-01-31 | 2017-06-13 |  | O |  | PKG-032-GCB
EL(15) | Electrical | 150601 | T16182-YT10-P0BAT-150601 | SIZING CALCULATION - GENERATOR STEP - UP TRANSFORMER | IFR | 2017-01-31 | 2017-06-13 |  | O |  | PKG-031-TR
EL(15) | Electrical | 152801 | T16182-YR02-P0ZEN-152801 | SIZING CALCULATION - MV/LV POWER CABLES | IFR | 2017-01-13 | 2017-05-30 |  | O
PT(12) | Mechanical | 120013 | T16182-XW03-P0GKS-120013 | SIZING CALCULATION - POTABLE WATER DISTRIBUTION PUMP | IFR | 2017-01-30 | 2017-04-30 |  | O
EL(15) | Electrical | 150651 | T16182-YT10-P0BBT-150651 | SIZING CALCULATION - UNIT AUXILIARY TRANSFORMER | IFR | 2017-02-28 | 2017-07-11 |  | O |  | PKG-031-TR
PS(11) | Mechanical | 110050 | T16182-XW03-P0PGB-110050 | SIZING CALCULATION FOR CLOSED COOLING WATER SYSTEM | IFR | 2017-02-28 | 2017-07-28 |  | O
PS(11) | Mechanical | 110046 | T16182-XW03-P0LC-110046 | SIZING CALCULATION FOR CONDENSATE EXTRACTION PUMP | IFR | 2017-03-01 | 2017-07-29
PS(11) | Mechanical | 110051 | T16182-XW03-P0GHC-110051 | SIZING CALCULATION FOR CYCLE MAKEUP WATER PUMP AND DM WATER SUPPLY PUMP | IFR | 2017-02-28 | 2017-07-28 |  | O
PS(11) | Mechanical | 110047 | T16182-XW03-P0LC-110047 | SIZING CALCULATION FOR FGP CONDENSATE PUMP | IFR | 2017-03-01 | 2017-07-29
PS(11) | Mechanical | 110049 | T16182-XW03-P0LA-110049 | SIZING CALCULATION FOR FGP FEEDWATER PUMP | IFR | 2017-01-19 | 2017-04-12
PS(11) | Mechanical | 110048 | T16182-XW03-P0LA-110048 | SIZING CALCULATION FOR HRSG FEEDWATER PUMP | IFR | 2017-01-19 | 2017-04-12
PS(11) | Mechanical | 110052 | T16182-XW03-P0QJA-110052 | SIZING CALCULATION FOR NITROGEN GAS SYSTEM | IFR | 2017-03-31 | 2017-06-30 |  | O |  | PKG-006-N2
MCH(13) | Mechanical | 130019 | T16182-YD00-P0GCF-130019 | SLEEVE AND WALL OPENING FOR WATER AND WASTE WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-06-30 |  | O |  | PKG-025-WT
CV(17) | Civil | 170101 | T16182-BF05-P0ZEN-170101 | SOIL INVESTIGATION REPORT | IFI | 2016-10-24 |  |  | O
MCH(13) | Mechanical | 136612 | T16182-YT01-P0SGE-136612 | SPRINKLER SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
S&A(18) | Structural & Architectural | 181005 | T16182-CA00-P0UBA-181005 | ST #1 LEB - ARCHITECTURAL MISC. DETAIL | IFR | 2017-04-01 | 2017-06-01
S&A(18) | Structural & Architectural | 181000 | T16182-CA06-P0UBA-181000 | ST #1 LEB - CALCULATION | IFR | 2017-04-01 | 2017-06-01
S&A(18) | Structural & Architectural | 181056 | T16182-CA02-P0UBA-181056 | ST #1 LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-04-01 | 2017-06-01
S&A(18) | Structural & Architectural | 181051 | T16182-CA01-P0UBA-181051 | ST #1 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-04-01 | 2017-06-01
S&A(18) | Structural & Architectural | 181055 | T16182-CA02-P0UBA-181055 | ST #1 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | IFR | 2017-04-01 | 2017-06-01
S&A(18) | Structural & Architectural | 181052 | T16182-CA01-P0UBA-181052 | ST #1 LEB - GROUND FLOOR FRAMING PLAN | IFR | 2017-04-01 | 2017-06-01
S&A(18) | Structural & Architectural | 181001 | T16182-CA00-P0UBA-181001 | ST #1 LEB - GROUND FLOOR PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | IFR | 2017-04-01 | 2017-06-01
S&A(18) | Structural & Architectural | 181054 | T16182-CA01-P0UBA-181054 | ST #1 LEB - LINE & ROW FRAMING ELEVATION | IFR | 2017-04-01 | 2017-06-01
S&A(18) | Structural & Architectural | 181004 | T16182-CA00-P0UBA-181004 | ST #1 LEB - MAIN SECTION | IFR | 2017-04-01 | 2017-06-01
S&A(18) | Structural & Architectural | 181053 | T16182-CA01-P0UBA-181053 | ST #1 LEB - ROOF FLOOR FRAMING PLAN | IFR | 2017-04-01 | 2017-06-01
S&A(18) | Structural & Architectural | 181002 | T16182-CA00-P0UBA-181002 | ST #1 LEB - ROOF PLAN | IFR | 2017-04-01 | 2017-06-01
S&A(18) | Structural & Architectural | 181003 | T16182-CA00-P0UBA-181003 | ST #1 LEB - SIDE WALL ELEVATION | IFR | 2017-04-01 | 2017-06-01
S&A(18) | Structural & Architectural | 181105 | T16182-CA00-P0UBA-181105 | ST #2 LEB - ARCHITECTURAL MISC. DETAIL | IFR | 2017-05-01 | 2017-07-01
S&A(18) | Structural & Architectural | 181100 | T16182-CA06-P0UBA-181100 | ST #2 LEB - CALCULATION | IFR | 2017-05-01 | 2017-07-01
S&A(18) | Structural & Architectural | 181156 | T16182-CA02-P0UBA-181156 | ST #2 LEB - COLUMN, BEAM & GIRDER RE - BAR SCHEDULE | IFR | 2017-05-01 | 2017-07-01
S&A(18) | Structural & Architectural | 181151 | T16182-CA01-P0UBA-181151 | ST #2 LEB - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-05-01 | 2017-07-01
S&A(18) | Structural & Architectural | 181155 | T16182-CA02-P0UBA-181155 | ST #2 LEB - FOUNDATION, SLAB & MISC. DETAIL RE - BAR DETAIL | IFR | 2017-05-01 | 2017-07-01
S&A(18) | Structural & Architectural | 181152 | T16182-CA01-P0UBA-181152 | ST #2 LEB - GROUND FLOOR FRAMING PLAN | IFR | 2017-05-01 | 2017-07-01
S&A(18) | Structural & Architectural | 181101 | T16182-CA00-P0UBA-181101 | ST #2 LEB - GROUND FLOOR PLAN & INTERIOR FINISH SCHEDULE(INCL. DOOR & WINDOW) | IFR | 2017-05-01 | 2017-07-01
S&A(18) | Structural & Architectural | 181154 | T16182-CA01-P0UBA-181154 | ST #2 LEB - LINE & ROW FRAMING ELEVATION | IFR | 2017-05-01 | 2017-07-01
S&A(18) | Structural & Architectural | 181104 | T16182-CA00-P0UBA-181104 | ST #2 LEB - MAIN SECTION | IFR | 2017-05-01 | 2017-07-01
S&A(18) | Structural & Architectural | 181153 | T16182-CA01-P0UBA-181153 | ST #2 LEB - ROOF FLOOR FRAMING PLAN | IFR | 2017-05-01 | 2017-07-01
S&A(18) | Structural & Architectural | 181102 | T16182-CA00-P0UBA-181102 | ST #2 LEB - ROOF PLAN | IFR | 2017-05-01 | 2017-07-01
S&A(18) | Structural & Architectural | 181103 | T16182-CA00-P0UBA-181103 | ST #2 LEB - SIDE WALL ELEVATION | IFR | 2017-05-01 | 2017-07-01
S&A(18) | Structural & Architectural | 180459 | T16182-CA03-P0UMA-180459 | ST BUILDING - BASE PLATE DETAIL | IFR | 2017-01-31 | 2017-03-31
S&A(18) | Structural & Architectural | 180458 | T16182-CA03-P0UMA-180458 | ST BUILDING - COLUMN LOCATION PLAN | IFR | 2017-01-31 | 2017-03-31
S&A(18) | Structural & Architectural | 180460 | T16182-CA03-P0UMA-180460 | ST BUILDING - CRANE GIRDER FRAMING PLAN | IFR | 2017-01-31 | 2017-03-31
S&A(18) | Structural & Architectural | 180491 | T16182-CA06-P0UMA-180491 | ST BUILDING - DESIGN CALCULATION FOR BASE PLATE, COLUMN, BEAM & ROOF TRUSS | IFR | 2017-01-31 | 2017-03-31
S&A(18) | Structural & Architectural | 180492 | T16182-CA06-P0UMA-180492 | ST BUILDING - DESIGN CALCULATION FOR CRANE GIRDER, PURLIN & SIDE GIRT | IFR | 2017-04-30 | 2017-05-30
S&A(18) | Structural & Architectural | 180490 | T16182-CA06-P0UMA-180490 | ST BUILDING - DESIGN CALCULATION FOR FOUNDATION | IFR | 2016-11-30 | 2017-01-24
S&A(18) | Structural & Architectural | 180406 | T16182-CA00-P0UMA-180406 | ST BUILDING - DOOR SCHEDULE | IFR | 2017-08-15 | 2017-10-15
S&A(18) | Structural & Architectural | 180403 | T16182-CA00-P0UMA-180403 | ST BUILDING - ELEVATION | IFR | 2016-11-30 | 2017-01-24
S&A(18) | Structural & Architectural | 180481 | T16182-CA05-P0UMA-180481 | ST BUILDING - EQUIPMENT DRAIN PLAN | IFR | 2017-04-15 | 2017-06-15
S&A(18) | Structural & Architectural | 180482 | T16182-CA05-P0UMA-180482 | ST BUILDING - EQUIPMENT DRAIN PLAN (ISO) | IFR | 2017-04-15 | 2017-06-15
S&A(18) | Structural & Architectural | 180452 | T16182-CA01-P0UMA-180452 | ST BUILDING - FOUNDATION LOCATION PLAN | IFR | 2016-11-30 | 2017-01-24
S&A(18) | Structural & Architectural | 180463 | T16182-CA03-P0UMA-180463 | ST BUILDING - FRAMING ELEVATION | IFR | 2017-01-31 | 2017-03-31
S&A(18) | Structural & Architectural | 180465 | T16182-CA03-P0UMA-180465 | ST BUILDING - GIRT EAST - WEST ELEVATION | IFR | 2017-04-30 | 2017-05-30
S&A(18) | Structural & Architectural | 180464 | T16182-CA03-P0UMA-180464 | ST BUILDING - GIRT NORTH - SOUTH ELEVATION | IFR | 2017-04-30 | 2017-05-30
S&A(18) | Structural & Architectural | 180401 | T16182-CA00-P0UMA-180401 | ST BUILDING - GROUND FLOOR PLAN | IFR | 2016-11-30 | 2017-01-24
S&A(18) | Structural & Architectural | 180405 | T16182-CA00-P0UMA-180405 | ST BUILDING - INTERIOR FINISH SCHEDULE | IFR | 2017-08-15 | 2017-10-15
S&A(18) | Structural & Architectural | 180466 | T16182-CA03-P0UMA-180466 | ST BUILDING - MISC. PLATFORM PLAN & SECTION | IFR | 2017-04-30 | 2017-05-30
S&A(18) | Structural & Architectural | 180451 | T16182-CA01-P0UMA-180451 | ST BUILDING - PILE ARRANGEMENT | IFR | 2016-11-30 | 2017-01-24
S&A(18) | Structural & Architectural | 180454 | T16182-CA01-P0UMA-180454 | ST BUILDING - PILE CAP & FOUNDATION REINFORCEMENT DETAIL | IFR | 2016-11-30 | 2017-01-24
S&A(18) | Structural & Architectural | 180462 | T16182-CA03-P0UMA-180462 | ST BUILDING - ROOF FRAMING PLAN | IFR | 2017-01-31 | 2017-03-31
S&A(18) | Structural & Architectural | 180402 | T16182-CA00-P0UMA-180402 | ST BUILDING - ROOF PLAN | IFR | 2016-11-30 | 2017-01-24
S&A(18) | Structural & Architectural | 180471 | T16182-CA03-P0UMA-180471 | ST BUILDING - ROOF PURLIN PLAN | IFR | 2017-04-30 | 2017-05-30
S&A(18) | Structural & Architectural | 180469 | T16182-CA03-P0UMA-180469 | ST BUILDING - ROOF WALKWAY FRAMING PLAN | IFR | 2017-04-30 | 2017-05-30
S&A(18) | Structural & Architectural | 180404 | T16182-CA00-P0UMA-180404 | ST BUILDING - SECTION | IFR | 2016-11-30 | 2017-01-24
S&A(18) | Structural & Architectural | 180467 | T16182-CA03-P0UMA-180467 | ST BUILDING - STAIR PLAN, ELEVATION & DETAIL | IFR | 2017-04-30 | 2017-05-30
S&A(18) | Structural & Architectural | 180408 | T16182-CA00-P0UMA-180408 | ST BUILDING - WALL SECTION | IFR | 2017-08-15 | 2017-10-15
S&A(18) | Structural & Architectural | 180468 | T16182-CA03-P0UMA-180468 | ST BUILDING – MAIN TRUSS DETAIL | IFR | 2017-02-28 | 2017-04-30
S&A(18) |  | 180500 | T16182-CA03-P0UMA-180500 | ST BUILDING_MISC. PLATFORM PLAN & SECTION | Internal
TG-MCH(22) | Civil | 220003 | T16182-UF00-P0MAA-220003 | ST FOUNDATION LOAD - PLAN | IFI | 2017-01-24 |  |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250023 | T16182-YD00-P0MKA-250023 | ST GENERATOR END SHIELD ASSY CE | IFI | 2017-11-14 |  |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250024 | T16182-YD00-P0MKA-250024 | ST GENERATOR END SHIELD ASSY TE | IFI | 2017-11-14 |  |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250003 | T16182-UF00-P6MKA-250003 | ST GENERATOR FOUNDATION LOADING | IFI | 2016-12-17 |  |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250016 | T16182-YD00-P0MKA-250016 | ST GENERATOR MECHANICAL OUTLINE | IFI | 2017-03-30 | 2017-11-20 |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250020 | T16182-YD00-P0MKA-250020 | ST GENERATOR TERMINAL BOX ASSEMBLY | IFI | 2017-03-30 |  |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250008 | T16182-YD00-P6MKA-250008 | ST GENERATOR UNIT HYDROGEN COOLER OUTLINE | IFI | 2017-01-05 |  |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260005 | T16182-XK00-P6MKA-260005 | ST GENERATOR UNIT#P6 AUX SYSTEM HANGER & SUPPORT | IFI | 2017-08-31 | 2017-10-30 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260004 | T16182-XH01-P6MKA-260004 | ST GENERATOR UNIT#P6 AUX SYSTEM PIPING ARRANGEMENT | IFR | 2017-06-30 | 2017-12-30 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260003 | T16182-XJ00-P6MKA-260003 | ST GENERATOR UNIT#P6 AUX SYSTEM PIPING ISO | IFI | 2017-08-31 | 2017-10-30 |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250001 | T16182-XB00-P6MKA-250001 | ST GENERATOR UNIT#P6 FOUNDATION ARRANGEMENT DRAWING | IFI | 2016-12-17 | 2017-08-31 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260008 | T16182-XK00-P7MKA-260008 | ST GENERATOR UNIT#P7 AUX SYSTEM HANGER & SUPPORT | IFI | 2017-08-31 | 2017-10-30 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260007 | T16182-XH01-P7MKA-260007 | ST GENERATOR UNIT#P7 AUX SYSTEM PIPING ARRANGEMENT | IFR | 2017-06-30 | 2017-12-30 |  |  |  | PKG-040-STG
GN-SYS(26) | Mechanical | 260006 | T16182-XJ00-P7MKA-260006 | ST GENERATOR UNIT#P7 AUX SYSTEM PIPING ISO | IFI | 2017-08-31 | 2017-10-30 |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250002 | T16182-XB00-P7MKA-250002 | ST GENERATOR UNIT#P7 FOUNDATION ARRANGEMENT DRAWING | IFI | 2016-12-17 | 2017-08-31 |  |  |  | PKG-040-STG
|  | 860003 | T16182-DN05-P0ZEN-860003 | ST LOAD REJECTION TEST
MCH(13) | Mechanical | 136611 | T16182-YT01-P0SGA-136611 | STAND PIPE SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
MCH(13) | Mechanical | 133302 | T16182-YK09-P0SAA-133302 | STANDARD DRAIWNG FOR HVAC SYSTEM | IFR | 2017-01-25 | 2017-04-15 |  | O |  | PKG-041-HVAC
S&A(18) | Structural & Architectural | 180034 | T16182-CC05-P0ZEN-180034 | STANDARD DRAWING - ABBREVIATIONS & WELDING | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180006 | T16182-CC05-P0ZEN-180006 | STANDARD DRAWING - CLADDING JOINT DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180020 | T16182-CC05-P0ZEN-180020 | STANDARD DRAWING - DOOR DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180019 | T16182-CC05-P0ZEN-180019 | STANDARD DRAWING - DOOR SCHEDULE | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180001 | T16182-CC05-P0ZEN-180001 | STANDARD DRAWING - GENERAL NOTES, ABBREVIATION, LEGEND & SIMBOLS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180033 | T16182-CC05-P0ZEN-180033 | STANDARD DRAWING - GENERAL NOTES, MATERIALS, CONNECTIONS & MEMBER SIZE DESIGNATION | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180040 | T16182-CC05-P0ZEN-180040 | STANDARD DRAWING - GIRTH & PURLIN CONNECTION DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180002 | T16182-CC05-P0ZEN-180002 | STANDARD DRAWING - INTERIOR FINISH DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180042 | T16182-CC05-P0ZEN-180042 | STANDARD DRAWING - LADDER DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180008 | T16182-CC05-P0ZEN-180008 | STANDARD DRAWING - MISC. ARCHITECTURAL DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180035 | T16182-CC05-P0ZEN-180035 | STANDARD DRAWING - MOMENT CONNECTION DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180044 | T16182-CC05-P0ZEN-180044 | STANDARD DRAWING - PLUMBING STANDARD GENERAL DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180043 | T16182-CC05-P0ZEN-180043 | STANDARD DRAWING - PLUMBING STANDARD SYMBOL & ABBREVIATION | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180030 | T16182-CC05-P0ZEN-180030 | STANDARD DRAWING - RE - BAR STANDARD | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180036 | T16182-CC05-P0ZEN-180036 | STANDARD DRAWING - SHEAR CONNECTION DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180041 | T16182-CC05-P0ZEN-180041 | STANDARD DRAWING - TYPICAL GRATING AND CHK'D PLATE DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180038 | T16182-CC05-P0ZEN-180038 | STANDARD DRAWING - TYPICAL STAIR & HANDRAIL DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180039 | T16182-CC05-P0ZEN-180039 | STANDARD DRAWING - TYPICAL STAIR STRINGER CONNECTION DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180037 | T16182-CC05-P0ZEN-180037 | STANDARD DRAWING - TYPICAL VERTICAL & HORIZONTAL BRACING CONNECTION DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180025 | T16182-CC05-P0ZEN-180025 | STANDARD DRAWING - WINDOW DETAILS | IFI | 2016-11-30
S&A(18) | Structural & Architectural | 180024 | T16182-CC05-P0ZEN-180024 | STANDARD DRAWING - WINDOW SCHEDULE | IFI | 2016-11-30
|  | 860009 | T16182-DN05-P0ZEN-860009 | STARTUP TIME TEST (COLD/WARM/HOT)
GN-MCH(25) | Mechanical | 250014 | T16182-UC02-P0MKA-250014 | STATOR WINDING DIAGRAM | IFI | 2017-04-14 |  |  |  |  | PKG-040-STG
PS(11) | Mechanical | 110201 | T16182-YR01-P0ZEN-110201 | STEAM BLOWING - OUT PROCEDURE | IFR | 2017-06-30 | 2017-09-18
PT(12) | Mechanical | 129031 | T16182-YD00-P0GHC-129031 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - GENERAL ARRANGEMENT DRAWING | IFI | 2017-07-13 | 2017-12-10 |  |  |  | PKG-024-BOPP
PT(12) | Mechanical | 129032 | T16182-YT01-P0GHC-129032 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-07-13 |  |  |  |  | PKG-024-BOPP
PT(12) | Instrumentation & Control | 129036 | T16182-YL00-P0GHC-129036 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - INSTRUMENT LIST AND DATA SHEET | IFI | 2017-07-13 |  |  |  |  | PKG-024-BOPP
PT(12) | Instrumentation & Control | 129037 | T16182-YK00-P0GHC-129037 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-09-28 |  |  |  |  | PKG-024-BOPP
PT(12) | Mechanical | 129034 | T16182-YT01-P0GHC-129034 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - MECHANICAL SEAL SPECIFICATION | IFI | 2017-08-29 |  |  |  |  | PKG-024-BOPP
PT(12) | Electrical | 129035 | T16182-YM01-P0GHC-129035 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - MOTOR DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-07-13 |  |  |  |  | PKG-024-BOPP
PT(12) | Mechanical | 129038 | T16182-YL22-P0GHC-129038 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - NAME PLATE DRAWING | IFI | 2017-09-28 |  |  |  |  | PKG-024-BOPP
PT(12) | Mechanical | 129033 | T16182-YK09-P0GHC-129033 | STEAM DRAIN & FGP DEMIN SUPPLY (2 PUMPS) - PUMP SECTIONAL DRAWING | IFI | 2017-07-29 | 2017-12-26 |  |  |  | PKG-024-BOPP
CV(17) | Civil | 171113 | T16182-XB02-P0MPA-171113 | STEAM TURBINE GENERATOR FOUNDATION ANCHOR BOLTS AND EMBEDMENT | IFR | 2017-07-28 | 2017-11-15
CV(17) | Civil | 171104 | T16182-XB02-P0MPA-171104 | STEAM TURBINE GENERATOR FOUNDATION LAYOUT | IFR | 2017-06-28 | 2017-09-11
CV(17) | Civil | 171105 | T16182-XB02-P0MPA-171105 | STEAM TURBINE GENERATOR FOUNDATION PILE ARRANGEMENT | IFR | 2017-02-28 | 2017-05-14
CV(17) | Civil | 171106 | T16182-XB02-P0MPA-171106 | STEAM TURBINE GENERATOR FOUNDATION PLAN AND SECTION | IFR | 2017-06-28 | 2017-09-11
CV(17) | Civil | 171117 | T16182-VK02-P0MPA-171117 | STEAM TURBINE GENERATOR FOUNDATION R.C DETAIL | IFR | 2017-06-28 | 2017-09-11
TG-MCH(22) | Mechanical | 220801 | T16182-YD00-P0MAA-220801 | STEAM TURBINE OUTLINE DRAWING | IFR | 2017-06-30 | 2017-12-29 | O |  |  | PKG-040-STG
EL(15) | Electrical | 150781 | T16182-YD00-P0BAA-150781 | STEEL SUPPORT STRUCTURE DRAWING - ISOLATED PHASE BUSDUCT FOR GTG UNIT | IFI | 2017-07-28 |  |  |  |  | PKG-033-IPB
EL(15) | Electrical | 150782 | T16182-YD00-P0BAA-150782 | STEEL SUPPORT STRUCTURE DRAWING - ISOLATED PHASE BUSDUCT FOR STG UNIT | IFI | 2017-08-25 |  |  |  |  | PKG-033-IPB
GN-MCH(25) | Mechanical | 250018 | T16182-YD00-P0MKA-250018 | STG FLOOR PLATE LAYOUT | IFI | 2017-03-30 | 2017-11-20 |  |  |  | PKG-040-STG
TG-MCH(22) | Civil | 220023 | T16182-CA07-P0MPA-220023 | STG FOUNDATION - DESIGN CRITERIA - UNIT P6 & P7 | IFI | 2017-01-24 |  |  |  |  | PKG-040-STG
GN-MCH(25) | Mechanical | 250017 | T16182-YD00-P0MKA-250017 | STG SOLE PLATE LAYOUT | IFI | 2017-03-30 | 2017-11-20 |  |  |  | PKG-040-STG
CV(17) | Civil | 172108 | T16182-XB02-P0UAG-172108 | STG STEP UP AND EXCITATION TRANSFORMER GRATING & GRATING SUPPORT ARRANGEMENT PLAN & SECTION | IFR | 2017-04-25 | 2017-07-24
CV(17) | Civil | 172102 | T16182-XB02-P0UAG-172102 | STG STEP UP AND EXCITATION TRANSFORMER PLAN & SECTION | IFR | 2017-04-25 | 2017-07-24
CV(17) | Civil | 172109 | T16182-VK02-P0UAG-172109 | STG STEP UP AND EXCITATION TRANSFORMER RE-BAR DETAIL | IFR | 2017-04-25 | 2017-07-24
CV(17) | Civil | 173303 | T16182-XB02-P0GUB-173303 | STORMWATER DRAINAGE LAYOUT | IFR | 2017-07-01 | 2018-08-29
CV(17) | Civil | 173302 | T16182-XB02-P0GUB-173302 | STORMWATER DRAINAGE OVERALL LAYOUT | IFR | 2017-07-01 | 2018-08-29
CV(17) | Civil | 173313 | T16182-VK02-P0GUB-173313 | STORMWATER DRAINAGE STRUCTURAL DETAIL | IFR | 2017-07-01 | 2018-08-29
CV(17) | Civil | 172804 | T16182-VK02-P0GUC-172804 | STORMWATER POND DETAIL | IFR | 2017-06-30 | 2017-08-29
TK(40) | Mechanical | 410002 | T16182-YT10-P0LCP-410002 | STRENGTH CALCULATION FOR CONDENSATE STORAGE TANK | IFR | 2017-02-24 | 2017-04-28 |  | O
TK(40) | Mechanical | 410012 | T16182-YT10-P0GHC-410012 | STRENGTH CALCULATION FOR DEMINERALIZED WATER STORAGE TANK | IFR | 2017-02-24 | 2017-04-28 |  | O
TK(40) | Mechanical | 410022 | T16182-YT10-P0GKB-410022 | STRENGTH CALCULATION FOR POTABLE & FIRE FIGHTING WATER STORAGE TANK | IFR | 2017-02-24 | 2017-04-28 |  | O
TK(40) | Mechanical | 410032 | T16182-YT10-P0GKB-410032 | STRENGTH CALCULATION FOR POTABLE WATER STORAGE TANK | IFR | 2017-02-24 | 2017-04-28 |  | O
PP(14) | Mechanical | 140017 | T16182-BP00-P0LCA-140017 | STRESS ANALYSIS REPORT FOR CONDENSATE SYSTEM | IFR | 2019-06-05 | 2019-07-05
PP(14) | Mechanical | 140014 | T16182-BP00-P0LAB-140014 | STRESS ANALYSIS REPORT FOR FEED WATER SYSTEM | IFR | 2017-04-28 | 2017-12-08 |  | O
PP(14) | Mechanical | 140015 | T16182-BP00-P0EKG-140015 | STRESS ANALYSIS REPORT FOR FUEL SYSTEM | IFR | 2017-04-28 | 2017-12-20 |  | O
PP(14) | Mechanical | 140011 | T16182-BP00-P0LBA-140011 | STRESS ANALYSIS REPORT FOR HP STEAM SYSTEM | IFR | 2017-04-28 | 2018-01-15
PP(14) | Mechanical | 140012 | T16182-BP00-P0LBC-140012 | STRESS ANALYSIS REPORT FOR IP STEAM SYSTEM | IFR | 2017-05-26 | 2018-01-15
PP(14) | Mechanical | 140016 | T16182-BP00-P0LBG-140016 | STRESS ANALYSIS REPORT FOR LP STEAM SYSTEM | IFR | 2017-06-02 | 2018-02-15
PP(14) | Mechanical | 140013 | T16182-BP00-P0LBS-140013 | STRESS ANALYSIS REPORT FOR PROCESS STEAM SYSTEM | IFR | 2017-04-28 | 2017-12-08 |  | O
GN-MCH(25) | Mechanical | 250019 | T16182-DM02-P0MKA-250019 | SUGGESTIONS FOR GROUTING STG WITH FLOWABLE GROUT | IFI | 2017-03-30 |  |  |  |  | PKG-040-STG
PT(12) | Mechanical | 128505 | T16182-XK00-P0GM-128505 | SUMP PUMP - COUPLING SPECIFICATION | IFI | 2017-09-18 |  |  |  |  | PKG-023-SUP
PT(12) | Mechanical | 128502 | T16182-YT01-P0GM-128502 | SUMP PUMP - DATA SHEET & CHARACTERISTIC CURVE | IFI | 2017-08-07 |  |  |  |  | PKG-023-SUP
PT(12) | Civil | 128506 | T16182-XB00-P0GM-128506 | SUMP PUMP - FOUNDATION DRAWINGS | IFI | 2017-08-07 | 2017-11-10 |  |  |  | PKG-023-SUP
PT(12) | Instrumentation & Control | 128512 | T16182-YL00-P0GM-128512 | SUMP PUMP - INSTRUMENT LIST | IFI | 2017-08-31 |  |  |  |  | PKG-023-SUP
PT(12) | Instrumentation & Control | 128508 | T16182-CV03-P0GM-128508 | SUMP PUMP - INSTRUMENT SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-023-SUP
PT(12) | Instrumentation & Control | 128509 | T16182-YK00-P0GM-128509 | SUMP PUMP - INSTRUMENTATION HOOK - UP DRAWING | IFI | 2017-08-31 |  |  |  |  | PKG-023-SUP
PT(12) | Mechanical | 128504 | T16182-XK00-P0GM-128504 | SUMP PUMP - MECHANICAL SEAL SPECIFICATION | IFI | 2017-09-18 |  |  |  |  | PKG-023-SUP
PT(12) | Electrical | 128507 | T16182-XW01-P0GM-128507 | SUMP PUMP - MOTOR SPECIFICATION | IFI | 2017-08-31 |  |  |  |  | PKG-023-SUP
PT(12) | Mechanical | 128510 | T16182-XF00-P0GM-128510 | SUMP PUMP - NAME PLATE DRAWING | IFI | 2017-09-29 |  |  |  |  | PKG-023-SUP
PT(12) | Mechanical | 128501 | T16182-YD00-P0GM-128501 | SUMP PUMP - PUMP OUTLINE DRAWING | IFI | 2017-08-07 | 2017-11-10 |  |  |  | PKG-023-SUP
PT(12) | Mechanical | 128503 | T16182-YD00-P0GM-128503 | SUMP PUMP - PUMP SECTIONAL DRAWING | IFI | 2017-08-07 |  |  |  |  | PKG-023-SUP
PT(12) | Electrical | 128511 | T16182-YR05-P0GM-128511 | SUMP PUMP - SCHEMATIC AND WIRING DIAGRAM WITH CONTROL PANEL LAYOUT DRAWING FOR WASTE WATER TRANSFER SYSTEM | IFI | 2017-08-31 |  |  |  |  | PKG-023-SUP
|  | 860022 | T16182-DN05-P0ZEN-860022 | SUPPLEMENTARY FIRING FOR HRSG
S&A(18) | Structural & Architectural | 183500 | T16182-CA06-P0UYB-183500 | SUPPORT BUILDING - CALCULATION | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183553 | T16182-CA02-P0UYB-183553 | SUPPORT BUILDING - COLUMN, GIRDER & BEAM RE - BAR DETAIL | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183551 | T16182-CA01-P0UYB-183551 | SUPPORT BUILDING - FOUNDATION DETAILS, GROUND FLOOR PLAN, ROOF FRAMING PLAN | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183554 | T16182-CA02-P0UYB-183554 | SUPPORT BUILDING - FOUNDATION, SLAB & MISC. RE - BAR DEDAIL | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183552 | T16182-CA01-P0UYB-183552 | SUPPORT BUILDING - FRAMING ELEVATIONS | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183501 | T16182-CA00-P0UYB-183501 | SUPPORT BUILDING - GROUND FLOOR PLAN, ROOF PLAN, ELEVATIONS & MAIN SECTION | IFR | 2018-01-15 | 2018-03-15
S&A(18) | Structural & Architectural | 183581 | T16182-CA05-P0UYB-183581 | SUPPORT BUILDING - PLUMBING EQUIPMENT SCHEDULE & PLUMBING SCHEMATIC DIAGRAM | IFR | 2018-02-01 | 2018-03-30
S&A(18) | Structural & Architectural | 183582 | T16182-CA05-P0UYB-183582 | SUPPORT BUILDING - PLUMBING PLAN | IFR | 2018-02-01 | 2018-03-30
S&A(18) | Structural & Architectural | 183502 | T16182-CA00-P0UYB-183502 | SUPPORT BUILDING - TOILET PLAN & ELEVATION | IFR | 2018-01-15 | 2018-03-15
EL(15) | Electrical | 150201 | T16182-YU02-P0ZEN-150201 | SYMBOL & LEGEND FOR ELECTRICAL SYSTEM | IFR | 2017-01-31 | 2017-06-13
MCH(13) | Mechanical | 130301 | T16182-XS00-P0QC-130301 | SYSTEM DESCRIPTION FOR CHEMICAL DOSING SYSTEM | IFR | 2017-10-05 | 2018-01-17 |  |  |  | PKG-027-CDS
PS(11) | Mechanical | 110043 | T16182-XS00-P0PGB-110043 | SYSTEM DESCRIPTION FOR CLOSED COOLING WATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 | O | O | O
PT(12) | Mechanical | 120015 | T16182-XS00-P0SCA-120015 | SYSTEM DESCRIPTION FOR COMPRESSED AIR SYSTEM | IFR | 2017-01-30 | 2017-04-30 | O | O | O
MCH(13) | Mechanical | 130201 | T16182-XS00-P0LD-130201 | SYSTEM DESCRIPTION FOR CONDENSATE POLISHING PLANT | IFR | 2017-06-03 | 2017-09-15 | O |  |  | PKG-026-CPP
PS(11) | Mechanical | 110041 | T16182-XS00-P0LC-110041 | SYSTEM DESCRIPTION FOR CONDENSATE SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  |  | O
PS(11) | Mechanical | 110044 | T16182-XS00-P0GHC-110044 | SYSTEM DESCRIPTION FOR DEMINERALIZED WATER STORAGE AND TRANSFER SYSTEM | IFR | 2016-10-28 | 2017-03-27 |  | O | O
PS(11) | Mechanical | 110042 | T16182-XS00-P0LA-110042 | SYSTEM DESCRIPTION FOR FEEDWATER SYSTEM | IFR | 2016-10-28 | 2017-03-27 | O |  | O
PT(12) | Mechanical | 120019 | T16182-XS00-P0EKG-120019 | SYSTEM DESCRIPTION FOR FUEL GAS SYSTEM | IFR | 2017-01-30 | 2017-04-30 | O | O | O | PKG-014-FGS
PS(11) | Mechanical | 110500 | T16182-XS00-P0QJA-110500 | SYSTEM DESCRIPTION FOR NITROGEN GAS SYSTEM | IFR | 2017-06-15 | 2017-08-30 |  | O |  | PKG-006-N2
PT(12) | Mechanical | 120051 | T16182-XS00-P0GKS-120051 | SYSTEM DESCRIPTION FOR POTABLE WATER SYSTEM | IFR | 2017-01-30 | 2017-04-30 |  | O | O
MCH(13) | Mechanical | 130401 | T16182-XS00-P0QU-130401 | SYSTEM DESCRIPTION FOR SAMPLING SYSTEM | IFR | 2017-10-04 | 2018-01-16 |  |  |  | PKG-028-SP
PS(11) | Mechanical | 110040 | T16182-XS00-P0LB-110040 | SYSTEM DESCRIPTION FOR STEAM AND BYPASS SYSTEM | IFR | 2016-10-28 | 2017-03-27 | O | O | O
PT(12) | Mechanical | 120022 | T16182-XS00-P0GM-120022 | SYSTEM DESCRIPTION FOR WASTE WATER TRANSFER SYSTEM | IFR | 2017-05-30 | 2017-08-28 |  |  | O
MCH(13) | Mechanical | 130101 | T16182-XS00-P0GNR-130101 | SYSTEM DESCRIPTION FOR WASTE WATER TREATMENT PLANT | IFR | 2017-03-06 | 2017-06-18 | O | O |  | PKG-025-WT
MCH(13) | Mechanical | 130001 | T16182-XS00-P0GCF-130001 | SYSTEM DESCRIPTION FOR WATER TREATMENT PLANT | IFR | 2017-02-04 | 2017-05-19 | O | O |  | PKG-025-WT
EL(15) | Electrical | 150306 | T16182-YT10-P0ZEN-150306 | TAP RATIO STUDY REPORT | IFR | 2017-07-30 | 2017-10-15 |  | O
MCH(13) | Mechanical | 130307 | T16182-YT01-P0QC-130307 | TECHNICAL DATA SHEET FOR CHEMICAL DOSING SYSTEM | IFI | 2017-12-04 |  |  |  |  | PKG-027-CDS
MCH(13) | Mechanical | 130214 | T16182-YT01-P0LD-130214 | TECHNICAL DATA SHEET FOR CONDENSATE POLISHING PLANT | IFI | 2017-08-02 |  |  |  |  | PKG-026-CPP
MCH(13) | Mechanical | 130405 | T16182-YT01-P0QU-130405 | TECHNICAL DATA SHEET FOR SAMPLING SYSTEM | IFI | 2017-12-03 |  |  |  |  | PKG-028-SP
EL(15) | Electrical | 150902 | T16182-YT01-P0BF-150902 | TECHNICAL SPECIFICATION - 13.8/0.48kV MOLD TRANSFORMER | IFR | 2017-04-30 | 2017-09-10 |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 152820 | T16182-DE00-P0ZEN-152820 | TECHNICAL SPECIFICATION - 380KV EHV CABLE AND ACCESSORIES | IFR | 2017-02-28 | 2017-05-16 | O | O
EL(15) | Electrical | 150903 | T16182-YT01-P0BF-150903 | TECHNICAL SPECIFICATION - 480V NON SEGREGATED PHASE BUS DUCT | IFR | 2017-04-30 | 2017-09-10 |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 152002 | T16182-DE00-P0ZEN-152002 | TECHNICAL SPECIFICATION - CABLE TRAY AND ACCESSORIES | IFR | 2017-05-30 | 2017-08-09
EL(15) | Electrical | 152840 | T16182-DE00-P0ZEN-152840 | TECHNICAL SPECIFICATION - CABLING ACCESSORIES | IFR | 2017-05-31 | 2017-08-09
EL(15) | Electrical | 154001 | T16182-DE00-P0CY-154001 | TECHNICAL SPECIFICATION - COMMUNICATION SYSTEM | IFR | 2017-10-15 | 2018-02-25
EL(15) | Electrical | 151011 | T16182-YT01-P0BT-151011 | TECHNICAL SPECIFICATION - DC & AC UPS SYSTEM | IFR | 2017-06-16 | 2017-09-25 |  |  |  | PKG-036-DCACUPS
EL(15) | Electrical | 152502 | T16182-DE00-P0BAU-152502 | TECHNICAL SPECIFICATION - EARTHING AND LIGHTNING PROTECTION SYSTEM | IFR | 2017-02-15 | 2017-05-02
EL(15) | Electrical | 152870 | T16182-DE00-P0ZEN-152870 | TECHNICAL SPECIFICATION - FIRE STOP MATERIAL | IFR | 2017-07-31 | 2017-10-09
EL(15) | Electrical | 150711 | T16182-YT01-P0BAC-150711 | TECHNICAL SPECIFICATION - GENERATOR CIRCUIT BREAKER | IFR | 2017-05-26 | 2017-09-10 | O |  |  | PKG-032-GCB
EL(15) | Electrical | 150611 | T16182-YT01-P0BAT-150611 | TECHNICAL SPECIFICATION - GENERATOR STEP - UP TRANSFORMER | IFR | 2017-03-17 | 2017-07-28 | O |  |  | PKG-031-TR
I&C(16) | Instrumentation & Control | 163425 | T16182-YR05-P0SAY-163425 | TECHNICAL SPECIFICATION - HVAC CONTROL SYSTEM | IFI | 2017-09-30 |  |  |  |  | PKG-041-HVAC
EL(15) | Electrical | 150751 | T16182-YT01-P0BAA-150751 | TECHNICAL SPECIFICATION - ISOLATED PHASE BUSDUCT FOR GTG UNIT | IFR | 2017-05-12 | 2017-09-10 |  |  |  | PKG-033-IPB
EL(15) | Electrical | 150752 | T16182-YT01-P0BAA-150752 | TECHNICAL SPECIFICATION - ISOLATED PHASE BUSDUCT FOR STG UNIT | IFR | 2017-06-16 | 2017-10-13 |  |  |  | PKG-033-IPB
EL(15) | Electrical | 152202 | T16182-DE00-P0ZEN-152202 | TECHNICAL SPECIFICATION - LIGHTING AND SMALL POWER | IFR | 2017-08-22 | 2017-11-30
EL(15) | Electrical | 150901 | T16182-YT01-P0BF-150901 | TECHNICAL SPECIFICATION - LV SWITCHGEAR | IFR | 2017-04-30 | 2017-09-10 |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 151161 | T16182-YT01-P0CFA-151161 | TECHNICAL SPECIFICATION - METERING PANEL | IFR | 2017-05-15 | 2017-09-11 |  |  |  | PKG-038-MP
EL(15) | Electrical | 150801 | T16182-YT01-P0BB-150801 | TECHNICAL SPECIFICATION - MV SWITCHGEAR | IFR | 2017-04-30 | 2017-09-10 |  |  |  | PKG-034-MVSWGR
EL(15) | Electrical | 152830 | T16182-DE00-P0ZEN-152830 | TECHNICAL SPECIFICATION - POWER & CONTROL & F/O CABLE | IFR | 2017-05-31 | 2017-08-09
EL(15) | Electrical | 151101 | T16182-YT01-P0CHB-151101 | TECHNICAL SPECIFICATION - PROTECTION RELAY PANEL | IFR | 2017-05-15 | 2017-09-11 |  |  |  | PKG-037-PRP
EL(15) | Electrical | 152701 | T16182-DE00-P0ZEN-152701 | TECHNICAL SPECIFICATION - PVC CONDUIT AND ACCESSORIES | IFI | 2017-02-03
EL(15) | Electrical | 152702 | T16182-DE00-P0ZEN-152702 | TECHNICAL SPECIFICATION - STEEL CONDUIT AND ACCESSORIES | IFI | 2017-05-31
EL(15) | Electrical | 150661 | T16182-YT01-P0BBT-150661 | TECHNICAL SPECIFICATION - UNIT AUXILIARY TRANSFORMER | IFR | 2017-03-17 | 2017-07-28 | O |  |  | PKG-031-TR
I&C(16) | Instrumentation & Control | 163201 | T16182-CV03-P0ZEN-163201 | TECHNICAL SPECIFICATION & DATA SHEET FOR CONTROL VALVE - BOP | IFR | 2017-05-31 | 2017-12-15 |  | O
I&C(16) | Instrumentation & Control | 163403 | T16182-CV03-P0SAY-163403 | TECHNICAL SPECIFICATION & DATA SHEET FOR FIELD INSTRUMENT - HVAC | IFI | 2017-07-01 |  |  | O |  | PKG-041-HVAC
I&C(16) | Instrumentation & Control | 163104 | T16182-CV03-P0ZEN-163104 | TECHNICAL SPECIFICATION & DATA SHEET FOR FLOW ELEMENT - BOP | IFR | 2017-05-31 | 2017-12-15 |  | O
I&C(16) | Instrumentation & Control | 163202 | T16182-CV03-P0EKU-163202 | TECHNICAL SPECIFICATION & DATA SHEET FOR GAS METERING SYSTEM | IFR | 2017-04-07 | 2017-11-15 |  | O
I&C(16) | Instrumentation & Control | 163102 | T16182-CV03-P0ZEN-163102 | TECHNICAL SPECIFICATION & DATA SHEET FOR LOCAL INSTRUMENT - BOP | IFR | 2017-05-31 | 2017-12-15 |  | O
I&C(16) | Instrumentation & Control | 163103 | T16182-CV03-P0ZEN-163103 | TECHNICAL SPECIFICATION & DATA SHEET FOR PROCESS TRANSMITTER - BOP | IFR | 2017-05-31 | 2017-12-15 |  | O
I&C(16) | Instrumentation & Control | 161134 | T16182-CV03-P0CWQ-161134 | TECHNICAL SPECIFICATION & DATA SHEET FOR SETTLEMENT SYSTEM | IFR | 2017-06-01 | 2017-10-15 | O
I&C(16) | Instrumentation & Control | 163203 | T16182-CV03-P0UCL-163203 | TECHNICAL SPECIFICATION & DATA SHEET FOR STEAM/WATER METERING SYSTEM | IFR | 2017-06-14 | 2017-12-15 |  | O
I&C(16) | Instrumentation & Control | 163331 | T16182-CV03-P0ZEN-163331 | TECHNICAL SPECIFICATION & DATA SHEET FOR VIBRATION MONITORING SYSTEM | IFR | 2017-08-01 | 2017-11-14
I&C(16) | Instrumentation & Control | 163204 | T16182-CV03-P0ZEN-163204 | TECHNICAL SPECIFICATION & DATA SHEET FOR WEATHER STATION | IFR | 2017-07-14 | 2018-01-14 |  | O
I&C(16) | Instrumentation & Control | 165701 | T16182-CV03-P0ZEN-165701 | TECHNICAL SPECIFICATION FOR I&C CABLE | IFR | 2017-07-15 | 2017-10-28 |  | O
I&C(16) | Instrumentation & Control | 165731 | T16182-CV03-P0ZEN-165731 | TECHNICAL SPECIFICATION FOR INSTRUMENT INSTALLATION MATERIALS | IFR | 2017-08-15 | 2017-11-20 |  | O
I&C(16) | Instrumentation & Control | 165711 | T16182-CV03-P0ZEN-165711 | TECHNICAL SPECIFICATION FOR JUNCTION BOX & RACK | IFR | 2017-07-15 | 2017-10-20 |  | O
GN-I&C(29) | Instrumentation & Control | 290014 | T16182-YR02-P0CJN-290014 | TECHNICAL SPECIFICATION OF EXCITATION SYSTEM FOR ST | IFR | 2017-04-07 | 2017-10-13 |  |  |  | PKG-040-STG
MCH(13) | Mechanical | 130108 | T16182-YT01-P0GNR-130108 | TEHCNICAL DATA SHEET FOR WASTE WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-07-20 |  | O |  | PKG-025-WT
MCH(13) | Mechanical | 130014 | T16182-YT01-P0GCF-130014 | TEHCNICAL DATA SHEET FOR WATER TREATMENT PLANT | IFI | 2017-04-05 | 2017-07-20 |  | O |  | PKG-025-WT
CV(17) | Civil | 170102 | T16182-BF05-P0ZEN-170102 | TOPOGRAPHIC SURVEY REPORT | IFI | 2016-10-24 |  |  | O
CV(17) | Civil | 172100 | T16182-XB02-P0UAG-172100 | TRANSFORMER FOUNDATION ARRANGEMENT PLAN | IFR | 2017-04-25 | 2017-07-24
|  | 860002 | T16182-DN05-P0ZEN-860002 | TRIAL RUN TEST OF THE PLANT
TG-MCH(22) | Instrumentation & Control | 220207 | T16182-YL08-P6MAA-220207 | TRIPS & ALARMS SETTINGS UNIT P6+P7 | IFI | 2017-11-30 |  |  |  |  | PKG-040-STG
EM(02) | Project Management | 020009 | T16182-DP00-P0ZEN-020009 | TYPICAL DANGER SIGN DRAWING | IFI | 2018-07-25
I&C(16) | Instrumentation & Control | 163301 | T16182-YS00-P0ZEN-163301 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM - INDEX | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163314 | T16182-YS00-P0ZEN-163314 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR ANALOG INPUT | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163315 | T16182-YS00-P0ZEN-163315 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR ANALOG OUTPUT | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163316 | T16182-YS00-P0ZEN-163316 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR BINARY INPUT | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163317 | T16182-YS00-P0ZEN-163317 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR BINARY OUTPUT | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163313 | T16182-YS00-P0ZEN-163313 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR BUS TIE | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163308 | T16182-YS00-P0ZEN-163308 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR INCOMER | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163309 | T16182-YS00-P0ZEN-163309 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR MOTOR FEEDER (ACB) | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163310 | T16182-YS00-P0ZEN-163310 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR MOTOR FEEDER (MCCB) | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163311 | T16182-YS00-P0ZEN-163311 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR NON MOTOR FEEDER (ACB) | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163312 | T16182-YS00-P0ZEN-163312 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR LV SWGR NON MOTOR FEEDER (MCCB EHS) | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163321 | T16182-YS00-P0ZEN-163321 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MOTOR OPERATED VALVE - FIELDBUS | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163320 | T16182-YS00-P0ZEN-163320 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MOTOR OPERATED VALVE - INTERNAL MCC | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163305 | T16182-YS00-P0ZEN-163305 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR BUS TIE | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163302 | T16182-YS00-P0ZEN-163302 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR INCOMER | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163303 | T16182-YS00-P0ZEN-163303 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR MOTOR FEEDER | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163304 | T16182-YS00-P0ZEN-163304 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR TR FEEDER | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163306 | T16182-YS00-P0ZEN-163306 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR MV SWGR UNIT/COMMON TIE | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163318 | T16182-YS00-P0ZEN-163318 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PNEUMATIC CONTROL VALVE - MODULATING | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163319 | T16182-YS00-P0ZEN-163319 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PNEUMATIC SHUT - OFF VALVE (SOLENOID VALVE) | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 163307 | T16182-YS00-P0ZEN-163307 | TYPICAL DCS ELEMENTARY WIRING DIAGRAM FOR PT PANEL | IFR | 2017-02-01 | 2017-05-15
I&C(16) | Instrumentation & Control | 165305 | T16182-YK00-P0ZEN-165305 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - CONDUIT SUPPORT | IFR | 2017-04-01 | 2017-07-15 |  | O
I&C(16) | Instrumentation & Control | 165301 | T16182-YK00-P0ZEN-165301 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - CONTROL VALVE | IFR | 2017-04-01 | 2017-07-15 |  | O
I&C(16) | Instrumentation & Control | 165304 | T16182-YK00-P0ZEN-165304 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - FIELD INSTRUMENT | IFR | 2017-04-01 | 2017-07-15 |  | O
I&C(16) | Instrumentation & Control | 165303 | T16182-YK00-P0ZEN-165303 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - INSTRUMENT RACK AND JUNCTION BOX | IFR | 2017-04-01 | 2017-07-15 |  | O
I&C(16) | Instrumentation & Control | 165302 | T16182-YK00-P0ZEN-165302 | TYPICAL I&C CABLE INSTALLATION DRAWINGS - MOV | IFR | 2017-04-01 | 2017-07-15 |  | O
EL(15) | Electrical | 154021 | T16182-YQ03-P0CY-154021 | TYPICAL INSTALLATION DRAWING - COMMUNICATION SYSTEM | IFR | 2017-04-07 | 2017-07-09
EL(15) | Electrical | 152501 | T16182-YE04-P0BAU-152501 | TYPICAL INSTALLATION DRAWING - EARTHING AND LIGHTNING PROTECTION | IFR | 2017-01-31 | 2017-04-17
EL(15) | Electrical | 152201 | T16182-YQ01-P0ZEN-152201 | TYPICAL INSTALLATION DRAWING - LIGHTING AND SMALL POWER | IFR | 2017-01-31 | 2017-05-01
EL(15) | Electrical | 152001 | T16182-YQ02-P0ZEN-152001 | TYPICAL INSTALLATION DRAWING - RACEWAY | IFR | 2017-01-31 | 2017-05-21
EM(02) | Engineering Management | 020010 | T16182-CA07-P0ZEN-020010 | UNDERGROUND PIPE MARKER DETAIL | IFC | 2019-07-26 | 2019-07-26
PS(11) | Mechanical | 110603 | T16182-YT01-P0LF-110603 | VALVE LIST & DATA SHEET FOR MOV (BUTTERFLY) | IFR | 2017-04-30 | 2017-09-14 |  | O |  | PKG-010-MOVB
PS(11) | Mechanical | 110601 | T16182-YT01-P0LF-110601 | VALVE LIST & DATA SHEET FOR MOV (G&G) | IFR | 2017-04-17 | 2017-09-14 |  | O |  | PKG-009-MOVG
MCH(13) | Mechanical | 130208 | T16182-XN00-P0LD-130208 | VALVE LIST FOR CONDENSATE POLISHING PLANT | IFI | 2017-07-03 |  |  |  |  | PKG-026-CPP
GN-SYS(26) | Mechanical | 260036 | T16182-XN00-P0MKA-260036 | VALVE LIST FOR ST GENERATOR | IFI | 2017-04-30 | 2017-06-30 |  |  |  | PKG-040-STG
MCH(13) | Mechanical | 130105 | T16182-XN00-P0GNR-130105 | VALVE LIST FOR WASTE WATER TREATMENT PLANT | IFI | 2017-03-06 | 2017-12-22 |  | O |  | PKG-025-WT
MCH(13) | Mechanical | 130008 | T16182-XN00-P0GCF-130008 | VALVE LIST FOR WATER TREATMENT PLANT | IFI | 2017-03-06 | 2017-06-30 |  | O |  | PKG-025-WT
MCH(13) | Mechanical | 136001 | T16182-YT01-P0SAA-136001 | VENDOR PRINT FOR HVAC EQUIPMENT-1 | IFR | 2018-07-25 | 2018-09-25 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 136002 | T16182-YT01-P0SAA-136002 | VENDOR PRINT FOR HVAC EQUIPMENT-2 | IFR | 2018-07-25 | 2018-09-25 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 136003 | T16182-YT01-P0SAA-136003 | VENDOR PRINT FOR HVAC EQUIPMENT-3 | IFR | 2018-07-25 | 2018-09-25 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 136004 | T16182-YT01-P0SAA-136004 | VENDOR PRINT FOR HVAC EQUIPMENT-4 | IFR | 2018-07-25 | 2018-09-25 |  |  |  | PKG-041-HVAC
MCH(13) | Mechanical | 136005 | T16182-YT01-P0SAA-136005 | VENDOR PRINT FOR HVAC EQUIPMENT-5 | IFR | 2018-07-25 | 2018-09-25 |  |  |  | PKG-041-HVAC
CV(17) | Civil | 173403 | T16182-UT01-P0GQB-173403 | WASTE WATER DRAINAGE LAYOUT | IFR | 2017-12-31 | 2018-03-31 |  | O
CV(17) | Civil | 173413 | T16182-UT01-P0GQB-173413 | WASTE WATER DRAINAGE MANHOLE SCHEDULE | IFR | 2017-12-31 | 2018-03-31 |  | O
CV(17) | Civil | 173402 | T16182-UT01-P0GQB-173402 | WASTE WATER DRAINAGE OVERALL LAYOUT | IFR | 2017-12-31 | 2018-03-31 |  | O
CV(17) | Civil | 173417 | T16182-VK02-P0GQB-173417 | WASTE WATER DRAINAGE STRUCTURE MANHOLE RE-BAR DETAIL | IFR | 2017-12-31 | 2018-03-31 |  | O
CV(17) | Civil | 171708 | T16182-XB02-P0UEM-171708 | WASTE WATER TREATMENT PLANT EMBEDMENT DETAIL | IFR | 2017-03-15 | 2017-05-16 |  | O
CV(17) | Civil | 171702 | T16182-XB02-P0UEM-171702 | WASTE WATER TREATMENT PLANT PLAN AND SECTION | IFR | 2017-03-15 | 2017-05-16 |  | O
CV(17) | Civil | 171711 | T16182-VK02-P0UEM-171711 | WASTE WATER TREATMENT R.C DETAIL | IFR | 2017-03-15 | 2017-05-16 |  | O
PT(12) | Mechanical | 120050 | T16182-XG07-P0ZEN-120050 | WATER BALANCE DIAGRAM | IFR | 2017-01-30 | 2017-04-30 |  | O
MCH(13) | Mechanical | 136613 | T16182-YT01-P0SGC-136613 | WATER SPRAY SYSTEM - DATASHEET | IFR | 2017-05-03 | 2017-08-01 |  | O |  | PKG-030-FF
CV(17) | Civil | 173503 | T16182-VK02-P0UZK-173503 | WATER TANK SECTION & DETAIL | IFR | 2019-06-01 | 2019-09-01
S&A(18) | Structural & Architectural | 181953 | T16182-CA01-P0UGD-181953 | WATER TREATMENT BUILDING - 1ST FLOOR FRAMING PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181902 | T16182-CA00-P0UGD-181902 | WATER TREATMENT BUILDING - 1ST FLOOR PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181984 | T16182-CA05-P0UGD-181984 | WATER TREATMENT BUILDING - 1ST FLOOR PLUMBING PLAN | IFR | 2017-02-28 | 2017-04-30
S&A(18) | Structural & Architectural | 181914 | T16182-CA00-P0UGD-181914 | WATER TREATMENT BUILDING - ARCHITECTURAL MISC. | IFR | 2017-06-30 | 2017-08-31 |  | O
S&A(18) | Structural & Architectural | 181900 | T16182-CA06-P0UGD-181900 | WATER TREATMENT BUILDING - CALCULATION | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181911 | T16182-CA00-P0UGD-181911 | WATER TREATMENT BUILDING - CEILING PLAN | IFR | 2017-06-30 | 2017-08-31 |  | O
S&A(18) | Structural & Architectural | 181959 | T16182-CA02-P0UGD-181959 | WATER TREATMENT BUILDING - COLUMN REBAR DETAIL | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181904 | T16182-CA00-P0UGD-181904 | WATER TREATMENT BUILDING - ELEVATION | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181963 | T16182-CA02-P0UGD-181963 | WATER TREATMENT BUILDING - EMBEDDED PLATE & SLEEVE PLAN | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 181986 | T16182-CA05-P0UGD-181986 | WATER TREATMENT BUILDING - ENLARGED PLUMBING PLAN | IFR | 2017-02-28 | 2017-04-30
S&A(18) | Structural & Architectural | 181966 | T16182-CA03-P0UGD-181966 | WATER TREATMENT BUILDING - ENLARGED ROOF FRAMING PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181962 | T16182-CA02-P0UGD-181962 | WATER TREATMENT BUILDING - EQUIPMENT FOUNDTAION ARRANGEMENT PLAN | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 181951 | T16182-CA01-P0UGD-181951 | WATER TREATMENT BUILDING - FOUNDATION & COLUMN ARRANGEMENT PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181958 | T16182-CA02-P0UGD-181958 | WATER TREATMENT BUILDING - FOUNDATION REBAR DETAIL | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181955 | T16182-CA01-P0UGD-181955 | WATER TREATMENT BUILDING - FRAMING ELEVATION | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181960 | T16182-CA02-P0UGD-181960 | WATER TREATMENT BUILDING - GIRDER & BEAM REBAR SCHEDULE | IFR | 2017-02-28 | 2017-04-30 |  | O
S&A(18) | Structural & Architectural | 181967 | T16182-CA03-P0UGD-181967 | WATER TREATMENT BUILDING - GIRT LINE & ROW ELEVATION | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 181952 | T16182-CA01-P0UGD-181952 | WATER TREATMENT BUILDING - GROUND FLOOR FRAMING | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181901 | T16182-CA00-P0UGD-181901 | WATER TREATMENT BUILDING - GROUND FLOOR PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181983 | T16182-CA05-P0UGD-181983 | WATER TREATMENT BUILDING - GROUND FLOOR PLUMBING PLAN | IFR | 2017-02-28 | 2017-04-30
S&A(18) | Structural & Architectural | 181906 | T16182-CA00-P0UGD-181906 | WATER TREATMENT BUILDING - INTERIOR FINISH & DOOR SCHEDULE | IFR | 2017-02-28 | 2017-04-30 |  | O
S&A(18) | Structural & Architectural | 181964 | T16182-CA02-P0UGD-181964 | WATER TREATMENT BUILDING - MISC. REBAR DETAIL | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 181981 | T16182-CA05-P0UGD-181981 | WATER TREATMENT BUILDING - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-02-28 | 2017-04-30
S&A(18) | Structural & Architectural | 181982 | T16182-CA05-P0UGD-181982 | WATER TREATMENT BUILDING - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-02-28 | 2017-04-30
S&A(18) | Structural & Architectural | 181965 | T16182-CA03-P0UGD-181965 | WATER TREATMENT BUILDING - ROOF COLUMN LOCATION PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181954 | T16182-CA01-P0UGD-181954 | WATER TREATMENT BUILDING - ROOF FLOOR FRAMING PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181903 | T16182-CA00-P0UGD-181903 | WATER TREATMENT BUILDING - ROOF FLOOR PLAN | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181985 | T16182-CA05-P0UGD-181985 | WATER TREATMENT BUILDING - ROOF PLUMBING PLAN | IFR | 2017-02-28 | 2017-04-30
S&A(18) | Structural & Architectural | 181905 | T16182-CA00-P0UGD-181905 | WATER TREATMENT BUILDING - SECTION | IFR | 2017-01-31 | 2017-03-31 |  | O
S&A(18) | Structural & Architectural | 181961 | T16182-CA02-P0UGD-181961 | WATER TREATMENT BUILDING - SLAB REBAR DETAIL | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 181912 | T16182-CA00-P0UGD-181912 | WATER TREATMENT BUILDING - STAIR ENLARGED PLAN | IFR | 2017-06-30 | 2017-08-31 |  | O
S&A(18) | Structural & Architectural | 181913 | T16182-CA00-P0UGD-181913 | WATER TREATMENT BUILDING - STAIR ENLARGED SECTION | IFR | 2017-06-30 | 2017-08-31 |  | O
S&A(18) | Structural & Architectural | 181956 | T16182-CA01-P0UGD-181956 | WATER TREATMENT BUILDING - STAIR FRAMING PLAN | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 181957 | T16182-CA01-P0UGD-181957 | WATER TREATMENT BUILDING - STAIR FRAMING SECTION | IFR | 2017-04-15 | 2017-06-15 |  | O
S&A(18) | Structural & Architectural | 181968 | T16182-CA03-P0UGD-181968 | WATER TREATMENT BUILDING - STEEL CONNECTION DETAIL | IFR | 2017-03-10 | 2017-05-10 |  | O
S&A(18) | Structural & Architectural | 181909 | T16182-CA00-P0UGD-181909 | WATER TREATMENT BUILDING - TOILET ENLARGED PLAN | IFR | 2017-06-30 | 2017-08-31 |  | O
S&A(18) | Structural & Architectural | 181910 | T16182-CA00-P0UGD-181910 | WATER TREATMENT BUILDING - WALL OPENING PLAN | IFR | 2017-06-30 | 2017-08-31 |  | O
S&A(18) | Structural & Architectural | 181908 | T16182-CA00-P0UGD-181908 | WATER TREATMENT BUILDING - WALL SECTION DETAIL | IFR | 2017-06-30 | 2017-08-31 |  | O
PT(12) | General | 123055 | T16182-VN01-P0MAG-123055 | WINDWALL LOGO FOR AIR COOLED CONDENSER | IFI | 2019-04-10
EL(15) | Electrical | 150956 | T16182-YU03-P0BFA-150956 | WIRING DIAGRAM - 480V BLOCK#1 ESSENTIAL SWITCHGEAR | IFI | 2017-06-16 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150957 | T16182-YU03-P0BFA-150957 | WIRING DIAGRAM - 480V BLOCK#2 ESSENTIAL SWITCHGEAR | IFI | 2017-07-31 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150958 | T16182-YU03-P0BFA-150958 | WIRING DIAGRAM - 480V COMMON ESSENTIAL SWITCHGEAR | IFI | 2017-06-16 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150953 | T16182-YU03-P0BFA-150953 | WIRING DIAGRAM - 480V COMMON SWITCHGEAR | IFI | 2017-06-16 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150955 | T16182-YU03-P0BFA-150955 | WIRING DIAGRAM - 480V FIRE BRIGADE SWITCHGEAR | IFI | 2017-07-31 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150951 | T16182-YU03-P0BFA-150951 | WIRING DIAGRAM - 480V GTG/HRSG SWITCHGEAR | IFI | 2017-06-16 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150952 | T16182-YU03-P0BFA-150952 | WIRING DIAGRAM - 480V STG/ACC SWITCHGEAR | IFI | 2017-07-31 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 150954 | T16182-YU03-P0BFA-150954 | WIRING DIAGRAM - 480V WT SWITCHGEAR | IFI | 2017-06-16 |  |  |  |  | PKG-035-LVSWGR
EL(15) | Electrical | 151181 | T16182-YU03-P0CFA-151181 | WIRING DIAGRAM - METERING PANEL | IFI | 2017-06-15 |  |  |  |  | PKG-038-MP
EL(15) | Electrical | 150831 | T16182-YU03-P0BB-150831 | WIRING DIAGRAM - MV SWITCHGEAR | IFI | 2017-06-16 |  |  |  |  | PKG-034-MVSWGR
EL(15) | Electrical | 151121 | T16182-YU03-P0CHB-151121 | WIRING DIAGRAM - PROTECTION RELAY PANEL & FMS FOR GTG UNIT | IFI | 2017-06-15 |  |  |  |  | PKG-037-PRP
EL(15) | Electrical | 151122 | T16182-YU03-P0CHB-151122 | WIRING DIAGRAM - PROTECTION RELAY PANEL & FMS FOR STG UNIT | IFI | 2017-06-15 |  |  |  |  | PKG-037-PRP
CV(17) | Civil | 170104 | T16182-VK02-P0ZEN-170104 | WORKING PILE DETAIL | IFR | 2016-10-24 | 2017-01-18
S&A(18) | Structural & Architectural | 182000 | T16182-CA06-P0UST-182000 | WORKSHOP & STORAGE BUILDING - CALCULATION | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182052 | T16182-CA01-P0UST-182052 | WORKSHOP & STORAGE BUILDING - COLUMN LOCATION PLAN | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182063 | T16182-CA03-P0UST-182063 | WORKSHOP & STORAGE BUILDING - CONNECTION DETAIL | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182061 | T16182-CA02-P0UST-182061 | WORKSHOP & STORAGE BUILDING - CRANE GIRDER & MISC. DETAIL | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182003 | T16182-CA00-P0UST-182003 | WORKSHOP & STORAGE BUILDING - ELEVATION | IFR | 2017-06-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182006 | T16182-CA00-P0UST-182006 | WORKSHOP & STORAGE BUILDING - ENLARGED PLAN, CEILING PLAN | IFR | 2018-04-15 | 2018-06-15
S&A(18) | Structural & Architectural | 182085 | T16182-CA05-P0UST-182085 | WORKSHOP & STORAGE BUILDING - ENLARGED PLUMBING PLAN | IFR | 2017-07-30 | 2017-10-15
S&A(18) | Structural & Architectural | 182058 | T16182-CA02-P0UST-182058 | WORKSHOP & STORAGE BUILDING - FOUNDATION DETAIL | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182051 | T16182-CA01-P0UST-182051 | WORKSHOP & STORAGE BUILDING - FOUNDATION PLAN | IFR | 2017-06-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182056 | T16182-CA03-P0UST-182056 | WORKSHOP & STORAGE BUILDING - FRAMING ELEVATION | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182053 | T16182-CA01-P0UST-182053 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR FRAMING PLAN | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182001 | T16182-CA00-P0UST-182001 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR PLAN | IFR | 2017-06-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182083 | T16182-CA05-P0UST-182083 | WORKSHOP & STORAGE BUILDING - GROUND FLOOR PLUMBING PLAN | IFR | 2017-07-30 | 2017-10-15
S&A(18) | Structural & Architectural | 182005 | T16182-CA00-P0UST-182005 | WORKSHOP & STORAGE BUILDING - INTERIOR FINISH, DOOR & WINDOW SCHEDULE | IFR | 2018-04-15 | 2018-06-15
S&A(18) | Structural & Architectural | 182081 | T16182-CA05-P0UST-182081 | WORKSHOP & STORAGE BUILDING - PLUMBING EQUIPMENT SCHEDULE | IFR | 2017-07-30 | 2017-10-15
S&A(18) | Structural & Architectural | 182082 | T16182-CA05-P0UST-182082 | WORKSHOP & STORAGE BUILDING - PLUMBING SCHEMATIC DIAGRAM | IFR | 2017-07-30 | 2017-10-15
S&A(18) | Structural & Architectural | 182059 | T16182-CA02-P0UST-182059 | WORKSHOP & STORAGE BUILDING - RC COLUMN DETAIL | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182054 | T16182-CA03-P0UST-182054 | WORKSHOP & STORAGE BUILDING - ROOF FRAMING PLAN | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182002 | T16182-CA00-P0UST-182002 | WORKSHOP & STORAGE BUILDING - ROOF PLAN | IFR | 2017-06-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182084 | T16182-CA05-P0UST-182084 | WORKSHOP & STORAGE BUILDING - ROOF PLUMBING PLAN | IFR | 2017-07-30 | 2017-10-15
S&A(18) | Structural & Architectural | 182004 | T16182-CA00-P0UST-182004 | WORKSHOP & STORAGE BUILDING - SECTION | IFR | 2017-06-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182060 | T16182-CA02-P0UST-182060 | WORKSHOP & STORAGE BUILDING - SLAB DETAIL | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182062 | T16182-CA03-P0UST-182062 | WORKSHOP & STORAGE BUILDING - STEEL COLUMN & BASE PLATE DETAIL | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 182055 | T16182-CA03-P0UST-182055 | WORKSHOP & STORAGE BUILDING - STEEL ROOF FRAMING PLAN | IFR | 2017-07-15 | 2017-09-15
S&A(18) | Structural & Architectural | 184700 | T16182-CA06-P0USR-184700 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - CALCULATION | IFR | 2017-03-15 | 2017-05-15 |  | O
S&A(18) | Structural & Architectural | 184702 | T16182-CA00-P0USR-184702 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - ELEVATIONS & SECTIONS | IFR | 2017-03-15 | 2017-05-15 |  | O
S&A(18) | Structural & Architectural | 184701 | T16182-CA00-P0USR-184701 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - GROUND & ROOF FLOOR PLAN | IFR | 2017-03-15 | 2017-05-15 |  | O
S&A(18) | Structural & Architectural | 184751 | T16182-CA03-P0USR-184751 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - STEEL COLUMN LOCATION & ROOF PLAN | IFR | 2017-03-15 | 2017-05-15 |  | O
S&A(18) | Structural & Architectural | 184752 | T16182-CA03-P0USR-184752 | WWT & BULK CHEMICAL STORAGE TANK SHELTER - STEEL FRAMING ELEVATIONS | IFR | 2017-03-15 | 2017-05-15 |  | O
S&A(18) |  | 189001 | T16182-CA03-P0HBD-189001 | YARD PLATFORM | Internal